## GEN_ALL
Outage ID | Feeder ID | Calendar Day Duration | Working Day Duration | Work Days | Outage Status | Start | Finish
TO-22-AD-SA1-2CB-01 | COUPLER/SECTIONALISING CB - AGHADA 220-AGHADA 220-220SA1-2CB | 2 | 2 | 2 | Scheduled | 04/01/2022 | 05/01/2022
TO-22-AD-SB1-2CB-01 | COUPLER/SECTIONALISING CB - AGHADA 220-AGHADA 220-220SB1-2CB | 2 | 2 |  | Scheduled | 10/01/2022 | 11/01/2022
TO-22-AA GIS-110SA1-3CB-01 | COUPLER/SECTIONALISING CB - ARDNACRUSHA GIS 110-ARDNACRUSHA GIS 110-110SA1-3CB | 2 | 2 | 2 | Tentative | 10/01/2022 | 11/01/2022
TO-22-ARV-GWE-1-03 | 110kV FEEDER - ARVA 110-GORTAWEE 110-1 | 5 | 5 | 5 | Scheduled | 10/01/2022 | 14/01/2022
TO-22-BYH-220K2-01 | COUPLER/SECTIONALISING CB - BALLYNAHULLA 220-BALLYNAHULLA 220-220K2 | 2 | 2 | 2 | Scheduled | 10/01/2022 | 11/01/2022
TO-22-KLS-220K1-2-02 | COUPLER/SECTIONALISING CB - KELLIS 220-KELLIS 220-220K1-2 | 10 | 8 |  | Scheduled | 10/01/2022 | 19/01/2022
TO-22-KNY-110K2-03 | COUPLER/SECTIONALISING CB - KNOCKRANNY 110-KNOCKRANNY 110-110K2 | 5 | 5 | 5 | Scheduled | 10/01/2022 | 14/01/2022
TO-22-SLB-110K2-01 | COUPLER/SECTIONALISING CB - SLIABH BAWN 110-SLIABH BAWN 110-110K2 | 5 | 5 | 5 | Scheduled | 10/01/2022 | 14/01/2022
TO-22-BYH-220K1-01 | COUPLER/SECTIONALISING CB - BALLYNAHULLA 220-BALLYNAHULLA 220-220K1 | 2 | 2 | 2 | Scheduled | 13/01/2022 | 14/01/2022
TO-22-CLG-T122-01 | TSO CUSTOMER TRANSFORMER - CLOGHRAN 110-CLOGHRAN 20-T122 | 107 | 73 | 73 | Scheduled | 13/01/2022 | 29/04/2022
TO-22-110 kV A1 @ FIN GIS-01 | BUSBAR SECTION - FINGLAS GIS 110-FINGLAS GIS 110-110A1 | 5 | 5 | 5 | Scheduled | 17/01/2022 | 21/01/2022
TO-22-110 kV A3 @ FIN GIS-01 | BUSBAR SECTION - FINGLAS GIS 110-FINGLAS GIS 110-110A3 | 5 | 5 | 5 | Scheduled | 17/01/2022 | 21/01/2022
TO-22-110 kV B1 @ FIN GIS-01 | BUSBAR SECTION - FINGLAS GIS 110-FINGLAS GIS 110-110B1 | 5 | 5 | 5 | Scheduled | 17/01/2022 | 21/01/2022
TO-22-110 kV B3 @ FIN GIS-01 | BUSBAR SECTION - FINGLAS GIS 110-FINGLAS GIS 110-110B3 | 5 | 5 | 5 | Scheduled | 17/01/2022 | 21/01/2022
TO-22-FIN GIS-110SA1-3CB-01 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110SA1-3CB | 5 | 5 | 5 | Scheduled | 17/01/2022 | 21/01/2022
TO-22-220 kV A1 @ GOR-01 | BUSBAR SECTION - GORMAN 220-GORMAN 220-220A1 | 4 | 4 | 4 | Scheduled | 17/01/2022 | 20/01/2022
TO-22-220 kV A2 @ GOR-01 | BUSBAR SECTION - GORMAN 220-GORMAN 220-220A2 | 4 | 4 | 4 | Scheduled | 17/01/2022 | 20/01/2022
TO-22-220 kV B1 @ GOR-01 | BUSBAR SECTION - GORMAN 220-GORMAN 220-220B1 | 4 | 4 | 4 | Scheduled | 17/01/2022 | 20/01/2022
TO-22-220 kV B2 @ GOR-01 | BUSBAR SECTION - GORMAN 220-GORMAN 220-220B2 | 4 | 4 | 4 | Scheduled | 17/01/2022 | 20/01/2022
TO-22-GOR-220K1-2-02 | COUPLER/SECTIONALISING CB - GORMAN 220-GORMAN 220-220K1-2 | 4 | 4 |  | Scheduled | 17/01/2022 | 20/01/2022
TO-22-110 kV A1 @ KNR-01 | BUSBAR SECTION - KNOCKANURE 110-KNOCKANURE 110-110A1 | 5 | 5 | 5 | Scheduled | 17/01/2022 | 21/01/2022
TO-22-110 kV B1 @ KNR-01 | BUSBAR SECTION - KNOCKANURE 110-KNOCKANURE 110-110B1 | 5 | 5 | 5 | Scheduled | 17/01/2022 | 21/01/2022
TO-22-KNR-110K1-01 | COUPLER/SECTIONALISING CB - KNOCKANURE 110-KNOCKANURE 110-110K1 | 5 | 5 | 5 | Scheduled | 17/01/2022 | 21/01/2022
TO-22-KNY-110SA1-2CB-03 | COUPLER/SECTIONALISING CB - KNOCKRANNY 110-KNOCKRANNY 110-110SA1-2CB | 5 | 5 | 5 | Scheduled | 17/01/2022 | 21/01/2022
TO-22-GWE-T101-02 | TSO CUSTOMER TRANSFORMER - GORTAWEE 110-GORTAWEE 10-T101 | 1 | 1 | 1 | Scheduled | 18/01/2022 | 18/01/2022
TO-22-GWE-T102-02 | TSO CUSTOMER TRANSFORMER - GORTAWEE 110-GORTAWEE 10-T102 | 1 | 1 | 1 | Scheduled | 19/01/2022 | 19/01/2022
TO-22-110 kV A1 @ CDU-01 | BUSBAR SECTION - CORDUFF 110-CORDUFF 110-110A1 | 5 | 5 | 5 | Tentative | 24/01/2022 | 28/01/2022
TO-22-110 kV A3 @ CDU-01 | BUSBAR SECTION - CORDUFF 110-CORDUFF 110-110A3 | 5 | 5 | 5 | Tentative | 24/01/2022 | 28/01/2022
TO-22-110 kV B1 @ CDU-01 | BUSBAR SECTION - CORDUFF 110-CORDUFF 110-110B1 | 5 | 5 | 5 | Tentative | 24/01/2022 | 28/01/2022
TO-22-110 kV B3 @ CDU-02 | BUSBAR SECTION - CORDUFF 110-CORDUFF 110-110B3 | 5 | 5 | 5 | Tentative | 24/01/2022 | 28/01/2022
TO-22-110 kV A4 @ KNR-01 | BUSBAR SECTION - KNOCKANURE 110-KNOCKANURE 110-110A4 | 5 | 5 | 5 | Scheduled | 24/01/2022 | 28/01/2022
TO-22-110 kV B4 @ KNR-01 | BUSBAR SECTION - KNOCKANURE 110-KNOCKANURE 110-110B4 | 5 | 5 | 5 | Scheduled | 24/01/2022 | 28/01/2022
TO-22-KNY-110K1-01 | COUPLER/SECTIONALISING CB - KNOCKRANNY 110-KNOCKRANNY 110-110K1 | 5 | 5 | 5 | Scheduled | 24/01/2022 | 28/01/2022
TO-22-SH-220K1-2-01 | COUPLER/SECTIONALISING CB - SHANNONBRIDGE 220-SHANNONBRIDGE 220-220K1-2 | 5 | 5 |  | Scheduled | 24/01/2022 | 28/01/2022
TO-22-110 kV A1/A2 @ MR-01 | BUSBAR SECTION - MARINA 110-MARINA 110-110A1-A2 | 1 | 1 | 1 | Scheduled | 25/01/2022 | 25/01/2022
TO-22-110 kV B1/B2 @ MR-01 | BUSBAR SECTION - MARINA 110-MARINA 110-110B1-B2 | 1 | 1 | 1 | Scheduled | 25/01/2022 | 25/01/2022
TO-22-220 kV A1/A2 @ DSN-01 | BUSBAR SECTION - DUNSTOWN 220-DUNSTOWN 220-220A1-A2 | 1 | 1 | 1 | Scheduled | 27/01/2022 | 27/01/2022
TO-22-220 kV B1/B2 @ DSN-01 | BUSBAR SECTION - DUNSTOWN 220-DUNSTOWN 220-220B1-B2 | 1 | 1 | 1 | Scheduled | 27/01/2022 | 27/01/2022
TO-22-400 kV A1/A2 @ DSN-01 | BUSBAR SECTION - DUNSTOWN 400-DUNSTOWN 400-400A1-A2 | 1 | 1 | 1 | Scheduled | 27/01/2022 | 27/01/2022
TO-22-400 kV B1/B2 @ DSN-01 | BUSBAR SECTION - DUNSTOWN 400-DUNSTOWN 400-400B1-B2 | 1 | 1 | 1 | Scheduled | 27/01/2022 | 27/01/2022
TO-22-KNR-T2102-02 | TRANSFORMER - KNOCKANURE 220-KNOCKANURE 110-T2102 | 10 | 8 | 8 | Tentative | 31/01/2022 | 09/02/2022
TO-22-MP GIS-220K1-01 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 220-MONEYPOINT GIS 220-220K1 | 2 | 2 | 2 | Scheduled | 31/01/2022 | 01/02/2022
TO-22-PB-R2001-02 | CAPACITOR/SVC/REACTOR - POOLBEG 220-POOLBEG 220-R2001 | 5 | 5 | 5 | Tentative | 31/01/2022 | 04/02/2022
TO-22-110 kV A2 @ DEY-01 | BUSBAR SECTION - DERRYCARNEY 110-DERRYCARNEY 110-110A2 | 1 | 1 | 1 | Scheduled | 01/02/2022 | 01/02/2022
TO-22-110 kV B2 @ DEY-01 | BUSBAR SECTION - DERRYCARNEY 110-DERRYCARNEY 110-110B2 | 1 | 1 | 1 | Scheduled | 01/02/2022 | 01/02/2022
TO-22-KPG-220SA1-2CB-03 | COUPLER/SECTIONALISING CB - KILPADDOGE 220-KILPADDOGE 220-220SA1-2CB | 4 | 4 | 4 | Scheduled | 01/02/2022 | 04/02/2022
TO-22-KTL-MON-1-01 | 110kV FEEDER - KILTEEL 110-MONREAD 110-1 | 7 | 5 | 5 | Scheduled | 01/02/2022 | 07/02/2022
TO-22-110 kV A1/A2 @ KNY-01 | BUSBAR SECTION - KNOCKRANNY 110-KNOCKRANNY 110-110A1-A2 | 1 | 1 | 1 | Scheduled | 03/02/2022 | 03/02/2022
TO-22-110 kV B1/B2 @ KNY-01 | BUSBAR SECTION - KNOCKRANNY 110-KNOCKRANNY 110-110B1-B2 | 1 | 1 | 1 | Scheduled | 03/02/2022 | 03/02/2022
TO-22-LOU-RRU-1-03 | 110kV FEEDER - LOUTH 110-RATRUSSAN 110-1 | 1 | 1 | 1 | Tentative | 03/02/2022 | 03/02/2022
TO-22-110 kV A1/A2 @ RRU-01 | BUSBAR SECTION - RATRUSSAN 110-RATRUSSAN 110-110A1-A2 | 1 | 1 | 1 | Tentative | 03/02/2022 | 03/02/2022
TO-22-RRU-110SA1-01 | SECTIONALISING DISCONNECT - RATRUSSAN 110-RATRUSSAN 110-110SA1 | 1 | 1 | 1 | Tentative | 03/02/2022 | 03/02/2022
TO-22-RRU-110SA2-01 | SECTIONALISING DISCONNECT - RATRUSSAN 110-RATRUSSAN 110-110SA2 | 1 | 1 | 1 | Tentative | 03/02/2022 | 03/02/2022
TO-22-RRU-SKL-1-03 | 110kV FEEDER - RATRUSSAN 110-SHANKILL 110-1 | 1 | 1 |  | Tentative | 03/02/2022 | 03/02/2022
TO-22-RRU-T121-01 | GENERATOR TRANSFORMER - RATRUSSAN 110-RATRUSSAN 20-T121 | 1 | 1 |  | Tentative | 03/02/2022 | 03/02/2022
TO-22-RRU-T122-03 | GENERATOR TRANSFORMER - RATRUSSAN 110-RATRUSSAN 20-T122 | 1 | 1 | 1 | Tentative | 03/02/2022 | 03/02/2022
TO-22-KPG-220K4-02 | COUPLER/SECTIONALISING CB - KILPADDOGE 220-KILPADDOGE 220-220K4 | 4 | 4 | 4 | Scheduled | 08/02/2022 | 11/02/2022
TO-22-MP GIS-220SA1-2CB-01 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 220-MONEYPOINT GIS 220-220SA1-2CB | 2 | 2 | 2 | Scheduled | 08/02/2022 | 09/02/2022
TO-22-110 kV A1/A2/A3/A4 @ RYB GIS-01 | BUSBAR SECTION - RYEBROOK GIS 110-RYEBROOK GIS 110-110A1-A2-A3-A4 | 1 | 1 | 1 | Scheduled | 08/02/2022 | 08/02/2022
TO-22-110 kV B1/B2/B3/B4 @ RYB GIS-01 | BUSBAR SECTION - RYEBROOK GIS 110-RYEBROOK GIS 110-110B1-B2-B3-B4 | 1 | 1 | 1 | Scheduled | 08/02/2022 | 08/02/2022
TO-22-220 kV B1 @ CSH-02 | BUSBAR SECTION - CASHLA 220-CASHLA 220-220B1 | 2 | 2 | 2 | Tentative | 09/02/2022 | 10/02/2022
TO-22-110 kV A1/A2/A3 @ AA GIS-01 | BUSBAR SECTION - ARDNACRUSHA GIS 110-ARDNACRUSHA GIS 110-110A1-A2-A3 | 1 | 1 | 1 | Scheduled | 10/02/2022 | 10/02/2022
TO-22-110 kV B1/B2/B3 @ AA GIS-01 | BUSBAR SECTION - ARDNACRUSHA GIS 110-ARDNACRUSHA GIS 110-110B1-B2-B3 | 1 | 1 | 1 | Scheduled | 10/02/2022 | 10/02/2022
TO-22-CLG-110K2-02 | COUPLER/SECTIONALISING CB - CLOGHRAN 110-CLOGHRAN 110-110K2 | 5 | 5 | 5 | Tentative | 14/02/2022 | 18/02/2022
TO-22-110 kV A1/A2/A3/A4 @ KPG-01 | BUSBAR SECTION - KILPADDOGE 110-KILPADDOGE 110-110A1-A2-A3-A4 | 1 | 1 | 1 | Scheduled | 15/02/2022 | 15/02/2022
TO-22-110 kV B1/B2/B3/B4 @ KPG-01 | BUSBAR SECTION - KILPADDOGE 110-KILPADDOGE 110-110B1-B2-B3-B4 | 1 | 1 | 1 | Scheduled | 15/02/2022 | 15/02/2022
TO-22-220 kV A1/A2/A3/A4 @ KPG-01 | BUSBAR SECTION - KILPADDOGE 220-KILPADDOGE 220-220A1-A2-A3-A4 | 1 | 1 | 1 | Scheduled | 16/02/2022 | 16/02/2022
TO-22-220 kV B1/B2/B3/B4 @ KPG-01 | BUSBAR SECTION - KILPADDOGE 220-KILPADDOGE 220-220B1-B2-B3-B4 | 1 | 1 | 1 | Scheduled | 16/02/2022 | 16/02/2022
TO-22-110 kV A1/A2 @ CF-01 | BUSBAR SECTION - CATHALEENS FALL 110-CATHALEENS FALL 110-110A1-A2 | 1 | 1 | 1 | Scheduled | 17/02/2022 | 17/02/2022
TO-22-110 kV B1/B2 @ CF-01 | BUSBAR SECTION - CATHALEENS FALL 110-CATHALEENS FALL 110-110B1-B2 | 1 | 1 | 1 | Scheduled | 17/02/2022 | 17/02/2022
TO-22-AA GIS-110SB1-3CB-01 | COUPLER/SECTIONALISING CB - ARDNACRUSHA GIS 110-ARDNACRUSHA GIS 110-110SB1-3CB | 5 | 5 | 5 | Scheduled | 21/02/2022 | 25/02/2022
TO-22-BVK-110SB1-2CB-02 | COUPLER/SECTIONALISING CB - BALLYVOUSKILL 110-BALLYVOUSKILL 110-110SB1-2CB | 5 | 5 | 5 | Scheduled | 21/02/2022 | 25/02/2022
TO-22-CLG-110SA1-2CB-03 | COUPLER/SECTIONALISING CB - CLOGHRAN 110-CLOGHRAN 110-110SA1-2CB | 5 | 5 | 5 | Tentative | 21/02/2022 | 25/02/2022
TO-22-FIN-MCD-1-01 | 110kV FEEDER - FINGLAS 110-McDERMOTT 110-1 | 124 | 84 | 84 | Reference | 21/02/2022 | 24/06/2022
TO-22-220 kV A1/A2 @ CLE-01 | BUSBAR SECTION - CLONEE 220-CLONEE 220-220A1-A2 | 1 | 1 | 1 | Tentative | 22/02/2022 | 22/02/2022
TO-22-220 kV B1/B2 @ CLE-01 | BUSBAR SECTION - CLONEE 220-CLONEE 220-220B1-B2 | 1 | 1 | 1 | Tentative | 22/02/2022 | 22/02/2022
TO-22-KPG-220SA2-4CB-03 | COUPLER/SECTIONALISING CB - KILPADDOGE 220-KILPADDOGE 220-220SA2-4CB | 4 | 4 | 4 | Scheduled | 22/02/2022 | 25/02/2022
TO-22-PLA-T105-02 | TSO CUSTOMER TRANSFORMER - PLATIN 110-PLATIN 10-T105 | 8 | 6 | 6 | Scheduled | 23/02/2022 | 02/03/2022
TO-22-110 kV A1/A2 @ CAH-01 | BUSBAR SECTION - CAHIR 110-CAHIR 110-110A1-A2 | 1 | 1 | 1 | Scheduled | 24/02/2022 | 24/02/2022
TO-22-110 kV B1/B2 @ CAH-01 | BUSBAR SECTION - CAHIR 110-CAHIR 110-110B1-B2 | 1 | 1 | 1 | Scheduled | 24/02/2022 | 24/02/2022
TO-22-110 kV A1 @ BYH-01 | BUSBAR SECTION - BALLYNAHULLA 110-BALLYNAHULLA 110-110A1 | 4 | 4 | 4 | Scheduled | 28/02/2022 | 03/03/2022
TO-22-110 kV B1 @ BYH-01 | BUSBAR SECTION - BALLYNAHULLA 110-BALLYNAHULLA 110-110B1 | 4 | 4 | 4 | Scheduled | 28/02/2022 | 03/03/2022
TO-22-220 kV A1 @ BYH-01 | BUSBAR SECTION - BALLYNAHULLA 220-BALLYNAHULLA 220-220A1 | 4 | 4 | 4 | Scheduled | 28/02/2022 | 03/03/2022
TO-22-220 kV B1 @ BYH-01 | BUSBAR SECTION - BALLYNAHULLA 220-BALLYNAHULLA 220-220B1 | 4 | 4 | 4 | Scheduled | 28/02/2022 | 03/03/2022
TO-22-BYH-KNR-1-02 | 220kV FEEDER - BALLYNAHULLA 220-KNOCKANURE 220-1 | 5 | 5 | 5 | Scheduled | 28/02/2022 | 04/03/2022
TO-22-BYH-T2101-01 | TRANSFORMER - BALLYNAHULLA 220-BALLYNAHULLA 110-T2101 | 5 | 5 |  | Scheduled | 28/02/2022 | 04/03/2022
TO-22-110 kV A2 @ CSH-03 | BUSBAR SECTION - CASHLA 110-CASHLA 110-110A2 | 8 | 6 | 6 | Tentative | 28/02/2022 | 07/03/2022
TO-22-CSH-110K1-2-03 | COUPLER/SECTIONALISING CB - CASHLA 110-CASHLA 110-110K1-2 | 8 | 6 | 6 | Tentative | 28/02/2022 | 07/03/2022
TO-22-CSH-CLN-1-05 | 110kV FEEDER - CASHLA 110-CLOON 110-1 | 1 | 1 | 1 | Tentative | 28/02/2022 | 28/02/2022
TO-22-CSH-PRO-1-01 | 220kV FEEDER - CASHLA 220-PROSPECT 220-1 | 31 | 22 | 22 | Scheduled | 28/02/2022 | 30/03/2022
TO-22-CBR-DLT-1-02 | 110kV FEEDER - CASTLEBAR 110-DALTON 110-1 | 5 | 5 | 5 | Tentative | 28/02/2022 | 04/03/2022
TO-22-110 kV A3 @ CDU-02 | BUSBAR SECTION - CORDUFF 110-CORDUFF 110-110A3 | 4 | 4 | 4 | Scheduled | 28/02/2022 | 03/03/2022
TO-22-110 kV B3 @ CDU-03 | BUSBAR SECTION - CORDUFF 110-CORDUFF 110-110B3 | 4 | 4 | 4 | Scheduled | 28/02/2022 | 03/03/2022
TO-22-CDU-PLA-1-01 | 110kV FEEDER - CORDUFF 110-PLATIN 110-1 | 159 | 108 | 108 | Scheduled | 28/02/2022 | 05/08/2022
TO-22-FLA-SLB-1-01 | 110kV FEEDER - FLAGFORD 110-SLIABH BAWN 110-1 | 59 | 40 | 40 | Scheduled | 28/02/2022 | 27/04/2022
TO-22-KLN-T2104-01 | TRANSFORMER - KILLONAN 220-KILLONAN 110-T2104 | 5 | 5 | 5 | Scheduled | 28/02/2022 | 04/03/2022
TO-22-MP GIS-PRO-1-01 | 220kV FEEDER - MONEYPOINT GIS 220-PROSPECT 220-1 | 5 | 5 | 5 | Scheduled | 28/02/2022 | 04/03/2022
TO-22-PRO-TB-1-04 | 220kV FEEDER - PROSPECT 220-TARBERT 220-1 | 5 | 5 | 5 | Scheduled | 28/02/2022 | 04/03/2022
TO-22-SOM-T142-01 | DISTRIBUTION TRANSFORMER - SOMERSET 110-SOMERSET 38-T142 | 79 | 52 | 52 | Reference | 28/02/2022 | 17/05/2022
TO-22-SOM,T-CSH-1-05 | 110kV FEEDER - SOMERSET tee-CASHLA 110-1 | 12 | 10 | 10 | Scheduled | 28/02/2022 | 11/03/2022
TO-22-SOM,T-SH-1-05 | 110kV FEEDER - SOMERSET tee-SHANNONBRIDGE 110-1 | 12 | 10 | 10 | Scheduled | 28/02/2022 | 11/03/2022
TO-22-CAH-TIP-1-01 | 110kV FEEDER - CAHIR 110-TIPPERARY 110-1 | 4 | 4 | 4 | Scheduled | 01/03/2022 | 04/03/2022
TO-22-CF-SRA-2-01 | 110kV FEEDER - CATHALEENS FALL 110-SRANANAGH 110-2 | 7 | 5 | 5 | Scheduled | 01/03/2022 | 07/03/2022
TO-22-FIN-HN-1-01 | 220kV FEEDER - FINGLAS 220-HUNTSTOWN 220-1 | 7 | 5 | 5 | Scheduled | 01/03/2022 | 07/03/2022
TO-22-HN-T2010/11-01 | GENERATOR TRANSFORMER - HUNTSTOWN 220-HUNTSTOWN G10/11-T2010/11 | 7 | 5 | 5 | Scheduled | 01/03/2022 | 07/03/2022
TO-22-KTN-WAT-1-01 | 110kV FEEDER - KILLOTERAN 110-WATERFORD 110-1 | 4 | 4 | 4 | Scheduled | 01/03/2022 | 04/03/2022
TO-22-LIS-LOU-1-05 | 110kV FEEDER - LISDRUM 110-LOUTH 110-1 | 3 | 3 | 3 | Scheduled | 01/03/2022 | 03/03/2022
TO-22-MCE-T121-01 | TSO CUSTOMER TRANSFORMER - MACETOWN 110-MACETOWN 20-T121 | 1 | 1 | 1 | Scheduled | 02/03/2022 | 02/03/2022
TO-22-MAY-RNW-1-04 | 110kV FEEDER - MAYNOOTH 110-RINAWADE 110-1 | 3 | 3 | 3 | Tentative | 02/03/2022 | 04/03/2022
TO-22-MAY-RYB GIS-1-02 | 110kV FEEDER - MAYNOOTH 110-RYEBROOK GIS 110-1 | 3 | 3 | 3 | Tentative | 02/03/2022 | 04/03/2022
TO-22-110 kV A1/A2 @ SNU-01 | BUSBAR SECTION - SNUGBOROUGH 110-SNUGBOROUGH 110-110A1-A2 | 1 | 1 | 1 | Scheduled | 02/03/2022 | 02/03/2022
TO-22-110 kV B1/B2 @ SNU-01 | BUSBAR SECTION - SNUGBOROUGH 110-SNUGBOROUGH 110-110B1-B2 | 1 | 1 | 1 | Scheduled | 02/03/2022 | 02/03/2022
TO-22-PLA-T101/2/3/4-04 | TSO CUSTOMER TRANSFORMER - PLATIN 110-PLATIN 10-T101/2/3/4 | 14 | 10 | 10 | Scheduled | 03/03/2022 | 16/03/2022
TO-22-110 kV A2 @ FIN-01 | BUSBAR SECTION - FINGLAS 110-FINGLAS 110-110A2 | 5 | 5 | 5 | Scheduled | 07/03/2022 | 11/03/2022
TO-22-FIN-220K1-11 | COUPLER/SECTIONALISING CB - FINGLAS 220-FINGLAS 220-220K1 | 5 | 5 | 5 | Scheduled | 07/03/2022 | 11/03/2022
TO-22-KLN-T2101-01 | TRANSFORMER - KILLONAN 220-KILLONAN 110-T2101 | 30 | 20 | 20 | Scheduled | 07/03/2022 | 05/04/2022
TO-22-MAY-WOO-1-02 | 220kV FEEDER - MAYNOOTH 220-WOODLAND 220-1 | 135 | 91 | 91 | Scheduled | 07/03/2022 | 19/07/2022
TO-22-110 kV A1 @ TB-01 | BUSBAR SECTION - TARBERT 110-TARBERT 110-110A1 | 29 | 19 | 19 | Scheduled | 07/03/2022 | 04/04/2022
TO-22-110 kV B1 @ TB-01 | BUSBAR SECTION - TARBERT 110-TARBERT 110-110B1 | 29 | 19 | 19 | Scheduled | 07/03/2022 | 04/04/2022
TO-22-ARK-BEG-1-01 | 110kV FEEDER - ARKLOW 110-BALLYBEG 110-1 | 2 | 2 | 2 | Scheduled | 08/03/2022 | 09/03/2022
TO-22-BIN-CF-1-03 | 110kV FEEDER - BINBANE 110-CATHALEENS FALL 110-1 | 4 | 4 | 4 | Scheduled | 08/03/2022 | 11/03/2022
TO-22-220 kV A1/A2 @ MP GIS-01 | BUSBAR SECTION - MONEYPOINT GIS 220-MONEYPOINT GIS 220-220A1-A2 | 1 | 1 | 1 | Scheduled | 09/03/2022 | 09/03/2022
TO-22-220 kV B1/B2 @ MP GIS-01 | BUSBAR SECTION - MONEYPOINT GIS 220-MONEYPOINT GIS 220-220B1-B2 | 1 | 1 | 1 | Scheduled | 09/03/2022 | 09/03/2022
TO-22-400 kV A1/A2/A3/A4 @ MP GIS-01 | BUSBAR SECTION - MONEYPOINT GIS 400-MONEYPOINT GIS 400-400A1-A2-A3-A4 | 1 | 1 | 1 | Scheduled | 09/03/2022 | 09/03/2022
TO-22-400 kV B1/B2/B3/B4 @ MP GIS-01 | BUSBAR SECTION - MONEYPOINT GIS 400-MONEYPOINT GIS 400-400B1-B2-B3-B4 | 1 | 1 | 1 | Scheduled | 09/03/2022 | 09/03/2022
TO-22-CDU-SNU-1-01 | 110kV FEEDER - CORDUFF 110-SNUGBOROUGH 110-1 | 2 | 2 |  | Scheduled | 14/03/2022 | 15/03/2022
TO-22-CRA-WEX-1-01 | 110kV FEEDER - CRANE 110-WEXFORD 110-1 | 9 | 5 | 5 | Scheduled | 14/03/2022 | 22/03/2022
TO-22-KRA-MID-1-01 | 110kV FEEDER - KNOCKRAHA 110-MIDLETON 110-1 | 3 | 3 | 3 | Scheduled | 14/03/2022 | 16/03/2022
TO-22-400 kV B1 @ WOO-03 | BUSBAR SECTION - WOODLAND 400-WOODLAND 400-400B1 | 1 | 1 | 1 | Scheduled | 14/03/2022 | 14/03/2022
TO-22-WOO-T4201-01 | TRANSFORMER - WOODLAND 400-WOODLAND 220-T4201 | 157 | 106 | 106 | Scheduled | 14/03/2022 | 17/08/2022
TO-22-BUT-KTN-1-01 | 110kV FEEDER - BUTLERSTOWN 110-KILLOTERAN 110-1 | 1 | 1 |  | Scheduled | 15/03/2022 | 15/03/2022
TO-22-PRN-T4301-01 | TRANSFORMER - PORTAN 400-PORTAN 260-T4301 | 16 | 10 | 10 | Scheduled | 15/03/2022 | 30/03/2022
TO-22-PRN-WOO-1-01 | 400kV FEEDER - PORTAN 400-WOODLAND 400-1 | 16 | 10 | 10 | Scheduled | 15/03/2022 | 30/03/2022
TO-22-110 kV A1/A2 @ PLS-01 | BUSBAR SECTION - PORTLAOISE 110-PORTLAOISE 110-110A1-A2 | 1 | 1 | 1 | Scheduled | 16/03/2022 | 16/03/2022
TO-22-110 kV B1/B2 @ PLS-01 | BUSBAR SECTION - PORTLAOISE 110-PORTLAOISE 110-110B1-B2 | 1 | 1 | 1 | Scheduled | 16/03/2022 | 16/03/2022
TO-22-AA GIS-110K3-01 | COUPLER/SECTIONALISING CB - ARDNACRUSHA GIS 110-ARDNACRUSHA GIS 110-110K3 | 5 | 5 | 5 | Scheduled | 21/03/2022 | 25/03/2022
TO-22-BYH-110K1-01 | COUPLER/SECTIONALISING CB - BALLYNAHULLA 110-BALLYNAHULLA 110-110K1 | 5 | 5 | 5 | Scheduled | 21/03/2022 | 25/03/2022
TO-22-220 kV A3 @ CKM GIS-03 | BUSBAR SECTION - CARRICKMINES GIS 220-CARRICKMINES GIS 220-220A3 | 12 | 10 | 10 | Scheduled | 21/03/2022 | 01/04/2022
TO-22-220 kV B3 @ CKM GIS-03 | BUSBAR SECTION - CARRICKMINES GIS 220-CARRICKMINES GIS 220-220B3 | 12 | 10 | 10 | Scheduled | 21/03/2022 | 01/04/2022
TO-22-CKM GIS-220K3-01 | COUPLER/SECTIONALISING CB - CARRICKMINES GIS 220-CARRICKMINES GIS 220-220K3 | 12 | 10 | 10 | Scheduled | 21/03/2022 | 01/04/2022
TO-22-110 kV A2 @ CDU-01 | BUSBAR SECTION - CORDUFF 110-CORDUFF 110-110A2 | 5 | 5 | 5 | Scheduled | 21/03/2022 | 25/03/2022
TO-22-110 kV B2 @ CDU-01 | BUSBAR SECTION - CORDUFF 110-CORDUFF 110-110B2 | 5 | 5 | 5 | Scheduled | 21/03/2022 | 25/03/2022
TO-22-CDU-T2102-01 | TRANSFORMER - CORDUFF 220-CORDUFF 110-T2102 | 12 | 10 | 10 | Scheduled | 21/03/2022 | 01/04/2022
TO-22-DMY-MAC-1-01 | 110kV FEEDER - DUNMANWAY 110-MACROOM 110-1 | 12 | 10 | 10 | Scheduled | 21/03/2022 | 01/04/2022
TO-22-110 kV A1 @ FIN GIS-02 | BUSBAR SECTION - FINGLAS GIS 110-FINGLAS GIS 110-110A1 | 5 | 5 | 5 | Scheduled | 21/03/2022 | 25/03/2022
TO-22-110 kV B1 @ FIN GIS-02 | BUSBAR SECTION - FINGLAS GIS 110-FINGLAS GIS 110-110B1 | 5 | 5 | 5 | Scheduled | 21/03/2022 | 25/03/2022
TO-22-FIN GIS-110K1-01 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110K1 | 5 | 5 | 5 | Scheduled | 21/03/2022 | 25/03/2022
TO-22-KNR-TRI-1-01 | 110kV FEEDER - KNOCKANURE 110-TRIEN 110-1 | 5 | 5 | 5 | Scheduled | 21/03/2022 | 25/03/2022
TO-22-LOU-MLN-1-01 | 110kV FEEDER - LOUTH 110-MULLAGHARLIN 110-1 | 1 | 1 | 1 | Scheduled | 21/03/2022 | 21/03/2022
TO-22-RAF-TBG-1-02 | 110kV FEEDER - RAFFEEN 110-TRABEG 110-1 | 5 | 5 | 5 | Scheduled | 21/03/2022 | 25/03/2022
TO-22-RYB GIS-T133-02 | TSO CUSTOMER TRANSFORMER - RYEBROOK GIS 110-RYEBROOK 33-T133 | 138 | 95 | 95 | Scheduled | 21/03/2022 | 05/08/2022
TO-22-110 kV B1 @ TBG-01 | BUSBAR SECTION - TRABEG 110-TRABEG 110-110B1 | 5 | 5 | 5 | Scheduled | 21/03/2022 | 25/03/2022
TO-22-110 kV B2 @ TBG-01 | BUSBAR SECTION - TRABEG 110-TRABEG 110-110B2 | 5 | 5 | 5 | Scheduled | 21/03/2022 | 25/03/2022
TO-22-110 kV A2 @ CAH-01 | BUSBAR SECTION - CAHIR 110-CAHIR 110-110A2 | 3 | 3 | 3 | Scheduled | 22/03/2022 | 24/03/2022
TO-22-DDK-LOU-1-01 | 110kV FEEDER - DUNDALK 110-LOUTH 110-1 | 4 | 4 | 4 | Scheduled | 22/03/2022 | 25/03/2022
TO-22-110 kV A1/A2/A4 @ KNR-01 | BUSBAR SECTION - KNOCKANURE 110-KNOCKANURE 110-110A1-A2-A4 | 1 | 1 | 1 | Scheduled | 23/03/2022 | 23/03/2022
TO-22-110 kV B1/B2/B4 @ KNR-01 | BUSBAR SECTION - KNOCKANURE 110-KNOCKANURE 110-110B1-B2-B4 | 1 | 1 | 1 | Scheduled | 23/03/2022 | 23/03/2022
TO-22-220 kV A1/A2 @ KNR-01 | BUSBAR SECTION - KNOCKANURE 220-KNOCKANURE 220-220A1-A2 | 1 | 1 | 1 | Scheduled | 23/03/2022 | 23/03/2022
TO-22-220 kV B1/B2 @ KNR-01 | BUSBAR SECTION - KNOCKANURE 220-KNOCKANURE 220-220B1-B2 | 1 | 1 | 1 | Scheduled | 23/03/2022 | 23/03/2022
TO-22-400 kV A1 @ WOO-02 | BUSBAR SECTION - WOODLAND 400-WOODLAND 400-400A1 | 21 | 15 | 15 | Scheduled | 24/03/2022 | 13/04/2022
TO-22-400 kV A2 @ WOO-01 | BUSBAR SECTION - WOODLAND 400-WOODLAND 400-400A2 | 21 | 15 | 15 | Scheduled | 24/03/2022 | 13/04/2022
TO-22-400 kV B1 @ WOO-02 | BUSBAR SECTION - WOODLAND 400-WOODLAND 400-400B1 | 21 | 15 | 15 | Scheduled | 24/03/2022 | 13/04/2022
TO-22-400 kV B2 @ WOO-01 | BUSBAR SECTION - WOODLAND 400-WOODLAND 400-400B2 | 21 | 15 | 15 | Scheduled | 24/03/2022 | 13/04/2022
TO-22-WOO-400K1-2-02 | COUPLER/SECTIONALISING CB - WOODLAND 400-WOODLAND 400-400K1-2 | 21 | 15 | 15 | Scheduled | 24/03/2022 | 13/04/2022
TO-22-ARK-220K1-2-02 | COUPLER/SECTIONALISING CB - ARKLOW 220-ARKLOW 220-220K1-2 | 23 | 15 |  | Scheduled | 28/03/2022 | 19/04/2022
TO-22-ARK-CKM GIS-1-01 | 220kV FEEDER - ARKLOW 220-CARRICKMINES GIS 220-1 | 23 | 15 | 15 | Scheduled | 28/03/2022 | 19/04/2022
TO-22-ARK-LWD-1-01 | 220kV FEEDER - ARKLOW 220-LODGEWOOD 220-1 | 25 | 17 | 17 | Scheduled | 28/03/2022 | 21/04/2022
TO-22-ARK-T2101-01 | TRANSFORMER - ARKLOW 220-ARKLOW 110-T2101 | 23 | 15 | 15 | Scheduled | 28/03/2022 | 19/04/2022
TO-22-ARK-T2102-01 | TRANSFORMER - ARKLOW 220-ARKLOW 110-T2102 | 23 | 15 | 15 | Scheduled | 28/03/2022 | 19/04/2022
TO-22-220 kV A2 @ CLE-04 | BUSBAR SECTION - CLONEE 220-CLONEE 220-220A2 | 5 | 5 | 5 | Scheduled | 28/03/2022 | 01/04/2022
TO-22-220 kV B2 @ CLE-03 | BUSBAR SECTION - CLONEE 220-CLONEE 220-220B2 | 5 | 5 | 5 | Scheduled | 28/03/2022 | 01/04/2022
TO-22-CLE-220K2-04 | COUPLER/SECTIONALISING CB - CLONEE 220-CLONEE 220-220K2 | 8 | 6 | 6 | Scheduled | 28/03/2022 | 04/04/2022
TO-22-CLE-220SA1-2CB-03 | COUPLER/SECTIONALISING CB - CLONEE 220-CLONEE 220-220SA1-2CB | 8 | 6 | 6 | Scheduled | 28/03/2022 | 04/04/2022
TO-22-CLE-220SB1-2CB-02 | COUPLER/SECTIONALISING CB - CLONEE 220-CLONEE 220-220SB1-2CB | 8 | 6 | 6 | Scheduled | 28/03/2022 | 04/04/2022
TO-22-CLE-WOO-1-06 | 220kV FEEDER - CLONEE 220-WOODLAND 220-1 | 8 | 6 | 6 | Scheduled | 28/03/2022 | 04/04/2022
TO-22-220 kV A2 @ CDU-04 | BUSBAR SECTION - CORDUFF 220-CORDUFF 220-220A2 | 5 | 5 | 5 | Scheduled | 28/03/2022 | 01/04/2022
TO-22-220 kV B2 @ CDU-05 | BUSBAR SECTION - CORDUFF 220-CORDUFF 220-220B2 | 5 | 5 | 5 | Scheduled | 28/03/2022 | 01/04/2022
TO-22-DDK-MLN-1-01 | 110kV FEEDER - DUNDALK 110-MULLAGHARLIN 110-1 | 100 | 68 | 68 | Scheduled | 28/03/2022 | 05/07/2022
TO-22-220 kV A1 @ KLN-01 | BUSBAR SECTION - KILLONAN 220-KILLONAN 220-220A1 | 5 | 5 | 5 | Scheduled | 28/03/2022 | 01/04/2022
TO-22-220 kV A2 @ KLN-01 | BUSBAR SECTION - KILLONAN 220-KILLONAN 220-220A2 | 5 | 5 | 9 | Scheduled | 28/03/2022 | 01/04/2022
TO-22-220 kV B1 @ KLN-01 | BUSBAR SECTION - KILLONAN 220-KILLONAN 220-220B1 | 5 | 5 | 9 | Scheduled | 28/03/2022 | 01/04/2022
TO-22-220 kV B2 @ KLN-01 | BUSBAR SECTION - KILLONAN 220-KILLONAN 220-220B2 | 5 | 5 | 5 | Scheduled | 28/03/2022 | 01/04/2022
TO-22-KPG-RAT-1-01 | 110kV FEEDER - KILPADDOGE 110-RATHKEALE 110-1 | 4 | 4 |  | Scheduled | 28/03/2022 | 31/03/2022
TO-22-KPG-TRL-2-01 | 110kV FEEDER - KILPADDOGE 110-TRALEE 110-2 | 5 | 5 | 5 | Scheduled | 28/03/2022 | 01/04/2022
TO-22-CAH-110K1-2-02 | COUPLER/SECTIONALISING CB - CAHIR 110-CAHIR 110-110K1-2 | 4 | 4 | 4 | Scheduled | 29/03/2022 | 01/04/2022
TO-22-MR-TBG-1-02 | 110kV FEEDER - MARINA 110-TRABEG 110-1 | 2 | 2 | 2 | Scheduled | 29/03/2022 | 30/03/2022
TO-22-110 kV A1 @ GRV-01 | BUSBAR SECTION - GARVAGH 110-GARVAGH 110-110A1 | 1 | 1 | 1 | Scheduled | 30/03/2022 | 30/03/2022
TO-22-110 kV B1 @ GRV-01 | BUSBAR SECTION - GARVAGH 110-GARVAGH 110-110B1 | 1 | 1 | 1 | Scheduled | 30/03/2022 | 30/03/2022
TO-22-AGL-SH-1-01 | 110kV FEEDER - AGANNYGAL 110-SHANNONBRIDGE 110-1 | 4 | 4 | 4 | Scheduled | 04/04/2022 | 07/04/2022
TO-22-AA GIS-T104-01 | GENERATOR TRANSFORMER - ARDNACRUSHA GIS 110-ARDNACRUSHA GIS G4-T104 | 54 | 37 | 37 | Scheduled | 04/04/2022 | 27/05/2022
TO-22-BDA-MON-1-01 | 110kV FEEDER - BARODA 110-MONREAD 110-1 | 11 | 9 | 9 | Scheduled | 04/04/2022 | 14/04/2022
TO-22-220 kV A1 @ CKM GIS-02 | BUSBAR SECTION - CARRICKMINES GIS 220-CARRICKMINES GIS 220-220A1 | 16 | 10 | 10 | Scheduled | 04/04/2022 | 19/04/2022
TO-22-220 kV A2 @ CKM GIS-01 | BUSBAR SECTION - CARRICKMINES GIS 220-CARRICKMINES GIS 220-220A2 | 16 | 10 | 10 | Scheduled | 04/04/2022 | 19/04/2022
TO-22-CKM GIS-220SA1-2CB-01 | COUPLER/SECTIONALISING CB - CARRICKMINES GIS 220-CARRICKMINES GIS 220-22SA1-2CB | 16 | 10 | 10 | Scheduled | 04/04/2022 | 19/04/2022
TO-22-220 kV A1 @ CBT-01 | BUSBAR SECTION - CASTLEBAGOT 220-CASTLEBAGOT 220-220A1 | 5 | 5 | 5 | Scheduled | 04/04/2022 | 08/04/2022
TO-22-220 kV A2 @ CBT-01 | BUSBAR SECTION - CASTLEBAGOT 220-CASTLEBAGOT 220-220A2 | 5 | 5 | 5 | Scheduled | 04/04/2022 | 08/04/2022
TO-22-CBT-220SA1-2CB-01 | COUPLER/SECTIONALISING CB - CASTLEBAGOT 220-CASTLEBAGOT 220-220SA1-2CB | 5 | 5 | 5 | Scheduled | 04/04/2022 | 08/04/2022
TO-22-CF-SRA-1-01 | 110kV FEEDER - CATHALEENS FALL 110-SRANANAGH 110-1 | 5 | 5 |  | Scheduled | 04/04/2022 | 08/04/2022
TO-22-CHA-GLE-1-01 | 110kV FEEDER - CHARLEVILLE 110-GLENLARA 110-1 | 9 | 7 | 7 | Scheduled | 04/04/2022 | 12/04/2022
TO-22-CLA-CKN-1-01 | 110kV FEEDER - CLASHAVOON 110-CLONKEEN 110-1 | 12 | 9 | 12 | Scheduled | 04/04/2022 | 15/04/2022
TO-22-CL-T101-03 | GENERATOR TRANSFORMER - CLIFF 110-CLIFF G1-T101 | 5 | 5 | 5 | Tentative | 04/04/2022 | 08/04/2022
TO-22-DDK-110SA1-01 | SECTIONALISING DISCONNECT - DUNDALK 110-DUNDALK 110-110SA1 | 5 | 5 | 5 | Scheduled | 04/04/2022 | 08/04/2022
TO-22-DDK-110SA2-01 | SECTIONALISING DISCONNECT - DUNDALK 110-DUNDALK 110-110SA2 | 5 | 5 | 5 | Scheduled | 04/04/2022 | 08/04/2022
TO-22-DDK-T141-01 | DISTRIBUTION TRANSFORMER - DUNDALK 110-DUNDALK 38-T141 | 5 | 5 | 5 | Reference | 04/04/2022 | 08/04/2022
TO-22-KPG-TB-1-03 | 220kV FEEDER - KILPADDOGE 220-TARBERT 220-1 | 5 | 5 | 5 | Scheduled | 04/04/2022 | 08/04/2022
TO-22-KPG-TRL-1-02 | 110kV FEEDER - KILPADDOGE 110-TRALEE 110-1 | 10 | 8 | 8 | Scheduled | 04/04/2022 | 13/04/2022
TO-22-MON-110SA1-01 | SECTIONALISING DISCONNECT - MONREAD 110-MONREAD 110-110SA1 | 11 | 9 | 9 | Scheduled | 04/04/2022 | 14/04/2022
TO-22-MON-110SA2-02 | SECTIONALISING DISCONNECT - MONREAD 110-MONREAD 110-110SA2 | 11 | 9 | 9 | Scheduled | 04/04/2022 | 14/04/2022
TO-22-MON-T101-01 | DISTRIBUTION TRANSFORMER - MONREAD 110-MONREAD 10-T101 | 11 | 9 | 9 | Reference | 04/04/2022 | 14/04/2022
TO-22-COL-FIN GIS-1-05 | 110kV FEEDER - COLLEGE PARK 110-FINGLAS GIS 110-1 | 1 | 1 | 1 | Scheduled | 05/04/2022 | 05/04/2022
TO-22-KPG-TB-1-01 | 220kV FEEDER - KILPADDOGE 220-TARBERT 220-1 | 168 | 115 | 115 | Scheduled | 05/04/2022 | 19/09/2022
TO-22-220 kV A1 @ TB-01 | BUSBAR SECTION - TARBERT 220-TARBERT 220-220A1 | 168 | 115 | 115 | Scheduled | 05/04/2022 | 19/09/2022
TO-22-220 kV B1 @ TB-01 | BUSBAR SECTION - TARBERT 220-TARBERT 220-220B1 | 168 | 115 | 115 | Scheduled | 05/04/2022 | 19/09/2022
TO-22-MP GIS-T4002-01 | GENERATOR TRANSFORMER - MONEYPOINT GIS 400-MONEYPOINT GIS G2-T4002 | 3 | 3 | 3 | Scheduled | 06/04/2022 | 08/04/2022
TO-22-TB-110K1-2-01 | COUPLER/SECTIONALISING CB - TARBERT 110-TARBERT 110-110K1-2 | 2 | 2 | 2 | Scheduled | 06/04/2022 | 07/04/2022
TO-22-110 kV A1/A2 @ TBG-01 | BUSBAR SECTION - TRABEG 110-TRABEG 110-110A1-A2 | 1 | 1 | 1 | Scheduled | 06/04/2022 | 06/04/2022
TO-22-110 kV B1/B2 @ TBG-01 | BUSBAR SECTION - TRABEG 110-TRABEG 110-110B1-B2 | 1 | 1 | 1 | Scheduled | 06/04/2022 | 06/04/2022
TO-22-BDA-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - BARODA 110-BARODA 110-110SA1-2CB | 1 | 1 | 1 | Scheduled | 08/04/2022 | 08/04/2022
TO-22-110 kV A1 @ CSH-06 | BUSBAR SECTION - CASHLA 110-CASHLA 110-110A1 | 4 | 4 | 4 | Scheduled | 11/04/2022 | 14/04/2022
TO-22-110 kV B1 @ CSH-06 | BUSBAR SECTION - CASHLA 110-CASHLA 110-110B1 | 4 | 4 | 4 | Scheduled | 11/04/2022 | 14/04/2022
TO-22-CSH-CAP1-01 | CAPACITOR/SVC/REACTOR - CASHLA 110-CASHLA 110-CAP1 | 4 | 4 | 4 | Scheduled | 11/04/2022 | 14/04/2022
TO-22-CNO-KPG-1-01 | 110kV FEEDER - COOLNANOONAGH 110-KILPADDOGE 110-1 | 4 | 4 | 4 | Scheduled | 11/04/2022 | 14/04/2022
TO-22-CNO-T131-01 | GENERATOR TRANSFORMER - COOLNANOONAGH 110-COOLNANOONAGH 33-T131 | 4 | 4 | 4 | Scheduled | 11/04/2022 | 14/04/2022
TO-22-KNY-SAL-1-02 | 110kV FEEDER - KNOCKRANNY-SALTHILL 110-1 | 12 | 8 | 8 | Scheduled | 11/04/2022 | 22/04/2022
TO-22-BLC-DND-1-01 | 110kV FEEDER - BELCAMP 110-DARNDALE 110-1 | 1 | 1 | 1 | Scheduled | 12/04/2022 | 12/04/2022
TO-22-BOL-ENN-1-01 | 110kV FEEDER - BOOLTIAGH 110-ENNIS 110-1 | 2 | 2 | 2 | Scheduled | 13/04/2022 | 14/04/2022
TO-22-110 kV A1/A2 @ CLG-01 | BUSBAR SECTION - CLOGHRAN 110-CLOGHRAN 110-110A1-A2 | 1 | 1 | 1 | Scheduled | 13/04/2022 | 13/04/2022
TO-22-110 kV B1/B2 @ CLG-01 | BUSBAR SECTION - CLOGHRAN 110-CLOGHRAN 110-110B1-B2 | 1 | 1 | 1 | Scheduled | 13/04/2022 | 13/04/2022
TO-22-DND-110K1-01 | COUPLER/SECTIONALISING CB - DARNDALE 110-DARNDALE 110-110K1 | 1 | 1 | 1 | Scheduled | 13/04/2022 | 13/04/2022
TO-22-DND-110K2-01 | COUPLER/SECTIONALISING CB - DARNDALE 110-DARNDALE 110-110K2 | 1 | 1 | 1 | Scheduled | 13/04/2022 | 13/04/2022
TO-22-BRT-220K2-01 | COUPLER/SECTIONALISING CB - BRACETOWN 220-BRACETOWN 220-220K2 | 1 | 1 | 1 | Scheduled | 14/04/2022 | 14/04/2022
TO-22-DEY-110K2-02 | COUPLER/SECTIONALISING CB - DERRYCARNEY 110-DERRYCARNEY 110-110K2 | 175 | 120 | 120 | Scheduled | 14/04/2022 | 05/10/2022
TO-22-220 kV A2 @ CLE-01 | BUSBAR SECTION - CLONEE 220-CLONEE 220-220A2 | 5 | 4 | 4 | Scheduled | 18/04/2022 | 22/04/2022
TO-22-220 kV B2 @ CLE-01 | BUSBAR SECTION - CLONEE 220-CLONEE 220-220B2 | 5 | 4 | 5 | Scheduled | 18/04/2022 | 22/04/2022
TO-22-CLE-CDU-1-06 | 220kV FEEDER - CLONEE 220-CORDUFF 220-1 | 5 | 4 | 4 | Scheduled | 18/04/2022 | 22/04/2022
TO-22-AA GIS-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - ARDNACRUSHA GIS 110-ARDNACRUSHA GIS 110-110SA1-2CB | 4 | 4 | 4 | Scheduled | 19/04/2022 | 22/04/2022
TO-22-AA GIS-LIM-1-01 | 110kV FEEDER - ARDNACRUSHA GIS 110-LIMERICK 110-1 | 15 | 10 | 10 | Scheduled | 19/04/2022 | 03/05/2022
TO-22-BK-CBR-1-04 | 110kV FEEDER - BELLACORICK 110-CASTLEBAR 110-1 | 11 | 9 | 9 | Scheduled | 19/04/2022 | 29/04/2022
TO-22-CLA-KRA-1-02 | 220kV FEEDER - CLASHAVOON 220-KNOCKRAHA 220-1 | 3 | 3 | 3 | Scheduled | 19/04/2022 | 21/04/2022
TO-22-KLN-LIM-2-01 | 110kV FEEDER - KILLONAN 110-LIMERICK 110-2 | 15 | 10 | 10 | Scheduled | 19/04/2022 | 03/05/2022
TO-22-KPG-KNR-1-110-01 | 110kV FEEDER - KILPADDOGE 110-KNOCKANURE 110-1-110 | 7 | 5 | 5 | Scheduled | 19/04/2022 | 25/04/2022
TO-22-KPG-TB-2-01 | 220kV FEEDER - KILPADDOGE 220-TARBERT 220-2 | 3 | 3 |  | Scheduled | 19/04/2022 | 21/04/2022
TO-22-LIM-110SA1-01 | SECTIONALISING DISCONNECT - LIMERICK 110-LIMERICK 110-110SA1 | 15 | 10 | 10 | Scheduled | 19/04/2022 | 03/05/2022
TO-22-LIM-110SA2-01 | SECTIONALISING DISCONNECT - LIMERICK 110-LIMERICK 110-110SA2 | 15 | 10 | 10 | Scheduled | 19/04/2022 | 03/05/2022
TO-22-LIM-RAT-1-01 | 110kV FEEDER - LIMERICK 110-RATHKEALE 110-1 | 15 | 10 | 10 | Scheduled | 19/04/2022 | 03/05/2022
TO-22-LIM-T142-01 | DISTRIBUTION TRANSFORMER - LIMERICK 110-LIMERICK 38-T142 | 15 | 10 | 10 | Reference | 19/04/2022 | 03/05/2022
TO-22-ARK-T101-01 | DISTRIBUTION TRANSFORMER - ARKLOW 110-ARKLOW 10-T101 | 2 | 2 | 2 | Reference | 20/04/2022 | 21/04/2022
TO-22-220 kV B2 @ CKM GIS-01 | BUSBAR SECTION - CARRICKMINES GIS 220-CARRICKMINES GIS 220-220B2 | 10 | 8 | 8 | Scheduled | 20/04/2022 | 29/04/2022
TO-22-220 kV B4 @ CKM GIS-02 | BUSBAR SECTION - CARRICKMINES GIS 220-CARRICKMINES GIS 220-220B4 | 10 | 8 | 8 | Scheduled | 20/04/2022 | 29/04/2022
TO-22-CKM GIS-220SB2-4CB-01 | COUPLER/SECTIONALISING CB - CARRICKMINES GIS 220-CARRICKMINES GIS 220-22SB2-4CB | 10 | 8 | 8 | Scheduled | 20/04/2022 | 29/04/2022
TO-22-DRM-LET-1-01 | 110kV FEEDER - DRUMKEEN 110-LETTERKENNY 110-1 | 2 | 2 | 2 | Scheduled | 20/04/2022 | 21/04/2022
TO-22-110 kV A1/A2 @ KLS-01 | BUSBAR SECTION - KELLIS 110-KELLIS 110-110A1-A2 | 1 | 1 | 1 | Scheduled | 20/04/2022 | 20/04/2022
TO-22-110 kV B1/B2 @ KLS-01 | BUSBAR SECTION - KELLIS 110-KELLIS 110-110B1-B2 | 1 | 1 | 1 | Scheduled | 20/04/2022 | 20/04/2022
TO-22-KIN-T101-02 | TSO CUSTOMER TRANSFORMER - KINNEGAD 110-KINNEGAD 10-T101 | 1 | 1 | 1 | Scheduled | 20/04/2022 | 20/04/2022
TO-22-LOU-T2103-03 | TRANSFORMER - LOUTH 220-LOUTH 110-T2103 | 1 | 1 | 1 | Scheduled | 20/04/2022 | 20/04/2022
TO-22-AA GIS-T101-01 | GENERATOR TRANSFORMER - ARDNACRUSHA GIS 110-ARDNACRUSHA GIS G1-T101 | 5 | 5 | 5 | Scheduled | 25/04/2022 | 29/04/2022
TO-22-CF-COR-1-02 | 110kV FEEDER - CATHALEENS FALL 110-CORRACLASSY 110-1 | 5 | 5 | 5 | Tentative | 25/04/2022 | 29/04/2022
TO-22-TB-T101-01 | GENERATOR TRANSFORMER - TARBERT 110-TARBERT G1-T101 | 5 | 5 | 5 | Scheduled | 25/04/2022 | 29/04/2022
TO-22-TB-T2101-01 | TRANSFORMER - TARBERT 220-TARBERT 110-T2101 | 5 | 5 | 5 | Scheduled | 25/04/2022 | 29/04/2022
TO-22-BVK-220SB1-2CB-01 | COUPLER/SECTIONALISING CB - BALLYVOUSKILL 220-BALLYVOUSKILL 220-220SB1-2CB | 4 | 4 | 4 | Scheduled | 26/04/2022 | 29/04/2022
TO-22-CVW-COW-1-01 | 110kV FEEDER - CASTLEVIEW 110-COW CROSS 110-1 | 15 | 10 | 10 | Scheduled | 26/04/2022 | 10/05/2022
TO-22-COW-OLD-1-01 | 110kV FEEDER - COW CROSS 110-OLDCOURT 110-1 | 15 | 10 | 10 | Reference | 26/04/2022 | 10/05/2022
TO-22-COW-WHI-1-01 | 110kV FEEDER - COW CROSS 110-WHITEGATE 110-1 | 15 | 10 | 10 | Scheduled | 26/04/2022 | 10/05/2022
TO-22-DND-T123-01 | TSO CUSTOMER TRANSFORMER - DARNDALE 110-DARNDALE 20-T123 | 3 | 3 | 3 | Scheduled | 26/04/2022 | 28/04/2022
TO-22-110 kV A1/A2 @ ARV-01 | BUSBAR SECTION - ARVA 110-ARVA 110-110A1-A2 | 1 | 1 | 1 | Scheduled | 27/04/2022 | 27/04/2022
TO-22-110 kV B1/B2 @ ARV-01 | BUSBAR SECTION - ARVA 110-ARVA 110-110B1-B2 | 1 | 1 | 1 | Scheduled | 27/04/2022 | 27/04/2022
TO-22-DND-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - DARNDALE 110-DARNDALE 110-110SA1-2CB | 1 | 1 | 1 | Scheduled | 27/04/2022 | 27/04/2022
TO-22-KNR-R2002-01 | CAPACITOR/SVC/REACTOR - KNOCKANURE 220-KNOCKANURE 220-R2002 | 2 | 2 | 2 | Scheduled | 27/04/2022 | 28/04/2022
TO-22-KNR-T2101-01 | TRANSFORMER - KNOCKANURE 220-KNOCKANURE 110-T2101 | 2 | 2 | 2 | Scheduled | 27/04/2022 | 28/04/2022
TO-22-MCE-T124-01 | TSO CUSTOMER TRANSFORMER - MACETOWN 110-MACETOWN 20-T124 | 1 | 1 | 1 | Scheduled | 27/04/2022 | 27/04/2022
TO-22-BK-CBR-1-01 | 110kV FEEDER - BELLACORICK 110-CASTLEBAR 110-1 | 2 | 2 |  | Scheduled | 28/04/2022 | 29/04/2022
TO-22-CBR-110SA1-2CB-04 | COUPLER/SECTIONALISING CB - CASTLEBAR 110-CASTLEBAR 110-110SA1-2CB | 2 | 2 | 2 | Scheduled | 28/04/2022 | 29/04/2022
TO-22-CBR-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - CASTLEBAR 110-CASTLEBAR 110-110SA1-2CB | 2 | 2 | 2 | Scheduled | 28/04/2022 | 29/04/2022
TO-22-CBR-CLN-1-01 | 110kV FEEDER - CASTLEBAR 110-CLOON 110-1 | 93 | 65 | 65 | Scheduled | 28/04/2022 | 29/07/2022
TO-22-CBR-SVC-01 | CAPACITOR/SVC/REACTOR - CASTLEBAR 110-CASTLEBAR 110-SVC | 33 | 22 |  | Scheduled | 28/04/2022 | 30/05/2022
TO-22-CBR-T141-01 | DISTRIBUTION TRANSFORMER - CASTLEBAR 110-CASTLEBAR 38-T141 | 93 | 65 | 65 | Reference | 28/04/2022 | 29/07/2022
TO-22-GI-KKY-1-05 | 110kV FEEDER - GREAT ISLAND 110-KILKENNY 110-1 | 22 | 15 | 15 | Scheduled | 28/04/2022 | 19/05/2022
TO-22-GI-T141-01 | DISTRIBUTION TRANSFORMER - GREAT ISLAND 110-GREAT ISLAND 38-T141 | 15 | 10 |  | Reference | 28/04/2022 | 12/05/2022
TO-22-KKY-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - KILKENNY 110-KILKENNY 110-110SA1-2CB | 22 | 15 | 15 | Scheduled | 28/04/2022 | 19/05/2022
TO-22-KKY-110SA1-2CB-03 | COUPLER/SECTIONALISING CB - KILKENNY 110-KILKENNY 110-110SA1-2CB | 22 | 15 | 15 | Scheduled | 28/04/2022 | 19/05/2022
TO-22-KKY-CAP2-02 | CAPACITOR/SVC/REACTOR - KILKENNY 110-KILKENNY 110-CAP2 | 22 | 15 | 15 | Scheduled | 28/04/2022 | 19/05/2022
TO-22-KKY-CAP2-03 | CAPACITOR/SVC/REACTOR - KILKENNY 110-KILKENNY 110-CAP2 | 22 | 15 | 15 | Scheduled | 28/04/2022 | 19/05/2022
TO-22-KKY-T142-01 | DISTRIBUTION TRANSFORMER - KILKENNY 110-KILKENNY 38-T142 | 22 | 15 | 15 | Reference | 28/04/2022 | 19/05/2022
TO-22-CBR-CLN-1-02 | 110kV FEEDER - CASTLEBAR 110-CLOON 110-1 | 8 | 5 | 5 | Scheduled | 29/04/2022 | 06/05/2022
TO-22-AGL-ENN-1-01 | 110kV FEEDER - AGANNYGAL 110-ENNIS 110-1 | 11 | 9 | 4 | Scheduled | 03/05/2022 | 13/05/2022
TO-22-CAH-DOO-1-02 | 110kV FEEDER - CAHIR 110-DOON 110-1 | 4 | 4 | 4 | Scheduled | 03/05/2022 | 06/05/2022
TO-22-FLA-SRA-1-02 | 220kV FEEDER - FLAGFORD 220-SRANANAGH 220-1 | 23 | 17 | 17 | Scheduled | 03/05/2022 | 25/05/2022
TO-22-GOR-T122-01 | GENERATOR TRANSFORMER - GORMAN 110-GORMAN 20-T122 | 4 | 4 | 4 | Scheduled | 03/05/2022 | 06/05/2022
TO-22-IA-MAC-1-01 | 110kV FEEDER - INNISCARRA 110-MACROOM 110-1 | 3 | 3 | 3 | Scheduled | 03/05/2022 | 05/05/2022
TO-22-IA-T101-01 | GENERATOR TRANSFORMER - INNISCARRA 110-INNISCARRA G1-T101 | 11 | 9 | 9 | Scheduled | 03/05/2022 | 13/05/2022
TO-22-KLN-KRA-1-01 | 220kV FEEDER - KILLONAN 220-KNOCKRAHA 220-1 | 8 | 6 | 6 | Scheduled | 03/05/2022 | 10/05/2022
TO-22-LA-RIC-2-01 | 110kV FEEDER - LANESBORO 110-RICHMOND 110-2 | 4 | 4 | 4 | Reference | 03/05/2022 | 06/05/2022
TO-22-OUG-T141-01 | DISTRIBUTION TRANSFORMER - OUGHTRAGH 110-OUGHTRAGH 38-T141 | 11 | 9 | 9 | Reference | 03/05/2022 | 13/05/2022
TO-22-OUG,T-KER-1-01 | 110kV FEEDER - OUGHTRAGH tee-KNOCKEARAGH 110-1 | 11 | 9 | 9 | Scheduled | 03/05/2022 | 13/05/2022
TO-22-OUG,T-OUG-1-01 | 110kV FEEDER - OUGHTRAGH tee-OUGHTRAGH 110-1 | 11 | 9 | 9 | Scheduled | 03/05/2022 | 13/05/2022
TO-22-OUG,T-TRL-1-01 | 110kV FEEDER - OUGHTRAGH tee-TRALEE 110-1 | 11 | 9 | 9 | Scheduled | 03/05/2022 | 13/05/2022
TO-22-REM-110SA1-01 | SECTIONALISING DISCONNECT - REAMORE 110-REAMORE 110-110SA1 | 4 | 4 | 4 | Scheduled | 03/05/2022 | 06/05/2022
TO-22-REM-110SA2-01 | SECTIONALISING DISCONNECT - REAMORE 110-REAMORE 110-110SA2 | 4 | 4 | 4 | Scheduled | 03/05/2022 | 06/05/2022
TO-22-REM-T141-01 | DISTRIBUTION TRANSFORMER - REAMORE 110-REAMORE 38-T141 | 4 | 4 | 4 | Reference | 03/05/2022 | 06/05/2022
TO-22-REM-T142-01 | DISTRIBUTION TRANSFORMER - REAMORE 110-REAMORE 38-T142 | 4 | 4 | 4 | Reference | 03/05/2022 | 06/05/2022
TO-22-REM-TRL-1-01 | 110kV FEEDER - REAMORE 110-TRALEE 110-1 | 4 | 4 | 4 | Scheduled | 03/05/2022 | 06/05/2022
TO-22-RYB GIS-T103-01 | TSO CUSTOMER TRANSFORMER - RYEBROOK GIS 110-RYEBROOK 10-T103 | 2 | 2 | 2 | Scheduled | 03/05/2022 | 04/05/2022
TO-22-SRA-220SA1-02 | SECTIONALISING DISCONNECT - SRANANAGH 220-SRANANAGH 220-220SA1 | 23 | 17 | 17 | Scheduled | 03/05/2022 | 25/05/2022
TO-22-SRA-220SA2-02 | SECTIONALISING DISCONNECT - SRANANAGH 220-SRANANAGH 220-220SA2 | 23 | 17 | 17 | Scheduled | 03/05/2022 | 25/05/2022
TO-22-SRA-T2102-02 | TRANSFORMER - SRANANAGH 220-SRANANAGH 110-T2102 | 23 | 17 | 17 | Scheduled | 03/05/2022 | 25/05/2022
TO-22-110 kV A1/A2 @ BVK-01 | BUSBAR SECTION - BALLYVOUSKILL 110-BALLYVOUSKILL 110-110A1-A2 | 1 | 1 | 1 | Scheduled | 04/05/2022 | 04/05/2022
TO-22-110 kV B1/B2 @ BVK-01 | BUSBAR SECTION - BALLYVOUSKILL 110-BALLYVOUSKILL 110-110B1-B2 | 1 | 1 | 1 | Scheduled | 04/05/2022 | 04/05/2022
TO-22-220 kV A1/A2 @ BVK-01 | BUSBAR SECTION - BALLYVOUSKILL 220-BALLYVOUSKILL 220-220A1-A2 | 1 | 1 | 1 | Scheduled | 04/05/2022 | 04/05/2022
TO-22-220 kV B1/B2 @ BVK-01 | BUSBAR SECTION - BALLYVOUSKILL 220-BALLYVOUSKILL 220-220B1-B2 | 1 | 1 | 1 | Scheduled | 04/05/2022 | 04/05/2022
TO-22-CLA-110K1-2-01 | COUPLER/SECTIONALISING CB - CLASHAVOON 110-CLASHAVOON 110-110K1-2 | 2 | 2 | 2 | Scheduled | 04/05/2022 | 05/05/2022
TO-22-DND-T124-01 | TSO CUSTOMER TRANSFORMER - DARNDALE 110-DARNDALE 20-T124 | 1 | 1 | 1 | Scheduled | 04/05/2022 | 04/05/2022
TO-22-WOH-T122-01 | GENERATOR TRANSFORMER - WOODHOUSE 110-WOODHOUSE 20-T122 | 2 | 2 | 2 | Scheduled | 04/05/2022 | 05/05/2022
TO-22-RYB GIS-T104-01 | TSO CUSTOMER TRANSFORMER - RYEBROOK GIS 110-RYEBROOK 10-T104 | 2 | 2 | 2 | Scheduled | 05/05/2022 | 06/05/2022
TO-22-CUS-MLC-1-02 | 110kV FEEDER - CUSHALING 110-MOUNTLUCAS 110-1 | 92 | 64 | 64 | Scheduled | 06/05/2022 | 05/08/2022
TO-22-220 kV A4 @ CKM GIS-02 | BUSBAR SECTION - CARRICKMINES GIS 220-CARRICKMINES GIS 220-220A4 | 12 | 10 | 10 | Scheduled | 09/05/2022 | 20/05/2022
TO-22-220 kV B4 @ CKM GIS-01 | BUSBAR SECTION - CARRICKMINES GIS 220-CARRICKMINES GIS 220-220B4 | 12 | 10 | 10 | Scheduled | 09/05/2022 | 20/05/2022
TO-22-CKM GIS-220K4-01 | COUPLER/SECTIONALISING CB - CARRICKMINES GIS 220-CARRICKMINES GIS 220-220K4 | 12 | 10 | 10 | Scheduled | 09/05/2022 | 20/05/2022
TO-22-CKM GIS-220SA2-4CB-03 | COUPLER/SECTIONALISING CB - CARRICKMINES GIS 220-CARRICKMINES GIS 220-22SA2-4CB | 12 | 10 | 10 | Scheduled | 09/05/2022 | 20/05/2022
TO-22-CKM GIS-220SB2-4CB-02 | COUPLER/SECTIONALISING CB - CARRICKMINES GIS 220-CARRICKMINES GIS 220-22SB2-4CB | 12 | 10 | 10 | Scheduled | 09/05/2022 | 20/05/2022
TO-22-CL-T102-01 | GENERATOR TRANSFORMER - CLIFF 110-CLIFF G2-T102 | 5 | 5 | 5 | Scheduled | 09/05/2022 | 13/05/2022
TO-22-110 kV B1 @ CLG-04 | BUSBAR SECTION - CLOGHRAN 110-CLOGHRAN 110-110B1 | 5 | 5 | 5 | Scheduled | 09/05/2022 | 13/05/2022
TO-22-110 kV B2 @ CLG-03 | BUSBAR SECTION - CLOGHRAN 110-CLOGHRAN 110-110B2 | 5 | 5 | 5 | Scheduled | 09/05/2022 | 13/05/2022
TO-22-CLG-110SB1-2CB-05 | COUPLER/SECTIONALISING CB - CLOGHRAN 110-CLOGHRAN 110-110SB1-2CB | 5 | 5 | 5 | Scheduled | 09/05/2022 | 13/05/2022
TO-22-RYB GIS-T105-01 | TSO CUSTOMER TRANSFORMER - RYEBROOK GIS 110-RYEBROOK 10-T105 | 2 | 2 | 2 | Scheduled | 09/05/2022 | 10/05/2022
TO-22-LOU-AT3-01 | TRANSFORMER - LOUTH 220-LOUTH 275-AT3 | 36 | 25 | 25 | Scheduled | 10/05/2022 | 14/06/2022
TO-22-TH-T2003/4-01 | GENERATOR TRANSFORMER - TURLOUGH HILL 220-TURLOUGH HILL G1-T2003/4 | 28 | 19 | 19 | Scheduled | 10/05/2022 | 06/06/2022
TO-22-CLG-T123-02 | TSO CUSTOMER TRANSFORMER - CLOGHRAN 110-CLOGHRAN 20-T123 | 1 | 1 | 1 | Scheduled | 11/05/2022 | 11/05/2022
TO-22-110 kV A1/A2 @ DND-01 | BUSBAR SECTION - DARNDALE 110-DARNDALE 110-110A1-A2 | 1 | 1 | 1 | Scheduled | 11/05/2022 | 11/05/2022
TO-22-110 kV B1/B2 @ DND-01 | BUSBAR SECTION - DARNDALE 110-DARNDALE 110-110B1-B2 | 1 | 1 | 1 | Scheduled | 11/05/2022 | 11/05/2022
TO-22-RYB GIS-T106-01 | TSO CUSTOMER TRANSFORMER - RYEBROOK GIS 110-RYEBROOK 10-T106 | 2 | 2 | 2 | Scheduled | 11/05/2022 | 12/05/2022
TO-22-AD-220K1-01 | COUPLER/SECTIONALISING CB - AGHADA 220-AGHADA 220-220K1 | 1 | 1 | 1 | Scheduled | 12/05/2022 | 12/05/2022
TO-22-CLH-TRI-1-01 | 110kV FEEDER - CLAHANE 110-TRIEN 110-1 | 80 | 56 | 56 | Scheduled | 16/05/2022 | 03/08/2022
TO-22-RYB GIS-T107-01 | TSO CUSTOMER TRANSFORMER - RYEBROOK GIS 110-RYEBROOK 10-T107 | 2 | 2 | 2 | Scheduled | 16/05/2022 | 17/05/2022
TO-22-SAL-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - SALTHILL 110-SALTHILL 110-110SA1-2CB | 3 | 3 | 3 | Scheduled | 16/05/2022 | 18/05/2022
TO-22-110 kV A1 @ TRI-01 | BUSBAR SECTION - TRIEN 110-TRIEN 110-110A1 | 80 | 56 | 56 | Scheduled | 16/05/2022 | 03/08/2022
TO-22-TRI-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - TRIEN 110-TRIEN 110-110SA1-2CB | 80 | 56 | 56 | Scheduled | 16/05/2022 | 03/08/2022
TO-22-TRI-T141-01 | DISTRIBUTION TRANSFORMER - TRIEN 110-TRIEN 38-T141 | 80 | 56 | 56 | Reference | 16/05/2022 | 03/08/2022
TO-22-ATE-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - ATHEA 110-ATHEA 110-110SA1-2CB | 4 | 4 | 4 | Scheduled | 17/05/2022 | 20/05/2022
TO-22-ATE-DRO-1-01 | 110kV FEEDER - ATHEA 110-DROMADA 110-1 | 4 | 4 | 4 | Scheduled | 17/05/2022 | 20/05/2022
TO-22-ATE-KNR-1-01 | 110kV FEEDER - ATHEA 110-KNOCKANURE 110-1 | 4 | 4 | 4 | Scheduled | 17/05/2022 | 20/05/2022
TO-22-ATE-T121-01 | GENERATOR TRANSFORMER - ATHEA 110-ATHEA 20-T121 | 4 | 4 | 4 | Scheduled | 17/05/2022 | 20/05/2022
TO-22-ATE-TOB-1-01 | 110kV FEEDER - ATHEA 110-TOBERTOREEN 110-1 | 4 | 4 | 4 | Scheduled | 17/05/2022 | 20/05/2022
TO-22-DND-110SB1-2CB-01 | COUPLER/SECTIONALISING CB - DARNDALE 110-DARNDALE 110-110SB1-2CB | 1 | 1 | 1 | Scheduled | 17/05/2022 | 17/05/2022
TO-22-DRO-T121-01 | GENERATOR TRANSFORMER - DROMADA 110-DROMADA 20-T121 | 4 | 4 | 4 | Scheduled | 17/05/2022 | 20/05/2022
TO-22-GOR-220K1-2-01 | COUPLER/SECTIONALISING CB - GORMAN 220-GORMAN 220-220K1-2 | 29 | 20 | 20 | Scheduled | 17/05/2022 | 14/06/2022
TO-22-TOB-T132-01 | GENERATOR TRANSFORMER - TOBERTOREEN 110-TOBERTOREEN 33-T132 | 4 | 4 | 4 | Scheduled | 17/05/2022 | 20/05/2022
TO-22-110 kV B1 @ AA GIS-01 | BUSBAR SECTION - ARDNACRUSHA GIS 110-ARDNACRUSHA GIS 110-110B1 | 1 | 1 | 1 | Scheduled | 18/05/2022 | 18/05/2022
TO-22-110 kV B3 @ AA GIS-01 | BUSBAR SECTION - ARDNACRUSHA GIS 110-ARDNACRUSHA GIS 110-110B3 | 1 | 1 | 1 | Scheduled | 18/05/2022 | 18/05/2022
TO-22-AA GIS-110SB1-3CB-02 | COUPLER/SECTIONALISING CB - ARDNACRUSHA GIS 110-ARDNACRUSHA GIS 110-110SB1-3CB | 1 | 1 | 1 | Scheduled | 18/05/2022 | 18/05/2022
TO-22-AA GIS-T103-02 | GENERATOR TRANSFORMER - ARDNACRUSHA GIS 110-ARDNACRUSHA GIS G3-T103 | 1 | 1 | 1 | Scheduled | 18/05/2022 | 18/05/2022
TO-22-BLC-DND-3-01 | 110kV FEEDER - BELCAMP 110-DARNDALE 110-3 | 1 | 1 | 1 | Scheduled | 18/05/2022 | 18/05/2022
TO-22-CLH-T122-02 | GENERATOR TRANSFORMER - CLAHANE 110-CLAHANE 20-T122 | 1 | 1 | 1 | Scheduled | 18/05/2022 | 18/05/2022
TO-22-CAH-KHL-1-01 | 110kV FEEDER - CAHIR 110-KILL HILL 110-1 | 5 | 5 | 5 | Scheduled | 23/05/2022 | 27/05/2022
TO-22-CD-T103-01 | GENERATOR TRANSFORMER - CARRIGADROHID 110-CARRIGADROHID G3-T103 | 12 | 10 | 10 | Scheduled | 23/05/2022 | 03/06/2022
TO-22-110 kV A1 @ CBA-01 | BUSBAR SECTION - CLOGHBOOLA 110-CLOGHBOOLA 110-110A1 | 5 | 5 | 5 | Scheduled | 23/05/2022 | 27/05/2022
TO-22-110 kV A2 @ CBA-01 | BUSBAR SECTION - CLOGHBOOLA 110-CLOGHBOOLA 110-110A2 | 5 | 5 | 5 | Scheduled | 23/05/2022 | 27/05/2022
TO-22-CBA-110SA1-01 | SECTIONALISING DISCONNECT - CLOGHBOOLA 110-CLOGHBOOLA 110-110SA1 | 5 | 5 | 5 | Scheduled | 23/05/2022 | 27/05/2022
TO-22-CBA-110SA2-01 | SECTIONALISING DISCONNECT - CLOGHBOOLA 110-CLOGHBOOLA 110-110SA2 | 5 | 5 | 5 | Scheduled | 23/05/2022 | 27/05/2022
TO-22-CBA-T122-01 | DISTRIBUTION TRANSFORMER - CLOGHBOOLA 110-CLOGHBOOLA 20-T122 | 5 | 5 | 5 | Reference | 23/05/2022 | 27/05/2022
TO-22-CBA-T131-01 | GENERATOR TRANSFORMER - CLOGHBOOLA 110-CLOGHBOOLA 33-T131 | 5 | 5 | 5 | Scheduled | 23/05/2022 | 27/05/2022
TO-22-CBA-TRI-1-01 | 110kV FEEDER - CLOGHBOOLA 110-TRIEN 110-1 | 5 | 5 | 5 | Scheduled | 23/05/2022 | 27/05/2022
TO-22-220 kV A1 @ DSN-02 | BUSBAR SECTION - DUNSTOWN 220-DUNSTOWN 220-220A1 | 5 | 5 | 5 | Scheduled | 23/05/2022 | 27/05/2022
TO-22-220 kV B1 @ DSN-02 | BUSBAR SECTION - DUNSTOWN 220-DUNSTOWN 220-220B1 | 5 | 5 | 5 | Scheduled | 23/05/2022 | 27/05/2022
TO-22-GOL-T101-03 | GENERATOR TRANSFORMER - GOLAGH 110-GOLAGH 10-T101 | 6 | 5 | 5 | Scheduled | 23/05/2022 | 28/05/2022
TO-22-GOL,T-CLO-1-01 | 110kV FEEDER - GOLAGH tee-CLOGHER 110-1 | 6 | 5 | 5 | Scheduled | 23/05/2022 | 28/05/2022
TO-22-GOL,T-GOL-1-02 | 110kV FEEDER - GOLAGH tee-GOLAGH 110-1 | 6 | 5 | 5 | Scheduled | 23/05/2022 | 28/05/2022
TO-22-GOL,T-LET-1-02 | 110kV FEEDER - GOLAGH tee-LETTERKENNY 110-1 | 6 | 5 | 5 | Scheduled | 23/05/2022 | 28/05/2022
TO-22-220 kV A2 @ INC-03 | BUSBAR SECTION - INCHICORE 220-INCHICORE 220-220A2 | 5 | 5 | 5 | Scheduled | 23/05/2022 | 27/05/2022
TO-22-INC-PB-2-02 | 220kV FEEDER - INCHICORE 220-POOLBEG 220-2 | 96 | 68 | 68 | Scheduled | 23/05/2022 | 26/08/2022
TO-22-MP GIS-T4201-01 | TRANSFORMER - MONEYPOINT GIS 400-MONEYPOINT GIS 220-T4201 | 12 | 10 | 10 | Scheduled | 23/05/2022 | 03/06/2022
TO-22-RYB GIS-T108-01 | TSO CUSTOMER TRANSFORMER - RYEBROOK GIS 110-RYEBROOK 10-T108 | 5 | 5 | 5 | Scheduled | 23/05/2022 | 27/05/2022
TO-22-RYB GIS-T109-01 | TSO CUSTOMER TRANSFORMER - RYEBROOK GIS 110-RYEBROOK 10-T109 | 2 | 2 | 2 | Proposed | 23/05/2022 | 24/05/2022
TO-22-SNU-T102-01 | TSO CUSTOMER TRANSFORMER - SNUGBOROUGH 110-SNUGBOROUGH 10-T102 | 1 | 1 | 1 | Scheduled | 23/05/2022 | 23/05/2022
TO-22-SNU-T102-02 | TSO CUSTOMER TRANSFORMER - SNUGBOROUGH 110-SNUGBOROUGH 10-T102 | 4 | 4 | 4 | Scheduled | 23/05/2022 | 26/05/2022
TO-22-220 kV A2 @ TH-03 | BUSBAR SECTION - TURLOUGH HILL 220-TURLOUGH HILL 220-220A2 | 5 | 5 | 5 | Scheduled | 23/05/2022 | 27/05/2022
TO-22-220 kV B2 @ TH-03 | BUSBAR SECTION - TURLOUGH HILL 220-TURLOUGH HILL 220-220B2 | 5 | 5 | 5 | Scheduled | 23/05/2022 | 27/05/2022
TO-22-CHA-110SA1-2CB-02 | COUPLER/SECTIONALISING CB - CHARLEVILLE 110-CHARLEVILLE 110-110SA1-2CB | 4 | 4 | 4 | Scheduled | 24/05/2022 | 27/05/2022
TO-22-SLB-T132-01 | GENERATOR TRANSFORMER - SLIABH BAWN 110-SLIABH BAWN 33-T132 | 2 | 2 | 2 | Scheduled | 24/05/2022 | 25/05/2022
TO-22-COL-FIN GIS-1-03 | 110kV FEEDER - COLLEGE PARK 110-FINGLAS GIS 110-1 | 1 | 1 | 1 | Scheduled | 25/05/2022 | 25/05/2022
TO-22-CNO-T131-02 | GENERATOR TRANSFORMER - COOLNANOONAGH 110-COOLNANOONAGH 33-T131 | 1 | 1 | 1 | Scheduled | 25/05/2022 | 25/05/2022
TO-22-BK-CBR-1-02 | 110kV FEEDER - BELLACORICK 110-CASTLEBAR 110-1 | 2 | 0 | 0 | Scheduled | 28/05/2022 | 29/05/2022
TO-22-CBR-110SA1-2CB-02 | COUPLER/SECTIONALISING CB - CASTLEBAR 110-CASTLEBAR 110-110SA1-2CB | 2 | 0 | 0 | Scheduled | 28/05/2022 | 29/05/2022
TO-22-220 kV A1 @ CDU-04 | BUSBAR SECTION - CORDUFF 220-CORDUFF 220-220A1 | 12 | 9 | 4 | Scheduled | 30/05/2022 | 10/06/2022
TO-22-220 kV A3 @ CDU-03 | BUSBAR SECTION - CORDUFF 220-CORDUFF 220-220A3 | 12 | 9 | 9 | Scheduled | 30/05/2022 | 10/06/2022
TO-22-220 kV B1 @ CDU-05 | BUSBAR SECTION - CORDUFF 220-CORDUFF 220-220B1 | 12 | 9 | 9 | Scheduled | 30/05/2022 | 10/06/2022
TO-22-220 kV B3 @ CDU-03 | BUSBAR SECTION - CORDUFF 220-CORDUFF 220-220B3 | 12 | 9 | 9 | Scheduled | 30/05/2022 | 10/06/2022
TO-22-CDU-220K1-3-03 | COUPLER/SECTIONALISING CB - CORDUFF 220-CORDUFF 220-220K1-3 | 12 | 9 | 9 | Scheduled | 30/05/2022 | 10/06/2022
TO-22-GRO-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - GARROW 110-GARROW 110-110SA1-2CB | 5 | 5 | 5 | Scheduled | 30/05/2022 | 03/06/2022
TO-22-GRO-T121-01 | DISTRIBUTION TRANSFORMER - GARROW 110-GARROW 20-T121 | 5 | 5 | 5 | Reference | 30/05/2022 | 03/06/2022
TO-22-GRO-T122-01 | GENERATOR TRANSFORMER - GARROW 110-GARROW 20-T122 | 5 | 5 | 5 | Scheduled | 30/05/2022 | 03/06/2022
TO-22-KLN-SH-1-01 | 220kV FEEDER - KILLONAN 220-SHANNONBRIDGE 220-1 | 13 | 9 | 9 | Scheduled | 30/05/2022 | 11/06/2022
TO-22-KIN-MUL-1-02 | 110kV FEEDER - KINNEGAD 110-MULLINGAR 110-1 | 5 | 5 | 5 | Tentative | 30/05/2022 | 03/06/2022
TO-22-MOY-T142-01 | DISTRIBUTION TRANSFORMER - MOY 110-MOY 38-T142 | 117 | 83 | 83 | Reference | 30/05/2022 | 23/09/2022
TO-22-MUL-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - MULLINGAR 110-MULLINGAR 110-110SA1-2CB | 5 | 5 | 5 | Tentative | 30/05/2022 | 03/06/2022
TO-22-MUL-CAP1-01 | CAPACITOR/SVC/REACTOR - MULLINGAR 110-MULLINGAR 110-CAP1 | 5 | 5 | 5 | Tentative | 30/05/2022 | 03/06/2022
TO-22-220 kV A3 @ PB-01 | BUSBAR SECTION - POOLBEG 220-POOLBEG 220-220A3 | 5 | 5 | 5 | Scheduled | 30/05/2022 | 03/06/2022
TO-22-220 kV B3 @ PB-01 | BUSBAR SECTION - POOLBEG 220-POOLBEG 220-220B3 | 5 | 5 | 5 | Scheduled | 30/05/2022 | 03/06/2022
TO-22-SHL-T2016-01 | GENERATOR TRANSFORMER - SHELLYBANKS 220-SHELLYBANKS G6-T2016 | 3 | 3 | 3 | Scheduled | 30/05/2022 | 01/06/2022
TO-22-SNU-T104-01 | TSO CUSTOMER TRANSFORMER - SNUGBOROUGH 110-SNUGBOROUGH 10-T104 | 4 | 4 | 4 | Scheduled | 30/05/2022 | 02/06/2022
TO-22-BYH-GLE-1-02 | 110kV FEEDER - BALLYNAHULLA 110-GLENLARA 110-1 | 4 | 4 | 4 | Scheduled | 31/05/2022 | 03/06/2022
TO-22-CVW-T101-01 | DISTRIBUTION TRANSFORMER - CASTLEVIEW 110-CASTLEVIEW 10-T101 | 2 | 2 | 2 | Reference | 01/06/2022 | 02/06/2022
TO-22-COW-T142-01 | DISTRIBUTION TRANSFORMER - COW CROSS 110-COW CROSS 38-T142 | 2 | 2 | 2 | Reference | 01/06/2022 | 02/06/2022
TO-22-MP GIS-400K3-02 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 400-MONEYPOINT GIS 400-400K3 | 1 | 1 | 1 | Scheduled | 01/06/2022 | 01/06/2022
TO-22-CF-COR-1-03 | 110kV FEEDER - CATHALEENS FALL 110-CORRACLASSY 110-1 | 29 | 20 | 20 | Scheduled | 06/06/2022 | 04/07/2022
TO-22-AUG-SK-3-01 | 110kV FEEDER - AUGHINISH 110-SEALROCK 110-3 | 4 | 4 | 4 | Scheduled | 07/06/2022 | 10/06/2022
TO-22-CD-KBY-1-05 | 110kV FEEDER - CARRIGADROHID 110-KILBARRY 110-1 | 4 | 4 | 4 | Scheduled | 07/06/2022 | 10/06/2022
TO-22-CTN-110SA1-02 | SECTIONALISING DISCONNECT - CAUTEEN 110-CAUTEEN 110-110SA1 | 4 | 4 | 4 | Scheduled | 07/06/2022 | 10/06/2022
TO-22-CTN-110SA2-01 | SECTIONALISING DISCONNECT - CAUTEEN 110-CAUTEEN 110-110SA2 | 4 | 4 | 4 | Scheduled | 07/06/2022 | 10/06/2022
TO-22-CTN-T142-01 | DISTRIBUTION TRANSFORMER - CAUTEEN 110-CAUTEEN 38-T142 | 4 | 4 | 4 | Reference | 07/06/2022 | 10/06/2022
TO-22-CTN-T144-01 | DISTRIBUTION TRANSFORMER - CAUTEEN 110-CAUTEEN 38-T144 | 4 | 4 | 4 | Reference | 07/06/2022 | 10/06/2022
TO-22-CTN-TIP-1-03 | 110kV FEEDER - CAUTEEN 110-TIPPERARY 110-1 | 11 | 9 | 9 | Scheduled | 07/06/2022 | 17/06/2022
TO-22-CLE-WOO-1-07 | 220kV FEEDER - CLONEE 220-WOODLAND 220-1 | 4 | 4 | 4 | Tentative | 07/06/2022 | 10/06/2022
TO-22-CDU-MCE-1-01 | 110kV FEEDER - CORDUFF 110-MACETOWN 110-1 | 4 | 4 | 4 | Scheduled | 07/06/2022 | 10/06/2022
TO-22-110 kV A6 @ FIN GIS-01 | BUSBAR SECTION - FINGLAS GIS 110-FINGLAS GIS 110-110A6 | 4 | 4 | 4 | Scheduled | 07/06/2022 | 10/06/2022
TO-22-110 kV B6 @ FIN GIS-01 | BUSBAR SECTION - FINGLAS GIS 110-FINGLAS GIS 110-110B6 | 4 | 4 | 4 | Scheduled | 07/06/2022 | 10/06/2022
TO-22-FIN GIS-110K6-01 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110K6 | 4 | 4 | 4 | Scheduled | 07/06/2022 | 10/06/2022
TO-22-FIN GIS-110SA4-6CB-02 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110SA4-6CB | 4 | 4 | 4 | Scheduled | 07/06/2022 | 10/06/2022
TO-22-FIN GIS-110SB4-6CB-02 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110SB4-6CB | 4 | 4 | 4 | Scheduled | 07/06/2022 | 10/06/2022
TO-22-MP GIS-T4202-02 | TRANSFORMER - MONEYPOINT GIS 400-MONEYPOINT GIS 220-T4202 | 8 | 6 | 6 | Scheduled | 07/06/2022 | 14/06/2022
TO-22-SK-T103-01 | GENERATOR TRANSFORMER - SEALROCK 110-SEALROCK G3-T103 | 4 | 4 | 4 | Scheduled | 07/06/2022 | 10/06/2022
TO-22-TH-T2001/2-01 | GENERATOR TRANSFORMER - TURLOUGH HILL 220-TURLOUGH HILL G1-T2001/2 | 17 | 13 | 13 | Scheduled | 07/06/2022 | 23/06/2022
TO-22-BAL-DRY-1-02 | 110kV FEEDER - BALTRASNA 110-DRYBRIDGE 110-1 | 2 | 2 | 2 | Scheduled | 08/06/2022 | 09/06/2022
TO-22-BRY-RAF-1-01 | 110kV FEEDER - BARNAHELY 110-RAFFEEN 110-1 | 2 | 2 | 2 | Reference | 08/06/2022 | 09/06/2022
TO-22-MP GIS-400SA1-2CB-01 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 400-MONEYPOINT GIS 400-400SA1-2CB | 1 | 1 | 1 | Scheduled | 08/06/2022 | 08/06/2022
TO-22-MOY-TAW-1-02 | 110kV FEEDER - MOY 110-TAWNAGHMORE 110-1 | 8 | 6 | 6 | Scheduled | 08/06/2022 | 15/06/2022
TO-22-MP GIS-220SB1-2CB-01 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 220-MONEYPOINT GIS 220-220SB1-2CB | 1 | 1 | 1 | Scheduled | 09/06/2022 | 09/06/2022
TO-22-MP GIS-400SA2-4CB-02 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 400-MONEYPOINT GIS 400-400SA2-4CB | 1 | 1 | 1 | Scheduled | 10/06/2022 | 10/06/2022
TO-22-ARK-BOG-1-02 | 110kV FEEDER - ARKLOW 110-BANOGE 110-1 | 1 | 0 | 0 | Scheduled | 12/06/2022 | 12/06/2022
TO-22-AA GIS-T102-01 | GENERATOR TRANSFORMER - ARDNACRUSHA GIS 110-ARDNACRUSHA GIS G2-T102 | 12 | 10 | 10 | Scheduled | 13/06/2022 | 24/06/2022
TO-22-AUG-CFM-1-01 | 110kV FEEDER - AUGHINISH 110-CASTLEFARM 110-1 | 12 | 10 | 10 | Scheduled | 13/06/2022 | 24/06/2022
TO-22-AUG-MTN-1-01 | 110kV FEEDER - AUGHINISH 110-MONETEEN 110-1 | 5 | 5 | 5 | Scheduled | 13/06/2022 | 17/06/2022
TO-22-CFM-T101-01 | TSO CUSTOMER TRANSFORMER - CASTLEFARM 110-CASTLEFARM 10-T101 | 12 | 10 | 10 | Reference | 13/06/2022 | 24/06/2022
TO-22-CLA-MAC-1-01 | 110kV FEEDER - CLASHAVOON 110-MACROOM 110-1 | 40 | 30 | 30 | Scheduled | 13/06/2022 | 22/07/2022
TO-22-CDY-T121-01 | DISTRIBUTION TRANSFORMER - CORDERRY 110-CORDERRY 20-T121 | 41 | 30 | 30 | Reference | 13/06/2022 | 23/07/2022
TO-22-CUN-T121-01 | GENERATOR TRANSFORMER - CUNGHILL 110-CUNGHILL 20-T121 | 4 | 4 | 4 | Scheduled | 13/06/2022 | 16/06/2022
TO-22-DOO-CAP1-02 | CAPACITOR/SVC/REACTOR - DOON 110-DOON 110-CAP1 | 5 | 5 | 5 | Scheduled | 13/06/2022 | 17/06/2022
TO-22-ENN-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - ENNIS 110-ENNIS 110-110SA1-2CB | 2 | 2 | 2 | Scheduled | 13/06/2022 | 14/06/2022
TO-22-ENN-SLC-1-01 | 110kV FEEDER - ENNIS 110-SLIEVECALLAN 110-1 | 12 | 10 | 10 | Scheduled | 13/06/2022 | 24/06/2022
TO-22-110 kV A2 @ FIN GIS-01 | BUSBAR SECTION - FINGLAS GIS 110-FINGLAS GIS 110-110A2 | 5 | 5 | 5 | Scheduled | 13/06/2022 | 17/06/2022
TO-22-110 kV B2 @ FIN GIS-01 | BUSBAR SECTION - FINGLAS GIS 110-FINGLAS GIS 110-110B2 | 5 | 5 | 5 | Scheduled | 13/06/2022 | 17/06/2022
TO-22-FIN GIS-110K2-01 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110K2 | 5 | 5 | 5 | Scheduled | 13/06/2022 | 17/06/2022
TO-22-FIN GIS-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110SA1-2CB | 5 | 5 | 5 | Scheduled | 13/06/2022 | 17/06/2022
TO-22-FIN GIS-110SA2-4CB-01 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110SA2-4CB | 5 | 5 | 5 | Scheduled | 13/06/2022 | 17/06/2022
TO-22-FIN GIS-110SB1-2CB-01 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110SB1-2CB | 5 | 5 | 5 | Scheduled | 13/06/2022 | 17/06/2022
TO-22-FIN GIS-110SB2-4CB-01 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110SB2-4CB | 5 | 5 | 5 | Scheduled | 13/06/2022 | 17/06/2022
TO-22-GLE-T141-01 | DISTRIBUTION TRANSFORMER - GLENLARA 110-GLENLARA 38-T141 | 5 | 5 | 5 | Reference | 13/06/2022 | 17/06/2022
TO-22-MTN-110SA1-01 | SECTIONALISING DISCONNECT - MONETEEN 110-MONETEEN 110-110SA1 | 5 | 5 | 5 | Scheduled | 13/06/2022 | 17/06/2022
TO-22-MTN-110SA2-01 | SECTIONALISING DISCONNECT - MONETEEN 110-MONETEEN 110-110SA2 | 5 | 5 | 5 | Scheduled | 13/06/2022 | 17/06/2022
TO-22-MTN-MUN-1-01 | 110kV FEEDER - MONETEEN 110-MUNGRET 110-1 | 5 | 5 | 5 | Scheduled | 13/06/2022 | 17/06/2022
TO-22-MLC-110SA1-01 | SECTIONALISING DISCONNECT - MOUNTLUCAS 110-MOUNTLUCAS 110-110SA1 | 5 | 5 | 5 | Scheduled | 13/06/2022 | 17/06/2022
TO-22-MLC-110SA2-01 | SECTIONALISING DISCONNECT - MOUNTLUCAS 110-MOUNTLUCAS 110-110SA2 | 5 | 5 |  | Scheduled | 13/06/2022 | 17/06/2022
TO-22-MLC-T121-01 | GENERATOR TRANSFORMER - MOUNTLUCAS 110-MOUNTLUCAS 20-T121 | 5 | 5 | 5 | Scheduled | 13/06/2022 | 17/06/2022
TO-22-MLC-TSB-1-01 | 110kV FEEDER - MOUNTLUCAS 110-THORNSBERRY 110-1 | 5 | 5 | 5 | Scheduled | 13/06/2022 | 17/06/2022
TO-22-MUN-T101-01 | TSO CUSTOMER TRANSFORMER - MUNGRET 110-MUNGRET 10-T101 | 5 | 5 | 5 | Reference | 13/06/2022 | 17/06/2022
TO-22-PB-R2001-05 | CAPACITOR/SVC/REACTOR - POOLBEG 220-POOLBEG 220-R2001 | 5 | 5 | 5 | Scheduled | 13/06/2022 | 17/06/2022
TO-22-SLC-110SA1-01 | SECTIONALISING DISCONNECT - SLIEVECALLAN 110-SLIEVECALLAN 110-110SA1 | 12 | 10 | 10 | Scheduled | 13/06/2022 | 24/06/2022
TO-22-SLC-110SA2-01 | SECTIONALISING DISCONNECT - SLIEVECALLAN 110-SLIEVECALLAN 110-110SA2 | 12 | 10 | 10 | Scheduled | 13/06/2022 | 24/06/2022
TO-22-SLC-T121-01 | GENERATOR TRANSFORMER - SLIEVECALLAN 110-SLIEVECALLAN 20-T121 | 12 | 10 | 10 | Scheduled | 13/06/2022 | 24/06/2022
TO-22-SLC-T122-01 | GENERATOR TRANSFORMER - SLIEVECALLAN 110-SLIEVECALLAN 20-T122 | 12 | 10 | 10 | Scheduled | 13/06/2022 | 24/06/2022
TO-22-STR,T-PA-1-03 | 110kV FEEDER - STRATFORD tee-POLLAPHUCA 110-1 | 5 | 5 | 5 | Scheduled | 13/06/2022 | 17/06/2022
TO-22-110 kV A1 @ GOR-02 | BUSBAR SECTION - GORMAN 110-GORMAN 110-110A1 | 4 | 4 | 4 | Scheduled | 14/06/2022 | 17/06/2022
TO-22-110 kV B1 @ GOR-01 | BUSBAR SECTION - GORMAN 110-GORMAN 110-110B1 | 4 | 4 | 4 | Scheduled | 14/06/2022 | 17/06/2022
TO-22-GOR-NAV-1-01 | 110kV FEEDER - GORMAN 110-NAVAN 110-1 | 4 | 4 | 4 | Scheduled | 14/06/2022 | 17/06/2022
TO-22-BYH-BVK-1-01 | 220kV FEEDER - BALLYNAHULLA 220-BALLYVOUSKILL 220-1 | 106 | 75 |  | Scheduled | 15/06/2022 | 28/09/2022
TO-22-KLN-KPG-1-02 | 220kV FEEDER - KILLONAN 220-KILPADDOGE 220-1 | 1 | 1 | 1 | Scheduled | 15/06/2022 | 15/06/2022
TO-22-KLN-T2101-03 | TRANSFORMER - KILLONAN 220-KILLONAN 110-T2101 | 1 | 1 | 1 | Scheduled | 15/06/2022 | 15/06/2022
TO-22-KLN-T2103-01 | TRANSFORMER - KILLONAN 220-KILLONAN 110-T2103 | 23 | 17 | 17 | Scheduled | 16/06/2022 | 08/07/2022
TO-22-AA GIS-ENN-1-01 | 110kV FEEDER - ARDNACRUSHA GIS 110-ENNIS 110-1 | 5 | 5 | 5 | Scheduled | 20/06/2022 | 24/06/2022
TO-22-BGH-110SA2-01 | SECTIONALISING DISCONNECT - BOGGERAGH 110-BOGGERAGH 110-110SA2 | 5 | 5 | 5 | Scheduled | 20/06/2022 | 24/06/2022
TO-22-BGH-CLA-1-01 | 110kV FEEDER - BOGGERAGH 110-CLASHAVOON 110-1 | 9 | 7 | 7 | Scheduled | 20/06/2022 | 28/06/2022
TO-22-BGH-T132-01 | GENERATOR TRANSFORMER - BOGGERAGH 110-BOGGERAGH 33-T132 | 5 | 5 | 5 | Scheduled | 20/06/2022 | 24/06/2022
TO-22-CSH-SAL-1-01 | 110kV FEEDER - CASHLA 110-SALTHILL 110-1 | 9 | 7 | 7 | Scheduled | 20/06/2022 | 28/06/2022
TO-22-CTN-110SA1-01 | SECTIONALISING DISCONNECT - CAUTEEN 110-CAUTEEN 110-110SA1 | 2 | 2 | 2 | Tentative | 20/06/2022 | 21/06/2022
TO-22-CTN-110SA2-02 | SECTIONALISING DISCONNECT - CAUTEEN 110-CAUTEEN 110-110SA2 | 2 | 2 | 2 | Tentative | 20/06/2022 | 21/06/2022
TO-22-CTN-KLN-1-01 | 110kV FEEDER - CAUTEEN 110-KILLONAN 110-1 | 10 | 8 | 8 | Scheduled | 20/06/2022 | 29/06/2022
TO-22-CTN-T141-01 | DISTRIBUTION TRANSFORMER - CAUTEEN 110-CAUTEEN 38-T141 | 2 | 2 | 2 | Reference (Tentative) | 20/06/2022 | 21/06/2022
TO-22-110 kV A2 @ FIN-02 | BUSBAR SECTION - FINGLAS 110-FINGLAS 110-110A2 | 5 | 5 | 5 | Scheduled | 20/06/2022 | 24/06/2022
TO-22-110 kV B2 @ FIN-01 | BUSBAR SECTION - FINGLAS 110-FINGLAS 110-110B2 | 5 | 5 | 5 | Scheduled | 20/06/2022 | 24/06/2022
TO-22-220 kV A1 @ FIN-08 | BUSBAR SECTION - FINGLAS 220-FINGLAS 220-220A1 | 5 | 5 | 5 | Scheduled | 20/06/2022 | 24/06/2022
TO-22-220 kV B1 @ FIN-09 | BUSBAR SECTION - FINGLAS 220-FINGLAS 220-220B1 | 5 | 5 | 5 | Scheduled | 20/06/2022 | 24/06/2022
TO-22-220 kV A4 @ KPG-01 | BUSBAR SECTION - KILPADDOGE 220-KILPADDOGE 220-220A4 | 5 | 5 | 5 | Scheduled | 20/06/2022 | 24/06/2022
TO-22-220 kV B4 @ KPG-01 | BUSBAR SECTION - KILPADDOGE 220-KILPADDOGE 220-220B4 | 5 | 5 | 5 | Scheduled | 20/06/2022 | 24/06/2022
TO-22-KPG-MP GIS-2-03 | 220kV FEEDER - KILPADDOGE 220-MONEYPOINT GIS 220-2 | 5 | 5 | 5 | Scheduled | 20/06/2022 | 24/06/2022
TO-22-220 kV A2 @ MP GIS-01 | BUSBAR SECTION - MONEYPOINT GIS 220-MONEYPOINT GIS 220-220A2 | 3 | 3 | 3 | Scheduled | 20/06/2022 | 22/06/2022
TO-22-220 kV B2 @ MP GIS-01 | BUSBAR SECTION - MONEYPOINT GIS 220-MONEYPOINT GIS 220-220B2 | 3 | 3 | 3 | Scheduled | 20/06/2022 | 22/06/2022
TO-22-NEW-PLS-1-05 | 110kV FEEDER - NEWBRIDGE 110-PORTLAOISE 110-1 | 16 | 12 | 12 | Scheduled | 20/06/2022 | 05/07/2022
TO-22-110 kV A1 @ CSH-07 | BUSBAR SECTION - CASHLA 110-CASHLA 110-110A1 | 4 | 4 | 4 | Scheduled | 21/06/2022 | 24/06/2022
TO-22-110 kV B1 @ CSH-07 | BUSBAR SECTION - CASHLA 110-CASHLA 110-110B1 | 4 | 4 | 4 | Scheduled | 21/06/2022 | 24/06/2022
TO-22-CDU-MUL-1-02 | 110kV FEEDER - CORDUFF 110-MULLINGAR 110-1 | 1 | 1 | 1 | Scheduled | 21/06/2022 | 21/06/2022
TO-22-MP GIS-220K2-01 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 220-MONEYPOINT GIS 220-220K2 | 2 | 2 | 2 | Scheduled | 21/06/2022 | 22/06/2022
TO-22-MUL-110SA1-2CB-02 | COUPLER/SECTIONALISING CB - MULLINGAR 110-MULLINGAR 110-110SA1-2CB | 1 | 1 | 1 | Scheduled | 21/06/2022 | 21/06/2022
TO-22-MUL-CAP2-02 | CAPACITOR/SVC/REACTOR - MULLINGAR 110-MULLINGAR 110-CAP2 | 1 | 1 | 1 | Scheduled | 21/06/2022 | 21/06/2022
TO-22-MUL-T102-01 | DISTRIBUTION TRANSFORMER - MULLINGAR 110-MULLINGAR 10-T102 | 1 | 1 | 1 | Reference | 21/06/2022 | 21/06/2022
TO-22-MUL-T142-01 | DISTRIBUTION TRANSFORMER - MULLINGAR 110-MULLINGAR 38-T142 | 1 | 1 | 1 | Reference | 21/06/2022 | 21/06/2022
TO-22-BGH-T121-01 | GENERATOR TRANSFORMER - BOGGERAGH 110-BOGGERAGH 20-T121 | 3 | 3 | 3 | Scheduled | 22/06/2022 | 24/06/2022
TO-22-FIN-220K1-08 | COUPLER/SECTIONALISING CB - FINGLAS 220-FINGLAS 220-220K1 | 1 | 1 | 1 | Scheduled | 23/06/2022 | 23/06/2022
TO-22-FIN-FIN GIS-2-03 | 110kV FEEDER - FINGLAS 110-FINGLAS GIS 110-2 | 2 | 2 | 2 | Scheduled | 23/06/2022 | 24/06/2022
TO-22-FIN-MCD-1-03 | 110kV FEEDER - FINGLAS 110-McDERMOTT 110-1 | 2 | 2 | 2 | Reference | 23/06/2022 | 24/06/2022
TO-22-MP GIS-400SB1-2CB-01 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 400-MONEYPOINT GIS 400-400SB1-2CB | 2 | 2 | 2 | Scheduled | 23/06/2022 | 24/06/2022
TO-22-FIN-220K2-03 | COUPLER/SECTIONALISING CB - FINGLAS 220-FINGLAS 220-220K2 | 1 | 1 | 1 | Scheduled | 24/06/2022 | 24/06/2022
TO-22-AA GIS-DRU-1-01 | 110kV FEEDER - ARDNACRUSHA GIS 110-DRUMLINE 110-1 | 5 | 5 | 5 | Scheduled | 27/06/2022 | 01/07/2022
TO-22-AUG-KPG-1-01 | 110kV FEEDER - AUGHINISH 110-KILPADDOGE 110-1 | 5 | 5 | 5 | Scheduled | 27/06/2022 | 01/07/2022
TO-22-BDN-MRK1-02 | TSO CUSTOMER TRANSFORMER - BALLYDINE 110-BALLYDINE 10-MRK1 | 8 | 6 | 6 | Scheduled | 27/06/2022 | 04/07/2022
TO-22-CF-T103-01 | GENERATOR TRANSFORMER - CATHALEENS FALL 110-CATHALEENS FALL G3-T103 | 5 | 5 | 5 | Tentative | 27/06/2022 | 01/07/2022
TO-22-DRU-110SA1-01 | SECTIONALISING DISCONNECT - DRUMLINE 110-DRUMLINE 110-110SA1 | 5 | 5 | 5 | Scheduled | 27/06/2022 | 01/07/2022
TO-22-DRU-110SA2-02 | SECTIONALISING DISCONNECT - DRUMLINE 110-DRUMLINE 110-110SA2 | 5 | 5 | 5 | Scheduled | 27/06/2022 | 01/07/2022
TO-22-DRU-CAP2-01 | CAPACITOR/SVC/REACTOR - DRUMLINE 110-DRUMLINE 110-CAP2 | 5 | 5 | 5 | Scheduled | 27/06/2022 | 01/07/2022
TO-22-DRU-T142-01 | DISTRIBUTION TRANSFORMER - DRUMLINE 110-DRUMLINE 38-T142 | 5 | 5 | 5 | Reference | 27/06/2022 | 01/07/2022
TO-22-110 kV A1 @ GI-02 | BUSBAR SECTION - GREAT ISLAND 110-GREAT ISLAND 110-110A1 | 4 | 4 | 4 | Scheduled | 27/06/2022 | 30/06/2022
TO-22-110 kV B1 @ GI-01 | BUSBAR SECTION - GREAT ISLAND 110-GREAT ISLAND 110-110B1 | 4 | 4 | 4 | Scheduled | 27/06/2022 | 30/06/2022
TO-22-GI-WEX-1-01 | 110kV FEEDER - GREAT ISLAND 110-WEXFORD 110-1 | 84 | 59 | 59 | Scheduled | 27/06/2022 | 18/09/2022
TO-22-CF-110K1-2-01 | COUPLER/SECTIONALISING CB - CATHALEENS FALL 110-CATHALEENS FALL 110-110K1-2 | 1 | 1 | 1 | Scheduled | 28/06/2022 | 28/06/2022
TO-22-MP GIS-T121-02 | GENERATOR TRANSFORMER - MONEYPOINT GIS 110-MONEYPOINT GIS 20-T121 | 2 | 2 | 2 | Scheduled | 28/06/2022 | 29/06/2022
TO-22-110 kV A1/A3 @ BLC-01 | BUSBAR SECTION - BELCAMP 110-BELCAMP 110-110A1-A3 | 1 | 1 | 1 | Scheduled | 29/06/2022 | 29/06/2022
TO-22-110 kV B1/B3 @ BLC-01 | BUSBAR SECTION - BELCAMP 110-BELCAMP 110-110B1-B3 | 1 | 1 | 1 | Scheduled | 29/06/2022 | 29/06/2022
TO-22-COL-FIN GIS-1-04 | 110kV FEEDER - COLLEGE PARK 110-FINGLAS GIS 110-1 | 1 | 1 | 1 | Scheduled | 29/06/2022 | 29/06/2022
TO-22-BDN-CUL-1-02 | 110kV FEEDER - BALLYDINE 110-CULLENAGH 110-1 | 2 | 2 | 2 | Scheduled | 30/06/2022 | 01/07/2022
TO-22-GI GIS-T2004-01 | GENERATOR TRANSFORMER - GREAT ISLAND GIS 220-GREAT ISLAND GIS G4-T2004 | 7 | 5 | 5 | Scheduled | 01/07/2022 | 07/07/2022
TO-22-KYT-WOO-1-03 | 220kV FEEDER - KELLYSTOWN 220-WOODLAND 220-1 | 34 | 23 | 23 | Scheduled | 01/07/2022 | 03/08/2022
TO-22-AA GIS-SNG-1-01 | 110kV FEEDER - ARDNACRUSHA GIS 110-SINGLAND 110-1 | 5 | 5 | 5 | Scheduled | 04/07/2022 | 08/07/2022
TO-22-ATH-110SA1-2CB-02 | COUPLER/SECTIONALISING CB - ATHLONE 110-ATHLONE 110-110SA1-2CB | 5 | 5 | 5 | Scheduled | 04/07/2022 | 08/07/2022
TO-22-ATH-CAP3-01 | CAPACITOR/SVC/REACTOR - ATHLONE 110-ATHLONE 110-CAP3 | 5 | 5 | 5 | Scheduled | 04/07/2022 | 08/07/2022
TO-22-ATH-LA-1-01 | 110kV FEEDER - ATHLONE 110-LANESBORO 110-1 | 12 | 10 | 10 | Scheduled | 04/07/2022 | 15/07/2022
TO-22-ATH-M/CAP1-01 | CAPACITOR/SVC/REACTOR - ATHLONE 110-ATHLONE 110-M/CAP1 | 5 | 5 | 5 | Scheduled | 04/07/2022 | 08/07/2022
TO-22-ATH-T141-01 | DISTRIBUTION TRANSFORMER - ATHLONE 110-ATHLONE 38-T141 | 5 | 5 | 5 | Reference | 04/07/2022 | 08/07/2022
TO-22-BDN-DOO-1-04 | 110kV FEEDER - BALLYDINE 110-DOON 110-1 | 5 | 5 |  | Scheduled | 04/07/2022 | 08/07/2022
TO-22-BAN-BRI-1-01 | 110kV FEEDER - BANDON 110-BRINNY 110-1 | 8 | 6 | 6 | Scheduled | 04/07/2022 | 11/07/2022
TO-22-BRI-T101-01 | TSO CUSTOMER TRANSFORMER - BRINNY 110-BRINNY 10-T101 | 8 | 6 | 6 | Scheduled | 04/07/2022 | 11/07/2022
TO-22-GAL-SAL-1-01 | 110kV FEEDER - GALWAY 110-SALTHILL 110-1 | 110 | 79 | 79 | Scheduled | 04/07/2022 | 21/10/2022
TO-22-GAL-T101-01 | DISTRIBUTION TRANSFORMER - GALWAY 110-GALWAY 10-T101 | 2 | 2 | 2 | Reference | 04/07/2022 | 05/07/2022
TO-22-220 kV A2 @ GI GIS-01 | BUSBAR SECTION - GREAT ISLAND GIS 220-GREAT ISLAND GIS 220-220A2 | 4 | 4 | 4 | Scheduled | 04/07/2022 | 07/07/2022
TO-22-220 kV B2 @ GI GIS-01 | BUSBAR SECTION - GREAT ISLAND GIS 220-GREAT ISLAND GIS 220-220B2 | 4 | 4 | 4 | Scheduled | 04/07/2022 | 07/07/2022
TO-22-KBY-KRA-2-02 | 110kV FEEDER - KILBARRY 110-KNOCKRAHA 110-2 | 12 | 10 | 10 | Scheduled | 04/07/2022 | 15/07/2022
TO-22-KBY-MAL-1-01 | 110kV FEEDER - KILBARRY 110-MALLOW 110-1 | 12 | 10 | 10 | Scheduled | 04/07/2022 | 15/07/2022
TO-22-LET-SVC-01 | CAPACITOR/SVC/REACTOR - LETTERKENNY 110-LETTERKENNY 110-SVC | 5 | 5 | 5 | Scheduled | 04/07/2022 | 08/07/2022
TO-22-LOU-MTH-1-04 | 110kV FEEDER - LOUTH 110-MEATH HILL 110-1 | 5 | 5 | 5 | Scheduled | 04/07/2022 | 08/07/2022
TO-22-MTH-110SA1-01 | SECTIONALISING DISCONNECT - MEATH HILL 110-MEATH HILL 110-110SA1 | 5 | 5 | 5 | Scheduled | 04/07/2022 | 08/07/2022
TO-22-MTH-110SA2-02 | SECTIONALISING DISCONNECT - MEATH HILL 110-MEATH HILL 110-110SA2 | 5 | 5 | 5 | Scheduled | 04/07/2022 | 08/07/2022
TO-22-MTH-T141-02 | DISTRIBUTION TRANSFORMER - MEATH HILL 110-MEATH HILL 38-T141 | 5 | 5 | 5 | Reference | 04/07/2022 | 08/07/2022
TO-22-RAF-T2102-01 | TRANSFORMER - RAFFEEN 220-RAFFEEN 110-T2102 | 8 | 6 | 6 | Scheduled | 04/07/2022 | 11/07/2022
TO-22-BDN-MRK3-01 | TSO CUSTOMER TRANSFORMER - BALLYDINE 110-BALLYDINE 10-MRK3 | 65 | 46 |  | Scheduled | 05/07/2022 | 07/09/2022
TO-22-BLC-110K1-01 | COUPLER/SECTIONALISING CB - BELCAMP 110-BELCAMP 110-110K1 | 1 | 1 | 1 | Scheduled | 05/07/2022 | 05/07/2022
TO-22-110 kV A1 @ MAY-01 | BUSBAR SECTION - MAYNOOTH 110-MAYNOOTH 110-110A1 | 3 | 3 | 3 | Scheduled | 06/07/2022 | 08/07/2022
TO-22-110 kV B1 @ MAY-01 | BUSBAR SECTION - MAYNOOTH 110-MAYNOOTH 110-110B1 | 3 | 3 | 3 | Scheduled | 06/07/2022 | 08/07/2022
TO-22-BAN-RAF-1-01 | 110kV FEEDER - BANDON 110-RAFFEEN 110-1 | 8 | 6 | 6 | Scheduled | 08/07/2022 | 15/07/2022
TO-22-ARV-SKL-1-05 | 110kV FEEDER - ARVA 110-SHANKILL 110-1 | 5 | 5 | 5 | Scheduled | 11/07/2022 | 15/07/2022
TO-22-110 kV A1 @ CLG-02 | BUSBAR SECTION - CLOGHRAN 110-CLOGHRAN 110-110A1 | 4 | 4 | 4 | Scheduled | 11/07/2022 | 14/07/2022
TO-22-110 kV B1 @ CLG-03 | BUSBAR SECTION - CLOGHRAN 110-CLOGHRAN 110-110B1 | 4 | 4 | 4 | Scheduled | 11/07/2022 | 14/07/2022
TO-22-CLG-FIN GIS-1-03 | 110kV FEEDER - CLOGHRAN 110-FINGLAS GIS 110-1 | 5 | 5 | 5 | Scheduled | 11/07/2022 | 15/07/2022
TO-22-110 kV A5 @ FIN GIS-01 | BUSBAR SECTION - FINGLAS GIS 110-FINGLAS GIS 110-110A5 | 4 | 4 | 4 | Scheduled | 11/07/2022 | 14/07/2022
TO-22-110 kV B5 @ FIN GIS-01 | BUSBAR SECTION - FINGLAS GIS 110-FINGLAS GIS 110-110B5 | 4 | 4 | 4 | Scheduled | 11/07/2022 | 14/07/2022
TO-22-KTL-T131-01 | GENERATOR TRANSFORMER - KILTEEL 110-KILTEEL 33-T131 | 5 | 5 | 5 | Scheduled | 11/07/2022 | 15/07/2022
TO-22-SKL-110SA1-05 | SECTIONALISING DISCONNECT - SHANKILL 110-SHANKILL 110-110SA1 | 5 | 5 | 5 | Scheduled | 11/07/2022 | 15/07/2022
TO-22-SKL-110SA2-03 | SECTIONALISING DISCONNECT - SHANKILL 110-SHANKILL 110-110SA2 | 5 | 5 | 5 | Scheduled | 11/07/2022 | 15/07/2022
TO-22-SKL-M/CAP2-03 | CAPACITOR/SVC/REACTOR - SHANKILL 110-SHANKILL 110-M/CAP2 | 5 | 5 | 5 | Scheduled | 11/07/2022 | 15/07/2022
TO-22-SKL-T142-02 | DISTRIBUTION TRANSFORMER - SHANKILL 110-SHANKILL 38-T142 | 5 | 5 | 5 | Reference | 11/07/2022 | 15/07/2022
TO-22-ANR-DOO-1-02 | 110kV FEEDER - ANNER 110-DOON 110-1 | 2 | 2 | 2 | Scheduled | 12/07/2022 | 13/07/2022
TO-22-ANR-T101-02 | TSO CUSTOMER TRANSFORMER - ANNER 110-ANNER 10-T101 | 2 | 2 | 2 | Reference | 12/07/2022 | 13/07/2022
TO-22-ANR-T103-02 | TSO CUSTOMER TRANSFORMER - ANNER 110-ANNER 10-T103 | 2 | 2 | 2 | Reference | 12/07/2022 | 13/07/2022
TO-22-SLI-SRA-1-03 | 110kV FEEDER - SLIGO 110-SRANANAGH 110-1 | 1 | 1 | 1 | Scheduled | 13/07/2022 | 13/07/2022
TO-22-CFN-T232-01 | GENERATOR TRANSFORMER - CLONIFFEEN 220-CLONIFFEEN 33-T232 | 2 | 2 | 2 | Scheduled | 14/07/2022 | 15/07/2022
TO-22-KPG-TB-2-02 | 220kV FEEDER - KILPADDOGE 220-TARBERT 220-2 | 7 | 5 | 5 | Scheduled | 15/07/2022 | 21/07/2022
TO-22-BAN-DMY-1-01 | 110kV FEEDER - BANDON 110-DUNMANWAY 110-1 | 10 | 8 | 8 | Scheduled | 18/07/2022 | 27/07/2022
TO-22-220 kV A1 @ CSH-03 | BUSBAR SECTION - CASHLA 220-CASHLA 220-220A1 | 5 | 5 | 5 | Scheduled | 18/07/2022 | 22/07/2022
TO-22-220 kV A2 @ CSH-02 | BUSBAR SECTION - CASHLA 220-CASHLA 220-220A2 | 5 | 5 | 5 | Scheduled | 18/07/2022 | 22/07/2022
TO-22-220 kV B1 @ CSH-03 | BUSBAR SECTION - CASHLA 220-CASHLA 220-220B1 | 5 | 5 | 5 | Scheduled | 18/07/2022 | 22/07/2022
TO-22-220 kV B2 @ CSH-02 | BUSBAR SECTION - CASHLA 220-CASHLA 220-220B2 | 5 | 5 | 5 | Scheduled | 18/07/2022 | 22/07/2022
TO-22-CSH-220K1-2-02 | COUPLER/SECTIONALISING CB - CASHLA 220-CASHLA 220-220K1-2 | 5 | 5 | 5 | Scheduled | 18/07/2022 | 22/07/2022
TO-22-CLA-CKN-1-02 | 110kV FEEDER - CLASHAVOON 110-CLONKEEN 110-1 | 5 | 5 | 5 | Scheduled | 18/07/2022 | 22/07/2022
TO-22-CKN-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - CLONKEEN 110-CLONKEEN 110-110SA1-2CB | 5 | 5 | 5 | Scheduled | 18/07/2022 | 22/07/2022
TO-22-CKN-CGL-1-01 | 110kV FEEDER - CLONKEEN 110-COOMAGEARLAHY 110-1 | 5 | 5 | 5 | Scheduled | 18/07/2022 | 22/07/2022
TO-22-CKN-GRO-1-01 | 110kV FEEDER - CLONKEEN 110-GARROW 110-1 | 5 | 5 | 5 | Scheduled | 18/07/2022 | 22/07/2022
TO-22-CKN-KER-1-01 | 110kV FEEDER - CLONKEEN 110-KNOCKEARAGH 110-1 | 5 | 5 | 5 | Scheduled | 18/07/2022 | 22/07/2022
TO-22-CGL-110SA1-01 | SECTIONALISING DISCONNECT - COOMAGEARLAHY 110-COOMAGEARLAHY 110-110SA1 | 5 | 5 | 5 | Scheduled | 18/07/2022 | 22/07/2022
TO-22-CGL-110SA2-01 | SECTIONALISING DISCONNECT - COOMAGEARLAHY 110-COOMAGEARLAHY 110-110SA2 | 5 | 5 | 5 | Scheduled | 18/07/2022 | 22/07/2022
TO-22-CGL-GAE-1-01 | 110kV FEEDER - COOMAGEARLAHY 110-GLANLEE 110-1 | 5 | 5 | 5 | Scheduled | 18/07/2022 | 22/07/2022
TO-22-CGL-T121-01 | GENERATOR TRANSFORMER - COOMAGEARLAHY 110-COOMAGEARLAHY 20-T121 | 5 | 5 | 5 | Scheduled | 18/07/2022 | 22/07/2022
TO-22-CGL-T122-01 | GENERATOR TRANSFORMER - COOMAGEARLAHY 110-COOMAGEARLAHY 20-T122 | 5 | 5 | 5 | Scheduled | 18/07/2022 | 22/07/2022
TO-22-DRM-MEE-1-02 | 110kV FEEDER - DRUMKEEN 110-MEENTYCAT 110-1 | 3 | 3 | 3 | Scheduled | 18/07/2022 | 20/07/2022
TO-22-GAE-T121-01 | GENERATOR TRANSFORMER - GLANLEE 110-GLANLEE 20-T121 | 5 | 5 | 5 | Scheduled | 18/07/2022 | 22/07/2022
TO-22-220 kV A1 @ GI GIS-03 | BUSBAR SECTION - GREAT ISLAND GIS 220-GREAT ISLAND GIS 220-220A1 | 5 | 5 | 5 | Scheduled | 18/07/2022 | 22/07/2022
TO-22-220 kV B1 @ GI GIS-02 | BUSBAR SECTION - GREAT ISLAND GIS 220-GREAT ISLAND GIS 220-220B1 | 5 | 5 | 5 | Scheduled | 18/07/2022 | 22/07/2022
TO-22-GI-T2101-01 | TRANSFORMER - GREAT ISLAND GIS 220-GREAT ISLAND 110-T2101 | 16 | 11 | 11 | Scheduled | 18/07/2022 | 02/08/2022
TO-22-MEE-T121-01 | GENERATOR TRANSFORMER - MEENTYCAT 110-MEENTYCAT 20-T121 | 3 | 3 | 3 | Scheduled | 18/07/2022 | 20/07/2022
TO-22-THU-CAP1-01 | CAPACITOR/SVC/REACTOR - THURLES 110-THURLES 110-CAP1 | 5 | 5 | 5 | Scheduled | 18/07/2022 | 22/07/2022
TO-22-MAY-WOO-1-15 | 220kV FEEDER - MAYNOOTH 220-WOODLAND 220-1 | 165 | 114 | 114 | Scheduled | 20/07/2022 | 31/12/2022
TO-22-BIN-CF-1-04 | 110kV FEEDER - BINBANE 110-CATHALEENS FALL 110-1 | 5 | 5 | 5 | Scheduled | 25/07/2022 | 29/07/2022
TO-22-220 kV B1 @ CKM GIS-03 | BUSBAR SECTION - CARRICKMINES GIS 220-CARRICKMINES GIS 220-220B1 | 3 | 3 | 3 | Scheduled | 25/07/2022 | 27/07/2022
TO-22-220 kV B2 @ CKM GIS-02 | BUSBAR SECTION - CARRICKMINES GIS 220-CARRICKMINES GIS 220-220B2 | 3 | 3 | 3 | Scheduled | 25/07/2022 | 27/07/2022
TO-22-220 kV A1/A2 @ FIN-02 | BUSBAR SECTION - FINGLAS 220-FINGLAS 220-220A1-A2 | 19 | 14 | 14 | Scheduled | 25/07/2022 | 12/08/2022
TO-22-FIN-220K1-12 | COUPLER/SECTIONALISING CB - FINGLAS 220-FINGLAS 220-220K1 | 19 | 14 | 14 | Scheduled | 25/07/2022 | 12/08/2022
TO-22-FIN-220K2-02 | COUPLER/SECTIONALISING CB - FINGLAS 220-FINGLAS 220-220K2 | 19 | 14 | 14 | Scheduled | 25/07/2022 | 12/08/2022
TO-22-110 kV A1 @ GI-03 | BUSBAR SECTION - GREAT ISLAND 110-GREAT ISLAND 110-110A1 | 5 | 5 | 5 | Scheduled | 25/07/2022 | 29/07/2022
TO-22-110 kV B1 @ GI-02 | BUSBAR SECTION - GREAT ISLAND 110-GREAT ISLAND 110-110B1 | 5 | 5 | 5 | Scheduled | 25/07/2022 | 29/07/2022
TO-22-110 kV B1 @ KPG-01 | BUSBAR SECTION - KILPADDOGE 110-KILPADDOGE 110-110B1 | 4 | 4 | 4 | Scheduled | 25/07/2022 | 28/07/2022
TO-22-110 kV B2 @ KPG-02 | BUSBAR SECTION - KILPADDOGE 110-KILPADDOGE 110-110B2 | 4 | 4 | 4 | Scheduled | 25/07/2022 | 28/07/2022
TO-22-KPG-110SB1-2CB-01 | COUPLER/SECTIONALISING CB - KILPADDOGE 110-KILPADDOGE 110-110SB1-2CB | 4 | 4 | 4 | Scheduled | 25/07/2022 | 28/07/2022
TO-22-LOU-T2101-01 | TRANSFORMER - LOUTH 220-LOUTH 110-T2101 | 5 | 5 | 5 | Scheduled | 25/07/2022 | 29/07/2022
TO-22-MP GIS-OST-1-02 | 400kV FEEDER - MONEYPOINT GIS 400-OLDSTREET 400-1 | 5 | 5 | 5 | Scheduled | 25/07/2022 | 29/07/2022
TO-22-BVK-110K2-01 | COUPLER/SECTIONALISING CB - BALLYVOUSKILL 110-BALLYVOUSKILL 110-110K2 | 4 | 4 | 4 | Scheduled | 26/07/2022 | 29/07/2022
TO-22-110 kV A2 @ CDU-02 | BUSBAR SECTION - CORDUFF 110-CORDUFF 110-110A2 | 4 | 4 | 4 | Scheduled | 26/07/2022 | 29/07/2022
TO-22-110 kV B2 @ CDU-02 | BUSBAR SECTION - CORDUFF 110-CORDUFF 110-110B2 | 4 | 4 | 4 | Scheduled | 26/07/2022 | 29/07/2022
TO-22-DND-T122-01 | TSO CUSTOMER TRANSFORMER - DARNDALE 110-DARNDALE 20-T122 | 3 | 3 | 3 | Scheduled | 26/07/2022 | 28/07/2022
TO-22-110 kV A1/A2 @ CLO-01 | BUSBAR SECTION - CLOGHER 110-CLOGHER 110-110A1-A2 | 1 | 1 | 1 | Scheduled | 27/07/2022 | 27/07/2022
TO-22-110 kV B1/B2 @ CLO-01 | BUSBAR SECTION - CLOGHER 110-CLOGHER 110-110B1-B2 | 1 | 1 | 1 | Scheduled | 27/07/2022 | 27/07/2022
TO-22-COL-FIN GIS-1-02 | 110kV FEEDER - COLLEGE PARK 110-FINGLAS GIS 110-1 | 1 | 1 | 1 | Scheduled | 27/07/2022 | 27/07/2022
TO-22-CD-MAC-1-02 | 110kV FEEDER - CARRIGADROHID 110-MACROOM 110-1 | 15 | 10 | 10 | Scheduled | 28/07/2022 | 11/08/2022
TO-22-BK-CBR-1-03 | 110kV FEEDER - BELLACORICK 110-CASTLEBAR 110-1 | 1 | 1 | 1 | Scheduled | 29/07/2022 | 29/07/2022
TO-22-CBR-110SA1-2CB-03 | COUPLER/SECTIONALISING CB - CASTLEBAR 110-CASTLEBAR 110-110SA1-2CB | 1 | 1 | 1 | Scheduled | 29/07/2022 | 29/07/2022
TO-22-CBR-SVC-02 | CAPACITOR/SVC/REACTOR - CASTLEBAR 110-CASTLEBAR 110-SVC | 1 | 1 | 1 | Scheduled | 29/07/2022 | 29/07/2022
TO-22-110 kV A1 @ BYH-02 | BUSBAR SECTION - BALLYNAHULLA 110-BALLYNAHULLA 110-110A1 | 4 | 4 | 4 | Scheduled | 02/08/2022 | 05/08/2022
TO-22-110 kV A2 @ BYH-02 | BUSBAR SECTION - BALLYNAHULLA 110-BALLYNAHULLA 110-110A2 | 4 | 4 | 4 | Scheduled | 02/08/2022 | 05/08/2022
TO-22-110 kV A2 @ BYH-03 | BUSBAR SECTION - BALLYNAHULLA 110-BALLYNAHULLA 110-110A2 | 4 | 4 | 4 | Scheduled | 02/08/2022 | 05/08/2022
TO-22-110 kV B1 @ BYH-02 | BUSBAR SECTION - BALLYNAHULLA 110-BALLYNAHULLA 110-110B1 | 4 | 4 | 4 | Scheduled | 02/08/2022 | 05/08/2022
TO-22-110 kV B2 @ BYH-02 | BUSBAR SECTION - BALLYNAHULLA 110-BALLYNAHULLA 110-110B2 | 4 | 4 | 4 | Scheduled | 02/08/2022 | 05/08/2022
TO-22-110 kV B2 @ BYH-03 | BUSBAR SECTION - BALLYNAHULLA 110-BALLYNAHULLA 110-110B2 | 4 | 4 | 4 | Scheduled | 02/08/2022 | 05/08/2022
TO-22-BYH-110K2-02 | COUPLER/SECTIONALISING CB - BALLYNAHULLA 110-BALLYNAHULLA 110-110K2 | 4 | 4 | 4 | Scheduled | 02/08/2022 | 05/08/2022
TO-22-BYH-110SA1-2CB-02 | COUPLER/SECTIONALISING CB - BALLYNAHULLA 110-BALLYNAHULLA 110-110SA1-2CB | 4 | 4 | 4 | Scheduled | 02/08/2022 | 05/08/2022
TO-22-BYH-110SB1-2CB-02 | COUPLER/SECTIONALISING CB - BALLYNAHULLA 110-BALLYNAHULLA 110-110SB1-2CB | 4 | 4 | 4 | Scheduled | 02/08/2022 | 05/08/2022
TO-22-CSH-ENN-1-01 | 110kV FEEDER - CASHLA 110-ENNIS 110-1 | 3 | 3 | 3 | Scheduled | 02/08/2022 | 04/08/2022
TO-22-CDY-SRA-1-01 | 110kV FEEDER - CORDERRY 110-SRANANAGH 110-1 | 4 | 4 | 4 | Scheduled | 02/08/2022 | 05/08/2022
TO-22-CUL-220K1-2-02 | COUPLER/SECTIONALISING CB - CULLENAGH 220-CULLENAGH 220-220K1-2 | 4 | 4 | 4 | Scheduled | 02/08/2022 | 05/08/2022
TO-22-MLN-T124-01 | TSO CUSTOMER TRANSFORMER - MULLAGHARLIN 110-MULLAGHARLIN 20-T124 | 2 | 2 | 2 | Scheduled | 02/08/2022 | 03/08/2022
TO-22-220 kV A2 @ TB-03 | BUSBAR SECTION - TARBERT 220-TARBERT 220-220A2 | 4 | 4 | 4 | Scheduled | 02/08/2022 | 05/08/2022
TO-22-220 kV B2 @ TB-03 | BUSBAR SECTION - TARBERT 220-TARBERT 220-220B2 | 4 | 4 | 4 | Scheduled | 02/08/2022 | 05/08/2022
TO-22-TB-T2003-02 | GENERATOR TRANSFORMER - TARBERT 220-TARBERT G3-T2003 | 25 | 19 | 19 | Scheduled | 02/08/2022 | 26/08/2022
TO-22-110 kV A1/A2 @ ARK-01 | BUSBAR SECTION - ARKLOW 110-ARKLOW 110-110A1-A2 | 1 | 1 | 1 | Scheduled | 03/08/2022 | 03/08/2022
TO-22-110 kV B1/B2 @ ARK-01 | BUSBAR SECTION - ARKLOW 110-ARKLOW 110-110B1-B2 | 1 | 1 | 1 | Scheduled | 03/08/2022 | 03/08/2022
TO-22-CLW-T142-02 | DISTRIBUTION TRANSFORMER - CARLOW 110-CARLOW 38-T142 | 2 | 2 | 2 | Reference | 03/08/2022 | 04/08/2022
TO-22-KNR-TRI-2-01 | 110kV FEEDER - KNOCKANURE 110-TRIEN 110-2 | 70 | 50 | 50 | Scheduled | 04/08/2022 | 12/10/2022
TO-22-MLN-T123-02 | TSO CUSTOMER TRANSFORMER - MULLAGHARLIN 110-MULLAGHARLIN 20-T123 | 2 | 2 | 2 | Scheduled | 04/08/2022 | 05/08/2022
TO-22-TRI-T142-01 | DISTRIBUTION TRANSFORMER - TRIEN 110-TRIEN 38-T142 | 70 | 50 | 50 | Reference | 04/08/2022 | 12/10/2022
TO-22-BIN-TIV-1-02 | 110kV FEEDER - BINBANE 110-TIEVEBRACK 110-1 | 4 | 4 | 4 | Scheduled | 08/08/2022 | 11/08/2022
TO-22-110 kV A2 @ CAH-02 | BUSBAR SECTION - CAHIR 110-CAHIR 110-110A2 | 5 | 5 | 5 | Scheduled | 08/08/2022 | 12/08/2022
TO-22-110 kV B2 @ CAH-02 | BUSBAR SECTION - CAHIR 110-CAHIR 110-110B2 | 5 | 5 | 5 | Scheduled | 08/08/2022 | 12/08/2022
TO-22-CAH-CAP2/4-01 | CAPACITOR/SVC/REACTOR - CAHIR 110-CAHIR 110-CAP2/4 | 5 | 5 | 5 | Scheduled | 08/08/2022 | 12/08/2022
TO-22-CVW-KRA-1-01 | 110kV FEEDER - CASTLEVIEW 110-KNOCKRAHA 110-1 | 8 | 6 | 6 | Scheduled | 08/08/2022 | 15/08/2022
TO-22-GI-T2102-01 | TRANSFORMER - GREAT ISLAND GIS 220-GREAT ISLAND 110-T2102 | 5 | 5 | 5 | Scheduled | 08/08/2022 | 12/08/2022
TO-22-110 kV A2 @ KRA-01 | BUSBAR SECTION - KNOCKRAHA 110-KNOCKRAHA 110-110A2 | 4 | 4 | 4 | Scheduled | 08/08/2022 | 11/08/2022
TO-22-110 kV B2 @ KRA-01 | BUSBAR SECTION - KNOCKRAHA 110-KNOCKRAHA 110-110B2 | 4 | 4 | 4 | Scheduled | 08/08/2022 | 11/08/2022
TO-22-220 kV A2 @ KRA-04 | BUSBAR SECTION - KNOCKRAHA 220-KNOCKRAHA 220-220A2 | 5 | 5 | 5 | Scheduled | 08/08/2022 | 12/08/2022
TO-22-220 kV B2 @ KRA-04 | BUSBAR SECTION - KNOCKRAHA 220-KNOCKRAHA 220-220B2 | 5 | 5 | 5 | Scheduled | 08/08/2022 | 12/08/2022
TO-22-KRA-T2102-01 | TRANSFORMER - KNOCKRAHA 220-KNOCKRAHA 110-T2102 | 19 | 15 | 15 | Scheduled | 08/08/2022 | 26/08/2022
TO-22-LIM-MTN-1-01 | 110kV FEEDER - LIMERICK 110-MONETEEN 110-1 | 3 | 3 | 3 | Scheduled | 08/08/2022 | 10/08/2022
TO-22-MLC-TSB-1-02 | 110kV FEEDER - MOUNTLUCAS 110-THORNSBERRY 110-1 | 5 | 5 | 5 | Scheduled | 08/08/2022 | 12/08/2022
TO-22-ATY-PLS-1-03 | 110kV FEEDER - ATHY 110-PORTLAOISE 110-1 | 3 | 3 | 3 | Scheduled | 09/08/2022 | 11/08/2022
TO-22-BYH-T2101-03 | TRANSFORMER - BALLYNAHULLA 220-BALLYNAHULLA 110-T2101 | 1 | 1 | 1 | Scheduled | 09/08/2022 | 09/08/2022
TO-22-BVK-110K1-02 | COUPLER/SECTIONALISING CB - BALLYVOUSKILL 110-BALLYVOUSKILL 110-110K1 | 4 | 4 | 4 | Scheduled | 09/08/2022 | 12/08/2022
TO-22-CLE-220K1-03 | COUPLER/SECTIONALISING CB - CLONEE 220-CLONEE 220-220K1 | 1 | 1 | 1 | Scheduled | 09/08/2022 | 09/08/2022
TO-22-LET-T141-01 | DISTRIBUTION TRANSFORMER - LETTERKENNY 110-LETTERKENNY 38-T141 | 2 | 2 | 2 | Reference | 09/08/2022 | 10/08/2022
TO-22-220 kV A1/A2 @ KLN-01 | BUSBAR SECTION - KILLONAN 220-KILLONAN 220-220A1-A2 | 1 | 1 | 1 | Scheduled | 10/08/2022 | 10/08/2022
TO-22-220 kV B1/B2 @ KLN-01 | BUSBAR SECTION - KILLONAN 220-KILLONAN 220-220B1-B2 | 1 | 1 | 1 | Scheduled | 10/08/2022 | 10/08/2022
TO-22-BVK-220K1-01 | COUPLER/SECTIONALISING CB - BALLYVOUSKILL 220-BALLYVOUSKILL 220-220K1 | 1 | 1 | 1 | Scheduled | 11/08/2022 | 11/08/2022
TO-22-BYH-220K1-03 | COUPLER/SECTIONALISING CB - BALLYNAHULLA 220-BALLYNAHULLA 220-220K1 | 1 | 1 | 1 | Scheduled | 12/08/2022 | 12/08/2022
TO-22-CL-T101-04 | GENERATOR TRANSFORMER - CLIFF 110-CLIFF G1-T101 | 1 | 1 | 1 | Tentative | 12/08/2022 | 12/08/2022
TO-22-CL-T102-02 | GENERATOR TRANSFORMER - CLIFF 110-CLIFF G2-T102 | 1 | 1 | 1 | Tentative | 12/08/2022 | 12/08/2022
TO-22-FIN-NW-1-06 | 220kV FEEDER - FINGLAS 220-NORTH WALL 220-1 | 1 | 1 | 1 | Scheduled | 12/08/2022 | 12/08/2022
TO-22-TAW-T1/T2-01 | GENERATOR TRANSFORMER - TAWNAGHMORE 110-TAWNAGHMORE 10-T1/T2 | 8 | 6 | 6 | Scheduled | 12/08/2022 | 19/08/2022
TO-22-BVK-COT-1-03 | 110kV FEEDER - BALLYVOUSKILL 110-COOMATAGGART 110-1 | 5 | 5 | 5 | Scheduled | 15/08/2022 | 19/08/2022
TO-22-BAN-BRI-2-01 | 110kV FEEDER - BANDON 110-BRINNY 110-2 | 6 | 5 | 5 | Scheduled | 15/08/2022 | 20/08/2022
TO-22-BRI-T102-01 | TSO CUSTOMER TRANSFORMER - BRINNY 110-BRINNY 10-T102 | 6 | 5 | 5 | Scheduled | 15/08/2022 | 20/08/2022
TO-22-CSH-TY-1-05 | 220kV FEEDER - CASHLA 220-TYNAGH 220-1 | 5 | 5 | 5 | Scheduled | 15/08/2022 | 19/08/2022
TO-22-CF-COR-1-01 | 110kV FEEDER - CATHALEENS FALL 110-CORRACLASSY 110-1 | 40 | 30 | 30 | Scheduled | 15/08/2022 | 23/09/2022
TO-22-CRO-IA-1-01 | 110kV FEEDER - COOLROE 110-INNISCARRA 110-1 | 12 | 10 | 10 | Scheduled | 15/08/2022 | 26/08/2022
TO-22-COT-110SA1-01 | SECTIONALISING DISCONNECT - COOMATAGGART 110-COOMATAGGART 110-110SA1 | 5 | 5 | 5 | Scheduled | 15/08/2022 | 19/08/2022
TO-22-COT-110SA2-01 | SECTIONALISING DISCONNECT - COOMATAGGART 110-COOMATAGGART 110-110SA2 | 5 | 5 | 5 | Scheduled | 15/08/2022 | 19/08/2022
TO-22-COT-FILTER1-01 | CAPACITOR/SVC/REACTOR - COOMATAGGART 110-COOMATAGGART 110-FILTER1 | 5 | 5 | 5 | Scheduled | 15/08/2022 | 19/08/2022
TO-22-COT-T132-01 | GENERATOR TRANSFORMER - COOMATAGGART 110-COOMATAGGART 33-T132 | 5 | 5 | 5 | Scheduled | 15/08/2022 | 19/08/2022
TO-22-COT-T141-01 | DISTRIBUTION TRANSFORMER - COOMATAGGART 110-COOMATAGGART 38-T141 | 5 | 5 | 5 | Reference | 15/08/2022 | 19/08/2022
TO-22-CDU-MUL-1-01 | 110kV FEEDER - CORDUFF 110-MULLINGAR 110-1 | 44 | 32 | 32 | Scheduled | 15/08/2022 | 27/09/2022
TO-22-DER-MAY-1-02 | 110kV FEEDER - DERRYIRON 110-MAYNOOTH 110-1 | 12 | 10 | 10 | Scheduled | 15/08/2022 | 26/08/2022
TO-22-DRU-110SA1-02 | SECTIONALISING DISCONNECT - DRUMLINE 110-DRUMLINE 110-110SA1 | 5 | 5 | 5 | Scheduled | 15/08/2022 | 19/08/2022
TO-22-DRU-110SA2-01 | SECTIONALISING DISCONNECT - DRUMLINE 110-DRUMLINE 110-110SA2 | 5 | 5 | 5 | Scheduled | 15/08/2022 | 19/08/2022
TO-22-DRU-ENN-1-01 | 110kV FEEDER - DRUMLINE 110-ENNIS 110-1 | 5 | 5 | 5 | Scheduled | 15/08/2022 | 19/08/2022
TO-22-DRU-T141-01 | DISTRIBUTION TRANSFORMER - DRUMLINE 110-DRUMLINE 38-T141 | 5 | 5 | 5 | Reference | 15/08/2022 | 19/08/2022
TO-22-110 kV A3 @ FIN-03 | BUSBAR SECTION - FINGLAS 110-FINGLAS 110-110A3 | 5 | 5 | 5 | Scheduled | 15/08/2022 | 19/08/2022
TO-22-110 kV B3 @ FIN-02 | BUSBAR SECTION - FINGLAS 110-FINGLAS 110-110B3 | 5 | 5 | 5 | Scheduled | 15/08/2022 | 19/08/2022
TO-22-220 kV A2 @ FIN-01 | BUSBAR SECTION - FINGLAS 220-FINGLAS 220-220A2 | 5 | 5 | 5 | Scheduled | 15/08/2022 | 19/08/2022
TO-22-220 kV B2 @ FIN-01 | BUSBAR SECTION - FINGLAS 220-FINGLAS 220-220B2 | 5 | 5 | 5 | Scheduled | 15/08/2022 | 19/08/2022
TO-22-FIN-T2104-03 | TRANSFORMER - FINGLAS 220-FINGLAS 110-T2104 | 12 | 10 | 10 | Scheduled | 15/08/2022 | 26/08/2022
TO-22-GLE-KCR-1-01 | 110kV FEEDER - GLENLARA 110-KNOCKACUMMER 110-1 | 5 | 5 | 5 | Scheduled | 15/08/2022 | 19/08/2022
TO-22-KLN-LIM-2-02 | 110kV FEEDER - KILLONAN 110-LIMERICK 110-2 | 12 | 10 | 10 | Scheduled | 15/08/2022 | 26/08/2022
TO-22-KCR-T121-01 | GENERATOR TRANSFORMER - KNOCKACUMMER 110-KNOCKACUMMER 20-T121 | 5 | 5 | 5 | Scheduled | 15/08/2022 | 19/08/2022
TO-22-110 kV A1 @ RYB GIS-02 | BUSBAR SECTION - RYEBROOK GIS 110-RYEBROOK GIS 110-110A1 | 5 | 5 | 5 | Scheduled | 15/08/2022 | 19/08/2022
TO-22-110 kV A3 @ RYB GIS-02 | BUSBAR SECTION - RYEBROOK GIS 110-RYEBROOK GIS 110-110A3 | 5 | 5 | 5 | Scheduled | 15/08/2022 | 19/08/2022
TO-22-RYB GIS-110SA1-3CB-01 | COUPLER/SECTIONALISING CB - RYEBROOK GIS 110-RYEBROOK GIS 110-110SA1-3CB | 5 | 5 | 5 | Scheduled | 15/08/2022 | 19/08/2022
TO-22-110 kV A2 @ SLB-01 | BUSBAR SECTION - SLIABH BAWN 110-SLIABH BAWN 110-110A2 | 5 | 5 | 5 | Scheduled | 15/08/2022 | 19/08/2022
TO-22-110 kV B2 @ SLB-01 | BUSBAR SECTION - SLIABH BAWN 110-SLIABH BAWN 110-110B2 | 5 | 5 | 5 | Scheduled | 15/08/2022 | 19/08/2022
TO-22-SLB-110K2-02 | COUPLER/SECTIONALISING CB - SLIABH BAWN 110-SLIABH BAWN 110-110K2 | 5 | 5 | 5 | Scheduled | 15/08/2022 | 19/08/2022
TO-22-TIV-110SA1-2CB-03 | COUPLER/SECTIONALISING CB - TIEVEBRACK 110-TIEVEBRACK 110-110SA1-2CB | 1 | 1 | 1 | Scheduled | 15/08/2022 | 15/08/2022
TO-22-CBT-110K1-05 | COUPLER/SECTIONALISING CB - CASTLEBAGOT 110-CASTLEBAGOT 110-110K1 | 1 | 1 | 1 | Scheduled | 16/08/2022 | 16/08/2022
TO-22-110 kV A1 @ CBT-04 | BUSBAR SECTION - CASTLEBAGOT 110-CASTLEBAGOT 110-110A1 | 3 | 3 | 3 | Scheduled | 17/08/2022 | 19/08/2022
TO-22-110 kV A2 @ CBT-01 | BUSBAR SECTION - CASTLEBAGOT 110-CASTLEBAGOT 110-110A2 | 3 | 3 | 3 | Scheduled | 17/08/2022 | 19/08/2022
TO-22-CBT-110SA1-2CB-03 | COUPLER/SECTIONALISING CB - CASTLEBAGOT 110-CASTLEBAGOT 110-110SA1-2CB | 3 | 3 | 3 | Scheduled | 17/08/2022 | 19/08/2022
TO-22-CLA-MAC-2-02 | 110kV FEEDER - CLASHAVOON 110-MACROOM 110-2 | 3 | 3 | 3 | Scheduled | 17/08/2022 | 19/08/2022
TO-22-LET-110SA1-3CB-01 | COUPLER/SECTIONALISING CB - LETTERKENNY 110-LETTERKENNY 110-110SA1-3CB | 1 | 1 | 1 | Scheduled | 17/08/2022 | 17/08/2022
TO-22-110 kV A1/A2 @ SRA-01 | BUSBAR SECTION - SRANANAGH 110-SRANANAGH 110-110A1-A2 | 1 | 1 | 1 | Scheduled | 17/08/2022 | 17/08/2022
TO-22-110 kV B1/B2 @ SRA-01 | BUSBAR SECTION - SRANANAGH 110-SRANANAGH 110-110B1-B2 | 1 | 1 | 1 | Scheduled | 17/08/2022 | 17/08/2022
TO-22-110 kV A1 @ AA GIS-01 | BUSBAR SECTION - ARDNACRUSHA GIS 110-ARDNACRUSHA GIS 110-110A1 | 5 | 5 | 5 | Scheduled | 22/08/2022 | 26/08/2022
TO-22-110 kV A3 @ AA GIS-01 | BUSBAR SECTION - ARDNACRUSHA GIS 110-ARDNACRUSHA GIS 110-110A3 | 5 | 5 | 5 | Scheduled | 22/08/2022 | 26/08/2022
TO-22-AA GIS-110SA1-3CB-02 | COUPLER/SECTIONALISING CB - ARDNACRUSHA GIS 110-ARDNACRUSHA GIS 110-110SA1-3CB | 5 | 5 | 5 | Scheduled | 22/08/2022 | 26/08/2022
TO-22-BWR-CRA-1-01 | 110kV FEEDER - BALLYWATER 110-CRANE 110-1 | 4 | 4 | 4 | Scheduled | 22/08/2022 | 25/08/2022
TO-22-BWR-T124-01 | GENERATOR TRANSFORMER - BALLYWATER 110-BALLYWATER 20-T124 | 4 | 4 | 4 | Reference | 22/08/2022 | 25/08/2022
TO-22-BOL-110SA1-01 | SECTIONALISING DISCONNECT - BOOLTIAGH 110-BOOLTIAGH 110-110SA1 | 5 | 5 | 5 | Scheduled | 22/08/2022 | 26/08/2022
TO-22-BOL-110SA1-3CB-01 | COUPLER/SECTIONALISING CB - BOOLTIAGH 110-BOOLTIAGH 110-110SA1-3CB | 5 | 5 | 5 | Scheduled | 22/08/2022 | 26/08/2022
TO-22-BOL-110SA2-01 | SECTIONALISING DISCONNECT - BOOLTIAGH 110-BOOLTIAGH 110-110SA2 | 5 | 5 | 5 | Scheduled | 22/08/2022 | 26/08/2022
TO-22-BOL-T121-03 | GENERATOR TRANSFORMER - BOOLTIAGH 110-BOOLTIAGH 20-T121 | 5 | 5 | 5 | Scheduled | 22/08/2022 | 26/08/2022
TO-22-CDU-WOO-1-02 | 220kV FEEDER - CORDUFF 220-WOODLAND 220-1 | 5 | 5 | 5 | Scheduled | 22/08/2022 | 26/08/2022
TO-22-GI-T2101-02 | TRANSFORMER - GREAT ISLAND GIS 220-GREAT ISLAND 110-T2101 | 8 | 6 | 6 | Scheduled | 22/08/2022 | 29/08/2022
TO-22-110 kV A3 @ KPG-02 | BUSBAR SECTION - KILPADDOGE 110-KILPADDOGE 110-110A3 | 4 | 4 | 4 | Scheduled | 22/08/2022 | 25/08/2022
TO-22-110 kV B3 @ KPG-01 | BUSBAR SECTION - KILPADDOGE 110-KILPADDOGE 110-110B3 | 4 | 4 | 4 | Scheduled | 22/08/2022 | 25/08/2022
TO-22-KPG-110K3-01 | COUPLER/SECTIONALISING CB - KILPADDOGE 110-KILPADDOGE 110-110K3 | 4 | 4 | 4 | Scheduled | 22/08/2022 | 25/08/2022
TO-22-LA-SLB-1-01 | 110kV FEEDER - LANESBORO 110-SLIABH BAWN 110-1 | 5 | 5 | 5 | Scheduled | 22/08/2022 | 26/08/2022
TO-22-CDK-LWD-1-02 | 110kV FEEDER - CASTLEDOCKRELL 110-LODGEWOOD 110-1 | 2 | 2 | 2 | Scheduled | 25/08/2022 | 26/08/2022
TO-22-CDK-T121-02 | GENERATOR TRANSFORMER - CASTLEDOCKRELL 110-CASTLEDOCKRELL 20-T121 | 2 | 2 | 2 | Reference | 25/08/2022 | 26/08/2022
TO-22-220 kV A1 @ CKM-01 | BUSBAR SECTION - CARRICKMINES 220-CARRICKMINES 220-220A1 | 12 | 10 | 10 | Scheduled | 29/08/2022 | 09/09/2022
TO-22-220 kV B1 @ CKM-01 | BUSBAR SECTION - CARRICKMINES 220-CARRICKMINES 220-220B1 | 12 | 10 | 10 | Scheduled | 29/08/2022 | 09/09/2022
TO-22-CKM-CKM GIS-1-01 | 220kV FEEDER - CARRICKMINES 220-CARRICKMINES GIS 220-1 | 26 | 20 | 20 | Scheduled | 29/08/2022 | 23/09/2022
TO-22-CKM-PB-1-01 | 220kV FEEDER - CARRICKMINES 220-POOLBEG 220-1 | 26 | 20 | 20 | Scheduled | 29/08/2022 | 23/09/2022
TO-22-CKM-PST2201-01 | TRANSFORMER - CARRICKMINES 220-CARRICKMINES 220-PST2201 | 26 | 20 | 20 | Scheduled | 29/08/2022 | 23/09/2022
TO-22-220 kV A2 @ CLE-05 | BUSBAR SECTION - CLONEE 220-CLONEE 220-220A2 | 5 | 5 | 5 | Scheduled | 29/08/2022 | 02/09/2022
TO-22-220 kV B2 @ CLE-04 | BUSBAR SECTION - CLONEE 220-CLONEE 220-220B2 | 5 | 5 | 5 | Scheduled | 29/08/2022 | 02/09/2022
TO-22-CLE-T224-01 | TSO CUSTOMER TRANSFORMER - CLONEE 220-CLONEE 20-T224 | 29 | 21 | 21 | Scheduled | 29/08/2022 | 26/09/2022
TO-22-110 kV A1 @ CUL-01 | BUSBAR SECTION - CULLENAGH 110-CULLENAGH 110-110A1 | 5 | 5 | 5 | Scheduled | 29/08/2022 | 02/09/2022
TO-22-110 kV B1 @ CUL-01 | BUSBAR SECTION - CULLENAGH 110-CULLENAGH 110-110B1 | 5 | 5 | 5 | Scheduled | 29/08/2022 | 02/09/2022
TO-22-220 kV A1 @ GI GIS-02 | BUSBAR SECTION - GREAT ISLAND GIS 220-GREAT ISLAND GIS 220-220A1 | 4 | 4 | 4 | Scheduled | 29/08/2022 | 01/09/2022
TO-22-220 kV A2 @ GI GIS-02 | BUSBAR SECTION - GREAT ISLAND GIS 220-GREAT ISLAND GIS 220-220A2 | 4 | 4 | 4 | Scheduled | 29/08/2022 | 01/09/2022
TO-22-GI GIS-220SA1-2CB-01 | COUPLER/SECTIONALISING CB - GREAT ISLAND GIS 220-GREAT ISLAND GIS 220-220SA1-2CB | 4 | 4 | 4 | Scheduled | 29/08/2022 | 01/09/2022
TO-22-110 kV A1 @ KPG-03 | BUSBAR SECTION - KILPADDOGE 110-KILPADDOGE 110-110A1 | 4 | 4 | 4 | Scheduled | 29/08/2022 | 01/09/2022
TO-22-110 kV B1 @ KPG-02 | BUSBAR SECTION - KILPADDOGE 110-KILPADDOGE 110-110B1 | 4 | 4 | 4 | Scheduled | 29/08/2022 | 01/09/2022
TO-22-220 kV A1 @ KPG-02 | BUSBAR SECTION - KILPADDOGE 220-KILPADDOGE 220-220A1 | 4 | 4 | 4 | Scheduled | 29/08/2022 | 01/09/2022
TO-22-220 kV B1 @ KPG-02 | BUSBAR SECTION - KILPADDOGE 220-KILPADDOGE 220-220B1 | 4 | 4 | 4 | Scheduled | 29/08/2022 | 01/09/2022
TO-22-KPG-T2101-01 | TRANSFORMER - KILPADDOGE 220-KILPADDOGE 110-T2101 | 8 | 6 | 6 | Scheduled | 29/08/2022 | 05/09/2022
TO-22-220 kV A2 @ PB-04 | BUSBAR SECTION - POOLBEG 220-POOLBEG 220-220A2 | 5 | 5 | 5 | Scheduled | 29/08/2022 | 02/09/2022
TO-22-220 kV B2 @ PB-03 | BUSBAR SECTION - POOLBEG 220-POOLBEG 220-220B2 | 5 | 5 | 5 | Scheduled | 29/08/2022 | 02/09/2022
TO-22-PB-220K2-3-02 | COUPLER/SECTIONALISING CB - POOLBEG 220-POOLBEG 220-220K2-3 | 5 | 5 | 5 | Scheduled | 29/08/2022 | 02/09/2022
TO-22-SH-T2102-01 | TRANSFORMER - SHANNONBRIDGE 220-SHANNONBRIDGE 110-T2102 | 5 | 5 | 5 | Scheduled | 29/08/2022 | 02/09/2022
TO-22-TRL-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - TRALEE 110-TRALEE 110-110SA1-2CB | 5 | 5 | 5 | Scheduled | 29/08/2022 | 02/09/2022
TO-22-TRL-T142-02 | DISTRIBUTION TRANSFORMER - TRALEE 110-TRALEE 38-T142 | 5 | 5 | 5 | Reference | 29/08/2022 | 02/09/2022
TO-22-110 kV B2 @ CBT-02 | BUSBAR SECTION - CASTLEBAGOT 110-CASTLEBAGOT 110-110B2 | 3 | 3 | 3 | Scheduled | 30/08/2022 | 01/09/2022
TO-22-110 kV B4 @ CBT-05 | BUSBAR SECTION - CASTLEBAGOT 110-CASTLEBAGOT 110-110B4 | 3 | 3 | 3 | Scheduled | 30/08/2022 | 01/09/2022
TO-22-CBT-110SB2-4CB-05 | COUPLER/SECTIONALISING CB - CASTLEBAGOT 110-CASTLEBAGOT 110-110SB2-4CB | 3 | 3 | 3 | Scheduled | 30/08/2022 | 01/09/2022
TO-22-GOR-110K1-2-02 | COUPLER/SECTIONALISING CB - GORMAN 110-GORMAN 110-110K1-2 | 1 | 1 | 1 | Tentative | 30/08/2022 | 30/08/2022
TO-22-LSN-T122-07 | GENERATOR TRANSFORMER - LISHEEN 110-LISHEEN 20-T122 | 3 | 3 | 3 | Scheduled | 30/08/2022 | 01/09/2022
TO-22-RYB GIS-T131-02 | TSO CUSTOMER TRANSFORMER - RYEBROOK GIS 110-RYEBROOK 33-T131 | 1 | 1 | 1 | Scheduled | 30/08/2022 | 30/08/2022
TO-22-SNG-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - SINGLAND 110-SINGLAND 110-110SA1-2CB | 2 | 2 | 2 | Scheduled | 30/08/2022 | 31/08/2022
TO-22-SNG-T101-01 | DISTRIBUTION TRANSFORMER - SINGLAND 110-SINGLAND 10-T101 | 2 | 2 | 2 | Reference | 30/08/2022 | 31/08/2022
TO-22-CRO-KBY-1-04 | 110kV FEEDER - COOLROE 110-KILBARRY 110-1 | 21 | 15 |  | Scheduled | 31/08/2022 | 20/09/2022
TO-22-CUL-T2101-01 | TRANSFORMER - CULLENAGH 220-CULLENAGH 110-T2101 | 42 | 30 |  | Scheduled | 31/08/2022 | 11/10/2022
TO-22-KNR-220K1-02 | COUPLER/SECTIONALISING CB - KNOCKANURE 220-KNOCKANURE 220-220K1 | 2 | 2 | 2 | Scheduled | 31/08/2022 | 01/09/2022
TO-22-KLN-SH-1-03 | 220kV FEEDER - KILLONAN 220-SHANNONBRIDGE 220-1 | 1 | 1 | 1 | Scheduled | 02/09/2022 | 02/09/2022
TO-22-ISH-T2001-01 | GENERATOR TRANSFORMER - IRISHTOWN 220-IRISHTOWN G1-T2001 | 23 | 16 | 16 | Scheduled | 04/09/2022 | 26/09/2022
TO-22-220 kV A1 @ AD-03 | BUSBAR SECTION - AGHADA 220-AGHADA 220-220A1 | 5 | 5 | 5 | Scheduled | 05/09/2022 | 09/09/2022
TO-22-220 kV B1 @ AD-04 | BUSBAR SECTION - AGHADA 220-AGHADA 220-220B1 | 5 | 5 | 5 | Scheduled | 05/09/2022 | 09/09/2022
TO-22-AD-LPT-1-01 | 220kV FEEDER - AGHADA 220-LONG POINT 220-1 | 5 | 5 | 5 | Scheduled | 05/09/2022 | 09/09/2022
TO-22-AA GIS-T103-01 | GENERATOR TRANSFORMER - ARDNACRUSHA GIS 110-ARDNACRUSHA GIS G3-T103 | 5 | 5 | 5 | Scheduled | 05/09/2022 | 09/09/2022
TO-22-110 kV A2 @ BYH-04 | BUSBAR SECTION - BALLYNAHULLA 110-BALLYNAHULLA 110-110A2 | 5 | 5 | 5 | Scheduled | 05/09/2022 | 09/09/2022
TO-22-110 kV B2 @ BYH-04 | BUSBAR SECTION - BALLYNAHULLA 110-BALLYNAHULLA 110-110B2 | 5 | 5 | 5 | Scheduled | 05/09/2022 | 09/09/2022
TO-22-BYH-CDL-1-02 | 110kV FEEDER - BALLYNAHULLA 110-CORDAL 110-1 | 5 | 5 |  | Scheduled | 05/09/2022 | 09/09/2022
TO-22-BDA-T101-01 | TSO CUSTOMER TRANSFORMER - BARODA 110-BARODA 10-T101 | 3 | 3 | 3 | Scheduled | 05/09/2022 | 07/09/2022
TO-22-BK-110SA1-04 | SECTIONALISING DISCONNECT - BELLACORICK 110-BELLACORICK 110-110SA1 | 5 | 5 | 5 | Tentative | 05/09/2022 | 09/09/2022
TO-22-BK-110SA2-04 | SECTIONALISING DISCONNECT - BELLACORICK 110-BELLACORICK 110-110SA2 | 5 | 5 | 5 | Tentative | 05/09/2022 | 09/09/2022
TO-22-BK-MOY-1-06 | 110kV FEEDER - BELLACORICK 110-MOY 110-1 | 5 | 5 | 5 | Tentative | 05/09/2022 | 09/09/2022
TO-22-BK-T141-03 | DISTRIBUTION TRANSFORMER - BELLACORICK 110-BELLACORICK 38-T141 | 5 | 5 | 5 | Reference (Tentative) | 05/09/2022 | 09/09/2022
TO-22-CF-T104-01 | GENERATOR TRANSFORMER - CATHALEENS FALL 110-CATHALEENS FALL G4-T104 | 1 | 1 | 1 | Scheduled | 05/09/2022 | 05/09/2022
TO-22-CDL-110SA1-02 | SECTIONALISING DISCONNECT - CORDAL 110-CORDAL 110-110SA1 | 5 | 5 |  | Scheduled | 05/09/2022 | 09/09/2022
TO-22-CDL-110SA2-02 | SECTIONALISING DISCONNECT - CORDAL 110-CORDAL 110-110SA2 | 5 | 5 |  | Scheduled | 05/09/2022 | 09/09/2022
TO-22-CDL-T132-02 | GENERATOR TRANSFORMER - CORDAL 110-CORDAL 33-T132 | 5 | 5 |  | Scheduled | 05/09/2022 | 09/09/2022
TO-22-CDL-T141-01 | DISTRIBUTION TRANSFORMER - CORDAL 110-CORDAL 38-T141 | 5 | 5 |  | Reference | 05/09/2022 | 09/09/2022
TO-22-220 kV A1 @ CUL-01 | BUSBAR SECTION - CULLENAGH 220-CULLENAGH 220-220A1 | 5 | 5 | 5 | Scheduled | 05/09/2022 | 09/09/2022
TO-22-220 kV B1 @ CUL-01 | BUSBAR SECTION - CULLENAGH 220-CULLENAGH 220-220B1 | 5 | 5 | 5 | Scheduled | 05/09/2022 | 09/09/2022
TO-22-DSN-MAY-1-01 | 220kV FEEDER - DUNSTOWN 220-MAYNOOTH 220-1 | 5 | 5 | 5 | Scheduled | 05/09/2022 | 09/09/2022
TO-22-110 kV A5 @ FIN GIS-02 | BUSBAR SECTION - FINGLAS GIS 110-FINGLAS GIS 110-110A5 | 5 | 5 | 5 | Scheduled | 05/09/2022 | 09/09/2022
TO-22-110 kV B5 @ FIN GIS-02 | BUSBAR SECTION - FINGLAS GIS 110-FINGLAS GIS 110-110B5 | 5 | 5 | 5 | Scheduled | 05/09/2022 | 09/09/2022
TO-22-FIN GIS-110K5-02 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110K5 | 5 | 5 | 5 | Scheduled | 05/09/2022 | 09/09/2022
TO-22-KLH-KNY-1-01 | 110kV FEEDER - KNOCKALOUGH-KNOCKRANNY 110-1 | 5 | 5 | 5 | Scheduled | 05/09/2022 | 09/09/2022
TO-22-KRA-T2101-01 | TRANSFORMER - KNOCKRAHA 220-KNOCKRAHA 110-T2101 | 16 | 12 | 12 | Scheduled | 05/09/2022 | 20/09/2022
TO-22-110 kV A2 @ KNY-03 | BUSBAR SECTION - KNOCKRANNY 110-KNOCKRANNY 110-110A2 | 4 | 4 | 4 | Scheduled | 05/09/2022 | 08/09/2022
TO-22-110 kV B2 @ KNY-03 | BUSBAR SECTION - KNOCKRANNY 110-KNOCKRANNY 110-110B2 | 4 | 4 | 4 | Scheduled | 05/09/2022 | 08/09/2022
TO-22-LPT-T2002-01 | GENERATOR TRANSFORMER - LONG POINT 220-LONG POINT G1-T2002 | 5 | 5 | 5 | Scheduled | 05/09/2022 | 09/09/2022
TO-22-110 kV A1 @ LOU-01 | BUSBAR SECTION - LOUTH 110-LOUTH 110-110A1 | 5 | 5 | 5 | Scheduled | 05/09/2022 | 09/09/2022
TO-22-110 kV B1 @ LOU-01 | BUSBAR SECTION - LOUTH 110-LOUTH 110-110B1 | 5 | 5 | 5 | Scheduled | 05/09/2022 | 09/09/2022
TO-22-LOU-CAP1-02 | CAPACITOR/SVC/REACTOR - LOUTH 110-LOUTH 110-CAP1 | 5 | 5 | 5 | Scheduled | 05/09/2022 | 09/09/2022
TO-22-110 kV A2 @ RYB GIS-02 | BUSBAR SECTION - RYEBROOK GIS 110-RYEBROOK GIS 110-110A2 | 5 | 5 | 5 | Scheduled | 05/09/2022 | 09/09/2022
TO-22-110 kV A4 @ RYB GIS-01 | BUSBAR SECTION - RYEBROOK GIS 110-RYEBROOK GIS 110-110A4 | 5 | 5 | 5 | Scheduled | 05/09/2022 | 09/09/2022
TO-22-RYB GIS-110SA2-4CB-02 | COUPLER/SECTIONALISING CB - RYEBROOK GIS 110-RYEBROOK GIS 110-110SA2-4CB | 5 | 5 | 5 | Scheduled | 05/09/2022 | 09/09/2022
TO-22-WHI-CKB-T102-01 | TSO CUSTOMER TRANSFORMER - WHITEGATE 110-WHITEGATE 10-CKB-T102 | 5 | 5 | 5 | Scheduled | 05/09/2022 | 09/09/2022
TO-22-GOR-PLA-1-01 | 110kV FEEDER - GORMAN 110-PLATIN 110-1 | 79 | 56 | 56 | Scheduled | 06/09/2022 | 23/11/2022
TO-22-SLI-110SA1-2CB-04 | COUPLER/SECTIONALISING CB - SLIGO 110-SLIGO 110-110SA1-2CB | 2 | 2 | 2 | Scheduled | 06/09/2022 | 07/09/2022
TO-22-GLR-T142-01 | DISTRIBUTION TRANSFORMER - GLENREE 110-GLENREE 38-T142 | 2 | 2 | 2 | Reference | 07/09/2022 | 08/09/2022
TO-22-GI-110K1-2-01 | COUPLER/SECTIONALISING CB - GREAT ISLAND 110-GREAT ISLAND 110-110K1-2 | 1 | 1 | 1 | Scheduled | 07/09/2022 | 07/09/2022
TO-22-220 kV A1/A2 @ WOO-01 | BUSBAR SECTION - WOODLAND 220-WOODLAND 220-220A1-A2 | 1 | 1 | 1 | Scheduled | 07/09/2022 | 07/09/2022
TO-22-220 kV B1/B2 @ WOO-01 | BUSBAR SECTION - WOODLAND 220-WOODLAND 220-220B1-B2 | 1 | 1 | 1 | Scheduled | 07/09/2022 | 07/09/2022
TO-22-CAH-TIP-1-02 | 110kV FEEDER - CAHIR 110-TIPPERARY 110-1 | 5 | 3 | 3 | Scheduled | 08/09/2022 | 12/09/2022
TO-22-GWE-T142-01 | DISTRIBUTION TRANSFORMER - GORTAWEE 110-GORTAWEE 38-T142 | 2 | 2 | 2 | Reference | 08/09/2022 | 09/09/2022
TO-22-GI GIS-220K1-01 | COUPLER/SECTIONALISING CB - GREAT ISLAND GIS 220-GREAT ISLAND GIS 220-220K1 | 1 | 1 | 1 | Scheduled | 08/09/2022 | 08/09/2022
TO-22-AD-RAF-1-02 | 220kV FEEDER - AGHADA 220-RAFFEEN 220-1 | 5 | 5 | 5 | Tentative | 12/09/2022 | 16/09/2022
TO-22-ARV-SKL-1-03 | 110kV FEEDER - ARVA 110-SHANKILL 110-1 | 5 | 5 | 5 | Scheduled | 12/09/2022 | 16/09/2022
TO-22-ATY-CLW-1-01 | 110kV FEEDER - ATHY 110-CARLOW 110-1 | 47 | 35 | 35 | Scheduled | 12/09/2022 | 28/10/2022
TO-22-110 kV A2 @ BYH-05 | BUSBAR SECTION - BALLYNAHULLA 110-BALLYNAHULLA 110-110A2 | 5 | 5 | 5 | Scheduled | 12/09/2022 | 16/09/2022
TO-22-110 kV B2 @ BYH-05 | BUSBAR SECTION - BALLYNAHULLA 110-BALLYNAHULLA 110-110B2 | 5 | 5 | 5 | Scheduled | 12/09/2022 | 16/09/2022
TO-22-220 kV A2 @ BYH-02 | BUSBAR SECTION - BALLYNAHULLA 220-BALLYNAHULLA 220-220A2 | 5 | 5 | 5 | Scheduled | 12/09/2022 | 16/09/2022
TO-22-220 kV B2 @ BYH-02 | BUSBAR SECTION - BALLYNAHULLA 220-BALLYNAHULLA 220-220B2 | 5 | 5 | 5 | Scheduled | 12/09/2022 | 16/09/2022
TO-22-BYH-T2102-03 | TRANSFORMER - BALLYNAHULLA 220-BALLYNAHULLA 110-T2102 | 5 | 5 |  | Scheduled | 12/09/2022 | 16/09/2022
TO-22-110 kV A1 @ CF-02 | BUSBAR SECTION - CATHALEENS FALL 110-CATHALEENS FALL 110-110A1 | 5 | 5 | 5 | Scheduled | 12/09/2022 | 16/09/2022
TO-22-110 kV B1 @ CF-02 | BUSBAR SECTION - CATHALEENS FALL 110-CATHALEENS FALL 110-110B1 | 5 | 5 | 5 | Scheduled | 12/09/2022 | 16/09/2022
TO-22-CF-CL-1-01 | 110kV FEEDER - CATHALEENS FALL 110-CLIFF 110-1 | 5 | 5 | 5 | Scheduled | 12/09/2022 | 16/09/2022
TO-22-CL-T101-02 | GENERATOR TRANSFORMER - CLIFF 110-CLIFF G1-T101 | 5 | 5 | 5 | Scheduled | 12/09/2022 | 16/09/2022
TO-22-CL-T102-03 | GENERATOR TRANSFORMER - CLIFF 110-CLIFF G2-T102 | 5 | 5 | 5 | Scheduled | 12/09/2022 | 16/09/2022
TO-22-CRO-110SA1-01 | SECTIONALISING DISCONNECT - COOLROE 110-COOLROE 110-110SA1 | 5 | 5 | 5 | Scheduled | 12/09/2022 | 16/09/2022
TO-22-CRO-110SA2-01 | SECTIONALISING DISCONNECT - COOLROE 110-COOLROE 110-110SA2 | 5 | 5 | 5 | Scheduled | 12/09/2022 | 16/09/2022
TO-22-CRO-T121-01 | DISTRIBUTION TRANSFORMER - COOLROE 110-COOLROE 20-T121 | 5 | 5 | 5 | Reference | 12/09/2022 | 16/09/2022
TO-22-DSN-T4201-02 | TRANSFORMER - DUNSTOWN 400-DUNSTOWN 220-T4201 | 26 | 20 | 20 | Scheduled | 12/09/2022 | 07/10/2022
TO-22-110 kV A2 @ FIN GIS-06 | BUSBAR SECTION - FINGLAS GIS 110-FINGLAS GIS 110-110A2 | 5 | 5 | 5 | Scheduled | 12/09/2022 | 16/09/2022
TO-22-110 kV A4 @ FIN GIS-01 | BUSBAR SECTION - FINGLAS GIS 110-FINGLAS GIS 110-110A4 | 5 | 5 | 5 | Scheduled | 12/09/2022 | 16/09/2022
TO-22-FIN GIS-110SA2-4CB-07 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110SA2-4CB | 5 | 5 | 5 | Scheduled | 12/09/2022 | 16/09/2022
TO-22-110 kV A2 @ KPG-02 | BUSBAR SECTION - KILPADDOGE 110-KILPADDOGE 110-110A2 | 8 | 6 | 6 | Scheduled | 12/09/2022 | 19/09/2022
TO-22-110 kV B2 @ KPG-01 | BUSBAR SECTION - KILPADDOGE 110-KILPADDOGE 110-110B2 | 8 | 6 | 6 | Scheduled | 12/09/2022 | 19/09/2022
TO-22-220 kV A2 @ KPG-02 | BUSBAR SECTION - KILPADDOGE 220-KILPADDOGE 220-220A2 | 8 | 6 | 6 | Scheduled | 12/09/2022 | 19/09/2022
TO-22-220 kV B2 @ KPG-02 | BUSBAR SECTION - KILPADDOGE 220-KILPADDOGE 220-220B2 | 8 | 6 | 6 | Scheduled | 12/09/2022 | 19/09/2022
TO-22-KPG-T2102-02 | TRANSFORMER - KILPADDOGE 220-KILPADDOGE 110-T2102 | 8 | 6 | 6 | Scheduled | 12/09/2022 | 19/09/2022
TO-22-KRA-RAF-1-05 | 220kV FEEDER - KNOCKRAHA 220-RAFFEEN 220-1 | 5 | 5 | 5 | Tentative | 12/09/2022 | 16/09/2022
TO-22-KUR-NAV-1-01 | 110kV FEEDER - KNOCKUMBER 110-NAVAN 110-1 | 5 | 5 | 5 | Scheduled | 12/09/2022 | 16/09/2022
TO-22-KUR-T3-01 | TSO CUSTOMER TRANSFORMER - KNOCKUMBER 110-KNOCKUMBER 10-T3 | 5 | 5 | 5 | Reference | 12/09/2022 | 16/09/2022
TO-22-KUR-T4-01 | TSO CUSTOMER TRANSFORMER - KNOCKUMBER 110-KNOCKUMBER 10-T4 | 5 | 5 | 5 | Reference | 12/09/2022 | 16/09/2022
TO-22-SNU-110SA1-2CB-02 | COUPLER/SECTIONALISING CB - SNUGBOROUGH 110-SNUGBOROUGH 110-110SA1-2CB | 1 | 1 | 1 | Scheduled | 12/09/2022 | 12/09/2022
TO-22-TB-220K1-2-01 | COUPLER/SECTIONALISING CB - TARBERT 220-TARBERT 220-220K1-2 | 7 | 5 | 5 | Scheduled | 12/09/2022 | 18/09/2022
TO-22-TB-T2004-01 | GENERATOR TRANSFORMER - TARBERT 220-TARBERT G4-T2004 | 36 | 26 | 26 | Scheduled | 12/09/2022 | 17/10/2022
TO-22-TB-T2101-02 | TRANSFORMER - TARBERT 220-TARBERT 110-T2101 | 7 | 5 | 5 | Scheduled | 12/09/2022 | 18/09/2022
TO-22-WHI-CKB-T101-01 | TSO CUSTOMER TRANSFORMER - WHITEGATE 110-WHITEGATE 10-CKB-T101 | 5 | 5 | 5 | Scheduled | 12/09/2022 | 16/09/2022
TO-22-110 kV B1 @ CBT-03 | BUSBAR SECTION - CASTLEBAGOT 110-CASTLEBAGOT 110-110B1 | 3 | 3 | 3 | Scheduled | 13/09/2022 | 15/09/2022
TO-22-110 kV B2 @ CBT-01 | BUSBAR SECTION - CASTLEBAGOT 110-CASTLEBAGOT 110-110B2 | 3 | 3 | 3 | Scheduled | 13/09/2022 | 15/09/2022
TO-22-CBT-110SB1-2CB-03 | COUPLER/SECTIONALISING CB - CASTLEBAGOT 110-CASTLEBAGOT 110-110SB1-2CB | 3 | 3 | 3 | Scheduled | 13/09/2022 | 15/09/2022
TO-22-CLA-DMY-1-01 | 110kV FEEDER - CLASHAVOON 110-DUNMANWAY 110-1 | 1 | 1 | 1 | Scheduled | 13/09/2022 | 13/09/2022
TO-22-IKE,T-THU-1-01 | 110kV FEEDER - IKERRIN tee-THURLES 110-1 | 15 | 11 | 11 | Scheduled | 13/09/2022 | 27/09/2022
TO-22-LSN-110SA2-4-01 | SECTIONALISING DISCONNECT - LISHEEN 110-LISHEEN 110-110SA2-4 | 15 | 11 | 11 | Scheduled | 13/09/2022 | 27/09/2022
TO-22-LSN-T122-01 | GENERATOR TRANSFORMER - LISHEEN 110-LISHEEN 20-T122 | 15 | 11 | 11 | Scheduled | 13/09/2022 | 27/09/2022
TO-22-LSN-T142-01 | DISTRIBUTION TRANSFORMER - LISHEEN 110-LISHEEN 38-T142 | 15 | 11 | 11 | Reference | 13/09/2022 | 27/09/2022
TO-22-LSN-THU-1-03 | 110kV FEEDER - LISHEEN 110-THURLES 110-1 | 3 | 3 | 3 | Scheduled | 13/09/2022 | 15/09/2022
TO-22-THU-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - THURLES 110-THURLES 110-110SA1-2CB | 15 | 11 | 11 | Scheduled | 13/09/2022 | 27/09/2022
TO-22-THU-CAP2-01 | CAPACITOR/SVC/REACTOR - THURLES 110-THURLES 110-CAP2 | 15 | 11 | 11 | Scheduled | 13/09/2022 | 27/09/2022
TO-22-THU-T142-01 | DISTRIBUTION TRANSFORMER - THURLES 110-THURLES 38-T142 | 15 | 11 | 11 | Reference | 13/09/2022 | 27/09/2022
TO-22-DMY-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - DUNMANWAY 110-DUNMANWAY 110-110SA1-2CB | 1 | 1 | 1 | Tentative | 14/09/2022 | 14/09/2022
TO-22-110 kV A2 @ PA-01 | BUSBAR SECTION - POLLAPHUCA 110-POLLAPHUCA 110-110A2 | 1 | 1 | 1 | Scheduled | 14/09/2022 | 14/09/2022
TO-22-PA-T101-04 | GENERATOR TRANSFORMER - POLLAPHUCA 110-POLLAPHUCA G1-T101 | 1 | 1 | 1 | Scheduled | 14/09/2022 | 14/09/2022
TO-22-110 kV A1/A2 @ SH-01 | BUSBAR SECTION - SHANNONBRIDGE 110-SHANNONBRIDGE 110-110A1-A2 | 1 | 1 | 1 | Scheduled | 14/09/2022 | 14/09/2022
TO-22-110 kV B1/B2 @ SH-01 | BUSBAR SECTION - SHANNONBRIDGE 110-SHANNONBRIDGE 110-110B1-B2 | 1 | 1 | 1 | Scheduled | 14/09/2022 | 14/09/2022
TO-22-220 kV A1/A2 @ SH-01 | BUSBAR SECTION - SHANNONBRIDGE 220-SHANNONBRIDGE 220-220A1-A2 | 1 | 1 | 1 | Scheduled | 14/09/2022 | 14/09/2022
TO-22-220 kV B1/B2 @ SH-01 | BUSBAR SECTION - SHANNONBRIDGE 220-SHANNONBRIDGE 220-220B1-B2 | 1 | 1 | 1 | Scheduled | 14/09/2022 | 14/09/2022
TO-22-KTN-T102-01 | DISTRIBUTION TRANSFORMER - KILLOTERAN 110-KILLOTERAN 10-T102 | 2 | 2 | 2 | Reference | 15/09/2022 | 16/09/2022
TO-22-SLI-CAP1-02 | CAPACITOR/SVC/REACTOR - SLIGO 110-SLIGO 110-CAP1 | 7 | 5 | 5 | Scheduled | 16/09/2022 | 22/09/2022
TO-22-ARK-BOG-1-01 | 110kV FEEDER - ARKLOW 110-BANOGE 110-1 | 5 | 5 | 5 | Scheduled | 19/09/2022 | 23/09/2022
TO-22-AUG-CFM-2-01 | 110kV FEEDER - AUGHINISH 110-CASTLEFARM 110-2 | 1 | 1 | 1 | Scheduled | 19/09/2022 | 19/09/2022
TO-22-BOG-110SA1-02 | SECTIONALISING DISCONNECT - BANOGE 110-BANOGE 110-110SA1 | 5 | 5 | 5 | Scheduled | 19/09/2022 | 23/09/2022
TO-22-BOG-110SA2-01 | SECTIONALISING DISCONNECT - BANOGE 110-BANOGE 110-110SA2 | 5 | 5 | 5 | Scheduled | 19/09/2022 | 23/09/2022
TO-22-BOG-T122-01 | DISTRIBUTION TRANSFORMER - BANOGE 110-BANOGE 20-T122 | 5 | 5 | 5 | Reference (Tentative) | 19/09/2022 | 23/09/2022
TO-22-CFM-T102-01 | TSO CUSTOMER TRANSFORMER - CASTLEFARM 110-CASTLEFARM 10-T102 | 5 | 5 | 5 | Reference | 19/09/2022 | 23/09/2022
TO-22-CFM-T102-02 | TSO CUSTOMER TRANSFORMER - CASTLEFARM 110-CASTLEFARM 10-T102 | 1 | 1 | 1 | Reference | 19/09/2022 | 19/09/2022
TO-22-CLG-CDU-1-02 | 110kV FEEDER - CLOGHRAN 110-CORDUFF 110-1 | 12 | 10 | 10 | Scheduled | 19/09/2022 | 30/09/2022
TO-22-110 kV A2 @ CDU-03 | BUSBAR SECTION - CORDUFF 110-CORDUFF 110-110A2 | 5 | 5 | 5 | Scheduled | 19/09/2022 | 23/09/2022
TO-22-110 kV B2 @ CDU-03 | BUSBAR SECTION - CORDUFF 110-CORDUFF 110-110B2 | 5 | 5 | 5 | Scheduled | 19/09/2022 | 23/09/2022
TO-22-220 kV A1 @ DSN-01 | BUSBAR SECTION - DUNSTOWN 220-DUNSTOWN 220-220A1 | 5 | 5 | 5 | Scheduled | 19/09/2022 | 23/09/2022
TO-22-220 kV B1 @ DSN-01 | BUSBAR SECTION - DUNSTOWN 220-DUNSTOWN 220-220B1 | 5 | 5 | 5 | Scheduled | 19/09/2022 | 23/09/2022
TO-22-KTL-T131-02 | GENERATOR TRANSFORMER - KILTEEL 110-KILTEEL 33-T131 | 2 | 2 | 2 | Scheduled | 19/09/2022 | 20/09/2022
TO-22-110 kV A1 @ KPG-01 | BUSBAR SECTION - KILPADDOGE 110-KILPADDOGE 110-110A1 | 4 | 4 | 4 | Scheduled | 20/09/2022 | 23/09/2022
TO-22-110 kV A2 @ KPG-01 | BUSBAR SECTION - KILPADDOGE 110-KILPADDOGE 110-110A2 | 4 | 4 | 4 | Scheduled | 20/09/2022 | 23/09/2022
TO-22-KPG-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - KILPADDOGE 110-KILPADDOGE 110-110SA1-2CB | 4 | 4 | 4 | Scheduled | 20/09/2022 | 23/09/2022
TO-22-WEX-CAP2-01 | CAPACITOR/SVC/REACTOR - WEXFORD 110-WEXFORD 110-CAP2 | 4 | 4 | 4 | Scheduled | 20/09/2022 | 23/09/2022
TO-22-WEX-CAP4-01 | CAPACITOR/SVC/REACTOR - WEXFORD 110-WEXFORD 110-CAP4 | 4 | 4 | 4 | Scheduled | 20/09/2022 | 23/09/2022
TO-22-110 kV A1/A2 @ GI-01 | BUSBAR SECTION - GREAT ISLAND 110-GREAT ISLAND 110-110A1-A2 | 1 | 1 | 1 | Scheduled | 21/09/2022 | 21/09/2022
TO-22-110 kV B1/B2 @ GI-01 | BUSBAR SECTION - GREAT ISLAND 110-GREAT ISLAND 110-110B1-B2 | 1 | 1 | 1 | Scheduled | 21/09/2022 | 21/09/2022
TO-22-220 kV A1/A2 @ GI GIS-01 | BUSBAR SECTION - GREAT ISLAND GIS 220-GREAT ISLAND GIS 220-220A1-A2 | 1 | 1 | 1 | Scheduled | 21/09/2022 | 21/09/2022
TO-22-220 kV B1/B2 @ GI GIS-01 | BUSBAR SECTION - GREAT ISLAND GIS 220-GREAT ISLAND GIS 220-220B1-B2 | 1 | 1 | 1 | Scheduled | 21/09/2022 | 21/09/2022
TO-22-CRO-T122-01 | DISTRIBUTION TRANSFORMER - COOLROE 110-COOLROE 20-T122 | 2 | 2 | 2 | Reference | 22/09/2022 | 23/09/2022
TO-22-AUG-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - AUGHINISH 110-AUGHINISH 110-110SA1-2CB | 1 | 1 | 1 | Scheduled | 23/09/2022 | 23/09/2022
TO-22-BK-MOY-1-02 | 110kV FEEDER - BELLACORICK 110-MOY 110-1 | 1 | 1 | 1 | Scheduled | 23/09/2022 | 23/09/2022
TO-22-DER-T1/T2-01 | GENERATOR TRANSFORMER - DERRYIRON 110-RHODE 110-T1/T2 | 11 | 7 | 7 | Scheduled | 23/09/2022 | 03/10/2022
TO-22-MOY-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - MOY 110-MOY 110-110SA1-2CB | 1 | 1 | 1 | Scheduled | 23/09/2022 | 23/09/2022
TO-22-MOY-CAP2-01 | CAPACITOR/SVC/REACTOR - MOY 110-MOY 110-CAP2 | 1 | 1 | 1 | Scheduled | 23/09/2022 | 23/09/2022
TO-22-MOY-TAW-2-02 | 110kV FEEDER - MOY 110-TAWNAGHMORE 110-2 | 1 | 1 | 1 | Scheduled | 23/09/2022 | 23/09/2022
TO-22-ARV-COS-1-01 | 110kV FEEDER - ARVA 110-CARRICK ON SHANNON 110-1 | 5 | 5 | 5 | Scheduled | 26/09/2022 | 30/09/2022
TO-22-ATY-110SA1-01 | SECTIONALISING DISCONNECT - ATHY 110-ATHY 110-110SA1 | 5 | 5 | 5 | Proposed | 26/09/2022 | 30/09/2022
TO-22-ATY-110SA2-02 | SECTIONALISING DISCONNECT - ATHY 110-ATHY 110-110SA2 | 5 | 5 | 5 | Proposed | 26/09/2022 | 30/09/2022
TO-22-ATY-T101-02 | DISTRIBUTION TRANSFORMER - ATHY 110-ATHY 10-T101 | 5 | 5 | 5 | Reference (Proposed) | 26/09/2022 | 30/09/2022
TO-22-AUG-SK-4-01 | 110kV FEEDER - AUGHINISH 110-SEALROCK 110-4 | 5 | 5 | 5 | Scheduled | 26/09/2022 | 30/09/2022
TO-22-BDA-T102-01 | TSO CUSTOMER TRANSFORMER - BARODA 110-BARODA 10-T102 | 2 | 2 | 2 | Proposed | 26/09/2022 | 27/09/2022
TO-22-CLW-110SA1-06 | SECTIONALISING DISCONNECT - CARLOW 110-CARLOW 110-110SA1 | 5 | 5 | 5 | Proposed | 26/09/2022 | 30/09/2022
TO-22-CLW-110SA2-04 | SECTIONALISING DISCONNECT - CARLOW 110-CARLOW 110-110SA2 | 5 | 5 | 5 | Proposed | 26/09/2022 | 30/09/2022
TO-22-CLW-KLS-1-06 | 110kV FEEDER - CARLOW 110-KELLIS 110-1 | 5 | 5 | 5 | Proposed | 26/09/2022 | 30/09/2022
TO-22-CLW-T141-04 | DISTRIBUTION TRANSFORMER - CARLOW 110-CARLOW 38-T141 | 5 | 5 | 5 | Reference (Proposed) | 26/09/2022 | 30/09/2022
TO-22-220 kV A1 @ CKM GIS-03 | BUSBAR SECTION - CARRICKMINES GIS 220-CARRICKMINES GIS 220-220A1 | 5 | 5 | 5 | Proposed | 26/09/2022 | 30/09/2022
TO-22-220 kV A3 @ CKM GIS-04 | BUSBAR SECTION - CARRICKMINES GIS 220-CARRICKMINES GIS 220-220A3 | 5 | 5 | 5 | Proposed | 26/09/2022 | 30/09/2022
TO-22-CKM GIS-220SA1-3CB-01 | COUPLER/SECTIONALISING CB - CARRICKMINES GIS 220-CARRICKMINES GIS 220-22SA1-3CB | 13 | 10 | 10 | Proposed | 26/09/2022 | 08/10/2022
TO-22-CSH-DLT-1-02 | 110kV FEEDER - CASHLA 110-DALTON 110-1 | 5 | 5 | 5 | Proposed | 26/09/2022 | 30/09/2022
TO-22-110 kV A2 @ CLG-03 | BUSBAR SECTION - CLOGHRAN 110-CLOGHRAN 110-110A2 | 5 | 5 | 5 | Scheduled | 26/09/2022 | 30/09/2022
TO-22-110 kV B2 @ CLG-04 | BUSBAR SECTION - CLOGHRAN 110-CLOGHRAN 110-110B2 | 5 | 5 | 5 | Scheduled | 26/09/2022 | 30/09/2022
TO-22-CDY-GRV-1-02 | 110kV FEEDER - CORDERRY 110-GARVAGH 110-1 | 5 | 5 | 5 | Proposed | 26/09/2022 | 30/09/2022
TO-22-CDU-RYB GIS-1-01 | 110kV FEEDER - CORDUFF 110-RYEBROOK GIS 110-1 | 12 | 10 | 10 | Proposed | 26/09/2022 | 07/10/2022
TO-22-COW-RAF-1-02 | 110kV FEEDER - COW CROSS 110-RAFFEEN 110-1 | 5 | 5 | 5 | Proposed | 26/09/2022 | 30/09/2022
TO-22-DLT-110SA1-03 | SECTIONALISING DISCONNECT - DALTON 110-DALTON 110-110SA1 | 4 | 4 | 4 | Proposed | 26/09/2022 | 29/09/2022
TO-22-DLT-110SA2-02 | SECTIONALISING DISCONNECT - DALTON 110-DALTON 110-110SA2 | 4 | 4 | 4 | Proposed | 26/09/2022 | 29/09/2022
TO-22-DLT-T142-02 | DISTRIBUTION TRANSFORMER - DALTON 110-DALTON 38-T142 | 4 | 4 | 4 | Reference (Proposed) | 26/09/2022 | 29/09/2022
TO-22-GRV-110K1-02 | COUPLER/SECTIONALISING CB - GARVAGH 110-GARVAGH 110-110K1 | 5 | 5 | 5 | Proposed | 26/09/2022 | 30/09/2022
TO-22-GRV-T121-03 | GENERATOR TRANSFORMER - GARVAGH 110-GARVAGH 20-T121 | 5 | 5 | 5 | Proposed | 26/09/2022 | 30/09/2022
TO-22-GRV-T141-02 | DISTRIBUTION TRANSFORMER - GARVAGH 110-GARVAGH 20-T141 | 5 | 5 | 5 | Reference (Proposed) | 26/09/2022 | 30/09/2022
TO-22-KKY-T141-01 | DISTRIBUTION TRANSFORMER - KILKENNY 110-KILKENNY 38-T141 | 2 | 2 | 2 | Reference (Proposed) | 26/09/2022 | 27/09/2022
TO-22-KNY-UGL-1-01 | 110kV FEEDER - KNOCKRANNY-UGGOOL 110-1 | 12 | 10 | 10 | Proposed | 26/09/2022 | 07/10/2022
TO-22-400 kV A3 @ MP GIS-01 | BUSBAR SECTION - MONEYPOINT GIS 400-MONEYPOINT GIS 400-400A3 | 5 | 5 | 5 | Scheduled | 26/09/2022 | 30/09/2022
TO-22-400 kV B3 @ MP GIS-01 | BUSBAR SECTION - MONEYPOINT GIS 400-MONEYPOINT GIS 400-400B3 | 5 | 5 | 5 | Scheduled | 26/09/2022 | 30/09/2022
TO-22-MP GIS-T4003-01 | GENERATOR TRANSFORMER - MONEYPOINT GIS 400-MONEYPOINT GIS G3-T4003 | 18 | 14 | 14 | Proposed | 26/09/2022 | 13/10/2022
TO-22-PB-R2001-03 | CAPACITOR/SVC/REACTOR - POOLBEG 220-POOLBEG 220-R2001 | 5 | 5 | 5 | Proposed | 26/09/2022 | 30/09/2022
TO-22-110 kV B2 @ RYB GIS-01 | BUSBAR SECTION - RYEBROOK GIS 110-RYEBROOK GIS 110-110B2 | 5 | 5 | 5 | Scheduled | 26/09/2022 | 30/09/2022
TO-22-110 kV B4 @ RYB GIS-01 | BUSBAR SECTION - RYEBROOK GIS 110-RYEBROOK GIS 110-110B4 | 5 | 5 | 5 | Scheduled | 26/09/2022 | 30/09/2022
TO-22-RYB GIS-110SB2-4CB-02 | COUPLER/SECTIONALISING CB - RYEBROOK GIS 110-RYEBROOK GIS 110-110SB2-4CB | 5 | 5 | 5 | Scheduled | 26/09/2022 | 30/09/2022
TO-22-SK-T104-01 | GENERATOR TRANSFORMER - SEALROCK 110-SEALROCK G4-T104 | 5 | 5 | 5 | Scheduled | 26/09/2022 | 30/09/2022
TO-22-UGL-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - UGGOOL 110-UGGOOL 110-110SA1-2CB | 12 | 10 | 10 | Proposed | 26/09/2022 | 07/10/2022
TO-22-UGL-T131-01 | GENERATOR TRANSFORMER - UGGOOL 110-UGGOOL 33-T131 | 12 | 10 | 10 | Proposed | 26/09/2022 | 07/10/2022
TO-22-UGL-T132-01 | GENERATOR TRANSFORMER - UGGOOL 110-UGGOOL 33-T132 | 12 | 10 | 10 | Proposed | 26/09/2022 | 07/10/2022
TO-22-UGL-T134-01 | GENERATOR TRANSFORMER - UGGOOL 110-UGGOOL 33-T134 | 12 | 10 | 10 | Proposed | 26/09/2022 | 07/10/2022
TO-22-WOO-T4204-01 | TRANSFORMER - WOODLAND 400-WOODLAND 220-T4204 | 12 | 10 | 10 | Proposed | 26/09/2022 | 07/10/2022
TO-22-220 kV A1 @ BVK-01 | BUSBAR SECTION - BALLYVOUSKILL 220-BALLYVOUSKILL 220-220A1 | 4 | 4 | 4 | Scheduled | 27/09/2022 | 30/09/2022
TO-22-220 kV A2 @ BVK-01 | BUSBAR SECTION - BALLYVOUSKILL 220-BALLYVOUSKILL 220-220A2 | 4 | 4 | 4 | Scheduled | 27/09/2022 | 30/09/2022
TO-22-BVK-220SA1-2CB-01 | COUPLER/SECTIONALISING CB - BALLYVOUSKILL 220-BALLYVOUSKILL 220-220SA1-2CB | 4 | 4 | 4 | Scheduled | 27/09/2022 | 30/09/2022
TO-22-COS-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - CARRICK ON SHANNON 110-CARRICK ON SHANNON 110-110SA1-2CB | 2 | 2 | 2 | Proposed | 27/09/2022 | 28/09/2022
TO-22-110 kV A1 @ CDU-03 | BUSBAR SECTION - CORDUFF 110-CORDUFF 110-110A1 | 4 | 4 | 4 | Proposed | 27/09/2022 | 30/09/2022
TO-22-110 kV B1 @ CDU-03 | BUSBAR SECTION - CORDUFF 110-CORDUFF 110-110B1 | 4 | 4 | 4 | Proposed | 27/09/2022 | 30/09/2022
TO-22-DRM-LET-1-02 | 110kV FEEDER - DRUMKEEN 110-LETTERKENNY 110-1 | 1 | 1 | 1 | Proposed | 27/09/2022 | 27/09/2022
TO-22-110 kV A1 @ KPG-02 | BUSBAR SECTION - KILPADDOGE 110-KILPADDOGE 110-110A1 | 4 | 4 | 4 | Scheduled | 27/09/2022 | 30/09/2022
TO-22-110 kV A3 @ KPG-01 | BUSBAR SECTION - KILPADDOGE 110-KILPADDOGE 110-110A3 | 4 | 4 | 4 | Scheduled | 27/09/2022 | 30/09/2022
TO-22-KPG-110SA1-3CB-01 | COUPLER/SECTIONALISING CB - KILPADDOGE 110-KILPADDOGE 110-110SA1-3CB | 4 | 4 | 4 | Scheduled | 27/09/2022 | 30/09/2022
TO-22-220 kV A3 @ KPG-01 | BUSBAR SECTION - KILPADDOGE 220-KILPADDOGE 220-220A3 | 4 | 4 | 4 | Scheduled | 27/09/2022 | 30/09/2022
TO-22-220 kV B3 @ KPG-01 | BUSBAR SECTION - KILPADDOGE 220-KILPADDOGE 220-220B3 | 4 | 4 | 4 | Scheduled | 27/09/2022 | 30/09/2022
TO-22-KPG-220K3-01 | COUPLER/SECTIONALISING CB - KILPADDOGE 220-KILPADDOGE 220-220K3 | 4 | 4 | 4 | Scheduled | 27/09/2022 | 30/09/2022
TO-22-MID-T102-01 | DISTRIBUTION TRANSFORMER - MIDLETON 110-MIDLETON 10-T102 | 2 | 2 | 2 | Reference (Proposed) | 27/09/2022 | 28/09/2022
TO-22-SOR-T124-01 | DISTRIBUTION TRANSFORMER - SORNE HILL 110-SORNE HILL 20-T124 | 1 | 1 | 1 | Reference | 27/09/2022 | 27/09/2022
TO-22-ARK-BEG-1-03 | 110kV FEEDER - ARKLOW 110-BALLYBEG 110-1 | 31 | 23 | 23 | Tentative | 28/09/2022 | 28/10/2022
TO-22-BRT-T224-01 | TSO CUSTOMER TRANSFORMER - BRACETOWN 220-BRACETOWN 20-T224 | 1 | 1 | 1 | Proposed | 28/09/2022 | 28/09/2022
TO-22-220 kV A1/A2 @ ISH-01 | BUSBAR SECTION - IRISHTOWN 220-IRISHTOWN 220-220A1-A2 | 1 | 1 | 1 | Scheduled | 28/09/2022 | 28/09/2022
TO-22-220 kV B1/B2 @ ISH-01 | BUSBAR SECTION - IRISHTOWN 220-IRISHTOWN 220-220B1-B2 | 1 | 1 | 1 | Scheduled | 28/09/2022 | 28/09/2022
TO-22-LET-TIV-1-03 | 110kV FEEDER - LETTERKENNY 110-TIEVEBRACK 110-1 | 3 | 3 | 3 | Proposed | 28/09/2022 | 30/09/2022
TO-22-110 kV B1 @ AA GIS-02 | BUSBAR SECTION - ARDNACRUSHA GIS 110-ARDNACRUSHA GIS 110-110B1 | 1 | 1 | 1 | Proposed | 29/09/2022 | 29/09/2022
TO-22-110 kV B2 @ AA GIS-01 | BUSBAR SECTION - ARDNACRUSHA GIS 110-ARDNACRUSHA GIS 110-110B2 | 1 | 1 | 1 | Proposed | 29/09/2022 | 29/09/2022
TO-22-AA GIS-110K2-03 | COUPLER/SECTIONALISING CB - ARDNACRUSHA GIS 110-ARDNACRUSHA GIS 110-110K2 | 1 | 1 | 1 | Proposed | 29/09/2022 | 29/09/2022
TO-22-AA GIS-110SB1-2CB-02 | COUPLER/SECTIONALISING CB - ARDNACRUSHA GIS 110-ARDNACRUSHA GIS 110-110SB1-2CB | 1 | 1 | 1 | Proposed | 29/09/2022 | 29/09/2022
TO-22-AA GIS-ENN-1-02 | 110kV FEEDER - ARDNACRUSHA GIS 110-ENNIS 110-1 | 1 | 1 | 1 | Proposed | 29/09/2022 | 29/09/2022
TO-22-SNU-110SB1-2CB-02 | COUPLER/SECTIONALISING CB - SNUGBOROUGH 110-SNUGBOROUGH 110-110SB1-2CB | 1 | 1 | 1 | Scheduled | 29/09/2022 | 29/09/2022
TO-22-220 kV B1 @ TH-01 | BUSBAR SECTION - TURLOUGH HILL 220-TURLOUGH HILL 220-220B1 | 1 | 1 | 1 | Scheduled | 29/09/2022 | 29/09/2022
TO-22-TH-T2001/2-02 | GENERATOR TRANSFORMER - TURLOUGH HILL 220-TURLOUGH HILL G1-T2001/2 | 1 | 1 | 1 | Scheduled | 29/09/2022 | 29/09/2022
TO-22-CRO-IA-1-03 | 110kV FEEDER - COOLROE 110-INNISCARRA 110-1 | 1 | 1 | 1 | Proposed | 30/09/2022 | 30/09/2022
TO-22-IA-MAC-1-02 | 110kV FEEDER - INNISCARRA 110-MACROOM 110-1 | 1 | 1 | 1 | Proposed | 30/09/2022 | 30/09/2022
TO-22-IA-T101-02 | GENERATOR TRANSFORMER - INNISCARRA 110-INNISCARRA G1-T101 | 1 | 1 | 1 | Proposed | 30/09/2022 | 30/09/2022
TO-22-CAH-DOO-1-03 | 110kV FEEDER - CAHIR 110-DOON 110-1 | 2 | 0 | 0 | Proposed | 01/10/2022 | 02/10/2022
TO-22-KBY-KRA-1-05 | 110kV FEEDER - KILBARRY 110-KNOCKRAHA 110-1 | 2 | 0 | 0 | Proposed | 01/10/2022 | 02/10/2022
TO-22-BVK-GRO-1-02 | 110kV FEEDER - BALLYVOUSKILL 110-GARROW 110-1 | 5 | 5 | 5 | Scheduled | 03/10/2022 | 07/10/2022
TO-22-BAL-CDU-1-02 | 110kV FEEDER - BALTRASNA 110-CORDUFF 110-1 | 12 | 10 | 10 | Proposed | 03/10/2022 | 14/10/2022
TO-22-BAL-T122-01 | DISTRIBUTION TRANSFORMER - BALTRASNA 110-BALTRASNA 20-T122 | 5 | 5 | 5 | Reference | 03/10/2022 | 07/10/2022
TO-22-CD-KBY-1-07 | 110kV FEEDER - CARRIGADROHID 110-KILBARRY 110-1 | 5 | 5 | 5 | Proposed | 03/10/2022 | 07/10/2022
TO-22-CF-SRA-2-02 | 110kV FEEDER - CATHALEENS FALL 110-SRANANAGH 110-2 | 5 | 5 | 5 | Proposed | 03/10/2022 | 07/10/2022
TO-22-CHA-GLE-1-02 | 110kV FEEDER - CHARLEVILLE 110-GLENLARA 110-1 | 12 | 10 | 10 | Proposed | 03/10/2022 | 14/10/2022
TO-22-CLN-110SA1-01 | SECTIONALISING DISCONNECT - CLOON 110-CLOON 110-110SA1 | 3 | 3 | 3 | Proposed | 03/10/2022 | 05/10/2022
TO-22-CLN-110SA2-01 | SECTIONALISING DISCONNECT - CLOON 110-CLOON 110-110SA2 | 3 | 3 | 3 | Proposed | 03/10/2022 | 05/10/2022
TO-22-CLN-LA-1-01 | 110kV FEEDER - CLOON 110-LANESBORO 110-1 | 3 | 3 | 3 | Scheduled | 03/10/2022 | 05/10/2022
TO-22-CLN-T142-01 | DISTRIBUTION TRANSFORMER - CLOON 110-CLOON 38-T142 | 3 | 3 | 3 | Reference (Proposed) | 03/10/2022 | 05/10/2022
TO-22-INC-PB-1-04 | 220kV FEEDER - INCHICORE 220-POOLBEG 220-1 | 19 | 15 | 15 | Proposed | 03/10/2022 | 21/10/2022
TO-22-KHL-THU-1-03 | 110kV FEEDER - KILL HILL 110-THURLES 110-1 | 12 | 10 | 10 | Proposed | 03/10/2022 | 14/10/2022
TO-22-220 kV A1 @ KPG-01 | BUSBAR SECTION - KILPADDOGE 220-KILPADDOGE 220-220A1 | 5 | 5 | 5 | Scheduled | 03/10/2022 | 07/10/2022
TO-22-220 kV B1 @ KPG-01 | BUSBAR SECTION - KILPADDOGE 220-KILPADDOGE 220-220B1 | 5 | 5 | 5 | Scheduled | 03/10/2022 | 07/10/2022
TO-22-KPG-KNR-1-01 | 220kV FEEDER - KILPADDOGE 220-KNOCKANURE 220-1 | 5 | 5 | 5 | Scheduled | 03/10/2022 | 07/10/2022
TO-22-PB-TF3-02 | TRANSFORMER - POOLBEG 220-POOLBEG 110-TF3 | 30 | 21 | 21 | Reference (Proposed) | 03/10/2022 | 01/11/2022
TO-22-PRO-TB-1-03 | 220kV FEEDER - PROSPECT 220-TARBERT 220-1 | 10 | 8 | 8 | Scheduled | 03/10/2022 | 12/10/2022
TO-22-RAF-T2101-01 | TRANSFORMER - RAFFEEN 220-RAFFEEN 110-T2101 | 5 | 5 | 5 | Proposed | 03/10/2022 | 07/10/2022
TO-22-ARV-110K1-2-02 | COUPLER/SECTIONALISING CB - ARVA 110-ARVA 110-110K1-2 | 2 | 2 | 2 | Proposed | 04/10/2022 | 05/10/2022
TO-22-BLC-110K3-01 | COUPLER/SECTIONALISING CB - BELCAMP 110-BELCAMP 110-110K3 | 3 | 3 | 3 | Scheduled | 04/10/2022 | 06/10/2022
TO-22-INC-T2102-01 | TRANSFORMER - INCHICORE 220-INCHICORE 110-T2102 | 2 | 2 | 2 | Reference (Proposed) | 04/10/2022 | 05/10/2022
TO-22-KLN-NEN-1-03 | 110kV FEEDER - KILLONAN 110-NENAGH 110-1 | 2 | 2 | 2 | Reference | 04/10/2022 | 05/10/2022
TO-22-NEN-T141-02 | DISTRIBUTION TRANSFORMER - NENAGH 110-NENAGH 38-T141 | 2 | 2 | 2 | Reference | 04/10/2022 | 05/10/2022
TO-22-220 kV A1 @ TB-03 | BUSBAR SECTION - TARBERT 220-TARBERT 220-220A1 | 14 | 10 | 10 | Scheduled | 04/10/2022 | 17/10/2022
TO-22-220 kV B1 @ TB-03 | BUSBAR SECTION - TARBERT 220-TARBERT 220-220B1 | 14 | 10 | 10 | Scheduled | 04/10/2022 | 17/10/2022
TO-22-BUT-KTN-1-02 | 110kV FEEDER - BUTLERSTOWN 110-KILLOTERAN 110-1 | 3 | 3 | 3 | Proposed | 05/10/2022 | 07/10/2022
TO-22-CKM GIS-T2104-01 | TRANSFORMER - CARRICKMINES GIS 220-CARRICKMINES GIS 110-T2104 | 2 | 2 | 2 | Reference (Proposed) | 05/10/2022 | 06/10/2022
TO-22-110 kV B1 @ CF-03 | BUSBAR SECTION - CATHALEENS FALL 110-CATHALEENS FALL 110-110B1 | 1 | 1 | 1 | Proposed | 05/10/2022 | 05/10/2022
TO-22-CL-T101-05 | GENERATOR TRANSFORMER - CLIFF 110-CLIFF G1-T101 | 1 | 1 | 1 | Proposed | 05/10/2022 | 05/10/2022
TO-22-CL-T102-05 | GENERATOR TRANSFORMER - CLIFF 110-CLIFF G2-T102 | 1 | 1 | 1 | Proposed | 05/10/2022 | 05/10/2022
TO-22-KTN-110SA1-01 | SECTIONALISING DISCONNECT - KILLOTERAN 110-KILLOTERAN 110-110SA1 | 3 | 3 | 3 | Proposed | 05/10/2022 | 07/10/2022
TO-22-KTN-110SA2-01 | SECTIONALISING DISCONNECT - KILLOTERAN 110-KILLOTERAN 110-110SA2 | 3 | 3 | 3 | Proposed | 05/10/2022 | 07/10/2022
TO-22-KTN-T101-01 | DISTRIBUTION TRANSFORMER - KILLOTERAN 110-KILLOTERAN 10-T101 | 3 | 3 | 3 | Reference (Proposed) | 05/10/2022 | 07/10/2022
TO-22-INC-T2106-01 | TRANSFORMER - INCHICORE 220-INCHICORE 110-T2106 | 2 | 2 | 2 | Reference (Proposed) | 06/10/2022 | 07/10/2022
TO-22-KRA-RAF-1-01 | 220kV FEEDER - KNOCKRAHA 220-RAFFEEN 220-1 | 12 | 8 | 8 | Proposed | 07/10/2022 | 18/10/2022
TO-22-AD-GGO-1-02 | 220kV FEEDER - AGHADA 220-GLANAGOW 220-1 | 5 | 5 | 5 | Proposed | 10/10/2022 | 14/10/2022
TO-22-ARV-NAV-1-01 | 110kV FEEDER - ARVA 110-NAVAN 110-1 | 9 | 7 | 7 | Proposed | 10/10/2022 | 18/10/2022
TO-22-ATH-SH-1-01 | 110kV FEEDER - ATHLONE 110-SHANNONBRIDGE 110-1 | 12 | 10 | 10 | Proposed | 10/10/2022 | 21/10/2022
TO-22-BVK-R2001-01 | CAPACITOR/SVC/REACTOR - BALLYVOUSKILL 220-BALLYVOUSKILL 220-R2001 | 3 | 3 | 3 | Scheduled | 10/10/2022 | 12/10/2022
TO-22-BK-110SA1-03 | SECTIONALISING DISCONNECT - BELLACORICK 110-BELLACORICK 110-110SA1 | 5 | 5 | 5 | Scheduled | 10/10/2022 | 14/10/2022
TO-22-BK-110SA2-02 | SECTIONALISING DISCONNECT - BELLACORICK 110-BELLACORICK 110-110SA2 | 5 | 5 | 5 | Scheduled | 10/10/2022 | 14/10/2022
TO-22-BK-CBR-1-05 | 110kV FEEDER - BELLACORICK 110-CASTLEBAR 110-1 | 5 | 5 | 5 | Scheduled | 10/10/2022 | 14/10/2022
TO-22-BK-SKY-1-01 | 110kV FEEDER - BELLACORICK 110-SRAHNAKILLY 110-1 | 5 | 5 | 5 | Scheduled | 10/10/2022 | 14/10/2022
TO-22-BK-T122-01 | DISTRIBUTION TRANSFORMER - BELLACORICK 110-BELLACORICK 20-T122 | 5 | 5 | 5 | Reference (Proposed) | 10/10/2022 | 14/10/2022
TO-22-110 kV A2 @ CLG-04 | BUSBAR SECTION - CLOGHRAN 110-CLOGHRAN 110-110A2 | 5 | 5 | 5 | Proposed | 10/10/2022 | 14/10/2022
TO-22-110 kV B2 @ CLG-05 | BUSBAR SECTION - CLOGHRAN 110-CLOGHRAN 110-110B2 | 5 | 5 | 5 | Proposed | 10/10/2022 | 14/10/2022
TO-22-CLG-T122-04 | TSO CUSTOMER TRANSFORMER - CLOGHRAN 110-CLOGHRAN 20-T122 | 5 | 5 | 5 | Proposed | 10/10/2022 | 14/10/2022
TO-22-110 kV A1 @ CDU-02 | BUSBAR SECTION - CORDUFF 110-CORDUFF 110-110A1 | 5 | 5 | 5 | Scheduled | 10/10/2022 | 14/10/2022
TO-22-110 kV A2 @ CDU-04 | BUSBAR SECTION - CORDUFF 110-CORDUFF 110-110A2 | 5 | 5 | 5 | Scheduled | 10/10/2022 | 14/10/2022
TO-22-110 kV B1 @ CDU-02 | BUSBAR SECTION - CORDUFF 110-CORDUFF 110-110B1 | 5 | 5 | 5 | Scheduled | 10/10/2022 | 14/10/2022
TO-22-110 kV B2 @ CDU-04 | BUSBAR SECTION - CORDUFF 110-CORDUFF 110-110B2 | 5 | 5 | 5 | Scheduled | 10/10/2022 | 14/10/2022
TO-22-CDU-110K1-2-01 | COUPLER/SECTIONALISING CB - CORDUFF 110-CORDUFF 110-110K1-2 | 12 | 10 | 10 | Scheduled | 10/10/2022 | 21/10/2022
TO-22-DRY-T141-03 | DISTRIBUTION TRANSFORMER - DRYBRIDGE 110-DRYBRIDGE 38-T141 | 5 | 5 | 5 | Reference (Proposed) | 10/10/2022 | 14/10/2022
TO-22-220 kV A2 @ DSN-02 | BUSBAR SECTION - DUNSTOWN 220-DUNSTOWN 220-220A2 | 5 | 5 | 5 | Proposed | 10/10/2022 | 14/10/2022
TO-22-220 kV B2 @ DSN-02 | BUSBAR SECTION - DUNSTOWN 220-DUNSTOWN 220-220B2 | 5 | 5 | 5 | Proposed | 10/10/2022 | 14/10/2022
TO-22-400 kV A2 @ DSN-02 | BUSBAR SECTION - DUNSTOWN 400-DUNSTOWN 400-400A2 | 5 | 5 | 5 | Proposed | 10/10/2022 | 14/10/2022
TO-22-400 kV B2 @ DSN-02 | BUSBAR SECTION - DUNSTOWN 400-DUNSTOWN 400-400B2 | 5 | 5 | 5 | Proposed | 10/10/2022 | 14/10/2022
TO-22-DSN-T4202-01 | TRANSFORMER - DUNSTOWN 400-DUNSTOWN 220-T4202 | 26 | 19 | 19 | Proposed | 10/10/2022 | 04/11/2022
TO-22-GGO-T2001-01 | GENERATOR TRANSFORMER - GLANAGOW 220-GLANAGOW G1-T2001 | 5 | 5 | 5 | Proposed | 10/10/2022 | 14/10/2022
TO-22-MAY-T2101-01 | TRANSFORMER - MAYNOOTH 220-MAYNOOTH 110-T2101 | 3 | 3 | 3 | Scheduled | 10/10/2022 | 12/10/2022
TO-22-RAF-TBG-2-03 | 110kV FEEDER - RAFFEEN 110-TRABEG 110-2 | 12 | 10 | 10 | Proposed | 10/10/2022 | 21/10/2022
TO-22-SKY-110SA1-01 | SECTIONALISING DISCONNECT - SRAHNAKILLY 110-SRAHNAKILLY 110-110SA1 | 5 | 5 | 5 | Scheduled | 10/10/2022 | 14/10/2022
TO-22-SKY-110SA2-01 | SECTIONALISING DISCONNECT - SRAHNAKILLY 110-SRAHNAKILLY 110-110SA2 | 5 | 5 | 5 | Scheduled | 10/10/2022 | 14/10/2022
TO-22-SKY-T131-02 | GENERATOR TRANSFORMER - SRAHNAKILLY 110-SRAHNAKILLY 33-T131 | 5 | 5 | 5 | Scheduled | 10/10/2022 | 14/10/2022
TO-22-THU-110SA1-2CB-04 | COUPLER/SECTIONALISING CB - THURLES 110-THURLES 110-110SA1-2CB | 5 | 5 | 5 | Proposed | 10/10/2022 | 14/10/2022
TO-22-THU-CAP1-02 | CAPACITOR/SVC/REACTOR - THURLES 110-THURLES 110-CAP1 | 5 | 5 | 5 | Proposed | 10/10/2022 | 14/10/2022
TO-22-THU-T141-01 | DISTRIBUTION TRANSFORMER - THURLES 110-THURLES 38-T141 | 5 | 5 | 5 | Reference (Proposed) | 10/10/2022 | 14/10/2022
TO-22-BLC-110SA1-3CB-01 | COUPLER/SECTIONALISING CB - BELCAMP 110-BELCAMP 110-110SA1-3CB | 1 | 1 | 1 | Scheduled | 11/10/2022 | 11/10/2022
TO-22-BRT-CLE-4-01 | 220kV FEEDER - BRACETOWN 220-CLONEE 220-4 | 2 | 2 | 2 | Proposed | 11/10/2022 | 12/10/2022
TO-22-BLC-110SB1-3CB-01 | COUPLER/SECTIONALISING CB - BELCAMP 110-BELCAMP 110-110SB1-3CB | 1 | 1 | 1 | Scheduled | 12/10/2022 | 12/10/2022
TO-22-KRA-WOH-1-01 | 110kV FEEDER - KNOCKRAHA 110-WOODHOUSE 110-1 | 3 | 3 | 3 | Scheduled | 12/10/2022 | 14/10/2022
TO-22-WOH-110SA1-02 | SECTIONALISING DISCONNECT - WOODHOUSE 110-WOODHOUSE 110-110SA1 | 3 | 3 | 3 | Scheduled | 12/10/2022 | 14/10/2022
TO-22-WOH-110SA2-01 | SECTIONALISING DISCONNECT - WOODHOUSE 110-WOODHOUSE 110-110SA2 | 3 | 3 | 3 | Scheduled | 12/10/2022 | 14/10/2022
TO-22-WOH-T122-03 | GENERATOR TRANSFORMER - WOODHOUSE 110-WOODHOUSE 20-T122 | 3 | 3 | 3 | Scheduled | 12/10/2022 | 14/10/2022
TO-22-CLH-TRL-1-02 | 110kV FEEDER - CLAHANE 110-TRALEE 110-1 | 9 | 7 | 7 | Proposed | 13/10/2022 | 21/10/2022
TO-22-ARI-T121-01 | DISTRIBUTION TRANSFORMER - ARIGNA 110-ARIGNA 20-T121 | 12 | 10 | 10 | Reference | 17/10/2022 | 28/10/2022
TO-22-ARI,T-ARI-1-01 | 110kV FEEDER - ARIGNA tee-ARIGNA 110-1 | 12 | 10 | 10 | Scheduled | 17/10/2022 | 28/10/2022
TO-22-ARI,T-COS-1-01 | 110kV FEEDER - ARIGNA tee-CARRICK ON SHANNON 110-1 | 12 | 10 | 10 | Scheduled | 17/10/2022 | 28/10/2022
TO-22-ARI,T-CDY-1-02 | 110kV FEEDER - ARIGNA tee-CORDERRY 110-1 | 12 | 10 | 10 | Scheduled | 17/10/2022 | 28/10/2022
TO-22-BDA-NEW-1-01 | 110kV FEEDER - BARODA 110-NEWBRIDGE 110-1 | 5 | 5 | 5 | Scheduled | 17/10/2022 | 21/10/2022
TO-22-BUT-CUL-1-01 | 110kV FEEDER - BUTLERSTOWN 110-CULLENAGH 110-1 | 5 | 5 | 5 | Scheduled | 17/10/2022 | 21/10/2022
TO-22-110 kV A2 @ CLG-05 | BUSBAR SECTION - CLOGHRAN 110-CLOGHRAN 110-110A2 | 5 | 5 | 5 | Proposed | 17/10/2022 | 21/10/2022
TO-22-110 kV B2 @ CLG-06 | BUSBAR SECTION - CLOGHRAN 110-CLOGHRAN 110-110B2 | 5 | 5 | 5 | Proposed | 17/10/2022 | 21/10/2022
TO-22-CLG-T124-01 | TSO CUSTOMER TRANSFORMER - CLOGHRAN 110-CLOGHRAN 20-T124 | 5 | 5 | 5 | Proposed | 17/10/2022 | 21/10/2022
TO-22-CRA-LWD-1-01 | 110kV FEEDER - CRANE 110-LODGEWOOD 110-1 | 5 | 5 | 5 | Proposed | 17/10/2022 | 21/10/2022
TO-22-CUL-KRA-1-01 | 220kV FEEDER - CULLENAGH 220-KNOCKRAHA 220-1 | 5 | 5 | 5 | Scheduled | 17/10/2022 | 21/10/2022
TO-22-DFR,T-KIN-1-05 | 110kV FEEDER - DUNFIRTH tee-KINNEGAD 110-1 | 5 | 5 | 5 | Proposed | 17/10/2022 | 21/10/2022
TO-22-FIN GIS-T2101-01 | TRANSFORMER - FINGLAS 220-FINGLAS GIS 110-T2101 | 19 | 14 | 14 | Proposed | 17/10/2022 | 04/11/2022
TO-22-KLN-KPG-1-01 | 220kV FEEDER - KILLONAN 220-KILPADDOGE 220-1 | 5 | 5 | 5 | Proposed | 17/10/2022 | 21/10/2022
TO-22-KIN-110SA1-2CB-02 | COUPLER/SECTIONALISING CB - KINNEGAD 110-KINNEGAD 110-110SA1-2CB | 5 | 5 | 5 | Proposed | 17/10/2022 | 21/10/2022
TO-22-KIN-T102-01 | TSO CUSTOMER TRANSFORMER - KINNEGAD 110-KINNEGAD 10-T102 | 5 | 5 | 5 | Proposed | 17/10/2022 | 21/10/2022
TO-22-LOU-WOO-1-02 | 220kV FEEDER - LOUTH 220-WOODLAND 220-1 | 10 | 8 | 8 | Scheduled | 17/10/2022 | 26/10/2022
TO-22-PB-SHL-1-01 | 220kV FEEDER - POOLBEG 220-SHELLYBANKS 220-1 | 19 | 14 | 14 | Proposed | 17/10/2022 | 04/11/2022
TO-22-SHL-D1/CB2-01 | COUPLER/SECTIONALISING CB - SHELLYBANKS 220-SHELLYBANKS 220-D1/CB2 | 4 | 4 | 4 | Proposed | 17/10/2022 | 20/10/2022
TO-22-SHL-D1/CB3-01 | COUPLER/SECTIONALISING CB - SHELLYBANKS 220-SHELLYBANKS 220-D1/CB3 | 4 | 4 | 4 | Proposed | 17/10/2022 | 20/10/2022
TO-22-SHL-D2/CB3-04 | COUPLER/SECTIONALISING CB - SHELLYBANKS 220-SHELLYBANKS 220-D2/CB3 | 4 | 4 | 4 | Proposed | 17/10/2022 | 20/10/2022
TO-22-GWE-CAP1-02 | CAPACITOR/SVC/REACTOR - GORTAWEE 110-GORTAWEE 110-CAP1 | 4 | 4 | 4 | Proposed | 18/10/2022 | 21/10/2022
TO-22-ARV-SKL-2-02 | 110kV FEEDER - ARVA 110-SHANKILL 110-2 | 7 | 5 | 5 | Proposed | 19/10/2022 | 25/10/2022
TO-22-BRT-CLE-2-01 | 220kV FEEDER - BRACETOWN 220-CLONEE 220-2 | 2 | 2 | 2 | Proposed | 20/10/2022 | 21/10/2022
TO-22-AUG-SK-3-02 | 110kV FEEDER - AUGHINISH 110-SEALROCK 110-3 | 3 | 3 | 3 | Proposed | 24/10/2022 | 26/10/2022
TO-22-BVK-CLA-1-01 | 220kV FEEDER - BALLYVOUSKILL 220-CLASHAVOON 220-1 | 5 | 5 | 5 | Scheduled | 24/10/2022 | 28/10/2022
TO-22-CUL-WAT-1-01 | 110kV FEEDER - CULLENAGH 110-WATERFORD 110-1 | 5 | 5 | 5 | Scheduled | 24/10/2022 | 28/10/2022
TO-22-CUS-T103/5-02 | GENERATOR TRANSFORMER - CUSHALING 110-CUSHALING G3/5-T103/5 | 1 | 1 | 1 | Scheduled | 24/10/2022 | 24/10/2022
TO-22-GI-WAT-1-02 | 110kV FEEDER - GREAT ISLAND 110-WATERFORD 110-1 | 5 | 5 | 5 | Proposed | 24/10/2022 | 28/10/2022
TO-22-KLN-LIM-1-01 | 110kV FEEDER - KILLONAN 110-LIMERICK 110-1 | 5 | 5 | 5 | Proposed | 24/10/2022 | 28/10/2022
TO-22-KPG-MP GIS-1-02 | 220kV FEEDER - KILPADDOGE 220-MONEYPOINT GIS 220-1 | 5 | 5 | 5 | Scheduled | 24/10/2022 | 28/10/2022
TO-22-MCE-SNU-1-03 | 110kV FEEDER - MACETOWN 110-SNUGBOROUGH 110-1 | 5 | 5 | 5 | Proposed | 24/10/2022 | 28/10/2022
TO-22-SK-T103-02 | GENERATOR TRANSFORMER - SEALROCK 110-SEALROCK G3-T103 | 3 | 3 | 3 | Proposed | 24/10/2022 | 26/10/2022
TO-22-CUN-GLR-1-01 | 110kV FEEDER - CUNGHILL 110-GLENREE 110-1 | 1 | 1 | 1 | Scheduled | 25/10/2022 | 25/10/2022
TO-22-MAY-RNW-1-03 | 110kV FEEDER - MAYNOOTH 110-RINAWADE 110-1 | 3 | 3 | 3 | Proposed | 25/10/2022 | 27/10/2022
TO-22-CSH-T2101-01 | TRANSFORMER - CASHLA 220-CASHLA 110-T2101 | 1 | 1 | 1 | Proposed | 26/10/2022 | 26/10/2022
TO-22-GLR-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - GLENREE 110-GLENREE 110-110SA1-2CB | 1 | 1 | 1 | Scheduled | 26/10/2022 | 26/10/2022
TO-22-DRY-LOU-1-03 | 110kV FEEDER - DRYBRIDGE 110-LOUTH 110-1 | 8 | 5 | 5 | Proposed | 27/10/2022 | 03/11/2022
TO-22-DSN-MAY-2-04 | 220kV FEEDER - DUNSTOWN 220-MAYNOOTH 220-2 | 5 | 4 | 4 | Proposed | 31/10/2022 | 04/11/2022
TO-22-BEG-CKM GIS-1-01 | 110kV FEEDER - BALLYBEG 110-CARRICKMINES GIS 110-1 | 4 | 4 | 4 | Proposed | 01/11/2022 | 04/11/2022
TO-22-BK-110SA1-02 | SECTIONALISING DISCONNECT - BELLACORICK 110-BELLACORICK 110-110SA1 | 4 | 4 | 4 | Proposed | 01/11/2022 | 04/11/2022
TO-22-BK-110SA2-03 | SECTIONALISING DISCONNECT - BELLACORICK 110-BELLACORICK 110-110SA2 | 4 | 4 | 4 | Proposed | 01/11/2022 | 04/11/2022
TO-22-BK-MOY-1-05 | 110kV FEEDER - BELLACORICK 110-MOY 110-1 | 4 | 4 | 4 | Proposed | 01/11/2022 | 04/11/2022
TO-22-BK-T141-02 | DISTRIBUTION TRANSFORMER - BELLACORICK 110-BELLACORICK 38-T141 | 4 | 4 | 4 | Reference (Proposed) | 01/11/2022 | 04/11/2022
TO-22-CLW-KLS-2-04 | 110kV FEEDER - CARLOW 110-KELLIS 110-2 | 11 | 9 | 9 | Proposed | 01/11/2022 | 11/11/2022
TO-22-CKM GIS-R2001-01 | CAPACITOR/SVC/REACTOR - CARRICKMINES GIS 220-CARRICKMINES GIS 220-R2001 | 11 | 9 | 9 | Proposed | 01/11/2022 | 11/11/2022
TO-22-CLA-KRA-1-01 | 220kV FEEDER - CLASHAVOON 220-KNOCKRAHA 220-1 | 21 | 15 | 15 | Proposed | 01/11/2022 | 21/11/2022
TO-22-DRM-110SA1-01 | SECTIONALISING DISCONNECT - DRUMKEEN 110-DRUMKEEN 110-110SA1 | 1 | 1 | 1 | Proposed | 01/11/2022 | 01/11/2022
TO-22-DRM-110SA2-01 | SECTIONALISING DISCONNECT - DRUMKEEN 110-DRUMKEEN 110-110SA2 | 1 | 1 | 1 | Proposed | 01/11/2022 | 01/11/2022
TO-22-DRM-LET-1-05 | 110kV FEEDER - DRUMKEEN 110-LETTERKENNY 110-1 | 1 | 1 | 1 | Proposed | 01/11/2022 | 01/11/2022
TO-22-DRM-MEE-1-03 | 110kV FEEDER - DRUMKEEN 110-MEENTYCAT 110-1 | 1 | 1 | 1 | Proposed | 01/11/2022 | 01/11/2022
TO-22-400 kV A1 @ DSN-01 | BUSBAR SECTION - DUNSTOWN 400-DUNSTOWN 400-400A1 | 11 | 9 | 9 | Proposed | 01/11/2022 | 11/11/2022
TO-22-400 kV A2 @ DSN-01 | BUSBAR SECTION - DUNSTOWN 400-DUNSTOWN 400-400A2 | 11 | 9 | 9 | Proposed | 01/11/2022 | 11/11/2022
TO-22-400 kV B1 @ DSN-01 | BUSBAR SECTION - DUNSTOWN 400-DUNSTOWN 400-400B1 | 11 | 9 | 9 | Proposed | 01/11/2022 | 11/11/2022
TO-22-400 kV B2 @ DSN-01 | BUSBAR SECTION - DUNSTOWN 400-DUNSTOWN 400-400B2 | 11 | 9 | 9 | Proposed | 01/11/2022 | 11/11/2022
TO-22-DSN-400K1-2-02 | COUPLER/SECTIONALISING CB - DUNSTOWN 400-DUNSTOWN 400-400K1-2 | 11 | 9 | 9 | Proposed | 01/11/2022 | 11/11/2022
TO-22-110 kV B2 @ FIN GIS-08 | BUSBAR SECTION - FINGLAS GIS 110-FINGLAS GIS 110-110B2 | 4 | 4 | 4 | Proposed | 01/11/2022 | 04/11/2022
TO-22-110 kV B4 @ FIN GIS-01 | BUSBAR SECTION - FINGLAS GIS 110-FINGLAS GIS 110-110B4 | 4 | 4 | 4 | Proposed | 01/11/2022 | 04/11/2022
TO-22-FIN GIS-110SB2-4CB-04 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110SB2-4CB | 4 | 4 | 4 | Proposed | 01/11/2022 | 04/11/2022
TO-22-GGO-220K1-2-01 | COUPLER/SECTIONALISING CB - GLANAGOW 220-GLANAGOW 220-220K1-2 | 2 | 2 | 2 | Proposed | 01/11/2022 | 02/11/2022
TO-22-IKE-T141-04 | DISTRIBUTION TRANSFORMER - IKERRIN 110-IKERRIN 38-T141 | 2 | 2 | 2 | Reference (Proposed) | 01/11/2022 | 02/11/2022
TO-22-IKE,T-IKE-1-04 | 110kV FEEDER - IKERRIN tee-IKERRIN 110-1 | 2 | 2 | 2 | Proposed | 01/11/2022 | 02/11/2022
TO-22-IKE,T-SH-1-05 | 110kV FEEDER - IKERRIN tee-SHANNONBRIDGE 110-1 | 21 | 15 | 15 | Proposed | 01/11/2022 | 21/11/2022
TO-22-IKE,T-THU-1-07 | 110kV FEEDER - IKERRIN tee-THURLES 110-1 | 2 | 2 | 2 | Proposed | 01/11/2022 | 02/11/2022
TO-22-110 kV B1 @ KPG-03 | BUSBAR SECTION - KILPADDOGE 110-KILPADDOGE 110-110B1 | 4 | 4 | 4 | Proposed | 01/11/2022 | 04/11/2022
TO-22-110 kV B3 @ KPG-02 | BUSBAR SECTION - KILPADDOGE 110-KILPADDOGE 110-110B3 | 4 | 4 | 4 | Proposed | 01/11/2022 | 04/11/2022
TO-22-KPG-110SB1-3CB-01 | COUPLER/SECTIONALISING CB - KILPADDOGE 110-KILPADDOGE 110-110SB1-3CB | 4 | 4 | 4 | Proposed | 01/11/2022 | 04/11/2022
TO-22-MEE-T121-02 | GENERATOR TRANSFORMER - MEENTYCAT 110-MEENTYCAT 20-T121 | 1 | 1 | 1 | Proposed | 01/11/2022 | 01/11/2022
TO-22-220 kV A1/A2 @ BVK-02 | BUSBAR SECTION - BALLYVOUSKILL 220-BALLYVOUSKILL 220-220A1-A2 | 3 | 3 | 3 | Proposed | 02/11/2022 | 04/11/2022
TO-22-CBR-SVC-03 | CAPACITOR/SVC/REACTOR - CASTLEBAR 110-CASTLEBAR 110-SVC | 2 | 2 | 2 | Proposed | 02/11/2022 | 03/11/2022
TO-22-CHA-MAL-1-01 | 110kV FEEDER - CHARLEVILLE 110-MALLOW 110-1 | 9 | 7 | 7 | Proposed | 02/11/2022 | 10/11/2022
TO-22-CLA-220K1-2-01 | COUPLER/SECTIONALISING CB - CLASHAVOON 220-CLASHAVOON 220-220K1-2 | 3 | 3 | 3 | Proposed | 02/11/2022 | 04/11/2022
TO-22-CLA-T2102-01 | TRANSFORMER - CLASHAVOON 220-CLASHAVOON 110-T2102 | 3 | 3 | 3 | Proposed | 02/11/2022 | 04/11/2022
TO-22-CDY-SRA-1-02 | 110kV FEEDER - CORDERRY 110-SRANANAGH 110-1 | 1 | 1 | 1 | Proposed | 02/11/2022 | 02/11/2022
TO-22-COR-GWE-1-02 | 110kV FEEDER - CORRACLASSY 110-GORTAWEE 110-1 | 3 | 3 | 3 | Proposed | 02/11/2022 | 04/11/2022
TO-22-110 kV A1/A2 @ CUL-01 | BUSBAR SECTION - CULLENAGH 110-CULLENAGH 110-110A1-A2 | 1 | 1 | 1 | Proposed | 02/11/2022 | 02/11/2022
TO-22-110 kV B1/B2 @ CUL-01 | BUSBAR SECTION - CULLENAGH 110-CULLENAGH 110-110B1-B2 | 1 | 1 | 1 | Proposed | 02/11/2022 | 02/11/2022
TO-22-DGN-WOH-1-01 | 110kV FEEDER - DUNGARVAN 110-WOODHOUSE 110-1 | 2 | 2 | 2 | Proposed | 02/11/2022 | 03/11/2022
TO-22-TB-220K1-2-02 | COUPLER/SECTIONALISING CB - TARBERT 220-TARBERT 220-220K1-2 | 3 | 3 | 3 | Proposed | 02/11/2022 | 04/11/2022
TO-22-LOU-110K1-2-03 | COUPLER/SECTIONALISING CB - LOUTH 110-LOUTH 110-110K1-2 | 1 | 1 | 1 | Proposed | 03/11/2022 | 03/11/2022
TO-22-MP GIS-ST101-01 | GENERATOR TRANSFORMER - MONEYPOINT GIS 110-MONEYPOINT GIS 10-ST101 | 11 | 7 | 7 | Proposed | 04/11/2022 | 14/11/2022
TO-22-ARV-GWE-1-02 | 110kV FEEDER - ARVA 110-GORTAWEE 110-1 | 5 | 5 | 5 | Proposed | 07/11/2022 | 11/11/2022
TO-22-CSH-GAL-2-04 | 110kV FEEDER - CASHLA 110-GALWAY 110-2 | 5 | 5 | 5 | Proposed | 07/11/2022 | 11/11/2022
TO-22-CBT-T2102-01 | TRANSFORMER - CASTLEBAGOT 220-CASTLEBAGOT 110-T2102 | 5 | 5 | 5 | Proposed | 07/11/2022 | 11/11/2022
TO-22-CBR-DLT-1-01 | 110kV FEEDER - CASTLEBAR 110-DALTON 110-1 | 5 | 5 | 5 | Proposed | 07/11/2022 | 11/11/2022
TO-22-CF-CLO-1-02 | 110kV FEEDER - CATHALEENS FALL 110-CLOGHER 110-1 | 12 | 10 | 10 | Proposed | 07/11/2022 | 18/11/2022
TO-22-CF-CLO-2-01 | 110kV FEEDER - CATHALEENS FALL 110-CLOGHER 110-2 | 12 | 10 | 10 | Proposed | 07/11/2022 | 18/11/2022
TO-22-DLT-110SA1-02 | SECTIONALISING DISCONNECT - DALTON 110-DALTON 110-110SA1 | 5 | 5 | 5 | Proposed | 07/11/2022 | 11/11/2022
TO-22-DLT-110SA2-03 | SECTIONALISING DISCONNECT - DALTON 110-DALTON 110-110SA2 | 5 | 5 | 5 | Proposed | 07/11/2022 | 11/11/2022
TO-22-DLT-CAP1-01 | CAPACITOR/SVC/REACTOR - DALTON 110-DALTON 110-CAP1 | 5 | 5 | 5 | Proposed | 07/11/2022 | 11/11/2022
TO-22-DLT-T141-01 | DISTRIBUTION TRANSFORMER - DALTON 110-DALTON 38-T141 | 5 | 5 | 5 | Reference (Proposed) | 07/11/2022 | 11/11/2022
TO-22-FIN GIS-110K2-07 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110K2 | 4 | 4 | 4 | Proposed | 07/11/2022 | 10/11/2022
TO-22-GI GIS-LWD-1-02 | 220kV FEEDER - GREAT ISLAND GIS 220-LODGEWOOD 220-1 | 5 | 5 | 5 | Proposed | 07/11/2022 | 11/11/2022
TO-22-GI-WAT-2-02 | 110kV FEEDER - GREAT ISLAND 110-WATERFORD 110-2 | 4 | 4 | 4 | Proposed | 07/11/2022 | 10/11/2022
TO-22-LWD-220K1-2-02 | COUPLER/SECTIONALISING CB - LODGEWOOD 220-LODGEWOOD 220-220K1-2 | 5 | 5 | 5 | Proposed | 07/11/2022 | 11/11/2022
TO-22-220 kV A2 @ MAY-06 | BUSBAR SECTION - MAYNOOTH 220-MAYNOOTH 220-220A2 | 5 | 5 | 5 | Proposed | 07/11/2022 | 11/11/2022
TO-22-220 kV B2 @ MAY-07 | BUSBAR SECTION - MAYNOOTH 220-MAYNOOTH 220-220B2 | 5 | 5 | 5 | Proposed | 07/11/2022 | 11/11/2022
TO-22-MAY-SH-1-04 | 220kV FEEDER - MAYNOOTH 220-SHANNONBRIDGE 220-1 | 5 | 5 | 5 | Proposed | 07/11/2022 | 11/11/2022
TO-22-MP GIS-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 110-MONEYPOINT GIS 110-110SA1-2CB | 5 | 5 | 5 | Proposed | 07/11/2022 | 11/11/2022
TO-22-MP GIS-T121-01 | GENERATOR TRANSFORMER - MONEYPOINT GIS 110-MONEYPOINT GIS 20-T121 | 5 | 5 | 5 | Proposed | 07/11/2022 | 11/11/2022
TO-22-110 kV A1 @ RYB GIS-01 | BUSBAR SECTION - RYEBROOK GIS 110-RYEBROOK GIS 110-110A1 | 5 | 5 | 5 | Proposed | 07/11/2022 | 11/11/2022
TO-22-110 kV A2 @ RYB GIS-01 | BUSBAR SECTION - RYEBROOK GIS 110-RYEBROOK GIS 110-110A2 | 5 | 5 | 5 | Proposed | 07/11/2022 | 11/11/2022
TO-22-RYB GIS-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - RYEBROOK GIS 110-RYEBROOK GIS 110-110SA1-2CB | 5 | 5 | 5 | Proposed | 07/11/2022 | 11/11/2022
TO-22-TBK-T141-01 | DISTRIBUTION TRANSFORMER - TULLABRACK 110-TULLABRACK 38-T141 | 5 | 5 | 5 | Reference (Proposed) | 07/11/2022 | 11/11/2022
TO-22-TBK,T-BOL-1-01 | 110kV FEEDER - TULLABRACK tee-BOOLTIAGH 110-1 | 5 | 5 | 5 | Proposed | 07/11/2022 | 11/11/2022
TO-22-TBK,T-MP GIS-1-01 | 110kV FEEDER - TULLABRACK tee-MONEYPOINT GIS 110-1 | 5 | 5 | 5 | Proposed | 07/11/2022 | 11/11/2022
TO-22-TBK,T-TBK-1-01 | 110kV FEEDER - TULLABRACK tee-TULLABRACK 110-1 | 5 | 5 | 5 | Proposed | 07/11/2022 | 11/11/2022
TO-22-220 kV A1 @ BYH-02 | BUSBAR SECTION - BALLYNAHULLA 220-BALLYNAHULLA 220-220A1 | 4 | 4 | 4 | Proposed | 08/11/2022 | 11/11/2022
TO-22-220 kV A2 @ BYH-03 | BUSBAR SECTION - BALLYNAHULLA 220-BALLYNAHULLA 220-220A2 | 4 | 4 | 4 | Proposed | 08/11/2022 | 11/11/2022
TO-22-BYH-220SA1-2CB-01 | COUPLER/SECTIONALISING CB - BALLYNAHULLA 220-BALLYNAHULLA 220-220SA1-2CB | 4 | 4 | 4 | Proposed | 08/11/2022 | 11/11/2022
TO-22-FIN-NW-1-04 | 220kV FEEDER - FINGLAS 220-NORTH WALL 220-1 | 11 | 9 | 9 | Proposed | 08/11/2022 | 18/11/2022
TO-22-110 kV A2 @ GOR-01 | BUSBAR SECTION - GORMAN 110-GORMAN 110-110A2 | 4 | 4 | 4 | Proposed | 08/11/2022 | 11/11/2022
TO-22-110 kV B2 @ GOR-01 | BUSBAR SECTION - GORMAN 110-GORMAN 110-110B2 | 4 | 4 | 4 | Proposed | 08/11/2022 | 11/11/2022
TO-22-GOR-MTH-1-02 | 110kV FEEDER - GORMAN 110-MEATH HILL 110-1 | 4 | 4 | 4 | Proposed | 08/11/2022 | 11/11/2022
TO-22-110 kV A2 @ KPG-03 | BUSBAR SECTION - KILPADDOGE 110-KILPADDOGE 110-110A2 | 4 | 4 | 4 | Proposed | 08/11/2022 | 11/11/2022
TO-22-110 kV A4 @ KPG-01 | BUSBAR SECTION - KILPADDOGE 110-KILPADDOGE 110-110A4 | 4 | 4 | 4 | Proposed | 08/11/2022 | 11/11/2022
TO-22-KPG-110SA2-4CB-01 | COUPLER/SECTIONALISING CB - KILPADDOGE 110-KILPADDOGE 110-110SA2-4CB | 4 | 4 | 4 | Proposed | 08/11/2022 | 11/11/2022
TO-22-MP GIS-T2102-01 | TRANSFORMER - MONEYPOINT GIS 220-MONEYPOINT GIS 110-T2102 | 4 | 4 | 4 | Proposed | 08/11/2022 | 11/11/2022
TO-22-110 kV A1/A2 @ KRA-01 | BUSBAR SECTION - KNOCKRAHA 110-KNOCKRAHA 110-110A1-A2 | 1 | 1 | 1 | Proposed | 09/11/2022 | 09/11/2022
TO-22-110 kV B1/B2 @ KRA-01 | BUSBAR SECTION - KNOCKRAHA 110-KNOCKRAHA 110-110B1-B2 | 1 | 1 | 1 | Proposed | 09/11/2022 | 09/11/2022
TO-22-110 kV A1 @ ARK-02 | BUSBAR SECTION - ARKLOW 110-ARKLOW 110-110A1 | 12 | 10 | 10 | Proposed | 14/11/2022 | 25/11/2022
TO-22-110 kV A2 @ ARK-01 | BUSBAR SECTION - ARKLOW 110-ARKLOW 110-110A2 | 12 | 10 | 10 | Proposed | 14/11/2022 | 25/11/2022
TO-22-110 kV B1 @ ARK-02 | BUSBAR SECTION - ARKLOW 110-ARKLOW 110-110B1 | 12 | 10 | 10 | Proposed | 14/11/2022 | 25/11/2022
TO-22-110 kV B2 @ ARK-01 | BUSBAR SECTION - ARKLOW 110-ARKLOW 110-110B2 | 12 | 10 | 10 | Proposed | 14/11/2022 | 25/11/2022
TO-22-ARK-110K1-2-01 | COUPLER/SECTIONALISING CB - ARKLOW 110-ARKLOW 110-110K1-2 | 12 | 10 | 10 | Proposed | 14/11/2022 | 25/11/2022
TO-22-220 kV A2 @ CKM GIS-02 | BUSBAR SECTION - CARRICKMINES GIS 220-CARRICKMINES GIS 220-220A2 | 5 | 5 | 5 | Proposed | 14/11/2022 | 18/11/2022
TO-22-220 kV A4 @ CKM GIS-03 | BUSBAR SECTION - CARRICKMINES GIS 220-CARRICKMINES GIS 220-220A4 | 5 | 5 | 5 | Proposed | 14/11/2022 | 18/11/2022
TO-22-CKM GIS-220SA2-4CB-01 | COUPLER/SECTIONALISING CB - CARRICKMINES GIS 220-CARRICKMINES GIS 220-22SA2-4CB | 12 | 10 | 10 | Proposed | 14/11/2022 | 25/11/2022
TO-22-220 kV A2 @ CSH-01 | BUSBAR SECTION - CASHLA 220-CASHLA 220-220A2 | 5 | 5 | 5 | Proposed | 14/11/2022 | 18/11/2022
TO-22-220 kV A4 @ CSH-01 | BUSBAR SECTION - CASHLA 220-CASHLA 220-220A4 | 5 | 5 | 5 | Proposed | 14/11/2022 | 18/11/2022
TO-22-220 kV B2 @ CSH-01 | BUSBAR SECTION - CASHLA 220-CASHLA 220-220B2 | 5 | 5 | 5 | Proposed | 14/11/2022 | 18/11/2022
TO-22-220 kV B4 @ CSH-01 | BUSBAR SECTION - CASHLA 220-CASHLA 220-220B4 | 5 | 5 | 5 | Proposed | 14/11/2022 | 18/11/2022
TO-22-CSH-220K2-4-01 | COUPLER/SECTIONALISING CB - CASHLA 220-CASHLA 220-220K2-4 | 5 | 5 | 5 | Proposed | 14/11/2022 | 18/11/2022
TO-22-CHA-KLN-1-01 | 110kV FEEDER - CHARLEVILLE 110-KILLONAN 110-1 | 5 | 5 | 5 | Proposed | 14/11/2022 | 18/11/2022
TO-22-FLA-SLI-1-04 | 110kV FEEDER - FLAGFORD 110-SLIGO 110-1 | 5 | 5 | 5 | Proposed | 14/11/2022 | 18/11/2022
TO-22-220 kV B2 @ GOR-03 | BUSBAR SECTION - GORMAN 220-GORMAN 220-220B2 | 2 | 2 | 2 | Proposed | 14/11/2022 | 15/11/2022
TO-22-GOR-LOU-1-01 | 220kV FEEDER - GORMAN 220-LOUTH 220-1 | 5 | 5 | 5 | Proposed | 14/11/2022 | 18/11/2022
TO-22-110 kV B2 @ KPG-03 | BUSBAR SECTION - KILPADDOGE 110-KILPADDOGE 110-110B2 | 4 | 4 | 4 | Proposed | 14/11/2022 | 17/11/2022
TO-22-110 kV B4 @ KPG-01 | BUSBAR SECTION - KILPADDOGE 110-KILPADDOGE 110-110B4 | 4 | 4 | 4 | Proposed | 14/11/2022 | 17/11/2022
TO-22-KPG-110SB2-4CB-01 | COUPLER/SECTIONALISING CB - KILPADDOGE 110-KILPADDOGE 110-110SB2-4CB | 4 | 4 | 4 | Proposed | 14/11/2022 | 17/11/2022
TO-22-110 kV B1 @ RYB GIS-01 | BUSBAR SECTION - RYEBROOK GIS 110-RYEBROOK GIS 110-110B1 | 5 | 5 | 5 | Proposed | 14/11/2022 | 18/11/2022
TO-22-110 kV B2 @ RYB GIS-02 | BUSBAR SECTION - RYEBROOK GIS 110-RYEBROOK GIS 110-110B2 | 5 | 5 | 5 | Proposed | 14/11/2022 | 18/11/2022
TO-22-RYB GIS-110SB1-2CB-02 | COUPLER/SECTIONALISING CB - RYEBROOK GIS 110-RYEBROOK GIS 110-110SB1-2CB | 5 | 5 | 5 | Proposed | 14/11/2022 | 18/11/2022
TO-22-220 kV B1 @ BYH-02 | BUSBAR SECTION - BALLYNAHULLA 220-BALLYNAHULLA 220-220B1 | 4 | 4 | 4 | Proposed | 15/11/2022 | 18/11/2022
TO-22-220 kV B2 @ BYH-03 | BUSBAR SECTION - BALLYNAHULLA 220-BALLYNAHULLA 220-220B2 | 4 | 4 | 4 | Proposed | 15/11/2022 | 18/11/2022
TO-22-BYH-220SB1-2CB-01 | COUPLER/SECTIONALISING CB - BALLYNAHULLA 220-BALLYNAHULLA 220-220SB1-2CB | 4 | 4 | 4 | Proposed | 15/11/2022 | 18/11/2022
TO-22-CSH-CLN-1-03 | 110kV FEEDER - CASHLA 110-CLOON 110-1 | 14 | 10 | 10 | Proposed | 15/11/2022 | 28/11/2022
TO-22-110 kV A1/A2/A3/A4 @ CDU-01 | BUSBAR SECTION - CORDUFF 110-CORDUFF 110-110A1-A2-A3-A4 | 1 | 1 | 1 | Proposed | 16/11/2022 | 16/11/2022
TO-22-110 kV B1/B2/B3/B4 @ CDU-01 | BUSBAR SECTION - CORDUFF 110-CORDUFF 110-110B1-B2-B3-B4 | 1 | 1 | 1 | Proposed | 16/11/2022 | 16/11/2022
TO-22-220 kV A2 @ GOR-02 | BUSBAR SECTION - GORMAN 220-GORMAN 220-220A2 | 7 | 5 | 5 | Proposed | 16/11/2022 | 22/11/2022
TO-22-220 kV B2 @ GOR-02 | BUSBAR SECTION - GORMAN 220-GORMAN 220-220B2 | 7 | 5 | 5 | Proposed | 16/11/2022 | 22/11/2022
TO-22-NAV-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - NAVAN 110-NAVAN 110-110SA1-2CB | 1 | 1 | 1 | Proposed | 16/11/2022 | 16/11/2022
TO-22-CDU-220SB2-4-03 | SECTIONALISING DISCONNECT - CORDUFF 220-CORDUFF 220-220SB2-4 | 5 | 5 | 5 | Proposed | 21/11/2022 | 25/11/2022
TO-22-CDU-WOO-1-01 | 220kV FEEDER - CORDUFF 220-WOODLAND 220-1 | 5 | 5 | 5 | Proposed | 21/11/2022 | 25/11/2022
TO-22-IKE-T141-05 | DISTRIBUTION TRANSFORMER - IKERRIN 110-IKERRIN 38-T141 | 1 | 1 | 1 | Reference (Proposed) | 21/11/2022 | 21/11/2022
TO-22-IKE,T-IKE-1-05 | 110kV FEEDER - IKERRIN tee-IKERRIN 110-1 | 1 | 1 | 1 | Proposed | 21/11/2022 | 21/11/2022
TO-22-IKE,T-THU-1-08 | 110kV FEEDER - IKERRIN tee-THURLES 110-1 | 1 | 1 | 1 | Proposed | 21/11/2022 | 21/11/2022
TO-22-220 kV B1 @ KPG-03 | BUSBAR SECTION - KILPADDOGE 220-KILPADDOGE 220-220B1 | 4 | 4 | 4 | Proposed | 21/11/2022 | 24/11/2022
TO-22-220 kV B2 @ KPG-03 | BUSBAR SECTION - KILPADDOGE 220-KILPADDOGE 220-220B2 | 4 | 4 | 4 | Proposed | 21/11/2022 | 24/11/2022
TO-22-KPG-220SB1-2CB-03 | COUPLER/SECTIONALISING CB - KILPADDOGE 220-KILPADDOGE 220-220SB1-2CB | 4 | 4 | 4 | Proposed | 21/11/2022 | 24/11/2022
TO-22-110 kV A1 @ KNR-02 | BUSBAR SECTION - KNOCKANURE 110-KNOCKANURE 110-110A1 | 5 | 5 | 5 | Proposed | 21/11/2022 | 25/11/2022
TO-22-KNR-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - KNOCKANURE 110-KNOCKANURE 110-110SA1-2CB | 5 | 5 | 5 | Proposed | 21/11/2022 | 25/11/2022
TO-22-110 kV A2 @ LOU-06 | BUSBAR SECTION - LOUTH 110-LOUTH 110-110A2 | 5 | 5 | 5 | Proposed | 21/11/2022 | 25/11/2022
TO-22-110 kV B2 @ LOU-06 | BUSBAR SECTION - LOUTH 110-LOUTH 110-110B2 | 5 | 5 | 5 | Proposed | 21/11/2022 | 25/11/2022
TO-22-MOY-TAW-2-01 | 110kV FEEDER - MOY 110-TAWNAGHMORE 110-2 | 5 | 5 |  | Proposed | 21/11/2022 | 25/11/2022
TO-22-PB-R2001-06 | CAPACITOR/SVC/REACTOR - POOLBEG 220-POOLBEG 220-R2001 | 4 | 4 | 4 | Proposed | 21/11/2022 | 24/11/2022
TO-22-110 kV B1 @ RYB GIS-02 | BUSBAR SECTION - RYEBROOK GIS 110-RYEBROOK GIS 110-110B1 | 5 | 5 | 5 | Proposed | 21/11/2022 | 25/11/2022
TO-22-110 kV B3 @ RYB GIS-02 | BUSBAR SECTION - RYEBROOK GIS 110-RYEBROOK GIS 110-110B3 | 5 | 5 | 5 | Proposed | 21/11/2022 | 25/11/2022
TO-22-RYB GIS-110SB1-3CB-02 | COUPLER/SECTIONALISING CB - RYEBROOK GIS 110-RYEBROOK GIS 110-110SB1-3CB | 5 | 5 | 5 | Proposed | 21/11/2022 | 25/11/2022
TO-22-KBY-MAL-1-04 | 110kV FEEDER - KILBARRY 110-MALLOW 110-1 | 2 | 2 | 2 | Proposed | 22/11/2022 | 23/11/2022
TO-22-MID-WHI-1-01 | 110kV FEEDER - MIDLETON 110-WHITEGATE 110-1 | 9 | 7 | 7 | Proposed | 22/11/2022 | 30/11/2022
TO-22-ARK-SHE-2-01 | 110kV FEEDER - ARKLOW 110-SHELTON ABBEY 110-2 | 1 | 1 | 1 | Proposed | 24/11/2022 | 24/11/2022
TO-22-SHE-T102-01 | TSO CUSTOMER TRANSFORMER - SHELTON ABBEY 110-SHELTON ABBEY 10-T102 | 1 | 1 | 1 | Reference (Proposed) | 24/11/2022 | 24/11/2022
TO-22-AUG-SK-4-02 | 110kV FEEDER - AUGHINISH 110-SEALROCK 110-4 | 3 | 3 | 3 | Proposed | 28/11/2022 | 30/11/2022
TO-22-220 kV B1/B2 @ BVK-02 | BUSBAR SECTION - BALLYVOUSKILL 220-BALLYVOUSKILL 220-220B1-B2 | 3 | 3 | 3 | Proposed | 28/11/2022 | 30/11/2022
TO-22-KRA-220SA2-4CB-04 | COUPLER/SECTIONALISING CB - KNOCKRAHA 220-KNOCKRAHA 220-220SA2-4CB | 1 | 1 | 1 | Proposed | 28/11/2022 | 28/11/2022
TO-22-LIS-T131-02 | GENERATOR TRANSFORMER - LISDRUM 110-LISDRUM 33-T131 | 2 | 2 | 2 | Proposed | 28/11/2022 | 29/11/2022
TO-22-LOU-T2102-01 | TRANSFORMER - LOUTH 220-LOUTH 110-T2102 | 2 | 2 | 2 | Proposed | 28/11/2022 | 29/11/2022
TO-22-SK-T104-02 | GENERATOR TRANSFORMER - SEALROCK 110-SEALROCK G4-T104 | 3 | 3 | 3 | Proposed | 28/11/2022 | 30/11/2022
TO-22-DRY-PLA-1-04 | 110kV FEEDER - DRYBRIDGE 110-PLATIN 110-1 | 1 | 1 | 1 | Proposed | 29/11/2022 | 29/11/2022
TO-22-FLA-SRA-1-03 | 220kV FEEDER - FLAGFORD 220-SRANANAGH 220-1 | 1 | 1 | 1 | Proposed | 29/11/2022 | 29/11/2022
TO-22-KRA-220SB2-4CB-04 | COUPLER/SECTIONALISING CB - KNOCKRAHA 220-KNOCKRAHA 220-220SB2-4CB | 1 | 1 | 1 | Proposed | 29/11/2022 | 29/11/2022
TO-22-KRA-220K4-01 | COUPLER/SECTIONALISING CB - KNOCKRAHA 220-KNOCKRAHA 220-220K4 | 1 | 1 | 1 | Proposed | 30/11/2022 | 30/11/2022

## GEN_AreaSouthWest
Outage ID | Feeder ID | Calendar Day Duration | Working Day Duration | Work Days | Outage Status | Start | Finish
TO-22-AA GIS-110SA1-3CB-01 | COUPLER/SECTIONALISING CB - ARDNACRUSHA GIS 110-ARDNACRUSHA GIS 110-110SA1-3CB | 2 | 2 | 2 | Tentative | 10/01/2022 | 11/01/2022
TO-22-BYH-220K2-01 | COUPLER/SECTIONALISING CB - BALLYNAHULLA 220-BALLYNAHULLA 220-220K2 | 2 | 2 | 2 | Scheduled | 10/01/2022 | 11/01/2022
TO-22-BYH-220K1-01 | COUPLER/SECTIONALISING CB - BALLYNAHULLA 220-BALLYNAHULLA 220-220K1 | 2 | 2 | 2 | Scheduled | 13/01/2022 | 14/01/2022
TO-22-110 kV A1 @ KNR-01 | BUSBAR SECTION - KNOCKANURE 110-KNOCKANURE 110-110A1 | 5 | 5 | 5 | Scheduled | 17/01/2022 | 21/01/2022
TO-22-110 kV B1 @ KNR-01 | BUSBAR SECTION - KNOCKANURE 110-KNOCKANURE 110-110B1 | 5 | 5 | 5 | Scheduled | 17/01/2022 | 21/01/2022
TO-22-KNR-110K1-01 | COUPLER/SECTIONALISING CB - KNOCKANURE 110-KNOCKANURE 110-110K1 | 5 | 5 | 5 | Scheduled | 17/01/2022 | 21/01/2022
TO-22-110 kV A4 @ KNR-01 | BUSBAR SECTION - KNOCKANURE 110-KNOCKANURE 110-110A4 | 5 | 5 | 5 | Scheduled | 24/01/2022 | 28/01/2022
TO-22-110 kV B4 @ KNR-01 | BUSBAR SECTION - KNOCKANURE 110-KNOCKANURE 110-110B4 | 5 | 5 | 5 | Scheduled | 24/01/2022 | 28/01/2022
TO-22-KNR-T2102-02 | TRANSFORMER - KNOCKANURE 220-KNOCKANURE 110-T2102 | 10 | 8 | 8 | Tentative | 31/01/2022 | 09/02/2022
TO-22-MP GIS-220K1-01 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 220-MONEYPOINT GIS 220-220K1 | 2 | 2 | 2 | Scheduled | 31/01/2022 | 01/02/2022
TO-22-KPG-220SA1-2CB-03 | COUPLER/SECTIONALISING CB - KILPADDOGE 220-KILPADDOGE 220-220SA1-2CB | 4 | 4 | 4 | Scheduled | 01/02/2022 | 04/02/2022
TO-22-KPG-220K4-02 | COUPLER/SECTIONALISING CB - KILPADDOGE 220-KILPADDOGE 220-220K4 | 4 | 4 | 4 | Scheduled | 08/02/2022 | 11/02/2022
TO-22-MP GIS-220SA1-2CB-01 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 220-MONEYPOINT GIS 220-220SA1-2CB | 2 | 2 | 2 | Scheduled | 08/02/2022 | 09/02/2022
TO-22-110 kV A1/A2/A3 @ AA GIS-01 | BUSBAR SECTION - ARDNACRUSHA GIS 110-ARDNACRUSHA GIS 110-110A1-A2-A3 | 1 | 1 | 1 | Scheduled | 10/02/2022 | 10/02/2022
TO-22-110 kV B1/B2/B3 @ AA GIS-01 | BUSBAR SECTION - ARDNACRUSHA GIS 110-ARDNACRUSHA GIS 110-110B1-B2-B3 | 1 | 1 | 1 | Scheduled | 10/02/2022 | 10/02/2022
TO-22-110 kV A1/A2/A3/A4 @ KPG-01 | BUSBAR SECTION - KILPADDOGE 110-KILPADDOGE 110-110A1-A2-A3-A4 | 1 | 1 | 1 | Scheduled | 15/02/2022 | 15/02/2022
TO-22-110 kV B1/B2/B3/B4 @ KPG-01 | BUSBAR SECTION - KILPADDOGE 110-KILPADDOGE 110-110B1-B2-B3-B4 | 1 | 1 | 1 | Scheduled | 15/02/2022 | 15/02/2022
TO-22-220 kV A1/A2/A3/A4 @ KPG-01 | BUSBAR SECTION - KILPADDOGE 220-KILPADDOGE 220-220A1-A2-A3-A4 | 1 | 1 | 1 | Scheduled | 16/02/2022 | 16/02/2022
TO-22-220 kV B1/B2/B3/B4 @ KPG-01 | BUSBAR SECTION - KILPADDOGE 220-KILPADDOGE 220-220B1-B2-B3-B4 | 1 | 1 | 1 | Scheduled | 16/02/2022 | 16/02/2022
TO-22-AA GIS-110SB1-3CB-01 | COUPLER/SECTIONALISING CB - ARDNACRUSHA GIS 110-ARDNACRUSHA GIS 110-110SB1-3CB | 5 | 5 | 5 | Scheduled | 21/02/2022 | 25/02/2022
TO-22-BVK-110SB1-2CB-02 | COUPLER/SECTIONALISING CB - BALLYVOUSKILL 110-BALLYVOUSKILL 110-110SB1-2CB | 5 | 5 | 5 | Scheduled | 21/02/2022 | 25/02/2022
TO-22-KPG-220SA2-4CB-03 | COUPLER/SECTIONALISING CB - KILPADDOGE 220-KILPADDOGE 220-220SA2-4CB | 4 | 4 | 4 | Scheduled | 22/02/2022 | 25/02/2022
TO-22-110 kV A1 @ BYH-01 | BUSBAR SECTION - BALLYNAHULLA 110-BALLYNAHULLA 110-110A1 | 4 | 4 | 4 | Scheduled | 28/02/2022 | 03/03/2022
TO-22-110 kV B1 @ BYH-01 | BUSBAR SECTION - BALLYNAHULLA 110-BALLYNAHULLA 110-110B1 | 4 | 4 | 4 | Scheduled | 28/02/2022 | 03/03/2022
TO-22-220 kV A1 @ BYH-01 | BUSBAR SECTION - BALLYNAHULLA 220-BALLYNAHULLA 220-220A1 | 4 | 4 | 4 | Scheduled | 28/02/2022 | 03/03/2022
TO-22-220 kV B1 @ BYH-01 | BUSBAR SECTION - BALLYNAHULLA 220-BALLYNAHULLA 220-220B1 | 4 | 4 | 4 | Scheduled | 28/02/2022 | 03/03/2022
TO-22-BYH-KNR-1-02 | 220kV FEEDER - BALLYNAHULLA 220-KNOCKANURE 220-1 | 5 | 5 | 5 | Scheduled | 28/02/2022 | 04/03/2022
TO-22-BYH-T2101-01 | TRANSFORMER - BALLYNAHULLA 220-BALLYNAHULLA 110-T2101 | 5 | 5 |  | Scheduled | 28/02/2022 | 04/03/2022
TO-22-CSH-PRO-1-01 | 220kV FEEDER - CASHLA 220-PROSPECT 220-1 | 31 | 22 | 22 | Scheduled | 28/02/2022 | 30/03/2022
TO-22-KLN-T2104-01 | TRANSFORMER - KILLONAN 220-KILLONAN 110-T2104 | 5 | 5 | 5 | Scheduled | 28/02/2022 | 04/03/2022
TO-22-MP GIS-PRO-1-01 | 220kV FEEDER - MONEYPOINT GIS 220-PROSPECT 220-1 | 5 | 5 | 5 | Scheduled | 28/02/2022 | 04/03/2022
TO-22-PRO-TB-1-04 | 220kV FEEDER - PROSPECT 220-TARBERT 220-1 | 5 | 5 | 5 | Scheduled | 28/02/2022 | 04/03/2022
TO-22-CAH-TIP-1-01 | 110kV FEEDER - CAHIR 110-TIPPERARY 110-1 | 4 | 4 | 4 | Scheduled | 01/03/2022 | 04/03/2022
TO-22-KLN-T2101-01 | TRANSFORMER - KILLONAN 220-KILLONAN 110-T2101 | 30 | 20 | 20 | Scheduled | 07/03/2022 | 05/04/2022
TO-22-110 kV A1 @ TB-01 | BUSBAR SECTION - TARBERT 110-TARBERT 110-110A1 | 29 | 19 | 19 | Scheduled | 07/03/2022 | 04/04/2022
TO-22-110 kV B1 @ TB-01 | BUSBAR SECTION - TARBERT 110-TARBERT 110-110B1 | 29 | 19 | 19 | Scheduled | 07/03/2022 | 04/04/2022
TO-22-220 kV A1/A2 @ MP GIS-01 | BUSBAR SECTION - MONEYPOINT GIS 220-MONEYPOINT GIS 220-220A1-A2 | 1 | 1 | 1 | Scheduled | 09/03/2022 | 09/03/2022
TO-22-220 kV B1/B2 @ MP GIS-01 | BUSBAR SECTION - MONEYPOINT GIS 220-MONEYPOINT GIS 220-220B1-B2 | 1 | 1 | 1 | Scheduled | 09/03/2022 | 09/03/2022
TO-22-400 kV A1/A2/A3/A4 @ MP GIS-01 | BUSBAR SECTION - MONEYPOINT GIS 400-MONEYPOINT GIS 400-400A1-A2-A3-A4 | 1 | 1 | 1 | Scheduled | 09/03/2022 | 09/03/2022
TO-22-400 kV B1/B2/B3/B4 @ MP GIS-01 | BUSBAR SECTION - MONEYPOINT GIS 400-MONEYPOINT GIS 400-400B1-B2-B3-B4 | 1 | 1 | 1 | Scheduled | 09/03/2022 | 09/03/2022
TO-22-AA GIS-110K3-01 | COUPLER/SECTIONALISING CB - ARDNACRUSHA GIS 110-ARDNACRUSHA GIS 110-110K3 | 5 | 5 | 5 | Scheduled | 21/03/2022 | 25/03/2022
TO-22-BYH-110K1-01 | COUPLER/SECTIONALISING CB - BALLYNAHULLA 110-BALLYNAHULLA 110-110K1 | 5 | 5 | 5 | Scheduled | 21/03/2022 | 25/03/2022
TO-22-KNR-TRI-1-01 | 110kV FEEDER - KNOCKANURE 110-TRIEN 110-1 | 5 | 5 | 5 | Scheduled | 21/03/2022 | 25/03/2022
TO-22-110 kV A1/A2/A4 @ KNR-01 | BUSBAR SECTION - KNOCKANURE 110-KNOCKANURE 110-110A1-A2-A4 | 1 | 1 | 1 | Scheduled | 23/03/2022 | 23/03/2022
TO-22-110 kV B1/B2/B4 @ KNR-01 | BUSBAR SECTION - KNOCKANURE 110-KNOCKANURE 110-110B1-B2-B4 | 1 | 1 | 1 | Scheduled | 23/03/2022 | 23/03/2022
TO-22-220 kV A1/A2 @ KNR-01 | BUSBAR SECTION - KNOCKANURE 220-KNOCKANURE 220-220A1-A2 | 1 | 1 | 1 | Scheduled | 23/03/2022 | 23/03/2022
TO-22-220 kV B1/B2 @ KNR-01 | BUSBAR SECTION - KNOCKANURE 220-KNOCKANURE 220-220B1-B2 | 1 | 1 | 1 | Scheduled | 23/03/2022 | 23/03/2022
TO-22-220 kV A1 @ KLN-01 | BUSBAR SECTION - KILLONAN 220-KILLONAN 220-220A1 | 5 | 5 | 5 | Scheduled | 28/03/2022 | 01/04/2022
TO-22-220 kV A2 @ KLN-01 | BUSBAR SECTION - KILLONAN 220-KILLONAN 220-220A2 | 5 | 5 | 9 | Scheduled | 28/03/2022 | 01/04/2022
TO-22-220 kV B1 @ KLN-01 | BUSBAR SECTION - KILLONAN 220-KILLONAN 220-220B1 | 5 | 5 | 9 | Scheduled | 28/03/2022 | 01/04/2022
TO-22-220 kV B2 @ KLN-01 | BUSBAR SECTION - KILLONAN 220-KILLONAN 220-220B2 | 5 | 5 | 5 | Scheduled | 28/03/2022 | 01/04/2022
TO-22-KPG-RAT-1-01 | 110kV FEEDER - KILPADDOGE 110-RATHKEALE 110-1 | 4 | 4 |  | Scheduled | 28/03/2022 | 31/03/2022
TO-22-KPG-TRL-2-01 | 110kV FEEDER - KILPADDOGE 110-TRALEE 110-2 | 5 | 5 | 5 | Scheduled | 28/03/2022 | 01/04/2022
TO-22-AA GIS-T104-01 | GENERATOR TRANSFORMER - ARDNACRUSHA GIS 110-ARDNACRUSHA GIS G4-T104 | 54 | 37 | 37 | Scheduled | 04/04/2022 | 27/05/2022
TO-22-CHA-GLE-1-01 | 110kV FEEDER - CHARLEVILLE 110-GLENLARA 110-1 | 9 | 7 | 7 | Scheduled | 04/04/2022 | 12/04/2022
TO-22-CLA-CKN-1-01 | 110kV FEEDER - CLASHAVOON 110-CLONKEEN 110-1 | 12 | 9 | 12 | Scheduled | 04/04/2022 | 15/04/2022
TO-22-KPG-TB-1-03 | 220kV FEEDER - KILPADDOGE 220-TARBERT 220-1 | 5 | 5 | 5 | Scheduled | 04/04/2022 | 08/04/2022
TO-22-KPG-TRL-1-02 | 110kV FEEDER - KILPADDOGE 110-TRALEE 110-1 | 10 | 8 | 8 | Scheduled | 04/04/2022 | 13/04/2022
TO-22-KPG-TB-1-01 | 220kV FEEDER - KILPADDOGE 220-TARBERT 220-1 | 168 | 115 | 115 | Scheduled | 05/04/2022 | 19/09/2022
TO-22-220 kV A1 @ TB-01 | BUSBAR SECTION - TARBERT 220-TARBERT 220-220A1 | 168 | 115 | 115 | Scheduled | 05/04/2022 | 19/09/2022
TO-22-220 kV B1 @ TB-01 | BUSBAR SECTION - TARBERT 220-TARBERT 220-220B1 | 168 | 115 | 115 | Scheduled | 05/04/2022 | 19/09/2022
TO-22-MP GIS-T4002-01 | GENERATOR TRANSFORMER - MONEYPOINT GIS 400-MONEYPOINT GIS G2-T4002 | 3 | 3 | 3 | Scheduled | 06/04/2022 | 08/04/2022
TO-22-TB-110K1-2-01 | COUPLER/SECTIONALISING CB - TARBERT 110-TARBERT 110-110K1-2 | 2 | 2 | 2 | Scheduled | 06/04/2022 | 07/04/2022
TO-22-CNO-KPG-1-01 | 110kV FEEDER - COOLNANOONAGH 110-KILPADDOGE 110-1 | 4 | 4 | 4 | Scheduled | 11/04/2022 | 14/04/2022
TO-22-CNO-T131-01 | GENERATOR TRANSFORMER - COOLNANOONAGH 110-COOLNANOONAGH 33-T131 | 4 | 4 | 4 | Scheduled | 11/04/2022 | 14/04/2022
TO-22-BOL-ENN-1-01 | 110kV FEEDER - BOOLTIAGH 110-ENNIS 110-1 | 2 | 2 | 2 | Scheduled | 13/04/2022 | 14/04/2022
TO-22-AA GIS-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - ARDNACRUSHA GIS 110-ARDNACRUSHA GIS 110-110SA1-2CB | 4 | 4 | 4 | Scheduled | 19/04/2022 | 22/04/2022
TO-22-AA GIS-LIM-1-01 | 110kV FEEDER - ARDNACRUSHA GIS 110-LIMERICK 110-1 | 15 | 10 | 10 | Scheduled | 19/04/2022 | 03/05/2022
TO-22-KLN-LIM-2-01 | 110kV FEEDER - KILLONAN 110-LIMERICK 110-2 | 15 | 10 | 10 | Scheduled | 19/04/2022 | 03/05/2022
TO-22-KPG-KNR-1-110-01 | 110kV FEEDER - KILPADDOGE 110-KNOCKANURE 110-1-110 | 7 | 5 | 5 | Scheduled | 19/04/2022 | 25/04/2022
TO-22-KPG-TB-2-01 | 220kV FEEDER - KILPADDOGE 220-TARBERT 220-2 | 3 | 3 |  | Scheduled | 19/04/2022 | 21/04/2022
TO-22-LIM-110SA1-01 | SECTIONALISING DISCONNECT - LIMERICK 110-LIMERICK 110-110SA1 | 15 | 10 | 10 | Scheduled | 19/04/2022 | 03/05/2022
TO-22-LIM-110SA2-01 | SECTIONALISING DISCONNECT - LIMERICK 110-LIMERICK 110-110SA2 | 15 | 10 | 10 | Scheduled | 19/04/2022 | 03/05/2022
TO-22-LIM-RAT-1-01 | 110kV FEEDER - LIMERICK 110-RATHKEALE 110-1 | 15 | 10 | 10 | Scheduled | 19/04/2022 | 03/05/2022
TO-22-LIM-T142-01 | DISTRIBUTION TRANSFORMER - LIMERICK 110-LIMERICK 38-T142 | 15 | 10 | 10 | Reference | 19/04/2022 | 03/05/2022
TO-22-AA GIS-T101-01 | GENERATOR TRANSFORMER - ARDNACRUSHA GIS 110-ARDNACRUSHA GIS G1-T101 | 5 | 5 | 5 | Scheduled | 25/04/2022 | 29/04/2022
TO-22-TB-T101-01 | GENERATOR TRANSFORMER - TARBERT 110-TARBERT G1-T101 | 5 | 5 | 5 | Scheduled | 25/04/2022 | 29/04/2022
TO-22-TB-T2101-01 | TRANSFORMER - TARBERT 220-TARBERT 110-T2101 | 5 | 5 | 5 | Scheduled | 25/04/2022 | 29/04/2022
TO-22-BVK-220SB1-2CB-01 | COUPLER/SECTIONALISING CB - BALLYVOUSKILL 220-BALLYVOUSKILL 220-220SB1-2CB | 4 | 4 | 4 | Scheduled | 26/04/2022 | 29/04/2022
TO-22-KNR-R2002-01 | CAPACITOR/SVC/REACTOR - KNOCKANURE 220-KNOCKANURE 220-R2002 | 2 | 2 | 2 | Scheduled | 27/04/2022 | 28/04/2022
TO-22-KNR-T2101-01 | TRANSFORMER - KNOCKANURE 220-KNOCKANURE 110-T2101 | 2 | 2 | 2 | Scheduled | 27/04/2022 | 28/04/2022
TO-22-AGL-ENN-1-01 | 110kV FEEDER - AGANNYGAL 110-ENNIS 110-1 | 11 | 9 | 4 | Scheduled | 03/05/2022 | 13/05/2022
TO-22-KLN-KRA-1-01 | 220kV FEEDER - KILLONAN 220-KNOCKRAHA 220-1 | 8 | 6 | 6 | Scheduled | 03/05/2022 | 10/05/2022
TO-22-OUG-T141-01 | DISTRIBUTION TRANSFORMER - OUGHTRAGH 110-OUGHTRAGH 38-T141 | 11 | 9 | 9 | Reference | 03/05/2022 | 13/05/2022
TO-22-OUG,T-KER-1-01 | 110kV FEEDER - OUGHTRAGH tee-KNOCKEARAGH 110-1 | 11 | 9 | 9 | Scheduled | 03/05/2022 | 13/05/2022
TO-22-OUG,T-OUG-1-01 | 110kV FEEDER - OUGHTRAGH tee-OUGHTRAGH 110-1 | 11 | 9 | 9 | Scheduled | 03/05/2022 | 13/05/2022
TO-22-OUG,T-TRL-1-01 | 110kV FEEDER - OUGHTRAGH tee-TRALEE 110-1 | 11 | 9 | 9 | Scheduled | 03/05/2022 | 13/05/2022
TO-22-REM-110SA1-01 | SECTIONALISING DISCONNECT - REAMORE 110-REAMORE 110-110SA1 | 4 | 4 | 4 | Scheduled | 03/05/2022 | 06/05/2022
TO-22-REM-110SA2-01 | SECTIONALISING DISCONNECT - REAMORE 110-REAMORE 110-110SA2 | 4 | 4 | 4 | Scheduled | 03/05/2022 | 06/05/2022
TO-22-REM-T141-01 | DISTRIBUTION TRANSFORMER - REAMORE 110-REAMORE 38-T141 | 4 | 4 | 4 | Reference | 03/05/2022 | 06/05/2022
TO-22-REM-T142-01 | DISTRIBUTION TRANSFORMER - REAMORE 110-REAMORE 38-T142 | 4 | 4 | 4 | Reference | 03/05/2022 | 06/05/2022
TO-22-REM-TRL-1-01 | 110kV FEEDER - REAMORE 110-TRALEE 110-1 | 4 | 4 | 4 | Scheduled | 03/05/2022 | 06/05/2022
TO-22-110 kV A1/A2 @ BVK-01 | BUSBAR SECTION - BALLYVOUSKILL 110-BALLYVOUSKILL 110-110A1-A2 | 1 | 1 | 1 | Scheduled | 04/05/2022 | 04/05/2022
TO-22-110 kV B1/B2 @ BVK-01 | BUSBAR SECTION - BALLYVOUSKILL 110-BALLYVOUSKILL 110-110B1-B2 | 1 | 1 | 1 | Scheduled | 04/05/2022 | 04/05/2022
TO-22-220 kV A1/A2 @ BVK-01 | BUSBAR SECTION - BALLYVOUSKILL 220-BALLYVOUSKILL 220-220A1-A2 | 1 | 1 | 1 | Scheduled | 04/05/2022 | 04/05/2022
TO-22-220 kV B1/B2 @ BVK-01 | BUSBAR SECTION - BALLYVOUSKILL 220-BALLYVOUSKILL 220-220B1-B2 | 1 | 1 | 1 | Scheduled | 04/05/2022 | 04/05/2022
TO-22-CLH-TRI-1-01 | 110kV FEEDER - CLAHANE 110-TRIEN 110-1 | 80 | 56 | 56 | Scheduled | 16/05/2022 | 03/08/2022
TO-22-110 kV A1 @ TRI-01 | BUSBAR SECTION - TRIEN 110-TRIEN 110-110A1 | 80 | 56 | 56 | Scheduled | 16/05/2022 | 03/08/2022
TO-22-TRI-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - TRIEN 110-TRIEN 110-110SA1-2CB | 80 | 56 | 56 | Scheduled | 16/05/2022 | 03/08/2022
TO-22-TRI-T141-01 | DISTRIBUTION TRANSFORMER - TRIEN 110-TRIEN 38-T141 | 80 | 56 | 56 | Reference | 16/05/2022 | 03/08/2022
TO-22-ATE-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - ATHEA 110-ATHEA 110-110SA1-2CB | 4 | 4 | 4 | Scheduled | 17/05/2022 | 20/05/2022
TO-22-ATE-DRO-1-01 | 110kV FEEDER - ATHEA 110-DROMADA 110-1 | 4 | 4 | 4 | Scheduled | 17/05/2022 | 20/05/2022
TO-22-ATE-KNR-1-01 | 110kV FEEDER - ATHEA 110-KNOCKANURE 110-1 | 4 | 4 | 4 | Scheduled | 17/05/2022 | 20/05/2022
TO-22-ATE-T121-01 | GENERATOR TRANSFORMER - ATHEA 110-ATHEA 20-T121 | 4 | 4 | 4 | Scheduled | 17/05/2022 | 20/05/2022
TO-22-ATE-TOB-1-01 | 110kV FEEDER - ATHEA 110-TOBERTOREEN 110-1 | 4 | 4 | 4 | Scheduled | 17/05/2022 | 20/05/2022
TO-22-DRO-T121-01 | GENERATOR TRANSFORMER - DROMADA 110-DROMADA 20-T121 | 4 | 4 | 4 | Scheduled | 17/05/2022 | 20/05/2022
TO-22-TOB-T132-01 | GENERATOR TRANSFORMER - TOBERTOREEN 110-TOBERTOREEN 33-T132 | 4 | 4 | 4 | Scheduled | 17/05/2022 | 20/05/2022
TO-22-110 kV B1 @ AA GIS-01 | BUSBAR SECTION - ARDNACRUSHA GIS 110-ARDNACRUSHA GIS 110-110B1 | 1 | 1 | 1 | Scheduled | 18/05/2022 | 18/05/2022
TO-22-110 kV B3 @ AA GIS-01 | BUSBAR SECTION - ARDNACRUSHA GIS 110-ARDNACRUSHA GIS 110-110B3 | 1 | 1 | 1 | Scheduled | 18/05/2022 | 18/05/2022
TO-22-AA GIS-110SB1-3CB-02 | COUPLER/SECTIONALISING CB - ARDNACRUSHA GIS 110-ARDNACRUSHA GIS 110-110SB1-3CB | 1 | 1 | 1 | Scheduled | 18/05/2022 | 18/05/2022
TO-22-AA GIS-T103-02 | GENERATOR TRANSFORMER - ARDNACRUSHA GIS 110-ARDNACRUSHA GIS G3-T103 | 1 | 1 | 1 | Scheduled | 18/05/2022 | 18/05/2022
TO-22-CLH-T122-02 | GENERATOR TRANSFORMER - CLAHANE 110-CLAHANE 20-T122 | 1 | 1 | 1 | Scheduled | 18/05/2022 | 18/05/2022
TO-22-CAH-KHL-1-01 | 110kV FEEDER - CAHIR 110-KILL HILL 110-1 | 5 | 5 | 5 | Scheduled | 23/05/2022 | 27/05/2022
TO-22-110 kV A1 @ CBA-01 | BUSBAR SECTION - CLOGHBOOLA 110-CLOGHBOOLA 110-110A1 | 5 | 5 | 5 | Scheduled | 23/05/2022 | 27/05/2022
TO-22-110 kV A2 @ CBA-01 | BUSBAR SECTION - CLOGHBOOLA 110-CLOGHBOOLA 110-110A2 | 5 | 5 | 5 | Scheduled | 23/05/2022 | 27/05/2022
TO-22-CBA-110SA1-01 | SECTIONALISING DISCONNECT - CLOGHBOOLA 110-CLOGHBOOLA 110-110SA1 | 5 | 5 | 5 | Scheduled | 23/05/2022 | 27/05/2022
TO-22-CBA-110SA2-01 | SECTIONALISING DISCONNECT - CLOGHBOOLA 110-CLOGHBOOLA 110-110SA2 | 5 | 5 | 5 | Scheduled | 23/05/2022 | 27/05/2022
TO-22-CBA-T122-01 | DISTRIBUTION TRANSFORMER - CLOGHBOOLA 110-CLOGHBOOLA 20-T122 | 5 | 5 | 5 | Reference | 23/05/2022 | 27/05/2022
TO-22-CBA-T131-01 | GENERATOR TRANSFORMER - CLOGHBOOLA 110-CLOGHBOOLA 33-T131 | 5 | 5 | 5 | Scheduled | 23/05/2022 | 27/05/2022
TO-22-CBA-TRI-1-01 | 110kV FEEDER - CLOGHBOOLA 110-TRIEN 110-1 | 5 | 5 | 5 | Scheduled | 23/05/2022 | 27/05/2022
TO-22-MP GIS-T4201-01 | TRANSFORMER - MONEYPOINT GIS 400-MONEYPOINT GIS 220-T4201 | 12 | 10 | 10 | Scheduled | 23/05/2022 | 03/06/2022
TO-22-CHA-110SA1-2CB-02 | COUPLER/SECTIONALISING CB - CHARLEVILLE 110-CHARLEVILLE 110-110SA1-2CB | 4 | 4 | 4 | Scheduled | 24/05/2022 | 27/05/2022
TO-22-CNO-T131-02 | GENERATOR TRANSFORMER - COOLNANOONAGH 110-COOLNANOONAGH 33-T131 | 1 | 1 | 1 | Scheduled | 25/05/2022 | 25/05/2022
TO-22-GRO-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - GARROW 110-GARROW 110-110SA1-2CB | 5 | 5 | 5 | Scheduled | 30/05/2022 | 03/06/2022
TO-22-GRO-T121-01 | DISTRIBUTION TRANSFORMER - GARROW 110-GARROW 20-T121 | 5 | 5 | 5 | Reference | 30/05/2022 | 03/06/2022
TO-22-GRO-T122-01 | GENERATOR TRANSFORMER - GARROW 110-GARROW 20-T122 | 5 | 5 | 5 | Scheduled | 30/05/2022 | 03/06/2022
TO-22-KLN-SH-1-01 | 220kV FEEDER - KILLONAN 220-SHANNONBRIDGE 220-1 | 13 | 9 | 9 | Scheduled | 30/05/2022 | 11/06/2022
TO-22-BYH-GLE-1-02 | 110kV FEEDER - BALLYNAHULLA 110-GLENLARA 110-1 | 4 | 4 | 4 | Scheduled | 31/05/2022 | 03/06/2022
TO-22-MP GIS-400K3-02 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 400-MONEYPOINT GIS 400-400K3 | 1 | 1 | 1 | Scheduled | 01/06/2022 | 01/06/2022
TO-22-AUG-SK-3-01 | 110kV FEEDER - AUGHINISH 110-SEALROCK 110-3 | 4 | 4 | 4 | Scheduled | 07/06/2022 | 10/06/2022
TO-22-CTN-110SA1-02 | SECTIONALISING DISCONNECT - CAUTEEN 110-CAUTEEN 110-110SA1 | 4 | 4 | 4 | Scheduled | 07/06/2022 | 10/06/2022
TO-22-CTN-110SA2-01 | SECTIONALISING DISCONNECT - CAUTEEN 110-CAUTEEN 110-110SA2 | 4 | 4 | 4 | Scheduled | 07/06/2022 | 10/06/2022
TO-22-CTN-T142-01 | DISTRIBUTION TRANSFORMER - CAUTEEN 110-CAUTEEN 38-T142 | 4 | 4 | 4 | Reference | 07/06/2022 | 10/06/2022
TO-22-CTN-T144-01 | DISTRIBUTION TRANSFORMER - CAUTEEN 110-CAUTEEN 38-T144 | 4 | 4 | 4 | Reference | 07/06/2022 | 10/06/2022
TO-22-CTN-TIP-1-03 | 110kV FEEDER - CAUTEEN 110-TIPPERARY 110-1 | 11 | 9 | 9 | Scheduled | 07/06/2022 | 17/06/2022
TO-22-MP GIS-T4202-02 | TRANSFORMER - MONEYPOINT GIS 400-MONEYPOINT GIS 220-T4202 | 8 | 6 | 6 | Scheduled | 07/06/2022 | 14/06/2022
TO-22-SK-T103-01 | GENERATOR TRANSFORMER - SEALROCK 110-SEALROCK G3-T103 | 4 | 4 | 4 | Scheduled | 07/06/2022 | 10/06/2022
TO-22-MP GIS-400SA1-2CB-01 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 400-MONEYPOINT GIS 400-400SA1-2CB | 1 | 1 | 1 | Scheduled | 08/06/2022 | 08/06/2022
TO-22-MP GIS-220SB1-2CB-01 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 220-MONEYPOINT GIS 220-220SB1-2CB | 1 | 1 | 1 | Scheduled | 09/06/2022 | 09/06/2022
TO-22-MP GIS-400SA2-4CB-02 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 400-MONEYPOINT GIS 400-400SA2-4CB | 1 | 1 | 1 | Scheduled | 10/06/2022 | 10/06/2022
TO-22-AA GIS-T102-01 | GENERATOR TRANSFORMER - ARDNACRUSHA GIS 110-ARDNACRUSHA GIS G2-T102 | 12 | 10 | 10 | Scheduled | 13/06/2022 | 24/06/2022
TO-22-AUG-CFM-1-01 | 110kV FEEDER - AUGHINISH 110-CASTLEFARM 110-1 | 12 | 10 | 10 | Scheduled | 13/06/2022 | 24/06/2022
TO-22-AUG-MTN-1-01 | 110kV FEEDER - AUGHINISH 110-MONETEEN 110-1 | 5 | 5 | 5 | Scheduled | 13/06/2022 | 17/06/2022
TO-22-CFM-T101-01 | TSO CUSTOMER TRANSFORMER - CASTLEFARM 110-CASTLEFARM 10-T101 | 12 | 10 | 10 | Reference | 13/06/2022 | 24/06/2022
TO-22-ENN-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - ENNIS 110-ENNIS 110-110SA1-2CB | 2 | 2 | 2 | Scheduled | 13/06/2022 | 14/06/2022
TO-22-ENN-SLC-1-01 | 110kV FEEDER - ENNIS 110-SLIEVECALLAN 110-1 | 12 | 10 | 10 | Scheduled | 13/06/2022 | 24/06/2022
TO-22-GLE-T141-01 | DISTRIBUTION TRANSFORMER - GLENLARA 110-GLENLARA 38-T141 | 5 | 5 | 5 | Reference | 13/06/2022 | 17/06/2022
TO-22-MTN-110SA1-01 | SECTIONALISING DISCONNECT - MONETEEN 110-MONETEEN 110-110SA1 | 5 | 5 | 5 | Scheduled | 13/06/2022 | 17/06/2022
TO-22-MTN-110SA2-01 | SECTIONALISING DISCONNECT - MONETEEN 110-MONETEEN 110-110SA2 | 5 | 5 | 5 | Scheduled | 13/06/2022 | 17/06/2022
TO-22-MTN-MUN-1-01 | 110kV FEEDER - MONETEEN 110-MUNGRET 110-1 | 5 | 5 | 5 | Scheduled | 13/06/2022 | 17/06/2022
TO-22-MUN-T101-01 | TSO CUSTOMER TRANSFORMER - MUNGRET 110-MUNGRET 10-T101 | 5 | 5 | 5 | Reference | 13/06/2022 | 17/06/2022
TO-22-SLC-110SA1-01 | SECTIONALISING DISCONNECT - SLIEVECALLAN 110-SLIEVECALLAN 110-110SA1 | 12 | 10 | 10 | Scheduled | 13/06/2022 | 24/06/2022
TO-22-SLC-110SA2-01 | SECTIONALISING DISCONNECT - SLIEVECALLAN 110-SLIEVECALLAN 110-110SA2 | 12 | 10 | 10 | Scheduled | 13/06/2022 | 24/06/2022
TO-22-SLC-T121-01 | GENERATOR TRANSFORMER - SLIEVECALLAN 110-SLIEVECALLAN 20-T121 | 12 | 10 | 10 | Scheduled | 13/06/2022 | 24/06/2022
TO-22-SLC-T122-01 | GENERATOR TRANSFORMER - SLIEVECALLAN 110-SLIEVECALLAN 20-T122 | 12 | 10 | 10 | Scheduled | 13/06/2022 | 24/06/2022
TO-22-BYH-BVK-1-01 | 220kV FEEDER - BALLYNAHULLA 220-BALLYVOUSKILL 220-1 | 106 | 75 |  | Scheduled | 15/06/2022 | 28/09/2022
TO-22-KLN-KPG-1-02 | 220kV FEEDER - KILLONAN 220-KILPADDOGE 220-1 | 1 | 1 | 1 | Scheduled | 15/06/2022 | 15/06/2022
TO-22-KLN-T2101-03 | TRANSFORMER - KILLONAN 220-KILLONAN 110-T2101 | 1 | 1 | 1 | Scheduled | 15/06/2022 | 15/06/2022
TO-22-KLN-T2103-01 | TRANSFORMER - KILLONAN 220-KILLONAN 110-T2103 | 23 | 17 | 17 | Scheduled | 16/06/2022 | 08/07/2022
TO-22-AA GIS-ENN-1-01 | 110kV FEEDER - ARDNACRUSHA GIS 110-ENNIS 110-1 | 5 | 5 | 5 | Scheduled | 20/06/2022 | 24/06/2022
TO-22-CTN-110SA1-01 | SECTIONALISING DISCONNECT - CAUTEEN 110-CAUTEEN 110-110SA1 | 2 | 2 | 2 | Tentative | 20/06/2022 | 21/06/2022
TO-22-CTN-110SA2-02 | SECTIONALISING DISCONNECT - CAUTEEN 110-CAUTEEN 110-110SA2 | 2 | 2 | 2 | Tentative | 20/06/2022 | 21/06/2022
TO-22-CTN-KLN-1-01 | 110kV FEEDER - CAUTEEN 110-KILLONAN 110-1 | 10 | 8 | 8 | Scheduled | 20/06/2022 | 29/06/2022
TO-22-CTN-T141-01 | DISTRIBUTION TRANSFORMER - CAUTEEN 110-CAUTEEN 38-T141 | 2 | 2 | 2 | Reference (Tentative) | 20/06/2022 | 21/06/2022
TO-22-220 kV A4 @ KPG-01 | BUSBAR SECTION - KILPADDOGE 220-KILPADDOGE 220-220A4 | 5 | 5 | 5 | Scheduled | 20/06/2022 | 24/06/2022
TO-22-220 kV B4 @ KPG-01 | BUSBAR SECTION - KILPADDOGE 220-KILPADDOGE 220-220B4 | 5 | 5 | 5 | Scheduled | 20/06/2022 | 24/06/2022
TO-22-KPG-MP GIS-2-03 | 220kV FEEDER - KILPADDOGE 220-MONEYPOINT GIS 220-2 | 5 | 5 | 5 | Scheduled | 20/06/2022 | 24/06/2022
TO-22-220 kV A2 @ MP GIS-01 | BUSBAR SECTION - MONEYPOINT GIS 220-MONEYPOINT GIS 220-220A2 | 3 | 3 | 3 | Scheduled | 20/06/2022 | 22/06/2022
TO-22-220 kV B2 @ MP GIS-01 | BUSBAR SECTION - MONEYPOINT GIS 220-MONEYPOINT GIS 220-220B2 | 3 | 3 | 3 | Scheduled | 20/06/2022 | 22/06/2022
TO-22-MP GIS-220K2-01 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 220-MONEYPOINT GIS 220-220K2 | 2 | 2 | 2 | Scheduled | 21/06/2022 | 22/06/2022
TO-22-MP GIS-400SB1-2CB-01 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 400-MONEYPOINT GIS 400-400SB1-2CB | 2 | 2 | 2 | Scheduled | 23/06/2022 | 24/06/2022
TO-22-AA GIS-DRU-1-01 | 110kV FEEDER - ARDNACRUSHA GIS 110-DRUMLINE 110-1 | 5 | 5 | 5 | Scheduled | 27/06/2022 | 01/07/2022
TO-22-AUG-KPG-1-01 | 110kV FEEDER - AUGHINISH 110-KILPADDOGE 110-1 | 5 | 5 | 5 | Scheduled | 27/06/2022 | 01/07/2022
TO-22-DRU-110SA1-01 | SECTIONALISING DISCONNECT - DRUMLINE 110-DRUMLINE 110-110SA1 | 5 | 5 | 5 | Scheduled | 27/06/2022 | 01/07/2022
TO-22-DRU-110SA2-02 | SECTIONALISING DISCONNECT - DRUMLINE 110-DRUMLINE 110-110SA2 | 5 | 5 | 5 | Scheduled | 27/06/2022 | 01/07/2022
TO-22-DRU-CAP2-01 | CAPACITOR/SVC/REACTOR - DRUMLINE 110-DRUMLINE 110-CAP2 | 5 | 5 | 5 | Scheduled | 27/06/2022 | 01/07/2022
TO-22-DRU-T142-01 | DISTRIBUTION TRANSFORMER - DRUMLINE 110-DRUMLINE 38-T142 | 5 | 5 | 5 | Reference | 27/06/2022 | 01/07/2022
TO-22-MP GIS-T121-02 | GENERATOR TRANSFORMER - MONEYPOINT GIS 110-MONEYPOINT GIS 20-T121 | 2 | 2 | 2 | Scheduled | 28/06/2022 | 29/06/2022
TO-22-AA GIS-SNG-1-01 | 110kV FEEDER - ARDNACRUSHA GIS 110-SINGLAND 110-1 | 5 | 5 | 5 | Scheduled | 04/07/2022 | 08/07/2022
TO-22-KPG-TB-2-02 | 220kV FEEDER - KILPADDOGE 220-TARBERT 220-2 | 7 | 5 | 5 | Scheduled | 15/07/2022 | 21/07/2022
TO-22-CLA-CKN-1-02 | 110kV FEEDER - CLASHAVOON 110-CLONKEEN 110-1 | 5 | 5 | 5 | Scheduled | 18/07/2022 | 22/07/2022
TO-22-CKN-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - CLONKEEN 110-CLONKEEN 110-110SA1-2CB | 5 | 5 | 5 | Scheduled | 18/07/2022 | 22/07/2022
TO-22-CKN-CGL-1-01 | 110kV FEEDER - CLONKEEN 110-COOMAGEARLAHY 110-1 | 5 | 5 | 5 | Scheduled | 18/07/2022 | 22/07/2022
TO-22-CKN-GRO-1-01 | 110kV FEEDER - CLONKEEN 110-GARROW 110-1 | 5 | 5 | 5 | Scheduled | 18/07/2022 | 22/07/2022
TO-22-CKN-KER-1-01 | 110kV FEEDER - CLONKEEN 110-KNOCKEARAGH 110-1 | 5 | 5 | 5 | Scheduled | 18/07/2022 | 22/07/2022
TO-22-CGL-110SA1-01 | SECTIONALISING DISCONNECT - COOMAGEARLAHY 110-COOMAGEARLAHY 110-110SA1 | 5 | 5 | 5 | Scheduled | 18/07/2022 | 22/07/2022
TO-22-CGL-110SA2-01 | SECTIONALISING DISCONNECT - COOMAGEARLAHY 110-COOMAGEARLAHY 110-110SA2 | 5 | 5 | 5 | Scheduled | 18/07/2022 | 22/07/2022
TO-22-CGL-GAE-1-01 | 110kV FEEDER - COOMAGEARLAHY 110-GLANLEE 110-1 | 5 | 5 | 5 | Scheduled | 18/07/2022 | 22/07/2022
TO-22-CGL-T121-01 | GENERATOR TRANSFORMER - COOMAGEARLAHY 110-COOMAGEARLAHY 20-T121 | 5 | 5 | 5 | Scheduled | 18/07/2022 | 22/07/2022
TO-22-CGL-T122-01 | GENERATOR TRANSFORMER - COOMAGEARLAHY 110-COOMAGEARLAHY 20-T122 | 5 | 5 | 5 | Scheduled | 18/07/2022 | 22/07/2022
TO-22-GAE-T121-01 | GENERATOR TRANSFORMER - GLANLEE 110-GLANLEE 20-T121 | 5 | 5 | 5 | Scheduled | 18/07/2022 | 22/07/2022
TO-22-THU-CAP1-01 | CAPACITOR/SVC/REACTOR - THURLES 110-THURLES 110-CAP1 | 5 | 5 | 5 | Scheduled | 18/07/2022 | 22/07/2022
TO-22-110 kV B1 @ KPG-01 | BUSBAR SECTION - KILPADDOGE 110-KILPADDOGE 110-110B1 | 4 | 4 | 4 | Scheduled | 25/07/2022 | 28/07/2022
TO-22-110 kV B2 @ KPG-02 | BUSBAR SECTION - KILPADDOGE 110-KILPADDOGE 110-110B2 | 4 | 4 | 4 | Scheduled | 25/07/2022 | 28/07/2022
TO-22-KPG-110SB1-2CB-01 | COUPLER/SECTIONALISING CB - KILPADDOGE 110-KILPADDOGE 110-110SB1-2CB | 4 | 4 | 4 | Scheduled | 25/07/2022 | 28/07/2022
TO-22-MP GIS-OST-1-02 | 400kV FEEDER - MONEYPOINT GIS 400-OLDSTREET 400-1 | 5 | 5 | 5 | Scheduled | 25/07/2022 | 29/07/2022
TO-22-BVK-110K2-01 | COUPLER/SECTIONALISING CB - BALLYVOUSKILL 110-BALLYVOUSKILL 110-110K2 | 4 | 4 | 4 | Scheduled | 26/07/2022 | 29/07/2022
TO-22-110 kV A1 @ BYH-02 | BUSBAR SECTION - BALLYNAHULLA 110-BALLYNAHULLA 110-110A1 | 4 | 4 | 4 | Scheduled | 02/08/2022 | 05/08/2022
TO-22-110 kV A2 @ BYH-03 | BUSBAR SECTION - BALLYNAHULLA 110-BALLYNAHULLA 110-110A2 | 4 | 4 | 4 | Scheduled | 02/08/2022 | 05/08/2022
TO-22-110 kV A2 @ BYH-02 | BUSBAR SECTION - BALLYNAHULLA 110-BALLYNAHULLA 110-110A2 | 4 | 4 | 4 | Scheduled | 02/08/2022 | 05/08/2022
TO-22-110 kV B1 @ BYH-02 | BUSBAR SECTION - BALLYNAHULLA 110-BALLYNAHULLA 110-110B1 | 4 | 4 | 4 | Scheduled | 02/08/2022 | 05/08/2022
TO-22-110 kV B2 @ BYH-02 | BUSBAR SECTION - BALLYNAHULLA 110-BALLYNAHULLA 110-110B2 | 4 | 4 | 4 | Scheduled | 02/08/2022 | 05/08/2022
TO-22-110 kV B2 @ BYH-03 | BUSBAR SECTION - BALLYNAHULLA 110-BALLYNAHULLA 110-110B2 | 4 | 4 | 4 | Scheduled | 02/08/2022 | 05/08/2022
TO-22-BYH-110K2-02 | COUPLER/SECTIONALISING CB - BALLYNAHULLA 110-BALLYNAHULLA 110-110K2 | 4 | 4 | 4 | Scheduled | 02/08/2022 | 05/08/2022
TO-22-BYH-110SA1-2CB-02 | COUPLER/SECTIONALISING CB - BALLYNAHULLA 110-BALLYNAHULLA 110-110SA1-2CB | 4 | 4 | 4 | Scheduled | 02/08/2022 | 05/08/2022
TO-22-BYH-110SB1-2CB-02 | COUPLER/SECTIONALISING CB - BALLYNAHULLA 110-BALLYNAHULLA 110-110SB1-2CB | 4 | 4 | 4 | Scheduled | 02/08/2022 | 05/08/2022
TO-22-CSH-ENN-1-01 | 110kV FEEDER - CASHLA 110-ENNIS 110-1 | 3 | 3 | 3 | Scheduled | 02/08/2022 | 04/08/2022
TO-22-220 kV A2 @ TB-03 | BUSBAR SECTION - TARBERT 220-TARBERT 220-220A2 | 4 | 4 | 4 | Scheduled | 02/08/2022 | 05/08/2022
TO-22-220 kV B2 @ TB-03 | BUSBAR SECTION - TARBERT 220-TARBERT 220-220B2 | 4 | 4 | 4 | Scheduled | 02/08/2022 | 05/08/2022
TO-22-TB-T2003-02 | GENERATOR TRANSFORMER - TARBERT 220-TARBERT G3-T2003 | 25 | 19 | 19 | Scheduled | 02/08/2022 | 26/08/2022
TO-22-KNR-TRI-2-01 | 110kV FEEDER - KNOCKANURE 110-TRIEN 110-2 | 70 | 50 | 50 | Scheduled | 04/08/2022 | 12/10/2022
TO-22-TRI-T142-01 | DISTRIBUTION TRANSFORMER - TRIEN 110-TRIEN 38-T142 | 70 | 50 | 50 | Reference | 04/08/2022 | 12/10/2022
TO-22-LIM-MTN-1-01 | 110kV FEEDER - LIMERICK 110-MONETEEN 110-1 | 3 | 3 | 3 | Scheduled | 08/08/2022 | 10/08/2022
TO-22-BYH-T2101-03 | TRANSFORMER - BALLYNAHULLA 220-BALLYNAHULLA 110-T2101 | 1 | 1 | 1 | Scheduled | 09/08/2022 | 09/08/2022
TO-22-BVK-110K1-02 | COUPLER/SECTIONALISING CB - BALLYVOUSKILL 110-BALLYVOUSKILL 110-110K1 | 4 | 4 | 4 | Scheduled | 09/08/2022 | 12/08/2022
TO-22-220 kV A1/A2 @ KLN-01 | BUSBAR SECTION - KILLONAN 220-KILLONAN 220-220A1-A2 | 1 | 1 | 1 | Scheduled | 10/08/2022 | 10/08/2022
TO-22-220 kV B1/B2 @ KLN-01 | BUSBAR SECTION - KILLONAN 220-KILLONAN 220-220B1-B2 | 1 | 1 | 1 | Scheduled | 10/08/2022 | 10/08/2022
TO-22-BVK-220K1-01 | COUPLER/SECTIONALISING CB - BALLYVOUSKILL 220-BALLYVOUSKILL 220-220K1 | 1 | 1 | 1 | Scheduled | 11/08/2022 | 11/08/2022
TO-22-BYH-220K1-03 | COUPLER/SECTIONALISING CB - BALLYNAHULLA 220-BALLYNAHULLA 220-220K1 | 1 | 1 | 1 | Scheduled | 12/08/2022 | 12/08/2022
TO-22-BVK-COT-1-03 | 110kV FEEDER - BALLYVOUSKILL 110-COOMATAGGART 110-1 | 5 | 5 | 5 | Scheduled | 15/08/2022 | 19/08/2022
TO-22-COT-110SA1-01 | SECTIONALISING DISCONNECT - COOMATAGGART 110-COOMATAGGART 110-110SA1 | 5 | 5 | 5 | Scheduled | 15/08/2022 | 19/08/2022
TO-22-COT-110SA2-01 | SECTIONALISING DISCONNECT - COOMATAGGART 110-COOMATAGGART 110-110SA2 | 5 | 5 | 5 | Scheduled | 15/08/2022 | 19/08/2022
TO-22-COT-FILTER1-01 | CAPACITOR/SVC/REACTOR - COOMATAGGART 110-COOMATAGGART 110-FILTER1 | 5 | 5 | 5 | Scheduled | 15/08/2022 | 19/08/2022
TO-22-COT-T132-01 | GENERATOR TRANSFORMER - COOMATAGGART 110-COOMATAGGART 33-T132 | 5 | 5 | 5 | Scheduled | 15/08/2022 | 19/08/2022
TO-22-COT-T141-01 | DISTRIBUTION TRANSFORMER - COOMATAGGART 110-COOMATAGGART 38-T141 | 5 | 5 | 5 | Reference | 15/08/2022 | 19/08/2022
TO-22-DRU-110SA1-02 | SECTIONALISING DISCONNECT - DRUMLINE 110-DRUMLINE 110-110SA1 | 5 | 5 | 5 | Scheduled | 15/08/2022 | 19/08/2022
TO-22-DRU-110SA2-01 | SECTIONALISING DISCONNECT - DRUMLINE 110-DRUMLINE 110-110SA2 | 5 | 5 | 5 | Scheduled | 15/08/2022 | 19/08/2022
TO-22-DRU-ENN-1-01 | 110kV FEEDER - DRUMLINE 110-ENNIS 110-1 | 5 | 5 | 5 | Scheduled | 15/08/2022 | 19/08/2022
TO-22-DRU-T141-01 | DISTRIBUTION TRANSFORMER - DRUMLINE 110-DRUMLINE 38-T141 | 5 | 5 | 5 | Reference | 15/08/2022 | 19/08/2022
TO-22-GLE-KCR-1-01 | 110kV FEEDER - GLENLARA 110-KNOCKACUMMER 110-1 | 5 | 5 | 5 | Scheduled | 15/08/2022 | 19/08/2022
TO-22-KLN-LIM-2-02 | 110kV FEEDER - KILLONAN 110-LIMERICK 110-2 | 12 | 10 | 10 | Scheduled | 15/08/2022 | 26/08/2022
TO-22-KCR-T121-01 | GENERATOR TRANSFORMER - KNOCKACUMMER 110-KNOCKACUMMER 20-T121 | 5 | 5 | 5 | Scheduled | 15/08/2022 | 19/08/2022
TO-22-110 kV A1 @ AA GIS-01 | BUSBAR SECTION - ARDNACRUSHA GIS 110-ARDNACRUSHA GIS 110-110A1 | 5 | 5 | 5 | Scheduled | 22/08/2022 | 26/08/2022
TO-22-110 kV A3 @ AA GIS-01 | BUSBAR SECTION - ARDNACRUSHA GIS 110-ARDNACRUSHA GIS 110-110A3 | 5 | 5 | 5 | Scheduled | 22/08/2022 | 26/08/2022
TO-22-AA GIS-110SA1-3CB-02 | COUPLER/SECTIONALISING CB - ARDNACRUSHA GIS 110-ARDNACRUSHA GIS 110-110SA1-3CB | 5 | 5 | 5 | Scheduled | 22/08/2022 | 26/08/2022
TO-22-BOL-110SA1-01 | SECTIONALISING DISCONNECT - BOOLTIAGH 110-BOOLTIAGH 110-110SA1 | 5 | 5 | 5 | Scheduled | 22/08/2022 | 26/08/2022
TO-22-BOL-110SA1-3CB-01 | COUPLER/SECTIONALISING CB - BOOLTIAGH 110-BOOLTIAGH 110-110SA1-3CB | 5 | 5 | 5 | Scheduled | 22/08/2022 | 26/08/2022
TO-22-BOL-110SA2-01 | SECTIONALISING DISCONNECT - BOOLTIAGH 110-BOOLTIAGH 110-110SA2 | 5 | 5 | 5 | Scheduled | 22/08/2022 | 26/08/2022
TO-22-BOL-T121-03 | GENERATOR TRANSFORMER - BOOLTIAGH 110-BOOLTIAGH 20-T121 | 5 | 5 | 5 | Scheduled | 22/08/2022 | 26/08/2022
TO-22-110 kV A3 @ KPG-02 | BUSBAR SECTION - KILPADDOGE 110-KILPADDOGE 110-110A3 | 4 | 4 | 4 | Scheduled | 22/08/2022 | 25/08/2022
TO-22-110 kV B3 @ KPG-01 | BUSBAR SECTION - KILPADDOGE 110-KILPADDOGE 110-110B3 | 4 | 4 | 4 | Scheduled | 22/08/2022 | 25/08/2022
TO-22-KPG-110K3-01 | COUPLER/SECTIONALISING CB - KILPADDOGE 110-KILPADDOGE 110-110K3 | 4 | 4 | 4 | Scheduled | 22/08/2022 | 25/08/2022
TO-22-110 kV A1 @ KPG-03 | BUSBAR SECTION - KILPADDOGE 110-KILPADDOGE 110-110A1 | 4 | 4 | 4 | Scheduled | 29/08/2022 | 01/09/2022
TO-22-110 kV B1 @ KPG-02 | BUSBAR SECTION - KILPADDOGE 110-KILPADDOGE 110-110B1 | 4 | 4 | 4 | Scheduled | 29/08/2022 | 01/09/2022
TO-22-220 kV A1 @ KPG-02 | BUSBAR SECTION - KILPADDOGE 220-KILPADDOGE 220-220A1 | 4 | 4 | 4 | Scheduled | 29/08/2022 | 01/09/2022
TO-22-220 kV B1 @ KPG-02 | BUSBAR SECTION - KILPADDOGE 220-KILPADDOGE 220-220B1 | 4 | 4 | 4 | Scheduled | 29/08/2022 | 01/09/2022
TO-22-KPG-T2101-01 | TRANSFORMER - KILPADDOGE 220-KILPADDOGE 110-T2101 | 8 | 6 | 6 | Scheduled | 29/08/2022 | 05/09/2022
TO-22-TRL-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - TRALEE 110-TRALEE 110-110SA1-2CB | 5 | 5 | 5 | Scheduled | 29/08/2022 | 02/09/2022
TO-22-TRL-T142-02 | DISTRIBUTION TRANSFORMER - TRALEE 110-TRALEE 38-T142 | 5 | 5 | 5 | Reference | 29/08/2022 | 02/09/2022
TO-22-LSN-T122-07 | GENERATOR TRANSFORMER - LISHEEN 110-LISHEEN 20-T122 | 3 | 3 | 3 | Scheduled | 30/08/2022 | 01/09/2022
TO-22-SNG-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - SINGLAND 110-SINGLAND 110-110SA1-2CB | 2 | 2 | 2 | Scheduled | 30/08/2022 | 31/08/2022
TO-22-SNG-T101-01 | DISTRIBUTION TRANSFORMER - SINGLAND 110-SINGLAND 10-T101 | 2 | 2 | 2 | Reference | 30/08/2022 | 31/08/2022
TO-22-KNR-220K1-02 | COUPLER/SECTIONALISING CB - KNOCKANURE 220-KNOCKANURE 220-220K1 | 2 | 2 | 2 | Scheduled | 31/08/2022 | 01/09/2022
TO-22-KLN-SH-1-03 | 220kV FEEDER - KILLONAN 220-SHANNONBRIDGE 220-1 | 1 | 1 | 1 | Scheduled | 02/09/2022 | 02/09/2022
TO-22-AA GIS-T103-01 | GENERATOR TRANSFORMER - ARDNACRUSHA GIS 110-ARDNACRUSHA GIS G3-T103 | 5 | 5 | 5 | Scheduled | 05/09/2022 | 09/09/2022
TO-22-110 kV A2 @ BYH-04 | BUSBAR SECTION - BALLYNAHULLA 110-BALLYNAHULLA 110-110A2 | 5 | 5 | 5 | Scheduled | 05/09/2022 | 09/09/2022
TO-22-110 kV B2 @ BYH-04 | BUSBAR SECTION - BALLYNAHULLA 110-BALLYNAHULLA 110-110B2 | 5 | 5 | 5 | Scheduled | 05/09/2022 | 09/09/2022
TO-22-BYH-CDL-1-02 | 110kV FEEDER - BALLYNAHULLA 110-CORDAL 110-1 | 5 | 5 |  | Scheduled | 05/09/2022 | 09/09/2022
TO-22-CDL-110SA1-02 | SECTIONALISING DISCONNECT - CORDAL 110-CORDAL 110-110SA1 | 5 | 5 |  | Scheduled | 05/09/2022 | 09/09/2022
TO-22-CDL-110SA2-02 | SECTIONALISING DISCONNECT - CORDAL 110-CORDAL 110-110SA2 | 5 | 5 |  | Scheduled | 05/09/2022 | 09/09/2022
TO-22-CDL-T132-02 | GENERATOR TRANSFORMER - CORDAL 110-CORDAL 33-T132 | 5 | 5 |  | Scheduled | 05/09/2022 | 09/09/2022
TO-22-CDL-T141-01 | DISTRIBUTION TRANSFORMER - CORDAL 110-CORDAL 38-T141 | 5 | 5 |  | Reference | 05/09/2022 | 09/09/2022
TO-22-CAH-TIP-1-02 | 110kV FEEDER - CAHIR 110-TIPPERARY 110-1 | 5 | 3 | 3 | Scheduled | 08/09/2022 | 12/09/2022
TO-22-110 kV A2 @ BYH-05 | BUSBAR SECTION - BALLYNAHULLA 110-BALLYNAHULLA 110-110A2 | 5 | 5 | 5 | Scheduled | 12/09/2022 | 16/09/2022
TO-22-110 kV B2 @ BYH-05 | BUSBAR SECTION - BALLYNAHULLA 110-BALLYNAHULLA 110-110B2 | 5 | 5 | 5 | Scheduled | 12/09/2022 | 16/09/2022
TO-22-220 kV A2 @ BYH-02 | BUSBAR SECTION - BALLYNAHULLA 220-BALLYNAHULLA 220-220A2 | 5 | 5 | 5 | Scheduled | 12/09/2022 | 16/09/2022
TO-22-220 kV B2 @ BYH-02 | BUSBAR SECTION - BALLYNAHULLA 220-BALLYNAHULLA 220-220B2 | 5 | 5 | 5 | Scheduled | 12/09/2022 | 16/09/2022
TO-22-BYH-T2102-03 | TRANSFORMER - BALLYNAHULLA 220-BALLYNAHULLA 110-T2102 | 5 | 5 |  | Scheduled | 12/09/2022 | 16/09/2022
TO-22-110 kV A2 @ KPG-02 | BUSBAR SECTION - KILPADDOGE 110-KILPADDOGE 110-110A2 | 8 | 6 | 6 | Scheduled | 12/09/2022 | 19/09/2022
TO-22-110 kV B2 @ KPG-01 | BUSBAR SECTION - KILPADDOGE 110-KILPADDOGE 110-110B2 | 8 | 6 | 6 | Scheduled | 12/09/2022 | 19/09/2022
TO-22-220 kV A2 @ KPG-02 | BUSBAR SECTION - KILPADDOGE 220-KILPADDOGE 220-220A2 | 8 | 6 | 6 | Scheduled | 12/09/2022 | 19/09/2022
TO-22-220 kV B2 @ KPG-02 | BUSBAR SECTION - KILPADDOGE 220-KILPADDOGE 220-220B2 | 8 | 6 | 6 | Scheduled | 12/09/2022 | 19/09/2022
TO-22-KPG-T2102-02 | TRANSFORMER - KILPADDOGE 220-KILPADDOGE 110-T2102 | 8 | 6 | 6 | Scheduled | 12/09/2022 | 19/09/2022
TO-22-TB-220K1-2-01 | COUPLER/SECTIONALISING CB - TARBERT 220-TARBERT 220-220K1-2 | 7 | 5 | 5 | Scheduled | 12/09/2022 | 18/09/2022
TO-22-TB-T2004-01 | GENERATOR TRANSFORMER - TARBERT 220-TARBERT G4-T2004 | 36 | 26 | 26 | Scheduled | 12/09/2022 | 17/10/2022
TO-22-TB-T2101-02 | TRANSFORMER - TARBERT 220-TARBERT 110-T2101 | 7 | 5 | 5 | Scheduled | 12/09/2022 | 18/09/2022
TO-22-IKE,T-THU-1-01 | 110kV FEEDER - IKERRIN tee-THURLES 110-1 | 15 | 11 | 11 | Scheduled | 13/09/2022 | 27/09/2022
TO-22-LSN-110SA2-4-01 | SECTIONALISING DISCONNECT - LISHEEN 110-LISHEEN 110-110SA2-4 | 15 | 11 | 11 | Scheduled | 13/09/2022 | 27/09/2022
TO-22-LSN-T122-01 | GENERATOR TRANSFORMER - LISHEEN 110-LISHEEN 20-T122 | 15 | 11 | 11 | Scheduled | 13/09/2022 | 27/09/2022
TO-22-LSN-T142-01 | DISTRIBUTION TRANSFORMER - LISHEEN 110-LISHEEN 38-T142 | 15 | 11 | 11 | Reference | 13/09/2022 | 27/09/2022
TO-22-LSN-THU-1-03 | 110kV FEEDER - LISHEEN 110-THURLES 110-1 | 3 | 3 | 3 | Scheduled | 13/09/2022 | 15/09/2022
TO-22-THU-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - THURLES 110-THURLES 110-110SA1-2CB | 15 | 11 | 11 | Scheduled | 13/09/2022 | 27/09/2022
TO-22-THU-CAP2-01 | CAPACITOR/SVC/REACTOR - THURLES 110-THURLES 110-CAP2 | 15 | 11 | 11 | Scheduled | 13/09/2022 | 27/09/2022
TO-22-THU-T142-01 | DISTRIBUTION TRANSFORMER - THURLES 110-THURLES 38-T142 | 15 | 11 | 11 | Reference | 13/09/2022 | 27/09/2022
TO-22-AUG-CFM-2-01 | 110kV FEEDER - AUGHINISH 110-CASTLEFARM 110-2 | 1 | 1 | 1 | Scheduled | 19/09/2022 | 19/09/2022
TO-22-CFM-T102-01 | TSO CUSTOMER TRANSFORMER - CASTLEFARM 110-CASTLEFARM 10-T102 | 5 | 5 | 5 | Reference | 19/09/2022 | 23/09/2022
TO-22-CFM-T102-02 | TSO CUSTOMER TRANSFORMER - CASTLEFARM 110-CASTLEFARM 10-T102 | 1 | 1 | 1 | Reference | 19/09/2022 | 19/09/2022
TO-22-110 kV A1 @ KPG-01 | BUSBAR SECTION - KILPADDOGE 110-KILPADDOGE 110-110A1 | 4 | 4 | 4 | Scheduled | 20/09/2022 | 23/09/2022
TO-22-110 kV A2 @ KPG-01 | BUSBAR SECTION - KILPADDOGE 110-KILPADDOGE 110-110A2 | 4 | 4 | 4 | Scheduled | 20/09/2022 | 23/09/2022
TO-22-KPG-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - KILPADDOGE 110-KILPADDOGE 110-110SA1-2CB | 4 | 4 | 4 | Scheduled | 20/09/2022 | 23/09/2022
TO-22-AUG-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - AUGHINISH 110-AUGHINISH 110-110SA1-2CB | 1 | 1 | 1 | Scheduled | 23/09/2022 | 23/09/2022
TO-22-AUG-SK-4-01 | 110kV FEEDER - AUGHINISH 110-SEALROCK 110-4 | 5 | 5 | 5 | Scheduled | 26/09/2022 | 30/09/2022
TO-22-400 kV A3 @ MP GIS-01 | BUSBAR SECTION - MONEYPOINT GIS 400-MONEYPOINT GIS 400-400A3 | 5 | 5 | 5 | Scheduled | 26/09/2022 | 30/09/2022
TO-22-400 kV B3 @ MP GIS-01 | BUSBAR SECTION - MONEYPOINT GIS 400-MONEYPOINT GIS 400-400B3 | 5 | 5 | 5 | Scheduled | 26/09/2022 | 30/09/2022
TO-22-MP GIS-T4003-01 | GENERATOR TRANSFORMER - MONEYPOINT GIS 400-MONEYPOINT GIS G3-T4003 | 18 | 14 | 14 | Proposed | 26/09/2022 | 13/10/2022
TO-22-SK-T104-01 | GENERATOR TRANSFORMER - SEALROCK 110-SEALROCK G4-T104 | 5 | 5 | 5 | Scheduled | 26/09/2022 | 30/09/2022
TO-22-220 kV A1 @ BVK-01 | BUSBAR SECTION - BALLYVOUSKILL 220-BALLYVOUSKILL 220-220A1 | 4 | 4 | 4 | Scheduled | 27/09/2022 | 30/09/2022
TO-22-220 kV A2 @ BVK-01 | BUSBAR SECTION - BALLYVOUSKILL 220-BALLYVOUSKILL 220-220A2 | 4 | 4 | 4 | Scheduled | 27/09/2022 | 30/09/2022
TO-22-BVK-220SA1-2CB-01 | COUPLER/SECTIONALISING CB - BALLYVOUSKILL 220-BALLYVOUSKILL 220-220SA1-2CB | 4 | 4 | 4 | Scheduled | 27/09/2022 | 30/09/2022
TO-22-110 kV A1 @ KPG-02 | BUSBAR SECTION - KILPADDOGE 110-KILPADDOGE 110-110A1 | 4 | 4 | 4 | Scheduled | 27/09/2022 | 30/09/2022
TO-22-110 kV A3 @ KPG-01 | BUSBAR SECTION - KILPADDOGE 110-KILPADDOGE 110-110A3 | 4 | 4 | 4 | Scheduled | 27/09/2022 | 30/09/2022
TO-22-KPG-110SA1-3CB-01 | COUPLER/SECTIONALISING CB - KILPADDOGE 110-KILPADDOGE 110-110SA1-3CB | 4 | 4 | 4 | Scheduled | 27/09/2022 | 30/09/2022
TO-22-220 kV A3 @ KPG-01 | BUSBAR SECTION - KILPADDOGE 220-KILPADDOGE 220-220A3 | 4 | 4 | 4 | Scheduled | 27/09/2022 | 30/09/2022
TO-22-220 kV B3 @ KPG-01 | BUSBAR SECTION - KILPADDOGE 220-KILPADDOGE 220-220B3 | 4 | 4 | 4 | Scheduled | 27/09/2022 | 30/09/2022
TO-22-KPG-220K3-01 | COUPLER/SECTIONALISING CB - KILPADDOGE 220-KILPADDOGE 220-220K3 | 4 | 4 | 4 | Scheduled | 27/09/2022 | 30/09/2022
TO-22-110 kV B1 @ AA GIS-02 | BUSBAR SECTION - ARDNACRUSHA GIS 110-ARDNACRUSHA GIS 110-110B1 | 1 | 1 | 1 | Proposed | 29/09/2022 | 29/09/2022
TO-22-110 kV B2 @ AA GIS-01 | BUSBAR SECTION - ARDNACRUSHA GIS 110-ARDNACRUSHA GIS 110-110B2 | 1 | 1 | 1 | Proposed | 29/09/2022 | 29/09/2022
TO-22-AA GIS-110K2-03 | COUPLER/SECTIONALISING CB - ARDNACRUSHA GIS 110-ARDNACRUSHA GIS 110-110K2 | 1 | 1 | 1 | Proposed | 29/09/2022 | 29/09/2022
TO-22-AA GIS-110SB1-2CB-02 | COUPLER/SECTIONALISING CB - ARDNACRUSHA GIS 110-ARDNACRUSHA GIS 110-110SB1-2CB | 1 | 1 | 1 | Proposed | 29/09/2022 | 29/09/2022
TO-22-AA GIS-ENN-1-02 | 110kV FEEDER - ARDNACRUSHA GIS 110-ENNIS 110-1 | 1 | 1 | 1 | Proposed | 29/09/2022 | 29/09/2022
TO-22-BVK-GRO-1-02 | 110kV FEEDER - BALLYVOUSKILL 110-GARROW 110-1 | 5 | 5 | 5 | Scheduled | 03/10/2022 | 07/10/2022
TO-22-CHA-GLE-1-02 | 110kV FEEDER - CHARLEVILLE 110-GLENLARA 110-1 | 12 | 10 | 10 | Proposed | 03/10/2022 | 14/10/2022
TO-22-KHL-THU-1-03 | 110kV FEEDER - KILL HILL 110-THURLES 110-1 | 12 | 10 | 10 | Proposed | 03/10/2022 | 14/10/2022
TO-22-220 kV A1 @ KPG-01 | BUSBAR SECTION - KILPADDOGE 220-KILPADDOGE 220-220A1 | 5 | 5 | 5 | Scheduled | 03/10/2022 | 07/10/2022
TO-22-220 kV B1 @ KPG-01 | BUSBAR SECTION - KILPADDOGE 220-KILPADDOGE 220-220B1 | 5 | 5 | 5 | Scheduled | 03/10/2022 | 07/10/2022
TO-22-KPG-KNR-1-01 | 220kV FEEDER - KILPADDOGE 220-KNOCKANURE 220-1 | 5 | 5 | 5 | Scheduled | 03/10/2022 | 07/10/2022
TO-22-PRO-TB-1-03 | 220kV FEEDER - PROSPECT 220-TARBERT 220-1 | 10 | 8 | 8 | Scheduled | 03/10/2022 | 12/10/2022
TO-22-KLN-NEN-1-03 | 110kV FEEDER - KILLONAN 110-NENAGH 110-1 | 2 | 2 | 2 | Reference | 04/10/2022 | 05/10/2022
TO-22-NEN-T141-02 | DISTRIBUTION TRANSFORMER - NENAGH 110-NENAGH 38-T141 | 2 | 2 | 2 | Reference | 04/10/2022 | 05/10/2022
TO-22-220 kV A1 @ TB-03 | BUSBAR SECTION - TARBERT 220-TARBERT 220-220A1 | 14 | 10 | 10 | Scheduled | 04/10/2022 | 17/10/2022
TO-22-220 kV B1 @ TB-03 | BUSBAR SECTION - TARBERT 220-TARBERT 220-220B1 | 14 | 10 | 10 | Scheduled | 04/10/2022 | 17/10/2022
TO-22-BVK-R2001-01 | CAPACITOR/SVC/REACTOR - BALLYVOUSKILL 220-BALLYVOUSKILL 220-R2001 | 3 | 3 | 3 | Scheduled | 10/10/2022 | 12/10/2022
TO-22-THU-110SA1-2CB-04 | COUPLER/SECTIONALISING CB - THURLES 110-THURLES 110-110SA1-2CB | 5 | 5 | 5 | Proposed | 10/10/2022 | 14/10/2022
TO-22-THU-CAP1-02 | CAPACITOR/SVC/REACTOR - THURLES 110-THURLES 110-CAP1 | 5 | 5 | 5 | Proposed | 10/10/2022 | 14/10/2022
TO-22-THU-T141-01 | DISTRIBUTION TRANSFORMER - THURLES 110-THURLES 38-T141 | 5 | 5 | 5 | Reference (Proposed) | 10/10/2022 | 14/10/2022
TO-22-CLH-TRL-1-02 | 110kV FEEDER - CLAHANE 110-TRALEE 110-1 | 9 | 7 | 7 | Proposed | 13/10/2022 | 21/10/2022
TO-22-KLN-KPG-1-01 | 220kV FEEDER - KILLONAN 220-KILPADDOGE 220-1 | 5 | 5 | 5 | Proposed | 17/10/2022 | 21/10/2022
TO-22-AUG-SK-3-02 | 110kV FEEDER - AUGHINISH 110-SEALROCK 110-3 | 3 | 3 | 3 | Proposed | 24/10/2022 | 26/10/2022
TO-22-BVK-CLA-1-01 | 220kV FEEDER - BALLYVOUSKILL 220-CLASHAVOON 220-1 | 5 | 5 | 5 | Scheduled | 24/10/2022 | 28/10/2022
TO-22-KLN-LIM-1-01 | 110kV FEEDER - KILLONAN 110-LIMERICK 110-1 | 5 | 5 | 5 | Proposed | 24/10/2022 | 28/10/2022
TO-22-KPG-MP GIS-1-02 | 220kV FEEDER - KILPADDOGE 220-MONEYPOINT GIS 220-1 | 5 | 5 | 5 | Scheduled | 24/10/2022 | 28/10/2022
TO-22-SK-T103-02 | GENERATOR TRANSFORMER - SEALROCK 110-SEALROCK G3-T103 | 3 | 3 | 3 | Proposed | 24/10/2022 | 26/10/2022
TO-22-IKE-T141-04 | DISTRIBUTION TRANSFORMER - IKERRIN 110-IKERRIN 38-T141 | 2 | 2 | 2 | Reference (Proposed) | 01/11/2022 | 02/11/2022
TO-22-IKE,T-IKE-1-04 | 110kV FEEDER - IKERRIN tee-IKERRIN 110-1 | 2 | 2 | 2 | Proposed | 01/11/2022 | 02/11/2022
TO-22-IKE,T-SH-1-05 | 110kV FEEDER - IKERRIN tee-SHANNONBRIDGE 110-1 | 21 | 15 | 15 | Proposed | 01/11/2022 | 21/11/2022
TO-22-IKE,T-THU-1-07 | 110kV FEEDER - IKERRIN tee-THURLES 110-1 | 2 | 2 | 2 | Proposed | 01/11/2022 | 02/11/2022
TO-22-110 kV B1 @ KPG-03 | BUSBAR SECTION - KILPADDOGE 110-KILPADDOGE 110-110B1 | 4 | 4 | 4 | Proposed | 01/11/2022 | 04/11/2022
TO-22-110 kV B3 @ KPG-02 | BUSBAR SECTION - KILPADDOGE 110-KILPADDOGE 110-110B3 | 4 | 4 | 4 | Proposed | 01/11/2022 | 04/11/2022
TO-22-KPG-110SB1-3CB-01 | COUPLER/SECTIONALISING CB - KILPADDOGE 110-KILPADDOGE 110-110SB1-3CB | 4 | 4 | 4 | Proposed | 01/11/2022 | 04/11/2022
TO-22-220 kV A1/A2 @ BVK-02 | BUSBAR SECTION - BALLYVOUSKILL 220-BALLYVOUSKILL 220-220A1-A2 | 3 | 3 | 3 | Proposed | 02/11/2022 | 04/11/2022
TO-22-CHA-MAL-1-01 | 110kV FEEDER - CHARLEVILLE 110-MALLOW 110-1 | 9 | 7 | 7 | Proposed | 02/11/2022 | 10/11/2022
TO-22-TB-220K1-2-02 | COUPLER/SECTIONALISING CB - TARBERT 220-TARBERT 220-220K1-2 | 3 | 3 | 3 | Proposed | 02/11/2022 | 04/11/2022
TO-22-MP GIS-ST101-01 | GENERATOR TRANSFORMER - MONEYPOINT GIS 110-MONEYPOINT GIS 10-ST101 | 11 | 7 | 7 | Proposed | 04/11/2022 | 14/11/2022
TO-22-MP GIS-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 110-MONEYPOINT GIS 110-110SA1-2CB | 5 | 5 | 5 | Proposed | 07/11/2022 | 11/11/2022
TO-22-MP GIS-T121-01 | GENERATOR TRANSFORMER - MONEYPOINT GIS 110-MONEYPOINT GIS 20-T121 | 5 | 5 | 5 | Proposed | 07/11/2022 | 11/11/2022
TO-22-TBK-T141-01 | DISTRIBUTION TRANSFORMER - TULLABRACK 110-TULLABRACK 38-T141 | 5 | 5 | 5 | Reference (Proposed) | 07/11/2022 | 11/11/2022
TO-22-TBK,T-BOL-1-01 | 110kV FEEDER - TULLABRACK tee-BOOLTIAGH 110-1 | 5 | 5 | 5 | Proposed | 07/11/2022 | 11/11/2022
TO-22-TBK,T-MP GIS-1-01 | 110kV FEEDER - TULLABRACK tee-MONEYPOINT GIS 110-1 | 5 | 5 | 5 | Proposed | 07/11/2022 | 11/11/2022
TO-22-TBK,T-TBK-1-01 | 110kV FEEDER - TULLABRACK tee-TULLABRACK 110-1 | 5 | 5 | 5 | Proposed | 07/11/2022 | 11/11/2022
TO-22-220 kV A1 @ BYH-02 | BUSBAR SECTION - BALLYNAHULLA 220-BALLYNAHULLA 220-220A1 | 4 | 4 | 4 | Proposed | 08/11/2022 | 11/11/2022
TO-22-220 kV A2 @ BYH-03 | BUSBAR SECTION - BALLYNAHULLA 220-BALLYNAHULLA 220-220A2 | 4 | 4 | 4 | Proposed | 08/11/2022 | 11/11/2022
TO-22-BYH-220SA1-2CB-01 | COUPLER/SECTIONALISING CB - BALLYNAHULLA 220-BALLYNAHULLA 220-220SA1-2CB | 4 | 4 | 4 | Proposed | 08/11/2022 | 11/11/2022
TO-22-110 kV A2 @ KPG-03 | BUSBAR SECTION - KILPADDOGE 110-KILPADDOGE 110-110A2 | 4 | 4 | 4 | Proposed | 08/11/2022 | 11/11/2022
TO-22-110 kV A4 @ KPG-01 | BUSBAR SECTION - KILPADDOGE 110-KILPADDOGE 110-110A4 | 4 | 4 | 4 | Proposed | 08/11/2022 | 11/11/2022
TO-22-KPG-110SA2-4CB-01 | COUPLER/SECTIONALISING CB - KILPADDOGE 110-KILPADDOGE 110-110SA2-4CB | 4 | 4 | 4 | Proposed | 08/11/2022 | 11/11/2022
TO-22-MP GIS-T2102-01 | TRANSFORMER - MONEYPOINT GIS 220-MONEYPOINT GIS 110-T2102 | 4 | 4 | 4 | Proposed | 08/11/2022 | 11/11/2022
TO-22-CHA-KLN-1-01 | 110kV FEEDER - CHARLEVILLE 110-KILLONAN 110-1 | 5 | 5 | 5 | Proposed | 14/11/2022 | 18/11/2022
TO-22-110 kV B2 @ KPG-03 | BUSBAR SECTION - KILPADDOGE 110-KILPADDOGE 110-110B2 | 4 | 4 | 4 | Proposed | 14/11/2022 | 17/11/2022
TO-22-110 kV B4 @ KPG-01 | BUSBAR SECTION - KILPADDOGE 110-KILPADDOGE 110-110B4 | 4 | 4 | 4 | Proposed | 14/11/2022 | 17/11/2022
TO-22-KPG-110SB2-4CB-01 | COUPLER/SECTIONALISING CB - KILPADDOGE 110-KILPADDOGE 110-110SB2-4CB | 4 | 4 | 4 | Proposed | 14/11/2022 | 17/11/2022
TO-22-220 kV B1 @ BYH-02 | BUSBAR SECTION - BALLYNAHULLA 220-BALLYNAHULLA 220-220B1 | 4 | 4 | 4 | Proposed | 15/11/2022 | 18/11/2022
TO-22-220 kV B2 @ BYH-03 | BUSBAR SECTION - BALLYNAHULLA 220-BALLYNAHULLA 220-220B2 | 4 | 4 | 4 | Proposed | 15/11/2022 | 18/11/2022
TO-22-BYH-220SB1-2CB-01 | COUPLER/SECTIONALISING CB - BALLYNAHULLA 220-BALLYNAHULLA 220-220SB1-2CB | 4 | 4 | 4 | Proposed | 15/11/2022 | 18/11/2022
TO-22-IKE-T141-05 | DISTRIBUTION TRANSFORMER - IKERRIN 110-IKERRIN 38-T141 | 1 | 1 | 1 | Reference (Proposed) | 21/11/2022 | 21/11/2022
TO-22-IKE,T-IKE-1-05 | 110kV FEEDER - IKERRIN tee-IKERRIN 110-1 | 1 | 1 | 1 | Proposed | 21/11/2022 | 21/11/2022
TO-22-IKE,T-THU-1-08 | 110kV FEEDER - IKERRIN tee-THURLES 110-1 | 1 | 1 | 1 | Proposed | 21/11/2022 | 21/11/2022
TO-22-220 kV B1 @ KPG-03 | BUSBAR SECTION - KILPADDOGE 220-KILPADDOGE 220-220B1 | 4 | 4 | 4 | Proposed | 21/11/2022 | 24/11/2022
TO-22-220 kV B2 @ KPG-03 | BUSBAR SECTION - KILPADDOGE 220-KILPADDOGE 220-220B2 | 4 | 4 | 4 | Proposed | 21/11/2022 | 24/11/2022
TO-22-KPG-220SB1-2CB-03 | COUPLER/SECTIONALISING CB - KILPADDOGE 220-KILPADDOGE 220-220SB1-2CB | 4 | 4 | 4 | Proposed | 21/11/2022 | 24/11/2022
TO-22-110 kV A1 @ KNR-02 | BUSBAR SECTION - KNOCKANURE 110-KNOCKANURE 110-110A1 | 5 | 5 | 5 | Proposed | 21/11/2022 | 25/11/2022
TO-22-KNR-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - KNOCKANURE 110-KNOCKANURE 110-110SA1-2CB | 5 | 5 | 5 | Proposed | 21/11/2022 | 25/11/2022
TO-22-AUG-SK-4-02 | 110kV FEEDER - AUGHINISH 110-SEALROCK 110-4 | 3 | 3 | 3 | Proposed | 28/11/2022 | 30/11/2022
TO-22-220 kV B1/B2 @ BVK-02 | BUSBAR SECTION - BALLYVOUSKILL 220-BALLYVOUSKILL 220-220B1-B2 | 3 | 3 | 3 | Proposed | 28/11/2022 | 30/11/2022
TO-22-SK-T104-02 | GENERATOR TRANSFORMER - SEALROCK 110-SEALROCK G4-T104 | 3 | 3 | 3 | Proposed | 28/11/2022 | 30/11/2022

## GEN_SouthEast
Outage ID | Feeder ID | Calendar Day Duration | Working Day Duration | Work Days | Outage Status | Start | Finish
TO-22-KLS-220K1-2-02 | COUPLER/SECTIONALISING CB - KELLIS 220-KELLIS 220-220K1-2 | 10 | 8 |  | Scheduled | 10/01/2022 | 19/01/2022
TO-22-110 kV A2 @ DEY-01 | BUSBAR SECTION - DERRYCARNEY 110-DERRYCARNEY 110-110A2 | 1 | 1 | 1 | Scheduled | 01/02/2022 | 01/02/2022
TO-22-110 kV B2 @ DEY-01 | BUSBAR SECTION - DERRYCARNEY 110-DERRYCARNEY 110-110B2 | 1 | 1 | 1 | Scheduled | 01/02/2022 | 01/02/2022
TO-22-KTL-MON-1-01 | 110kV FEEDER - KILTEEL 110-MONREAD 110-1 | 7 | 5 | 5 | Scheduled | 01/02/2022 | 07/02/2022
TO-22-110 kV A1/A2 @ CAH-01 | BUSBAR SECTION - CAHIR 110-CAHIR 110-110A1-A2 | 1 | 1 | 1 | Scheduled | 24/02/2022 | 24/02/2022
TO-22-110 kV B1/B2 @ CAH-01 | BUSBAR SECTION - CAHIR 110-CAHIR 110-110B1-B2 | 1 | 1 | 1 | Scheduled | 24/02/2022 | 24/02/2022
TO-22-CAH-TIP-1-01 | 110kV FEEDER - CAHIR 110-TIPPERARY 110-1 | 4 | 4 | 4 | Scheduled | 01/03/2022 | 04/03/2022
TO-22-KTN-WAT-1-01 | 110kV FEEDER - KILLOTERAN 110-WATERFORD 110-1 | 4 | 4 | 4 | Scheduled | 01/03/2022 | 04/03/2022
TO-22-ARK-BEG-1-01 | 110kV FEEDER - ARKLOW 110-BALLYBEG 110-1 | 2 | 2 | 2 | Scheduled | 08/03/2022 | 09/03/2022
TO-22-CRA-WEX-1-01 | 110kV FEEDER - CRANE 110-WEXFORD 110-1 | 9 | 5 | 5 | Scheduled | 14/03/2022 | 22/03/2022
TO-22-BUT-KTN-1-01 | 110kV FEEDER - BUTLERSTOWN 110-KILLOTERAN 110-1 | 1 | 1 |  | Scheduled | 15/03/2022 | 15/03/2022
TO-22-110 kV A1/A2 @ PLS-01 | BUSBAR SECTION - PORTLAOISE 110-PORTLAOISE 110-110A1-A2 | 1 | 1 | 1 | Scheduled | 16/03/2022 | 16/03/2022
TO-22-110 kV B1/B2 @ PLS-01 | BUSBAR SECTION - PORTLAOISE 110-PORTLAOISE 110-110B1-B2 | 1 | 1 | 1 | Scheduled | 16/03/2022 | 16/03/2022
TO-22-110 kV A2 @ CAH-01 | BUSBAR SECTION - CAHIR 110-CAHIR 110-110A2 | 3 | 3 | 3 | Scheduled | 22/03/2022 | 24/03/2022
TO-22-ARK-220K1-2-02 | COUPLER/SECTIONALISING CB - ARKLOW 220-ARKLOW 220-220K1-2 | 23 | 15 |  | Scheduled | 28/03/2022 | 19/04/2022
TO-22-ARK-CKM GIS-1-01 | 220kV FEEDER - ARKLOW 220-CARRICKMINES GIS 220-1 | 23 | 15 | 15 | Scheduled | 28/03/2022 | 19/04/2022
TO-22-ARK-LWD-1-01 | 220kV FEEDER - ARKLOW 220-LODGEWOOD 220-1 | 25 | 17 | 17 | Scheduled | 28/03/2022 | 21/04/2022
TO-22-ARK-T2101-01 | TRANSFORMER - ARKLOW 220-ARKLOW 110-T2101 | 23 | 15 | 15 | Scheduled | 28/03/2022 | 19/04/2022
TO-22-ARK-T2102-01 | TRANSFORMER - ARKLOW 220-ARKLOW 110-T2102 | 23 | 15 | 15 | Scheduled | 28/03/2022 | 19/04/2022
TO-22-CAH-110K1-2-02 | COUPLER/SECTIONALISING CB - CAHIR 110-CAHIR 110-110K1-2 | 4 | 4 | 4 | Scheduled | 29/03/2022 | 01/04/2022
TO-22-BDA-MON-1-01 | 110kV FEEDER - BARODA 110-MONREAD 110-1 | 11 | 9 | 9 | Scheduled | 04/04/2022 | 14/04/2022
TO-22-MON-110SA1-01 | SECTIONALISING DISCONNECT - MONREAD 110-MONREAD 110-110SA1 | 11 | 9 | 9 | Scheduled | 04/04/2022 | 14/04/2022
TO-22-MON-110SA2-02 | SECTIONALISING DISCONNECT - MONREAD 110-MONREAD 110-110SA2 | 11 | 9 | 9 | Scheduled | 04/04/2022 | 14/04/2022
TO-22-MON-T101-01 | DISTRIBUTION TRANSFORMER - MONREAD 110-MONREAD 10-T101 | 11 | 9 | 9 | Reference | 04/04/2022 | 14/04/2022
TO-22-BDA-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - BARODA 110-BARODA 110-110SA1-2CB | 1 | 1 | 1 | Scheduled | 08/04/2022 | 08/04/2022
TO-22-DEY-110K2-02 | COUPLER/SECTIONALISING CB - DERRYCARNEY 110-DERRYCARNEY 110-110K2 | 175 | 120 | 120 | Scheduled | 14/04/2022 | 05/10/2022
TO-22-ARK-T101-01 | DISTRIBUTION TRANSFORMER - ARKLOW 110-ARKLOW 10-T101 | 2 | 2 | 2 | Reference | 20/04/2022 | 21/04/2022
TO-22-110 kV A1/A2 @ KLS-01 | BUSBAR SECTION - KELLIS 110-KELLIS 110-110A1-A2 | 1 | 1 | 1 | Scheduled | 20/04/2022 | 20/04/2022
TO-22-110 kV B1/B2 @ KLS-01 | BUSBAR SECTION - KELLIS 110-KELLIS 110-110B1-B2 | 1 | 1 | 1 | Scheduled | 20/04/2022 | 20/04/2022
TO-22-GI-KKY-1-05 | 110kV FEEDER - GREAT ISLAND 110-KILKENNY 110-1 | 22 | 15 | 15 | Scheduled | 28/04/2022 | 19/05/2022
TO-22-GI-T141-01 | DISTRIBUTION TRANSFORMER - GREAT ISLAND 110-GREAT ISLAND 38-T141 | 15 | 10 |  | Reference | 28/04/2022 | 12/05/2022
TO-22-KKY-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - KILKENNY 110-KILKENNY 110-110SA1-2CB | 22 | 15 | 15 | Scheduled | 28/04/2022 | 19/05/2022
TO-22-KKY-110SA1-2CB-03 | COUPLER/SECTIONALISING CB - KILKENNY 110-KILKENNY 110-110SA1-2CB | 22 | 15 | 15 | Scheduled | 28/04/2022 | 19/05/2022
TO-22-KKY-CAP2-02 | CAPACITOR/SVC/REACTOR - KILKENNY 110-KILKENNY 110-CAP2 | 22 | 15 | 15 | Scheduled | 28/04/2022 | 19/05/2022
TO-22-KKY-CAP2-03 | CAPACITOR/SVC/REACTOR - KILKENNY 110-KILKENNY 110-CAP2 | 22 | 15 | 15 | Scheduled | 28/04/2022 | 19/05/2022
TO-22-KKY-T142-01 | DISTRIBUTION TRANSFORMER - KILKENNY 110-KILKENNY 38-T142 | 22 | 15 | 15 | Reference | 28/04/2022 | 19/05/2022
TO-22-CAH-DOO-1-02 | 110kV FEEDER - CAHIR 110-DOON 110-1 | 4 | 4 | 4 | Scheduled | 03/05/2022 | 06/05/2022
TO-22-WOH-T122-01 | GENERATOR TRANSFORMER - WOODHOUSE 110-WOODHOUSE 20-T122 | 2 | 2 | 2 | Scheduled | 04/05/2022 | 05/05/2022
TO-22-CUS-MLC-1-02 | 110kV FEEDER - CUSHALING 110-MOUNTLUCAS 110-1 | 92 | 64 | 64 | Scheduled | 06/05/2022 | 05/08/2022
TO-22-CAH-KHL-1-01 | 110kV FEEDER - CAHIR 110-KILL HILL 110-1 | 5 | 5 | 5 | Scheduled | 23/05/2022 | 27/05/2022
TO-22-ARK-BOG-1-02 | 110kV FEEDER - ARKLOW 110-BANOGE 110-1 | 1 | 0 | 0 | Scheduled | 12/06/2022 | 12/06/2022
TO-22-DOO-CAP1-02 | CAPACITOR/SVC/REACTOR - DOON 110-DOON 110-CAP1 | 5 | 5 | 5 | Scheduled | 13/06/2022 | 17/06/2022
TO-22-NEW-PLS-1-05 | 110kV FEEDER - NEWBRIDGE 110-PORTLAOISE 110-1 | 16 | 12 | 12 | Scheduled | 20/06/2022 | 05/07/2022
TO-22-BDN-MRK1-02 | TSO CUSTOMER TRANSFORMER - BALLYDINE 110-BALLYDINE 10-MRK1 | 8 | 6 | 6 | Scheduled | 27/06/2022 | 04/07/2022
TO-22-110 kV A1 @ GI-02 | BUSBAR SECTION - GREAT ISLAND 110-GREAT ISLAND 110-110A1 | 4 | 4 | 4 | Scheduled | 27/06/2022 | 30/06/2022
TO-22-110 kV B1 @ GI-01 | BUSBAR SECTION - GREAT ISLAND 110-GREAT ISLAND 110-110B1 | 4 | 4 | 4 | Scheduled | 27/06/2022 | 30/06/2022
TO-22-GI-WEX-1-01 | 110kV FEEDER - GREAT ISLAND 110-WEXFORD 110-1 | 84 | 59 | 59 | Scheduled | 27/06/2022 | 18/09/2022
TO-22-BDN-CUL-1-02 | 110kV FEEDER - BALLYDINE 110-CULLENAGH 110-1 | 2 | 2 | 2 | Scheduled | 30/06/2022 | 01/07/2022
TO-22-GI GIS-T2004-01 | GENERATOR TRANSFORMER - GREAT ISLAND GIS 220-GREAT ISLAND GIS G4-T2004 | 7 | 5 | 5 | Scheduled | 01/07/2022 | 07/07/2022
TO-22-BDN-DOO-1-04 | 110kV FEEDER - BALLYDINE 110-DOON 110-1 | 5 | 5 |  | Scheduled | 04/07/2022 | 08/07/2022
TO-22-220 kV A2 @ GI GIS-01 | BUSBAR SECTION - GREAT ISLAND GIS 220-GREAT ISLAND GIS 220-220A2 | 4 | 4 | 4 | Scheduled | 04/07/2022 | 07/07/2022
TO-22-220 kV B2 @ GI GIS-01 | BUSBAR SECTION - GREAT ISLAND GIS 220-GREAT ISLAND GIS 220-220B2 | 4 | 4 | 4 | Scheduled | 04/07/2022 | 07/07/2022
TO-22-BDN-MRK3-01 | TSO CUSTOMER TRANSFORMER - BALLYDINE 110-BALLYDINE 10-MRK3 | 65 | 46 |  | Scheduled | 05/07/2022 | 07/09/2022
TO-22-ANR-DOO-1-02 | 110kV FEEDER - ANNER 110-DOON 110-1 | 2 | 2 | 2 | Scheduled | 12/07/2022 | 13/07/2022
TO-22-ANR-T101-02 | TSO CUSTOMER TRANSFORMER - ANNER 110-ANNER 10-T101 | 2 | 2 | 2 | Reference | 12/07/2022 | 13/07/2022
TO-22-ANR-T103-02 | TSO CUSTOMER TRANSFORMER - ANNER 110-ANNER 10-T103 | 2 | 2 | 2 | Reference | 12/07/2022 | 13/07/2022
TO-22-220 kV A1 @ GI GIS-03 | BUSBAR SECTION - GREAT ISLAND GIS 220-GREAT ISLAND GIS 220-220A1 | 5 | 5 | 5 | Scheduled | 18/07/2022 | 22/07/2022
TO-22-220 kV B1 @ GI GIS-02 | BUSBAR SECTION - GREAT ISLAND GIS 220-GREAT ISLAND GIS 220-220B1 | 5 | 5 | 5 | Scheduled | 18/07/2022 | 22/07/2022
TO-22-GI-T2101-01 | TRANSFORMER - GREAT ISLAND GIS 220-GREAT ISLAND 110-T2101 | 16 | 11 | 11 | Scheduled | 18/07/2022 | 02/08/2022
TO-22-110 kV A1 @ GI-03 | BUSBAR SECTION - GREAT ISLAND 110-GREAT ISLAND 110-110A1 | 5 | 5 | 5 | Scheduled | 25/07/2022 | 29/07/2022
TO-22-110 kV B1 @ GI-02 | BUSBAR SECTION - GREAT ISLAND 110-GREAT ISLAND 110-110B1 | 5 | 5 | 5 | Scheduled | 25/07/2022 | 29/07/2022
TO-22-CUL-220K1-2-02 | COUPLER/SECTIONALISING CB - CULLENAGH 220-CULLENAGH 220-220K1-2 | 4 | 4 | 4 | Scheduled | 02/08/2022 | 05/08/2022
TO-22-110 kV A1/A2 @ ARK-01 | BUSBAR SECTION - ARKLOW 110-ARKLOW 110-110A1-A2 | 1 | 1 | 1 | Scheduled | 03/08/2022 | 03/08/2022
TO-22-110 kV B1/B2 @ ARK-01 | BUSBAR SECTION - ARKLOW 110-ARKLOW 110-110B1-B2 | 1 | 1 | 1 | Scheduled | 03/08/2022 | 03/08/2022
TO-22-CLW-T142-02 | DISTRIBUTION TRANSFORMER - CARLOW 110-CARLOW 38-T142 | 2 | 2 | 2 | Reference | 03/08/2022 | 04/08/2022
TO-22-110 kV A2 @ CAH-02 | BUSBAR SECTION - CAHIR 110-CAHIR 110-110A2 | 5 | 5 | 5 | Scheduled | 08/08/2022 | 12/08/2022
TO-22-110 kV B2 @ CAH-02 | BUSBAR SECTION - CAHIR 110-CAHIR 110-110B2 | 5 | 5 | 5 | Scheduled | 08/08/2022 | 12/08/2022
TO-22-CAH-CAP2/4-01 | CAPACITOR/SVC/REACTOR - CAHIR 110-CAHIR 110-CAP2/4 | 5 | 5 | 5 | Scheduled | 08/08/2022 | 12/08/2022
TO-22-GI-T2102-01 | TRANSFORMER - GREAT ISLAND GIS 220-GREAT ISLAND 110-T2102 | 5 | 5 | 5 | Scheduled | 08/08/2022 | 12/08/2022
TO-22-ATY-PLS-1-03 | 110kV FEEDER - ATHY 110-PORTLAOISE 110-1 | 3 | 3 | 3 | Scheduled | 09/08/2022 | 11/08/2022
TO-22-DER-MAY-1-02 | 110kV FEEDER - DERRYIRON 110-MAYNOOTH 110-1 | 12 | 10 | 10 | Scheduled | 15/08/2022 | 26/08/2022
TO-22-BWR-CRA-1-01 | 110kV FEEDER - BALLYWATER 110-CRANE 110-1 | 4 | 4 | 4 | Scheduled | 22/08/2022 | 25/08/2022
TO-22-BWR-T124-01 | GENERATOR TRANSFORMER - BALLYWATER 110-BALLYWATER 20-T124 | 4 | 4 | 4 | Reference | 22/08/2022 | 25/08/2022
TO-22-GI-T2101-02 | TRANSFORMER - GREAT ISLAND GIS 220-GREAT ISLAND 110-T2101 | 8 | 6 | 6 | Scheduled | 22/08/2022 | 29/08/2022
TO-22-CDK-LWD-1-02 | 110kV FEEDER - CASTLEDOCKRELL 110-LODGEWOOD 110-1 | 2 | 2 | 2 | Scheduled | 25/08/2022 | 26/08/2022
TO-22-CDK-T121-02 | GENERATOR TRANSFORMER - CASTLEDOCKRELL 110-CASTLEDOCKRELL 20-T121 | 2 | 2 | 2 | Reference | 25/08/2022 | 26/08/2022
TO-22-110 kV A1 @ CUL-01 | BUSBAR SECTION - CULLENAGH 110-CULLENAGH 110-110A1 | 5 | 5 | 5 | Scheduled | 29/08/2022 | 02/09/2022
TO-22-110 kV B1 @ CUL-01 | BUSBAR SECTION - CULLENAGH 110-CULLENAGH 110-110B1 | 5 | 5 | 5 | Scheduled | 29/08/2022 | 02/09/2022
TO-22-220 kV A1 @ GI GIS-02 | BUSBAR SECTION - GREAT ISLAND GIS 220-GREAT ISLAND GIS 220-220A1 | 4 | 4 | 4 | Scheduled | 29/08/2022 | 01/09/2022
TO-22-220 kV A2 @ GI GIS-02 | BUSBAR SECTION - GREAT ISLAND GIS 220-GREAT ISLAND GIS 220-220A2 | 4 | 4 | 4 | Scheduled | 29/08/2022 | 01/09/2022
TO-22-GI GIS-220SA1-2CB-01 | COUPLER/SECTIONALISING CB - GREAT ISLAND GIS 220-GREAT ISLAND GIS 220-220SA1-2CB | 4 | 4 | 4 | Scheduled | 29/08/2022 | 01/09/2022
TO-22-CUL-T2101-01 | TRANSFORMER - CULLENAGH 220-CULLENAGH 110-T2101 | 42 | 30 |  | Scheduled | 31/08/2022 | 11/10/2022
TO-22-BDA-T101-01 | TSO CUSTOMER TRANSFORMER - BARODA 110-BARODA 10-T101 | 3 | 3 | 3 | Scheduled | 05/09/2022 | 07/09/2022
TO-22-220 kV A1 @ CUL-01 | BUSBAR SECTION - CULLENAGH 220-CULLENAGH 220-220A1 | 5 | 5 | 5 | Scheduled | 05/09/2022 | 09/09/2022
TO-22-220 kV B1 @ CUL-01 | BUSBAR SECTION - CULLENAGH 220-CULLENAGH 220-220B1 | 5 | 5 | 5 | Scheduled | 05/09/2022 | 09/09/2022
TO-22-GI-110K1-2-01 | COUPLER/SECTIONALISING CB - GREAT ISLAND 110-GREAT ISLAND 110-110K1-2 | 1 | 1 | 1 | Scheduled | 07/09/2022 | 07/09/2022
TO-22-CAH-TIP-1-02 | 110kV FEEDER - CAHIR 110-TIPPERARY 110-1 | 5 | 3 | 3 | Scheduled | 08/09/2022 | 12/09/2022
TO-22-GI GIS-220K1-01 | COUPLER/SECTIONALISING CB - GREAT ISLAND GIS 220-GREAT ISLAND GIS 220-220K1 | 1 | 1 | 1 | Scheduled | 08/09/2022 | 08/09/2022
TO-22-ATY-CLW-1-01 | 110kV FEEDER - ATHY 110-CARLOW 110-1 | 47 | 35 | 35 | Scheduled | 12/09/2022 | 28/10/2022
TO-22-KTN-T102-01 | DISTRIBUTION TRANSFORMER - KILLOTERAN 110-KILLOTERAN 10-T102 | 2 | 2 | 2 | Reference | 15/09/2022 | 16/09/2022
TO-22-ARK-BOG-1-01 | 110kV FEEDER - ARKLOW 110-BANOGE 110-1 | 5 | 5 | 5 | Scheduled | 19/09/2022 | 23/09/2022
TO-22-BOG-110SA1-02 | SECTIONALISING DISCONNECT - BANOGE 110-BANOGE 110-110SA1 | 5 | 5 | 5 | Scheduled | 19/09/2022 | 23/09/2022
TO-22-BOG-110SA2-01 | SECTIONALISING DISCONNECT - BANOGE 110-BANOGE 110-110SA2 | 5 | 5 | 5 | Scheduled | 19/09/2022 | 23/09/2022
TO-22-BOG-T122-01 | DISTRIBUTION TRANSFORMER - BANOGE 110-BANOGE 20-T122 | 5 | 5 | 5 | Reference (Tentative) | 19/09/2022 | 23/09/2022
TO-22-WEX-CAP2-01 | CAPACITOR/SVC/REACTOR - WEXFORD 110-WEXFORD 110-CAP2 | 4 | 4 | 4 | Scheduled | 20/09/2022 | 23/09/2022
TO-22-WEX-CAP4-01 | CAPACITOR/SVC/REACTOR - WEXFORD 110-WEXFORD 110-CAP4 | 4 | 4 | 4 | Scheduled | 20/09/2022 | 23/09/2022
TO-22-110 kV A1/A2 @ GI-01 | BUSBAR SECTION - GREAT ISLAND 110-GREAT ISLAND 110-110A1-A2 | 1 | 1 | 1 | Scheduled | 21/09/2022 | 21/09/2022
TO-22-110 kV B1/B2 @ GI-01 | BUSBAR SECTION - GREAT ISLAND 110-GREAT ISLAND 110-110B1-B2 | 1 | 1 | 1 | Scheduled | 21/09/2022 | 21/09/2022
TO-22-220 kV A1/A2 @ GI GIS-01 | BUSBAR SECTION - GREAT ISLAND GIS 220-GREAT ISLAND GIS 220-220A1-A2 | 1 | 1 | 1 | Scheduled | 21/09/2022 | 21/09/2022
TO-22-220 kV B1/B2 @ GI GIS-01 | BUSBAR SECTION - GREAT ISLAND GIS 220-GREAT ISLAND GIS 220-220B1-B2 | 1 | 1 | 1 | Scheduled | 21/09/2022 | 21/09/2022
TO-22-ATY-110SA1-01 | SECTIONALISING DISCONNECT - ATHY 110-ATHY 110-110SA1 | 5 | 5 | 5 | Proposed | 26/09/2022 | 30/09/2022
TO-22-ATY-110SA2-02 | SECTIONALISING DISCONNECT - ATHY 110-ATHY 110-110SA2 | 5 | 5 | 5 | Proposed | 26/09/2022 | 30/09/2022
TO-22-ATY-T101-02 | DISTRIBUTION TRANSFORMER - ATHY 110-ATHY 10-T101 | 5 | 5 | 5 | Reference (Proposed) | 26/09/2022 | 30/09/2022
TO-22-BDA-T102-01 | TSO CUSTOMER TRANSFORMER - BARODA 110-BARODA 10-T102 | 2 | 2 | 2 | Proposed | 26/09/2022 | 27/09/2022
TO-22-CLW-110SA1-06 | SECTIONALISING DISCONNECT - CARLOW 110-CARLOW 110-110SA1 | 5 | 5 | 5 | Proposed | 26/09/2022 | 30/09/2022
TO-22-CLW-110SA2-04 | SECTIONALISING DISCONNECT - CARLOW 110-CARLOW 110-110SA2 | 5 | 5 | 5 | Proposed | 26/09/2022 | 30/09/2022
TO-22-CLW-KLS-1-06 | 110kV FEEDER - CARLOW 110-KELLIS 110-1 | 5 | 5 | 5 | Proposed | 26/09/2022 | 30/09/2022
TO-22-CLW-T141-04 | DISTRIBUTION TRANSFORMER - CARLOW 110-CARLOW 38-T141 | 5 | 5 | 5 | Reference (Proposed) | 26/09/2022 | 30/09/2022
TO-22-KKY-T141-01 | DISTRIBUTION TRANSFORMER - KILKENNY 110-KILKENNY 38-T141 | 2 | 2 | 2 | Reference (Proposed) | 26/09/2022 | 27/09/2022
TO-22-ARK-BEG-1-03 | 110kV FEEDER - ARKLOW 110-BALLYBEG 110-1 | 31 | 23 | 23 | Tentative | 28/09/2022 | 28/10/2022
TO-22-CAH-DOO-1-03 | 110kV FEEDER - CAHIR 110-DOON 110-1 | 2 | 0 | 0 | Proposed | 01/10/2022 | 02/10/2022
TO-22-BUT-KTN-1-02 | 110kV FEEDER - BUTLERSTOWN 110-KILLOTERAN 110-1 | 3 | 3 | 3 | Proposed | 05/10/2022 | 07/10/2022
TO-22-KTN-110SA1-01 | SECTIONALISING DISCONNECT - KILLOTERAN 110-KILLOTERAN 110-110SA1 | 3 | 3 | 3 | Proposed | 05/10/2022 | 07/10/2022
TO-22-KTN-110SA2-01 | SECTIONALISING DISCONNECT - KILLOTERAN 110-KILLOTERAN 110-110SA2 | 3 | 3 | 3 | Proposed | 05/10/2022 | 07/10/2022
TO-22-KTN-T101-01 | DISTRIBUTION TRANSFORMER - KILLOTERAN 110-KILLOTERAN 10-T101 | 3 | 3 | 3 | Reference (Proposed) | 05/10/2022 | 07/10/2022
TO-22-KRA-WOH-1-01 | 110kV FEEDER - KNOCKRAHA 110-WOODHOUSE 110-1 | 3 | 3 | 3 | Scheduled | 12/10/2022 | 14/10/2022
TO-22-WOH-110SA1-02 | SECTIONALISING DISCONNECT - WOODHOUSE 110-WOODHOUSE 110-110SA1 | 3 | 3 | 3 | Scheduled | 12/10/2022 | 14/10/2022
TO-22-WOH-110SA2-01 | SECTIONALISING DISCONNECT - WOODHOUSE 110-WOODHOUSE 110-110SA2 | 3 | 3 | 3 | Scheduled | 12/10/2022 | 14/10/2022
TO-22-WOH-T122-03 | GENERATOR TRANSFORMER - WOODHOUSE 110-WOODHOUSE 20-T122 | 3 | 3 | 3 | Scheduled | 12/10/2022 | 14/10/2022
TO-22-BDA-NEW-1-01 | 110kV FEEDER - BARODA 110-NEWBRIDGE 110-1 | 5 | 5 | 5 | Scheduled | 17/10/2022 | 21/10/2022
TO-22-BUT-CUL-1-01 | 110kV FEEDER - BUTLERSTOWN 110-CULLENAGH 110-1 | 5 | 5 | 5 | Scheduled | 17/10/2022 | 21/10/2022
TO-22-CRA-LWD-1-01 | 110kV FEEDER - CRANE 110-LODGEWOOD 110-1 | 5 | 5 | 5 | Proposed | 17/10/2022 | 21/10/2022
TO-22-CUL-KRA-1-01 | 220kV FEEDER - CULLENAGH 220-KNOCKRAHA 220-1 | 5 | 5 | 5 | Scheduled | 17/10/2022 | 21/10/2022
TO-22-CUL-WAT-1-01 | 110kV FEEDER - CULLENAGH 110-WATERFORD 110-1 | 5 | 5 | 5 | Scheduled | 24/10/2022 | 28/10/2022
TO-22-CUS-T103/5-02 | GENERATOR TRANSFORMER - CUSHALING 110-CUSHALING G3/5-T103/5 | 1 | 1 | 1 | Scheduled | 24/10/2022 | 24/10/2022
TO-22-GI-WAT-1-02 | 110kV FEEDER - GREAT ISLAND 110-WATERFORD 110-1 | 5 | 5 | 5 | Proposed | 24/10/2022 | 28/10/2022
TO-22-BEG-CKM GIS-1-01 | 110kV FEEDER - BALLYBEG 110-CARRICKMINES GIS 110-1 | 4 | 4 | 4 | Proposed | 01/11/2022 | 04/11/2022
TO-22-CLW-KLS-2-04 | 110kV FEEDER - CARLOW 110-KELLIS 110-2 | 11 | 9 | 9 | Proposed | 01/11/2022 | 11/11/2022
TO-22-110 kV A1/A2 @ CUL-01 | BUSBAR SECTION - CULLENAGH 110-CULLENAGH 110-110A1-A2 | 1 | 1 | 1 | Proposed | 02/11/2022 | 02/11/2022
TO-22-110 kV B1/B2 @ CUL-01 | BUSBAR SECTION - CULLENAGH 110-CULLENAGH 110-110B1-B2 | 1 | 1 | 1 | Proposed | 02/11/2022 | 02/11/2022
TO-22-DGN-WOH-1-01 | 110kV FEEDER - DUNGARVAN 110-WOODHOUSE 110-1 | 2 | 2 | 2 | Proposed | 02/11/2022 | 03/11/2022
TO-22-GI GIS-LWD-1-02 | 220kV FEEDER - GREAT ISLAND GIS 220-LODGEWOOD 220-1 | 5 | 5 | 5 | Proposed | 07/11/2022 | 11/11/2022
TO-22-GI-WAT-2-02 | 110kV FEEDER - GREAT ISLAND 110-WATERFORD 110-2 | 4 | 4 | 4 | Proposed | 07/11/2022 | 10/11/2022
TO-22-LWD-220K1-2-02 | COUPLER/SECTIONALISING CB - LODGEWOOD 220-LODGEWOOD 220-220K1-2 | 5 | 5 | 5 | Proposed | 07/11/2022 | 11/11/2022
TO-22-MAY-SH-1-04 | 220kV FEEDER - MAYNOOTH 220-SHANNONBRIDGE 220-1 | 5 | 5 | 5 | Proposed | 07/11/2022 | 11/11/2022
TO-22-110 kV A1 @ ARK-02 | BUSBAR SECTION - ARKLOW 110-ARKLOW 110-110A1 | 12 | 10 | 10 | Proposed | 14/11/2022 | 25/11/2022
TO-22-110 kV A2 @ ARK-01 | BUSBAR SECTION - ARKLOW 110-ARKLOW 110-110A2 | 12 | 10 | 10 | Proposed | 14/11/2022 | 25/11/2022
TO-22-110 kV B1 @ ARK-02 | BUSBAR SECTION - ARKLOW 110-ARKLOW 110-110B1 | 12 | 10 | 10 | Proposed | 14/11/2022 | 25/11/2022
TO-22-110 kV B2 @ ARK-01 | BUSBAR SECTION - ARKLOW 110-ARKLOW 110-110B2 | 12 | 10 | 10 | Proposed | 14/11/2022 | 25/11/2022
TO-22-ARK-110K1-2-01 | COUPLER/SECTIONALISING CB - ARKLOW 110-ARKLOW 110-110K1-2 | 12 | 10 | 10 | Proposed | 14/11/2022 | 25/11/2022
TO-22-ARK-SHE-2-01 | 110kV FEEDER - ARKLOW 110-SHELTON ABBEY 110-2 | 1 | 1 | 1 | Proposed | 24/11/2022 | 24/11/2022
TO-22-SHE-T102-01 | TSO CUSTOMER TRANSFORMER - SHELTON ABBEY 110-SHELTON ABBEY 10-T102 | 1 | 1 | 1 | Reference (Proposed) | 24/11/2022 | 24/11/2022

## GEN_NorthWest
Outage ID | Feeder ID | Calendar Day Duration | Working Day Duration | Work Days | Outage Status | Start | Finish
TO-22-KNY-110K2-03 | COUPLER/SECTIONALISING CB - KNOCKRANNY 110-KNOCKRANNY 110-110K2 | 5 | 5 | 5 | Scheduled | 10/01/2022 | 14/01/2022
TO-22-KNY-110SA1-2CB-03 | COUPLER/SECTIONALISING CB - KNOCKRANNY 110-KNOCKRANNY 110-110SA1-2CB | 5 | 5 | 5 | Scheduled | 17/01/2022 | 21/01/2022
TO-22-KNY-110K1-01 | COUPLER/SECTIONALISING CB - KNOCKRANNY 110-KNOCKRANNY 110-110K1 | 5 | 5 | 5 | Scheduled | 24/01/2022 | 28/01/2022
TO-22-110 kV A1/A2 @ KNY-01 | BUSBAR SECTION - KNOCKRANNY 110-KNOCKRANNY 110-110A1-A2 | 1 | 1 | 1 | Scheduled | 03/02/2022 | 03/02/2022
TO-22-110 kV B1/B2 @ KNY-01 | BUSBAR SECTION - KNOCKRANNY 110-KNOCKRANNY 110-110B1-B2 | 1 | 1 | 1 | Scheduled | 03/02/2022 | 03/02/2022
TO-22-220 kV B1 @ CSH-02 | BUSBAR SECTION - CASHLA 220-CASHLA 220-220B1 | 2 | 2 | 2 | Tentative | 09/02/2022 | 10/02/2022
TO-22-110 kV A1/A2 @ CF-01 | BUSBAR SECTION - CATHALEENS FALL 110-CATHALEENS FALL 110-110A1-A2 | 1 | 1 | 1 | Scheduled | 17/02/2022 | 17/02/2022
TO-22-110 kV B1/B2 @ CF-01 | BUSBAR SECTION - CATHALEENS FALL 110-CATHALEENS FALL 110-110B1-B2 | 1 | 1 | 1 | Scheduled | 17/02/2022 | 17/02/2022
TO-22-110 kV A2 @ CSH-03 | BUSBAR SECTION - CASHLA 110-CASHLA 110-110A2 | 8 | 6 | 6 | Tentative | 28/02/2022 | 07/03/2022
TO-22-CSH-110K1-2-03 | COUPLER/SECTIONALISING CB - CASHLA 110-CASHLA 110-110K1-2 | 8 | 6 | 6 | Tentative | 28/02/2022 | 07/03/2022
TO-22-CSH-CLN-1-05 | 110kV FEEDER - CASHLA 110-CLOON 110-1 | 1 | 1 | 1 | Tentative | 28/02/2022 | 28/02/2022
TO-22-CSH-PRO-1-01 | 220kV FEEDER - CASHLA 220-PROSPECT 220-1 | 31 | 22 | 22 | Scheduled | 28/02/2022 | 30/03/2022
TO-22-CBR-DLT-1-02 | 110kV FEEDER - CASTLEBAR 110-DALTON 110-1 | 5 | 5 | 5 | Tentative | 28/02/2022 | 04/03/2022
TO-22-FLA-SLB-1-01 | 110kV FEEDER - FLAGFORD 110-SLIABH BAWN 110-1 | 59 | 40 | 40 | Scheduled | 28/02/2022 | 27/04/2022
TO-22-SOM,T-CSH-1-05 | 110kV FEEDER - SOMERSET tee-CASHLA 110-1 | 12 | 10 | 10 | Scheduled | 28/02/2022 | 11/03/2022
TO-22-CF-SRA-2-01 | 110kV FEEDER - CATHALEENS FALL 110-SRANANAGH 110-2 | 7 | 5 | 5 | Scheduled | 01/03/2022 | 07/03/2022
TO-22-BIN-CF-1-03 | 110kV FEEDER - BINBANE 110-CATHALEENS FALL 110-1 | 4 | 4 | 4 | Scheduled | 08/03/2022 | 11/03/2022
TO-22-110 kV A1 @ GRV-01 | BUSBAR SECTION - GARVAGH 110-GARVAGH 110-110A1 | 1 | 1 | 1 | Scheduled | 30/03/2022 | 30/03/2022
TO-22-110 kV B1 @ GRV-01 | BUSBAR SECTION - GARVAGH 110-GARVAGH 110-110B1 | 1 | 1 | 1 | Scheduled | 30/03/2022 | 30/03/2022
TO-22-CF-SRA-1-01 | 110kV FEEDER - CATHALEENS FALL 110-SRANANAGH 110-1 | 5 | 5 |  | Scheduled | 04/04/2022 | 08/04/2022
TO-22-CL-T101-03 | GENERATOR TRANSFORMER - CLIFF 110-CLIFF G1-T101 | 5 | 5 | 5 | Tentative | 04/04/2022 | 08/04/2022
TO-22-110 kV A1 @ CSH-06 | BUSBAR SECTION - CASHLA 110-CASHLA 110-110A1 | 4 | 4 | 4 | Scheduled | 11/04/2022 | 14/04/2022
TO-22-110 kV B1 @ CSH-06 | BUSBAR SECTION - CASHLA 110-CASHLA 110-110B1 | 4 | 4 | 4 | Scheduled | 11/04/2022 | 14/04/2022
TO-22-CSH-CAP1-01 | CAPACITOR/SVC/REACTOR - CASHLA 110-CASHLA 110-CAP1 | 4 | 4 | 4 | Scheduled | 11/04/2022 | 14/04/2022
TO-22-KNY-SAL-1-02 | 110kV FEEDER - KNOCKRANNY-SALTHILL 110-1 | 12 | 8 | 8 | Scheduled | 11/04/2022 | 22/04/2022
TO-22-BK-CBR-1-04 | 110kV FEEDER - BELLACORICK 110-CASTLEBAR 110-1 | 11 | 9 | 9 | Scheduled | 19/04/2022 | 29/04/2022
TO-22-DRM-LET-1-01 | 110kV FEEDER - DRUMKEEN 110-LETTERKENNY 110-1 | 2 | 2 | 2 | Scheduled | 20/04/2022 | 21/04/2022
TO-22-CF-COR-1-02 | 110kV FEEDER - CATHALEENS FALL 110-CORRACLASSY 110-1 | 5 | 5 | 5 | Tentative | 25/04/2022 | 29/04/2022
TO-22-BK-CBR-1-01 | 110kV FEEDER - BELLACORICK 110-CASTLEBAR 110-1 | 2 | 2 |  | Scheduled | 28/04/2022 | 29/04/2022
TO-22-CBR-110SA1-2CB-04 | COUPLER/SECTIONALISING CB - CASTLEBAR 110-CASTLEBAR 110-110SA1-2CB | 2 | 2 | 2 | Scheduled | 28/04/2022 | 29/04/2022
TO-22-CBR-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - CASTLEBAR 110-CASTLEBAR 110-110SA1-2CB | 2 | 2 | 2 | Scheduled | 28/04/2022 | 29/04/2022
TO-22-CBR-CLN-1-01 | 110kV FEEDER - CASTLEBAR 110-CLOON 110-1 | 93 | 65 | 65 | Scheduled | 28/04/2022 | 29/07/2022
TO-22-CBR-SVC-01 | CAPACITOR/SVC/REACTOR - CASTLEBAR 110-CASTLEBAR 110-SVC | 33 | 22 |  | Scheduled | 28/04/2022 | 30/05/2022
TO-22-CBR-T141-01 | DISTRIBUTION TRANSFORMER - CASTLEBAR 110-CASTLEBAR 38-T141 | 93 | 65 | 65 | Reference | 28/04/2022 | 29/07/2022
TO-22-CBR-CLN-1-02 | 110kV FEEDER - CASTLEBAR 110-CLOON 110-1 | 8 | 5 | 5 | Scheduled | 29/04/2022 | 06/05/2022
TO-22-FLA-SRA-1-02 | 220kV FEEDER - FLAGFORD 220-SRANANAGH 220-1 | 23 | 17 | 17 | Scheduled | 03/05/2022 | 25/05/2022
TO-22-SRA-220SA1-02 | SECTIONALISING DISCONNECT - SRANANAGH 220-SRANANAGH 220-220SA1 | 23 | 17 | 17 | Scheduled | 03/05/2022 | 25/05/2022
TO-22-SRA-220SA2-02 | SECTIONALISING DISCONNECT - SRANANAGH 220-SRANANAGH 220-220SA2 | 23 | 17 | 17 | Scheduled | 03/05/2022 | 25/05/2022
TO-22-SRA-T2102-02 | TRANSFORMER - SRANANAGH 220-SRANANAGH 110-T2102 | 23 | 17 | 17 | Scheduled | 03/05/2022 | 25/05/2022
TO-22-CL-T102-01 | GENERATOR TRANSFORMER - CLIFF 110-CLIFF G2-T102 | 5 | 5 | 5 | Scheduled | 09/05/2022 | 13/05/2022
TO-22-SAL-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - SALTHILL 110-SALTHILL 110-110SA1-2CB | 3 | 3 | 3 | Scheduled | 16/05/2022 | 18/05/2022
TO-22-GOL-T101-03 | GENERATOR TRANSFORMER - GOLAGH 110-GOLAGH 10-T101 | 6 | 5 | 5 | Scheduled | 23/05/2022 | 28/05/2022
TO-22-GOL,T-CLO-1-01 | 110kV FEEDER - GOLAGH tee-CLOGHER 110-1 | 6 | 5 | 5 | Scheduled | 23/05/2022 | 28/05/2022
TO-22-GOL,T-GOL-1-02 | 110kV FEEDER - GOLAGH tee-GOLAGH 110-1 | 6 | 5 | 5 | Scheduled | 23/05/2022 | 28/05/2022
TO-22-GOL,T-LET-1-02 | 110kV FEEDER - GOLAGH tee-LETTERKENNY 110-1 | 6 | 5 | 5 | Scheduled | 23/05/2022 | 28/05/2022
TO-22-BK-CBR-1-02 | 110kV FEEDER - BELLACORICK 110-CASTLEBAR 110-1 | 2 | 0 | 0 | Scheduled | 28/05/2022 | 29/05/2022
TO-22-CBR-110SA1-2CB-02 | COUPLER/SECTIONALISING CB - CASTLEBAR 110-CASTLEBAR 110-110SA1-2CB | 2 | 0 | 0 | Scheduled | 28/05/2022 | 29/05/2022
TO-22-MOY-T142-01 | DISTRIBUTION TRANSFORMER - MOY 110-MOY 38-T142 | 117 | 83 | 83 | Reference | 30/05/2022 | 23/09/2022
TO-22-CF-COR-1-03 | 110kV FEEDER - CATHALEENS FALL 110-CORRACLASSY 110-1 | 29 | 20 | 20 | Scheduled | 06/06/2022 | 04/07/2022
TO-22-MOY-TAW-1-02 | 110kV FEEDER - MOY 110-TAWNAGHMORE 110-1 | 8 | 6 | 6 | Scheduled | 08/06/2022 | 15/06/2022
TO-22-CDY-T121-01 | DISTRIBUTION TRANSFORMER - CORDERRY 110-CORDERRY 20-T121 | 41 | 30 | 30 | Reference | 13/06/2022 | 23/07/2022
TO-22-CUN-T121-01 | GENERATOR TRANSFORMER - CUNGHILL 110-CUNGHILL 20-T121 | 4 | 4 | 4 | Scheduled | 13/06/2022 | 16/06/2022
TO-22-CSH-SAL-1-01 | 110kV FEEDER - CASHLA 110-SALTHILL 110-1 | 9 | 7 | 7 | Scheduled | 20/06/2022 | 28/06/2022
TO-22-110 kV A1 @ CSH-07 | BUSBAR SECTION - CASHLA 110-CASHLA 110-110A1 | 4 | 4 | 4 | Scheduled | 21/06/2022 | 24/06/2022
TO-22-110 kV B1 @ CSH-07 | BUSBAR SECTION - CASHLA 110-CASHLA 110-110B1 | 4 | 4 | 4 | Scheduled | 21/06/2022 | 24/06/2022
TO-22-CF-T103-01 | GENERATOR TRANSFORMER - CATHALEENS FALL 110-CATHALEENS FALL G3-T103 | 5 | 5 | 5 | Tentative | 27/06/2022 | 01/07/2022
TO-22-CF-110K1-2-01 | COUPLER/SECTIONALISING CB - CATHALEENS FALL 110-CATHALEENS FALL 110-110K1-2 | 1 | 1 | 1 | Scheduled | 28/06/2022 | 28/06/2022
TO-22-GAL-SAL-1-01 | 110kV FEEDER - GALWAY 110-SALTHILL 110-1 | 110 | 79 | 79 | Scheduled | 04/07/2022 | 21/10/2022
TO-22-GAL-T101-01 | DISTRIBUTION TRANSFORMER - GALWAY 110-GALWAY 10-T101 | 2 | 2 | 2 | Reference | 04/07/2022 | 05/07/2022
TO-22-LET-SVC-01 | CAPACITOR/SVC/REACTOR - LETTERKENNY 110-LETTERKENNY 110-SVC | 5 | 5 | 5 | Scheduled | 04/07/2022 | 08/07/2022
TO-22-SLI-SRA-1-03 | 110kV FEEDER - SLIGO 110-SRANANAGH 110-1 | 1 | 1 | 1 | Scheduled | 13/07/2022 | 13/07/2022
TO-22-220 kV A1 @ CSH-03 | BUSBAR SECTION - CASHLA 220-CASHLA 220-220A1 | 5 | 5 | 5 | Scheduled | 18/07/2022 | 22/07/2022
TO-22-220 kV A2 @ CSH-02 | BUSBAR SECTION - CASHLA 220-CASHLA 220-220A2 | 5 | 5 | 5 | Scheduled | 18/07/2022 | 22/07/2022
TO-22-220 kV B1 @ CSH-03 | BUSBAR SECTION - CASHLA 220-CASHLA 220-220B1 | 5 | 5 | 5 | Scheduled | 18/07/2022 | 22/07/2022
TO-22-220 kV B2 @ CSH-02 | BUSBAR SECTION - CASHLA 220-CASHLA 220-220B2 | 5 | 5 | 5 | Scheduled | 18/07/2022 | 22/07/2022
TO-22-CSH-220K1-2-02 | COUPLER/SECTIONALISING CB - CASHLA 220-CASHLA 220-220K1-2 | 5 | 5 | 5 | Scheduled | 18/07/2022 | 22/07/2022
TO-22-DRM-MEE-1-02 | 110kV FEEDER - DRUMKEEN 110-MEENTYCAT 110-1 | 3 | 3 | 3 | Scheduled | 18/07/2022 | 20/07/2022
TO-22-MEE-T121-01 | GENERATOR TRANSFORMER - MEENTYCAT 110-MEENTYCAT 20-T121 | 3 | 3 | 3 | Scheduled | 18/07/2022 | 20/07/2022
TO-22-BIN-CF-1-04 | 110kV FEEDER - BINBANE 110-CATHALEENS FALL 110-1 | 5 | 5 | 5 | Scheduled | 25/07/2022 | 29/07/2022
TO-22-110 kV A1/A2 @ CLO-01 | BUSBAR SECTION - CLOGHER 110-CLOGHER 110-110A1-A2 | 1 | 1 | 1 | Scheduled | 27/07/2022 | 27/07/2022
TO-22-110 kV B1/B2 @ CLO-01 | BUSBAR SECTION - CLOGHER 110-CLOGHER 110-110B1-B2 | 1 | 1 | 1 | Scheduled | 27/07/2022 | 27/07/2022
TO-22-BK-CBR-1-03 | 110kV FEEDER - BELLACORICK 110-CASTLEBAR 110-1 | 1 | 1 | 1 | Scheduled | 29/07/2022 | 29/07/2022
TO-22-CBR-110SA1-2CB-03 | COUPLER/SECTIONALISING CB - CASTLEBAR 110-CASTLEBAR 110-110SA1-2CB | 1 | 1 | 1 | Scheduled | 29/07/2022 | 29/07/2022
TO-22-CBR-SVC-02 | CAPACITOR/SVC/REACTOR - CASTLEBAR 110-CASTLEBAR 110-SVC | 1 | 1 | 1 | Scheduled | 29/07/2022 | 29/07/2022
TO-22-CSH-ENN-1-01 | 110kV FEEDER - CASHLA 110-ENNIS 110-1 | 3 | 3 | 3 | Scheduled | 02/08/2022 | 04/08/2022
TO-22-CDY-SRA-1-01 | 110kV FEEDER - CORDERRY 110-SRANANAGH 110-1 | 4 | 4 | 4 | Scheduled | 02/08/2022 | 05/08/2022
TO-22-BIN-TIV-1-02 | 110kV FEEDER - BINBANE 110-TIEVEBRACK 110-1 | 4 | 4 | 4 | Scheduled | 08/08/2022 | 11/08/2022
TO-22-LET-T141-01 | DISTRIBUTION TRANSFORMER - LETTERKENNY 110-LETTERKENNY 38-T141 | 2 | 2 | 2 | Reference | 09/08/2022 | 10/08/2022
TO-22-CL-T101-04 | GENERATOR TRANSFORMER - CLIFF 110-CLIFF G1-T101 | 1 | 1 | 1 | Tentative | 12/08/2022 | 12/08/2022
TO-22-CL-T102-02 | GENERATOR TRANSFORMER - CLIFF 110-CLIFF G2-T102 | 1 | 1 | 1 | Tentative | 12/08/2022 | 12/08/2022
TO-22-TAW-T1/T2-01 | GENERATOR TRANSFORMER - TAWNAGHMORE 110-TAWNAGHMORE 10-T1/T2 | 8 | 6 | 6 | Scheduled | 12/08/2022 | 19/08/2022
TO-22-CSH-TY-1-05 | 220kV FEEDER - CASHLA 220-TYNAGH 220-1 | 5 | 5 | 5 | Scheduled | 15/08/2022 | 19/08/2022
TO-22-CF-COR-1-01 | 110kV FEEDER - CATHALEENS FALL 110-CORRACLASSY 110-1 | 40 | 30 | 30 | Scheduled | 15/08/2022 | 23/09/2022
TO-22-TIV-110SA1-2CB-03 | COUPLER/SECTIONALISING CB - TIEVEBRACK 110-TIEVEBRACK 110-110SA1-2CB | 1 | 1 | 1 | Scheduled | 15/08/2022 | 15/08/2022
TO-22-LET-110SA1-3CB-01 | COUPLER/SECTIONALISING CB - LETTERKENNY 110-LETTERKENNY 110-110SA1-3CB | 1 | 1 | 1 | Scheduled | 17/08/2022 | 17/08/2022
TO-22-110 kV A1/A2 @ SRA-01 | BUSBAR SECTION - SRANANAGH 110-SRANANAGH 110-110A1-A2 | 1 | 1 | 1 | Scheduled | 17/08/2022 | 17/08/2022
TO-22-110 kV B1/B2 @ SRA-01 | BUSBAR SECTION - SRANANAGH 110-SRANANAGH 110-110B1-B2 | 1 | 1 | 1 | Scheduled | 17/08/2022 | 17/08/2022
TO-22-BK-110SA1-04 | SECTIONALISING DISCONNECT - BELLACORICK 110-BELLACORICK 110-110SA1 | 5 | 5 | 5 | Tentative | 05/09/2022 | 09/09/2022
TO-22-BK-110SA2-04 | SECTIONALISING DISCONNECT - BELLACORICK 110-BELLACORICK 110-110SA2 | 5 | 5 | 5 | Tentative | 05/09/2022 | 09/09/2022
TO-22-BK-MOY-1-06 | 110kV FEEDER - BELLACORICK 110-MOY 110-1 | 5 | 5 | 5 | Tentative | 05/09/2022 | 09/09/2022
TO-22-BK-T141-03 | DISTRIBUTION TRANSFORMER - BELLACORICK 110-BELLACORICK 38-T141 | 5 | 5 | 5 | Reference (Tentative) | 05/09/2022 | 09/09/2022
TO-22-CF-T104-01 | GENERATOR TRANSFORMER - CATHALEENS FALL 110-CATHALEENS FALL G4-T104 | 1 | 1 | 1 | Scheduled | 05/09/2022 | 05/09/2022
TO-22-KLH-KNY-1-01 | 110kV FEEDER - KNOCKALOUGH-KNOCKRANNY 110-1 | 5 | 5 | 5 | Scheduled | 05/09/2022 | 09/09/2022
TO-22-110 kV A2 @ KNY-03 | BUSBAR SECTION - KNOCKRANNY 110-KNOCKRANNY 110-110A2 | 4 | 4 | 4 | Scheduled | 05/09/2022 | 08/09/2022
TO-22-110 kV B2 @ KNY-03 | BUSBAR SECTION - KNOCKRANNY 110-KNOCKRANNY 110-110B2 | 4 | 4 | 4 | Scheduled | 05/09/2022 | 08/09/2022
TO-22-SLI-110SA1-2CB-04 | COUPLER/SECTIONALISING CB - SLIGO 110-SLIGO 110-110SA1-2CB | 2 | 2 | 2 | Scheduled | 06/09/2022 | 07/09/2022
TO-22-GLR-T142-01 | DISTRIBUTION TRANSFORMER - GLENREE 110-GLENREE 38-T142 | 2 | 2 | 2 | Reference | 07/09/2022 | 08/09/2022
TO-22-110 kV A1 @ CF-02 | BUSBAR SECTION - CATHALEENS FALL 110-CATHALEENS FALL 110-110A1 | 5 | 5 | 5 | Scheduled | 12/09/2022 | 16/09/2022
TO-22-110 kV B1 @ CF-02 | BUSBAR SECTION - CATHALEENS FALL 110-CATHALEENS FALL 110-110B1 | 5 | 5 | 5 | Scheduled | 12/09/2022 | 16/09/2022
TO-22-CF-CL-1-01 | 110kV FEEDER - CATHALEENS FALL 110-CLIFF 110-1 | 5 | 5 | 5 | Scheduled | 12/09/2022 | 16/09/2022
TO-22-CL-T101-02 | GENERATOR TRANSFORMER - CLIFF 110-CLIFF G1-T101 | 5 | 5 | 5 | Scheduled | 12/09/2022 | 16/09/2022
TO-22-CL-T102-03 | GENERATOR TRANSFORMER - CLIFF 110-CLIFF G2-T102 | 5 | 5 | 5 | Scheduled | 12/09/2022 | 16/09/2022
TO-22-SLI-CAP1-02 | CAPACITOR/SVC/REACTOR - SLIGO 110-SLIGO 110-CAP1 | 7 | 5 | 5 | Scheduled | 16/09/2022 | 22/09/2022
TO-22-BK-MOY-1-02 | 110kV FEEDER - BELLACORICK 110-MOY 110-1 | 1 | 1 | 1 | Scheduled | 23/09/2022 | 23/09/2022
TO-22-MOY-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - MOY 110-MOY 110-110SA1-2CB | 1 | 1 | 1 | Scheduled | 23/09/2022 | 23/09/2022
TO-22-MOY-CAP2-01 | CAPACITOR/SVC/REACTOR - MOY 110-MOY 110-CAP2 | 1 | 1 | 1 | Scheduled | 23/09/2022 | 23/09/2022
TO-22-MOY-TAW-2-02 | 110kV FEEDER - MOY 110-TAWNAGHMORE 110-2 | 1 | 1 | 1 | Scheduled | 23/09/2022 | 23/09/2022
TO-22-ARV-COS-1-01 | 110kV FEEDER - ARVA 110-CARRICK ON SHANNON 110-1 | 5 | 5 | 5 | Scheduled | 26/09/2022 | 30/09/2022
TO-22-CSH-DLT-1-02 | 110kV FEEDER - CASHLA 110-DALTON 110-1 | 5 | 5 | 5 | Proposed | 26/09/2022 | 30/09/2022
TO-22-CDY-GRV-1-02 | 110kV FEEDER - CORDERRY 110-GARVAGH 110-1 | 5 | 5 | 5 | Proposed | 26/09/2022 | 30/09/2022
TO-22-DLT-110SA1-03 | SECTIONALISING DISCONNECT - DALTON 110-DALTON 110-110SA1 | 4 | 4 | 4 | Proposed | 26/09/2022 | 29/09/2022
TO-22-DLT-110SA2-02 | SECTIONALISING DISCONNECT - DALTON 110-DALTON 110-110SA2 | 4 | 4 | 4 | Proposed | 26/09/2022 | 29/09/2022
TO-22-DLT-T142-02 | DISTRIBUTION TRANSFORMER - DALTON 110-DALTON 38-T142 | 4 | 4 | 4 | Reference (Proposed) | 26/09/2022 | 29/09/2022
TO-22-GRV-110K1-02 | COUPLER/SECTIONALISING CB - GARVAGH 110-GARVAGH 110-110K1 | 5 | 5 | 5 | Proposed | 26/09/2022 | 30/09/2022
TO-22-GRV-T121-03 | GENERATOR TRANSFORMER - GARVAGH 110-GARVAGH 20-T121 | 5 | 5 | 5 | Proposed | 26/09/2022 | 30/09/2022
TO-22-GRV-T141-02 | DISTRIBUTION TRANSFORMER - GARVAGH 110-GARVAGH 20-T141 | 5 | 5 | 5 | Reference (Proposed) | 26/09/2022 | 30/09/2022
TO-22-KNY-UGL-1-01 | 110kV FEEDER - KNOCKRANNY-UGGOOL 110-1 | 12 | 10 | 10 | Proposed | 26/09/2022 | 07/10/2022
TO-22-UGL-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - UGGOOL 110-UGGOOL 110-110SA1-2CB | 12 | 10 | 10 | Proposed | 26/09/2022 | 07/10/2022
TO-22-UGL-T131-01 | GENERATOR TRANSFORMER - UGGOOL 110-UGGOOL 33-T131 | 12 | 10 | 10 | Proposed | 26/09/2022 | 07/10/2022
TO-22-UGL-T132-01 | GENERATOR TRANSFORMER - UGGOOL 110-UGGOOL 33-T132 | 12 | 10 | 10 | Proposed | 26/09/2022 | 07/10/2022
TO-22-UGL-T134-01 | GENERATOR TRANSFORMER - UGGOOL 110-UGGOOL 33-T134 | 12 | 10 | 10 | Proposed | 26/09/2022 | 07/10/2022
TO-22-COS-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - CARRICK ON SHANNON 110-CARRICK ON SHANNON 110-110SA1-2CB | 2 | 2 | 2 | Proposed | 27/09/2022 | 28/09/2022
TO-22-DRM-LET-1-02 | 110kV FEEDER - DRUMKEEN 110-LETTERKENNY 110-1 | 1 | 1 | 1 | Proposed | 27/09/2022 | 27/09/2022
TO-22-SOR-T124-01 | DISTRIBUTION TRANSFORMER - SORNE HILL 110-SORNE HILL 20-T124 | 1 | 1 | 1 | Reference | 27/09/2022 | 27/09/2022
TO-22-LET-TIV-1-03 | 110kV FEEDER - LETTERKENNY 110-TIEVEBRACK 110-1 | 3 | 3 | 3 | Proposed | 28/09/2022 | 30/09/2022
TO-22-CF-SRA-2-02 | 110kV FEEDER - CATHALEENS FALL 110-SRANANAGH 110-2 | 5 | 5 | 5 | Proposed | 03/10/2022 | 07/10/2022
TO-22-CLN-110SA1-01 | SECTIONALISING DISCONNECT - CLOON 110-CLOON 110-110SA1 | 3 | 3 | 3 | Proposed | 03/10/2022 | 05/10/2022
TO-22-CLN-110SA2-01 | SECTIONALISING DISCONNECT - CLOON 110-CLOON 110-110SA2 | 3 | 3 | 3 | Proposed | 03/10/2022 | 05/10/2022
TO-22-CLN-LA-1-01 | 110kV FEEDER - CLOON 110-LANESBORO 110-1 | 3 | 3 | 3 | Scheduled | 03/10/2022 | 05/10/2022
TO-22-CLN-T142-01 | DISTRIBUTION TRANSFORMER - CLOON 110-CLOON 38-T142 | 3 | 3 | 3 | Reference (Proposed) | 03/10/2022 | 05/10/2022
TO-22-110 kV B1 @ CF-03 | BUSBAR SECTION - CATHALEENS FALL 110-CATHALEENS FALL 110-110B1 | 1 | 1 | 1 | Proposed | 05/10/2022 | 05/10/2022
TO-22-CL-T101-05 | GENERATOR TRANSFORMER - CLIFF 110-CLIFF G1-T101 | 1 | 1 | 1 | Proposed | 05/10/2022 | 05/10/2022
TO-22-CL-T102-05 | GENERATOR TRANSFORMER - CLIFF 110-CLIFF G2-T102 | 1 | 1 | 1 | Proposed | 05/10/2022 | 05/10/2022
TO-22-BK-110SA1-03 | SECTIONALISING DISCONNECT - BELLACORICK 110-BELLACORICK 110-110SA1 | 5 | 5 | 5 | Scheduled | 10/10/2022 | 14/10/2022
TO-22-BK-110SA2-02 | SECTIONALISING DISCONNECT - BELLACORICK 110-BELLACORICK 110-110SA2 | 5 | 5 | 5 | Scheduled | 10/10/2022 | 14/10/2022
TO-22-BK-CBR-1-05 | 110kV FEEDER - BELLACORICK 110-CASTLEBAR 110-1 | 5 | 5 | 5 | Scheduled | 10/10/2022 | 14/10/2022
TO-22-BK-SKY-1-01 | 110kV FEEDER - BELLACORICK 110-SRAHNAKILLY 110-1 | 5 | 5 | 5 | Scheduled | 10/10/2022 | 14/10/2022
TO-22-BK-T122-01 | DISTRIBUTION TRANSFORMER - BELLACORICK 110-BELLACORICK 20-T122 | 5 | 5 | 5 | Reference (Proposed) | 10/10/2022 | 14/10/2022
TO-22-SKY-110SA1-01 | SECTIONALISING DISCONNECT - SRAHNAKILLY 110-SRAHNAKILLY 110-110SA1 | 5 | 5 | 5 | Scheduled | 10/10/2022 | 14/10/2022
TO-22-SKY-110SA2-01 | SECTIONALISING DISCONNECT - SRAHNAKILLY 110-SRAHNAKILLY 110-110SA2 | 5 | 5 | 5 | Scheduled | 10/10/2022 | 14/10/2022
TO-22-SKY-T131-02 | GENERATOR TRANSFORMER - SRAHNAKILLY 110-SRAHNAKILLY 33-T131 | 5 | 5 | 5 | Scheduled | 10/10/2022 | 14/10/2022
TO-22-ARI-T121-01 | DISTRIBUTION TRANSFORMER - ARIGNA 110-ARIGNA 20-T121 | 12 | 10 | 10 | Reference | 17/10/2022 | 28/10/2022
TO-22-ARI,T-ARI-1-01 | 110kV FEEDER - ARIGNA tee-ARIGNA 110-1 | 12 | 10 | 10 | Scheduled | 17/10/2022 | 28/10/2022
TO-22-ARI,T-COS-1-01 | 110kV FEEDER - ARIGNA tee-CARRICK ON SHANNON 110-1 | 12 | 10 | 10 | Scheduled | 17/10/2022 | 28/10/2022
TO-22-ARI,T-CDY-1-02 | 110kV FEEDER - ARIGNA tee-CORDERRY 110-1 | 12 | 10 | 10 | Scheduled | 17/10/2022 | 28/10/2022
TO-22-CUN-GLR-1-01 | 110kV FEEDER - CUNGHILL 110-GLENREE 110-1 | 1 | 1 | 1 | Scheduled | 25/10/2022 | 25/10/2022
TO-22-CSH-T2101-01 | TRANSFORMER - CASHLA 220-CASHLA 110-T2101 | 1 | 1 | 1 | Proposed | 26/10/2022 | 26/10/2022
TO-22-GLR-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - GLENREE 110-GLENREE 110-110SA1-2CB | 1 | 1 | 1 | Scheduled | 26/10/2022 | 26/10/2022
TO-22-BK-110SA1-02 | SECTIONALISING DISCONNECT - BELLACORICK 110-BELLACORICK 110-110SA1 | 4 | 4 | 4 | Proposed | 01/11/2022 | 04/11/2022
TO-22-BK-110SA2-03 | SECTIONALISING DISCONNECT - BELLACORICK 110-BELLACORICK 110-110SA2 | 4 | 4 | 4 | Proposed | 01/11/2022 | 04/11/2022
TO-22-BK-MOY-1-05 | 110kV FEEDER - BELLACORICK 110-MOY 110-1 | 4 | 4 | 4 | Proposed | 01/11/2022 | 04/11/2022
TO-22-BK-T141-02 | DISTRIBUTION TRANSFORMER - BELLACORICK 110-BELLACORICK 38-T141 | 4 | 4 | 4 | Reference (Proposed) | 01/11/2022 | 04/11/2022
TO-22-DRM-110SA1-01 | SECTIONALISING DISCONNECT - DRUMKEEN 110-DRUMKEEN 110-110SA1 | 1 | 1 | 1 | Proposed | 01/11/2022 | 01/11/2022
TO-22-DRM-110SA2-01 | SECTIONALISING DISCONNECT - DRUMKEEN 110-DRUMKEEN 110-110SA2 | 1 | 1 | 1 | Proposed | 01/11/2022 | 01/11/2022
TO-22-DRM-LET-1-05 | 110kV FEEDER - DRUMKEEN 110-LETTERKENNY 110-1 | 1 | 1 | 1 | Proposed | 01/11/2022 | 01/11/2022
TO-22-DRM-MEE-1-03 | 110kV FEEDER - DRUMKEEN 110-MEENTYCAT 110-1 | 1 | 1 | 1 | Proposed | 01/11/2022 | 01/11/2022
TO-22-MEE-T121-02 | GENERATOR TRANSFORMER - MEENTYCAT 110-MEENTYCAT 20-T121 | 1 | 1 | 1 | Proposed | 01/11/2022 | 01/11/2022
TO-22-CBR-SVC-03 | CAPACITOR/SVC/REACTOR - CASTLEBAR 110-CASTLEBAR 110-SVC | 2 | 2 | 2 | Proposed | 02/11/2022 | 03/11/2022
TO-22-CDY-SRA-1-02 | 110kV FEEDER - CORDERRY 110-SRANANAGH 110-1 | 1 | 1 | 1 | Proposed | 02/11/2022 | 02/11/2022
TO-22-CSH-GAL-2-04 | 110kV FEEDER - CASHLA 110-GALWAY 110-2 | 5 | 5 | 5 | Proposed | 07/11/2022 | 11/11/2022
TO-22-CBR-DLT-1-01 | 110kV FEEDER - CASTLEBAR 110-DALTON 110-1 | 5 | 5 | 5 | Proposed | 07/11/2022 | 11/11/2022
TO-22-CF-CLO-1-02 | 110kV FEEDER - CATHALEENS FALL 110-CLOGHER 110-1 | 12 | 10 | 10 | Proposed | 07/11/2022 | 18/11/2022
TO-22-CF-CLO-2-01 | 110kV FEEDER - CATHALEENS FALL 110-CLOGHER 110-2 | 12 | 10 | 10 | Proposed | 07/11/2022 | 18/11/2022
TO-22-DLT-110SA1-02 | SECTIONALISING DISCONNECT - DALTON 110-DALTON 110-110SA1 | 5 | 5 | 5 | Proposed | 07/11/2022 | 11/11/2022
TO-22-DLT-110SA2-03 | SECTIONALISING DISCONNECT - DALTON 110-DALTON 110-110SA2 | 5 | 5 | 5 | Proposed | 07/11/2022 | 11/11/2022
TO-22-DLT-CAP1-01 | CAPACITOR/SVC/REACTOR - DALTON 110-DALTON 110-CAP1 | 5 | 5 | 5 | Proposed | 07/11/2022 | 11/11/2022
TO-22-DLT-T141-01 | DISTRIBUTION TRANSFORMER - DALTON 110-DALTON 38-T141 | 5 | 5 | 5 | Reference (Proposed) | 07/11/2022 | 11/11/2022
TO-22-220 kV A2 @ CSH-01 | BUSBAR SECTION - CASHLA 220-CASHLA 220-220A2 | 5 | 5 | 5 | Proposed | 14/11/2022 | 18/11/2022
TO-22-220 kV A4 @ CSH-01 | BUSBAR SECTION - CASHLA 220-CASHLA 220-220A4 | 5 | 5 | 5 | Proposed | 14/11/2022 | 18/11/2022
TO-22-220 kV B2 @ CSH-01 | BUSBAR SECTION - CASHLA 220-CASHLA 220-220B2 | 5 | 5 | 5 | Proposed | 14/11/2022 | 18/11/2022
TO-22-220 kV B4 @ CSH-01 | BUSBAR SECTION - CASHLA 220-CASHLA 220-220B4 | 5 | 5 | 5 | Proposed | 14/11/2022 | 18/11/2022
TO-22-CSH-220K2-4-01 | COUPLER/SECTIONALISING CB - CASHLA 220-CASHLA 220-220K2-4 | 5 | 5 | 5 | Proposed | 14/11/2022 | 18/11/2022
TO-22-FLA-SLI-1-04 | 110kV FEEDER - FLAGFORD 110-SLIGO 110-1 | 5 | 5 | 5 | Proposed | 14/11/2022 | 18/11/2022
TO-22-CSH-CLN-1-03 | 110kV FEEDER - CASHLA 110-CLOON 110-1 | 14 | 10 | 10 | Proposed | 15/11/2022 | 28/11/2022
TO-22-MOY-TAW-2-01 | 110kV FEEDER - MOY 110-TAWNAGHMORE 110-2 | 5 | 5 |  | Proposed | 21/11/2022 | 25/11/2022
TO-22-FLA-SRA-1-03 | 220kV FEEDER - FLAGFORD 220-SRANANAGH 220-1 | 1 | 1 | 1 | Proposed | 29/11/2022 | 29/11/2022

## GEN_NorthEast
Outage ID | Feeder ID | Calendar Day Duration | Working Day Duration | Work Days | Outage Status | Start | Finish
TO-22-ARV-GWE-1-03 | 110kV FEEDER - ARVA 110-GORTAWEE 110-1 | 5 | 5 | 5 | Scheduled | 10/01/2022 | 14/01/2022
TO-22-SLB-110K2-01 | COUPLER/SECTIONALISING CB - SLIABH BAWN 110-SLIABH BAWN 110-110K2 | 5 | 5 | 5 | Scheduled | 10/01/2022 | 14/01/2022
TO-22-220 kV A1 @ GOR-01 | BUSBAR SECTION - GORMAN 220-GORMAN 220-220A1 | 4 | 4 | 4 | Scheduled | 17/01/2022 | 20/01/2022
TO-22-220 kV A2 @ GOR-01 | BUSBAR SECTION - GORMAN 220-GORMAN 220-220A2 | 4 | 4 | 4 | Scheduled | 17/01/2022 | 20/01/2022
TO-22-220 kV B1 @ GOR-01 | BUSBAR SECTION - GORMAN 220-GORMAN 220-220B1 | 4 | 4 | 4 | Scheduled | 17/01/2022 | 20/01/2022
TO-22-220 kV B2 @ GOR-01 | BUSBAR SECTION - GORMAN 220-GORMAN 220-220B2 | 4 | 4 | 4 | Scheduled | 17/01/2022 | 20/01/2022
TO-22-GOR-220K1-2-02 | COUPLER/SECTIONALISING CB - GORMAN 220-GORMAN 220-220K1-2 | 4 | 4 |  | Scheduled | 17/01/2022 | 20/01/2022
TO-22-GWE-T101-02 | TSO CUSTOMER TRANSFORMER - GORTAWEE 110-GORTAWEE 10-T101 | 1 | 1 | 1 | Scheduled | 18/01/2022 | 18/01/2022
TO-22-GWE-T102-02 | TSO CUSTOMER TRANSFORMER - GORTAWEE 110-GORTAWEE 10-T102 | 1 | 1 | 1 | Scheduled | 19/01/2022 | 19/01/2022
TO-22-SH-220K1-2-01 | COUPLER/SECTIONALISING CB - SHANNONBRIDGE 220-SHANNONBRIDGE 220-220K1-2 | 5 | 5 |  | Scheduled | 24/01/2022 | 28/01/2022
TO-22-LOU-RRU-1-03 | 110kV FEEDER - LOUTH 110-RATRUSSAN 110-1 | 1 | 1 | 1 | Tentative | 03/02/2022 | 03/02/2022
TO-22-110 kV A1/A2 @ RRU-01 | BUSBAR SECTION - RATRUSSAN 110-RATRUSSAN 110-110A1-A2 | 1 | 1 | 1 | Tentative | 03/02/2022 | 03/02/2022
TO-22-RRU-110SA1-01 | SECTIONALISING DISCONNECT - RATRUSSAN 110-RATRUSSAN 110-110SA1 | 1 | 1 | 1 | Tentative | 03/02/2022 | 03/02/2022
TO-22-RRU-110SA2-01 | SECTIONALISING DISCONNECT - RATRUSSAN 110-RATRUSSAN 110-110SA2 | 1 | 1 | 1 | Tentative | 03/02/2022 | 03/02/2022
TO-22-RRU-SKL-1-03 | 110kV FEEDER - RATRUSSAN 110-SHANKILL 110-1 | 1 | 1 |  | Tentative | 03/02/2022 | 03/02/2022
TO-22-RRU-T121-01 | GENERATOR TRANSFORMER - RATRUSSAN 110-RATRUSSAN 20-T121 | 1 | 1 |  | Tentative | 03/02/2022 | 03/02/2022
TO-22-RRU-T122-03 | GENERATOR TRANSFORMER - RATRUSSAN 110-RATRUSSAN 20-T122 | 1 | 1 | 1 | Tentative | 03/02/2022 | 03/02/2022
TO-22-PLA-T105-02 | TSO CUSTOMER TRANSFORMER - PLATIN 110-PLATIN 10-T105 | 8 | 6 | 6 | Scheduled | 23/02/2022 | 02/03/2022
TO-22-CDU-PLA-1-01 | 110kV FEEDER - CORDUFF 110-PLATIN 110-1 | 159 | 108 | 108 | Scheduled | 28/02/2022 | 05/08/2022
TO-22-FLA-SLB-1-01 | 110kV FEEDER - FLAGFORD 110-SLIABH BAWN 110-1 | 59 | 40 | 40 | Scheduled | 28/02/2022 | 27/04/2022
TO-22-SOM-T142-01 | DISTRIBUTION TRANSFORMER - SOMERSET 110-SOMERSET 38-T142 | 79 | 52 | 52 | Reference | 28/02/2022 | 17/05/2022
TO-22-SOM,T-CSH-1-05 | 110kV FEEDER - SOMERSET tee-CASHLA 110-1 | 12 | 10 | 10 | Scheduled | 28/02/2022 | 11/03/2022
TO-22-SOM,T-SH-1-05 | 110kV FEEDER - SOMERSET tee-SHANNONBRIDGE 110-1 | 12 | 10 | 10 | Scheduled | 28/02/2022 | 11/03/2022
TO-22-LIS-LOU-1-05 | 110kV FEEDER - LISDRUM 110-LOUTH 110-1 | 3 | 3 | 3 | Scheduled | 01/03/2022 | 03/03/2022
TO-22-PLA-T101/2/3/4-04 | TSO CUSTOMER TRANSFORMER - PLATIN 110-PLATIN 10-T101/2/3/4 | 14 | 10 | 10 | Scheduled | 03/03/2022 | 16/03/2022
TO-22-LOU-MLN-1-01 | 110kV FEEDER - LOUTH 110-MULLAGHARLIN 110-1 | 1 | 1 | 1 | Scheduled | 21/03/2022 | 21/03/2022
TO-22-DDK-LOU-1-01 | 110kV FEEDER - DUNDALK 110-LOUTH 110-1 | 4 | 4 | 4 | Scheduled | 22/03/2022 | 25/03/2022
TO-22-DDK-MLN-1-01 | 110kV FEEDER - DUNDALK 110-MULLAGHARLIN 110-1 | 100 | 68 | 68 | Scheduled | 28/03/2022 | 05/07/2022
TO-22-AGL-SH-1-01 | 110kV FEEDER - AGANNYGAL 110-SHANNONBRIDGE 110-1 | 4 | 4 | 4 | Scheduled | 04/04/2022 | 07/04/2022
TO-22-DDK-110SA1-01 | SECTIONALISING DISCONNECT - DUNDALK 110-DUNDALK 110-110SA1 | 5 | 5 | 5 | Scheduled | 04/04/2022 | 08/04/2022
TO-22-DDK-110SA2-01 | SECTIONALISING DISCONNECT - DUNDALK 110-DUNDALK 110-110SA2 | 5 | 5 | 5 | Scheduled | 04/04/2022 | 08/04/2022
TO-22-DDK-T141-01 | DISTRIBUTION TRANSFORMER - DUNDALK 110-DUNDALK 38-T141 | 5 | 5 | 5 | Reference | 04/04/2022 | 08/04/2022
TO-22-KIN-T101-02 | TSO CUSTOMER TRANSFORMER - KINNEGAD 110-KINNEGAD 10-T101 | 1 | 1 | 1 | Scheduled | 20/04/2022 | 20/04/2022
TO-22-LOU-T2103-03 | TRANSFORMER - LOUTH 220-LOUTH 110-T2103 | 1 | 1 | 1 | Scheduled | 20/04/2022 | 20/04/2022
TO-22-CF-COR-1-02 | 110kV FEEDER - CATHALEENS FALL 110-CORRACLASSY 110-1 | 5 | 5 | 5 | Tentative | 25/04/2022 | 29/04/2022
TO-22-110 kV A1/A2 @ ARV-01 | BUSBAR SECTION - ARVA 110-ARVA 110-110A1-A2 | 1 | 1 | 1 | Scheduled | 27/04/2022 | 27/04/2022
TO-22-110 kV B1/B2 @ ARV-01 | BUSBAR SECTION - ARVA 110-ARVA 110-110B1-B2 | 1 | 1 | 1 | Scheduled | 27/04/2022 | 27/04/2022
TO-22-AGL-ENN-1-01 | 110kV FEEDER - AGANNYGAL 110-ENNIS 110-1 | 11 | 9 | 4 | Scheduled | 03/05/2022 | 13/05/2022
TO-22-GOR-T122-01 | GENERATOR TRANSFORMER - GORMAN 110-GORMAN 20-T122 | 4 | 4 | 4 | Scheduled | 03/05/2022 | 06/05/2022
TO-22-LA-RIC-2-01 | 110kV FEEDER - LANESBORO 110-RICHMOND 110-2 | 4 | 4 | 4 | Reference | 03/05/2022 | 06/05/2022
TO-22-CUS-MLC-1-02 | 110kV FEEDER - CUSHALING 110-MOUNTLUCAS 110-1 | 92 | 64 | 64 | Scheduled | 06/05/2022 | 05/08/2022
TO-22-LOU-AT3-01 | TRANSFORMER - LOUTH 220-LOUTH 275-AT3 | 36 | 25 | 25 | Scheduled | 10/05/2022 | 14/06/2022
TO-22-GOR-220K1-2-01 | COUPLER/SECTIONALISING CB - GORMAN 220-GORMAN 220-220K1-2 | 29 | 20 | 20 | Scheduled | 17/05/2022 | 14/06/2022
TO-22-SLB-T132-01 | GENERATOR TRANSFORMER - SLIABH BAWN 110-SLIABH BAWN 33-T132 | 2 | 2 | 2 | Scheduled | 24/05/2022 | 25/05/2022
TO-22-KLN-SH-1-01 | 220kV FEEDER - KILLONAN 220-SHANNONBRIDGE 220-1 | 13 | 9 | 9 | Scheduled | 30/05/2022 | 11/06/2022
TO-22-KIN-MUL-1-02 | 110kV FEEDER - KINNEGAD 110-MULLINGAR 110-1 | 5 | 5 | 5 | Tentative | 30/05/2022 | 03/06/2022
TO-22-MUL-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - MULLINGAR 110-MULLINGAR 110-110SA1-2CB | 5 | 5 | 5 | Tentative | 30/05/2022 | 03/06/2022
TO-22-MUL-CAP1-01 | CAPACITOR/SVC/REACTOR - MULLINGAR 110-MULLINGAR 110-CAP1 | 5 | 5 | 5 | Tentative | 30/05/2022 | 03/06/2022
TO-22-CF-COR-1-03 | 110kV FEEDER - CATHALEENS FALL 110-CORRACLASSY 110-1 | 29 | 20 | 20 | Scheduled | 06/06/2022 | 04/07/2022
TO-22-BAL-DRY-1-02 | 110kV FEEDER - BALTRASNA 110-DRYBRIDGE 110-1 | 2 | 2 | 2 | Scheduled | 08/06/2022 | 09/06/2022
TO-22-MLC-110SA1-01 | SECTIONALISING DISCONNECT - MOUNTLUCAS 110-MOUNTLUCAS 110-110SA1 | 5 | 5 | 5 | Scheduled | 13/06/2022 | 17/06/2022
TO-22-MLC-110SA2-01 | SECTIONALISING DISCONNECT - MOUNTLUCAS 110-MOUNTLUCAS 110-110SA2 | 5 | 5 |  | Scheduled | 13/06/2022 | 17/06/2022
TO-22-MLC-T121-01 | GENERATOR TRANSFORMER - MOUNTLUCAS 110-MOUNTLUCAS 20-T121 | 5 | 5 | 5 | Scheduled | 13/06/2022 | 17/06/2022
TO-22-MLC-TSB-1-01 | 110kV FEEDER - MOUNTLUCAS 110-THORNSBERRY 110-1 | 5 | 5 | 5 | Scheduled | 13/06/2022 | 17/06/2022
TO-22-110 kV A1 @ GOR-02 | BUSBAR SECTION - GORMAN 110-GORMAN 110-110A1 | 4 | 4 | 4 | Scheduled | 14/06/2022 | 17/06/2022
TO-22-110 kV B1 @ GOR-01 | BUSBAR SECTION - GORMAN 110-GORMAN 110-110B1 | 4 | 4 | 4 | Scheduled | 14/06/2022 | 17/06/2022
TO-22-GOR-NAV-1-01 | 110kV FEEDER - GORMAN 110-NAVAN 110-1 | 4 | 4 | 4 | Scheduled | 14/06/2022 | 17/06/2022
TO-22-CDU-MUL-1-02 | 110kV FEEDER - CORDUFF 110-MULLINGAR 110-1 | 1 | 1 | 1 | Scheduled | 21/06/2022 | 21/06/2022
TO-22-MUL-110SA1-2CB-02 | COUPLER/SECTIONALISING CB - MULLINGAR 110-MULLINGAR 110-110SA1-2CB | 1 | 1 | 1 | Scheduled | 21/06/2022 | 21/06/2022
TO-22-MUL-CAP2-02 | CAPACITOR/SVC/REACTOR - MULLINGAR 110-MULLINGAR 110-CAP2 | 1 | 1 | 1 | Scheduled | 21/06/2022 | 21/06/2022
TO-22-MUL-T102-01 | DISTRIBUTION TRANSFORMER - MULLINGAR 110-MULLINGAR 10-T102 | 1 | 1 | 1 | Reference | 21/06/2022 | 21/06/2022
TO-22-MUL-T142-01 | DISTRIBUTION TRANSFORMER - MULLINGAR 110-MULLINGAR 38-T142 | 1 | 1 | 1 | Reference | 21/06/2022 | 21/06/2022
TO-22-ATH-110SA1-2CB-02 | COUPLER/SECTIONALISING CB - ATHLONE 110-ATHLONE 110-110SA1-2CB | 5 | 5 | 5 | Scheduled | 04/07/2022 | 08/07/2022
TO-22-ATH-CAP3-01 | CAPACITOR/SVC/REACTOR - ATHLONE 110-ATHLONE 110-CAP3 | 5 | 5 | 5 | Scheduled | 04/07/2022 | 08/07/2022
TO-22-ATH-LA-1-01 | 110kV FEEDER - ATHLONE 110-LANESBORO 110-1 | 12 | 10 | 10 | Scheduled | 04/07/2022 | 15/07/2022
TO-22-ATH-M/CAP1-01 | CAPACITOR/SVC/REACTOR - ATHLONE 110-ATHLONE 110-M/CAP1 | 5 | 5 | 5 | Scheduled | 04/07/2022 | 08/07/2022
TO-22-ATH-T141-01 | DISTRIBUTION TRANSFORMER - ATHLONE 110-ATHLONE 38-T141 | 5 | 5 | 5 | Reference | 04/07/2022 | 08/07/2022
TO-22-LOU-MTH-1-04 | 110kV FEEDER - LOUTH 110-MEATH HILL 110-1 | 5 | 5 | 5 | Scheduled | 04/07/2022 | 08/07/2022
TO-22-MTH-110SA1-01 | SECTIONALISING DISCONNECT - MEATH HILL 110-MEATH HILL 110-110SA1 | 5 | 5 | 5 | Scheduled | 04/07/2022 | 08/07/2022
TO-22-MTH-110SA2-02 | SECTIONALISING DISCONNECT - MEATH HILL 110-MEATH HILL 110-110SA2 | 5 | 5 | 5 | Scheduled | 04/07/2022 | 08/07/2022
TO-22-MTH-T141-02 | DISTRIBUTION TRANSFORMER - MEATH HILL 110-MEATH HILL 38-T141 | 5 | 5 | 5 | Reference | 04/07/2022 | 08/07/2022
TO-22-ARV-SKL-1-05 | 110kV FEEDER - ARVA 110-SHANKILL 110-1 | 5 | 5 | 5 | Scheduled | 11/07/2022 | 15/07/2022
TO-22-SKL-110SA1-05 | SECTIONALISING DISCONNECT - SHANKILL 110-SHANKILL 110-110SA1 | 5 | 5 | 5 | Scheduled | 11/07/2022 | 15/07/2022
TO-22-SKL-110SA2-03 | SECTIONALISING DISCONNECT - SHANKILL 110-SHANKILL 110-110SA2 | 5 | 5 | 5 | Scheduled | 11/07/2022 | 15/07/2022
TO-22-SKL-M/CAP2-03 | CAPACITOR/SVC/REACTOR - SHANKILL 110-SHANKILL 110-M/CAP2 | 5 | 5 | 5 | Scheduled | 11/07/2022 | 15/07/2022
TO-22-SKL-T142-02 | DISTRIBUTION TRANSFORMER - SHANKILL 110-SHANKILL 38-T142 | 5 | 5 | 5 | Reference | 11/07/2022 | 15/07/2022
TO-22-CFN-T232-01 | GENERATOR TRANSFORMER - CLONIFFEEN 220-CLONIFFEEN 33-T232 | 2 | 2 | 2 | Scheduled | 14/07/2022 | 15/07/2022
TO-22-LOU-T2101-01 | TRANSFORMER - LOUTH 220-LOUTH 110-T2101 | 5 | 5 | 5 | Scheduled | 25/07/2022 | 29/07/2022
TO-22-MP GIS-OST-1-02 | 400kV FEEDER - MONEYPOINT GIS 400-OLDSTREET 400-1 | 5 | 5 | 5 | Scheduled | 25/07/2022 | 29/07/2022
TO-22-MLN-T124-01 | TSO CUSTOMER TRANSFORMER - MULLAGHARLIN 110-MULLAGHARLIN 20-T124 | 2 | 2 | 2 | Scheduled | 02/08/2022 | 03/08/2022
TO-22-MLN-T123-02 | TSO CUSTOMER TRANSFORMER - MULLAGHARLIN 110-MULLAGHARLIN 20-T123 | 2 | 2 | 2 | Scheduled | 04/08/2022 | 05/08/2022
TO-22-MLC-TSB-1-02 | 110kV FEEDER - MOUNTLUCAS 110-THORNSBERRY 110-1 | 5 | 5 | 5 | Scheduled | 08/08/2022 | 12/08/2022
TO-22-CSH-TY-1-05 | 220kV FEEDER - CASHLA 220-TYNAGH 220-1 | 5 | 5 | 5 | Scheduled | 15/08/2022 | 19/08/2022
TO-22-CF-COR-1-01 | 110kV FEEDER - CATHALEENS FALL 110-CORRACLASSY 110-1 | 40 | 30 | 30 | Scheduled | 15/08/2022 | 23/09/2022
TO-22-CDU-MUL-1-01 | 110kV FEEDER - CORDUFF 110-MULLINGAR 110-1 | 44 | 32 | 32 | Scheduled | 15/08/2022 | 27/09/2022
TO-22-110 kV A2 @ SLB-01 | BUSBAR SECTION - SLIABH BAWN 110-SLIABH BAWN 110-110A2 | 5 | 5 | 5 | Scheduled | 15/08/2022 | 19/08/2022
TO-22-110 kV B2 @ SLB-01 | BUSBAR SECTION - SLIABH BAWN 110-SLIABH BAWN 110-110B2 | 5 | 5 | 5 | Scheduled | 15/08/2022 | 19/08/2022
TO-22-SLB-110K2-02 | COUPLER/SECTIONALISING CB - SLIABH BAWN 110-SLIABH BAWN 110-110K2 | 5 | 5 | 5 | Scheduled | 15/08/2022 | 19/08/2022
TO-22-LA-SLB-1-01 | 110kV FEEDER - LANESBORO 110-SLIABH BAWN 110-1 | 5 | 5 | 5 | Scheduled | 22/08/2022 | 26/08/2022
TO-22-SH-T2102-01 | TRANSFORMER - SHANNONBRIDGE 220-SHANNONBRIDGE 110-T2102 | 5 | 5 | 5 | Scheduled | 29/08/2022 | 02/09/2022
TO-22-GOR-110K1-2-02 | COUPLER/SECTIONALISING CB - GORMAN 110-GORMAN 110-110K1-2 | 1 | 1 | 1 | Tentative | 30/08/2022 | 30/08/2022
TO-22-KLN-SH-1-03 | 220kV FEEDER - KILLONAN 220-SHANNONBRIDGE 220-1 | 1 | 1 | 1 | Scheduled | 02/09/2022 | 02/09/2022
TO-22-110 kV A1 @ LOU-01 | BUSBAR SECTION - LOUTH 110-LOUTH 110-110A1 | 5 | 5 | 5 | Scheduled | 05/09/2022 | 09/09/2022
TO-22-110 kV B1 @ LOU-01 | BUSBAR SECTION - LOUTH 110-LOUTH 110-110B1 | 5 | 5 | 5 | Scheduled | 05/09/2022 | 09/09/2022
TO-22-LOU-CAP1-02 | CAPACITOR/SVC/REACTOR - LOUTH 110-LOUTH 110-CAP1 | 5 | 5 | 5 | Scheduled | 05/09/2022 | 09/09/2022
TO-22-GOR-PLA-1-01 | 110kV FEEDER - GORMAN 110-PLATIN 110-1 | 79 | 56 | 56 | Scheduled | 06/09/2022 | 23/11/2022
TO-22-GWE-T142-01 | DISTRIBUTION TRANSFORMER - GORTAWEE 110-GORTAWEE 38-T142 | 2 | 2 | 2 | Reference | 08/09/2022 | 09/09/2022
TO-22-ARV-SKL-1-03 | 110kV FEEDER - ARVA 110-SHANKILL 110-1 | 5 | 5 | 5 | Scheduled | 12/09/2022 | 16/09/2022
TO-22-KUR-NAV-1-01 | 110kV FEEDER - KNOCKUMBER 110-NAVAN 110-1 | 5 | 5 | 5 | Scheduled | 12/09/2022 | 16/09/2022
TO-22-KUR-T3-01 | TSO CUSTOMER TRANSFORMER - KNOCKUMBER 110-KNOCKUMBER 10-T3 | 5 | 5 | 5 | Reference | 12/09/2022 | 16/09/2022
TO-22-KUR-T4-01 | TSO CUSTOMER TRANSFORMER - KNOCKUMBER 110-KNOCKUMBER 10-T4 | 5 | 5 | 5 | Reference | 12/09/2022 | 16/09/2022
TO-22-110 kV A1/A2 @ SH-01 | BUSBAR SECTION - SHANNONBRIDGE 110-SHANNONBRIDGE 110-110A1-A2 | 1 | 1 | 1 | Scheduled | 14/09/2022 | 14/09/2022
TO-22-110 kV B1/B2 @ SH-01 | BUSBAR SECTION - SHANNONBRIDGE 110-SHANNONBRIDGE 110-110B1-B2 | 1 | 1 | 1 | Scheduled | 14/09/2022 | 14/09/2022
TO-22-220 kV A1/A2 @ SH-01 | BUSBAR SECTION - SHANNONBRIDGE 220-SHANNONBRIDGE 220-220A1-A2 | 1 | 1 | 1 | Scheduled | 14/09/2022 | 14/09/2022
TO-22-220 kV B1/B2 @ SH-01 | BUSBAR SECTION - SHANNONBRIDGE 220-SHANNONBRIDGE 220-220B1-B2 | 1 | 1 | 1 | Scheduled | 14/09/2022 | 14/09/2022
TO-22-DER-T1/T2-01 | GENERATOR TRANSFORMER - DERRYIRON 110-RHODE 110-T1/T2 | 11 | 7 | 7 | Scheduled | 23/09/2022 | 03/10/2022
TO-22-ARV-COS-1-01 | 110kV FEEDER - ARVA 110-CARRICK ON SHANNON 110-1 | 5 | 5 | 5 | Scheduled | 26/09/2022 | 30/09/2022
TO-22-CLN-LA-1-01 | 110kV FEEDER - CLOON 110-LANESBORO 110-1 | 3 | 3 | 3 | Scheduled | 03/10/2022 | 05/10/2022
TO-22-ARV-110K1-2-02 | COUPLER/SECTIONALISING CB - ARVA 110-ARVA 110-110K1-2 | 2 | 2 | 2 | Proposed | 04/10/2022 | 05/10/2022
TO-22-ARV-NAV-1-01 | 110kV FEEDER - ARVA 110-NAVAN 110-1 | 9 | 7 | 7 | Proposed | 10/10/2022 | 18/10/2022
TO-22-ATH-SH-1-01 | 110kV FEEDER - ATHLONE 110-SHANNONBRIDGE 110-1 | 12 | 10 | 10 | Proposed | 10/10/2022 | 21/10/2022
TO-22-DRY-T141-03 | DISTRIBUTION TRANSFORMER - DRYBRIDGE 110-DRYBRIDGE 38-T141 | 5 | 5 | 5 | Reference (Proposed) | 10/10/2022 | 14/10/2022
TO-22-DFR,T-KIN-1-05 | 110kV FEEDER - DUNFIRTH tee-KINNEGAD 110-1 | 5 | 5 | 5 | Proposed | 17/10/2022 | 21/10/2022
TO-22-KIN-110SA1-2CB-02 | COUPLER/SECTIONALISING CB - KINNEGAD 110-KINNEGAD 110-110SA1-2CB | 5 | 5 | 5 | Proposed | 17/10/2022 | 21/10/2022
TO-22-KIN-T102-01 | TSO CUSTOMER TRANSFORMER - KINNEGAD 110-KINNEGAD 10-T102 | 5 | 5 | 5 | Proposed | 17/10/2022 | 21/10/2022
TO-22-LOU-WOO-1-02 | 220kV FEEDER - LOUTH 220-WOODLAND 220-1 | 10 | 8 | 8 | Scheduled | 17/10/2022 | 26/10/2022
TO-22-GWE-CAP1-02 | CAPACITOR/SVC/REACTOR - GORTAWEE 110-GORTAWEE 110-CAP1 | 4 | 4 | 4 | Proposed | 18/10/2022 | 21/10/2022
TO-22-ARV-SKL-2-02 | 110kV FEEDER - ARVA 110-SHANKILL 110-2 | 7 | 5 | 5 | Proposed | 19/10/2022 | 25/10/2022
TO-22-DRY-LOU-1-03 | 110kV FEEDER - DRYBRIDGE 110-LOUTH 110-1 | 8 | 5 | 5 | Proposed | 27/10/2022 | 03/11/2022
TO-22-IKE,T-SH-1-05 | 110kV FEEDER - IKERRIN tee-SHANNONBRIDGE 110-1 | 21 | 15 | 15 | Proposed | 01/11/2022 | 21/11/2022
TO-22-COR-GWE-1-02 | 110kV FEEDER - CORRACLASSY 110-GORTAWEE 110-1 | 3 | 3 | 3 | Proposed | 02/11/2022 | 04/11/2022
TO-22-LOU-110K1-2-03 | COUPLER/SECTIONALISING CB - LOUTH 110-LOUTH 110-110K1-2 | 1 | 1 | 1 | Proposed | 03/11/2022 | 03/11/2022
TO-22-ARV-GWE-1-02 | 110kV FEEDER - ARVA 110-GORTAWEE 110-1 | 5 | 5 | 5 | Proposed | 07/11/2022 | 11/11/2022
TO-22-MAY-SH-1-04 | 220kV FEEDER - MAYNOOTH 220-SHANNONBRIDGE 220-1 | 5 | 5 | 5 | Proposed | 07/11/2022 | 11/11/2022
TO-22-110 kV A2 @ GOR-01 | BUSBAR SECTION - GORMAN 110-GORMAN 110-110A2 | 4 | 4 | 4 | Proposed | 08/11/2022 | 11/11/2022
TO-22-110 kV B2 @ GOR-01 | BUSBAR SECTION - GORMAN 110-GORMAN 110-110B2 | 4 | 4 | 4 | Proposed | 08/11/2022 | 11/11/2022
TO-22-GOR-MTH-1-02 | 110kV FEEDER - GORMAN 110-MEATH HILL 110-1 | 4 | 4 | 4 | Proposed | 08/11/2022 | 11/11/2022
TO-22-220 kV B2 @ GOR-03 | BUSBAR SECTION - GORMAN 220-GORMAN 220-220B2 | 2 | 2 | 2 | Proposed | 14/11/2022 | 15/11/2022
TO-22-GOR-LOU-1-01 | 220kV FEEDER - GORMAN 220-LOUTH 220-1 | 5 | 5 | 5 | Proposed | 14/11/2022 | 18/11/2022
TO-22-220 kV A2 @ GOR-02 | BUSBAR SECTION - GORMAN 220-GORMAN 220-220A2 | 7 | 5 | 5 | Proposed | 16/11/2022 | 22/11/2022
TO-22-220 kV B2 @ GOR-02 | BUSBAR SECTION - GORMAN 220-GORMAN 220-220B2 | 7 | 5 | 5 | Proposed | 16/11/2022 | 22/11/2022
TO-22-NAV-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - NAVAN 110-NAVAN 110-110SA1-2CB | 1 | 1 | 1 | Proposed | 16/11/2022 | 16/11/2022
TO-22-110 kV A2 @ LOU-06 | BUSBAR SECTION - LOUTH 110-LOUTH 110-110A2 | 5 | 5 | 5 | Proposed | 21/11/2022 | 25/11/2022
TO-22-110 kV B2 @ LOU-06 | BUSBAR SECTION - LOUTH 110-LOUTH 110-110B2 | 5 | 5 | 5 | Proposed | 21/11/2022 | 25/11/2022
TO-22-LIS-T131-02 | GENERATOR TRANSFORMER - LISDRUM 110-LISDRUM 33-T131 | 2 | 2 | 2 | Proposed | 28/11/2022 | 29/11/2022
TO-22-LOU-T2102-01 | TRANSFORMER - LOUTH 220-LOUTH 110-T2102 | 2 | 2 | 2 | Proposed | 28/11/2022 | 29/11/2022
TO-22-DRY-PLA-1-04 | 110kV FEEDER - DRYBRIDGE 110-PLATIN 110-1 | 1 | 1 | 1 | Proposed | 29/11/2022 | 29/11/2022

## GEN_Dublin
Outage ID | Feeder ID | Calendar Day Duration | Working Day Duration | Work Days | Outage Status | Start | Finish
TO-22-CLG-T122-01 | TSO CUSTOMER TRANSFORMER - CLOGHRAN 110-CLOGHRAN 20-T122 | 107 | 73 | 73 | Scheduled | 13/01/2022 | 29/04/2022
TO-22-110 kV A1 @ FIN GIS-01 | BUSBAR SECTION - FINGLAS GIS 110-FINGLAS GIS 110-110A1 | 5 | 5 | 5 | Scheduled | 17/01/2022 | 21/01/2022
TO-22-110 kV A3 @ FIN GIS-01 | BUSBAR SECTION - FINGLAS GIS 110-FINGLAS GIS 110-110A3 | 5 | 5 | 5 | Scheduled | 17/01/2022 | 21/01/2022
TO-22-110 kV B1 @ FIN GIS-01 | BUSBAR SECTION - FINGLAS GIS 110-FINGLAS GIS 110-110B1 | 5 | 5 | 5 | Scheduled | 17/01/2022 | 21/01/2022
TO-22-110 kV B3 @ FIN GIS-01 | BUSBAR SECTION - FINGLAS GIS 110-FINGLAS GIS 110-110B3 | 5 | 5 | 5 | Scheduled | 17/01/2022 | 21/01/2022
TO-22-FIN GIS-110SA1-3CB-01 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110SA1-3CB | 5 | 5 | 5 | Scheduled | 17/01/2022 | 21/01/2022
TO-22-110 kV A1 @ CDU-01 | BUSBAR SECTION - CORDUFF 110-CORDUFF 110-110A1 | 5 | 5 | 5 | Tentative | 24/01/2022 | 28/01/2022
TO-22-110 kV A3 @ CDU-01 | BUSBAR SECTION - CORDUFF 110-CORDUFF 110-110A3 | 5 | 5 | 5 | Tentative | 24/01/2022 | 28/01/2022
TO-22-110 kV B1 @ CDU-01 | BUSBAR SECTION - CORDUFF 110-CORDUFF 110-110B1 | 5 | 5 | 5 | Tentative | 24/01/2022 | 28/01/2022
TO-22-110 kV B3 @ CDU-02 | BUSBAR SECTION - CORDUFF 110-CORDUFF 110-110B3 | 5 | 5 | 5 | Tentative | 24/01/2022 | 28/01/2022
TO-22-220 kV A1/A2 @ DSN-01 | BUSBAR SECTION - DUNSTOWN 220-DUNSTOWN 220-220A1-A2 | 1 | 1 | 1 | Scheduled | 27/01/2022 | 27/01/2022
TO-22-220 kV B1/B2 @ DSN-01 | BUSBAR SECTION - DUNSTOWN 220-DUNSTOWN 220-220B1-B2 | 1 | 1 | 1 | Scheduled | 27/01/2022 | 27/01/2022
TO-22-400 kV A1/A2 @ DSN-01 | BUSBAR SECTION - DUNSTOWN 400-DUNSTOWN 400-400A1-A2 | 1 | 1 | 1 | Scheduled | 27/01/2022 | 27/01/2022
TO-22-400 kV B1/B2 @ DSN-01 | BUSBAR SECTION - DUNSTOWN 400-DUNSTOWN 400-400B1-B2 | 1 | 1 | 1 | Scheduled | 27/01/2022 | 27/01/2022
TO-22-PB-R2001-02 | CAPACITOR/SVC/REACTOR - POOLBEG 220-POOLBEG 220-R2001 | 5 | 5 | 5 | Tentative | 31/01/2022 | 04/02/2022
TO-22-KTL-MON-1-01 | 110kV FEEDER - KILTEEL 110-MONREAD 110-1 | 7 | 5 | 5 | Scheduled | 01/02/2022 | 07/02/2022
TO-22-110 kV A1/A2/A3/A4 @ RYB GIS-01 | BUSBAR SECTION - RYEBROOK GIS 110-RYEBROOK GIS 110-110A1-A2-A3-A4 | 1 | 1 | 1 | Scheduled | 08/02/2022 | 08/02/2022
TO-22-110 kV B1/B2/B3/B4 @ RYB GIS-01 | BUSBAR SECTION - RYEBROOK GIS 110-RYEBROOK GIS 110-110B1-B2-B3-B4 | 1 | 1 | 1 | Scheduled | 08/02/2022 | 08/02/2022
TO-22-CLG-110K2-02 | COUPLER/SECTIONALISING CB - CLOGHRAN 110-CLOGHRAN 110-110K2 | 5 | 5 | 5 | Tentative | 14/02/2022 | 18/02/2022
TO-22-CLG-110SA1-2CB-03 | COUPLER/SECTIONALISING CB - CLOGHRAN 110-CLOGHRAN 110-110SA1-2CB | 5 | 5 | 5 | Tentative | 21/02/2022 | 25/02/2022
TO-22-FIN-MCD-1-01 | 110kV FEEDER - FINGLAS 110-McDERMOTT 110-1 | 124 | 84 | 84 | Reference | 21/02/2022 | 24/06/2022
TO-22-220 kV A1/A2 @ CLE-01 | BUSBAR SECTION - CLONEE 220-CLONEE 220-220A1-A2 | 1 | 1 | 1 | Tentative | 22/02/2022 | 22/02/2022
TO-22-220 kV B1/B2 @ CLE-01 | BUSBAR SECTION - CLONEE 220-CLONEE 220-220B1-B2 | 1 | 1 | 1 | Tentative | 22/02/2022 | 22/02/2022
TO-22-110 kV A3 @ CDU-02 | BUSBAR SECTION - CORDUFF 110-CORDUFF 110-110A3 | 4 | 4 | 4 | Scheduled | 28/02/2022 | 03/03/2022
TO-22-110 kV B3 @ CDU-03 | BUSBAR SECTION - CORDUFF 110-CORDUFF 110-110B3 | 4 | 4 | 4 | Scheduled | 28/02/2022 | 03/03/2022
TO-22-CDU-PLA-1-01 | 110kV FEEDER - CORDUFF 110-PLATIN 110-1 | 159 | 108 | 108 | Scheduled | 28/02/2022 | 05/08/2022
TO-22-FIN-HN-1-01 | 220kV FEEDER - FINGLAS 220-HUNTSTOWN 220-1 | 7 | 5 | 5 | Scheduled | 01/03/2022 | 07/03/2022
TO-22-HN-T2010/11-01 | GENERATOR TRANSFORMER - HUNTSTOWN 220-HUNTSTOWN G10/11-T2010/11 | 7 | 5 | 5 | Scheduled | 01/03/2022 | 07/03/2022
TO-22-MCE-T121-01 | TSO CUSTOMER TRANSFORMER - MACETOWN 110-MACETOWN 20-T121 | 1 | 1 | 1 | Scheduled | 02/03/2022 | 02/03/2022
TO-22-MAY-RNW-1-04 | 110kV FEEDER - MAYNOOTH 110-RINAWADE 110-1 | 3 | 3 | 3 | Tentative | 02/03/2022 | 04/03/2022
TO-22-MAY-RYB GIS-1-02 | 110kV FEEDER - MAYNOOTH 110-RYEBROOK GIS 110-1 | 3 | 3 | 3 | Tentative | 02/03/2022 | 04/03/2022
TO-22-110 kV A1/A2 @ SNU-01 | BUSBAR SECTION - SNUGBOROUGH 110-SNUGBOROUGH 110-110A1-A2 | 1 | 1 | 1 | Scheduled | 02/03/2022 | 02/03/2022
TO-22-110 kV B1/B2 @ SNU-01 | BUSBAR SECTION - SNUGBOROUGH 110-SNUGBOROUGH 110-110B1-B2 | 1 | 1 | 1 | Scheduled | 02/03/2022 | 02/03/2022
TO-22-110 kV A2 @ FIN-01 | BUSBAR SECTION - FINGLAS 110-FINGLAS 110-110A2 | 5 | 5 | 5 | Scheduled | 07/03/2022 | 11/03/2022
TO-22-FIN-220K1-11 | COUPLER/SECTIONALISING CB - FINGLAS 220-FINGLAS 220-220K1 | 5 | 5 | 5 | Scheduled | 07/03/2022 | 11/03/2022
TO-22-MAY-WOO-1-02 | 220kV FEEDER - MAYNOOTH 220-WOODLAND 220-1 | 135 | 91 | 91 | Scheduled | 07/03/2022 | 19/07/2022
TO-22-CDU-SNU-1-01 | 110kV FEEDER - CORDUFF 110-SNUGBOROUGH 110-1 | 2 | 2 |  | Scheduled | 14/03/2022 | 15/03/2022
TO-22-400 kV B1 @ WOO-03 | BUSBAR SECTION - WOODLAND 400-WOODLAND 400-400B1 | 1 | 1 | 1 | Scheduled | 14/03/2022 | 14/03/2022
TO-22-WOO-T4201-01 | TRANSFORMER - WOODLAND 400-WOODLAND 220-T4201 | 157 | 106 | 106 | Scheduled | 14/03/2022 | 17/08/2022
TO-22-PRN-T4301-01 | TRANSFORMER - PORTAN 400-PORTAN 260-T4301 | 16 | 10 | 10 | Scheduled | 15/03/2022 | 30/03/2022
TO-22-PRN-WOO-1-01 | 400kV FEEDER - PORTAN 400-WOODLAND 400-1 | 16 | 10 | 10 | Scheduled | 15/03/2022 | 30/03/2022
TO-22-220 kV A3 @ CKM GIS-03 | BUSBAR SECTION - CARRICKMINES GIS 220-CARRICKMINES GIS 220-220A3 | 12 | 10 | 10 | Scheduled | 21/03/2022 | 01/04/2022
TO-22-220 kV B3 @ CKM GIS-03 | BUSBAR SECTION - CARRICKMINES GIS 220-CARRICKMINES GIS 220-220B3 | 12 | 10 | 10 | Scheduled | 21/03/2022 | 01/04/2022
TO-22-CKM GIS-220K3-01 | COUPLER/SECTIONALISING CB - CARRICKMINES GIS 220-CARRICKMINES GIS 220-220K3 | 12 | 10 | 10 | Scheduled | 21/03/2022 | 01/04/2022
TO-22-110 kV A2 @ CDU-01 | BUSBAR SECTION - CORDUFF 110-CORDUFF 110-110A2 | 5 | 5 | 5 | Scheduled | 21/03/2022 | 25/03/2022
TO-22-110 kV B2 @ CDU-01 | BUSBAR SECTION - CORDUFF 110-CORDUFF 110-110B2 | 5 | 5 | 5 | Scheduled | 21/03/2022 | 25/03/2022
TO-22-CDU-T2102-01 | TRANSFORMER - CORDUFF 220-CORDUFF 110-T2102 | 12 | 10 | 10 | Scheduled | 21/03/2022 | 01/04/2022
TO-22-110 kV A1 @ FIN GIS-02 | BUSBAR SECTION - FINGLAS GIS 110-FINGLAS GIS 110-110A1 | 5 | 5 | 5 | Scheduled | 21/03/2022 | 25/03/2022
TO-22-110 kV B1 @ FIN GIS-02 | BUSBAR SECTION - FINGLAS GIS 110-FINGLAS GIS 110-110B1 | 5 | 5 | 5 | Scheduled | 21/03/2022 | 25/03/2022
TO-22-FIN GIS-110K1-01 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110K1 | 5 | 5 | 5 | Scheduled | 21/03/2022 | 25/03/2022
TO-22-RYB GIS-T133-02 | TSO CUSTOMER TRANSFORMER - RYEBROOK GIS 110-RYEBROOK 33-T133 | 138 | 95 | 95 | Scheduled | 21/03/2022 | 05/08/2022
TO-22-400 kV A1 @ WOO-02 | BUSBAR SECTION - WOODLAND 400-WOODLAND 400-400A1 | 21 | 15 | 15 | Scheduled | 24/03/2022 | 13/04/2022
TO-22-400 kV A2 @ WOO-01 | BUSBAR SECTION - WOODLAND 400-WOODLAND 400-400A2 | 21 | 15 | 15 | Scheduled | 24/03/2022 | 13/04/2022
TO-22-400 kV B1 @ WOO-02 | BUSBAR SECTION - WOODLAND 400-WOODLAND 400-400B1 | 21 | 15 | 15 | Scheduled | 24/03/2022 | 13/04/2022
TO-22-400 kV B2 @ WOO-01 | BUSBAR SECTION - WOODLAND 400-WOODLAND 400-400B2 | 21 | 15 | 15 | Scheduled | 24/03/2022 | 13/04/2022
TO-22-WOO-400K1-2-02 | COUPLER/SECTIONALISING CB - WOODLAND 400-WOODLAND 400-400K1-2 | 21 | 15 | 15 | Scheduled | 24/03/2022 | 13/04/2022
TO-22-ARK-CKM GIS-1-01 | 220kV FEEDER - ARKLOW 220-CARRICKMINES GIS 220-1 | 23 | 15 | 15 | Scheduled | 28/03/2022 | 19/04/2022
TO-22-220 kV A2 @ CLE-04 | BUSBAR SECTION - CLONEE 220-CLONEE 220-220A2 | 5 | 5 | 5 | Scheduled | 28/03/2022 | 01/04/2022
TO-22-220 kV B2 @ CLE-03 | BUSBAR SECTION - CLONEE 220-CLONEE 220-220B2 | 5 | 5 | 5 | Scheduled | 28/03/2022 | 01/04/2022
TO-22-CLE-220K2-04 | COUPLER/SECTIONALISING CB - CLONEE 220-CLONEE 220-220K2 | 8 | 6 | 6 | Scheduled | 28/03/2022 | 04/04/2022
TO-22-CLE-220SA1-2CB-03 | COUPLER/SECTIONALISING CB - CLONEE 220-CLONEE 220-220SA1-2CB | 8 | 6 | 6 | Scheduled | 28/03/2022 | 04/04/2022
TO-22-CLE-220SB1-2CB-02 | COUPLER/SECTIONALISING CB - CLONEE 220-CLONEE 220-220SB1-2CB | 8 | 6 | 6 | Scheduled | 28/03/2022 | 04/04/2022
TO-22-CLE-WOO-1-06 | 220kV FEEDER - CLONEE 220-WOODLAND 220-1 | 8 | 6 | 6 | Scheduled | 28/03/2022 | 04/04/2022
TO-22-220 kV A2 @ CDU-04 | BUSBAR SECTION - CORDUFF 220-CORDUFF 220-220A2 | 5 | 5 | 5 | Scheduled | 28/03/2022 | 01/04/2022
TO-22-220 kV B2 @ CDU-05 | BUSBAR SECTION - CORDUFF 220-CORDUFF 220-220B2 | 5 | 5 | 5 | Scheduled | 28/03/2022 | 01/04/2022
TO-22-220 kV A1 @ CKM GIS-02 | BUSBAR SECTION - CARRICKMINES GIS 220-CARRICKMINES GIS 220-220A1 | 16 | 10 | 10 | Scheduled | 04/04/2022 | 19/04/2022
TO-22-220 kV A2 @ CKM GIS-01 | BUSBAR SECTION - CARRICKMINES GIS 220-CARRICKMINES GIS 220-220A2 | 16 | 10 | 10 | Scheduled | 04/04/2022 | 19/04/2022
TO-22-CKM GIS-220SA1-2CB-01 | COUPLER/SECTIONALISING CB - CARRICKMINES GIS 220-CARRICKMINES GIS 220-22SA1-2CB | 16 | 10 | 10 | Scheduled | 04/04/2022 | 19/04/2022
TO-22-220 kV A1 @ CBT-01 | BUSBAR SECTION - CASTLEBAGOT 220-CASTLEBAGOT 220-220A1 | 5 | 5 | 5 | Scheduled | 04/04/2022 | 08/04/2022
TO-22-220 kV A2 @ CBT-01 | BUSBAR SECTION - CASTLEBAGOT 220-CASTLEBAGOT 220-220A2 | 5 | 5 | 5 | Scheduled | 04/04/2022 | 08/04/2022
TO-22-CBT-220SA1-2CB-01 | COUPLER/SECTIONALISING CB - CASTLEBAGOT 220-CASTLEBAGOT 220-220SA1-2CB | 5 | 5 | 5 | Scheduled | 04/04/2022 | 08/04/2022
TO-22-COL-FIN GIS-1-05 | 110kV FEEDER - COLLEGE PARK 110-FINGLAS GIS 110-1 | 1 | 1 | 1 | Scheduled | 05/04/2022 | 05/04/2022
TO-22-BLC-DND-1-01 | 110kV FEEDER - BELCAMP 110-DARNDALE 110-1 | 1 | 1 | 1 | Scheduled | 12/04/2022 | 12/04/2022
TO-22-110 kV A1/A2 @ CLG-01 | BUSBAR SECTION - CLOGHRAN 110-CLOGHRAN 110-110A1-A2 | 1 | 1 | 1 | Scheduled | 13/04/2022 | 13/04/2022
TO-22-110 kV B1/B2 @ CLG-01 | BUSBAR SECTION - CLOGHRAN 110-CLOGHRAN 110-110B1-B2 | 1 | 1 | 1 | Scheduled | 13/04/2022 | 13/04/2022
TO-22-DND-110K1-01 | COUPLER/SECTIONALISING CB - DARNDALE 110-DARNDALE 110-110K1 | 1 | 1 | 1 | Scheduled | 13/04/2022 | 13/04/2022
TO-22-DND-110K2-01 | COUPLER/SECTIONALISING CB - DARNDALE 110-DARNDALE 110-110K2 | 1 | 1 | 1 | Scheduled | 13/04/2022 | 13/04/2022
TO-22-BRT-220K2-01 | COUPLER/SECTIONALISING CB - BRACETOWN 220-BRACETOWN 220-220K2 | 1 | 1 | 1 | Scheduled | 14/04/2022 | 14/04/2022
TO-22-220 kV A2 @ CLE-01 | BUSBAR SECTION - CLONEE 220-CLONEE 220-220A2 | 5 | 4 | 4 | Scheduled | 18/04/2022 | 22/04/2022
TO-22-220 kV B2 @ CLE-01 | BUSBAR SECTION - CLONEE 220-CLONEE 220-220B2 | 5 | 4 | 5 | Scheduled | 18/04/2022 | 22/04/2022
TO-22-CLE-CDU-1-06 | 220kV FEEDER - CLONEE 220-CORDUFF 220-1 | 5 | 4 | 4 | Scheduled | 18/04/2022 | 22/04/2022
TO-22-220 kV B2 @ CKM GIS-01 | BUSBAR SECTION - CARRICKMINES GIS 220-CARRICKMINES GIS 220-220B2 | 10 | 8 | 8 | Scheduled | 20/04/2022 | 29/04/2022
TO-22-220 kV B4 @ CKM GIS-02 | BUSBAR SECTION - CARRICKMINES GIS 220-CARRICKMINES GIS 220-220B4 | 10 | 8 | 8 | Scheduled | 20/04/2022 | 29/04/2022
TO-22-CKM GIS-220SB2-4CB-01 | COUPLER/SECTIONALISING CB - CARRICKMINES GIS 220-CARRICKMINES GIS 220-22SB2-4CB | 10 | 8 | 8 | Scheduled | 20/04/2022 | 29/04/2022
TO-22-DND-T123-01 | TSO CUSTOMER TRANSFORMER - DARNDALE 110-DARNDALE 20-T123 | 3 | 3 | 3 | Scheduled | 26/04/2022 | 28/04/2022
TO-22-DND-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - DARNDALE 110-DARNDALE 110-110SA1-2CB | 1 | 1 | 1 | Scheduled | 27/04/2022 | 27/04/2022
TO-22-MCE-T124-01 | TSO CUSTOMER TRANSFORMER - MACETOWN 110-MACETOWN 20-T124 | 1 | 1 | 1 | Scheduled | 27/04/2022 | 27/04/2022
TO-22-RYB GIS-T103-01 | TSO CUSTOMER TRANSFORMER - RYEBROOK GIS 110-RYEBROOK 10-T103 | 2 | 2 | 2 | Scheduled | 03/05/2022 | 04/05/2022
TO-22-DND-T124-01 | TSO CUSTOMER TRANSFORMER - DARNDALE 110-DARNDALE 20-T124 | 1 | 1 | 1 | Scheduled | 04/05/2022 | 04/05/2022
TO-22-RYB GIS-T104-01 | TSO CUSTOMER TRANSFORMER - RYEBROOK GIS 110-RYEBROOK 10-T104 | 2 | 2 | 2 | Scheduled | 05/05/2022 | 06/05/2022
TO-22-220 kV A4 @ CKM GIS-02 | BUSBAR SECTION - CARRICKMINES GIS 220-CARRICKMINES GIS 220-220A4 | 12 | 10 | 10 | Scheduled | 09/05/2022 | 20/05/2022
TO-22-220 kV B4 @ CKM GIS-01 | BUSBAR SECTION - CARRICKMINES GIS 220-CARRICKMINES GIS 220-220B4 | 12 | 10 | 10 | Scheduled | 09/05/2022 | 20/05/2022
TO-22-CKM GIS-220K4-01 | COUPLER/SECTIONALISING CB - CARRICKMINES GIS 220-CARRICKMINES GIS 220-220K4 | 12 | 10 | 10 | Scheduled | 09/05/2022 | 20/05/2022
TO-22-CKM GIS-220SA2-4CB-03 | COUPLER/SECTIONALISING CB - CARRICKMINES GIS 220-CARRICKMINES GIS 220-22SA2-4CB | 12 | 10 | 10 | Scheduled | 09/05/2022 | 20/05/2022
TO-22-CKM GIS-220SB2-4CB-02 | COUPLER/SECTIONALISING CB - CARRICKMINES GIS 220-CARRICKMINES GIS 220-22SB2-4CB | 12 | 10 | 10 | Scheduled | 09/05/2022 | 20/05/2022
TO-22-110 kV B1 @ CLG-04 | BUSBAR SECTION - CLOGHRAN 110-CLOGHRAN 110-110B1 | 5 | 5 | 5 | Scheduled | 09/05/2022 | 13/05/2022
TO-22-110 kV B2 @ CLG-03 | BUSBAR SECTION - CLOGHRAN 110-CLOGHRAN 110-110B2 | 5 | 5 | 5 | Scheduled | 09/05/2022 | 13/05/2022
TO-22-CLG-110SB1-2CB-05 | COUPLER/SECTIONALISING CB - CLOGHRAN 110-CLOGHRAN 110-110SB1-2CB | 5 | 5 | 5 | Scheduled | 09/05/2022 | 13/05/2022
TO-22-RYB GIS-T105-01 | TSO CUSTOMER TRANSFORMER - RYEBROOK GIS 110-RYEBROOK 10-T105 | 2 | 2 | 2 | Scheduled | 09/05/2022 | 10/05/2022
TO-22-TH-T2003/4-01 | GENERATOR TRANSFORMER - TURLOUGH HILL 220-TURLOUGH HILL G1-T2003/4 | 28 | 19 | 19 | Scheduled | 10/05/2022 | 06/06/2022
TO-22-CLG-T123-02 | TSO CUSTOMER TRANSFORMER - CLOGHRAN 110-CLOGHRAN 20-T123 | 1 | 1 | 1 | Scheduled | 11/05/2022 | 11/05/2022
TO-22-110 kV A1/A2 @ DND-01 | BUSBAR SECTION - DARNDALE 110-DARNDALE 110-110A1-A2 | 1 | 1 | 1 | Scheduled | 11/05/2022 | 11/05/2022
TO-22-110 kV B1/B2 @ DND-01 | BUSBAR SECTION - DARNDALE 110-DARNDALE 110-110B1-B2 | 1 | 1 | 1 | Scheduled | 11/05/2022 | 11/05/2022
TO-22-RYB GIS-T106-01 | TSO CUSTOMER TRANSFORMER - RYEBROOK GIS 110-RYEBROOK 10-T106 | 2 | 2 | 2 | Scheduled | 11/05/2022 | 12/05/2022
TO-22-RYB GIS-T107-01 | TSO CUSTOMER TRANSFORMER - RYEBROOK GIS 110-RYEBROOK 10-T107 | 2 | 2 | 2 | Scheduled | 16/05/2022 | 17/05/2022
TO-22-DND-110SB1-2CB-01 | COUPLER/SECTIONALISING CB - DARNDALE 110-DARNDALE 110-110SB1-2CB | 1 | 1 | 1 | Scheduled | 17/05/2022 | 17/05/2022
TO-22-BLC-DND-3-01 | 110kV FEEDER - BELCAMP 110-DARNDALE 110-3 | 1 | 1 | 1 | Scheduled | 18/05/2022 | 18/05/2022
TO-22-220 kV A1 @ DSN-02 | BUSBAR SECTION - DUNSTOWN 220-DUNSTOWN 220-220A1 | 5 | 5 | 5 | Scheduled | 23/05/2022 | 27/05/2022
TO-22-220 kV B1 @ DSN-02 | BUSBAR SECTION - DUNSTOWN 220-DUNSTOWN 220-220B1 | 5 | 5 | 5 | Scheduled | 23/05/2022 | 27/05/2022
TO-22-220 kV A2 @ INC-03 | BUSBAR SECTION - INCHICORE 220-INCHICORE 220-220A2 | 5 | 5 | 5 | Scheduled | 23/05/2022 | 27/05/2022
TO-22-INC-PB-2-02 | 220kV FEEDER - INCHICORE 220-POOLBEG 220-2 | 96 | 68 | 68 | Scheduled | 23/05/2022 | 26/08/2022
TO-22-RYB GIS-T108-01 | TSO CUSTOMER TRANSFORMER - RYEBROOK GIS 110-RYEBROOK 10-T108 | 5 | 5 | 5 | Scheduled | 23/05/2022 | 27/05/2022
TO-22-RYB GIS-T109-01 | TSO CUSTOMER TRANSFORMER - RYEBROOK GIS 110-RYEBROOK 10-T109 | 2 | 2 | 2 | Proposed | 23/05/2022 | 24/05/2022
TO-22-SNU-T102-01 | TSO CUSTOMER TRANSFORMER - SNUGBOROUGH 110-SNUGBOROUGH 10-T102 | 1 | 1 | 1 | Scheduled | 23/05/2022 | 23/05/2022
TO-22-SNU-T102-02 | TSO CUSTOMER TRANSFORMER - SNUGBOROUGH 110-SNUGBOROUGH 10-T102 | 4 | 4 | 4 | Scheduled | 23/05/2022 | 26/05/2022
TO-22-220 kV A2 @ TH-03 | BUSBAR SECTION - TURLOUGH HILL 220-TURLOUGH HILL 220-220A2 | 5 | 5 | 5 | Scheduled | 23/05/2022 | 27/05/2022
TO-22-220 kV B2 @ TH-03 | BUSBAR SECTION - TURLOUGH HILL 220-TURLOUGH HILL 220-220B2 | 5 | 5 | 5 | Scheduled | 23/05/2022 | 27/05/2022
TO-22-COL-FIN GIS-1-03 | 110kV FEEDER - COLLEGE PARK 110-FINGLAS GIS 110-1 | 1 | 1 | 1 | Scheduled | 25/05/2022 | 25/05/2022
TO-22-220 kV A1 @ CDU-04 | BUSBAR SECTION - CORDUFF 220-CORDUFF 220-220A1 | 12 | 9 | 4 | Scheduled | 30/05/2022 | 10/06/2022
TO-22-220 kV A3 @ CDU-03 | BUSBAR SECTION - CORDUFF 220-CORDUFF 220-220A3 | 12 | 9 | 9 | Scheduled | 30/05/2022 | 10/06/2022
TO-22-220 kV B1 @ CDU-05 | BUSBAR SECTION - CORDUFF 220-CORDUFF 220-220B1 | 12 | 9 | 9 | Scheduled | 30/05/2022 | 10/06/2022
TO-22-220 kV B3 @ CDU-03 | BUSBAR SECTION - CORDUFF 220-CORDUFF 220-220B3 | 12 | 9 | 9 | Scheduled | 30/05/2022 | 10/06/2022
TO-22-CDU-220K1-3-03 | COUPLER/SECTIONALISING CB - CORDUFF 220-CORDUFF 220-220K1-3 | 12 | 9 | 9 | Scheduled | 30/05/2022 | 10/06/2022
TO-22-220 kV A3 @ PB-01 | BUSBAR SECTION - POOLBEG 220-POOLBEG 220-220A3 | 5 | 5 | 5 | Scheduled | 30/05/2022 | 03/06/2022
TO-22-220 kV B3 @ PB-01 | BUSBAR SECTION - POOLBEG 220-POOLBEG 220-220B3 | 5 | 5 | 5 | Scheduled | 30/05/2022 | 03/06/2022
TO-22-SHL-T2016-01 | GENERATOR TRANSFORMER - SHELLYBANKS 220-SHELLYBANKS G6-T2016 | 3 | 3 | 3 | Scheduled | 30/05/2022 | 01/06/2022
TO-22-SNU-T104-01 | TSO CUSTOMER TRANSFORMER - SNUGBOROUGH 110-SNUGBOROUGH 10-T104 | 4 | 4 | 4 | Scheduled | 30/05/2022 | 02/06/2022
TO-22-CLE-WOO-1-07 | 220kV FEEDER - CLONEE 220-WOODLAND 220-1 | 4 | 4 | 4 | Tentative | 07/06/2022 | 10/06/2022
TO-22-CDU-MCE-1-01 | 110kV FEEDER - CORDUFF 110-MACETOWN 110-1 | 4 | 4 | 4 | Scheduled | 07/06/2022 | 10/06/2022
TO-22-110 kV A6 @ FIN GIS-01 | BUSBAR SECTION - FINGLAS GIS 110-FINGLAS GIS 110-110A6 | 4 | 4 | 4 | Scheduled | 07/06/2022 | 10/06/2022
TO-22-110 kV B6 @ FIN GIS-01 | BUSBAR SECTION - FINGLAS GIS 110-FINGLAS GIS 110-110B6 | 4 | 4 | 4 | Scheduled | 07/06/2022 | 10/06/2022
TO-22-FIN GIS-110K6-01 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110K6 | 4 | 4 | 4 | Scheduled | 07/06/2022 | 10/06/2022
TO-22-FIN GIS-110SA4-6CB-02 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110SA4-6CB | 4 | 4 | 4 | Scheduled | 07/06/2022 | 10/06/2022
TO-22-FIN GIS-110SB4-6CB-02 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110SB4-6CB | 4 | 4 | 4 | Scheduled | 07/06/2022 | 10/06/2022
TO-22-TH-T2001/2-01 | GENERATOR TRANSFORMER - TURLOUGH HILL 220-TURLOUGH HILL G1-T2001/2 | 17 | 13 | 13 | Scheduled | 07/06/2022 | 23/06/2022
TO-22-BAL-DRY-1-02 | 110kV FEEDER - BALTRASNA 110-DRYBRIDGE 110-1 | 2 | 2 | 2 | Scheduled | 08/06/2022 | 09/06/2022
TO-22-110 kV A2 @ FIN GIS-01 | BUSBAR SECTION - FINGLAS GIS 110-FINGLAS GIS 110-110A2 | 5 | 5 | 5 | Scheduled | 13/06/2022 | 17/06/2022
TO-22-110 kV B2 @ FIN GIS-01 | BUSBAR SECTION - FINGLAS GIS 110-FINGLAS GIS 110-110B2 | 5 | 5 | 5 | Scheduled | 13/06/2022 | 17/06/2022
TO-22-FIN GIS-110K2-01 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110K2 | 5 | 5 | 5 | Scheduled | 13/06/2022 | 17/06/2022
TO-22-FIN GIS-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110SA1-2CB | 5 | 5 | 5 | Scheduled | 13/06/2022 | 17/06/2022
TO-22-FIN GIS-110SA2-4CB-01 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110SA2-4CB | 5 | 5 | 5 | Scheduled | 13/06/2022 | 17/06/2022
TO-22-FIN GIS-110SB1-2CB-01 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110SB1-2CB | 5 | 5 | 5 | Scheduled | 13/06/2022 | 17/06/2022
TO-22-FIN GIS-110SB2-4CB-01 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110SB2-4CB | 5 | 5 | 5 | Scheduled | 13/06/2022 | 17/06/2022
TO-22-PB-R2001-05 | CAPACITOR/SVC/REACTOR - POOLBEG 220-POOLBEG 220-R2001 | 5 | 5 | 5 | Scheduled | 13/06/2022 | 17/06/2022
TO-22-110 kV A2 @ FIN-02 | BUSBAR SECTION - FINGLAS 110-FINGLAS 110-110A2 | 5 | 5 | 5 | Scheduled | 20/06/2022 | 24/06/2022
TO-22-110 kV B2 @ FIN-01 | BUSBAR SECTION - FINGLAS 110-FINGLAS 110-110B2 | 5 | 5 | 5 | Scheduled | 20/06/2022 | 24/06/2022
TO-22-220 kV A1 @ FIN-08 | BUSBAR SECTION - FINGLAS 220-FINGLAS 220-220A1 | 5 | 5 | 5 | Scheduled | 20/06/2022 | 24/06/2022
TO-22-220 kV B1 @ FIN-09 | BUSBAR SECTION - FINGLAS 220-FINGLAS 220-220B1 | 5 | 5 | 5 | Scheduled | 20/06/2022 | 24/06/2022
TO-22-CDU-MUL-1-02 | 110kV FEEDER - CORDUFF 110-MULLINGAR 110-1 | 1 | 1 | 1 | Scheduled | 21/06/2022 | 21/06/2022
TO-22-FIN-220K1-08 | COUPLER/SECTIONALISING CB - FINGLAS 220-FINGLAS 220-220K1 | 1 | 1 | 1 | Scheduled | 23/06/2022 | 23/06/2022
TO-22-FIN-FIN GIS-2-03 | 110kV FEEDER - FINGLAS 110-FINGLAS GIS 110-2 | 2 | 2 | 2 | Scheduled | 23/06/2022 | 24/06/2022
TO-22-FIN-MCD-1-03 | 110kV FEEDER - FINGLAS 110-McDERMOTT 110-1 | 2 | 2 | 2 | Reference | 23/06/2022 | 24/06/2022
TO-22-FIN-220K2-03 | COUPLER/SECTIONALISING CB - FINGLAS 220-FINGLAS 220-220K2 | 1 | 1 | 1 | Scheduled | 24/06/2022 | 24/06/2022
TO-22-110 kV A1/A3 @ BLC-01 | BUSBAR SECTION - BELCAMP 110-BELCAMP 110-110A1-A3 | 1 | 1 | 1 | Scheduled | 29/06/2022 | 29/06/2022
TO-22-110 kV B1/B3 @ BLC-01 | BUSBAR SECTION - BELCAMP 110-BELCAMP 110-110B1-B3 | 1 | 1 | 1 | Scheduled | 29/06/2022 | 29/06/2022
TO-22-COL-FIN GIS-1-04 | 110kV FEEDER - COLLEGE PARK 110-FINGLAS GIS 110-1 | 1 | 1 | 1 | Scheduled | 29/06/2022 | 29/06/2022
TO-22-KYT-WOO-1-03 | 220kV FEEDER - KELLYSTOWN 220-WOODLAND 220-1 | 34 | 23 | 23 | Scheduled | 01/07/2022 | 03/08/2022
TO-22-BLC-110K1-01 | COUPLER/SECTIONALISING CB - BELCAMP 110-BELCAMP 110-110K1 | 1 | 1 | 1 | Scheduled | 05/07/2022 | 05/07/2022
TO-22-110 kV A1 @ MAY-01 | BUSBAR SECTION - MAYNOOTH 110-MAYNOOTH 110-110A1 | 3 | 3 | 3 | Scheduled | 06/07/2022 | 08/07/2022
TO-22-110 kV B1 @ MAY-01 | BUSBAR SECTION - MAYNOOTH 110-MAYNOOTH 110-110B1 | 3 | 3 | 3 | Scheduled | 06/07/2022 | 08/07/2022
TO-22-110 kV A1 @ CLG-02 | BUSBAR SECTION - CLOGHRAN 110-CLOGHRAN 110-110A1 | 4 | 4 | 4 | Scheduled | 11/07/2022 | 14/07/2022
TO-22-110 kV B1 @ CLG-03 | BUSBAR SECTION - CLOGHRAN 110-CLOGHRAN 110-110B1 | 4 | 4 | 4 | Scheduled | 11/07/2022 | 14/07/2022
TO-22-CLG-FIN GIS-1-03 | 110kV FEEDER - CLOGHRAN 110-FINGLAS GIS 110-1 | 5 | 5 | 5 | Scheduled | 11/07/2022 | 15/07/2022
TO-22-110 kV A5 @ FIN GIS-01 | BUSBAR SECTION - FINGLAS GIS 110-FINGLAS GIS 110-110A5 | 4 | 4 | 4 | Scheduled | 11/07/2022 | 14/07/2022
TO-22-110 kV B5 @ FIN GIS-01 | BUSBAR SECTION - FINGLAS GIS 110-FINGLAS GIS 110-110B5 | 4 | 4 | 4 | Scheduled | 11/07/2022 | 14/07/2022
TO-22-KTL-T131-01 | GENERATOR TRANSFORMER - KILTEEL 110-KILTEEL 33-T131 | 5 | 5 | 5 | Scheduled | 11/07/2022 | 15/07/2022
TO-22-MAY-WOO-1-15 | 220kV FEEDER - MAYNOOTH 220-WOODLAND 220-1 | 165 | 114 | 114 | Scheduled | 20/07/2022 | 31/12/2022
TO-22-220 kV B1 @ CKM GIS-03 | BUSBAR SECTION - CARRICKMINES GIS 220-CARRICKMINES GIS 220-220B1 | 3 | 3 | 3 | Scheduled | 25/07/2022 | 27/07/2022
TO-22-220 kV B2 @ CKM GIS-02 | BUSBAR SECTION - CARRICKMINES GIS 220-CARRICKMINES GIS 220-220B2 | 3 | 3 | 3 | Scheduled | 25/07/2022 | 27/07/2022
TO-22-220 kV A1/A2 @ FIN-02 | BUSBAR SECTION - FINGLAS 220-FINGLAS 220-220A1-A2 | 19 | 14 | 14 | Scheduled | 25/07/2022 | 12/08/2022
TO-22-FIN-220K1-12 | COUPLER/SECTIONALISING CB - FINGLAS 220-FINGLAS 220-220K1 | 19 | 14 | 14 | Scheduled | 25/07/2022 | 12/08/2022
TO-22-FIN-220K2-02 | COUPLER/SECTIONALISING CB - FINGLAS 220-FINGLAS 220-220K2 | 19 | 14 | 14 | Scheduled | 25/07/2022 | 12/08/2022
TO-22-110 kV A2 @ CDU-02 | BUSBAR SECTION - CORDUFF 110-CORDUFF 110-110A2 | 4 | 4 | 4 | Scheduled | 26/07/2022 | 29/07/2022
TO-22-110 kV B2 @ CDU-02 | BUSBAR SECTION - CORDUFF 110-CORDUFF 110-110B2 | 4 | 4 | 4 | Scheduled | 26/07/2022 | 29/07/2022
TO-22-DND-T122-01 | TSO CUSTOMER TRANSFORMER - DARNDALE 110-DARNDALE 20-T122 | 3 | 3 | 3 | Scheduled | 26/07/2022 | 28/07/2022
TO-22-COL-FIN GIS-1-02 | 110kV FEEDER - COLLEGE PARK 110-FINGLAS GIS 110-1 | 1 | 1 | 1 | Scheduled | 27/07/2022 | 27/07/2022
TO-22-CLE-220K1-03 | COUPLER/SECTIONALISING CB - CLONEE 220-CLONEE 220-220K1 | 1 | 1 | 1 | Scheduled | 09/08/2022 | 09/08/2022
TO-22-FIN-NW-1-06 | 220kV FEEDER - FINGLAS 220-NORTH WALL 220-1 | 1 | 1 | 1 | Scheduled | 12/08/2022 | 12/08/2022
TO-22-CDU-MUL-1-01 | 110kV FEEDER - CORDUFF 110-MULLINGAR 110-1 | 44 | 32 | 32 | Scheduled | 15/08/2022 | 27/09/2022
TO-22-DER-MAY-1-02 | 110kV FEEDER - DERRYIRON 110-MAYNOOTH 110-1 | 12 | 10 | 10 | Scheduled | 15/08/2022 | 26/08/2022
TO-22-110 kV A3 @ FIN-03 | BUSBAR SECTION - FINGLAS 110-FINGLAS 110-110A3 | 5 | 5 | 5 | Scheduled | 15/08/2022 | 19/08/2022
TO-22-110 kV B3 @ FIN-02 | BUSBAR SECTION - FINGLAS 110-FINGLAS 110-110B3 | 5 | 5 | 5 | Scheduled | 15/08/2022 | 19/08/2022
TO-22-220 kV A2 @ FIN-01 | BUSBAR SECTION - FINGLAS 220-FINGLAS 220-220A2 | 5 | 5 | 5 | Scheduled | 15/08/2022 | 19/08/2022
TO-22-220 kV B2 @ FIN-01 | BUSBAR SECTION - FINGLAS 220-FINGLAS 220-220B2 | 5 | 5 | 5 | Scheduled | 15/08/2022 | 19/08/2022
TO-22-FIN-T2104-03 | TRANSFORMER - FINGLAS 220-FINGLAS 110-T2104 | 12 | 10 | 10 | Scheduled | 15/08/2022 | 26/08/2022
TO-22-110 kV A1 @ RYB GIS-02 | BUSBAR SECTION - RYEBROOK GIS 110-RYEBROOK GIS 110-110A1 | 5 | 5 | 5 | Scheduled | 15/08/2022 | 19/08/2022
TO-22-110 kV A3 @ RYB GIS-02 | BUSBAR SECTION - RYEBROOK GIS 110-RYEBROOK GIS 110-110A3 | 5 | 5 | 5 | Scheduled | 15/08/2022 | 19/08/2022
TO-22-RYB GIS-110SA1-3CB-01 | COUPLER/SECTIONALISING CB - RYEBROOK GIS 110-RYEBROOK GIS 110-110SA1-3CB | 5 | 5 | 5 | Scheduled | 15/08/2022 | 19/08/2022
TO-22-CBT-110K1-05 | COUPLER/SECTIONALISING CB - CASTLEBAGOT 110-CASTLEBAGOT 110-110K1 | 1 | 1 | 1 | Scheduled | 16/08/2022 | 16/08/2022
TO-22-110 kV A1 @ CBT-04 | BUSBAR SECTION - CASTLEBAGOT 110-CASTLEBAGOT 110-110A1 | 3 | 3 | 3 | Scheduled | 17/08/2022 | 19/08/2022
TO-22-110 kV A2 @ CBT-01 | BUSBAR SECTION - CASTLEBAGOT 110-CASTLEBAGOT 110-110A2 | 3 | 3 | 3 | Scheduled | 17/08/2022 | 19/08/2022
TO-22-CBT-110SA1-2CB-03 | COUPLER/SECTIONALISING CB - CASTLEBAGOT 110-CASTLEBAGOT 110-110SA1-2CB | 3 | 3 | 3 | Scheduled | 17/08/2022 | 19/08/2022
TO-22-CDU-WOO-1-02 | 220kV FEEDER - CORDUFF 220-WOODLAND 220-1 | 5 | 5 | 5 | Scheduled | 22/08/2022 | 26/08/2022
TO-22-220 kV A1 @ CKM-01 | BUSBAR SECTION - CARRICKMINES 220-CARRICKMINES 220-220A1 | 12 | 10 | 10 | Scheduled | 29/08/2022 | 09/09/2022
TO-22-220 kV B1 @ CKM-01 | BUSBAR SECTION - CARRICKMINES 220-CARRICKMINES 220-220B1 | 12 | 10 | 10 | Scheduled | 29/08/2022 | 09/09/2022
TO-22-CKM-CKM GIS-1-01 | 220kV FEEDER - CARRICKMINES 220-CARRICKMINES GIS 220-1 | 26 | 20 | 20 | Scheduled | 29/08/2022 | 23/09/2022
TO-22-CKM-PB-1-01 | 220kV FEEDER - CARRICKMINES 220-POOLBEG 220-1 | 26 | 20 | 20 | Scheduled | 29/08/2022 | 23/09/2022
TO-22-CKM-PST2201-01 | TRANSFORMER - CARRICKMINES 220-CARRICKMINES 220-PST2201 | 26 | 20 | 20 | Scheduled | 29/08/2022 | 23/09/2022
TO-22-220 kV A2 @ CLE-05 | BUSBAR SECTION - CLONEE 220-CLONEE 220-220A2 | 5 | 5 | 5 | Scheduled | 29/08/2022 | 02/09/2022
TO-22-220 kV B2 @ CLE-04 | BUSBAR SECTION - CLONEE 220-CLONEE 220-220B2 | 5 | 5 | 5 | Scheduled | 29/08/2022 | 02/09/2022
TO-22-CLE-T224-01 | TSO CUSTOMER TRANSFORMER - CLONEE 220-CLONEE 20-T224 | 29 | 21 | 21 | Scheduled | 29/08/2022 | 26/09/2022
TO-22-220 kV A2 @ PB-04 | BUSBAR SECTION - POOLBEG 220-POOLBEG 220-220A2 | 5 | 5 | 5 | Scheduled | 29/08/2022 | 02/09/2022
TO-22-220 kV B2 @ PB-03 | BUSBAR SECTION - POOLBEG 220-POOLBEG 220-220B2 | 5 | 5 | 5 | Scheduled | 29/08/2022 | 02/09/2022
TO-22-PB-220K2-3-02 | COUPLER/SECTIONALISING CB - POOLBEG 220-POOLBEG 220-220K2-3 | 5 | 5 | 5 | Scheduled | 29/08/2022 | 02/09/2022
TO-22-110 kV B2 @ CBT-02 | BUSBAR SECTION - CASTLEBAGOT 110-CASTLEBAGOT 110-110B2 | 3 | 3 | 3 | Scheduled | 30/08/2022 | 01/09/2022
TO-22-110 kV B4 @ CBT-05 | BUSBAR SECTION - CASTLEBAGOT 110-CASTLEBAGOT 110-110B4 | 3 | 3 | 3 | Scheduled | 30/08/2022 | 01/09/2022
TO-22-CBT-110SB2-4CB-05 | COUPLER/SECTIONALISING CB - CASTLEBAGOT 110-CASTLEBAGOT 110-110SB2-4CB | 3 | 3 | 3 | Scheduled | 30/08/2022 | 01/09/2022
TO-22-RYB GIS-T131-02 | TSO CUSTOMER TRANSFORMER - RYEBROOK GIS 110-RYEBROOK 33-T131 | 1 | 1 | 1 | Scheduled | 30/08/2022 | 30/08/2022
TO-22-ISH-T2001-01 | GENERATOR TRANSFORMER - IRISHTOWN 220-IRISHTOWN G1-T2001 | 23 | 16 | 16 | Scheduled | 04/09/2022 | 26/09/2022
TO-22-DSN-MAY-1-01 | 220kV FEEDER - DUNSTOWN 220-MAYNOOTH 220-1 | 5 | 5 | 5 | Scheduled | 05/09/2022 | 09/09/2022
TO-22-110 kV A5 @ FIN GIS-02 | BUSBAR SECTION - FINGLAS GIS 110-FINGLAS GIS 110-110A5 | 5 | 5 | 5 | Scheduled | 05/09/2022 | 09/09/2022
TO-22-110 kV B5 @ FIN GIS-02 | BUSBAR SECTION - FINGLAS GIS 110-FINGLAS GIS 110-110B5 | 5 | 5 | 5 | Scheduled | 05/09/2022 | 09/09/2022
TO-22-FIN GIS-110K5-02 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110K5 | 5 | 5 | 5 | Scheduled | 05/09/2022 | 09/09/2022
TO-22-110 kV A2 @ RYB GIS-02 | BUSBAR SECTION - RYEBROOK GIS 110-RYEBROOK GIS 110-110A2 | 5 | 5 | 5 | Scheduled | 05/09/2022 | 09/09/2022
TO-22-110 kV A4 @ RYB GIS-01 | BUSBAR SECTION - RYEBROOK GIS 110-RYEBROOK GIS 110-110A4 | 5 | 5 | 5 | Scheduled | 05/09/2022 | 09/09/2022
TO-22-RYB GIS-110SA2-4CB-02 | COUPLER/SECTIONALISING CB - RYEBROOK GIS 110-RYEBROOK GIS 110-110SA2-4CB | 5 | 5 | 5 | Scheduled | 05/09/2022 | 09/09/2022
TO-22-220 kV A1/A2 @ WOO-01 | BUSBAR SECTION - WOODLAND 220-WOODLAND 220-220A1-A2 | 1 | 1 | 1 | Scheduled | 07/09/2022 | 07/09/2022
TO-22-220 kV B1/B2 @ WOO-01 | BUSBAR SECTION - WOODLAND 220-WOODLAND 220-220B1-B2 | 1 | 1 | 1 | Scheduled | 07/09/2022 | 07/09/2022
TO-22-DSN-T4201-02 | TRANSFORMER - DUNSTOWN 400-DUNSTOWN 220-T4201 | 26 | 20 | 20 | Scheduled | 12/09/2022 | 07/10/2022
TO-22-110 kV A2 @ FIN GIS-06 | BUSBAR SECTION - FINGLAS GIS 110-FINGLAS GIS 110-110A2 | 5 | 5 | 5 | Scheduled | 12/09/2022 | 16/09/2022
TO-22-110 kV A4 @ FIN GIS-01 | BUSBAR SECTION - FINGLAS GIS 110-FINGLAS GIS 110-110A4 | 5 | 5 | 5 | Scheduled | 12/09/2022 | 16/09/2022
TO-22-FIN GIS-110SA2-4CB-07 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110SA2-4CB | 5 | 5 | 5 | Scheduled | 12/09/2022 | 16/09/2022
TO-22-SNU-110SA1-2CB-02 | COUPLER/SECTIONALISING CB - SNUGBOROUGH 110-SNUGBOROUGH 110-110SA1-2CB | 1 | 1 | 1 | Scheduled | 12/09/2022 | 12/09/2022
TO-22-110 kV B1 @ CBT-03 | BUSBAR SECTION - CASTLEBAGOT 110-CASTLEBAGOT 110-110B1 | 3 | 3 | 3 | Scheduled | 13/09/2022 | 15/09/2022
TO-22-110 kV B2 @ CBT-01 | BUSBAR SECTION - CASTLEBAGOT 110-CASTLEBAGOT 110-110B2 | 3 | 3 | 3 | Scheduled | 13/09/2022 | 15/09/2022
TO-22-CBT-110SB1-2CB-03 | COUPLER/SECTIONALISING CB - CASTLEBAGOT 110-CASTLEBAGOT 110-110SB1-2CB | 3 | 3 | 3 | Scheduled | 13/09/2022 | 15/09/2022
TO-22-110 kV A2 @ PA-01 | BUSBAR SECTION - POLLAPHUCA 110-POLLAPHUCA 110-110A2 | 1 | 1 | 1 | Scheduled | 14/09/2022 | 14/09/2022
TO-22-PA-T101-04 | GENERATOR TRANSFORMER - POLLAPHUCA 110-POLLAPHUCA G1-T101 | 1 | 1 | 1 | Scheduled | 14/09/2022 | 14/09/2022
TO-22-CLG-CDU-1-02 | 110kV FEEDER - CLOGHRAN 110-CORDUFF 110-1 | 12 | 10 | 10 | Scheduled | 19/09/2022 | 30/09/2022
TO-22-110 kV A2 @ CDU-03 | BUSBAR SECTION - CORDUFF 110-CORDUFF 110-110A2 | 5 | 5 | 5 | Scheduled | 19/09/2022 | 23/09/2022
TO-22-110 kV B2 @ CDU-03 | BUSBAR SECTION - CORDUFF 110-CORDUFF 110-110B2 | 5 | 5 | 5 | Scheduled | 19/09/2022 | 23/09/2022
TO-22-220 kV A1 @ DSN-01 | BUSBAR SECTION - DUNSTOWN 220-DUNSTOWN 220-220A1 | 5 | 5 | 5 | Scheduled | 19/09/2022 | 23/09/2022
TO-22-220 kV B1 @ DSN-01 | BUSBAR SECTION - DUNSTOWN 220-DUNSTOWN 220-220B1 | 5 | 5 | 5 | Scheduled | 19/09/2022 | 23/09/2022
TO-22-KTL-T131-02 | GENERATOR TRANSFORMER - KILTEEL 110-KILTEEL 33-T131 | 2 | 2 | 2 | Scheduled | 19/09/2022 | 20/09/2022
TO-22-220 kV A1 @ CKM GIS-03 | BUSBAR SECTION - CARRICKMINES GIS 220-CARRICKMINES GIS 220-220A1 | 5 | 5 | 5 | Proposed | 26/09/2022 | 30/09/2022
TO-22-220 kV A3 @ CKM GIS-04 | BUSBAR SECTION - CARRICKMINES GIS 220-CARRICKMINES GIS 220-220A3 | 5 | 5 | 5 | Proposed | 26/09/2022 | 30/09/2022
TO-22-CKM GIS-220SA1-3CB-01 | COUPLER/SECTIONALISING CB - CARRICKMINES GIS 220-CARRICKMINES GIS 220-22SA1-3CB | 13 | 10 | 10 | Proposed | 26/09/2022 | 08/10/2022
TO-22-110 kV A2 @ CLG-03 | BUSBAR SECTION - CLOGHRAN 110-CLOGHRAN 110-110A2 | 5 | 5 | 5 | Scheduled | 26/09/2022 | 30/09/2022
TO-22-110 kV B2 @ CLG-04 | BUSBAR SECTION - CLOGHRAN 110-CLOGHRAN 110-110B2 | 5 | 5 | 5 | Scheduled | 26/09/2022 | 30/09/2022
TO-22-CDU-RYB GIS-1-01 | 110kV FEEDER - CORDUFF 110-RYEBROOK GIS 110-1 | 12 | 10 | 10 | Proposed | 26/09/2022 | 07/10/2022
TO-22-PB-R2001-03 | CAPACITOR/SVC/REACTOR - POOLBEG 220-POOLBEG 220-R2001 | 5 | 5 | 5 | Proposed | 26/09/2022 | 30/09/2022
TO-22-110 kV B2 @ RYB GIS-01 | BUSBAR SECTION - RYEBROOK GIS 110-RYEBROOK GIS 110-110B2 | 5 | 5 | 5 | Scheduled | 26/09/2022 | 30/09/2022
TO-22-110 kV B4 @ RYB GIS-01 | BUSBAR SECTION - RYEBROOK GIS 110-RYEBROOK GIS 110-110B4 | 5 | 5 | 5 | Scheduled | 26/09/2022 | 30/09/2022
TO-22-RYB GIS-110SB2-4CB-02 | COUPLER/SECTIONALISING CB - RYEBROOK GIS 110-RYEBROOK GIS 110-110SB2-4CB | 5 | 5 | 5 | Scheduled | 26/09/2022 | 30/09/2022
TO-22-WOO-T4204-01 | TRANSFORMER - WOODLAND 400-WOODLAND 220-T4204 | 12 | 10 | 10 | Proposed | 26/09/2022 | 07/10/2022
TO-22-110 kV A1 @ CDU-03 | BUSBAR SECTION - CORDUFF 110-CORDUFF 110-110A1 | 4 | 4 | 4 | Proposed | 27/09/2022 | 30/09/2022
TO-22-110 kV B1 @ CDU-03 | BUSBAR SECTION - CORDUFF 110-CORDUFF 110-110B1 | 4 | 4 | 4 | Proposed | 27/09/2022 | 30/09/2022
TO-22-BRT-T224-01 | TSO CUSTOMER TRANSFORMER - BRACETOWN 220-BRACETOWN 20-T224 | 1 | 1 | 1 | Proposed | 28/09/2022 | 28/09/2022
TO-22-220 kV A1/A2 @ ISH-01 | BUSBAR SECTION - IRISHTOWN 220-IRISHTOWN 220-220A1-A2 | 1 | 1 | 1 | Scheduled | 28/09/2022 | 28/09/2022
TO-22-220 kV B1/B2 @ ISH-01 | BUSBAR SECTION - IRISHTOWN 220-IRISHTOWN 220-220B1-B2 | 1 | 1 | 1 | Scheduled | 28/09/2022 | 28/09/2022
TO-22-SNU-110SB1-2CB-02 | COUPLER/SECTIONALISING CB - SNUGBOROUGH 110-SNUGBOROUGH 110-110SB1-2CB | 1 | 1 | 1 | Scheduled | 29/09/2022 | 29/09/2022
TO-22-220 kV B1 @ TH-01 | BUSBAR SECTION - TURLOUGH HILL 220-TURLOUGH HILL 220-220B1 | 1 | 1 | 1 | Scheduled | 29/09/2022 | 29/09/2022
TO-22-TH-T2001/2-02 | GENERATOR TRANSFORMER - TURLOUGH HILL 220-TURLOUGH HILL G1-T2001/2 | 1 | 1 | 1 | Scheduled | 29/09/2022 | 29/09/2022
TO-22-BAL-CDU-1-02 | 110kV FEEDER - BALTRASNA 110-CORDUFF 110-1 | 12 | 10 | 10 | Proposed | 03/10/2022 | 14/10/2022
TO-22-BAL-T122-01 | DISTRIBUTION TRANSFORMER - BALTRASNA 110-BALTRASNA 20-T122 | 5 | 5 | 5 | Reference | 03/10/2022 | 07/10/2022
TO-22-INC-PB-1-04 | 220kV FEEDER - INCHICORE 220-POOLBEG 220-1 | 19 | 15 | 15 | Proposed | 03/10/2022 | 21/10/2022
TO-22-PB-TF3-02 | TRANSFORMER - POOLBEG 220-POOLBEG 110-TF3 | 30 | 21 | 21 | Reference (Proposed) | 03/10/2022 | 01/11/2022
TO-22-BLC-110K3-01 | COUPLER/SECTIONALISING CB - BELCAMP 110-BELCAMP 110-110K3 | 3 | 3 | 3 | Scheduled | 04/10/2022 | 06/10/2022
TO-22-INC-T2102-01 | TRANSFORMER - INCHICORE 220-INCHICORE 110-T2102 | 2 | 2 | 2 | Reference (Proposed) | 04/10/2022 | 05/10/2022
TO-22-CKM GIS-T2104-01 | TRANSFORMER - CARRICKMINES GIS 220-CARRICKMINES GIS 110-T2104 | 2 | 2 | 2 | Reference (Proposed) | 05/10/2022 | 06/10/2022
TO-22-INC-T2106-01 | TRANSFORMER - INCHICORE 220-INCHICORE 110-T2106 | 2 | 2 | 2 | Reference (Proposed) | 06/10/2022 | 07/10/2022
TO-22-110 kV A2 @ CLG-04 | BUSBAR SECTION - CLOGHRAN 110-CLOGHRAN 110-110A2 | 5 | 5 | 5 | Proposed | 10/10/2022 | 14/10/2022
TO-22-110 kV B2 @ CLG-05 | BUSBAR SECTION - CLOGHRAN 110-CLOGHRAN 110-110B2 | 5 | 5 | 5 | Proposed | 10/10/2022 | 14/10/2022
TO-22-CLG-T122-04 | TSO CUSTOMER TRANSFORMER - CLOGHRAN 110-CLOGHRAN 20-T122 | 5 | 5 | 5 | Proposed | 10/10/2022 | 14/10/2022
TO-22-110 kV A1 @ CDU-02 | BUSBAR SECTION - CORDUFF 110-CORDUFF 110-110A1 | 5 | 5 | 5 | Scheduled | 10/10/2022 | 14/10/2022
TO-22-110 kV A2 @ CDU-04 | BUSBAR SECTION - CORDUFF 110-CORDUFF 110-110A2 | 5 | 5 | 5 | Scheduled | 10/10/2022 | 14/10/2022
TO-22-110 kV B1 @ CDU-02 | BUSBAR SECTION - CORDUFF 110-CORDUFF 110-110B1 | 5 | 5 | 5 | Scheduled | 10/10/2022 | 14/10/2022
TO-22-110 kV B2 @ CDU-04 | BUSBAR SECTION - CORDUFF 110-CORDUFF 110-110B2 | 5 | 5 | 5 | Scheduled | 10/10/2022 | 14/10/2022
TO-22-CDU-110K1-2-01 | COUPLER/SECTIONALISING CB - CORDUFF 110-CORDUFF 110-110K1-2 | 12 | 10 | 10 | Scheduled | 10/10/2022 | 21/10/2022
TO-22-220 kV A2 @ DSN-02 | BUSBAR SECTION - DUNSTOWN 220-DUNSTOWN 220-220A2 | 5 | 5 | 5 | Proposed | 10/10/2022 | 14/10/2022
TO-22-220 kV B2 @ DSN-02 | BUSBAR SECTION - DUNSTOWN 220-DUNSTOWN 220-220B2 | 5 | 5 | 5 | Proposed | 10/10/2022 | 14/10/2022
TO-22-400 kV A2 @ DSN-02 | BUSBAR SECTION - DUNSTOWN 400-DUNSTOWN 400-400A2 | 5 | 5 | 5 | Proposed | 10/10/2022 | 14/10/2022
TO-22-400 kV B2 @ DSN-02 | BUSBAR SECTION - DUNSTOWN 400-DUNSTOWN 400-400B2 | 5 | 5 | 5 | Proposed | 10/10/2022 | 14/10/2022
TO-22-DSN-T4202-01 | TRANSFORMER - DUNSTOWN 400-DUNSTOWN 220-T4202 | 26 | 19 | 19 | Proposed | 10/10/2022 | 04/11/2022
TO-22-MAY-T2101-01 | TRANSFORMER - MAYNOOTH 220-MAYNOOTH 110-T2101 | 3 | 3 | 3 | Scheduled | 10/10/2022 | 12/10/2022
TO-22-BLC-110SA1-3CB-01 | COUPLER/SECTIONALISING CB - BELCAMP 110-BELCAMP 110-110SA1-3CB | 1 | 1 | 1 | Scheduled | 11/10/2022 | 11/10/2022
TO-22-BRT-CLE-4-01 | 220kV FEEDER - BRACETOWN 220-CLONEE 220-4 | 2 | 2 | 2 | Proposed | 11/10/2022 | 12/10/2022
TO-22-BLC-110SB1-3CB-01 | COUPLER/SECTIONALISING CB - BELCAMP 110-BELCAMP 110-110SB1-3CB | 1 | 1 | 1 | Scheduled | 12/10/2022 | 12/10/2022
TO-22-BDA-NEW-1-01 | 110kV FEEDER - BARODA 110-NEWBRIDGE 110-1 | 5 | 5 | 5 | Scheduled | 17/10/2022 | 21/10/2022
TO-22-110 kV A2 @ CLG-05 | BUSBAR SECTION - CLOGHRAN 110-CLOGHRAN 110-110A2 | 5 | 5 | 5 | Proposed | 17/10/2022 | 21/10/2022
TO-22-110 kV B2 @ CLG-06 | BUSBAR SECTION - CLOGHRAN 110-CLOGHRAN 110-110B2 | 5 | 5 | 5 | Proposed | 17/10/2022 | 21/10/2022
TO-22-CLG-T124-01 | TSO CUSTOMER TRANSFORMER - CLOGHRAN 110-CLOGHRAN 20-T124 | 5 | 5 | 5 | Proposed | 17/10/2022 | 21/10/2022
TO-22-FIN GIS-T2101-01 | TRANSFORMER - FINGLAS 220-FINGLAS GIS 110-T2101 | 19 | 14 | 14 | Proposed | 17/10/2022 | 04/11/2022
TO-22-LOU-WOO-1-02 | 220kV FEEDER - LOUTH 220-WOODLAND 220-1 | 10 | 8 | 8 | Scheduled | 17/10/2022 | 26/10/2022
TO-22-PB-SHL-1-01 | 220kV FEEDER - POOLBEG 220-SHELLYBANKS 220-1 | 19 | 14 | 14 | Proposed | 17/10/2022 | 04/11/2022
TO-22-SHL-D1/CB2-01 | COUPLER/SECTIONALISING CB - SHELLYBANKS 220-SHELLYBANKS 220-D1/CB2 | 4 | 4 | 4 | Proposed | 17/10/2022 | 20/10/2022
TO-22-SHL-D1/CB3-01 | COUPLER/SECTIONALISING CB - SHELLYBANKS 220-SHELLYBANKS 220-D1/CB3 | 4 | 4 | 4 | Proposed | 17/10/2022 | 20/10/2022
TO-22-SHL-D2/CB3-04 | COUPLER/SECTIONALISING CB - SHELLYBANKS 220-SHELLYBANKS 220-D2/CB3 | 4 | 4 | 4 | Proposed | 17/10/2022 | 20/10/2022
TO-22-BRT-CLE-2-01 | 220kV FEEDER - BRACETOWN 220-CLONEE 220-2 | 2 | 2 | 2 | Proposed | 20/10/2022 | 21/10/2022
TO-22-MCE-SNU-1-03 | 110kV FEEDER - MACETOWN 110-SNUGBOROUGH 110-1 | 5 | 5 | 5 | Proposed | 24/10/2022 | 28/10/2022
TO-22-MAY-RNW-1-03 | 110kV FEEDER - MAYNOOTH 110-RINAWADE 110-1 | 3 | 3 | 3 | Proposed | 25/10/2022 | 27/10/2022
TO-22-DSN-MAY-2-04 | 220kV FEEDER - DUNSTOWN 220-MAYNOOTH 220-2 | 5 | 4 | 4 | Proposed | 31/10/2022 | 04/11/2022
TO-22-BEG-CKM GIS-1-01 | 110kV FEEDER - BALLYBEG 110-CARRICKMINES GIS 110-1 | 4 | 4 | 4 | Proposed | 01/11/2022 | 04/11/2022
TO-22-CKM GIS-R2001-01 | CAPACITOR/SVC/REACTOR - CARRICKMINES GIS 220-CARRICKMINES GIS 220-R2001 | 11 | 9 | 9 | Proposed | 01/11/2022 | 11/11/2022
TO-22-400 kV A1 @ DSN-01 | BUSBAR SECTION - DUNSTOWN 400-DUNSTOWN 400-400A1 | 11 | 9 | 9 | Proposed | 01/11/2022 | 11/11/2022
TO-22-400 kV A2 @ DSN-01 | BUSBAR SECTION - DUNSTOWN 400-DUNSTOWN 400-400A2 | 11 | 9 | 9 | Proposed | 01/11/2022 | 11/11/2022
TO-22-400 kV B1 @ DSN-01 | BUSBAR SECTION - DUNSTOWN 400-DUNSTOWN 400-400B1 | 11 | 9 | 9 | Proposed | 01/11/2022 | 11/11/2022
TO-22-400 kV B2 @ DSN-01 | BUSBAR SECTION - DUNSTOWN 400-DUNSTOWN 400-400B2 | 11 | 9 | 9 | Proposed | 01/11/2022 | 11/11/2022
TO-22-DSN-400K1-2-02 | COUPLER/SECTIONALISING CB - DUNSTOWN 400-DUNSTOWN 400-400K1-2 | 11 | 9 | 9 | Proposed | 01/11/2022 | 11/11/2022
TO-22-110 kV B2 @ FIN GIS-08 | BUSBAR SECTION - FINGLAS GIS 110-FINGLAS GIS 110-110B2 | 4 | 4 | 4 | Proposed | 01/11/2022 | 04/11/2022
TO-22-110 kV B4 @ FIN GIS-01 | BUSBAR SECTION - FINGLAS GIS 110-FINGLAS GIS 110-110B4 | 4 | 4 | 4 | Proposed | 01/11/2022 | 04/11/2022
TO-22-FIN GIS-110SB2-4CB-04 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110SB2-4CB | 4 | 4 | 4 | Proposed | 01/11/2022 | 04/11/2022
TO-22-CBT-T2102-01 | TRANSFORMER - CASTLEBAGOT 220-CASTLEBAGOT 110-T2102 | 5 | 5 | 5 | Proposed | 07/11/2022 | 11/11/2022
TO-22-FIN GIS-110K2-07 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110K2 | 4 | 4 | 4 | Proposed | 07/11/2022 | 10/11/2022
TO-22-220 kV A2 @ MAY-06 | BUSBAR SECTION - MAYNOOTH 220-MAYNOOTH 220-220A2 | 5 | 5 | 5 | Proposed | 07/11/2022 | 11/11/2022
TO-22-220 kV B2 @ MAY-07 | BUSBAR SECTION - MAYNOOTH 220-MAYNOOTH 220-220B2 | 5 | 5 | 5 | Proposed | 07/11/2022 | 11/11/2022
TO-22-MAY-SH-1-04 | 220kV FEEDER - MAYNOOTH 220-SHANNONBRIDGE 220-1 | 5 | 5 | 5 | Proposed | 07/11/2022 | 11/11/2022
TO-22-110 kV A1 @ RYB GIS-01 | BUSBAR SECTION - RYEBROOK GIS 110-RYEBROOK GIS 110-110A1 | 5 | 5 | 5 | Proposed | 07/11/2022 | 11/11/2022
TO-22-110 kV A2 @ RYB GIS-01 | BUSBAR SECTION - RYEBROOK GIS 110-RYEBROOK GIS 110-110A2 | 5 | 5 | 5 | Proposed | 07/11/2022 | 11/11/2022
TO-22-RYB GIS-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - RYEBROOK GIS 110-RYEBROOK GIS 110-110SA1-2CB | 5 | 5 | 5 | Proposed | 07/11/2022 | 11/11/2022
TO-22-FIN-NW-1-04 | 220kV FEEDER - FINGLAS 220-NORTH WALL 220-1 | 11 | 9 | 9 | Proposed | 08/11/2022 | 18/11/2022
TO-22-220 kV A2 @ CKM GIS-02 | BUSBAR SECTION - CARRICKMINES GIS 220-CARRICKMINES GIS 220-220A2 | 5 | 5 | 5 | Proposed | 14/11/2022 | 18/11/2022
TO-22-220 kV A4 @ CKM GIS-03 | BUSBAR SECTION - CARRICKMINES GIS 220-CARRICKMINES GIS 220-220A4 | 5 | 5 | 5 | Proposed | 14/11/2022 | 18/11/2022
TO-22-CKM GIS-220SA2-4CB-01 | COUPLER/SECTIONALISING CB - CARRICKMINES GIS 220-CARRICKMINES GIS 220-22SA2-4CB | 12 | 10 | 10 | Proposed | 14/11/2022 | 25/11/2022
TO-22-110 kV B1 @ RYB GIS-01 | BUSBAR SECTION - RYEBROOK GIS 110-RYEBROOK GIS 110-110B1 | 5 | 5 | 5 | Proposed | 14/11/2022 | 18/11/2022
TO-22-110 kV B2 @ RYB GIS-02 | BUSBAR SECTION - RYEBROOK GIS 110-RYEBROOK GIS 110-110B2 | 5 | 5 | 5 | Proposed | 14/11/2022 | 18/11/2022
TO-22-RYB GIS-110SB1-2CB-02 | COUPLER/SECTIONALISING CB - RYEBROOK GIS 110-RYEBROOK GIS 110-110SB1-2CB | 5 | 5 | 5 | Proposed | 14/11/2022 | 18/11/2022
TO-22-110 kV A1/A2/A3/A4 @ CDU-01 | BUSBAR SECTION - CORDUFF 110-CORDUFF 110-110A1-A2-A3-A4 | 1 | 1 | 1 | Proposed | 16/11/2022 | 16/11/2022
TO-22-110 kV B1/B2/B3/B4 @ CDU-01 | BUSBAR SECTION - CORDUFF 110-CORDUFF 110-110B1-B2-B3-B4 | 1 | 1 | 1 | Proposed | 16/11/2022 | 16/11/2022
TO-22-CDU-220SB2-4-03 | SECTIONALISING DISCONNECT - CORDUFF 220-CORDUFF 220-220SB2-4 | 5 | 5 | 5 | Proposed | 21/11/2022 | 25/11/2022
TO-22-CDU-WOO-1-01 | 220kV FEEDER - CORDUFF 220-WOODLAND 220-1 | 5 | 5 | 5 | Proposed | 21/11/2022 | 25/11/2022
TO-22-PB-R2001-06 | CAPACITOR/SVC/REACTOR - POOLBEG 220-POOLBEG 220-R2001 | 4 | 4 | 4 | Proposed | 21/11/2022 | 24/11/2022
TO-22-110 kV B1 @ RYB GIS-02 | BUSBAR SECTION - RYEBROOK GIS 110-RYEBROOK GIS 110-110B1 | 5 | 5 | 5 | Proposed | 21/11/2022 | 25/11/2022
TO-22-110 kV B3 @ RYB GIS-02 | BUSBAR SECTION - RYEBROOK GIS 110-RYEBROOK GIS 110-110B3 | 5 | 5 | 5 | Proposed | 21/11/2022 | 25/11/2022
TO-22-RYB GIS-110SB1-3CB-02 | COUPLER/SECTIONALISING CB - RYEBROOK GIS 110-RYEBROOK GIS 110-110SB1-3CB | 5 | 5 | 5 | Proposed | 21/11/2022 | 25/11/2022

## GEN_Cork
Outage ID | Feeder ID | Calendar Day Duration | Working Day Duration | Work Days | Outage Status | Start | Finish
TO-22-AD-SA1-2CB-01 | COUPLER/SECTIONALISING CB - AGHADA 220-AGHADA 220-220SA1-2CB | 2 | 2 | 2 | Scheduled | 04/01/2022 | 05/01/2022
TO-22-AD-SB1-2CB-01 | COUPLER/SECTIONALISING CB - AGHADA 220-AGHADA 220-220SB1-2CB | 2 | 2 |  | Scheduled | 10/01/2022 | 11/01/2022
TO-22-110 kV A1/A2 @ MR-01 | BUSBAR SECTION - MARINA 110-MARINA 110-110A1-A2 | 1 | 1 | 1 | Scheduled | 25/01/2022 | 25/01/2022
TO-22-110 kV B1/B2 @ MR-01 | BUSBAR SECTION - MARINA 110-MARINA 110-110B1-B2 | 1 | 1 | 1 | Scheduled | 25/01/2022 | 25/01/2022
TO-22-KRA-MID-1-01 | 110kV FEEDER - KNOCKRAHA 110-MIDLETON 110-1 | 3 | 3 | 3 | Scheduled | 14/03/2022 | 16/03/2022
TO-22-DMY-MAC-1-01 | 110kV FEEDER - DUNMANWAY 110-MACROOM 110-1 | 12 | 10 | 10 | Scheduled | 21/03/2022 | 01/04/2022
TO-22-RAF-TBG-1-02 | 110kV FEEDER - RAFFEEN 110-TRABEG 110-1 | 5 | 5 | 5 | Scheduled | 21/03/2022 | 25/03/2022
TO-22-110 kV B1 @ TBG-01 | BUSBAR SECTION - TRABEG 110-TRABEG 110-110B1 | 5 | 5 | 5 | Scheduled | 21/03/2022 | 25/03/2022
TO-22-110 kV B2 @ TBG-01 | BUSBAR SECTION - TRABEG 110-TRABEG 110-110B2 | 5 | 5 | 5 | Scheduled | 21/03/2022 | 25/03/2022
TO-22-MR-TBG-1-02 | 110kV FEEDER - MARINA 110-TRABEG 110-1 | 2 | 2 | 2 | Scheduled | 29/03/2022 | 30/03/2022
TO-22-CLA-CKN-1-01 | 110kV FEEDER - CLASHAVOON 110-CLONKEEN 110-1 | 12 | 9 | 12 | Scheduled | 04/04/2022 | 15/04/2022
TO-22-110 kV A1/A2 @ TBG-01 | BUSBAR SECTION - TRABEG 110-TRABEG 110-110A1-A2 | 1 | 1 | 1 | Scheduled | 06/04/2022 | 06/04/2022
TO-22-110 kV B1/B2 @ TBG-01 | BUSBAR SECTION - TRABEG 110-TRABEG 110-110B1-B2 | 1 | 1 | 1 | Scheduled | 06/04/2022 | 06/04/2022
TO-22-CLA-KRA-1-02 | 220kV FEEDER - CLASHAVOON 220-KNOCKRAHA 220-1 | 3 | 3 | 3 | Scheduled | 19/04/2022 | 21/04/2022
TO-22-CVW-COW-1-01 | 110kV FEEDER - CASTLEVIEW 110-COW CROSS 110-1 | 15 | 10 | 10 | Scheduled | 26/04/2022 | 10/05/2022
TO-22-COW-OLD-1-01 | 110kV FEEDER - COW CROSS 110-OLDCOURT 110-1 | 15 | 10 | 10 | Reference | 26/04/2022 | 10/05/2022
TO-22-COW-WHI-1-01 | 110kV FEEDER - COW CROSS 110-WHITEGATE 110-1 | 15 | 10 | 10 | Scheduled | 26/04/2022 | 10/05/2022
TO-22-IA-MAC-1-01 | 110kV FEEDER - INNISCARRA 110-MACROOM 110-1 | 3 | 3 | 3 | Scheduled | 03/05/2022 | 05/05/2022
TO-22-IA-T101-01 | GENERATOR TRANSFORMER - INNISCARRA 110-INNISCARRA G1-T101 | 11 | 9 | 9 | Scheduled | 03/05/2022 | 13/05/2022
TO-22-KLN-KRA-1-01 | 220kV FEEDER - KILLONAN 220-KNOCKRAHA 220-1 | 8 | 6 | 6 | Scheduled | 03/05/2022 | 10/05/2022
TO-22-CLA-110K1-2-01 | COUPLER/SECTIONALISING CB - CLASHAVOON 110-CLASHAVOON 110-110K1-2 | 2 | 2 | 2 | Scheduled | 04/05/2022 | 05/05/2022
TO-22-AD-220K1-01 | COUPLER/SECTIONALISING CB - AGHADA 220-AGHADA 220-220K1 | 1 | 1 | 1 | Scheduled | 12/05/2022 | 12/05/2022
TO-22-CD-T103-01 | GENERATOR TRANSFORMER - CARRIGADROHID 110-CARRIGADROHID G3-T103 | 12 | 10 | 10 | Scheduled | 23/05/2022 | 03/06/2022
TO-22-CVW-T101-01 | DISTRIBUTION TRANSFORMER - CASTLEVIEW 110-CASTLEVIEW 10-T101 | 2 | 2 | 2 | Reference | 01/06/2022 | 02/06/2022
TO-22-COW-T142-01 | DISTRIBUTION TRANSFORMER - COW CROSS 110-COW CROSS 38-T142 | 2 | 2 | 2 | Reference | 01/06/2022 | 02/06/2022
TO-22-CD-KBY-1-05 | 110kV FEEDER - CARRIGADROHID 110-KILBARRY 110-1 | 4 | 4 | 4 | Scheduled | 07/06/2022 | 10/06/2022
TO-22-BRY-RAF-1-01 | 110kV FEEDER - BARNAHELY 110-RAFFEEN 110-1 | 2 | 2 | 2 | Reference | 08/06/2022 | 09/06/2022
TO-22-CLA-MAC-1-01 | 110kV FEEDER - CLASHAVOON 110-MACROOM 110-1 | 40 | 30 | 30 | Scheduled | 13/06/2022 | 22/07/2022
TO-22-BGH-110SA2-01 | SECTIONALISING DISCONNECT - BOGGERAGH 110-BOGGERAGH 110-110SA2 | 5 | 5 | 5 | Scheduled | 20/06/2022 | 24/06/2022
TO-22-BGH-CLA-1-01 | 110kV FEEDER - BOGGERAGH 110-CLASHAVOON 110-1 | 9 | 7 | 7 | Scheduled | 20/06/2022 | 28/06/2022
TO-22-BGH-T132-01 | GENERATOR TRANSFORMER - BOGGERAGH 110-BOGGERAGH 33-T132 | 5 | 5 | 5 | Scheduled | 20/06/2022 | 24/06/2022
TO-22-BGH-T121-01 | GENERATOR TRANSFORMER - BOGGERAGH 110-BOGGERAGH 20-T121 | 3 | 3 | 3 | Scheduled | 22/06/2022 | 24/06/2022
TO-22-BAN-BRI-1-01 | 110kV FEEDER - BANDON 110-BRINNY 110-1 | 8 | 6 | 6 | Scheduled | 04/07/2022 | 11/07/2022
TO-22-BRI-T101-01 | TSO CUSTOMER TRANSFORMER - BRINNY 110-BRINNY 10-T101 | 8 | 6 | 6 | Scheduled | 04/07/2022 | 11/07/2022
TO-22-KBY-KRA-2-02 | 110kV FEEDER - KILBARRY 110-KNOCKRAHA 110-2 | 12 | 10 | 10 | Scheduled | 04/07/2022 | 15/07/2022
TO-22-KBY-MAL-1-01 | 110kV FEEDER - KILBARRY 110-MALLOW 110-1 | 12 | 10 | 10 | Scheduled | 04/07/2022 | 15/07/2022
TO-22-RAF-T2102-01 | TRANSFORMER - RAFFEEN 220-RAFFEEN 110-T2102 | 8 | 6 | 6 | Scheduled | 04/07/2022 | 11/07/2022
TO-22-BAN-RAF-1-01 | 110kV FEEDER - BANDON 110-RAFFEEN 110-1 | 8 | 6 | 6 | Scheduled | 08/07/2022 | 15/07/2022
TO-22-BAN-DMY-1-01 | 110kV FEEDER - BANDON 110-DUNMANWAY 110-1 | 10 | 8 | 8 | Scheduled | 18/07/2022 | 27/07/2022
TO-22-CLA-CKN-1-02 | 110kV FEEDER - CLASHAVOON 110-CLONKEEN 110-1 | 5 | 5 | 5 | Scheduled | 18/07/2022 | 22/07/2022
TO-22-CD-MAC-1-02 | 110kV FEEDER - CARRIGADROHID 110-MACROOM 110-1 | 15 | 10 | 10 | Scheduled | 28/07/2022 | 11/08/2022
TO-22-CVW-KRA-1-01 | 110kV FEEDER - CASTLEVIEW 110-KNOCKRAHA 110-1 | 8 | 6 | 6 | Scheduled | 08/08/2022 | 15/08/2022
TO-22-110 kV A2 @ KRA-01 | BUSBAR SECTION - KNOCKRAHA 110-KNOCKRAHA 110-110A2 | 4 | 4 | 4 | Scheduled | 08/08/2022 | 11/08/2022
TO-22-110 kV B2 @ KRA-01 | BUSBAR SECTION - KNOCKRAHA 110-KNOCKRAHA 110-110B2 | 4 | 4 | 4 | Scheduled | 08/08/2022 | 11/08/2022
TO-22-220 kV A2 @ KRA-04 | BUSBAR SECTION - KNOCKRAHA 220-KNOCKRAHA 220-220A2 | 5 | 5 | 5 | Scheduled | 08/08/2022 | 12/08/2022
TO-22-220 kV B2 @ KRA-04 | BUSBAR SECTION - KNOCKRAHA 220-KNOCKRAHA 220-220B2 | 5 | 5 | 5 | Scheduled | 08/08/2022 | 12/08/2022
TO-22-KRA-T2102-01 | TRANSFORMER - KNOCKRAHA 220-KNOCKRAHA 110-T2102 | 19 | 15 | 15 | Scheduled | 08/08/2022 | 26/08/2022
TO-22-BAN-BRI-2-01 | 110kV FEEDER - BANDON 110-BRINNY 110-2 | 6 | 5 | 5 | Scheduled | 15/08/2022 | 20/08/2022
TO-22-BRI-T102-01 | TSO CUSTOMER TRANSFORMER - BRINNY 110-BRINNY 10-T102 | 6 | 5 | 5 | Scheduled | 15/08/2022 | 20/08/2022
TO-22-CRO-IA-1-01 | 110kV FEEDER - COOLROE 110-INNISCARRA 110-1 | 12 | 10 | 10 | Scheduled | 15/08/2022 | 26/08/2022
TO-22-CLA-MAC-2-02 | 110kV FEEDER - CLASHAVOON 110-MACROOM 110-2 | 3 | 3 | 3 | Scheduled | 17/08/2022 | 19/08/2022
TO-22-CRO-KBY-1-04 | 110kV FEEDER - COOLROE 110-KILBARRY 110-1 | 21 | 15 |  | Scheduled | 31/08/2022 | 20/09/2022
TO-22-220 kV A1 @ AD-03 | BUSBAR SECTION - AGHADA 220-AGHADA 220-220A1 | 5 | 5 | 5 | Scheduled | 05/09/2022 | 09/09/2022
TO-22-220 kV B1 @ AD-04 | BUSBAR SECTION - AGHADA 220-AGHADA 220-220B1 | 5 | 5 | 5 | Scheduled | 05/09/2022 | 09/09/2022
TO-22-AD-LPT-1-01 | 220kV FEEDER - AGHADA 220-LONG POINT 220-1 | 5 | 5 | 5 | Scheduled | 05/09/2022 | 09/09/2022
TO-22-KRA-T2101-01 | TRANSFORMER - KNOCKRAHA 220-KNOCKRAHA 110-T2101 | 16 | 12 | 12 | Scheduled | 05/09/2022 | 20/09/2022
TO-22-LPT-T2002-01 | GENERATOR TRANSFORMER - LONG POINT 220-LONG POINT G1-T2002 | 5 | 5 | 5 | Scheduled | 05/09/2022 | 09/09/2022
TO-22-WHI-CKB-T102-01 | TSO CUSTOMER TRANSFORMER - WHITEGATE 110-WHITEGATE 10-CKB-T102 | 5 | 5 | 5 | Scheduled | 05/09/2022 | 09/09/2022
TO-22-AD-RAF-1-02 | 220kV FEEDER - AGHADA 220-RAFFEEN 220-1 | 5 | 5 | 5 | Tentative | 12/09/2022 | 16/09/2022
TO-22-CRO-110SA1-01 | SECTIONALISING DISCONNECT - COOLROE 110-COOLROE 110-110SA1 | 5 | 5 | 5 | Scheduled | 12/09/2022 | 16/09/2022
TO-22-CRO-110SA2-01 | SECTIONALISING DISCONNECT - COOLROE 110-COOLROE 110-110SA2 | 5 | 5 | 5 | Scheduled | 12/09/2022 | 16/09/2022
TO-22-CRO-T121-01 | DISTRIBUTION TRANSFORMER - COOLROE 110-COOLROE 20-T121 | 5 | 5 | 5 | Reference | 12/09/2022 | 16/09/2022
TO-22-KRA-RAF-1-05 | 220kV FEEDER - KNOCKRAHA 220-RAFFEEN 220-1 | 5 | 5 | 5 | Tentative | 12/09/2022 | 16/09/2022
TO-22-WHI-CKB-T101-01 | TSO CUSTOMER TRANSFORMER - WHITEGATE 110-WHITEGATE 10-CKB-T101 | 5 | 5 | 5 | Scheduled | 12/09/2022 | 16/09/2022
TO-22-CLA-DMY-1-01 | 110kV FEEDER - CLASHAVOON 110-DUNMANWAY 110-1 | 1 | 1 | 1 | Scheduled | 13/09/2022 | 13/09/2022
TO-22-DMY-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - DUNMANWAY 110-DUNMANWAY 110-110SA1-2CB | 1 | 1 | 1 | Tentative | 14/09/2022 | 14/09/2022
TO-22-CRO-T122-01 | DISTRIBUTION TRANSFORMER - COOLROE 110-COOLROE 20-T122 | 2 | 2 | 2 | Reference | 22/09/2022 | 23/09/2022
TO-22-COW-RAF-1-02 | 110kV FEEDER - COW CROSS 110-RAFFEEN 110-1 | 5 | 5 | 5 | Proposed | 26/09/2022 | 30/09/2022
TO-22-MID-T102-01 | DISTRIBUTION TRANSFORMER - MIDLETON 110-MIDLETON 10-T102 | 2 | 2 | 2 | Reference (Proposed) | 27/09/2022 | 28/09/2022
TO-22-CRO-IA-1-03 | 110kV FEEDER - COOLROE 110-INNISCARRA 110-1 | 1 | 1 | 1 | Proposed | 30/09/2022 | 30/09/2022
TO-22-IA-MAC-1-02 | 110kV FEEDER - INNISCARRA 110-MACROOM 110-1 | 1 | 1 | 1 | Proposed | 30/09/2022 | 30/09/2022
TO-22-IA-T101-02 | GENERATOR TRANSFORMER - INNISCARRA 110-INNISCARRA G1-T101 | 1 | 1 | 1 | Proposed | 30/09/2022 | 30/09/2022
TO-22-KBY-KRA-1-05 | 110kV FEEDER - KILBARRY 110-KNOCKRAHA 110-1 | 2 | 0 | 0 | Proposed | 01/10/2022 | 02/10/2022
TO-22-CD-KBY-1-07 | 110kV FEEDER - CARRIGADROHID 110-KILBARRY 110-1 | 5 | 5 | 5 | Proposed | 03/10/2022 | 07/10/2022
TO-22-RAF-T2101-01 | TRANSFORMER - RAFFEEN 220-RAFFEEN 110-T2101 | 5 | 5 | 5 | Proposed | 03/10/2022 | 07/10/2022
TO-22-KRA-RAF-1-01 | 220kV FEEDER - KNOCKRAHA 220-RAFFEEN 220-1 | 12 | 8 | 8 | Proposed | 07/10/2022 | 18/10/2022
TO-22-AD-GGO-1-02 | 220kV FEEDER - AGHADA 220-GLANAGOW 220-1 | 5 | 5 | 5 | Proposed | 10/10/2022 | 14/10/2022
TO-22-GGO-T2001-01 | GENERATOR TRANSFORMER - GLANAGOW 220-GLANAGOW G1-T2001 | 5 | 5 | 5 | Proposed | 10/10/2022 | 14/10/2022
TO-22-RAF-TBG-2-03 | 110kV FEEDER - RAFFEEN 110-TRABEG 110-2 | 12 | 10 | 10 | Proposed | 10/10/2022 | 21/10/2022
TO-22-KRA-WOH-1-01 | 110kV FEEDER - KNOCKRAHA 110-WOODHOUSE 110-1 | 3 | 3 | 3 | Scheduled | 12/10/2022 | 14/10/2022
TO-22-CUL-KRA-1-01 | 220kV FEEDER - CULLENAGH 220-KNOCKRAHA 220-1 | 5 | 5 | 5 | Scheduled | 17/10/2022 | 21/10/2022
TO-22-CLA-KRA-1-01 | 220kV FEEDER - CLASHAVOON 220-KNOCKRAHA 220-1 | 21 | 15 | 15 | Proposed | 01/11/2022 | 21/11/2022
TO-22-GGO-220K1-2-01 | COUPLER/SECTIONALISING CB - GLANAGOW 220-GLANAGOW 220-220K1-2 | 2 | 2 | 2 | Proposed | 01/11/2022 | 02/11/2022
TO-22-CHA-MAL-1-01 | 110kV FEEDER - CHARLEVILLE 110-MALLOW 110-1 | 9 | 7 | 7 | Proposed | 02/11/2022 | 10/11/2022
TO-22-CLA-220K1-2-01 | COUPLER/SECTIONALISING CB - CLASHAVOON 220-CLASHAVOON 220-220K1-2 | 3 | 3 | 3 | Proposed | 02/11/2022 | 04/11/2022
TO-22-CLA-T2102-01 | TRANSFORMER - CLASHAVOON 220-CLASHAVOON 110-T2102 | 3 | 3 | 3 | Proposed | 02/11/2022 | 04/11/2022
TO-22-110 kV A1/A2 @ KRA-01 | BUSBAR SECTION - KNOCKRAHA 110-KNOCKRAHA 110-110A1-A2 | 1 | 1 | 1 | Proposed | 09/11/2022 | 09/11/2022
TO-22-110 kV B1/B2 @ KRA-01 | BUSBAR SECTION - KNOCKRAHA 110-KNOCKRAHA 110-110B1-B2 | 1 | 1 | 1 | Proposed | 09/11/2022 | 09/11/2022
TO-22-KBY-MAL-1-04 | 110kV FEEDER - KILBARRY 110-MALLOW 110-1 | 2 | 2 | 2 | Proposed | 22/11/2022 | 23/11/2022
TO-22-MID-WHI-1-01 | 110kV FEEDER - MIDLETON 110-WHITEGATE 110-1 | 9 | 7 | 7 | Proposed | 22/11/2022 | 30/11/2022
TO-22-KRA-220SA2-4CB-04 | COUPLER/SECTIONALISING CB - KNOCKRAHA 220-KNOCKRAHA 220-220SA2-4CB | 1 | 1 | 1 | Proposed | 28/11/2022 | 28/11/2022
TO-22-KRA-220SB2-4CB-04 | COUPLER/SECTIONALISING CB - KNOCKRAHA 220-KNOCKRAHA 220-220SB2-4CB | 1 | 1 | 1 | Proposed | 29/11/2022 | 29/11/2022
TO-22-KRA-220K4-01 | COUPLER/SECTIONALISING CB - KNOCKRAHA 220-KNOCKRAHA 220-220K4 | 1 | 1 | 1 | Proposed | 30/11/2022 | 30/11/2022