## GEN_ALL
Outage ID | Feeder ID | Calendar Day Duration | Working Day Duration | Work Days | Outage Status | Start | Finish
TO-23-AA GIS-T104-01 | GENERATOR TRANSFORMER - ARDNACRUSHA GIS 110-ARDNACRUSHA GIS G4-T104 | 400 | 281 | 281 | Scheduled | 23/03/2022 | 26/04/2023
TO-23-GGO-220K1-2-01 | COUPLER/SECTIONALISING CB - GLANAGOW 220-GLANAGOW 220-220K1-2 | 251 | 172 | 172 | Scheduled | 01/01/2023 | 08/09/2023
TO-23-TB-T101-02 | GENERATOR TRANSFORMER - TARBERT 110-TARBERT G1-T101 | 365 | 249 | 249 | Scheduled | 01/01/2023 | 31/12/2023
TO-23-SLI-T142-01 | DISTRIBUTION TRANSFORMER - SLIGO 110-SLIGO 38-T142 | 82 | 58 | 58 | Reference | 09/01/2023 | 31/03/2023
TO-23-THU-CAP2-01 | CAPACITOR/SVC/REACTOR - THURLES 110-THURLES 110-CAP2 | 350 | 240 | 240 | Scheduled | 16/01/2023 | 31/12/2023
TO-23-GWE-T101-03 | TSO CUSTOMER TRANSFORMER - GORTAWEE 110-GORTAWEE 10-T101 | 40 | 29 | 29 | Scheduled | 30/01/2023 | 10/03/2023
TO-23-KRA-220K1-03 | COUPLER/SECTIONALISING CB - KNOCKRAHA 220-KNOCKRAHA 220-220K1 | 33 | 24 | 24 | Scheduled | 30/01/2023 | 03/03/2023
TO-23-CRU-CDU-2-01 | 220kV FEEDER - CRUISERATH 220-CORDUFF 220-2 | 9 | 5 | 5 | Scheduled | 25/02/2023 | 05/03/2023
TO-23-220 kV A2 @ AD-01 | BUSBAR SECTION - AGHADA 220-AGHADA 220-220A2 | 234 | 162 | 162 | Scheduled | 27/02/2023 | 18/10/2023
TO-23-220 kV B2 @ AD-01 | BUSBAR SECTION - AGHADA 220-AGHADA 220-220B2 | 234 | 162 | 162 | Scheduled | 27/02/2023 | 18/10/2023
TO-23-AD-SA1-2CB-01 | COUPLER/SECTIONALISING CB - AGHADA 220-AGHADA 220-220SA1-2CB | 234 | 162 | 162 | Scheduled | 27/02/2023 | 18/10/2023
TO-23-AD-SB1-2CB-01 | COUPLER/SECTIONALISING CB - AGHADA 220-AGHADA 220-220SB1-2CB | 234 | 162 | 162 | Scheduled | 27/02/2023 | 18/10/2023
TO-23-AD-T2001-03 | GENERATOR TRANSFORMER - AGHADA 220-AGHADA G1-T2001 | 234 | 162 | 162 | Scheduled | 27/02/2023 | 18/10/2023
TO-23-ARK-BOG-1-01 | 110kV FEEDER - ARKLOW 110-BANOGE 110-1 | 3 | 3 | 3 | Scheduled | 27/02/2023 | 01/03/2023
TO-23-BYH-BVK-1-03 | 220kV FEEDER - BALLYNAHULLA 220-BALLYVOUSKILL 220-1 | 12 | 10 | 10 | Scheduled | 27/02/2023 | 10/03/2023
TO-23-BDA-MON-1-01 | 110kV FEEDER - BARODA 110-MONREAD 110-1 | 12 | 10 | 10 | Scheduled | 27/02/2023 | 10/03/2023
TO-23-BUT-KTN-1-03 | 110kV FEEDER - BUTLERSTOWN 110-KILLOTERAN 110-1 | 5 | 5 | 5 | Scheduled | 27/02/2023 | 03/03/2023
TO-23-CSH-GAL-3-02 | 110kV FEEDER - CASHLA 110-GALWAY 110-3 | 88 | 60 | 61 | Scheduled | 27/02/2023 | 25/05/2023
TO-23-CVW-110SA1-01 | SECTIONALISING DISCONNECT - CASTLEVIEW 110-CASTLEVIEW 110-110SA1 | 3 | 3 | 3 | Scheduled | 27/02/2023 | 01/03/2023
TO-23-CVW-110SA2-01 | SECTIONALISING DISCONNECT - CASTLEVIEW 110-CASTLEVIEW 110-110SA2 | 3 | 3 | 3 | Scheduled | 27/02/2023 | 01/03/2023
TO-23-CVW-COW-1-02 | 110kV FEEDER - CASTLEVIEW 110-COW CROSS 110-1 | 3 | 3 | 3 | Scheduled | 27/02/2023 | 01/03/2023
TO-23-CVW-T101-01 | DISTRIBUTION TRANSFORMER - CASTLEVIEW 110-CASTLEVIEW 10-T101 | 3 | 3 | 3 | Reference | 27/02/2023 | 01/03/2023
TO-23-CTN-TIP-1-01 | 110kV FEEDER - CAUTEEN 110-TIPPERARY 110-1 | 68 | 46 | 46 | Scheduled | 27/02/2023 | 05/05/2023
TO-23-110 kV A4 @ CDU-01 | BUSBAR SECTION - CORDUFF 110-CORDUFF 110-110A4 | 24 | 17 | 17 | Scheduled | 27/02/2023 | 22/03/2023
TO-23-110 kV B4 @ CDU-01 | BUSBAR SECTION - CORDUFF 110-CORDUFF 110-110B4 | 24 | 17 | 17 | Scheduled | 27/02/2023 | 22/03/2023
TO-23-DER-110SA1-01 | SECTIONALISING DISCONNECT - DERRYIRON 110-DERRYIRON 110-110SA1 | 5 | 5 | 5 | Scheduled | 27/02/2023 | 03/03/2023
TO-23-DER-110SA2-01 | SECTIONALISING DISCONNECT - DERRYIRON 110-DERRYIRON 110-110SA2 | 5 | 5 | 5 | Scheduled | 27/02/2023 | 03/03/2023
TO-23-DER-KIN-1-01 | 110kV FEEDER - DERRYIRON 110-KINNEGAD 110-1 | 5 | 5 | 5 | Scheduled | 27/02/2023 | 03/03/2023
TO-23-DDK-MLN-1-02 | 110kV FEEDER - DUNDALK 110-MULLAGHARLIN 110-1 | 10 | 8 | 8 | Scheduled | 27/02/2023 | 08/03/2023
TO-23-GAL-110K2-3-02 | COUPLER/SECTIONALISING CB - GALWAY 110-GALWAY 110-110K2-3 | 308 | 211 | 211 | Scheduled | 27/02/2023 | 31/12/2023
TO-23-GAL-T142-02 | DISTRIBUTION TRANSFORMER - GALWAY 110-GALWAY 38-T142 | 95 | 65 | 65 | Reference | 27/02/2023 | 01/06/2023
TO-23-GOR-MTH-1-01 | 110kV FEEDER - GORMAN 110-MEATH HILL 110-1 | 68 | 46 | 46 | Scheduled | 27/02/2023 | 05/05/2023
TO-23-GI-KKY-1-01 | 110kV FEEDER - GREAT ISLAND 110-KILKENNY 110-1 | 2 | 2 | 2 | Scheduled | 27/02/2023 | 28/02/2023
TO-23-KIN-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - KINNEGAD 110-KINNEGAD 110-110SA1-2CB | 5 | 5 | 5 | Scheduled | 27/02/2023 | 03/03/2023
TO-23-KIN-MUL-1-01 | 110kV FEEDER - KINNEGAD 110-MULLINGAR 110-1 | 5 | 5 | 5 | Scheduled | 27/02/2023 | 03/03/2023
TO-23-KIN-T101-01 | TSO CUSTOMER TRANSFORMER - KINNEGAD 110-KINNEGAD 10-T101 | 5 | 5 | 5 | Scheduled | 27/02/2023 | 03/03/2023
TO-23-KRA-220K1-2-03 | COUPLER/SECTIONALISING CB - KNOCKRAHA 220-KNOCKRAHA 220-220K1-2 | 308 | 211 | 211 | Scheduled | 27/02/2023 | 31/12/2023
TO-23-110 kV A1 @ LOU-03 | BUSBAR SECTION - LOUTH 110-LOUTH 110-110A1 | 12 | 10 | 10 | Scheduled | 27/02/2023 | 10/03/2023
TO-23-110 kV B1 @ LOU-03 | BUSBAR SECTION - LOUTH 110-LOUTH 110-110B1 | 12 | 10 | 10 | Scheduled | 27/02/2023 | 10/03/2023
TO-23-220 kV A1 @ LOU-02 | BUSBAR SECTION - LOUTH 220-LOUTH 220-220A1 | 12 | 10 | 10 | Scheduled | 27/02/2023 | 10/03/2023
TO-23-220 kV B1 @ LOU-01 | BUSBAR SECTION - LOUTH 220-LOUTH 220-220B1 | 12 | 10 | 10 | Scheduled | 27/02/2023 | 10/03/2023
TO-23-LOU-T2101-03 | TRANSFORMER - LOUTH 220-LOUTH 110-T2101 | 12 | 10 | 10 | Scheduled | 27/02/2023 | 10/03/2023
TO-23-220 kV B1 @ CKM GIS-02 | BUSBAR SECTION - CARRICKMINES GIS 220-CARRICKMINES GIS 220-220B1 | 4 | 4 | 4 | Scheduled | 28/02/2023 | 03/03/2023
TO-23-220 kV B3 @ CKM GIS-02 | BUSBAR SECTION - CARRICKMINES GIS 220-CARRICKMINES GIS 220-220B3 | 4 | 4 | 4 | Scheduled | 28/02/2023 | 03/03/2023
TO-23-CKM GIS-220SB1-3CB-02 | COUPLER/SECTIONALISING CB - CARRICKMINES GIS 220-CARRICKMINES GIS 220-22SB1-3CB | 4 | 4 | 4 | Scheduled | 28/02/2023 | 03/03/2023
TO-23-110 kV A1/A2 @ CAH-01 | BUSBAR SECTION - CAHIR 110-CAHIR 110-110A1-A2 | 1 | 1 | 1 | Scheduled | 01/03/2023 | 01/03/2023
TO-23-110 kV B1/B2 @ CAH-01 | BUSBAR SECTION - CAHIR 110-CAHIR 110-110B1-B2 | 1 | 1 | 1 | Scheduled | 01/03/2023 | 01/03/2023
TO-23-CRO-KBY-1-01 | 110kV FEEDER - COOLROE 110-KILBARRY 110-1 | 1 | 1 | 1 | Scheduled | 01/03/2023 | 01/03/2023
TO-23-KLS-KKY-1-01 | 110kV FEEDER - KELLIS 110-KILKENNY 110-1 | 59 | 40 |  | Scheduled | 01/03/2023 | 28/04/2023
TO-23-KKY-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - KILKENNY 110-KILKENNY 110-110SA1-2CB | 59 | 40 |  | Scheduled | 01/03/2023 | 28/04/2023
TO-23-KKY-T141-01 | DISTRIBUTION TRANSFORMER - KILKENNY 110-KILKENNY 38-T141 | 59 | 40 |  | Reference | 01/03/2023 | 28/04/2023
TO-23-220 kV A1/A2 @ KRA-01 | BUSBAR SECTION - KNOCKRAHA 220-KNOCKRAHA 220-220A1-A2 | 46 | 29 | 29 | Scheduled | 03/03/2023 | 17/04/2023
TO-23-KRA-220K1-04 | COUPLER/SECTIONALISING CB - KNOCKRAHA 220-KNOCKRAHA 220-220K1 | 46 | 29 | 29 | Scheduled | 03/03/2023 | 17/04/2023
TO-23-KRA-220SA2-4CB-02 | COUPLER/SECTIONALISING CB - KNOCKRAHA 220-KNOCKRAHA 220-220SA2-4CB | 46 | 29 | 29 | Scheduled | 03/03/2023 | 17/04/2023
TO-23-CDU-220K1-2-05 | COUPLER/SECTIONALISING CB - CORDUFF 220-CORDUFF 220-220K1-2 | 2 | 0 | 0 | Scheduled | 04/03/2023 | 05/03/2023
TO-23-CDU-220SA2-4-03 | SECTIONALISING DISCONNECT - CORDUFF 220-CORDUFF 220-220SA2-4 | 2 | 0 | 0 | Scheduled | 04/03/2023 | 05/03/2023
TO-23-CDU-220SB2-4-04 | SECTIONALISING DISCONNECT - CORDUFF 220-CORDUFF 220-220SB2-4 | 2 | 0 | 0 | Scheduled | 04/03/2023 | 05/03/2023
TO-23-CDU-FIN-2-05 | 220kV FEEDER - CORDUFF 220-FINGLAS 220-2 | 2 | 0 | 0 | Scheduled | 04/03/2023 | 05/03/2023
TO-23-CDU-T2102-02 | TRANSFORMER - CORDUFF 220-CORDUFF 110-T2102 | 2 | 0 | 0 | Scheduled | 04/03/2023 | 05/03/2023
TO-23-CDU-WOO-1-06 | 220kV FEEDER - CORDUFF 220-WOODLAND 220-1 | 2 | 0 | 0 | Scheduled | 04/03/2023 | 05/03/2023
TO-23-220 kV A2/A4 @ CDU-01 | BUSBAR SECTION - CORDUFF 220-CORDUFF 220-220A2-A4 | 1 | 0 | 0 | Scheduled | 05/03/2023 | 05/03/2023
TO-23-110 kV A2 @ AA GIS-01 | BUSBAR SECTION - ARDNACRUSHA GIS 110-ARDNACRUSHA GIS 110-110A2 | 5 | 5 | 5 | Scheduled | 06/03/2023 | 10/03/2023
TO-23-110 kV B2 @ AA GIS-01 | BUSBAR SECTION - ARDNACRUSHA GIS 110-ARDNACRUSHA GIS 110-110B2 | 5 | 5 | 5 | Scheduled | 06/03/2023 | 10/03/2023
TO-23-AA GIS-SNG-1-01 | 110kV FEEDER - ARDNACRUSHA GIS 110-SINGLAND 110-1 | 5 | 5 | 5 | Scheduled | 06/03/2023 | 10/03/2023
TO-23-110 kV A2 @ ARV-01 | BUSBAR SECTION - ARVA 110-ARVA 110-110A2 | 8 | 6 | 6 | Scheduled | 06/03/2023 | 13/03/2023
TO-23-110 kV B2 @ ARV-01 | BUSBAR SECTION - ARVA 110-ARVA 110-110B2 | 8 | 6 | 6 | Scheduled | 06/03/2023 | 13/03/2023
TO-23-ARV-COS-1-01 | 110kV FEEDER - ARVA 110-CARRICK ON SHANNON 110-1 | 8 | 6 | 6 | Scheduled | 06/03/2023 | 13/03/2023
TO-23-COS-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - CARRICK ON SHANNON 110-CARRICK ON SHANNON 110-110SA1-2CB | 3 | 3 | 3 | Scheduled | 06/03/2023 | 08/03/2023
TO-23-COS-FLA-1-01 | 110kV FEEDER - CARRICK ON SHANNON 110-FLAGFORD 110-1 | 3 | 3 | 3 | Scheduled | 06/03/2023 | 08/03/2023
TO-23-COS-T141-01 | DISTRIBUTION TRANSFORMER - CARRICK ON SHANNON 110-CARRICK ON SHANNON 38-T141 | 3 | 3 | 3 | Reference | 06/03/2023 | 08/03/2023
TO-23-CBR-DLT-1-01 | 110kV FEEDER - CASTLEBAR 110-DALTON 110-1 | 5 | 5 | 5 | Scheduled | 06/03/2023 | 10/03/2023
TO-23-COW-RAF-1-01 | 110kV FEEDER - COW CROSS 110-RAFFEEN 110-1 | 5 | 5 | 5 | Scheduled | 06/03/2023 | 10/03/2023
TO-23-CRA-LWD-1-01 | 110kV FEEDER - CRANE 110-LODGEWOOD 110-1 | 5 | 5 |  | Scheduled | 06/03/2023 | 10/03/2023
TO-23-DND-T123-01 | TSO CUSTOMER TRANSFORMER - DARNDALE 110-DARNDALE 20-T123 | 5 | 5 | 5 | Scheduled | 06/03/2023 | 10/03/2023
TO-23-110 kV A1 @ RAF-01 | BUSBAR SECTION - RAFFEEN 110-RAFFEEN 110-110A1 | 5 | 5 | 5 | Scheduled | 06/03/2023 | 10/03/2023
TO-23-110 kV B1 @ RAF-01 | BUSBAR SECTION - RAFFEEN 110-RAFFEEN 110-110B1 | 5 | 5 | 5 | Scheduled | 06/03/2023 | 10/03/2023
TO-23-110 kV A2 @ SRA-01 | BUSBAR SECTION - SRANANAGH 110-SRANANAGH 110-110A2 | 5 | 5 | 5 | Scheduled | 06/03/2023 | 10/03/2023
TO-23-110 kV B2 @ SRA-01 | BUSBAR SECTION - SRANANAGH 110-SRANANAGH 110-110B2 | 5 | 5 | 5 | Scheduled | 06/03/2023 | 10/03/2023
TO-23-TB-T2003-02 | GENERATOR TRANSFORMER - TARBERT 220-TARBERT G3-T2003 | 3 | 3 | 3 | Proposed | 06/03/2023 | 08/03/2023
TO-23-GOR-220K1-2-02 | COUPLER/SECTIONALISING CB - GORMAN 220-GORMAN 220-220K1-2 | 1 | 1 | 1 | Scheduled | 07/03/2023 | 07/03/2023
TO-23-220 kV A1 @ CDU-01 | BUSBAR SECTION - CORDUFF 220-CORDUFF 220-220A1 | 1 | 1 | 1 | Scheduled | 08/03/2023 | 08/03/2023
TO-23-220 kV A2 @ CDU-02 | BUSBAR SECTION - CORDUFF 220-CORDUFF 220-220A2 | 1 | 1 | 1 | Scheduled | 08/03/2023 | 08/03/2023
TO-23-220 kV A3 @ CDU-01 | BUSBAR SECTION - CORDUFF 220-CORDUFF 220-220A3 | 1 | 1 | 1 | Scheduled | 08/03/2023 | 08/03/2023
TO-23-220 kV A4 @ CDU-03 | BUSBAR SECTION - CORDUFF 220-CORDUFF 220-220A4 | 1 | 1 | 1 | Scheduled | 08/03/2023 | 08/03/2023
TO-23-220 kV B1 @ CDU-01 | BUSBAR SECTION - CORDUFF 220-CORDUFF 220-220B1 | 1 | 1 | 1 | Scheduled | 08/03/2023 | 08/03/2023
TO-23-220 kV B2 @ CDU-02 | BUSBAR SECTION - CORDUFF 220-CORDUFF 220-220B2 | 1 | 1 | 1 | Scheduled | 08/03/2023 | 08/03/2023
TO-23-220 kV B3 @ CDU-01 | BUSBAR SECTION - CORDUFF 220-CORDUFF 220-220B3 | 1 | 1 | 1 | Scheduled | 08/03/2023 | 08/03/2023
TO-23-220 kV B4 @ CDU-03 | BUSBAR SECTION - CORDUFF 220-CORDUFF 220-220B4 | 1 | 1 | 1 | Scheduled | 08/03/2023 | 08/03/2023
TO-23-CDU-220K1-2-02 | COUPLER/SECTIONALISING CB - CORDUFF 220-CORDUFF 220-220K1-2 | 1 | 1 | 1 | Scheduled | 08/03/2023 | 08/03/2023
TO-23-CDU-220K1-3-02 | COUPLER/SECTIONALISING CB - CORDUFF 220-CORDUFF 220-220K1-3 | 1 | 1 | 1 | Scheduled | 08/03/2023 | 08/03/2023
TO-23-CDU-220SA2-4-01 | SECTIONALISING DISCONNECT - CORDUFF 220-CORDUFF 220-220SA2-4 | 1 | 1 | 1 | Scheduled | 08/03/2023 | 08/03/2023
TO-23-CDU-220SB2-4-01 | SECTIONALISING DISCONNECT - CORDUFF 220-CORDUFF 220-220SB2-4 | 1 | 1 | 1 | Scheduled | 08/03/2023 | 08/03/2023
TO-23-110 kV A1/A2 @ KNY-01 | BUSBAR SECTION - KNOCKRANNY 110-KNOCKRANNY 110-110A1-A2 | 1 | 1 | 1 | Scheduled | 08/03/2023 | 08/03/2023
TO-23-110 kV B1/B2 @ KNY-01 | BUSBAR SECTION - KNOCKRANNY 110-KNOCKRANNY 110-110B1-B2 | 1 | 1 | 1 | Scheduled | 08/03/2023 | 08/03/2023
TO-23-BOL-ENN-1-02 | 110kV FEEDER - BOOLTIAGH 110-ENNIS 110-1 | 2 | 2 | 2 | Scheduled | 13/03/2023 | 14/03/2023
TO-23-CHA-KLN-1-02 | 110kV FEEDER - CHARLEVILLE 110-KILLONAN 110-1 | 4 | 4 | 4 | Scheduled | 13/03/2023 | 16/03/2023
TO-23-CBA-110SA1-01 | SECTIONALISING DISCONNECT - CLOGHBOOLA 110-CLOGHBOOLA 110-110SA1 | 4 | 4 | 4 | Scheduled | 13/03/2023 | 16/03/2023
TO-23-CBA-110SA2-01 | SECTIONALISING DISCONNECT - CLOGHBOOLA 110-CLOGHBOOLA 110-110SA2 | 4 | 4 | 4 | Scheduled | 13/03/2023 | 16/03/2023
TO-23-CBA-T122-02 | DISTRIBUTION TRANSFORMER - CLOGHBOOLA 110-CLOGHBOOLA 20-T122 | 4 | 4 | 4 | Reference | 13/03/2023 | 16/03/2023
TO-23-CBA-T131-01 | GENERATOR TRANSFORMER - CLOGHBOOLA 110-CLOGHBOOLA 33-T131 | 4 | 4 | 4 | Scheduled | 13/03/2023 | 16/03/2023
TO-23-CBA-TRI-1-01 | 110kV FEEDER - CLOGHBOOLA 110-TRIEN 110-1 | 4 | 4 | 4 | Scheduled | 13/03/2023 | 16/03/2023
TO-23-220 kV A1 @ CLE-01 | BUSBAR SECTION - CLONEE 220-CLONEE 220-220A1 | 4 | 4 | 4 | Proposed | 13/03/2023 | 16/03/2023
TO-23-220 kV A2 @ CLE-01 | BUSBAR SECTION - CLONEE 220-CLONEE 220-220A2 | 4 | 4 | 4 | Proposed | 13/03/2023 | 16/03/2023
TO-23-CLE-220K1-01 | COUPLER/SECTIONALISING CB - CLONEE 220-CLONEE 220-220K1 | 4 | 4 | 4 | Proposed | 13/03/2023 | 16/03/2023
TO-23-CLE-220K2-01 | COUPLER/SECTIONALISING CB - CLONEE 220-CLONEE 220-220K2 | 4 | 4 | 4 | Proposed | 13/03/2023 | 16/03/2023
TO-23-CLE-220SA1-2CB-01 | COUPLER/SECTIONALISING CB - CLONEE 220-CLONEE 220-220SA1-2CB | 4 | 4 | 4 | Proposed | 13/03/2023 | 16/03/2023
TO-23-CLE-WOO-1-03 | 220kV FEEDER - CLONEE 220-WOODLAND 220-1 | 4 | 4 | 4 | Proposed | 13/03/2023 | 16/03/2023
TO-23-CDU-MUL-1-02 | 110kV FEEDER - CORDUFF 110-MULLINGAR 110-1 | 165 | 113 | 113 | Scheduled | 13/03/2023 | 24/08/2023
TO-23-CUS-MLC-1-01 | 110kV FEEDER - CUSHALING 110-MOUNTLUCAS 110-1 | 12 | 9 | 9 | Scheduled | 13/03/2023 | 24/03/2023
TO-23-DSN-TH-1-03 | 220kV FEEDER - DUNSTOWN 220-TURLOUGH HILL 220-1 | 4 | 4 | 4 | Scheduled | 13/03/2023 | 16/03/2023
TO-23-LIS-T141-01 | DISTRIBUTION TRANSFORMER - LISDRUM 110-LISDRUM 38-T141 | 130 | 89 | 89 | Reference | 13/03/2023 | 20/07/2023
TO-23-PRO-TB-1-02 | 220kV FEEDER - PROSPECT 220-TARBERT 220-1 | 80 | 54 | 54 | Scheduled | 13/03/2023 | 31/05/2023
TO-23-BIN-TIV-1-01 | 110kV FEEDER - BINBANE 110-TIEVEBRACK 110-1 | 2 | 2 | 2 | Scheduled | 14/03/2023 | 15/03/2023
TO-23-CLN-LA-1-03 | 110kV FEEDER - CLOON 110-LANESBORO 110-1 | 8 | 5 | 5 | Scheduled | 14/03/2023 | 21/03/2023
TO-23-GOR-NAV-1-02 | 110kV FEEDER - GORMAN 110-NAVAN 110-1 | 1 | 1 | 1 | Scheduled | 14/03/2023 | 14/03/2023
TO-23-LOU-AT2-04 | TRANSFORMER - LOUTH 220-LOUTH 275-AT2 | 8 | 5 | 5 | Scheduled | 19/03/2023 | 26/03/2023
TO-23-LOU-TAN-2-04 | 275kV FEEDER - LOUTH 275-TANDRAGEE 275-2 | 8 | 5 | 5 | Scheduled | 19/03/2023 | 26/03/2023
TO-23-AUG-MTN-1-01 | 110kV FEEDER - AUGHINISH 110-MONETEEN 110-1 | 1 | 1 | 1 | Scheduled | 20/03/2023 | 20/03/2023
TO-23-AUG-SK-4-01 | 110kV FEEDER - AUGHINISH 110-SEALROCK 110-4 | 10 | 8 | 8 | Scheduled | 20/03/2023 | 29/03/2023
TO-23-BOG-110SA1-01 | SECTIONALISING DISCONNECT - BANOGE 110-BANOGE 110-110SA1 | 5 | 5 | 5 | Scheduled | 20/03/2023 | 24/03/2023
TO-23-BOG-110SA2-02 | SECTIONALISING DISCONNECT - BANOGE 110-BANOGE 110-110SA2 | 5 | 5 | 5 | Scheduled | 20/03/2023 | 24/03/2023
TO-23-BOG-CRA-1-02 | 110kV FEEDER - BANOGE 110-CRANE 110-1 | 5 | 5 | 5 | Scheduled | 20/03/2023 | 24/03/2023
TO-23-BOG-T121-01 | DISTRIBUTION TRANSFORMER - BANOGE 110-BANOGE 20-T121 | 5 | 5 | 5 | Reference | 20/03/2023 | 24/03/2023
TO-23-220 kV A2 @ CKM GIS-03 | BUSBAR SECTION - CARRICKMINES GIS 220-CARRICKMINES GIS 220-220A2 | 12 | 10 | 10 | Scheduled | 20/03/2023 | 31/03/2023
TO-23-220 kV B2 @ CKM GIS-03 | BUSBAR SECTION - CARRICKMINES GIS 220-CARRICKMINES GIS 220-220B2 | 12 | 10 | 10 | Scheduled | 20/03/2023 | 31/03/2023
TO-23-CKM GIS-220SA1-2CB-03 | COUPLER/SECTIONALISING CB - CARRICKMINES GIS 220-CARRICKMINES GIS 220-22SA1-2CB | 12 | 10 | 10 | Scheduled | 20/03/2023 | 31/03/2023
TO-23-CKM GIS-220SA2-4CB-03 | COUPLER/SECTIONALISING CB - CARRICKMINES GIS 220-CARRICKMINES GIS 220-22SA2-4CB | 12 | 10 | 10 | Scheduled | 20/03/2023 | 31/03/2023
TO-23-CKM GIS-220SB1-2CB-03 | COUPLER/SECTIONALISING CB - CARRICKMINES GIS 220-CARRICKMINES GIS 220-22SB1-2CB | 12 | 10 | 10 | Scheduled | 20/03/2023 | 31/03/2023
TO-23-CKM GIS-220SB2-4CB-03 | COUPLER/SECTIONALISING CB - CARRICKMINES GIS 220-CARRICKMINES GIS 220-22SB2-4CB | 12 | 10 | 10 | Scheduled | 20/03/2023 | 31/03/2023
TO-23-CKM GIS-ISH-1-01 | 220kV FEEDER - CARRICKMINES GIS 220-IRISHTOWN 220-1 | 12 | 10 | 10 | Scheduled | 20/03/2023 | 31/03/2023
TO-23-CLH-TRL-1-01 | 110kV FEEDER - CLAHANE 110-TRALEE 110-1 | 5 | 5 | 5 | Scheduled | 20/03/2023 | 24/03/2023
TO-23-GOL-T101-01 | GENERATOR TRANSFORMER - GOLAGH 110-GOLAGH 10-T101 | 5 | 5 | 5 | Scheduled | 20/03/2023 | 24/03/2023
TO-23-GOL,T-CLO-1-01 | 110kV FEEDER - GOLAGH tee-CLOGHER 110-1 | 5 | 5 | 5 | Scheduled | 20/03/2023 | 24/03/2023
TO-23-GOL,T-GOL-1-01 | 110kV FEEDER - GOLAGH tee-GOLAGH 110-1 | 5 | 5 | 5 | Scheduled | 20/03/2023 | 24/03/2023
TO-23-GOL,T-LET-1-01 | 110kV FEEDER - GOLAGH tee-LETTERKENNY 110-1 | 5 | 5 | 5 | Scheduled | 20/03/2023 | 24/03/2023
TO-23-KPG-TRL-1-01 | 110kV FEEDER - KILPADDOGE 110-TRALEE 110-1 | 5 | 5 | 5 | Scheduled | 20/03/2023 | 24/03/2023
TO-23-110 kV A2 @ RAF-02 | BUSBAR SECTION - RAFFEEN 110-RAFFEEN 110-110A2 | 18 | 14 | 14 | Scheduled | 20/03/2023 | 06/04/2023
TO-23-110 kV B2 @ RAF-02 | BUSBAR SECTION - RAFFEEN 110-RAFFEEN 110-110B2 | 18 | 14 | 14 | Scheduled | 20/03/2023 | 06/04/2023
TO-23-RAF-TBG-2-01 | 110kV FEEDER - RAFFEEN 110-TRABEG 110-2 | 18 | 14 | 14 | Scheduled | 20/03/2023 | 06/04/2023
TO-23-REM-110SA1-01 | SECTIONALISING DISCONNECT - REAMORE 110-REAMORE 110-110SA1 | 5 | 5 | 5 | Scheduled | 20/03/2023 | 24/03/2023
TO-23-REM-110SA2-01 | SECTIONALISING DISCONNECT - REAMORE 110-REAMORE 110-110SA2 | 5 | 5 | 5 | Scheduled | 20/03/2023 | 24/03/2023
TO-23-REM-T141-01 | DISTRIBUTION TRANSFORMER - REAMORE 110-REAMORE 38-T141 | 5 | 5 | 5 | Reference | 20/03/2023 | 24/03/2023
TO-23-REM-T142-01 | DISTRIBUTION TRANSFORMER - REAMORE 110-REAMORE 38-T142 | 5 | 5 | 5 | Reference | 20/03/2023 | 24/03/2023
TO-23-REM-TRL-1-01 | 110kV FEEDER - REAMORE 110-TRALEE 110-1 | 5 | 5 | 5 | Scheduled | 20/03/2023 | 24/03/2023
TO-23-SK-T104-01 | GENERATOR TRANSFORMER - SEALROCK 110-SEALROCK G4-T104 | 26 | 18 | 18 | Scheduled | 20/03/2023 | 14/04/2023
TO-23-SLI-SRA-2-01 | 110kV FEEDER - SLIGO 110-SRANANAGH 110-2 | 5 | 5 | 5 | Scheduled | 20/03/2023 | 24/03/2023
TO-23-TRL-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - TRALEE 110-TRALEE 110-110SA1-2CB | 5 | 5 | 5 | Scheduled | 20/03/2023 | 24/03/2023
TO-23-TRL-T141-01 | DISTRIBUTION TRANSFORMER - TRALEE 110-TRALEE 38-T141 | 5 | 5 | 5 | Reference | 20/03/2023 | 24/03/2023
TO-23-COR-GWE-1-03 | 110kV FEEDER - CORRACLASSY 110-GORTAWEE 110-1 | 3 | 3 | 3 | Scheduled | 21/03/2023 | 23/03/2023
TO-23-CUL-WAT-1-02 | 110kV FEEDER - CULLENAGH 110-WATERFORD 110-1 | 3 | 3 | 3 | Scheduled | 21/03/2023 | 23/03/2023
TO-23-110 kV A2 @ CBT-03 | BUSBAR SECTION - CASTLEBAGOT 110-CASTLEBAGOT 110-110A2 | 2 | 2 | 2 | Scheduled | 23/03/2023 | 24/03/2023
TO-23-110 kV B2 @ CBT-01 | BUSBAR SECTION - CASTLEBAGOT 110-CASTLEBAGOT 110-110B2 | 2 | 2 | 2 | Scheduled | 23/03/2023 | 24/03/2023
TO-23-CBT-110SA1-2CB-03 | COUPLER/SECTIONALISING CB - CASTLEBAGOT 110-CASTLEBAGOT 110-110SA1-2CB | 2 | 2 | 2 | Scheduled | 23/03/2023 | 24/03/2023
TO-23-CBT-110SA2-4CB-03 | COUPLER/SECTIONALISING CB - CASTLEBAGOT 110-CASTLEBAGOT 110-110SA2-4CB | 2 | 2 | 2 | Scheduled | 23/03/2023 | 24/03/2023
TO-23-CBT-110SB1-2CB-04 | COUPLER/SECTIONALISING CB - CASTLEBAGOT 110-CASTLEBAGOT 110-110SB1-2CB | 2 | 2 | 2 | Scheduled | 23/03/2023 | 24/03/2023
TO-23-CBT-110SB2-4CB-03 | COUPLER/SECTIONALISING CB - CASTLEBAGOT 110-CASTLEBAGOT 110-110SB2-4CB | 2 | 2 | 2 | Scheduled | 23/03/2023 | 24/03/2023
TO-23-220 kV A2 @ CBT-01 | BUSBAR SECTION - CASTLEBAGOT 220-CASTLEBAGOT 220-220A2 | 2 | 2 | 2 | Scheduled | 23/03/2023 | 24/03/2023
TO-23-220 kV B2 @ CBT-01 | BUSBAR SECTION - CASTLEBAGOT 220-CASTLEBAGOT 220-220B2 | 2 | 2 | 2 | Scheduled | 23/03/2023 | 24/03/2023
TO-23-CBT-220K2-01 | COUPLER/SECTIONALISING CB - CASTLEBAGOT 220-CASTLEBAGOT 220-220K2 | 2 | 2 | 2 | Scheduled | 23/03/2023 | 24/03/2023
TO-23-CBT-220SA1-2CB-01 | COUPLER/SECTIONALISING CB - CASTLEBAGOT 220-CASTLEBAGOT 220-220SA1-2CB | 2 | 2 | 2 | Scheduled | 23/03/2023 | 24/03/2023
TO-23-CBT-220SB1-2CB-01 | COUPLER/SECTIONALISING CB - CASTLEBAGOT 220-CASTLEBAGOT 220-220SB1-2CB | 2 | 2 | 2 | Scheduled | 23/03/2023 | 24/03/2023
TO-23-CBT-T2102-02 | TRANSFORMER - CASTLEBAGOT 220-CASTLEBAGOT 110-T2102 | 2 | 2 | 2 | Scheduled | 23/03/2023 | 24/03/2023
TO-23-110 kV A4 @ CDU-02 | BUSBAR SECTION - CORDUFF 110-CORDUFF 110-110A4 | 54 | 35 | 35 | Scheduled | 23/03/2023 | 15/05/2023
TO-23-110 kV B4 @ CDU-02 | BUSBAR SECTION - CORDUFF 110-CORDUFF 110-110B4 | 54 | 35 | 35 | Scheduled | 23/03/2023 | 15/05/2023
TO-23-110 kV A2 @ KNY-01 | BUSBAR SECTION - KNOCKRANNY 110-KNOCKRANNY 110-110A2 | 8 | 6 | 6 | Scheduled | 23/03/2023 | 30/03/2023
TO-23-110 kV B2 @ KNY-01 | BUSBAR SECTION - KNOCKRANNY 110-KNOCKRANNY 110-110B2 | 8 | 6 | 6 | Scheduled | 23/03/2023 | 30/03/2023
TO-23-KNY-110K2-01 | COUPLER/SECTIONALISING CB - KNOCKRANNY 110-KNOCKRANNY 110-110K2 | 8 | 6 | 6 | Scheduled | 23/03/2023 | 30/03/2023
TO-23-KNY-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - KNOCKRANNY 110-KNOCKRANNY 110-110SA1-2CB | 8 | 6 | 6 | Scheduled | 23/03/2023 | 30/03/2023
TO-23-KNY-110SB1-2CB-01 | COUPLER/SECTIONALISING CB - KNOCKRANNY 110-KNOCKRANNY 110-110SB1-2CB | 8 | 6 | 6 | Scheduled | 23/03/2023 | 30/03/2023
TO-23-FIN-HN-1-01 | 220kV FEEDER - FINGLAS 220-HUNTSTOWN 220-1 | 14 | 9 | 9 | Scheduled | 25/03/2023 | 07/04/2023
TO-23-HN-T2010/11-01 | GENERATOR TRANSFORMER - HUNTSTOWN 220-HUNTSTOWN G10/11-T2010/11 | 14 | 9 | 9 | Scheduled | 25/03/2023 | 07/04/2023
TO-23-110 kV A1 @ CLA-01 | BUSBAR SECTION - CLASHAVOON 110-CLASHAVOON 110-110A1 | 5 | 5 | 5 | Scheduled | 27/03/2023 | 31/03/2023
TO-23-110 kV B1 @ CLA-01 | BUSBAR SECTION - CLASHAVOON 110-CLASHAVOON 110-110B1 | 5 | 5 | 5 | Scheduled | 27/03/2023 | 31/03/2023
TO-23-CLA-MAC-1-03 | 110kV FEEDER - CLASHAVOON 110-MACROOM 110-1 | 5 | 5 | 5 | Scheduled | 27/03/2023 | 31/03/2023
TO-23-COR-PST-01 | TRANSFORMER - CORRACLASSY 110-ENNISKILLEN 110-PST | 40 | 27 | 27 | Scheduled | 27/03/2023 | 05/05/2023
TO-23-110 kV A2 @ GI-02 | BUSBAR SECTION - GREAT ISLAND 110-GREAT ISLAND 110-110A2 | 5 | 5 | 5 | Scheduled | 27/03/2023 | 31/03/2023
TO-23-110 kV B2 @ GI-02 | BUSBAR SECTION - GREAT ISLAND 110-GREAT ISLAND 110-110B2 | 5 | 5 | 5 | Scheduled | 27/03/2023 | 31/03/2023
TO-23-GI-ROP-1-01 | 110kV FEEDER - GREAT ISLAND 110-ROSSPILE 110-1 | 5 | 5 | 5 | Scheduled | 27/03/2023 | 31/03/2023
TO-23-KTN-WAT-1-01 | 110kV FEEDER - KILLOTERAN 110-WATERFORD 110-1 | 5 | 5 |  | Scheduled | 27/03/2023 | 31/03/2023
TO-23-KPG-T2101-01 | TRANSFORMER - KILPADDOGE 220-KILPADDOGE 110-T2101 | 5 | 5 |  | Scheduled | 27/03/2023 | 31/03/2023
TO-23-KTL-MAY-1-01 | 110kV FEEDER - KILTEEL 110-MAYNOOTH 110-1 | 26 | 18 |  | Scheduled | 27/03/2023 | 21/04/2023
TO-23-LET-TIV-1-01 | 110kV FEEDER - LETTERKENNY 110-TIEVEBRACK 110-1 | 130 | 90 | 90 | Scheduled | 27/03/2023 | 03/08/2023
TO-23-LIS-LOU-1-04 | 110kV FEEDER - LISDRUM 110-LOUTH 110-1 | 5 | 5 | 5 | Scheduled | 27/03/2023 | 31/03/2023
TO-23-220 kV B1/B2 @ LOU-02 | BUSBAR SECTION - LOUTH 220-LOUTH 220-220B1-B2 | 19 | 13 | 13 | Scheduled | 27/03/2023 | 14/04/2023
TO-23-LOU-220K1-2-01 | COUPLER/SECTIONALISING CB - LOUTH 220-LOUTH 220-220K1-2 | 28 | 18 | 18 | Scheduled | 27/03/2023 | 23/04/2023
TO-23-110 kV A1 @ MAY-01 | BUSBAR SECTION - MAYNOOTH 110-MAYNOOTH 110-110A1 | 26 | 18 | 18 | Scheduled | 27/03/2023 | 21/04/2023
TO-23-110 kV B1 @ MAY-01 | BUSBAR SECTION - MAYNOOTH 110-MAYNOOTH 110-110B1 | 26 | 18 | 18 | Scheduled | 27/03/2023 | 21/04/2023
TO-23-AGL-ENN-1-01 | 110kV FEEDER - AGANNYGAL 110-ENNIS 110-1 | 3 | 3 | 3 | Scheduled | 28/03/2023 | 30/03/2023
TO-23-220 kV A1/A2 @ ARK-01 | BUSBAR SECTION - ARKLOW 220-ARKLOW 220-220A1-A2 | 1 | 1 | 1 | Scheduled | 29/03/2023 | 29/03/2023
TO-23-220 kV B1/B2 @ ARK-01 | BUSBAR SECTION - ARKLOW 220-ARKLOW 220-220B1-B2 | 1 | 1 | 1 | Scheduled | 29/03/2023 | 29/03/2023
TO-23-FIN-220K2-01 | COUPLER/SECTIONALISING CB - FINGLAS 220-FINGLAS 220-220K2 | 15 | 9 | 9 | Scheduled | 29/03/2023 | 12/04/2023
TO-23-FIN-220SA1-2CB-01 | COUPLER/SECTIONALISING CB - FINGLAS 220-FINGLAS 220-220SA1-2CB | 15 | 9 | 9 | Scheduled | 29/03/2023 | 12/04/2023
TO-23-FIN-220SB1-2CB-03 | COUPLER/SECTIONALISING CB - FINGLAS 220-FINGLAS 220-220SB1-2CB | 15 | 9 | 9 | Scheduled | 29/03/2023 | 12/04/2023
TO-23-110 kV A1 @ FLA-01 | BUSBAR SECTION - FLAGFORD 110-FLAGFORD 110-110A1 | 2 | 2 | 2 | Scheduled | 29/03/2023 | 30/03/2023
TO-23-110 kV B1 @ FLA-01 | BUSBAR SECTION - FLAGFORD 110-FLAGFORD 110-110B1 | 2 | 2 | 2 | Scheduled | 29/03/2023 | 30/03/2023
TO-23-220 kV B1 @ FLA-02 | BUSBAR SECTION - FLAGFORD 220-FLAGFORD 220-220B1 | 2 | 2 | 2 | Scheduled | 29/03/2023 | 30/03/2023
TO-23-FLA-T2101-01 | TRANSFORMER - FLAGFORD 220-FLAGFORD 110-T2101 | 109 | 74 |  | Scheduled | 29/03/2023 | 15/07/2023
TO-23-110 kV A1 @ SH-03 | BUSBAR SECTION - SHANNONBRIDGE 110-SHANNONBRIDGE 110-110A1 | 125 | 85 | 85 | Scheduled | 29/03/2023 | 31/07/2023
TO-23-110 kV A1 @ SH-05 | BUSBAR SECTION - SHANNONBRIDGE 110-SHANNONBRIDGE 110-110A1 | 262 | 182 | 182 | Scheduled | 29/03/2023 | 15/12/2023
TO-23-110 kV A2 @ SH-03 | BUSBAR SECTION - SHANNONBRIDGE 110-SHANNONBRIDGE 110-110A2 | 262 | 182 | 182 | Scheduled | 29/03/2023 | 15/12/2023
TO-23-110 kV A2 @ SH-04 | BUSBAR SECTION - SHANNONBRIDGE 110-SHANNONBRIDGE 110-110A2 | 125 | 85 | 85 | Scheduled | 29/03/2023 | 31/07/2023
TO-23-110 kV B1 @ SH-02 | BUSBAR SECTION - SHANNONBRIDGE 110-SHANNONBRIDGE 110-110B1 | 262 | 182 | 182 | Scheduled | 29/03/2023 | 15/12/2023
TO-23-110 kV B1 @ SH-07 | BUSBAR SECTION - SHANNONBRIDGE 110-SHANNONBRIDGE 110-110B1 | 125 | 85 | 85 | Scheduled | 29/03/2023 | 31/07/2023
TO-23-110 kV B2 @ SH-02 | BUSBAR SECTION - SHANNONBRIDGE 110-SHANNONBRIDGE 110-110B2 | 262 | 182 | 182 | Scheduled | 29/03/2023 | 15/12/2023
TO-23-110 kV B2 @ SH-03 | BUSBAR SECTION - SHANNONBRIDGE 110-SHANNONBRIDGE 110-110B2 | 125 | 85 | 85 | Scheduled | 29/03/2023 | 31/07/2023
TO-23-SH-T104-02 | GENERATOR TRANSFORMER - SHANNONBRIDGE 110-SHANNONBRIDGE G4-T104 | 7 | 5 | 5 | Scheduled | 29/03/2023 | 04/04/2023
TO-23-CUN-SLI-1-01 | 110kV FEEDER - CUNGHILL 110-SLIGO 110-1 | 1 | 1 | 1 | Scheduled | 31/03/2023 | 31/03/2023
TO-23-FLA-SLI-1-03 | 110kV FEEDER - FLAGFORD 110-SLIGO 110-1 | 1 | 1 | 1 | Scheduled | 31/03/2023 | 31/03/2023
TO-23-SLI-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - SLIGO 110-SLIGO 110-110SA1-2CB | 1 | 1 | 1 | Scheduled | 31/03/2023 | 31/03/2023
TO-23-SLI-SRA-2-02 | 110kV FEEDER - SLIGO 110-SRANANAGH 110-2 | 1 | 1 | 1 | Scheduled | 31/03/2023 | 31/03/2023
TO-23-BVK-110SA1-2CB-04 | COUPLER/SECTIONALISING CB - BALLYVOUSKILL 110-BALLYVOUSKILL 110-110SA1-2CB | 1 | 1 | 1 | Scheduled | 03/04/2023 | 03/04/2023
TO-23-110 kV A1 @ CBT-03 | BUSBAR SECTION - CASTLEBAGOT 110-CASTLEBAGOT 110-110A1 | 4 | 4 | 4 | Scheduled | 03/04/2023 | 06/04/2023
TO-23-110 kV B1 @ CBT-02 | BUSBAR SECTION - CASTLEBAGOT 110-CASTLEBAGOT 110-110B1 | 4 | 4 | 4 | Scheduled | 03/04/2023 | 06/04/2023
TO-23-CBT-110K1-01 | COUPLER/SECTIONALISING CB - CASTLEBAGOT 110-CASTLEBAGOT 110-110K1 | 4 | 4 | 4 | Scheduled | 03/04/2023 | 06/04/2023
TO-23-CBT-110SA1-2CB-06 | COUPLER/SECTIONALISING CB - CASTLEBAGOT 110-CASTLEBAGOT 110-110SA1-2CB | 4 | 4 | 4 | Scheduled | 03/04/2023 | 06/04/2023
TO-23-CBT-110SB1-2CB-05 | COUPLER/SECTIONALISING CB - CASTLEBAGOT 110-CASTLEBAGOT 110-110SB1-2CB | 4 | 4 | 4 | Scheduled | 03/04/2023 | 06/04/2023
TO-23-CLA-MAC-2-01 | 110kV FEEDER - CLASHAVOON 110-MACROOM 110-2 | 9 | 5 | 5 | Scheduled | 03/04/2023 | 11/04/2023
TO-23-GI-WAT-2-01 | 110kV FEEDER - GREAT ISLAND 110-WATERFORD 110-2 | 4 | 4 | 4 | Scheduled | 03/04/2023 | 06/04/2023
TO-23-KTN-WAT-1-04 | 110kV FEEDER - KILLOTERAN 110-WATERFORD 110-1 | 4 | 4 | 4 | Scheduled | 03/04/2023 | 06/04/2023
TO-23-KPG-T2102-01 | TRANSFORMER - KILPADDOGE 220-KILPADDOGE 110-T2102 | 4 | 4 | 4 | Scheduled | 03/04/2023 | 06/04/2023
TO-23-LIM-RAT-1-01 | 110kV FEEDER - LIMERICK 110-RATHKEALE 110-1 | 4 | 4 | 4 | Scheduled | 03/04/2023 | 06/04/2023
TO-23-110 kV A3 @ RYB GIS-01 | BUSBAR SECTION - RYEBROOK GIS 110-RYEBROOK GIS 110-110A3 | 4 | 4 | 4 | Scheduled | 03/04/2023 | 06/04/2023
TO-23-110 kV B3 @ RYB GIS-01 | BUSBAR SECTION - RYEBROOK GIS 110-RYEBROOK GIS 110-110B3 | 4 | 4 | 4 | Scheduled | 03/04/2023 | 06/04/2023
TO-23-RYB GIS-110K3-01 | COUPLER/SECTIONALISING CB - RYEBROOK GIS 110-RYEBROOK GIS 110-110K3 | 4 | 4 | 4 | Scheduled | 03/04/2023 | 06/04/2023
TO-23-RYB GIS-110SA1-3CB-02 | COUPLER/SECTIONALISING CB - RYEBROOK GIS 110-RYEBROOK GIS 110-110SA1-3CB | 4 | 4 | 4 | Scheduled | 03/04/2023 | 06/04/2023
TO-23-RYB GIS-110SB1-3CB-04 | COUPLER/SECTIONALISING CB - RYEBROOK GIS 110-RYEBROOK GIS 110-110SB1-3CB | 4 | 4 | 4 | Scheduled | 03/04/2023 | 06/04/2023
TO-23-WAT-110SA1-01 | SECTIONALISING DISCONNECT - WATERFORD 110-WATERFORD 110-110SA1 | 4 | 4 |  | Scheduled | 03/04/2023 | 06/04/2023
TO-23-WAT-110SA2-01 | SECTIONALISING DISCONNECT - WATERFORD 110-WATERFORD 110-110SA2 | 4 | 4 | 4 | Scheduled | 03/04/2023 | 06/04/2023
TO-23-WAT-T141-02 | DISTRIBUTION TRANSFORMER - WATERFORD 110-WATERFORD 38-T141 | 4 | 4 | 4 | Reference | 03/04/2023 | 06/04/2023
TO-23-ARK-T2101-01 | TRANSFORMER - ARKLOW 220-ARKLOW 110-T2101 | 2 | 2 |  | Scheduled | 04/04/2023 | 05/04/2023
TO-23-CLE-220SA1-2CB-03 | COUPLER/SECTIONALISING CB - CLONEE 220-CLONEE 220-220SA1-2CB | 1 | 1 | 1 | Scheduled | 04/04/2023 | 04/04/2023
TO-23-CLE-220SB1-2CB-02 | COUPLER/SECTIONALISING CB - CLONEE 220-CLONEE 220-220SB1-2CB | 1 | 1 | 1 | Scheduled | 05/04/2023 | 05/04/2023
TO-23-INC-ISH-1-01 | 220kV FEEDER - INCHICORE 220-IRISHTOWN 220-1 | 16 | 10 |  | Scheduled | 06/04/2023 | 21/04/2023
TO-23-ISH-220K1-2-01 | COUPLER/SECTIONALISING CB - IRISHTOWN 220-IRISHTOWN 220-220K1-2 | 16 | 10 |  | Scheduled | 06/04/2023 | 21/04/2023
TO-23-ISH-SHL-1-01 | 220kV FEEDER - IRISHTOWN 220-SHELLYBANKS 220-1 | 16 | 10 |  | Scheduled | 06/04/2023 | 21/04/2023
TO-23-CVW-KRA-1-01 | 110kV FEEDER - CASTLEVIEW 110-KNOCKRAHA 110-1 | 3 | 3 | 3 | Scheduled | 11/04/2023 | 13/04/2023
TO-23-KLN-KPG-1-01 | 220kV FEEDER - KILLONAN 220-KILPADDOGE 220-1 | 4 | 4 |  | Scheduled | 11/04/2023 | 14/04/2023
TO-23-220 kV A4 @ KPG-03 | BUSBAR SECTION - KILPADDOGE 220-KILPADDOGE 220-220A4 | 4 | 4 | 4 | Scheduled | 11/04/2023 | 14/04/2023
TO-23-220 kV B4 @ KPG-03 | BUSBAR SECTION - KILPADDOGE 220-KILPADDOGE 220-220B4 | 4 | 4 | 4 | Scheduled | 11/04/2023 | 14/04/2023
TO-23-KPG-220K4-02 | COUPLER/SECTIONALISING CB - KILPADDOGE 220-KILPADDOGE 220-220K4 | 4 | 4 | 4 | Scheduled | 11/04/2023 | 14/04/2023
TO-23-KPG-220SA2-4CB-02 | COUPLER/SECTIONALISING CB - KILPADDOGE 220-KILPADDOGE 220-220SA2-4CB | 4 | 4 | 4 | Scheduled | 11/04/2023 | 14/04/2023
TO-23-KPG-220SB2-4CB-03 | COUPLER/SECTIONALISING CB - KILPADDOGE 220-KILPADDOGE 220-220SB2-4CB | 4 | 4 | 4 | Scheduled | 11/04/2023 | 14/04/2023
TO-23-LWD-T2102-01 | TRANSFORMER - LODGEWOOD 220-LODGEWOOD 110-T2102 | 11 | 9 | 9 | Scheduled | 11/04/2023 | 21/04/2023
TO-23-220 kV A1 @ TH-01 | BUSBAR SECTION - TURLOUGH HILL 220-TURLOUGH HILL 220-220A1 | 4 | 4 | 4 | Scheduled | 11/04/2023 | 14/04/2023
TO-23-220 kV A2 @ TH-01 | BUSBAR SECTION - TURLOUGH HILL 220-TURLOUGH HILL 220-220A2 | 4 | 4 | 4 | Scheduled | 11/04/2023 | 14/04/2023
TO-23-220 kV B1 @ TH-01 | BUSBAR SECTION - TURLOUGH HILL 220-TURLOUGH HILL 220-220B1 | 4 | 4 | 4 | Scheduled | 11/04/2023 | 14/04/2023
TO-23-220 kV B2 @ TH-01 | BUSBAR SECTION - TURLOUGH HILL 220-TURLOUGH HILL 220-220B2 | 4 | 4 | 4 | Scheduled | 11/04/2023 | 14/04/2023
TO-23-TH-220K1-2-01 | COUPLER/SECTIONALISING CB - TURLOUGH HILL 220-TURLOUGH HILL 220-220K1-2 | 4 | 4 | 4 | Scheduled | 11/04/2023 | 14/04/2023
TO-23-KLN-T2104-01 | TRANSFORMER - KILLONAN 220-KILLONAN 110-T2104 | 7 | 5 | 5 | Scheduled | 12/04/2023 | 18/04/2023
TO-23-FLA-LOU-1-08 | 220kV FEEDER - FLAGFORD 220-LOUTH 220-1 | 2 | 0 | 0 | Scheduled | 15/04/2023 | 16/04/2023
TO-23-GOR-LOU-1-02 | 220kV FEEDER - GORMAN 220-LOUTH 220-1 | 2 | 0 | 0 | Scheduled | 15/04/2023 | 16/04/2023
TO-23-LOU-AT1-02 | TRANSFORMER - LOUTH 220-LOUTH 275-AT1 | 2 | 0 | 0 | Scheduled | 15/04/2023 | 16/04/2023
TO-23-LOU-AT3-02 | TRANSFORMER - LOUTH 220-LOUTH 275-AT3 | 2 | 0 | 0 | Scheduled | 15/04/2023 | 16/04/2023
TO-23-LOU-T2102-06 | TRANSFORMER - LOUTH 220-LOUTH 110-T2102 | 2 | 0 | 0 | Scheduled | 15/04/2023 | 16/04/2023
TO-23-LOU-T2104-04 | TRANSFORMER - LOUTH 220-LOUTH 110-T2104 | 2 | 0 | 0 | Scheduled | 15/04/2023 | 16/04/2023
TO-23-LOU-TAN-1-01 | 275kV FEEDER - LOUTH 275-TANDRAGEE 275-1 | 2 | 0 | 0 | Scheduled | 15/04/2023 | 16/04/2023
TO-23-CBT-110K1-05 | COUPLER/SECTIONALISING CB - CASTLEBAGOT 110-CASTLEBAGOT 110-110K1 | 5 | 5 | 5 | Scheduled | 17/04/2023 | 21/04/2023
TO-23-CBT-110SA2-4CB-06 | COUPLER/SECTIONALISING CB - CASTLEBAGOT 110-CASTLEBAGOT 110-110SA2-4CB | 5 | 5 | 5 | Scheduled | 17/04/2023 | 21/04/2023
TO-23-CBR-SVC-01 | CAPACITOR/SVC/REACTOR - CASTLEBAR 110-CASTLEBAR 110-SVC | 5 | 5 | 5 | Scheduled | 17/04/2023 | 21/04/2023
TO-23-CL-T102-01 | GENERATOR TRANSFORMER - CLIFF 110-CLIFF G2-T102 | 19 | 14 | 14 | Scheduled | 17/04/2023 | 05/05/2023
TO-23-CDU-RYB GIS-1-02 | 110kV FEEDER - CORDUFF 110-RYEBROOK GIS 110-1 | 47 | 34 |  | Scheduled | 17/04/2023 | 02/06/2023
TO-23-DRU-ENN-1-04 | 110kV FEEDER - DRUMLINE 110-ENNIS 110-1 | 5 | 5 | 5 | Scheduled | 17/04/2023 | 21/04/2023
TO-23-110 kV A2 @ GOR-01 | BUSBAR SECTION - GORMAN 110-GORMAN 110-110A2 | 5 | 5 | 5 | Scheduled | 17/04/2023 | 21/04/2023
TO-23-110 kV B2 @ GOR-01 | BUSBAR SECTION - GORMAN 110-GORMAN 110-110B2 | 5 | 5 | 5 | Scheduled | 17/04/2023 | 21/04/2023
TO-23-KPG-TRL-2-01 | 110kV FEEDER - KILPADDOGE 110-TRALEE 110-2 | 5 | 5 |  | Scheduled | 17/04/2023 | 21/04/2023
TO-23-MP GIS-T4201-02 | TRANSFORMER - MONEYPOINT GIS 400-MONEYPOINT GIS 220-T4201 | 5 | 5 | 5 | Scheduled | 17/04/2023 | 21/04/2023
TO-23-110 kV B1 @ RYB GIS-02 | BUSBAR SECTION - RYEBROOK GIS 110-RYEBROOK GIS 110-110B1 | 5 | 5 | 5 | Scheduled | 17/04/2023 | 21/04/2023
TO-23-110 kV B2 @ RYB GIS-01 | BUSBAR SECTION - RYEBROOK GIS 110-RYEBROOK GIS 110-110B2 | 5 | 5 | 5 | Scheduled | 17/04/2023 | 21/04/2023
TO-23-RYB GIS-110SB1-2CB-01 | COUPLER/SECTIONALISING CB - RYEBROOK GIS 110-RYEBROOK GIS 110-110SB1-2CB | 5 | 5 | 5 | Scheduled | 17/04/2023 | 21/04/2023
TO-23-RYB GIS-110SB1-3CB-05 | COUPLER/SECTIONALISING CB - RYEBROOK GIS 110-RYEBROOK GIS 110-110SB1-3CB | 5 | 5 | 5 | Scheduled | 17/04/2023 | 21/04/2023
TO-23-RYB GIS-110SB2-4CB-02 | COUPLER/SECTIONALISING CB - RYEBROOK GIS 110-RYEBROOK GIS 110-110SB2-4CB | 5 | 5 | 5 | Scheduled | 17/04/2023 | 21/04/2023
TO-23-400 kV A2 @ WOO-01 | BUSBAR SECTION - WOODLAND 400-WOODLAND 400-400A2 | 5 | 5 | 5 | Scheduled | 17/04/2023 | 21/04/2023
TO-23-WOO-T4204-02 | TRANSFORMER - WOODLAND 400-WOODLAND 220-T4204 | 5 | 5 | 5 | Scheduled | 17/04/2023 | 21/04/2023
TO-23-IA-T101-02 | GENERATOR TRANSFORMER - INNISCARRA 110-INNISCARRA G1-T101 | 9 | 7 | 7 | Scheduled | 18/04/2023 | 26/04/2023
TO-23-220 kV B1/B2 @ KRA-01 | BUSBAR SECTION - KNOCKRAHA 220-KNOCKRAHA 220-220B1-B2 | 131 | 91 |  | Scheduled | 18/04/2023 | 26/08/2023
TO-23-KRA-220K1-05 | COUPLER/SECTIONALISING CB - KNOCKRAHA 220-KNOCKRAHA 220-220K1 | 131 | 91 |  | Scheduled | 18/04/2023 | 26/08/2023
TO-23-KRA-220SB1-2CB-01 | COUPLER/SECTIONALISING CB - KNOCKRAHA 220-KNOCKRAHA 220-220SB1-2CB | 131 | 91 | 91 | Scheduled | 18/04/2023 | 26/08/2023
TO-23-KRA-220SB2-4CB-02 | COUPLER/SECTIONALISING CB - KNOCKRAHA 220-KNOCKRAHA 220-220SB2-4CB | 131 | 91 |  | Scheduled | 18/04/2023 | 26/08/2023
TO-23-MCE-SNU-1-02 | 110kV FEEDER - MACETOWN 110-SNUGBOROUGH 110-1 | 17 | 12 | 12 | Scheduled | 19/04/2023 | 05/05/2023
TO-23-110 kV A2 @ PA-02 | BUSBAR SECTION - POLLAPHUCA 110-POLLAPHUCA 110-110A2 | 1 | 1 | 1 | Scheduled | 20/04/2023 | 20/04/2023
TO-23-PA-110SA1-04 | SECTIONALISING DISCONNECT - POLLAPHUCA 110-POLLAPHUCA 110-110SA1 | 1 | 1 | 1 | Scheduled | 20/04/2023 | 20/04/2023
TO-23-PA-110SA2-04 | SECTIONALISING DISCONNECT - POLLAPHUCA 110-POLLAPHUCA 110-110SA2 | 1 | 1 | 1 | Scheduled | 20/04/2023 | 20/04/2023
TO-23-PA-T101-04 | GENERATOR TRANSFORMER - POLLAPHUCA 110-POLLAPHUCA G1-T101 | 1 | 1 | 1 | Scheduled | 20/04/2023 | 20/04/2023
TO-23-LOU-AT2-02 | TRANSFORMER - LOUTH 220-LOUTH 275-AT2 | 2 | 0 | 0 | Scheduled | 22/04/2023 | 23/04/2023
TO-23-LOU-T2101-01 | TRANSFORMER - LOUTH 220-LOUTH 110-T2101 | 2 | 0 | 0 | Scheduled | 22/04/2023 | 23/04/2023
TO-23-LOU-T2103-02 | TRANSFORMER - LOUTH 220-LOUTH 110-T2103 | 2 | 0 | 0 | Scheduled | 22/04/2023 | 23/04/2023
TO-23-LOU-TAN-2-02 | 275kV FEEDER - LOUTH 275-TANDRAGEE 275-2 | 2 | 0 | 0 | Scheduled | 22/04/2023 | 23/04/2023
TO-23-LOU-WOO-1-01 | 220kV FEEDER - LOUTH 220-WOODLAND 220-1 | 2 | 0 | 0 | Scheduled | 22/04/2023 | 23/04/2023
TO-23-ARK-LWD-1-01 | 220kV FEEDER - ARKLOW 220-LODGEWOOD 220-1 | 4 | 4 | 4 | Scheduled | 24/04/2023 | 27/04/2023
TO-23-BK-110SA1-03 | SECTIONALISING DISCONNECT - BELLACORICK 110-BELLACORICK 110-110SA1 | 12 | 9 | 9 | Scheduled | 24/04/2023 | 05/05/2023
TO-23-BK-110SA2-03 | SECTIONALISING DISCONNECT - BELLACORICK 110-BELLACORICK 110-110SA2 | 12 | 9 | 9 | Scheduled | 24/04/2023 | 05/05/2023
TO-23-BK-MOY-1-01 | 110kV FEEDER - BELLACORICK 110-MOY 110-1 | 12 | 9 | 9 | Scheduled | 24/04/2023 | 05/05/2023
TO-23-BK-T141-02 | DISTRIBUTION TRANSFORMER - BELLACORICK 110-BELLACORICK 38-T141 | 12 | 9 | 9 | Reference | 24/04/2023 | 05/05/2023
TO-23-110 kV A1 @ CBT-01 | BUSBAR SECTION - CASTLEBAGOT 110-CASTLEBAGOT 110-110A1 | 1 | 1 |  | Scheduled | 24/04/2023 | 24/04/2023
TO-23-110 kV B1 @ CBT-04 | BUSBAR SECTION - CASTLEBAGOT 110-CASTLEBAGOT 110-110B1 | 1 | 1 |  | Scheduled | 24/04/2023 | 24/04/2023
TO-23-CBT-110K1-02 | COUPLER/SECTIONALISING CB - CASTLEBAGOT 110-CASTLEBAGOT 110-110K1 | 1 | 1 |  | Scheduled | 24/04/2023 | 24/04/2023
TO-23-CBT-110SA1-2CB-02 | COUPLER/SECTIONALISING CB - CASTLEBAGOT 110-CASTLEBAGOT 110-110SA1-2CB | 1 | 1 |  | Scheduled | 24/04/2023 | 24/04/2023
TO-23-CBT-110SB1-2CB-06 | COUPLER/SECTIONALISING CB - CASTLEBAGOT 110-CASTLEBAGOT 110-110SB1-2CB | 1 | 1 |  | Scheduled | 24/04/2023 | 24/04/2023
TO-23-CDU-110K1-3-03 | COUPLER/SECTIONALISING CB - CORDUFF 110-CORDUFF 110-110K1-3 | 5 | 5 | 5 | Scheduled | 24/04/2023 | 28/04/2023
TO-23-DEY-PLS-1-01 | 110kV FEEDER - DERRYCARNEY 110-PORTLAOISE 110-1 | 5 | 5 |  | Scheduled | 24/04/2023 | 28/04/2023
TO-23-DMY-MAC-1-03 | 110kV FEEDER - DUNMANWAY 110-MACROOM 110-1 | 5 | 5 | 5 | Scheduled | 24/04/2023 | 28/04/2023
TO-23-220 kV A1 @ KPG-03 | BUSBAR SECTION - KILPADDOGE 220-KILPADDOGE 220-220A1 | 4 | 4 | 4 | Scheduled | 24/04/2023 | 27/04/2023
TO-23-220 kV B1 @ KPG-03 | BUSBAR SECTION - KILPADDOGE 220-KILPADDOGE 220-220B1 | 4 | 4 | 4 | Scheduled | 24/04/2023 | 27/04/2023
TO-23-KPG-220SA1-2CB-03 | COUPLER/SECTIONALISING CB - KILPADDOGE 220-KILPADDOGE 220-220SA1-2CB | 4 | 4 | 4 | Scheduled | 24/04/2023 | 27/04/2023
TO-23-KPG-220SA1-3CB-03 | COUPLER/SECTIONALISING CB - KILPADDOGE 220-KILPADDOGE 220-220SA1-3CB | 4 | 4 | 4 | Scheduled | 24/04/2023 | 27/04/2023
TO-23-KPG-220SB1-2CB-03 | COUPLER/SECTIONALISING CB - KILPADDOGE 220-KILPADDOGE 220-220SB1-2CB | 4 | 4 | 4 | Scheduled | 24/04/2023 | 27/04/2023
TO-23-KPG-220SB1-3CB-04 | COUPLER/SECTIONALISING CB - KILPADDOGE 220-KILPADDOGE 220-220SB1-3CB | 4 | 4 | 4 | Scheduled | 24/04/2023 | 27/04/2023
TO-23-KPG-KNR-1-01 | 220kV FEEDER - KILPADDOGE 220-KNOCKANURE 220-1 | 4 | 4 | 4 | Scheduled | 24/04/2023 | 27/04/2023
TO-23-KNR-TRI-2-01 | 110kV FEEDER - KNOCKANURE 110-TRIEN 110-2 | 4 | 4 | 4 | Scheduled | 24/04/2023 | 27/04/2023
TO-23-LIM-MTN-1-02 | 110kV FEEDER - LIMERICK 110-MONETEEN 110-1 | 5 | 5 | 5 | Scheduled | 24/04/2023 | 28/04/2023
TO-23-LIS-SKL-1-04 | 110kV FEEDER - LISDRUM 110-SHANKILL 110-1 | 26 | 19 | 19 | Scheduled | 24/04/2023 | 19/05/2023
TO-23-220 kV A1/A2 @ LOU-01 | BUSBAR SECTION - LOUTH 220-LOUTH 220-220A1-A2 | 126 | 87 |  | Scheduled | 24/04/2023 | 27/08/2023
TO-23-PB-220K2-3-02 | COUPLER/SECTIONALISING CB - POOLBEG 220-POOLBEG 220-220K2-3 | 5 | 5 | 5 | Proposed | 24/04/2023 | 28/04/2023
TO-23-PRN-T4301-01 | TRANSFORMER - PORTAN 400-PORTAN 260-T4301 | 5 | 5 | 5 | Proposed | 24/04/2023 | 28/04/2023
TO-23-PRN-WOO-1-01 | 400kV FEEDER - PORTAN 400-WOODLAND 400-1 | 5 | 5 | 5 | Proposed | 24/04/2023 | 28/04/2023
TO-23-110 kV A2 @ PLS-01 | BUSBAR SECTION - PORTLAOISE 110-PORTLAOISE 110-110A2 | 5 | 5 | 5 | Scheduled | 24/04/2023 | 28/04/2023
TO-23-110 kV B2 @ PLS-01 | BUSBAR SECTION - PORTLAOISE 110-PORTLAOISE 110-110B2 | 5 | 5 | 5 | Scheduled | 24/04/2023 | 28/04/2023
TO-23-400 kV A1 @ WOO-01 | BUSBAR SECTION - WOODLAND 400-WOODLAND 400-400A1 | 1 | 1 | 1 | Proposed | 24/04/2023 | 24/04/2023
TO-23-CKM-PST2201-02 | TRANSFORMER - CARRICKMINES 220-CARRICKMINES 220-PST2201 | 2 | 2 | 2 | Proposed | 25/04/2023 | 26/04/2023
TO-23-110 kV A4 @ CBT-03 | BUSBAR SECTION - CASTLEBAGOT 110-CASTLEBAGOT 110-110A4 | 1 | 1 |  | Scheduled | 25/04/2023 | 25/04/2023
TO-23-110 kV B4 @ CBT-02 | BUSBAR SECTION - CASTLEBAGOT 110-CASTLEBAGOT 110-110B4 | 1 | 1 |  | Scheduled | 25/04/2023 | 25/04/2023
TO-23-CBT-110K4-02 | COUPLER/SECTIONALISING CB - CASTLEBAGOT 110-CASTLEBAGOT 110-110K4 | 1 | 1 |  | Scheduled | 25/04/2023 | 25/04/2023
TO-23-CBT-110SA2-4CB-05 | COUPLER/SECTIONALISING CB - CASTLEBAGOT 110-CASTLEBAGOT 110-110SA2-4CB | 1 | 1 |  | Scheduled | 25/04/2023 | 25/04/2023
TO-23-CBT-110SB2-4CB-04 | COUPLER/SECTIONALISING CB - CASTLEBAGOT 110-CASTLEBAGOT 110-110SB2-4CB | 1 | 1 |  | Scheduled | 25/04/2023 | 25/04/2023
TO-23-BDN-T141-01 | DISTRIBUTION TRANSFORMER - BALLYDINE 110-BALLYDINE 38-T141 | 72 | 50 |  | Reference | 27/04/2023 | 07/07/2023
TO-23-DRY-T141-02 | DISTRIBUTION TRANSFORMER - DRYBRIDGE 110-DRYBRIDGE 38-T141 | 112 | 77 | 77 | Reference | 27/04/2023 | 16/08/2023
TO-23-110 kV A2 @ AA GIS-02 | BUSBAR SECTION - ARDNACRUSHA GIS 110-ARDNACRUSHA GIS 110-110A2 | 1 | 1 | 1 | Scheduled | 28/04/2023 | 28/04/2023
TO-23-AA GIS-110K2-01 | COUPLER/SECTIONALISING CB - ARDNACRUSHA GIS 110-ARDNACRUSHA GIS 110-110K2 | 1 | 1 | 1 | Scheduled | 28/04/2023 | 28/04/2023
TO-23-AA GIS-110SA1-2CB-02 | COUPLER/SECTIONALISING CB - ARDNACRUSHA GIS 110-ARDNACRUSHA GIS 110-110SA1-2CB | 1 | 1 | 1 | Scheduled | 28/04/2023 | 28/04/2023
TO-23-AA GIS-T102-03 | GENERATOR TRANSFORMER - ARDNACRUSHA GIS 110-ARDNACRUSHA GIS G2-T102 | 1 | 1 | 1 | Scheduled | 28/04/2023 | 28/04/2023
TO-23-220 kV A1 @ CBT-01 | BUSBAR SECTION - CASTLEBAGOT 220-CASTLEBAGOT 220-220A1 | 5 | 2 | 2 | Scheduled | 29/04/2023 | 03/05/2023
TO-23-CBT-220K1-02 | COUPLER/SECTIONALISING CB - CASTLEBAGOT 220-CASTLEBAGOT 220-220K1 | 5 | 2 | 2 | Scheduled | 29/04/2023 | 03/05/2023
TO-23-CBT-220SA1-2CB-03 | COUPLER/SECTIONALISING CB - CASTLEBAGOT 220-CASTLEBAGOT 220-220SA1-2CB | 5 | 2 | 2 | Scheduled | 29/04/2023 | 03/05/2023
TO-23-CBT-MAY-1-01 | 220kV FEEDER - CASTLEBAGOT 220-MAYNOOTH 220-1 | 5 | 2 |  | Scheduled | 29/04/2023 | 03/05/2023
TO-23-CSH-220K2-4-01 | COUPLER/SECTIONALISING CB - CASHLA 220-CASHLA 220-220K2-4 | 44 | 30 |  | Scheduled | 01/05/2023 | 13/06/2023
TO-23-ARK-T2102-01 | TRANSFORMER - ARKLOW 220-ARKLOW 110-T2102 | 2 | 2 | 2 | Scheduled | 02/05/2023 | 03/05/2023
TO-23-CFN-SH-1-01 | 220kV FEEDER - CLONIFFEEN 220-SHANNONBRIDGE 220-1 | 28 | 20 |  | Scheduled | 02/05/2023 | 29/05/2023
TO-23-CFN-T232-01 | GENERATOR TRANSFORMER - CLONIFFEEN 220-CLONIFFEEN 33-T232 | 28 | 20 |  | Scheduled | 02/05/2023 | 29/05/2023
TO-23-KLN-LIM-2-01 | 110kV FEEDER - KILLONAN 110-LIMERICK 110-2 | 4 | 4 |  | Scheduled | 02/05/2023 | 05/05/2023
TO-23-220 kV A2 @ KPG-04 | BUSBAR SECTION - KILPADDOGE 220-KILPADDOGE 220-220A2 | 4 | 4 | 4 | Scheduled | 02/05/2023 | 05/05/2023
TO-23-220 kV B2 @ KPG-04 | BUSBAR SECTION - KILPADDOGE 220-KILPADDOGE 220-220B2 | 4 | 4 | 4 | Scheduled | 02/05/2023 | 05/05/2023
TO-23-KPG-220SA1-2CB-04 | COUPLER/SECTIONALISING CB - KILPADDOGE 220-KILPADDOGE 220-220SA1-2CB | 4 | 4 | 4 | Scheduled | 02/05/2023 | 05/05/2023
TO-23-KPG-220SA2-4CB-03 | COUPLER/SECTIONALISING CB - KILPADDOGE 220-KILPADDOGE 220-220SA2-4CB | 4 | 4 | 4 | Scheduled | 02/05/2023 | 05/05/2023
TO-23-KPG-220SB1-2CB-05 | COUPLER/SECTIONALISING CB - KILPADDOGE 220-KILPADDOGE 220-220SB1-2CB | 4 | 4 | 4 | Scheduled | 02/05/2023 | 05/05/2023
TO-23-KPG-220SB2-4CB-04 | COUPLER/SECTIONALISING CB - KILPADDOGE 220-KILPADDOGE 220-220SB2-4CB | 4 | 4 | 4 | Scheduled | 02/05/2023 | 05/05/2023
TO-23-KPG-KNR-2-01 | 220kV FEEDER - KILPADDOGE 220-KNOCKANURE 220-2 | 4 | 4 |  | Scheduled | 02/05/2023 | 05/05/2023
TO-23-KNR-TRI-1-01 | 110kV FEEDER - KNOCKANURE 110-TRIEN 110-1 | 4 | 4 |  | Scheduled | 02/05/2023 | 05/05/2023
TO-23-400 kV A3 @ MP GIS-02 | BUSBAR SECTION - MONEYPOINT GIS 400-MONEYPOINT GIS 400-400A3 | 9 | 7 | 7 | Scheduled | 02/05/2023 | 10/05/2023
TO-23-400 kV B3 @ MP GIS-01 | BUSBAR SECTION - MONEYPOINT GIS 400-MONEYPOINT GIS 400-400B3 | 9 | 7 | 7 | Scheduled | 02/05/2023 | 10/05/2023
TO-23-MP GIS-400K3-01 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 400-MONEYPOINT GIS 400-400K3 | 9 | 7 | 7 | Scheduled | 02/05/2023 | 10/05/2023
TO-23-MP GIS-400SA1-3CB-02 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 400-MONEYPOINT GIS 400-400SA1-3CB | 9 | 7 | 7 | Scheduled | 02/05/2023 | 10/05/2023
TO-23-MP GIS-400SB1-3CB-01 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 400-MONEYPOINT GIS 400-400SB1-3CB | 9 | 7 | 7 | Scheduled | 02/05/2023 | 10/05/2023
TO-23-MP GIS-OST-1-01 | 400kV FEEDER - MONEYPOINT GIS 400-OLDSTREET 400-1 | 28 | 20 |  | Scheduled | 02/05/2023 | 29/05/2023
TO-23-MP GIS-T4202-02 | TRANSFORMER - MONEYPOINT GIS 400-MONEYPOINT GIS 220-T4202 | 128 | 90 |  | Scheduled | 02/05/2023 | 06/09/2023
TO-23-MOY-TAW-2-01 | 110kV FEEDER - MOY 110-TAWNAGHMORE 110-2 | 2 | 2 | 2 | Scheduled | 02/05/2023 | 03/05/2023
TO-23-110 kV A2 @ KBY-03 | BUSBAR SECTION - KILBARRY 110-KILBARRY 110-110A2 | 1 | 1 | 1 | Scheduled | 03/05/2023 | 03/05/2023
TO-23-110 kV B2 @ KBY-01 | BUSBAR SECTION - KILBARRY 110-KILBARRY 110-110B2 | 1 | 1 | 1 | Scheduled | 03/05/2023 | 03/05/2023
TO-23-KBY-MR-1-01 | 110kV FEEDER - KILBARRY 110-MARINA 110-1 | 93 | 66 | 66 | Scheduled | 03/05/2023 | 03/08/2023
TO-23-KBY-MR-2-03 | 110kV FEEDER - KILBARRY 110-MARINA 110-2 | 93 | 66 | 66 | Scheduled | 03/05/2023 | 03/08/2023
TO-23-110 kV A2 @ KNY-02 | BUSBAR SECTION - KNOCKRANNY 110-KNOCKRANNY 110-110A2 | 2 | 2 | 2 | Scheduled | 03/05/2023 | 04/05/2023
TO-23-110 kV B2 @ KNY-02 | BUSBAR SECTION - KNOCKRANNY 110-KNOCKRANNY 110-110B2 | 2 | 2 | 2 | Scheduled | 03/05/2023 | 04/05/2023
TO-23-KNY-110K2-02 | COUPLER/SECTIONALISING CB - KNOCKRANNY 110-KNOCKRANNY 110-110K2 | 2 | 2 | 2 | Scheduled | 03/05/2023 | 04/05/2023
TO-23-KNY-110SA1-2CB-02 | COUPLER/SECTIONALISING CB - KNOCKRANNY 110-KNOCKRANNY 110-110SA1-2CB | 2 | 2 | 2 | Scheduled | 03/05/2023 | 04/05/2023
TO-23-KNY-110SB1-2CB-02 | COUPLER/SECTIONALISING CB - KNOCKRANNY 110-KNOCKRANNY 110-110SB1-2CB | 2 | 2 | 2 | Scheduled | 03/05/2023 | 04/05/2023
TO-23-KNY-SAL-1-02 | 110kV FEEDER - KNOCKRANNY 110-SALTHILL 110-1 | 2 | 2 | 2 | Scheduled | 03/05/2023 | 04/05/2023
TO-23-RAF-220K1-2-01 | COUPLER/SECTIONALISING CB - RAFFEEN 220-RAFFEEN 220-220K1-2 | 2 | 2 | 2 | Scheduled | 03/05/2023 | 04/05/2023
TO-23-TH-T2001/2-01 | GENERATOR TRANSFORMER - TURLOUGH HILL 220-TURLOUGH HILL G1-T2001/2 | 10 | 8 | 8 | Scheduled | 03/05/2023 | 12/05/2023
TO-23-ARK-T101-01 | DISTRIBUTION TRANSFORMER - ARKLOW 110-ARKLOW 10-T101 | 2 | 2 |  | Reference (Proposed) | 04/05/2023 | 05/05/2023
TO-23-110 kV B2 @ KBY-03 | BUSBAR SECTION - KILBARRY 110-KILBARRY 110-110B2 | 89 | 62 | 62 | Scheduled | 04/05/2023 | 31/07/2023
TO-23-MOY-TAW-1-01 | 110kV FEEDER - MOY 110-TAWNAGHMORE 110-1 | 2 | 2 | 2 | Scheduled | 04/05/2023 | 05/05/2023
TO-23-AGL-110SA1-01 | SECTIONALISING DISCONNECT - AGANNYGAL 110-AGANNYGAL 110-110SA1 | 5 | 5 | 5 | Scheduled | 08/05/2023 | 12/05/2023
TO-23-AGL-110SA2-01 | SECTIONALISING DISCONNECT - AGANNYGAL 110-AGANNYGAL 110-110SA2 | 5 | 5 | 5 | Scheduled | 08/05/2023 | 12/05/2023
TO-23-AGL-DYN-1-01 | 110kV FEEDER - AGANNYGAL 110-DERRYBRIEN 110-1 | 5 | 5 | 5 | Scheduled | 08/05/2023 | 12/05/2023
TO-23-AGL-ENN-1-02 | 110kV FEEDER - AGANNYGAL 110-ENNIS 110-1 | 5 | 5 | 5 | Scheduled | 08/05/2023 | 12/05/2023
TO-23-AGL-SH-1-03 | 110kV FEEDER - AGANNYGAL 110-SHANNONBRIDGE 110-1 | 5 | 5 | 5 | Scheduled | 08/05/2023 | 12/05/2023
TO-23-ARV-GWE-1-03 | 110kV FEEDER - ARVA 110-GORTAWEE 110-1 | 55 | 39 |  | Scheduled | 08/05/2023 | 01/07/2023
TO-23-AUG-CFM-1-01 | 110kV FEEDER - AUGHINISH 110-CASTLEFARM 110-1 | 3 | 3 | 3 | Scheduled | 08/05/2023 | 10/05/2023
TO-23-110 kV A2 @ CSH-05 | BUSBAR SECTION - CASHLA 110-CASHLA 110-110A2 | 5 | 5 | 5 | Scheduled | 08/05/2023 | 12/05/2023
TO-23-110 kV B2 @ CSH-06 | BUSBAR SECTION - CASHLA 110-CASHLA 110-110B2 | 5 | 5 | 5 | Scheduled | 08/05/2023 | 12/05/2023
TO-23-220 kV A2 @ CSH-01 | BUSBAR SECTION - CASHLA 220-CASHLA 220-220A2 | 5 | 5 | 5 | Scheduled | 08/05/2023 | 12/05/2023
TO-23-220 kV A4 @ CSH-01 | BUSBAR SECTION - CASHLA 220-CASHLA 220-220A4 | 5 | 5 | 5 | Scheduled | 08/05/2023 | 12/05/2023
TO-23-CFM-T101-01 | TSO CUSTOMER TRANSFORMER - CASTLEFARM 110-CASTLEFARM 10-T101 | 5 | 5 | 5 | Reference | 08/05/2023 | 12/05/2023
TO-23-CF-T104-01 | GENERATOR TRANSFORMER - CATHALEENS FALL 110-CATHALEENS FALL G4-T104 | 10 | 8 | 8 | Scheduled | 08/05/2023 | 17/05/2023
TO-23-CHA-GLE-1-01 | 110kV FEEDER - CHARLEVILLE 110-GLENLARA 110-1 | 12 | 10 | 10 | Scheduled | 08/05/2023 | 19/05/2023
TO-23-220 kV A1 @ CDU-03 | BUSBAR SECTION - CORDUFF 220-CORDUFF 220-220A1 | 2 | 2 | 2 | Scheduled | 08/05/2023 | 09/05/2023
TO-23-220 kV A2 @ CDU-03 | BUSBAR SECTION - CORDUFF 220-CORDUFF 220-220A2 | 2 | 2 | 2 | Scheduled | 08/05/2023 | 09/05/2023
TO-23-220 kV A3 @ CDU-02 | BUSBAR SECTION - CORDUFF 220-CORDUFF 220-220A3 | 2 | 2 | 2 | Scheduled | 08/05/2023 | 09/05/2023
TO-23-220 kV A4 @ CDU-04 | BUSBAR SECTION - CORDUFF 220-CORDUFF 220-220A4 | 2 | 2 | 2 | Scheduled | 08/05/2023 | 09/05/2023
TO-23-220 kV B1 @ CDU-03 | BUSBAR SECTION - CORDUFF 220-CORDUFF 220-220B1 | 2 | 2 | 2 | Scheduled | 08/05/2023 | 09/05/2023
TO-23-220 kV B2 @ CDU-03 | BUSBAR SECTION - CORDUFF 220-CORDUFF 220-220B2 | 2 | 2 | 2 | Scheduled | 08/05/2023 | 09/05/2023
TO-23-220 kV B3 @ CDU-02 | BUSBAR SECTION - CORDUFF 220-CORDUFF 220-220B3 | 2 | 2 | 2 | Scheduled | 08/05/2023 | 09/05/2023
TO-23-220 kV B4 @ CDU-04 | BUSBAR SECTION - CORDUFF 220-CORDUFF 220-220B4 | 2 | 2 | 2 | Scheduled | 08/05/2023 | 09/05/2023
TO-23-CDU-220K1-2-04 | COUPLER/SECTIONALISING CB - CORDUFF 220-CORDUFF 220-220K1-2 | 2 | 2 | 2 | Scheduled | 08/05/2023 | 09/05/2023
TO-23-CDU-220K1-3-05 | COUPLER/SECTIONALISING CB - CORDUFF 220-CORDUFF 220-220K1-3 | 2 | 2 | 2 | Scheduled | 08/05/2023 | 09/05/2023
TO-23-CDU-220SA2-4-04 | SECTIONALISING DISCONNECT - CORDUFF 220-CORDUFF 220-220SA2-4 | 2 | 2 | 2 | Scheduled | 08/05/2023 | 09/05/2023
TO-23-CDU-220SB2-4-06 | SECTIONALISING DISCONNECT - CORDUFF 220-CORDUFF 220-220SB2-4 | 2 | 2 | 2 | Scheduled | 08/05/2023 | 09/05/2023
TO-23-CUL-DGN-1-01 | 110kV FEEDER - CULLENAGH 110-DUNGARVAN 110-1 | 43 | 30 | 30 | Scheduled | 08/05/2023 | 19/06/2023
TO-23-DYN-T121-01 | GENERATOR TRANSFORMER - DERRYBRIEN 110-DERRYBRIEN 20-T121 | 5 | 5 | 5 | Reference | 08/05/2023 | 12/05/2023
TO-23-DFR-T122-01 | DISTRIBUTION TRANSFORMER - DUNFIRTH 110-DUNFIRTH 20-T122 | 2 | 2 | 2 | Reference | 08/05/2023 | 09/05/2023
TO-23-DFR,T-DFR-1-02 | 110kV FEEDER - DUNFIRTH tee-DUNFIRTH 110-1 | 2 | 2 | 2 | Scheduled | 08/05/2023 | 09/05/2023
TO-23-DFR,T-KIN-1-04 | 110kV FEEDER - DUNFIRTH tee-KINNEGAD 110-1 | 2 | 2 | 2 | Scheduled | 08/05/2023 | 09/05/2023
TO-23-DFR,T-RNW-1-04 | 110kV FEEDER - DUNFIRTH tee-RINAWADE 110-1 | 2 | 2 | 2 | Scheduled | 08/05/2023 | 09/05/2023
TO-23-FIN-220K2-03 | COUPLER/SECTIONALISING CB - FINGLAS 220-FINGLAS 220-220K2 | 12 | 10 | 10 | Scheduled | 08/05/2023 | 19/05/2023
TO-23-FIN-220SA1-2CB-02 | COUPLER/SECTIONALISING CB - FINGLAS 220-FINGLAS 220-220SA1-2CB | 12 | 10 | 10 | Scheduled | 08/05/2023 | 19/05/2023
TO-23-FIN-220SB1-2CB-05 | COUPLER/SECTIONALISING CB - FINGLAS 220-FINGLAS 220-220SB1-2CB | 12 | 10 | 10 | Scheduled | 08/05/2023 | 19/05/2023
TO-23-110 kV A1 @ MR-01 | BUSBAR SECTION - MARINA 110-MARINA 110-110A1 | 9 | 7 | 7 | Scheduled | 08/05/2023 | 16/05/2023
TO-23-110 kV B1 @ MR-01 | BUSBAR SECTION - MARINA 110-MARINA 110-110B1 | 9 | 7 | 7 | Scheduled | 08/05/2023 | 16/05/2023
TO-23-110 kV A1 @ MAY-02 | BUSBAR SECTION - MAYNOOTH 110-MAYNOOTH 110-110A1 | 12 | 10 | 10 | Scheduled | 08/05/2023 | 19/05/2023
TO-23-110 kV A2 @ MAY-01 | BUSBAR SECTION - MAYNOOTH 110-MAYNOOTH 110-110A2 | 12 | 10 | 10 | Scheduled | 08/05/2023 | 19/05/2023
TO-23-110 kV B1 @ MAY-02 | BUSBAR SECTION - MAYNOOTH 110-MAYNOOTH 110-110B1 | 12 | 10 | 10 | Scheduled | 08/05/2023 | 19/05/2023
TO-23-110 kV B2 @ MAY-01 | BUSBAR SECTION - MAYNOOTH 110-MAYNOOTH 110-110B2 | 12 | 10 | 10 | Scheduled | 08/05/2023 | 19/05/2023
TO-23-MAY-110K1-2-01 | COUPLER/SECTIONALISING CB - MAYNOOTH 110-MAYNOOTH 110-110K1-2 | 12 | 10 | 10 | Scheduled | 08/05/2023 | 19/05/2023
TO-23-MP GIS-T4002-01 | GENERATOR TRANSFORMER - MONEYPOINT GIS 400-MONEYPOINT GIS G2-T4002 | 1 | 1 | 1 | Scheduled | 08/05/2023 | 08/05/2023
TO-23-110 kV A1 @ RAF-03 | BUSBAR SECTION - RAFFEEN 110-RAFFEEN 110-110A1 | 5 | 5 | 5 | Scheduled | 08/05/2023 | 12/05/2023
TO-23-110 kV A2 @ RAF-03 | BUSBAR SECTION - RAFFEEN 110-RAFFEEN 110-110A2 | 5 | 5 | 5 | Scheduled | 08/05/2023 | 12/05/2023
TO-23-110 kV B1 @ RAF-03 | BUSBAR SECTION - RAFFEEN 110-RAFFEEN 110-110B1 | 5 | 5 | 5 | Scheduled | 08/05/2023 | 12/05/2023
TO-23-110 kV B2 @ RAF-03 | BUSBAR SECTION - RAFFEEN 110-RAFFEEN 110-110B2 | 5 | 5 | 5 | Scheduled | 08/05/2023 | 12/05/2023
TO-23-RAF-110K1-2-01 | COUPLER/SECTIONALISING CB - RAFFEEN 110-RAFFEEN 110-110K1-2 | 5 | 5 | 5 | Scheduled | 08/05/2023 | 12/05/2023
TO-23-WEX-CAP2-01 | CAPACITOR/SVC/REACTOR - WEXFORD 110-WEXFORD 110-CAP2 | 5 | 5 | 5 | Scheduled | 08/05/2023 | 12/05/2023
TO-23-WEX-CAP4-01 | CAPACITOR/SVC/REACTOR - WEXFORD 110-WEXFORD 110-CAP4 | 5 | 5 | 5 | Scheduled | 08/05/2023 | 12/05/2023
TO-23-WOH-T122-01 | GENERATOR TRANSFORMER - WOODHOUSE 110-WOODHOUSE 20-T122 | 19 | 15 | 15 | Scheduled | 08/05/2023 | 26/05/2023
TO-23-CDU-MCE-1-06 | 110kV FEEDER - CORDUFF 110-MACETOWN 110-1 | 2 | 2 | 2 | Scheduled | 09/05/2023 | 10/05/2023
TO-23-BVK-T2101-01 | TRANSFORMER - BALLYVOUSKILL 220-BALLYVOUSKILL 110-T2101 | 8 | 6 | 6 | Scheduled | 10/05/2023 | 17/05/2023
TO-23-110 kV A1 @ CBT-02 | BUSBAR SECTION - CASTLEBAGOT 110-CASTLEBAGOT 110-110A1 | 3 | 3 | 3 | Scheduled | 10/05/2023 | 12/05/2023
TO-23-110 kV A4 @ CBT-01 | BUSBAR SECTION - CASTLEBAGOT 110-CASTLEBAGOT 110-110A4 | 3 | 3 | 3 | Scheduled | 10/05/2023 | 12/05/2023
TO-23-110 kV B1 @ CBT-01 | BUSBAR SECTION - CASTLEBAGOT 110-CASTLEBAGOT 110-110B1 | 3 | 3 | 3 | Scheduled | 10/05/2023 | 12/05/2023
TO-23-110 kV B4 @ CBT-01 | BUSBAR SECTION - CASTLEBAGOT 110-CASTLEBAGOT 110-110B4 | 3 | 3 | 3 | Scheduled | 10/05/2023 | 12/05/2023
TO-23-CBT-110K1-04 | COUPLER/SECTIONALISING CB - CASTLEBAGOT 110-CASTLEBAGOT 110-110K1 | 3 | 3 | 3 | Scheduled | 10/05/2023 | 12/05/2023
TO-23-CBT-110K4-01 | COUPLER/SECTIONALISING CB - CASTLEBAGOT 110-CASTLEBAGOT 110-110K4 | 3 | 3 | 3 | Scheduled | 10/05/2023 | 12/05/2023
TO-23-CBT-110SA1-2CB-05 | COUPLER/SECTIONALISING CB - CASTLEBAGOT 110-CASTLEBAGOT 110-110SA1-2CB | 3 | 3 | 3 | Scheduled | 10/05/2023 | 12/05/2023
TO-23-CBT-110SA2-4CB-02 | COUPLER/SECTIONALISING CB - CASTLEBAGOT 110-CASTLEBAGOT 110-110SA2-4CB | 3 | 3 | 3 | Scheduled | 10/05/2023 | 12/05/2023
TO-23-CBT-110SB1-2CB-02 | COUPLER/SECTIONALISING CB - CASTLEBAGOT 110-CASTLEBAGOT 110-110SB1-2CB | 3 | 3 | 3 | Scheduled | 10/05/2023 | 12/05/2023
TO-23-CBT-110SB2-4CB-02 | COUPLER/SECTIONALISING CB - CASTLEBAGOT 110-CASTLEBAGOT 110-110SB2-4CB | 3 | 3 | 3 | Scheduled | 10/05/2023 | 12/05/2023
TO-23-CBT-T2103-05 | TRANSFORMER - CASTLEBAGOT 220-CASTLEBAGOT 110-T2103 | 3 | 3 | 3 | Scheduled | 10/05/2023 | 12/05/2023
TO-23-DFR,T-RNW-1-06 | 110kV FEEDER - DUNFIRTH tee-RINAWADE 110-1 | 16 | 12 | 12 | Scheduled | 10/05/2023 | 25/05/2023
TO-23-GOR-T122-01 | GENERATOR TRANSFORMER - GORMAN 110-GORMAN 20-T122 | 2 | 2 | 2 | Scheduled | 10/05/2023 | 11/05/2023
TO-23-CRO-IA-1-04 | 110kV FEEDER - COOLROE 110-INNISCARRA 110-1 | 1 | 1 | 1 | Scheduled | 11/05/2023 | 11/05/2023
TO-23-110 kV A1 @ IA-01 | BUSBAR SECTION - INNISCARRA 110-INNISCARRA 110-110A1 | 1 | 1 | 1 | Scheduled | 11/05/2023 | 11/05/2023
TO-23-IA-MAC-1-04 | 110kV FEEDER - INNISCARRA 110-MACROOM 110-1 | 1 | 1 | 1 | Scheduled | 11/05/2023 | 11/05/2023
TO-23-IA-T101-03 | GENERATOR TRANSFORMER - INNISCARRA 110-INNISCARRA G1-T101 | 1 | 1 | 1 | Scheduled | 11/05/2023 | 11/05/2023
TO-23-BYH-T2101-01 | TRANSFORMER - BALLYNAHULLA 220-BALLYNAHULLA 110-T2101 | 15 | 11 | 11 | Scheduled | 12/05/2023 | 26/05/2023
TO-23-CDU-GLN-1-03 | 110kV FEEDER - CORDUFF 110-GALLANSTOWN 110-1 | 34 | 23 | 23 | Scheduled | 12/05/2023 | 14/06/2023
TO-23-110 kV A3 @ AA GIS-01 | BUSBAR SECTION - ARDNACRUSHA GIS 110-ARDNACRUSHA GIS 110-110A3 | 5 | 5 | 5 | Scheduled | 15/05/2023 | 19/05/2023
TO-23-110 kV B3 @ AA GIS-01 | BUSBAR SECTION - ARDNACRUSHA GIS 110-ARDNACRUSHA GIS 110-110B3 | 5 | 5 | 5 | Scheduled | 15/05/2023 | 19/05/2023
TO-23-AA GIS-110K3-02 | COUPLER/SECTIONALISING CB - ARDNACRUSHA GIS 110-ARDNACRUSHA GIS 110-110K3 | 5 | 5 | 5 | Scheduled | 15/05/2023 | 19/05/2023
TO-23-AA GIS-110SA1-3CB-01 | COUPLER/SECTIONALISING CB - ARDNACRUSHA GIS 110-ARDNACRUSHA GIS 110-110SA1-3CB | 5 | 5 | 5 | Scheduled | 15/05/2023 | 19/05/2023
TO-23-AA GIS-110SB1-3CB-01 | COUPLER/SECTIONALISING CB - ARDNACRUSHA GIS 110-ARDNACRUSHA GIS 110-110SB1-3CB | 5 | 5 | 5 | Scheduled | 15/05/2023 | 19/05/2023
TO-23-AA GIS-DRU-1-01 | 110kV FEEDER - ARDNACRUSHA GIS 110-DRUMLINE 110-1 | 5 | 5 | 5 | Scheduled | 15/05/2023 | 19/05/2023
TO-23-CKM-PB-1-02 | 220kV FEEDER - CARRICKMINES 220-POOLBEG 220-1 | 5 | 5 | 5 | Scheduled | 15/05/2023 | 19/05/2023
TO-23-CKM-PST2201-01 | TRANSFORMER - CARRICKMINES 220-CARRICKMINES 220-PST2201 | 5 | 5 | 5 | Scheduled | 15/05/2023 | 19/05/2023
TO-23-CLH-110SA1-01 | SECTIONALISING DISCONNECT - CLAHANE 110-CLAHANE 110-110SA1 | 4 | 4 | 4 | Scheduled | 15/05/2023 | 18/05/2023
TO-23-CLH-110SA2-01 | SECTIONALISING DISCONNECT - CLAHANE 110-CLAHANE 110-110SA2 | 4 | 4 | 4 | Scheduled | 15/05/2023 | 18/05/2023
TO-23-CLH-T122-01 | GENERATOR TRANSFORMER - CLAHANE 110-CLAHANE 20-T122 | 4 | 4 | 4 | Scheduled | 15/05/2023 | 18/05/2023
TO-23-CLH-TRI-1-01 | 110kV FEEDER - CLAHANE 110-TRIEN 110-1 | 4 | 4 | 4 | Scheduled | 15/05/2023 | 18/05/2023
TO-23-DDK-LOU-1-01 | 110kV FEEDER - DUNDALK 110-LOUTH 110-1 | 146 | 103 |  | Scheduled | 15/05/2023 | 07/10/2023
TO-23-110 kV A2 @ GAL GIS-03 | BUSBAR SECTION - GALWAY GIS 110-GALWAY GIS 110-110A2 | 5 | 5 | 5 | Scheduled | 15/05/2023 | 19/05/2023
TO-23-110 kV B2 @ GAL GIS-03 | BUSBAR SECTION - GALWAY GIS 110-GALWAY GIS 110-110B2 | 5 | 5 | 5 | Scheduled | 15/05/2023 | 19/05/2023
TO-23-GAL GIS-110K2-02 | COUPLER/SECTIONALISING CB - GALWAY GIS 110-GALWAY GIS 110-110K2 | 5 | 5 | 5 | Scheduled | 15/05/2023 | 19/05/2023
TO-23-GAL GIS-110SA1-2CB-03 | COUPLER/SECTIONALISING CB - GALWAY GIS 110-GALWAY GIS 110-110SA1-2CB | 5 | 5 | 5 | Scheduled | 15/05/2023 | 19/05/2023
TO-23-GAL GIS-110SB1-2CB-03 | COUPLER/SECTIONALISING CB - GALWAY GIS 110-GALWAY GIS 110-110SB1-2CB | 5 | 5 | 5 | Scheduled | 15/05/2023 | 19/05/2023
TO-23-110 kV A2 @ LOU-01 | BUSBAR SECTION - LOUTH 110-LOUTH 110-110A2 | 146 | 103 | 103 | Scheduled | 15/05/2023 | 07/10/2023
TO-23-110 kV B2 @ LOU-01 | BUSBAR SECTION - LOUTH 110-LOUTH 110-110B2 | 146 | 103 | 103 | Scheduled | 15/05/2023 | 07/10/2023
TO-23-LOU-220K1-2-07 | COUPLER/SECTIONALISING CB - LOUTH 220-LOUTH 220-220K1-2 | 3 | 3 | 3 | Scheduled | 15/05/2023 | 17/05/2023
TO-23-220 kV A2 @ PB-01 | BUSBAR SECTION - POOLBEG 220-POOLBEG 220-220A2 | 9 | 7 | 7 | Scheduled | 15/05/2023 | 23/05/2023
TO-23-220 kV B2 @ PB-01 | BUSBAR SECTION - POOLBEG 220-POOLBEG 220-220B2 | 9 | 7 | 7 | Scheduled | 15/05/2023 | 23/05/2023
TO-23-PB-220K2-3-03 | COUPLER/SECTIONALISING CB - POOLBEG 220-POOLBEG 220-220K2-3 | 5 | 5 | 5 | Scheduled | 15/05/2023 | 19/05/2023
TO-23-PB-220SA1-2-03 | SECTIONALISING DISCONNECT - POOLBEG 220-POOLBEG 220-220SA1-2 | 5 | 5 | 5 | Scheduled | 15/05/2023 | 19/05/2023
TO-23-PB-220SA1-2-04 | SECTIONALISING DISCONNECT - POOLBEG 220-POOLBEG 220-220SA1-2 | 9 | 7 | 7 | Scheduled | 15/05/2023 | 23/05/2023
TO-23-PB-220SB1-2-03 | SECTIONALISING DISCONNECT - POOLBEG 220-POOLBEG 220-220SB1-2 | 9 | 7 | 7 | Scheduled | 15/05/2023 | 23/05/2023
TO-23-PB-220SB1-2-04 | SECTIONALISING DISCONNECT - POOLBEG 220-POOLBEG 220-220SB1-2 | 5 | 5 | 5 | Scheduled | 15/05/2023 | 19/05/2023
TO-23-CD-T103-01 | GENERATOR TRANSFORMER - CARRIGADROHID 110-CARRIGADROHID G3-T103 | 9 | 7 | 7 | Scheduled | 16/05/2023 | 24/05/2023
TO-23-110 kV A1 @ AA GIS-01 | BUSBAR SECTION - ARDNACRUSHA GIS 110-ARDNACRUSHA GIS 110-110A1 | 5 | 5 |  | Scheduled | 22/05/2023 | 26/05/2023
TO-23-110 kV B1 @ AA GIS-01 | BUSBAR SECTION - ARDNACRUSHA GIS 110-ARDNACRUSHA GIS 110-110B1 | 5 | 5 | 5 | Scheduled | 22/05/2023 | 26/05/2023
TO-23-AA GIS-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - ARDNACRUSHA GIS 110-ARDNACRUSHA GIS 110-110SA1-2CB | 5 | 5 | 5 | Scheduled | 22/05/2023 | 26/05/2023
TO-23-AA GIS-110SA1-3CB-02 | COUPLER/SECTIONALISING CB - ARDNACRUSHA GIS 110-ARDNACRUSHA GIS 110-110SA1-3CB | 5 | 5 | 5 | Scheduled | 22/05/2023 | 26/05/2023
TO-23-AA GIS-110SB1-2CB-02 | COUPLER/SECTIONALISING CB - ARDNACRUSHA GIS 110-ARDNACRUSHA GIS 110-110SB1-2CB | 5 | 5 | 5 | Scheduled | 22/05/2023 | 26/05/2023
TO-23-AA GIS-110SB1-3CB-02 | COUPLER/SECTIONALISING CB - ARDNACRUSHA GIS 110-ARDNACRUSHA GIS 110-110SB1-3CB | 5 | 5 | 5 | Scheduled | 22/05/2023 | 26/05/2023
TO-23-AA GIS-LIM-1-01 | 110kV FEEDER - ARDNACRUSHA GIS 110-LIMERICK 110-1 | 5 | 5 | 5 | Scheduled | 22/05/2023 | 26/05/2023
TO-23-110 kV A1 @ CBT-04 | BUSBAR SECTION - CASTLEBAGOT 110-CASTLEBAGOT 110-110A1 | 5 | 5 | 5 | Scheduled | 22/05/2023 | 26/05/2023
TO-23-110 kV A2 @ CBT-01 | BUSBAR SECTION - CASTLEBAGOT 110-CASTLEBAGOT 110-110A2 | 5 | 5 | 5 | Scheduled | 22/05/2023 | 26/05/2023
TO-23-CBT-110K1-06 | COUPLER/SECTIONALISING CB - CASTLEBAGOT 110-CASTLEBAGOT 110-110K1 | 5 | 5 | 5 | Scheduled | 22/05/2023 | 26/05/2023
TO-23-CBT-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - CASTLEBAGOT 110-CASTLEBAGOT 110-110SA1-2CB | 5 | 5 | 5 | Scheduled | 22/05/2023 | 26/05/2023
TO-23-CBT-110SA2-4CB-07 | COUPLER/SECTIONALISING CB - CASTLEBAGOT 110-CASTLEBAGOT 110-110SA2-4CB | 5 | 5 | 5 | Scheduled | 22/05/2023 | 26/05/2023
TO-23-KLN-T2101-01 | TRANSFORMER - KILLONAN 220-KILLONAN 110-T2101 | 5 | 5 |  | Scheduled | 22/05/2023 | 26/05/2023
TO-23-KPG-TB-1-02 | 220kV FEEDER - KILPADDOGE 220-TARBERT 220-1 | 149 | 105 | 105 | Scheduled | 22/05/2023 | 17/10/2023
TO-23-KPG-TRL-1-03 | 110kV FEEDER - KILPADDOGE 110-TRALEE 110-1 | 9 | 7 | 7 | Scheduled | 22/05/2023 | 30/05/2023
TO-23-MP GIS-T4001-01 | GENERATOR TRANSFORMER - MONEYPOINT GIS 400-MONEYPOINT GIS G1-T4001 | 2 | 2 | 2 | Scheduled | 22/05/2023 | 23/05/2023
TO-23-TB-220K1-2-01 | COUPLER/SECTIONALISING CB - TARBERT 220-TARBERT 220-220K1-2 | 149 | 105 | 105 | Scheduled | 22/05/2023 | 17/10/2023
TO-23-TB-T2004-03 | GENERATOR TRANSFORMER - TARBERT 220-TARBERT G4-T2004 | 149 | 105 | 105 | Scheduled | 22/05/2023 | 17/10/2023
TO-23-TB-T2101-03 | TRANSFORMER - TARBERT 220-TARBERT 110-T2101 | 149 | 105 | 105 | Scheduled | 22/05/2023 | 17/10/2023
TO-23-GI-WAT-1-01 | 110kV FEEDER - GREAT ISLAND 110-WATERFORD 110-1 | 4 | 4 | 4 | Scheduled | 23/05/2023 | 26/05/2023
TO-23-110 kV A2 @ MUL-01 | BUSBAR SECTION - MULLINGAR 110-MULLINGAR 110-110A2 | 4 | 4 | 4 | Proposed | 23/05/2023 | 26/05/2023
TO-23-MUL-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - MULLINGAR 110-MULLINGAR 110-110SA1-2CB | 4 | 4 | 4 | Proposed | 23/05/2023 | 26/05/2023
TO-23-MUL-T102-01 | DISTRIBUTION TRANSFORMER - MULLINGAR 110-MULLINGAR 10-T102 | 4 | 4 | 4 | Reference (Proposed) | 23/05/2023 | 26/05/2023
TO-23-MUL-T142-01 | DISTRIBUTION TRANSFORMER - MULLINGAR 110-MULLINGAR 38-T142 | 4 | 4 | 4 | Reference (Proposed) | 23/05/2023 | 26/05/2023
TO-23-DFR-T122-02 | DISTRIBUTION TRANSFORMER - DUNFIRTH 110-DUNFIRTH 20-T122 | 2 | 2 | 2 | Reference | 24/05/2023 | 25/05/2023
TO-23-DFR,T-DFR-1-03 | 110kV FEEDER - DUNFIRTH tee-DUNFIRTH 110-1 | 2 | 2 | 2 | Scheduled | 24/05/2023 | 25/05/2023
TO-23-DFR,T-KIN-1-06 | 110kV FEEDER - DUNFIRTH tee-KINNEGAD 110-1 | 2 | 2 | 2 | Scheduled | 24/05/2023 | 25/05/2023
TO-23-GAL-GAL GIS-1-02 | 110kV FEEDER - GALWAY 110-GALWAY GIS 110-1 | 2 | 2 | 2 | Scheduled | 24/05/2023 | 25/05/2023
TO-23-110 kV A2 @ GAL GIS-02 | BUSBAR SECTION - GALWAY GIS 110-GALWAY GIS 110-110A2 | 2 | 2 | 2 | Scheduled | 24/05/2023 | 25/05/2023
TO-23-110 kV B2 @ GAL GIS-02 | BUSBAR SECTION - GALWAY GIS 110-GALWAY GIS 110-110B2 | 2 | 2 | 2 | Scheduled | 24/05/2023 | 25/05/2023
TO-23-GAL GIS-110K2-03 | COUPLER/SECTIONALISING CB - GALWAY GIS 110-GALWAY GIS 110-110K2 | 2 | 2 | 2 | Scheduled | 24/05/2023 | 25/05/2023
TO-23-GAL GIS-110SA1-2CB-04 | COUPLER/SECTIONALISING CB - GALWAY GIS 110-GALWAY GIS 110-110SA1-2CB | 2 | 2 | 2 | Scheduled | 24/05/2023 | 25/05/2023
TO-23-GAL GIS-110SB1-2CB-04 | COUPLER/SECTIONALISING CB - GALWAY GIS 110-GALWAY GIS 110-110SB1-2CB | 2 | 2 | 2 | Scheduled | 24/05/2023 | 25/05/2023
TO-23-MLC-T121-01 | GENERATOR TRANSFORMER - MOUNTLUCAS 110-MOUNTLUCAS 20-T121 | 1 | 1 | 1 | Scheduled | 24/05/2023 | 24/05/2023
TO-23-PB-T2007/8-03 | GENERATOR TRANSFORMER - POOLBEG 220-POOLBEG G7/8-T2007/8 | 3 | 3 | 3 | Scheduled | 24/05/2023 | 26/05/2023
TO-23-110 kV B1 @ CF-01 | BUSBAR SECTION - CATHALEENS FALL 110-CATHALEENS FALL 110-110B1 | 1 | 1 | 1 | Scheduled | 25/05/2023 | 25/05/2023
TO-23-CF-T103-02 | GENERATOR TRANSFORMER - CATHALEENS FALL 110-CATHALEENS FALL G3-T103 | 1 | 1 | 1 | Scheduled | 25/05/2023 | 25/05/2023
TO-23-CKM-PB-1-04 | 220kV FEEDER - CARRICKMINES 220-POOLBEG 220-1 | 3 | 1 | 1 | Scheduled | 26/05/2023 | 28/05/2023
TO-23-CKM-PST2201-04 | TRANSFORMER - CARRICKMINES 220-CARRICKMINES 220-PST2201 | 3 | 1 | 1 | Scheduled | 26/05/2023 | 28/05/2023
TO-23-HN-T2002-01 | GENERATOR TRANSFORMER - HUNTSTOWN 220-HUNTSTOWN G2-T2002 | 16 | 10 | 10 | Scheduled | 26/05/2023 | 10/06/2023
TO-23-INC-PB-1-02 | 220kV FEEDER - INCHICORE 220-POOLBEG 220-1 | 3 | 1 | 1 | Scheduled | 26/05/2023 | 28/05/2023
TO-23-PB-220K2-3-04 | COUPLER/SECTIONALISING CB - POOLBEG 220-POOLBEG 220-220K2-3 | 3 | 1 | 1 | Scheduled | 26/05/2023 | 28/05/2023
TO-23-PB-220SA1-2-02 | SECTIONALISING DISCONNECT - POOLBEG 220-POOLBEG 220-220SA1-2 | 3 | 1 | 1 | Scheduled | 26/05/2023 | 28/05/2023
TO-23-PB-220SB1-2-02 | SECTIONALISING DISCONNECT - POOLBEG 220-POOLBEG 220-220SB1-2 | 3 | 1 | 1 | Scheduled | 26/05/2023 | 28/05/2023
TO-23-PB-R2001-03 | CAPACITOR/SVC/REACTOR - POOLBEG 220-POOLBEG 220-R2001 | 3 | 1 | 1 | Scheduled | 26/05/2023 | 28/05/2023
TO-23-CSH-GAL-2-02 | 110kV FEEDER - CASHLA 110-GALWAY 110-2 | 86 | 60 |  | Scheduled | 29/05/2023 | 22/08/2023
TO-23-110 kV A1/A2 @ CLA-02 | BUSBAR SECTION - CLASHAVOON 110-CLASHAVOON 110-110A1-A2 | 10 | 7 | 7 | Scheduled | 29/05/2023 | 07/06/2023
TO-23-110 kV B1/B2 @ CLA-02 | BUSBAR SECTION - CLASHAVOON 110-CLASHAVOON 110-110B1-B2 | 10 | 7 | 7 | Scheduled | 29/05/2023 | 07/06/2023
TO-23-CLA-110K1-2-01 | COUPLER/SECTIONALISING CB - CLASHAVOON 110-CLASHAVOON 110-110K1-2 | 10 | 7 | 7 | Scheduled | 29/05/2023 | 07/06/2023
TO-23-220 kV A1 @ CDU-02 | BUSBAR SECTION - CORDUFF 220-CORDUFF 220-220A1 | 13 | 9 | 9 | Scheduled | 29/05/2023 | 10/06/2023
TO-23-220 kV B1 @ CDU-02 | BUSBAR SECTION - CORDUFF 220-CORDUFF 220-220B1 | 13 | 9 | 9 | Scheduled | 29/05/2023 | 10/06/2023
TO-23-CDU-HN-1-01 | 220kV FEEDER - CORDUFF 220-HUNTSTOWN 220-1 | 13 | 9 | 9 | Scheduled | 29/05/2023 | 10/06/2023
TO-23-KPG-110K3-01 | COUPLER/SECTIONALISING CB - KILPADDOGE 110-KILPADDOGE 110-110K3 | 1 | 1 | 1 | Scheduled | 29/05/2023 | 29/05/2023
TO-23-REM-110SA1-02 | SECTIONALISING DISCONNECT - REAMORE 110-REAMORE 110-110SA1 | 5 | 5 | 5 | Scheduled | 29/05/2023 | 02/06/2023
TO-23-REM-110SA2-02 | SECTIONALISING DISCONNECT - REAMORE 110-REAMORE 110-110SA2 | 5 | 5 | 5 | Scheduled | 29/05/2023 | 02/06/2023
TO-23-REM-T141-03 | DISTRIBUTION TRANSFORMER - REAMORE 110-REAMORE 38-T141 | 5 | 5 | 5 | Reference | 29/05/2023 | 02/06/2023
TO-23-REM-T142-02 | DISTRIBUTION TRANSFORMER - REAMORE 110-REAMORE 38-T142 | 5 | 5 | 5 | Reference | 29/05/2023 | 02/06/2023
TO-23-REM-TRL-1-02 | 110kV FEEDER - REAMORE 110-TRALEE 110-1 | 5 | 5 | 5 | Scheduled | 29/05/2023 | 02/06/2023
TO-23-110 kV A1 @ SNU-03 | BUSBAR SECTION - SNUGBOROUGH 110-SNUGBOROUGH 110-110A1 | 3 | 3 | 3 | Scheduled | 29/05/2023 | 31/05/2023
TO-23-110 kV B1 @ SNU-03 | BUSBAR SECTION - SNUGBOROUGH 110-SNUGBOROUGH 110-110B1 | 3 | 3 | 3 | Scheduled | 29/05/2023 | 31/05/2023
TO-23-SNU-110K1-03 | COUPLER/SECTIONALISING CB - SNUGBOROUGH 110-SNUGBOROUGH 110-110K1 | 3 | 3 | 3 | Scheduled | 29/05/2023 | 31/05/2023
TO-23-SNU-110SA1-2CB-03 | COUPLER/SECTIONALISING CB - SNUGBOROUGH 110-SNUGBOROUGH 110-110SA1-2CB | 3 | 3 | 3 | Scheduled | 29/05/2023 | 31/05/2023
TO-23-SNU-110SB1-2CB-03 | COUPLER/SECTIONALISING CB - SNUGBOROUGH 110-SNUGBOROUGH 110-110SB1-2CB | 3 | 3 | 3 | Scheduled | 29/05/2023 | 31/05/2023
TO-23-BNK-CBT-2-01 | 110kV FEEDER - BARNAKYLE 110-CASTLEBAGOT 110-2 | 2 | 2 | 2 | Scheduled | 30/05/2023 | 31/05/2023
TO-23-KPG-110SA2-4CB-02 | COUPLER/SECTIONALISING CB - KILPADDOGE 110-KILPADDOGE 110-110SA2-4CB | 1 | 1 | 1 | Scheduled | 30/05/2023 | 30/05/2023
TO-23-GAL-GAL GIS-1-01 | 110kV FEEDER - GALWAY 110-GALWAY GIS 110-1 | 2 | 2 | 2 | Scheduled | 31/05/2023 | 01/06/2023
TO-23-110 kV A2 @ GAL GIS-01 | BUSBAR SECTION - GALWAY GIS 110-GALWAY GIS 110-110A2 | 2 | 2 | 2 | Scheduled | 31/05/2023 | 01/06/2023
TO-23-110 kV B2 @ GAL GIS-01 | BUSBAR SECTION - GALWAY GIS 110-GALWAY GIS 110-110B2 | 2 | 2 | 2 | Scheduled | 31/05/2023 | 01/06/2023
TO-23-GAL GIS-110K2-01 | COUPLER/SECTIONALISING CB - GALWAY GIS 110-GALWAY GIS 110-110K2 | 2 | 2 | 2 | Scheduled | 31/05/2023 | 01/06/2023
TO-23-GAL GIS-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - GALWAY GIS 110-GALWAY GIS 110-110SA1-2CB | 2 | 2 | 2 | Scheduled | 31/05/2023 | 01/06/2023
TO-23-GAL GIS-110SB1-2CB-01 | COUPLER/SECTIONALISING CB - GALWAY GIS 110-GALWAY GIS 110-110SB1-2CB | 2 | 2 | 2 | Scheduled | 31/05/2023 | 01/06/2023
TO-23-KPG-110SB1-2CB-01 | COUPLER/SECTIONALISING CB - KILPADDOGE 110-KILPADDOGE 110-110SB1-2CB | 1 | 1 | 1 | Scheduled | 31/05/2023 | 31/05/2023
TO-23-110 kV A1 @ BAG-02 | BUSBAR SECTION - BARNAGEERAGH 110-BARNAGEERAGH 110-110A1 | 2 | 2 |  | Scheduled | 01/06/2023 | 02/06/2023
TO-23-110 kV B1 @ BAG-02 | BUSBAR SECTION - BARNAGEERAGH 110-BARNAGEERAGH 110-110B1 | 2 | 2 |  | Scheduled | 01/06/2023 | 02/06/2023
TO-23-BAG-110K1-01 | COUPLER/SECTIONALISING CB - BARNAGEERAGH 110-BARNAGEERAGH 110-110K1 | 2 | 2 |  | Scheduled | 01/06/2023 | 02/06/2023
TO-23-BAG-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - BARNAGEERAGH 110-BARNAGEERAGH 110-110SA1-2CB | 2 | 2 |  | Scheduled | 01/06/2023 | 02/06/2023
TO-23-BAG-110SB1-2CB-01 | COUPLER/SECTIONALISING CB - BARNAGEERAGH 110-BARNAGEERAGH 110-110SB1-2CB | 2 | 2 |  | Scheduled | 01/06/2023 | 02/06/2023
TO-23-110 kV A1 @ CUL-01 | BUSBAR SECTION - CULLENAGH 110-CULLENAGH 110-110A1 | 12 | 7 | 7 | Scheduled | 01/06/2023 | 12/06/2023
TO-23-110 kV B1 @ CUL-01 | BUSBAR SECTION - CULLENAGH 110-CULLENAGH 110-110B1 | 12 | 7 | 7 | Scheduled | 01/06/2023 | 12/06/2023
TO-23-KPG-110SB1-3CB-02 | COUPLER/SECTIONALISING CB - KILPADDOGE 110-KILPADDOGE 110-110SB1-3CB | 1 | 1 | 1 | Scheduled | 01/06/2023 | 01/06/2023
TO-23-110 kV A1 @ SNU-01 | BUSBAR SECTION - SNUGBOROUGH 110-SNUGBOROUGH 110-110A1 | 2 | 2 |  | Scheduled | 01/06/2023 | 02/06/2023
TO-23-110 kV B1 @ SNU-01 | BUSBAR SECTION - SNUGBOROUGH 110-SNUGBOROUGH 110-110B1 | 2 | 2 |  | Scheduled | 01/06/2023 | 02/06/2023
TO-23-SNU-110K1-02 | COUPLER/SECTIONALISING CB - SNUGBOROUGH 110-SNUGBOROUGH 110-110K1 | 2 | 2 |  | Scheduled | 01/06/2023 | 02/06/2023
TO-23-SNU-110SA1-2CB-02 | COUPLER/SECTIONALISING CB - SNUGBOROUGH 110-SNUGBOROUGH 110-110SA1-2CB | 2 | 2 |  | Scheduled | 01/06/2023 | 02/06/2023
TO-23-SNU-110SB1-2CB-02 | COUPLER/SECTIONALISING CB - SNUGBOROUGH 110-SNUGBOROUGH 110-110SB1-2CB | 2 | 2 |  | Scheduled | 01/06/2023 | 02/06/2023
TO-23-KPG-110SB2-4CB-01 | COUPLER/SECTIONALISING CB - KILPADDOGE 110-KILPADDOGE 110-110SB2-4CB | 1 | 1 | 1 | Scheduled | 02/06/2023 | 02/06/2023
TO-23-AA GIS-T103-01 | GENERATOR TRANSFORMER - ARDNACRUSHA GIS 110-ARDNACRUSHA GIS G3-T103 | 32 | 24 | 24 | Scheduled | 06/06/2023 | 07/07/2023
TO-23-220 kV A4 @ CDU-01 | BUSBAR SECTION - CORDUFF 220-CORDUFF 220-220A4 | 60 | 44 | 44 | Scheduled | 06/06/2023 | 04/08/2023
TO-23-220 kV B4 @ CDU-01 | BUSBAR SECTION - CORDUFF 220-CORDUFF 220-220B4 | 60 | 44 | 44 | Scheduled | 06/06/2023 | 04/08/2023
TO-23-CRU-T221-01 | TSO CUSTOMER TRANSFORMER - CRUISERATH 220-CRUISERATH 20-T221 | 4 | 4 | 4 | Scheduled | 06/06/2023 | 09/06/2023
TO-23-KLS-KKY-1-02 | 110kV FEEDER - KELLIS 110-KILKENNY 110-1 | 67 | 48 | 48 | Scheduled | 06/06/2023 | 11/08/2023
TO-23-KKY-110SA1-2CB-02 | COUPLER/SECTIONALISING CB - KILKENNY 110-KILKENNY 110-110SA1-2CB | 67 | 48 | 48 | Scheduled | 06/06/2023 | 11/08/2023
TO-23-KKY-T141-02 | DISTRIBUTION TRANSFORMER - KILKENNY 110-KILKENNY 38-T141 | 67 | 48 | 48 | Reference | 06/06/2023 | 11/08/2023
TO-23-KPG-KNR-1-110-01 | 110kV FEEDER - KILPADDOGE 110-KNOCKANURE 110-1-110 | 3 | 3 |  | Scheduled | 06/06/2023 | 08/06/2023
TO-23-110 kV A1 @ BVK-01 | BUSBAR SECTION - BALLYVOUSKILL 110-BALLYVOUSKILL 110-110A1 | 3 | 3 | 3 | Scheduled | 07/06/2023 | 09/06/2023
TO-23-110 kV B1 @ BVK-01 | BUSBAR SECTION - BALLYVOUSKILL 110-BALLYVOUSKILL 110-110B1 | 3 | 3 | 3 | Scheduled | 07/06/2023 | 09/06/2023
TO-23-BVK-110K1-01 | COUPLER/SECTIONALISING CB - BALLYVOUSKILL 110-BALLYVOUSKILL 110-110K1 | 3 | 3 | 3 | Scheduled | 07/06/2023 | 09/06/2023
TO-23-BVK-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - BALLYVOUSKILL 110-BALLYVOUSKILL 110-110SA1-2CB | 3 | 3 | 3 | Scheduled | 07/06/2023 | 09/06/2023
TO-23-BVK-110SB1-2CB-01 | COUPLER/SECTIONALISING CB - BALLYVOUSKILL 110-BALLYVOUSKILL 110-110SB1-2CB | 3 | 3 | 3 | Scheduled | 07/06/2023 | 09/06/2023
TO-23-BAN-BRI-2-01 | 110kV FEEDER - BANDON 110-BRINNY 110-2 | 1 | 1 | 1 | Scheduled | 07/06/2023 | 07/06/2023
TO-23-BRI-T102-01 | TSO CUSTOMER TRANSFORMER - BRINNY 110-BRINNY 10-T102 | 1 | 1 | 1 | Scheduled | 07/06/2023 | 07/06/2023
TO-23-110 kV A1 @ CAH-01 | BUSBAR SECTION - CAHIR 110-CAHIR 110-110A1 | 2 | 2 | 2 | Scheduled | 07/06/2023 | 08/06/2023
TO-23-110 kV A2 @ CAH-01 | BUSBAR SECTION - CAHIR 110-CAHIR 110-110A2 | 2 | 2 | 2 | Scheduled | 07/06/2023 | 08/06/2023
TO-23-CAH-110K1-2-03 | COUPLER/SECTIONALISING CB - CAHIR 110-CAHIR 110-110K1-2 | 2 | 2 | 2 | Scheduled | 07/06/2023 | 08/06/2023
TO-23-KPG-RAT-1-01 | 110kV FEEDER - KILPADDOGE 110-RATHKEALE 110-1 | 1 | 1 | 1 | Scheduled | 07/06/2023 | 07/06/2023
TO-23-110 kV A1 @ PA-01 | BUSBAR SECTION - POLLAPHUCA 110-POLLAPHUCA 110-110A1 | 17 | 13 | 13 | Scheduled | 07/06/2023 | 23/06/2023
TO-23-110 kV A2 @ PA-01 | BUSBAR SECTION - POLLAPHUCA 110-POLLAPHUCA 110-110A2 | 17 | 13 | 13 | Scheduled | 07/06/2023 | 23/06/2023
TO-23-PA-110SA1-01 | SECTIONALISING DISCONNECT - POLLAPHUCA 110-POLLAPHUCA 110-110SA1 | 17 | 13 | 13 | Scheduled | 07/06/2023 | 23/06/2023
TO-23-PA-110SA2-01 | SECTIONALISING DISCONNECT - POLLAPHUCA 110-POLLAPHUCA 110-110SA2 | 17 | 13 | 13 | Scheduled | 07/06/2023 | 23/06/2023
TO-23-STR-T141-01 | DISTRIBUTION TRANSFORMER - STRATFORD 110-STRATFORD 38-T141 | 17 | 13 | 13 | Reference | 07/06/2023 | 23/06/2023
TO-23-STR,T-CLW-1-01 | 110kV FEEDER - STRATFORD tee-CARLOW 110-1 | 17 | 13 | 13 | Scheduled | 07/06/2023 | 23/06/2023
TO-23-STR,T-PA-1-03 | 110kV FEEDER - STRATFORD tee-POLLAPHUCA 110-1 | 17 | 13 | 13 | Scheduled | 07/06/2023 | 23/06/2023
TO-23-STR,T-STR-1-01 | 110kV FEEDER - STRATFORD tee-STRATFORD 110-1 | 17 | 13 | 13 | Scheduled | 07/06/2023 | 23/06/2023
TO-23-220 kV A1 @ WOO-01 | BUSBAR SECTION - WOODLAND 220-WOODLAND 220-220A1 | 45 | 33 | 33 | Scheduled | 07/06/2023 | 21/07/2023
TO-23-BAN-BRI-1-01 | 110kV FEEDER - BANDON 110-BRINNY 110-1 | 9 | 7 | 7 | Scheduled | 08/06/2023 | 16/06/2023
TO-23-BRI-T101-01 | TSO CUSTOMER TRANSFORMER - BRINNY 110-BRINNY 10-T101 | 9 | 7 | 7 | Scheduled | 08/06/2023 | 16/06/2023
TO-23-INC-PB-1-04 | 220kV FEEDER - INCHICORE 220-POOLBEG 220-1 | 2 | 2 | 2 | Scheduled | 08/06/2023 | 09/06/2023
TO-23-PA-T101-01 | GENERATOR TRANSFORMER - POLLAPHUCA 110-POLLAPHUCA G1-T101 | 51 | 37 | 37 | Scheduled | 08/06/2023 | 28/07/2023
TO-23-220 kV A1 @ PB-02 | BUSBAR SECTION - POOLBEG 220-POOLBEG 220-220A1 | 2 | 2 | 2 | Scheduled | 08/06/2023 | 09/06/2023
TO-23-220 kV A2 @ PB-02 | BUSBAR SECTION - POOLBEG 220-POOLBEG 220-220A2 | 2 | 2 | 2 | Scheduled | 08/06/2023 | 09/06/2023
TO-23-220 kV B1 @ PB-02 | BUSBAR SECTION - POOLBEG 220-POOLBEG 220-220B1 | 2 | 2 | 2 | Scheduled | 08/06/2023 | 09/06/2023
TO-23-220 kV B2 @ PB-02 | BUSBAR SECTION - POOLBEG 220-POOLBEG 220-220B2 | 2 | 2 | 2 | Scheduled | 08/06/2023 | 09/06/2023
TO-23-PB-220SA1-2-05 | SECTIONALISING DISCONNECT - POOLBEG 220-POOLBEG 220-220SA1-2 | 2 | 2 | 2 | Scheduled | 08/06/2023 | 09/06/2023
TO-23-PB-220SB1-2-05 | SECTIONALISING DISCONNECT - POOLBEG 220-POOLBEG 220-220SB1-2 | 2 | 2 | 2 | Scheduled | 08/06/2023 | 09/06/2023
TO-23-BYH-T2102-02 | TRANSFORMER - BALLYNAHULLA 220-BALLYNAHULLA 110-T2102 | 15 | 11 | 11 | Scheduled | 09/06/2023 | 23/06/2023
TO-23-COW-T142-01 | DISTRIBUTION TRANSFORMER - COW CROSS 110-COW CROSS 38-T142 | 16 | 10 |  | Reference | 10/06/2023 | 25/06/2023
TO-23-ATE-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - ATHEA 110-ATHEA 110-110SA1-2CB | 5 | 5 | 5 | Scheduled | 12/06/2023 | 16/06/2023
TO-23-ATE-DRO-1-01 | 110kV FEEDER - ATHEA 110-DROMADA 110-1 | 5 | 5 | 5 | Scheduled | 12/06/2023 | 16/06/2023
TO-23-ATE-KNR-1-01 | 110kV FEEDER - ATHEA 110-KNOCKANURE 110-1 | 5 | 5 |  | Scheduled | 12/06/2023 | 16/06/2023
TO-23-ATE-T121-01 | GENERATOR TRANSFORMER - ATHEA 110-ATHEA 20-T121 | 5 | 5 | 5 | Scheduled | 12/06/2023 | 16/06/2023
TO-23-ATE-TOB-1-01 | 110kV FEEDER - ATHEA 110-TOBERTOREEN 110-1 | 5 | 5 | 5 | Scheduled | 12/06/2023 | 16/06/2023
TO-23-CRU-T223-01 | TSO CUSTOMER TRANSFORMER - CRUISERATH 220-CRUISERATH 20-T223 | 4 | 4 | 4 | Scheduled | 12/06/2023 | 15/06/2023
TO-23-DRO-T121-01 | GENERATOR TRANSFORMER - DROMADA 110-DROMADA 20-T121 | 5 | 5 | 5 | Scheduled | 12/06/2023 | 16/06/2023
TO-23-ENN-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - ENNIS 110-ENNIS 110-110SA1-2CB | 5 | 5 | 5 | Scheduled | 12/06/2023 | 16/06/2023
TO-23-ENN-SLC-1-01 | 110kV FEEDER - ENNIS 110-SLIEVECALLAN 110-1 | 5 | 5 | 5 | Scheduled | 12/06/2023 | 16/06/2023
TO-23-ENN-T101-01 | DISTRIBUTION TRANSFORMER - ENNIS 110-ENNIS 10-T101 | 5 | 5 | 5 | Reference | 12/06/2023 | 16/06/2023
TO-23-ENN-T141-01 | DISTRIBUTION TRANSFORMER - ENNIS 110-ENNIS 38-T141 | 5 | 5 | 5 | Reference | 12/06/2023 | 16/06/2023
TO-23-FIN-NW-1-03 | 220kV FEEDER - FINGLAS 220-NORTH WALL 220-1 | 13 | 10 | 10 | Scheduled | 12/06/2023 | 24/06/2023
TO-23-KYT-T232-01 | TSO CUSTOMER TRANSFORMER - KELLYSTOWN 220-KELLYSTOWN 34.5-T232 | 2 | 2 | 2 | Scheduled | 12/06/2023 | 13/06/2023
TO-23-220 kV A2 @ MP GIS-01 | BUSBAR SECTION - MONEYPOINT GIS 220-MONEYPOINT GIS 220-220A2 | 5 | 5 | 5 | Scheduled | 12/06/2023 | 16/06/2023
TO-23-220 kV B2 @ MP GIS-01 | BUSBAR SECTION - MONEYPOINT GIS 220-MONEYPOINT GIS 220-220B2 | 5 | 5 | 5 | Scheduled | 12/06/2023 | 16/06/2023
TO-23-MP GIS-220K2-01 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 220-MONEYPOINT GIS 220-220K2 | 5 | 5 | 5 | Scheduled | 12/06/2023 | 16/06/2023
TO-23-MP GIS-220SA1-2CB-01 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 220-MONEYPOINT GIS 220-220SA1-2CB | 5 | 5 | 5 | Scheduled | 12/06/2023 | 16/06/2023
TO-23-MP GIS-220SB1-2CB-01 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 220-MONEYPOINT GIS 220-220SB1-2CB | 5 | 5 | 5 | Scheduled | 12/06/2023 | 16/06/2023
TO-23-400 kV A4 @ MP GIS-02 | BUSBAR SECTION - MONEYPOINT GIS 400-MONEYPOINT GIS 400-400A4 | 5 | 5 | 5 | Scheduled | 12/06/2023 | 16/06/2023
TO-23-400 kV B4 @ MP GIS-01 | BUSBAR SECTION - MONEYPOINT GIS 400-MONEYPOINT GIS 400-400B4 | 5 | 5 | 5 | Scheduled | 12/06/2023 | 16/06/2023
TO-23-MP GIS-400K4-02 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 400-MONEYPOINT GIS 400-400K4 | 5 | 5 | 5 | Scheduled | 12/06/2023 | 16/06/2023
TO-23-MP GIS-400SA2-4CB-02 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 400-MONEYPOINT GIS 400-400SA2-4CB | 5 | 5 | 5 | Scheduled | 12/06/2023 | 16/06/2023
TO-23-MP GIS-400SB2-4CB-01 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 400-MONEYPOINT GIS 400-400SB2-4CB | 5 | 5 | 5 | Scheduled | 12/06/2023 | 16/06/2023
TO-23-NW-PB-1-03 | 220kV FEEDER - NORTH WALL 220-POOLBEG 220-1 | 13 | 10 | 10 | Scheduled | 12/06/2023 | 24/06/2023
TO-23-NW-T2004/5-01 | GENERATOR TRANSFORMER - NORTH WALL 220-NORTH WALL G4/5-T2004/5 | 13 | 10 | 10 | Scheduled | 12/06/2023 | 24/06/2023
TO-23-SLC-110SA1-01 | SECTIONALISING DISCONNECT - SLIEVECALLAN 110-SLIEVECALLAN 110-110SA1 | 5 | 5 | 5 | Scheduled | 12/06/2023 | 16/06/2023
TO-23-SLC-110SA2-01 | SECTIONALISING DISCONNECT - SLIEVECALLAN 110-SLIEVECALLAN 110-110SA2 | 5 | 5 | 5 | Scheduled | 12/06/2023 | 16/06/2023
TO-23-SLC-T121-01 | GENERATOR TRANSFORMER - SLIEVECALLAN 110-SLIEVECALLAN 20-T121 | 5 | 5 | 5 | Scheduled | 12/06/2023 | 16/06/2023
TO-23-SLC-T122-01 | GENERATOR TRANSFORMER - SLIEVECALLAN 110-SLIEVECALLAN 20-T122 | 5 | 5 | 5 | Scheduled | 12/06/2023 | 16/06/2023
TO-23-TOB-T132-01 | GENERATOR TRANSFORMER - TOBERTOREEN 110-TOBERTOREEN 33-T132 | 5 | 5 | 5 | Scheduled | 12/06/2023 | 16/06/2023
TO-23-ANR-DOO-1-03 | 110kV FEEDER - ANNER 110-DOON 110-1 | 2 | 2 | 2 | Scheduled | 13/06/2023 | 14/06/2023
TO-23-ANR-T101-02 | TSO CUSTOMER TRANSFORMER - ANNER 110-ANNER 10-T101 | 2 | 2 | 2 | Reference | 13/06/2023 | 14/06/2023
TO-23-ANR-T103-02 | TSO CUSTOMER TRANSFORMER - ANNER 110-ANNER 10-T103 | 2 | 2 | 2 | Reference | 13/06/2023 | 14/06/2023
TO-23-110 kV A2 @ CSH-01 | BUSBAR SECTION - CASHLA 110-CASHLA 110-110A2 | 71 | 50 |  | Scheduled | 13/06/2023 | 22/08/2023
TO-23-110 kV B2 @ CSH-02 | BUSBAR SECTION - CASHLA 110-CASHLA 110-110B2 | 71 | 50 |  | Scheduled | 13/06/2023 | 22/08/2023
TO-23-110 kV A6 @ FIN GIS-01 | BUSBAR SECTION - FINGLAS GIS 110-FINGLAS GIS 110-110A6 | 1 | 1 | 1 | Scheduled | 13/06/2023 | 13/06/2023
TO-23-110 kV B6 @ FIN GIS-01 | BUSBAR SECTION - FINGLAS GIS 110-FINGLAS GIS 110-110B6 | 1 | 1 | 1 | Scheduled | 13/06/2023 | 13/06/2023
TO-23-FIN GIS-110K6-02 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110K6 | 1 | 1 | 1 | Scheduled | 13/06/2023 | 13/06/2023
TO-23-FIN GIS-110SA4-6CB-01 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110SA4-6CB | 1 | 1 | 1 | Scheduled | 13/06/2023 | 13/06/2023
TO-23-FIN GIS-110SB4-6CB-01 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110SB4-6CB | 1 | 1 | 1 | Scheduled | 13/06/2023 | 13/06/2023
TO-23-BOL-T121-01 | GENERATOR TRANSFORMER - BOOLTIAGH 110-BOOLTIAGH 20-T121 | 1 | 1 | 1 | Scheduled | 14/06/2023 | 14/06/2023
TO-23-KYT-T233-02 | TSO CUSTOMER TRANSFORMER - KELLYSTOWN 220-KELLYSTOWN 34.5-T233 | 2 | 2 | 2 | Scheduled | 14/06/2023 | 15/06/2023
TO-23-CDU-GLN-1-05 | 110kV FEEDER - CORDUFF 110-GALLANSTOWN 110-1 | 31 | 22 | 22 | Scheduled | 15/06/2023 | 15/07/2023
TO-23-110 kV A1 @ FLA-02 | BUSBAR SECTION - FLAGFORD 110-FLAGFORD 110-110A1 | 2 | 2 | 2 | Scheduled | 15/06/2023 | 16/06/2023
TO-23-110 kV B1 @ FLA-02 | BUSBAR SECTION - FLAGFORD 110-FLAGFORD 110-110B1 | 2 | 2 | 2 | Scheduled | 15/06/2023 | 16/06/2023
TO-23-OST-WOO-1-02 | 400kV FEEDER - OLDSTREET 400-WOODLAND 400-1 | 16 | 12 | 12 | Scheduled | 15/06/2023 | 30/06/2023
TO-23-220 kV B1 @ TH-03 | BUSBAR SECTION - TURLOUGH HILL 220-TURLOUGH HILL 220-220B1 | 1 | 1 | 1 | Scheduled | 16/06/2023 | 16/06/2023
TO-23-TH-T2001/2-02 | GENERATOR TRANSFORMER - TURLOUGH HILL 220-TURLOUGH HILL G1-T2001/2 | 1 | 1 | 1 | Scheduled | 16/06/2023 | 16/06/2023
TO-23-AUG-SK-3-01 | 110kV FEEDER - AUGHINISH 110-SEALROCK 110-3 | 22 | 16 | 16 | Scheduled | 19/06/2023 | 10/07/2023
TO-23-BK-SKY-1-01 | 110kV FEEDER - BELLACORICK 110-SRAHNAKILLY 110-1 | 26 | 20 | 20 | Scheduled | 19/06/2023 | 14/07/2023
TO-23-CDL-110SA1-01 | SECTIONALISING DISCONNECT - CORDAL 110-CORDAL 110-110SA1 | 5 | 5 | 5 | Scheduled | 19/06/2023 | 23/06/2023
TO-23-CDL-110SA2-01 | SECTIONALISING DISCONNECT - CORDAL 110-CORDAL 110-110SA2 | 5 | 5 | 5 | Scheduled | 19/06/2023 | 23/06/2023
TO-23-CDL-T132-01 | GENERATOR TRANSFORMER - CORDAL 110-CORDAL 33-T132 | 5 | 5 | 5 | Scheduled | 19/06/2023 | 23/06/2023
TO-23-CDL-T141-01 | DISTRIBUTION TRANSFORMER - CORDAL 110-CORDAL 38-T141 | 5 | 5 | 5 | Reference | 19/06/2023 | 23/06/2023
TO-23-IA-MAC-1-03 | 110kV FEEDER - INNISCARRA 110-MACROOM 110-1 | 76 | 54 | 54 | Scheduled | 19/06/2023 | 02/09/2023
TO-23-LIS-110SA1-05 | SECTIONALISING DISCONNECT - LISDRUM 110-LISDRUM 110-110SA1 | 5 | 5 |  | Scheduled | 19/06/2023 | 23/06/2023
TO-23-LIS-110SA2-05 | SECTIONALISING DISCONNECT - LISDRUM 110-LISDRUM 110-110SA2 | 5 | 5 |  | Scheduled | 19/06/2023 | 23/06/2023
TO-23-LIS-CAP1-03 | CAPACITOR/SVC/REACTOR - LISDRUM 110-LISDRUM 110-CAP1 | 5 | 5 |  | Scheduled | 19/06/2023 | 23/06/2023
TO-23-LIS-LOU-1-02 | 110kV FEEDER - LISDRUM 110-LOUTH 110-1 | 5 | 5 |  | Scheduled | 19/06/2023 | 23/06/2023
TO-23-LIS-T131-04 | GENERATOR TRANSFORMER - LISDRUM 110-LISDRUM 33-T131 | 5 | 5 |  | Scheduled | 19/06/2023 | 23/06/2023
TO-23-LIS-T141-04 | DISTRIBUTION TRANSFORMER - LISDRUM 110-LISDRUM 38-T141 | 5 | 5 |  | Reference | 19/06/2023 | 23/06/2023
TO-23-SK-T103-01 | GENERATOR TRANSFORMER - SEALROCK 110-SEALROCK G3-T103 | 22 | 16 | 16 | Scheduled | 19/06/2023 | 10/07/2023
TO-23-SKY-110SA1-01 | SECTIONALISING DISCONNECT - SRAHNAKILLY 110-SRAHNAKILLY 110-110SA1 | 26 | 20 | 20 | Scheduled | 19/06/2023 | 14/07/2023
TO-23-SKY-110SA2-01 | SECTIONALISING DISCONNECT - SRAHNAKILLY 110-SRAHNAKILLY 110-110SA2 | 26 | 20 | 20 | Scheduled | 19/06/2023 | 14/07/2023
TO-23-SKY-T131-01 | GENERATOR TRANSFORMER - SRAHNAKILLY 110-SRAHNAKILLY 33-T131 | 26 | 20 | 20 | Scheduled | 19/06/2023 | 14/07/2023
TO-23-SKY-T132-01 | GENERATOR TRANSFORMER - SRAHNAKILLY 110-SRAHNAKILLY 33-T132 | 26 | 20 | 20 | Scheduled | 19/06/2023 | 14/07/2023
TO-23-220 kV B1 @ FLA-03 | BUSBAR SECTION - FLAGFORD 220-FLAGFORD 220-220B1 | 2 | 2 | 2 | Scheduled | 22/06/2023 | 23/06/2023
TO-23-220 kV A1 @ INC-02 | BUSBAR SECTION - INCHICORE 220-INCHICORE 220-220A1 | 1 | 1 | 1 | Scheduled | 22/06/2023 | 22/06/2023
TO-23-220 kV A2 @ INC-02 | BUSBAR SECTION - INCHICORE 220-INCHICORE 220-220A2 | 1 | 1 | 1 | Scheduled | 22/06/2023 | 22/06/2023
TO-23-220 kV B1 @ INC-02 | BUSBAR SECTION - INCHICORE 220-INCHICORE 220-220B1 | 1 | 1 | 1 | Scheduled | 22/06/2023 | 22/06/2023
TO-23-220 kV B2 @ INC-02 | BUSBAR SECTION - INCHICORE 220-INCHICORE 220-220B2 | 1 | 1 | 1 | Scheduled | 22/06/2023 | 22/06/2023
TO-23-INC-220K1-2-03 | COUPLER/SECTIONALISING CB - INCHICORE 220-INCHICORE 220-220K1-2 | 1 | 1 | 1 | Scheduled | 22/06/2023 | 22/06/2023
TO-23-ISH-T2001-01 | GENERATOR TRANSFORMER - IRISHTOWN 220-IRISHTOWN G1-T2001 | 8 | 5 | 5 | Scheduled | 25/06/2023 | 02/07/2023
TO-23-BDN-110SA1-02 | SECTIONALISING DISCONNECT - BALLYDINE 110-BALLYDINE 110-110SA1 | 11 | 9 | 9 | Scheduled | 26/06/2023 | 06/07/2023
TO-23-BDN-110SA2-05 | SECTIONALISING DISCONNECT - BALLYDINE 110-BALLYDINE 110-110SA2 | 11 | 9 | 9 | Scheduled | 26/06/2023 | 06/07/2023
TO-23-BDN-CUL-1-04 | 110kV FEEDER - BALLYDINE 110-CULLENAGH 110-1 | 11 | 9 | 9 | Scheduled | 26/06/2023 | 06/07/2023
TO-23-BDN-MRK1-01 | TSO CUSTOMER TRANSFORMER - BALLYDINE 110-BALLYDINE 10-MRK1 | 124 | 89 | 89 | Scheduled | 26/06/2023 | 27/10/2023
TO-23-BYH-110SA1-2CB-03 | COUPLER/SECTIONALISING CB - BALLYNAHULLA 110-BALLYNAHULLA 110-110SA1-2CB | 1 | 1 | 1 | Scheduled | 26/06/2023 | 26/06/2023
TO-23-CF-T103-01 | GENERATOR TRANSFORMER - CATHALEENS FALL 110-CATHALEENS FALL G3-T103 | 5 | 5 | 5 | Scheduled | 26/06/2023 | 30/06/2023
TO-23-CL-T102-02 | GENERATOR TRANSFORMER - CLIFF 110-CLIFF G2-T102 | 12 | 10 | 10 | Scheduled | 26/06/2023 | 07/07/2023
TO-23-110 kV A2 @ FLA-01 | BUSBAR SECTION - FLAGFORD 110-FLAGFORD 110-110A2 | 2 | 2 | 2 | Scheduled | 26/06/2023 | 27/06/2023
TO-23-110 kV B2 @ FLA-01 | BUSBAR SECTION - FLAGFORD 110-FLAGFORD 110-110B2 | 2 | 2 | 2 | Scheduled | 26/06/2023 | 27/06/2023
TO-23-FLA-SLI-1-01 | 110kV FEEDER - FLAGFORD 110-SLIGO 110-1 | 87 | 62 | 62 | Scheduled | 26/06/2023 | 20/09/2023
TO-23-KLN-SNG-1-01 | 110kV FEEDER - KILLONAN 110-SINGLAND 110-1 | 4 | 4 | 4 | Scheduled | 26/06/2023 | 29/06/2023
TO-23-LOU-T2102-08 | TRANSFORMER - LOUTH 220-LOUTH 110-T2102 | 12 | 10 | 10 | Scheduled | 26/06/2023 | 07/07/2023
TO-23-SNG-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - SINGLAND 110-SINGLAND 110-110SA1-2CB | 4 | 4 | 4 | Scheduled | 26/06/2023 | 29/06/2023
TO-23-SNG-T101-01 | DISTRIBUTION TRANSFORMER - SINGLAND 110-SINGLAND 10-T101 | 4 | 4 | 4 | Reference | 26/06/2023 | 29/06/2023
TO-23-110 kV A2 @ ARV-02 | BUSBAR SECTION - ARVA 110-ARVA 110-110A2 | 4 | 4 | 4 | Scheduled | 27/06/2023 | 30/06/2023
TO-23-110 kV B2 @ ARV-02 | BUSBAR SECTION - ARVA 110-ARVA 110-110B2 | 4 | 4 | 4 | Scheduled | 27/06/2023 | 30/06/2023
TO-23-BYH-110SB1-2CB-03 | COUPLER/SECTIONALISING CB - BALLYNAHULLA 110-BALLYNAHULLA 110-110SB1-2CB | 1 | 1 | 1 | Scheduled | 27/06/2023 | 27/06/2023
TO-23-KHL-T131-02 | GENERATOR TRANSFORMER - KILL HILL 110-KILL HILL 33-T131 | 3 | 3 | 3 | Scheduled | 27/06/2023 | 29/06/2023
TO-23-BYH-GLE-1-02 | 110kV FEEDER - BALLYNAHULLA 110-GLENLARA 110-1 | 1 | 1 | 1 | Scheduled | 28/06/2023 | 28/06/2023
TO-23-BLC-DND-3-01 | 110kV FEEDER - BELCAMP 110-DARNDALE 110-3 | 2 | 2 | 2 | Scheduled | 28/06/2023 | 29/06/2023
TO-23-110 kV A2 @ DND-02 | BUSBAR SECTION - DARNDALE 110-DARNDALE 110-110A2 | 2 | 2 | 2 | Scheduled | 28/06/2023 | 29/06/2023
TO-23-110 kV B2 @ DND-02 | BUSBAR SECTION - DARNDALE 110-DARNDALE 110-110B2 | 2 | 2 | 2 | Scheduled | 28/06/2023 | 29/06/2023
TO-23-DND-110K2-03 | COUPLER/SECTIONALISING CB - DARNDALE 110-DARNDALE 110-110K2 | 2 | 2 | 2 | Scheduled | 28/06/2023 | 29/06/2023
TO-23-DND-110SA1-2CB-02 | COUPLER/SECTIONALISING CB - DARNDALE 110-DARNDALE 110-110SA1-2CB | 2 | 2 | 2 | Scheduled | 28/06/2023 | 29/06/2023
TO-23-DND-110SB1-2CB-03 | COUPLER/SECTIONALISING CB - DARNDALE 110-DARNDALE 110-110SB1-2CB | 2 | 2 | 2 | Scheduled | 28/06/2023 | 29/06/2023
TO-23-110 kV A1 @ FLA-05 | BUSBAR SECTION - FLAGFORD 110-FLAGFORD 110-110A1 | 13 | 9 | 9 | Scheduled | 28/06/2023 | 10/07/2023
TO-23-110 kV B1 @ FLA-05 | BUSBAR SECTION - FLAGFORD 110-FLAGFORD 110-110B1 | 13 | 9 | 9 | Scheduled | 28/06/2023 | 10/07/2023
TO-23-220 kV A1 @ FLA-03 | BUSBAR SECTION - FLAGFORD 220-FLAGFORD 220-220A1 | 13 | 9 | 9 | Scheduled | 28/06/2023 | 10/07/2023
TO-23-220 kV B1 @ FLA-05 | BUSBAR SECTION - FLAGFORD 220-FLAGFORD 220-220B1 | 13 | 9 | 9 | Scheduled | 28/06/2023 | 10/07/2023
TO-23-CLA-T2102-02 | TRANSFORMER - CLASHAVOON 220-CLASHAVOON 110-T2102 | 15 | 11 | 11 | Scheduled | 30/06/2023 | 14/07/2023
TO-23-ARV-NAV-1-01 | 110kV FEEDER - ARVA 110-NAVAN 110-1 | 40 | 29 | 29 | Scheduled | 03/07/2023 | 11/08/2023
TO-23-CNO-KPG-1-01 | 110kV FEEDER - COOLNANOONAGH 110-KILPADDOGE 110-1 | 4 | 4 | 4 | Scheduled | 03/07/2023 | 06/07/2023
TO-23-CNO-T131-01 | GENERATOR TRANSFORMER - COOLNANOONAGH 110-COOLNANOONAGH 33-T131 | 4 | 4 | 4 | Scheduled | 03/07/2023 | 06/07/2023
TO-23-NEW-PLS-1-01 | 110kV FEEDER - NEWBRIDGE 110-PORTLAOISE 110-1 | 12 | 10 | 10 | Scheduled | 03/07/2023 | 14/07/2023
TO-23-220 kV A1 @ TH-02 | BUSBAR SECTION - TURLOUGH HILL 220-TURLOUGH HILL 220-220A1 | 12 | 10 | 10 | Scheduled | 03/07/2023 | 14/07/2023
TO-23-220 kV B1 @ TH-02 | BUSBAR SECTION - TURLOUGH HILL 220-TURLOUGH HILL 220-220B1 | 12 | 10 | 10 | Scheduled | 03/07/2023 | 14/07/2023
TO-23-KPG-F13-1-CUB-01 | CUBICLE - KILPADDOGE 220-F13 SPARE 220-1-CUB | 4 | 4 | 4 | Scheduled | 04/07/2023 | 07/07/2023
TO-23-220 kV A3 @ KPG-03 | BUSBAR SECTION - KILPADDOGE 220-KILPADDOGE 220-220A3 | 4 | 4 | 4 | Scheduled | 04/07/2023 | 07/07/2023
TO-23-220 kV B3 @ KPG-03 | BUSBAR SECTION - KILPADDOGE 220-KILPADDOGE 220-220B3 | 4 | 4 | 4 | Scheduled | 04/07/2023 | 07/07/2023
TO-23-SLB-T132-01 | GENERATOR TRANSFORMER - SLIABH BAWN 110-SLIABH BAWN 33-T132 | 2 | 2 | 2 | Scheduled | 04/07/2023 | 05/07/2023
TO-23-BDN-110SA1-03 | SECTIONALISING DISCONNECT - BALLYDINE 110-BALLYDINE 110-110SA1 | 1 | 1 | 1 | Scheduled | 07/07/2023 | 07/07/2023
TO-23-BDN-110SA2-04 | SECTIONALISING DISCONNECT - BALLYDINE 110-BALLYDINE 110-110SA2 | 1 | 1 | 1 | Scheduled | 07/07/2023 | 07/07/2023
TO-23-BDN-CUL-1-02 | 110kV FEEDER - BALLYDINE 110-CULLENAGH 110-1 | 1 | 1 | 1 | Scheduled | 07/07/2023 | 07/07/2023
TO-23-110 kV A2 @ ARK-01 | BUSBAR SECTION - ARKLOW 110-ARKLOW 110-110A2 | 10 | 8 | 8 | Scheduled | 10/07/2023 | 19/07/2023
TO-23-110 kV B2 @ ARK-01 | BUSBAR SECTION - ARKLOW 110-ARKLOW 110-110B2 | 10 | 8 | 8 | Scheduled | 10/07/2023 | 19/07/2023
TO-23-ARK-BEG-1-01 | 110kV FEEDER - ARKLOW 110-BALLYBEG 110-1 | 10 | 8 | 8 | Scheduled | 10/07/2023 | 19/07/2023
TO-23-AUG-KPG-1-01 | 110kV FEEDER - AUGHINISH 110-KILPADDOGE 110-1 | 4 | 4 | 4 | Scheduled | 10/07/2023 | 13/07/2023
TO-23-BDN-CUL-1-01 | 110kV FEEDER - BALLYDINE 110-CULLENAGH 110-1 | 44 | 31 | 31 | Scheduled | 10/07/2023 | 22/08/2023
TO-23-BRT-T222-01 | TSO CUSTOMER TRANSFORMER - BRACETOWN 220-BRACETOWN 20-T222 | 5 | 5 | 5 | Scheduled | 10/07/2023 | 14/07/2023
TO-23-110 kV A2 @ CUL-01 | BUSBAR SECTION - CULLENAGH 110-CULLENAGH 110-110A2 | 12 | 10 | 10 | Scheduled | 10/07/2023 | 21/07/2023
TO-23-110 kV B2 @ CUL-01 | BUSBAR SECTION - CULLENAGH 110-CULLENAGH 110-110B2 | 12 | 10 | 10 | Scheduled | 10/07/2023 | 21/07/2023
TO-23-CUS-NEW-1-01 | 110kV FEEDER - CUSHALING 110-NEWBRIDGE 110-1 | 12 | 10 | 10 | Scheduled | 10/07/2023 | 21/07/2023
TO-23-DEY-T132-03 | GENERATOR TRANSFORMER - DERRYCARNEY 110-DERRYCARNEY 33-T132 | 2 | 2 | 2 | Scheduled | 10/07/2023 | 11/07/2023
TO-23-220 kV A1 @ DSN-02 | BUSBAR SECTION - DUNSTOWN 220-DUNSTOWN 220-220A1 | 5 | 5 | 5 | Scheduled | 10/07/2023 | 14/07/2023
TO-23-220 kV B1 @ DSN-02 | BUSBAR SECTION - DUNSTOWN 220-DUNSTOWN 220-220B1 | 5 | 5 | 5 | Scheduled | 10/07/2023 | 14/07/2023
TO-23-110 kV A2 @ KPG-04 | BUSBAR SECTION - KILPADDOGE 110-KILPADDOGE 110-110A2 | 4 | 4 | 4 | Scheduled | 10/07/2023 | 13/07/2023
TO-23-110 kV B2 @ KPG-02 | BUSBAR SECTION - KILPADDOGE 110-KILPADDOGE 110-110B2 | 4 | 4 | 4 | Scheduled | 10/07/2023 | 13/07/2023
TO-23-KPG-110SA1-2CB-04 | COUPLER/SECTIONALISING CB - KILPADDOGE 110-KILPADDOGE 110-110SA1-2CB | 4 | 4 | 4 | Scheduled | 10/07/2023 | 13/07/2023
TO-23-KPG-110SA2-4CB-04 | COUPLER/SECTIONALISING CB - KILPADDOGE 110-KILPADDOGE 110-110SA2-4CB | 4 | 4 | 4 | Scheduled | 10/07/2023 | 13/07/2023
TO-23-KPG-110SB1-2CB-05 | COUPLER/SECTIONALISING CB - KILPADDOGE 110-KILPADDOGE 110-110SB1-2CB | 4 | 4 | 4 | Scheduled | 10/07/2023 | 13/07/2023
TO-23-KPG-110SB2-4CB-04 | COUPLER/SECTIONALISING CB - KILPADDOGE 110-KILPADDOGE 110-110SB2-4CB | 4 | 4 | 4 | Scheduled | 10/07/2023 | 13/07/2023
TO-23-NEW-110SA1-01 | SECTIONALISING DISCONNECT - NEWBRIDGE 110-NEWBRIDGE 110-110SA1 | 5 | 5 | 5 | Scheduled | 10/07/2023 | 14/07/2023
TO-23-NEW-110SA2-03 | SECTIONALISING DISCONNECT - NEWBRIDGE 110-NEWBRIDGE 110-110SA2 | 5 | 5 | 5 | Scheduled | 10/07/2023 | 14/07/2023
TO-23-NEW-T141-01 | DISTRIBUTION TRANSFORMER - NEWBRIDGE 110-NEWBRIDGE 38-T141 | 5 | 5 | 5 | Reference | 10/07/2023 | 14/07/2023
TO-23-UGL-T132-01 | GENERATOR TRANSFORMER - UGGOOL 110-UGGOOL 33-T132 | 8 | 6 | 6 | Scheduled | 10/07/2023 | 17/07/2023
TO-23-UGL-T134-01 | GENERATOR TRANSFORMER - UGGOOL 110-UGGOOL 33-T134 | 8 | 6 | 6 | Scheduled | 10/07/2023 | 17/07/2023
TO-23-BEG-110SA1-01 | SECTIONALISING DISCONNECT - BALLYBEG 110-BALLYBEG 110-110SA1 | 3 | 3 | 3 | Scheduled | 11/07/2023 | 13/07/2023
TO-23-BEG-110SA2-01 | SECTIONALISING DISCONNECT - BALLYBEG 110-BALLYBEG 110-110SA2 | 3 | 3 | 3 | Scheduled | 11/07/2023 | 13/07/2023
TO-23-BEG-T101-01 | DISTRIBUTION TRANSFORMER - BALLYBEG 110-BALLYBEG 10-T101 | 3 | 3 | 3 | Reference | 11/07/2023 | 13/07/2023
TO-23-KPG-F14-1-CUB-01 | CUBICLE - KILPADDOGE 220-F14 SPARE 220-1-CUB | 4 | 4 | 4 | Scheduled | 11/07/2023 | 14/07/2023
TO-23-220 kV A4 @ KPG-04 | BUSBAR SECTION - KILPADDOGE 220-KILPADDOGE 220-220A4 | 4 | 4 | 4 | Scheduled | 11/07/2023 | 14/07/2023
TO-23-220 kV B4 @ KPG-04 | BUSBAR SECTION - KILPADDOGE 220-KILPADDOGE 220-220B4 | 4 | 4 | 4 | Scheduled | 11/07/2023 | 14/07/2023
TO-23-KPG-220K3-03 | COUPLER/SECTIONALISING CB - KILPADDOGE 220-KILPADDOGE 220-220K3 | 3 | 3 | 3 | Proposed | 11/07/2023 | 13/07/2023
TO-23-KPG-220SA1-3CB-05 | COUPLER/SECTIONALISING CB - KILPADDOGE 220-KILPADDOGE 220-220SA1-3CB | 3 | 3 | 3 | Proposed | 11/07/2023 | 13/07/2023
TO-23-KPG-220SB1-3CB-05 | COUPLER/SECTIONALISING CB - KILPADDOGE 220-KILPADDOGE 220-220SB1-3CB | 3 | 3 | 3 | Proposed | 11/07/2023 | 13/07/2023
TO-23-UGL-110SA1-2CB-03 | COUPLER/SECTIONALISING CB - UGGOOL 110-UGGOOL 110-110SA1-2CB | 4 | 4 | 4 | Scheduled | 11/07/2023 | 14/07/2023
TO-23-ATH-LA-1-01 | 110kV FEEDER - ATHLONE 110-LANESBORO 110-1 | 9 | 7 | 7 | Scheduled | 13/07/2023 | 21/07/2023
TO-23-220 kV B1/B2 @ FLA-02 | BUSBAR SECTION - FLAGFORD 220-FLAGFORD 220-220B1-B2 | 1 | 0 | 0 | Scheduled | 15/07/2023 | 15/07/2023
TO-23-FLA-LOU-1-03 | 220kV FEEDER - FLAGFORD 220-LOUTH 220-1 | 1 | 0 | 0 | Scheduled | 15/07/2023 | 15/07/2023
TO-23-AD-T2011/12-01 | GENERATOR TRANSFORMER - AGHADA 220-AGHADA G11/12-T2011/12 | 4 | 4 | 4 | Scheduled | 17/07/2023 | 20/07/2023
TO-23-CDY-GRV-1-01 | 110kV FEEDER - CORDERRY 110-GARVAGH 110-1 | 5 | 5 | 5 | Scheduled | 17/07/2023 | 21/07/2023
TO-23-COW-OLD-2-01 | 110kV FEEDER - COW CROSS 110-OLDCOURT 110-2 | 5 | 5 | 5 | Reference | 17/07/2023 | 21/07/2023
TO-23-GRV-110K1-01 | COUPLER/SECTIONALISING CB - GARVAGH 110-GARVAGH 110-110K1 | 5 | 5 | 5 | Scheduled | 17/07/2023 | 21/07/2023
TO-23-GRV-T121-01 | GENERATOR TRANSFORMER - GARVAGH 110-GARVAGH 20-T121 | 5 | 5 | 5 | Scheduled | 17/07/2023 | 21/07/2023
TO-23-GRV-T141-01 | DISTRIBUTION TRANSFORMER - GARVAGH 110-GARVAGH 20-T141 | 5 | 5 | 5 | Reference | 17/07/2023 | 21/07/2023
TO-23-INC-ISH-1-03 | 220kV FEEDER - INCHICORE 220-IRISHTOWN 220-1 | 19 | 15 | 15 | Scheduled | 17/07/2023 | 04/08/2023
TO-23-LIM-RAT-1-04 | 110kV FEEDER - LIMERICK 110-RATHKEALE 110-1 | 12 | 10 | 10 | Proposed | 17/07/2023 | 28/07/2023
TO-23-LIM-RAT-1-02 | 110kV FEEDER - LIMERICK 110-RATHKEALE 110-1 | 12 | 10 | 10 | Scheduled | 17/07/2023 | 28/07/2023
TO-23-110 kV A2 @ MAY-02 | BUSBAR SECTION - MAYNOOTH 110-MAYNOOTH 110-110A2 | 12 | 10 | 10 | Scheduled | 17/07/2023 | 28/07/2023
TO-23-110 kV A3 @ MAY-02 | BUSBAR SECTION - MAYNOOTH 110-MAYNOOTH 110-110A3 | 12 | 10 | 10 | Scheduled | 17/07/2023 | 28/07/2023
TO-23-110 kV B2 @ MAY-02 | BUSBAR SECTION - MAYNOOTH 110-MAYNOOTH 110-110B2 | 12 | 10 | 10 | Scheduled | 17/07/2023 | 28/07/2023
TO-23-110 kV B3 @ MAY-02 | BUSBAR SECTION - MAYNOOTH 110-MAYNOOTH 110-110B3 | 12 | 10 | 10 | Scheduled | 17/07/2023 | 28/07/2023
TO-23-220 kV A1 @ MAY-05 | BUSBAR SECTION - MAYNOOTH 220-MAYNOOTH 220-220A1 | 12 | 10 | 10 | Scheduled | 17/07/2023 | 28/07/2023
TO-23-220 kV B1 @ MAY-05 | BUSBAR SECTION - MAYNOOTH 220-MAYNOOTH 220-220B1 | 12 | 10 | 10 | Scheduled | 17/07/2023 | 28/07/2023
TO-23-MAY-T2102-01 | TRANSFORMER - MAYNOOTH 220-MAYNOOTH 110-T2102 | 12 | 10 | 10 | Scheduled | 17/07/2023 | 28/07/2023
TO-23-MP GIS-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 110-MONEYPOINT GIS 110-110SA1-2CB | 5 | 5 |  | Scheduled | 17/07/2023 | 21/07/2023
TO-23-MP GIS-T121-01 | GENERATOR TRANSFORMER - MONEYPOINT GIS 110-MONEYPOINT GIS 20-T121 | 5 | 5 |  | Scheduled | 17/07/2023 | 21/07/2023
TO-23-OLD-T102-01 | DISTRIBUTION TRANSFORMER - OLDCOURT 110-OLDCOURT 10-T102 | 5 | 5 | 5 | Reference | 17/07/2023 | 21/07/2023
TO-23-UGL-T131-01 | GENERATOR TRANSFORMER - UGGOOL 110-UGGOOL 33-T131 | 5 | 5 | 5 | Scheduled | 17/07/2023 | 21/07/2023
TO-23-COL-FIN GIS-1-04 | 110kV FEEDER - COLLEGE PARK 110-FINGLAS GIS 110-1 | 2 | 2 |  | Scheduled | 20/07/2023 | 21/07/2023
TO-23-LIS-110SA1-01 | SECTIONALISING DISCONNECT - LISDRUM 110-LISDRUM 110-110SA1 | 1 | 1 | 1 | Scheduled | 20/07/2023 | 20/07/2023
TO-23-LIS-110SA2-01 | SECTIONALISING DISCONNECT - LISDRUM 110-LISDRUM 110-110SA2 | 1 | 1 | 1 | Scheduled | 20/07/2023 | 20/07/2023
TO-23-LIS-CAP1-01 | CAPACITOR/SVC/REACTOR - LISDRUM 110-LISDRUM 110-CAP1 | 1 | 1 | 1 | Scheduled | 20/07/2023 | 20/07/2023
TO-23-LIS-LOU-1-03 | 110kV FEEDER - LISDRUM 110-LOUTH 110-1 | 1 | 1 | 1 | Scheduled | 20/07/2023 | 20/07/2023
TO-23-LIS-T131-02 | GENERATOR TRANSFORMER - LISDRUM 110-LISDRUM 33-T131 | 1 | 1 | 1 | Scheduled | 20/07/2023 | 20/07/2023
TO-23-AD-T2014-01 | GENERATOR TRANSFORMER - AGHADA 220-AGHADA G14-T2014 | 5 | 5 | 5 | Scheduled | 24/07/2023 | 28/07/2023
TO-23-CUN-T121-01 | GENERATOR TRANSFORMER - CUNGHILL 110-CUNGHILL 20-T121 | 3 | 3 | 3 | Scheduled | 24/07/2023 | 26/07/2023
TO-23-DER-T1/T2-01 | GENERATOR TRANSFORMER - DERRYIRON 110-RHODE 110-T1/T2 | 12 | 10 | 10 | Scheduled | 24/07/2023 | 04/08/2023
TO-23-LOU-220K1-2-03 | COUPLER/SECTIONALISING CB - LOUTH 220-LOUTH 220-220K1-2 | 35 | 24 | 24 | Scheduled | 24/07/2023 | 27/08/2023
TO-23-KIR-T131-02 | GENERATOR TRANSFORMER - KILCUMBER 110-KILCUMBER 33-T131 | 1 | 1 | 1 | Scheduled | 26/07/2023 | 26/07/2023
TO-23-KLH-T121-01 | GENERATOR TRANSFORMER - KNOCKALOUGH 110-KNOCKALOUGH 20-T121 | 3 | 3 | 3 | Scheduled | 26/07/2023 | 28/07/2023
TO-23-BUT-T141-02 | DISTRIBUTION TRANSFORMER - BUTLERSTOWN 110-BUTLERSTOWN 38-T141 | 106 | 74 | 74 | Reference | 31/07/2023 | 13/11/2023
TO-23-110 kV B2 @ CBT-03 | BUSBAR SECTION - CASTLEBAGOT 110-CASTLEBAGOT 110-110B2 | 1 | 1 | 1 | Scheduled | 31/07/2023 | 31/07/2023
TO-23-110 kV B4 @ CBT-03 | BUSBAR SECTION - CASTLEBAGOT 110-CASTLEBAGOT 110-110B4 | 1 | 1 | 1 | Scheduled | 31/07/2023 | 31/07/2023
TO-23-CBT-110SB2-4CB-01 | COUPLER/SECTIONALISING CB - CASTLEBAGOT 110-CASTLEBAGOT 110-110SB2-4CB | 1 | 1 | 1 | Scheduled | 31/07/2023 | 31/07/2023
TO-23-110 kV A1 @ KLN-02 | BUSBAR SECTION - KILLONAN 110-KILLONAN 110-110A1 | 10 | 7 | 7 | Scheduled | 31/07/2023 | 09/08/2023
TO-23-110 kV B1 @ KLN-02 | BUSBAR SECTION - KILLONAN 110-KILLONAN 110-110B1 | 10 | 7 | 7 | Scheduled | 31/07/2023 | 09/08/2023
TO-23-KLN-LIM-1-01 | 110kV FEEDER - KILLONAN 110-LIMERICK 110-1 | 10 | 7 |  | Scheduled | 31/07/2023 | 09/08/2023
TO-23-MCE-110SA2-01 | SECTIONALISING DISCONNECT - MACETOWN 110-MACETOWN 110-110SA2 | 5 | 5 | 5 | Scheduled | 31/07/2023 | 04/08/2023
TO-23-MCE-SNU-1-01 | 110kV FEEDER - MACETOWN 110-SNUGBOROUGH 110-1 | 5 | 5 | 5 | Scheduled | 31/07/2023 | 04/08/2023
TO-23-MCE-T102-01 | DISTRIBUTION TRANSFORMER - MACETOWN 110-MACETOWN 10-T102 | 5 | 5 | 5 | Reference | 31/07/2023 | 04/08/2023
TO-23-MCE-T124-01 | TSO CUSTOMER TRANSFORMER - MACETOWN 110-MACETOWN 20-T124 | 5 | 5 | 5 | Scheduled | 31/07/2023 | 04/08/2023
TO-23-PB-R2001-01 | CAPACITOR/SVC/REACTOR - POOLBEG 220-POOLBEG 220-R2001 | 5 | 5 |  | Scheduled | 31/07/2023 | 04/08/2023
TO-23-110 kV A2 @ CBT-02 | BUSBAR SECTION - CASTLEBAGOT 110-CASTLEBAGOT 110-110A2 | 1 | 1 | 1 | Scheduled | 01/08/2023 | 01/08/2023
TO-23-110 kV A4 @ CBT-02 | BUSBAR SECTION - CASTLEBAGOT 110-CASTLEBAGOT 110-110A4 | 1 | 1 | 1 | Scheduled | 01/08/2023 | 01/08/2023
TO-23-CBT-110SA2-4CB-01 | COUPLER/SECTIONALISING CB - CASTLEBAGOT 110-CASTLEBAGOT 110-110SA2-4CB | 1 | 1 | 1 | Scheduled | 01/08/2023 | 01/08/2023
TO-23-110 kV A2 @ KBY-02 | BUSBAR SECTION - KILBARRY 110-KILBARRY 110-110A2 | 3 | 3 | 3 | Scheduled | 01/08/2023 | 03/08/2023
TO-23-110 kV B2 @ KBY-02 | BUSBAR SECTION - KILBARRY 110-KILBARRY 110-110B2 | 3 | 3 | 3 | Scheduled | 01/08/2023 | 03/08/2023
TO-23-MLC-110SA1-02 | SECTIONALISING DISCONNECT - MOUNTLUCAS 110-MOUNTLUCAS 110-110SA1 | 3 | 3 | 3 | Scheduled | 01/08/2023 | 03/08/2023
TO-23-MLC-110SA2-02 | SECTIONALISING DISCONNECT - MOUNTLUCAS 110-MOUNTLUCAS 110-110SA2 | 3 | 3 | 3 | Scheduled | 01/08/2023 | 03/08/2023
TO-23-MLC-TSB-1-05 | 110kV FEEDER - MOUNTLUCAS 110-THORNSBERRY 110-1 | 3 | 3 | 3 | Scheduled | 01/08/2023 | 03/08/2023
TO-23-MLN-T124-01 | TSO CUSTOMER TRANSFORMER - MULLAGHARLIN 110-MULLAGHARLIN 20-T124 | 2 | 2 | 2 | Scheduled | 01/08/2023 | 02/08/2023
TO-23-ROP-WEX-1-01 | 110kV FEEDER - ROSSPILE 110-WEXFORD 110-1 | 14 | 9 | 9 | Scheduled | 01/08/2023 | 14/08/2023
TO-23-BRT-T224-01 | TSO CUSTOMER TRANSFORMER - BRACETOWN 220-BRACETOWN 20-T224 | 7 | 4 | 4 | Scheduled | 02/08/2023 | 08/08/2023
TO-23-LIS-LOU-1-01 | 110kV FEEDER - LISDRUM 110-LOUTH 110-1 | 5 | 3 | 3 | Scheduled | 02/08/2023 | 06/08/2023
TO-23-LOU-110K1-2-01 | COUPLER/SECTIONALISING CB - LOUTH 110-LOUTH 110-110K1-2 | 5 | 3 | 3 | Scheduled | 02/08/2023 | 06/08/2023
TO-23-LOU-MTH-1-01 | 110kV FEEDER - LOUTH 110-MEATH HILL 110-1 | 5 | 3 | 3 | Scheduled | 02/08/2023 | 06/08/2023
TO-23-LOU-T2102-02 | TRANSFORMER - LOUTH 220-LOUTH 110-T2102 | 5 | 3 | 3 | Scheduled | 02/08/2023 | 06/08/2023
TO-23-LOU-T2104-02 | TRANSFORMER - LOUTH 220-LOUTH 110-T2104 | 5 | 3 | 3 | Scheduled | 02/08/2023 | 06/08/2023
TO-23-TIV-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - TIEVEBRACK 110-TIEVEBRACK 110-110SA1-2CB | 2 | 2 | 2 | Scheduled | 02/08/2023 | 03/08/2023
TO-23-MLN-T123-01 | TSO CUSTOMER TRANSFORMER - MULLAGHARLIN 110-MULLAGHARLIN 20-T123 | 2 | 2 | 2 | Scheduled | 03/08/2023 | 04/08/2023
TO-23-AD-KRA-1-04 | 220kV FEEDER - AGHADA 220-KNOCKRAHA 220-1 | 8 | 5 | 5 | Scheduled | 04/08/2023 | 11/08/2023
TO-23-BIN-CF-1-01 | 110kV FEEDER - BINBANE 110-CATHALEENS FALL 110-1 | 50 | 35 | 35 | Scheduled | 04/08/2023 | 22/09/2023
TO-23-400 kV A2 @ DSN-01 | BUSBAR SECTION - DUNSTOWN 400-DUNSTOWN 400-400A2 | 36 | 25 | 25 | Scheduled | 04/08/2023 | 08/09/2023
TO-23-400 kV B2 @ DSN-01 | BUSBAR SECTION - DUNSTOWN 400-DUNSTOWN 400-400B2 | 36 | 25 | 25 | Scheduled | 04/08/2023 | 08/09/2023
TO-23-DSN-T4202-01 | TRANSFORMER - DUNSTOWN 400-DUNSTOWN 220-T4202 | 41 | 28 | 28 | Scheduled | 04/08/2023 | 13/09/2023
TO-23-KRA-220SB1-2CB-02 | COUPLER/SECTIONALISING CB - KNOCKRAHA 220-KNOCKRAHA 220-220SB1-2CB | 8 | 5 | 5 | Scheduled | 04/08/2023 | 11/08/2023
TO-23-KRA-220SB2-4CB-03 | COUPLER/SECTIONALISING CB - KNOCKRAHA 220-KNOCKRAHA 220-220SB2-4CB | 8 | 5 | 5 | Scheduled | 04/08/2023 | 11/08/2023
TO-23-COW-OLD-1-01 | 110kV FEEDER - COW CROSS 110-OLDCOURT 110-1 | 5 | 4 | 4 | Reference | 07/08/2023 | 11/08/2023
TO-23-DRY-110SA1-04 | SECTIONALISING DISCONNECT - DRYBRIDGE 110-DRYBRIDGE 110-110SA1 | 5 | 4 | 4 | Scheduled | 07/08/2023 | 11/08/2023
TO-23-DRY-110SA2-04 | SECTIONALISING DISCONNECT - DRYBRIDGE 110-DRYBRIDGE 110-110SA2 | 5 | 4 | 4 | Scheduled | 07/08/2023 | 11/08/2023
TO-23-DRY-LOU-1-02 | 110kV FEEDER - DRYBRIDGE 110-LOUTH 110-1 | 10 | 7 | 7 | Scheduled | 07/08/2023 | 16/08/2023
TO-23-DRY-PLA-1-04 | 110kV FEEDER - DRYBRIDGE 110-PLATIN 110-1 | 82 | 59 | 59 | Scheduled | 07/08/2023 | 27/10/2023
TO-23-DRY-T141-03 | DISTRIBUTION TRANSFORMER - DRYBRIDGE 110-DRYBRIDGE 38-T141 | 5 | 4 | 4 | Reference | 07/08/2023 | 11/08/2023
TO-23-OLD-T101-01 | DISTRIBUTION TRANSFORMER - OLDCOURT 110-OLDCOURT 10-T101 | 5 | 4 | 4 | Reference | 07/08/2023 | 11/08/2023
TO-23-PLA-110SA1-03 | SECTIONALISING DISCONNECT - PLATIN 110-PLATIN 110-110SA1 | 13 | 9 | 9 | Scheduled | 07/08/2023 | 19/08/2023
TO-23-PLA-110SA2-03 | SECTIONALISING DISCONNECT - PLATIN 110-PLATIN 110-110SA2 | 13 | 9 | 9 | Scheduled | 07/08/2023 | 19/08/2023
TO-23-PLA-T101/2/3/4-03 | TSO CUSTOMER TRANSFORMER - PLATIN 110-PLATIN 10-T101/2/3/4 | 13 | 9 | 9 | Scheduled | 07/08/2023 | 19/08/2023
TO-23-BVK-COT-1-01 | 110kV FEEDER - BALLYVOUSKILL 110-COOMATAGGART 110-1 | 11 | 9 | 9 | Scheduled | 08/08/2023 | 18/08/2023
TO-23-COT-110SA1-01 | SECTIONALISING DISCONNECT - COOMATAGGART 110-COOMATAGGART 110-110SA1 | 11 | 9 | 9 | Scheduled | 08/08/2023 | 18/08/2023
TO-23-COT-110SA2-01 | SECTIONALISING DISCONNECT - COOMATAGGART 110-COOMATAGGART 110-110SA2 | 11 | 9 | 9 | Scheduled | 08/08/2023 | 18/08/2023
TO-23-COT-FILTER1-02 | CAPACITOR/SVC/REACTOR - COOMATAGGART 110-COOMATAGGART 110-FILTER1 | 11 | 9 | 9 | Scheduled | 08/08/2023 | 18/08/2023
TO-23-COT-T132-01 | GENERATOR TRANSFORMER - COOMATAGGART 110-COOMATAGGART 33-T132 | 11 | 9 | 9 | Scheduled | 08/08/2023 | 18/08/2023
TO-23-COT-T141-01 | DISTRIBUTION TRANSFORMER - COOMATAGGART 110-COOMATAGGART 38-T141 | 11 | 9 | 9 | Reference | 08/08/2023 | 18/08/2023
TO-23-CUS-PLS-1-02 | 110kV FEEDER - CUSHALING 110-PORTLAOISE 110-1 | 14 | 10 |  | Scheduled | 08/08/2023 | 21/08/2023
TO-23-110 kV A1 @ GAL GIS-03 | BUSBAR SECTION - GALWAY GIS 110-GALWAY GIS 110-110A1 | 5 | 4 | 4 | Scheduled | 08/08/2023 | 12/08/2023
TO-23-110 kV B1 @ GAL GIS-03 | BUSBAR SECTION - GALWAY GIS 110-GALWAY GIS 110-110B1 | 5 | 4 | 4 | Scheduled | 08/08/2023 | 12/08/2023
TO-23-GAL GIS-110SA1-2CB-05 | COUPLER/SECTIONALISING CB - GALWAY GIS 110-GALWAY GIS 110-110SA1-2CB | 5 | 4 | 4 | Scheduled | 08/08/2023 | 12/08/2023
TO-23-GAL GIS-110SA1-3CB-04 | COUPLER/SECTIONALISING CB - GALWAY GIS 110-GALWAY GIS 110-110SA1-3CB | 5 | 4 | 4 | Scheduled | 08/08/2023 | 12/08/2023
TO-23-GAL GIS-110SB1-2CB-05 | COUPLER/SECTIONALISING CB - GALWAY GIS 110-GALWAY GIS 110-110SB1-2CB | 5 | 4 | 4 | Scheduled | 08/08/2023 | 12/08/2023
TO-23-GAL GIS-110SB1-3CB-04 | COUPLER/SECTIONALISING CB - GALWAY GIS 110-GALWAY GIS 110-110SB1-3CB | 5 | 4 | 4 | Scheduled | 08/08/2023 | 12/08/2023
TO-23-KLN-T2102-01 | TRANSFORMER - KILLONAN 220-KILLONAN 110-T2102 | 4 | 4 | 4 | Scheduled | 08/08/2023 | 11/08/2023
TO-23-110 kV A2 @ PLS-02 | BUSBAR SECTION - PORTLAOISE 110-PORTLAOISE 110-110A2 | 14 | 10 | 10 | Scheduled | 08/08/2023 | 21/08/2023
TO-23-110 kV B2 @ PLS-02 | BUSBAR SECTION - PORTLAOISE 110-PORTLAOISE 110-110B2 | 14 | 10 | 10 | Scheduled | 08/08/2023 | 21/08/2023
TO-23-CUS-T101-01 | GENERATOR TRANSFORMER - CUSHALING 110-CUSHALING G1-T101 | 9 | 7 | 7 | Scheduled | 10/08/2023 | 18/08/2023
TO-23-ARV-SKL-2-03 | 110kV FEEDER - ARVA 110-SHANKILL 110-2 | 2 | 0 | 0 | Scheduled | 12/08/2023 | 13/08/2023
TO-23-LIS-SKL-1-06 | 110kV FEEDER - LISDRUM 110-SHANKILL 110-1 | 104 | 73 |  | Scheduled | 12/08/2023 | 23/11/2023
TO-23-RRU-SKL-1-03 | 110kV FEEDER - RATRUSSAN 110-SHANKILL 110-1 | 2 | 0 | 0 | Scheduled | 12/08/2023 | 13/08/2023
TO-23-SKL-110SA1-03 | SECTIONALISING DISCONNECT - SHANKILL 110-SHANKILL 110-110SA1 | 2 | 0 | 0 | Scheduled | 12/08/2023 | 13/08/2023
TO-23-SKL-110SA2-02 | SECTIONALISING DISCONNECT - SHANKILL 110-SHANKILL 110-110SA2 | 2 | 0 | 0 | Scheduled | 12/08/2023 | 13/08/2023
TO-23-SKL-T141-02 | DISTRIBUTION TRANSFORMER - SHANKILL 110-SHANKILL 38-T141 | 2 | 0 | 0 | Reference | 12/08/2023 | 13/08/2023
TO-23-220 kV A1 @ CSH-03 | BUSBAR SECTION - CASHLA 220-CASHLA 220-220A1 | 5 | 5 | 5 | Scheduled | 14/08/2023 | 18/08/2023
TO-23-220 kV A2 @ CSH-03 | BUSBAR SECTION - CASHLA 220-CASHLA 220-220A2 | 5 | 5 | 5 | Scheduled | 14/08/2023 | 18/08/2023
TO-23-220 kV B1 @ CSH-01 | BUSBAR SECTION - CASHLA 220-CASHLA 220-220B1 | 5 | 5 | 5 | Scheduled | 14/08/2023 | 18/08/2023
TO-23-220 kV B2 @ CSH-03 | BUSBAR SECTION - CASHLA 220-CASHLA 220-220B2 | 5 | 5 | 5 | Scheduled | 14/08/2023 | 18/08/2023
TO-23-CSH-220K1-2-01 | COUPLER/SECTIONALISING CB - CASHLA 220-CASHLA 220-220K1-2 | 5 | 5 |  | Scheduled | 14/08/2023 | 18/08/2023
TO-23-COW-RAF-1-02 | 110kV FEEDER - COW CROSS 110-RAFFEEN 110-1 | 4 | 4 | 4 | Scheduled | 14/08/2023 | 17/08/2023
TO-23-INC-MAY-2-07 | 220kV FEEDER - INCHICORE 220-MAYNOOTH 220-2 | 12 | 10 | 10 | Scheduled | 14/08/2023 | 25/08/2023
TO-23-KCR-T121-01 | GENERATOR TRANSFORMER - KNOCKACUMMER 110-KNOCKACUMMER 20-T121 | 1 | 1 | 1 | Scheduled | 14/08/2023 | 14/08/2023
TO-23-LIS-110SA1-04 | SECTIONALISING DISCONNECT - LISDRUM 110-LISDRUM 110-110SA1 | 26 | 20 | 20 | Scheduled | 14/08/2023 | 08/09/2023
TO-23-LIS-110SA2-04 | SECTIONALISING DISCONNECT - LISDRUM 110-LISDRUM 110-110SA2 | 26 | 20 | 20 | Scheduled | 14/08/2023 | 08/09/2023
TO-23-LIS-CAP2-04 | CAPACITOR/SVC/REACTOR - LISDRUM 110-LISDRUM 110-CAP2 | 26 | 20 | 20 | Scheduled | 14/08/2023 | 08/09/2023
TO-23-LIS-T142-03 | DISTRIBUTION TRANSFORMER - LISDRUM 110-LISDRUM 38-T142 | 26 | 20 | 20 | Reference | 14/08/2023 | 08/09/2023
TO-23-MEE-T121-01 | GENERATOR TRANSFORMER - MEENTYCAT 110-MEENTYCAT 20-T121 | 4 | 4 | 4 | Scheduled | 14/08/2023 | 17/08/2023
TO-23-BEG-CKM GIS-1-01 | 110kV FEEDER - BALLYBEG 110-CARRICKMINES GIS 110-1 | 8 | 6 | 6 | Scheduled | 15/08/2023 | 22/08/2023
TO-23-CUS-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - CUSHALING 110-CUSHALING 110-110SA1-2CB | 4 | 4 | 4 | Scheduled | 15/08/2023 | 18/08/2023
TO-23-CUS-KIR-1-02 | 110kV FEEDER - CUSHALING 110-KILCUMBER 110-1 | 4 | 4 | 4 | Scheduled | 15/08/2023 | 18/08/2023
TO-23-CUS-MLC-1-04 | 110kV FEEDER - CUSHALING 110-MOUNTLUCAS 110-1 | 4 | 4 | 4 | Scheduled | 15/08/2023 | 18/08/2023
TO-23-KIR-T131-03 | GENERATOR TRANSFORMER - KILCUMBER 110-KILCUMBER 33-T131 | 4 | 4 | 4 | Scheduled | 15/08/2023 | 18/08/2023
TO-23-CKN-KER-1-02 | 110kV FEEDER - CLONKEEN 110-KNOCKEARAGH 110-1 | 2 | 2 | 2 | Scheduled | 16/08/2023 | 17/08/2023
TO-23-DRY-110SA1-02 | SECTIONALISING DISCONNECT - DRYBRIDGE 110-DRYBRIDGE 110-110SA1 | 1 | 1 | 1 | Scheduled | 16/08/2023 | 16/08/2023
TO-23-DRY-110SA2-01 | SECTIONALISING DISCONNECT - DRYBRIDGE 110-DRYBRIDGE 110-110SA2 | 1 | 1 | 1 | Scheduled | 16/08/2023 | 16/08/2023
TO-23-GAE-T121-03 | GENERATOR TRANSFORMER - GLANLEE 110-GLANLEE 20-T121 | 3 | 3 | 3 | Scheduled | 16/08/2023 | 18/08/2023
TO-23-AD-GGO-1-01 | 220kV FEEDER - AGHADA 220-GLANAGOW 220-1 | 22 | 16 | 16 | Scheduled | 18/08/2023 | 08/09/2023
TO-23-AD-KRA-2-04 | 220kV FEEDER - AGHADA 220-KNOCKRAHA 220-2 | 7 | 5 | 5 | Scheduled | 18/08/2023 | 24/08/2023
TO-23-FLA-LOU-1-09 | 220kV FEEDER - FLAGFORD 220-LOUTH 220-1 | 3 | 1 |  | Scheduled | 18/08/2023 | 20/08/2023
TO-23-GGO-RAF-1-01 | 220kV FEEDER - GLANAGOW 220-RAFFEEN 220-1 | 22 | 16 | 16 | Scheduled | 18/08/2023 | 08/09/2023
TO-23-GGO-T2001-01 | GENERATOR TRANSFORMER - GLANAGOW 220-GLANAGOW G1-T2001 | 22 | 16 | 16 | Scheduled | 18/08/2023 | 08/09/2023
TO-23-GOR-LOU-1-03 | 220kV FEEDER - GORMAN 220-LOUTH 220-1 | 3 | 1 |  | Scheduled | 18/08/2023 | 20/08/2023
TO-23-KRA-220SB1-2CB-03 | COUPLER/SECTIONALISING CB - KNOCKRAHA 220-KNOCKRAHA 220-220SB1-2CB | 7 | 5 | 5 | Scheduled | 18/08/2023 | 24/08/2023
TO-23-LOU-AT1-03 | TRANSFORMER - LOUTH 220-LOUTH 275-AT1 | 3 | 1 |  | Scheduled | 18/08/2023 | 20/08/2023
TO-23-LOU-AT3-04 | TRANSFORMER - LOUTH 220-LOUTH 275-AT3 | 3 | 1 |  | Scheduled | 18/08/2023 | 20/08/2023
TO-23-LOU-T2102-07 | TRANSFORMER - LOUTH 220-LOUTH 110-T2102 | 3 | 1 |  | Scheduled | 18/08/2023 | 20/08/2023
TO-23-LOU-T2104-01 | TRANSFORMER - LOUTH 220-LOUTH 110-T2104 | 3 | 1 |  | Scheduled | 18/08/2023 | 20/08/2023
TO-23-LOU-TAN-1-02 | 275kV FEEDER - LOUTH 275-TANDRAGEE 275-1 | 3 | 1 |  | Scheduled | 18/08/2023 | 20/08/2023
TO-23-DSN-KLS-1-05 | 220kV FEEDER - DUNSTOWN 220-KELLIS 220-1 | 2 | 0 | 0 | Scheduled | 19/08/2023 | 20/08/2023
TO-23-KLS-T2101-04 | TRANSFORMER - KELLIS 220-KELLIS 110-T2101 | 2 | 0 | 0 | Scheduled | 19/08/2023 | 20/08/2023
TO-23-ARV-NAV-1-05 | 110kV FEEDER - ARVA 110-NAVAN 110-1 | 26 | 20 | 20 | Scheduled | 21/08/2023 | 15/09/2023
TO-23-BOG-CRA-1-01 | 110kV FEEDER - BANOGE 110-CRANE 110-1 | 113 | 80 |  | Scheduled | 21/08/2023 | 11/12/2023
TO-23-CLA-CKN-1-01 | 110kV FEEDER - CLASHAVOON 110-CLONKEEN 110-1 | 11 | 9 | 9 | Scheduled | 21/08/2023 | 31/08/2023
TO-23-CKN-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - CLONKEEN 110-CLONKEEN 110-110SA1-2CB | 11 | 9 | 9 | Scheduled | 21/08/2023 | 31/08/2023
TO-23-CKN-CGL-1-01 | 110kV FEEDER - CLONKEEN 110-COOMAGEARLAHY 110-1 | 11 | 9 | 9 | Scheduled | 21/08/2023 | 31/08/2023
TO-23-CKN-GRO-1-01 | 110kV FEEDER - CLONKEEN 110-GARROW 110-1 | 11 | 9 | 9 | Scheduled | 21/08/2023 | 31/08/2023
TO-23-CKN-KER-1-01 | 110kV FEEDER - CLONKEEN 110-KNOCKEARAGH 110-1 | 11 | 9 | 9 | Scheduled | 21/08/2023 | 31/08/2023
TO-23-CGL-110SA1-01 | SECTIONALISING DISCONNECT - COOMAGEARLAHY 110-COOMAGEARLAHY 110-110SA1 | 11 | 9 | 9 | Scheduled | 21/08/2023 | 31/08/2023
TO-23-CGL-110SA2-01 | SECTIONALISING DISCONNECT - COOMAGEARLAHY 110-COOMAGEARLAHY 110-110SA2 | 11 | 9 | 9 | Scheduled | 21/08/2023 | 31/08/2023
TO-23-CGL-GAE-1-01 | 110kV FEEDER - COOMAGEARLAHY 110-GLANLEE 110-1 | 11 | 9 | 9 | Scheduled | 21/08/2023 | 31/08/2023
TO-23-CGL-T121-01 | GENERATOR TRANSFORMER - COOMAGEARLAHY 110-COOMAGEARLAHY 20-T121 | 11 | 9 | 9 | Scheduled | 21/08/2023 | 31/08/2023
TO-23-CGL-T122-01 | GENERATOR TRANSFORMER - COOMAGEARLAHY 110-COOMAGEARLAHY 20-T122 | 11 | 9 | 9 | Scheduled | 21/08/2023 | 31/08/2023
TO-23-220 kV A2 @ DSN-02 | BUSBAR SECTION - DUNSTOWN 220-DUNSTOWN 220-220A2 | 19 | 15 | 15 | Scheduled | 21/08/2023 | 08/09/2023
TO-23-220 kV B2 @ DSN-02 | BUSBAR SECTION - DUNSTOWN 220-DUNSTOWN 220-220B2 | 19 | 15 | 15 | Scheduled | 21/08/2023 | 08/09/2023
TO-23-110 kV A2 @ FIN GIS-08 | BUSBAR SECTION - FINGLAS GIS 110-FINGLAS GIS 110-110A2 | 5 | 5 | 5 | Scheduled | 21/08/2023 | 25/08/2023
TO-23-110 kV B2 @ FIN GIS-07 | BUSBAR SECTION - FINGLAS GIS 110-FINGLAS GIS 110-110B2 | 5 | 5 | 5 | Scheduled | 21/08/2023 | 25/08/2023
TO-23-FIN GIS-110K2-09 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110K2 | 5 | 5 | 5 | Scheduled | 21/08/2023 | 25/08/2023
TO-23-FIN GIS-110SA1-2CB-09 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110SA1-2CB | 5 | 5 | 5 | Scheduled | 21/08/2023 | 25/08/2023
TO-23-FIN GIS-110SA2-4CB-09 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110SA2-4CB | 5 | 5 | 5 | Scheduled | 21/08/2023 | 25/08/2023
TO-23-FIN GIS-110SB1-2CB-09 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110SB1-2CB | 5 | 5 | 5 | Scheduled | 21/08/2023 | 25/08/2023
TO-23-FIN GIS-110SB2-4CB-09 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110SB2-4CB | 5 | 5 | 5 | Scheduled | 21/08/2023 | 25/08/2023
TO-23-110 kV A1 @ GAL GIS-02 | BUSBAR SECTION - GALWAY GIS 110-GALWAY GIS 110-110A1 | 2 | 2 | 2 | Scheduled | 21/08/2023 | 22/08/2023
TO-23-110 kV B1 @ GAL GIS-02 | BUSBAR SECTION - GALWAY GIS 110-GALWAY GIS 110-110B1 | 2 | 2 | 2 | Scheduled | 21/08/2023 | 22/08/2023
TO-23-GAL GIS-110SA1-2CB-06 | COUPLER/SECTIONALISING CB - GALWAY GIS 110-GALWAY GIS 110-110SA1-2CB | 2 | 2 | 2 | Scheduled | 21/08/2023 | 22/08/2023
TO-23-GAL GIS-110SA1-3CB-02 | COUPLER/SECTIONALISING CB - GALWAY GIS 110-GALWAY GIS 110-110SA1-3CB | 2 | 2 | 2 | Scheduled | 21/08/2023 | 22/08/2023
TO-23-GAL GIS-110SB1-2CB-07 | COUPLER/SECTIONALISING CB - GALWAY GIS 110-GALWAY GIS 110-110SB1-2CB | 2 | 2 | 2 | Scheduled | 21/08/2023 | 22/08/2023
TO-23-GAL GIS-110SB1-2CB-06 | COUPLER/SECTIONALISING CB - GALWAY GIS 110-GALWAY GIS 110-110SB1-2CB | 2 | 2 | 2 | Scheduled | 21/08/2023 | 22/08/2023
TO-23-GAL GIS-110SB1-3CB-02 | COUPLER/SECTIONALISING CB - GALWAY GIS 110-GALWAY GIS 110-110SB1-3CB | 2 | 2 | 2 | Scheduled | 21/08/2023 | 22/08/2023
TO-23-GAL GIS-SAL-1-04 | 110kV FEEDER - GALWAY GIS 110-SALTHILL 110-1 | 2 | 2 |  | Scheduled | 21/08/2023 | 22/08/2023
TO-23-GAE-T121-01 | GENERATOR TRANSFORMER - GLANLEE 110-GLANLEE 20-T121 | 11 | 9 | 9 | Scheduled | 21/08/2023 | 31/08/2023
TO-23-MRY-T131-01 | GENERATOR TRANSFORMER - MULREAVY 110-MULREAVY 33-T131 | 5 | 5 | 5 | Scheduled | 21/08/2023 | 25/08/2023
TO-23-AA GIS-ENN-1-01 | 110kV FEEDER - ARDNACRUSHA GIS 110-ENNIS 110-1 | 2 | 2 | 2 | Scheduled | 22/08/2023 | 23/08/2023
TO-23-ATY-PLS-1-03 | 110kV FEEDER - ATHY 110-PORTLAOISE 110-1 | 3 | 3 | 3 | Scheduled | 22/08/2023 | 24/08/2023
TO-23-BDN-110SA1-04 | SECTIONALISING DISCONNECT - BALLYDINE 110-BALLYDINE 110-110SA1 | 1 | 1 | 1 | Scheduled | 22/08/2023 | 22/08/2023
TO-23-BDN-110SA2-01 | SECTIONALISING DISCONNECT - BALLYDINE 110-BALLYDINE 110-110SA2 | 1 | 1 |  | Scheduled | 22/08/2023 | 22/08/2023
TO-23-BDN-T141-03 | DISTRIBUTION TRANSFORMER - BALLYDINE 110-BALLYDINE 38-T141 | 1 | 1 | 1 | Reference | 22/08/2023 | 22/08/2023
TO-23-DOO-T142-02 | DISTRIBUTION TRANSFORMER - DOON 110-DOON 38-T142 | 80 | 57 | 57 | Reference | 23/08/2023 | 10/11/2023
TO-23-FIN-FIN GIS-1-03 | 110kV FEEDER - FINGLAS 110-FINGLAS GIS 110-1 | 2 | 2 | 2 | Scheduled | 24/08/2023 | 25/08/2023
TO-23-110 kV A2 @ FIN GIS-06 | BUSBAR SECTION - FINGLAS GIS 110-FINGLAS GIS 110-110A2 | 2 | 2 | 2 | Scheduled | 24/08/2023 | 25/08/2023
TO-23-110 kV A4 @ FIN GIS-03 | BUSBAR SECTION - FINGLAS GIS 110-FINGLAS GIS 110-110A4 | 2 | 2 | 2 | Scheduled | 24/08/2023 | 25/08/2023
TO-23-110 kV B2 @ FIN GIS-05 | BUSBAR SECTION - FINGLAS GIS 110-FINGLAS GIS 110-110B2 | 2 | 2 | 2 | Scheduled | 24/08/2023 | 25/08/2023
TO-23-110 kV B4 @ FIN GIS-03 | BUSBAR SECTION - FINGLAS GIS 110-FINGLAS GIS 110-110B4 | 2 | 2 | 2 | Scheduled | 24/08/2023 | 25/08/2023
TO-23-FIN GIS-110K2-08 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110K2 | 2 | 2 | 2 | Scheduled | 24/08/2023 | 25/08/2023
TO-23-FIN GIS-110SA1-2CB-08 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110SA1-2CB | 2 | 2 | 2 | Scheduled | 24/08/2023 | 25/08/2023
TO-23-FIN GIS-110SA2-4CB-08 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110SA2-4CB | 2 | 2 | 2 | Scheduled | 24/08/2023 | 25/08/2023
TO-23-FIN GIS-110SA4-6CB-05 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110SA4-6CB | 2 | 2 | 2 | Scheduled | 24/08/2023 | 25/08/2023
TO-23-FIN GIS-110SB1-2CB-08 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110SB1-2CB | 2 | 2 | 2 | Scheduled | 24/08/2023 | 25/08/2023
TO-23-FIN GIS-110SB2-4CB-08 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110SB2-4CB | 2 | 2 | 2 | Scheduled | 24/08/2023 | 25/08/2023
TO-23-FIN GIS-110SB4-6CB-05 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110SB4-6CB | 2 | 2 | 2 | Scheduled | 24/08/2023 | 25/08/2023
TO-23-PB-T2007/8-02 | GENERATOR TRANSFORMER - POOLBEG 220-POOLBEG G7/8-T2007/8 | 67 | 47 |  | Scheduled | 24/08/2023 | 29/10/2023
TO-23-CLW-KLS-2-06 | 110kV FEEDER - CARLOW 110-KELLIS 110-2 | 1 | 1 | 1 | Scheduled | 25/08/2023 | 25/08/2023
TO-23-CSH-GAL-1-01 | 110kV FEEDER - CASHLA 110-GALWAY 110-1 | 85 | 60 |  | Scheduled | 25/08/2023 | 17/11/2023
TO-23-KPG-F11-1-CUB-01 | CUBICLE - KILPADDOGE 220-F11 SPARE 220-1-CUB | 4 | 2 | 2 | Scheduled | 25/08/2023 | 28/08/2023
TO-23-220 kV A3 @ KPG-04 | BUSBAR SECTION - KILPADDOGE 220-KILPADDOGE 220-220A3 | 4 | 2 | 2 | Scheduled | 25/08/2023 | 28/08/2023
TO-23-220 kV B3 @ KPG-04 | BUSBAR SECTION - KILPADDOGE 220-KILPADDOGE 220-220B3 | 4 | 2 | 2 | Scheduled | 25/08/2023 | 28/08/2023
TO-23-LOU-AT2-03 | TRANSFORMER - LOUTH 220-LOUTH 275-AT2 | 3 | 1 | 1 | Scheduled | 25/08/2023 | 27/08/2023
TO-23-LOU-T2101-02 | TRANSFORMER - LOUTH 220-LOUTH 110-T2101 | 3 | 1 | 1 | Scheduled | 25/08/2023 | 27/08/2023
TO-23-LOU-T2103-03 | TRANSFORMER - LOUTH 220-LOUTH 110-T2103 | 3 | 1 | 1 | Scheduled | 25/08/2023 | 27/08/2023
TO-23-LOU-TAN-2-03 | 275kV FEEDER - LOUTH 275-TANDRAGEE 275-2 | 3 | 1 | 1 | Scheduled | 25/08/2023 | 27/08/2023
TO-23-LOU-WOO-1-02 | 220kV FEEDER - LOUTH 220-WOODLAND 220-1 | 3 | 1 | 1 | Scheduled | 25/08/2023 | 27/08/2023
TO-23-TAW-T1/T2-01 | GENERATOR TRANSFORMER - TAWNAGHMORE 110-TAWNAGHMORE 10-T1/T2 | 8 | 6 | 6 | Scheduled | 25/08/2023 | 01/09/2023
TO-23-AD-KRA-2-06 | 220kV FEEDER - AGHADA 220-KNOCKRAHA 220-2 | 1 | 0 | 0 | Scheduled | 26/08/2023 | 26/08/2023
TO-23-DSN-KLS-1-06 | 220kV FEEDER - DUNSTOWN 220-KELLIS 220-1 | 2 | 0 | 0 | Scheduled | 26/08/2023 | 27/08/2023
TO-23-KLS-T2101-05 | TRANSFORMER - KELLIS 220-KELLIS 110-T2101 | 2 | 0 | 0 | Scheduled | 26/08/2023 | 27/08/2023
TO-23-KRA-220SB1-2CB-04 | COUPLER/SECTIONALISING CB - KNOCKRAHA 220-KNOCKRAHA 220-220SB1-2CB | 1 | 0 | 0 | Scheduled | 26/08/2023 | 26/08/2023
TO-23-110 kV A2 @ CSH-02 | BUSBAR SECTION - CASHLA 110-CASHLA 110-110A2 | 4 | 4 |  | Scheduled | 28/08/2023 | 31/08/2023
TO-23-CSH-T2104-01 | TRANSFORMER - CASHLA 220-CASHLA 110-T2104 | 4 | 4 | 4 | Scheduled | 28/08/2023 | 31/08/2023
TO-23-CLE-T221-01 | TSO CUSTOMER TRANSFORMER - CLONEE 220-CLONEE 20-T221 | 29 | 21 | 21 | Scheduled | 28/08/2023 | 25/09/2023
TO-23-110 kV A2 @ KLS-05 | BUSBAR SECTION - KELLIS 110-KELLIS 110-110A2 | 12 | 10 | 10 | Scheduled | 28/08/2023 | 08/09/2023
TO-23-110 kV B2 @ KLS-05 | BUSBAR SECTION - KELLIS 110-KELLIS 110-110B2 | 12 | 10 | 10 | Scheduled | 28/08/2023 | 08/09/2023
TO-23-KLS-T2102-01 | TRANSFORMER - KELLIS 220-KELLIS 110-T2102 | 12 | 10 |  | Scheduled | 28/08/2023 | 08/09/2023
TO-23-BUT-CUL-1-02 | 110kV FEEDER - BUTLERSTOWN 110-CULLENAGH 110-1 | 77 | 54 | 54 | Scheduled | 29/08/2023 | 13/11/2023
TO-23-IKE,T-THU-1-07 | 110kV FEEDER - IKERRIN tee-THURLES 110-1 | 1 | 1 | 1 | Scheduled | 29/08/2023 | 29/08/2023
TO-23-IKE,T-THU-1-08 | 110kV FEEDER - IKERRIN tee-THURLES 110-1 | 10 | 8 | 8 | Scheduled | 29/08/2023 | 07/09/2023
TO-23-LSN-110SA1-2-06 | SECTIONALISING DISCONNECT - LISHEEN 110-LISHEEN 110-110SA1-2 | 10 | 8 | 8 | Scheduled | 29/08/2023 | 07/09/2023
TO-23-LSN-110SA2-4-06 | SECTIONALISING DISCONNECT - LISHEEN 110-LISHEEN 110-110SA2-4 | 10 | 8 | 8 | Scheduled | 29/08/2023 | 07/09/2023
TO-23-LSN-T122-06 | GENERATOR TRANSFORMER - LISHEEN 110-LISHEEN 20-T122 | 10 | 8 | 8 | Scheduled | 29/08/2023 | 07/09/2023
TO-23-LSN-T131-06 | GENERATOR TRANSFORMER - LISHEEN 110-LISHEEN 33-T131 | 10 | 8 | 8 | Scheduled | 29/08/2023 | 07/09/2023
TO-23-LSN-T142-06 | DISTRIBUTION TRANSFORMER - LISHEEN 110-LISHEEN 38-T142 | 10 | 8 | 8 | Reference | 29/08/2023 | 07/09/2023
TO-23-LSN-THU-1-07 | 110kV FEEDER - LISHEEN 110-THURLES 110-1 | 10 | 8 | 8 | Scheduled | 29/08/2023 | 07/09/2023
TO-23-THU-110SA1-2CB-06 | COUPLER/SECTIONALISING CB - THURLES 110-THURLES 110-110SA1-2CB | 10 | 8 | 8 | Scheduled | 29/08/2023 | 07/09/2023
TO-23-THU-T142-05 | DISTRIBUTION TRANSFORMER - THURLES 110-THURLES 38-T142 | 10 | 8 | 8 | Reference | 29/08/2023 | 07/09/2023
TO-23-110 kV A2 @ FLA-02 | BUSBAR SECTION - FLAGFORD 110-FLAGFORD 110-110A2 | 3 | 3 | 3 | Scheduled | 30/08/2023 | 01/09/2023
TO-23-110 kV B2 @ FLA-02 | BUSBAR SECTION - FLAGFORD 110-FLAGFORD 110-110B2 | 3 | 3 | 3 | Scheduled | 30/08/2023 | 01/09/2023
TO-23-IA-T101-04 | GENERATOR TRANSFORMER - INNISCARRA 110-INNISCARRA G1-T101 | 2 | 2 | 2 | Scheduled | 30/08/2023 | 31/08/2023
TO-23-220 kV A1/A2 @ KRA-02 | BUSBAR SECTION - KNOCKRAHA 220-KNOCKRAHA 220-220A1-A2 | 65 | 46 |  | Scheduled | 30/08/2023 | 02/11/2023
TO-23-KRA-220K1-06 | COUPLER/SECTIONALISING CB - KNOCKRAHA 220-KNOCKRAHA 220-220K1 | 65 | 46 |  | Scheduled | 30/08/2023 | 02/11/2023
TO-23-KRA-220SA2-4CB-03 | COUPLER/SECTIONALISING CB - KNOCKRAHA 220-KNOCKRAHA 220-220SA2-4CB | 65 | 46 |  | Scheduled | 30/08/2023 | 02/11/2023
TO-23-TAW-T3-01 | GENERATOR TRANSFORMER - TAWNAGHMORE 110-TAWNAGHMORE 10-T3 | 8 | 6 | 6 | Scheduled | 01/09/2023 | 08/09/2023
TO-23-CLA-MAC-1-02 | 110kV FEEDER - CLASHAVOON 110-MACROOM 110-1 | 1 | 0 | 0 | Scheduled | 02/09/2023 | 02/09/2023
TO-23-DMY-MAC-1-02 | 110kV FEEDER - DUNMANWAY 110-MACROOM 110-1 | 1 | 0 | 0 | Scheduled | 02/09/2023 | 02/09/2023
TO-23-MAC-110SA1-2CB-02 | COUPLER/SECTIONALISING CB - MACROOM 110-MACROOM 110-110SA1-2CB | 1 | 0 | 0 | Scheduled | 02/09/2023 | 02/09/2023
TO-23-MAC-T142-02 | DISTRIBUTION TRANSFORMER - MACROOM 110-MACROOM 38-T142 | 1 | 0 | 0 | Reference | 02/09/2023 | 02/09/2023
TO-23-AA GIS-T101-01 | GENERATOR TRANSFORMER - ARDNACRUSHA GIS 110-ARDNACRUSHA GIS G1-T101 | 5 | 5 | 5 | Scheduled | 04/09/2023 | 08/09/2023
TO-23-110 kV A2 @ CSH-07 | BUSBAR SECTION - CASHLA 110-CASHLA 110-110A2 | 8 | 6 | 6 | Scheduled | 04/09/2023 | 11/09/2023
TO-23-110 kV B2 @ CSH-08 | BUSBAR SECTION - CASHLA 110-CASHLA 110-110B2 | 8 | 6 | 6 | Scheduled | 04/09/2023 | 11/09/2023
TO-23-CL-T101-01 | GENERATOR TRANSFORMER - CLIFF 110-CLIFF G1-T101 | 5 | 5 | 5 | Scheduled | 04/09/2023 | 08/09/2023
TO-23-CLG-T124-01 | TSO CUSTOMER TRANSFORMER - CLOGHRAN 110-CLOGHRAN 20-T124 | 5 | 5 | 5 | Scheduled | 04/09/2023 | 08/09/2023
TO-23-GRO-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - GARROW 110-GARROW 110-110SA1-2CB | 4 | 4 | 4 | Scheduled | 04/09/2023 | 07/09/2023
TO-23-GRO-T122-01 | GENERATOR TRANSFORMER - GARROW 110-GARROW 20-T122 | 4 | 4 | 4 | Scheduled | 04/09/2023 | 07/09/2023
TO-23-KBY-MR-1-06 | 110kV FEEDER - KILBARRY 110-MARINA 110-1 | 82 | 59 |  | Scheduled | 04/09/2023 | 24/11/2023
TO-23-KBY-MR-2-02 | 110kV FEEDER - KILBARRY 110-MARINA 110-2 | 82 | 59 |  | Scheduled | 04/09/2023 | 24/11/2023
TO-23-KIN-T102-01 | TSO CUSTOMER TRANSFORMER - KINNEGAD 110-KINNEGAD 10-T102 | 9 | 7 | 7 | Scheduled | 04/09/2023 | 12/09/2023
TO-23-KRA-MID-1-01 | 110kV FEEDER - KNOCKRAHA 110-MIDLETON 110-1 | 96 | 69 | 69 | Scheduled | 04/09/2023 | 08/12/2023
TO-23-MOY-TAW-2-04 | 110kV FEEDER - MOY 110-TAWNAGHMORE 110-2 | 5 | 5 | 5 | Scheduled | 04/09/2023 | 08/09/2023
TO-23-SOM-T142-04 | DISTRIBUTION TRANSFORMER - SOMERSET 110-SOMERSET 38-T142 | 8 | 6 | 6 | Reference | 04/09/2023 | 11/09/2023
TO-23-SOM,T-CSH-1-03 | 110kV FEEDER - SOMERSET tee-CASHLA 110-1 | 8 | 6 | 6 | Scheduled | 04/09/2023 | 11/09/2023
TO-23-SOM,T-SH-1-05 | 110kV FEEDER - SOMERSET tee-SHANNONBRIDGE 110-1 | 8 | 6 | 6 | Scheduled | 04/09/2023 | 11/09/2023
TO-23-SOM,T-SOM-1-04 | 110kV FEEDER - SOMERSET tee-SOMERSET 110-1 | 8 | 6 | 6 | Scheduled | 04/09/2023 | 11/09/2023
TO-23-TAW-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - TAWNAGHMORE 110-TAWNAGHMORE 110-110SA1-2CB | 5 | 5 | 5 | Scheduled | 04/09/2023 | 08/09/2023
TO-23-TAW-T142-01 | DISTRIBUTION TRANSFORMER - TAWNAGHMORE 110-TAWNAGHMORE 38-T142 | 5 | 5 | 5 | Reference | 04/09/2023 | 08/09/2023
TO-23-110 kV A1 @ TBG-01 | BUSBAR SECTION - TRABEG 110-TRABEG 110-110A1 | 5 | 5 | 5 | Scheduled | 04/09/2023 | 08/09/2023
TO-23-110 kV A2 @ TBG-02 | BUSBAR SECTION - TRABEG 110-TRABEG 110-110A2 | 5 | 5 | 5 | Scheduled | 04/09/2023 | 08/09/2023
TO-23-110 kV B1 @ TBG-01 | BUSBAR SECTION - TRABEG 110-TRABEG 110-110B1 | 5 | 5 | 5 | Scheduled | 04/09/2023 | 08/09/2023
TO-23-110 kV B2 @ TBG-02 | BUSBAR SECTION - TRABEG 110-TRABEG 110-110B2 | 5 | 5 | 5 | Scheduled | 04/09/2023 | 08/09/2023
TO-23-TBG-110K1-2-02 | COUPLER/SECTIONALISING CB - TRABEG 110-TRABEG 110-110K1-2 | 5 | 5 | 5 | Scheduled | 04/09/2023 | 08/09/2023
TO-23-TBG-T101-01 | DISTRIBUTION TRANSFORMER - TRABEG 110-TRABEG 10-T101 | 5 | 5 | 5 | Reference | 04/09/2023 | 08/09/2023
TO-23-TBG-T141-01 | DISTRIBUTION TRANSFORMER - TRABEG 110-TRABEG 38-T141 | 5 | 5 | 5 | Reference | 04/09/2023 | 08/09/2023
TO-23-GLR-MOY-1-01 | 110kV FEEDER - GLENREE 110-MOY 110-1 | 21 | 15 | 15 | Scheduled | 05/09/2023 | 25/09/2023
TO-23-LOU-T2104-06 | TRANSFORMER - LOUTH 220-LOUTH 110-T2104 | 4 | 4 | 4 | Scheduled | 05/09/2023 | 08/09/2023
TO-23-400 kV A1 @ MP GIS-03 | BUSBAR SECTION - MONEYPOINT GIS 400-MONEYPOINT GIS 400-400A1 | 2 | 2 | 2 | Scheduled | 05/09/2023 | 06/09/2023
TO-23-400 kV A2 @ MP GIS-01 | BUSBAR SECTION - MONEYPOINT GIS 400-MONEYPOINT GIS 400-400A2 | 2 | 2 | 2 | Scheduled | 05/09/2023 | 06/09/2023
TO-23-400 kV A3 @ MP GIS-03 | BUSBAR SECTION - MONEYPOINT GIS 400-MONEYPOINT GIS 400-400A3 | 2 | 2 | 2 | Scheduled | 05/09/2023 | 06/09/2023
TO-23-400 kV A4 @ MP GIS-03 | BUSBAR SECTION - MONEYPOINT GIS 400-MONEYPOINT GIS 400-400A4 | 2 | 2 | 2 | Scheduled | 05/09/2023 | 06/09/2023
TO-23-400 kV B1 @ MP GIS-03 | BUSBAR SECTION - MONEYPOINT GIS 400-MONEYPOINT GIS 400-400B1 | 2 | 2 | 2 | Scheduled | 05/09/2023 | 06/09/2023
TO-23-400 kV B2 @ MP GIS-01 | BUSBAR SECTION - MONEYPOINT GIS 400-MONEYPOINT GIS 400-400B2 | 2 | 2 | 2 | Scheduled | 05/09/2023 | 06/09/2023
TO-23-400 kV B3 @ MP GIS-02 | BUSBAR SECTION - MONEYPOINT GIS 400-MONEYPOINT GIS 400-400B3 | 2 | 2 | 2 | Scheduled | 05/09/2023 | 06/09/2023
TO-23-400 kV B4 @ MP GIS-02 | BUSBAR SECTION - MONEYPOINT GIS 400-MONEYPOINT GIS 400-400B4 | 2 | 2 | 2 | Scheduled | 05/09/2023 | 06/09/2023
TO-23-MP GIS-400K3-02 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 400-MONEYPOINT GIS 400-400K3 | 2 | 2 | 2 | Scheduled | 05/09/2023 | 06/09/2023
TO-23-MP GIS-400K4-01 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 400-MONEYPOINT GIS 400-400K4 | 2 | 2 |  | Scheduled | 05/09/2023 | 06/09/2023
TO-23-MP GIS-400SA1-2CB-01 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 400-MONEYPOINT GIS 400-400SA1-2CB | 2 | 2 | 2 | Scheduled | 05/09/2023 | 06/09/2023
TO-23-MP GIS-400SA1-3CB-03 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 400-MONEYPOINT GIS 400-400SA1-3CB | 2 | 2 | 2 | Scheduled | 05/09/2023 | 06/09/2023
TO-23-MP GIS-400SA2-4CB-01 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 400-MONEYPOINT GIS 400-400SA2-4CB | 2 | 2 |  | Scheduled | 05/09/2023 | 06/09/2023
TO-23-MP GIS-400SB1-2CB-01 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 400-MONEYPOINT GIS 400-400SB1-2CB | 2 | 2 | 2 | Scheduled | 05/09/2023 | 06/09/2023
TO-23-MP GIS-400SB1-3CB-02 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 400-MONEYPOINT GIS 400-400SB1-3CB | 2 | 2 | 2 | Scheduled | 05/09/2023 | 06/09/2023
TO-23-MP GIS-400SB2-4CB-02 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 400-MONEYPOINT GIS 400-400SB2-4CB | 2 | 2 | 2 | Scheduled | 05/09/2023 | 06/09/2023
TO-23-MP GIS-OST-1-06 | 400kV FEEDER - MONEYPOINT GIS 400-OLDSTREET 400-1 | 2 | 2 | 2 | Scheduled | 05/09/2023 | 06/09/2023
TO-23-SHL-T2014-01 | GENERATOR TRANSFORMER - SHELLYBANKS 220-SHELLYBANKS G4-T2014 | 1 | 1 | 1 | Scheduled | 06/09/2023 | 06/09/2023
TO-23-BYH-BVK-1-01 | 220kV FEEDER - BALLYNAHULLA 220-BALLYVOUSKILL 220-1 | 8 | 6 | 6 | Scheduled | 07/09/2023 | 14/09/2023
TO-23-CGG-T131-02 | GENERATOR TRANSFORMER - CARRIGDANGAN 110-CARRIGDANGAN 33-T131 | 1 | 1 | 1 | Scheduled | 07/09/2023 | 07/09/2023
TO-23-GGO-RAF-1-05 | 220kV FEEDER - GLANAGOW 220-RAFFEEN 220-1 | 13 | 9 | 9 | Scheduled | 08/09/2023 | 20/09/2023
TO-23-KHL-THU-1-01 | 110kV FEEDER - KILL HILL 110-THURLES 110-1 | 8 | 6 | 6 | Scheduled | 08/09/2023 | 15/09/2023
TO-23-THU-110SA1-2CB-07 | COUPLER/SECTIONALISING CB - THURLES 110-THURLES 110-110SA1-2CB | 8 | 6 | 6 | Scheduled | 08/09/2023 | 15/09/2023
TO-23-THU-CAP1-02 | CAPACITOR/SVC/REACTOR - THURLES 110-THURLES 110-CAP1 | 8 | 6 | 6 | Scheduled | 08/09/2023 | 15/09/2023
TO-23-THU-T141-01 | DISTRIBUTION TRANSFORMER - THURLES 110-THURLES 38-T141 | 8 | 6 | 6 | Reference | 08/09/2023 | 15/09/2023
TO-23-AA GIS-T102-04 | GENERATOR TRANSFORMER - ARDNACRUSHA GIS 110-ARDNACRUSHA GIS G2-T102 | 19 | 15 | 15 | Scheduled | 11/09/2023 | 29/09/2023
TO-23-BDA-T102-01 | TSO CUSTOMER TRANSFORMER - BARODA 110-BARODA 10-T102 | 5 | 5 |  | Scheduled | 11/09/2023 | 15/09/2023
TO-23-CKM GIS-DSN-1-04 | 220kV FEEDER - CARRICKMINES GIS 220-DUNSTOWN 220-1 | 6 | 5 | 5 | Scheduled | 11/09/2023 | 16/09/2023
TO-23-110 kV A1 @ CLG-03 | BUSBAR SECTION - CLOGHRAN 110-CLOGHRAN 110-110A1 | 5 | 5 | 5 | Scheduled | 11/09/2023 | 15/09/2023
TO-23-110 kV A2 @ CLG-01 | BUSBAR SECTION - CLOGHRAN 110-CLOGHRAN 110-110A2 | 5 | 5 | 5 | Scheduled | 11/09/2023 | 15/09/2023
TO-23-110 kV B1 @ CLG-03 | BUSBAR SECTION - CLOGHRAN 110-CLOGHRAN 110-110B1 | 5 | 5 | 5 | Scheduled | 11/09/2023 | 15/09/2023
TO-23-110 kV B2 @ CLG-01 | BUSBAR SECTION - CLOGHRAN 110-CLOGHRAN 110-110B2 | 5 | 5 | 5 | Scheduled | 11/09/2023 | 15/09/2023
TO-23-CLG-110K2-02 | COUPLER/SECTIONALISING CB - CLOGHRAN 110-CLOGHRAN 110-110K2 | 5 | 5 | 5 | Scheduled | 11/09/2023 | 15/09/2023
TO-23-CLG-110SA1-2CB-02 | COUPLER/SECTIONALISING CB - CLOGHRAN 110-CLOGHRAN 110-110SA1-2CB | 5 | 5 | 5 | Scheduled | 11/09/2023 | 15/09/2023
TO-23-CLG-110SB1-2CB-02 | COUPLER/SECTIONALISING CB - CLOGHRAN 110-CLOGHRAN 110-110SB1-2CB | 5 | 5 | 5 | Scheduled | 11/09/2023 | 15/09/2023
TO-23-CLG-T126-01 | TSO CUSTOMER TRANSFORMER - CLOGHRAN 110-CLOGHRAN 20-T126 | 5 | 5 | 5 | Scheduled | 11/09/2023 | 15/09/2023
TO-23-220 kV A1 @ DSN-01 | BUSBAR SECTION - DUNSTOWN 220-DUNSTOWN 220-220A1 | 12 | 10 | 10 | Scheduled | 11/09/2023 | 22/09/2023
TO-23-220 kV A2 @ DSN-01 | BUSBAR SECTION - DUNSTOWN 220-DUNSTOWN 220-220A2 | 12 | 10 | 10 | Scheduled | 11/09/2023 | 22/09/2023
TO-23-220 kV B1 @ DSN-01 | BUSBAR SECTION - DUNSTOWN 220-DUNSTOWN 220-220B1 | 12 | 10 | 10 | Scheduled | 11/09/2023 | 22/09/2023
TO-23-220 kV B2 @ DSN-01 | BUSBAR SECTION - DUNSTOWN 220-DUNSTOWN 220-220B2 | 12 | 10 | 10 | Scheduled | 11/09/2023 | 22/09/2023
TO-23-FIN-NW-1-05 | 220kV FEEDER - FINGLAS 220-NORTH WALL 220-1 | 5 | 5 | 5 | Scheduled | 11/09/2023 | 15/09/2023
TO-23-GRI-T141-02 | DISTRIBUTION TRANSFORMER - GRIFFINRATH 110-GRIFFINRATH 38-T141 | 12 | 10 | 10 | Reference | 11/09/2023 | 22/09/2023
TO-23-GRI,T-GCA-1-03 | 110kV FEEDER - GRIFFINRATH tee-GRANGE CASTLE 110-1 | 72 | 51 | 51 | Scheduled | 11/09/2023 | 21/11/2023
TO-23-GRI,T-GRI-1-02 | 110kV FEEDER - GRIFFINRATH tee-GRIFFINRATH 110-1 | 12 | 10 | 10 | Scheduled | 11/09/2023 | 22/09/2023
TO-23-GRI,T-MAY-1-03 | 110kV FEEDER - GRIFFINRATH tee-MAYNOOTH 110-1 | 12 | 10 | 10 | Scheduled | 11/09/2023 | 22/09/2023
TO-23-KUR-NAV-1-01 | 110kV FEEDER - KNOCKUMBER 110-NAVAN 110-1 | 1 | 1 | 1 | Scheduled | 11/09/2023 | 11/09/2023
TO-23-KUR-T3-01 | TSO CUSTOMER TRANSFORMER - KNOCKUMBER 110-KNOCKUMBER 10-T3 | 1 | 1 | 1 | Reference | 11/09/2023 | 11/09/2023
TO-23-KUR-T4-01 | TSO CUSTOMER TRANSFORMER - KNOCKUMBER 110-KNOCKUMBER 10-T4 | 1 | 1 | 1 | Reference | 11/09/2023 | 11/09/2023
TO-23-NW-PB-1-05 | 220kV FEEDER - NORTH WALL 220-POOLBEG 220-1 | 5 | 5 | 5 | Scheduled | 11/09/2023 | 15/09/2023
TO-23-NW-T2004/5-02 | GENERATOR TRANSFORMER - NORTH WALL 220-NORTH WALL G4/5-T2004/5 | 5 | 5 | 5 | Scheduled | 11/09/2023 | 15/09/2023
TO-23-TY-T2001/2-01 | GENERATOR TRANSFORMER - TYNAGH 220-TYNAGH G1/2-T2001/2 | 3 | 3 | 3 | Scheduled | 11/09/2023 | 13/09/2023
TO-23-WHI-CKB-T101-01 | TSO CUSTOMER TRANSFORMER - WHITEGATE 110-WHITEGATE 10-CKB-T101 | 5 | 5 | 5 | Scheduled | 11/09/2023 | 15/09/2023
TO-23-BNK-CBT-1-01 | 110kV FEEDER - BARNAKYLE 110-CASTLEBAGOT 110-1 | 2 | 2 | 2 | Scheduled | 12/09/2023 | 13/09/2023
TO-23-MTN-MUN-2-01 | 110kV FEEDER - MONETEEN 110-MUNGRET 110-2 | 4 | 4 | 4 | Scheduled | 12/09/2023 | 15/09/2023
TO-23-220 kV A1/A2 @ MP GIS-02 | BUSBAR SECTION - MONEYPOINT GIS 220-MONEYPOINT GIS 220-220A1-A2 | 3 | 3 | 3 | Scheduled | 12/09/2023 | 14/09/2023
TO-23-MUN-T102-01 | TSO CUSTOMER TRANSFORMER - MUNGRET 110-MUNGRET 10-T102 | 4 | 4 | 4 | Reference | 12/09/2023 | 15/09/2023
TO-23-OST-T4202-01 | TRANSFORMER - OLDSTREET 400-OLDSTREET 220-T4202 | 9 | 7 | 7 | Scheduled | 14/09/2023 | 22/09/2023
TO-23-OST-TY-1-04 | 220kV FEEDER - OLDSTREET 220-TYNAGH 220-1 | 9 | 7 | 7 | Scheduled | 14/09/2023 | 22/09/2023
TO-23-KLN-T2103-02 | TRANSFORMER - KILLONAN 220-KILLONAN 110-T2103 | 22 | 16 | 16 | Scheduled | 15/09/2023 | 06/10/2023
TO-23-FIN-NW-1-04 | 220kV FEEDER - FINGLAS 220-NORTH WALL 220-1 | 2 | 0 | 0 | Scheduled | 16/09/2023 | 17/09/2023
TO-23-NW-PB-1-02 | 220kV FEEDER - NORTH WALL 220-POOLBEG 220-1 | 2 | 0 | 0 | Scheduled | 16/09/2023 | 17/09/2023
TO-23-NW-T2004/5-03 | GENERATOR TRANSFORMER - NORTH WALL 220-NORTH WALL G4/5-T2004/5 | 2 | 0 | 0 | Scheduled | 16/09/2023 | 17/09/2023
TO-23-AUG-CFM-2-01 | 110kV FEEDER - AUGHINISH 110-CASTLEFARM 110-2 | 5 | 5 | 5 | Scheduled | 18/09/2023 | 22/09/2023
TO-23-CFM-T102-01 | TSO CUSTOMER TRANSFORMER - CASTLEFARM 110-CASTLEFARM 10-T102 | 5 | 5 | 5 | Reference | 18/09/2023 | 22/09/2023
TO-23-CRO-IA-1-02 | 110kV FEEDER - COOLROE 110-INNISCARRA 110-1 | 68 | 49 | 49 | Scheduled | 18/09/2023 | 24/11/2023
TO-23-DSN-220K1-2-01 | COUPLER/SECTIONALISING CB - DUNSTOWN 220-DUNSTOWN 220-220K1-2 | 12 | 10 | 10 | Scheduled | 18/09/2023 | 29/09/2023
TO-23-220 kV A1 @ GI GIS-02 | BUSBAR SECTION - GREAT ISLAND GIS 220-GREAT ISLAND GIS 220-220A1 | 5 | 5 | 5 | Scheduled | 18/09/2023 | 22/09/2023
TO-23-220 kV A2 @ GI GIS-02 | BUSBAR SECTION - GREAT ISLAND GIS 220-GREAT ISLAND GIS 220-220A2 | 5 | 5 | 5 | Scheduled | 18/09/2023 | 22/09/2023
TO-23-GI GIS-220SA1-2CB-01 | COUPLER/SECTIONALISING CB - GREAT ISLAND GIS 220-GREAT ISLAND GIS 220-220SA1-2CB | 5 | 5 |  | Scheduled | 18/09/2023 | 22/09/2023
TO-23-IKE-T141-03 | DISTRIBUTION TRANSFORMER - IKERRIN 110-IKERRIN 38-T141 | 2 | 2 |  | Reference | 18/09/2023 | 19/09/2023
TO-23-IKE,T-IKE-1-02 | 110kV FEEDER - IKERRIN tee-IKERRIN 110-1 | 2 | 2 |  | Scheduled | 18/09/2023 | 19/09/2023
TO-23-IKE,T-SH-1-05 | 110kV FEEDER - IKERRIN tee-SHANNONBRIDGE 110-1 | 2 | 2 |  | Scheduled | 18/09/2023 | 19/09/2023
TO-23-IKE,T-THU-1-10 | 110kV FEEDER - IKERRIN tee-THURLES 110-1 | 2 | 2 |  | Scheduled | 18/09/2023 | 19/09/2023
TO-23-110 kV A1 @ KLS-03 | BUSBAR SECTION - KELLIS 110-KELLIS 110-110A1 | 12 | 10 | 10 | Scheduled | 18/09/2023 | 29/09/2023
TO-23-110 kV A2 @ KLS-04 | BUSBAR SECTION - KELLIS 110-KELLIS 110-110A2 | 12 | 10 | 10 | Scheduled | 18/09/2023 | 29/09/2023
TO-23-110 kV B1 @ KLS-03 | BUSBAR SECTION - KELLIS 110-KELLIS 110-110B1 | 12 | 10 | 10 | Scheduled | 18/09/2023 | 29/09/2023
TO-23-110 kV B2 @ KLS-04 | BUSBAR SECTION - KELLIS 110-KELLIS 110-110B2 | 12 | 10 | 10 | Scheduled | 18/09/2023 | 29/09/2023
TO-23-KLS-110K1-2-02 | COUPLER/SECTIONALISING CB - KELLIS 110-KELLIS 110-110K1-2 | 12 | 10 | 10 | Scheduled | 18/09/2023 | 29/09/2023
TO-23-LOU-RRU-1-02 | 110kV FEEDER - LOUTH 110-RATRUSSAN 110-1 | 4 | 4 | 4 | Scheduled | 18/09/2023 | 21/09/2023
TO-23-PLA-110SA1-04 | SECTIONALISING DISCONNECT - PLATIN 110-PLATIN 110-110SA1 | 5 | 5 | 5 | Scheduled | 18/09/2023 | 22/09/2023
TO-23-PLA-110SA2-04 | SECTIONALISING DISCONNECT - PLATIN 110-PLATIN 110-110SA2 | 5 | 5 | 5 | Scheduled | 18/09/2023 | 22/09/2023
TO-23-PLA-T101/2/3/4-04 | TSO CUSTOMER TRANSFORMER - PLATIN 110-PLATIN 10-T101/2/3/4 | 5 | 5 | 5 | Scheduled | 18/09/2023 | 22/09/2023
TO-23-RRU-110SA1-03 | SECTIONALISING DISCONNECT - RATRUSSAN 110-RATRUSSAN 110-110SA1 | 4 | 4 | 4 | Scheduled | 18/09/2023 | 21/09/2023
TO-23-RRU-110SA2-03 | SECTIONALISING DISCONNECT - RATRUSSAN 110-RATRUSSAN 110-110SA2 | 4 | 4 | 4 | Scheduled | 18/09/2023 | 21/09/2023
TO-23-RRU-SKL-1-01 | 110kV FEEDER - RATRUSSAN 110-SHANKILL 110-1 | 4 | 4 | 4 | Scheduled | 18/09/2023 | 21/09/2023
TO-23-RRU-T121-03 | GENERATOR TRANSFORMER - RATRUSSAN 110-RATRUSSAN 20-T121 | 4 | 4 | 4 | Scheduled | 18/09/2023 | 21/09/2023
TO-23-RRU-T122-04 | GENERATOR TRANSFORMER - RATRUSSAN 110-RATRUSSAN 20-T122 | 4 | 4 | 4 | Scheduled | 18/09/2023 | 21/09/2023
TO-23-WHI-CKB-T102-01 | TSO CUSTOMER TRANSFORMER - WHITEGATE 110-WHITEGATE 10-CKB-T102 | 5 | 5 | 5 | Scheduled | 18/09/2023 | 22/09/2023
TO-23-110 kV A1/A2/A3/A4 @ CDU-02 | BUSBAR SECTION - CORDUFF 110-CORDUFF 110-110A1-A2-A3-A4 | 2 | 2 | 2 | Scheduled | 19/09/2023 | 20/09/2023
TO-23-CDU-110K1-2-02 | COUPLER/SECTIONALISING CB - CORDUFF 110-CORDUFF 110-110K1-2 | 2 | 2 | 2 | Scheduled | 19/09/2023 | 20/09/2023
TO-23-CDU-110K1-3-01 | COUPLER/SECTIONALISING CB - CORDUFF 110-CORDUFF 110-110K1-3 | 2 | 2 | 2 | Scheduled | 19/09/2023 | 20/09/2023
TO-23-CDU-110SA2-4-01 | SECTIONALISING DISCONNECT - CORDUFF 110-CORDUFF 110-110SA2-4 | 2 | 2 | 2 | Scheduled | 19/09/2023 | 20/09/2023
TO-23-CDU-SNU-1-03 | 110kV FEEDER - CORDUFF 110-SNUGBOROUGH 110-1 | 4 | 4 | 4 | Scheduled | 19/09/2023 | 22/09/2023
TO-23-MOY-110SA1-2CB-03 | COUPLER/SECTIONALISING CB - MOY 110-MOY 110-110SA1-2CB | 7 | 5 | 5 | Scheduled | 19/09/2023 | 25/09/2023
TO-23-MOY-CAP1-01 | CAPACITOR/SVC/REACTOR - MOY 110-MOY 110-CAP1 | 7 | 5 | 5 | Scheduled | 19/09/2023 | 25/09/2023
TO-23-MOY-T141-01 | DISTRIBUTION TRANSFORMER - MOY 110-MOY 38-T141 | 7 | 5 | 5 | Reference | 19/09/2023 | 25/09/2023
TO-23-MOY-TAW-1-03 | 110kV FEEDER - MOY 110-TAWNAGHMORE 110-1 | 7 | 5 | 5 | Scheduled | 19/09/2023 | 25/09/2023
TO-23-CHA-KLN-1-03 | 110kV FEEDER - CHARLEVILLE 110-KILLONAN 110-1 | 3 | 3 | 3 | Scheduled | 20/09/2023 | 22/09/2023
TO-23-110 kV B2 @ FLA-03 | BUSBAR SECTION - FLAGFORD 110-FLAGFORD 110-110B2 | 1 | 1 | 1 | Scheduled | 20/09/2023 | 20/09/2023
TO-23-FLA-T2102-03 | TRANSFORMER - FLAGFORD 220-FLAGFORD 110-T2102 | 1 | 1 | 1 | Scheduled | 20/09/2023 | 20/09/2023
TO-23-110 kV B1/B2/B3/B4 @ CDU-02 | BUSBAR SECTION - CORDUFF 110-CORDUFF 110-110B1-B2-B3-B4 | 2 | 2 | 2 | Scheduled | 21/09/2023 | 22/09/2023
TO-23-CDU-110K1-2-03 | COUPLER/SECTIONALISING CB - CORDUFF 110-CORDUFF 110-110K1-2 | 2 | 2 | 2 | Scheduled | 21/09/2023 | 22/09/2023
TO-23-CDU-110K1-3-02 | COUPLER/SECTIONALISING CB - CORDUFF 110-CORDUFF 110-110K1-3 | 2 | 2 | 2 | Scheduled | 21/09/2023 | 22/09/2023
TO-23-CDU-110SB2-4-01 | SECTIONALISING DISCONNECT - CORDUFF 110-CORDUFF 110-110SB2-4 | 2 | 2 | 2 | Scheduled | 21/09/2023 | 22/09/2023
TO-23-PB-R223-4-03 | CAPACITOR/SVC/REACTOR - POOLBEG 220-POOLBEG 220-R223-4 | 1 | 0 | 0 | Scheduled | 23/09/2023 | 23/09/2023
TO-23-110 kV A1 @ BVK-02 | BUSBAR SECTION - BALLYVOUSKILL 110-BALLYVOUSKILL 110-110A1 | 2 | 2 | 2 | Scheduled | 25/09/2023 | 26/09/2023
TO-23-110 kV B1 @ BVK-02 | BUSBAR SECTION - BALLYVOUSKILL 110-BALLYVOUSKILL 110-110B1 | 2 | 2 | 2 | Scheduled | 25/09/2023 | 26/09/2023
TO-23-BVK-110K1-03 | COUPLER/SECTIONALISING CB - BALLYVOUSKILL 110-BALLYVOUSKILL 110-110K1 | 2 | 2 | 2 | Scheduled | 25/09/2023 | 26/09/2023
TO-23-BVK-110SA1-2CB-02 | COUPLER/SECTIONALISING CB - BALLYVOUSKILL 110-BALLYVOUSKILL 110-110SA1-2CB | 2 | 2 | 2 | Scheduled | 25/09/2023 | 26/09/2023
TO-23-BVK-110SB1-2CB-02 | COUPLER/SECTIONALISING CB - BALLYVOUSKILL 110-BALLYVOUSKILL 110-110SB1-2CB | 2 | 2 | 2 | Scheduled | 25/09/2023 | 26/09/2023
TO-23-BVK-GRO-1-01 | 110kV FEEDER - BALLYVOUSKILL 110-GARROW 110-1 | 2 | 2 | 2 | Scheduled | 25/09/2023 | 26/09/2023
TO-23-CAH-KHL-1-01 | 110kV FEEDER - CAHIR 110-KILL HILL 110-1 | 3 | 3 | 3 | Scheduled | 25/09/2023 | 27/09/2023
TO-23-LET-PST-01 | TRANSFORMER - LETTERKENNY 110-STRABANE 110-PST | 54 | 39 | 39 | Scheduled | 25/09/2023 | 17/11/2023
TO-23-MP GIS-T4003-01 | GENERATOR TRANSFORMER - MONEYPOINT GIS 400-MONEYPOINT GIS G3-T4003 | 2 | 2 | 2 | Scheduled | 25/09/2023 | 26/09/2023
TO-23-NEW-PLS-1-04 | 110kV FEEDER - NEWBRIDGE 110-PORTLAOISE 110-1 | 1 | 1 | 1 | Scheduled | 25/09/2023 | 25/09/2023
TO-23-ARV-GWE-1-04 | 110kV FEEDER - ARVA 110-GORTAWEE 110-1 | 3 | 3 | 3 | Scheduled | 26/09/2023 | 28/09/2023
TO-23-ATY-CLW-1-04 | 110kV FEEDER - ATHY 110-CARLOW 110-1 | 11 | 9 | 9 | Scheduled | 26/09/2023 | 06/10/2023
TO-23-KIN-MUL-1-04 | 110kV FEEDER - KINNEGAD 110-MULLINGAR 110-1 | 1 | 1 | 1 | Scheduled | 26/09/2023 | 26/09/2023
TO-23-LA-MUL-1-02 | 110kV FEEDER - LANESBORO 110-MULLINGAR 110-1 | 1 | 1 | 1 | Scheduled | 26/09/2023 | 26/09/2023
TO-23-MUL-110SA1-2CB-02 | COUPLER/SECTIONALISING CB - MULLINGAR 110-MULLINGAR 110-110SA1-2CB | 1 | 1 | 1 | Scheduled | 26/09/2023 | 26/09/2023
TO-23-MUL-CAP1-03 | CAPACITOR/SVC/REACTOR - MULLINGAR 110-MULLINGAR 110-CAP1 | 1 | 1 | 1 | Scheduled | 26/09/2023 | 26/09/2023
TO-23-MUL-T101-01 | DISTRIBUTION TRANSFORMER - MULLINGAR 110-MULLINGAR 10-T101 | 1 | 1 | 1 | Reference | 26/09/2023 | 26/09/2023
TO-23-MUL-T141-01 | DISTRIBUTION TRANSFORMER - MULLINGAR 110-MULLINGAR 38-T141 | 1 | 1 | 1 | Reference | 26/09/2023 | 26/09/2023
TO-23-220 kV A1 @ CLE-02 | BUSBAR SECTION - CLONEE 220-CLONEE 220-220A1 | 2 | 2 | 2 | Scheduled | 27/09/2023 | 28/09/2023
TO-23-220 kV A2 @ CLE-02 | BUSBAR SECTION - CLONEE 220-CLONEE 220-220A2 | 2 | 2 | 2 | Scheduled | 27/09/2023 | 28/09/2023
TO-23-220 kV B1 @ CLE-01 | BUSBAR SECTION - CLONEE 220-CLONEE 220-220B1 | 2 | 2 | 2 | Scheduled | 27/09/2023 | 28/09/2023
TO-23-220 kV B2 @ CLE-01 | BUSBAR SECTION - CLONEE 220-CLONEE 220-220B2 | 2 | 2 | 2 | Scheduled | 27/09/2023 | 28/09/2023
TO-23-CLE-220K1-02 | COUPLER/SECTIONALISING CB - CLONEE 220-CLONEE 220-220K1 | 2 | 2 | 2 | Scheduled | 27/09/2023 | 28/09/2023
TO-23-CLE-220K2-03 | COUPLER/SECTIONALISING CB - CLONEE 220-CLONEE 220-220K2 | 2 | 2 | 2 | Scheduled | 27/09/2023 | 28/09/2023
TO-23-CLE-220SA1-2CB-02 | COUPLER/SECTIONALISING CB - CLONEE 220-CLONEE 220-220SA1-2CB | 2 | 2 | 2 | Scheduled | 27/09/2023 | 28/09/2023
TO-23-CLE-220SB1-2CB-01 | COUPLER/SECTIONALISING CB - CLONEE 220-CLONEE 220-220SB1-2CB | 2 | 2 | 2 | Scheduled | 27/09/2023 | 28/09/2023
TO-23-CLE-WOO-1-04 | 220kV FEEDER - CLONEE 220-WOODLAND 220-1 | 1 | 1 | 1 | Scheduled | 27/09/2023 | 27/09/2023
TO-23-CAH-TIP-1-01 | 110kV FEEDER - CAHIR 110-TIPPERARY 110-1 | 2 | 2 | 2 | Scheduled | 28/09/2023 | 29/09/2023
TO-23-KLS-KKY-1-05 | 110kV FEEDER - KELLIS 110-KILKENNY 110-1 | 2 | 2 | 2 | Scheduled | 28/09/2023 | 29/09/2023
TO-23-KKY-110SA1-2CB-03 | COUPLER/SECTIONALISING CB - KILKENNY 110-KILKENNY 110-110SA1-2CB | 2 | 2 | 2 | Scheduled | 28/09/2023 | 29/09/2023
TO-23-KKY-T141-04 | DISTRIBUTION TRANSFORMER - KILKENNY 110-KILKENNY 38-T141 | 2 | 2 | 2 | Reference | 28/09/2023 | 29/09/2023
TO-23-ATH-T142-03 | DISTRIBUTION TRANSFORMER - ATHLONE 110-ATHLONE 38-T142 | 2 | 2 | 2 | Reference | 02/10/2023 | 03/10/2023
TO-23-AUG-CFM-1-03 | 110kV FEEDER - AUGHINISH 110-CASTLEFARM 110-1 | 5 | 5 | 5 | Scheduled | 02/10/2023 | 06/10/2023
TO-23-220 kV A1 @ BVK-01 | BUSBAR SECTION - BALLYVOUSKILL 220-BALLYVOUSKILL 220-220A1 | 11 | 9 | 9 | Scheduled | 02/10/2023 | 12/10/2023
TO-23-220 kV B1 @ BVK-01 | BUSBAR SECTION - BALLYVOUSKILL 220-BALLYVOUSKILL 220-220B1 | 11 | 9 | 9 | Scheduled | 02/10/2023 | 12/10/2023
TO-23-BVK-CLA-1-01 | 220kV FEEDER - BALLYVOUSKILL 220-CLASHAVOON 220-1 | 11 | 9 |  | Scheduled | 02/10/2023 | 12/10/2023
TO-23-BK-MOY-1-03 | 110kV FEEDER - BELLACORICK 110-MOY 110-1 | 40 | 29 | 29 | Scheduled | 02/10/2023 | 10/11/2023
TO-23-CFM-T101-02 | TSO CUSTOMER TRANSFORMER - CASTLEFARM 110-CASTLEFARM 10-T101 | 5 | 5 | 5 | Reference | 02/10/2023 | 06/10/2023
TO-23-CLH-110SA1-02 | SECTIONALISING DISCONNECT - CLAHANE 110-CLAHANE 110-110SA1 | 5 | 5 | 5 | Scheduled | 02/10/2023 | 06/10/2023
TO-23-CLH-110SA2-02 | SECTIONALISING DISCONNECT - CLAHANE 110-CLAHANE 110-110SA2 | 5 | 5 | 5 | Scheduled | 02/10/2023 | 06/10/2023
TO-23-CLH-TRL-1-02 | 110kV FEEDER - CLAHANE 110-TRALEE 110-1 | 5 | 5 | 5 | Scheduled | 02/10/2023 | 06/10/2023
TO-23-CDU-WOO-1-03 | 220kV FEEDER - CORDUFF 220-WOODLAND 220-1 | 2 | 2 | 2 | Scheduled | 02/10/2023 | 03/10/2023
TO-23-110 kV A1 @ FIN GIS-03 | BUSBAR SECTION - FINGLAS GIS 110-FINGLAS GIS 110-110A1 | 2 | 2 | 2 | Scheduled | 02/10/2023 | 03/10/2023
TO-23-110 kV B1 @ FIN GIS-04 | BUSBAR SECTION - FINGLAS GIS 110-FINGLAS GIS 110-110B1 | 2 | 2 | 2 | Scheduled | 02/10/2023 | 03/10/2023
TO-23-FIN GIS-110K1-01 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110K1 | 2 | 2 | 2 | Scheduled | 02/10/2023 | 03/10/2023
TO-23-FIN GIS-110SA1-2CB-07 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110SA1-2CB | 2 | 2 | 2 | Scheduled | 02/10/2023 | 03/10/2023
TO-23-FIN GIS-110SA1-3CB-04 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110SA1-3CB | 2 | 2 | 2 | Scheduled | 02/10/2023 | 03/10/2023
TO-23-FIN GIS-110SB1-2CB-07 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110SB1-2CB | 2 | 2 | 2 | Scheduled | 02/10/2023 | 03/10/2023
TO-23-FIN GIS-110SB1-3CB-05 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110SB1-3CB | 2 | 2 | 2 | Scheduled | 02/10/2023 | 03/10/2023
TO-23-COL-CDU-1-02 | 110kV FEEDER - COLLEGE PARK 110-CORDUFF 110-1 | 3 | 3 | 3 | Scheduled | 03/10/2023 | 05/10/2023
TO-23-DRY-LOU-1-08 | 110kV FEEDER - DRYBRIDGE 110-LOUTH 110-1 | 1 | 1 | 1 | Scheduled | 04/10/2023 | 04/10/2023
TO-23-LOU-T2104-07 | TRANSFORMER - LOUTH 220-LOUTH 110-T2104 | 1 | 1 | 1 | Scheduled | 05/10/2023 | 05/10/2023
TO-23-AD-KRA-1-05 | 220kV FEEDER - AGHADA 220-KNOCKRAHA 220-1 | 8 | 6 |  | Scheduled | 06/10/2023 | 13/10/2023
TO-23-CUS-T103/5-01 | GENERATOR TRANSFORMER - CUSHALING 110-CUSHALING G3/5-T103/5 | 1 | 1 | 1 | Scheduled | 06/10/2023 | 06/10/2023
TO-23-MP GIS-T2102-01 | TRANSFORMER - MONEYPOINT GIS 220-MONEYPOINT GIS 110-T2102 | 15 | 11 | 11 | Scheduled | 06/10/2023 | 20/10/2023
TO-23-DSN-KLS-1-07 | 220kV FEEDER - DUNSTOWN 220-KELLIS 220-1 | 1 | 0 | 0 | Proposed | 07/10/2023 | 07/10/2023
TO-23-KLS-220K1-2-05 | COUPLER/SECTIONALISING CB - KELLIS 220-KELLIS 220-220K1-2 | 1 | 0 | 0 | Proposed | 07/10/2023 | 07/10/2023
TO-23-KLS-T2101-06 | TRANSFORMER - KELLIS 220-KELLIS 110-T2101 | 1 | 0 | 0 | Proposed | 07/10/2023 | 07/10/2023
TO-23-LOU-T2104-08 | TRANSFORMER - LOUTH 220-LOUTH 110-T2104 | 1 | 0 | 0 | Scheduled | 07/10/2023 | 07/10/2023
TO-23-ATY-T101-01 | DISTRIBUTION TRANSFORMER - ATHY 110-ATHY 10-T101 | 4 | 4 | 4 | Reference | 09/10/2023 | 12/10/2023
TO-23-BLK-T142-03 | DISTRIBUTION TRANSFORMER - BLAKE 110-BLAKE 38-T142 | 19 | 15 | 15 | Reference | 09/10/2023 | 27/10/2023
TO-23-BLK,T-BLK-1-03 | 110kV FEEDER - BLAKE tee-BLAKE 110-1 | 19 | 15 | 15 | Scheduled | 09/10/2023 | 27/10/2023
TO-23-BLK,T-MAY-1-02 | 110kV FEEDER - BLAKE tee-MAYNOOTH 110-1 | 19 | 15 | 15 | Scheduled | 09/10/2023 | 27/10/2023
TO-23-BLK,T-NEW-1-01 | 110kV FEEDER - BLAKE tee-NEWBRIDGE 110-1 | 19 | 15 | 15 | Scheduled | 09/10/2023 | 27/10/2023
TO-23-BGH-T121-01 | GENERATOR TRANSFORMER - BOGGERAGH 110-BOGGERAGH 20-T121 | 1 | 1 | 1 | Scheduled | 09/10/2023 | 09/10/2023
TO-23-110 kV A2 @ CSH-11 | BUSBAR SECTION - CASHLA 110-CASHLA 110-110A2 | 5 | 5 | 5 | Scheduled | 09/10/2023 | 13/10/2023
TO-23-110 kV B2 @ CSH-12 | BUSBAR SECTION - CASHLA 110-CASHLA 110-110B2 | 5 | 5 | 5 | Scheduled | 09/10/2023 | 13/10/2023
TO-23-CSH-ENN-1-02 | 110kV FEEDER - CASHLA 110-ENNIS 110-1 | 5 | 5 | 5 | Scheduled | 09/10/2023 | 13/10/2023
TO-23-110 kV A2 @ CDU-03 | BUSBAR SECTION - CORDUFF 110-CORDUFF 110-110A2 | 12 | 10 | 10 | Scheduled | 09/10/2023 | 20/10/2023
TO-23-110 kV A4 @ CDU-05 | BUSBAR SECTION - CORDUFF 110-CORDUFF 110-110A4 | 12 | 10 | 10 | Scheduled | 09/10/2023 | 20/10/2023
TO-23-110 kV B2 @ CDU-02 | BUSBAR SECTION - CORDUFF 110-CORDUFF 110-110B2 | 12 | 10 | 10 | Scheduled | 09/10/2023 | 20/10/2023
TO-23-110 kV B4 @ CDU-05 | BUSBAR SECTION - CORDUFF 110-CORDUFF 110-110B4 | 12 | 10 | 10 | Scheduled | 09/10/2023 | 20/10/2023
TO-23-110 kV A2 @ KBY-04 | BUSBAR SECTION - KILBARRY 110-KILBARRY 110-110A2 | 14 | 10 | 10 | Scheduled | 09/10/2023 | 22/10/2023
TO-23-110 kV B2 @ KBY-05 | BUSBAR SECTION - KILBARRY 110-KILBARRY 110-110B2 | 14 | 10 | 10 | Scheduled | 09/10/2023 | 22/10/2023
TO-23-110 kV A2 @ KRA-02 | BUSBAR SECTION - KNOCKRAHA 110-KNOCKRAHA 110-110A2 | 12 | 10 | 10 | Scheduled | 09/10/2023 | 20/10/2023
TO-23-110 kV B2 @ KRA-04 | BUSBAR SECTION - KNOCKRAHA 110-KNOCKRAHA 110-110B2 | 12 | 10 | 10 | Scheduled | 09/10/2023 | 20/10/2023
TO-23-110 kV A1 @ MR-02 | BUSBAR SECTION - MARINA 110-MARINA 110-110A1 | 14 | 10 | 10 | Scheduled | 09/10/2023 | 22/10/2023
TO-23-110 kV B1 @ MR-02 | BUSBAR SECTION - MARINA 110-MARINA 110-110B1 | 14 | 10 | 10 | Scheduled | 09/10/2023 | 22/10/2023
TO-23-AD-LPT-1-01 | 220kV FEEDER - AGHADA 220-LONG POINT 220-1 | 7 | 5 | 5 | Scheduled | 10/10/2023 | 16/10/2023
TO-23-BRT-220K2-01 | COUPLER/SECTIONALISING CB - BRACETOWN 220-BRACETOWN 220-220K2 | 1 | 1 | 1 | Scheduled | 10/10/2023 | 10/10/2023
TO-23-LPT-T2002-01 | GENERATOR TRANSFORMER - LONG POINT 220-LONG POINT G1-T2002 | 7 | 5 |  | Scheduled | 10/10/2023 | 16/10/2023
TO-23-ROP-T131-01 | GENERATOR TRANSFORMER - ROSSPILE 110-ROSSPILE 33-T131 | 2 | 2 | 2 | Scheduled | 10/10/2023 | 11/10/2023
TO-23-RAF-TBG-1-03 | 110kV FEEDER - RAFFEEN 110-TRABEG 110-1 | 2 | 0 | 0 | Scheduled | 14/10/2023 | 15/10/2023
TO-23-CKM-PB-1-05 | 220kV FEEDER - CARRICKMINES 220-POOLBEG 220-1 | 4 | 3 | 3 | Scheduled | 15/10/2023 | 18/10/2023
TO-23-CKM-PST2201-06 | TRANSFORMER - CARRICKMINES 220-CARRICKMINES 220-PST2201 | 4 | 3 |  | Scheduled | 15/10/2023 | 18/10/2023
TO-23-BAG-T103-01 | TSO CUSTOMER TRANSFORMER - BARNAGEERAGH 110-BARNAGEERAGH 11-T103 | 2 | 2 | 2 | Scheduled | 16/10/2023 | 17/10/2023
TO-23-CTN-KLN-1-01 | 110kV FEEDER - CAUTEEN 110-KILLONAN 110-1 | 5 | 5 | 5 | Scheduled | 16/10/2023 | 20/10/2023
TO-23-CHA-MAL-1-03 | 110kV FEEDER - CHARLEVILLE 110-MALLOW 110-1 | 5 | 5 | 5 | Scheduled | 16/10/2023 | 20/10/2023
TO-23-CDU-MCE-1-02 | 110kV FEEDER - CORDUFF 110-MACETOWN 110-1 | 2 | 2 | 2 | Scheduled | 16/10/2023 | 17/10/2023
TO-23-GOR-110K1-2-02 | COUPLER/SECTIONALISING CB - GORMAN 110-GORMAN 110-110K1-2 | 26 | 19 | 19 | Scheduled | 16/10/2023 | 10/11/2023
TO-23-KLS-T2101-03 | TRANSFORMER - KELLIS 220-KELLIS 110-T2101 | 33 | 24 | 24 | Scheduled | 16/10/2023 | 17/11/2023
TO-23-MAY-SH-1-01 | 220kV FEEDER - MAYNOOTH 220-SHANNONBRIDGE 220-1 | 53 | 38 | 38 | Scheduled | 16/10/2023 | 07/12/2023
TO-23-220 kV A1 @ TB-01 | BUSBAR SECTION - TARBERT 220-TARBERT 220-220A1 | 2 | 2 | 2 | Scheduled | 16/10/2023 | 17/10/2023
TO-23-110 kV A5 @ FIN GIS-02 | BUSBAR SECTION - FINGLAS GIS 110-FINGLAS GIS 110-110A5 | 3 | 3 | 3 | Scheduled | 17/10/2023 | 19/10/2023
TO-23-110 kV B5 @ FIN GIS-02 | BUSBAR SECTION - FINGLAS GIS 110-FINGLAS GIS 110-110B5 | 3 | 3 | 3 | Scheduled | 17/10/2023 | 19/10/2023
TO-23-FIN GIS-110K5-01 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110K5 | 3 | 3 | 3 | Scheduled | 17/10/2023 | 19/10/2023
TO-23-FIN GIS-110SA3-5CB-04 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110SA3-5CB | 3 | 3 | 3 | Scheduled | 17/10/2023 | 19/10/2023
TO-23-FIN GIS-110SB3-5CB-04 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110SB3-5CB | 3 | 3 | 3 | Scheduled | 17/10/2023 | 19/10/2023
TO-23-CDU-220K1-3-03 | COUPLER/SECTIONALISING CB - CORDUFF 220-CORDUFF 220-220K1-3 | 1 | 1 | 1 | Scheduled | 18/10/2023 | 18/10/2023
TO-23-DSN-T4201-04 | TRANSFORMER - DUNSTOWN 400-DUNSTOWN 220-T4201 | 2 | 2 | 2 | Scheduled | 18/10/2023 | 19/10/2023
TO-23-MOY-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - MOY 110-MOY 110-110SA1-2CB | 7 | 5 | 5 | Scheduled | 19/10/2023 | 25/10/2023
TO-23-MOY-CAP2-01 | CAPACITOR/SVC/REACTOR - MOY 110-MOY 110-CAP2 | 7 | 5 | 5 | Scheduled | 19/10/2023 | 25/10/2023
TO-23-MOY-T142-01 | DISTRIBUTION TRANSFORMER - MOY 110-MOY 38-T142 | 7 | 5 | 5 | Reference | 19/10/2023 | 25/10/2023
TO-23-MOY-TAW-2-02 | 110kV FEEDER - MOY 110-TAWNAGHMORE 110-2 | 7 | 5 |  | Scheduled | 19/10/2023 | 25/10/2023
TO-23-220 kV A2 @ AD-05 | BUSBAR SECTION - AGHADA 220-AGHADA 220-220A2 | 7 | 5 | 5 | Scheduled | 20/10/2023 | 26/10/2023
TO-23-220 kV B2 @ AD-06 | BUSBAR SECTION - AGHADA 220-AGHADA 220-220B2 | 7 | 5 | 5 | Scheduled | 20/10/2023 | 26/10/2023
TO-23-AD-KRA-2-01 | 220kV FEEDER - AGHADA 220-KNOCKRAHA 220-2 | 7 | 5 | 5 | Scheduled | 20/10/2023 | 26/10/2023
TO-23-LLA-T133-01 | GENERATOR TRANSFORMER - LENALEA 110-LENALEA 33-T133 | 1 | 0 | 0 | Scheduled | 21/10/2023 | 21/10/2023
TO-23-110 kV A1 @ ARV-02 | BUSBAR SECTION - ARVA 110-ARVA 110-110A1 | 5 | 5 | 5 | Scheduled | 23/10/2023 | 27/10/2023
TO-23-110 kV B1 @ ARV-01 | BUSBAR SECTION - ARVA 110-ARVA 110-110B1 | 5 | 5 | 5 | Scheduled | 23/10/2023 | 27/10/2023
TO-23-ARV-SKL-1-02 | 110kV FEEDER - ARVA 110-SHANKILL 110-1 | 5 | 5 | 5 | Scheduled | 23/10/2023 | 27/10/2023
TO-23-CAH-DOO-1-04 | 110kV FEEDER - CAHIR 110-DOON 110-1 | 1 | 1 | 1 | Scheduled | 23/10/2023 | 23/10/2023
TO-23-CKM GIS-220K4-02 | COUPLER/SECTIONALISING CB - CARRICKMINES GIS 220-CARRICKMINES GIS 220-220K4 | 5 | 5 | 5 | Scheduled | 23/10/2023 | 27/10/2023
TO-23-CKM GIS-220SA2-4CB-05 | COUPLER/SECTIONALISING CB - CARRICKMINES GIS 220-CARRICKMINES GIS 220-22SA2-4CB | 5 | 5 | 5 | Scheduled | 23/10/2023 | 27/10/2023
TO-23-CKM GIS-220SB2-4CB-05 | COUPLER/SECTIONALISING CB - CARRICKMINES GIS 220-CARRICKMINES GIS 220-22SB2-4CB | 5 | 5 | 5 | Scheduled | 23/10/2023 | 27/10/2023
TO-23-DOO-110SA1-04 | SECTIONALISING DISCONNECT - DOON 110-DOON 110-110SA1 | 1 | 1 | 1 | Scheduled | 23/10/2023 | 23/10/2023
TO-23-DOO-110SA2-04 | SECTIONALISING DISCONNECT - DOON 110-DOON 110-110SA2 | 1 | 1 | 1 | Scheduled | 23/10/2023 | 23/10/2023
TO-23-DRU-CAP2-03 | CAPACITOR/SVC/REACTOR - DRUMLINE 110-DRUMLINE 110-CAP2 | 5 | 5 | 5 | Scheduled | 23/10/2023 | 27/10/2023
TO-23-DRY-110SA1-05 | SECTIONALISING DISCONNECT - DRYBRIDGE 110-DRYBRIDGE 110-110SA1 | 5 | 5 | 5 | Scheduled | 23/10/2023 | 27/10/2023
TO-23-DRY-110SA2-05 | SECTIONALISING DISCONNECT - DRYBRIDGE 110-DRYBRIDGE 110-110SA2 | 5 | 5 | 5 | Scheduled | 23/10/2023 | 27/10/2023
TO-23-DRY-LOU-1-06 | 110kV FEEDER - DRYBRIDGE 110-LOUTH 110-1 | 5 | 5 | 5 | Scheduled | 23/10/2023 | 27/10/2023
TO-23-DRY-T141-04 | DISTRIBUTION TRANSFORMER - DRYBRIDGE 110-DRYBRIDGE 38-T141 | 5 | 5 | 5 | Reference | 23/10/2023 | 27/10/2023
TO-23-KYT-T237-01 | TSO CUSTOMER TRANSFORMER - KELLYSTOWN 220-KELLYSTOWN 34.5-T237 | 26 | 19 | 19 | Scheduled | 23/10/2023 | 17/11/2023
TO-23-110 kV A2 @ KNY-03 | BUSBAR SECTION - KNOCKRANNY 110-KNOCKRANNY 110-110A2 | 5 | 5 | 5 | Scheduled | 23/10/2023 | 27/10/2023
TO-23-110 kV B2 @ KNY-03 | BUSBAR SECTION - KNOCKRANNY 110-KNOCKRANNY 110-110B2 | 5 | 5 | 5 | Scheduled | 23/10/2023 | 27/10/2023
TO-23-110 kV A1 @ LOU-04 | BUSBAR SECTION - LOUTH 110-LOUTH 110-110A1 | 4 | 4 | 4 | Scheduled | 23/10/2023 | 26/10/2023
TO-23-110 kV B1 @ LOU-04 | BUSBAR SECTION - LOUTH 110-LOUTH 110-110B1 | 4 | 4 | 4 | Scheduled | 23/10/2023 | 26/10/2023
TO-23-220 kV A1 @ LOU-01 | BUSBAR SECTION - LOUTH 220-LOUTH 220-220A1 | 33 | 24 | 24 | Scheduled | 23/10/2023 | 24/11/2023
TO-23-220 kV B1 @ LOU-02 | BUSBAR SECTION - LOUTH 220-LOUTH 220-220B1 | 33 | 24 | 24 | Scheduled | 23/10/2023 | 24/11/2023
TO-23-LOU-T2103-01 | TRANSFORMER - LOUTH 220-LOUTH 110-T2103 | 33 | 24 | 24 | Scheduled | 23/10/2023 | 24/11/2023
TO-23-MP GIS-110SA1-2CB-02 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 110-MONEYPOINT GIS 110-110SA1-2CB | 4 | 4 | 4 | Scheduled | 23/10/2023 | 26/10/2023
TO-23-MP GIS-ST101-03 | GENERATOR TRANSFORMER - MONEYPOINT GIS 110-MONEYPOINT GIS 10-ST101 | 4 | 4 | 4 | Scheduled | 23/10/2023 | 26/10/2023
TO-23-MP GIS-T121-03 | GENERATOR TRANSFORMER - MONEYPOINT GIS 110-MONEYPOINT GIS 20-T121 | 5 | 5 | 5 | Scheduled | 23/10/2023 | 27/10/2023
TO-23-MP GIS-T2102-02 | TRANSFORMER - MONEYPOINT GIS 220-MONEYPOINT GIS 110-T2102 | 4 | 4 | 4 | Scheduled | 23/10/2023 | 26/10/2023
TO-23-PLA-110SA1-05 | SECTIONALISING DISCONNECT - PLATIN 110-PLATIN 110-110SA1 | 5 | 5 | 5 | Scheduled | 23/10/2023 | 27/10/2023
TO-23-PLA-110SA2-05 | SECTIONALISING DISCONNECT - PLATIN 110-PLATIN 110-110SA2 | 5 | 5 | 5 | Scheduled | 23/10/2023 | 27/10/2023
TO-23-PLA-T101/2/3/4-05 | TSO CUSTOMER TRANSFORMER - PLATIN 110-PLATIN 10-T101/2/3/4 | 5 | 5 | 5 | Scheduled | 23/10/2023 | 27/10/2023
TO-23-220 kV A1 @ PB-04 | BUSBAR SECTION - POOLBEG 220-POOLBEG 220-220A1 | 5 | 5 |  | Scheduled | 23/10/2023 | 27/10/2023
TO-23-220 kV A2 @ PB-03 | BUSBAR SECTION - POOLBEG 220-POOLBEG 220-220A2 | 5 | 5 | 5 | Scheduled | 23/10/2023 | 27/10/2023
TO-23-220 kV B1 @ PB-04 | BUSBAR SECTION - POOLBEG 220-POOLBEG 220-220B1 | 5 | 5 |  | Scheduled | 23/10/2023 | 27/10/2023
TO-23-220 kV B2 @ PB-03 | BUSBAR SECTION - POOLBEG 220-POOLBEG 220-220B2 | 5 | 5 | 5 | Scheduled | 23/10/2023 | 27/10/2023
TO-23-PB-220SA1-2-06 | SECTIONALISING DISCONNECT - POOLBEG 220-POOLBEG 220-220SA1-2 | 5 | 5 | 5 | Scheduled | 23/10/2023 | 27/10/2023
TO-23-PB-220SB1-2-06 | SECTIONALISING DISCONNECT - POOLBEG 220-POOLBEG 220-220SB1-2 | 5 | 5 | 5 | Scheduled | 23/10/2023 | 27/10/2023
TO-23-TBK,T-MP GIS-1-03 | 110kV FEEDER - TULLABRACK tee-MONEYPOINT GIS 110-1 | 4 | 4 | 4 | Scheduled | 23/10/2023 | 26/10/2023
TO-23-BDA-T101-01 | TSO CUSTOMER TRANSFORMER - BARODA 110-BARODA 10-T101 | 3 | 3 | 3 | Scheduled | 24/10/2023 | 26/10/2023
TO-23-BK-110SA1-01 | SECTIONALISING DISCONNECT - BELLACORICK 110-BELLACORICK 110-110SA1 | 18 | 13 | 20 | Scheduled | 24/10/2023 | 10/11/2023
TO-23-BK-110SA2-01 | SECTIONALISING DISCONNECT - BELLACORICK 110-BELLACORICK 110-110SA2 | 18 | 13 | 13 | Scheduled | 24/10/2023 | 10/11/2023
TO-23-BK-T141-01 | DISTRIBUTION TRANSFORMER - BELLACORICK 110-BELLACORICK 38-T141 | 18 | 13 | 13 | Reference | 24/10/2023 | 10/11/2023
TO-23-BWR-T124-01 | GENERATOR TRANSFORMER - BALLYWATER 110-BALLYWATER 20-T124 | 1 | 1 | 1 | Reference (Proposed) | 25/10/2023 | 25/10/2023
TO-23-INC-PB-1-05 | 220kV FEEDER - INCHICORE 220-POOLBEG 220-1 | 2 | 0 | 0 | Scheduled | 28/10/2023 | 29/10/2023
TO-23-220 kV A1 @ PB-03 | BUSBAR SECTION - POOLBEG 220-POOLBEG 220-220A1 | 2 | 0 | 0 | Scheduled | 28/10/2023 | 29/10/2023
TO-23-220 kV A2 @ PB-04 | BUSBAR SECTION - POOLBEG 220-POOLBEG 220-220A2 | 2 | 0 | 0 | Scheduled | 28/10/2023 | 29/10/2023
TO-23-220 kV B1 @ PB-03 | BUSBAR SECTION - POOLBEG 220-POOLBEG 220-220B1 | 2 | 0 | 0 | Scheduled | 28/10/2023 | 29/10/2023
TO-23-220 kV B2 @ PB-04 | BUSBAR SECTION - POOLBEG 220-POOLBEG 220-220B2 | 2 | 0 | 0 | Scheduled | 28/10/2023 | 29/10/2023
TO-23-PB-220SA1-2-07 | SECTIONALISING DISCONNECT - POOLBEG 220-POOLBEG 220-220SA1-2 | 2 | 0 | 0 | Scheduled | 28/10/2023 | 29/10/2023
TO-23-PB-220SB1-2-07 | SECTIONALISING DISCONNECT - POOLBEG 220-POOLBEG 220-220SB1-2 | 2 | 0 | 0 | Scheduled | 28/10/2023 | 29/10/2023
TO-23-ARV-110K1-2-01 | COUPLER/SECTIONALISING CB - ARVA 110-ARVA 110-110K1-2 | 43 | 30 | 30 | Scheduled | 30/10/2023 | 11/12/2023
TO-23-AGL-110SA1-02 | SECTIONALISING DISCONNECT - AGANNYGAL 110-AGANNYGAL 110-110SA1 | 1 | 1 | 1 | Scheduled | 31/10/2023 | 31/10/2023
TO-23-AGL-110SA2-02 | SECTIONALISING DISCONNECT - AGANNYGAL 110-AGANNYGAL 110-110SA2 | 1 | 1 | 1 | Scheduled | 31/10/2023 | 31/10/2023
TO-23-AGL-DYN-1-04 | 110kV FEEDER - AGANNYGAL 110-DERRYBRIEN 110-1 | 1 | 1 | 1 | Scheduled | 31/10/2023 | 31/10/2023
TO-23-AGL-ENN-1-04 | 110kV FEEDER - AGANNYGAL 110-ENNIS 110-1 | 11 | 9 | 9 | Scheduled | 31/10/2023 | 10/11/2023
TO-23-AGL-SH-1-05 | 110kV FEEDER - AGANNYGAL 110-SHANNONBRIDGE 110-1 | 1 | 1 | 1 | Scheduled | 31/10/2023 | 31/10/2023
TO-23-DND-T124-01 | TSO CUSTOMER TRANSFORMER - DARNDALE 110-DARNDALE 20-T124 | 4 | 4 | 4 | Scheduled | 31/10/2023 | 03/11/2023
TO-23-DYN-T121-04 | GENERATOR TRANSFORMER - DERRYBRIEN 110-DERRYBRIEN 20-T121 | 2 | 2 | 2 | Reference | 31/10/2023 | 01/11/2023
TO-23-KPG-MP GIS-1-01 | 220kV FEEDER - KILPADDOGE 220-MONEYPOINT GIS 220-1 | 4 | 4 | 4 | Scheduled | 31/10/2023 | 03/11/2023
TO-23-220 kV A1 @ MP GIS-01 | BUSBAR SECTION - MONEYPOINT GIS 220-MONEYPOINT GIS 220-220A1 | 4 | 4 | 4 | Scheduled | 31/10/2023 | 03/11/2023
TO-23-MP GIS-220K1-01 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 220-MONEYPOINT GIS 220-220K1 | 4 | 4 | 4 | Scheduled | 31/10/2023 | 03/11/2023
TO-23-MP GIS-220SA1-2CB-02 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 220-MONEYPOINT GIS 220-220SA1-2CB | 4 | 4 | 4 | Scheduled | 31/10/2023 | 03/11/2023
TO-23-PB-R2001-02 | CAPACITOR/SVC/REACTOR - POOLBEG 220-POOLBEG 220-R2001 | 4 | 4 | 4 | Scheduled | 31/10/2023 | 03/11/2023
TO-23-UGL-T132-05 | GENERATOR TRANSFORMER - UGGOOL 110-UGGOOL 33-T132 | 3 | 3 | 3 | Proposed | 31/10/2023 | 02/11/2023
TO-23-INC-ISH-1-04 | 220kV FEEDER - INCHICORE 220-IRISHTOWN 220-1 | 29 | 21 |  | Scheduled | 01/11/2023 | 29/11/2023
TO-23-ISH-220K1-2-02 | COUPLER/SECTIONALISING CB - IRISHTOWN 220-IRISHTOWN 220-220K1-2 | 29 | 21 |  | Scheduled | 01/11/2023 | 29/11/2023
TO-23-ISH-SHL-1-04 | 220kV FEEDER - IRISHTOWN 220-SHELLYBANKS 220-1 | 29 | 21 |  | Scheduled | 01/11/2023 | 29/11/2023
TO-23-KLN-KRA-1-03 | 220kV FEEDER - KILLONAN 220-KNOCKRAHA 220-1 | 1 | 1 |  | Scheduled | 02/11/2023 | 02/11/2023
TO-23-BVK-T2101-02 | TRANSFORMER - BALLYVOUSKILL 220-BALLYVOUSKILL 110-T2101 | 15 | 11 | 11 | Scheduled | 03/11/2023 | 17/11/2023
TO-23-BYH-T2101-03 | TRANSFORMER - BALLYNAHULLA 220-BALLYNAHULLA 110-T2101 | 5 | 5 | 5 | Scheduled | 06/11/2023 | 10/11/2023
TO-23-BAN-BRI-2-02 | 110kV FEEDER - BANDON 110-BRINNY 110-2 | 2 | 2 | 2 | Scheduled | 06/11/2023 | 07/11/2023
TO-23-BRI-T102-02 | TSO CUSTOMER TRANSFORMER - BRINNY 110-BRINNY 10-T102 | 2 | 2 | 2 | Scheduled | 06/11/2023 | 07/11/2023
TO-23-220 kV B1 @ GI GIS-02 | BUSBAR SECTION - GREAT ISLAND GIS 220-GREAT ISLAND GIS 220-220B1 | 5 | 5 | 5 | Scheduled | 06/11/2023 | 10/11/2023
TO-23-220 kV B2 @ GI GIS-03 | BUSBAR SECTION - GREAT ISLAND GIS 220-GREAT ISLAND GIS 220-220B2 | 5 | 5 | 5 | Scheduled | 06/11/2023 | 10/11/2023
TO-23-GI GIS-220SB1-2CB-01 | COUPLER/SECTIONALISING CB - GREAT ISLAND GIS 220-GREAT ISLAND GIS 220-220SB1-2CB | 5 | 5 |  | Scheduled | 06/11/2023 | 10/11/2023
TO-23-110 kV A1 @ KLN-03 | BUSBAR SECTION - KILLONAN 110-KILLONAN 110-110A1 | 4 | 4 | 4 | Scheduled | 06/11/2023 | 09/11/2023
TO-23-110 kV A2 @ KLN-02 | BUSBAR SECTION - KILLONAN 110-KILLONAN 110-110A2 | 4 | 4 | 4 | Scheduled | 06/11/2023 | 09/11/2023
TO-23-110 kV B1 @ KLN-03 | BUSBAR SECTION - KILLONAN 110-KILLONAN 110-110B1 | 4 | 4 | 4 | Scheduled | 06/11/2023 | 09/11/2023
TO-23-110 kV B2 @ KLN-02 | BUSBAR SECTION - KILLONAN 110-KILLONAN 110-110B2 | 4 | 4 | 4 | Scheduled | 06/11/2023 | 09/11/2023
TO-23-KLN-110K1-2-01 | COUPLER/SECTIONALISING CB - KILLONAN 110-KILLONAN 110-110K1-2 | 8 | 6 | 6 | Scheduled | 06/11/2023 | 13/11/2023
TO-23-220 kV A4 @ KPG-05 | BUSBAR SECTION - KILPADDOGE 220-KILPADDOGE 220-220A4 | 5 | 5 | 5 | Scheduled | 06/11/2023 | 10/11/2023
TO-23-220 kV B4 @ KPG-05 | BUSBAR SECTION - KILPADDOGE 220-KILPADDOGE 220-220B4 | 5 | 5 | 5 | Scheduled | 06/11/2023 | 10/11/2023
TO-23-KPG-220K4-05 | COUPLER/SECTIONALISING CB - KILPADDOGE 220-KILPADDOGE 220-220K4 | 5 | 5 | 5 | Scheduled | 06/11/2023 | 10/11/2023
TO-23-KPG-220SA2-4CB-05 | COUPLER/SECTIONALISING CB - KILPADDOGE 220-KILPADDOGE 220-220SA2-4CB | 5 | 5 | 5 | Scheduled | 06/11/2023 | 10/11/2023
TO-23-KPG-220SB2-4CB-06 | COUPLER/SECTIONALISING CB - KILPADDOGE 220-KILPADDOGE 220-220SB2-4CB | 5 | 5 | 5 | Scheduled | 06/11/2023 | 10/11/2023
TO-23-KPG-MP GIS-2-01 | 220kV FEEDER - KILPADDOGE 220-MONEYPOINT GIS 220-2 | 5 | 5 |  | Scheduled | 06/11/2023 | 10/11/2023
TO-23-110 kV A1 @ CSH-04 | BUSBAR SECTION - CASHLA 110-CASHLA 110-110A1 | 5 | 4 | 4 | Scheduled | 07/11/2023 | 11/11/2023
TO-23-110 kV B1 @ CSH-04 | BUSBAR SECTION - CASHLA 110-CASHLA 110-110B1 | 5 | 4 | 4 | Scheduled | 07/11/2023 | 11/11/2023
TO-23-CSH-CAP1-01 | CAPACITOR/SVC/REACTOR - CASHLA 110-CASHLA 110-CAP1 | 5 | 4 | 4 | Scheduled | 07/11/2023 | 11/11/2023
TO-23-CRO-T122-02 | DISTRIBUTION TRANSFORMER - COOLROE 110-COOLROE 20-T122 | 2 | 2 | 2 | Reference | 07/11/2023 | 08/11/2023
TO-23-DFR-T122-03 | DISTRIBUTION TRANSFORMER - DUNFIRTH 110-DUNFIRTH 20-T122 | 2 | 2 | 2 | Reference | 07/11/2023 | 08/11/2023
TO-23-AGL-110SA1-03 | SECTIONALISING DISCONNECT - AGANNYGAL 110-AGANNYGAL 110-110SA1 | 1 | 1 | 1 | Scheduled | 10/11/2023 | 10/11/2023
TO-23-AGL-110SA2-03 | SECTIONALISING DISCONNECT - AGANNYGAL 110-AGANNYGAL 110-110SA2 | 1 | 1 | 1 | Scheduled | 10/11/2023 | 10/11/2023
TO-23-AGL-DYN-1-05 | 110kV FEEDER - AGANNYGAL 110-DERRYBRIEN 110-1 | 1 | 1 | 1 | Scheduled | 10/11/2023 | 10/11/2023
TO-23-AGL-SH-1-07 | 110kV FEEDER - AGANNYGAL 110-SHANNONBRIDGE 110-1 | 1 | 1 | 1 | Scheduled | 10/11/2023 | 10/11/2023
TO-23-CAH-DOO-1-01 | 110kV FEEDER - CAHIR 110-DOON 110-1 | 1 | 1 | 1 | Scheduled | 10/11/2023 | 10/11/2023
TO-23-DYN-T121-05 | GENERATOR TRANSFORMER - DERRYBRIEN 110-DERRYBRIEN 20-T121 | 1 | 1 | 1 | Reference | 10/11/2023 | 10/11/2023
TO-23-DOO-110SA1-03 | SECTIONALISING DISCONNECT - DOON 110-DOON 110-110SA1 | 1 | 1 | 1 | Scheduled | 10/11/2023 | 10/11/2023
TO-23-DOO-110SA2-03 | SECTIONALISING DISCONNECT - DOON 110-DOON 110-110SA2 | 1 | 1 | 1 | Scheduled | 10/11/2023 | 10/11/2023
TO-23-LIS-110SA1-06 | SECTIONALISING DISCONNECT - LISDRUM 110-LISDRUM 110-110SA1 | 4 | 2 | 2 | Scheduled | 10/11/2023 | 13/11/2023
TO-23-LIS-110SA2-06 | SECTIONALISING DISCONNECT - LISDRUM 110-LISDRUM 110-110SA2 | 4 | 2 | 2 | Scheduled | 10/11/2023 | 13/11/2023
TO-23-LIS-CAP2-05 | CAPACITOR/SVC/REACTOR - LISDRUM 110-LISDRUM 110-CAP2 | 4 | 2 | 2 | Scheduled | 10/11/2023 | 13/11/2023
TO-23-LIS-T142-04 | DISTRIBUTION TRANSFORMER - LISDRUM 110-LISDRUM 38-T142 | 4 | 2 |  | Reference | 10/11/2023 | 13/11/2023
TO-23-AA GIS-ENN-1-04 | 110kV FEEDER - ARDNACRUSHA GIS 110-ENNIS 110-1 | 5 | 5 | 5 | Scheduled | 13/11/2023 | 17/11/2023
TO-23-BWR-T124-02 | GENERATOR TRANSFORMER - BALLYWATER 110-BALLYWATER 20-T124 | 1 | 1 |  | Reference | 13/11/2023 | 13/11/2023
TO-23-BAN-BRI-1-02 | 110kV FEEDER - BANDON 110-BRINNY 110-1 | 5 | 5 | 5 | Scheduled | 13/11/2023 | 17/11/2023
TO-23-BDA-MON-1-02 | 110kV FEEDER - BARODA 110-MONREAD 110-1 | 10 | 8 | 8 | Scheduled | 13/11/2023 | 22/11/2023
TO-23-BK-CBR-1-01 | 110kV FEEDER - BELLACORICK 110-CASTLEBAR 110-1 | 19 | 15 | 15 | Scheduled | 13/11/2023 | 01/12/2023
TO-23-BRI-T101-02 | TSO CUSTOMER TRANSFORMER - BRINNY 110-BRINNY 10-T101 | 5 | 5 |  | Scheduled | 13/11/2023 | 17/11/2023
TO-23-BUT-110SA1-01 | SECTIONALISING DISCONNECT - BUTLERSTOWN 110-BUTLERSTOWN 110-110SA1 | 1 | 1 | 1 | Scheduled | 13/11/2023 | 13/11/2023
TO-23-BUT-110SA2-01 | SECTIONALISING DISCONNECT - BUTLERSTOWN 110-BUTLERSTOWN 110-110SA2 | 1 | 1 | 1 | Scheduled | 13/11/2023 | 13/11/2023
TO-23-220 kV B1 @ CKM GIS-03 | BUSBAR SECTION - CARRICKMINES GIS 220-CARRICKMINES GIS 220-220B1 | 12 | 10 | 10 | Scheduled | 13/11/2023 | 24/11/2023
TO-23-220 kV B2 @ CKM GIS-04 | BUSBAR SECTION - CARRICKMINES GIS 220-CARRICKMINES GIS 220-220B2 | 12 | 10 | 10 | Scheduled | 13/11/2023 | 24/11/2023
TO-23-CKM GIS-220SB1-2CB-02 | COUPLER/SECTIONALISING CB - CARRICKMINES GIS 220-CARRICKMINES GIS 220-22SB1-2CB | 12 | 10 | 10 | Scheduled | 13/11/2023 | 24/11/2023
TO-23-SK-T103-03 | GENERATOR TRANSFORMER - SEALROCK 110-SEALROCK G3-T103 | 2 | 2 | 2 | Scheduled | 13/11/2023 | 14/11/2023
TO-23-110 kV A2 @ BYH-02 | BUSBAR SECTION - BALLYNAHULLA 110-BALLYNAHULLA 110-110A2 | 2 | 2 | 2 | Scheduled | 14/11/2023 | 15/11/2023
TO-23-110 kV B2 @ BYH-02 | BUSBAR SECTION - BALLYNAHULLA 110-BALLYNAHULLA 110-110B2 | 2 | 2 | 2 | Scheduled | 14/11/2023 | 15/11/2023
TO-23-BYH-110K2-03 | COUPLER/SECTIONALISING CB - BALLYNAHULLA 110-BALLYNAHULLA 110-110K2 | 2 | 2 | 2 | Scheduled | 14/11/2023 | 15/11/2023
TO-23-BYH-110SA1-2CB-02 | COUPLER/SECTIONALISING CB - BALLYNAHULLA 110-BALLYNAHULLA 110-110SA1-2CB | 2 | 2 | 2 | Scheduled | 14/11/2023 | 15/11/2023
TO-23-BYH-110SB1-2CB-02 | COUPLER/SECTIONALISING CB - BALLYNAHULLA 110-BALLYNAHULLA 110-110SB1-2CB | 2 | 2 | 2 | Scheduled | 14/11/2023 | 15/11/2023
TO-23-BYH-T2102-01 | TRANSFORMER - BALLYNAHULLA 220-BALLYNAHULLA 110-T2102 | 2 | 2 | 2 | Scheduled | 14/11/2023 | 15/11/2023
TO-23-110 kV A1 @ GAL GIS-04 | BUSBAR SECTION - GALWAY GIS 110-GALWAY GIS 110-110A1 | 2 | 2 | 2 | Scheduled | 16/11/2023 | 17/11/2023
TO-23-110 kV A3 @ GAL GIS-01 | BUSBAR SECTION - GALWAY GIS 110-GALWAY GIS 110-110A3 | 2 | 2 |  | Scheduled | 16/11/2023 | 17/11/2023
TO-23-110 kV B1 @ GAL GIS-04 | BUSBAR SECTION - GALWAY GIS 110-GALWAY GIS 110-110B1 | 2 | 2 | 2 | Scheduled | 16/11/2023 | 17/11/2023
TO-23-110 kV B3 @ GAL GIS-01 | BUSBAR SECTION - GALWAY GIS 110-GALWAY GIS 110-110B3 | 2 | 2 |  | Scheduled | 16/11/2023 | 17/11/2023
TO-23-GAL GIS-110K3-01 | COUPLER/SECTIONALISING CB - GALWAY GIS 110-GALWAY GIS 110-110K3 | 2 | 2 |  | Scheduled | 16/11/2023 | 17/11/2023
TO-23-GAL GIS-110SA1-2CB-07 | COUPLER/SECTIONALISING CB - GALWAY GIS 110-GALWAY GIS 110-110SA1-2CB | 2 | 2 | 2 | Scheduled | 16/11/2023 | 17/11/2023
TO-23-GAL GIS-110SA1-3CB-03 | COUPLER/SECTIONALISING CB - GALWAY GIS 110-GALWAY GIS 110-110SA1-3CB | 2 | 2 |  | Scheduled | 16/11/2023 | 17/11/2023
TO-23-GAL GIS-110SB1-2CB-08 | COUPLER/SECTIONALISING CB - GALWAY GIS 110-GALWAY GIS 110-110SB1-2CB | 2 | 2 | 2 | Scheduled | 16/11/2023 | 17/11/2023
TO-23-GAL GIS-110SB1-3CB-03 | COUPLER/SECTIONALISING CB - GALWAY GIS 110-GALWAY GIS 110-110SB1-3CB | 2 | 2 | 2 | Scheduled | 16/11/2023 | 17/11/2023
TO-23-GAL GIS-SAL-1-05 | 110kV FEEDER - GALWAY GIS 110-SALTHILL 110-1 | 2 | 2 | 2 | Scheduled | 16/11/2023 | 17/11/2023
TO-23-IA-MAC-1-07 | 110kV FEEDER - INNISCARRA 110-MACROOM 110-1 | 2 | 2 | 2 | Scheduled | 16/11/2023 | 17/11/2023
TO-23-IA-T101-06 | GENERATOR TRANSFORMER - INNISCARRA 110-INNISCARRA G1-T101 | 2 | 2 | 2 | Scheduled | 16/11/2023 | 17/11/2023
TO-23-KIR-T131-04 | GENERATOR TRANSFORMER - KILCUMBER 110-KILCUMBER 33-T131 | 1 | 1 | 1 | Scheduled | 16/11/2023 | 16/11/2023
TO-23-110 kV A2 @ DND-01 | BUSBAR SECTION - DARNDALE 110-DARNDALE 110-110A2 | 7 | 5 | 5 | Scheduled | 17/11/2023 | 23/11/2023
TO-23-110 kV B2 @ DND-01 | BUSBAR SECTION - DARNDALE 110-DARNDALE 110-110B2 | 7 | 5 | 16 | Scheduled | 17/11/2023 | 23/11/2023
TO-23-DND-110K2-02 | COUPLER/SECTIONALISING CB - DARNDALE 110-DARNDALE 110-110K2 | 7 | 5 | 5 | Scheduled | 17/11/2023 | 23/11/2023
TO-23-DND-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - DARNDALE 110-DARNDALE 110-110SA1-2CB | 7 | 5 | 5 | Scheduled | 17/11/2023 | 23/11/2023
TO-23-DND-110SB1-2CB-02 | COUPLER/SECTIONALISING CB - DARNDALE 110-DARNDALE 110-110SB1-2CB | 7 | 5 | 16 | Scheduled | 17/11/2023 | 23/11/2023
TO-23-BVK-R2001-01 | CAPACITOR/SVC/REACTOR - BALLYVOUSKILL 220-BALLYVOUSKILL 220-R2001 | 3 | 3 | 3 | Scheduled | 20/11/2023 | 22/11/2023
TO-23-BAN-RAF-1-01 | 110kV FEEDER - BANDON 110-RAFFEEN 110-1 | 3 | 3 |  | Scheduled | 20/11/2023 | 22/11/2023
TO-23-BNK-T121-01 | TSO CUSTOMER TRANSFORMER - BARNAKYLE 110-BARNAKYLE 20-T121 | 2 | 2 | 2 | Scheduled | 20/11/2023 | 21/11/2023
TO-23-BIN-TIV-1-02 | 110kV FEEDER - BINBANE 110-TIEVEBRACK 110-1 | 2 | 2 | 2 | Scheduled | 20/11/2023 | 21/11/2023
TO-23-CKM GIS-220SB1-3CB-01 | COUPLER/SECTIONALISING CB - CARRICKMINES GIS 220-CARRICKMINES GIS 220-22SB1-3CB | 12 | 10 | 10 | Scheduled | 20/11/2023 | 01/12/2023
TO-23-CHA-MAL-1-01 | 110kV FEEDER - CHARLEVILLE 110-MALLOW 110-1 | 10 | 8 | 8 | Scheduled | 20/11/2023 | 29/11/2023
TO-23-KPG-TRL-1-04 | 110kV FEEDER - KILPADDOGE 110-TRALEE 110-1 | 4 | 4 | 4 | Scheduled | 20/11/2023 | 23/11/2023
TO-23-KNR-T2101-01 | TRANSFORMER - KNOCKANURE 220-KNOCKANURE 110-T2101 | 2 | 2 | 2 | Scheduled | 20/11/2023 | 21/11/2023
TO-23-LA-SLB-1-01 | 110kV FEEDER - LANESBORO 110-SLIABH BAWN 110-1 | 5 | 5 | 5 | Scheduled | 20/11/2023 | 24/11/2023
TO-23-220 kV A2 @ SH-02 | BUSBAR SECTION - SHANNONBRIDGE 220-SHANNONBRIDGE 220-220A2 | 33 | 25 | 25 | Scheduled | 20/11/2023 | 22/12/2023
TO-23-220 kV B2 @ SH-02 | BUSBAR SECTION - SHANNONBRIDGE 220-SHANNONBRIDGE 220-220B2 | 33 | 25 | 25 | Scheduled | 20/11/2023 | 22/12/2023
TO-23-BYH-T132-01 | CAPACITOR/SVC/REACTOR - BALLYNAHULLA 110-BALLYNAHULLA 110-T132 | 3 | 3 | 3 | Scheduled | 21/11/2023 | 23/11/2023
TO-23-SKL-T142-01 | DISTRIBUTION TRANSFORMER - SHANKILL 110-SHANKILL 38-T142 | 2 | 2 | 2 | Reference | 21/11/2023 | 22/11/2023
TO-23-SNU-110K1-01 | COUPLER/SECTIONALISING CB - SNUGBOROUGH 110-SNUGBOROUGH 110-110K1 | 1 | 1 | 1 | Scheduled | 21/11/2023 | 21/11/2023
TO-23-KTL-T141-01 | DISTRIBUTION TRANSFORMER - KILTEEL 110-KILTEEL 38-T141 | 2 | 2 | 2 | Reference | 22/11/2023 | 23/11/2023
TO-23-KNR-TRI-1-02 | 110kV FEEDER - KNOCKANURE 110-TRIEN 110-1 | 2 | 2 | 2 | Scheduled | 22/11/2023 | 23/11/2023
TO-23-AGL-SH-1-02 | 110kV FEEDER - AGANNYGAL 110-SHANNONBRIDGE 110-1 | 2 | 2 | 2 | Scheduled | 23/11/2023 | 24/11/2023
TO-23-CDY-SRA-1-01 | 110kV FEEDER - CORDERRY 110-SRANANAGH 110-1 | 1 | 1 |  | Scheduled | 23/11/2023 | 23/11/2023
TO-23-GI-WAT-1-04 | 110kV FEEDER - GREAT ISLAND 110-WATERFORD 110-1 | 2 | 0 | 0 | Scheduled | 25/11/2023 | 26/11/2023
TO-23-GI-WAT-2-02 | 110kV FEEDER - GREAT ISLAND 110-WATERFORD 110-2 | 5 | 3 |  | Scheduled | 25/11/2023 | 29/11/2023
TO-23-220 kV B1 @ CKM GIS-04 | BUSBAR SECTION - CARRICKMINES GIS 220-CARRICKMINES GIS 220-220B1 | 12 | 10 | 10 | Scheduled | 27/11/2023 | 08/12/2023
TO-23-220 kV B3 @ CKM GIS-03 | BUSBAR SECTION - CARRICKMINES GIS 220-CARRICKMINES GIS 220-220B3 | 12 | 10 | 10 | Scheduled | 27/11/2023 | 08/12/2023
TO-23-CUS-MLC-1-02 | 110kV FEEDER - CUSHALING 110-MOUNTLUCAS 110-1 | 1 | 1 | 1 | Proposed | 27/11/2023 | 27/11/2023
TO-23-GAR-GOR-1-01 | 110kV FEEDER - GARBALLAGH 110-GORMAN 110-1 | 3 | 3 | 3 | Scheduled | 27/11/2023 | 29/11/2023
TO-23-GRI-T141-03 | DISTRIBUTION TRANSFORMER - GRIFFINRATH 110-GRIFFINRATH 38-T141 | 5 | 5 | 5 | Reference (Proposed) | 27/11/2023 | 01/12/2023
TO-23-GRI,T-GCA-1-05 | 110kV FEEDER - GRIFFINRATH tee-GRANGE CASTLE 110-1 | 5 | 5 | 5 | Proposed | 27/11/2023 | 01/12/2023
TO-23-GRI,T-GRI-1-03 | 110kV FEEDER - GRIFFINRATH tee-GRIFFINRATH 110-1 | 5 | 5 | 5 | Proposed | 27/11/2023 | 01/12/2023
TO-23-GRI,T-MAY-1-01 | 110kV FEEDER - GRIFFINRATH tee-MAYNOOTH 110-1 | 5 | 5 | 5 | Proposed | 27/11/2023 | 01/12/2023
TO-23-110 kV A2 @ KBY-05 | BUSBAR SECTION - KILBARRY 110-KILBARRY 110-110A2 | 8 | 6 | 6 | Scheduled | 27/11/2023 | 04/12/2023
TO-23-110 kV B2 @ KBY-06 | BUSBAR SECTION - KILBARRY 110-KILBARRY 110-110B2 | 8 | 6 | 6 | Scheduled | 27/11/2023 | 04/12/2023
TO-23-KBY-KRA-2-01 | 110kV FEEDER - KILBARRY 110-KNOCKRAHA 110-2 | 8 | 6 | 6 | Scheduled | 27/11/2023 | 04/12/2023
TO-23-KPG-TB-2-01 | 220kV FEEDER - KILPADDOGE 220-TARBERT 220-2 | 3 | 3 | 3 | Proposed | 27/11/2023 | 29/11/2023
TO-23-KNR-T2102-01 | TRANSFORMER - KNOCKANURE 220-KNOCKANURE 110-T2102 | 4 | 4 | 4 | Proposed | 27/11/2023 | 30/11/2023
TO-23-110 kV A2 @ KRA-03 | BUSBAR SECTION - KNOCKRAHA 110-KNOCKRAHA 110-110A2 | 8 | 6 | 6 | Scheduled | 27/11/2023 | 04/12/2023
TO-23-110 kV B2 @ KRA-05 | BUSBAR SECTION - KNOCKRAHA 110-KNOCKRAHA 110-110B2 | 8 | 6 | 6 | Scheduled | 27/11/2023 | 04/12/2023
TO-23-110 kV A2 @ LOU-04 | BUSBAR SECTION - LOUTH 110-LOUTH 110-110A2 | 5 | 5 | 5 | Scheduled | 27/11/2023 | 01/12/2023
TO-23-110 kV B2 @ LOU-04 | BUSBAR SECTION - LOUTH 110-LOUTH 110-110B2 | 5 | 5 | 5 | Scheduled | 27/11/2023 | 01/12/2023
TO-23-LOU-T2104-03 | TRANSFORMER - LOUTH 220-LOUTH 110-T2104 | 5 | 5 | 5 | Proposed | 27/11/2023 | 01/12/2023
TO-23-110 kV A2 @ MAY-03 | BUSBAR SECTION - MAYNOOTH 110-MAYNOOTH 110-110A2 | 5 | 5 | 5 | Proposed | 27/11/2023 | 01/12/2023
TO-23-110 kV B2 @ MAY-03 | BUSBAR SECTION - MAYNOOTH 110-MAYNOOTH 110-110B2 | 5 | 5 | 5 | Proposed | 27/11/2023 | 01/12/2023
TO-23-110 kV A1 @ PLS-01 | BUSBAR SECTION - PORTLAOISE 110-PORTLAOISE 110-110A1 | 4 | 4 | 4 | Scheduled | 27/11/2023 | 30/11/2023
TO-23-110 kV A2 @ PLS-03 | BUSBAR SECTION - PORTLAOISE 110-PORTLAOISE 110-110A2 | 4 | 4 | 4 | Scheduled | 27/11/2023 | 30/11/2023
TO-23-110 kV B1 @ PLS-01 | BUSBAR SECTION - PORTLAOISE 110-PORTLAOISE 110-110B1 | 4 | 4 | 4 | Scheduled | 27/11/2023 | 30/11/2023
TO-23-110 kV B2 @ PLS-03 | BUSBAR SECTION - PORTLAOISE 110-PORTLAOISE 110-110B2 | 4 | 4 | 4 | Scheduled | 27/11/2023 | 30/11/2023
TO-23-PLS-110K1-2-01 | COUPLER/SECTIONALISING CB - PORTLAOISE 110-PORTLAOISE 110-110K1-2 | 4 | 4 | 4 | Scheduled | 27/11/2023 | 30/11/2023
TO-23-SH-T2102-02 | TRANSFORMER - SHANNONBRIDGE 220-SHANNONBRIDGE 110-T2102 | 5 | 5 | 5 | Scheduled | 27/11/2023 | 01/12/2023
TO-23-BYH-T132-02 | CAPACITOR/SVC/REACTOR - BALLYNAHULLA 110-BALLYNAHULLA 110-T132 | 3 | 3 | 3 | Scheduled | 28/11/2023 | 30/11/2023
TO-23-KBY-T101-02 | DISTRIBUTION TRANSFORMER - KILBARRY 110-KILBARRY 10-T101 | 2 | 2 | 2 | Reference | 28/11/2023 | 29/11/2023
TO-23-MLC-110SA1-01 | SECTIONALISING DISCONNECT - MOUNTLUCAS 110-MOUNTLUCAS 110-110SA1 | 16 | 12 | 12 | Proposed | 28/11/2023 | 13/12/2023
TO-23-MLC-110SA2-01 | SECTIONALISING DISCONNECT - MOUNTLUCAS 110-MOUNTLUCAS 110-110SA2 | 16 | 12 | 12 | Proposed | 28/11/2023 | 13/12/2023
TO-23-MLC-TSB-1-01 | 110kV FEEDER - MOUNTLUCAS 110-THORNSBERRY 110-1 | 5 | 4 | 4 | Proposed | 28/11/2023 | 02/12/2023
TO-23-MLC-TSB-1-03 | 110kV FEEDER - MOUNTLUCAS 110-THORNSBERRY 110-1 | 16 | 12 | 12 | Proposed | 28/11/2023 | 13/12/2023
TO-23-MLC-TSB-1-04 | 110kV FEEDER - MOUNTLUCAS 110-THORNSBERRY 110-1 | 16 | 12 | 12 | Proposed | 28/11/2023 | 13/12/2023
TO-23-TSB-110SA1-01 | SECTIONALISING DISCONNECT - THORNSBERRY 110-THORNSBERRY 110-110SA1 | 5 | 4 | 4 | Proposed | 28/11/2023 | 02/12/2023
TO-23-TSB-110SA2-01 | SECTIONALISING DISCONNECT - THORNSBERRY 110-THORNSBERRY 110-110SA2 | 5 | 4 | 4 | Proposed | 28/11/2023 | 02/12/2023
TO-23-TSB-T141-01 | DISTRIBUTION TRANSFORMER - THORNSBERRY 110-THORNSBERRY 38-T141 | 5 | 4 | 4 | Reference (Proposed) | 28/11/2023 | 02/12/2023
TO-23-BLC-DND-3-02 | 110kV FEEDER - BELCAMP 110-DARNDALE 110-3 | 2 | 2 | 2 | Scheduled | 30/11/2023 | 01/12/2023
TO-23-110 kV A2 @ DND-03 | BUSBAR SECTION - DARNDALE 110-DARNDALE 110-110A2 | 2 | 2 | 2 | Scheduled | 30/11/2023 | 01/12/2023
TO-23-110 kV B2 @ DND-03 | BUSBAR SECTION - DARNDALE 110-DARNDALE 110-110B2 | 2 | 2 | 2 | Scheduled | 30/11/2023 | 01/12/2023
TO-23-DND-110K2-04 | COUPLER/SECTIONALISING CB - DARNDALE 110-DARNDALE 110-110K2 | 2 | 2 | 2 | Scheduled | 30/11/2023 | 01/12/2023
TO-23-DND-110SA1-2CB-03 | COUPLER/SECTIONALISING CB - DARNDALE 110-DARNDALE 110-110SA1-2CB | 2 | 2 | 2 | Scheduled | 30/11/2023 | 01/12/2023
TO-23-DND-110SB1-2CB-04 | COUPLER/SECTIONALISING CB - DARNDALE 110-DARNDALE 110-110SB1-2CB | 2 | 2 | 2 | Scheduled | 30/11/2023 | 01/12/2023
TO-23-DSN-T4201-02 | TRANSFORMER - DUNSTOWN 400-DUNSTOWN 220-T4201 | 2 | 2 | 2 | Scheduled | 30/11/2023 | 01/12/2023
TO-23-220 kV A2 @ ISH-01 | BUSBAR SECTION - IRISHTOWN 220-IRISHTOWN 220-220A2 | 14 | 10 | 10 | Scheduled | 30/11/2023 | 13/12/2023
TO-23-220 kV B2 @ ISH-01 | BUSBAR SECTION - IRISHTOWN 220-IRISHTOWN 220-220B2 | 14 | 10 | 10 | Scheduled | 30/11/2023 | 13/12/2023
TO-23-KLN-NEN-1-02 | 110kV FEEDER - KILLONAN 110-NENAGH 110-1 | 2 | 2 | 2 | Reference (Proposed) | 30/11/2023 | 01/12/2023
TO-23-NEN-T141-02 | DISTRIBUTION TRANSFORMER - NENAGH 110-NENAGH 38-T141 | 2 | 2 | 2 | Reference (Proposed) | 30/11/2023 | 01/12/2023
TO-23-INC-T2101-01 | TRANSFORMER - INCHICORE 220-INCHICORE 110-T2101 | 15 | 11 | 11 | Reference | 01/12/2023 | 15/12/2023

## GEN_AreaSouthWest
Outage ID | Feeder ID | Calendar Day Duration | Working Day Duration | Work Days | Outage Status | Start | Finish
TO-23-AA GIS-T104-01 | GENERATOR TRANSFORMER - ARDNACRUSHA GIS 110-ARDNACRUSHA GIS G4-T104 | 400 | 281 | 281 | Scheduled | 23/03/2022 | 26/04/2023
TO-23-TB-T101-02 | GENERATOR TRANSFORMER - TARBERT 110-TARBERT G1-T101 | 365 | 249 | 249 | Scheduled | 01/01/2023 | 31/12/2023
TO-23-THU-CAP2-01 | CAPACITOR/SVC/REACTOR - THURLES 110-THURLES 110-CAP2 | 350 | 240 | 240 | Scheduled | 16/01/2023 | 31/12/2023
TO-23-BYH-BVK-1-03 | 220kV FEEDER - BALLYNAHULLA 220-BALLYVOUSKILL 220-1 | 12 | 10 | 10 | Scheduled | 27/02/2023 | 10/03/2023
TO-23-CTN-TIP-1-01 | 110kV FEEDER - CAUTEEN 110-TIPPERARY 110-1 | 68 | 46 | 46 | Scheduled | 27/02/2023 | 05/05/2023
TO-23-110 kV A2 @ AA GIS-01 | BUSBAR SECTION - ARDNACRUSHA GIS 110-ARDNACRUSHA GIS 110-110A2 | 5 | 5 | 5 | Scheduled | 06/03/2023 | 10/03/2023
TO-23-110 kV B2 @ AA GIS-01 | BUSBAR SECTION - ARDNACRUSHA GIS 110-ARDNACRUSHA GIS 110-110B2 | 5 | 5 | 5 | Scheduled | 06/03/2023 | 10/03/2023
TO-23-AA GIS-SNG-1-01 | 110kV FEEDER - ARDNACRUSHA GIS 110-SINGLAND 110-1 | 5 | 5 | 5 | Scheduled | 06/03/2023 | 10/03/2023
TO-23-TB-T2003-02 | GENERATOR TRANSFORMER - TARBERT 220-TARBERT G3-T2003 | 3 | 3 | 3 | Proposed | 06/03/2023 | 08/03/2023
TO-23-BOL-ENN-1-02 | 110kV FEEDER - BOOLTIAGH 110-ENNIS 110-1 | 2 | 2 | 2 | Scheduled | 13/03/2023 | 14/03/2023
TO-23-CHA-KLN-1-02 | 110kV FEEDER - CHARLEVILLE 110-KILLONAN 110-1 | 4 | 4 | 4 | Scheduled | 13/03/2023 | 16/03/2023
TO-23-CBA-110SA1-01 | SECTIONALISING DISCONNECT - CLOGHBOOLA 110-CLOGHBOOLA 110-110SA1 | 4 | 4 | 4 | Scheduled | 13/03/2023 | 16/03/2023
TO-23-CBA-110SA2-01 | SECTIONALISING DISCONNECT - CLOGHBOOLA 110-CLOGHBOOLA 110-110SA2 | 4 | 4 | 4 | Scheduled | 13/03/2023 | 16/03/2023
TO-23-CBA-T122-02 | DISTRIBUTION TRANSFORMER - CLOGHBOOLA 110-CLOGHBOOLA 20-T122 | 4 | 4 | 4 | Reference | 13/03/2023 | 16/03/2023
TO-23-CBA-T131-01 | GENERATOR TRANSFORMER - CLOGHBOOLA 110-CLOGHBOOLA 33-T131 | 4 | 4 | 4 | Scheduled | 13/03/2023 | 16/03/2023
TO-23-CBA-TRI-1-01 | 110kV FEEDER - CLOGHBOOLA 110-TRIEN 110-1 | 4 | 4 | 4 | Scheduled | 13/03/2023 | 16/03/2023
TO-23-PRO-TB-1-02 | 220kV FEEDER - PROSPECT 220-TARBERT 220-1 | 80 | 54 | 54 | Scheduled | 13/03/2023 | 31/05/2023
TO-23-AUG-MTN-1-01 | 110kV FEEDER - AUGHINISH 110-MONETEEN 110-1 | 1 | 1 | 1 | Scheduled | 20/03/2023 | 20/03/2023
TO-23-AUG-SK-4-01 | 110kV FEEDER - AUGHINISH 110-SEALROCK 110-4 | 10 | 8 | 8 | Scheduled | 20/03/2023 | 29/03/2023
TO-23-CLH-TRL-1-01 | 110kV FEEDER - CLAHANE 110-TRALEE 110-1 | 5 | 5 | 5 | Scheduled | 20/03/2023 | 24/03/2023
TO-23-KPG-TRL-1-01 | 110kV FEEDER - KILPADDOGE 110-TRALEE 110-1 | 5 | 5 | 5 | Scheduled | 20/03/2023 | 24/03/2023
TO-23-REM-110SA1-01 | SECTIONALISING DISCONNECT - REAMORE 110-REAMORE 110-110SA1 | 5 | 5 | 5 | Scheduled | 20/03/2023 | 24/03/2023
TO-23-REM-110SA2-01 | SECTIONALISING DISCONNECT - REAMORE 110-REAMORE 110-110SA2 | 5 | 5 | 5 | Scheduled | 20/03/2023 | 24/03/2023
TO-23-REM-T141-01 | DISTRIBUTION TRANSFORMER - REAMORE 110-REAMORE 38-T141 | 5 | 5 | 5 | Reference | 20/03/2023 | 24/03/2023
TO-23-REM-T142-01 | DISTRIBUTION TRANSFORMER - REAMORE 110-REAMORE 38-T142 | 5 | 5 | 5 | Reference | 20/03/2023 | 24/03/2023
TO-23-REM-TRL-1-01 | 110kV FEEDER - REAMORE 110-TRALEE 110-1 | 5 | 5 | 5 | Scheduled | 20/03/2023 | 24/03/2023
TO-23-SK-T104-01 | GENERATOR TRANSFORMER - SEALROCK 110-SEALROCK G4-T104 | 26 | 18 | 18 | Scheduled | 20/03/2023 | 14/04/2023
TO-23-TRL-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - TRALEE 110-TRALEE 110-110SA1-2CB | 5 | 5 | 5 | Scheduled | 20/03/2023 | 24/03/2023
TO-23-TRL-T141-01 | DISTRIBUTION TRANSFORMER - TRALEE 110-TRALEE 38-T141 | 5 | 5 | 5 | Reference | 20/03/2023 | 24/03/2023
TO-23-KPG-T2101-01 | TRANSFORMER - KILPADDOGE 220-KILPADDOGE 110-T2101 | 5 | 5 |  | Scheduled | 27/03/2023 | 31/03/2023
TO-23-AGL-ENN-1-01 | 110kV FEEDER - AGANNYGAL 110-ENNIS 110-1 | 3 | 3 | 3 | Scheduled | 28/03/2023 | 30/03/2023
TO-23-BVK-110SA1-2CB-04 | COUPLER/SECTIONALISING CB - BALLYVOUSKILL 110-BALLYVOUSKILL 110-110SA1-2CB | 1 | 1 | 1 | Scheduled | 03/04/2023 | 03/04/2023
TO-23-KPG-T2102-01 | TRANSFORMER - KILPADDOGE 220-KILPADDOGE 110-T2102 | 4 | 4 | 4 | Scheduled | 03/04/2023 | 06/04/2023
TO-23-LIM-RAT-1-01 | 110kV FEEDER - LIMERICK 110-RATHKEALE 110-1 | 4 | 4 | 4 | Scheduled | 03/04/2023 | 06/04/2023
TO-23-KLN-KPG-1-01 | 220kV FEEDER - KILLONAN 220-KILPADDOGE 220-1 | 4 | 4 |  | Scheduled | 11/04/2023 | 14/04/2023
TO-23-220 kV A4 @ KPG-03 | BUSBAR SECTION - KILPADDOGE 220-KILPADDOGE 220-220A4 | 4 | 4 | 4 | Scheduled | 11/04/2023 | 14/04/2023
TO-23-220 kV B4 @ KPG-03 | BUSBAR SECTION - KILPADDOGE 220-KILPADDOGE 220-220B4 | 4 | 4 | 4 | Scheduled | 11/04/2023 | 14/04/2023
TO-23-KPG-220K4-02 | COUPLER/SECTIONALISING CB - KILPADDOGE 220-KILPADDOGE 220-220K4 | 4 | 4 | 4 | Scheduled | 11/04/2023 | 14/04/2023
TO-23-KPG-220SA2-4CB-02 | COUPLER/SECTIONALISING CB - KILPADDOGE 220-KILPADDOGE 220-220SA2-4CB | 4 | 4 | 4 | Scheduled | 11/04/2023 | 14/04/2023
TO-23-KPG-220SB2-4CB-03 | COUPLER/SECTIONALISING CB - KILPADDOGE 220-KILPADDOGE 220-220SB2-4CB | 4 | 4 | 4 | Scheduled | 11/04/2023 | 14/04/2023
TO-23-KLN-T2104-01 | TRANSFORMER - KILLONAN 220-KILLONAN 110-T2104 | 7 | 5 | 5 | Scheduled | 12/04/2023 | 18/04/2023
TO-23-DRU-ENN-1-04 | 110kV FEEDER - DRUMLINE 110-ENNIS 110-1 | 5 | 5 | 5 | Scheduled | 17/04/2023 | 21/04/2023
TO-23-KPG-TRL-2-01 | 110kV FEEDER - KILPADDOGE 110-TRALEE 110-2 | 5 | 5 |  | Scheduled | 17/04/2023 | 21/04/2023
TO-23-MP GIS-T4201-02 | TRANSFORMER - MONEYPOINT GIS 400-MONEYPOINT GIS 220-T4201 | 5 | 5 | 5 | Scheduled | 17/04/2023 | 21/04/2023
TO-23-220 kV A1 @ KPG-03 | BUSBAR SECTION - KILPADDOGE 220-KILPADDOGE 220-220A1 | 4 | 4 | 4 | Scheduled | 24/04/2023 | 27/04/2023
TO-23-220 kV B1 @ KPG-03 | BUSBAR SECTION - KILPADDOGE 220-KILPADDOGE 220-220B1 | 4 | 4 | 4 | Scheduled | 24/04/2023 | 27/04/2023
TO-23-KPG-220SA1-2CB-03 | COUPLER/SECTIONALISING CB - KILPADDOGE 220-KILPADDOGE 220-220SA1-2CB | 4 | 4 | 4 | Scheduled | 24/04/2023 | 27/04/2023
TO-23-KPG-220SA1-3CB-03 | COUPLER/SECTIONALISING CB - KILPADDOGE 220-KILPADDOGE 220-220SA1-3CB | 4 | 4 | 4 | Scheduled | 24/04/2023 | 27/04/2023
TO-23-KPG-220SB1-2CB-03 | COUPLER/SECTIONALISING CB - KILPADDOGE 220-KILPADDOGE 220-220SB1-2CB | 4 | 4 | 4 | Scheduled | 24/04/2023 | 27/04/2023
TO-23-KPG-220SB1-3CB-04 | COUPLER/SECTIONALISING CB - KILPADDOGE 220-KILPADDOGE 220-220SB1-3CB | 4 | 4 | 4 | Scheduled | 24/04/2023 | 27/04/2023
TO-23-KPG-KNR-1-01 | 220kV FEEDER - KILPADDOGE 220-KNOCKANURE 220-1 | 4 | 4 | 4 | Scheduled | 24/04/2023 | 27/04/2023
TO-23-KNR-TRI-2-01 | 110kV FEEDER - KNOCKANURE 110-TRIEN 110-2 | 4 | 4 | 4 | Scheduled | 24/04/2023 | 27/04/2023
TO-23-LIM-MTN-1-02 | 110kV FEEDER - LIMERICK 110-MONETEEN 110-1 | 5 | 5 | 5 | Scheduled | 24/04/2023 | 28/04/2023
TO-23-110 kV A2 @ AA GIS-02 | BUSBAR SECTION - ARDNACRUSHA GIS 110-ARDNACRUSHA GIS 110-110A2 | 1 | 1 | 1 | Scheduled | 28/04/2023 | 28/04/2023
TO-23-AA GIS-110K2-01 | COUPLER/SECTIONALISING CB - ARDNACRUSHA GIS 110-ARDNACRUSHA GIS 110-110K2 | 1 | 1 | 1 | Scheduled | 28/04/2023 | 28/04/2023
TO-23-AA GIS-110SA1-2CB-02 | COUPLER/SECTIONALISING CB - ARDNACRUSHA GIS 110-ARDNACRUSHA GIS 110-110SA1-2CB | 1 | 1 | 1 | Scheduled | 28/04/2023 | 28/04/2023
TO-23-AA GIS-T102-03 | GENERATOR TRANSFORMER - ARDNACRUSHA GIS 110-ARDNACRUSHA GIS G2-T102 | 1 | 1 | 1 | Scheduled | 28/04/2023 | 28/04/2023
TO-23-KLN-LIM-2-01 | 110kV FEEDER - KILLONAN 110-LIMERICK 110-2 | 4 | 4 |  | Scheduled | 02/05/2023 | 05/05/2023
TO-23-220 kV A2 @ KPG-04 | BUSBAR SECTION - KILPADDOGE 220-KILPADDOGE 220-220A2 | 4 | 4 | 4 | Scheduled | 02/05/2023 | 05/05/2023
TO-23-220 kV B2 @ KPG-04 | BUSBAR SECTION - KILPADDOGE 220-KILPADDOGE 220-220B2 | 4 | 4 | 4 | Scheduled | 02/05/2023 | 05/05/2023
TO-23-KPG-220SA1-2CB-04 | COUPLER/SECTIONALISING CB - KILPADDOGE 220-KILPADDOGE 220-220SA1-2CB | 4 | 4 | 4 | Scheduled | 02/05/2023 | 05/05/2023
TO-23-KPG-220SA2-4CB-03 | COUPLER/SECTIONALISING CB - KILPADDOGE 220-KILPADDOGE 220-220SA2-4CB | 4 | 4 | 4 | Scheduled | 02/05/2023 | 05/05/2023
TO-23-KPG-220SB1-2CB-05 | COUPLER/SECTIONALISING CB - KILPADDOGE 220-KILPADDOGE 220-220SB1-2CB | 4 | 4 | 4 | Scheduled | 02/05/2023 | 05/05/2023
TO-23-KPG-220SB2-4CB-04 | COUPLER/SECTIONALISING CB - KILPADDOGE 220-KILPADDOGE 220-220SB2-4CB | 4 | 4 | 4 | Scheduled | 02/05/2023 | 05/05/2023
TO-23-KPG-KNR-2-01 | 220kV FEEDER - KILPADDOGE 220-KNOCKANURE 220-2 | 4 | 4 |  | Scheduled | 02/05/2023 | 05/05/2023
TO-23-KNR-TRI-1-01 | 110kV FEEDER - KNOCKANURE 110-TRIEN 110-1 | 4 | 4 |  | Scheduled | 02/05/2023 | 05/05/2023
TO-23-400 kV A3 @ MP GIS-02 | BUSBAR SECTION - MONEYPOINT GIS 400-MONEYPOINT GIS 400-400A3 | 9 | 7 | 7 | Scheduled | 02/05/2023 | 10/05/2023
TO-23-400 kV B3 @ MP GIS-01 | BUSBAR SECTION - MONEYPOINT GIS 400-MONEYPOINT GIS 400-400B3 | 9 | 7 | 7 | Scheduled | 02/05/2023 | 10/05/2023
TO-23-MP GIS-400K3-01 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 400-MONEYPOINT GIS 400-400K3 | 9 | 7 | 7 | Scheduled | 02/05/2023 | 10/05/2023
TO-23-MP GIS-400SA1-3CB-02 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 400-MONEYPOINT GIS 400-400SA1-3CB | 9 | 7 | 7 | Scheduled | 02/05/2023 | 10/05/2023
TO-23-MP GIS-400SB1-3CB-01 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 400-MONEYPOINT GIS 400-400SB1-3CB | 9 | 7 | 7 | Scheduled | 02/05/2023 | 10/05/2023
TO-23-MP GIS-OST-1-01 | 400kV FEEDER - MONEYPOINT GIS 400-OLDSTREET 400-1 | 28 | 20 |  | Scheduled | 02/05/2023 | 29/05/2023
TO-23-MP GIS-T4202-02 | TRANSFORMER - MONEYPOINT GIS 400-MONEYPOINT GIS 220-T4202 | 128 | 90 |  | Scheduled | 02/05/2023 | 06/09/2023
TO-23-AGL-ENN-1-02 | 110kV FEEDER - AGANNYGAL 110-ENNIS 110-1 | 5 | 5 | 5 | Scheduled | 08/05/2023 | 12/05/2023
TO-23-AUG-CFM-1-01 | 110kV FEEDER - AUGHINISH 110-CASTLEFARM 110-1 | 3 | 3 | 3 | Scheduled | 08/05/2023 | 10/05/2023
TO-23-CFM-T101-01 | TSO CUSTOMER TRANSFORMER - CASTLEFARM 110-CASTLEFARM 10-T101 | 5 | 5 | 5 | Reference | 08/05/2023 | 12/05/2023
TO-23-CHA-GLE-1-01 | 110kV FEEDER - CHARLEVILLE 110-GLENLARA 110-1 | 12 | 10 | 10 | Scheduled | 08/05/2023 | 19/05/2023
TO-23-MP GIS-T4002-01 | GENERATOR TRANSFORMER - MONEYPOINT GIS 400-MONEYPOINT GIS G2-T4002 | 1 | 1 | 1 | Scheduled | 08/05/2023 | 08/05/2023
TO-23-BVK-T2101-01 | TRANSFORMER - BALLYVOUSKILL 220-BALLYVOUSKILL 110-T2101 | 8 | 6 | 6 | Scheduled | 10/05/2023 | 17/05/2023
TO-23-BYH-T2101-01 | TRANSFORMER - BALLYNAHULLA 220-BALLYNAHULLA 110-T2101 | 15 | 11 | 11 | Scheduled | 12/05/2023 | 26/05/2023
TO-23-110 kV A3 @ AA GIS-01 | BUSBAR SECTION - ARDNACRUSHA GIS 110-ARDNACRUSHA GIS 110-110A3 | 5 | 5 | 5 | Scheduled | 15/05/2023 | 19/05/2023
TO-23-110 kV B3 @ AA GIS-01 | BUSBAR SECTION - ARDNACRUSHA GIS 110-ARDNACRUSHA GIS 110-110B3 | 5 | 5 | 5 | Scheduled | 15/05/2023 | 19/05/2023
TO-23-AA GIS-110K3-02 | COUPLER/SECTIONALISING CB - ARDNACRUSHA GIS 110-ARDNACRUSHA GIS 110-110K3 | 5 | 5 | 5 | Scheduled | 15/05/2023 | 19/05/2023
TO-23-AA GIS-110SA1-3CB-01 | COUPLER/SECTIONALISING CB - ARDNACRUSHA GIS 110-ARDNACRUSHA GIS 110-110SA1-3CB | 5 | 5 | 5 | Scheduled | 15/05/2023 | 19/05/2023
TO-23-AA GIS-110SB1-3CB-01 | COUPLER/SECTIONALISING CB - ARDNACRUSHA GIS 110-ARDNACRUSHA GIS 110-110SB1-3CB | 5 | 5 | 5 | Scheduled | 15/05/2023 | 19/05/2023
TO-23-AA GIS-DRU-1-01 | 110kV FEEDER - ARDNACRUSHA GIS 110-DRUMLINE 110-1 | 5 | 5 | 5 | Scheduled | 15/05/2023 | 19/05/2023
TO-23-CLH-110SA1-01 | SECTIONALISING DISCONNECT - CLAHANE 110-CLAHANE 110-110SA1 | 4 | 4 | 4 | Scheduled | 15/05/2023 | 18/05/2023
TO-23-CLH-110SA2-01 | SECTIONALISING DISCONNECT - CLAHANE 110-CLAHANE 110-110SA2 | 4 | 4 | 4 | Scheduled | 15/05/2023 | 18/05/2023
TO-23-CLH-T122-01 | GENERATOR TRANSFORMER - CLAHANE 110-CLAHANE 20-T122 | 4 | 4 | 4 | Scheduled | 15/05/2023 | 18/05/2023
TO-23-CLH-TRI-1-01 | 110kV FEEDER - CLAHANE 110-TRIEN 110-1 | 4 | 4 | 4 | Scheduled | 15/05/2023 | 18/05/2023
TO-23-110 kV A1 @ AA GIS-01 | BUSBAR SECTION - ARDNACRUSHA GIS 110-ARDNACRUSHA GIS 110-110A1 | 5 | 5 |  | Scheduled | 22/05/2023 | 26/05/2023
TO-23-110 kV B1 @ AA GIS-01 | BUSBAR SECTION - ARDNACRUSHA GIS 110-ARDNACRUSHA GIS 110-110B1 | 5 | 5 | 5 | Scheduled | 22/05/2023 | 26/05/2023
TO-23-AA GIS-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - ARDNACRUSHA GIS 110-ARDNACRUSHA GIS 110-110SA1-2CB | 5 | 5 | 5 | Scheduled | 22/05/2023 | 26/05/2023
TO-23-AA GIS-110SA1-3CB-02 | COUPLER/SECTIONALISING CB - ARDNACRUSHA GIS 110-ARDNACRUSHA GIS 110-110SA1-3CB | 5 | 5 | 5 | Scheduled | 22/05/2023 | 26/05/2023
TO-23-AA GIS-110SB1-2CB-02 | COUPLER/SECTIONALISING CB - ARDNACRUSHA GIS 110-ARDNACRUSHA GIS 110-110SB1-2CB | 5 | 5 | 5 | Scheduled | 22/05/2023 | 26/05/2023
TO-23-AA GIS-110SB1-3CB-02 | COUPLER/SECTIONALISING CB - ARDNACRUSHA GIS 110-ARDNACRUSHA GIS 110-110SB1-3CB | 5 | 5 | 5 | Scheduled | 22/05/2023 | 26/05/2023
TO-23-AA GIS-LIM-1-01 | 110kV FEEDER - ARDNACRUSHA GIS 110-LIMERICK 110-1 | 5 | 5 | 5 | Scheduled | 22/05/2023 | 26/05/2023
TO-23-KLN-T2101-01 | TRANSFORMER - KILLONAN 220-KILLONAN 110-T2101 | 5 | 5 |  | Scheduled | 22/05/2023 | 26/05/2023
TO-23-KPG-TB-1-02 | 220kV FEEDER - KILPADDOGE 220-TARBERT 220-1 | 149 | 105 | 105 | Scheduled | 22/05/2023 | 17/10/2023
TO-23-KPG-TRL-1-03 | 110kV FEEDER - KILPADDOGE 110-TRALEE 110-1 | 9 | 7 | 7 | Scheduled | 22/05/2023 | 30/05/2023
TO-23-MP GIS-T4001-01 | GENERATOR TRANSFORMER - MONEYPOINT GIS 400-MONEYPOINT GIS G1-T4001 | 2 | 2 | 2 | Scheduled | 22/05/2023 | 23/05/2023
TO-23-TB-220K1-2-01 | COUPLER/SECTIONALISING CB - TARBERT 220-TARBERT 220-220K1-2 | 149 | 105 | 105 | Scheduled | 22/05/2023 | 17/10/2023
TO-23-TB-T2004-03 | GENERATOR TRANSFORMER - TARBERT 220-TARBERT G4-T2004 | 149 | 105 | 105 | Scheduled | 22/05/2023 | 17/10/2023
TO-23-TB-T2101-03 | TRANSFORMER - TARBERT 220-TARBERT 110-T2101 | 149 | 105 | 105 | Scheduled | 22/05/2023 | 17/10/2023
TO-23-KPG-110K3-01 | COUPLER/SECTIONALISING CB - KILPADDOGE 110-KILPADDOGE 110-110K3 | 1 | 1 | 1 | Scheduled | 29/05/2023 | 29/05/2023
TO-23-REM-110SA1-02 | SECTIONALISING DISCONNECT - REAMORE 110-REAMORE 110-110SA1 | 5 | 5 | 5 | Scheduled | 29/05/2023 | 02/06/2023
TO-23-REM-110SA2-02 | SECTIONALISING DISCONNECT - REAMORE 110-REAMORE 110-110SA2 | 5 | 5 | 5 | Scheduled | 29/05/2023 | 02/06/2023
TO-23-REM-T141-03 | DISTRIBUTION TRANSFORMER - REAMORE 110-REAMORE 38-T141 | 5 | 5 | 5 | Reference | 29/05/2023 | 02/06/2023
TO-23-REM-T142-02 | DISTRIBUTION TRANSFORMER - REAMORE 110-REAMORE 38-T142 | 5 | 5 | 5 | Reference | 29/05/2023 | 02/06/2023
TO-23-REM-TRL-1-02 | 110kV FEEDER - REAMORE 110-TRALEE 110-1 | 5 | 5 | 5 | Scheduled | 29/05/2023 | 02/06/2023
TO-23-KPG-110SA2-4CB-02 | COUPLER/SECTIONALISING CB - KILPADDOGE 110-KILPADDOGE 110-110SA2-4CB | 1 | 1 | 1 | Scheduled | 30/05/2023 | 30/05/2023
TO-23-KPG-110SB1-2CB-01 | COUPLER/SECTIONALISING CB - KILPADDOGE 110-KILPADDOGE 110-110SB1-2CB | 1 | 1 | 1 | Scheduled | 31/05/2023 | 31/05/2023
TO-23-KPG-110SB1-3CB-02 | COUPLER/SECTIONALISING CB - KILPADDOGE 110-KILPADDOGE 110-110SB1-3CB | 1 | 1 | 1 | Scheduled | 01/06/2023 | 01/06/2023
TO-23-KPG-110SB2-4CB-01 | COUPLER/SECTIONALISING CB - KILPADDOGE 110-KILPADDOGE 110-110SB2-4CB | 1 | 1 | 1 | Scheduled | 02/06/2023 | 02/06/2023
TO-23-AA GIS-T103-01 | GENERATOR TRANSFORMER - ARDNACRUSHA GIS 110-ARDNACRUSHA GIS G3-T103 | 32 | 24 | 24 | Scheduled | 06/06/2023 | 07/07/2023
TO-23-KPG-KNR-1-110-01 | 110kV FEEDER - KILPADDOGE 110-KNOCKANURE 110-1-110 | 3 | 3 |  | Scheduled | 06/06/2023 | 08/06/2023
TO-23-110 kV A1 @ BVK-01 | BUSBAR SECTION - BALLYVOUSKILL 110-BALLYVOUSKILL 110-110A1 | 3 | 3 | 3 | Scheduled | 07/06/2023 | 09/06/2023
TO-23-110 kV B1 @ BVK-01 | BUSBAR SECTION - BALLYVOUSKILL 110-BALLYVOUSKILL 110-110B1 | 3 | 3 | 3 | Scheduled | 07/06/2023 | 09/06/2023
TO-23-BVK-110K1-01 | COUPLER/SECTIONALISING CB - BALLYVOUSKILL 110-BALLYVOUSKILL 110-110K1 | 3 | 3 | 3 | Scheduled | 07/06/2023 | 09/06/2023
TO-23-BVK-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - BALLYVOUSKILL 110-BALLYVOUSKILL 110-110SA1-2CB | 3 | 3 | 3 | Scheduled | 07/06/2023 | 09/06/2023
TO-23-BVK-110SB1-2CB-01 | COUPLER/SECTIONALISING CB - BALLYVOUSKILL 110-BALLYVOUSKILL 110-110SB1-2CB | 3 | 3 | 3 | Scheduled | 07/06/2023 | 09/06/2023
TO-23-KPG-RAT-1-01 | 110kV FEEDER - KILPADDOGE 110-RATHKEALE 110-1 | 1 | 1 | 1 | Scheduled | 07/06/2023 | 07/06/2023
TO-23-BYH-T2102-02 | TRANSFORMER - BALLYNAHULLA 220-BALLYNAHULLA 110-T2102 | 15 | 11 | 11 | Scheduled | 09/06/2023 | 23/06/2023
TO-23-ATE-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - ATHEA 110-ATHEA 110-110SA1-2CB | 5 | 5 | 5 | Scheduled | 12/06/2023 | 16/06/2023
TO-23-ATE-DRO-1-01 | 110kV FEEDER - ATHEA 110-DROMADA 110-1 | 5 | 5 | 5 | Scheduled | 12/06/2023 | 16/06/2023
TO-23-ATE-KNR-1-01 | 110kV FEEDER - ATHEA 110-KNOCKANURE 110-1 | 5 | 5 |  | Scheduled | 12/06/2023 | 16/06/2023
TO-23-ATE-T121-01 | GENERATOR TRANSFORMER - ATHEA 110-ATHEA 20-T121 | 5 | 5 | 5 | Scheduled | 12/06/2023 | 16/06/2023
TO-23-ATE-TOB-1-01 | 110kV FEEDER - ATHEA 110-TOBERTOREEN 110-1 | 5 | 5 | 5 | Scheduled | 12/06/2023 | 16/06/2023
TO-23-DRO-T121-01 | GENERATOR TRANSFORMER - DROMADA 110-DROMADA 20-T121 | 5 | 5 | 5 | Scheduled | 12/06/2023 | 16/06/2023
TO-23-ENN-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - ENNIS 110-ENNIS 110-110SA1-2CB | 5 | 5 | 5 | Scheduled | 12/06/2023 | 16/06/2023
TO-23-ENN-SLC-1-01 | 110kV FEEDER - ENNIS 110-SLIEVECALLAN 110-1 | 5 | 5 | 5 | Scheduled | 12/06/2023 | 16/06/2023
TO-23-ENN-T101-01 | DISTRIBUTION TRANSFORMER - ENNIS 110-ENNIS 10-T101 | 5 | 5 | 5 | Reference | 12/06/2023 | 16/06/2023
TO-23-ENN-T141-01 | DISTRIBUTION TRANSFORMER - ENNIS 110-ENNIS 38-T141 | 5 | 5 | 5 | Reference | 12/06/2023 | 16/06/2023
TO-23-220 kV A2 @ MP GIS-01 | BUSBAR SECTION - MONEYPOINT GIS 220-MONEYPOINT GIS 220-220A2 | 5 | 5 | 5 | Scheduled | 12/06/2023 | 16/06/2023
TO-23-220 kV B2 @ MP GIS-01 | BUSBAR SECTION - MONEYPOINT GIS 220-MONEYPOINT GIS 220-220B2 | 5 | 5 | 5 | Scheduled | 12/06/2023 | 16/06/2023
TO-23-MP GIS-220K2-01 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 220-MONEYPOINT GIS 220-220K2 | 5 | 5 | 5 | Scheduled | 12/06/2023 | 16/06/2023
TO-23-MP GIS-220SA1-2CB-01 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 220-MONEYPOINT GIS 220-220SA1-2CB | 5 | 5 | 5 | Scheduled | 12/06/2023 | 16/06/2023
TO-23-MP GIS-220SB1-2CB-01 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 220-MONEYPOINT GIS 220-220SB1-2CB | 5 | 5 | 5 | Scheduled | 12/06/2023 | 16/06/2023
TO-23-400 kV A4 @ MP GIS-02 | BUSBAR SECTION - MONEYPOINT GIS 400-MONEYPOINT GIS 400-400A4 | 5 | 5 | 5 | Scheduled | 12/06/2023 | 16/06/2023
TO-23-400 kV B4 @ MP GIS-01 | BUSBAR SECTION - MONEYPOINT GIS 400-MONEYPOINT GIS 400-400B4 | 5 | 5 | 5 | Scheduled | 12/06/2023 | 16/06/2023
TO-23-MP GIS-400K4-02 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 400-MONEYPOINT GIS 400-400K4 | 5 | 5 | 5 | Scheduled | 12/06/2023 | 16/06/2023
TO-23-MP GIS-400SA2-4CB-02 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 400-MONEYPOINT GIS 400-400SA2-4CB | 5 | 5 | 5 | Scheduled | 12/06/2023 | 16/06/2023
TO-23-MP GIS-400SB2-4CB-01 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 400-MONEYPOINT GIS 400-400SB2-4CB | 5 | 5 | 5 | Scheduled | 12/06/2023 | 16/06/2023
TO-23-SLC-110SA1-01 | SECTIONALISING DISCONNECT - SLIEVECALLAN 110-SLIEVECALLAN 110-110SA1 | 5 | 5 | 5 | Scheduled | 12/06/2023 | 16/06/2023
TO-23-SLC-110SA2-01 | SECTIONALISING DISCONNECT - SLIEVECALLAN 110-SLIEVECALLAN 110-110SA2 | 5 | 5 | 5 | Scheduled | 12/06/2023 | 16/06/2023
TO-23-SLC-T121-01 | GENERATOR TRANSFORMER - SLIEVECALLAN 110-SLIEVECALLAN 20-T121 | 5 | 5 | 5 | Scheduled | 12/06/2023 | 16/06/2023
TO-23-SLC-T122-01 | GENERATOR TRANSFORMER - SLIEVECALLAN 110-SLIEVECALLAN 20-T122 | 5 | 5 | 5 | Scheduled | 12/06/2023 | 16/06/2023
TO-23-TOB-T132-01 | GENERATOR TRANSFORMER - TOBERTOREEN 110-TOBERTOREEN 33-T132 | 5 | 5 | 5 | Scheduled | 12/06/2023 | 16/06/2023
TO-23-BOL-T121-01 | GENERATOR TRANSFORMER - BOOLTIAGH 110-BOOLTIAGH 20-T121 | 1 | 1 | 1 | Scheduled | 14/06/2023 | 14/06/2023
TO-23-OST-WOO-1-02 | 400kV FEEDER - OLDSTREET 400-WOODLAND 400-1 | 16 | 12 | 12 | Scheduled | 15/06/2023 | 30/06/2023
TO-23-AUG-SK-3-01 | 110kV FEEDER - AUGHINISH 110-SEALROCK 110-3 | 22 | 16 | 16 | Scheduled | 19/06/2023 | 10/07/2023
TO-23-CDL-110SA1-01 | SECTIONALISING DISCONNECT - CORDAL 110-CORDAL 110-110SA1 | 5 | 5 | 5 | Scheduled | 19/06/2023 | 23/06/2023
TO-23-CDL-110SA2-01 | SECTIONALISING DISCONNECT - CORDAL 110-CORDAL 110-110SA2 | 5 | 5 | 5 | Scheduled | 19/06/2023 | 23/06/2023
TO-23-CDL-T132-01 | GENERATOR TRANSFORMER - CORDAL 110-CORDAL 33-T132 | 5 | 5 | 5 | Scheduled | 19/06/2023 | 23/06/2023
TO-23-CDL-T141-01 | DISTRIBUTION TRANSFORMER - CORDAL 110-CORDAL 38-T141 | 5 | 5 | 5 | Reference | 19/06/2023 | 23/06/2023
TO-23-SK-T103-01 | GENERATOR TRANSFORMER - SEALROCK 110-SEALROCK G3-T103 | 22 | 16 | 16 | Scheduled | 19/06/2023 | 10/07/2023
TO-23-BYH-110SA1-2CB-03 | COUPLER/SECTIONALISING CB - BALLYNAHULLA 110-BALLYNAHULLA 110-110SA1-2CB | 1 | 1 | 1 | Scheduled | 26/06/2023 | 26/06/2023
TO-23-KLN-SNG-1-01 | 110kV FEEDER - KILLONAN 110-SINGLAND 110-1 | 4 | 4 | 4 | Scheduled | 26/06/2023 | 29/06/2023
TO-23-SNG-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - SINGLAND 110-SINGLAND 110-110SA1-2CB | 4 | 4 | 4 | Scheduled | 26/06/2023 | 29/06/2023
TO-23-SNG-T101-01 | DISTRIBUTION TRANSFORMER - SINGLAND 110-SINGLAND 10-T101 | 4 | 4 | 4 | Reference | 26/06/2023 | 29/06/2023
TO-23-BYH-110SB1-2CB-03 | COUPLER/SECTIONALISING CB - BALLYNAHULLA 110-BALLYNAHULLA 110-110SB1-2CB | 1 | 1 | 1 | Scheduled | 27/06/2023 | 27/06/2023
TO-23-KHL-T131-02 | GENERATOR TRANSFORMER - KILL HILL 110-KILL HILL 33-T131 | 3 | 3 | 3 | Scheduled | 27/06/2023 | 29/06/2023
TO-23-BYH-GLE-1-02 | 110kV FEEDER - BALLYNAHULLA 110-GLENLARA 110-1 | 1 | 1 | 1 | Scheduled | 28/06/2023 | 28/06/2023
TO-23-CNO-KPG-1-01 | 110kV FEEDER - COOLNANOONAGH 110-KILPADDOGE 110-1 | 4 | 4 | 4 | Scheduled | 03/07/2023 | 06/07/2023
TO-23-CNO-T131-01 | GENERATOR TRANSFORMER - COOLNANOONAGH 110-COOLNANOONAGH 33-T131 | 4 | 4 | 4 | Scheduled | 03/07/2023 | 06/07/2023
TO-23-KPG-F13-1-CUB-01 | CUBICLE - KILPADDOGE 220-F13 SPARE 220-1-CUB | 4 | 4 | 4 | Scheduled | 04/07/2023 | 07/07/2023
TO-23-220 kV A3 @ KPG-03 | BUSBAR SECTION - KILPADDOGE 220-KILPADDOGE 220-220A3 | 4 | 4 | 4 | Scheduled | 04/07/2023 | 07/07/2023
TO-23-220 kV B3 @ KPG-03 | BUSBAR SECTION - KILPADDOGE 220-KILPADDOGE 220-220B3 | 4 | 4 | 4 | Scheduled | 04/07/2023 | 07/07/2023
TO-23-AUG-KPG-1-01 | 110kV FEEDER - AUGHINISH 110-KILPADDOGE 110-1 | 4 | 4 | 4 | Scheduled | 10/07/2023 | 13/07/2023
TO-23-110 kV A2 @ KPG-04 | BUSBAR SECTION - KILPADDOGE 110-KILPADDOGE 110-110A2 | 4 | 4 | 4 | Scheduled | 10/07/2023 | 13/07/2023
TO-23-110 kV B2 @ KPG-02 | BUSBAR SECTION - KILPADDOGE 110-KILPADDOGE 110-110B2 | 4 | 4 | 4 | Scheduled | 10/07/2023 | 13/07/2023
TO-23-KPG-110SA1-2CB-04 | COUPLER/SECTIONALISING CB - KILPADDOGE 110-KILPADDOGE 110-110SA1-2CB | 4 | 4 | 4 | Scheduled | 10/07/2023 | 13/07/2023
TO-23-KPG-110SA2-4CB-04 | COUPLER/SECTIONALISING CB - KILPADDOGE 110-KILPADDOGE 110-110SA2-4CB | 4 | 4 | 4 | Scheduled | 10/07/2023 | 13/07/2023
TO-23-KPG-110SB1-2CB-05 | COUPLER/SECTIONALISING CB - KILPADDOGE 110-KILPADDOGE 110-110SB1-2CB | 4 | 4 | 4 | Scheduled | 10/07/2023 | 13/07/2023
TO-23-KPG-110SB2-4CB-04 | COUPLER/SECTIONALISING CB - KILPADDOGE 110-KILPADDOGE 110-110SB2-4CB | 4 | 4 | 4 | Scheduled | 10/07/2023 | 13/07/2023
TO-23-KPG-F14-1-CUB-01 | CUBICLE - KILPADDOGE 220-F14 SPARE 220-1-CUB | 4 | 4 | 4 | Scheduled | 11/07/2023 | 14/07/2023
TO-23-220 kV A4 @ KPG-04 | BUSBAR SECTION - KILPADDOGE 220-KILPADDOGE 220-220A4 | 4 | 4 | 4 | Scheduled | 11/07/2023 | 14/07/2023
TO-23-220 kV B4 @ KPG-04 | BUSBAR SECTION - KILPADDOGE 220-KILPADDOGE 220-220B4 | 4 | 4 | 4 | Scheduled | 11/07/2023 | 14/07/2023
TO-23-KPG-220K3-03 | COUPLER/SECTIONALISING CB - KILPADDOGE 220-KILPADDOGE 220-220K3 | 3 | 3 | 3 | Proposed | 11/07/2023 | 13/07/2023
TO-23-KPG-220SA1-3CB-05 | COUPLER/SECTIONALISING CB - KILPADDOGE 220-KILPADDOGE 220-220SA1-3CB | 3 | 3 | 3 | Proposed | 11/07/2023 | 13/07/2023
TO-23-KPG-220SB1-3CB-05 | COUPLER/SECTIONALISING CB - KILPADDOGE 220-KILPADDOGE 220-220SB1-3CB | 3 | 3 | 3 | Proposed | 11/07/2023 | 13/07/2023
TO-23-LIM-RAT-1-02 | 110kV FEEDER - LIMERICK 110-RATHKEALE 110-1 | 12 | 10 | 10 | Scheduled | 17/07/2023 | 28/07/2023
TO-23-LIM-RAT-1-04 | 110kV FEEDER - LIMERICK 110-RATHKEALE 110-1 | 12 | 10 | 10 | Proposed | 17/07/2023 | 28/07/2023
TO-23-MP GIS-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 110-MONEYPOINT GIS 110-110SA1-2CB | 5 | 5 |  | Scheduled | 17/07/2023 | 21/07/2023
TO-23-MP GIS-T121-01 | GENERATOR TRANSFORMER - MONEYPOINT GIS 110-MONEYPOINT GIS 20-T121 | 5 | 5 |  | Scheduled | 17/07/2023 | 21/07/2023
TO-23-110 kV A1 @ KLN-02 | BUSBAR SECTION - KILLONAN 110-KILLONAN 110-110A1 | 10 | 7 | 7 | Scheduled | 31/07/2023 | 09/08/2023
TO-23-110 kV B1 @ KLN-02 | BUSBAR SECTION - KILLONAN 110-KILLONAN 110-110B1 | 10 | 7 | 7 | Scheduled | 31/07/2023 | 09/08/2023
TO-23-KLN-LIM-1-01 | 110kV FEEDER - KILLONAN 110-LIMERICK 110-1 | 10 | 7 |  | Scheduled | 31/07/2023 | 09/08/2023
TO-23-BVK-COT-1-01 | 110kV FEEDER - BALLYVOUSKILL 110-COOMATAGGART 110-1 | 11 | 9 | 9 | Scheduled | 08/08/2023 | 18/08/2023
TO-23-COT-110SA1-01 | SECTIONALISING DISCONNECT - COOMATAGGART 110-COOMATAGGART 110-110SA1 | 11 | 9 | 9 | Scheduled | 08/08/2023 | 18/08/2023
TO-23-COT-110SA2-01 | SECTIONALISING DISCONNECT - COOMATAGGART 110-COOMATAGGART 110-110SA2 | 11 | 9 | 9 | Scheduled | 08/08/2023 | 18/08/2023
TO-23-COT-FILTER1-02 | CAPACITOR/SVC/REACTOR - COOMATAGGART 110-COOMATAGGART 110-FILTER1 | 11 | 9 | 9 | Scheduled | 08/08/2023 | 18/08/2023
TO-23-COT-T132-01 | GENERATOR TRANSFORMER - COOMATAGGART 110-COOMATAGGART 33-T132 | 11 | 9 | 9 | Scheduled | 08/08/2023 | 18/08/2023
TO-23-COT-T141-01 | DISTRIBUTION TRANSFORMER - COOMATAGGART 110-COOMATAGGART 38-T141 | 11 | 9 | 9 | Reference | 08/08/2023 | 18/08/2023
TO-23-KLN-T2102-01 | TRANSFORMER - KILLONAN 220-KILLONAN 110-T2102 | 4 | 4 | 4 | Scheduled | 08/08/2023 | 11/08/2023
TO-23-KCR-T121-01 | GENERATOR TRANSFORMER - KNOCKACUMMER 110-KNOCKACUMMER 20-T121 | 1 | 1 | 1 | Scheduled | 14/08/2023 | 14/08/2023
TO-23-CKN-KER-1-02 | 110kV FEEDER - CLONKEEN 110-KNOCKEARAGH 110-1 | 2 | 2 | 2 | Scheduled | 16/08/2023 | 17/08/2023
TO-23-GAE-T121-03 | GENERATOR TRANSFORMER - GLANLEE 110-GLANLEE 20-T121 | 3 | 3 | 3 | Scheduled | 16/08/2023 | 18/08/2023
TO-23-CLA-CKN-1-01 | 110kV FEEDER - CLASHAVOON 110-CLONKEEN 110-1 | 11 | 9 | 9 | Scheduled | 21/08/2023 | 31/08/2023
TO-23-CKN-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - CLONKEEN 110-CLONKEEN 110-110SA1-2CB | 11 | 9 | 9 | Scheduled | 21/08/2023 | 31/08/2023
TO-23-CKN-CGL-1-01 | 110kV FEEDER - CLONKEEN 110-COOMAGEARLAHY 110-1 | 11 | 9 | 9 | Scheduled | 21/08/2023 | 31/08/2023
TO-23-CKN-GRO-1-01 | 110kV FEEDER - CLONKEEN 110-GARROW 110-1 | 11 | 9 | 9 | Scheduled | 21/08/2023 | 31/08/2023
TO-23-CKN-KER-1-01 | 110kV FEEDER - CLONKEEN 110-KNOCKEARAGH 110-1 | 11 | 9 | 9 | Scheduled | 21/08/2023 | 31/08/2023
TO-23-CGL-110SA1-01 | SECTIONALISING DISCONNECT - COOMAGEARLAHY 110-COOMAGEARLAHY 110-110SA1 | 11 | 9 | 9 | Scheduled | 21/08/2023 | 31/08/2023
TO-23-CGL-110SA2-01 | SECTIONALISING DISCONNECT - COOMAGEARLAHY 110-COOMAGEARLAHY 110-110SA2 | 11 | 9 | 9 | Scheduled | 21/08/2023 | 31/08/2023
TO-23-CGL-GAE-1-01 | 110kV FEEDER - COOMAGEARLAHY 110-GLANLEE 110-1 | 11 | 9 | 9 | Scheduled | 21/08/2023 | 31/08/2023
TO-23-CGL-T121-01 | GENERATOR TRANSFORMER - COOMAGEARLAHY 110-COOMAGEARLAHY 20-T121 | 11 | 9 | 9 | Scheduled | 21/08/2023 | 31/08/2023
TO-23-CGL-T122-01 | GENERATOR TRANSFORMER - COOMAGEARLAHY 110-COOMAGEARLAHY 20-T122 | 11 | 9 | 9 | Scheduled | 21/08/2023 | 31/08/2023
TO-23-GAE-T121-01 | GENERATOR TRANSFORMER - GLANLEE 110-GLANLEE 20-T121 | 11 | 9 | 9 | Scheduled | 21/08/2023 | 31/08/2023
TO-23-AA GIS-ENN-1-01 | 110kV FEEDER - ARDNACRUSHA GIS 110-ENNIS 110-1 | 2 | 2 | 2 | Scheduled | 22/08/2023 | 23/08/2023
TO-23-KPG-F11-1-CUB-01 | CUBICLE - KILPADDOGE 220-F11 SPARE 220-1-CUB | 4 | 2 | 2 | Scheduled | 25/08/2023 | 28/08/2023
TO-23-220 kV A3 @ KPG-04 | BUSBAR SECTION - KILPADDOGE 220-KILPADDOGE 220-220A3 | 4 | 2 | 2 | Scheduled | 25/08/2023 | 28/08/2023
TO-23-220 kV B3 @ KPG-04 | BUSBAR SECTION - KILPADDOGE 220-KILPADDOGE 220-220B3 | 4 | 2 | 2 | Scheduled | 25/08/2023 | 28/08/2023
TO-23-IKE,T-THU-1-08 | 110kV FEEDER - IKERRIN tee-THURLES 110-1 | 10 | 8 | 8 | Scheduled | 29/08/2023 | 07/09/2023
TO-23-IKE,T-THU-1-07 | 110kV FEEDER - IKERRIN tee-THURLES 110-1 | 1 | 1 | 1 | Scheduled | 29/08/2023 | 29/08/2023
TO-23-LSN-110SA1-2-06 | SECTIONALISING DISCONNECT - LISHEEN 110-LISHEEN 110-110SA1-2 | 10 | 8 | 8 | Scheduled | 29/08/2023 | 07/09/2023
TO-23-LSN-110SA2-4-06 | SECTIONALISING DISCONNECT - LISHEEN 110-LISHEEN 110-110SA2-4 | 10 | 8 | 8 | Scheduled | 29/08/2023 | 07/09/2023
TO-23-LSN-T122-06 | GENERATOR TRANSFORMER - LISHEEN 110-LISHEEN 20-T122 | 10 | 8 | 8 | Scheduled | 29/08/2023 | 07/09/2023
TO-23-LSN-T131-06 | GENERATOR TRANSFORMER - LISHEEN 110-LISHEEN 33-T131 | 10 | 8 | 8 | Scheduled | 29/08/2023 | 07/09/2023
TO-23-LSN-T142-06 | DISTRIBUTION TRANSFORMER - LISHEEN 110-LISHEEN 38-T142 | 10 | 8 | 8 | Reference | 29/08/2023 | 07/09/2023
TO-23-LSN-THU-1-07 | 110kV FEEDER - LISHEEN 110-THURLES 110-1 | 10 | 8 | 8 | Scheduled | 29/08/2023 | 07/09/2023
TO-23-THU-110SA1-2CB-06 | COUPLER/SECTIONALISING CB - THURLES 110-THURLES 110-110SA1-2CB | 10 | 8 | 8 | Scheduled | 29/08/2023 | 07/09/2023
TO-23-THU-T142-05 | DISTRIBUTION TRANSFORMER - THURLES 110-THURLES 38-T142 | 10 | 8 | 8 | Reference | 29/08/2023 | 07/09/2023
TO-23-AA GIS-T101-01 | GENERATOR TRANSFORMER - ARDNACRUSHA GIS 110-ARDNACRUSHA GIS G1-T101 | 5 | 5 | 5 | Scheduled | 04/09/2023 | 08/09/2023
TO-23-GRO-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - GARROW 110-GARROW 110-110SA1-2CB | 4 | 4 | 4 | Scheduled | 04/09/2023 | 07/09/2023
TO-23-GRO-T122-01 | GENERATOR TRANSFORMER - GARROW 110-GARROW 20-T122 | 4 | 4 | 4 | Scheduled | 04/09/2023 | 07/09/2023
TO-23-400 kV A1 @ MP GIS-03 | BUSBAR SECTION - MONEYPOINT GIS 400-MONEYPOINT GIS 400-400A1 | 2 | 2 | 2 | Scheduled | 05/09/2023 | 06/09/2023
TO-23-400 kV A2 @ MP GIS-01 | BUSBAR SECTION - MONEYPOINT GIS 400-MONEYPOINT GIS 400-400A2 | 2 | 2 | 2 | Scheduled | 05/09/2023 | 06/09/2023
TO-23-400 kV A3 @ MP GIS-03 | BUSBAR SECTION - MONEYPOINT GIS 400-MONEYPOINT GIS 400-400A3 | 2 | 2 | 2 | Scheduled | 05/09/2023 | 06/09/2023
TO-23-400 kV A4 @ MP GIS-03 | BUSBAR SECTION - MONEYPOINT GIS 400-MONEYPOINT GIS 400-400A4 | 2 | 2 | 2 | Scheduled | 05/09/2023 | 06/09/2023
TO-23-400 kV B1 @ MP GIS-03 | BUSBAR SECTION - MONEYPOINT GIS 400-MONEYPOINT GIS 400-400B1 | 2 | 2 | 2 | Scheduled | 05/09/2023 | 06/09/2023
TO-23-400 kV B2 @ MP GIS-01 | BUSBAR SECTION - MONEYPOINT GIS 400-MONEYPOINT GIS 400-400B2 | 2 | 2 | 2 | Scheduled | 05/09/2023 | 06/09/2023
TO-23-400 kV B3 @ MP GIS-02 | BUSBAR SECTION - MONEYPOINT GIS 400-MONEYPOINT GIS 400-400B3 | 2 | 2 | 2 | Scheduled | 05/09/2023 | 06/09/2023
TO-23-400 kV B4 @ MP GIS-02 | BUSBAR SECTION - MONEYPOINT GIS 400-MONEYPOINT GIS 400-400B4 | 2 | 2 | 2 | Scheduled | 05/09/2023 | 06/09/2023
TO-23-MP GIS-400K3-02 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 400-MONEYPOINT GIS 400-400K3 | 2 | 2 | 2 | Scheduled | 05/09/2023 | 06/09/2023
TO-23-MP GIS-400K4-01 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 400-MONEYPOINT GIS 400-400K4 | 2 | 2 |  | Scheduled | 05/09/2023 | 06/09/2023
TO-23-MP GIS-400SA1-2CB-01 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 400-MONEYPOINT GIS 400-400SA1-2CB | 2 | 2 | 2 | Scheduled | 05/09/2023 | 06/09/2023
TO-23-MP GIS-400SA1-3CB-03 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 400-MONEYPOINT GIS 400-400SA1-3CB | 2 | 2 | 2 | Scheduled | 05/09/2023 | 06/09/2023
TO-23-MP GIS-400SA2-4CB-01 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 400-MONEYPOINT GIS 400-400SA2-4CB | 2 | 2 |  | Scheduled | 05/09/2023 | 06/09/2023
TO-23-MP GIS-400SB1-2CB-01 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 400-MONEYPOINT GIS 400-400SB1-2CB | 2 | 2 | 2 | Scheduled | 05/09/2023 | 06/09/2023
TO-23-MP GIS-400SB1-3CB-02 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 400-MONEYPOINT GIS 400-400SB1-3CB | 2 | 2 | 2 | Scheduled | 05/09/2023 | 06/09/2023
TO-23-MP GIS-400SB2-4CB-02 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 400-MONEYPOINT GIS 400-400SB2-4CB | 2 | 2 | 2 | Scheduled | 05/09/2023 | 06/09/2023
TO-23-MP GIS-OST-1-06 | 400kV FEEDER - MONEYPOINT GIS 400-OLDSTREET 400-1 | 2 | 2 | 2 | Scheduled | 05/09/2023 | 06/09/2023
TO-23-BYH-BVK-1-01 | 220kV FEEDER - BALLYNAHULLA 220-BALLYVOUSKILL 220-1 | 8 | 6 | 6 | Scheduled | 07/09/2023 | 14/09/2023
TO-23-KHL-THU-1-01 | 110kV FEEDER - KILL HILL 110-THURLES 110-1 | 8 | 6 | 6 | Scheduled | 08/09/2023 | 15/09/2023
TO-23-THU-110SA1-2CB-07 | COUPLER/SECTIONALISING CB - THURLES 110-THURLES 110-110SA1-2CB | 8 | 6 | 6 | Scheduled | 08/09/2023 | 15/09/2023
TO-23-THU-CAP1-02 | CAPACITOR/SVC/REACTOR - THURLES 110-THURLES 110-CAP1 | 8 | 6 | 6 | Scheduled | 08/09/2023 | 15/09/2023
TO-23-THU-T141-01 | DISTRIBUTION TRANSFORMER - THURLES 110-THURLES 38-T141 | 8 | 6 | 6 | Reference | 08/09/2023 | 15/09/2023
TO-23-AA GIS-T102-04 | GENERATOR TRANSFORMER - ARDNACRUSHA GIS 110-ARDNACRUSHA GIS G2-T102 | 19 | 15 | 15 | Scheduled | 11/09/2023 | 29/09/2023
TO-23-MTN-MUN-2-01 | 110kV FEEDER - MONETEEN 110-MUNGRET 110-2 | 4 | 4 | 4 | Scheduled | 12/09/2023 | 15/09/2023
TO-23-220 kV A1/A2 @ MP GIS-02 | BUSBAR SECTION - MONEYPOINT GIS 220-MONEYPOINT GIS 220-220A1-A2 | 3 | 3 | 3 | Scheduled | 12/09/2023 | 14/09/2023
TO-23-MUN-T102-01 | TSO CUSTOMER TRANSFORMER - MUNGRET 110-MUNGRET 10-T102 | 4 | 4 | 4 | Reference | 12/09/2023 | 15/09/2023
TO-23-OST-T4202-01 | TRANSFORMER - OLDSTREET 400-OLDSTREET 220-T4202 | 9 | 7 | 7 | Scheduled | 14/09/2023 | 22/09/2023
TO-23-OST-TY-1-04 | 220kV FEEDER - OLDSTREET 220-TYNAGH 220-1 | 9 | 7 | 7 | Scheduled | 14/09/2023 | 22/09/2023
TO-23-KLN-T2103-02 | TRANSFORMER - KILLONAN 220-KILLONAN 110-T2103 | 22 | 16 | 16 | Scheduled | 15/09/2023 | 06/10/2023
TO-23-AUG-CFM-2-01 | 110kV FEEDER - AUGHINISH 110-CASTLEFARM 110-2 | 5 | 5 | 5 | Scheduled | 18/09/2023 | 22/09/2023
TO-23-CFM-T102-01 | TSO CUSTOMER TRANSFORMER - CASTLEFARM 110-CASTLEFARM 10-T102 | 5 | 5 | 5 | Reference | 18/09/2023 | 22/09/2023
TO-23-IKE-T141-03 | DISTRIBUTION TRANSFORMER - IKERRIN 110-IKERRIN 38-T141 | 2 | 2 |  | Reference | 18/09/2023 | 19/09/2023
TO-23-IKE,T-IKE-1-02 | 110kV FEEDER - IKERRIN tee-IKERRIN 110-1 | 2 | 2 |  | Scheduled | 18/09/2023 | 19/09/2023
TO-23-IKE,T-SH-1-05 | 110kV FEEDER - IKERRIN tee-SHANNONBRIDGE 110-1 | 2 | 2 |  | Scheduled | 18/09/2023 | 19/09/2023
TO-23-IKE,T-THU-1-10 | 110kV FEEDER - IKERRIN tee-THURLES 110-1 | 2 | 2 |  | Scheduled | 18/09/2023 | 19/09/2023
TO-23-CHA-KLN-1-03 | 110kV FEEDER - CHARLEVILLE 110-KILLONAN 110-1 | 3 | 3 | 3 | Scheduled | 20/09/2023 | 22/09/2023
TO-23-110 kV A1 @ BVK-02 | BUSBAR SECTION - BALLYVOUSKILL 110-BALLYVOUSKILL 110-110A1 | 2 | 2 | 2 | Scheduled | 25/09/2023 | 26/09/2023
TO-23-110 kV B1 @ BVK-02 | BUSBAR SECTION - BALLYVOUSKILL 110-BALLYVOUSKILL 110-110B1 | 2 | 2 | 2 | Scheduled | 25/09/2023 | 26/09/2023
TO-23-BVK-110K1-03 | COUPLER/SECTIONALISING CB - BALLYVOUSKILL 110-BALLYVOUSKILL 110-110K1 | 2 | 2 | 2 | Scheduled | 25/09/2023 | 26/09/2023
TO-23-BVK-110SA1-2CB-02 | COUPLER/SECTIONALISING CB - BALLYVOUSKILL 110-BALLYVOUSKILL 110-110SA1-2CB | 2 | 2 | 2 | Scheduled | 25/09/2023 | 26/09/2023
TO-23-BVK-110SB1-2CB-02 | COUPLER/SECTIONALISING CB - BALLYVOUSKILL 110-BALLYVOUSKILL 110-110SB1-2CB | 2 | 2 | 2 | Scheduled | 25/09/2023 | 26/09/2023
TO-23-BVK-GRO-1-01 | 110kV FEEDER - BALLYVOUSKILL 110-GARROW 110-1 | 2 | 2 | 2 | Scheduled | 25/09/2023 | 26/09/2023
TO-23-CAH-KHL-1-01 | 110kV FEEDER - CAHIR 110-KILL HILL 110-1 | 3 | 3 | 3 | Scheduled | 25/09/2023 | 27/09/2023
TO-23-MP GIS-T4003-01 | GENERATOR TRANSFORMER - MONEYPOINT GIS 400-MONEYPOINT GIS G3-T4003 | 2 | 2 | 2 | Scheduled | 25/09/2023 | 26/09/2023
TO-23-CAH-TIP-1-01 | 110kV FEEDER - CAHIR 110-TIPPERARY 110-1 | 2 | 2 | 2 | Scheduled | 28/09/2023 | 29/09/2023
TO-23-AUG-CFM-1-03 | 110kV FEEDER - AUGHINISH 110-CASTLEFARM 110-1 | 5 | 5 | 5 | Scheduled | 02/10/2023 | 06/10/2023
TO-23-220 kV A1 @ BVK-01 | BUSBAR SECTION - BALLYVOUSKILL 220-BALLYVOUSKILL 220-220A1 | 11 | 9 | 9 | Scheduled | 02/10/2023 | 12/10/2023
TO-23-220 kV B1 @ BVK-01 | BUSBAR SECTION - BALLYVOUSKILL 220-BALLYVOUSKILL 220-220B1 | 11 | 9 | 9 | Scheduled | 02/10/2023 | 12/10/2023
TO-23-BVK-CLA-1-01 | 220kV FEEDER - BALLYVOUSKILL 220-CLASHAVOON 220-1 | 11 | 9 |  | Scheduled | 02/10/2023 | 12/10/2023
TO-23-CFM-T101-02 | TSO CUSTOMER TRANSFORMER - CASTLEFARM 110-CASTLEFARM 10-T101 | 5 | 5 | 5 | Reference | 02/10/2023 | 06/10/2023
TO-23-CLH-110SA1-02 | SECTIONALISING DISCONNECT - CLAHANE 110-CLAHANE 110-110SA1 | 5 | 5 | 5 | Scheduled | 02/10/2023 | 06/10/2023
TO-23-CLH-110SA2-02 | SECTIONALISING DISCONNECT - CLAHANE 110-CLAHANE 110-110SA2 | 5 | 5 | 5 | Scheduled | 02/10/2023 | 06/10/2023
TO-23-CLH-TRL-1-02 | 110kV FEEDER - CLAHANE 110-TRALEE 110-1 | 5 | 5 | 5 | Scheduled | 02/10/2023 | 06/10/2023
TO-23-MP GIS-T2102-01 | TRANSFORMER - MONEYPOINT GIS 220-MONEYPOINT GIS 110-T2102 | 15 | 11 | 11 | Scheduled | 06/10/2023 | 20/10/2023
TO-23-CSH-ENN-1-02 | 110kV FEEDER - CASHLA 110-ENNIS 110-1 | 5 | 5 | 5 | Scheduled | 09/10/2023 | 13/10/2023
TO-23-CTN-KLN-1-01 | 110kV FEEDER - CAUTEEN 110-KILLONAN 110-1 | 5 | 5 | 5 | Scheduled | 16/10/2023 | 20/10/2023
TO-23-CHA-MAL-1-03 | 110kV FEEDER - CHARLEVILLE 110-MALLOW 110-1 | 5 | 5 | 5 | Scheduled | 16/10/2023 | 20/10/2023
TO-23-220 kV A1 @ TB-01 | BUSBAR SECTION - TARBERT 220-TARBERT 220-220A1 | 2 | 2 | 2 | Scheduled | 16/10/2023 | 17/10/2023
TO-23-DRU-CAP2-03 | CAPACITOR/SVC/REACTOR - DRUMLINE 110-DRUMLINE 110-CAP2 | 5 | 5 | 5 | Scheduled | 23/10/2023 | 27/10/2023
TO-23-MP GIS-110SA1-2CB-02 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 110-MONEYPOINT GIS 110-110SA1-2CB | 4 | 4 | 4 | Scheduled | 23/10/2023 | 26/10/2023
TO-23-MP GIS-ST101-03 | GENERATOR TRANSFORMER - MONEYPOINT GIS 110-MONEYPOINT GIS 10-ST101 | 4 | 4 | 4 | Scheduled | 23/10/2023 | 26/10/2023
TO-23-MP GIS-T121-03 | GENERATOR TRANSFORMER - MONEYPOINT GIS 110-MONEYPOINT GIS 20-T121 | 5 | 5 | 5 | Scheduled | 23/10/2023 | 27/10/2023
TO-23-MP GIS-T2102-02 | TRANSFORMER - MONEYPOINT GIS 220-MONEYPOINT GIS 110-T2102 | 4 | 4 | 4 | Scheduled | 23/10/2023 | 26/10/2023
TO-23-TBK,T-MP GIS-1-03 | 110kV FEEDER - TULLABRACK tee-MONEYPOINT GIS 110-1 | 4 | 4 | 4 | Scheduled | 23/10/2023 | 26/10/2023
TO-23-AGL-ENN-1-04 | 110kV FEEDER - AGANNYGAL 110-ENNIS 110-1 | 11 | 9 | 9 | Scheduled | 31/10/2023 | 10/11/2023
TO-23-KPG-MP GIS-1-01 | 220kV FEEDER - KILPADDOGE 220-MONEYPOINT GIS 220-1 | 4 | 4 | 4 | Scheduled | 31/10/2023 | 03/11/2023
TO-23-220 kV A1 @ MP GIS-01 | BUSBAR SECTION - MONEYPOINT GIS 220-MONEYPOINT GIS 220-220A1 | 4 | 4 | 4 | Scheduled | 31/10/2023 | 03/11/2023
TO-23-MP GIS-220K1-01 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 220-MONEYPOINT GIS 220-220K1 | 4 | 4 | 4 | Scheduled | 31/10/2023 | 03/11/2023
TO-23-MP GIS-220SA1-2CB-02 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 220-MONEYPOINT GIS 220-220SA1-2CB | 4 | 4 | 4 | Scheduled | 31/10/2023 | 03/11/2023
TO-23-KLN-KRA-1-03 | 220kV FEEDER - KILLONAN 220-KNOCKRAHA 220-1 | 1 | 1 |  | Scheduled | 02/11/2023 | 02/11/2023
TO-23-BVK-T2101-02 | TRANSFORMER - BALLYVOUSKILL 220-BALLYVOUSKILL 110-T2101 | 15 | 11 | 11 | Scheduled | 03/11/2023 | 17/11/2023
TO-23-BYH-T2101-03 | TRANSFORMER - BALLYNAHULLA 220-BALLYNAHULLA 110-T2101 | 5 | 5 | 5 | Scheduled | 06/11/2023 | 10/11/2023
TO-23-110 kV A1 @ KLN-03 | BUSBAR SECTION - KILLONAN 110-KILLONAN 110-110A1 | 4 | 4 | 4 | Scheduled | 06/11/2023 | 09/11/2023
TO-23-110 kV A2 @ KLN-02 | BUSBAR SECTION - KILLONAN 110-KILLONAN 110-110A2 | 4 | 4 | 4 | Scheduled | 06/11/2023 | 09/11/2023
TO-23-110 kV B1 @ KLN-03 | BUSBAR SECTION - KILLONAN 110-KILLONAN 110-110B1 | 4 | 4 | 4 | Scheduled | 06/11/2023 | 09/11/2023
TO-23-110 kV B2 @ KLN-02 | BUSBAR SECTION - KILLONAN 110-KILLONAN 110-110B2 | 4 | 4 | 4 | Scheduled | 06/11/2023 | 09/11/2023
TO-23-KLN-110K1-2-01 | COUPLER/SECTIONALISING CB - KILLONAN 110-KILLONAN 110-110K1-2 | 8 | 6 | 6 | Scheduled | 06/11/2023 | 13/11/2023
TO-23-220 kV A4 @ KPG-05 | BUSBAR SECTION - KILPADDOGE 220-KILPADDOGE 220-220A4 | 5 | 5 | 5 | Scheduled | 06/11/2023 | 10/11/2023
TO-23-220 kV B4 @ KPG-05 | BUSBAR SECTION - KILPADDOGE 220-KILPADDOGE 220-220B4 | 5 | 5 | 5 | Scheduled | 06/11/2023 | 10/11/2023
TO-23-KPG-220K4-05 | COUPLER/SECTIONALISING CB - KILPADDOGE 220-KILPADDOGE 220-220K4 | 5 | 5 | 5 | Scheduled | 06/11/2023 | 10/11/2023
TO-23-KPG-220SA2-4CB-05 | COUPLER/SECTIONALISING CB - KILPADDOGE 220-KILPADDOGE 220-220SA2-4CB | 5 | 5 | 5 | Scheduled | 06/11/2023 | 10/11/2023
TO-23-KPG-220SB2-4CB-06 | COUPLER/SECTIONALISING CB - KILPADDOGE 220-KILPADDOGE 220-220SB2-4CB | 5 | 5 | 5 | Scheduled | 06/11/2023 | 10/11/2023
TO-23-KPG-MP GIS-2-01 | 220kV FEEDER - KILPADDOGE 220-MONEYPOINT GIS 220-2 | 5 | 5 |  | Scheduled | 06/11/2023 | 10/11/2023
TO-23-AA GIS-ENN-1-04 | 110kV FEEDER - ARDNACRUSHA GIS 110-ENNIS 110-1 | 5 | 5 | 5 | Scheduled | 13/11/2023 | 17/11/2023
TO-23-SK-T103-03 | GENERATOR TRANSFORMER - SEALROCK 110-SEALROCK G3-T103 | 2 | 2 | 2 | Scheduled | 13/11/2023 | 14/11/2023
TO-23-110 kV A2 @ BYH-02 | BUSBAR SECTION - BALLYNAHULLA 110-BALLYNAHULLA 110-110A2 | 2 | 2 | 2 | Scheduled | 14/11/2023 | 15/11/2023
TO-23-110 kV B2 @ BYH-02 | BUSBAR SECTION - BALLYNAHULLA 110-BALLYNAHULLA 110-110B2 | 2 | 2 | 2 | Scheduled | 14/11/2023 | 15/11/2023
TO-23-BYH-110K2-03 | COUPLER/SECTIONALISING CB - BALLYNAHULLA 110-BALLYNAHULLA 110-110K2 | 2 | 2 | 2 | Scheduled | 14/11/2023 | 15/11/2023
TO-23-BYH-110SA1-2CB-02 | COUPLER/SECTIONALISING CB - BALLYNAHULLA 110-BALLYNAHULLA 110-110SA1-2CB | 2 | 2 | 2 | Scheduled | 14/11/2023 | 15/11/2023
TO-23-BYH-110SB1-2CB-02 | COUPLER/SECTIONALISING CB - BALLYNAHULLA 110-BALLYNAHULLA 110-110SB1-2CB | 2 | 2 | 2 | Scheduled | 14/11/2023 | 15/11/2023
TO-23-BYH-T2102-01 | TRANSFORMER - BALLYNAHULLA 220-BALLYNAHULLA 110-T2102 | 2 | 2 | 2 | Scheduled | 14/11/2023 | 15/11/2023
TO-23-BVK-R2001-01 | CAPACITOR/SVC/REACTOR - BALLYVOUSKILL 220-BALLYVOUSKILL 220-R2001 | 3 | 3 | 3 | Scheduled | 20/11/2023 | 22/11/2023
TO-23-CHA-MAL-1-01 | 110kV FEEDER - CHARLEVILLE 110-MALLOW 110-1 | 10 | 8 | 8 | Scheduled | 20/11/2023 | 29/11/2023
TO-23-KPG-TRL-1-04 | 110kV FEEDER - KILPADDOGE 110-TRALEE 110-1 | 4 | 4 | 4 | Scheduled | 20/11/2023 | 23/11/2023
TO-23-KNR-T2101-01 | TRANSFORMER - KNOCKANURE 220-KNOCKANURE 110-T2101 | 2 | 2 | 2 | Scheduled | 20/11/2023 | 21/11/2023
TO-23-BYH-T132-01 | CAPACITOR/SVC/REACTOR - BALLYNAHULLA 110-BALLYNAHULLA 110-T132 | 3 | 3 | 3 | Scheduled | 21/11/2023 | 23/11/2023
TO-23-KNR-TRI-1-02 | 110kV FEEDER - KNOCKANURE 110-TRIEN 110-1 | 2 | 2 | 2 | Scheduled | 22/11/2023 | 23/11/2023
TO-23-KPG-TB-2-01 | 220kV FEEDER - KILPADDOGE 220-TARBERT 220-2 | 3 | 3 | 3 | Proposed | 27/11/2023 | 29/11/2023
TO-23-KNR-T2102-01 | TRANSFORMER - KNOCKANURE 220-KNOCKANURE 110-T2102 | 4 | 4 | 4 | Proposed | 27/11/2023 | 30/11/2023
TO-23-BYH-T132-02 | CAPACITOR/SVC/REACTOR - BALLYNAHULLA 110-BALLYNAHULLA 110-T132 | 3 | 3 | 3 | Scheduled | 28/11/2023 | 30/11/2023
TO-23-KLN-NEN-1-02 | 110kV FEEDER - KILLONAN 110-NENAGH 110-1 | 2 | 2 | 2 | Reference (Proposed) | 30/11/2023 | 01/12/2023
TO-23-NEN-T141-02 | DISTRIBUTION TRANSFORMER - NENAGH 110-NENAGH 38-T141 | 2 | 2 | 2 | Reference (Proposed) | 30/11/2023 | 01/12/2023

## GEN_SouthEast
Outage ID | Feeder ID | Calendar Day Duration | Working Day Duration | Work Days | Outage Status | Start | Finish
TO-23-ARK-BOG-1-01 | 110kV FEEDER - ARKLOW 110-BANOGE 110-1 | 3 | 3 | 3 | Scheduled | 27/02/2023 | 01/03/2023
TO-23-BDA-MON-1-01 | 110kV FEEDER - BARODA 110-MONREAD 110-1 | 12 | 10 | 10 | Scheduled | 27/02/2023 | 10/03/2023
TO-23-BUT-KTN-1-03 | 110kV FEEDER - BUTLERSTOWN 110-KILLOTERAN 110-1 | 5 | 5 | 5 | Scheduled | 27/02/2023 | 03/03/2023
TO-23-GI-KKY-1-01 | 110kV FEEDER - GREAT ISLAND 110-KILKENNY 110-1 | 2 | 2 | 2 | Scheduled | 27/02/2023 | 28/02/2023
TO-23-110 kV A1/A2 @ CAH-01 | BUSBAR SECTION - CAHIR 110-CAHIR 110-110A1-A2 | 1 | 1 | 1 | Scheduled | 01/03/2023 | 01/03/2023
TO-23-110 kV B1/B2 @ CAH-01 | BUSBAR SECTION - CAHIR 110-CAHIR 110-110B1-B2 | 1 | 1 | 1 | Scheduled | 01/03/2023 | 01/03/2023
TO-23-KLS-KKY-1-01 | 110kV FEEDER - KELLIS 110-KILKENNY 110-1 | 59 | 40 |  | Scheduled | 01/03/2023 | 28/04/2023
TO-23-KKY-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - KILKENNY 110-KILKENNY 110-110SA1-2CB | 59 | 40 |  | Scheduled | 01/03/2023 | 28/04/2023
TO-23-KKY-T141-01 | DISTRIBUTION TRANSFORMER - KILKENNY 110-KILKENNY 38-T141 | 59 | 40 |  | Reference | 01/03/2023 | 28/04/2023
TO-23-CRA-LWD-1-01 | 110kV FEEDER - CRANE 110-LODGEWOOD 110-1 | 5 | 5 |  | Scheduled | 06/03/2023 | 10/03/2023
TO-23-CUS-MLC-1-01 | 110kV FEEDER - CUSHALING 110-MOUNTLUCAS 110-1 | 12 | 9 | 9 | Scheduled | 13/03/2023 | 24/03/2023
TO-23-BOG-110SA1-01 | SECTIONALISING DISCONNECT - BANOGE 110-BANOGE 110-110SA1 | 5 | 5 | 5 | Scheduled | 20/03/2023 | 24/03/2023
TO-23-BOG-110SA2-02 | SECTIONALISING DISCONNECT - BANOGE 110-BANOGE 110-110SA2 | 5 | 5 | 5 | Scheduled | 20/03/2023 | 24/03/2023
TO-23-BOG-CRA-1-02 | 110kV FEEDER - BANOGE 110-CRANE 110-1 | 5 | 5 | 5 | Scheduled | 20/03/2023 | 24/03/2023
TO-23-BOG-T121-01 | DISTRIBUTION TRANSFORMER - BANOGE 110-BANOGE 20-T121 | 5 | 5 | 5 | Reference | 20/03/2023 | 24/03/2023
TO-23-CUL-WAT-1-02 | 110kV FEEDER - CULLENAGH 110-WATERFORD 110-1 | 3 | 3 | 3 | Scheduled | 21/03/2023 | 23/03/2023
TO-23-110 kV A2 @ GI-02 | BUSBAR SECTION - GREAT ISLAND 110-GREAT ISLAND 110-110A2 | 5 | 5 | 5 | Scheduled | 27/03/2023 | 31/03/2023
TO-23-110 kV B2 @ GI-02 | BUSBAR SECTION - GREAT ISLAND 110-GREAT ISLAND 110-110B2 | 5 | 5 | 5 | Scheduled | 27/03/2023 | 31/03/2023
TO-23-GI-ROP-1-01 | 110kV FEEDER - GREAT ISLAND 110-ROSSPILE 110-1 | 5 | 5 | 5 | Scheduled | 27/03/2023 | 31/03/2023
TO-23-KTN-WAT-1-01 | 110kV FEEDER - KILLOTERAN 110-WATERFORD 110-1 | 5 | 5 |  | Scheduled | 27/03/2023 | 31/03/2023
TO-23-220 kV A1/A2 @ ARK-01 | BUSBAR SECTION - ARKLOW 220-ARKLOW 220-220A1-A2 | 1 | 1 | 1 | Scheduled | 29/03/2023 | 29/03/2023
TO-23-220 kV B1/B2 @ ARK-01 | BUSBAR SECTION - ARKLOW 220-ARKLOW 220-220B1-B2 | 1 | 1 | 1 | Scheduled | 29/03/2023 | 29/03/2023
TO-23-GI-WAT-2-01 | 110kV FEEDER - GREAT ISLAND 110-WATERFORD 110-2 | 4 | 4 | 4 | Scheduled | 03/04/2023 | 06/04/2023
TO-23-KTN-WAT-1-04 | 110kV FEEDER - KILLOTERAN 110-WATERFORD 110-1 | 4 | 4 | 4 | Scheduled | 03/04/2023 | 06/04/2023
TO-23-WAT-110SA1-01 | SECTIONALISING DISCONNECT - WATERFORD 110-WATERFORD 110-110SA1 | 4 | 4 |  | Scheduled | 03/04/2023 | 06/04/2023
TO-23-WAT-110SA2-01 | SECTIONALISING DISCONNECT - WATERFORD 110-WATERFORD 110-110SA2 | 4 | 4 | 4 | Scheduled | 03/04/2023 | 06/04/2023
TO-23-WAT-T141-02 | DISTRIBUTION TRANSFORMER - WATERFORD 110-WATERFORD 38-T141 | 4 | 4 | 4 | Reference | 03/04/2023 | 06/04/2023
TO-23-ARK-T2101-01 | TRANSFORMER - ARKLOW 220-ARKLOW 110-T2101 | 2 | 2 |  | Scheduled | 04/04/2023 | 05/04/2023
TO-23-LWD-T2102-01 | TRANSFORMER - LODGEWOOD 220-LODGEWOOD 110-T2102 | 11 | 9 | 9 | Scheduled | 11/04/2023 | 21/04/2023
TO-23-ARK-LWD-1-01 | 220kV FEEDER - ARKLOW 220-LODGEWOOD 220-1 | 4 | 4 | 4 | Scheduled | 24/04/2023 | 27/04/2023
TO-23-DEY-PLS-1-01 | 110kV FEEDER - DERRYCARNEY 110-PORTLAOISE 110-1 | 5 | 5 |  | Scheduled | 24/04/2023 | 28/04/2023
TO-23-110 kV A2 @ PLS-01 | BUSBAR SECTION - PORTLAOISE 110-PORTLAOISE 110-110A2 | 5 | 5 | 5 | Scheduled | 24/04/2023 | 28/04/2023
TO-23-110 kV B2 @ PLS-01 | BUSBAR SECTION - PORTLAOISE 110-PORTLAOISE 110-110B2 | 5 | 5 | 5 | Scheduled | 24/04/2023 | 28/04/2023
TO-23-BDN-T141-01 | DISTRIBUTION TRANSFORMER - BALLYDINE 110-BALLYDINE 38-T141 | 72 | 50 |  | Reference | 27/04/2023 | 07/07/2023
TO-23-ARK-T2102-01 | TRANSFORMER - ARKLOW 220-ARKLOW 110-T2102 | 2 | 2 | 2 | Scheduled | 02/05/2023 | 03/05/2023
TO-23-ARK-T101-01 | DISTRIBUTION TRANSFORMER - ARKLOW 110-ARKLOW 10-T101 | 2 | 2 |  | Reference (Proposed) | 04/05/2023 | 05/05/2023
TO-23-CUL-DGN-1-01 | 110kV FEEDER - CULLENAGH 110-DUNGARVAN 110-1 | 43 | 30 | 30 | Scheduled | 08/05/2023 | 19/06/2023
TO-23-WEX-CAP2-01 | CAPACITOR/SVC/REACTOR - WEXFORD 110-WEXFORD 110-CAP2 | 5 | 5 | 5 | Scheduled | 08/05/2023 | 12/05/2023
TO-23-WEX-CAP4-01 | CAPACITOR/SVC/REACTOR - WEXFORD 110-WEXFORD 110-CAP4 | 5 | 5 | 5 | Scheduled | 08/05/2023 | 12/05/2023
TO-23-WOH-T122-01 | GENERATOR TRANSFORMER - WOODHOUSE 110-WOODHOUSE 20-T122 | 19 | 15 | 15 | Scheduled | 08/05/2023 | 26/05/2023
TO-23-GI-WAT-1-01 | 110kV FEEDER - GREAT ISLAND 110-WATERFORD 110-1 | 4 | 4 | 4 | Scheduled | 23/05/2023 | 26/05/2023
TO-23-110 kV A1 @ CUL-01 | BUSBAR SECTION - CULLENAGH 110-CULLENAGH 110-110A1 | 12 | 7 | 7 | Scheduled | 01/06/2023 | 12/06/2023
TO-23-110 kV B1 @ CUL-01 | BUSBAR SECTION - CULLENAGH 110-CULLENAGH 110-110B1 | 12 | 7 | 7 | Scheduled | 01/06/2023 | 12/06/2023
TO-23-KLS-KKY-1-02 | 110kV FEEDER - KELLIS 110-KILKENNY 110-1 | 67 | 48 | 48 | Scheduled | 06/06/2023 | 11/08/2023
TO-23-KKY-110SA1-2CB-02 | COUPLER/SECTIONALISING CB - KILKENNY 110-KILKENNY 110-110SA1-2CB | 67 | 48 | 48 | Scheduled | 06/06/2023 | 11/08/2023
TO-23-KKY-T141-02 | DISTRIBUTION TRANSFORMER - KILKENNY 110-KILKENNY 38-T141 | 67 | 48 | 48 | Reference | 06/06/2023 | 11/08/2023
TO-23-110 kV A1 @ CAH-01 | BUSBAR SECTION - CAHIR 110-CAHIR 110-110A1 | 2 | 2 | 2 | Scheduled | 07/06/2023 | 08/06/2023
TO-23-110 kV A2 @ CAH-01 | BUSBAR SECTION - CAHIR 110-CAHIR 110-110A2 | 2 | 2 | 2 | Scheduled | 07/06/2023 | 08/06/2023
TO-23-CAH-110K1-2-03 | COUPLER/SECTIONALISING CB - CAHIR 110-CAHIR 110-110K1-2 | 2 | 2 | 2 | Scheduled | 07/06/2023 | 08/06/2023
TO-23-STR-T141-01 | DISTRIBUTION TRANSFORMER - STRATFORD 110-STRATFORD 38-T141 | 17 | 13 | 13 | Reference | 07/06/2023 | 23/06/2023
TO-23-STR,T-CLW-1-01 | 110kV FEEDER - STRATFORD tee-CARLOW 110-1 | 17 | 13 | 13 | Scheduled | 07/06/2023 | 23/06/2023
TO-23-STR,T-PA-1-03 | 110kV FEEDER - STRATFORD tee-POLLAPHUCA 110-1 | 17 | 13 | 13 | Scheduled | 07/06/2023 | 23/06/2023
TO-23-STR,T-STR-1-01 | 110kV FEEDER - STRATFORD tee-STRATFORD 110-1 | 17 | 13 | 13 | Scheduled | 07/06/2023 | 23/06/2023
TO-23-ANR-DOO-1-03 | 110kV FEEDER - ANNER 110-DOON 110-1 | 2 | 2 | 2 | Scheduled | 13/06/2023 | 14/06/2023
TO-23-ANR-T101-02 | TSO CUSTOMER TRANSFORMER - ANNER 110-ANNER 10-T101 | 2 | 2 | 2 | Reference | 13/06/2023 | 14/06/2023
TO-23-ANR-T103-02 | TSO CUSTOMER TRANSFORMER - ANNER 110-ANNER 10-T103 | 2 | 2 | 2 | Reference | 13/06/2023 | 14/06/2023
TO-23-BDN-110SA1-02 | SECTIONALISING DISCONNECT - BALLYDINE 110-BALLYDINE 110-110SA1 | 11 | 9 | 9 | Scheduled | 26/06/2023 | 06/07/2023
TO-23-BDN-110SA2-05 | SECTIONALISING DISCONNECT - BALLYDINE 110-BALLYDINE 110-110SA2 | 11 | 9 | 9 | Scheduled | 26/06/2023 | 06/07/2023
TO-23-BDN-CUL-1-04 | 110kV FEEDER - BALLYDINE 110-CULLENAGH 110-1 | 11 | 9 | 9 | Scheduled | 26/06/2023 | 06/07/2023
TO-23-BDN-MRK1-01 | TSO CUSTOMER TRANSFORMER - BALLYDINE 110-BALLYDINE 10-MRK1 | 124 | 89 | 89 | Scheduled | 26/06/2023 | 27/10/2023
TO-23-NEW-PLS-1-01 | 110kV FEEDER - NEWBRIDGE 110-PORTLAOISE 110-1 | 12 | 10 | 10 | Scheduled | 03/07/2023 | 14/07/2023
TO-23-BDN-110SA1-03 | SECTIONALISING DISCONNECT - BALLYDINE 110-BALLYDINE 110-110SA1 | 1 | 1 | 1 | Scheduled | 07/07/2023 | 07/07/2023
TO-23-BDN-110SA2-04 | SECTIONALISING DISCONNECT - BALLYDINE 110-BALLYDINE 110-110SA2 | 1 | 1 | 1 | Scheduled | 07/07/2023 | 07/07/2023
TO-23-BDN-CUL-1-02 | 110kV FEEDER - BALLYDINE 110-CULLENAGH 110-1 | 1 | 1 | 1 | Scheduled | 07/07/2023 | 07/07/2023
TO-23-110 kV A2 @ ARK-01 | BUSBAR SECTION - ARKLOW 110-ARKLOW 110-110A2 | 10 | 8 | 8 | Scheduled | 10/07/2023 | 19/07/2023
TO-23-110 kV B2 @ ARK-01 | BUSBAR SECTION - ARKLOW 110-ARKLOW 110-110B2 | 10 | 8 | 8 | Scheduled | 10/07/2023 | 19/07/2023
TO-23-ARK-BEG-1-01 | 110kV FEEDER - ARKLOW 110-BALLYBEG 110-1 | 10 | 8 | 8 | Scheduled | 10/07/2023 | 19/07/2023
TO-23-BDN-CUL-1-01 | 110kV FEEDER - BALLYDINE 110-CULLENAGH 110-1 | 44 | 31 | 31 | Scheduled | 10/07/2023 | 22/08/2023
TO-23-110 kV A2 @ CUL-01 | BUSBAR SECTION - CULLENAGH 110-CULLENAGH 110-110A2 | 12 | 10 | 10 | Scheduled | 10/07/2023 | 21/07/2023
TO-23-110 kV B2 @ CUL-01 | BUSBAR SECTION - CULLENAGH 110-CULLENAGH 110-110B2 | 12 | 10 | 10 | Scheduled | 10/07/2023 | 21/07/2023
TO-23-CUS-NEW-1-01 | 110kV FEEDER - CUSHALING 110-NEWBRIDGE 110-1 | 12 | 10 | 10 | Scheduled | 10/07/2023 | 21/07/2023
TO-23-NEW-110SA1-01 | SECTIONALISING DISCONNECT - NEWBRIDGE 110-NEWBRIDGE 110-110SA1 | 5 | 5 | 5 | Scheduled | 10/07/2023 | 14/07/2023
TO-23-NEW-110SA2-03 | SECTIONALISING DISCONNECT - NEWBRIDGE 110-NEWBRIDGE 110-110SA2 | 5 | 5 | 5 | Scheduled | 10/07/2023 | 14/07/2023
TO-23-NEW-T141-01 | DISTRIBUTION TRANSFORMER - NEWBRIDGE 110-NEWBRIDGE 38-T141 | 5 | 5 | 5 | Reference | 10/07/2023 | 14/07/2023
TO-23-BEG-110SA1-01 | SECTIONALISING DISCONNECT - BALLYBEG 110-BALLYBEG 110-110SA1 | 3 | 3 | 3 | Scheduled | 11/07/2023 | 13/07/2023
TO-23-BEG-110SA2-01 | SECTIONALISING DISCONNECT - BALLYBEG 110-BALLYBEG 110-110SA2 | 3 | 3 | 3 | Scheduled | 11/07/2023 | 13/07/2023
TO-23-BEG-T101-01 | DISTRIBUTION TRANSFORMER - BALLYBEG 110-BALLYBEG 10-T101 | 3 | 3 | 3 | Reference | 11/07/2023 | 13/07/2023
TO-23-KIR-T131-02 | GENERATOR TRANSFORMER - KILCUMBER 110-KILCUMBER 33-T131 | 1 | 1 | 1 | Scheduled | 26/07/2023 | 26/07/2023
TO-23-BUT-T141-02 | DISTRIBUTION TRANSFORMER - BUTLERSTOWN 110-BUTLERSTOWN 38-T141 | 106 | 74 | 74 | Reference | 31/07/2023 | 13/11/2023
TO-23-ROP-WEX-1-01 | 110kV FEEDER - ROSSPILE 110-WEXFORD 110-1 | 14 | 9 | 9 | Scheduled | 01/08/2023 | 14/08/2023
TO-23-CUS-PLS-1-02 | 110kV FEEDER - CUSHALING 110-PORTLAOISE 110-1 | 14 | 10 |  | Scheduled | 08/08/2023 | 21/08/2023
TO-23-110 kV A2 @ PLS-02 | BUSBAR SECTION - PORTLAOISE 110-PORTLAOISE 110-110A2 | 14 | 10 | 10 | Scheduled | 08/08/2023 | 21/08/2023
TO-23-110 kV B2 @ PLS-02 | BUSBAR SECTION - PORTLAOISE 110-PORTLAOISE 110-110B2 | 14 | 10 | 10 | Scheduled | 08/08/2023 | 21/08/2023
TO-23-CUS-T101-01 | GENERATOR TRANSFORMER - CUSHALING 110-CUSHALING G1-T101 | 9 | 7 | 7 | Scheduled | 10/08/2023 | 18/08/2023
TO-23-BEG-CKM GIS-1-01 | 110kV FEEDER - BALLYBEG 110-CARRICKMINES GIS 110-1 | 8 | 6 | 6 | Scheduled | 15/08/2023 | 22/08/2023
TO-23-CUS-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - CUSHALING 110-CUSHALING 110-110SA1-2CB | 4 | 4 | 4 | Scheduled | 15/08/2023 | 18/08/2023
TO-23-CUS-KIR-1-02 | 110kV FEEDER - CUSHALING 110-KILCUMBER 110-1 | 4 | 4 | 4 | Scheduled | 15/08/2023 | 18/08/2023
TO-23-CUS-MLC-1-04 | 110kV FEEDER - CUSHALING 110-MOUNTLUCAS 110-1 | 4 | 4 | 4 | Scheduled | 15/08/2023 | 18/08/2023
TO-23-KIR-T131-03 | GENERATOR TRANSFORMER - KILCUMBER 110-KILCUMBER 33-T131 | 4 | 4 | 4 | Scheduled | 15/08/2023 | 18/08/2023
TO-23-DSN-KLS-1-05 | 220kV FEEDER - DUNSTOWN 220-KELLIS 220-1 | 2 | 0 | 0 | Scheduled | 19/08/2023 | 20/08/2023
TO-23-KLS-T2101-04 | TRANSFORMER - KELLIS 220-KELLIS 110-T2101 | 2 | 0 | 0 | Scheduled | 19/08/2023 | 20/08/2023
TO-23-BOG-CRA-1-01 | 110kV FEEDER - BANOGE 110-CRANE 110-1 | 113 | 80 |  | Scheduled | 21/08/2023 | 11/12/2023
TO-23-ATY-PLS-1-03 | 110kV FEEDER - ATHY 110-PORTLAOISE 110-1 | 3 | 3 | 3 | Scheduled | 22/08/2023 | 24/08/2023
TO-23-BDN-110SA1-04 | SECTIONALISING DISCONNECT - BALLYDINE 110-BALLYDINE 110-110SA1 | 1 | 1 | 1 | Scheduled | 22/08/2023 | 22/08/2023
TO-23-BDN-110SA2-01 | SECTIONALISING DISCONNECT - BALLYDINE 110-BALLYDINE 110-110SA2 | 1 | 1 |  | Scheduled | 22/08/2023 | 22/08/2023
TO-23-BDN-T141-03 | DISTRIBUTION TRANSFORMER - BALLYDINE 110-BALLYDINE 38-T141 | 1 | 1 | 1 | Reference | 22/08/2023 | 22/08/2023
TO-23-DOO-T142-02 | DISTRIBUTION TRANSFORMER - DOON 110-DOON 38-T142 | 80 | 57 | 57 | Reference | 23/08/2023 | 10/11/2023
TO-23-CLW-KLS-2-06 | 110kV FEEDER - CARLOW 110-KELLIS 110-2 | 1 | 1 | 1 | Scheduled | 25/08/2023 | 25/08/2023
TO-23-DSN-KLS-1-06 | 220kV FEEDER - DUNSTOWN 220-KELLIS 220-1 | 2 | 0 | 0 | Scheduled | 26/08/2023 | 27/08/2023
TO-23-KLS-T2101-05 | TRANSFORMER - KELLIS 220-KELLIS 110-T2101 | 2 | 0 | 0 | Scheduled | 26/08/2023 | 27/08/2023
TO-23-110 kV A2 @ KLS-05 | BUSBAR SECTION - KELLIS 110-KELLIS 110-110A2 | 12 | 10 | 10 | Scheduled | 28/08/2023 | 08/09/2023
TO-23-110 kV B2 @ KLS-05 | BUSBAR SECTION - KELLIS 110-KELLIS 110-110B2 | 12 | 10 | 10 | Scheduled | 28/08/2023 | 08/09/2023
TO-23-KLS-T2102-01 | TRANSFORMER - KELLIS 220-KELLIS 110-T2102 | 12 | 10 |  | Scheduled | 28/08/2023 | 08/09/2023
TO-23-BUT-CUL-1-02 | 110kV FEEDER - BUTLERSTOWN 110-CULLENAGH 110-1 | 77 | 54 | 54 | Scheduled | 29/08/2023 | 13/11/2023
TO-23-BDA-T102-01 | TSO CUSTOMER TRANSFORMER - BARODA 110-BARODA 10-T102 | 5 | 5 |  | Scheduled | 11/09/2023 | 15/09/2023
TO-23-220 kV A1 @ GI GIS-02 | BUSBAR SECTION - GREAT ISLAND GIS 220-GREAT ISLAND GIS 220-220A1 | 5 | 5 | 5 | Scheduled | 18/09/2023 | 22/09/2023
TO-23-220 kV A2 @ GI GIS-02 | BUSBAR SECTION - GREAT ISLAND GIS 220-GREAT ISLAND GIS 220-220A2 | 5 | 5 | 5 | Scheduled | 18/09/2023 | 22/09/2023
TO-23-GI GIS-220SA1-2CB-01 | COUPLER/SECTIONALISING CB - GREAT ISLAND GIS 220-GREAT ISLAND GIS 220-220SA1-2CB | 5 | 5 |  | Scheduled | 18/09/2023 | 22/09/2023
TO-23-110 kV A1 @ KLS-03 | BUSBAR SECTION - KELLIS 110-KELLIS 110-110A1 | 12 | 10 | 10 | Scheduled | 18/09/2023 | 29/09/2023
TO-23-110 kV A2 @ KLS-04 | BUSBAR SECTION - KELLIS 110-KELLIS 110-110A2 | 12 | 10 | 10 | Scheduled | 18/09/2023 | 29/09/2023
TO-23-110 kV B1 @ KLS-03 | BUSBAR SECTION - KELLIS 110-KELLIS 110-110B1 | 12 | 10 | 10 | Scheduled | 18/09/2023 | 29/09/2023
TO-23-110 kV B2 @ KLS-04 | BUSBAR SECTION - KELLIS 110-KELLIS 110-110B2 | 12 | 10 | 10 | Scheduled | 18/09/2023 | 29/09/2023
TO-23-KLS-110K1-2-02 | COUPLER/SECTIONALISING CB - KELLIS 110-KELLIS 110-110K1-2 | 12 | 10 | 10 | Scheduled | 18/09/2023 | 29/09/2023
TO-23-CAH-KHL-1-01 | 110kV FEEDER - CAHIR 110-KILL HILL 110-1 | 3 | 3 | 3 | Scheduled | 25/09/2023 | 27/09/2023
TO-23-NEW-PLS-1-04 | 110kV FEEDER - NEWBRIDGE 110-PORTLAOISE 110-1 | 1 | 1 | 1 | Scheduled | 25/09/2023 | 25/09/2023
TO-23-ATY-CLW-1-04 | 110kV FEEDER - ATHY 110-CARLOW 110-1 | 11 | 9 | 9 | Scheduled | 26/09/2023 | 06/10/2023
TO-23-CAH-TIP-1-01 | 110kV FEEDER - CAHIR 110-TIPPERARY 110-1 | 2 | 2 | 2 | Scheduled | 28/09/2023 | 29/09/2023
TO-23-KLS-KKY-1-05 | 110kV FEEDER - KELLIS 110-KILKENNY 110-1 | 2 | 2 | 2 | Scheduled | 28/09/2023 | 29/09/2023
TO-23-KKY-110SA1-2CB-03 | COUPLER/SECTIONALISING CB - KILKENNY 110-KILKENNY 110-110SA1-2CB | 2 | 2 | 2 | Scheduled | 28/09/2023 | 29/09/2023
TO-23-KKY-T141-04 | DISTRIBUTION TRANSFORMER - KILKENNY 110-KILKENNY 38-T141 | 2 | 2 | 2 | Reference | 28/09/2023 | 29/09/2023
TO-23-CUS-T103/5-01 | GENERATOR TRANSFORMER - CUSHALING 110-CUSHALING G3/5-T103/5 | 1 | 1 | 1 | Scheduled | 06/10/2023 | 06/10/2023
TO-23-DSN-KLS-1-07 | 220kV FEEDER - DUNSTOWN 220-KELLIS 220-1 | 1 | 0 | 0 | Proposed | 07/10/2023 | 07/10/2023
TO-23-KLS-220K1-2-05 | COUPLER/SECTIONALISING CB - KELLIS 220-KELLIS 220-220K1-2 | 1 | 0 | 0 | Proposed | 07/10/2023 | 07/10/2023
TO-23-KLS-T2101-06 | TRANSFORMER - KELLIS 220-KELLIS 110-T2101 | 1 | 0 | 0 | Proposed | 07/10/2023 | 07/10/2023
TO-23-ATY-T101-01 | DISTRIBUTION TRANSFORMER - ATHY 110-ATHY 10-T101 | 4 | 4 | 4 | Reference | 09/10/2023 | 12/10/2023
TO-23-BLK-T142-03 | DISTRIBUTION TRANSFORMER - BLAKE 110-BLAKE 38-T142 | 19 | 15 | 15 | Reference | 09/10/2023 | 27/10/2023
TO-23-BLK,T-BLK-1-03 | 110kV FEEDER - BLAKE tee-BLAKE 110-1 | 19 | 15 | 15 | Scheduled | 09/10/2023 | 27/10/2023
TO-23-BLK,T-NEW-1-01 | 110kV FEEDER - BLAKE tee-NEWBRIDGE 110-1 | 19 | 15 | 15 | Scheduled | 09/10/2023 | 27/10/2023
TO-23-ROP-T131-01 | GENERATOR TRANSFORMER - ROSSPILE 110-ROSSPILE 33-T131 | 2 | 2 | 2 | Scheduled | 10/10/2023 | 11/10/2023
TO-23-KLS-T2101-03 | TRANSFORMER - KELLIS 220-KELLIS 110-T2101 | 33 | 24 | 24 | Scheduled | 16/10/2023 | 17/11/2023
TO-23-MAY-SH-1-01 | 220kV FEEDER - MAYNOOTH 220-SHANNONBRIDGE 220-1 | 53 | 38 | 38 | Scheduled | 16/10/2023 | 07/12/2023
TO-23-CAH-DOO-1-04 | 110kV FEEDER - CAHIR 110-DOON 110-1 | 1 | 1 | 1 | Scheduled | 23/10/2023 | 23/10/2023
TO-23-DOO-110SA1-04 | SECTIONALISING DISCONNECT - DOON 110-DOON 110-110SA1 | 1 | 1 | 1 | Scheduled | 23/10/2023 | 23/10/2023
TO-23-DOO-110SA2-04 | SECTIONALISING DISCONNECT - DOON 110-DOON 110-110SA2 | 1 | 1 | 1 | Scheduled | 23/10/2023 | 23/10/2023
TO-23-BDA-T101-01 | TSO CUSTOMER TRANSFORMER - BARODA 110-BARODA 10-T101 | 3 | 3 | 3 | Scheduled | 24/10/2023 | 26/10/2023
TO-23-BWR-T124-01 | GENERATOR TRANSFORMER - BALLYWATER 110-BALLYWATER 20-T124 | 1 | 1 | 1 | Reference (Proposed) | 25/10/2023 | 25/10/2023
TO-23-220 kV B1 @ GI GIS-02 | BUSBAR SECTION - GREAT ISLAND GIS 220-GREAT ISLAND GIS 220-220B1 | 5 | 5 | 5 | Scheduled | 06/11/2023 | 10/11/2023
TO-23-220 kV B2 @ GI GIS-03 | BUSBAR SECTION - GREAT ISLAND GIS 220-GREAT ISLAND GIS 220-220B2 | 5 | 5 | 5 | Scheduled | 06/11/2023 | 10/11/2023
TO-23-GI GIS-220SB1-2CB-01 | COUPLER/SECTIONALISING CB - GREAT ISLAND GIS 220-GREAT ISLAND GIS 220-220SB1-2CB | 5 | 5 |  | Scheduled | 06/11/2023 | 10/11/2023
TO-23-CAH-DOO-1-01 | 110kV FEEDER - CAHIR 110-DOON 110-1 | 1 | 1 | 1 | Scheduled | 10/11/2023 | 10/11/2023
TO-23-DOO-110SA1-03 | SECTIONALISING DISCONNECT - DOON 110-DOON 110-110SA1 | 1 | 1 | 1 | Scheduled | 10/11/2023 | 10/11/2023
TO-23-DOO-110SA2-03 | SECTIONALISING DISCONNECT - DOON 110-DOON 110-110SA2 | 1 | 1 | 1 | Scheduled | 10/11/2023 | 10/11/2023
TO-23-BWR-T124-02 | GENERATOR TRANSFORMER - BALLYWATER 110-BALLYWATER 20-T124 | 1 | 1 |  | Reference | 13/11/2023 | 13/11/2023
TO-23-BDA-MON-1-02 | 110kV FEEDER - BARODA 110-MONREAD 110-1 | 10 | 8 | 8 | Scheduled | 13/11/2023 | 22/11/2023
TO-23-BUT-110SA1-01 | SECTIONALISING DISCONNECT - BUTLERSTOWN 110-BUTLERSTOWN 110-110SA1 | 1 | 1 | 1 | Scheduled | 13/11/2023 | 13/11/2023
TO-23-BUT-110SA2-01 | SECTIONALISING DISCONNECT - BUTLERSTOWN 110-BUTLERSTOWN 110-110SA2 | 1 | 1 | 1 | Scheduled | 13/11/2023 | 13/11/2023
TO-23-KIR-T131-04 | GENERATOR TRANSFORMER - KILCUMBER 110-KILCUMBER 33-T131 | 1 | 1 | 1 | Scheduled | 16/11/2023 | 16/11/2023
TO-23-GI-WAT-1-04 | 110kV FEEDER - GREAT ISLAND 110-WATERFORD 110-1 | 2 | 0 | 0 | Scheduled | 25/11/2023 | 26/11/2023
TO-23-GI-WAT-2-02 | 110kV FEEDER - GREAT ISLAND 110-WATERFORD 110-2 | 5 | 3 |  | Scheduled | 25/11/2023 | 29/11/2023
TO-23-CUS-MLC-1-02 | 110kV FEEDER - CUSHALING 110-MOUNTLUCAS 110-1 | 1 | 1 | 1 | Proposed | 27/11/2023 | 27/11/2023
TO-23-110 kV A1 @ PLS-01 | BUSBAR SECTION - PORTLAOISE 110-PORTLAOISE 110-110A1 | 4 | 4 | 4 | Scheduled | 27/11/2023 | 30/11/2023
TO-23-110 kV A2 @ PLS-03 | BUSBAR SECTION - PORTLAOISE 110-PORTLAOISE 110-110A2 | 4 | 4 | 4 | Scheduled | 27/11/2023 | 30/11/2023
TO-23-110 kV B1 @ PLS-01 | BUSBAR SECTION - PORTLAOISE 110-PORTLAOISE 110-110B1 | 4 | 4 | 4 | Scheduled | 27/11/2023 | 30/11/2023
TO-23-110 kV B2 @ PLS-03 | BUSBAR SECTION - PORTLAOISE 110-PORTLAOISE 110-110B2 | 4 | 4 | 4 | Scheduled | 27/11/2023 | 30/11/2023
TO-23-PLS-110K1-2-01 | COUPLER/SECTIONALISING CB - PORTLAOISE 110-PORTLAOISE 110-110K1-2 | 4 | 4 | 4 | Scheduled | 27/11/2023 | 30/11/2023

## GEN_NorthWest
Outage ID | Feeder ID | Calendar Day Duration | Working Day Duration | Work Days | Outage Status | Start | Finish
TO-23-SLI-T142-01 | DISTRIBUTION TRANSFORMER - SLIGO 110-SLIGO 38-T142 | 82 | 58 | 58 | Reference | 09/01/2023 | 31/03/2023
TO-23-CSH-GAL-3-02 | 110kV FEEDER - CASHLA 110-GALWAY 110-3 | 88 | 60 | 61 | Scheduled | 27/02/2023 | 25/05/2023
TO-23-GAL-110K2-3-02 | COUPLER/SECTIONALISING CB - GALWAY 110-GALWAY 110-110K2-3 | 308 | 211 | 211 | Scheduled | 27/02/2023 | 31/12/2023
TO-23-GAL-T142-02 | DISTRIBUTION TRANSFORMER - GALWAY 110-GALWAY 38-T142 | 95 | 65 | 65 | Reference | 27/02/2023 | 01/06/2023
TO-23-ARV-COS-1-01 | 110kV FEEDER - ARVA 110-CARRICK ON SHANNON 110-1 | 8 | 6 | 6 | Scheduled | 06/03/2023 | 13/03/2023
TO-23-COS-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - CARRICK ON SHANNON 110-CARRICK ON SHANNON 110-110SA1-2CB | 3 | 3 | 3 | Scheduled | 06/03/2023 | 08/03/2023
TO-23-COS-FLA-1-01 | 110kV FEEDER - CARRICK ON SHANNON 110-FLAGFORD 110-1 | 3 | 3 | 3 | Scheduled | 06/03/2023 | 08/03/2023
TO-23-COS-T141-01 | DISTRIBUTION TRANSFORMER - CARRICK ON SHANNON 110-CARRICK ON SHANNON 38-T141 | 3 | 3 | 3 | Reference | 06/03/2023 | 08/03/2023
TO-23-CBR-DLT-1-01 | 110kV FEEDER - CASTLEBAR 110-DALTON 110-1 | 5 | 5 | 5 | Scheduled | 06/03/2023 | 10/03/2023
TO-23-110 kV A2 @ SRA-01 | BUSBAR SECTION - SRANANAGH 110-SRANANAGH 110-110A2 | 5 | 5 | 5 | Scheduled | 06/03/2023 | 10/03/2023
TO-23-110 kV B2 @ SRA-01 | BUSBAR SECTION - SRANANAGH 110-SRANANAGH 110-110B2 | 5 | 5 | 5 | Scheduled | 06/03/2023 | 10/03/2023
TO-23-110 kV A1/A2 @ KNY-01 | BUSBAR SECTION - KNOCKRANNY 110-KNOCKRANNY 110-110A1-A2 | 1 | 1 | 1 | Scheduled | 08/03/2023 | 08/03/2023
TO-23-110 kV B1/B2 @ KNY-01 | BUSBAR SECTION - KNOCKRANNY 110-KNOCKRANNY 110-110B1-B2 | 1 | 1 | 1 | Scheduled | 08/03/2023 | 08/03/2023
TO-23-BIN-TIV-1-01 | 110kV FEEDER - BINBANE 110-TIEVEBRACK 110-1 | 2 | 2 | 2 | Scheduled | 14/03/2023 | 15/03/2023
TO-23-CLN-LA-1-03 | 110kV FEEDER - CLOON 110-LANESBORO 110-1 | 8 | 5 | 5 | Scheduled | 14/03/2023 | 21/03/2023
TO-23-GOL-T101-01 | GENERATOR TRANSFORMER - GOLAGH 110-GOLAGH 10-T101 | 5 | 5 | 5 | Scheduled | 20/03/2023 | 24/03/2023
TO-23-GOL,T-CLO-1-01 | 110kV FEEDER - GOLAGH tee-CLOGHER 110-1 | 5 | 5 | 5 | Scheduled | 20/03/2023 | 24/03/2023
TO-23-GOL,T-GOL-1-01 | 110kV FEEDER - GOLAGH tee-GOLAGH 110-1 | 5 | 5 | 5 | Scheduled | 20/03/2023 | 24/03/2023
TO-23-GOL,T-LET-1-01 | 110kV FEEDER - GOLAGH tee-LETTERKENNY 110-1 | 5 | 5 | 5 | Scheduled | 20/03/2023 | 24/03/2023
TO-23-SLI-SRA-2-01 | 110kV FEEDER - SLIGO 110-SRANANAGH 110-2 | 5 | 5 | 5 | Scheduled | 20/03/2023 | 24/03/2023
TO-23-110 kV A2 @ KNY-01 | BUSBAR SECTION - KNOCKRANNY 110-KNOCKRANNY 110-110A2 | 8 | 6 | 6 | Scheduled | 23/03/2023 | 30/03/2023
TO-23-110 kV B2 @ KNY-01 | BUSBAR SECTION - KNOCKRANNY 110-KNOCKRANNY 110-110B2 | 8 | 6 | 6 | Scheduled | 23/03/2023 | 30/03/2023
TO-23-KNY-110K2-01 | COUPLER/SECTIONALISING CB - KNOCKRANNY 110-KNOCKRANNY 110-110K2 | 8 | 6 | 6 | Scheduled | 23/03/2023 | 30/03/2023
TO-23-KNY-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - KNOCKRANNY 110-KNOCKRANNY 110-110SA1-2CB | 8 | 6 | 6 | Scheduled | 23/03/2023 | 30/03/2023
TO-23-KNY-110SB1-2CB-01 | COUPLER/SECTIONALISING CB - KNOCKRANNY 110-KNOCKRANNY 110-110SB1-2CB | 8 | 6 | 6 | Scheduled | 23/03/2023 | 30/03/2023
TO-23-LET-TIV-1-01 | 110kV FEEDER - LETTERKENNY 110-TIEVEBRACK 110-1 | 130 | 90 | 90 | Scheduled | 27/03/2023 | 03/08/2023
TO-23-110 kV A1 @ FLA-01 | BUSBAR SECTION - FLAGFORD 110-FLAGFORD 110-110A1 | 2 | 2 | 2 | Scheduled | 29/03/2023 | 30/03/2023
TO-23-110 kV B1 @ FLA-01 | BUSBAR SECTION - FLAGFORD 110-FLAGFORD 110-110B1 | 2 | 2 | 2 | Scheduled | 29/03/2023 | 30/03/2023
TO-23-220 kV B1 @ FLA-02 | BUSBAR SECTION - FLAGFORD 220-FLAGFORD 220-220B1 | 2 | 2 | 2 | Scheduled | 29/03/2023 | 30/03/2023
TO-23-FLA-T2101-01 | TRANSFORMER - FLAGFORD 220-FLAGFORD 110-T2101 | 109 | 74 |  | Scheduled | 29/03/2023 | 15/07/2023
TO-23-CUN-SLI-1-01 | 110kV FEEDER - CUNGHILL 110-SLIGO 110-1 | 1 | 1 | 1 | Scheduled | 31/03/2023 | 31/03/2023
TO-23-FLA-SLI-1-03 | 110kV FEEDER - FLAGFORD 110-SLIGO 110-1 | 1 | 1 | 1 | Scheduled | 31/03/2023 | 31/03/2023
TO-23-SLI-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - SLIGO 110-SLIGO 110-110SA1-2CB | 1 | 1 | 1 | Scheduled | 31/03/2023 | 31/03/2023
TO-23-SLI-SRA-2-02 | 110kV FEEDER - SLIGO 110-SRANANAGH 110-2 | 1 | 1 | 1 | Scheduled | 31/03/2023 | 31/03/2023
TO-23-FLA-LOU-1-08 | 220kV FEEDER - FLAGFORD 220-LOUTH 220-1 | 2 | 0 | 0 | Scheduled | 15/04/2023 | 16/04/2023
TO-23-CBR-SVC-01 | CAPACITOR/SVC/REACTOR - CASTLEBAR 110-CASTLEBAR 110-SVC | 5 | 5 | 5 | Scheduled | 17/04/2023 | 21/04/2023
TO-23-CL-T102-01 | GENERATOR TRANSFORMER - CLIFF 110-CLIFF G2-T102 | 19 | 14 | 14 | Scheduled | 17/04/2023 | 05/05/2023
TO-23-BK-110SA1-03 | SECTIONALISING DISCONNECT - BELLACORICK 110-BELLACORICK 110-110SA1 | 12 | 9 | 9 | Scheduled | 24/04/2023 | 05/05/2023
TO-23-BK-110SA2-03 | SECTIONALISING DISCONNECT - BELLACORICK 110-BELLACORICK 110-110SA2 | 12 | 9 | 9 | Scheduled | 24/04/2023 | 05/05/2023
TO-23-BK-MOY-1-01 | 110kV FEEDER - BELLACORICK 110-MOY 110-1 | 12 | 9 | 9 | Scheduled | 24/04/2023 | 05/05/2023
TO-23-BK-T141-02 | DISTRIBUTION TRANSFORMER - BELLACORICK 110-BELLACORICK 38-T141 | 12 | 9 | 9 | Reference | 24/04/2023 | 05/05/2023
TO-23-CSH-220K2-4-01 | COUPLER/SECTIONALISING CB - CASHLA 220-CASHLA 220-220K2-4 | 44 | 30 |  | Scheduled | 01/05/2023 | 13/06/2023
TO-23-MOY-TAW-2-01 | 110kV FEEDER - MOY 110-TAWNAGHMORE 110-2 | 2 | 2 | 2 | Scheduled | 02/05/2023 | 03/05/2023
TO-23-110 kV A2 @ KNY-02 | BUSBAR SECTION - KNOCKRANNY 110-KNOCKRANNY 110-110A2 | 2 | 2 | 2 | Scheduled | 03/05/2023 | 04/05/2023
TO-23-110 kV B2 @ KNY-02 | BUSBAR SECTION - KNOCKRANNY 110-KNOCKRANNY 110-110B2 | 2 | 2 | 2 | Scheduled | 03/05/2023 | 04/05/2023
TO-23-KNY-110K2-02 | COUPLER/SECTIONALISING CB - KNOCKRANNY 110-KNOCKRANNY 110-110K2 | 2 | 2 | 2 | Scheduled | 03/05/2023 | 04/05/2023
TO-23-KNY-110SA1-2CB-02 | COUPLER/SECTIONALISING CB - KNOCKRANNY 110-KNOCKRANNY 110-110SA1-2CB | 2 | 2 | 2 | Scheduled | 03/05/2023 | 04/05/2023
TO-23-KNY-110SB1-2CB-02 | COUPLER/SECTIONALISING CB - KNOCKRANNY 110-KNOCKRANNY 110-110SB1-2CB | 2 | 2 | 2 | Scheduled | 03/05/2023 | 04/05/2023
TO-23-KNY-SAL-1-02 | 110kV FEEDER - KNOCKRANNY 110-SALTHILL 110-1 | 2 | 2 | 2 | Scheduled | 03/05/2023 | 04/05/2023
TO-23-MOY-TAW-1-01 | 110kV FEEDER - MOY 110-TAWNAGHMORE 110-1 | 2 | 2 | 2 | Scheduled | 04/05/2023 | 05/05/2023
TO-23-110 kV A2 @ CSH-05 | BUSBAR SECTION - CASHLA 110-CASHLA 110-110A2 | 5 | 5 | 5 | Scheduled | 08/05/2023 | 12/05/2023
TO-23-110 kV B2 @ CSH-06 | BUSBAR SECTION - CASHLA 110-CASHLA 110-110B2 | 5 | 5 | 5 | Scheduled | 08/05/2023 | 12/05/2023
TO-23-220 kV A2 @ CSH-01 | BUSBAR SECTION - CASHLA 220-CASHLA 220-220A2 | 5 | 5 | 5 | Scheduled | 08/05/2023 | 12/05/2023
TO-23-220 kV A4 @ CSH-01 | BUSBAR SECTION - CASHLA 220-CASHLA 220-220A4 | 5 | 5 | 5 | Scheduled | 08/05/2023 | 12/05/2023
TO-23-CF-T104-01 | GENERATOR TRANSFORMER - CATHALEENS FALL 110-CATHALEENS FALL G4-T104 | 10 | 8 | 8 | Scheduled | 08/05/2023 | 17/05/2023
TO-23-DYN-T121-01 | GENERATOR TRANSFORMER - DERRYBRIEN 110-DERRYBRIEN 20-T121 | 5 | 5 | 5 | Reference | 08/05/2023 | 12/05/2023
TO-23-110 kV A2 @ GAL GIS-03 | BUSBAR SECTION - GALWAY GIS 110-GALWAY GIS 110-110A2 | 5 | 5 | 5 | Scheduled | 15/05/2023 | 19/05/2023
TO-23-110 kV B2 @ GAL GIS-03 | BUSBAR SECTION - GALWAY GIS 110-GALWAY GIS 110-110B2 | 5 | 5 | 5 | Scheduled | 15/05/2023 | 19/05/2023
TO-23-GAL GIS-110K2-02 | COUPLER/SECTIONALISING CB - GALWAY GIS 110-GALWAY GIS 110-110K2 | 5 | 5 | 5 | Scheduled | 15/05/2023 | 19/05/2023
TO-23-GAL GIS-110SA1-2CB-03 | COUPLER/SECTIONALISING CB - GALWAY GIS 110-GALWAY GIS 110-110SA1-2CB | 5 | 5 | 5 | Scheduled | 15/05/2023 | 19/05/2023
TO-23-GAL GIS-110SB1-2CB-03 | COUPLER/SECTIONALISING CB - GALWAY GIS 110-GALWAY GIS 110-110SB1-2CB | 5 | 5 | 5 | Scheduled | 15/05/2023 | 19/05/2023
TO-23-GAL-GAL GIS-1-02 | 110kV FEEDER - GALWAY 110-GALWAY GIS 110-1 | 2 | 2 | 2 | Scheduled | 24/05/2023 | 25/05/2023
TO-23-110 kV A2 @ GAL GIS-02 | BUSBAR SECTION - GALWAY GIS 110-GALWAY GIS 110-110A2 | 2 | 2 | 2 | Scheduled | 24/05/2023 | 25/05/2023
TO-23-110 kV B2 @ GAL GIS-02 | BUSBAR SECTION - GALWAY GIS 110-GALWAY GIS 110-110B2 | 2 | 2 | 2 | Scheduled | 24/05/2023 | 25/05/2023
TO-23-GAL GIS-110K2-03 | COUPLER/SECTIONALISING CB - GALWAY GIS 110-GALWAY GIS 110-110K2 | 2 | 2 | 2 | Scheduled | 24/05/2023 | 25/05/2023
TO-23-GAL GIS-110SA1-2CB-04 | COUPLER/SECTIONALISING CB - GALWAY GIS 110-GALWAY GIS 110-110SA1-2CB | 2 | 2 | 2 | Scheduled | 24/05/2023 | 25/05/2023
TO-23-GAL GIS-110SB1-2CB-04 | COUPLER/SECTIONALISING CB - GALWAY GIS 110-GALWAY GIS 110-110SB1-2CB | 2 | 2 | 2 | Scheduled | 24/05/2023 | 25/05/2023
TO-23-110 kV B1 @ CF-01 | BUSBAR SECTION - CATHALEENS FALL 110-CATHALEENS FALL 110-110B1 | 1 | 1 | 1 | Scheduled | 25/05/2023 | 25/05/2023
TO-23-CF-T103-02 | GENERATOR TRANSFORMER - CATHALEENS FALL 110-CATHALEENS FALL G3-T103 | 1 | 1 | 1 | Scheduled | 25/05/2023 | 25/05/2023
TO-23-CSH-GAL-2-02 | 110kV FEEDER - CASHLA 110-GALWAY 110-2 | 86 | 60 |  | Scheduled | 29/05/2023 | 22/08/2023
TO-23-GAL-GAL GIS-1-01 | 110kV FEEDER - GALWAY 110-GALWAY GIS 110-1 | 2 | 2 | 2 | Scheduled | 31/05/2023 | 01/06/2023
TO-23-110 kV A2 @ GAL GIS-01 | BUSBAR SECTION - GALWAY GIS 110-GALWAY GIS 110-110A2 | 2 | 2 | 2 | Scheduled | 31/05/2023 | 01/06/2023
TO-23-110 kV B2 @ GAL GIS-01 | BUSBAR SECTION - GALWAY GIS 110-GALWAY GIS 110-110B2 | 2 | 2 | 2 | Scheduled | 31/05/2023 | 01/06/2023
TO-23-GAL GIS-110K2-01 | COUPLER/SECTIONALISING CB - GALWAY GIS 110-GALWAY GIS 110-110K2 | 2 | 2 | 2 | Scheduled | 31/05/2023 | 01/06/2023
TO-23-GAL GIS-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - GALWAY GIS 110-GALWAY GIS 110-110SA1-2CB | 2 | 2 | 2 | Scheduled | 31/05/2023 | 01/06/2023
TO-23-GAL GIS-110SB1-2CB-01 | COUPLER/SECTIONALISING CB - GALWAY GIS 110-GALWAY GIS 110-110SB1-2CB | 2 | 2 | 2 | Scheduled | 31/05/2023 | 01/06/2023
TO-23-110 kV A2 @ CSH-01 | BUSBAR SECTION - CASHLA 110-CASHLA 110-110A2 | 71 | 50 |  | Scheduled | 13/06/2023 | 22/08/2023
TO-23-110 kV B2 @ CSH-02 | BUSBAR SECTION - CASHLA 110-CASHLA 110-110B2 | 71 | 50 |  | Scheduled | 13/06/2023 | 22/08/2023
TO-23-110 kV A1 @ FLA-02 | BUSBAR SECTION - FLAGFORD 110-FLAGFORD 110-110A1 | 2 | 2 | 2 | Scheduled | 15/06/2023 | 16/06/2023
TO-23-110 kV B1 @ FLA-02 | BUSBAR SECTION - FLAGFORD 110-FLAGFORD 110-110B1 | 2 | 2 | 2 | Scheduled | 15/06/2023 | 16/06/2023
TO-23-BK-SKY-1-01 | 110kV FEEDER - BELLACORICK 110-SRAHNAKILLY 110-1 | 26 | 20 | 20 | Scheduled | 19/06/2023 | 14/07/2023
TO-23-SKY-110SA1-01 | SECTIONALISING DISCONNECT - SRAHNAKILLY 110-SRAHNAKILLY 110-110SA1 | 26 | 20 | 20 | Scheduled | 19/06/2023 | 14/07/2023
TO-23-SKY-110SA2-01 | SECTIONALISING DISCONNECT - SRAHNAKILLY 110-SRAHNAKILLY 110-110SA2 | 26 | 20 | 20 | Scheduled | 19/06/2023 | 14/07/2023
TO-23-SKY-T131-01 | GENERATOR TRANSFORMER - SRAHNAKILLY 110-SRAHNAKILLY 33-T131 | 26 | 20 | 20 | Scheduled | 19/06/2023 | 14/07/2023
TO-23-SKY-T132-01 | GENERATOR TRANSFORMER - SRAHNAKILLY 110-SRAHNAKILLY 33-T132 | 26 | 20 | 20 | Scheduled | 19/06/2023 | 14/07/2023
TO-23-220 kV B1 @ FLA-03 | BUSBAR SECTION - FLAGFORD 220-FLAGFORD 220-220B1 | 2 | 2 | 2 | Scheduled | 22/06/2023 | 23/06/2023
TO-23-CF-T103-01 | GENERATOR TRANSFORMER - CATHALEENS FALL 110-CATHALEENS FALL G3-T103 | 5 | 5 | 5 | Scheduled | 26/06/2023 | 30/06/2023
TO-23-CL-T102-02 | GENERATOR TRANSFORMER - CLIFF 110-CLIFF G2-T102 | 12 | 10 | 10 | Scheduled | 26/06/2023 | 07/07/2023
TO-23-110 kV A2 @ FLA-01 | BUSBAR SECTION - FLAGFORD 110-FLAGFORD 110-110A2 | 2 | 2 | 2 | Scheduled | 26/06/2023 | 27/06/2023
TO-23-110 kV B2 @ FLA-01 | BUSBAR SECTION - FLAGFORD 110-FLAGFORD 110-110B2 | 2 | 2 | 2 | Scheduled | 26/06/2023 | 27/06/2023
TO-23-FLA-SLI-1-01 | 110kV FEEDER - FLAGFORD 110-SLIGO 110-1 | 87 | 62 | 62 | Scheduled | 26/06/2023 | 20/09/2023
TO-23-110 kV A1 @ FLA-05 | BUSBAR SECTION - FLAGFORD 110-FLAGFORD 110-110A1 | 13 | 9 | 9 | Scheduled | 28/06/2023 | 10/07/2023
TO-23-110 kV B1 @ FLA-05 | BUSBAR SECTION - FLAGFORD 110-FLAGFORD 110-110B1 | 13 | 9 | 9 | Scheduled | 28/06/2023 | 10/07/2023
TO-23-220 kV A1 @ FLA-03 | BUSBAR SECTION - FLAGFORD 220-FLAGFORD 220-220A1 | 13 | 9 | 9 | Scheduled | 28/06/2023 | 10/07/2023
TO-23-220 kV B1 @ FLA-05 | BUSBAR SECTION - FLAGFORD 220-FLAGFORD 220-220B1 | 13 | 9 | 9 | Scheduled | 28/06/2023 | 10/07/2023
TO-23-UGL-T132-01 | GENERATOR TRANSFORMER - UGGOOL 110-UGGOOL 33-T132 | 8 | 6 | 6 | Scheduled | 10/07/2023 | 17/07/2023
TO-23-UGL-T134-01 | GENERATOR TRANSFORMER - UGGOOL 110-UGGOOL 33-T134 | 8 | 6 | 6 | Scheduled | 10/07/2023 | 17/07/2023
TO-23-UGL-110SA1-2CB-03 | COUPLER/SECTIONALISING CB - UGGOOL 110-UGGOOL 110-110SA1-2CB | 4 | 4 | 4 | Scheduled | 11/07/2023 | 14/07/2023
TO-23-220 kV B1/B2 @ FLA-02 | BUSBAR SECTION - FLAGFORD 220-FLAGFORD 220-220B1-B2 | 1 | 0 | 0 | Scheduled | 15/07/2023 | 15/07/2023
TO-23-FLA-LOU-1-03 | 220kV FEEDER - FLAGFORD 220-LOUTH 220-1 | 1 | 0 | 0 | Scheduled | 15/07/2023 | 15/07/2023
TO-23-CDY-GRV-1-01 | 110kV FEEDER - CORDERRY 110-GARVAGH 110-1 | 5 | 5 | 5 | Scheduled | 17/07/2023 | 21/07/2023
TO-23-GRV-110K1-01 | COUPLER/SECTIONALISING CB - GARVAGH 110-GARVAGH 110-110K1 | 5 | 5 | 5 | Scheduled | 17/07/2023 | 21/07/2023
TO-23-GRV-T121-01 | GENERATOR TRANSFORMER - GARVAGH 110-GARVAGH 20-T121 | 5 | 5 | 5 | Scheduled | 17/07/2023 | 21/07/2023
TO-23-GRV-T141-01 | DISTRIBUTION TRANSFORMER - GARVAGH 110-GARVAGH 20-T141 | 5 | 5 | 5 | Reference | 17/07/2023 | 21/07/2023
TO-23-UGL-T131-01 | GENERATOR TRANSFORMER - UGGOOL 110-UGGOOL 33-T131 | 5 | 5 | 5 | Scheduled | 17/07/2023 | 21/07/2023
TO-23-CUN-T121-01 | GENERATOR TRANSFORMER - CUNGHILL 110-CUNGHILL 20-T121 | 3 | 3 | 3 | Scheduled | 24/07/2023 | 26/07/2023
TO-23-KLH-T121-01 | GENERATOR TRANSFORMER - KNOCKALOUGH 110-KNOCKALOUGH 20-T121 | 3 | 3 | 3 | Scheduled | 26/07/2023 | 28/07/2023
TO-23-TIV-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - TIEVEBRACK 110-TIEVEBRACK 110-110SA1-2CB | 2 | 2 | 2 | Scheduled | 02/08/2023 | 03/08/2023
TO-23-BIN-CF-1-01 | 110kV FEEDER - BINBANE 110-CATHALEENS FALL 110-1 | 50 | 35 | 35 | Scheduled | 04/08/2023 | 22/09/2023
TO-23-110 kV A1 @ GAL GIS-03 | BUSBAR SECTION - GALWAY GIS 110-GALWAY GIS 110-110A1 | 5 | 4 | 4 | Scheduled | 08/08/2023 | 12/08/2023
TO-23-110 kV B1 @ GAL GIS-03 | BUSBAR SECTION - GALWAY GIS 110-GALWAY GIS 110-110B1 | 5 | 4 | 4 | Scheduled | 08/08/2023 | 12/08/2023
TO-23-GAL GIS-110SA1-2CB-05 | COUPLER/SECTIONALISING CB - GALWAY GIS 110-GALWAY GIS 110-110SA1-2CB | 5 | 4 | 4 | Scheduled | 08/08/2023 | 12/08/2023
TO-23-GAL GIS-110SA1-3CB-04 | COUPLER/SECTIONALISING CB - GALWAY GIS 110-GALWAY GIS 110-110SA1-3CB | 5 | 4 | 4 | Scheduled | 08/08/2023 | 12/08/2023
TO-23-GAL GIS-110SB1-2CB-05 | COUPLER/SECTIONALISING CB - GALWAY GIS 110-GALWAY GIS 110-110SB1-2CB | 5 | 4 | 4 | Scheduled | 08/08/2023 | 12/08/2023
TO-23-GAL GIS-110SB1-3CB-04 | COUPLER/SECTIONALISING CB - GALWAY GIS 110-GALWAY GIS 110-110SB1-3CB | 5 | 4 | 4 | Scheduled | 08/08/2023 | 12/08/2023
TO-23-220 kV A1 @ CSH-03 | BUSBAR SECTION - CASHLA 220-CASHLA 220-220A1 | 5 | 5 | 5 | Scheduled | 14/08/2023 | 18/08/2023
TO-23-220 kV A2 @ CSH-03 | BUSBAR SECTION - CASHLA 220-CASHLA 220-220A2 | 5 | 5 | 5 | Scheduled | 14/08/2023 | 18/08/2023
TO-23-220 kV B1 @ CSH-01 | BUSBAR SECTION - CASHLA 220-CASHLA 220-220B1 | 5 | 5 | 5 | Scheduled | 14/08/2023 | 18/08/2023
TO-23-220 kV B2 @ CSH-03 | BUSBAR SECTION - CASHLA 220-CASHLA 220-220B2 | 5 | 5 | 5 | Scheduled | 14/08/2023 | 18/08/2023
TO-23-CSH-220K1-2-01 | COUPLER/SECTIONALISING CB - CASHLA 220-CASHLA 220-220K1-2 | 5 | 5 |  | Scheduled | 14/08/2023 | 18/08/2023
TO-23-MEE-T121-01 | GENERATOR TRANSFORMER - MEENTYCAT 110-MEENTYCAT 20-T121 | 4 | 4 | 4 | Scheduled | 14/08/2023 | 17/08/2023
TO-23-FLA-LOU-1-09 | 220kV FEEDER - FLAGFORD 220-LOUTH 220-1 | 3 | 1 |  | Scheduled | 18/08/2023 | 20/08/2023
TO-23-110 kV A1 @ GAL GIS-02 | BUSBAR SECTION - GALWAY GIS 110-GALWAY GIS 110-110A1 | 2 | 2 | 2 | Scheduled | 21/08/2023 | 22/08/2023
TO-23-110 kV B1 @ GAL GIS-02 | BUSBAR SECTION - GALWAY GIS 110-GALWAY GIS 110-110B1 | 2 | 2 | 2 | Scheduled | 21/08/2023 | 22/08/2023
TO-23-GAL GIS-110SA1-2CB-06 | COUPLER/SECTIONALISING CB - GALWAY GIS 110-GALWAY GIS 110-110SA1-2CB | 2 | 2 | 2 | Scheduled | 21/08/2023 | 22/08/2023
TO-23-GAL GIS-110SA1-3CB-02 | COUPLER/SECTIONALISING CB - GALWAY GIS 110-GALWAY GIS 110-110SA1-3CB | 2 | 2 | 2 | Scheduled | 21/08/2023 | 22/08/2023
TO-23-GAL GIS-110SB1-2CB-06 | COUPLER/SECTIONALISING CB - GALWAY GIS 110-GALWAY GIS 110-110SB1-2CB | 2 | 2 | 2 | Scheduled | 21/08/2023 | 22/08/2023
TO-23-GAL GIS-110SB1-2CB-07 | COUPLER/SECTIONALISING CB - GALWAY GIS 110-GALWAY GIS 110-110SB1-2CB | 2 | 2 | 2 | Scheduled | 21/08/2023 | 22/08/2023
TO-23-GAL GIS-110SB1-3CB-02 | COUPLER/SECTIONALISING CB - GALWAY GIS 110-GALWAY GIS 110-110SB1-3CB | 2 | 2 | 2 | Scheduled | 21/08/2023 | 22/08/2023
TO-23-GAL GIS-SAL-1-04 | 110kV FEEDER - GALWAY GIS 110-SALTHILL 110-1 | 2 | 2 |  | Scheduled | 21/08/2023 | 22/08/2023
TO-23-MRY-T131-01 | GENERATOR TRANSFORMER - MULREAVY 110-MULREAVY 33-T131 | 5 | 5 | 5 | Scheduled | 21/08/2023 | 25/08/2023
TO-23-CSH-GAL-1-01 | 110kV FEEDER - CASHLA 110-GALWAY 110-1 | 85 | 60 |  | Scheduled | 25/08/2023 | 17/11/2023
TO-23-TAW-T1/T2-01 | GENERATOR TRANSFORMER - TAWNAGHMORE 110-TAWNAGHMORE 10-T1/T2 | 8 | 6 | 6 | Scheduled | 25/08/2023 | 01/09/2023
TO-23-110 kV A2 @ CSH-02 | BUSBAR SECTION - CASHLA 110-CASHLA 110-110A2 | 4 | 4 |  | Scheduled | 28/08/2023 | 31/08/2023
TO-23-CSH-T2104-01 | TRANSFORMER - CASHLA 220-CASHLA 110-T2104 | 4 | 4 | 4 | Scheduled | 28/08/2023 | 31/08/2023
TO-23-110 kV A2 @ FLA-02 | BUSBAR SECTION - FLAGFORD 110-FLAGFORD 110-110A2 | 3 | 3 | 3 | Scheduled | 30/08/2023 | 01/09/2023
TO-23-110 kV B2 @ FLA-02 | BUSBAR SECTION - FLAGFORD 110-FLAGFORD 110-110B2 | 3 | 3 | 3 | Scheduled | 30/08/2023 | 01/09/2023
TO-23-TAW-T3-01 | GENERATOR TRANSFORMER - TAWNAGHMORE 110-TAWNAGHMORE 10-T3 | 8 | 6 | 6 | Scheduled | 01/09/2023 | 08/09/2023
TO-23-110 kV A2 @ CSH-07 | BUSBAR SECTION - CASHLA 110-CASHLA 110-110A2 | 8 | 6 | 6 | Scheduled | 04/09/2023 | 11/09/2023
TO-23-110 kV B2 @ CSH-08 | BUSBAR SECTION - CASHLA 110-CASHLA 110-110B2 | 8 | 6 | 6 | Scheduled | 04/09/2023 | 11/09/2023
TO-23-CL-T101-01 | GENERATOR TRANSFORMER - CLIFF 110-CLIFF G1-T101 | 5 | 5 | 5 | Scheduled | 04/09/2023 | 08/09/2023
TO-23-MOY-TAW-2-04 | 110kV FEEDER - MOY 110-TAWNAGHMORE 110-2 | 5 | 5 | 5 | Scheduled | 04/09/2023 | 08/09/2023
TO-23-SOM,T-CSH-1-03 | 110kV FEEDER - SOMERSET tee-CASHLA 110-1 | 8 | 6 | 6 | Scheduled | 04/09/2023 | 11/09/2023
TO-23-TAW-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - TAWNAGHMORE 110-TAWNAGHMORE 110-110SA1-2CB | 5 | 5 | 5 | Scheduled | 04/09/2023 | 08/09/2023
TO-23-TAW-T142-01 | DISTRIBUTION TRANSFORMER - TAWNAGHMORE 110-TAWNAGHMORE 38-T142 | 5 | 5 | 5 | Reference | 04/09/2023 | 08/09/2023
TO-23-GLR-MOY-1-01 | 110kV FEEDER - GLENREE 110-MOY 110-1 | 21 | 15 | 15 | Scheduled | 05/09/2023 | 25/09/2023
TO-23-MOY-110SA1-2CB-03 | COUPLER/SECTIONALISING CB - MOY 110-MOY 110-110SA1-2CB | 7 | 5 | 5 | Scheduled | 19/09/2023 | 25/09/2023
TO-23-MOY-CAP1-01 | CAPACITOR/SVC/REACTOR - MOY 110-MOY 110-CAP1 | 7 | 5 | 5 | Scheduled | 19/09/2023 | 25/09/2023
TO-23-MOY-T141-01 | DISTRIBUTION TRANSFORMER - MOY 110-MOY 38-T141 | 7 | 5 | 5 | Reference | 19/09/2023 | 25/09/2023
TO-23-MOY-TAW-1-03 | 110kV FEEDER - MOY 110-TAWNAGHMORE 110-1 | 7 | 5 | 5 | Scheduled | 19/09/2023 | 25/09/2023
TO-23-110 kV B2 @ FLA-03 | BUSBAR SECTION - FLAGFORD 110-FLAGFORD 110-110B2 | 1 | 1 | 1 | Scheduled | 20/09/2023 | 20/09/2023
TO-23-FLA-T2102-03 | TRANSFORMER - FLAGFORD 220-FLAGFORD 110-T2102 | 1 | 1 | 1 | Scheduled | 20/09/2023 | 20/09/2023
TO-23-LET-PST-01 | TRANSFORMER - LETTERKENNY 110-STRABANE 110-PST | 54 | 39 | 39 | Scheduled | 25/09/2023 | 17/11/2023
TO-23-BK-MOY-1-03 | 110kV FEEDER - BELLACORICK 110-MOY 110-1 | 40 | 29 | 29 | Scheduled | 02/10/2023 | 10/11/2023
TO-23-110 kV A2 @ CSH-11 | BUSBAR SECTION - CASHLA 110-CASHLA 110-110A2 | 5 | 5 | 5 | Scheduled | 09/10/2023 | 13/10/2023
TO-23-110 kV B2 @ CSH-12 | BUSBAR SECTION - CASHLA 110-CASHLA 110-110B2 | 5 | 5 | 5 | Scheduled | 09/10/2023 | 13/10/2023
TO-23-CSH-ENN-1-02 | 110kV FEEDER - CASHLA 110-ENNIS 110-1 | 5 | 5 | 5 | Scheduled | 09/10/2023 | 13/10/2023
TO-23-MOY-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - MOY 110-MOY 110-110SA1-2CB | 7 | 5 | 5 | Scheduled | 19/10/2023 | 25/10/2023
TO-23-MOY-CAP2-01 | CAPACITOR/SVC/REACTOR - MOY 110-MOY 110-CAP2 | 7 | 5 | 5 | Scheduled | 19/10/2023 | 25/10/2023
TO-23-MOY-T142-01 | DISTRIBUTION TRANSFORMER - MOY 110-MOY 38-T142 | 7 | 5 | 5 | Reference | 19/10/2023 | 25/10/2023
TO-23-MOY-TAW-2-02 | 110kV FEEDER - MOY 110-TAWNAGHMORE 110-2 | 7 | 5 |  | Scheduled | 19/10/2023 | 25/10/2023
TO-23-LLA-T133-01 | GENERATOR TRANSFORMER - LENALEA 110-LENALEA 33-T133 | 1 | 0 | 0 | Scheduled | 21/10/2023 | 21/10/2023
TO-23-110 kV A2 @ KNY-03 | BUSBAR SECTION - KNOCKRANNY 110-KNOCKRANNY 110-110A2 | 5 | 5 | 5 | Scheduled | 23/10/2023 | 27/10/2023
TO-23-110 kV B2 @ KNY-03 | BUSBAR SECTION - KNOCKRANNY 110-KNOCKRANNY 110-110B2 | 5 | 5 | 5 | Scheduled | 23/10/2023 | 27/10/2023
TO-23-BK-110SA1-01 | SECTIONALISING DISCONNECT - BELLACORICK 110-BELLACORICK 110-110SA1 | 18 | 13 | 20 | Scheduled | 24/10/2023 | 10/11/2023
TO-23-BK-110SA2-01 | SECTIONALISING DISCONNECT - BELLACORICK 110-BELLACORICK 110-110SA2 | 18 | 13 | 13 | Scheduled | 24/10/2023 | 10/11/2023
TO-23-BK-T141-01 | DISTRIBUTION TRANSFORMER - BELLACORICK 110-BELLACORICK 38-T141 | 18 | 13 | 13 | Reference | 24/10/2023 | 10/11/2023
TO-23-DYN-T121-04 | GENERATOR TRANSFORMER - DERRYBRIEN 110-DERRYBRIEN 20-T121 | 2 | 2 | 2 | Reference | 31/10/2023 | 01/11/2023
TO-23-UGL-T132-05 | GENERATOR TRANSFORMER - UGGOOL 110-UGGOOL 33-T132 | 3 | 3 | 3 | Proposed | 31/10/2023 | 02/11/2023
TO-23-110 kV A1 @ CSH-04 | BUSBAR SECTION - CASHLA 110-CASHLA 110-110A1 | 5 | 4 | 4 | Scheduled | 07/11/2023 | 11/11/2023
TO-23-110 kV B1 @ CSH-04 | BUSBAR SECTION - CASHLA 110-CASHLA 110-110B1 | 5 | 4 | 4 | Scheduled | 07/11/2023 | 11/11/2023
TO-23-CSH-CAP1-01 | CAPACITOR/SVC/REACTOR - CASHLA 110-CASHLA 110-CAP1 | 5 | 4 | 4 | Scheduled | 07/11/2023 | 11/11/2023
TO-23-DYN-T121-05 | GENERATOR TRANSFORMER - DERRYBRIEN 110-DERRYBRIEN 20-T121 | 1 | 1 | 1 | Reference | 10/11/2023 | 10/11/2023
TO-23-BK-CBR-1-01 | 110kV FEEDER - BELLACORICK 110-CASTLEBAR 110-1 | 19 | 15 | 15 | Scheduled | 13/11/2023 | 01/12/2023
TO-23-110 kV A1 @ GAL GIS-04 | BUSBAR SECTION - GALWAY GIS 110-GALWAY GIS 110-110A1 | 2 | 2 | 2 | Scheduled | 16/11/2023 | 17/11/2023
TO-23-110 kV A3 @ GAL GIS-01 | BUSBAR SECTION - GALWAY GIS 110-GALWAY GIS 110-110A3 | 2 | 2 |  | Scheduled | 16/11/2023 | 17/11/2023
TO-23-110 kV B1 @ GAL GIS-04 | BUSBAR SECTION - GALWAY GIS 110-GALWAY GIS 110-110B1 | 2 | 2 | 2 | Scheduled | 16/11/2023 | 17/11/2023
TO-23-110 kV B3 @ GAL GIS-01 | BUSBAR SECTION - GALWAY GIS 110-GALWAY GIS 110-110B3 | 2 | 2 |  | Scheduled | 16/11/2023 | 17/11/2023
TO-23-GAL GIS-110K3-01 | COUPLER/SECTIONALISING CB - GALWAY GIS 110-GALWAY GIS 110-110K3 | 2 | 2 |  | Scheduled | 16/11/2023 | 17/11/2023
TO-23-GAL GIS-110SA1-2CB-07 | COUPLER/SECTIONALISING CB - GALWAY GIS 110-GALWAY GIS 110-110SA1-2CB | 2 | 2 | 2 | Scheduled | 16/11/2023 | 17/11/2023
TO-23-GAL GIS-110SA1-3CB-03 | COUPLER/SECTIONALISING CB - GALWAY GIS 110-GALWAY GIS 110-110SA1-3CB | 2 | 2 |  | Scheduled | 16/11/2023 | 17/11/2023
TO-23-GAL GIS-110SB1-2CB-08 | COUPLER/SECTIONALISING CB - GALWAY GIS 110-GALWAY GIS 110-110SB1-2CB | 2 | 2 | 2 | Scheduled | 16/11/2023 | 17/11/2023
TO-23-GAL GIS-110SB1-3CB-03 | COUPLER/SECTIONALISING CB - GALWAY GIS 110-GALWAY GIS 110-110SB1-3CB | 2 | 2 | 2 | Scheduled | 16/11/2023 | 17/11/2023
TO-23-GAL GIS-SAL-1-05 | 110kV FEEDER - GALWAY GIS 110-SALTHILL 110-1 | 2 | 2 | 2 | Scheduled | 16/11/2023 | 17/11/2023
TO-23-BIN-TIV-1-02 | 110kV FEEDER - BINBANE 110-TIEVEBRACK 110-1 | 2 | 2 | 2 | Scheduled | 20/11/2023 | 21/11/2023
TO-23-CDY-SRA-1-01 | 110kV FEEDER - CORDERRY 110-SRANANAGH 110-1 | 1 | 1 |  | Scheduled | 23/11/2023 | 23/11/2023

## GEN_NorthEast
Outage ID | Feeder ID | Calendar Day Duration | Working Day Duration | Work Days | Outage Status | Start | Finish
TO-23-GWE-T101-03 | TSO CUSTOMER TRANSFORMER - GORTAWEE 110-GORTAWEE 10-T101 | 40 | 29 | 29 | Scheduled | 30/01/2023 | 10/03/2023
TO-23-DER-110SA1-01 | SECTIONALISING DISCONNECT - DERRYIRON 110-DERRYIRON 110-110SA1 | 5 | 5 | 5 | Scheduled | 27/02/2023 | 03/03/2023
TO-23-DER-110SA2-01 | SECTIONALISING DISCONNECT - DERRYIRON 110-DERRYIRON 110-110SA2 | 5 | 5 | 5 | Scheduled | 27/02/2023 | 03/03/2023
TO-23-DER-KIN-1-01 | 110kV FEEDER - DERRYIRON 110-KINNEGAD 110-1 | 5 | 5 | 5 | Scheduled | 27/02/2023 | 03/03/2023
TO-23-DDK-MLN-1-02 | 110kV FEEDER - DUNDALK 110-MULLAGHARLIN 110-1 | 10 | 8 | 8 | Scheduled | 27/02/2023 | 08/03/2023
TO-23-GOR-MTH-1-01 | 110kV FEEDER - GORMAN 110-MEATH HILL 110-1 | 68 | 46 | 46 | Scheduled | 27/02/2023 | 05/05/2023
TO-23-KIN-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - KINNEGAD 110-KINNEGAD 110-110SA1-2CB | 5 | 5 | 5 | Scheduled | 27/02/2023 | 03/03/2023
TO-23-KIN-MUL-1-01 | 110kV FEEDER - KINNEGAD 110-MULLINGAR 110-1 | 5 | 5 | 5 | Scheduled | 27/02/2023 | 03/03/2023
TO-23-KIN-T101-01 | TSO CUSTOMER TRANSFORMER - KINNEGAD 110-KINNEGAD 10-T101 | 5 | 5 | 5 | Scheduled | 27/02/2023 | 03/03/2023
TO-23-110 kV A1 @ LOU-03 | BUSBAR SECTION - LOUTH 110-LOUTH 110-110A1 | 12 | 10 | 10 | Scheduled | 27/02/2023 | 10/03/2023
TO-23-110 kV B1 @ LOU-03 | BUSBAR SECTION - LOUTH 110-LOUTH 110-110B1 | 12 | 10 | 10 | Scheduled | 27/02/2023 | 10/03/2023
TO-23-220 kV A1 @ LOU-02 | BUSBAR SECTION - LOUTH 220-LOUTH 220-220A1 | 12 | 10 | 10 | Scheduled | 27/02/2023 | 10/03/2023
TO-23-220 kV B1 @ LOU-01 | BUSBAR SECTION - LOUTH 220-LOUTH 220-220B1 | 12 | 10 | 10 | Scheduled | 27/02/2023 | 10/03/2023
TO-23-LOU-T2101-03 | TRANSFORMER - LOUTH 220-LOUTH 110-T2101 | 12 | 10 | 10 | Scheduled | 27/02/2023 | 10/03/2023
TO-23-110 kV A2 @ ARV-01 | BUSBAR SECTION - ARVA 110-ARVA 110-110A2 | 8 | 6 | 6 | Scheduled | 06/03/2023 | 13/03/2023
TO-23-110 kV B2 @ ARV-01 | BUSBAR SECTION - ARVA 110-ARVA 110-110B2 | 8 | 6 | 6 | Scheduled | 06/03/2023 | 13/03/2023
TO-23-ARV-COS-1-01 | 110kV FEEDER - ARVA 110-CARRICK ON SHANNON 110-1 | 8 | 6 | 6 | Scheduled | 06/03/2023 | 13/03/2023
TO-23-GOR-220K1-2-02 | COUPLER/SECTIONALISING CB - GORMAN 220-GORMAN 220-220K1-2 | 1 | 1 | 1 | Scheduled | 07/03/2023 | 07/03/2023
TO-23-CDU-MUL-1-02 | 110kV FEEDER - CORDUFF 110-MULLINGAR 110-1 | 165 | 113 | 113 | Scheduled | 13/03/2023 | 24/08/2023
TO-23-CUS-MLC-1-01 | 110kV FEEDER - CUSHALING 110-MOUNTLUCAS 110-1 | 12 | 9 | 9 | Scheduled | 13/03/2023 | 24/03/2023
TO-23-LIS-T141-01 | DISTRIBUTION TRANSFORMER - LISDRUM 110-LISDRUM 38-T141 | 130 | 89 | 89 | Reference | 13/03/2023 | 20/07/2023
TO-23-CLN-LA-1-03 | 110kV FEEDER - CLOON 110-LANESBORO 110-1 | 8 | 5 | 5 | Scheduled | 14/03/2023 | 21/03/2023
TO-23-GOR-NAV-1-02 | 110kV FEEDER - GORMAN 110-NAVAN 110-1 | 1 | 1 | 1 | Scheduled | 14/03/2023 | 14/03/2023
TO-23-LOU-AT2-04 | TRANSFORMER - LOUTH 220-LOUTH 275-AT2 | 8 | 5 | 5 | Scheduled | 19/03/2023 | 26/03/2023
TO-23-LOU-TAN-2-04 | 275kV FEEDER - LOUTH 275-TANDRAGEE 275-2 | 8 | 5 | 5 | Scheduled | 19/03/2023 | 26/03/2023
TO-23-COR-GWE-1-03 | 110kV FEEDER - CORRACLASSY 110-GORTAWEE 110-1 | 3 | 3 | 3 | Scheduled | 21/03/2023 | 23/03/2023
TO-23-COR-PST-01 | TRANSFORMER - CORRACLASSY 110-ENNISKILLEN 110-PST | 40 | 27 | 27 | Scheduled | 27/03/2023 | 05/05/2023
TO-23-LIS-LOU-1-04 | 110kV FEEDER - LISDRUM 110-LOUTH 110-1 | 5 | 5 | 5 | Scheduled | 27/03/2023 | 31/03/2023
TO-23-220 kV B1/B2 @ LOU-02 | BUSBAR SECTION - LOUTH 220-LOUTH 220-220B1-B2 | 19 | 13 | 13 | Scheduled | 27/03/2023 | 14/04/2023
TO-23-LOU-220K1-2-01 | COUPLER/SECTIONALISING CB - LOUTH 220-LOUTH 220-220K1-2 | 28 | 18 | 18 | Scheduled | 27/03/2023 | 23/04/2023
TO-23-AGL-ENN-1-01 | 110kV FEEDER - AGANNYGAL 110-ENNIS 110-1 | 3 | 3 | 3 | Scheduled | 28/03/2023 | 30/03/2023
TO-23-110 kV A1 @ SH-03 | BUSBAR SECTION - SHANNONBRIDGE 110-SHANNONBRIDGE 110-110A1 | 125 | 85 | 85 | Scheduled | 29/03/2023 | 31/07/2023
TO-23-110 kV A1 @ SH-05 | BUSBAR SECTION - SHANNONBRIDGE 110-SHANNONBRIDGE 110-110A1 | 262 | 182 | 182 | Scheduled | 29/03/2023 | 15/12/2023
TO-23-110 kV A2 @ SH-04 | BUSBAR SECTION - SHANNONBRIDGE 110-SHANNONBRIDGE 110-110A2 | 125 | 85 | 85 | Scheduled | 29/03/2023 | 31/07/2023
TO-23-110 kV A2 @ SH-03 | BUSBAR SECTION - SHANNONBRIDGE 110-SHANNONBRIDGE 110-110A2 | 262 | 182 | 182 | Scheduled | 29/03/2023 | 15/12/2023
TO-23-110 kV B1 @ SH-07 | BUSBAR SECTION - SHANNONBRIDGE 110-SHANNONBRIDGE 110-110B1 | 125 | 85 | 85 | Scheduled | 29/03/2023 | 31/07/2023
TO-23-110 kV B1 @ SH-02 | BUSBAR SECTION - SHANNONBRIDGE 110-SHANNONBRIDGE 110-110B1 | 262 | 182 | 182 | Scheduled | 29/03/2023 | 15/12/2023
TO-23-110 kV B2 @ SH-02 | BUSBAR SECTION - SHANNONBRIDGE 110-SHANNONBRIDGE 110-110B2 | 262 | 182 | 182 | Scheduled | 29/03/2023 | 15/12/2023
TO-23-110 kV B2 @ SH-03 | BUSBAR SECTION - SHANNONBRIDGE 110-SHANNONBRIDGE 110-110B2 | 125 | 85 | 85 | Scheduled | 29/03/2023 | 31/07/2023
TO-23-SH-T104-02 | GENERATOR TRANSFORMER - SHANNONBRIDGE 110-SHANNONBRIDGE G4-T104 | 7 | 5 | 5 | Scheduled | 29/03/2023 | 04/04/2023
TO-23-FLA-LOU-1-08 | 220kV FEEDER - FLAGFORD 220-LOUTH 220-1 | 2 | 0 | 0 | Scheduled | 15/04/2023 | 16/04/2023
TO-23-GOR-LOU-1-02 | 220kV FEEDER - GORMAN 220-LOUTH 220-1 | 2 | 0 | 0 | Scheduled | 15/04/2023 | 16/04/2023
TO-23-LOU-AT1-02 | TRANSFORMER - LOUTH 220-LOUTH 275-AT1 | 2 | 0 | 0 | Scheduled | 15/04/2023 | 16/04/2023
TO-23-LOU-AT3-02 | TRANSFORMER - LOUTH 220-LOUTH 275-AT3 | 2 | 0 | 0 | Scheduled | 15/04/2023 | 16/04/2023
TO-23-LOU-T2102-06 | TRANSFORMER - LOUTH 220-LOUTH 110-T2102 | 2 | 0 | 0 | Scheduled | 15/04/2023 | 16/04/2023
TO-23-LOU-T2104-04 | TRANSFORMER - LOUTH 220-LOUTH 110-T2104 | 2 | 0 | 0 | Scheduled | 15/04/2023 | 16/04/2023
TO-23-LOU-TAN-1-01 | 275kV FEEDER - LOUTH 275-TANDRAGEE 275-1 | 2 | 0 | 0 | Scheduled | 15/04/2023 | 16/04/2023
TO-23-110 kV A2 @ GOR-01 | BUSBAR SECTION - GORMAN 110-GORMAN 110-110A2 | 5 | 5 | 5 | Scheduled | 17/04/2023 | 21/04/2023
TO-23-110 kV B2 @ GOR-01 | BUSBAR SECTION - GORMAN 110-GORMAN 110-110B2 | 5 | 5 | 5 | Scheduled | 17/04/2023 | 21/04/2023
TO-23-LOU-AT2-02 | TRANSFORMER - LOUTH 220-LOUTH 275-AT2 | 2 | 0 | 0 | Scheduled | 22/04/2023 | 23/04/2023
TO-23-LOU-T2101-01 | TRANSFORMER - LOUTH 220-LOUTH 110-T2101 | 2 | 0 | 0 | Scheduled | 22/04/2023 | 23/04/2023
TO-23-LOU-T2103-02 | TRANSFORMER - LOUTH 220-LOUTH 110-T2103 | 2 | 0 | 0 | Scheduled | 22/04/2023 | 23/04/2023
TO-23-LOU-TAN-2-02 | 275kV FEEDER - LOUTH 275-TANDRAGEE 275-2 | 2 | 0 | 0 | Scheduled | 22/04/2023 | 23/04/2023
TO-23-LOU-WOO-1-01 | 220kV FEEDER - LOUTH 220-WOODLAND 220-1 | 2 | 0 | 0 | Scheduled | 22/04/2023 | 23/04/2023
TO-23-LIS-SKL-1-04 | 110kV FEEDER - LISDRUM 110-SHANKILL 110-1 | 26 | 19 | 19 | Scheduled | 24/04/2023 | 19/05/2023
TO-23-220 kV A1/A2 @ LOU-01 | BUSBAR SECTION - LOUTH 220-LOUTH 220-220A1-A2 | 126 | 87 |  | Scheduled | 24/04/2023 | 27/08/2023
TO-23-DRY-T141-02 | DISTRIBUTION TRANSFORMER - DRYBRIDGE 110-DRYBRIDGE 38-T141 | 112 | 77 | 77 | Reference | 27/04/2023 | 16/08/2023
TO-23-CFN-SH-1-01 | 220kV FEEDER - CLONIFFEEN 220-SHANNONBRIDGE 220-1 | 28 | 20 |  | Scheduled | 02/05/2023 | 29/05/2023
TO-23-CFN-T232-01 | GENERATOR TRANSFORMER - CLONIFFEEN 220-CLONIFFEEN 33-T232 | 28 | 20 |  | Scheduled | 02/05/2023 | 29/05/2023
TO-23-MP GIS-OST-1-01 | 400kV FEEDER - MONEYPOINT GIS 400-OLDSTREET 400-1 | 28 | 20 |  | Scheduled | 02/05/2023 | 29/05/2023
TO-23-AGL-110SA1-01 | SECTIONALISING DISCONNECT - AGANNYGAL 110-AGANNYGAL 110-110SA1 | 5 | 5 | 5 | Scheduled | 08/05/2023 | 12/05/2023
TO-23-AGL-110SA2-01 | SECTIONALISING DISCONNECT - AGANNYGAL 110-AGANNYGAL 110-110SA2 | 5 | 5 | 5 | Scheduled | 08/05/2023 | 12/05/2023
TO-23-AGL-DYN-1-01 | 110kV FEEDER - AGANNYGAL 110-DERRYBRIEN 110-1 | 5 | 5 | 5 | Scheduled | 08/05/2023 | 12/05/2023
TO-23-AGL-ENN-1-02 | 110kV FEEDER - AGANNYGAL 110-ENNIS 110-1 | 5 | 5 | 5 | Scheduled | 08/05/2023 | 12/05/2023
TO-23-AGL-SH-1-03 | 110kV FEEDER - AGANNYGAL 110-SHANNONBRIDGE 110-1 | 5 | 5 | 5 | Scheduled | 08/05/2023 | 12/05/2023
TO-23-ARV-GWE-1-03 | 110kV FEEDER - ARVA 110-GORTAWEE 110-1 | 55 | 39 |  | Scheduled | 08/05/2023 | 01/07/2023
TO-23-DFR-T122-01 | DISTRIBUTION TRANSFORMER - DUNFIRTH 110-DUNFIRTH 20-T122 | 2 | 2 | 2 | Reference | 08/05/2023 | 09/05/2023
TO-23-DFR,T-DFR-1-02 | 110kV FEEDER - DUNFIRTH tee-DUNFIRTH 110-1 | 2 | 2 | 2 | Scheduled | 08/05/2023 | 09/05/2023
TO-23-DFR,T-KIN-1-04 | 110kV FEEDER - DUNFIRTH tee-KINNEGAD 110-1 | 2 | 2 | 2 | Scheduled | 08/05/2023 | 09/05/2023
TO-23-DFR,T-RNW-1-04 | 110kV FEEDER - DUNFIRTH tee-RINAWADE 110-1 | 2 | 2 | 2 | Scheduled | 08/05/2023 | 09/05/2023
TO-23-DFR,T-RNW-1-06 | 110kV FEEDER - DUNFIRTH tee-RINAWADE 110-1 | 16 | 12 | 12 | Scheduled | 10/05/2023 | 25/05/2023
TO-23-GOR-T122-01 | GENERATOR TRANSFORMER - GORMAN 110-GORMAN 20-T122 | 2 | 2 | 2 | Scheduled | 10/05/2023 | 11/05/2023
TO-23-CDU-GLN-1-03 | 110kV FEEDER - CORDUFF 110-GALLANSTOWN 110-1 | 34 | 23 | 23 | Scheduled | 12/05/2023 | 14/06/2023
TO-23-DDK-LOU-1-01 | 110kV FEEDER - DUNDALK 110-LOUTH 110-1 | 146 | 103 |  | Scheduled | 15/05/2023 | 07/10/2023
TO-23-110 kV A2 @ LOU-01 | BUSBAR SECTION - LOUTH 110-LOUTH 110-110A2 | 146 | 103 | 103 | Scheduled | 15/05/2023 | 07/10/2023
TO-23-110 kV B2 @ LOU-01 | BUSBAR SECTION - LOUTH 110-LOUTH 110-110B2 | 146 | 103 | 103 | Scheduled | 15/05/2023 | 07/10/2023
TO-23-LOU-220K1-2-07 | COUPLER/SECTIONALISING CB - LOUTH 220-LOUTH 220-220K1-2 | 3 | 3 | 3 | Scheduled | 15/05/2023 | 17/05/2023
TO-23-110 kV A2 @ MUL-01 | BUSBAR SECTION - MULLINGAR 110-MULLINGAR 110-110A2 | 4 | 4 | 4 | Proposed | 23/05/2023 | 26/05/2023
TO-23-MUL-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - MULLINGAR 110-MULLINGAR 110-110SA1-2CB | 4 | 4 | 4 | Proposed | 23/05/2023 | 26/05/2023
TO-23-MUL-T102-01 | DISTRIBUTION TRANSFORMER - MULLINGAR 110-MULLINGAR 10-T102 | 4 | 4 | 4 | Reference (Proposed) | 23/05/2023 | 26/05/2023
TO-23-MUL-T142-01 | DISTRIBUTION TRANSFORMER - MULLINGAR 110-MULLINGAR 38-T142 | 4 | 4 | 4 | Reference (Proposed) | 23/05/2023 | 26/05/2023
TO-23-DFR-T122-02 | DISTRIBUTION TRANSFORMER - DUNFIRTH 110-DUNFIRTH 20-T122 | 2 | 2 | 2 | Reference | 24/05/2023 | 25/05/2023
TO-23-DFR,T-DFR-1-03 | 110kV FEEDER - DUNFIRTH tee-DUNFIRTH 110-1 | 2 | 2 | 2 | Scheduled | 24/05/2023 | 25/05/2023
TO-23-DFR,T-KIN-1-06 | 110kV FEEDER - DUNFIRTH tee-KINNEGAD 110-1 | 2 | 2 | 2 | Scheduled | 24/05/2023 | 25/05/2023
TO-23-MLC-T121-01 | GENERATOR TRANSFORMER - MOUNTLUCAS 110-MOUNTLUCAS 20-T121 | 1 | 1 | 1 | Scheduled | 24/05/2023 | 24/05/2023
TO-23-CDU-GLN-1-05 | 110kV FEEDER - CORDUFF 110-GALLANSTOWN 110-1 | 31 | 22 | 22 | Scheduled | 15/06/2023 | 15/07/2023
TO-23-OST-WOO-1-02 | 400kV FEEDER - OLDSTREET 400-WOODLAND 400-1 | 16 | 12 | 12 | Scheduled | 15/06/2023 | 30/06/2023
TO-23-LIS-110SA1-05 | SECTIONALISING DISCONNECT - LISDRUM 110-LISDRUM 110-110SA1 | 5 | 5 |  | Scheduled | 19/06/2023 | 23/06/2023
TO-23-LIS-110SA2-05 | SECTIONALISING DISCONNECT - LISDRUM 110-LISDRUM 110-110SA2 | 5 | 5 |  | Scheduled | 19/06/2023 | 23/06/2023
TO-23-LIS-CAP1-03 | CAPACITOR/SVC/REACTOR - LISDRUM 110-LISDRUM 110-CAP1 | 5 | 5 |  | Scheduled | 19/06/2023 | 23/06/2023
TO-23-LIS-LOU-1-02 | 110kV FEEDER - LISDRUM 110-LOUTH 110-1 | 5 | 5 |  | Scheduled | 19/06/2023 | 23/06/2023
TO-23-LIS-T131-04 | GENERATOR TRANSFORMER - LISDRUM 110-LISDRUM 33-T131 | 5 | 5 |  | Scheduled | 19/06/2023 | 23/06/2023
TO-23-LIS-T141-04 | DISTRIBUTION TRANSFORMER - LISDRUM 110-LISDRUM 38-T141 | 5 | 5 |  | Reference | 19/06/2023 | 23/06/2023
TO-23-LOU-T2102-08 | TRANSFORMER - LOUTH 220-LOUTH 110-T2102 | 12 | 10 | 10 | Scheduled | 26/06/2023 | 07/07/2023
TO-23-110 kV A2 @ ARV-02 | BUSBAR SECTION - ARVA 110-ARVA 110-110A2 | 4 | 4 | 4 | Scheduled | 27/06/2023 | 30/06/2023
TO-23-110 kV B2 @ ARV-02 | BUSBAR SECTION - ARVA 110-ARVA 110-110B2 | 4 | 4 | 4 | Scheduled | 27/06/2023 | 30/06/2023
TO-23-ARV-NAV-1-01 | 110kV FEEDER - ARVA 110-NAVAN 110-1 | 40 | 29 | 29 | Scheduled | 03/07/2023 | 11/08/2023
TO-23-SLB-T132-01 | GENERATOR TRANSFORMER - SLIABH BAWN 110-SLIABH BAWN 33-T132 | 2 | 2 | 2 | Scheduled | 04/07/2023 | 05/07/2023
TO-23-DEY-T132-03 | GENERATOR TRANSFORMER - DERRYCARNEY 110-DERRYCARNEY 33-T132 | 2 | 2 | 2 | Scheduled | 10/07/2023 | 11/07/2023
TO-23-ATH-LA-1-01 | 110kV FEEDER - ATHLONE 110-LANESBORO 110-1 | 9 | 7 | 7 | Scheduled | 13/07/2023 | 21/07/2023
TO-23-FLA-LOU-1-03 | 220kV FEEDER - FLAGFORD 220-LOUTH 220-1 | 1 | 0 | 0 | Scheduled | 15/07/2023 | 15/07/2023
TO-23-LIS-110SA1-01 | SECTIONALISING DISCONNECT - LISDRUM 110-LISDRUM 110-110SA1 | 1 | 1 | 1 | Scheduled | 20/07/2023 | 20/07/2023
TO-23-LIS-110SA2-01 | SECTIONALISING DISCONNECT - LISDRUM 110-LISDRUM 110-110SA2 | 1 | 1 | 1 | Scheduled | 20/07/2023 | 20/07/2023
TO-23-LIS-CAP1-01 | CAPACITOR/SVC/REACTOR - LISDRUM 110-LISDRUM 110-CAP1 | 1 | 1 | 1 | Scheduled | 20/07/2023 | 20/07/2023
TO-23-LIS-LOU-1-03 | 110kV FEEDER - LISDRUM 110-LOUTH 110-1 | 1 | 1 | 1 | Scheduled | 20/07/2023 | 20/07/2023
TO-23-LIS-T131-02 | GENERATOR TRANSFORMER - LISDRUM 110-LISDRUM 33-T131 | 1 | 1 | 1 | Scheduled | 20/07/2023 | 20/07/2023
TO-23-DER-T1/T2-01 | GENERATOR TRANSFORMER - DERRYIRON 110-RHODE 110-T1/T2 | 12 | 10 | 10 | Scheduled | 24/07/2023 | 04/08/2023
TO-23-LOU-220K1-2-03 | COUPLER/SECTIONALISING CB - LOUTH 220-LOUTH 220-220K1-2 | 35 | 24 | 24 | Scheduled | 24/07/2023 | 27/08/2023
TO-23-MLC-110SA1-02 | SECTIONALISING DISCONNECT - MOUNTLUCAS 110-MOUNTLUCAS 110-110SA1 | 3 | 3 | 3 | Scheduled | 01/08/2023 | 03/08/2023
TO-23-MLC-110SA2-02 | SECTIONALISING DISCONNECT - MOUNTLUCAS 110-MOUNTLUCAS 110-110SA2 | 3 | 3 | 3 | Scheduled | 01/08/2023 | 03/08/2023
TO-23-MLC-TSB-1-05 | 110kV FEEDER - MOUNTLUCAS 110-THORNSBERRY 110-1 | 3 | 3 | 3 | Scheduled | 01/08/2023 | 03/08/2023
TO-23-MLN-T124-01 | TSO CUSTOMER TRANSFORMER - MULLAGHARLIN 110-MULLAGHARLIN 20-T124 | 2 | 2 | 2 | Scheduled | 01/08/2023 | 02/08/2023
TO-23-LIS-LOU-1-01 | 110kV FEEDER - LISDRUM 110-LOUTH 110-1 | 5 | 3 | 3 | Scheduled | 02/08/2023 | 06/08/2023
TO-23-LOU-110K1-2-01 | COUPLER/SECTIONALISING CB - LOUTH 110-LOUTH 110-110K1-2 | 5 | 3 | 3 | Scheduled | 02/08/2023 | 06/08/2023
TO-23-LOU-MTH-1-01 | 110kV FEEDER - LOUTH 110-MEATH HILL 110-1 | 5 | 3 | 3 | Scheduled | 02/08/2023 | 06/08/2023
TO-23-LOU-T2102-02 | TRANSFORMER - LOUTH 220-LOUTH 110-T2102 | 5 | 3 | 3 | Scheduled | 02/08/2023 | 06/08/2023
TO-23-LOU-T2104-02 | TRANSFORMER - LOUTH 220-LOUTH 110-T2104 | 5 | 3 | 3 | Scheduled | 02/08/2023 | 06/08/2023
TO-23-MLN-T123-01 | TSO CUSTOMER TRANSFORMER - MULLAGHARLIN 110-MULLAGHARLIN 20-T123 | 2 | 2 | 2 | Scheduled | 03/08/2023 | 04/08/2023
TO-23-DRY-110SA1-04 | SECTIONALISING DISCONNECT - DRYBRIDGE 110-DRYBRIDGE 110-110SA1 | 5 | 4 | 4 | Scheduled | 07/08/2023 | 11/08/2023
TO-23-DRY-110SA2-04 | SECTIONALISING DISCONNECT - DRYBRIDGE 110-DRYBRIDGE 110-110SA2 | 5 | 4 | 4 | Scheduled | 07/08/2023 | 11/08/2023
TO-23-DRY-LOU-1-02 | 110kV FEEDER - DRYBRIDGE 110-LOUTH 110-1 | 10 | 7 | 7 | Scheduled | 07/08/2023 | 16/08/2023
TO-23-DRY-PLA-1-04 | 110kV FEEDER - DRYBRIDGE 110-PLATIN 110-1 | 82 | 59 | 59 | Scheduled | 07/08/2023 | 27/10/2023
TO-23-DRY-T141-03 | DISTRIBUTION TRANSFORMER - DRYBRIDGE 110-DRYBRIDGE 38-T141 | 5 | 4 | 4 | Reference | 07/08/2023 | 11/08/2023
TO-23-PLA-110SA1-03 | SECTIONALISING DISCONNECT - PLATIN 110-PLATIN 110-110SA1 | 13 | 9 | 9 | Scheduled | 07/08/2023 | 19/08/2023
TO-23-PLA-110SA2-03 | SECTIONALISING DISCONNECT - PLATIN 110-PLATIN 110-110SA2 | 13 | 9 | 9 | Scheduled | 07/08/2023 | 19/08/2023
TO-23-PLA-T101/2/3/4-03 | TSO CUSTOMER TRANSFORMER - PLATIN 110-PLATIN 10-T101/2/3/4 | 13 | 9 | 9 | Scheduled | 07/08/2023 | 19/08/2023
TO-23-ARV-SKL-2-03 | 110kV FEEDER - ARVA 110-SHANKILL 110-2 | 2 | 0 | 0 | Scheduled | 12/08/2023 | 13/08/2023
TO-23-LIS-SKL-1-06 | 110kV FEEDER - LISDRUM 110-SHANKILL 110-1 | 104 | 73 |  | Scheduled | 12/08/2023 | 23/11/2023
TO-23-RRU-SKL-1-03 | 110kV FEEDER - RATRUSSAN 110-SHANKILL 110-1 | 2 | 0 | 0 | Scheduled | 12/08/2023 | 13/08/2023
TO-23-SKL-110SA1-03 | SECTIONALISING DISCONNECT - SHANKILL 110-SHANKILL 110-110SA1 | 2 | 0 | 0 | Scheduled | 12/08/2023 | 13/08/2023
TO-23-SKL-110SA2-02 | SECTIONALISING DISCONNECT - SHANKILL 110-SHANKILL 110-110SA2 | 2 | 0 | 0 | Scheduled | 12/08/2023 | 13/08/2023
TO-23-SKL-T141-02 | DISTRIBUTION TRANSFORMER - SHANKILL 110-SHANKILL 38-T141 | 2 | 0 | 0 | Reference | 12/08/2023 | 13/08/2023
TO-23-LIS-110SA1-04 | SECTIONALISING DISCONNECT - LISDRUM 110-LISDRUM 110-110SA1 | 26 | 20 | 20 | Scheduled | 14/08/2023 | 08/09/2023
TO-23-LIS-110SA2-04 | SECTIONALISING DISCONNECT - LISDRUM 110-LISDRUM 110-110SA2 | 26 | 20 | 20 | Scheduled | 14/08/2023 | 08/09/2023
TO-23-LIS-CAP2-04 | CAPACITOR/SVC/REACTOR - LISDRUM 110-LISDRUM 110-CAP2 | 26 | 20 | 20 | Scheduled | 14/08/2023 | 08/09/2023
TO-23-LIS-T142-03 | DISTRIBUTION TRANSFORMER - LISDRUM 110-LISDRUM 38-T142 | 26 | 20 | 20 | Reference | 14/08/2023 | 08/09/2023
TO-23-CUS-MLC-1-04 | 110kV FEEDER - CUSHALING 110-MOUNTLUCAS 110-1 | 4 | 4 | 4 | Scheduled | 15/08/2023 | 18/08/2023
TO-23-DRY-110SA1-02 | SECTIONALISING DISCONNECT - DRYBRIDGE 110-DRYBRIDGE 110-110SA1 | 1 | 1 | 1 | Scheduled | 16/08/2023 | 16/08/2023
TO-23-DRY-110SA2-01 | SECTIONALISING DISCONNECT - DRYBRIDGE 110-DRYBRIDGE 110-110SA2 | 1 | 1 | 1 | Scheduled | 16/08/2023 | 16/08/2023
TO-23-FLA-LOU-1-09 | 220kV FEEDER - FLAGFORD 220-LOUTH 220-1 | 3 | 1 |  | Scheduled | 18/08/2023 | 20/08/2023
TO-23-GOR-LOU-1-03 | 220kV FEEDER - GORMAN 220-LOUTH 220-1 | 3 | 1 |  | Scheduled | 18/08/2023 | 20/08/2023
TO-23-LOU-AT1-03 | TRANSFORMER - LOUTH 220-LOUTH 275-AT1 | 3 | 1 |  | Scheduled | 18/08/2023 | 20/08/2023
TO-23-LOU-AT3-04 | TRANSFORMER - LOUTH 220-LOUTH 275-AT3 | 3 | 1 |  | Scheduled | 18/08/2023 | 20/08/2023
TO-23-LOU-T2102-07 | TRANSFORMER - LOUTH 220-LOUTH 110-T2102 | 3 | 1 |  | Scheduled | 18/08/2023 | 20/08/2023
TO-23-LOU-T2104-01 | TRANSFORMER - LOUTH 220-LOUTH 110-T2104 | 3 | 1 |  | Scheduled | 18/08/2023 | 20/08/2023
TO-23-LOU-TAN-1-02 | 275kV FEEDER - LOUTH 275-TANDRAGEE 275-1 | 3 | 1 |  | Scheduled | 18/08/2023 | 20/08/2023
TO-23-ARV-NAV-1-05 | 110kV FEEDER - ARVA 110-NAVAN 110-1 | 26 | 20 | 20 | Scheduled | 21/08/2023 | 15/09/2023
TO-23-LOU-AT2-03 | TRANSFORMER - LOUTH 220-LOUTH 275-AT2 | 3 | 1 | 1 | Scheduled | 25/08/2023 | 27/08/2023
TO-23-LOU-T2101-02 | TRANSFORMER - LOUTH 220-LOUTH 110-T2101 | 3 | 1 | 1 | Scheduled | 25/08/2023 | 27/08/2023
TO-23-LOU-T2103-03 | TRANSFORMER - LOUTH 220-LOUTH 110-T2103 | 3 | 1 | 1 | Scheduled | 25/08/2023 | 27/08/2023
TO-23-LOU-TAN-2-03 | 275kV FEEDER - LOUTH 275-TANDRAGEE 275-2 | 3 | 1 | 1 | Scheduled | 25/08/2023 | 27/08/2023
TO-23-LOU-WOO-1-02 | 220kV FEEDER - LOUTH 220-WOODLAND 220-1 | 3 | 1 | 1 | Scheduled | 25/08/2023 | 27/08/2023
TO-23-KIN-T102-01 | TSO CUSTOMER TRANSFORMER - KINNEGAD 110-KINNEGAD 10-T102 | 9 | 7 | 7 | Scheduled | 04/09/2023 | 12/09/2023
TO-23-SOM-T142-04 | DISTRIBUTION TRANSFORMER - SOMERSET 110-SOMERSET 38-T142 | 8 | 6 | 6 | Reference | 04/09/2023 | 11/09/2023
TO-23-SOM,T-CSH-1-03 | 110kV FEEDER - SOMERSET tee-CASHLA 110-1 | 8 | 6 | 6 | Scheduled | 04/09/2023 | 11/09/2023
TO-23-SOM,T-SH-1-05 | 110kV FEEDER - SOMERSET tee-SHANNONBRIDGE 110-1 | 8 | 6 | 6 | Scheduled | 04/09/2023 | 11/09/2023
TO-23-SOM,T-SOM-1-04 | 110kV FEEDER - SOMERSET tee-SOMERSET 110-1 | 8 | 6 | 6 | Scheduled | 04/09/2023 | 11/09/2023
TO-23-LOU-T2104-06 | TRANSFORMER - LOUTH 220-LOUTH 110-T2104 | 4 | 4 | 4 | Scheduled | 05/09/2023 | 08/09/2023
TO-23-MP GIS-OST-1-06 | 400kV FEEDER - MONEYPOINT GIS 400-OLDSTREET 400-1 | 2 | 2 | 2 | Scheduled | 05/09/2023 | 06/09/2023
TO-23-KUR-NAV-1-01 | 110kV FEEDER - KNOCKUMBER 110-NAVAN 110-1 | 1 | 1 | 1 | Scheduled | 11/09/2023 | 11/09/2023
TO-23-KUR-T3-01 | TSO CUSTOMER TRANSFORMER - KNOCKUMBER 110-KNOCKUMBER 10-T3 | 1 | 1 | 1 | Reference | 11/09/2023 | 11/09/2023
TO-23-KUR-T4-01 | TSO CUSTOMER TRANSFORMER - KNOCKUMBER 110-KNOCKUMBER 10-T4 | 1 | 1 | 1 | Reference | 11/09/2023 | 11/09/2023
TO-23-TY-T2001/2-01 | GENERATOR TRANSFORMER - TYNAGH 220-TYNAGH G1/2-T2001/2 | 3 | 3 | 3 | Scheduled | 11/09/2023 | 13/09/2023
TO-23-OST-TY-1-04 | 220kV FEEDER - OLDSTREET 220-TYNAGH 220-1 | 9 | 7 | 7 | Scheduled | 14/09/2023 | 22/09/2023
TO-23-IKE,T-SH-1-05 | 110kV FEEDER - IKERRIN tee-SHANNONBRIDGE 110-1 | 2 | 2 |  | Scheduled | 18/09/2023 | 19/09/2023
TO-23-LOU-RRU-1-02 | 110kV FEEDER - LOUTH 110-RATRUSSAN 110-1 | 4 | 4 | 4 | Scheduled | 18/09/2023 | 21/09/2023
TO-23-PLA-110SA1-04 | SECTIONALISING DISCONNECT - PLATIN 110-PLATIN 110-110SA1 | 5 | 5 | 5 | Scheduled | 18/09/2023 | 22/09/2023
TO-23-PLA-110SA2-04 | SECTIONALISING DISCONNECT - PLATIN 110-PLATIN 110-110SA2 | 5 | 5 | 5 | Scheduled | 18/09/2023 | 22/09/2023
TO-23-PLA-T101/2/3/4-04 | TSO CUSTOMER TRANSFORMER - PLATIN 110-PLATIN 10-T101/2/3/4 | 5 | 5 | 5 | Scheduled | 18/09/2023 | 22/09/2023
TO-23-RRU-110SA1-03 | SECTIONALISING DISCONNECT - RATRUSSAN 110-RATRUSSAN 110-110SA1 | 4 | 4 | 4 | Scheduled | 18/09/2023 | 21/09/2023
TO-23-RRU-110SA2-03 | SECTIONALISING DISCONNECT - RATRUSSAN 110-RATRUSSAN 110-110SA2 | 4 | 4 | 4 | Scheduled | 18/09/2023 | 21/09/2023
TO-23-RRU-SKL-1-01 | 110kV FEEDER - RATRUSSAN 110-SHANKILL 110-1 | 4 | 4 | 4 | Scheduled | 18/09/2023 | 21/09/2023
TO-23-RRU-T121-03 | GENERATOR TRANSFORMER - RATRUSSAN 110-RATRUSSAN 20-T121 | 4 | 4 | 4 | Scheduled | 18/09/2023 | 21/09/2023
TO-23-RRU-T122-04 | GENERATOR TRANSFORMER - RATRUSSAN 110-RATRUSSAN 20-T122 | 4 | 4 | 4 | Scheduled | 18/09/2023 | 21/09/2023
TO-23-ARV-GWE-1-04 | 110kV FEEDER - ARVA 110-GORTAWEE 110-1 | 3 | 3 | 3 | Scheduled | 26/09/2023 | 28/09/2023
TO-23-KIN-MUL-1-04 | 110kV FEEDER - KINNEGAD 110-MULLINGAR 110-1 | 1 | 1 | 1 | Scheduled | 26/09/2023 | 26/09/2023
TO-23-LA-MUL-1-02 | 110kV FEEDER - LANESBORO 110-MULLINGAR 110-1 | 1 | 1 | 1 | Scheduled | 26/09/2023 | 26/09/2023
TO-23-MUL-110SA1-2CB-02 | COUPLER/SECTIONALISING CB - MULLINGAR 110-MULLINGAR 110-110SA1-2CB | 1 | 1 | 1 | Scheduled | 26/09/2023 | 26/09/2023
TO-23-MUL-CAP1-03 | CAPACITOR/SVC/REACTOR - MULLINGAR 110-MULLINGAR 110-CAP1 | 1 | 1 | 1 | Scheduled | 26/09/2023 | 26/09/2023
TO-23-MUL-T101-01 | DISTRIBUTION TRANSFORMER - MULLINGAR 110-MULLINGAR 10-T101 | 1 | 1 | 1 | Reference | 26/09/2023 | 26/09/2023
TO-23-MUL-T141-01 | DISTRIBUTION TRANSFORMER - MULLINGAR 110-MULLINGAR 38-T141 | 1 | 1 | 1 | Reference | 26/09/2023 | 26/09/2023
TO-23-ATH-T142-03 | DISTRIBUTION TRANSFORMER - ATHLONE 110-ATHLONE 38-T142 | 2 | 2 | 2 | Reference | 02/10/2023 | 03/10/2023
TO-23-DRY-LOU-1-08 | 110kV FEEDER - DRYBRIDGE 110-LOUTH 110-1 | 1 | 1 | 1 | Scheduled | 04/10/2023 | 04/10/2023
TO-23-LOU-T2104-07 | TRANSFORMER - LOUTH 220-LOUTH 110-T2104 | 1 | 1 | 1 | Scheduled | 05/10/2023 | 05/10/2023
TO-23-LOU-T2104-08 | TRANSFORMER - LOUTH 220-LOUTH 110-T2104 | 1 | 0 | 0 | Scheduled | 07/10/2023 | 07/10/2023
TO-23-GOR-110K1-2-02 | COUPLER/SECTIONALISING CB - GORMAN 110-GORMAN 110-110K1-2 | 26 | 19 | 19 | Scheduled | 16/10/2023 | 10/11/2023
TO-23-MAY-SH-1-01 | 220kV FEEDER - MAYNOOTH 220-SHANNONBRIDGE 220-1 | 53 | 38 | 38 | Scheduled | 16/10/2023 | 07/12/2023
TO-23-110 kV A1 @ ARV-02 | BUSBAR SECTION - ARVA 110-ARVA 110-110A1 | 5 | 5 | 5 | Scheduled | 23/10/2023 | 27/10/2023
TO-23-110 kV B1 @ ARV-01 | BUSBAR SECTION - ARVA 110-ARVA 110-110B1 | 5 | 5 | 5 | Scheduled | 23/10/2023 | 27/10/2023
TO-23-ARV-SKL-1-02 | 110kV FEEDER - ARVA 110-SHANKILL 110-1 | 5 | 5 | 5 | Scheduled | 23/10/2023 | 27/10/2023
TO-23-DRY-110SA1-05 | SECTIONALISING DISCONNECT - DRYBRIDGE 110-DRYBRIDGE 110-110SA1 | 5 | 5 | 5 | Scheduled | 23/10/2023 | 27/10/2023
TO-23-DRY-110SA2-05 | SECTIONALISING DISCONNECT - DRYBRIDGE 110-DRYBRIDGE 110-110SA2 | 5 | 5 | 5 | Scheduled | 23/10/2023 | 27/10/2023
TO-23-DRY-LOU-1-06 | 110kV FEEDER - DRYBRIDGE 110-LOUTH 110-1 | 5 | 5 | 5 | Scheduled | 23/10/2023 | 27/10/2023
TO-23-DRY-T141-04 | DISTRIBUTION TRANSFORMER - DRYBRIDGE 110-DRYBRIDGE 38-T141 | 5 | 5 | 5 | Reference | 23/10/2023 | 27/10/2023
TO-23-110 kV A1 @ LOU-04 | BUSBAR SECTION - LOUTH 110-LOUTH 110-110A1 | 4 | 4 | 4 | Scheduled | 23/10/2023 | 26/10/2023
TO-23-110 kV B1 @ LOU-04 | BUSBAR SECTION - LOUTH 110-LOUTH 110-110B1 | 4 | 4 | 4 | Scheduled | 23/10/2023 | 26/10/2023
TO-23-220 kV A1 @ LOU-01 | BUSBAR SECTION - LOUTH 220-LOUTH 220-220A1 | 33 | 24 | 24 | Scheduled | 23/10/2023 | 24/11/2023
TO-23-220 kV B1 @ LOU-02 | BUSBAR SECTION - LOUTH 220-LOUTH 220-220B1 | 33 | 24 | 24 | Scheduled | 23/10/2023 | 24/11/2023
TO-23-LOU-T2103-01 | TRANSFORMER - LOUTH 220-LOUTH 110-T2103 | 33 | 24 | 24 | Scheduled | 23/10/2023 | 24/11/2023
TO-23-PLA-110SA1-05 | SECTIONALISING DISCONNECT - PLATIN 110-PLATIN 110-110SA1 | 5 | 5 | 5 | Scheduled | 23/10/2023 | 27/10/2023
TO-23-PLA-110SA2-05 | SECTIONALISING DISCONNECT - PLATIN 110-PLATIN 110-110SA2 | 5 | 5 | 5 | Scheduled | 23/10/2023 | 27/10/2023
TO-23-PLA-T101/2/3/4-05 | TSO CUSTOMER TRANSFORMER - PLATIN 110-PLATIN 10-T101/2/3/4 | 5 | 5 | 5 | Scheduled | 23/10/2023 | 27/10/2023
TO-23-ARV-110K1-2-01 | COUPLER/SECTIONALISING CB - ARVA 110-ARVA 110-110K1-2 | 43 | 30 | 30 | Scheduled | 30/10/2023 | 11/12/2023
TO-23-AGL-110SA1-02 | SECTIONALISING DISCONNECT - AGANNYGAL 110-AGANNYGAL 110-110SA1 | 1 | 1 | 1 | Scheduled | 31/10/2023 | 31/10/2023
TO-23-AGL-110SA2-02 | SECTIONALISING DISCONNECT - AGANNYGAL 110-AGANNYGAL 110-110SA2 | 1 | 1 | 1 | Scheduled | 31/10/2023 | 31/10/2023
TO-23-AGL-DYN-1-04 | 110kV FEEDER - AGANNYGAL 110-DERRYBRIEN 110-1 | 1 | 1 | 1 | Scheduled | 31/10/2023 | 31/10/2023
TO-23-AGL-ENN-1-04 | 110kV FEEDER - AGANNYGAL 110-ENNIS 110-1 | 11 | 9 | 9 | Scheduled | 31/10/2023 | 10/11/2023
TO-23-AGL-SH-1-05 | 110kV FEEDER - AGANNYGAL 110-SHANNONBRIDGE 110-1 | 1 | 1 | 1 | Scheduled | 31/10/2023 | 31/10/2023
TO-23-DFR-T122-03 | DISTRIBUTION TRANSFORMER - DUNFIRTH 110-DUNFIRTH 20-T122 | 2 | 2 | 2 | Reference | 07/11/2023 | 08/11/2023
TO-23-AGL-110SA1-03 | SECTIONALISING DISCONNECT - AGANNYGAL 110-AGANNYGAL 110-110SA1 | 1 | 1 | 1 | Scheduled | 10/11/2023 | 10/11/2023
TO-23-AGL-110SA2-03 | SECTIONALISING DISCONNECT - AGANNYGAL 110-AGANNYGAL 110-110SA2 | 1 | 1 | 1 | Scheduled | 10/11/2023 | 10/11/2023
TO-23-AGL-DYN-1-05 | 110kV FEEDER - AGANNYGAL 110-DERRYBRIEN 110-1 | 1 | 1 | 1 | Scheduled | 10/11/2023 | 10/11/2023
TO-23-AGL-SH-1-07 | 110kV FEEDER - AGANNYGAL 110-SHANNONBRIDGE 110-1 | 1 | 1 | 1 | Scheduled | 10/11/2023 | 10/11/2023
TO-23-LIS-110SA1-06 | SECTIONALISING DISCONNECT - LISDRUM 110-LISDRUM 110-110SA1 | 4 | 2 | 2 | Scheduled | 10/11/2023 | 13/11/2023
TO-23-LIS-110SA2-06 | SECTIONALISING DISCONNECT - LISDRUM 110-LISDRUM 110-110SA2 | 4 | 2 | 2 | Scheduled | 10/11/2023 | 13/11/2023
TO-23-LIS-CAP2-05 | CAPACITOR/SVC/REACTOR - LISDRUM 110-LISDRUM 110-CAP2 | 4 | 2 | 2 | Scheduled | 10/11/2023 | 13/11/2023
TO-23-LIS-T142-04 | DISTRIBUTION TRANSFORMER - LISDRUM 110-LISDRUM 38-T142 | 4 | 2 |  | Reference | 10/11/2023 | 13/11/2023
TO-23-LA-SLB-1-01 | 110kV FEEDER - LANESBORO 110-SLIABH BAWN 110-1 | 5 | 5 | 5 | Scheduled | 20/11/2023 | 24/11/2023
TO-23-220 kV A2 @ SH-02 | BUSBAR SECTION - SHANNONBRIDGE 220-SHANNONBRIDGE 220-220A2 | 33 | 25 | 25 | Scheduled | 20/11/2023 | 22/12/2023
TO-23-220 kV B2 @ SH-02 | BUSBAR SECTION - SHANNONBRIDGE 220-SHANNONBRIDGE 220-220B2 | 33 | 25 | 25 | Scheduled | 20/11/2023 | 22/12/2023
TO-23-SKL-T142-01 | DISTRIBUTION TRANSFORMER - SHANKILL 110-SHANKILL 38-T142 | 2 | 2 | 2 | Reference | 21/11/2023 | 22/11/2023
TO-23-AGL-SH-1-02 | 110kV FEEDER - AGANNYGAL 110-SHANNONBRIDGE 110-1 | 2 | 2 | 2 | Scheduled | 23/11/2023 | 24/11/2023
TO-23-CUS-MLC-1-02 | 110kV FEEDER - CUSHALING 110-MOUNTLUCAS 110-1 | 1 | 1 | 1 | Proposed | 27/11/2023 | 27/11/2023
TO-23-GAR-GOR-1-01 | 110kV FEEDER - GARBALLAGH 110-GORMAN 110-1 | 3 | 3 | 3 | Scheduled | 27/11/2023 | 29/11/2023
TO-23-110 kV A2 @ LOU-04 | BUSBAR SECTION - LOUTH 110-LOUTH 110-110A2 | 5 | 5 | 5 | Scheduled | 27/11/2023 | 01/12/2023
TO-23-110 kV B2 @ LOU-04 | BUSBAR SECTION - LOUTH 110-LOUTH 110-110B2 | 5 | 5 | 5 | Scheduled | 27/11/2023 | 01/12/2023
TO-23-LOU-T2104-03 | TRANSFORMER - LOUTH 220-LOUTH 110-T2104 | 5 | 5 | 5 | Proposed | 27/11/2023 | 01/12/2023
TO-23-SH-T2102-02 | TRANSFORMER - SHANNONBRIDGE 220-SHANNONBRIDGE 110-T2102 | 5 | 5 | 5 | Scheduled | 27/11/2023 | 01/12/2023
TO-23-MLC-110SA1-01 | SECTIONALISING DISCONNECT - MOUNTLUCAS 110-MOUNTLUCAS 110-110SA1 | 16 | 12 | 12 | Proposed | 28/11/2023 | 13/12/2023
TO-23-MLC-110SA2-01 | SECTIONALISING DISCONNECT - MOUNTLUCAS 110-MOUNTLUCAS 110-110SA2 | 16 | 12 | 12 | Proposed | 28/11/2023 | 13/12/2023
TO-23-MLC-TSB-1-03 | 110kV FEEDER - MOUNTLUCAS 110-THORNSBERRY 110-1 | 16 | 12 | 12 | Proposed | 28/11/2023 | 13/12/2023
TO-23-MLC-TSB-1-04 | 110kV FEEDER - MOUNTLUCAS 110-THORNSBERRY 110-1 | 16 | 12 | 12 | Proposed | 28/11/2023 | 13/12/2023
TO-23-MLC-TSB-1-01 | 110kV FEEDER - MOUNTLUCAS 110-THORNSBERRY 110-1 | 5 | 4 | 4 | Proposed | 28/11/2023 | 02/12/2023
TO-23-TSB-110SA1-01 | SECTIONALISING DISCONNECT - THORNSBERRY 110-THORNSBERRY 110-110SA1 | 5 | 4 | 4 | Proposed | 28/11/2023 | 02/12/2023
TO-23-TSB-110SA2-01 | SECTIONALISING DISCONNECT - THORNSBERRY 110-THORNSBERRY 110-110SA2 | 5 | 4 | 4 | Proposed | 28/11/2023 | 02/12/2023
TO-23-TSB-T141-01 | DISTRIBUTION TRANSFORMER - THORNSBERRY 110-THORNSBERRY 38-T141 | 5 | 4 | 4 | Reference (Proposed) | 28/11/2023 | 02/12/2023

## GEN_Dublin
Outage ID | Feeder ID | Calendar Day Duration | Working Day Duration | Work Days | Outage Status | Start | Finish
TO-23-CRU-CDU-2-01 | 220kV FEEDER - CRUISERATH 220-CORDUFF 220-2 | 9 | 5 | 5 | Scheduled | 25/02/2023 | 05/03/2023
TO-23-BDA-MON-1-01 | 110kV FEEDER - BARODA 110-MONREAD 110-1 | 12 | 10 | 10 | Scheduled | 27/02/2023 | 10/03/2023
TO-23-110 kV A4 @ CDU-01 | BUSBAR SECTION - CORDUFF 110-CORDUFF 110-110A4 | 24 | 17 | 17 | Scheduled | 27/02/2023 | 22/03/2023
TO-23-110 kV B4 @ CDU-01 | BUSBAR SECTION - CORDUFF 110-CORDUFF 110-110B4 | 24 | 17 | 17 | Scheduled | 27/02/2023 | 22/03/2023
TO-23-220 kV B1 @ CKM GIS-02 | BUSBAR SECTION - CARRICKMINES GIS 220-CARRICKMINES GIS 220-220B1 | 4 | 4 | 4 | Scheduled | 28/02/2023 | 03/03/2023
TO-23-220 kV B3 @ CKM GIS-02 | BUSBAR SECTION - CARRICKMINES GIS 220-CARRICKMINES GIS 220-220B3 | 4 | 4 | 4 | Scheduled | 28/02/2023 | 03/03/2023
TO-23-CKM GIS-220SB1-3CB-02 | COUPLER/SECTIONALISING CB - CARRICKMINES GIS 220-CARRICKMINES GIS 220-22SB1-3CB | 4 | 4 | 4 | Scheduled | 28/02/2023 | 03/03/2023
TO-23-CDU-220K1-2-05 | COUPLER/SECTIONALISING CB - CORDUFF 220-CORDUFF 220-220K1-2 | 2 | 0 | 0 | Scheduled | 04/03/2023 | 05/03/2023
TO-23-CDU-220SA2-4-03 | SECTIONALISING DISCONNECT - CORDUFF 220-CORDUFF 220-220SA2-4 | 2 | 0 | 0 | Scheduled | 04/03/2023 | 05/03/2023
TO-23-CDU-220SB2-4-04 | SECTIONALISING DISCONNECT - CORDUFF 220-CORDUFF 220-220SB2-4 | 2 | 0 | 0 | Scheduled | 04/03/2023 | 05/03/2023
TO-23-CDU-FIN-2-05 | 220kV FEEDER - CORDUFF 220-FINGLAS 220-2 | 2 | 0 | 0 | Scheduled | 04/03/2023 | 05/03/2023
TO-23-CDU-T2102-02 | TRANSFORMER - CORDUFF 220-CORDUFF 110-T2102 | 2 | 0 | 0 | Scheduled | 04/03/2023 | 05/03/2023
TO-23-CDU-WOO-1-06 | 220kV FEEDER - CORDUFF 220-WOODLAND 220-1 | 2 | 0 | 0 | Scheduled | 04/03/2023 | 05/03/2023
TO-23-220 kV A2/A4 @ CDU-01 | BUSBAR SECTION - CORDUFF 220-CORDUFF 220-220A2-A4 | 1 | 0 | 0 | Scheduled | 05/03/2023 | 05/03/2023
TO-23-DND-T123-01 | TSO CUSTOMER TRANSFORMER - DARNDALE 110-DARNDALE 20-T123 | 5 | 5 | 5 | Scheduled | 06/03/2023 | 10/03/2023
TO-23-220 kV A1 @ CDU-01 | BUSBAR SECTION - CORDUFF 220-CORDUFF 220-220A1 | 1 | 1 | 1 | Scheduled | 08/03/2023 | 08/03/2023
TO-23-220 kV A2 @ CDU-02 | BUSBAR SECTION - CORDUFF 220-CORDUFF 220-220A2 | 1 | 1 | 1 | Scheduled | 08/03/2023 | 08/03/2023
TO-23-220 kV A3 @ CDU-01 | BUSBAR SECTION - CORDUFF 220-CORDUFF 220-220A3 | 1 | 1 | 1 | Scheduled | 08/03/2023 | 08/03/2023
TO-23-220 kV A4 @ CDU-03 | BUSBAR SECTION - CORDUFF 220-CORDUFF 220-220A4 | 1 | 1 | 1 | Scheduled | 08/03/2023 | 08/03/2023
TO-23-220 kV B1 @ CDU-01 | BUSBAR SECTION - CORDUFF 220-CORDUFF 220-220B1 | 1 | 1 | 1 | Scheduled | 08/03/2023 | 08/03/2023
TO-23-220 kV B2 @ CDU-02 | BUSBAR SECTION - CORDUFF 220-CORDUFF 220-220B2 | 1 | 1 | 1 | Scheduled | 08/03/2023 | 08/03/2023
TO-23-220 kV B3 @ CDU-01 | BUSBAR SECTION - CORDUFF 220-CORDUFF 220-220B3 | 1 | 1 | 1 | Scheduled | 08/03/2023 | 08/03/2023
TO-23-220 kV B4 @ CDU-03 | BUSBAR SECTION - CORDUFF 220-CORDUFF 220-220B4 | 1 | 1 | 1 | Scheduled | 08/03/2023 | 08/03/2023
TO-23-CDU-220K1-2-02 | COUPLER/SECTIONALISING CB - CORDUFF 220-CORDUFF 220-220K1-2 | 1 | 1 | 1 | Scheduled | 08/03/2023 | 08/03/2023
TO-23-CDU-220K1-3-02 | COUPLER/SECTIONALISING CB - CORDUFF 220-CORDUFF 220-220K1-3 | 1 | 1 | 1 | Scheduled | 08/03/2023 | 08/03/2023
TO-23-CDU-220SA2-4-01 | SECTIONALISING DISCONNECT - CORDUFF 220-CORDUFF 220-220SA2-4 | 1 | 1 | 1 | Scheduled | 08/03/2023 | 08/03/2023
TO-23-CDU-220SB2-4-01 | SECTIONALISING DISCONNECT - CORDUFF 220-CORDUFF 220-220SB2-4 | 1 | 1 | 1 | Scheduled | 08/03/2023 | 08/03/2023
TO-23-220 kV A1 @ CLE-01 | BUSBAR SECTION - CLONEE 220-CLONEE 220-220A1 | 4 | 4 | 4 | Proposed | 13/03/2023 | 16/03/2023
TO-23-220 kV A2 @ CLE-01 | BUSBAR SECTION - CLONEE 220-CLONEE 220-220A2 | 4 | 4 | 4 | Proposed | 13/03/2023 | 16/03/2023
TO-23-CLE-220K1-01 | COUPLER/SECTIONALISING CB - CLONEE 220-CLONEE 220-220K1 | 4 | 4 | 4 | Proposed | 13/03/2023 | 16/03/2023
TO-23-CLE-220K2-01 | COUPLER/SECTIONALISING CB - CLONEE 220-CLONEE 220-220K2 | 4 | 4 | 4 | Proposed | 13/03/2023 | 16/03/2023
TO-23-CLE-220SA1-2CB-01 | COUPLER/SECTIONALISING CB - CLONEE 220-CLONEE 220-220SA1-2CB | 4 | 4 | 4 | Proposed | 13/03/2023 | 16/03/2023
TO-23-CLE-WOO-1-03 | 220kV FEEDER - CLONEE 220-WOODLAND 220-1 | 4 | 4 | 4 | Proposed | 13/03/2023 | 16/03/2023
TO-23-CDU-MUL-1-02 | 110kV FEEDER - CORDUFF 110-MULLINGAR 110-1 | 165 | 113 | 113 | Scheduled | 13/03/2023 | 24/08/2023
TO-23-DSN-TH-1-03 | 220kV FEEDER - DUNSTOWN 220-TURLOUGH HILL 220-1 | 4 | 4 | 4 | Scheduled | 13/03/2023 | 16/03/2023
TO-23-220 kV A2 @ CKM GIS-03 | BUSBAR SECTION - CARRICKMINES GIS 220-CARRICKMINES GIS 220-220A2 | 12 | 10 | 10 | Scheduled | 20/03/2023 | 31/03/2023
TO-23-220 kV B2 @ CKM GIS-03 | BUSBAR SECTION - CARRICKMINES GIS 220-CARRICKMINES GIS 220-220B2 | 12 | 10 | 10 | Scheduled | 20/03/2023 | 31/03/2023
TO-23-CKM GIS-220SA1-2CB-03 | COUPLER/SECTIONALISING CB - CARRICKMINES GIS 220-CARRICKMINES GIS 220-22SA1-2CB | 12 | 10 | 10 | Scheduled | 20/03/2023 | 31/03/2023
TO-23-CKM GIS-220SA2-4CB-03 | COUPLER/SECTIONALISING CB - CARRICKMINES GIS 220-CARRICKMINES GIS 220-22SA2-4CB | 12 | 10 | 10 | Scheduled | 20/03/2023 | 31/03/2023
TO-23-CKM GIS-220SB1-2CB-03 | COUPLER/SECTIONALISING CB - CARRICKMINES GIS 220-CARRICKMINES GIS 220-22SB1-2CB | 12 | 10 | 10 | Scheduled | 20/03/2023 | 31/03/2023
TO-23-CKM GIS-220SB2-4CB-03 | COUPLER/SECTIONALISING CB - CARRICKMINES GIS 220-CARRICKMINES GIS 220-22SB2-4CB | 12 | 10 | 10 | Scheduled | 20/03/2023 | 31/03/2023
TO-23-CKM GIS-ISH-1-01 | 220kV FEEDER - CARRICKMINES GIS 220-IRISHTOWN 220-1 | 12 | 10 | 10 | Scheduled | 20/03/2023 | 31/03/2023
TO-23-110 kV A2 @ CBT-03 | BUSBAR SECTION - CASTLEBAGOT 110-CASTLEBAGOT 110-110A2 | 2 | 2 | 2 | Scheduled | 23/03/2023 | 24/03/2023
TO-23-110 kV B2 @ CBT-01 | BUSBAR SECTION - CASTLEBAGOT 110-CASTLEBAGOT 110-110B2 | 2 | 2 | 2 | Scheduled | 23/03/2023 | 24/03/2023
TO-23-CBT-110SA1-2CB-03 | COUPLER/SECTIONALISING CB - CASTLEBAGOT 110-CASTLEBAGOT 110-110SA1-2CB | 2 | 2 | 2 | Scheduled | 23/03/2023 | 24/03/2023
TO-23-CBT-110SA2-4CB-03 | COUPLER/SECTIONALISING CB - CASTLEBAGOT 110-CASTLEBAGOT 110-110SA2-4CB | 2 | 2 | 2 | Scheduled | 23/03/2023 | 24/03/2023
TO-23-CBT-110SB1-2CB-04 | COUPLER/SECTIONALISING CB - CASTLEBAGOT 110-CASTLEBAGOT 110-110SB1-2CB | 2 | 2 | 2 | Scheduled | 23/03/2023 | 24/03/2023
TO-23-CBT-110SB2-4CB-03 | COUPLER/SECTIONALISING CB - CASTLEBAGOT 110-CASTLEBAGOT 110-110SB2-4CB | 2 | 2 | 2 | Scheduled | 23/03/2023 | 24/03/2023
TO-23-220 kV A2 @ CBT-01 | BUSBAR SECTION - CASTLEBAGOT 220-CASTLEBAGOT 220-220A2 | 2 | 2 | 2 | Scheduled | 23/03/2023 | 24/03/2023
TO-23-220 kV B2 @ CBT-01 | BUSBAR SECTION - CASTLEBAGOT 220-CASTLEBAGOT 220-220B2 | 2 | 2 | 2 | Scheduled | 23/03/2023 | 24/03/2023
TO-23-CBT-220K2-01 | COUPLER/SECTIONALISING CB - CASTLEBAGOT 220-CASTLEBAGOT 220-220K2 | 2 | 2 | 2 | Scheduled | 23/03/2023 | 24/03/2023
TO-23-CBT-220SA1-2CB-01 | COUPLER/SECTIONALISING CB - CASTLEBAGOT 220-CASTLEBAGOT 220-220SA1-2CB | 2 | 2 | 2 | Scheduled | 23/03/2023 | 24/03/2023
TO-23-CBT-220SB1-2CB-01 | COUPLER/SECTIONALISING CB - CASTLEBAGOT 220-CASTLEBAGOT 220-220SB1-2CB | 2 | 2 | 2 | Scheduled | 23/03/2023 | 24/03/2023
TO-23-CBT-T2102-02 | TRANSFORMER - CASTLEBAGOT 220-CASTLEBAGOT 110-T2102 | 2 | 2 | 2 | Scheduled | 23/03/2023 | 24/03/2023
TO-23-110 kV A4 @ CDU-02 | BUSBAR SECTION - CORDUFF 110-CORDUFF 110-110A4 | 54 | 35 | 35 | Scheduled | 23/03/2023 | 15/05/2023
TO-23-110 kV B4 @ CDU-02 | BUSBAR SECTION - CORDUFF 110-CORDUFF 110-110B4 | 54 | 35 | 35 | Scheduled | 23/03/2023 | 15/05/2023
TO-23-FIN-HN-1-01 | 220kV FEEDER - FINGLAS 220-HUNTSTOWN 220-1 | 14 | 9 | 9 | Scheduled | 25/03/2023 | 07/04/2023
TO-23-HN-T2010/11-01 | GENERATOR TRANSFORMER - HUNTSTOWN 220-HUNTSTOWN G10/11-T2010/11 | 14 | 9 | 9 | Scheduled | 25/03/2023 | 07/04/2023
TO-23-KTL-MAY-1-01 | 110kV FEEDER - KILTEEL 110-MAYNOOTH 110-1 | 26 | 18 |  | Scheduled | 27/03/2023 | 21/04/2023
TO-23-110 kV A1 @ MAY-01 | BUSBAR SECTION - MAYNOOTH 110-MAYNOOTH 110-110A1 | 26 | 18 | 18 | Scheduled | 27/03/2023 | 21/04/2023
TO-23-110 kV B1 @ MAY-01 | BUSBAR SECTION - MAYNOOTH 110-MAYNOOTH 110-110B1 | 26 | 18 | 18 | Scheduled | 27/03/2023 | 21/04/2023
TO-23-FIN-220K2-01 | COUPLER/SECTIONALISING CB - FINGLAS 220-FINGLAS 220-220K2 | 15 | 9 | 9 | Scheduled | 29/03/2023 | 12/04/2023
TO-23-FIN-220SA1-2CB-01 | COUPLER/SECTIONALISING CB - FINGLAS 220-FINGLAS 220-220SA1-2CB | 15 | 9 | 9 | Scheduled | 29/03/2023 | 12/04/2023
TO-23-FIN-220SB1-2CB-03 | COUPLER/SECTIONALISING CB - FINGLAS 220-FINGLAS 220-220SB1-2CB | 15 | 9 | 9 | Scheduled | 29/03/2023 | 12/04/2023
TO-23-110 kV A1 @ CBT-03 | BUSBAR SECTION - CASTLEBAGOT 110-CASTLEBAGOT 110-110A1 | 4 | 4 | 4 | Scheduled | 03/04/2023 | 06/04/2023
TO-23-110 kV B1 @ CBT-02 | BUSBAR SECTION - CASTLEBAGOT 110-CASTLEBAGOT 110-110B1 | 4 | 4 | 4 | Scheduled | 03/04/2023 | 06/04/2023
TO-23-CBT-110K1-01 | COUPLER/SECTIONALISING CB - CASTLEBAGOT 110-CASTLEBAGOT 110-110K1 | 4 | 4 | 4 | Scheduled | 03/04/2023 | 06/04/2023
TO-23-CBT-110SA1-2CB-06 | COUPLER/SECTIONALISING CB - CASTLEBAGOT 110-CASTLEBAGOT 110-110SA1-2CB | 4 | 4 | 4 | Scheduled | 03/04/2023 | 06/04/2023
TO-23-CBT-110SB1-2CB-05 | COUPLER/SECTIONALISING CB - CASTLEBAGOT 110-CASTLEBAGOT 110-110SB1-2CB | 4 | 4 | 4 | Scheduled | 03/04/2023 | 06/04/2023
TO-23-110 kV A3 @ RYB GIS-01 | BUSBAR SECTION - RYEBROOK GIS 110-RYEBROOK GIS 110-110A3 | 4 | 4 | 4 | Scheduled | 03/04/2023 | 06/04/2023
TO-23-110 kV B3 @ RYB GIS-01 | BUSBAR SECTION - RYEBROOK GIS 110-RYEBROOK GIS 110-110B3 | 4 | 4 | 4 | Scheduled | 03/04/2023 | 06/04/2023
TO-23-RYB GIS-110K3-01 | COUPLER/SECTIONALISING CB - RYEBROOK GIS 110-RYEBROOK GIS 110-110K3 | 4 | 4 | 4 | Scheduled | 03/04/2023 | 06/04/2023
TO-23-RYB GIS-110SA1-3CB-02 | COUPLER/SECTIONALISING CB - RYEBROOK GIS 110-RYEBROOK GIS 110-110SA1-3CB | 4 | 4 | 4 | Scheduled | 03/04/2023 | 06/04/2023
TO-23-RYB GIS-110SB1-3CB-04 | COUPLER/SECTIONALISING CB - RYEBROOK GIS 110-RYEBROOK GIS 110-110SB1-3CB | 4 | 4 | 4 | Scheduled | 03/04/2023 | 06/04/2023
TO-23-CLE-220SA1-2CB-03 | COUPLER/SECTIONALISING CB - CLONEE 220-CLONEE 220-220SA1-2CB | 1 | 1 | 1 | Scheduled | 04/04/2023 | 04/04/2023
TO-23-CLE-220SB1-2CB-02 | COUPLER/SECTIONALISING CB - CLONEE 220-CLONEE 220-220SB1-2CB | 1 | 1 | 1 | Scheduled | 05/04/2023 | 05/04/2023
TO-23-INC-ISH-1-01 | 220kV FEEDER - INCHICORE 220-IRISHTOWN 220-1 | 16 | 10 |  | Scheduled | 06/04/2023 | 21/04/2023
TO-23-ISH-220K1-2-01 | COUPLER/SECTIONALISING CB - IRISHTOWN 220-IRISHTOWN 220-220K1-2 | 16 | 10 |  | Scheduled | 06/04/2023 | 21/04/2023
TO-23-ISH-SHL-1-01 | 220kV FEEDER - IRISHTOWN 220-SHELLYBANKS 220-1 | 16 | 10 |  | Scheduled | 06/04/2023 | 21/04/2023
TO-23-220 kV A1 @ TH-01 | BUSBAR SECTION - TURLOUGH HILL 220-TURLOUGH HILL 220-220A1 | 4 | 4 | 4 | Scheduled | 11/04/2023 | 14/04/2023
TO-23-220 kV A2 @ TH-01 | BUSBAR SECTION - TURLOUGH HILL 220-TURLOUGH HILL 220-220A2 | 4 | 4 | 4 | Scheduled | 11/04/2023 | 14/04/2023
TO-23-220 kV B1 @ TH-01 | BUSBAR SECTION - TURLOUGH HILL 220-TURLOUGH HILL 220-220B1 | 4 | 4 | 4 | Scheduled | 11/04/2023 | 14/04/2023
TO-23-220 kV B2 @ TH-01 | BUSBAR SECTION - TURLOUGH HILL 220-TURLOUGH HILL 220-220B2 | 4 | 4 | 4 | Scheduled | 11/04/2023 | 14/04/2023
TO-23-TH-220K1-2-01 | COUPLER/SECTIONALISING CB - TURLOUGH HILL 220-TURLOUGH HILL 220-220K1-2 | 4 | 4 | 4 | Scheduled | 11/04/2023 | 14/04/2023
TO-23-CBT-110K1-05 | COUPLER/SECTIONALISING CB - CASTLEBAGOT 110-CASTLEBAGOT 110-110K1 | 5 | 5 | 5 | Scheduled | 17/04/2023 | 21/04/2023
TO-23-CBT-110SA2-4CB-06 | COUPLER/SECTIONALISING CB - CASTLEBAGOT 110-CASTLEBAGOT 110-110SA2-4CB | 5 | 5 | 5 | Scheduled | 17/04/2023 | 21/04/2023
TO-23-CDU-RYB GIS-1-02 | 110kV FEEDER - CORDUFF 110-RYEBROOK GIS 110-1 | 47 | 34 |  | Scheduled | 17/04/2023 | 02/06/2023
TO-23-110 kV B1 @ RYB GIS-02 | BUSBAR SECTION - RYEBROOK GIS 110-RYEBROOK GIS 110-110B1 | 5 | 5 | 5 | Scheduled | 17/04/2023 | 21/04/2023
TO-23-110 kV B2 @ RYB GIS-01 | BUSBAR SECTION - RYEBROOK GIS 110-RYEBROOK GIS 110-110B2 | 5 | 5 | 5 | Scheduled | 17/04/2023 | 21/04/2023
TO-23-RYB GIS-110SB1-2CB-01 | COUPLER/SECTIONALISING CB - RYEBROOK GIS 110-RYEBROOK GIS 110-110SB1-2CB | 5 | 5 | 5 | Scheduled | 17/04/2023 | 21/04/2023
TO-23-RYB GIS-110SB1-3CB-05 | COUPLER/SECTIONALISING CB - RYEBROOK GIS 110-RYEBROOK GIS 110-110SB1-3CB | 5 | 5 | 5 | Scheduled | 17/04/2023 | 21/04/2023
TO-23-RYB GIS-110SB2-4CB-02 | COUPLER/SECTIONALISING CB - RYEBROOK GIS 110-RYEBROOK GIS 110-110SB2-4CB | 5 | 5 | 5 | Scheduled | 17/04/2023 | 21/04/2023
TO-23-400 kV A2 @ WOO-01 | BUSBAR SECTION - WOODLAND 400-WOODLAND 400-400A2 | 5 | 5 | 5 | Scheduled | 17/04/2023 | 21/04/2023
TO-23-WOO-T4204-02 | TRANSFORMER - WOODLAND 400-WOODLAND 220-T4204 | 5 | 5 | 5 | Scheduled | 17/04/2023 | 21/04/2023
TO-23-MCE-SNU-1-02 | 110kV FEEDER - MACETOWN 110-SNUGBOROUGH 110-1 | 17 | 12 | 12 | Scheduled | 19/04/2023 | 05/05/2023
TO-23-110 kV A2 @ PA-02 | BUSBAR SECTION - POLLAPHUCA 110-POLLAPHUCA 110-110A2 | 1 | 1 | 1 | Scheduled | 20/04/2023 | 20/04/2023
TO-23-PA-110SA1-04 | SECTIONALISING DISCONNECT - POLLAPHUCA 110-POLLAPHUCA 110-110SA1 | 1 | 1 | 1 | Scheduled | 20/04/2023 | 20/04/2023
TO-23-PA-110SA2-04 | SECTIONALISING DISCONNECT - POLLAPHUCA 110-POLLAPHUCA 110-110SA2 | 1 | 1 | 1 | Scheduled | 20/04/2023 | 20/04/2023
TO-23-PA-T101-04 | GENERATOR TRANSFORMER - POLLAPHUCA 110-POLLAPHUCA G1-T101 | 1 | 1 | 1 | Scheduled | 20/04/2023 | 20/04/2023
TO-23-LOU-WOO-1-01 | 220kV FEEDER - LOUTH 220-WOODLAND 220-1 | 2 | 0 | 0 | Scheduled | 22/04/2023 | 23/04/2023
TO-23-110 kV A1 @ CBT-01 | BUSBAR SECTION - CASTLEBAGOT 110-CASTLEBAGOT 110-110A1 | 1 | 1 |  | Scheduled | 24/04/2023 | 24/04/2023
TO-23-110 kV B1 @ CBT-04 | BUSBAR SECTION - CASTLEBAGOT 110-CASTLEBAGOT 110-110B1 | 1 | 1 |  | Scheduled | 24/04/2023 | 24/04/2023
TO-23-CBT-110K1-02 | COUPLER/SECTIONALISING CB - CASTLEBAGOT 110-CASTLEBAGOT 110-110K1 | 1 | 1 |  | Scheduled | 24/04/2023 | 24/04/2023
TO-23-CBT-110SA1-2CB-02 | COUPLER/SECTIONALISING CB - CASTLEBAGOT 110-CASTLEBAGOT 110-110SA1-2CB | 1 | 1 |  | Scheduled | 24/04/2023 | 24/04/2023
TO-23-CBT-110SB1-2CB-06 | COUPLER/SECTIONALISING CB - CASTLEBAGOT 110-CASTLEBAGOT 110-110SB1-2CB | 1 | 1 |  | Scheduled | 24/04/2023 | 24/04/2023
TO-23-CDU-110K1-3-03 | COUPLER/SECTIONALISING CB - CORDUFF 110-CORDUFF 110-110K1-3 | 5 | 5 | 5 | Scheduled | 24/04/2023 | 28/04/2023
TO-23-PB-220K2-3-02 | COUPLER/SECTIONALISING CB - POOLBEG 220-POOLBEG 220-220K2-3 | 5 | 5 | 5 | Proposed | 24/04/2023 | 28/04/2023
TO-23-PRN-T4301-01 | TRANSFORMER - PORTAN 400-PORTAN 260-T4301 | 5 | 5 | 5 | Proposed | 24/04/2023 | 28/04/2023
TO-23-PRN-WOO-1-01 | 400kV FEEDER - PORTAN 400-WOODLAND 400-1 | 5 | 5 | 5 | Proposed | 24/04/2023 | 28/04/2023
TO-23-400 kV A1 @ WOO-01 | BUSBAR SECTION - WOODLAND 400-WOODLAND 400-400A1 | 1 | 1 | 1 | Proposed | 24/04/2023 | 24/04/2023
TO-23-CKM-PST2201-02 | TRANSFORMER - CARRICKMINES 220-CARRICKMINES 220-PST2201 | 2 | 2 | 2 | Proposed | 25/04/2023 | 26/04/2023
TO-23-110 kV A4 @ CBT-03 | BUSBAR SECTION - CASTLEBAGOT 110-CASTLEBAGOT 110-110A4 | 1 | 1 |  | Scheduled | 25/04/2023 | 25/04/2023
TO-23-110 kV B4 @ CBT-02 | BUSBAR SECTION - CASTLEBAGOT 110-CASTLEBAGOT 110-110B4 | 1 | 1 |  | Scheduled | 25/04/2023 | 25/04/2023
TO-23-CBT-110K4-02 | COUPLER/SECTIONALISING CB - CASTLEBAGOT 110-CASTLEBAGOT 110-110K4 | 1 | 1 |  | Scheduled | 25/04/2023 | 25/04/2023
TO-23-CBT-110SA2-4CB-05 | COUPLER/SECTIONALISING CB - CASTLEBAGOT 110-CASTLEBAGOT 110-110SA2-4CB | 1 | 1 |  | Scheduled | 25/04/2023 | 25/04/2023
TO-23-CBT-110SB2-4CB-04 | COUPLER/SECTIONALISING CB - CASTLEBAGOT 110-CASTLEBAGOT 110-110SB2-4CB | 1 | 1 |  | Scheduled | 25/04/2023 | 25/04/2023
TO-23-220 kV A1 @ CBT-01 | BUSBAR SECTION - CASTLEBAGOT 220-CASTLEBAGOT 220-220A1 | 5 | 2 | 2 | Scheduled | 29/04/2023 | 03/05/2023
TO-23-CBT-220K1-02 | COUPLER/SECTIONALISING CB - CASTLEBAGOT 220-CASTLEBAGOT 220-220K1 | 5 | 2 | 2 | Scheduled | 29/04/2023 | 03/05/2023
TO-23-CBT-220SA1-2CB-03 | COUPLER/SECTIONALISING CB - CASTLEBAGOT 220-CASTLEBAGOT 220-220SA1-2CB | 5 | 2 | 2 | Scheduled | 29/04/2023 | 03/05/2023
TO-23-CBT-MAY-1-01 | 220kV FEEDER - CASTLEBAGOT 220-MAYNOOTH 220-1 | 5 | 2 |  | Scheduled | 29/04/2023 | 03/05/2023
TO-23-TH-T2001/2-01 | GENERATOR TRANSFORMER - TURLOUGH HILL 220-TURLOUGH HILL G1-T2001/2 | 10 | 8 | 8 | Scheduled | 03/05/2023 | 12/05/2023
TO-23-220 kV A1 @ CDU-03 | BUSBAR SECTION - CORDUFF 220-CORDUFF 220-220A1 | 2 | 2 | 2 | Scheduled | 08/05/2023 | 09/05/2023
TO-23-220 kV A2 @ CDU-03 | BUSBAR SECTION - CORDUFF 220-CORDUFF 220-220A2 | 2 | 2 | 2 | Scheduled | 08/05/2023 | 09/05/2023
TO-23-220 kV A3 @ CDU-02 | BUSBAR SECTION - CORDUFF 220-CORDUFF 220-220A3 | 2 | 2 | 2 | Scheduled | 08/05/2023 | 09/05/2023
TO-23-220 kV A4 @ CDU-04 | BUSBAR SECTION - CORDUFF 220-CORDUFF 220-220A4 | 2 | 2 | 2 | Scheduled | 08/05/2023 | 09/05/2023
TO-23-220 kV B1 @ CDU-03 | BUSBAR SECTION - CORDUFF 220-CORDUFF 220-220B1 | 2 | 2 | 2 | Scheduled | 08/05/2023 | 09/05/2023
TO-23-220 kV B2 @ CDU-03 | BUSBAR SECTION - CORDUFF 220-CORDUFF 220-220B2 | 2 | 2 | 2 | Scheduled | 08/05/2023 | 09/05/2023
TO-23-220 kV B3 @ CDU-02 | BUSBAR SECTION - CORDUFF 220-CORDUFF 220-220B3 | 2 | 2 | 2 | Scheduled | 08/05/2023 | 09/05/2023
TO-23-220 kV B4 @ CDU-04 | BUSBAR SECTION - CORDUFF 220-CORDUFF 220-220B4 | 2 | 2 | 2 | Scheduled | 08/05/2023 | 09/05/2023
TO-23-CDU-220K1-2-04 | COUPLER/SECTIONALISING CB - CORDUFF 220-CORDUFF 220-220K1-2 | 2 | 2 | 2 | Scheduled | 08/05/2023 | 09/05/2023
TO-23-CDU-220K1-3-05 | COUPLER/SECTIONALISING CB - CORDUFF 220-CORDUFF 220-220K1-3 | 2 | 2 | 2 | Scheduled | 08/05/2023 | 09/05/2023
TO-23-CDU-220SA2-4-04 | SECTIONALISING DISCONNECT - CORDUFF 220-CORDUFF 220-220SA2-4 | 2 | 2 | 2 | Scheduled | 08/05/2023 | 09/05/2023
TO-23-CDU-220SB2-4-06 | SECTIONALISING DISCONNECT - CORDUFF 220-CORDUFF 220-220SB2-4 | 2 | 2 | 2 | Scheduled | 08/05/2023 | 09/05/2023
TO-23-DFR,T-RNW-1-04 | 110kV FEEDER - DUNFIRTH tee-RINAWADE 110-1 | 2 | 2 | 2 | Scheduled | 08/05/2023 | 09/05/2023
TO-23-FIN-220K2-03 | COUPLER/SECTIONALISING CB - FINGLAS 220-FINGLAS 220-220K2 | 12 | 10 | 10 | Scheduled | 08/05/2023 | 19/05/2023
TO-23-FIN-220SA1-2CB-02 | COUPLER/SECTIONALISING CB - FINGLAS 220-FINGLAS 220-220SA1-2CB | 12 | 10 | 10 | Scheduled | 08/05/2023 | 19/05/2023
TO-23-FIN-220SB1-2CB-05 | COUPLER/SECTIONALISING CB - FINGLAS 220-FINGLAS 220-220SB1-2CB | 12 | 10 | 10 | Scheduled | 08/05/2023 | 19/05/2023
TO-23-110 kV A1 @ MAY-02 | BUSBAR SECTION - MAYNOOTH 110-MAYNOOTH 110-110A1 | 12 | 10 | 10 | Scheduled | 08/05/2023 | 19/05/2023
TO-23-110 kV A2 @ MAY-01 | BUSBAR SECTION - MAYNOOTH 110-MAYNOOTH 110-110A2 | 12 | 10 | 10 | Scheduled | 08/05/2023 | 19/05/2023
TO-23-110 kV B1 @ MAY-02 | BUSBAR SECTION - MAYNOOTH 110-MAYNOOTH 110-110B1 | 12 | 10 | 10 | Scheduled | 08/05/2023 | 19/05/2023
TO-23-110 kV B2 @ MAY-01 | BUSBAR SECTION - MAYNOOTH 110-MAYNOOTH 110-110B2 | 12 | 10 | 10 | Scheduled | 08/05/2023 | 19/05/2023
TO-23-MAY-110K1-2-01 | COUPLER/SECTIONALISING CB - MAYNOOTH 110-MAYNOOTH 110-110K1-2 | 12 | 10 | 10 | Scheduled | 08/05/2023 | 19/05/2023
TO-23-CDU-MCE-1-06 | 110kV FEEDER - CORDUFF 110-MACETOWN 110-1 | 2 | 2 | 2 | Scheduled | 09/05/2023 | 10/05/2023
TO-23-110 kV A1 @ CBT-02 | BUSBAR SECTION - CASTLEBAGOT 110-CASTLEBAGOT 110-110A1 | 3 | 3 | 3 | Scheduled | 10/05/2023 | 12/05/2023
TO-23-110 kV A4 @ CBT-01 | BUSBAR SECTION - CASTLEBAGOT 110-CASTLEBAGOT 110-110A4 | 3 | 3 | 3 | Scheduled | 10/05/2023 | 12/05/2023
TO-23-110 kV B1 @ CBT-01 | BUSBAR SECTION - CASTLEBAGOT 110-CASTLEBAGOT 110-110B1 | 3 | 3 | 3 | Scheduled | 10/05/2023 | 12/05/2023
TO-23-110 kV B4 @ CBT-01 | BUSBAR SECTION - CASTLEBAGOT 110-CASTLEBAGOT 110-110B4 | 3 | 3 | 3 | Scheduled | 10/05/2023 | 12/05/2023
TO-23-CBT-110K1-04 | COUPLER/SECTIONALISING CB - CASTLEBAGOT 110-CASTLEBAGOT 110-110K1 | 3 | 3 | 3 | Scheduled | 10/05/2023 | 12/05/2023
TO-23-CBT-110K4-01 | COUPLER/SECTIONALISING CB - CASTLEBAGOT 110-CASTLEBAGOT 110-110K4 | 3 | 3 | 3 | Scheduled | 10/05/2023 | 12/05/2023
TO-23-CBT-110SA1-2CB-05 | COUPLER/SECTIONALISING CB - CASTLEBAGOT 110-CASTLEBAGOT 110-110SA1-2CB | 3 | 3 | 3 | Scheduled | 10/05/2023 | 12/05/2023
TO-23-CBT-110SA2-4CB-02 | COUPLER/SECTIONALISING CB - CASTLEBAGOT 110-CASTLEBAGOT 110-110SA2-4CB | 3 | 3 | 3 | Scheduled | 10/05/2023 | 12/05/2023
TO-23-CBT-110SB1-2CB-02 | COUPLER/SECTIONALISING CB - CASTLEBAGOT 110-CASTLEBAGOT 110-110SB1-2CB | 3 | 3 | 3 | Scheduled | 10/05/2023 | 12/05/2023
TO-23-CBT-110SB2-4CB-02 | COUPLER/SECTIONALISING CB - CASTLEBAGOT 110-CASTLEBAGOT 110-110SB2-4CB | 3 | 3 | 3 | Scheduled | 10/05/2023 | 12/05/2023
TO-23-CBT-T2103-05 | TRANSFORMER - CASTLEBAGOT 220-CASTLEBAGOT 110-T2103 | 3 | 3 | 3 | Scheduled | 10/05/2023 | 12/05/2023
TO-23-DFR,T-RNW-1-06 | 110kV FEEDER - DUNFIRTH tee-RINAWADE 110-1 | 16 | 12 | 12 | Scheduled | 10/05/2023 | 25/05/2023
TO-23-CDU-GLN-1-03 | 110kV FEEDER - CORDUFF 110-GALLANSTOWN 110-1 | 34 | 23 | 23 | Scheduled | 12/05/2023 | 14/06/2023
TO-23-CKM-PB-1-02 | 220kV FEEDER - CARRICKMINES 220-POOLBEG 220-1 | 5 | 5 | 5 | Scheduled | 15/05/2023 | 19/05/2023
TO-23-CKM-PST2201-01 | TRANSFORMER - CARRICKMINES 220-CARRICKMINES 220-PST2201 | 5 | 5 | 5 | Scheduled | 15/05/2023 | 19/05/2023
TO-23-220 kV A2 @ PB-01 | BUSBAR SECTION - POOLBEG 220-POOLBEG 220-220A2 | 9 | 7 | 7 | Scheduled | 15/05/2023 | 23/05/2023
TO-23-220 kV B2 @ PB-01 | BUSBAR SECTION - POOLBEG 220-POOLBEG 220-220B2 | 9 | 7 | 7 | Scheduled | 15/05/2023 | 23/05/2023
TO-23-PB-220K2-3-03 | COUPLER/SECTIONALISING CB - POOLBEG 220-POOLBEG 220-220K2-3 | 5 | 5 | 5 | Scheduled | 15/05/2023 | 19/05/2023
TO-23-PB-220SA1-2-04 | SECTIONALISING DISCONNECT - POOLBEG 220-POOLBEG 220-220SA1-2 | 9 | 7 | 7 | Scheduled | 15/05/2023 | 23/05/2023
TO-23-PB-220SA1-2-03 | SECTIONALISING DISCONNECT - POOLBEG 220-POOLBEG 220-220SA1-2 | 5 | 5 | 5 | Scheduled | 15/05/2023 | 19/05/2023
TO-23-PB-220SB1-2-03 | SECTIONALISING DISCONNECT - POOLBEG 220-POOLBEG 220-220SB1-2 | 9 | 7 | 7 | Scheduled | 15/05/2023 | 23/05/2023
TO-23-PB-220SB1-2-04 | SECTIONALISING DISCONNECT - POOLBEG 220-POOLBEG 220-220SB1-2 | 5 | 5 | 5 | Scheduled | 15/05/2023 | 19/05/2023
TO-23-110 kV A1 @ CBT-04 | BUSBAR SECTION - CASTLEBAGOT 110-CASTLEBAGOT 110-110A1 | 5 | 5 | 5 | Scheduled | 22/05/2023 | 26/05/2023
TO-23-110 kV A2 @ CBT-01 | BUSBAR SECTION - CASTLEBAGOT 110-CASTLEBAGOT 110-110A2 | 5 | 5 | 5 | Scheduled | 22/05/2023 | 26/05/2023
TO-23-CBT-110K1-06 | COUPLER/SECTIONALISING CB - CASTLEBAGOT 110-CASTLEBAGOT 110-110K1 | 5 | 5 | 5 | Scheduled | 22/05/2023 | 26/05/2023
TO-23-CBT-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - CASTLEBAGOT 110-CASTLEBAGOT 110-110SA1-2CB | 5 | 5 | 5 | Scheduled | 22/05/2023 | 26/05/2023
TO-23-CBT-110SA2-4CB-07 | COUPLER/SECTIONALISING CB - CASTLEBAGOT 110-CASTLEBAGOT 110-110SA2-4CB | 5 | 5 | 5 | Scheduled | 22/05/2023 | 26/05/2023
TO-23-PB-T2007/8-03 | GENERATOR TRANSFORMER - POOLBEG 220-POOLBEG G7/8-T2007/8 | 3 | 3 | 3 | Scheduled | 24/05/2023 | 26/05/2023
TO-23-CKM-PB-1-04 | 220kV FEEDER - CARRICKMINES 220-POOLBEG 220-1 | 3 | 1 | 1 | Scheduled | 26/05/2023 | 28/05/2023
TO-23-CKM-PST2201-04 | TRANSFORMER - CARRICKMINES 220-CARRICKMINES 220-PST2201 | 3 | 1 | 1 | Scheduled | 26/05/2023 | 28/05/2023
TO-23-HN-T2002-01 | GENERATOR TRANSFORMER - HUNTSTOWN 220-HUNTSTOWN G2-T2002 | 16 | 10 | 10 | Scheduled | 26/05/2023 | 10/06/2023
TO-23-INC-PB-1-02 | 220kV FEEDER - INCHICORE 220-POOLBEG 220-1 | 3 | 1 | 1 | Scheduled | 26/05/2023 | 28/05/2023
TO-23-PB-220K2-3-04 | COUPLER/SECTIONALISING CB - POOLBEG 220-POOLBEG 220-220K2-3 | 3 | 1 | 1 | Scheduled | 26/05/2023 | 28/05/2023
TO-23-PB-220SA1-2-02 | SECTIONALISING DISCONNECT - POOLBEG 220-POOLBEG 220-220SA1-2 | 3 | 1 | 1 | Scheduled | 26/05/2023 | 28/05/2023
TO-23-PB-220SB1-2-02 | SECTIONALISING DISCONNECT - POOLBEG 220-POOLBEG 220-220SB1-2 | 3 | 1 | 1 | Scheduled | 26/05/2023 | 28/05/2023
TO-23-PB-R2001-03 | CAPACITOR/SVC/REACTOR - POOLBEG 220-POOLBEG 220-R2001 | 3 | 1 | 1 | Scheduled | 26/05/2023 | 28/05/2023
TO-23-220 kV A1 @ CDU-02 | BUSBAR SECTION - CORDUFF 220-CORDUFF 220-220A1 | 13 | 9 | 9 | Scheduled | 29/05/2023 | 10/06/2023
TO-23-220 kV B1 @ CDU-02 | BUSBAR SECTION - CORDUFF 220-CORDUFF 220-220B1 | 13 | 9 | 9 | Scheduled | 29/05/2023 | 10/06/2023
TO-23-CDU-HN-1-01 | 220kV FEEDER - CORDUFF 220-HUNTSTOWN 220-1 | 13 | 9 | 9 | Scheduled | 29/05/2023 | 10/06/2023
TO-23-110 kV A1 @ SNU-03 | BUSBAR SECTION - SNUGBOROUGH 110-SNUGBOROUGH 110-110A1 | 3 | 3 | 3 | Scheduled | 29/05/2023 | 31/05/2023
TO-23-110 kV B1 @ SNU-03 | BUSBAR SECTION - SNUGBOROUGH 110-SNUGBOROUGH 110-110B1 | 3 | 3 | 3 | Scheduled | 29/05/2023 | 31/05/2023
TO-23-SNU-110K1-03 | COUPLER/SECTIONALISING CB - SNUGBOROUGH 110-SNUGBOROUGH 110-110K1 | 3 | 3 | 3 | Scheduled | 29/05/2023 | 31/05/2023
TO-23-SNU-110SA1-2CB-03 | COUPLER/SECTIONALISING CB - SNUGBOROUGH 110-SNUGBOROUGH 110-110SA1-2CB | 3 | 3 | 3 | Scheduled | 29/05/2023 | 31/05/2023
TO-23-SNU-110SB1-2CB-03 | COUPLER/SECTIONALISING CB - SNUGBOROUGH 110-SNUGBOROUGH 110-110SB1-2CB | 3 | 3 | 3 | Scheduled | 29/05/2023 | 31/05/2023
TO-23-BNK-CBT-2-01 | 110kV FEEDER - BARNAKYLE 110-CASTLEBAGOT 110-2 | 2 | 2 | 2 | Scheduled | 30/05/2023 | 31/05/2023
TO-23-110 kV A1 @ BAG-02 | BUSBAR SECTION - BARNAGEERAGH 110-BARNAGEERAGH 110-110A1 | 2 | 2 |  | Scheduled | 01/06/2023 | 02/06/2023
TO-23-110 kV B1 @ BAG-02 | BUSBAR SECTION - BARNAGEERAGH 110-BARNAGEERAGH 110-110B1 | 2 | 2 |  | Scheduled | 01/06/2023 | 02/06/2023
TO-23-BAG-110K1-01 | COUPLER/SECTIONALISING CB - BARNAGEERAGH 110-BARNAGEERAGH 110-110K1 | 2 | 2 |  | Scheduled | 01/06/2023 | 02/06/2023
TO-23-BAG-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - BARNAGEERAGH 110-BARNAGEERAGH 110-110SA1-2CB | 2 | 2 |  | Scheduled | 01/06/2023 | 02/06/2023
TO-23-BAG-110SB1-2CB-01 | COUPLER/SECTIONALISING CB - BARNAGEERAGH 110-BARNAGEERAGH 110-110SB1-2CB | 2 | 2 |  | Scheduled | 01/06/2023 | 02/06/2023
TO-23-110 kV A1 @ SNU-01 | BUSBAR SECTION - SNUGBOROUGH 110-SNUGBOROUGH 110-110A1 | 2 | 2 |  | Scheduled | 01/06/2023 | 02/06/2023
TO-23-110 kV B1 @ SNU-01 | BUSBAR SECTION - SNUGBOROUGH 110-SNUGBOROUGH 110-110B1 | 2 | 2 |  | Scheduled | 01/06/2023 | 02/06/2023
TO-23-SNU-110K1-02 | COUPLER/SECTIONALISING CB - SNUGBOROUGH 110-SNUGBOROUGH 110-110K1 | 2 | 2 |  | Scheduled | 01/06/2023 | 02/06/2023
TO-23-SNU-110SA1-2CB-02 | COUPLER/SECTIONALISING CB - SNUGBOROUGH 110-SNUGBOROUGH 110-110SA1-2CB | 2 | 2 |  | Scheduled | 01/06/2023 | 02/06/2023
TO-23-SNU-110SB1-2CB-02 | COUPLER/SECTIONALISING CB - SNUGBOROUGH 110-SNUGBOROUGH 110-110SB1-2CB | 2 | 2 |  | Scheduled | 01/06/2023 | 02/06/2023
TO-23-220 kV A4 @ CDU-01 | BUSBAR SECTION - CORDUFF 220-CORDUFF 220-220A4 | 60 | 44 | 44 | Scheduled | 06/06/2023 | 04/08/2023
TO-23-220 kV B4 @ CDU-01 | BUSBAR SECTION - CORDUFF 220-CORDUFF 220-220B4 | 60 | 44 | 44 | Scheduled | 06/06/2023 | 04/08/2023
TO-23-CRU-T221-01 | TSO CUSTOMER TRANSFORMER - CRUISERATH 220-CRUISERATH 20-T221 | 4 | 4 | 4 | Scheduled | 06/06/2023 | 09/06/2023
TO-23-110 kV A1 @ PA-01 | BUSBAR SECTION - POLLAPHUCA 110-POLLAPHUCA 110-110A1 | 17 | 13 | 13 | Scheduled | 07/06/2023 | 23/06/2023
TO-23-110 kV A2 @ PA-01 | BUSBAR SECTION - POLLAPHUCA 110-POLLAPHUCA 110-110A2 | 17 | 13 | 13 | Scheduled | 07/06/2023 | 23/06/2023
TO-23-PA-110SA1-01 | SECTIONALISING DISCONNECT - POLLAPHUCA 110-POLLAPHUCA 110-110SA1 | 17 | 13 | 13 | Scheduled | 07/06/2023 | 23/06/2023
TO-23-PA-110SA2-01 | SECTIONALISING DISCONNECT - POLLAPHUCA 110-POLLAPHUCA 110-110SA2 | 17 | 13 | 13 | Scheduled | 07/06/2023 | 23/06/2023
TO-23-220 kV A1 @ WOO-01 | BUSBAR SECTION - WOODLAND 220-WOODLAND 220-220A1 | 45 | 33 | 33 | Scheduled | 07/06/2023 | 21/07/2023
TO-23-INC-PB-1-04 | 220kV FEEDER - INCHICORE 220-POOLBEG 220-1 | 2 | 2 | 2 | Scheduled | 08/06/2023 | 09/06/2023
TO-23-PA-T101-01 | GENERATOR TRANSFORMER - POLLAPHUCA 110-POLLAPHUCA G1-T101 | 51 | 37 | 37 | Scheduled | 08/06/2023 | 28/07/2023
TO-23-220 kV A1 @ PB-02 | BUSBAR SECTION - POOLBEG 220-POOLBEG 220-220A1 | 2 | 2 | 2 | Scheduled | 08/06/2023 | 09/06/2023
TO-23-220 kV A2 @ PB-02 | BUSBAR SECTION - POOLBEG 220-POOLBEG 220-220A2 | 2 | 2 | 2 | Scheduled | 08/06/2023 | 09/06/2023
TO-23-220 kV B1 @ PB-02 | BUSBAR SECTION - POOLBEG 220-POOLBEG 220-220B1 | 2 | 2 | 2 | Scheduled | 08/06/2023 | 09/06/2023
TO-23-220 kV B2 @ PB-02 | BUSBAR SECTION - POOLBEG 220-POOLBEG 220-220B2 | 2 | 2 | 2 | Scheduled | 08/06/2023 | 09/06/2023
TO-23-PB-220SA1-2-05 | SECTIONALISING DISCONNECT - POOLBEG 220-POOLBEG 220-220SA1-2 | 2 | 2 | 2 | Scheduled | 08/06/2023 | 09/06/2023
TO-23-PB-220SB1-2-05 | SECTIONALISING DISCONNECT - POOLBEG 220-POOLBEG 220-220SB1-2 | 2 | 2 | 2 | Scheduled | 08/06/2023 | 09/06/2023
TO-23-CRU-T223-01 | TSO CUSTOMER TRANSFORMER - CRUISERATH 220-CRUISERATH 20-T223 | 4 | 4 | 4 | Scheduled | 12/06/2023 | 15/06/2023
TO-23-FIN-NW-1-03 | 220kV FEEDER - FINGLAS 220-NORTH WALL 220-1 | 13 | 10 | 10 | Scheduled | 12/06/2023 | 24/06/2023
TO-23-KYT-T232-01 | TSO CUSTOMER TRANSFORMER - KELLYSTOWN 220-KELLYSTOWN 34.5-T232 | 2 | 2 | 2 | Scheduled | 12/06/2023 | 13/06/2023
TO-23-NW-PB-1-03 | 220kV FEEDER - NORTH WALL 220-POOLBEG 220-1 | 13 | 10 | 10 | Scheduled | 12/06/2023 | 24/06/2023
TO-23-NW-T2004/5-01 | GENERATOR TRANSFORMER - NORTH WALL 220-NORTH WALL G4/5-T2004/5 | 13 | 10 | 10 | Scheduled | 12/06/2023 | 24/06/2023
TO-23-110 kV A6 @ FIN GIS-01 | BUSBAR SECTION - FINGLAS GIS 110-FINGLAS GIS 110-110A6 | 1 | 1 | 1 | Scheduled | 13/06/2023 | 13/06/2023
TO-23-110 kV B6 @ FIN GIS-01 | BUSBAR SECTION - FINGLAS GIS 110-FINGLAS GIS 110-110B6 | 1 | 1 | 1 | Scheduled | 13/06/2023 | 13/06/2023
TO-23-FIN GIS-110K6-02 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110K6 | 1 | 1 | 1 | Scheduled | 13/06/2023 | 13/06/2023
TO-23-FIN GIS-110SA4-6CB-01 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110SA4-6CB | 1 | 1 | 1 | Scheduled | 13/06/2023 | 13/06/2023
TO-23-FIN GIS-110SB4-6CB-01 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110SB4-6CB | 1 | 1 | 1 | Scheduled | 13/06/2023 | 13/06/2023
TO-23-KYT-T233-02 | TSO CUSTOMER TRANSFORMER - KELLYSTOWN 220-KELLYSTOWN 34.5-T233 | 2 | 2 | 2 | Scheduled | 14/06/2023 | 15/06/2023
TO-23-CDU-GLN-1-05 | 110kV FEEDER - CORDUFF 110-GALLANSTOWN 110-1 | 31 | 22 | 22 | Scheduled | 15/06/2023 | 15/07/2023
TO-23-OST-WOO-1-02 | 400kV FEEDER - OLDSTREET 400-WOODLAND 400-1 | 16 | 12 | 12 | Scheduled | 15/06/2023 | 30/06/2023
TO-23-220 kV B1 @ TH-03 | BUSBAR SECTION - TURLOUGH HILL 220-TURLOUGH HILL 220-220B1 | 1 | 1 | 1 | Scheduled | 16/06/2023 | 16/06/2023
TO-23-TH-T2001/2-02 | GENERATOR TRANSFORMER - TURLOUGH HILL 220-TURLOUGH HILL G1-T2001/2 | 1 | 1 | 1 | Scheduled | 16/06/2023 | 16/06/2023
TO-23-220 kV A1 @ INC-02 | BUSBAR SECTION - INCHICORE 220-INCHICORE 220-220A1 | 1 | 1 | 1 | Scheduled | 22/06/2023 | 22/06/2023
TO-23-220 kV A2 @ INC-02 | BUSBAR SECTION - INCHICORE 220-INCHICORE 220-220A2 | 1 | 1 | 1 | Scheduled | 22/06/2023 | 22/06/2023
TO-23-220 kV B1 @ INC-02 | BUSBAR SECTION - INCHICORE 220-INCHICORE 220-220B1 | 1 | 1 | 1 | Scheduled | 22/06/2023 | 22/06/2023
TO-23-220 kV B2 @ INC-02 | BUSBAR SECTION - INCHICORE 220-INCHICORE 220-220B2 | 1 | 1 | 1 | Scheduled | 22/06/2023 | 22/06/2023
TO-23-INC-220K1-2-03 | COUPLER/SECTIONALISING CB - INCHICORE 220-INCHICORE 220-220K1-2 | 1 | 1 | 1 | Scheduled | 22/06/2023 | 22/06/2023
TO-23-ISH-T2001-01 | GENERATOR TRANSFORMER - IRISHTOWN 220-IRISHTOWN G1-T2001 | 8 | 5 | 5 | Scheduled | 25/06/2023 | 02/07/2023
TO-23-BLC-DND-3-01 | 110kV FEEDER - BELCAMP 110-DARNDALE 110-3 | 2 | 2 | 2 | Scheduled | 28/06/2023 | 29/06/2023
TO-23-110 kV A2 @ DND-02 | BUSBAR SECTION - DARNDALE 110-DARNDALE 110-110A2 | 2 | 2 | 2 | Scheduled | 28/06/2023 | 29/06/2023
TO-23-110 kV B2 @ DND-02 | BUSBAR SECTION - DARNDALE 110-DARNDALE 110-110B2 | 2 | 2 | 2 | Scheduled | 28/06/2023 | 29/06/2023
TO-23-DND-110K2-03 | COUPLER/SECTIONALISING CB - DARNDALE 110-DARNDALE 110-110K2 | 2 | 2 | 2 | Scheduled | 28/06/2023 | 29/06/2023
TO-23-DND-110SA1-2CB-02 | COUPLER/SECTIONALISING CB - DARNDALE 110-DARNDALE 110-110SA1-2CB | 2 | 2 | 2 | Scheduled | 28/06/2023 | 29/06/2023
TO-23-DND-110SB1-2CB-03 | COUPLER/SECTIONALISING CB - DARNDALE 110-DARNDALE 110-110SB1-2CB | 2 | 2 | 2 | Scheduled | 28/06/2023 | 29/06/2023
TO-23-220 kV A1 @ TH-02 | BUSBAR SECTION - TURLOUGH HILL 220-TURLOUGH HILL 220-220A1 | 12 | 10 | 10 | Scheduled | 03/07/2023 | 14/07/2023
TO-23-220 kV B1 @ TH-02 | BUSBAR SECTION - TURLOUGH HILL 220-TURLOUGH HILL 220-220B1 | 12 | 10 | 10 | Scheduled | 03/07/2023 | 14/07/2023
TO-23-BRT-T222-01 | TSO CUSTOMER TRANSFORMER - BRACETOWN 220-BRACETOWN 20-T222 | 5 | 5 | 5 | Scheduled | 10/07/2023 | 14/07/2023
TO-23-220 kV A1 @ DSN-02 | BUSBAR SECTION - DUNSTOWN 220-DUNSTOWN 220-220A1 | 5 | 5 | 5 | Scheduled | 10/07/2023 | 14/07/2023
TO-23-220 kV B1 @ DSN-02 | BUSBAR SECTION - DUNSTOWN 220-DUNSTOWN 220-220B1 | 5 | 5 | 5 | Scheduled | 10/07/2023 | 14/07/2023
TO-23-INC-ISH-1-03 | 220kV FEEDER - INCHICORE 220-IRISHTOWN 220-1 | 19 | 15 | 15 | Scheduled | 17/07/2023 | 04/08/2023
TO-23-110 kV A2 @ MAY-02 | BUSBAR SECTION - MAYNOOTH 110-MAYNOOTH 110-110A2 | 12 | 10 | 10 | Scheduled | 17/07/2023 | 28/07/2023
TO-23-110 kV A3 @ MAY-02 | BUSBAR SECTION - MAYNOOTH 110-MAYNOOTH 110-110A3 | 12 | 10 | 10 | Scheduled | 17/07/2023 | 28/07/2023
TO-23-110 kV B2 @ MAY-02 | BUSBAR SECTION - MAYNOOTH 110-MAYNOOTH 110-110B2 | 12 | 10 | 10 | Scheduled | 17/07/2023 | 28/07/2023
TO-23-110 kV B3 @ MAY-02 | BUSBAR SECTION - MAYNOOTH 110-MAYNOOTH 110-110B3 | 12 | 10 | 10 | Scheduled | 17/07/2023 | 28/07/2023
TO-23-220 kV A1 @ MAY-05 | BUSBAR SECTION - MAYNOOTH 220-MAYNOOTH 220-220A1 | 12 | 10 | 10 | Scheduled | 17/07/2023 | 28/07/2023
TO-23-220 kV B1 @ MAY-05 | BUSBAR SECTION - MAYNOOTH 220-MAYNOOTH 220-220B1 | 12 | 10 | 10 | Scheduled | 17/07/2023 | 28/07/2023
TO-23-MAY-T2102-01 | TRANSFORMER - MAYNOOTH 220-MAYNOOTH 110-T2102 | 12 | 10 | 10 | Scheduled | 17/07/2023 | 28/07/2023
TO-23-COL-FIN GIS-1-04 | 110kV FEEDER - COLLEGE PARK 110-FINGLAS GIS 110-1 | 2 | 2 |  | Scheduled | 20/07/2023 | 21/07/2023
TO-23-110 kV B2 @ CBT-03 | BUSBAR SECTION - CASTLEBAGOT 110-CASTLEBAGOT 110-110B2 | 1 | 1 | 1 | Scheduled | 31/07/2023 | 31/07/2023
TO-23-110 kV B4 @ CBT-03 | BUSBAR SECTION - CASTLEBAGOT 110-CASTLEBAGOT 110-110B4 | 1 | 1 | 1 | Scheduled | 31/07/2023 | 31/07/2023
TO-23-CBT-110SB2-4CB-01 | COUPLER/SECTIONALISING CB - CASTLEBAGOT 110-CASTLEBAGOT 110-110SB2-4CB | 1 | 1 | 1 | Scheduled | 31/07/2023 | 31/07/2023
TO-23-MCE-110SA2-01 | SECTIONALISING DISCONNECT - MACETOWN 110-MACETOWN 110-110SA2 | 5 | 5 | 5 | Scheduled | 31/07/2023 | 04/08/2023
TO-23-MCE-SNU-1-01 | 110kV FEEDER - MACETOWN 110-SNUGBOROUGH 110-1 | 5 | 5 | 5 | Scheduled | 31/07/2023 | 04/08/2023
TO-23-MCE-T102-01 | DISTRIBUTION TRANSFORMER - MACETOWN 110-MACETOWN 10-T102 | 5 | 5 | 5 | Reference | 31/07/2023 | 04/08/2023
TO-23-MCE-T124-01 | TSO CUSTOMER TRANSFORMER - MACETOWN 110-MACETOWN 20-T124 | 5 | 5 | 5 | Scheduled | 31/07/2023 | 04/08/2023
TO-23-PB-R2001-01 | CAPACITOR/SVC/REACTOR - POOLBEG 220-POOLBEG 220-R2001 | 5 | 5 |  | Scheduled | 31/07/2023 | 04/08/2023
TO-23-110 kV A2 @ CBT-02 | BUSBAR SECTION - CASTLEBAGOT 110-CASTLEBAGOT 110-110A2 | 1 | 1 | 1 | Scheduled | 01/08/2023 | 01/08/2023
TO-23-110 kV A4 @ CBT-02 | BUSBAR SECTION - CASTLEBAGOT 110-CASTLEBAGOT 110-110A4 | 1 | 1 | 1 | Scheduled | 01/08/2023 | 01/08/2023
TO-23-CBT-110SA2-4CB-01 | COUPLER/SECTIONALISING CB - CASTLEBAGOT 110-CASTLEBAGOT 110-110SA2-4CB | 1 | 1 | 1 | Scheduled | 01/08/2023 | 01/08/2023
TO-23-BRT-T224-01 | TSO CUSTOMER TRANSFORMER - BRACETOWN 220-BRACETOWN 20-T224 | 7 | 4 | 4 | Scheduled | 02/08/2023 | 08/08/2023
TO-23-400 kV A2 @ DSN-01 | BUSBAR SECTION - DUNSTOWN 400-DUNSTOWN 400-400A2 | 36 | 25 | 25 | Scheduled | 04/08/2023 | 08/09/2023
TO-23-400 kV B2 @ DSN-01 | BUSBAR SECTION - DUNSTOWN 400-DUNSTOWN 400-400B2 | 36 | 25 | 25 | Scheduled | 04/08/2023 | 08/09/2023
TO-23-DSN-T4202-01 | TRANSFORMER - DUNSTOWN 400-DUNSTOWN 220-T4202 | 41 | 28 | 28 | Scheduled | 04/08/2023 | 13/09/2023
TO-23-INC-MAY-2-07 | 220kV FEEDER - INCHICORE 220-MAYNOOTH 220-2 | 12 | 10 | 10 | Scheduled | 14/08/2023 | 25/08/2023
TO-23-BEG-CKM GIS-1-01 | 110kV FEEDER - BALLYBEG 110-CARRICKMINES GIS 110-1 | 8 | 6 | 6 | Scheduled | 15/08/2023 | 22/08/2023
TO-23-DSN-KLS-1-05 | 220kV FEEDER - DUNSTOWN 220-KELLIS 220-1 | 2 | 0 | 0 | Scheduled | 19/08/2023 | 20/08/2023
TO-23-220 kV A2 @ DSN-02 | BUSBAR SECTION - DUNSTOWN 220-DUNSTOWN 220-220A2 | 19 | 15 | 15 | Scheduled | 21/08/2023 | 08/09/2023
TO-23-220 kV B2 @ DSN-02 | BUSBAR SECTION - DUNSTOWN 220-DUNSTOWN 220-220B2 | 19 | 15 | 15 | Scheduled | 21/08/2023 | 08/09/2023
TO-23-110 kV A2 @ FIN GIS-08 | BUSBAR SECTION - FINGLAS GIS 110-FINGLAS GIS 110-110A2 | 5 | 5 | 5 | Scheduled | 21/08/2023 | 25/08/2023
TO-23-110 kV B2 @ FIN GIS-07 | BUSBAR SECTION - FINGLAS GIS 110-FINGLAS GIS 110-110B2 | 5 | 5 | 5 | Scheduled | 21/08/2023 | 25/08/2023
TO-23-FIN GIS-110K2-09 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110K2 | 5 | 5 | 5 | Scheduled | 21/08/2023 | 25/08/2023
TO-23-FIN GIS-110SA1-2CB-09 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110SA1-2CB | 5 | 5 | 5 | Scheduled | 21/08/2023 | 25/08/2023
TO-23-FIN GIS-110SA2-4CB-09 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110SA2-4CB | 5 | 5 | 5 | Scheduled | 21/08/2023 | 25/08/2023
TO-23-FIN GIS-110SB1-2CB-09 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110SB1-2CB | 5 | 5 | 5 | Scheduled | 21/08/2023 | 25/08/2023
TO-23-FIN GIS-110SB2-4CB-09 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110SB2-4CB | 5 | 5 | 5 | Scheduled | 21/08/2023 | 25/08/2023
TO-23-FIN-FIN GIS-1-03 | 110kV FEEDER - FINGLAS 110-FINGLAS GIS 110-1 | 2 | 2 | 2 | Scheduled | 24/08/2023 | 25/08/2023
TO-23-110 kV A2 @ FIN GIS-06 | BUSBAR SECTION - FINGLAS GIS 110-FINGLAS GIS 110-110A2 | 2 | 2 | 2 | Scheduled | 24/08/2023 | 25/08/2023
TO-23-110 kV A4 @ FIN GIS-03 | BUSBAR SECTION - FINGLAS GIS 110-FINGLAS GIS 110-110A4 | 2 | 2 | 2 | Scheduled | 24/08/2023 | 25/08/2023
TO-23-110 kV B2 @ FIN GIS-05 | BUSBAR SECTION - FINGLAS GIS 110-FINGLAS GIS 110-110B2 | 2 | 2 | 2 | Scheduled | 24/08/2023 | 25/08/2023
TO-23-110 kV B4 @ FIN GIS-03 | BUSBAR SECTION - FINGLAS GIS 110-FINGLAS GIS 110-110B4 | 2 | 2 | 2 | Scheduled | 24/08/2023 | 25/08/2023
TO-23-FIN GIS-110K2-08 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110K2 | 2 | 2 | 2 | Scheduled | 24/08/2023 | 25/08/2023
TO-23-FIN GIS-110SA1-2CB-08 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110SA1-2CB | 2 | 2 | 2 | Scheduled | 24/08/2023 | 25/08/2023
TO-23-FIN GIS-110SA2-4CB-08 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110SA2-4CB | 2 | 2 | 2 | Scheduled | 24/08/2023 | 25/08/2023
TO-23-FIN GIS-110SA4-6CB-05 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110SA4-6CB | 2 | 2 | 2 | Scheduled | 24/08/2023 | 25/08/2023
TO-23-FIN GIS-110SB1-2CB-08 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110SB1-2CB | 2 | 2 | 2 | Scheduled | 24/08/2023 | 25/08/2023
TO-23-FIN GIS-110SB2-4CB-08 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110SB2-4CB | 2 | 2 | 2 | Scheduled | 24/08/2023 | 25/08/2023
TO-23-FIN GIS-110SB4-6CB-05 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110SB4-6CB | 2 | 2 | 2 | Scheduled | 24/08/2023 | 25/08/2023
TO-23-PB-T2007/8-02 | GENERATOR TRANSFORMER - POOLBEG 220-POOLBEG G7/8-T2007/8 | 67 | 47 |  | Scheduled | 24/08/2023 | 29/10/2023
TO-23-LOU-WOO-1-02 | 220kV FEEDER - LOUTH 220-WOODLAND 220-1 | 3 | 1 | 1 | Scheduled | 25/08/2023 | 27/08/2023
TO-23-DSN-KLS-1-06 | 220kV FEEDER - DUNSTOWN 220-KELLIS 220-1 | 2 | 0 | 0 | Scheduled | 26/08/2023 | 27/08/2023
TO-23-CLE-T221-01 | TSO CUSTOMER TRANSFORMER - CLONEE 220-CLONEE 20-T221 | 29 | 21 | 21 | Scheduled | 28/08/2023 | 25/09/2023
TO-23-CLG-T124-01 | TSO CUSTOMER TRANSFORMER - CLOGHRAN 110-CLOGHRAN 20-T124 | 5 | 5 | 5 | Scheduled | 04/09/2023 | 08/09/2023
TO-23-SHL-T2014-01 | GENERATOR TRANSFORMER - SHELLYBANKS 220-SHELLYBANKS G4-T2014 | 1 | 1 | 1 | Scheduled | 06/09/2023 | 06/09/2023
TO-23-CKM GIS-DSN-1-04 | 220kV FEEDER - CARRICKMINES GIS 220-DUNSTOWN 220-1 | 6 | 5 | 5 | Scheduled | 11/09/2023 | 16/09/2023
TO-23-110 kV A1 @ CLG-03 | BUSBAR SECTION - CLOGHRAN 110-CLOGHRAN 110-110A1 | 5 | 5 | 5 | Scheduled | 11/09/2023 | 15/09/2023
TO-23-110 kV A2 @ CLG-01 | BUSBAR SECTION - CLOGHRAN 110-CLOGHRAN 110-110A2 | 5 | 5 | 5 | Scheduled | 11/09/2023 | 15/09/2023
TO-23-110 kV B1 @ CLG-03 | BUSBAR SECTION - CLOGHRAN 110-CLOGHRAN 110-110B1 | 5 | 5 | 5 | Scheduled | 11/09/2023 | 15/09/2023
TO-23-110 kV B2 @ CLG-01 | BUSBAR SECTION - CLOGHRAN 110-CLOGHRAN 110-110B2 | 5 | 5 | 5 | Scheduled | 11/09/2023 | 15/09/2023
TO-23-CLG-110K2-02 | COUPLER/SECTIONALISING CB - CLOGHRAN 110-CLOGHRAN 110-110K2 | 5 | 5 | 5 | Scheduled | 11/09/2023 | 15/09/2023
TO-23-CLG-110SA1-2CB-02 | COUPLER/SECTIONALISING CB - CLOGHRAN 110-CLOGHRAN 110-110SA1-2CB | 5 | 5 | 5 | Scheduled | 11/09/2023 | 15/09/2023
TO-23-CLG-110SB1-2CB-02 | COUPLER/SECTIONALISING CB - CLOGHRAN 110-CLOGHRAN 110-110SB1-2CB | 5 | 5 | 5 | Scheduled | 11/09/2023 | 15/09/2023
TO-23-CLG-T126-01 | TSO CUSTOMER TRANSFORMER - CLOGHRAN 110-CLOGHRAN 20-T126 | 5 | 5 | 5 | Scheduled | 11/09/2023 | 15/09/2023
TO-23-220 kV A1 @ DSN-01 | BUSBAR SECTION - DUNSTOWN 220-DUNSTOWN 220-220A1 | 12 | 10 | 10 | Scheduled | 11/09/2023 | 22/09/2023
TO-23-220 kV A2 @ DSN-01 | BUSBAR SECTION - DUNSTOWN 220-DUNSTOWN 220-220A2 | 12 | 10 | 10 | Scheduled | 11/09/2023 | 22/09/2023
TO-23-220 kV B1 @ DSN-01 | BUSBAR SECTION - DUNSTOWN 220-DUNSTOWN 220-220B1 | 12 | 10 | 10 | Scheduled | 11/09/2023 | 22/09/2023
TO-23-220 kV B2 @ DSN-01 | BUSBAR SECTION - DUNSTOWN 220-DUNSTOWN 220-220B2 | 12 | 10 | 10 | Scheduled | 11/09/2023 | 22/09/2023
TO-23-FIN-NW-1-05 | 220kV FEEDER - FINGLAS 220-NORTH WALL 220-1 | 5 | 5 | 5 | Scheduled | 11/09/2023 | 15/09/2023
TO-23-GRI-T141-02 | DISTRIBUTION TRANSFORMER - GRIFFINRATH 110-GRIFFINRATH 38-T141 | 12 | 10 | 10 | Reference | 11/09/2023 | 22/09/2023
TO-23-GRI,T-GCA-1-03 | 110kV FEEDER - GRIFFINRATH tee-GRANGE CASTLE 110-1 | 72 | 51 | 51 | Scheduled | 11/09/2023 | 21/11/2023
TO-23-GRI,T-MAY-1-03 | 110kV FEEDER - GRIFFINRATH tee-MAYNOOTH 110-1 | 12 | 10 | 10 | Scheduled | 11/09/2023 | 22/09/2023
TO-23-NW-PB-1-05 | 220kV FEEDER - NORTH WALL 220-POOLBEG 220-1 | 5 | 5 | 5 | Scheduled | 11/09/2023 | 15/09/2023
TO-23-NW-T2004/5-02 | GENERATOR TRANSFORMER - NORTH WALL 220-NORTH WALL G4/5-T2004/5 | 5 | 5 | 5 | Scheduled | 11/09/2023 | 15/09/2023
TO-23-BNK-CBT-1-01 | 110kV FEEDER - BARNAKYLE 110-CASTLEBAGOT 110-1 | 2 | 2 | 2 | Scheduled | 12/09/2023 | 13/09/2023
TO-23-FIN-NW-1-04 | 220kV FEEDER - FINGLAS 220-NORTH WALL 220-1 | 2 | 0 | 0 | Scheduled | 16/09/2023 | 17/09/2023
TO-23-NW-PB-1-02 | 220kV FEEDER - NORTH WALL 220-POOLBEG 220-1 | 2 | 0 | 0 | Scheduled | 16/09/2023 | 17/09/2023
TO-23-NW-T2004/5-03 | GENERATOR TRANSFORMER - NORTH WALL 220-NORTH WALL G4/5-T2004/5 | 2 | 0 | 0 | Scheduled | 16/09/2023 | 17/09/2023
TO-23-DSN-220K1-2-01 | COUPLER/SECTIONALISING CB - DUNSTOWN 220-DUNSTOWN 220-220K1-2 | 12 | 10 | 10 | Scheduled | 18/09/2023 | 29/09/2023
TO-23-110 kV A1/A2/A3/A4 @ CDU-02 | BUSBAR SECTION - CORDUFF 110-CORDUFF 110-110A1-A2-A3-A4 | 2 | 2 | 2 | Scheduled | 19/09/2023 | 20/09/2023
TO-23-CDU-110K1-2-02 | COUPLER/SECTIONALISING CB - CORDUFF 110-CORDUFF 110-110K1-2 | 2 | 2 | 2 | Scheduled | 19/09/2023 | 20/09/2023
TO-23-CDU-110K1-3-01 | COUPLER/SECTIONALISING CB - CORDUFF 110-CORDUFF 110-110K1-3 | 2 | 2 | 2 | Scheduled | 19/09/2023 | 20/09/2023
TO-23-CDU-110SA2-4-01 | SECTIONALISING DISCONNECT - CORDUFF 110-CORDUFF 110-110SA2-4 | 2 | 2 | 2 | Scheduled | 19/09/2023 | 20/09/2023
TO-23-CDU-SNU-1-03 | 110kV FEEDER - CORDUFF 110-SNUGBOROUGH 110-1 | 4 | 4 | 4 | Scheduled | 19/09/2023 | 22/09/2023
TO-23-110 kV B1/B2/B3/B4 @ CDU-02 | BUSBAR SECTION - CORDUFF 110-CORDUFF 110-110B1-B2-B3-B4 | 2 | 2 | 2 | Scheduled | 21/09/2023 | 22/09/2023
TO-23-CDU-110K1-2-03 | COUPLER/SECTIONALISING CB - CORDUFF 110-CORDUFF 110-110K1-2 | 2 | 2 | 2 | Scheduled | 21/09/2023 | 22/09/2023
TO-23-CDU-110K1-3-02 | COUPLER/SECTIONALISING CB - CORDUFF 110-CORDUFF 110-110K1-3 | 2 | 2 | 2 | Scheduled | 21/09/2023 | 22/09/2023
TO-23-CDU-110SB2-4-01 | SECTIONALISING DISCONNECT - CORDUFF 110-CORDUFF 110-110SB2-4 | 2 | 2 | 2 | Scheduled | 21/09/2023 | 22/09/2023
TO-23-PB-R223-4-03 | CAPACITOR/SVC/REACTOR - POOLBEG 220-POOLBEG 220-R223-4 | 1 | 0 | 0 | Scheduled | 23/09/2023 | 23/09/2023
TO-23-220 kV A1 @ CLE-02 | BUSBAR SECTION - CLONEE 220-CLONEE 220-220A1 | 2 | 2 | 2 | Scheduled | 27/09/2023 | 28/09/2023
TO-23-220 kV A2 @ CLE-02 | BUSBAR SECTION - CLONEE 220-CLONEE 220-220A2 | 2 | 2 | 2 | Scheduled | 27/09/2023 | 28/09/2023
TO-23-220 kV B1 @ CLE-01 | BUSBAR SECTION - CLONEE 220-CLONEE 220-220B1 | 2 | 2 | 2 | Scheduled | 27/09/2023 | 28/09/2023
TO-23-220 kV B2 @ CLE-01 | BUSBAR SECTION - CLONEE 220-CLONEE 220-220B2 | 2 | 2 | 2 | Scheduled | 27/09/2023 | 28/09/2023
TO-23-CLE-220K1-02 | COUPLER/SECTIONALISING CB - CLONEE 220-CLONEE 220-220K1 | 2 | 2 | 2 | Scheduled | 27/09/2023 | 28/09/2023
TO-23-CLE-220K2-03 | COUPLER/SECTIONALISING CB - CLONEE 220-CLONEE 220-220K2 | 2 | 2 | 2 | Scheduled | 27/09/2023 | 28/09/2023
TO-23-CLE-220SA1-2CB-02 | COUPLER/SECTIONALISING CB - CLONEE 220-CLONEE 220-220SA1-2CB | 2 | 2 | 2 | Scheduled | 27/09/2023 | 28/09/2023
TO-23-CLE-220SB1-2CB-01 | COUPLER/SECTIONALISING CB - CLONEE 220-CLONEE 220-220SB1-2CB | 2 | 2 | 2 | Scheduled | 27/09/2023 | 28/09/2023
TO-23-CLE-WOO-1-04 | 220kV FEEDER - CLONEE 220-WOODLAND 220-1 | 1 | 1 | 1 | Scheduled | 27/09/2023 | 27/09/2023
TO-23-CDU-WOO-1-03 | 220kV FEEDER - CORDUFF 220-WOODLAND 220-1 | 2 | 2 | 2 | Scheduled | 02/10/2023 | 03/10/2023
TO-23-110 kV A1 @ FIN GIS-03 | BUSBAR SECTION - FINGLAS GIS 110-FINGLAS GIS 110-110A1 | 2 | 2 | 2 | Scheduled | 02/10/2023 | 03/10/2023
TO-23-110 kV B1 @ FIN GIS-04 | BUSBAR SECTION - FINGLAS GIS 110-FINGLAS GIS 110-110B1 | 2 | 2 | 2 | Scheduled | 02/10/2023 | 03/10/2023
TO-23-FIN GIS-110K1-01 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110K1 | 2 | 2 | 2 | Scheduled | 02/10/2023 | 03/10/2023
TO-23-FIN GIS-110SA1-2CB-07 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110SA1-2CB | 2 | 2 | 2 | Scheduled | 02/10/2023 | 03/10/2023
TO-23-FIN GIS-110SA1-3CB-04 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110SA1-3CB | 2 | 2 | 2 | Scheduled | 02/10/2023 | 03/10/2023
TO-23-FIN GIS-110SB1-2CB-07 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110SB1-2CB | 2 | 2 | 2 | Scheduled | 02/10/2023 | 03/10/2023
TO-23-FIN GIS-110SB1-3CB-05 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110SB1-3CB | 2 | 2 | 2 | Scheduled | 02/10/2023 | 03/10/2023
TO-23-COL-CDU-1-02 | 110kV FEEDER - COLLEGE PARK 110-CORDUFF 110-1 | 3 | 3 | 3 | Scheduled | 03/10/2023 | 05/10/2023
TO-23-DSN-KLS-1-07 | 220kV FEEDER - DUNSTOWN 220-KELLIS 220-1 | 1 | 0 | 0 | Proposed | 07/10/2023 | 07/10/2023
TO-23-BLK,T-MAY-1-02 | 110kV FEEDER - BLAKE tee-MAYNOOTH 110-1 | 19 | 15 | 15 | Scheduled | 09/10/2023 | 27/10/2023
TO-23-110 kV A2 @ CDU-03 | BUSBAR SECTION - CORDUFF 110-CORDUFF 110-110A2 | 12 | 10 | 10 | Scheduled | 09/10/2023 | 20/10/2023
TO-23-110 kV A4 @ CDU-05 | BUSBAR SECTION - CORDUFF 110-CORDUFF 110-110A4 | 12 | 10 | 10 | Scheduled | 09/10/2023 | 20/10/2023
TO-23-110 kV B2 @ CDU-02 | BUSBAR SECTION - CORDUFF 110-CORDUFF 110-110B2 | 12 | 10 | 10 | Scheduled | 09/10/2023 | 20/10/2023
TO-23-110 kV B4 @ CDU-05 | BUSBAR SECTION - CORDUFF 110-CORDUFF 110-110B4 | 12 | 10 | 10 | Scheduled | 09/10/2023 | 20/10/2023
TO-23-BRT-220K2-01 | COUPLER/SECTIONALISING CB - BRACETOWN 220-BRACETOWN 220-220K2 | 1 | 1 | 1 | Scheduled | 10/10/2023 | 10/10/2023
TO-23-CKM-PB-1-05 | 220kV FEEDER - CARRICKMINES 220-POOLBEG 220-1 | 4 | 3 | 3 | Scheduled | 15/10/2023 | 18/10/2023
TO-23-CKM-PST2201-06 | TRANSFORMER - CARRICKMINES 220-CARRICKMINES 220-PST2201 | 4 | 3 |  | Scheduled | 15/10/2023 | 18/10/2023
TO-23-BAG-T103-01 | TSO CUSTOMER TRANSFORMER - BARNAGEERAGH 110-BARNAGEERAGH 11-T103 | 2 | 2 | 2 | Scheduled | 16/10/2023 | 17/10/2023
TO-23-CDU-MCE-1-02 | 110kV FEEDER - CORDUFF 110-MACETOWN 110-1 | 2 | 2 | 2 | Scheduled | 16/10/2023 | 17/10/2023
TO-23-MAY-SH-1-01 | 220kV FEEDER - MAYNOOTH 220-SHANNONBRIDGE 220-1 | 53 | 38 | 38 | Scheduled | 16/10/2023 | 07/12/2023
TO-23-110 kV A5 @ FIN GIS-02 | BUSBAR SECTION - FINGLAS GIS 110-FINGLAS GIS 110-110A5 | 3 | 3 | 3 | Scheduled | 17/10/2023 | 19/10/2023
TO-23-110 kV B5 @ FIN GIS-02 | BUSBAR SECTION - FINGLAS GIS 110-FINGLAS GIS 110-110B5 | 3 | 3 | 3 | Scheduled | 17/10/2023 | 19/10/2023
TO-23-FIN GIS-110K5-01 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110K5 | 3 | 3 | 3 | Scheduled | 17/10/2023 | 19/10/2023
TO-23-FIN GIS-110SA3-5CB-04 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110SA3-5CB | 3 | 3 | 3 | Scheduled | 17/10/2023 | 19/10/2023
TO-23-FIN GIS-110SB3-5CB-04 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110SB3-5CB | 3 | 3 | 3 | Scheduled | 17/10/2023 | 19/10/2023
TO-23-CDU-220K1-3-03 | COUPLER/SECTIONALISING CB - CORDUFF 220-CORDUFF 220-220K1-3 | 1 | 1 | 1 | Scheduled | 18/10/2023 | 18/10/2023
TO-23-DSN-T4201-04 | TRANSFORMER - DUNSTOWN 400-DUNSTOWN 220-T4201 | 2 | 2 | 2 | Scheduled | 18/10/2023 | 19/10/2023
TO-23-CKM GIS-220K4-02 | COUPLER/SECTIONALISING CB - CARRICKMINES GIS 220-CARRICKMINES GIS 220-220K4 | 5 | 5 | 5 | Scheduled | 23/10/2023 | 27/10/2023
TO-23-CKM GIS-220SA2-4CB-05 | COUPLER/SECTIONALISING CB - CARRICKMINES GIS 220-CARRICKMINES GIS 220-22SA2-4CB | 5 | 5 | 5 | Scheduled | 23/10/2023 | 27/10/2023
TO-23-CKM GIS-220SB2-4CB-05 | COUPLER/SECTIONALISING CB - CARRICKMINES GIS 220-CARRICKMINES GIS 220-22SB2-4CB | 5 | 5 | 5 | Scheduled | 23/10/2023 | 27/10/2023
TO-23-KYT-T237-01 | TSO CUSTOMER TRANSFORMER - KELLYSTOWN 220-KELLYSTOWN 34.5-T237 | 26 | 19 | 19 | Scheduled | 23/10/2023 | 17/11/2023
TO-23-220 kV A1 @ PB-04 | BUSBAR SECTION - POOLBEG 220-POOLBEG 220-220A1 | 5 | 5 |  | Scheduled | 23/10/2023 | 27/10/2023
TO-23-220 kV A2 @ PB-03 | BUSBAR SECTION - POOLBEG 220-POOLBEG 220-220A2 | 5 | 5 | 5 | Scheduled | 23/10/2023 | 27/10/2023
TO-23-220 kV B1 @ PB-04 | BUSBAR SECTION - POOLBEG 220-POOLBEG 220-220B1 | 5 | 5 |  | Scheduled | 23/10/2023 | 27/10/2023
TO-23-220 kV B2 @ PB-03 | BUSBAR SECTION - POOLBEG 220-POOLBEG 220-220B2 | 5 | 5 | 5 | Scheduled | 23/10/2023 | 27/10/2023
TO-23-PB-220SA1-2-06 | SECTIONALISING DISCONNECT - POOLBEG 220-POOLBEG 220-220SA1-2 | 5 | 5 | 5 | Scheduled | 23/10/2023 | 27/10/2023
TO-23-PB-220SB1-2-06 | SECTIONALISING DISCONNECT - POOLBEG 220-POOLBEG 220-220SB1-2 | 5 | 5 | 5 | Scheduled | 23/10/2023 | 27/10/2023
TO-23-INC-PB-1-05 | 220kV FEEDER - INCHICORE 220-POOLBEG 220-1 | 2 | 0 | 0 | Scheduled | 28/10/2023 | 29/10/2023
TO-23-220 kV A1 @ PB-03 | BUSBAR SECTION - POOLBEG 220-POOLBEG 220-220A1 | 2 | 0 | 0 | Scheduled | 28/10/2023 | 29/10/2023
TO-23-220 kV A2 @ PB-04 | BUSBAR SECTION - POOLBEG 220-POOLBEG 220-220A2 | 2 | 0 | 0 | Scheduled | 28/10/2023 | 29/10/2023
TO-23-220 kV B1 @ PB-03 | BUSBAR SECTION - POOLBEG 220-POOLBEG 220-220B1 | 2 | 0 | 0 | Scheduled | 28/10/2023 | 29/10/2023
TO-23-220 kV B2 @ PB-04 | BUSBAR SECTION - POOLBEG 220-POOLBEG 220-220B2 | 2 | 0 | 0 | Scheduled | 28/10/2023 | 29/10/2023
TO-23-PB-220SA1-2-07 | SECTIONALISING DISCONNECT - POOLBEG 220-POOLBEG 220-220SA1-2 | 2 | 0 | 0 | Scheduled | 28/10/2023 | 29/10/2023
TO-23-PB-220SB1-2-07 | SECTIONALISING DISCONNECT - POOLBEG 220-POOLBEG 220-220SB1-2 | 2 | 0 | 0 | Scheduled | 28/10/2023 | 29/10/2023
TO-23-DND-T124-01 | TSO CUSTOMER TRANSFORMER - DARNDALE 110-DARNDALE 20-T124 | 4 | 4 | 4 | Scheduled | 31/10/2023 | 03/11/2023
TO-23-PB-R2001-02 | CAPACITOR/SVC/REACTOR - POOLBEG 220-POOLBEG 220-R2001 | 4 | 4 | 4 | Scheduled | 31/10/2023 | 03/11/2023
TO-23-INC-ISH-1-04 | 220kV FEEDER - INCHICORE 220-IRISHTOWN 220-1 | 29 | 21 |  | Scheduled | 01/11/2023 | 29/11/2023
TO-23-ISH-220K1-2-02 | COUPLER/SECTIONALISING CB - IRISHTOWN 220-IRISHTOWN 220-220K1-2 | 29 | 21 |  | Scheduled | 01/11/2023 | 29/11/2023
TO-23-ISH-SHL-1-04 | 220kV FEEDER - IRISHTOWN 220-SHELLYBANKS 220-1 | 29 | 21 |  | Scheduled | 01/11/2023 | 29/11/2023
TO-23-BDA-MON-1-02 | 110kV FEEDER - BARODA 110-MONREAD 110-1 | 10 | 8 | 8 | Scheduled | 13/11/2023 | 22/11/2023
TO-23-220 kV B1 @ CKM GIS-03 | BUSBAR SECTION - CARRICKMINES GIS 220-CARRICKMINES GIS 220-220B1 | 12 | 10 | 10 | Scheduled | 13/11/2023 | 24/11/2023
TO-23-220 kV B2 @ CKM GIS-04 | BUSBAR SECTION - CARRICKMINES GIS 220-CARRICKMINES GIS 220-220B2 | 12 | 10 | 10 | Scheduled | 13/11/2023 | 24/11/2023
TO-23-CKM GIS-220SB1-2CB-02 | COUPLER/SECTIONALISING CB - CARRICKMINES GIS 220-CARRICKMINES GIS 220-22SB1-2CB | 12 | 10 | 10 | Scheduled | 13/11/2023 | 24/11/2023
TO-23-110 kV A2 @ DND-01 | BUSBAR SECTION - DARNDALE 110-DARNDALE 110-110A2 | 7 | 5 | 5 | Scheduled | 17/11/2023 | 23/11/2023
TO-23-110 kV B2 @ DND-01 | BUSBAR SECTION - DARNDALE 110-DARNDALE 110-110B2 | 7 | 5 | 16 | Scheduled | 17/11/2023 | 23/11/2023
TO-23-DND-110K2-02 | COUPLER/SECTIONALISING CB - DARNDALE 110-DARNDALE 110-110K2 | 7 | 5 | 5 | Scheduled | 17/11/2023 | 23/11/2023
TO-23-DND-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - DARNDALE 110-DARNDALE 110-110SA1-2CB | 7 | 5 | 5 | Scheduled | 17/11/2023 | 23/11/2023
TO-23-DND-110SB1-2CB-02 | COUPLER/SECTIONALISING CB - DARNDALE 110-DARNDALE 110-110SB1-2CB | 7 | 5 | 16 | Scheduled | 17/11/2023 | 23/11/2023
TO-23-BNK-T121-01 | TSO CUSTOMER TRANSFORMER - BARNAKYLE 110-BARNAKYLE 20-T121 | 2 | 2 | 2 | Scheduled | 20/11/2023 | 21/11/2023
TO-23-CKM GIS-220SB1-3CB-01 | COUPLER/SECTIONALISING CB - CARRICKMINES GIS 220-CARRICKMINES GIS 220-22SB1-3CB | 12 | 10 | 10 | Scheduled | 20/11/2023 | 01/12/2023
TO-23-SNU-110K1-01 | COUPLER/SECTIONALISING CB - SNUGBOROUGH 110-SNUGBOROUGH 110-110K1 | 1 | 1 | 1 | Scheduled | 21/11/2023 | 21/11/2023
TO-23-KTL-T141-01 | DISTRIBUTION TRANSFORMER - KILTEEL 110-KILTEEL 38-T141 | 2 | 2 | 2 | Reference | 22/11/2023 | 23/11/2023
TO-23-220 kV B1 @ CKM GIS-04 | BUSBAR SECTION - CARRICKMINES GIS 220-CARRICKMINES GIS 220-220B1 | 12 | 10 | 10 | Scheduled | 27/11/2023 | 08/12/2023
TO-23-220 kV B3 @ CKM GIS-03 | BUSBAR SECTION - CARRICKMINES GIS 220-CARRICKMINES GIS 220-220B3 | 12 | 10 | 10 | Scheduled | 27/11/2023 | 08/12/2023
TO-23-GRI-T141-03 | DISTRIBUTION TRANSFORMER - GRIFFINRATH 110-GRIFFINRATH 38-T141 | 5 | 5 | 5 | Reference (Proposed) | 27/11/2023 | 01/12/2023
TO-23-GRI,T-GCA-1-05 | 110kV FEEDER - GRIFFINRATH tee-GRANGE CASTLE 110-1 | 5 | 5 | 5 | Proposed | 27/11/2023 | 01/12/2023
TO-23-GRI,T-MAY-1-01 | 110kV FEEDER - GRIFFINRATH tee-MAYNOOTH 110-1 | 5 | 5 | 5 | Proposed | 27/11/2023 | 01/12/2023
TO-23-110 kV A2 @ MAY-03 | BUSBAR SECTION - MAYNOOTH 110-MAYNOOTH 110-110A2 | 5 | 5 | 5 | Proposed | 27/11/2023 | 01/12/2023
TO-23-110 kV B2 @ MAY-03 | BUSBAR SECTION - MAYNOOTH 110-MAYNOOTH 110-110B2 | 5 | 5 | 5 | Proposed | 27/11/2023 | 01/12/2023
TO-23-BLC-DND-3-02 | 110kV FEEDER - BELCAMP 110-DARNDALE 110-3 | 2 | 2 | 2 | Scheduled | 30/11/2023 | 01/12/2023
TO-23-110 kV A2 @ DND-03 | BUSBAR SECTION - DARNDALE 110-DARNDALE 110-110A2 | 2 | 2 | 2 | Scheduled | 30/11/2023 | 01/12/2023
TO-23-110 kV B2 @ DND-03 | BUSBAR SECTION - DARNDALE 110-DARNDALE 110-110B2 | 2 | 2 | 2 | Scheduled | 30/11/2023 | 01/12/2023
TO-23-DND-110K2-04 | COUPLER/SECTIONALISING CB - DARNDALE 110-DARNDALE 110-110K2 | 2 | 2 | 2 | Scheduled | 30/11/2023 | 01/12/2023
TO-23-DND-110SA1-2CB-03 | COUPLER/SECTIONALISING CB - DARNDALE 110-DARNDALE 110-110SA1-2CB | 2 | 2 | 2 | Scheduled | 30/11/2023 | 01/12/2023
TO-23-DND-110SB1-2CB-04 | COUPLER/SECTIONALISING CB - DARNDALE 110-DARNDALE 110-110SB1-2CB | 2 | 2 | 2 | Scheduled | 30/11/2023 | 01/12/2023
TO-23-DSN-T4201-02 | TRANSFORMER - DUNSTOWN 400-DUNSTOWN 220-T4201 | 2 | 2 | 2 | Scheduled | 30/11/2023 | 01/12/2023
TO-23-220 kV A2 @ ISH-01 | BUSBAR SECTION - IRISHTOWN 220-IRISHTOWN 220-220A2 | 14 | 10 | 10 | Scheduled | 30/11/2023 | 13/12/2023
TO-23-220 kV B2 @ ISH-01 | BUSBAR SECTION - IRISHTOWN 220-IRISHTOWN 220-220B2 | 14 | 10 | 10 | Scheduled | 30/11/2023 | 13/12/2023
TO-23-INC-T2101-01 | TRANSFORMER - INCHICORE 220-INCHICORE 110-T2101 | 15 | 11 | 11 | Reference | 01/12/2023 | 15/12/2023

## GEN_Cork
Outage ID | Feeder ID | Calendar Day Duration | Working Day Duration | Work Days | Outage Status | Start | Finish
TO-23-GGO-220K1-2-01 | COUPLER/SECTIONALISING CB - GLANAGOW 220-GLANAGOW 220-220K1-2 | 251 | 172 | 172 | Scheduled | 01/01/2023 | 08/09/2023
TO-23-KRA-220K1-03 | COUPLER/SECTIONALISING CB - KNOCKRAHA 220-KNOCKRAHA 220-220K1 | 33 | 24 | 24 | Scheduled | 30/01/2023 | 03/03/2023
TO-23-220 kV A2 @ AD-01 | BUSBAR SECTION - AGHADA 220-AGHADA 220-220A2 | 234 | 162 | 162 | Scheduled | 27/02/2023 | 18/10/2023
TO-23-220 kV B2 @ AD-01 | BUSBAR SECTION - AGHADA 220-AGHADA 220-220B2 | 234 | 162 | 162 | Scheduled | 27/02/2023 | 18/10/2023
TO-23-AD-SA1-2CB-01 | COUPLER/SECTIONALISING CB - AGHADA 220-AGHADA 220-220SA1-2CB | 234 | 162 | 162 | Scheduled | 27/02/2023 | 18/10/2023
TO-23-AD-SB1-2CB-01 | COUPLER/SECTIONALISING CB - AGHADA 220-AGHADA 220-220SB1-2CB | 234 | 162 | 162 | Scheduled | 27/02/2023 | 18/10/2023
TO-23-AD-T2001-03 | GENERATOR TRANSFORMER - AGHADA 220-AGHADA G1-T2001 | 234 | 162 | 162 | Scheduled | 27/02/2023 | 18/10/2023
TO-23-CVW-110SA1-01 | SECTIONALISING DISCONNECT - CASTLEVIEW 110-CASTLEVIEW 110-110SA1 | 3 | 3 | 3 | Scheduled | 27/02/2023 | 01/03/2023
TO-23-CVW-110SA2-01 | SECTIONALISING DISCONNECT - CASTLEVIEW 110-CASTLEVIEW 110-110SA2 | 3 | 3 | 3 | Scheduled | 27/02/2023 | 01/03/2023
TO-23-CVW-COW-1-02 | 110kV FEEDER - CASTLEVIEW 110-COW CROSS 110-1 | 3 | 3 | 3 | Scheduled | 27/02/2023 | 01/03/2023
TO-23-CVW-T101-01 | DISTRIBUTION TRANSFORMER - CASTLEVIEW 110-CASTLEVIEW 10-T101 | 3 | 3 | 3 | Reference | 27/02/2023 | 01/03/2023
TO-23-KRA-220K1-2-03 | COUPLER/SECTIONALISING CB - KNOCKRAHA 220-KNOCKRAHA 220-220K1-2 | 308 | 211 | 211 | Scheduled | 27/02/2023 | 31/12/2023
TO-23-CRO-KBY-1-01 | 110kV FEEDER - COOLROE 110-KILBARRY 110-1 | 1 | 1 | 1 | Scheduled | 01/03/2023 | 01/03/2023
TO-23-220 kV A1/A2 @ KRA-01 | BUSBAR SECTION - KNOCKRAHA 220-KNOCKRAHA 220-220A1-A2 | 46 | 29 | 29 | Scheduled | 03/03/2023 | 17/04/2023
TO-23-KRA-220K1-04 | COUPLER/SECTIONALISING CB - KNOCKRAHA 220-KNOCKRAHA 220-220K1 | 46 | 29 | 29 | Scheduled | 03/03/2023 | 17/04/2023
TO-23-KRA-220SA2-4CB-02 | COUPLER/SECTIONALISING CB - KNOCKRAHA 220-KNOCKRAHA 220-220SA2-4CB | 46 | 29 | 29 | Scheduled | 03/03/2023 | 17/04/2023
TO-23-COW-RAF-1-01 | 110kV FEEDER - COW CROSS 110-RAFFEEN 110-1 | 5 | 5 | 5 | Scheduled | 06/03/2023 | 10/03/2023
TO-23-110 kV A1 @ RAF-01 | BUSBAR SECTION - RAFFEEN 110-RAFFEEN 110-110A1 | 5 | 5 | 5 | Scheduled | 06/03/2023 | 10/03/2023
TO-23-110 kV B1 @ RAF-01 | BUSBAR SECTION - RAFFEEN 110-RAFFEEN 110-110B1 | 5 | 5 | 5 | Scheduled | 06/03/2023 | 10/03/2023
TO-23-110 kV A2 @ RAF-02 | BUSBAR SECTION - RAFFEEN 110-RAFFEEN 110-110A2 | 18 | 14 | 14 | Scheduled | 20/03/2023 | 06/04/2023
TO-23-110 kV B2 @ RAF-02 | BUSBAR SECTION - RAFFEEN 110-RAFFEEN 110-110B2 | 18 | 14 | 14 | Scheduled | 20/03/2023 | 06/04/2023
TO-23-RAF-TBG-2-01 | 110kV FEEDER - RAFFEEN 110-TRABEG 110-2 | 18 | 14 | 14 | Scheduled | 20/03/2023 | 06/04/2023
TO-23-110 kV A1 @ CLA-01 | BUSBAR SECTION - CLASHAVOON 110-CLASHAVOON 110-110A1 | 5 | 5 | 5 | Scheduled | 27/03/2023 | 31/03/2023
TO-23-110 kV B1 @ CLA-01 | BUSBAR SECTION - CLASHAVOON 110-CLASHAVOON 110-110B1 | 5 | 5 | 5 | Scheduled | 27/03/2023 | 31/03/2023
TO-23-CLA-MAC-1-03 | 110kV FEEDER - CLASHAVOON 110-MACROOM 110-1 | 5 | 5 | 5 | Scheduled | 27/03/2023 | 31/03/2023
TO-23-CLA-MAC-2-01 | 110kV FEEDER - CLASHAVOON 110-MACROOM 110-2 | 9 | 5 | 5 | Scheduled | 03/04/2023 | 11/04/2023
TO-23-CVW-KRA-1-01 | 110kV FEEDER - CASTLEVIEW 110-KNOCKRAHA 110-1 | 3 | 3 | 3 | Scheduled | 11/04/2023 | 13/04/2023
TO-23-IA-T101-02 | GENERATOR TRANSFORMER - INNISCARRA 110-INNISCARRA G1-T101 | 9 | 7 | 7 | Scheduled | 18/04/2023 | 26/04/2023
TO-23-220 kV B1/B2 @ KRA-01 | BUSBAR SECTION - KNOCKRAHA 220-KNOCKRAHA 220-220B1-B2 | 131 | 91 |  | Scheduled | 18/04/2023 | 26/08/2023
TO-23-KRA-220K1-05 | COUPLER/SECTIONALISING CB - KNOCKRAHA 220-KNOCKRAHA 220-220K1 | 131 | 91 |  | Scheduled | 18/04/2023 | 26/08/2023
TO-23-KRA-220SB1-2CB-01 | COUPLER/SECTIONALISING CB - KNOCKRAHA 220-KNOCKRAHA 220-220SB1-2CB | 131 | 91 | 91 | Scheduled | 18/04/2023 | 26/08/2023
TO-23-KRA-220SB2-4CB-02 | COUPLER/SECTIONALISING CB - KNOCKRAHA 220-KNOCKRAHA 220-220SB2-4CB | 131 | 91 |  | Scheduled | 18/04/2023 | 26/08/2023
TO-23-DMY-MAC-1-03 | 110kV FEEDER - DUNMANWAY 110-MACROOM 110-1 | 5 | 5 | 5 | Scheduled | 24/04/2023 | 28/04/2023
TO-23-110 kV A2 @ KBY-03 | BUSBAR SECTION - KILBARRY 110-KILBARRY 110-110A2 | 1 | 1 | 1 | Scheduled | 03/05/2023 | 03/05/2023
TO-23-110 kV B2 @ KBY-01 | BUSBAR SECTION - KILBARRY 110-KILBARRY 110-110B2 | 1 | 1 | 1 | Scheduled | 03/05/2023 | 03/05/2023
TO-23-KBY-MR-1-01 | 110kV FEEDER - KILBARRY 110-MARINA 110-1 | 93 | 66 | 66 | Scheduled | 03/05/2023 | 03/08/2023
TO-23-KBY-MR-2-03 | 110kV FEEDER - KILBARRY 110-MARINA 110-2 | 93 | 66 | 66 | Scheduled | 03/05/2023 | 03/08/2023
TO-23-RAF-220K1-2-01 | COUPLER/SECTIONALISING CB - RAFFEEN 220-RAFFEEN 220-220K1-2 | 2 | 2 | 2 | Scheduled | 03/05/2023 | 04/05/2023
TO-23-110 kV B2 @ KBY-03 | BUSBAR SECTION - KILBARRY 110-KILBARRY 110-110B2 | 89 | 62 | 62 | Scheduled | 04/05/2023 | 31/07/2023
TO-23-110 kV A1 @ MR-01 | BUSBAR SECTION - MARINA 110-MARINA 110-110A1 | 9 | 7 | 7 | Scheduled | 08/05/2023 | 16/05/2023
TO-23-110 kV B1 @ MR-01 | BUSBAR SECTION - MARINA 110-MARINA 110-110B1 | 9 | 7 | 7 | Scheduled | 08/05/2023 | 16/05/2023
TO-23-110 kV A1 @ RAF-03 | BUSBAR SECTION - RAFFEEN 110-RAFFEEN 110-110A1 | 5 | 5 | 5 | Scheduled | 08/05/2023 | 12/05/2023
TO-23-110 kV A2 @ RAF-03 | BUSBAR SECTION - RAFFEEN 110-RAFFEEN 110-110A2 | 5 | 5 | 5 | Scheduled | 08/05/2023 | 12/05/2023
TO-23-110 kV B1 @ RAF-03 | BUSBAR SECTION - RAFFEEN 110-RAFFEEN 110-110B1 | 5 | 5 | 5 | Scheduled | 08/05/2023 | 12/05/2023
TO-23-110 kV B2 @ RAF-03 | BUSBAR SECTION - RAFFEEN 110-RAFFEEN 110-110B2 | 5 | 5 | 5 | Scheduled | 08/05/2023 | 12/05/2023
TO-23-RAF-110K1-2-01 | COUPLER/SECTIONALISING CB - RAFFEEN 110-RAFFEEN 110-110K1-2 | 5 | 5 | 5 | Scheduled | 08/05/2023 | 12/05/2023
TO-23-CRO-IA-1-04 | 110kV FEEDER - COOLROE 110-INNISCARRA 110-1 | 1 | 1 | 1 | Scheduled | 11/05/2023 | 11/05/2023
TO-23-110 kV A1 @ IA-01 | BUSBAR SECTION - INNISCARRA 110-INNISCARRA 110-110A1 | 1 | 1 | 1 | Scheduled | 11/05/2023 | 11/05/2023
TO-23-IA-MAC-1-04 | 110kV FEEDER - INNISCARRA 110-MACROOM 110-1 | 1 | 1 | 1 | Scheduled | 11/05/2023 | 11/05/2023
TO-23-IA-T101-03 | GENERATOR TRANSFORMER - INNISCARRA 110-INNISCARRA G1-T101 | 1 | 1 | 1 | Scheduled | 11/05/2023 | 11/05/2023
TO-23-CD-T103-01 | GENERATOR TRANSFORMER - CARRIGADROHID 110-CARRIGADROHID G3-T103 | 9 | 7 | 7 | Scheduled | 16/05/2023 | 24/05/2023
TO-23-110 kV A1/A2 @ CLA-02 | BUSBAR SECTION - CLASHAVOON 110-CLASHAVOON 110-110A1-A2 | 10 | 7 | 7 | Scheduled | 29/05/2023 | 07/06/2023
TO-23-110 kV B1/B2 @ CLA-02 | BUSBAR SECTION - CLASHAVOON 110-CLASHAVOON 110-110B1-B2 | 10 | 7 | 7 | Scheduled | 29/05/2023 | 07/06/2023
TO-23-CLA-110K1-2-01 | COUPLER/SECTIONALISING CB - CLASHAVOON 110-CLASHAVOON 110-110K1-2 | 10 | 7 | 7 | Scheduled | 29/05/2023 | 07/06/2023
TO-23-BAN-BRI-2-01 | 110kV FEEDER - BANDON 110-BRINNY 110-2 | 1 | 1 | 1 | Scheduled | 07/06/2023 | 07/06/2023
TO-23-BRI-T102-01 | TSO CUSTOMER TRANSFORMER - BRINNY 110-BRINNY 10-T102 | 1 | 1 | 1 | Scheduled | 07/06/2023 | 07/06/2023
TO-23-BAN-BRI-1-01 | 110kV FEEDER - BANDON 110-BRINNY 110-1 | 9 | 7 | 7 | Scheduled | 08/06/2023 | 16/06/2023
TO-23-BRI-T101-01 | TSO CUSTOMER TRANSFORMER - BRINNY 110-BRINNY 10-T101 | 9 | 7 | 7 | Scheduled | 08/06/2023 | 16/06/2023
TO-23-COW-T142-01 | DISTRIBUTION TRANSFORMER - COW CROSS 110-COW CROSS 38-T142 | 16 | 10 |  | Reference | 10/06/2023 | 25/06/2023
TO-23-IA-MAC-1-03 | 110kV FEEDER - INNISCARRA 110-MACROOM 110-1 | 76 | 54 | 54 | Scheduled | 19/06/2023 | 02/09/2023
TO-23-CLA-T2102-02 | TRANSFORMER - CLASHAVOON 220-CLASHAVOON 110-T2102 | 15 | 11 | 11 | Scheduled | 30/06/2023 | 14/07/2023
TO-23-AD-T2011/12-01 | GENERATOR TRANSFORMER - AGHADA 220-AGHADA G11/12-T2011/12 | 4 | 4 | 4 | Scheduled | 17/07/2023 | 20/07/2023
TO-23-COW-OLD-2-01 | 110kV FEEDER - COW CROSS 110-OLDCOURT 110-2 | 5 | 5 | 5 | Reference | 17/07/2023 | 21/07/2023
TO-23-OLD-T102-01 | DISTRIBUTION TRANSFORMER - OLDCOURT 110-OLDCOURT 10-T102 | 5 | 5 | 5 | Reference | 17/07/2023 | 21/07/2023
TO-23-AD-T2014-01 | GENERATOR TRANSFORMER - AGHADA 220-AGHADA G14-T2014 | 5 | 5 | 5 | Scheduled | 24/07/2023 | 28/07/2023
TO-23-110 kV A2 @ KBY-02 | BUSBAR SECTION - KILBARRY 110-KILBARRY 110-110A2 | 3 | 3 | 3 | Scheduled | 01/08/2023 | 03/08/2023
TO-23-110 kV B2 @ KBY-02 | BUSBAR SECTION - KILBARRY 110-KILBARRY 110-110B2 | 3 | 3 | 3 | Scheduled | 01/08/2023 | 03/08/2023
TO-23-AD-KRA-1-04 | 220kV FEEDER - AGHADA 220-KNOCKRAHA 220-1 | 8 | 5 | 5 | Scheduled | 04/08/2023 | 11/08/2023
TO-23-KRA-220SB1-2CB-02 | COUPLER/SECTIONALISING CB - KNOCKRAHA 220-KNOCKRAHA 220-220SB1-2CB | 8 | 5 | 5 | Scheduled | 04/08/2023 | 11/08/2023
TO-23-KRA-220SB2-4CB-03 | COUPLER/SECTIONALISING CB - KNOCKRAHA 220-KNOCKRAHA 220-220SB2-4CB | 8 | 5 | 5 | Scheduled | 04/08/2023 | 11/08/2023
TO-23-COW-OLD-1-01 | 110kV FEEDER - COW CROSS 110-OLDCOURT 110-1 | 5 | 4 | 4 | Reference | 07/08/2023 | 11/08/2023
TO-23-OLD-T101-01 | DISTRIBUTION TRANSFORMER - OLDCOURT 110-OLDCOURT 10-T101 | 5 | 4 | 4 | Reference | 07/08/2023 | 11/08/2023
TO-23-COW-RAF-1-02 | 110kV FEEDER - COW CROSS 110-RAFFEEN 110-1 | 4 | 4 | 4 | Scheduled | 14/08/2023 | 17/08/2023
TO-23-AD-GGO-1-01 | 220kV FEEDER - AGHADA 220-GLANAGOW 220-1 | 22 | 16 | 16 | Scheduled | 18/08/2023 | 08/09/2023
TO-23-AD-KRA-2-04 | 220kV FEEDER - AGHADA 220-KNOCKRAHA 220-2 | 7 | 5 | 5 | Scheduled | 18/08/2023 | 24/08/2023
TO-23-GGO-RAF-1-01 | 220kV FEEDER - GLANAGOW 220-RAFFEEN 220-1 | 22 | 16 | 16 | Scheduled | 18/08/2023 | 08/09/2023
TO-23-GGO-T2001-01 | GENERATOR TRANSFORMER - GLANAGOW 220-GLANAGOW G1-T2001 | 22 | 16 | 16 | Scheduled | 18/08/2023 | 08/09/2023
TO-23-KRA-220SB1-2CB-03 | COUPLER/SECTIONALISING CB - KNOCKRAHA 220-KNOCKRAHA 220-220SB1-2CB | 7 | 5 | 5 | Scheduled | 18/08/2023 | 24/08/2023
TO-23-CLA-CKN-1-01 | 110kV FEEDER - CLASHAVOON 110-CLONKEEN 110-1 | 11 | 9 | 9 | Scheduled | 21/08/2023 | 31/08/2023
TO-23-AD-KRA-2-06 | 220kV FEEDER - AGHADA 220-KNOCKRAHA 220-2 | 1 | 0 | 0 | Scheduled | 26/08/2023 | 26/08/2023
TO-23-KRA-220SB1-2CB-04 | COUPLER/SECTIONALISING CB - KNOCKRAHA 220-KNOCKRAHA 220-220SB1-2CB | 1 | 0 | 0 | Scheduled | 26/08/2023 | 26/08/2023
TO-23-IA-T101-04 | GENERATOR TRANSFORMER - INNISCARRA 110-INNISCARRA G1-T101 | 2 | 2 | 2 | Scheduled | 30/08/2023 | 31/08/2023
TO-23-220 kV A1/A2 @ KRA-02 | BUSBAR SECTION - KNOCKRAHA 220-KNOCKRAHA 220-220A1-A2 | 65 | 46 |  | Scheduled | 30/08/2023 | 02/11/2023
TO-23-KRA-220K1-06 | COUPLER/SECTIONALISING CB - KNOCKRAHA 220-KNOCKRAHA 220-220K1 | 65 | 46 |  | Scheduled | 30/08/2023 | 02/11/2023
TO-23-KRA-220SA2-4CB-03 | COUPLER/SECTIONALISING CB - KNOCKRAHA 220-KNOCKRAHA 220-220SA2-4CB | 65 | 46 |  | Scheduled | 30/08/2023 | 02/11/2023
TO-23-CLA-MAC-1-02 | 110kV FEEDER - CLASHAVOON 110-MACROOM 110-1 | 1 | 0 | 0 | Scheduled | 02/09/2023 | 02/09/2023
TO-23-DMY-MAC-1-02 | 110kV FEEDER - DUNMANWAY 110-MACROOM 110-1 | 1 | 0 | 0 | Scheduled | 02/09/2023 | 02/09/2023
TO-23-MAC-110SA1-2CB-02 | COUPLER/SECTIONALISING CB - MACROOM 110-MACROOM 110-110SA1-2CB | 1 | 0 | 0 | Scheduled | 02/09/2023 | 02/09/2023
TO-23-MAC-T142-02 | DISTRIBUTION TRANSFORMER - MACROOM 110-MACROOM 38-T142 | 1 | 0 | 0 | Reference | 02/09/2023 | 02/09/2023
TO-23-KBY-MR-1-06 | 110kV FEEDER - KILBARRY 110-MARINA 110-1 | 82 | 59 |  | Scheduled | 04/09/2023 | 24/11/2023
TO-23-KBY-MR-2-02 | 110kV FEEDER - KILBARRY 110-MARINA 110-2 | 82 | 59 |  | Scheduled | 04/09/2023 | 24/11/2023
TO-23-KRA-MID-1-01 | 110kV FEEDER - KNOCKRAHA 110-MIDLETON 110-1 | 96 | 69 | 69 | Scheduled | 04/09/2023 | 08/12/2023
TO-23-110 kV A1 @ TBG-01 | BUSBAR SECTION - TRABEG 110-TRABEG 110-110A1 | 5 | 5 | 5 | Scheduled | 04/09/2023 | 08/09/2023
TO-23-110 kV A2 @ TBG-02 | BUSBAR SECTION - TRABEG 110-TRABEG 110-110A2 | 5 | 5 | 5 | Scheduled | 04/09/2023 | 08/09/2023
TO-23-110 kV B1 @ TBG-01 | BUSBAR SECTION - TRABEG 110-TRABEG 110-110B1 | 5 | 5 | 5 | Scheduled | 04/09/2023 | 08/09/2023
TO-23-110 kV B2 @ TBG-02 | BUSBAR SECTION - TRABEG 110-TRABEG 110-110B2 | 5 | 5 | 5 | Scheduled | 04/09/2023 | 08/09/2023
TO-23-TBG-110K1-2-02 | COUPLER/SECTIONALISING CB - TRABEG 110-TRABEG 110-110K1-2 | 5 | 5 | 5 | Scheduled | 04/09/2023 | 08/09/2023
TO-23-TBG-T101-01 | DISTRIBUTION TRANSFORMER - TRABEG 110-TRABEG 10-T101 | 5 | 5 | 5 | Reference | 04/09/2023 | 08/09/2023
TO-23-TBG-T141-01 | DISTRIBUTION TRANSFORMER - TRABEG 110-TRABEG 38-T141 | 5 | 5 | 5 | Reference | 04/09/2023 | 08/09/2023
TO-23-CGG-T131-02 | GENERATOR TRANSFORMER - CARRIGDANGAN 110-CARRIGDANGAN 33-T131 | 1 | 1 | 1 | Scheduled | 07/09/2023 | 07/09/2023
TO-23-GGO-RAF-1-05 | 220kV FEEDER - GLANAGOW 220-RAFFEEN 220-1 | 13 | 9 | 9 | Scheduled | 08/09/2023 | 20/09/2023
TO-23-WHI-CKB-T101-01 | TSO CUSTOMER TRANSFORMER - WHITEGATE 110-WHITEGATE 10-CKB-T101 | 5 | 5 | 5 | Scheduled | 11/09/2023 | 15/09/2023
TO-23-CRO-IA-1-02 | 110kV FEEDER - COOLROE 110-INNISCARRA 110-1 | 68 | 49 | 49 | Scheduled | 18/09/2023 | 24/11/2023
TO-23-WHI-CKB-T102-01 | TSO CUSTOMER TRANSFORMER - WHITEGATE 110-WHITEGATE 10-CKB-T102 | 5 | 5 | 5 | Scheduled | 18/09/2023 | 22/09/2023
TO-23-AD-KRA-1-05 | 220kV FEEDER - AGHADA 220-KNOCKRAHA 220-1 | 8 | 6 |  | Scheduled | 06/10/2023 | 13/10/2023
TO-23-BGH-T121-01 | GENERATOR TRANSFORMER - BOGGERAGH 110-BOGGERAGH 20-T121 | 1 | 1 | 1 | Scheduled | 09/10/2023 | 09/10/2023
TO-23-110 kV A2 @ KBY-04 | BUSBAR SECTION - KILBARRY 110-KILBARRY 110-110A2 | 14 | 10 | 10 | Scheduled | 09/10/2023 | 22/10/2023
TO-23-110 kV B2 @ KBY-05 | BUSBAR SECTION - KILBARRY 110-KILBARRY 110-110B2 | 14 | 10 | 10 | Scheduled | 09/10/2023 | 22/10/2023
TO-23-110 kV A2 @ KRA-02 | BUSBAR SECTION - KNOCKRAHA 110-KNOCKRAHA 110-110A2 | 12 | 10 | 10 | Scheduled | 09/10/2023 | 20/10/2023
TO-23-110 kV B2 @ KRA-04 | BUSBAR SECTION - KNOCKRAHA 110-KNOCKRAHA 110-110B2 | 12 | 10 | 10 | Scheduled | 09/10/2023 | 20/10/2023
TO-23-110 kV A1 @ MR-02 | BUSBAR SECTION - MARINA 110-MARINA 110-110A1 | 14 | 10 | 10 | Scheduled | 09/10/2023 | 22/10/2023
TO-23-110 kV B1 @ MR-02 | BUSBAR SECTION - MARINA 110-MARINA 110-110B1 | 14 | 10 | 10 | Scheduled | 09/10/2023 | 22/10/2023
TO-23-AD-LPT-1-01 | 220kV FEEDER - AGHADA 220-LONG POINT 220-1 | 7 | 5 | 5 | Scheduled | 10/10/2023 | 16/10/2023
TO-23-LPT-T2002-01 | GENERATOR TRANSFORMER - LONG POINT 220-LONG POINT G1-T2002 | 7 | 5 |  | Scheduled | 10/10/2023 | 16/10/2023
TO-23-RAF-TBG-1-03 | 110kV FEEDER - RAFFEEN 110-TRABEG 110-1 | 2 | 0 | 0 | Scheduled | 14/10/2023 | 15/10/2023
TO-23-CHA-MAL-1-03 | 110kV FEEDER - CHARLEVILLE 110-MALLOW 110-1 | 5 | 5 | 5 | Scheduled | 16/10/2023 | 20/10/2023
TO-23-220 kV A2 @ AD-05 | BUSBAR SECTION - AGHADA 220-AGHADA 220-220A2 | 7 | 5 | 5 | Scheduled | 20/10/2023 | 26/10/2023
TO-23-220 kV B2 @ AD-06 | BUSBAR SECTION - AGHADA 220-AGHADA 220-220B2 | 7 | 5 | 5 | Scheduled | 20/10/2023 | 26/10/2023
TO-23-AD-KRA-2-01 | 220kV FEEDER - AGHADA 220-KNOCKRAHA 220-2 | 7 | 5 | 5 | Scheduled | 20/10/2023 | 26/10/2023
TO-23-KLN-KRA-1-03 | 220kV FEEDER - KILLONAN 220-KNOCKRAHA 220-1 | 1 | 1 |  | Scheduled | 02/11/2023 | 02/11/2023
TO-23-BAN-BRI-2-02 | 110kV FEEDER - BANDON 110-BRINNY 110-2 | 2 | 2 | 2 | Scheduled | 06/11/2023 | 07/11/2023
TO-23-BRI-T102-02 | TSO CUSTOMER TRANSFORMER - BRINNY 110-BRINNY 10-T102 | 2 | 2 | 2 | Scheduled | 06/11/2023 | 07/11/2023
TO-23-CRO-T122-02 | DISTRIBUTION TRANSFORMER - COOLROE 110-COOLROE 20-T122 | 2 | 2 | 2 | Reference | 07/11/2023 | 08/11/2023
TO-23-BAN-BRI-1-02 | 110kV FEEDER - BANDON 110-BRINNY 110-1 | 5 | 5 | 5 | Scheduled | 13/11/2023 | 17/11/2023
TO-23-BRI-T101-02 | TSO CUSTOMER TRANSFORMER - BRINNY 110-BRINNY 10-T101 | 5 | 5 |  | Scheduled | 13/11/2023 | 17/11/2023
TO-23-IA-MAC-1-07 | 110kV FEEDER - INNISCARRA 110-MACROOM 110-1 | 2 | 2 | 2 | Scheduled | 16/11/2023 | 17/11/2023
TO-23-IA-T101-06 | GENERATOR TRANSFORMER - INNISCARRA 110-INNISCARRA G1-T101 | 2 | 2 | 2 | Scheduled | 16/11/2023 | 17/11/2023
TO-23-BAN-RAF-1-01 | 110kV FEEDER - BANDON 110-RAFFEEN 110-1 | 3 | 3 |  | Scheduled | 20/11/2023 | 22/11/2023
TO-23-CHA-MAL-1-01 | 110kV FEEDER - CHARLEVILLE 110-MALLOW 110-1 | 10 | 8 | 8 | Scheduled | 20/11/2023 | 29/11/2023
TO-23-110 kV A2 @ KBY-05 | BUSBAR SECTION - KILBARRY 110-KILBARRY 110-110A2 | 8 | 6 | 6 | Scheduled | 27/11/2023 | 04/12/2023
TO-23-110 kV B2 @ KBY-06 | BUSBAR SECTION - KILBARRY 110-KILBARRY 110-110B2 | 8 | 6 | 6 | Scheduled | 27/11/2023 | 04/12/2023
TO-23-KBY-KRA-2-01 | 110kV FEEDER - KILBARRY 110-KNOCKRAHA 110-2 | 8 | 6 | 6 | Scheduled | 27/11/2023 | 04/12/2023
TO-23-110 kV A2 @ KRA-03 | BUSBAR SECTION - KNOCKRAHA 110-KNOCKRAHA 110-110A2 | 8 | 6 | 6 | Scheduled | 27/11/2023 | 04/12/2023
TO-23-110 kV B2 @ KRA-05 | BUSBAR SECTION - KNOCKRAHA 110-KNOCKRAHA 110-110B2 | 8 | 6 | 6 | Scheduled | 27/11/2023 | 04/12/2023
TO-23-KBY-T101-02 | DISTRIBUTION TRANSFORMER - KILBARRY 110-KILBARRY 10-T101 | 2 | 2 | 2 | Reference | 28/11/2023 | 29/11/2023