## GEN_ALL
Outage ID | Feeder ID | Calendar Day Duration | Working Day Duration | Work Days | Outage Status | Start | Finish
TO-24-KPG-TB-1-02 | 220kV FEEDER - KILPADDOGE 220-TARBERT 220-1 | 167 | 113 | 113 | Scheduled | 02/01/2024 | 16/06/2024
TO-24-110 kV A1 @ SH-01 | BUSBAR SECTION - SHANNONBRIDGE 110-SHANNONBRIDGE 110-110A1 | 23 | 17 | 17 | Scheduled | 02/01/2024 | 24/01/2024
TO-24-110 kV B1 @ SH-01 | BUSBAR SECTION - SHANNONBRIDGE 110-SHANNONBRIDGE 110-110B1 | 23 | 17 | 17 | Scheduled | 02/01/2024 | 24/01/2024
TO-24-220 kV A2 @ TB-01 | BUSBAR SECTION - TARBERT 220-TARBERT 220-220A2 | 287 | 198 | 198 | Scheduled | 02/01/2024 | 14/10/2024
TO-24-220 kV B2 @ TB-01 | BUSBAR SECTION - TARBERT 220-TARBERT 220-220B2 | 287 | 198 | 198 | Scheduled | 02/01/2024 | 14/10/2024
TO-24-TB-220K1-2-02 | COUPLER/SECTIONALISING CB - TARBERT 220-TARBERT 220-220K1-2 | 167 | 113 | 113 | Scheduled | 02/01/2024 | 16/06/2024
TO-24-TB-T2004-02 | GENERATOR TRANSFORMER - TARBERT 220-TARBERT G4-T2004 | 167 | 113 | 113 | Scheduled | 02/01/2024 | 16/06/2024
TO-24-BOT-MLC-1-01 | 110kV FEEDER - BOGTOWN 110-MOUNTLUCAS 110-1 | 7 | 5 |  | Scheduled | 03/01/2024 | 09/01/2024
TO-24-BOT-T132-01 | GENERATOR TRANSFORMER - BOGTOWN 110-BOGTOWN 33-T132 | 7 | 5 | 5 | Scheduled | 03/01/2024 | 09/01/2024
TO-24-MLC-110SA1-01 | SECTIONALISING DISCONNECT - MOUNTLUCAS 110-MOUNTLUCAS 110-110SA1 | 7 | 5 | 5 | Scheduled | 03/01/2024 | 09/01/2024
TO-24-MLC-110SA2-01 | SECTIONALISING DISCONNECT - MOUNTLUCAS 110-MOUNTLUCAS 110-110SA2 | 7 | 5 | 5 | Scheduled | 03/01/2024 | 09/01/2024
TO-24-MLC-TSB-1-01 | 110kV FEEDER - MOUNTLUCAS 110-THORNSBERRY 110-1 | 7 | 5 | 5 | Scheduled | 03/01/2024 | 09/01/2024
TO-24-AUG-CFM-1-01 | 110kV FEEDER - AUGHINISH 110-CASTLEFARM 110-1 | 5 | 5 | 5 | Scheduled | 08/01/2024 | 12/01/2024
TO-24-220 kV A2 @ CSH-01 | BUSBAR SECTION - CASHLA 220-CASHLA 220-220A2 | 5 | 5 | 5 | Scheduled | 08/01/2024 | 12/01/2024
TO-24-220 kV A4 @ CSH-02 | BUSBAR SECTION - CASHLA 220-CASHLA 220-220A4 | 5 | 5 | 5 | Scheduled | 08/01/2024 | 12/01/2024
TO-24-220 kV B2 @ CSH-03 | BUSBAR SECTION - CASHLA 220-CASHLA 220-220B2 | 5 | 5 | 5 | Scheduled | 08/01/2024 | 12/01/2024
TO-24-220 kV B4 @ CSH-01 | BUSBAR SECTION - CASHLA 220-CASHLA 220-220B4 | 5 | 5 | 5 | Scheduled | 08/01/2024 | 12/01/2024
TO-24-CSH-220K2-4-02 | COUPLER/SECTIONALISING CB - CASHLA 220-CASHLA 220-220K2-4 | 5 | 5 | 5 | Scheduled | 08/01/2024 | 12/01/2024
TO-24-CFM-T101-01 | TSO CUSTOMER TRANSFORMER - CASTLEFARM 110-CASTLEFARM 10-T101 | 5 | 5 | 5 | Reference | 08/01/2024 | 12/01/2024
TO-24-LIM-MTN-1-02 | 110kV FEEDER - LIMERICK 110-MONETEEN 110-1 | 2 | 2 | 2 | Scheduled | 08/01/2024 | 09/01/2024
TO-24-110 kV A1 @ LOU-02 | BUSBAR SECTION - LOUTH 110-LOUTH 110-110A1 | 12 | 10 | 10 | Scheduled | 08/01/2024 | 19/01/2024
TO-24-110 kV B1 @ LOU-02 | BUSBAR SECTION - LOUTH 110-LOUTH 110-110B1 | 12 | 10 | 10 | Scheduled | 08/01/2024 | 19/01/2024
TO-24-220 kV A1 @ MAY-01 | BUSBAR SECTION - MAYNOOTH 220-MAYNOOTH 220-220A1 | 12 | 10 | 10 | Proposed | 08/01/2024 | 19/01/2024
TO-24-220 kV B1 @ MAY-01 | BUSBAR SECTION - MAYNOOTH 220-MAYNOOTH 220-220B1 | 12 | 10 | 10 | Proposed | 08/01/2024 | 19/01/2024
TO-24-220 kV A3 @ PB-01 | BUSBAR SECTION - POOLBEG 220-POOLBEG 220-220A3 | 12 | 10 | 10 | Scheduled | 08/01/2024 | 19/01/2024
TO-24-220 kV A4 @ PB-02 | BUSBAR SECTION - POOLBEG 220-POOLBEG 220-220A4 | 12 | 10 | 10 | Scheduled | 08/01/2024 | 19/01/2024
TO-24-220 kV B3 @ PB-01 | BUSBAR SECTION - POOLBEG 220-POOLBEG 220-220B3 | 12 | 10 | 10 | Scheduled | 08/01/2024 | 19/01/2024
TO-24-220 kV B4 @ PB-01 | BUSBAR SECTION - POOLBEG 220-POOLBEG 220-220B4 | 12 | 10 | 10 | Scheduled | 08/01/2024 | 19/01/2024
TO-24-PB-R223-4-01 | CAPACITOR/SVC/REACTOR - POOLBEG 220-POOLBEG 220-R223-4 | 12 | 10 | 10 | Scheduled | 08/01/2024 | 19/01/2024
TO-24-CLN-T142-01 | DISTRIBUTION TRANSFORMER - CLOON 110-CLOON 38-T142 | 152 | 104 | 104 | Reference | 15/01/2024 | 14/06/2024
TO-24-DER-MAY-1-02 | 110kV FEEDER - DERRYIRON 110-MAYNOOTH 110-1 | 5 | 5 | 5 | Scheduled | 15/01/2024 | 19/01/2024
TO-24-DER-TSB-1-01 | 110kV FEEDER - DERRYIRON 110-THORNSBERRY 110-1 | 5 | 5 | 5 | Scheduled | 15/01/2024 | 19/01/2024
TO-24-GI-T141-03 | DISTRIBUTION TRANSFORMER - GREAT ISLAND 110-GREAT ISLAND 38-T141 | 5 | 5 | 5 | Reference | 15/01/2024 | 19/01/2024
TO-24-IKE,T-THU-1-04 | 110kV FEEDER - IKERRIN tee-THURLES 110-1 | 3 | 3 | 3 | Scheduled | 15/01/2024 | 17/01/2024
TO-24-LSN-110SA1-2-02 | SECTIONALISING DISCONNECT - LISHEEN 110-LISHEEN 110-110SA1-2 | 3 | 3 | 3 | Scheduled | 15/01/2024 | 17/01/2024
TO-24-LSN-110SA2-4-02 | SECTIONALISING DISCONNECT - LISHEEN 110-LISHEEN 110-110SA2-4 | 3 | 3 | 3 | Scheduled | 15/01/2024 | 17/01/2024
TO-24-LSN-T122-02 | GENERATOR TRANSFORMER - LISHEEN 110-LISHEEN 20-T122 | 3 | 3 | 3 | Scheduled | 15/01/2024 | 17/01/2024
TO-24-LSN-T131-02 | GENERATOR TRANSFORMER - LISHEEN 110-LISHEEN 33-T131 | 3 | 3 | 3 | Scheduled | 15/01/2024 | 17/01/2024
TO-24-LSN-T142-03 | DISTRIBUTION TRANSFORMER - LISHEEN 110-LISHEEN 38-T142 | 3 | 3 | 3 | Reference | 15/01/2024 | 17/01/2024
TO-24-LSN-THU-1-02 | 110kV FEEDER - LISHEEN 110-THURLES 110-1 | 3 | 3 | 3 | Scheduled | 15/01/2024 | 17/01/2024
TO-24-220 kV A2 @ SH-01 | BUSBAR SECTION - SHANNONBRIDGE 220-SHANNONBRIDGE 220-220A2 | 89 | 61 |  | Scheduled | 15/01/2024 | 12/04/2024
TO-24-220 kV B2 @ SH-01 | BUSBAR SECTION - SHANNONBRIDGE 220-SHANNONBRIDGE 220-220B2 | 89 | 61 |  | Scheduled | 15/01/2024 | 12/04/2024
TO-24-THU-110SA1-2CB-02 | COUPLER/SECTIONALISING CB - THURLES 110-THURLES 110-110SA1-2CB | 3 | 3 | 3 | Scheduled | 15/01/2024 | 17/01/2024
TO-24-THU-T142-02 | DISTRIBUTION TRANSFORMER - THURLES 110-THURLES 38-T142 | 3 | 3 | 3 | Reference | 15/01/2024 | 17/01/2024
TO-24-AUN-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - AUNGIERSTOWN 110-AUNGIERSTOWN 110-110SA1-2CB | 3 | 3 |  | Scheduled | 22/01/2024 | 24/01/2024
TO-24-AUN-T123-01 | TSO CUSTOMER TRANSFORMER - AUNGIERSTOWN 110-AUNGIERSTOWN 20-T123 | 2 | 2 |  | Scheduled | 22/01/2024 | 23/01/2024
TO-24-RYB GIS-T108-01 | TSO CUSTOMER TRANSFORMER - RYEBROOK GIS 110-RYEBROOK 10-T108 | 5 | 5 | 5 | Scheduled | 22/01/2024 | 26/01/2024
TO-24-AUN-T121-01 | TSO CUSTOMER TRANSFORMER - AUNGIERSTOWN 110-AUNGIERSTOWN 20-T121 | 1 | 1 |  | Scheduled | 24/01/2024 | 24/01/2024
TO-24-BAL-CDU-1-03 | 110kV FEEDER - BALTRASNA 110-CORDUFF 110-1 | 3 | 3 | 3 | Scheduled | 24/01/2024 | 26/01/2024
TO-24-BLU-CDU-1-03 | 110kV FEEDER - BLUNDELSTOWN 110-CORDUFF 110-1 | 3 | 3 | 3 | Scheduled | 24/01/2024 | 26/01/2024
TO-24-110 kV B2/B4 @ CDU-01 | BUSBAR SECTION - CORDUFF 110-CORDUFF 110-110B2-B4 | 3 | 3 | 3 | Scheduled | 24/01/2024 | 26/01/2024
TO-24-AGL-SH-1-05 | 110kV FEEDER - AGANNYGAL 110-SHANNONBRIDGE 110-1 | 2 | 2 | 2 | Scheduled | 25/01/2024 | 26/01/2024
TO-24-110 kV A2 @ SH-01 | BUSBAR SECTION - SHANNONBRIDGE 110-SHANNONBRIDGE 110-110A2 | 2 | 2 | 2 | Scheduled | 25/01/2024 | 26/01/2024
TO-24-110 kV B2 @ SH-01 | BUSBAR SECTION - SHANNONBRIDGE 110-SHANNONBRIDGE 110-110B2 | 2 | 2 | 2 | Scheduled | 25/01/2024 | 26/01/2024
TO-24-BAL-CDU-1-04 | 110kV FEEDER - BALTRASNA 110-CORDUFF 110-1 | 2 | 2 |  | Scheduled | 29/01/2024 | 30/01/2024
TO-24-220 kV A4 @ CKM GIS-01 | BUSBAR SECTION - CARRICKMINES GIS 220-CARRICKMINES GIS 220-220A4 | 3 | 3 | 3 | Scheduled | 29/01/2024 | 31/01/2024
TO-24-220 kV B4 @ CKM GIS-01 | BUSBAR SECTION - CARRICKMINES GIS 220-CARRICKMINES GIS 220-220B4 | 3 | 3 | 3 | Scheduled | 29/01/2024 | 31/01/2024
TO-24-CKM GIS-220K4-01 | COUPLER/SECTIONALISING CB - CARRICKMINES GIS 220-CARRICKMINES GIS 220-220K4 | 3 | 3 | 3 | Scheduled | 29/01/2024 | 31/01/2024
TO-24-CKM GIS-220SA2-4CB-01 | COUPLER/SECTIONALISING CB - CARRICKMINES GIS 220-CARRICKMINES GIS 220-22SA2-4CB | 3 | 3 | 3 | Scheduled | 29/01/2024 | 31/01/2024
TO-24-CKM GIS-220SB2-4CB-01 | COUPLER/SECTIONALISING CB - CARRICKMINES GIS 220-CARRICKMINES GIS 220-22SB2-4CB | 3 | 3 | 3 | Scheduled | 29/01/2024 | 31/01/2024
TO-24-CKM GIS-DSN-1-02 | 220kV FEEDER - CARRICKMINES GIS 220-DUNSTOWN 220-1 | 3 | 3 | 3 | Scheduled | 29/01/2024 | 31/01/2024
TO-24-CKM GIS-T2104-01 | TRANSFORMER - CARRICKMINES GIS 220-CARRICKMINES GIS 110-T2104 | 3 | 3 | 3 | Reference | 29/01/2024 | 31/01/2024
TO-24-CDU-110SB2-4-02 | SECTIONALISING DISCONNECT - CORDUFF 110-CORDUFF 110-110SB2-4 | 2 | 2 |  | Scheduled | 29/01/2024 | 30/01/2024
TO-24-CDU-MCE-1-03 | 110kV FEEDER - CORDUFF 110-MACETOWN 110-1 | 2 | 2 |  | Scheduled | 29/01/2024 | 30/01/2024
TO-24-DER-KIN-1-01 | 110kV FEEDER - DERRYIRON 110-KINNEGAD 110-1 | 5 | 5 | 5 | Scheduled | 29/01/2024 | 02/02/2024
TO-24-DER-T1/T2-01 | GENERATOR TRANSFORMER - DERRYIRON 110-RHODE 110-T1/T2 | 5 | 5 | 5 | Scheduled | 29/01/2024 | 02/02/2024
TO-24-KLS-KKY-1-02 | 110kV FEEDER - KELLIS 110-KILKENNY 110-1 | 10 | 7 | 7 | Scheduled | 29/01/2024 | 07/02/2024
TO-24-CUL-WAT-1-02 | 110kV FEEDER - CULLENAGH 110-WATERFORD 110-1 | 3 | 3 | 3 | Scheduled | 30/01/2024 | 01/02/2024
TO-24-OBE-PLA-1-01 | 110kV FEEDER - OLDBRIDGE 110-PLATIN 110-1 | 5 | 4 | 4 | Scheduled | 30/01/2024 | 03/02/2024
TO-24-PLA-110SA1-02 | SECTIONALISING DISCONNECT - PLATIN 110-PLATIN 110-110SA1 | 5 | 4 | 4 | Scheduled | 30/01/2024 | 03/02/2024
TO-24-PLA-110SA2-02 | SECTIONALISING DISCONNECT - PLATIN 110-PLATIN 110-110SA2 | 5 | 4 | 4 | Scheduled | 30/01/2024 | 03/02/2024
TO-24-PLA-T101/2/3/4-01 | TSO CUSTOMER TRANSFORMER - PLATIN 110-PLATIN 10-T101/2/3/4 | 72 | 48 | 48 | Scheduled | 30/01/2024 | 10/04/2024
TO-24-CAH-TIP-1-02 | 110kV FEEDER - CAHIR 110-TIPPERARY 110-1 | 2 | 2 | 2 | Scheduled | 31/01/2024 | 01/02/2024
TO-24-WOO-220K1-2-02 | COUPLER/SECTIONALISING CB - WOODLAND 220-WOODLAND 220-220K1-2 | 2 | 2 | 2 | Scheduled | 31/01/2024 | 01/02/2024
TO-24-PB-T2007/8-01 | GENERATOR TRANSFORMER - POOLBEG 220-POOLBEG G7/8-T2007/8 | 3 | 2 | 2 | Scheduled | 01/02/2024 | 03/02/2024
TO-24-DRY-LOU-1-03 | 110kV FEEDER - DRYBRIDGE 110-LOUTH 110-1 | 12 | 9 |  | Scheduled | 05/02/2024 | 16/02/2024
TO-24-110 kV A1 @ LOU-04 | BUSBAR SECTION - LOUTH 110-LOUTH 110-110A1 | 12 | 9 | 9 | Scheduled | 05/02/2024 | 16/02/2024
TO-24-110 kV B1 @ LOU-03 | BUSBAR SECTION - LOUTH 110-LOUTH 110-110B1 | 12 | 9 |  | Scheduled | 05/02/2024 | 16/02/2024
TO-24-LOU-RRU-1-03 | 110kV FEEDER - LOUTH 110-RATRUSSAN 110-1 | 12 | 9 | 9 | Scheduled | 05/02/2024 | 16/02/2024
TO-24-220 kV A1 @ CKM-01 | BUSBAR SECTION - CARRICKMINES 220-CARRICKMINES 220-220A1 | 5 | 4 | 4 | Scheduled | 06/02/2024 | 10/02/2024
TO-24-CKM-CKM GIS-1-01 | 220kV FEEDER - CARRICKMINES 220-CARRICKMINES GIS 220-1 | 5 | 4 | 4 | Scheduled | 06/02/2024 | 10/02/2024
TO-24-CKM-PB-1-02 | 220kV FEEDER - CARRICKMINES 220-POOLBEG 220-1 | 5 | 4 | 4 | Scheduled | 06/02/2024 | 10/02/2024
TO-24-CKM-PST2201-01 | TRANSFORMER - CARRICKMINES 220-CARRICKMINES 220-PST2201 | 5 | 4 | 4 | Scheduled | 06/02/2024 | 10/02/2024
TO-24-DER-MAY-1-03 | 110kV FEEDER - DERRYIRON 110-MAYNOOTH 110-1 | 18 | 14 |  | Scheduled | 06/02/2024 | 23/02/2024
TO-24-DER-TSB-1-02 | 110kV FEEDER - DERRYIRON 110-THORNSBERRY 110-1 | 18 | 14 |  | Scheduled | 06/02/2024 | 23/02/2024
TO-24-IKE,T-SH-1-03 | 110kV FEEDER - IKERRIN tee-SHANNONBRIDGE 110-1 | 3 | 3 | 3 | Scheduled | 06/02/2024 | 08/02/2024
TO-24-RYB GIS-T109-01 | TSO CUSTOMER TRANSFORMER - RYEBROOK GIS 110-RYEBROOK 10-T109 | 4 | 4 | 4 | Scheduled | 06/02/2024 | 09/02/2024
TO-24-110 kV B1 @ SH-02 | BUSBAR SECTION - SHANNONBRIDGE 110-SHANNONBRIDGE 110-110B1 | 3 | 3 |  | Scheduled | 06/02/2024 | 08/02/2024
TO-24-KRA-220SA2-4CB-01 | COUPLER/SECTIONALISING CB - KNOCKRAHA 220-KNOCKRAHA 220-220SA2-4CB | 1 | 1 | 1 | Scheduled | 07/02/2024 | 07/02/2024
TO-24-BRT-CLE-4-01 | 220kV FEEDER - BRACETOWN 220-CLONEE 220-4 | 1 | 1 | 1 | Scheduled | 08/02/2024 | 08/02/2024
TO-24-SH-T2101-01 | TRANSFORMER - SHANNONBRIDGE 220-SHANNONBRIDGE 110-T2101 | 1 | 1 |  | Scheduled | 08/02/2024 | 08/02/2024
TO-24-ARV-SKL-1-02 | 110kV FEEDER - ARVA 110-SHANKILL 110-1 | 75 | 50 | 50 | Scheduled | 09/02/2024 | 23/04/2024
TO-24-KRA-220K4-01 | COUPLER/SECTIONALISING CB - KNOCKRAHA 220-KNOCKRAHA 220-220K4 | 1 | 1 | 1 | Scheduled | 09/02/2024 | 09/02/2024
TO-24-BRT-T222-01 | TSO CUSTOMER TRANSFORMER - BRACETOWN 220-BRACETOWN 20-T222 | 38 | 27 | 27 | Scheduled | 12/02/2024 | 20/03/2024
TO-24-CKM GIS-T2103-01 | TRANSFORMER - CARRICKMINES GIS 220-CARRICKMINES GIS 110-T2103 | 5 | 5 | 5 | Reference | 12/02/2024 | 16/02/2024
TO-24-CF-T104-02 | GENERATOR TRANSFORMER - CATHALEENS FALL 110-CATHALEENS FALL G4-T104 | 2 | 2 | 2 | Scheduled | 12/02/2024 | 13/02/2024
TO-24-COW-WHI-1-03 | 110kV FEEDER - COW CROSS 110-WHITEGATE 110-1 | 5 | 5 | 5 | Scheduled | 12/02/2024 | 16/02/2024
TO-24-DND-T121-01 | TSO CUSTOMER TRANSFORMER - DARNDALE 110-DARNDALE 20-T121 | 324 | 223 | 223 | Scheduled | 12/02/2024 | 31/12/2024
TO-24-DSN-T4201-02 | TRANSFORMER - DUNSTOWN 400-DUNSTOWN 220-T4201 | 19 | 15 | 15 | Scheduled | 12/02/2024 | 01/03/2024
TO-24-GLN-T133-03 | GENERATOR TRANSFORMER - GALLANSTOWN 110-GALLANSTOWN 33-T133 | 26 | 20 | 20 | Scheduled | 12/02/2024 | 08/03/2024
TO-24-KNR-TRI-1-02 | 110kV FEEDER - KNOCKANURE 110-TRIEN 110-1 | 9 | 7 | 7 | Scheduled | 12/02/2024 | 20/02/2024
TO-24-110 kV A1 @ ATH-01 | BUSBAR SECTION - ATHLONE 110-ATHLONE 110-110A1 | 2 | 2 | 2 | Proposed | 14/02/2024 | 15/02/2024
TO-24-BUF-T131-01 | GENERATOR TRANSFORMER - BUFFY 110-BUFFY 33-T131 | 1 | 1 | 1 | Scheduled | 19/02/2024 | 19/02/2024
TO-24-110 kV A4 @ CBT-02 | BUSBAR SECTION - CASTLEBAGOT 110-CASTLEBAGOT 110-110A4 | 5 | 5 | 5 | Scheduled | 19/02/2024 | 23/02/2024
TO-24-110 kV B4 @ CBT-02 | BUSBAR SECTION - CASTLEBAGOT 110-CASTLEBAGOT 110-110B4 | 5 | 5 | 5 | Scheduled | 19/02/2024 | 23/02/2024
TO-24-CBT-CKG-2-03 | 110kV FEEDER - CASTLEBAGOT 110-CORKAGH 110-2 | 5 | 5 | 5 | Scheduled | 19/02/2024 | 23/02/2024
TO-24-CLN-110SA1-01 | SECTIONALISING DISCONNECT - CLOON 110-CLOON 110-110SA1 | 12 | 10 | 10 | Scheduled | 19/02/2024 | 01/03/2024
TO-24-CLN-110SA2-01 | SECTIONALISING DISCONNECT - CLOON 110-CLOON 110-110SA2 | 12 | 10 | 10 | Scheduled | 19/02/2024 | 01/03/2024
TO-24-CLN-LA-1-01 | 110kV FEEDER - CLOON 110-LANESBORO 110-1 | 12 | 10 | 10 | Scheduled | 19/02/2024 | 01/03/2024
TO-24-CUL-GI GIS-1-04 | 220kV FEEDER - CULLENAGH 220-GREAT ISLAND GIS 220-1 | 2 | 2 | 2 | Scheduled | 19/02/2024 | 20/02/2024
TO-24-IKE,T-SH-1-04 | 110kV FEEDER - IKERRIN tee-SHANNONBRIDGE 110-1 | 4 | 4 | 4 | Scheduled | 19/02/2024 | 22/02/2024
TO-24-LYT-T132-01 | GENERATOR TRANSFORMER - LYSAGHTSTOWN 110-LYSAGHTSTOWN 33-T132 | 1 | 1 | 1 | Scheduled | 19/02/2024 | 19/02/2024
TO-24-RAF-TBG-2-02 | 110kV FEEDER - RAFFEEN 110-TRABEG 110-2 | 5 | 5 | 5 | Scheduled | 19/02/2024 | 23/02/2024
TO-24-110 kV A1 @ SH-02 | BUSBAR SECTION - SHANNONBRIDGE 110-SHANNONBRIDGE 110-110A1 | 5 | 5 | 5 | Scheduled | 19/02/2024 | 23/02/2024
TO-24-KRA-110K1-2-01 | COUPLER/SECTIONALISING CB - KNOCKRAHA 110-KNOCKRAHA 110-110K1-2 | 1 | 1 | 1 | Scheduled | 20/02/2024 | 20/02/2024
TO-24-110 kV B2 @ MAY-03 | BUSBAR SECTION - MAYNOOTH 110-MAYNOOTH 110-110B2 | 3 | 3 |  | Scheduled | 20/02/2024 | 22/02/2024
TO-24-TSB-110SA1-01 | SECTIONALISING DISCONNECT - THORNSBERRY 110-THORNSBERRY 110-110SA1 | 3 | 3 |  | Scheduled | 20/02/2024 | 22/02/2024
TO-24-TSB-110SA2-01 | SECTIONALISING DISCONNECT - THORNSBERRY 110-THORNSBERRY 110-110SA2 | 3 | 3 |  | Scheduled | 20/02/2024 | 22/02/2024
TO-24-TSB-T142-01 | DISTRIBUTION TRANSFORMER - THORNSBERRY 110-THORNSBERRY 38-T142 | 3 | 3 |  | Reference | 20/02/2024 | 22/02/2024
TO-24-SH-T2101-05 | TRANSFORMER - SHANNONBRIDGE 220-SHANNONBRIDGE 110-T2101 | 1 | 1 | 1 | Scheduled | 23/02/2024 | 23/02/2024
TO-24-AD-LPT-1-01 | 220kV FEEDER - AGHADA 220-LONG POINT 220-1 | 78 | 52 | 52 | Scheduled | 26/02/2024 | 13/05/2024
TO-24-AA GIS-SNG-1-01 | 110kV FEEDER - ARDNACRUSHA GIS 110-SINGLAND 110-1 | 5 | 5 |  | Scheduled | 26/02/2024 | 01/03/2024
TO-24-110 kV A1 @ ARK-01 | BUSBAR SECTION - ARKLOW 110-ARKLOW 110-110A1 | 12 | 10 | 10 | Scheduled | 26/02/2024 | 08/03/2024
TO-24-110 kV B1 @ ARK-01 | BUSBAR SECTION - ARKLOW 110-ARKLOW 110-110B1 | 12 | 10 | 10 | Scheduled | 26/02/2024 | 08/03/2024
TO-24-ARK-BOG-1-01 | 110kV FEEDER - ARKLOW 110-BANOGE 110-1 | 12 | 10 | 10 | Scheduled | 26/02/2024 | 08/03/2024
TO-24-ATH-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - ATHLONE 110-ATHLONE 110-110SA1-2CB | 2 | 2 | 2 | Scheduled | 26/02/2024 | 27/02/2024
TO-24-ATH-CAP3-02 | CAPACITOR/SVC/REACTOR - ATHLONE 110-ATHLONE 110-CAP3 | 2 | 2 | 2 | Scheduled | 26/02/2024 | 27/02/2024
TO-24-ATH-LA-1-01 | 110kV FEEDER - ATHLONE 110-LANESBORO 110-1 | 2 | 2 | 2 | Scheduled | 26/02/2024 | 27/02/2024
TO-24-ATH-T141-01 | DISTRIBUTION TRANSFORMER - ATHLONE 110-ATHLONE 38-T141 | 2 | 2 | 2 | Reference | 26/02/2024 | 27/02/2024
TO-24-CSH-T2104-02 | TRANSFORMER - CASHLA 220-CASHLA 110-T2104 | 66 | 45 |  | Scheduled | 26/02/2024 | 01/05/2024
TO-24-CVW-COW-1-01 | 110kV FEEDER - CASTLEVIEW 110-COW CROSS 110-1 | 5 | 5 | 5 | Scheduled | 26/02/2024 | 01/03/2024
TO-24-110 kV A1 @ CDU-01 | BUSBAR SECTION - CORDUFF 110-CORDUFF 110-110A1 | 4 | 4 | 4 | Scheduled | 26/02/2024 | 29/02/2024
TO-24-110 kV A2 @ CDU-01 | BUSBAR SECTION - CORDUFF 110-CORDUFF 110-110A2 | 4 | 4 | 4 | Scheduled | 26/02/2024 | 29/02/2024
TO-24-110 kV A3 @ CDU-01 | BUSBAR SECTION - CORDUFF 110-CORDUFF 110-110A3 | 4 | 4 | 4 | Scheduled | 26/02/2024 | 29/02/2024
TO-24-110 kV A4 @ CDU-01 | BUSBAR SECTION - CORDUFF 110-CORDUFF 110-110A4 | 4 | 4 | 4 | Scheduled | 26/02/2024 | 29/02/2024
TO-24-110 kV B1 @ CDU-01 | BUSBAR SECTION - CORDUFF 110-CORDUFF 110-110B1 | 4 | 4 | 4 | Scheduled | 26/02/2024 | 29/02/2024
TO-24-110 kV B2 @ CDU-01 | BUSBAR SECTION - CORDUFF 110-CORDUFF 110-110B2 | 4 | 4 | 4 | Scheduled | 26/02/2024 | 29/02/2024
TO-24-110 kV B3 @ CDU-01 | BUSBAR SECTION - CORDUFF 110-CORDUFF 110-110B3 | 4 | 4 | 4 | Scheduled | 26/02/2024 | 29/02/2024
TO-24-110 kV B4 @ CDU-01 | BUSBAR SECTION - CORDUFF 110-CORDUFF 110-110B4 | 4 | 4 | 4 | Scheduled | 26/02/2024 | 29/02/2024
TO-24-LPT-T2002-02 | GENERATOR TRANSFORMER - LONG POINT 220-LONG POINT G1-T2002 | 100 | 67 | 67 | Scheduled | 26/02/2024 | 04/06/2024
TO-24-220 kV B1/B2 @ LOU-01 | BUSBAR SECTION - LOUTH 220-LOUTH 220-220B1-B2 | 73 | 49 |  | Scheduled | 26/02/2024 | 08/05/2024
TO-24-LOU-220K1-2-01 | COUPLER/SECTIONALISING CB - LOUTH 220-LOUTH 220-220K1-2 | 73 | 49 |  | Scheduled | 26/02/2024 | 08/05/2024
TO-24-OST-WOO-1-01 | 400kV FEEDER - OLDSTREET 400-WOODLAND 400-1 | 5 | 5 | 5 | Scheduled | 26/02/2024 | 01/03/2024
TO-24-110 kV A1 @ RAF-02 | BUSBAR SECTION - RAFFEEN 110-RAFFEEN 110-110A1 | 5 | 5 | 5 | Scheduled | 26/02/2024 | 01/03/2024
TO-24-110 kV B1 @ RAF-02 | BUSBAR SECTION - RAFFEEN 110-RAFFEEN 110-110B1 | 5 | 5 | 5 | Scheduled | 26/02/2024 | 01/03/2024
TO-24-220 kV A1 @ RAF-02 | BUSBAR SECTION - RAFFEEN 220-RAFFEEN 220-220A1 | 5 | 5 | 5 | Scheduled | 26/02/2024 | 01/03/2024
TO-24-220 kV B1 @ RAF-02 | BUSBAR SECTION - RAFFEEN 220-RAFFEEN 220-220B1 | 5 | 5 | 5 | Scheduled | 26/02/2024 | 01/03/2024
TO-24-110 kV A2 @ CBT-01 | BUSBAR SECTION - CASTLEBAGOT 110-CASTLEBAGOT 110-110A2 | 2 | 2 | 2 | Scheduled | 27/02/2024 | 28/02/2024
TO-24-110 kV B2 @ CBT-01 | BUSBAR SECTION - CASTLEBAGOT 110-CASTLEBAGOT 110-110B2 | 2 | 2 | 2 | Scheduled | 27/02/2024 | 28/02/2024
TO-24-CBT-110SA1-2CB-02 | COUPLER/SECTIONALISING CB - CASTLEBAGOT 110-CASTLEBAGOT 110-110SA1-2CB | 2 | 2 | 2 | Scheduled | 27/02/2024 | 28/02/2024
TO-24-CBT-110SA2-4CB-02 | COUPLER/SECTIONALISING CB - CASTLEBAGOT 110-CASTLEBAGOT 110-110SA2-4CB | 2 | 2 | 2 | Scheduled | 27/02/2024 | 28/02/2024
TO-24-CBT-110SB1-2CB-02 | COUPLER/SECTIONALISING CB - CASTLEBAGOT 110-CASTLEBAGOT 110-110SB1-2CB | 2 | 2 | 2 | Scheduled | 27/02/2024 | 28/02/2024
TO-24-CBT-110SB2-4CB-02 | COUPLER/SECTIONALISING CB - CASTLEBAGOT 110-CASTLEBAGOT 110-110SB2-4CB | 2 | 2 | 2 | Scheduled | 27/02/2024 | 28/02/2024
TO-24-CBT-T2101-01 | TRANSFORMER - CASTLEBAGOT 220-CASTLEBAGOT 110-T2101 | 2 | 2 | 2 | Scheduled | 27/02/2024 | 28/02/2024
TO-24-CKN-KER-1-03 | 110kV FEEDER - CLONKEEN 110-KNOCKEARAGH 110-1 | 1 | 1 | 1 | Scheduled | 27/02/2024 | 27/02/2024
TO-24-110 kV A1 @ GLN-01 | BUSBAR SECTION - GALLANSTOWN 110-GALLANSTOWN 110-110A1 | 2 | 2 | 2 | Scheduled | 27/02/2024 | 28/02/2024
TO-24-GLN-110K1-02 | COUPLER/SECTIONALISING CB - GALLANSTOWN 110-GALLANSTOWN 110-110K1 | 2 | 2 | 2 | Scheduled | 27/02/2024 | 28/02/2024
TO-24-CAH-DOO-1-03 | 110kV FEEDER - CAHIR 110-DOON 110-1 | 1 | 1 | 1 | Scheduled | 28/02/2024 | 28/02/2024
TO-24-KPG-TRL-1-01 | 110kV FEEDER - KILPADDOGE 110-TRALEE 110-1 | 10 | 8 | 8 | Scheduled | 28/02/2024 | 08/03/2024
TO-24-ATH-110SA1-2CB-04 | COUPLER/SECTIONALISING CB - ATHLONE 110-ATHLONE 110-110SA1-2CB | 2 | 2 | 2 | Scheduled | 29/02/2024 | 01/03/2024
TO-24-ATH-CAP3-05 | CAPACITOR/SVC/REACTOR - ATHLONE 110-ATHLONE 110-CAP3 | 2 | 2 | 2 | Scheduled | 29/02/2024 | 01/03/2024
TO-24-ATH-LA-1-04 | 110kV FEEDER - ATHLONE 110-LANESBORO 110-1 | 2 | 2 | 2 | Scheduled | 29/02/2024 | 01/03/2024
TO-24-ATH-T141-02 | DISTRIBUTION TRANSFORMER - ATHLONE 110-ATHLONE 38-T141 | 2 | 2 | 2 | Reference | 29/02/2024 | 01/03/2024
TO-24-BYH-STATCOM-01 | CAPACITOR/SVC/REACTOR - BALLYNAHULLA 110-BALLYNAHULLA 110-STATCOM | 1 | 1 | 1 | Scheduled | 29/02/2024 | 29/02/2024
TO-24-SKY-T132-01 | GENERATOR TRANSFORMER - SRAHNAKILLY 110-SRAHNAKILLY 33-T132 | 2 | 2 | 2 | Scheduled | 29/02/2024 | 01/03/2024
TO-24-TH-T2001/2-03 | GENERATOR TRANSFORMER - TURLOUGH HILL 220-TURLOUGH HILL G1-T2001/2 | 1 | 0 | 0 | Scheduled | 03/03/2024 | 03/03/2024
TO-24-TH-T2003/4-02 | GENERATOR TRANSFORMER - TURLOUGH HILL 220-TURLOUGH HILL G1-T2003/4 | 4 | 3 | 3 | Scheduled | 03/03/2024 | 06/03/2024
TO-24-AGL-110SA1-01 | SECTIONALISING DISCONNECT - AGANNYGAL 110-AGANNYGAL 110-110SA1 | 22 | 15 |  | Scheduled | 04/03/2024 | 25/03/2024
TO-24-AGL-110SA2-01 | SECTIONALISING DISCONNECT - AGANNYGAL 110-AGANNYGAL 110-110SA2 | 22 | 15 |  | Scheduled | 04/03/2024 | 25/03/2024
TO-24-AGL-DYN-1-01 | 110kV FEEDER - AGANNYGAL 110-DERRYBRIEN 110-1 | 22 | 15 |  | Scheduled | 04/03/2024 | 25/03/2024
TO-24-AGL-ENN-1-01 | 110kV FEEDER - AGANNYGAL 110-ENNIS 110-1 | 22 | 15 | 15 | Scheduled | 04/03/2024 | 25/03/2024
TO-24-AGL-SH-1-01 | 110kV FEEDER - AGANNYGAL 110-SHANNONBRIDGE 110-1 | 22 | 15 | 15 | Scheduled | 04/03/2024 | 25/03/2024
TO-24-220 kV A2 @ AD-04 | BUSBAR SECTION - AGHADA 220-AGHADA 220-220A2 | 12 | 10 | 10 | Scheduled | 04/03/2024 | 15/03/2024
TO-24-220 kV B2 @ AD-04 | BUSBAR SECTION - AGHADA 220-AGHADA 220-220B2 | 12 | 10 | 10 | Scheduled | 04/03/2024 | 15/03/2024
TO-24-AD-SA1-2CB-06 | COUPLER/SECTIONALISING CB - AGHADA 220-AGHADA 220-220SA1-2CB | 12 | 10 | 10 | Scheduled | 04/03/2024 | 15/03/2024
TO-24-AD-SB1-2CB-06 | COUPLER/SECTIONALISING CB - AGHADA 220-AGHADA 220-220SB1-2CB | 12 | 10 | 10 | Scheduled | 04/03/2024 | 15/03/2024
TO-24-AD-KRA-2-01 | 220kV FEEDER - AGHADA 220-KNOCKRAHA 220-2 | 12 | 10 |  | Scheduled | 04/03/2024 | 15/03/2024
TO-24-BAG-T103-01 | TSO CUSTOMER TRANSFORMER - BARNAGEERAGH 110-BARNAGEERAGH 11-T103 | 2 | 2 | 2 | Scheduled | 04/03/2024 | 05/03/2024
TO-24-110 kV A1 @ CBT-02 | BUSBAR SECTION - CASTLEBAGOT 110-CASTLEBAGOT 110-110A1 | 5 | 5 | 5 | Scheduled | 04/03/2024 | 08/03/2024
TO-24-110 kV B1 @ CBT-02 | BUSBAR SECTION - CASTLEBAGOT 110-CASTLEBAGOT 110-110B1 | 5 | 5 | 5 | Scheduled | 04/03/2024 | 08/03/2024
TO-24-CBT-110K1-04 | COUPLER/SECTIONALISING CB - CASTLEBAGOT 110-CASTLEBAGOT 110-110K1 | 5 | 5 | 5 | Scheduled | 04/03/2024 | 08/03/2024
TO-24-CBT-110SA1-2CB-04 | COUPLER/SECTIONALISING CB - CASTLEBAGOT 110-CASTLEBAGOT 110-110SA1-2CB | 5 | 5 | 5 | Scheduled | 04/03/2024 | 08/03/2024
TO-24-CBT-110SB1-2CB-04 | COUPLER/SECTIONALISING CB - CASTLEBAGOT 110-CASTLEBAGOT 110-110SB1-2CB | 5 | 5 | 5 | Scheduled | 04/03/2024 | 08/03/2024
TO-24-CBT-CKG-1-03 | 110kV FEEDER - CASTLEBAGOT 110-CORKAGH 110-1 | 5 | 5 | 5 | Scheduled | 04/03/2024 | 08/03/2024
TO-24-COW-WHI-1-01 | 110kV FEEDER - COW CROSS 110-WHITEGATE 110-1 | 5 | 5 | 5 | Scheduled | 04/03/2024 | 08/03/2024
TO-24-DYN-T121-01 | GENERATOR TRANSFORMER - DERRYBRIEN 110-DERRYBRIEN 20-T121 | 22 | 15 |  | Reference | 04/03/2024 | 25/03/2024
TO-24-220 kV A1 @ DSN-01 | BUSBAR SECTION - DUNSTOWN 220-DUNSTOWN 220-220A1 | 12 | 10 | 10 | Scheduled | 04/03/2024 | 15/03/2024
TO-24-220 kV B1 @ DSN-01 | BUSBAR SECTION - DUNSTOWN 220-DUNSTOWN 220-220B1 | 12 | 10 | 10 | Scheduled | 04/03/2024 | 15/03/2024
TO-24-DSN-TH-1-01 | 220kV FEEDER - DUNSTOWN 220-TURLOUGH HILL 220-1 | 12 | 10 |  | Scheduled | 04/03/2024 | 15/03/2024
TO-24-FLA-SLB-1-04 | 110kV FEEDER - FLAGFORD 110-SLIABH BAWN 110-1 | 47 | 32 | 32 | Scheduled | 04/03/2024 | 19/04/2024
TO-24-220 kV A1 @ KRA-02 | BUSBAR SECTION - KNOCKRAHA 220-KNOCKRAHA 220-220A1 | 12 | 10 | 10 | Scheduled | 04/03/2024 | 15/03/2024
TO-24-220 kV B1 @ KRA-02 | BUSBAR SECTION - KNOCKRAHA 220-KNOCKRAHA 220-220B1 | 12 | 10 | 10 | Scheduled | 04/03/2024 | 15/03/2024
TO-24-KRA-220K1-03 | COUPLER/SECTIONALISING CB - KNOCKRAHA 220-KNOCKRAHA 220-220K1 | 12 | 10 | 10 | Scheduled | 04/03/2024 | 15/03/2024
TO-24-KRA-220SA1-2CB-03 | COUPLER/SECTIONALISING CB - KNOCKRAHA 220-KNOCKRAHA 220-220SA1-2CB | 12 | 10 | 10 | Scheduled | 04/03/2024 | 15/03/2024
TO-24-KRA-220SB1-2CB-03 | COUPLER/SECTIONALISING CB - KNOCKRAHA 220-KNOCKRAHA 220-220SB1-2CB | 12 | 10 | 10 | Scheduled | 04/03/2024 | 15/03/2024
TO-24-PB-R2001-01 | CAPACITOR/SVC/REACTOR - POOLBEG 220-POOLBEG 220-R2001 | 5 | 5 | 5 | Scheduled | 04/03/2024 | 08/03/2024
TO-24-RAF-RSY-1-01 | 110kV FEEDER - RAFFEEN 110-RINGASKIDDY 110-1 | 12 | 10 |  | Reference | 04/03/2024 | 15/03/2024
TO-24-220 kV A1 @ TH-01 | BUSBAR SECTION - TURLOUGH HILL 220-TURLOUGH HILL 220-220A1 | 12 | 10 | 10 | Scheduled | 04/03/2024 | 15/03/2024
TO-24-220 kV B1 @ TH-01 | BUSBAR SECTION - TURLOUGH HILL 220-TURLOUGH HILL 220-220B1 | 12 | 10 | 10 | Scheduled | 04/03/2024 | 15/03/2024
TO-24-BDN-DOO-1-01 | 110kV FEEDER - BALLYDINE 110-DOON 110-1 | 9 | 7 | 7 | Scheduled | 05/03/2024 | 13/03/2024
TO-24-BVK-STATCOM-01 | CAPACITOR/SVC/REACTOR - BALLYVOUSKILL 110-BALLYVOUSKILL 110-STATCOM | 1 | 1 | 1 | Scheduled | 05/03/2024 | 05/03/2024
TO-24-KRA-220K4-02 | COUPLER/SECTIONALISING CB - KNOCKRAHA 220-KNOCKRAHA 220-220K4 | 85 | 57 | 57 | Scheduled | 05/03/2024 | 28/05/2024
TO-24-KRA-220SA2-4CB-02 | COUPLER/SECTIONALISING CB - KNOCKRAHA 220-KNOCKRAHA 220-220SA2-4CB | 85 | 57 | 57 | Scheduled | 05/03/2024 | 28/05/2024
TO-24-KRA-220SB2-4CB-01 | COUPLER/SECTIONALISING CB - KNOCKRAHA 220-KNOCKRAHA 220-220SB2-4CB | 85 | 57 | 57 | Scheduled | 05/03/2024 | 28/05/2024
TO-24-110 kV A1 @ GLN-02 | BUSBAR SECTION - GALLANSTOWN 110-GALLANSTOWN 110-110A1 | 1 | 1 | 1 | Scheduled | 06/03/2024 | 06/03/2024
TO-24-GLN-110K1-05 | COUPLER/SECTIONALISING CB - GALLANSTOWN 110-GALLANSTOWN 110-110K1 | 1 | 1 | 1 | Scheduled | 06/03/2024 | 06/03/2024
TO-24-GLN-T133-06 | GENERATOR TRANSFORMER - GALLANSTOWN 110-GALLANSTOWN 33-T133 | 1 | 1 | 1 | Scheduled | 06/03/2024 | 06/03/2024
TO-24-ISH-T2002/3-01 | GENERATOR TRANSFORMER - IRISHTOWN 220-IRISHTOWN G2/3-T2002/3 | 2 | 2 | 2 | Scheduled | 06/03/2024 | 07/03/2024
TO-24-TH-T2001/2-02 | GENERATOR TRANSFORMER - TURLOUGH HILL 220-TURLOUGH HILL G1-T2001/2 | 4 | 3 | 3 | Scheduled | 10/03/2024 | 13/03/2024
TO-24-220 kV A1 @ AD-03 | BUSBAR SECTION - AGHADA 220-AGHADA 220-220A1 | 5 | 5 | 5 | Scheduled | 11/03/2024 | 15/03/2024
TO-24-220 kV B1 @ AD-02 | BUSBAR SECTION - AGHADA 220-AGHADA 220-220B1 | 5 | 5 | 5 | Scheduled | 11/03/2024 | 15/03/2024
TO-24-AD-220K1-04 | COUPLER/SECTIONALISING CB - AGHADA 220-AGHADA 220-220K1 | 5 | 5 | 5 | Scheduled | 11/03/2024 | 15/03/2024
TO-24-AD-SA1-2CB-03 | COUPLER/SECTIONALISING CB - AGHADA 220-AGHADA 220-220SA1-2CB | 5 | 5 | 5 | Scheduled | 11/03/2024 | 15/03/2024
TO-24-AD-SB1-2CB-03 | COUPLER/SECTIONALISING CB - AGHADA 220-AGHADA 220-220SB1-2CB | 5 | 5 | 5 | Scheduled | 11/03/2024 | 15/03/2024
TO-24-ARK-BEG-1-01 | 110kV FEEDER - ARKLOW 110-BALLYBEG 110-1 | 12 | 9 |  | Scheduled | 11/03/2024 | 22/03/2024
TO-24-BYH-T2101-01 | TRANSFORMER - BALLYNAHULLA 220-BALLYNAHULLA 110-T2101 | 5 | 5 | 5 | Scheduled | 11/03/2024 | 15/03/2024
TO-24-220 kV A2 @ CBT-03 | BUSBAR SECTION - CASTLEBAGOT 220-CASTLEBAGOT 220-220A2 | 12 | 9 | 9 | Scheduled | 11/03/2024 | 22/03/2024
TO-24-220 kV B2 @ CBT-03 | BUSBAR SECTION - CASTLEBAGOT 220-CASTLEBAGOT 220-220B2 | 12 | 9 | 9 | Scheduled | 11/03/2024 | 22/03/2024
TO-24-CBT-220K2-04 | COUPLER/SECTIONALISING CB - CASTLEBAGOT 220-CASTLEBAGOT 220-220K2 | 12 | 9 | 9 | Scheduled | 11/03/2024 | 22/03/2024
TO-24-CBT-220SA1-2CB-03 | COUPLER/SECTIONALISING CB - CASTLEBAGOT 220-CASTLEBAGOT 220-220SA1-2CB | 12 | 9 | 9 | Scheduled | 11/03/2024 | 22/03/2024
TO-24-CBT-220SB1-2CB-04 | COUPLER/SECTIONALISING CB - CASTLEBAGOT 220-CASTLEBAGOT 220-220SB1-2CB | 12 | 9 | 9 | Scheduled | 11/03/2024 | 22/03/2024
TO-24-220 kV B2/B4 @ CDU-01 | BUSBAR SECTION - CORDUFF 220-CORDUFF 220-220B2-B4 | 5 | 5 | 5 | Scheduled | 11/03/2024 | 15/03/2024
TO-24-CDU-WOO-1-02 | 220kV FEEDER - CORDUFF 220-WOODLAND 220-1 | 5 | 5 | 5 | Scheduled | 11/03/2024 | 15/03/2024
TO-24-COW-RAF-1-02 | 110kV FEEDER - COW CROSS 110-RAFFEEN 110-1 | 5 | 5 | 5 | Scheduled | 11/03/2024 | 15/03/2024
TO-24-LPT-T2002-01 | GENERATOR TRANSFORMER - LONG POINT 220-LONG POINT G1-T2002 | 5 | 5 | 5 | Scheduled | 11/03/2024 | 15/03/2024
TO-24-BAG-T101-01 | TSO CUSTOMER TRANSFORMER - BARNAGEERAGH 110-BARNAGEERAGH 11-T101 | 2 | 2 | 2 | Scheduled | 12/03/2024 | 13/03/2024
TO-24-110 kV A1 @ CBT-03 | BUSBAR SECTION - CASTLEBAGOT 110-CASTLEBAGOT 110-110A1 | 3 | 3 | 3 | Scheduled | 12/03/2024 | 14/03/2024
TO-24-110 kV A2 @ CBT-02 | BUSBAR SECTION - CASTLEBAGOT 110-CASTLEBAGOT 110-110A2 | 3 | 3 | 3 | Scheduled | 12/03/2024 | 14/03/2024
TO-24-CBT-110SA1-2CB-03 | COUPLER/SECTIONALISING CB - CASTLEBAGOT 110-CASTLEBAGOT 110-110SA1-2CB | 3 | 3 | 3 | Scheduled | 12/03/2024 | 14/03/2024
TO-24-BAN-110SA1-01 | SECTIONALISING DISCONNECT - BANDON 110-BANDON 110-110SA1 | 15 | 10 | 10 | Scheduled | 14/03/2024 | 28/03/2024
TO-24-BAN-110SA2-02 | SECTIONALISING DISCONNECT - BANDON 110-BANDON 110-110SA2 | 15 | 10 | 10 | Scheduled | 14/03/2024 | 28/03/2024
TO-24-BAN-BRI-1-01 | 110kV FEEDER - BANDON 110-BRINNY 110-1 | 15 | 10 | 10 | Scheduled | 14/03/2024 | 28/03/2024
TO-24-BAN-CAP1-02 | CAPACITOR/SVC/REACTOR - BANDON 110-BANDON 110-CAP1 | 15 | 10 | 10 | Scheduled | 14/03/2024 | 28/03/2024
TO-24-BAN-DMY-1-02 | 110kV FEEDER - BANDON 110-DUNMANWAY 110-1 | 15 | 10 | 10 | Scheduled | 14/03/2024 | 28/03/2024
TO-24-BAN-T101-01 | DISTRIBUTION TRANSFORMER - BANDON 110-BANDON 10-T101 | 15 | 10 | 10 | Reference | 14/03/2024 | 28/03/2024
TO-24-BAN-T141-01 | DISTRIBUTION TRANSFORMER - BANDON 110-BANDON 38-T141 | 15 | 10 | 10 | Reference | 14/03/2024 | 28/03/2024
TO-24-BRI-T101-02 | TSO CUSTOMER TRANSFORMER - BRINNY 110-BRINNY 10-T101 | 15 | 10 | 10 | Scheduled | 14/03/2024 | 28/03/2024
TO-24-THU-CAP1-03 | CAPACITOR/SVC/REACTOR - THURLES 110-THURLES 110-CAP1 | 1 | 1 | 1 | Scheduled | 14/03/2024 | 14/03/2024
TO-24-THU-STATCOM-02 | CAPACITOR/SVC/REACTOR - THURLES 110-THURLES 110-STATCOM | 1 | 1 | 1 | Scheduled | 14/03/2024 | 14/03/2024
TO-24-BOL-T141-01 | DISTRIBUTION TRANSFORMER - BOOLTIAGH 110-BOOLTIAGH 38-T141 | 154 | 104 | 104 | Reference | 15/03/2024 | 15/08/2024
TO-24-CKM GIS-T2104-02 | TRANSFORMER - CARRICKMINES GIS 220-CARRICKMINES GIS 110-T2104 | 11 | 8 | 8 | Reference | 18/03/2024 | 28/03/2024
TO-24-CUN-GLR-1-01 | 110kV FEEDER - CUNGHILL 110-GLENREE 110-1 | 5 | 4 | 4 | Scheduled | 18/03/2024 | 22/03/2024
TO-24-110 kV A2 @ GLR-01 | BUSBAR SECTION - GLENREE 110-GLENREE 110-110A2 | 5 | 4 | 4 | Scheduled | 18/03/2024 | 22/03/2024
TO-24-GLR-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - GLENREE 110-GLENREE 110-110SA1-2CB | 5 | 4 | 4 | Scheduled | 18/03/2024 | 22/03/2024
TO-24-GLR-T142-01 | DISTRIBUTION TRANSFORMER - GLENREE 110-GLENREE 38-T142 | 5 | 4 | 4 | Reference | 18/03/2024 | 22/03/2024
TO-24-220 kV A1 @ AD-02 | BUSBAR SECTION - AGHADA 220-AGHADA 220-220A1 | 16 | 10 | 10 | Scheduled | 19/03/2024 | 03/04/2024
TO-24-220 kV A2 @ AD-01 | BUSBAR SECTION - AGHADA 220-AGHADA 220-220A2 | 16 | 10 | 10 | Scheduled | 19/03/2024 | 03/04/2024
TO-24-220 kV B1 @ AD-01 | BUSBAR SECTION - AGHADA 220-AGHADA 220-220B1 | 16 | 10 | 10 | Scheduled | 19/03/2024 | 03/04/2024
TO-24-220 kV B2 @ AD-01 | BUSBAR SECTION - AGHADA 220-AGHADA 220-220B2 | 16 | 10 | 10 | Scheduled | 19/03/2024 | 03/04/2024
TO-24-AD-220K1-03 | COUPLER/SECTIONALISING CB - AGHADA 220-AGHADA 220-220K1 | 16 | 10 | 10 | Scheduled | 19/03/2024 | 03/04/2024
TO-24-AD-SA1-2CB-01 | COUPLER/SECTIONALISING CB - AGHADA 220-AGHADA 220-220SA1-2CB | 16 | 10 | 10 | Scheduled | 19/03/2024 | 03/04/2024
TO-24-AD-SB1-2CB-01 | COUPLER/SECTIONALISING CB - AGHADA 220-AGHADA 220-220SB1-2CB | 16 | 10 | 10 | Scheduled | 19/03/2024 | 03/04/2024
TO-24-AD-KRA-1-01 | 220kV FEEDER - AGHADA 220-KNOCKRAHA 220-1 | 16 | 10 |  | Scheduled | 19/03/2024 | 03/04/2024
TO-24-AD-T2102-01 | TRANSFORMER - AGHADA 220-AGHADA 110-T2102 | 16 | 10 | 10 | Scheduled | 19/03/2024 | 03/04/2024
TO-24-BIN-TIV-1-01 | 110kV FEEDER - BINBANE 110-TIEVEBRACK 110-1 | 4 | 4 | 4 | Scheduled | 19/03/2024 | 22/03/2024
TO-24-110 kV A1/A2 @ CAH-01 | BUSBAR SECTION - CAHIR 110-CAHIR 110-110A1-A2 | 10 | 8 | 8 | Scheduled | 19/03/2024 | 28/03/2024
TO-24-110 kV B1/B2 @ CAH-01 | BUSBAR SECTION - CAHIR 110-CAHIR 110-110B1-B2 | 10 | 8 | 8 | Scheduled | 19/03/2024 | 28/03/2024
TO-24-CAH-110K1-2-01 | COUPLER/SECTIONALISING CB - CAHIR 110-CAHIR 110-110K1-2 | 10 | 8 | 8 | Scheduled | 19/03/2024 | 28/03/2024
TO-24-CAH-T141-01 | DISTRIBUTION TRANSFORMER - CAHIR 110-CAHIR 38-T141 | 7 | 5 | 5 | Reference | 19/03/2024 | 25/03/2024
TO-24-CGG-DMY-1-01 | 110kV FEEDER - CARRIGDANGAN 110-DUNMANWAY 110-1 | 7 | 5 | 5 | Scheduled | 19/03/2024 | 25/03/2024
TO-24-CGG-T131-01 | GENERATOR TRANSFORMER - CARRIGDANGAN 110-CARRIGDANGAN 33-T131 | 7 | 5 | 5 | Scheduled | 19/03/2024 | 25/03/2024
TO-24-110 kV A2 @ CLA-01 | BUSBAR SECTION - CLASHAVOON 110-CLASHAVOON 110-110A2 | 10 | 8 | 8 | Scheduled | 19/03/2024 | 28/03/2024
TO-24-110 kV B2 @ CLA-01 | BUSBAR SECTION - CLASHAVOON 110-CLASHAVOON 110-110B2 | 10 | 8 | 8 | Scheduled | 19/03/2024 | 28/03/2024
TO-24-CLA-MAC-2-03 | 110kV FEEDER - CLASHAVOON 110-MACROOM 110-2 | 10 | 8 | 8 | Scheduled | 19/03/2024 | 28/03/2024
TO-24-DER-110SA1-01 | SECTIONALISING DISCONNECT - DERRYIRON 110-DERRYIRON 110-110SA1 | 23 | 15 | 15 | Scheduled | 19/03/2024 | 10/04/2024
TO-24-DER-110SA2-01 | SECTIONALISING DISCONNECT - DERRYIRON 110-DERRYIRON 110-110SA2 | 23 | 15 | 15 | Scheduled | 19/03/2024 | 10/04/2024
TO-24-DER-KIN-1-02 | 110kV FEEDER - DERRYIRON 110-KINNEGAD 110-1 | 23 | 15 | 15 | Scheduled | 19/03/2024 | 10/04/2024
TO-24-DER-T1/T2-02 | GENERATOR TRANSFORMER - DERRYIRON 110-RHODE 110-T1/T2 | 23 | 15 | 15 | Scheduled | 19/03/2024 | 10/04/2024
TO-24-GI-WAT-2-01 | 110kV FEEDER - GREAT ISLAND 110-WATERFORD 110-2 | 4 | 4 | 4 | Scheduled | 19/03/2024 | 22/03/2024
TO-24-KYT-MAY-1-01 | 220kV FEEDER - KELLYSTOWN 220-MAYNOOTH 220-1 | 10 | 8 | 8 | Scheduled | 19/03/2024 | 28/03/2024
TO-24-220 kV A2 @ KRA-02 | BUSBAR SECTION - KNOCKRAHA 220-KNOCKRAHA 220-220A2 | 16 | 10 | 10 | Scheduled | 19/03/2024 | 03/04/2024
TO-24-220 kV B2 @ KRA-02 | BUSBAR SECTION - KNOCKRAHA 220-KNOCKRAHA 220-220B2 | 16 | 10 | 10 | Scheduled | 19/03/2024 | 03/04/2024
TO-24-KRA-220SA1-2CB-02 | COUPLER/SECTIONALISING CB - KNOCKRAHA 220-KNOCKRAHA 220-220SA1-2CB | 16 | 10 | 10 | Scheduled | 19/03/2024 | 03/04/2024
TO-24-KRA-220SB1-2CB-02 | COUPLER/SECTIONALISING CB - KNOCKRAHA 220-KNOCKRAHA 220-220SB1-2CB | 16 | 10 | 10 | Scheduled | 19/03/2024 | 03/04/2024
TO-24-NAV-T141-01 | DISTRIBUTION TRANSFORMER - NAVAN 110-NAVAN 38-T141 | 81 | 55 |  | Reference | 19/03/2024 | 07/06/2024
TO-24-WOO-400K1-2-01 | COUPLER/SECTIONALISING CB - WOODLAND 400-WOODLAND 400-400K1-2 | 4 | 4 | 4 | Scheduled | 19/03/2024 | 22/03/2024
TO-24-CBA-110SA1-01 | SECTIONALISING DISCONNECT - CLOGHBOOLA 110-CLOGHBOOLA 110-110SA1 | 2 | 2 | 2 | Scheduled | 20/03/2024 | 21/03/2024
TO-24-CBA-110SA2-01 | SECTIONALISING DISCONNECT - CLOGHBOOLA 110-CLOGHBOOLA 110-110SA2 | 2 | 2 | 2 | Scheduled | 20/03/2024 | 21/03/2024
TO-24-CBA-T122-02 | DISTRIBUTION TRANSFORMER - CLOGHBOOLA 110-CLOGHBOOLA 20-T122 | 2 | 2 | 2 | Reference | 20/03/2024 | 21/03/2024
TO-24-CBA-T131-02 | GENERATOR TRANSFORMER - CLOGHBOOLA 110-CLOGHBOOLA 33-T131 | 2 | 2 | 2 | Scheduled | 20/03/2024 | 21/03/2024
TO-24-DEY-T134-02 | GENERATOR TRANSFORMER - DERRYCARNEY 110-DERRYCARNEY 33-T134 | 2 | 2 | 2 | Scheduled | 20/03/2024 | 21/03/2024
TO-24-110 kV A1 @ GOR-02 | BUSBAR SECTION - GORMAN 110-GORMAN 110-110A1 | 9 | 7 | 7 | Scheduled | 20/03/2024 | 28/03/2024
TO-24-110 kV B1 @ GOR-01 | BUSBAR SECTION - GORMAN 110-GORMAN 110-110B1 | 9 | 7 | 7 | Scheduled | 20/03/2024 | 28/03/2024
TO-24-110 kV A1 @ SH-03 | BUSBAR SECTION - SHANNONBRIDGE 110-SHANNONBRIDGE 110-110A1 | 2 | 2 |  | Scheduled | 21/03/2024 | 22/03/2024
TO-24-SH-T2101-02 | TRANSFORMER - SHANNONBRIDGE 220-SHANNONBRIDGE 110-T2101 | 2 | 2 |  | Scheduled | 21/03/2024 | 22/03/2024
TO-24-BYH-T2102-01 | TRANSFORMER - BALLYNAHULLA 220-BALLYNAHULLA 110-T2102 | 4 | 4 | 4 | Scheduled | 25/03/2024 | 28/03/2024
TO-24-CAH-T142-01 | DISTRIBUTION TRANSFORMER - CAHIR 110-CAHIR 38-T142 | 4 | 4 | 4 | Reference | 25/03/2024 | 28/03/2024
TO-24-CBR-DLT-1-03 | 110kV FEEDER - CASTLEBAR 110-DALTON 110-1 | 4 | 4 | 4 | Scheduled | 25/03/2024 | 28/03/2024
TO-24-110 kV A2 @ CF-04 | BUSBAR SECTION - CATHALEENS FALL 110-CATHALEENS FALL 110-110A2 | 4 | 4 | 4 | Scheduled | 25/03/2024 | 28/03/2024
TO-24-110 kV B2 @ CF-01 | BUSBAR SECTION - CATHALEENS FALL 110-CATHALEENS FALL 110-110B2 | 4 | 4 | 4 | Scheduled | 25/03/2024 | 28/03/2024
TO-24-CF-SRA-2-03 | 110kV FEEDER - CATHALEENS FALL 110-SRANANAGH 110-2 | 4 | 4 | 4 | Scheduled | 25/03/2024 | 28/03/2024
TO-24-220 kV A1 @ CDU-01 | BUSBAR SECTION - CORDUFF 220-CORDUFF 220-220A1 | 4 | 4 | 4 | Scheduled | 25/03/2024 | 28/03/2024
TO-24-220 kV A2 @ CDU-01 | BUSBAR SECTION - CORDUFF 220-CORDUFF 220-220A2 | 4 | 4 | 4 | Scheduled | 25/03/2024 | 28/03/2024
TO-24-220 kV A3 @ CDU-01 | BUSBAR SECTION - CORDUFF 220-CORDUFF 220-220A3 | 4 | 4 | 4 | Scheduled | 25/03/2024 | 28/03/2024
TO-24-220 kV A4 @ CDU-01 | BUSBAR SECTION - CORDUFF 220-CORDUFF 220-220A4 | 4 | 4 | 4 | Scheduled | 25/03/2024 | 28/03/2024
TO-24-220 kV B1 @ CDU-01 | BUSBAR SECTION - CORDUFF 220-CORDUFF 220-220B1 | 4 | 4 | 4 | Scheduled | 25/03/2024 | 28/03/2024
TO-24-220 kV B2 @ CDU-01 | BUSBAR SECTION - CORDUFF 220-CORDUFF 220-220B2 | 4 | 4 | 4 | Scheduled | 25/03/2024 | 28/03/2024
TO-24-220 kV B3 @ CDU-01 | BUSBAR SECTION - CORDUFF 220-CORDUFF 220-220B3 | 4 | 4 | 4 | Scheduled | 25/03/2024 | 28/03/2024
TO-24-220 kV B4 @ CDU-01 | BUSBAR SECTION - CORDUFF 220-CORDUFF 220-220B4 | 4 | 4 | 4 | Scheduled | 25/03/2024 | 28/03/2024
TO-24-TAW-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - TAWNAGHMORE 110-TAWNAGHMORE 110-110SA1-2CB | 4 | 4 | 4 | Scheduled | 25/03/2024 | 28/03/2024
TO-24-CKM GIS-R2001-01 | CAPACITOR/SVC/REACTOR - CARRICKMINES GIS 220-CARRICKMINES GIS 220-R2001 | 18 | 12 |  | Scheduled | 26/03/2024 | 12/04/2024
TO-24-DAL,T-SH-1-02 | 110kV FEEDER - DALLOW tee-SHANNONBRIDGE 110-1 | 77 | 51 | 51 | Scheduled | 26/03/2024 | 10/06/2024
TO-24-AUG-KPG-1-01 | 110kV FEEDER - AUGHINISH 110-KILPADDOGE 110-1 | 4 | 4 |  | Scheduled | 02/04/2024 | 05/04/2024
TO-24-CBR-SVC-02 | CAPACITOR/SVC/REACTOR - CASTLEBAR 110-CASTLEBAR 110-SVC | 4 | 4 | 4 | Scheduled | 02/04/2024 | 05/04/2024
TO-24-220 kV A2 @ CDU-03 | BUSBAR SECTION - CORDUFF 220-CORDUFF 220-220A2 | 25 | 19 | 19 | Scheduled | 02/04/2024 | 26/04/2024
TO-24-220 kV A4 @ CDU-02 | BUSBAR SECTION - CORDUFF 220-CORDUFF 220-220A4 | 11 | 9 | 9 | Scheduled | 02/04/2024 | 12/04/2024
TO-24-220 kV B2 @ CDU-03 | BUSBAR SECTION - CORDUFF 220-CORDUFF 220-220B2 | 25 | 19 | 19 | Scheduled | 02/04/2024 | 26/04/2024
TO-24-220 kV B4 @ CDU-02 | BUSBAR SECTION - CORDUFF 220-CORDUFF 220-220B4 | 11 | 9 | 9 | Scheduled | 02/04/2024 | 12/04/2024
TO-24-DRM-LET-1-01 | 110kV FEEDER - DRUMKEEN 110-LETTERKENNY 110-1 | 4 | 4 | 4 | Scheduled | 02/04/2024 | 05/04/2024
TO-24-GI-T141-01 | DISTRIBUTION TRANSFORMER - GREAT ISLAND 110-GREAT ISLAND 38-T141 | 232 | 162 | 162 | Reference | 02/04/2024 | 19/11/2024
TO-24-OBE-PLA-1-02 | 110kV FEEDER - OLDBRIDGE 110-PLATIN 110-1 | 9 | 7 |  | Scheduled | 02/04/2024 | 10/04/2024
TO-24-PLA-110SA1-03 | SECTIONALISING DISCONNECT - PLATIN 110-PLATIN 110-110SA1 | 9 | 7 |  | Scheduled | 02/04/2024 | 10/04/2024
TO-24-PLA-110SA2-03 | SECTIONALISING DISCONNECT - PLATIN 110-PLATIN 110-110SA2 | 9 | 7 |  | Scheduled | 02/04/2024 | 10/04/2024
TO-24-BLU-110K1-01 | COUPLER/SECTIONALISING CB - BLUNDELSTOWN 110-BLUNDELSTOWN 110-110K1 | 1 | 1 | 1 | Scheduled | 03/04/2024 | 03/04/2024
TO-24-GAR-110K1-01 | COUPLER/SECTIONALISING CB - GARBALLAGH 110-GARBALLAGH 110-110K1 | 1 | 1 | 1 | Scheduled | 03/04/2024 | 03/04/2024
TO-24-LET-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - LETTERKENNY 110-LETTERKENNY 110-110SA1-2CB | 2 | 2 | 2 | Scheduled | 03/04/2024 | 04/04/2024
TO-24-LET-110SA1-3CB-02 | COUPLER/SECTIONALISING CB - LETTERKENNY 110-LETTERKENNY 110-110SA1-3CB | 2 | 2 | 2 | Scheduled | 03/04/2024 | 04/04/2024
TO-24-LET-M/CAP1-01 | CAPACITOR/SVC/REACTOR - LETTERKENNY 110-LETTERKENNY 110-M/CAP1 | 2 | 2 | 2 | Scheduled | 03/04/2024 | 04/04/2024
TO-24-LET-PST-01 | TRANSFORMER - LETTERKENNY 110-STRABANE 110-PST | 2 | 2 | 2 | Scheduled | 03/04/2024 | 04/04/2024
TO-24-LET-SVC-01 | CAPACITOR/SVC/REACTOR - LETTERKENNY 110-LETTERKENNY 110-SVC | 2 | 2 | 2 | Scheduled | 03/04/2024 | 04/04/2024
TO-24-LET-T141-01 | DISTRIBUTION TRANSFORMER - LETTERKENNY 110-LETTERKENNY 38-T141 | 2 | 2 |  | Reference | 03/04/2024 | 04/04/2024
TO-24-BYH-220SB1-2CB-01 | COUPLER/SECTIONALISING CB - BALLYNAHULLA 220-BALLYNAHULLA 220-220SB1-2CB | 1 | 1 | 1 | Scheduled | 04/04/2024 | 04/04/2024
TO-24-BVK-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - BALLYVOUSKILL 110-BALLYVOUSKILL 110-110SA1-2CB | 1 | 1 | 1 | Scheduled | 04/04/2024 | 04/04/2024
TO-24-CKM GIS-220SB1-3CB-01 | COUPLER/SECTIONALISING CB - CARRICKMINES GIS 220-CARRICKMINES GIS 220-22SB1-3CB | 1 | 1 | 1 | Scheduled | 04/04/2024 | 04/04/2024
TO-24-220 kV A2 @ CUL-02 | BUSBAR SECTION - CULLENAGH 220-CULLENAGH 220-220A2 | 43 | 30 | 30 | Scheduled | 04/04/2024 | 16/05/2024
TO-24-220 kV B2 @ CUL-02 | BUSBAR SECTION - CULLENAGH 220-CULLENAGH 220-220B2 | 43 | 30 | 30 | Scheduled | 04/04/2024 | 16/05/2024
TO-24-CUL-KRA-1-01 | 220kV FEEDER - CULLENAGH 220-KNOCKRAHA 220-1 | 55 | 38 | 38 | Scheduled | 04/04/2024 | 28/05/2024
TO-24-GAR-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - GARBALLAGH 110-GARBALLAGH 110-110SA1-2CB | 1 | 1 | 1 | Scheduled | 04/04/2024 | 04/04/2024
TO-24-GI-KKY-1-01 | 110kV FEEDER - GREAT ISLAND 110-KILKENNY 110-1 | 9 | 7 | 7 | Scheduled | 04/04/2024 | 12/04/2024
TO-24-GI-WAT-1-01 | 110kV FEEDER - GREAT ISLAND 110-WATERFORD 110-1 | 2 | 2 | 2 | Scheduled | 04/04/2024 | 05/04/2024
TO-24-220 kV A2 @ KRA-01 | BUSBAR SECTION - KNOCKRAHA 220-KNOCKRAHA 220-220A2 | 55 | 38 | 38 | Scheduled | 04/04/2024 | 28/05/2024
TO-24-220 kV B2 @ KRA-01 | BUSBAR SECTION - KNOCKRAHA 220-KNOCKRAHA 220-220B2 | 55 | 38 | 38 | Scheduled | 04/04/2024 | 28/05/2024
TO-24-KRA-220SA1-2CB-01 | COUPLER/SECTIONALISING CB - KNOCKRAHA 220-KNOCKRAHA 220-220SA1-2CB | 55 | 38 | 38 | Scheduled | 04/04/2024 | 28/05/2024
TO-24-KRA-220SB1-2CB-01 | COUPLER/SECTIONALISING CB - KNOCKRAHA 220-KNOCKRAHA 220-220SB1-2CB | 55 | 38 | 38 | Scheduled | 04/04/2024 | 28/05/2024
TO-24-KRA-RAF-1-01 | 220kV FEEDER - KNOCKRAHA 220-RAFFEEN 220-1 | 55 | 38 | 38 | Scheduled | 04/04/2024 | 28/05/2024
TO-24-BVK-110SB1-2CB-01 | COUPLER/SECTIONALISING CB - BALLYVOUSKILL 110-BALLYVOUSKILL 110-110SB1-2CB | 1 | 1 | 1 | Scheduled | 05/04/2024 | 05/04/2024
TO-24-GAR-110SB1-2CB-01 | COUPLER/SECTIONALISING CB - GARBALLAGH 110-GARBALLAGH 110-110SB1-2CB | 1 | 1 | 1 | Scheduled | 05/04/2024 | 05/04/2024
TO-24-220 kV A1 @ BYH-01 | BUSBAR SECTION - BALLYNAHULLA 220-BALLYNAHULLA 220-220A1 | 5 | 5 | 5 | Scheduled | 08/04/2024 | 12/04/2024
TO-24-220 kV B1 @ BYH-01 | BUSBAR SECTION - BALLYNAHULLA 220-BALLYNAHULLA 220-220B1 | 5 | 5 | 5 | Scheduled | 08/04/2024 | 12/04/2024
TO-24-BYH-220K1-01 | COUPLER/SECTIONALISING CB - BALLYNAHULLA 220-BALLYNAHULLA 220-220K1 | 5 | 5 | 5 | Scheduled | 08/04/2024 | 12/04/2024
TO-24-BYH-220SA1-2CB-01 | COUPLER/SECTIONALISING CB - BALLYNAHULLA 220-BALLYNAHULLA 220-220SA1-2CB | 5 | 5 | 5 | Scheduled | 08/04/2024 | 12/04/2024
TO-24-BYH-220SB1-2CB-02 | COUPLER/SECTIONALISING CB - BALLYNAHULLA 220-BALLYNAHULLA 220-220SB1-2CB | 5 | 5 | 5 | Scheduled | 08/04/2024 | 12/04/2024
TO-24-BK-CBR-1-01 | 110kV FEEDER - BELLACORICK 110-CASTLEBAR 110-1 | 12 | 10 | 10 | Scheduled | 08/04/2024 | 19/04/2024
TO-24-BK-SKY-1-01 | 110kV FEEDER - BELLACORICK 110-SRAHNAKILLY 110-1 | 33 | 24 | 24 | Scheduled | 08/04/2024 | 10/05/2024
TO-24-110 kV A4 @ CBT-03 | BUSBAR SECTION - CASTLEBAGOT 110-CASTLEBAGOT 110-110A4 | 5 | 5 | 5 | Scheduled | 08/04/2024 | 12/04/2024
TO-24-110 kV B4 @ CBT-03 | BUSBAR SECTION - CASTLEBAGOT 110-CASTLEBAGOT 110-110B4 | 5 | 5 | 5 | Scheduled | 08/04/2024 | 12/04/2024
TO-24-CBT-110K4-02 | COUPLER/SECTIONALISING CB - CASTLEBAGOT 110-CASTLEBAGOT 110-110K4 | 5 | 5 | 5 | Scheduled | 08/04/2024 | 12/04/2024
TO-24-CBT-110SA2-4CB-04 | COUPLER/SECTIONALISING CB - CASTLEBAGOT 110-CASTLEBAGOT 110-110SA2-4CB | 5 | 5 | 5 | Scheduled | 08/04/2024 | 12/04/2024
TO-24-CBT-110SB2-4CB-04 | COUPLER/SECTIONALISING CB - CASTLEBAGOT 110-CASTLEBAGOT 110-110SB2-4CB | 5 | 5 | 5 | Scheduled | 08/04/2024 | 12/04/2024
TO-24-CL-T101-02 | GENERATOR TRANSFORMER - CLIFF 110-CLIFF G1-T101 | 5 | 5 |  | Scheduled | 08/04/2024 | 12/04/2024
TO-24-CRO-110SA1-01 | SECTIONALISING DISCONNECT - COOLROE 110-COOLROE 110-110SA1 | 5 | 5 | 5 | Scheduled | 08/04/2024 | 12/04/2024
TO-24-CRO-110SA2-02 | SECTIONALISING DISCONNECT - COOLROE 110-COOLROE 110-110SA2 | 5 | 5 | 5 | Scheduled | 08/04/2024 | 12/04/2024
TO-24-CRO-KBY-1-01 | 110kV FEEDER - COOLROE 110-KILBARRY 110-1 | 5 | 5 |  | Scheduled | 08/04/2024 | 12/04/2024
TO-24-CRO-T121-01 | DISTRIBUTION TRANSFORMER - COOLROE 110-COOLROE 20-T121 | 5 | 5 | 5 | Reference | 08/04/2024 | 12/04/2024
TO-24-220 kV A1 @ RAF-03 | BUSBAR SECTION - RAFFEEN 220-RAFFEEN 220-220A1 | 5 | 5 | 5 | Scheduled | 08/04/2024 | 12/04/2024
TO-24-220 kV B1 @ RAF-03 | BUSBAR SECTION - RAFFEEN 220-RAFFEEN 220-220B1 | 5 | 5 | 5 | Scheduled | 08/04/2024 | 12/04/2024
TO-24-110 kV A2 @ SLB-01 | BUSBAR SECTION - SLIABH BAWN 110-SLIABH BAWN 110-110A2 | 5 | 5 | 5 | Scheduled | 08/04/2024 | 12/04/2024
TO-24-110 kV B2 @ SLB-01 | BUSBAR SECTION - SLIABH BAWN 110-SLIABH BAWN 110-110B2 | 5 | 5 | 5 | Scheduled | 08/04/2024 | 12/04/2024
TO-24-SKY-110SA1-01 | SECTIONALISING DISCONNECT - SRAHNAKILLY 110-SRAHNAKILLY 110-110SA1 | 33 | 24 | 24 | Scheduled | 08/04/2024 | 10/05/2024
TO-24-SKY-110SA2-01 | SECTIONALISING DISCONNECT - SRAHNAKILLY 110-SRAHNAKILLY 110-110SA2 | 33 | 24 | 24 | Scheduled | 08/04/2024 | 10/05/2024
TO-24-SKY-T131-02 | GENERATOR TRANSFORMER - SRAHNAKILLY 110-SRAHNAKILLY 33-T131 | 33 | 24 | 24 | Scheduled | 08/04/2024 | 10/05/2024
TO-24-SKY-T132-02 | GENERATOR TRANSFORMER - SRAHNAKILLY 110-SRAHNAKILLY 33-T132 | 33 | 24 | 24 | Scheduled | 08/04/2024 | 10/05/2024
TO-24-CBT-MAY-1-02 | 220kV FEEDER - CASTLEBAGOT 220-MAYNOOTH 220-1 | 4 | 4 | 4 | Scheduled | 09/04/2024 | 12/04/2024
TO-24-INC-MAY-2-01 | 220kV FEEDER - INCHICORE 220-MAYNOOTH 220-2 | 4 | 4 | 4 | Scheduled | 09/04/2024 | 12/04/2024
TO-24-LLA-T133-01 | GENERATOR TRANSFORMER - LENALEA 110-LENALEA 33-T133 | 1 | 1 | 1 | Scheduled | 09/04/2024 | 09/04/2024
TO-24-BAL-CDU-1-05 | 110kV FEEDER - BALTRASNA 110-CORDUFF 110-1 | 9 | 7 |  | Scheduled | 11/04/2024 | 19/04/2024
TO-24-CDU-110SA2-4-01 | SECTIONALISING DISCONNECT - CORDUFF 110-CORDUFF 110-110SA2-4 | 9 | 7 |  | Scheduled | 11/04/2024 | 19/04/2024
TO-24-CDU-110SB2-4-01 | SECTIONALISING DISCONNECT - CORDUFF 110-CORDUFF 110-110SB2-4 | 9 | 7 |  | Scheduled | 11/04/2024 | 19/04/2024
TO-24-CDU-MCE-1-02 | 110kV FEEDER - CORDUFF 110-MACETOWN 110-1 | 9 | 7 |  | Scheduled | 11/04/2024 | 19/04/2024
TO-24-CDU-T102-01 | GENERATOR TRANSFORMER - CORDUFF 110-CORDUFF 10.5-T102 | 9 | 7 |  | Scheduled | 11/04/2024 | 19/04/2024
TO-24-110 kV A2 @ FIN GIS-02 | BUSBAR SECTION - FINGLAS GIS 110-FINGLAS GIS 110-110A2 | 7 | 5 | 5 | Scheduled | 11/04/2024 | 17/04/2024
TO-24-110 kV B2 @ FIN GIS-02 | BUSBAR SECTION - FINGLAS GIS 110-FINGLAS GIS 110-110B2 | 7 | 5 | 5 | Scheduled | 11/04/2024 | 17/04/2024
TO-24-GOR-220K1-2-01 | COUPLER/SECTIONALISING CB - GORMAN 220-GORMAN 220-220K1-2 | 1 | 1 | 1 | Scheduled | 12/04/2024 | 12/04/2024
TO-24-CDU-WOO-1-03 | 220kV FEEDER - CORDUFF 220-WOODLAND 220-1 | 7 | 5 | 5 | Scheduled | 13/04/2024 | 19/04/2024
TO-24-BGT-110K1-01 | COUPLER/SECTIONALISING CB - BALLYRAGGET 110-BALLYRAGGET 110-110K1 | 3 | 3 | 3 | Scheduled | 15/04/2024 | 17/04/2024
TO-24-BGT-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - BALLYRAGGET 110-BALLYRAGGET 110-110SA1-2CB | 3 | 3 | 3 | Scheduled | 15/04/2024 | 17/04/2024
TO-24-BGT-110SB1-2CB-01 | COUPLER/SECTIONALISING CB - BALLYRAGGET 110-BALLYRAGGET 110-110SB1-2CB | 3 | 3 | 3 | Scheduled | 15/04/2024 | 17/04/2024
TO-24-BGT-KKY-1-01 | 110kV FEEDER - BALLYRAGGET 110-KILKENNY 110-1 | 3 | 3 | 3 | Scheduled | 15/04/2024 | 17/04/2024
TO-24-BGT-141-01 | DISTRIBUTION TRANSFORMER - BALLYRAGGET 110-BALLYRAGGET 38-T141 | 3 | 3 | 3 | Reference | 15/04/2024 | 17/04/2024
TO-24-BGH-T132-02 | GENERATOR TRANSFORMER - BOGGERAGH 110-BOGGERAGH 33-T132 | 2 | 2 | 2 | Scheduled | 15/04/2024 | 16/04/2024
TO-24-220 kV B2 @ CKM GIS-01 | BUSBAR SECTION - CARRICKMINES GIS 220-CARRICKMINES GIS 220-220B2 | 9 | 7 | 7 | Scheduled | 15/04/2024 | 23/04/2024
TO-24-220 kV B4 @ CKM GIS-02 | BUSBAR SECTION - CARRICKMINES GIS 220-CARRICKMINES GIS 220-220B4 | 9 | 7 | 7 | Scheduled | 15/04/2024 | 23/04/2024
TO-24-CKM GIS-220SB2-4CB-02 | COUPLER/SECTIONALISING CB - CARRICKMINES GIS 220-CARRICKMINES GIS 220-22SB2-4CB | 9 | 7 | 7 | Scheduled | 15/04/2024 | 23/04/2024
TO-24-CTN-TIP-1-01 | 110kV FEEDER - CAUTEEN 110-TIPPERARY 110-1 | 5 | 5 | 5 | Scheduled | 15/04/2024 | 19/04/2024
TO-24-CRO-110SA1-02 | SECTIONALISING DISCONNECT - COOLROE 110-COOLROE 110-110SA1 | 5 | 5 | 5 | Scheduled | 15/04/2024 | 19/04/2024
TO-24-CRO-110SA2-01 | SECTIONALISING DISCONNECT - COOLROE 110-COOLROE 110-110SA2 | 5 | 5 | 5 | Scheduled | 15/04/2024 | 19/04/2024
TO-24-CRO-IA-1-01 | 110kV FEEDER - COOLROE 110-INNISCARRA 110-1 | 5 | 5 | 5 | Scheduled | 15/04/2024 | 19/04/2024
TO-24-CRO-T122-01 | DISTRIBUTION TRANSFORMER - COOLROE 110-COOLROE 20-T122 | 5 | 5 | 5 | Reference | 15/04/2024 | 19/04/2024
TO-24-CDU-220SA2-4-01 | SECTIONALISING DISCONNECT - CORDUFF 220-CORDUFF 220-220SA2-4 | 5 | 5 | 5 | Scheduled | 15/04/2024 | 19/04/2024
TO-24-CDU-220SB2-4-01 | SECTIONALISING DISCONNECT - CORDUFF 220-CORDUFF 220-220SB2-4 | 5 | 5 | 5 | Scheduled | 15/04/2024 | 19/04/2024
TO-24-COR-PST-03 | TRANSFORMER - CORRACLASSY 110-ENNISKILLEN 110-PST | 19 | 15 | 15 | Scheduled | 15/04/2024 | 03/05/2024
TO-24-KLN-SH-1-02 | 220kV FEEDER - KILLONAN 220-SHANNONBRIDGE 220-1 | 2 | 2 |  | Scheduled | 15/04/2024 | 16/04/2024
TO-24-KPG-T2101-01 | TRANSFORMER - KILPADDOGE 220-KILPADDOGE 110-T2101 | 5 | 5 | 5 | Scheduled | 15/04/2024 | 19/04/2024
TO-24-PRN-T4301-01 | TRANSFORMER - PORTAN 400-PORTAN 260-T4301 | 1 | 1 | 1 | Scheduled | 15/04/2024 | 15/04/2024
TO-24-PRN-WOO-1-04 | 400kV FEEDER - PORTAN 400-WOODLAND 400-1 | 1 | 1 | 1 | Scheduled | 15/04/2024 | 15/04/2024
TO-24-400 kV A1 @ WOO-01 | BUSBAR SECTION - WOODLAND 400-WOODLAND 400-400A1 | 1 | 1 | 1 | Scheduled | 15/04/2024 | 15/04/2024
TO-24-MP GIS-220K1-01 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 220-MONEYPOINT GIS 220-220K1 | 1 | 1 | 1 | Scheduled | 16/04/2024 | 16/04/2024
TO-24-PRN-WOO-1-01 | 400kV FEEDER - PORTAN 400-WOODLAND 400-1 | 4 | 4 | 4 | Scheduled | 16/04/2024 | 19/04/2024
TO-24-MP GIS-220K2-01 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 220-MONEYPOINT GIS 220-220K2 | 1 | 1 | 1 | Scheduled | 17/04/2024 | 17/04/2024
TO-24-SH-220K1-2-02 | COUPLER/SECTIONALISING CB - SHANNONBRIDGE 220-SHANNONBRIDGE 220-220K1-2 | 2 | 2 |  | Scheduled | 17/04/2024 | 18/04/2024
TO-24-AA GIS-T104-04 | GENERATOR TRANSFORMER - ARDNACRUSHA GIS 110-ARDNACRUSHA GIS G4-T104 | 1 | 1 | 1 | Scheduled | 18/04/2024 | 18/04/2024
TO-24-MP GIS-220SA1-2CB-01 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 220-MONEYPOINT GIS 220-220SA1-2CB | 1 | 1 | 1 | Scheduled | 18/04/2024 | 18/04/2024
TO-24-MP GIS-220SB1-2CB-01 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 220-MONEYPOINT GIS 220-220SB1-2CB | 1 | 1 | 1 | Scheduled | 19/04/2024 | 19/04/2024
TO-24-SH-110K1-2-02 | COUPLER/SECTIONALISING CB - SHANNONBRIDGE 110-SHANNONBRIDGE 110-110K1-2 | 4 | 2 | 2 | Scheduled | 19/04/2024 | 22/04/2024
TO-24-TB-T2102-03 | TRANSFORMER - TARBERT 220-TARBERT 110-T2102 | 3 | 1 | 1 | Scheduled | 19/04/2024 | 21/04/2024
TO-24-AD-ST101-01 | GENERATOR TRANSFORMER - AGHADA 110-AGHADA 10-ST101 | 10 | 8 | 8 | Scheduled | 22/04/2024 | 01/05/2024
TO-24-AD-WHI-1-03 | 110kV FEEDER - AGHADA 110-WHITEGATE 110-1 | 5 | 5 | 5 | Scheduled | 22/04/2024 | 26/04/2024
TO-24-BIN-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - BINBANE 110-BINBANE 110-110SA1-2CB | 3 | 3 | 3 | Scheduled | 22/04/2024 | 24/04/2024
TO-24-BIN-CF-1-01 | 110kV FEEDER - BINBANE 110-CATHALEENS FALL 110-1 | 180 | 127 | 127 | Scheduled | 22/04/2024 | 18/10/2024
TO-24-BIN-T142-02 | DISTRIBUTION TRANSFORMER - BINBANE 110-BINBANE 38-T142 | 3 | 3 | 3 | Reference | 22/04/2024 | 24/04/2024
TO-24-COS-FLA-1-03 | 110kV FEEDER - CARRICK ON SHANNON 110-FLAGFORD 110-1 | 58 | 40 |  | Scheduled | 22/04/2024 | 18/06/2024
TO-24-CD-KBY-1-01 | 110kV FEEDER - CARRIGADROHID 110-KILBARRY 110-1 | 12 | 10 | 10 | Scheduled | 22/04/2024 | 03/05/2024
TO-24-110 kV A2 @ CF-01 | BUSBAR SECTION - CATHALEENS FALL 110-CATHALEENS FALL 110-110A2 | 100 | 70 | 70 | Scheduled | 22/04/2024 | 30/07/2024
TO-24-110 kV A2 @ CLO-02 | BUSBAR SECTION - CLOGHER 110-CLOGHER 110-110A2 | 8 | 6 | 6 | Scheduled | 22/04/2024 | 29/04/2024
TO-24-110 kV B2 @ CLO-02 | BUSBAR SECTION - CLOGHER 110-CLOGHER 110-110B2 | 8 | 6 | 6 | Scheduled | 22/04/2024 | 29/04/2024
TO-24-CLO-MRY-1-01 | 110kV FEEDER - CLOGHER 110-MULREAVY 110-1 | 8 | 6 | 6 | Scheduled | 22/04/2024 | 29/04/2024
TO-24-220 kV A2 @ CRU-01 | BUSBAR SECTION - CRUISERATH 220-CRUISERATH 220-220A2 | 9 | 7 | 7 | Scheduled | 22/04/2024 | 30/04/2024
TO-24-220 kV B2 @ CRU-01 | BUSBAR SECTION - CRUISERATH 220-CRUISERATH 220-220B2 | 9 | 7 | 7 | Scheduled | 22/04/2024 | 30/04/2024
TO-24-CRU-220K2-01 | COUPLER/SECTIONALISING CB - CRUISERATH 220-CRUISERATH 220-220K2 | 9 | 7 | 7 | Scheduled | 22/04/2024 | 30/04/2024
TO-24-CRU-SA1-2CB-01 | COUPLER/SECTIONALISING CB - CRUISERATH 220-CRUISERATH 220-220SA1-2CB | 9 | 7 | 7 | Scheduled | 22/04/2024 | 30/04/2024
TO-24-CRU-SB1-2CB-01 | COUPLER/SECTIONALISING CB - CRUISERATH 220-CRUISERATH 220-220SB1-2CB | 9 | 7 | 7 | Scheduled | 22/04/2024 | 30/04/2024
TO-24-110 kV A1 @ FLA-04 | BUSBAR SECTION - FLAGFORD 110-FLAGFORD 110-110A1 | 54 | 38 | 38 | Scheduled | 22/04/2024 | 14/06/2024
TO-24-110 kV B1 @ FLA-05 | BUSBAR SECTION - FLAGFORD 110-FLAGFORD 110-110B1 | 54 | 38 | 38 | Scheduled | 22/04/2024 | 14/06/2024
TO-24-KTN-WAT-1-01 | 110kV FEEDER - KILLOTERAN 110-WATERFORD 110-1 | 5 | 5 | 5 | Scheduled | 22/04/2024 | 26/04/2024
TO-24-LIM-RAT-1-01 | 110kV FEEDER - LIMERICK 110-RATHKEALE 110-1 | 5 | 5 | 5 | Scheduled | 22/04/2024 | 26/04/2024
TO-24-MRY-T131-01 | GENERATOR TRANSFORMER - MULREAVY 110-MULREAVY 33-T131 | 8 | 6 | 6 | Scheduled | 22/04/2024 | 29/04/2024
TO-24-UGL-T132-03 | GENERATOR TRANSFORMER - UGGOOL 110-UGGOOL 33-T132 | 5 | 5 | 5 | Scheduled | 22/04/2024 | 26/04/2024
TO-24-UGL-T134-02 | GENERATOR TRANSFORMER - UGGOOL 110-UGGOOL 33-T134 | 5 | 5 | 5 | Scheduled | 22/04/2024 | 26/04/2024
TO-24-WOO-T4201-03 | TRANSFORMER - WOODLAND 400-WOODLAND 220-T4201 | 5 | 5 | 5 | Scheduled | 22/04/2024 | 26/04/2024
TO-24-110 kV A1 @ ARV-01 | BUSBAR SECTION - ARVA 110-ARVA 110-110A1 | 1 | 1 | 1 | Scheduled | 23/04/2024 | 23/04/2024
TO-24-ARV-NAV-1-01 | 110kV FEEDER - ARVA 110-NAVAN 110-1 | 1 | 1 | 1 | Scheduled | 23/04/2024 | 23/04/2024
TO-24-BUF-T131-02 | GENERATOR TRANSFORMER - BUFFY 110-BUFFY 33-T131 | 1 | 1 | 1 | Scheduled | 23/04/2024 | 23/04/2024
TO-24-CGL-GAE-1-05 | 110kV FEEDER - COOMAGEARLAHY 110-GLANLEE 110-1 | 2 | 2 | 2 | Scheduled | 23/04/2024 | 24/04/2024
TO-24-GAE-T121-02 | GENERATOR TRANSFORMER - GLANLEE 110-GLANLEE 20-T121 | 2 | 2 | 2 | Scheduled | 23/04/2024 | 24/04/2024
TO-24-KPG-220SB1-3CB-01 | COUPLER/SECTIONALISING CB - KILPADDOGE 220-KILPADDOGE 220-220SB1-3CB | 2 | 2 | 2 | Scheduled | 23/04/2024 | 24/04/2024
TO-24-SH-T2101-03 | TRANSFORMER - SHANNONBRIDGE 220-SHANNONBRIDGE 110-T2101 | 2 | 2 |  | Scheduled | 23/04/2024 | 24/04/2024
TO-24-110 kV A1 @ LOU-01 | BUSBAR SECTION - LOUTH 110-LOUTH 110-110A1 | 160 | 111 | 111 | Scheduled | 24/04/2024 | 30/09/2024
TO-24-110 kV B1 @ LOU-01 | BUSBAR SECTION - LOUTH 110-LOUTH 110-110B1 | 160 | 111 | 111 | Scheduled | 24/04/2024 | 30/09/2024
TO-24-LOU-RRU-1-01 | 110kV FEEDER - LOUTH 110-RATRUSSAN 110-1 | 156 | 109 | 109 | Scheduled | 24/04/2024 | 26/09/2024
TO-24-RRU-110SA1-03 | SECTIONALISING DISCONNECT - RATRUSSAN 110-RATRUSSAN 110-110SA1 | 29 | 20 |  | Scheduled | 24/04/2024 | 22/05/2024
TO-24-RRU-110SA2-03 | SECTIONALISING DISCONNECT - RATRUSSAN 110-RATRUSSAN 110-110SA2 | 29 | 20 |  | Scheduled | 24/04/2024 | 22/05/2024
TO-24-RRU-SKL-1-03 | 110kV FEEDER - RATRUSSAN 110-SHANKILL 110-1 | 29 | 20 |  | Scheduled | 24/04/2024 | 22/05/2024
TO-24-RRU-T121-03 | GENERATOR TRANSFORMER - RATRUSSAN 110-RATRUSSAN 20-T121 | 29 | 20 |  | Scheduled | 24/04/2024 | 22/05/2024
TO-24-RRU-T122-01 | GENERATOR TRANSFORMER - RATRUSSAN 110-RATRUSSAN 20-T122 | 29 | 20 |  | Scheduled | 24/04/2024 | 22/05/2024
TO-24-AGL-SH-1-02 | 110kV FEEDER - AGANNYGAL 110-SHANNONBRIDGE 110-1 | 2 | 2 |  | Scheduled | 25/04/2024 | 26/04/2024
TO-24-110 kV A3 @ AA GIS-01 | BUSBAR SECTION - ARDNACRUSHA GIS 110-ARDNACRUSHA GIS 110-110A3 | 1 | 1 | 1 | Scheduled | 25/04/2024 | 25/04/2024
TO-24-AA GIS-T104-02 | GENERATOR TRANSFORMER - ARDNACRUSHA GIS 110-ARDNACRUSHA GIS G4-T104 | 1 | 1 | 1 | Scheduled | 25/04/2024 | 25/04/2024
TO-24-BYH-STATCOM-02 | CAPACITOR/SVC/REACTOR - BALLYNAHULLA 110-BALLYNAHULLA 110-STATCOM | 1 | 1 | 1 | Scheduled | 25/04/2024 | 25/04/2024
TO-24-LOU-T2104-02 | TRANSFORMER - LOUTH 220-LOUTH 110-T2104 | 1 | 1 | 1 | Scheduled | 25/04/2024 | 25/04/2024
TO-24-110 kV A2 @ SH-03 | BUSBAR SECTION - SHANNONBRIDGE 110-SHANNONBRIDGE 110-110A2 | 14 | 9 | 9 | Scheduled | 26/04/2024 | 09/05/2024
TO-24-110 kV B2 @ SH-03 | BUSBAR SECTION - SHANNONBRIDGE 110-SHANNONBRIDGE 110-110B2 | 14 | 9 | 9 | Scheduled | 26/04/2024 | 09/05/2024
TO-24-220 kV A1 @ FIN-02 | BUSBAR SECTION - FINGLAS 220-FINGLAS 220-220A1 | 12 | 7 | 7 | Scheduled | 27/04/2024 | 08/05/2024
TO-24-220 kV B1 @ FIN-02 | BUSBAR SECTION - FINGLAS 220-FINGLAS 220-220B1 | 12 | 7 | 7 | Scheduled | 27/04/2024 | 08/05/2024
TO-24-FIN-220K1-03 | COUPLER/SECTIONALISING CB - FINGLAS 220-FINGLAS 220-220K1 | 12 | 7 | 7 | Scheduled | 27/04/2024 | 08/05/2024
TO-24-FIN-220SA1-2CB-02 | COUPLER/SECTIONALISING CB - FINGLAS 220-FINGLAS 220-220SA1-2CB | 12 | 7 | 7 | Scheduled | 27/04/2024 | 08/05/2024
TO-24-FIN-220SB1-2CB-03 | COUPLER/SECTIONALISING CB - FINGLAS 220-FINGLAS 220-220SB1-2CB | 12 | 7 | 7 | Scheduled | 27/04/2024 | 08/05/2024
TO-24-FIN-HN-1-01 | 220kV FEEDER - FINGLAS 220-HUNTSTOWN 220-1 | 12 | 7 | 7 | Scheduled | 27/04/2024 | 08/05/2024
TO-24-HN-T2010/11-01 | GENERATOR TRANSFORMER - HUNTSTOWN 220-HUNTSTOWN G10/11-T2010/11 | 12 | 7 | 7 | Scheduled | 27/04/2024 | 08/05/2024
TO-24-110 kV A3 @ AA GIS-02 | BUSBAR SECTION - ARDNACRUSHA GIS 110-ARDNACRUSHA GIS 110-110A3 | 5 | 5 | 5 | Scheduled | 29/04/2024 | 03/05/2024
TO-24-110 kV B3 @ AA GIS-01 | BUSBAR SECTION - ARDNACRUSHA GIS 110-ARDNACRUSHA GIS 110-110B3 | 5 | 5 | 5 | Scheduled | 29/04/2024 | 03/05/2024
TO-23-AA GIS-110K3-01 | COUPLER/SECTIONALISING CB - ARDNACRUSHA GIS 110-ARDNACRUSHA GIS 110-110K3 | 5 | 5 | 5 | Scheduled | 29/04/2024 | 03/05/2024
TO-24-AA GIS-110SA1-3CB-01 | COUPLER/SECTIONALISING CB - ARDNACRUSHA GIS 110-ARDNACRUSHA GIS 110-110SA1-3CB | 5 | 5 | 5 | Scheduled | 29/04/2024 | 03/05/2024
TO-24-AA GIS-110SB1-3CB-01 | COUPLER/SECTIONALISING CB - ARDNACRUSHA GIS 110-ARDNACRUSHA GIS 110-110SB1-3CB | 5 | 5 | 5 | Scheduled | 29/04/2024 | 03/05/2024
TO-24-AA GIS-CAP1-01 | CAPACITOR/SVC/REACTOR - ARDNACRUSHA GIS 110-ARDNACRUSHA GIS 110-CAP1 | 5 | 5 | 5 | Scheduled | 29/04/2024 | 03/05/2024
TO-24-ARK-T2102-01 | TRANSFORMER - ARKLOW 220-ARKLOW 110-T2102 | 5 | 5 | 5 | Scheduled | 29/04/2024 | 03/05/2024
TO-24-MCE-T124-03 | TSO CUSTOMER TRANSFORMER - MACETOWN 110-MACETOWN 20-T124 | 3 | 3 | 3 | Scheduled | 29/04/2024 | 01/05/2024
TO-24-110 kV A2 @ RAF-02 | BUSBAR SECTION - RAFFEEN 110-RAFFEEN 110-110A2 | 215 | 151 | 151 | Scheduled | 29/04/2024 | 29/11/2024
TO-24-110 kV B2 @ RAF-02 | BUSBAR SECTION - RAFFEEN 110-RAFFEEN 110-110B2 | 215 | 151 | 151 | Scheduled | 29/04/2024 | 29/11/2024
TO-24-ATH-LA-1-02 | 110kV FEEDER - ATHLONE 110-LANESBORO 110-1 | 18 | 13 | 13 | Scheduled | 30/04/2024 | 17/05/2024
TO-24-CHA-GLE-1-01 | 110kV FEEDER - CHARLEVILLE 110-GLENLARA 110-1 | 3 | 3 | 3 | Scheduled | 30/04/2024 | 02/05/2024
TO-24-CRO-IA-1-04 | 110kV FEEDER - COOLROE 110-INNISCARRA 110-1 | 1 | 1 | 1 | Scheduled | 30/04/2024 | 30/04/2024
TO-24-110 kV A1 @ IA-02 | BUSBAR SECTION - INNISCARRA 110-INNISCARRA 110-110A1 | 1 | 1 | 1 | Scheduled | 30/04/2024 | 30/04/2024
TO-24-IA-MAC-1-04 | 110kV FEEDER - INNISCARRA 110-MACROOM 110-1 | 1 | 1 | 1 | Scheduled | 30/04/2024 | 30/04/2024
TO-24-IA-T101-04 | GENERATOR TRANSFORMER - INNISCARRA 110-INNISCARRA G1-T101 | 1 | 1 | 1 | Scheduled | 30/04/2024 | 30/04/2024
TO-24-AA GIS-T101-01 | GENERATOR TRANSFORMER - ARDNACRUSHA GIS 110-ARDNACRUSHA GIS G1-T101 | 171 | 120 | 120 | Scheduled | 01/05/2024 | 18/10/2024
TO-24-MAY-TSB-1-02 | 110kV FEEDER - MAYNOOTH 110-THORNSBERRY 110-1 | 120 | 83 | 83 | Scheduled | 02/05/2024 | 29/08/2024
TO-24-110 kV A2 @ AA GIS-01 | BUSBAR SECTION - ARDNACRUSHA GIS 110-ARDNACRUSHA GIS 110-110A2 | 10 | 8 | 8 | Scheduled | 07/05/2024 | 16/05/2024
TO-24-110 kV B2 @ AA GIS-01 | BUSBAR SECTION - ARDNACRUSHA GIS 110-ARDNACRUSHA GIS 110-110B2 | 10 | 8 | 8 | Scheduled | 07/05/2024 | 16/05/2024
TO-24-AA GIS-110K2-01 | COUPLER/SECTIONALISING CB - ARDNACRUSHA GIS 110-ARDNACRUSHA GIS 110-110K2 | 10 | 8 | 8 | Scheduled | 07/05/2024 | 16/05/2024
TO-24-AA GIS-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - ARDNACRUSHA GIS 110-ARDNACRUSHA GIS 110-110SA1-2CB | 10 | 8 | 8 | Scheduled | 07/05/2024 | 16/05/2024
TO-24-AA GIS-110SB1-2CB-01 | COUPLER/SECTIONALISING CB - ARDNACRUSHA GIS 110-ARDNACRUSHA GIS 110-110SB1-2CB | 10 | 8 | 8 | Scheduled | 07/05/2024 | 16/05/2024
TO-24-AA GIS-ENN-1-04 | 110kV FEEDER - ARDNACRUSHA GIS 110-ENNIS 110-1 | 10 | 8 | 8 | Scheduled | 07/05/2024 | 16/05/2024
TO-24-BUT-CUL-1-01 | 110kV FEEDER - BUTLERSTOWN 110-CULLENAGH 110-1 | 3 | 3 | 3 | Scheduled | 07/05/2024 | 09/05/2024
TO-24-CBR-CAP2-01 | CAPACITOR/SVC/REACTOR - CASTLEBAR 110-CASTLEBAR 110-CAP2 | 4 | 4 | 4 | Scheduled | 07/05/2024 | 10/05/2024
TO-24-INC-MAY-2-02 | 220kV FEEDER - INCHICORE 220-MAYNOOTH 220-2 | 9 | 7 |  | Scheduled | 07/05/2024 | 15/05/2024
TO-24-KTL-T131-01 | GENERATOR TRANSFORMER - KILTEEL 110-KILTEEL 33-T131 | 1 | 1 | 1 | Scheduled | 07/05/2024 | 07/05/2024
TO-24-MEE-T121-01 | GENERATOR TRANSFORMER - MEENTYCAT 110-MEENTYCAT 20-T121 | 3 | 3 | 3 | Scheduled | 07/05/2024 | 09/05/2024
TO-24-AD-220K1-02 | COUPLER/SECTIONALISING CB - AGHADA 220-AGHADA 220-220K1 | 1 | 1 | 1 | Scheduled | 08/05/2024 | 08/05/2024
TO-24-CSH-GAL GIS-2-02 | 110kV FEEDER - CASHLA 110-GALWAY GIS 110-2 | 1 | 1 | 1 | Scheduled | 08/05/2024 | 08/05/2024
TO-24-GOR-LOU-1-01 | 220kV FEEDER - GORMAN 220-LOUTH 220-1 | 1 | 1 |  | Scheduled | 08/05/2024 | 08/05/2024
TO-24-LIS-T131-01 | GENERATOR TRANSFORMER - LISDRUM 110-LISDRUM 33-T131 | 1 | 1 | 1 | Scheduled | 08/05/2024 | 08/05/2024
TO-24-ROP-110K1-01 | COUPLER/SECTIONALISING CB - ROSSPILE 110-ROSSPILE 110-110K1 | 1 | 1 | 1 | Scheduled | 08/05/2024 | 08/05/2024
TO-24-AA GIS-T104-01 | GENERATOR TRANSFORMER - ARDNACRUSHA GIS 110-ARDNACRUSHA GIS G4-T104 | 14 | 10 | 10 | Scheduled | 09/05/2024 | 22/05/2024
TO-24-ARK-T101-01 | DISTRIBUTION TRANSFORMER - ARKLOW 110-ARKLOW 10-T101 | 2 | 2 | 2 | Reference | 09/05/2024 | 10/05/2024
TO-24-BLC-110SA1-3CB-01 | COUPLER/SECTIONALISING CB - BELCAMP 110-BELCAMP 110-110SA1-3CB | 1 | 1 | 1 | Scheduled | 09/05/2024 | 09/05/2024
TO-24-110 kV A2 @ CSH-04 | BUSBAR SECTION - CASHLA 110-CASHLA 110-110A2 | 72 | 51 | 51 | Scheduled | 09/05/2024 | 19/07/2024
TO-24-110 kV B2 @ CSH-04 | BUSBAR SECTION - CASHLA 110-CASHLA 110-110B2 | 72 | 51 | 51 | Scheduled | 09/05/2024 | 19/07/2024
TO-24-220 kV B2 @ CSH-01 | BUSBAR SECTION - CASHLA 220-CASHLA 220-220B2 | 72 | 51 | 51 | Scheduled | 09/05/2024 | 19/07/2024
TO-24-CSH-220K2-4-03 | COUPLER/SECTIONALISING CB - CASHLA 220-CASHLA 220-220K2-4 | 72 | 51 | 51 | Scheduled | 09/05/2024 | 19/07/2024
TO-24-CSH-T2102-01 | TRANSFORMER - CASHLA 220-CASHLA 110-T2102 | 72 | 51 | 51 | Scheduled | 09/05/2024 | 19/07/2024
TO-24-WOH-T122-01 | GENERATOR TRANSFORMER - WOODHOUSE 110-WOODHOUSE 20-T122 | 2 | 2 | 2 | Scheduled | 09/05/2024 | 10/05/2024
TO-24-BLC-110SB1-3CB-01 | COUPLER/SECTIONALISING CB - BELCAMP 110-BELCAMP 110-110SB1-3CB | 1 | 1 | 1 | Scheduled | 10/05/2024 | 10/05/2024
TO-24-BAL-DRY-1-05 | 110kV FEEDER - BALTRASNA 110-DRYBRIDGE 110-1 | 197 | 138 | 138 | Scheduled | 13/05/2024 | 25/11/2024
TO-24-110 kV A1 @ CSH-06 | BUSBAR SECTION - CASHLA 110-CASHLA 110-110A1 | 6 | 5 | 5 | Scheduled | 13/05/2024 | 18/05/2024
TO-24-110 kV B1 @ CSH-03 | BUSBAR SECTION - CASHLA 110-CASHLA 110-110B1 | 6 | 5 | 5 | Scheduled | 13/05/2024 | 18/05/2024
TO-24-CLH-110SA2-01 | SECTIONALISING DISCONNECT - CLAHANE 110-CLAHANE 110-110SA2 | 3 | 3 | 3 | Scheduled | 13/05/2024 | 15/05/2024
TO-24-CLH-T122-01 | GENERATOR TRANSFORMER - CLAHANE 110-CLAHANE 20-T122 | 5 | 5 | 5 | Scheduled | 13/05/2024 | 17/05/2024
TO-24-CLH-TRI-1-01 | 110kV FEEDER - CLAHANE 110-TRIEN 110-1 | 3 | 3 | 3 | Scheduled | 13/05/2024 | 15/05/2024
TO-24-CL-T102-03 | GENERATOR TRANSFORMER - CLIFF 110-CLIFF G2-T102 | 11 | 9 |  | Scheduled | 13/05/2024 | 23/05/2024
TO-24-400 kV A1 @ DSN-02 | BUSBAR SECTION - DUNSTOWN 400-DUNSTOWN 400-400A1 | 12 | 10 | 10 | Scheduled | 13/05/2024 | 24/05/2024
TO-24-400 kV A2 @ DSN-01 | BUSBAR SECTION - DUNSTOWN 400-DUNSTOWN 400-400A2 | 12 | 10 | 10 | Scheduled | 13/05/2024 | 24/05/2024
TO-24-400 kV B1 @ DSN-02 | BUSBAR SECTION - DUNSTOWN 400-DUNSTOWN 400-400B1 | 12 | 10 | 10 | Scheduled | 13/05/2024 | 24/05/2024
TO-24-400 kV B2 @ DSN-01 | BUSBAR SECTION - DUNSTOWN 400-DUNSTOWN 400-400B2 | 12 | 10 | 10 | Scheduled | 13/05/2024 | 24/05/2024
TO-24-DSN-400K1-2-01 | COUPLER/SECTIONALISING CB - DUNSTOWN 400-DUNSTOWN 400-400K1-2 | 12 | 10 | 10 | Scheduled | 13/05/2024 | 24/05/2024
TO-24-GI-WAT-1-04 | 110kV FEEDER - GREAT ISLAND 110-WATERFORD 110-1 | 5 | 5 | 5 | Scheduled | 13/05/2024 | 17/05/2024
TO-24-KLS-220K1-2-01 | COUPLER/SECTIONALISING CB - KELLIS 220-KELLIS 220-220K1-2 | 57 | 40 | 40 | Scheduled | 13/05/2024 | 08/07/2024
TO-24-110 kV A2 @ LOU-01 | BUSBAR SECTION - LOUTH 110-LOUTH 110-110A2 | 5 | 5 | 5 | Scheduled | 13/05/2024 | 17/05/2024
TO-24-110 kV B2 @ LOU-01 | BUSBAR SECTION - LOUTH 110-LOUTH 110-110B2 | 5 | 5 | 5 | Scheduled | 13/05/2024 | 17/05/2024
TO-24-LOU-MTH-1-01 | 110kV FEEDER - LOUTH 110-MEATH HILL 110-1 | 9 | 7 | 7 | Scheduled | 13/05/2024 | 21/05/2024
TO-24-400 kV A1 @ MP GIS-02 | BUSBAR SECTION - MONEYPOINT GIS 400-MONEYPOINT GIS 400-400A1 | 12 | 10 | 10 | Scheduled | 13/05/2024 | 24/05/2024
TO-24-400 kV B1 @ MP GIS-04 | BUSBAR SECTION - MONEYPOINT GIS 400-MONEYPOINT GIS 400-400B1 | 12 | 10 | 10 | Scheduled | 13/05/2024 | 24/05/2024
TO-24-MP GIS-400SA1-2CB-02 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 400-MONEYPOINT GIS 400-400SA1-2CB | 12 | 10 | 10 | Scheduled | 13/05/2024 | 24/05/2024
TO-24-MP GIS-400SB1-2CB-03 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 400-MONEYPOINT GIS 400-400SB1-2CB | 12 | 10 | 10 | Scheduled | 13/05/2024 | 24/05/2024
TO-24-MP GIS-400SB1-3CB-02 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 400-MONEYPOINT GIS 400-400SB1-3CB | 12 | 10 | 10 | Scheduled | 13/05/2024 | 24/05/2024
TO-24-RAF-110K1-2-01 | COUPLER/SECTIONALISING CB - RAFFEEN 110-RAFFEEN 110-110K1-2 | 3 | 3 | 3 | Scheduled | 13/05/2024 | 15/05/2024
TO-24-CRO-IA-1-02 | 110kV FEEDER - COOLROE 110-INNISCARRA 110-1 | 7 | 5 | 5 | Scheduled | 14/05/2024 | 20/05/2024
TO-24-CRA-LWD-1-06 | 110kV FEEDER - CRANE 110-LODGEWOOD 110-1 | 4 | 4 | 4 | Scheduled | 14/05/2024 | 17/05/2024
TO-24-IA-MAC-1-01 | 110kV FEEDER - INNISCARRA 110-MACROOM 110-1 | 7 | 5 | 5 | Scheduled | 14/05/2024 | 20/05/2024
TO-24-IA-T101-01 | GENERATOR TRANSFORMER - INNISCARRA 110-INNISCARRA G1-T101 | 10 | 8 | 8 | Scheduled | 14/05/2024 | 23/05/2024
TO-24-MOY-CAP2-01 | CAPACITOR/SVC/REACTOR - MOY 110-MOY 110-CAP2 | 2 | 2 | 2 | Scheduled | 14/05/2024 | 15/05/2024
TO-24-LOU-MLN-1-01 | 110kV FEEDER - LOUTH 110-MULLAGHARLIN 110-1 | 146 | 102 | 102 | Scheduled | 15/05/2024 | 07/10/2024
TO-24-220 kV A2 @ CRU-03 | BUSBAR SECTION - CRUISERATH 220-CRUISERATH 220-220A2 | 2 | 2 | 2 | Scheduled | 16/05/2024 | 17/05/2024
TO-24-220 kV B2 @ CRU-03 | BUSBAR SECTION - CRUISERATH 220-CRUISERATH 220-220B2 | 2 | 2 | 2 | Scheduled | 16/05/2024 | 17/05/2024
TO-24-CRU-220K2-05 | COUPLER/SECTIONALISING CB - CRUISERATH 220-CRUISERATH 220-220K2 | 2 | 2 | 2 | Scheduled | 16/05/2024 | 17/05/2024
TO-24-CRU-SA1-2CB-05 | COUPLER/SECTIONALISING CB - CRUISERATH 220-CRUISERATH 220-220SA1-2CB | 2 | 2 | 2 | Scheduled | 16/05/2024 | 17/05/2024
TO-24-CRU-SB1-2CB-05 | COUPLER/SECTIONALISING CB - CRUISERATH 220-CRUISERATH 220-220SB1-2CB | 2 | 2 | 2 | Scheduled | 16/05/2024 | 17/05/2024
TO-24-SLC-T122-03 | GENERATOR TRANSFORMER - SLIEVECALLAN 110-SLIEVECALLAN 20-T122 | 1 | 1 | 1 | Scheduled | 16/05/2024 | 16/05/2024
TO-24-BVK-T2101-01 | TRANSFORMER - BALLYVOUSKILL 220-BALLYVOUSKILL 110-T2101 | 15 | 11 |  | Scheduled | 17/05/2024 | 31/05/2024
TO-24-CLE-WOO-1-01 | 220kV FEEDER - CLONEE 220-WOODLAND 220-1 | 141 | 99 | 99 | Scheduled | 17/05/2024 | 04/10/2024
TO-24-KYT-WOO-1-01 | 220kV FEEDER - KELLYSTOWN 220-WOODLAND 220-1 | 141 | 99 | 99 | Scheduled | 17/05/2024 | 04/10/2024
TO-24-110 kV A1 @ CSH-05 | BUSBAR SECTION - CASHLA 110-CASHLA 110-110A1 | 3 | 3 | 3 | Scheduled | 20/05/2024 | 22/05/2024
TO-24-CSH-GAL GIS-1-01 | 110kV FEEDER - CASHLA 110-GALWAY GIS 110-1 | 3 | 3 | 3 | Scheduled | 20/05/2024 | 22/05/2024
TO-24-CRO-T121-02 | DISTRIBUTION TRANSFORMER - COOLROE 110-COOLROE 20-T121 | 117 | 83 | 83 | Reference | 20/05/2024 | 13/09/2024
TO-24-220 kV A2 @ CDU-04 | BUSBAR SECTION - CORDUFF 220-CORDUFF 220-220A2 | 43 | 30 | 30 | Scheduled | 20/05/2024 | 01/07/2024
TO-24-220 kV A4 @ CDU-04 | BUSBAR SECTION - CORDUFF 220-CORDUFF 220-220A4 | 43 | 30 |  | Scheduled | 20/05/2024 | 01/07/2024
TO-24-220 kV B2 @ CDU-04 | BUSBAR SECTION - CORDUFF 220-CORDUFF 220-220B2 | 43 | 30 | 30 | Scheduled | 20/05/2024 | 01/07/2024
TO-24-220 kV B4 @ CDU-04 | BUSBAR SECTION - CORDUFF 220-CORDUFF 220-220B4 | 43 | 30 |  | Scheduled | 20/05/2024 | 01/07/2024
TO-24-220 kV A2 @ CRU-02 | BUSBAR SECTION - CRUISERATH 220-CRUISERATH 220-220A2 | 2 | 2 | 2 | Scheduled | 20/05/2024 | 21/05/2024
TO-24-220 kV B2 @ CRU-02 | BUSBAR SECTION - CRUISERATH 220-CRUISERATH 220-220B2 | 2 | 2 | 2 | Scheduled | 20/05/2024 | 21/05/2024
TO-24-CRU-220K2-02 | COUPLER/SECTIONALISING CB - CRUISERATH 220-CRUISERATH 220-220K2 | 2 | 2 | 2 | Scheduled | 20/05/2024 | 21/05/2024
TO-24-CRU-SA1-2CB-02 | COUPLER/SECTIONALISING CB - CRUISERATH 220-CRUISERATH 220-220SA1-2CB | 2 | 2 | 2 | Scheduled | 20/05/2024 | 21/05/2024
TO-24-CRU-SB1-2CB-02 | COUPLER/SECTIONALISING CB - CRUISERATH 220-CRUISERATH 220-220SB1-2CB | 2 | 2 | 2 | Scheduled | 20/05/2024 | 21/05/2024
TO-24-220 kV A1 @ FLA-02 | BUSBAR SECTION - FLAGFORD 220-FLAGFORD 220-220A1 | 5 | 5 | 5 | Scheduled | 20/05/2024 | 24/05/2024
TO-24-220 kV A2 @ FLA-04 | BUSBAR SECTION - FLAGFORD 220-FLAGFORD 220-220A2 | 5 | 5 | 5 | Scheduled | 20/05/2024 | 24/05/2024
TO-24-220 kV B1 @ FLA-03 | BUSBAR SECTION - FLAGFORD 220-FLAGFORD 220-220B1 | 5 | 5 | 5 | Scheduled | 20/05/2024 | 24/05/2024
TO-24-220 kV B2 @ FLA-03 | BUSBAR SECTION - FLAGFORD 220-FLAGFORD 220-220B2 | 5 | 5 | 5 | Scheduled | 20/05/2024 | 24/05/2024
TO-24-FLA-220K1-2-01 | COUPLER/SECTIONALISING CB - FLAGFORD 220-FLAGFORD 220-220K1-2 | 5 | 5 | 5 | Scheduled | 20/05/2024 | 24/05/2024
TO-24-KLN-KPG-1-01 | 220kV FEEDER - KILLONAN 220-KILPADDOGE 220-1 | 12 | 10 | 10 | Scheduled | 20/05/2024 | 31/05/2024
TO-24-220 kV A4 @ KPG-01 | BUSBAR SECTION - KILPADDOGE 220-KILPADDOGE 220-220A4 | 12 | 10 | 10 | Scheduled | 20/05/2024 | 31/05/2024
TO-24-220 kV B4 @ KPG-01 | BUSBAR SECTION - KILPADDOGE 220-KILPADDOGE 220-220B4 | 12 | 10 | 10 | Scheduled | 20/05/2024 | 31/05/2024
TO-24-KPG-220K4-02 | COUPLER/SECTIONALISING CB - KILPADDOGE 220-KILPADDOGE 220-220K4 | 12 | 10 | 10 | Scheduled | 20/05/2024 | 31/05/2024
TO-24-KPG-220SA2-4CB-02 | COUPLER/SECTIONALISING CB - KILPADDOGE 220-KILPADDOGE 220-220SA2-4CB | 12 | 10 | 10 | Scheduled | 20/05/2024 | 31/05/2024
TO-24-KPG-220SB2-4CB-01 | COUPLER/SECTIONALISING CB - KILPADDOGE 220-KILPADDOGE 220-220SB2-4CB | 12 | 10 | 10 | Scheduled | 20/05/2024 | 31/05/2024
TO-24-220 kV A1 @ MP GIS-01 | BUSBAR SECTION - MONEYPOINT GIS 220-MONEYPOINT GIS 220-220A1 | 5 | 5 | 5 | Scheduled | 20/05/2024 | 24/05/2024
TO-24-220 kV B1 @ MP GIS-01 | BUSBAR SECTION - MONEYPOINT GIS 220-MONEYPOINT GIS 220-220B1 | 5 | 5 | 5 | Scheduled | 20/05/2024 | 24/05/2024
TO-24-MP GIS-220K1-02 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 220-MONEYPOINT GIS 220-220K1 | 5 | 5 | 5 | Scheduled | 20/05/2024 | 24/05/2024
TO-24-MP GIS-220SA1-2CB-03 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 220-MONEYPOINT GIS 220-220SA1-2CB | 5 | 5 | 5 | Scheduled | 20/05/2024 | 24/05/2024
TO-24-MP GIS-220SB1-2CB-02 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 220-MONEYPOINT GIS 220-220SB1-2CB | 5 | 5 | 5 | Scheduled | 20/05/2024 | 24/05/2024
TO-24-MP GIS-T4001-01 | GENERATOR TRANSFORMER - MONEYPOINT GIS 400-MONEYPOINT GIS G1-T4001 | 12 | 10 | 10 | Scheduled | 20/05/2024 | 31/05/2024
TO-24-MP GIS-T4201-01 | TRANSFORMER - MONEYPOINT GIS 400-MONEYPOINT GIS 220-T4201 | 5 | 5 | 5 | Scheduled | 20/05/2024 | 24/05/2024
TO-24-220 kV A2 @ GI GIS-01 | BUSBAR SECTION - GREAT ISLAND GIS 220-GREAT ISLAND GIS 220-220A2 | 3 | 3 | 3 | Scheduled | 21/05/2024 | 23/05/2024
TO-24-GI GIS-220K2-01 | COUPLER/SECTIONALISING CB - GREAT ISLAND GIS 220-GREAT ISLAND GIS 220-220K2 | 3 | 3 | 3 | Scheduled | 21/05/2024 | 23/05/2024
TO-24-GI GIS-220SA1-2CB-04 | COUPLER/SECTIONALISING CB - GREAT ISLAND GIS 220-GREAT ISLAND GIS 220-220SA1-2CB | 3 | 3 | 3 | Scheduled | 21/05/2024 | 23/05/2024
TO-24-GI GIS-T2004-02 | GENERATOR TRANSFORMER - GREAT ISLAND GIS 220-GREAT ISLAND GIS G4-T2004 | 11 | 9 | 9 | Scheduled | 21/05/2024 | 31/05/2024
TO-24-LIS-CAP2-01 | CAPACITOR/SVC/REACTOR - LISDRUM 110-LISDRUM 110-CAP2 | 4 | 4 | 4 | Scheduled | 21/05/2024 | 24/05/2024
TO-24-BYH-CDL-1-01 | 110kV FEEDER - BALLYNAHULLA 110-CORDAL 110-1 | 4 | 4 | 4 | Scheduled | 27/05/2024 | 30/05/2024
TO-24-BOG-TTU-1-01 | 110kV FEEDER - BANOGE 110-TULLABEG 110-1 | 3 | 3 | 3 | Scheduled | 27/05/2024 | 29/05/2024
TO-24-BNK-T122-02 | TSO CUSTOMER TRANSFORMER - BARNAKYLE 110-BARNAKYLE 20-T122 | 5 | 5 | 5 | Scheduled | 27/05/2024 | 31/05/2024
TO-24-110 kV A2 @ CAH-03 | BUSBAR SECTION - CAHIR 110-CAHIR 110-110A2 | 12 | 9 | 9 | Scheduled | 27/05/2024 | 07/06/2024
TO-24-110 kV B2 @ CAH-03 | BUSBAR SECTION - CAHIR 110-CAHIR 110-110B2 | 12 | 9 | 9 | Scheduled | 27/05/2024 | 07/06/2024
TO-24-CAH-DOO-1-01 | 110kV FEEDER - CAHIR 110-DOON 110-1 | 12 | 9 | 9 | Scheduled | 27/05/2024 | 07/06/2024
TO-24-CDL-110SA1-01 | SECTIONALISING DISCONNECT - CORDAL 110-CORDAL 110-110SA1 | 4 | 4 | 4 | Scheduled | 27/05/2024 | 30/05/2024
TO-24-CDL-110SA2-01 | SECTIONALISING DISCONNECT - CORDAL 110-CORDAL 110-110SA2 | 4 | 4 | 4 | Scheduled | 27/05/2024 | 30/05/2024
TO-24-CDL-T132-01 | GENERATOR TRANSFORMER - CORDAL 110-CORDAL 33-T132 | 4 | 4 |  | Scheduled | 27/05/2024 | 30/05/2024
TO-24-CDL-T141-01 | DISTRIBUTION TRANSFORMER - CORDAL 110-CORDAL 38-T141 | 4 | 4 | 4 | Reference | 27/05/2024 | 30/05/2024
TO-24-DND-T122-01 | TSO CUSTOMER TRANSFORMER - DARNDALE 110-DARNDALE 20-T122 | 5 | 5 | 5 | Scheduled | 27/05/2024 | 31/05/2024
TO-24-KBY-MR-1-02 | 110kV FEEDER - KILBARRY 110-MARINA 110-1 | 107 | 75 | 75 | Scheduled | 27/05/2024 | 10/09/2024
TO-24-KBY-MR-2-02 | 110kV FEEDER - KILBARRY 110-MARINA 110-2 | 107 | 75 | 75 | Scheduled | 27/05/2024 | 10/09/2024
TO-24-400 kV A2 @ MP GIS-01 | BUSBAR SECTION - MONEYPOINT GIS 400-MONEYPOINT GIS 400-400A2 | 5 | 5 | 5 | Scheduled | 27/05/2024 | 31/05/2024
TO-24-400 kV B2 @ MP GIS-01 | BUSBAR SECTION - MONEYPOINT GIS 400-MONEYPOINT GIS 400-400B2 | 5 | 5 | 5 | Scheduled | 27/05/2024 | 31/05/2024
TO-24-MP GIS-400SA1-2CB-03 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 400-MONEYPOINT GIS 400-400SA1-2CB | 5 | 5 | 5 | Scheduled | 27/05/2024 | 31/05/2024
TO-24-MP GIS-400SA2-4CB-03 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 400-MONEYPOINT GIS 400-400SA2-4CB | 5 | 5 | 5 | Scheduled | 27/05/2024 | 31/05/2024
TO-24-MP GIS-400SB1-2CB-05 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 400-MONEYPOINT GIS 400-400SB1-2CB | 5 | 5 | 5 | Scheduled | 27/05/2024 | 31/05/2024
TO-24-MP GIS-400SB2-4CB-01 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 400-MONEYPOINT GIS 400-400SB2-4CB | 5 | 5 | 5 | Scheduled | 27/05/2024 | 31/05/2024
TO-24-MP GIS-T4002-02 | GENERATOR TRANSFORMER - MONEYPOINT GIS 400-MONEYPOINT GIS G2-T4002 | 5 | 5 | 5 | Scheduled | 27/05/2024 | 31/05/2024
TO-24-DEY-T134-03 | GENERATOR TRANSFORMER - DERRYCARNEY 110-DERRYCARNEY 33-T134 | 1 | 1 | 1 | Scheduled | 28/05/2024 | 28/05/2024
TO-24-110 kV A2 @ FIN-03 | BUSBAR SECTION - FINGLAS 110-FINGLAS 110-110A2 | 3 | 3 | 3 | Scheduled | 28/05/2024 | 30/05/2024
TO-24-110 kV B2 @ FIN-03 | BUSBAR SECTION - FINGLAS 110-FINGLAS 110-110B2 | 3 | 3 | 3 | Scheduled | 28/05/2024 | 30/05/2024
TO-24-110 kV A2 @ CDU-03 | BUSBAR SECTION - CORDUFF 110-CORDUFF 110-110A2 | 57 | 40 | 40 | Scheduled | 29/05/2024 | 24/07/2024
TO-24-110 kV A4 @ CDU-02 | BUSBAR SECTION - CORDUFF 110-CORDUFF 110-110A4 | 57 | 40 | 40 | Scheduled | 29/05/2024 | 24/07/2024
TO-24-110 kV B2 @ CDU-04 | BUSBAR SECTION - CORDUFF 110-CORDUFF 110-110B2 | 57 | 40 | 40 | Scheduled | 29/05/2024 | 24/07/2024
TO-24-110 kV B4 @ CDU-02 | BUSBAR SECTION - CORDUFF 110-CORDUFF 110-110B4 | 57 | 40 | 40 | Scheduled | 29/05/2024 | 24/07/2024
TO-24-DSN-KLS-1-03 | 220kV FEEDER - DUNSTOWN 220-KELLIS 220-1 | 7 | 4 | 4 | Scheduled | 29/05/2024 | 04/06/2024
TO-24-KLS-T2101-05 | TRANSFORMER - KELLIS 220-KELLIS 110-T2101 | 7 | 4 | 4 | Scheduled | 29/05/2024 | 04/06/2024
TO-24-MLC-T121-01 | GENERATOR TRANSFORMER - MOUNTLUCAS 110-MOUNTLUCAS 20-T121 | 1 | 1 | 1 | Scheduled | 29/05/2024 | 29/05/2024
TO-24-LOU-T2101-04 | TRANSFORMER - LOUTH 220-LOUTH 110-T2101 | 15 | 10 | 10 | Scheduled | 30/05/2024 | 13/06/2024
TO-24-ARV-NAV-1-04 | 110kV FEEDER - ARVA 110-NAVAN 110-1 | 2 | 0 |  | Scheduled | 01/06/2024 | 02/06/2024
TO-24-GOR-NAV-2-05 | 110kV FEEDER - GORMAN 110-NAVAN 110-2 | 2 | 0 |  | Scheduled | 01/06/2024 | 02/06/2024
TO-24-NAV-110SA1-2CB-04 | COUPLER/SECTIONALISING CB - NAVAN 110-NAVAN 110-110SA1-2CB | 2 | 0 |  | Scheduled | 01/06/2024 | 02/06/2024
TO-24-NAV-M/CAP1-03 | CAPACITOR/SVC/REACTOR - NAVAN 110-NAVAN 110-M/CAP1 | 2 | 0 |  | Scheduled | 01/06/2024 | 02/06/2024
TO-24-GLE-KCR-1-01 | 110kV FEEDER - GLENLARA 110-KNOCKACUMMER 110-1 | 4 | 4 | 4 | Scheduled | 04/06/2024 | 07/06/2024
TO-24-GOR-NAV-2-02 | 110kV FEEDER - GORMAN 110-NAVAN 110-2 | 77 | 54 | 54 | Scheduled | 04/06/2024 | 19/08/2024
TO-24-KCR-T121-01 | GENERATOR TRANSFORMER - KNOCKACUMMER 110-KNOCKACUMMER 20-T121 | 4 | 4 | 4 | Scheduled | 04/06/2024 | 07/06/2024
TO-24-PA-T101-04 | GENERATOR TRANSFORMER - POLLAPHUCA 110-POLLAPHUCA G1-T101 | 8 | 6 | 6 | Scheduled | 04/06/2024 | 11/06/2024
TO-24-AA GIS-LIM-1-01 | 110kV FEEDER - ARDNACRUSHA GIS 110-LIMERICK 110-1 | 3 | 3 | 3 | Scheduled | 05/06/2024 | 07/06/2024
TO-24-BYH-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - BALLYNAHULLA 110-BALLYNAHULLA 110-110SA1-2CB | 1 | 1 | 1 | Scheduled | 05/06/2024 | 05/06/2024
TO-24-BDA-T102-01 | TSO CUSTOMER TRANSFORMER - BARODA 110-BARODA 10-T102 | 3 | 3 | 3 | Scheduled | 05/06/2024 | 07/06/2024
TO-24-CF-SRA-1-02 | 110kV FEEDER - CATHALEENS FALL 110-SRANANAGH 110-1 | 70 | 49 | 49 | Scheduled | 05/06/2024 | 13/08/2024
TO-24-CDU-110K1-3-01 | COUPLER/SECTIONALISING CB - CORDUFF 110-CORDUFF 110-110K1-3 | 1 | 1 | 1 | Scheduled | 05/06/2024 | 05/06/2024
TO-24-CKG-110K2-02 | COUPLER/SECTIONALISING CB - CORKAGH 110-CORKAGH 110-110K2 | 1 | 1 | 1 | Scheduled | 05/06/2024 | 05/06/2024
TO-24-DAL-T141-02 | DISTRIBUTION TRANSFORMER - DALLOW 110-DALLOW 38-T141 | 6 | 4 | 4 | Reference | 05/06/2024 | 10/06/2024
TO-24-DAL,T-DAL-1-02 | 110kV FEEDER - DALLOW tee-DALLOW 110-1 | 6 | 4 | 4 | Scheduled | 05/06/2024 | 10/06/2024
TO-24-DAL,T-DEY-1-03 | 110kV FEEDER - DALLOW tee-DERRYCARNEY 110-1 | 92 | 65 |  | Scheduled | 05/06/2024 | 04/09/2024
TO-24-DEY-110K2-01 | COUPLER/SECTIONALISING CB - DERRYCARNEY 110-DERRYCARNEY 110-110K2 | 1 | 1 | 1 | Scheduled | 05/06/2024 | 05/06/2024
TO-24-220 kV A1 @ GI GIS-03 | BUSBAR SECTION - GREAT ISLAND GIS 220-GREAT ISLAND GIS 220-220A1 | 13 | 9 | 9 | Scheduled | 05/06/2024 | 17/06/2024
TO-24-220 kV B1 @ GI GIS-02 | BUSBAR SECTION - GREAT ISLAND GIS 220-GREAT ISLAND GIS 220-220B1 | 13 | 9 | 9 | Scheduled | 05/06/2024 | 17/06/2024
TO-24-GI GIS-KLS-1-01 | 220kV FEEDER - GREAT ISLAND GIS 220-KELLIS 220-1 | 13 | 9 | 9 | Scheduled | 05/06/2024 | 17/06/2024
TO-24-KLS-T2102-01 | TRANSFORMER - KELLIS 220-KELLIS 110-T2102 | 7 | 5 | 5 | Scheduled | 05/06/2024 | 11/06/2024
TO-24-KLN-T2101-01 | TRANSFORMER - KILLONAN 220-KILLONAN 110-T2101 | 3 | 3 | 3 | Scheduled | 05/06/2024 | 07/06/2024
TO-24-CKM GIS-220SA1-3CB-01 | COUPLER/SECTIONALISING CB - CARRICKMINES GIS 220-CARRICKMINES GIS 220-22SA1-3CB | 2 | 2 | 2 | Scheduled | 06/06/2024 | 07/06/2024
TO-24-CLN-110SA1-02 | SECTIONALISING DISCONNECT - CLOON 110-CLOON 110-110SA1 | 9 | 7 | 7 | Scheduled | 06/06/2024 | 14/06/2024
TO-24-CLN-110SA2-02 | SECTIONALISING DISCONNECT - CLOON 110-CLOON 110-110SA2 | 9 | 7 | 7 | Scheduled | 06/06/2024 | 14/06/2024
TO-24-CLN-LA-1-02 | 110kV FEEDER - CLOON 110-LANESBORO 110-1 | 9 | 7 | 7 | Scheduled | 06/06/2024 | 14/06/2024
TO-24-CDU-220K1-3-01 | COUPLER/SECTIONALISING CB - CORDUFF 220-CORDUFF 220-220K1-3 | 1 | 1 | 1 | Proposed | 07/06/2024 | 07/06/2024
TO-24-AA GIS-T102-01 | GENERATOR TRANSFORMER - ARDNACRUSHA GIS 110-ARDNACRUSHA GIS G2-T102 | 5 | 5 | 5 | Scheduled | 10/06/2024 | 14/06/2024
TO-24-AUG-CFM-2-01 | 110kV FEEDER - AUGHINISH 110-CASTLEFARM 110-2 | 5 | 5 | 5 | Scheduled | 10/06/2024 | 14/06/2024
TO-24-AUG-SK-3-01 | 110kV FEEDER - AUGHINISH 110-SEALROCK 110-3 | 5 | 5 | 5 | Scheduled | 10/06/2024 | 14/06/2024
TO-24-CFM-T102-01 | TSO CUSTOMER TRANSFORMER - CASTLEFARM 110-CASTLEFARM 10-T102 | 5 | 5 | 5 | Reference | 10/06/2024 | 14/06/2024
TO-24-CF-T103-01 | GENERATOR TRANSFORMER - CATHALEENS FALL 110-CATHALEENS FALL G3-T103 | 5 | 5 | 5 | Scheduled | 10/06/2024 | 14/06/2024
TO-24-CLA-MAC-1-02 | 110kV FEEDER - CLASHAVOON 110-MACROOM 110-1 | 5 | 5 | 5 | Scheduled | 10/06/2024 | 14/06/2024
TO-24-CRA-LWD-1-01 | 110kV FEEDER - CRANE 110-LODGEWOOD 110-1 | 5 | 5 | 5 | Scheduled | 10/06/2024 | 14/06/2024
TO-24-CRY-LWD-1-01 | 110kV FEEDER - CRORY 110-LODGEWOOD 110-1 | 5 | 5 | 5 | Reference | 10/06/2024 | 14/06/2024
TO-24-CRY-T121-01 | DISTRIBUTION TRANSFORMER - CRORY 110-CRORY 20-T121 | 5 | 5 | 5 | Reference | 10/06/2024 | 14/06/2024
TO-24-110 kV A1 @ DND-01 | BUSBAR SECTION - DARNDALE 110-DARNDALE 110-110A1 | 5 | 5 | 5 | Scheduled | 10/06/2024 | 14/06/2024
TO-24-110 kV B1 @ DND-01 | BUSBAR SECTION - DARNDALE 110-DARNDALE 110-110B1 | 5 | 5 | 5 | Scheduled | 10/06/2024 | 14/06/2024
TO-24-DND-110K1-01 | COUPLER/SECTIONALISING CB - DARNDALE 110-DARNDALE 110-110K1 | 5 | 5 | 5 | Scheduled | 10/06/2024 | 14/06/2024
TO-24-DND-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - DARNDALE 110-DARNDALE 110-110SA1-2CB | 5 | 5 | 5 | Scheduled | 10/06/2024 | 14/06/2024
TO-24-DND-110SB1-2CB-01 | COUPLER/SECTIONALISING CB - DARNDALE 110-DARNDALE 110-110SB1-2CB | 5 | 5 | 5 | Scheduled | 10/06/2024 | 14/06/2024
TO-24-DRU-ENN-1-02 | 110kV FEEDER - DRUMLINE 110-ENNIS 110-1 | 123 | 88 | 88 | Scheduled | 10/06/2024 | 10/10/2024
TO-24-110 kV A1 @ GAL GIS-01 | BUSBAR SECTION - GALWAY GIS 110-GALWAY GIS 110-110A1 | 7 | 5 | 5 | Scheduled | 10/06/2024 | 16/06/2024
TO-24-110 kV B1 @ GAL GIS-01 | BUSBAR SECTION - GALWAY GIS 110-GALWAY GIS 110-110B1 | 7 | 5 | 5 | Scheduled | 10/06/2024 | 16/06/2024
TO-24-GAL GIS-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - GALWAY GIS 110-GALWAY GIS 110-110SA1-2CB | 7 | 5 | 5 | Scheduled | 10/06/2024 | 16/06/2024
TO-24-GAL GIS-110SA1-3CB-01 | COUPLER/SECTIONALISING CB - GALWAY GIS 110-GALWAY GIS 110-110SA1-3CB | 7 | 5 | 5 | Scheduled | 10/06/2024 | 16/06/2024
TO-24-GAL GIS-110SB1-2CB-01 | COUPLER/SECTIONALISING CB - GALWAY GIS 110-GALWAY GIS 110-110SB1-2CB | 7 | 5 | 5 | Scheduled | 10/06/2024 | 16/06/2024
TO-24-GAL GIS-110SB1-3CB-01 | COUPLER/SECTIONALISING CB - GALWAY GIS 110-GALWAY GIS 110-110SB1-3CB | 7 | 5 | 5 | Scheduled | 10/06/2024 | 16/06/2024
TO-24-KPG-TRL-2-02 | 110kV FEEDER - KILPADDOGE 110-TRALEE 110-2 | 8 | 6 | 6 | Scheduled | 10/06/2024 | 17/06/2024
TO-24-LWD-110SA1-01 | SECTIONALISING DISCONNECT - LODGEWOOD 110-LODGEWOOD 110-110SA1 | 5 | 5 | 5 | Scheduled | 10/06/2024 | 14/06/2024
TO-24-LWD-110SA2-01 | SECTIONALISING DISCONNECT - LODGEWOOD 110-LODGEWOOD 110-110SA2 | 5 | 5 | 5 | Scheduled | 10/06/2024 | 14/06/2024
TO-24-SK-T103-01 | GENERATOR TRANSFORMER - SEALROCK 110-SEALROCK G3-T103 | 5 | 5 | 5 | Scheduled | 10/06/2024 | 14/06/2024
TO-24-BNK-T121-01 | TSO CUSTOMER TRANSFORMER - BARNAKYLE 110-BARNAKYLE 20-T121 | 2 | 2 | 2 | Scheduled | 11/06/2024 | 12/06/2024
TO-24-CHA-MAL-1-01 | 110kV FEEDER - CHARLEVILLE 110-MALLOW 110-1 | 14 | 10 | 10 | Scheduled | 11/06/2024 | 24/06/2024
TO-24-110 kV A1 @ CAH-02 | BUSBAR SECTION - CAHIR 110-CAHIR 110-110A1 | 2 | 2 | 2 | Scheduled | 12/06/2024 | 13/06/2024
TO-24-CAH-KHL-1-01 | 110kV FEEDER - CAHIR 110-KILL HILL 110-1 | 2 | 2 | 2 | Scheduled | 12/06/2024 | 13/06/2024
TO-24-SLB-T132-01 | GENERATOR TRANSFORMER - SLIABH BAWN 110-SLIABH BAWN 33-T132 | 3 | 3 | 3 | Scheduled | 12/06/2024 | 14/06/2024
TO-24-AGL-DYN-1-04 | 110kV FEEDER - AGANNYGAL 110-DERRYBRIEN 110-1 | 2 | 2 | 2 | Scheduled | 13/06/2024 | 14/06/2024
TO-24-ATE-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - ATHEA 110-ATHEA 110-110SA1-2CB | 10 | 8 | 8 | Scheduled | 17/06/2024 | 26/06/2024
TO-24-ATE-DRO-1-01 | 110kV FEEDER - ATHEA 110-DROMADA 110-1 | 10 | 8 | 8 | Scheduled | 17/06/2024 | 26/06/2024
TO-24-ATE-KNR-1-01 | 110kV FEEDER - ATHEA 110-KNOCKANURE 110-1 | 10 | 8 | 8 | Scheduled | 17/06/2024 | 26/06/2024
TO-24-ATE-T121-01 | GENERATOR TRANSFORMER - ATHEA 110-ATHEA 20-T121 | 10 | 8 | 8 | Scheduled | 17/06/2024 | 26/06/2024
TO-24-ATE-TOB-1-02 | 110kV FEEDER - ATHEA 110-TOBERTOREEN 110-1 | 10 | 8 | 8 | Scheduled | 17/06/2024 | 26/06/2024
TO-24-ATH-SH-1-02 | 110kV FEEDER - ATHLONE 110-SHANNONBRIDGE 110-1 | 12 | 10 | 10 | Scheduled | 17/06/2024 | 28/06/2024
TO-24-BLC-DND-1-01 | 110kV FEEDER - BELCAMP 110-DARNDALE 110-1 | 2 | 2 | 2 | Scheduled | 17/06/2024 | 18/06/2024
TO-24-110 kV A1 @ CAH-04 | BUSBAR SECTION - CAHIR 110-CAHIR 110-110A1 | 9 | 7 | 7 | Scheduled | 17/06/2024 | 25/06/2024
TO-24-110 kV B1 @ CAH-03 | BUSBAR SECTION - CAHIR 110-CAHIR 110-110B1 | 9 | 7 | 7 | Scheduled | 17/06/2024 | 25/06/2024
TO-24-CAH-CAP1/3-01 | CAPACITOR/SVC/REACTOR - CAHIR 110-CAHIR 110-CAP1/3 | 9 | 7 | 7 | Scheduled | 17/06/2024 | 25/06/2024
TO-24-CDK-LWD-1-01 | 110kV FEEDER - CASTLEDOCKRELL 110-LODGEWOOD 110-1 | 5 | 5 | 5 | Scheduled | 17/06/2024 | 21/06/2024
TO-24-CDK-T121-01 | GENERATOR TRANSFORMER - CASTLEDOCKRELL 110-CASTLEDOCKRELL 20-T121 | 5 | 5 | 5 | Reference | 17/06/2024 | 21/06/2024
TO-24-CUN-T121-01 | GENERATOR TRANSFORMER - CUNGHILL 110-CUNGHILL 20-T121 | 5 | 5 | 5 | Scheduled | 17/06/2024 | 21/06/2024
TO-24-110 kV A1 @ DND-02 | BUSBAR SECTION - DARNDALE 110-DARNDALE 110-110A1 | 2 | 2 | 2 | Scheduled | 17/06/2024 | 18/06/2024
TO-24-110 kV B1 @ DND-02 | BUSBAR SECTION - DARNDALE 110-DARNDALE 110-110B1 | 2 | 2 | 2 | Scheduled | 17/06/2024 | 18/06/2024
TO-24-DND-110K1-02 | COUPLER/SECTIONALISING CB - DARNDALE 110-DARNDALE 110-110K1 | 2 | 2 | 2 | Scheduled | 17/06/2024 | 18/06/2024
TO-24-DND-110SA1-2CB-02 | COUPLER/SECTIONALISING CB - DARNDALE 110-DARNDALE 110-110SA1-2CB | 2 | 2 | 2 | Scheduled | 17/06/2024 | 18/06/2024
TO-24-DND-110SB1-2CB-02 | COUPLER/SECTIONALISING CB - DARNDALE 110-DARNDALE 110-110SB1-2CB | 2 | 2 | 2 | Scheduled | 17/06/2024 | 18/06/2024
TO-24-DRO-T121-02 | GENERATOR TRANSFORMER - DROMADA 110-DROMADA 20-T121 | 10 | 8 | 8 | Scheduled | 17/06/2024 | 26/06/2024
TO-24-110 kV A1 @ FLA-05 | BUSBAR SECTION - FLAGFORD 110-FLAGFORD 110-110A1 | 2 | 2 |  | Scheduled | 17/06/2024 | 18/06/2024
TO-24-110 kV B1 @ FLA-06 | BUSBAR SECTION - FLAGFORD 110-FLAGFORD 110-110B1 | 2 | 2 |  | Scheduled | 17/06/2024 | 18/06/2024
TO-24-KKY-CAP2-01 | CAPACITOR/SVC/REACTOR - KILKENNY 110-KILKENNY 110-CAP2 | 5 | 5 | 5 | Scheduled | 17/06/2024 | 21/06/2024
TO-24-KPG-TB-2-03 | 220kV FEEDER - KILPADDOGE 220-TARBERT 220-2 | 14 | 10 |  | Scheduled | 17/06/2024 | 30/06/2024
TO-24-KRA-WOH-1-02 | 110kV FEEDER - KNOCKRAHA 110-WOODHOUSE 110-1 | 12 | 10 | 10 | Scheduled | 17/06/2024 | 28/06/2024
TO-24-LWD-110SA1-02 | SECTIONALISING DISCONNECT - LODGEWOOD 110-LODGEWOOD 110-110SA1 | 5 | 5 | 5 | Scheduled | 17/06/2024 | 21/06/2024
TO-24-LWD-110SA2-02 | SECTIONALISING DISCONNECT - LODGEWOOD 110-LODGEWOOD 110-110SA2 | 5 | 5 | 5 | Scheduled | 17/06/2024 | 21/06/2024
TO-24-LWD-T2102-01 | TRANSFORMER - LODGEWOOD 220-LODGEWOOD 110-T2102 | 5 | 5 | 5 | Scheduled | 17/06/2024 | 21/06/2024
TO-24-400 kV A1 @ MP GIS-03 | BUSBAR SECTION - MONEYPOINT GIS 400-MONEYPOINT GIS 400-400A1 | 5 | 5 | 5 | Scheduled | 17/06/2024 | 21/06/2024
TO-24-400 kV A3 @ MP GIS-01 | BUSBAR SECTION - MONEYPOINT GIS 400-MONEYPOINT GIS 400-400A3 | 5 | 5 | 5 | Scheduled | 17/06/2024 | 21/06/2024
TO-24-MP GIS-400K3-03 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 400-MONEYPOINT GIS 400-400K3 | 5 | 5 | 5 | Scheduled | 17/06/2024 | 21/06/2024
TO-24-MP GIS-400SA1-2CB-04 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 400-MONEYPOINT GIS 400-400SA1-2CB | 5 | 5 | 5 | Scheduled | 17/06/2024 | 21/06/2024
TO-24-MP GIS-400SA1-3CB-01 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 400-MONEYPOINT GIS 400-400SA1-3CB | 5 | 5 | 5 | Scheduled | 17/06/2024 | 21/06/2024
TO-24-110 kV A1 @ SH-05 | BUSBAR SECTION - SHANNONBRIDGE 110-SHANNONBRIDGE 110-110A1 | 12 | 10 | 10 | Scheduled | 17/06/2024 | 28/06/2024
TO-24-110 kV B1 @ SH-05 | BUSBAR SECTION - SHANNONBRIDGE 110-SHANNONBRIDGE 110-110B1 | 12 | 10 | 10 | Scheduled | 17/06/2024 | 28/06/2024
TO-24-220 kV A1/A2 @ TB-02 | BUSBAR SECTION - TARBERT 220-TARBERT 220-220A1-A2 | 14 | 10 |  | Scheduled | 17/06/2024 | 30/06/2024
TO-24-TOB-T132-02 | GENERATOR TRANSFORMER - TOBERTOREEN 110-TOBERTOREEN 33-T132 | 10 | 8 | 8 | Scheduled | 17/06/2024 | 26/06/2024
TO-24-AUG-MTN-1-01 | 110kV FEEDER - AUGHINISH 110-MONETEEN 110-1 | 9 | 7 | 7 | Scheduled | 18/06/2024 | 26/06/2024
TO-24-CLO-CRD-1-01 | 110kV FEEDER - CLOGHER 110-CROAGHONAGH 110-1 | 4 | 4 | 4 | Scheduled | 18/06/2024 | 21/06/2024
TO-24-CRD-T131-01 | GENERATOR TRANSFORMER - CROAGHONAGH 110-CROAGHONAGH 33-T131 | 4 | 4 | 4 | Scheduled | 18/06/2024 | 21/06/2024
TO-24-FLA-T2101-01 | TRANSFORMER - FLAGFORD 220-FLAGFORD 110-T2101 | 1 | 1 |  | Scheduled | 18/06/2024 | 18/06/2024
TO-24-110 kV B2 @ DND-01 | BUSBAR SECTION - DARNDALE 110-DARNDALE 110-110B2 | 1 | 1 | 1 | Scheduled | 19/06/2024 | 19/06/2024
TO-24-DND-110K2-03 | COUPLER/SECTIONALISING CB - DARNDALE 110-DARNDALE 110-110K2 | 1 | 1 | 1 | Scheduled | 19/06/2024 | 19/06/2024
TO-24-DND-110SB1-2CB-04 | COUPLER/SECTIONALISING CB - DARNDALE 110-DARNDALE 110-110SB1-2CB | 1 | 1 | 1 | Scheduled | 19/06/2024 | 19/06/2024
TO-24-DND-T126-01 | TSO CUSTOMER TRANSFORMER - DARNDALE 110-DARNDALE 20-T126 | 1 | 1 | 1 | Scheduled | 19/06/2024 | 19/06/2024
TO-24-GOR-T122-01 | GENERATOR TRANSFORMER - GORMAN 110-GORMAN 20-T122 | 2 | 2 | 2 | Proposed | 19/06/2024 | 20/06/2024
TO-24-220 kV B1 @ AD-03 | BUSBAR SECTION - AGHADA 220-AGHADA 220-220B1 | 1 | 1 | 1 | Scheduled | 20/06/2024 | 20/06/2024
TO-24-AD-T2011/12-03 | GENERATOR TRANSFORMER - AGHADA 220-AGHADA G11/12-T2011/12 | 1 | 1 | 1 | Scheduled | 20/06/2024 | 20/06/2024
TO-24-220 kV B2 @ CRU-04 | BUSBAR SECTION - CRUISERATH 220-CRUISERATH 220-220B2 | 2 | 2 | 2 | Scheduled | 20/06/2024 | 21/06/2024
TO-24-CRU-220K2-06 | COUPLER/SECTIONALISING CB - CRUISERATH 220-CRUISERATH 220-220K2 | 2 | 2 | 2 | Scheduled | 20/06/2024 | 21/06/2024
TO-24-CRU-SB1-2CB-06 | COUPLER/SECTIONALISING CB - CRUISERATH 220-CRUISERATH 220-220SB1-2CB | 2 | 2 | 2 | Scheduled | 20/06/2024 | 21/06/2024
TO-24-CRU-T222-01 | TSO CUSTOMER TRANSFORMER - CRUISERATH 220-CRUISERATH 20-T222 | 2 | 2 | 2 | Scheduled | 20/06/2024 | 21/06/2024
TO-24-TY-T2001/2-04 | GENERATOR TRANSFORMER - TYNAGH 220-TYNAGH G1/2-T2001/2 | 7 | 5 | 5 | Scheduled | 23/06/2024 | 29/06/2024
TO-24-CUS-KIR-1-02 | 110kV FEEDER - CUSHALING 110-KILCUMBER 110-1 | 24 | 18 | 18 | Scheduled | 24/06/2024 | 17/07/2024
TO-24-DYN-T121-03 | GENERATOR TRANSFORMER - DERRYBRIEN 110-DERRYBRIEN 20-T121 | 3 | 3 | 3 | Reference | 24/06/2024 | 26/06/2024
TO-24-DMY-MAC-1-03 | 110kV FEEDER - DUNMANWAY 110-MACROOM 110-1 | 5 | 5 | 5 | Scheduled | 24/06/2024 | 28/06/2024
TO-24-110 kV A1 @ GAL GIS-02 | BUSBAR SECTION - GALWAY GIS 110-GALWAY GIS 110-110A1 | 2 | 2 | 2 | Scheduled | 24/06/2024 | 25/06/2024
TO-24-110 kV B1 @ GAL GIS-02 | BUSBAR SECTION - GALWAY GIS 110-GALWAY GIS 110-110B1 | 2 | 2 | 2 | Scheduled | 24/06/2024 | 25/06/2024
TO-24-GAL GIS-110SA1-2CB-02 | COUPLER/SECTIONALISING CB - GALWAY GIS 110-GALWAY GIS 110-110SA1-2CB | 2 | 2 | 2 | Scheduled | 24/06/2024 | 25/06/2024
TO-24-GAL GIS-110SA1-3CB-02 | COUPLER/SECTIONALISING CB - GALWAY GIS 110-GALWAY GIS 110-110SA1-3CB | 2 | 2 | 2 | Scheduled | 24/06/2024 | 25/06/2024
TO-24-GAL GIS-110SB1-2CB-02 | COUPLER/SECTIONALISING CB - GALWAY GIS 110-GALWAY GIS 110-110SB1-2CB | 2 | 2 | 2 | Scheduled | 24/06/2024 | 25/06/2024
TO-24-GAL GIS-110SB1-3CB-02 | COUPLER/SECTIONALISING CB - GALWAY GIS 110-GALWAY GIS 110-110SB1-3CB | 2 | 2 | 2 | Scheduled | 24/06/2024 | 25/06/2024
TO-24-GAL GIS-SAL-1-01 | 110kV FEEDER - GALWAY GIS 110-SALTHILL 110-1 | 2 | 2 | 2 | Scheduled | 24/06/2024 | 25/06/2024
TO-24-GI-KKY-1-03 | 110kV FEEDER - GREAT ISLAND 110-KILKENNY 110-1 | 8 | 6 |  | Scheduled | 24/06/2024 | 01/07/2024
TO-24-110 kV A2 @ KBY-01 | BUSBAR SECTION - KILBARRY 110-KILBARRY 110-110A2 | 19 | 15 | 15 | Scheduled | 24/06/2024 | 12/07/2024
TO-24-110 kV B2 @ KBY-01 | BUSBAR SECTION - KILBARRY 110-KILBARRY 110-110B2 | 19 | 15 | 15 | Scheduled | 24/06/2024 | 12/07/2024
TO-24-KIR-T131-02 | GENERATOR TRANSFORMER - KILCUMBER 110-KILCUMBER 33-T131 | 24 | 18 | 18 | Scheduled | 24/06/2024 | 17/07/2024
TO-24-KKY-110SA1-2CB-02 | COUPLER/SECTIONALISING CB - KILKENNY 110-KILKENNY 110-110SA1-2CB | 8 | 6 |  | Scheduled | 24/06/2024 | 01/07/2024
TO-24-KKY-CAP2-02 | CAPACITOR/SVC/REACTOR - KILKENNY 110-KILKENNY 110-CAP2 | 8 | 6 |  | Scheduled | 24/06/2024 | 01/07/2024
TO-24-KKY-T142-01 | DISTRIBUTION TRANSFORMER - KILKENNY 110-KILKENNY 38-T142 | 8 | 6 |  | Reference | 24/06/2024 | 01/07/2024
TO-24-OBE-T123-01 | TSO CUSTOMER TRANSFORMER - OLDBRIDGE 110-OLDBRIDGE 20-T123 | 2 | 2 | 2 | Scheduled | 24/06/2024 | 25/06/2024
TO-24-220 kV A4 @ PB-01 | BUSBAR SECTION - POOLBEG 220-POOLBEG 220-220A4 | 5 | 5 | 5 | Scheduled | 24/06/2024 | 28/06/2024
TO-24-220 kV B4 @ PB-02 | BUSBAR SECTION - POOLBEG 220-POOLBEG 220-220B4 | 5 | 5 | 5 | Scheduled | 24/06/2024 | 28/06/2024
TO-24-220 kV A1 @ SH-03 | BUSBAR SECTION - SHANNONBRIDGE 220-SHANNONBRIDGE 220-220A1 | 12 | 10 | 10 | Scheduled | 24/06/2024 | 05/07/2024
TO-24-220 kV A2 @ SH-02 | BUSBAR SECTION - SHANNONBRIDGE 220-SHANNONBRIDGE 220-220A2 | 12 | 10 | 10 | Scheduled | 24/06/2024 | 05/07/2024
TO-24-220 kV B1 @ SH-03 | BUSBAR SECTION - SHANNONBRIDGE 220-SHANNONBRIDGE 220-220B1 | 12 | 10 | 10 | Scheduled | 24/06/2024 | 05/07/2024
TO-24-220 kV B2 @ SH-03 | BUSBAR SECTION - SHANNONBRIDGE 220-SHANNONBRIDGE 220-220B2 | 12 | 10 | 10 | Scheduled | 24/06/2024 | 05/07/2024
TO-24-SH-220K1-2-01 | COUPLER/SECTIONALISING CB - SHANNONBRIDGE 220-SHANNONBRIDGE 220-220K1-2 | 12 | 10 | 10 | Scheduled | 24/06/2024 | 05/07/2024
TO-24-CTN-KLN-1-01 | 110kV FEEDER - CAUTEEN 110-KILLONAN 110-1 | 4 | 4 | 4 | Scheduled | 25/06/2024 | 28/06/2024
TO-24-110 kV A1 @ KLS-02 | BUSBAR SECTION - KELLIS 110-KELLIS 110-110A1 | 1 | 1 | 1 | Scheduled | 25/06/2024 | 25/06/2024
TO-24-110 kV A2 @ KLS-05 | BUSBAR SECTION - KELLIS 110-KELLIS 110-110A2 | 1 | 1 | 1 | Scheduled | 25/06/2024 | 25/06/2024
TO-24-110 kV B1 @ KLS-02 | BUSBAR SECTION - KELLIS 110-KELLIS 110-110B1 | 1 | 1 | 1 | Scheduled | 25/06/2024 | 25/06/2024
TO-24-110 kV B2 @ KLS-04 | BUSBAR SECTION - KELLIS 110-KELLIS 110-110B2 | 1 | 1 | 1 | Scheduled | 25/06/2024 | 25/06/2024
TO-24-GAL GIS-T142-04 | DISTRIBUTION TRANSFORMER - GALWAY GIS 110-GALWAY 38-T142 | 14 | 10 | 10 | Reference | 26/06/2024 | 09/07/2024
TO-24-TY-T2001/2-02 | GENERATOR TRANSFORMER - TYNAGH 220-TYNAGH G1/2-T2001/2 | 1 | 1 | 1 | Scheduled | 26/06/2024 | 26/06/2024
TO-24-CNO-KPG-1-01 | 110kV FEEDER - COOLNANOONAGH 110-KILPADDOGE 110-1 | 2 | 2 | 2 | Scheduled | 27/06/2024 | 28/06/2024
TO-24-CNO-T131-01 | GENERATOR TRANSFORMER - COOLNANOONAGH 110-COOLNANOONAGH 33-T131 | 2 | 2 |  | Scheduled | 27/06/2024 | 28/06/2024
TO-24-BVK-COT-1-01 | 110kV FEEDER - BALLYVOUSKILL 110-COOMATAGGART 110-1 | 9 | 7 |  | Scheduled | 01/07/2024 | 09/07/2024
TO-24-COT-110SA1-01 | SECTIONALISING DISCONNECT - COOMATAGGART 110-COOMATAGGART 110-110SA1 | 9 | 7 | 7 | Scheduled | 01/07/2024 | 09/07/2024
TO-24-COT-110SA2-01 | SECTIONALISING DISCONNECT - COOMATAGGART 110-COOMATAGGART 110-110SA2 | 9 | 7 | 7 | Scheduled | 01/07/2024 | 09/07/2024
TO-24-COT-FILTER1-01 | CAPACITOR/SVC/REACTOR - COOMATAGGART 110-COOMATAGGART 110-FILTER1 | 9 | 7 | 7 | Scheduled | 01/07/2024 | 09/07/2024
TO-24-COT-T132-01 | GENERATOR TRANSFORMER - COOMATAGGART 110-COOMATAGGART 33-T132 | 9 | 7 |  | Scheduled | 01/07/2024 | 09/07/2024
TO-24-COT-T141-01 | DISTRIBUTION TRANSFORMER - COOMATAGGART 110-COOMATAGGART 38-T141 | 9 | 7 | 7 | Reference | 01/07/2024 | 09/07/2024
TO-24-DGN-WOH-1-02 | 110kV FEEDER - DUNGARVAN 110-WOODHOUSE 110-1 | 5 | 5 | 5 | Scheduled | 01/07/2024 | 05/07/2024
TO-24-110 kV A2 @ FLA-04 | BUSBAR SECTION - FLAGFORD 110-FLAGFORD 110-110A2 | 12 | 10 | 10 | Scheduled | 01/07/2024 | 12/07/2024
TO-24-110 kV B2 @ FLA-04 | BUSBAR SECTION - FLAGFORD 110-FLAGFORD 110-110B2 | 12 | 10 | 10 | Scheduled | 01/07/2024 | 12/07/2024
TO-24-220 kV A2 @ FLA-05 | BUSBAR SECTION - FLAGFORD 220-FLAGFORD 220-220A2 | 12 | 10 | 10 | Scheduled | 01/07/2024 | 12/07/2024
TO-24-220 kV B2 @ FLA-04 | BUSBAR SECTION - FLAGFORD 220-FLAGFORD 220-220B2 | 12 | 10 | 10 | Scheduled | 01/07/2024 | 12/07/2024
TO-24-FLA-T2102-01 | TRANSFORMER - FLAGFORD 220-FLAGFORD 110-T2102 | 12 | 10 | 10 | Scheduled | 01/07/2024 | 12/07/2024
TO-24-220 kV A2 @ LOU-01 | BUSBAR SECTION - LOUTH 220-LOUTH 220-220A2 | 12 | 10 | 10 | Scheduled | 01/07/2024 | 12/07/2024
TO-24-220 kV B2 @ LOU-01 | BUSBAR SECTION - LOUTH 220-LOUTH 220-220B2 | 12 | 10 | 10 | Scheduled | 01/07/2024 | 12/07/2024
TO-24-LOU-AT1-01 | TRANSFORMER - LOUTH 220-LOUTH 275-AT1 | 12 | 10 | 10 | Scheduled | 01/07/2024 | 12/07/2024
TO-24-LOU-AT3-02 | TRANSFORMER - LOUTH 220-LOUTH 275-AT3 | 12 | 10 | 10 | Scheduled | 01/07/2024 | 12/07/2024
TO-24-LOU-TAN-1-01 | 275kV FEEDER - LOUTH 275-TANDRAGEE 275-1 | 12 | 10 | 10 | Scheduled | 01/07/2024 | 12/07/2024
TO-24-MID-110SA1-03 | SECTIONALISING DISCONNECT - MIDLETON 110-MIDLETON 110-110SA1 | 12 | 10 | 10 | Scheduled | 01/07/2024 | 12/07/2024
TO-24-MID-110SA2-01 | SECTIONALISING DISCONNECT - MIDLETON 110-MIDLETON 110-110SA2 | 12 | 10 | 10 | Scheduled | 01/07/2024 | 12/07/2024
TO-24-MID-T102-01 | DISTRIBUTION TRANSFORMER - MIDLETON 110-MIDLETON 10-T102 | 12 | 10 | 10 | Reference | 01/07/2024 | 12/07/2024
TO-24-MID-WHI-1-01 | 110kV FEEDER - MIDLETON 110-WHITEGATE 110-1 | 12 | 10 | 10 | Scheduled | 01/07/2024 | 12/07/2024
TO-24-ARI,T-CDY-1-01 | 110kV FEEDER - ARIGNA tee-CORDERRY 110-1 | 1 | 1 | 1 | Scheduled | 02/07/2024 | 02/07/2024
TO-24-KLS-KKY-1-03 | 110kV FEEDER - KELLIS 110-KILKENNY 110-1 | 10 | 8 | 8 | Scheduled | 02/07/2024 | 11/07/2024
TO-24-CRO-110SA1-03 | SECTIONALISING DISCONNECT - COOLROE 110-COOLROE 110-110SA1 | 10 | 8 | 8 | Scheduled | 03/07/2024 | 12/07/2024
TO-24-CRO-110SA2-03 | SECTIONALISING DISCONNECT - COOLROE 110-COOLROE 110-110SA2 | 10 | 8 | 8 | Scheduled | 03/07/2024 | 12/07/2024
TO-24-CRO-KBY-1-04 | 110kV FEEDER - COOLROE 110-KILBARRY 110-1 | 10 | 8 | 8 | Scheduled | 03/07/2024 | 12/07/2024
TO-24-CRO-T121-04 | DISTRIBUTION TRANSFORMER - COOLROE 110-COOLROE 20-T121 | 10 | 8 | 8 | Reference | 03/07/2024 | 12/07/2024
TO-24-ENN-SLC-1-02 | 110kV FEEDER - ENNIS 110-SLIEVECALLAN 110-1 | 3 | 3 | 3 | Scheduled | 03/07/2024 | 05/07/2024
TO-24-SLC-110SA1-02 | SECTIONALISING DISCONNECT - SLIEVECALLAN 110-SLIEVECALLAN 110-110SA1 | 3 | 3 | 3 | Scheduled | 03/07/2024 | 05/07/2024
TO-24-SLC-110SA2-02 | SECTIONALISING DISCONNECT - SLIEVECALLAN 110-SLIEVECALLAN 110-110SA2 | 3 | 3 | 3 | Scheduled | 03/07/2024 | 05/07/2024
TO-24-SLC-T121-02 | GENERATOR TRANSFORMER - SLIEVECALLAN 110-SLIEVECALLAN 20-T121 | 3 | 3 | 3 | Scheduled | 03/07/2024 | 05/07/2024
TO-24-SLC-T122-02 | GENERATOR TRANSFORMER - SLIEVECALLAN 110-SLIEVECALLAN 20-T122 | 3 | 3 | 3 | Scheduled | 03/07/2024 | 05/07/2024
TO-24-ARK-LWD-1-02 | 220kV FEEDER - ARKLOW 220-LODGEWOOD 220-1 | 10 | 8 | 8 | Scheduled | 08/07/2024 | 17/07/2024
TO-24-AUG-SK-4-01 | 110kV FEEDER - AUGHINISH 110-SEALROCK 110-4 | 65 | 46 | 46 | Scheduled | 08/07/2024 | 10/09/2024
TO-24-CLA-CKN-1-01 | 110kV FEEDER - CLASHAVOON 110-CLONKEEN 110-1 | 19 | 15 | 15 | Scheduled | 08/07/2024 | 26/07/2024
TO-24-CFN-SH-1-01 | 220kV FEEDER - CLONIFFEEN 220-SHANNONBRIDGE 220-1 | 2 | 2 | 2 | Scheduled | 08/07/2024 | 09/07/2024
TO-24-CFN-T232-01 | GENERATOR TRANSFORMER - CLONIFFEEN 220-CLONIFFEEN 33-T232 | 2 | 2 | 2 | Scheduled | 08/07/2024 | 09/07/2024
TO-24-CKN-110SA1-2CB-02 | COUPLER/SECTIONALISING CB - CLONKEEN 110-CLONKEEN 110-110SA1-2CB | 19 | 15 | 15 | Scheduled | 08/07/2024 | 26/07/2024
TO-24-CKN-CGL-1-02 | 110kV FEEDER - CLONKEEN 110-COOMAGEARLAHY 110-1 | 19 | 15 | 15 | Scheduled | 08/07/2024 | 26/07/2024
TO-24-CKN-GRO-1-02 | 110kV FEEDER - CLONKEEN 110-GARROW 110-1 | 19 | 15 | 15 | Scheduled | 08/07/2024 | 26/07/2024
TO-24-CKN-KER-1-02 | 110kV FEEDER - CLONKEEN 110-KNOCKEARAGH 110-1 | 19 | 15 | 15 | Scheduled | 08/07/2024 | 26/07/2024
TO-24-CGL-110SA1-02 | SECTIONALISING DISCONNECT - COOMAGEARLAHY 110-COOMAGEARLAHY 110-110SA1 | 19 | 15 | 15 | Scheduled | 08/07/2024 | 26/07/2024
TO-24-CGL-110SA2-02 | SECTIONALISING DISCONNECT - COOMAGEARLAHY 110-COOMAGEARLAHY 110-110SA2 | 19 | 15 | 15 | Scheduled | 08/07/2024 | 26/07/2024
TO-24-CGL-GAE-1-02 | 110kV FEEDER - COOMAGEARLAHY 110-GLANLEE 110-1 | 19 | 15 | 15 | Scheduled | 08/07/2024 | 26/07/2024
TO-24-CGL-T121-02 | GENERATOR TRANSFORMER - COOMAGEARLAHY 110-COOMAGEARLAHY 20-T121 | 19 | 15 | 15 | Scheduled | 08/07/2024 | 26/07/2024
TO-24-CGL-T122-02 | GENERATOR TRANSFORMER - COOMAGEARLAHY 110-COOMAGEARLAHY 20-T122 | 19 | 15 |  | Scheduled | 08/07/2024 | 26/07/2024
TO-24-CRA-LWD-1-02 | 110kV FEEDER - CRANE 110-LODGEWOOD 110-1 | 5 | 5 | 5 | Scheduled | 08/07/2024 | 12/07/2024
TO-24-CRY-LWD-1-02 | 110kV FEEDER - CRORY 110-LODGEWOOD 110-1 | 5 | 5 | 5 | Reference | 08/07/2024 | 12/07/2024
TO-24-CRY-T121-02 | DISTRIBUTION TRANSFORMER - CRORY 110-CRORY 20-T121 | 5 | 5 | 5 | Reference | 08/07/2024 | 12/07/2024
TO-24-CUL-DGN-1-03 | 110kV FEEDER - CULLENAGH 110-DUNGARVAN 110-1 | 128 | 90 | 90 | Scheduled | 08/07/2024 | 12/11/2024
TO-24-GAE-T121-01 | GENERATOR TRANSFORMER - GLANLEE 110-GLANLEE 20-T121 | 19 | 15 | 15 | Scheduled | 08/07/2024 | 26/07/2024
TO-24-LWD-110SA1-03 | SECTIONALISING DISCONNECT - LODGEWOOD 110-LODGEWOOD 110-110SA1 | 5 | 5 | 5 | Scheduled | 08/07/2024 | 12/07/2024
TO-24-LWD-110SA2-03 | SECTIONALISING DISCONNECT - LODGEWOOD 110-LODGEWOOD 110-110SA2 | 5 | 5 | 5 | Scheduled | 08/07/2024 | 12/07/2024
TO-24-110 kV A2 @ MAY-01 | BUSBAR SECTION - MAYNOOTH 110-MAYNOOTH 110-110A2 | 61 | 44 | 44 | Scheduled | 08/07/2024 | 06/09/2024
TO-24-110 kV A3 @ MAY-03 | BUSBAR SECTION - MAYNOOTH 110-MAYNOOTH 110-110A3 | 61 | 44 | 44 | Scheduled | 08/07/2024 | 06/09/2024
TO-24-110 kV B2 @ MAY-01 | BUSBAR SECTION - MAYNOOTH 110-MAYNOOTH 110-110B2 | 61 | 44 | 44 | Scheduled | 08/07/2024 | 06/09/2024
TO-24-110 kV B3 @ MAY-03 | BUSBAR SECTION - MAYNOOTH 110-MAYNOOTH 110-110B3 | 61 | 44 | 44 | Scheduled | 08/07/2024 | 06/09/2024
TO-24-PB-R2001-03 | CAPACITOR/SVC/REACTOR - POOLBEG 220-POOLBEG 220-R2001 | 5 | 5 | 5 | Scheduled | 08/07/2024 | 12/07/2024
TO-24-SK-T104-01 | GENERATOR TRANSFORMER - SEALROCK 110-SEALROCK G4-T104 | 65 | 46 | 46 | Scheduled | 08/07/2024 | 10/09/2024
TO-24-TAW-T1/T2-01 | GENERATOR TRANSFORMER - TAWNAGHMORE 110-TAWNAGHMORE 10-T1/T2 | 12 | 10 | 10 | Scheduled | 08/07/2024 | 19/07/2024
TO-24-TAW-T3-01 | GENERATOR TRANSFORMER - TAWNAGHMORE 110-TAWNAGHMORE 10-T3 | 12 | 10 | 10 | Scheduled | 08/07/2024 | 19/07/2024
TO-24-DSN-T4202-01 | TRANSFORMER - DUNSTOWN 400-DUNSTOWN 220-T4202 | 1 | 1 | 1 | Scheduled | 10/07/2024 | 10/07/2024
TO-24-KPG-TB-1-07 | 220kV FEEDER - KILPADDOGE 220-TARBERT 220-1 | 26 | 18 | 18 | Scheduled | 10/07/2024 | 04/08/2024
TO-24-PB-T2007/8-03 | GENERATOR TRANSFORMER - POOLBEG 220-POOLBEG G7/8-T2007/8 | 3 | 3 | 3 | Scheduled | 10/07/2024 | 12/07/2024
TO-24-TB-220K1-2-08 | COUPLER/SECTIONALISING CB - TARBERT 220-TARBERT 220-220K1-2 | 26 | 18 | 18 | Scheduled | 10/07/2024 | 04/08/2024
TO-24-TB-T2004-05 | GENERATOR TRANSFORMER - TARBERT 220-TARBERT G4-T2004 | 26 | 18 | 18 | Scheduled | 10/07/2024 | 04/08/2024
TO-24-GAL-GAL GIS-2-02 | 110kV FEEDER - GALWAY 110-GALWAY GIS 110-2 | 174 | 120 | 120 | Scheduled | 11/07/2024 | 31/12/2024
TO-24-GAL-T141-02 | DISTRIBUTION TRANSFORMER - GALWAY 110-GALWAY 38-T141 | 97 | 68 | 68 | Reference | 11/07/2024 | 15/10/2024
TO-24-110 kV A1 @ CAH-03 | BUSBAR SECTION - CAHIR 110-CAHIR 110-110A1 | 5 | 5 | 5 | Scheduled | 15/07/2024 | 19/07/2024
TO-24-110 kV B1 @ CAH-02 | BUSBAR SECTION - CAHIR 110-CAHIR 110-110B1 | 5 | 5 | 5 | Scheduled | 15/07/2024 | 19/07/2024
TO-24-CAH-TIP-1-03 | 110kV FEEDER - CAHIR 110-TIPPERARY 110-1 | 5 | 5 | 5 | Scheduled | 15/07/2024 | 19/07/2024
TO-24-CDK-LWD-1-02 | 110kV FEEDER - CASTLEDOCKRELL 110-LODGEWOOD 110-1 | 9 | 7 | 7 | Scheduled | 15/07/2024 | 23/07/2024
TO-24-CDK-T121-02 | GENERATOR TRANSFORMER - CASTLEDOCKRELL 110-CASTLEDOCKRELL 20-T121 | 9 | 7 | 7 | Reference | 15/07/2024 | 23/07/2024
TO-24-CDY-GRV-1-01 | 110kV FEEDER - CORDERRY 110-GARVAGH 110-1 | 2 | 2 | 2 | Scheduled | 15/07/2024 | 16/07/2024
TO-24-GRO-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - GARROW 110-GARROW 110-110SA1-2CB | 5 | 5 | 5 | Scheduled | 15/07/2024 | 19/07/2024
TO-24-GRO-T122-01 | GENERATOR TRANSFORMER - GARROW 110-GARROW 20-T122 | 5 | 5 | 5 | Scheduled | 15/07/2024 | 19/07/2024
TO-24-GRV-110K1-01 | COUPLER/SECTIONALISING CB - GARVAGH 110-GARVAGH 110-110K1 | 2 | 2 | 2 | Scheduled | 15/07/2024 | 16/07/2024
TO-24-GRV-T121-01 | GENERATOR TRANSFORMER - GARVAGH 110-GARVAGH 20-T121 | 9 | 7 | 7 | Scheduled | 15/07/2024 | 23/07/2024
TO-24-GRV-T141-02 | DISTRIBUTION TRANSFORMER - GARVAGH 110-GARVAGH 20-T141 | 2 | 2 | 2 | Reference | 15/07/2024 | 16/07/2024
TO-24-220 kV A4 @ KPG-02 | BUSBAR SECTION - KILPADDOGE 220-KILPADDOGE 220-220A4 | 5 | 5 | 5 | Scheduled | 15/07/2024 | 19/07/2024
TO-24-220 kV B4 @ KPG-02 | BUSBAR SECTION - KILPADDOGE 220-KILPADDOGE 220-220B4 | 5 | 5 | 5 | Scheduled | 15/07/2024 | 19/07/2024
TO-24-KPG-220K4-03 | COUPLER/SECTIONALISING CB - KILPADDOGE 220-KILPADDOGE 220-220K4 | 5 | 5 | 5 | Scheduled | 15/07/2024 | 19/07/2024
TO-24-KPG-220SA2-4CB-03 | COUPLER/SECTIONALISING CB - KILPADDOGE 220-KILPADDOGE 220-220SA2-4CB | 5 | 5 | 5 | Scheduled | 15/07/2024 | 19/07/2024
TO-24-KPG-220SB2-4CB-02 | COUPLER/SECTIONALISING CB - KILPADDOGE 220-KILPADDOGE 220-220SB2-4CB | 5 | 5 | 5 | Scheduled | 15/07/2024 | 19/07/2024
TO-24-KPG-MP GIS-2-01 | 220kV FEEDER - KILPADDOGE 220-MONEYPOINT GIS 220-2 | 5 | 5 | 5 | Scheduled | 15/07/2024 | 19/07/2024
TO-24-KIN-T101-02 | TSO CUSTOMER TRANSFORMER - KINNEGAD 110-KINNEGAD 10-T101 | 12 | 10 | 10 | Scheduled | 15/07/2024 | 26/07/2024
TO-24-LWD-110SA1-04 | SECTIONALISING DISCONNECT - LODGEWOOD 110-LODGEWOOD 110-110SA1 | 9 | 7 | 7 | Scheduled | 15/07/2024 | 23/07/2024
TO-24-LWD-110SA2-04 | SECTIONALISING DISCONNECT - LODGEWOOD 110-LODGEWOOD 110-110SA2 | 9 | 7 | 7 | Scheduled | 15/07/2024 | 23/07/2024
TO-24-LWD-T2102-02 | TRANSFORMER - LODGEWOOD 220-LODGEWOOD 110-T2102 | 9 | 7 | 7 | Scheduled | 15/07/2024 | 23/07/2024
TO-24-BLC-DND-1-03 | 110kV FEEDER - BELCAMP 110-DARNDALE 110-1 | 4 | 4 | 4 | Scheduled | 16/07/2024 | 19/07/2024
TO-24-KHL-T131-01 | GENERATOR TRANSFORMER - KILL HILL 110-KILL HILL 33-T131 | 1 | 1 | 1 | Scheduled | 16/07/2024 | 16/07/2024
TO-24-CLA-220K1-2-02 | COUPLER/SECTIONALISING CB - CLASHAVOON 220-CLASHAVOON 220-220K1-2 | 45 | 32 | 32 | Scheduled | 17/07/2024 | 30/08/2024
TO-24-DER-TSB-1-05 | 110kV FEEDER - DERRYIRON 110-THORNSBERRY 110-1 | 3 | 3 |  | Scheduled | 17/07/2024 | 19/07/2024
TO-24-TSB-110SA1-02 | SECTIONALISING DISCONNECT - THORNSBERRY 110-THORNSBERRY 110-110SA1 | 3 | 3 | 3 | Scheduled | 17/07/2024 | 19/07/2024
TO-24-TSB-110SA2-02 | SECTIONALISING DISCONNECT - THORNSBERRY 110-THORNSBERRY 110-110SA2 | 3 | 3 | 3 | Scheduled | 17/07/2024 | 19/07/2024
TO-24-TSB-T142-02 | DISTRIBUTION TRANSFORMER - THORNSBERRY 110-THORNSBERRY 38-T142 | 3 | 3 | 3 | Reference | 17/07/2024 | 19/07/2024
TO-24-TSB-TEN-1-01 | 110kV FEEDER - THORNSBERRY 110-TIMAHOE 110-1 | 3 | 3 | 3 | Scheduled | 17/07/2024 | 19/07/2024
TO-24-OBE-T121-01 | TSO CUSTOMER TRANSFORMER - OLDBRIDGE 110-OLDBRIDGE 20-T121 | 2 | 2 | 2 | Scheduled | 18/07/2024 | 19/07/2024
TO-24-220 kV B2/B4 @ CSH-01 | BUSBAR SECTION - CASHLA 220-CASHLA 220-220B2-B4 | 1 | 1 |  | Scheduled | 19/07/2024 | 19/07/2024
TO-24-CSH-PRO-1-04 | 220kV FEEDER - CASHLA 220-PROSPECT 220-1 | 1 | 1 |  | Scheduled | 19/07/2024 | 19/07/2024
TO-24-CKM GIS-DSN-1-06 | 220kV FEEDER - CARRICKMINES GIS 220-DUNSTOWN 220-1 | 2 | 0 | 0 | Scheduled | 20/07/2024 | 21/07/2024
TO-24-KIN-MUL-1-01 | 110kV FEEDER - KINNEGAD 110-MULLINGAR 110-1 | 2 | 0 | 0 | Scheduled | 20/07/2024 | 21/07/2024
TO-24-LA-MUL-1-02 | 110kV FEEDER - LANESBORO 110-MULLINGAR 110-1 | 2 | 0 | 0 | Scheduled | 20/07/2024 | 21/07/2024
TO-24-MUL-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - MULLINGAR 110-MULLINGAR 110-110SA1-2CB | 2 | 0 | 0 | Scheduled | 20/07/2024 | 21/07/2024
TO-24-MUL-T101-01 | DISTRIBUTION TRANSFORMER - MULLINGAR 110-MULLINGAR 10-T101 | 2 | 0 | 0 | Reference | 20/07/2024 | 21/07/2024
TO-24-MUL-T141-01 | DISTRIBUTION TRANSFORMER - MULLINGAR 110-MULLINGAR 38-T141 | 2 | 0 | 0 | Reference | 20/07/2024 | 21/07/2024
TO-24-ARV-NAV-1-05 | 110kV FEEDER - ARVA 110-NAVAN 110-1 | 1 | 1 | 1 | Scheduled | 22/07/2024 | 22/07/2024
TO-24-BK-CBR-1-03 | 110kV FEEDER - BELLACORICK 110-CASTLEBAR 110-1 | 10 | 8 | 8 | Scheduled | 22/07/2024 | 31/07/2024
TO-24-DEY-T132-01 | GENERATOR TRANSFORMER - DERRYCARNEY 110-DERRYCARNEY 33-T132 | 2 | 2 | 2 | Scheduled | 22/07/2024 | 23/07/2024
TO-24-GOR-NAV-2-06 | 110kV FEEDER - GORMAN 110-NAVAN 110-2 | 1 | 1 | 1 | Scheduled | 22/07/2024 | 22/07/2024
TO-24-LOU-AT2-01 | TRANSFORMER - LOUTH 220-LOUTH 275-AT2 | 5 | 5 | 5 | Scheduled | 22/07/2024 | 26/07/2024
TO-24-LOU-TAN-2-01 | 275kV FEEDER - LOUTH 275-TANDRAGEE 275-2 | 5 | 5 | 5 | Scheduled | 22/07/2024 | 26/07/2024
TO-24-NAV-110SA1-2CB-03 | COUPLER/SECTIONALISING CB - NAVAN 110-NAVAN 110-110SA1-2CB | 1 | 1 | 1 | Scheduled | 22/07/2024 | 22/07/2024
TO-24-NAV-M/CAP1-02 | CAPACITOR/SVC/REACTOR - NAVAN 110-NAVAN 110-M/CAP1 | 1 | 1 | 1 | Scheduled | 22/07/2024 | 22/07/2024
TO-24-NAV-T141-03 | DISTRIBUTION TRANSFORMER - NAVAN 110-NAVAN 38-T141 | 1 | 1 | 1 | Reference | 22/07/2024 | 22/07/2024
TO-24-RAF-T2102-01 | TRANSFORMER - RAFFEEN 220-RAFFEEN 110-T2102 | 8 | 6 | 6 | Scheduled | 22/07/2024 | 29/07/2024
TO-24-WHI-CKB-T101-01 | TSO CUSTOMER TRANSFORMER - WHITEGATE 110-WHITEGATE 10-CKB-T101 | 5 | 5 | 5 | Scheduled | 22/07/2024 | 26/07/2024
TO-24-BLC-DND-3-01 | 110kV FEEDER - BELCAMP 110-DARNDALE 110-3 | 4 | 4 | 4 | Scheduled | 23/07/2024 | 26/07/2024
TO-24-TON-T142-02 | DISTRIBUTION TRANSFORMER - TONROE 110-TONROE 38-T142 | 2 | 2 | 2 | Reference | 23/07/2024 | 24/07/2024
TO-24-CRA-LWD-1-03 | 110kV FEEDER - CRANE 110-LODGEWOOD 110-1 | 7 | 5 | 5 | Scheduled | 24/07/2024 | 30/07/2024
TO-24-CRY-LWD-1-03 | 110kV FEEDER - CRORY 110-LODGEWOOD 110-1 | 7 | 5 | 5 | Reference | 24/07/2024 | 30/07/2024
TO-24-CRY-T121-03 | DISTRIBUTION TRANSFORMER - CRORY 110-CRORY 20-T121 | 7 | 5 | 5 | Reference | 24/07/2024 | 30/07/2024
TO-24-LWD-110SA1-05 | SECTIONALISING DISCONNECT - LODGEWOOD 110-LODGEWOOD 110-110SA1 | 7 | 5 | 5 | Scheduled | 24/07/2024 | 30/07/2024
TO-24-LWD-110SA2-05 | SECTIONALISING DISCONNECT - LODGEWOOD 110-LODGEWOOD 110-110SA2 | 7 | 5 | 5 | Scheduled | 24/07/2024 | 30/07/2024
TO-24-CSH-T2101-01 | TRANSFORMER - CASHLA 220-CASHLA 110-T2101 | 75 | 52 | 52 | Scheduled | 25/07/2024 | 07/10/2024
TO-24-220 kV A2 @ FIN-05 | BUSBAR SECTION - FINGLAS 220-FINGLAS 220-220A2 | 9 | 7 | 7 | Scheduled | 25/07/2024 | 02/08/2024
TO-24-KPG-TB-1-03 | 220kV FEEDER - KILPADDOGE 220-TARBERT 220-1 | 2 | 2 | 2 | Scheduled | 25/07/2024 | 26/07/2024
TO-24-TB-220K1-2-03 | COUPLER/SECTIONALISING CB - TARBERT 220-TARBERT 220-220K1-2 | 2 | 2 | 2 | Scheduled | 25/07/2024 | 26/07/2024
TO-24-TB-T2004-03 | GENERATOR TRANSFORMER - TARBERT 220-TARBERT G4-T2004 | 2 | 2 | 2 | Scheduled | 25/07/2024 | 26/07/2024
TO-24-CKM GIS-DSN-1-07 | 220kV FEEDER - CARRICKMINES GIS 220-DUNSTOWN 220-1 | 2 | 0 | 0 | Scheduled | 27/07/2024 | 28/07/2024
TO-24-CBA-110SA1-02 | SECTIONALISING DISCONNECT - CLOGHBOOLA 110-CLOGHBOOLA 110-110SA1 | 5 | 5 | 5 | Scheduled | 29/07/2024 | 02/08/2024
TO-24-CBA-110SA2-02 | SECTIONALISING DISCONNECT - CLOGHBOOLA 110-CLOGHBOOLA 110-110SA2 | 5 | 5 | 5 | Scheduled | 29/07/2024 | 02/08/2024
TO-24-CBA-T122-01 | DISTRIBUTION TRANSFORMER - CLOGHBOOLA 110-CLOGHBOOLA 20-T122 | 5 | 5 | 5 | Reference | 29/07/2024 | 02/08/2024
TO-24-CBA-T131-01 | GENERATOR TRANSFORMER - CLOGHBOOLA 110-CLOGHBOOLA 33-T131 | 5 | 5 | 5 | Scheduled | 29/07/2024 | 02/08/2024
TO-24-CBA-TRI-1-01 | 110kV FEEDER - CLOGHBOOLA 110-TRIEN 110-1 | 5 | 5 |  | Scheduled | 29/07/2024 | 02/08/2024
TO-24-110 kV A1 @ FLA-06 | BUSBAR SECTION - FLAGFORD 110-FLAGFORD 110-110A1 | 5 | 5 | 5 | Scheduled | 29/07/2024 | 02/08/2024
TO-24-110 kV B1 @ FLA-07 | BUSBAR SECTION - FLAGFORD 110-FLAGFORD 110-110B1 | 5 | 5 | 5 | Scheduled | 29/07/2024 | 02/08/2024
TO-24-FLA-GIL-1-01 | 110kV FEEDER - FLAGFORD 110-GILRA 110-1 | 5 | 5 | 5 | Scheduled | 29/07/2024 | 02/08/2024
TO-24-GIL-T121-02 | TSO CUSTOMER TRANSFORMER - GILRA 110-GILRA 20-T121 | 5 | 5 | 5 | Reference | 29/07/2024 | 02/08/2024
TO-24-WHI-CKB-T102-01 | TSO CUSTOMER TRANSFORMER - WHITEGATE 110-WHITEGATE 10-CKB-T102 | 10 | 7 | 7 | Scheduled | 29/07/2024 | 07/08/2024
TO-24-AD-KRA-1-04 | 220kV FEEDER - AGHADA 220-KNOCKRAHA 220-1 | 3 | 3 | 3 | Proposed | 30/07/2024 | 01/08/2024
TO-24-BNK-CBT-1-01 | 110kV FEEDER - BARNAKYLE 110-CASTLEBAGOT 110-1 | 2 | 2 | 2 | Scheduled | 30/07/2024 | 31/07/2024
TO-24-GOR-MTH-1-03 | 110kV FEEDER - GORMAN 110-MEATH HILL 110-1 | 3 | 3 | 3 | Scheduled | 30/07/2024 | 01/08/2024
TO-24-CDK-LWD-1-03 | 110kV FEEDER - CASTLEDOCKRELL 110-LODGEWOOD 110-1 | 8 | 5 | 5 | Scheduled | 31/07/2024 | 07/08/2024
TO-24-CDK-T121-03 | GENERATOR TRANSFORMER - CASTLEDOCKRELL 110-CASTLEDOCKRELL 20-T121 | 8 | 5 | 5 | Reference | 31/07/2024 | 07/08/2024
TO-24-KNR-T2101-02 | TRANSFORMER - KNOCKANURE 220-KNOCKANURE 110-T2101 | 2 | 2 | 2 | Scheduled | 31/07/2024 | 01/08/2024
TO-24-LWD-110SA1-06 | SECTIONALISING DISCONNECT - LODGEWOOD 110-LODGEWOOD 110-110SA1 | 8 | 5 | 5 | Scheduled | 31/07/2024 | 07/08/2024
TO-24-LWD-110SA2-06 | SECTIONALISING DISCONNECT - LODGEWOOD 110-LODGEWOOD 110-110SA2 | 8 | 5 | 5 | Scheduled | 31/07/2024 | 07/08/2024
TO-24-LWD-T2102-03 | TRANSFORMER - LODGEWOOD 220-LODGEWOOD 110-T2102 | 8 | 5 | 5 | Scheduled | 31/07/2024 | 07/08/2024
TO-24-PLA-T101/2/3/4-05 | TSO CUSTOMER TRANSFORMER - PLATIN 110-PLATIN 10-T101/2/3/4 | 9 | 6 | 6 | Scheduled | 31/07/2024 | 08/08/2024
TO-24-TSB-TEN-1-03 | 110kV FEEDER - THORNSBERRY 110-TIMAHOE 110-1 | 9 | 6 | 6 | Scheduled | 01/08/2024 | 09/08/2024
TO-24-CKM GIS-DSN-1-08 | 220kV FEEDER - CARRICKMINES GIS 220-DUNSTOWN 220-1 | 2 | 0 | 0 | Scheduled | 03/08/2024 | 04/08/2024
TO-24-KPG-TB-1-04 | 220kV FEEDER - KILPADDOGE 220-TARBERT 220-1 | 4 | 3 |  | Scheduled | 05/08/2024 | 08/08/2024
TO-24-TB-220K1-2-04 | COUPLER/SECTIONALISING CB - TARBERT 220-TARBERT 220-220K1-2 | 4 | 3 |  | Scheduled | 05/08/2024 | 08/08/2024
TO-24-TB-T2004-04 | GENERATOR TRANSFORMER - TARBERT 220-TARBERT G4-T2004 | 4 | 3 |  | Scheduled | 05/08/2024 | 08/08/2024
TO-24-BVK-T2102-02 | TRANSFORMER - BALLYVOUSKILL 220-BALLYVOUSKILL 110-T2102 | 2 | 2 | 2 | Scheduled | 06/08/2024 | 07/08/2024
TO-24-CBR-CLN-1-04 | 110kV FEEDER - CASTLEBAR 110-CLOON 110-1 | 4 | 4 | 4 | Scheduled | 06/08/2024 | 09/08/2024
TO-24-CUS-T101-01 | GENERATOR TRANSFORMER - CUSHALING 110-CUSHALING G1-T101 | 17 | 13 | 13 | Scheduled | 06/08/2024 | 22/08/2024
TO-24-LSN-110SA1-2-03 | SECTIONALISING DISCONNECT - LISHEEN 110-LISHEEN 110-110SA1-2 | 11 | 9 | 9 | Scheduled | 06/08/2024 | 16/08/2024
TO-24-LSN-110SA2-4-03 | SECTIONALISING DISCONNECT - LISHEEN 110-LISHEEN 110-110SA2-4 | 11 | 9 | 9 | Scheduled | 06/08/2024 | 16/08/2024
TO-24-LSN-T122-03 | GENERATOR TRANSFORMER - LISHEEN 110-LISHEEN 20-T122 | 11 | 9 | 9 | Scheduled | 06/08/2024 | 16/08/2024
TO-24-LSN-T131-03 | GENERATOR TRANSFORMER - LISHEEN 110-LISHEEN 33-T131 | 11 | 9 | 9 | Scheduled | 06/08/2024 | 16/08/2024
TO-24-LSN-T142-02 | DISTRIBUTION TRANSFORMER - LISHEEN 110-LISHEEN 38-T142 | 11 | 9 | 9 | Reference | 06/08/2024 | 16/08/2024
TO-24-LSN-THU-1-03 | 110kV FEEDER - LISHEEN 110-THURLES 110-1 | 11 | 9 | 9 | Scheduled | 06/08/2024 | 16/08/2024
TO-24-MLN-T124-02 | TSO CUSTOMER TRANSFORMER - MULLAGHARLIN 110-MULLAGHARLIN 20-T124 | 2 | 2 | 2 | Scheduled | 06/08/2024 | 07/08/2024
TO-24-110 kV A2 @ DEY-01 | BUSBAR SECTION - DERRYCARNEY 110-DERRYCARNEY 110-110A2 | 17 | 13 | 13 | Scheduled | 07/08/2024 | 23/08/2024
TO-24-110 kV B2 @ DEY-01 | BUSBAR SECTION - DERRYCARNEY 110-DERRYCARNEY 110-110B2 | 17 | 13 | 13 | Scheduled | 07/08/2024 | 23/08/2024
TO-24-DEY-110K2-03 | COUPLER/SECTIONALISING CB - DERRYCARNEY 110-DERRYCARNEY 110-110K2 | 17 | 13 | 13 | Scheduled | 07/08/2024 | 23/08/2024
TO-24-REM-110SA1-01 | SECTIONALISING DISCONNECT - REAMORE 110-REAMORE 110-110SA1 | 22 | 16 | 16 | Scheduled | 07/08/2024 | 28/08/2024
TO-24-REM-110SA2-01 | SECTIONALISING DISCONNECT - REAMORE 110-REAMORE 110-110SA2 | 22 | 16 | 16 | Scheduled | 07/08/2024 | 28/08/2024
TO-24-REM-T141-01 | DISTRIBUTION TRANSFORMER - REAMORE 110-REAMORE 38-T141 | 22 | 16 | 16 | Reference | 07/08/2024 | 28/08/2024
TO-24-REM-T142-01 | DISTRIBUTION TRANSFORMER - REAMORE 110-REAMORE 38-T142 | 22 | 16 | 16 | Reference | 07/08/2024 | 28/08/2024
TO-24-REM-TRL-1-01 | 110kV FEEDER - REAMORE 110-TRALEE 110-1 | 22 | 16 | 16 | Scheduled | 07/08/2024 | 28/08/2024
TO-24-BLU-CDU-1-01 | 110kV FEEDER - BLUNDELSTOWN 110-CORDUFF 110-1 | 58 | 42 | 42 | Scheduled | 08/08/2024 | 04/10/2024
TO-24-MLN-T123-03 | TSO CUSTOMER TRANSFORMER - MULLAGHARLIN 110-MULLAGHARLIN 20-T123 | 2 | 2 | 2 | Scheduled | 08/08/2024 | 09/08/2024
TO-24-GAR-T131-02 | GENERATOR TRANSFORMER - GARBALLAGH 110-GARBALLAGH 33-T131 | 1 | 1 | 1 | Scheduled | 09/08/2024 | 09/08/2024
TO-24-KPG-TB-1-08 | 220kV FEEDER - KILPADDOGE 220-TARBERT 220-1 | 73 | 51 | 51 | Scheduled | 09/08/2024 | 20/10/2024
TO-24-TB-220K1-2-09 | COUPLER/SECTIONALISING CB - TARBERT 220-TARBERT 220-220K1-2 | 67 | 47 | 47 | Scheduled | 09/08/2024 | 14/10/2024
TO-24-TB-T2004-06 | GENERATOR TRANSFORMER - TARBERT 220-TARBERT G4-T2004 | 67 | 47 | 47 | Scheduled | 09/08/2024 | 14/10/2024
TO-24-ISH-T2001-01 | GENERATOR TRANSFORMER - IRISHTOWN 220-IRISHTOWN G1-T2001 | 20 | 15 | 15 | Scheduled | 11/08/2024 | 30/08/2024
TO-24-BYH-BVK-1-02 | 220kV FEEDER - BALLYNAHULLA 220-BALLYVOUSKILL 220-1 | 12 | 10 | 10 | Scheduled | 12/08/2024 | 23/08/2024
TO-24-220 kV A2 @ BVK-03 | BUSBAR SECTION - BALLYVOUSKILL 220-BALLYVOUSKILL 220-220A2 | 12 | 10 | 10 | Scheduled | 12/08/2024 | 23/08/2024
TO-24-220 kV B2 @ BVK-03 | BUSBAR SECTION - BALLYVOUSKILL 220-BALLYVOUSKILL 220-220B2 | 12 | 10 | 10 | Scheduled | 12/08/2024 | 23/08/2024
TO-24-BVK-220K2-06 | COUPLER/SECTIONALISING CB - BALLYVOUSKILL 220-BALLYVOUSKILL 220-220K2 | 12 | 10 | 10 | Scheduled | 12/08/2024 | 23/08/2024
TO-24-BVK-220SA1-2CB-04 | COUPLER/SECTIONALISING CB - BALLYVOUSKILL 220-BALLYVOUSKILL 220-220SA1-2CB | 12 | 10 | 10 | Scheduled | 12/08/2024 | 23/08/2024
TO-24-BVK-220SB1-2CB-04 | COUPLER/SECTIONALISING CB - BALLYVOUSKILL 220-BALLYVOUSKILL 220-220SB1-2CB | 12 | 10 | 10 | Scheduled | 12/08/2024 | 23/08/2024
TO-24-CRA-LWD-1-04 | 110kV FEEDER - CRANE 110-LODGEWOOD 110-1 | 5 | 5 | 5 | Scheduled | 12/08/2024 | 16/08/2024
TO-24-CRY-LWD-1-04 | 110kV FEEDER - CRORY 110-LODGEWOOD 110-1 | 5 | 5 | 5 | Reference | 12/08/2024 | 16/08/2024
TO-24-CRY-T121-04 | DISTRIBUTION TRANSFORMER - CRORY 110-CRORY 20-T121 | 5 | 5 | 5 | Reference | 12/08/2024 | 16/08/2024
TO-24-DRU-T141-01 | DISTRIBUTION TRANSFORMER - DRUMLINE 110-DRUMLINE 38-T141 | 85 | 60 |  | Reference | 12/08/2024 | 04/11/2024
TO-24-DRY-LOU-1-01 | 110kV FEEDER - DRYBRIDGE 110-LOUTH 110-1 | 5 | 5 | 5 | Scheduled | 12/08/2024 | 16/08/2024
TO-24-LWD-110SA1-07 | SECTIONALISING DISCONNECT - LODGEWOOD 110-LODGEWOOD 110-110SA1 | 5 | 5 | 5 | Scheduled | 12/08/2024 | 16/08/2024
TO-24-LWD-110SA2-07 | SECTIONALISING DISCONNECT - LODGEWOOD 110-LODGEWOOD 110-110SA2 | 5 | 5 |  | Scheduled | 12/08/2024 | 16/08/2024
TO-24-LOU-110K1-2-01 | COUPLER/SECTIONALISING CB - LOUTH 110-LOUTH 110-110K1-2 | 5 | 5 |  | Scheduled | 12/08/2024 | 16/08/2024
TO-24-LOU-CAP1-03 | CAPACITOR/SVC/REACTOR - LOUTH 110-LOUTH 110-CAP1 | 5 | 5 | 5 | Scheduled | 12/08/2024 | 16/08/2024
TO-24-LOU-T2101-01 | TRANSFORMER - LOUTH 220-LOUTH 110-T2101 | 5 | 5 |  | Scheduled | 12/08/2024 | 16/08/2024
TO-24-LOU-T2103-01 | TRANSFORMER - LOUTH 220-LOUTH 110-T2103 | 5 | 5 |  | Scheduled | 12/08/2024 | 16/08/2024
TO-24-220 kV A2 @ BYH-03 | BUSBAR SECTION - BALLYNAHULLA 220-BALLYNAHULLA 220-220A2 | 11 | 9 | 9 | Scheduled | 13/08/2024 | 23/08/2024
TO-24-220 kV B2 @ BYH-03 | BUSBAR SECTION - BALLYNAHULLA 220-BALLYNAHULLA 220-220B2 | 11 | 9 | 9 | Scheduled | 13/08/2024 | 23/08/2024
TO-24-BYH-220K2-04 | COUPLER/SECTIONALISING CB - BALLYNAHULLA 220-BALLYNAHULLA 220-220K2 | 11 | 9 | 9 | Scheduled | 13/08/2024 | 23/08/2024
TO-24-BYH-220SA1-2CB-05 | COUPLER/SECTIONALISING CB - BALLYNAHULLA 220-BALLYNAHULLA 220-220SA1-2CB | 11 | 9 | 9 | Scheduled | 13/08/2024 | 23/08/2024
TO-24-BYH-220SB1-2CB-06 | COUPLER/SECTIONALISING CB - BALLYNAHULLA 220-BALLYNAHULLA 220-220SB1-2CB | 11 | 9 | 9 | Scheduled | 13/08/2024 | 23/08/2024
TO-24-CUN-110SA1-03 | SECTIONALISING DISCONNECT - CUNGHILL 110-CUNGHILL 110-110SA1 | 3 | 3 | 3 | Scheduled | 13/08/2024 | 15/08/2024
TO-24-CUN-110SA2-01 | SECTIONALISING DISCONNECT - CUNGHILL 110-CUNGHILL 110-110SA2 | 3 | 3 | 3 | Scheduled | 13/08/2024 | 15/08/2024
TO-24-CUN-SLI-1-03 | 110kV FEEDER - CUNGHILL 110-SLIGO 110-1 | 3 | 3 | 3 | Scheduled | 13/08/2024 | 15/08/2024
TO-24-CUN-T121-02 | GENERATOR TRANSFORMER - CUNGHILL 110-CUNGHILL 20-T121 | 3 | 3 | 3 | Scheduled | 13/08/2024 | 15/08/2024
TO-24-BAN-DMY-1-03 | 110kV FEEDER - BANDON 110-DUNMANWAY 110-1 | 3 | 3 | 3 | Scheduled | 14/08/2024 | 16/08/2024
TO-24-BOL-110SA1-3CB-02 | COUPLER/SECTIONALISING CB - BOOLTIAGH 110-BOOLTIAGH 110-110SA1-3CB | 2 | 2 | 33 | Proposed | 14/08/2024 | 15/08/2024
TO-24-BOL-ENN-1-02 | 110kV FEEDER - BOOLTIAGH 110-ENNIS 110-1 | 2 | 2 | 2 | Proposed | 14/08/2024 | 15/08/2024
TO-24-BOL-T143-02 | DISTRIBUTION TRANSFORMER - BOOLTIAGH 110-BOOLTIAGH 38-T143 | 2 | 2 | 2 | Reference (Proposed) | 14/08/2024 | 15/08/2024
TO-24-AUN-CBT-3-01 | 110kV FEEDER - AUNGIERSTOWN 110-CASTLEBAGOT 110-3 | 99 | 70 |  | Scheduled | 15/08/2024 | 21/11/2024
TO-24-GAR-T131-03 | GENERATOR TRANSFORMER - GARBALLAGH 110-GARBALLAGH 33-T131 | 1 | 1 | 1 | Scheduled | 15/08/2024 | 15/08/2024
TO-24-110 kV A1 @ ARV-02 | BUSBAR SECTION - ARVA 110-ARVA 110-110A1 | 5 | 5 | 5 | Scheduled | 19/08/2024 | 23/08/2024
TO-24-110 kV A2 @ ARV-01 | BUSBAR SECTION - ARVA 110-ARVA 110-110A2 | 5 | 5 | 5 | Scheduled | 19/08/2024 | 23/08/2024
TO-24-110 kV B1 @ ARV-01 | BUSBAR SECTION - ARVA 110-ARVA 110-110B1 | 5 | 5 | 5 | Scheduled | 19/08/2024 | 23/08/2024
TO-24-110 kV B2 @ ARV-01 | BUSBAR SECTION - ARVA 110-ARVA 110-110B2 | 5 | 5 | 5 | Scheduled | 19/08/2024 | 23/08/2024
TO-24-ARV-110K1-2-01 | COUPLER/SECTIONALISING CB - ARVA 110-ARVA 110-110K1-2 | 5 | 5 | 5 | Scheduled | 19/08/2024 | 23/08/2024
TO-24-BAN-RAF-1-02 | 110kV FEEDER - BANDON 110-RAFFEEN 110-1 | 5 | 5 | 5 | Scheduled | 19/08/2024 | 23/08/2024
TO-24-BGH-110SA1-01 | SECTIONALISING DISCONNECT - BOGGERAGH 110-BOGGERAGH 110-110SA1 | 12 | 10 | 10 | Scheduled | 19/08/2024 | 30/08/2024
TO-24-BGH-110SA2-01 | SECTIONALISING DISCONNECT - BOGGERAGH 110-BOGGERAGH 110-110SA2 | 12 | 10 | 10 | Scheduled | 19/08/2024 | 30/08/2024
TO-24-BGH-CLA-1-01 | 110kV FEEDER - BOGGERAGH 110-CLASHAVOON 110-1 | 12 | 10 | 10 | Scheduled | 19/08/2024 | 30/08/2024
TO-24-BGH-T121-01 | GENERATOR TRANSFORMER - BOGGERAGH 110-BOGGERAGH 20-T121 | 12 | 10 | 10 | Scheduled | 19/08/2024 | 30/08/2024
TO-24-BGH-T132-01 | GENERATOR TRANSFORMER - BOGGERAGH 110-BOGGERAGH 33-T132 | 12 | 10 | 10 | Scheduled | 19/08/2024 | 30/08/2024
TO-24-BGH-T142-01 | DISTRIBUTION TRANSFORMER - BOGGERAGH 110-BOGGERAGH 38-T142 | 12 | 10 | 10 | Reference | 19/08/2024 | 30/08/2024
TO-24-BOL-110SA1-3CB-03 | COUPLER/SECTIONALISING CB - BOOLTIAGH 110-BOOLTIAGH 110-110SA1-3CB | 12 | 10 | 10 | Scheduled | 19/08/2024 | 30/08/2024
TO-24-BOL-T121-01 | GENERATOR TRANSFORMER - BOOLTIAGH 110-BOOLTIAGH 20-T121 | 12 | 10 | 10 | Scheduled | 19/08/2024 | 30/08/2024
TO-24-CDK-LWD-1-04 | 110kV FEEDER - CASTLEDOCKRELL 110-LODGEWOOD 110-1 | 19 | 15 |  | Scheduled | 19/08/2024 | 06/09/2024
TO-24-CDK-T121-04 | GENERATOR TRANSFORMER - CASTLEDOCKRELL 110-CASTLEDOCKRELL 20-T121 | 19 | 15 |  | Reference | 19/08/2024 | 06/09/2024
TO-24-110 kV A1 @ CLA-01 | BUSBAR SECTION - CLASHAVOON 110-CLASHAVOON 110-110A1 | 12 | 10 | 10 | Scheduled | 19/08/2024 | 30/08/2024
TO-24-110 kV B1 @ CLA-01 | BUSBAR SECTION - CLASHAVOON 110-CLASHAVOON 110-110B1 | 12 | 10 | 10 | Scheduled | 19/08/2024 | 30/08/2024
TO-24-CDU-220SB2-4-02 | SECTIONALISING DISCONNECT - CORDUFF 220-CORDUFF 220-220SB2-4 | 3 | 3 |  | Scheduled | 19/08/2024 | 21/08/2024
TO-24-GOL-T101-03 | GENERATOR TRANSFORMER - GOLAGH 110-GOLAGH 10-T101 | 4 | 4 | 4 | Scheduled | 19/08/2024 | 22/08/2024
TO-24-110 kV A2 @ GOR-01 | BUSBAR SECTION - GORMAN 110-GORMAN 110-110A2 | 1 | 1 | 1 | Scheduled | 19/08/2024 | 19/08/2024
TO-24-GOR-MTH-1-01 | 110kV FEEDER - GORMAN 110-MEATH HILL 110-1 | 1 | 1 | 1 | Scheduled | 19/08/2024 | 19/08/2024
TO-24-KHL-THU-1-01 | 110kV FEEDER - KILL HILL 110-THURLES 110-1 | 9 | 7 | 7 | Scheduled | 19/08/2024 | 27/08/2024
TO-24-LWD-110SA1-08 | SECTIONALISING DISCONNECT - LODGEWOOD 110-LODGEWOOD 110-110SA1 | 19 | 15 |  | Scheduled | 19/08/2024 | 06/09/2024
TO-24-LWD-110SA2-08 | SECTIONALISING DISCONNECT - LODGEWOOD 110-LODGEWOOD 110-110SA2 | 19 | 15 |  | Scheduled | 19/08/2024 | 06/09/2024
TO-24-LWD-T2102-06 | TRANSFORMER - LODGEWOOD 220-LODGEWOOD 110-T2102 | 19 | 15 |  | Scheduled | 19/08/2024 | 06/09/2024
TO-24-RNW-T122-01 | TSO CUSTOMER TRANSFORMER - RINAWADE 110-RINAWADE 20-T122 | 5 | 5 | 5 | Proposed | 19/08/2024 | 23/08/2024
TO-24-TBK-T141-01 | DISTRIBUTION TRANSFORMER - TULLABRACK 110-TULLABRACK 38-T141 | 12 | 10 | 10 | Reference | 19/08/2024 | 30/08/2024
TO-24-TBK,T-BOL-1-01 | 110kV FEEDER - TULLABRACK tee-BOOLTIAGH 110-1 | 12 | 10 | 10 | Scheduled | 19/08/2024 | 30/08/2024
TO-24-TBK,T-MP GIS-1-01 | 110kV FEEDER - TULLABRACK tee-MONEYPOINT GIS 110-1 | 12 | 10 | 10 | Scheduled | 19/08/2024 | 30/08/2024
TO-24-TBK,T-TBK-1-01 | 110kV FEEDER - TULLABRACK tee-TULLABRACK 110-1 | 12 | 10 | 10 | Scheduled | 19/08/2024 | 30/08/2024
TO-24-UGL-T131-02 | GENERATOR TRANSFORMER - UGGOOL 110-UGGOOL 33-T131 | 5 | 5 | 5 | Scheduled | 19/08/2024 | 23/08/2024
TO-24-UGL-T132-04 | GENERATOR TRANSFORMER - UGGOOL 110-UGGOOL 33-T132 | 10 | 8 | 8 | Scheduled | 19/08/2024 | 28/08/2024
TO-24-UGL-T134-03 | GENERATOR TRANSFORMER - UGGOOL 110-UGGOOL 33-T134 | 10 | 8 | 8 | Scheduled | 19/08/2024 | 28/08/2024
TO-24-220 kV A1 @ AD-06 | BUSBAR SECTION - AGHADA 220-AGHADA 220-220A1 | 1 | 1 | 1 | Proposed | 20/08/2024 | 20/08/2024
TO-24-AD-T2011/12-06 | GENERATOR TRANSFORMER - AGHADA 220-AGHADA G11/12-T2011/12 | 1 | 1 | 1 | Proposed | 20/08/2024 | 20/08/2024
TO-24-DAL-T141-06 | DISTRIBUTION TRANSFORMER - DALLOW 110-DALLOW 38-T141 | 16 | 12 | 12 | Reference | 20/08/2024 | 04/09/2024
TO-24-DAL,T-DAL-1-08 | 110kV FEEDER - DALLOW tee-DALLOW 110-1 | 16 | 12 | 12 | Scheduled | 20/08/2024 | 04/09/2024
TO-24-DAL,T-SH-1-10 | 110kV FEEDER - DALLOW tee-SHANNONBRIDGE 110-1 | 16 | 12 | 12 | Scheduled | 20/08/2024 | 04/09/2024
TO-24-GOR-NAV-1-01 | 110kV FEEDER - GORMAN 110-NAVAN 110-1 | 70 | 49 | 49 | Scheduled | 20/08/2024 | 28/10/2024
TO-24-220 kV A6 @ INC-01 | BUSBAR SECTION - INCHICORE 220-INCHICORE 220-220A6 | 4 | 4 | 4 | Scheduled | 20/08/2024 | 23/08/2024
TO-24-220 kV B6 @ INC-01 | BUSBAR SECTION - INCHICORE 220-INCHICORE 220-220B6 | 4 | 4 | 4 | Scheduled | 20/08/2024 | 23/08/2024
TO-24-INC-T2106-02 | TRANSFORMER - INCHICORE 220-INCHICORE 110-T2106 | 4 | 4 | 4 | Reference | 20/08/2024 | 23/08/2024
TO-24-110 kV A2 @ SH-05 | BUSBAR SECTION - SHANNONBRIDGE 110-SHANNONBRIDGE 110-110A2 | 1 | 1 | 1 | Scheduled | 20/08/2024 | 20/08/2024
TO-24-110 kV B2 @ SH-05 | BUSBAR SECTION - SHANNONBRIDGE 110-SHANNONBRIDGE 110-110B2 | 1 | 1 | 1 | Scheduled | 20/08/2024 | 20/08/2024
TO-24-220 kV A1 @ AD-05 | BUSBAR SECTION - AGHADA 220-AGHADA 220-220A1 | 8 | 6 | 6 | Scheduled | 21/08/2024 | 28/08/2024
TO-24-220 kV B1 @ AD-04 | BUSBAR SECTION - AGHADA 220-AGHADA 220-220B1 | 8 | 6 | 6 | Scheduled | 21/08/2024 | 28/08/2024
TO-24-AD-220K1-06 | COUPLER/SECTIONALISING CB - AGHADA 220-AGHADA 220-220K1 | 8 | 6 | 6 | Scheduled | 21/08/2024 | 28/08/2024
TO-24-AD-SA1-2CB-08 | COUPLER/SECTIONALISING CB - AGHADA 220-AGHADA 220-220SA1-2CB | 8 | 6 | 6 | Scheduled | 21/08/2024 | 28/08/2024
TO-24-AD-SB1-2CB-08 | COUPLER/SECTIONALISING CB - AGHADA 220-AGHADA 220-220SB1-2CB | 8 | 6 | 6 | Scheduled | 21/08/2024 | 28/08/2024
TO-24-AD-T2011/12-02 | GENERATOR TRANSFORMER - AGHADA 220-AGHADA G11/12-T2011/12 | 8 | 6 | 6 | Scheduled | 21/08/2024 | 28/08/2024
TO-24-AD-T2014-02 | GENERATOR TRANSFORMER - AGHADA 220-AGHADA G14-T2014 | 8 | 6 | 6 | Scheduled | 21/08/2024 | 28/08/2024
TO-24-110 kV B1 @ CF-04 | BUSBAR SECTION - CATHALEENS FALL 110-CATHALEENS FALL 110-110B1 | 1 | 1 | 1 | Proposed | 22/08/2024 | 22/08/2024
TO-24-CF-CL-1-02 | 110kV FEEDER - CATHALEENS FALL 110-CLIFF 110-1 | 2 | 2 | 2 | Proposed | 22/08/2024 | 23/08/2024
TO-24-CL-T101-04 | GENERATOR TRANSFORMER - CLIFF 110-CLIFF G1-T101 | 1 | 1 | 1 | Proposed | 22/08/2024 | 22/08/2024
TO-24-CL-T102-06 | GENERATOR TRANSFORMER - CLIFF 110-CLIFF G2-T102 | 1 | 1 | 1 | Proposed | 22/08/2024 | 22/08/2024
TO-24-110 kV A1 @ CF-04 | BUSBAR SECTION - CATHALEENS FALL 110-CATHALEENS FALL 110-110A1 | 12 | 10 | 10 | Scheduled | 26/08/2024 | 06/09/2024
TO-24-110 kV A2 @ CF-02 | BUSBAR SECTION - CATHALEENS FALL 110-CATHALEENS FALL 110-110A2 | 5 | 5 | 5 | Scheduled | 26/08/2024 | 30/08/2024
TO-24-110 kV B1 @ CF-03 | BUSBAR SECTION - CATHALEENS FALL 110-CATHALEENS FALL 110-110B1 | 12 | 10 | 10 | Scheduled | 26/08/2024 | 06/09/2024
TO-24-CF-COR-1-01 | 110kV FEEDER - CATHALEENS FALL 110-CORRACLASSY 110-1 | 12 | 10 |  | Scheduled | 26/08/2024 | 06/09/2024
TO-24-CRO-110SA1-05 | SECTIONALISING DISCONNECT - COOLROE 110-COOLROE 110-110SA1 | 5 | 5 | 5 | Scheduled | 26/08/2024 | 30/08/2024
TO-24-CRO-110SA2-05 | SECTIONALISING DISCONNECT - COOLROE 110-COOLROE 110-110SA2 | 5 | 5 | 5 | Scheduled | 26/08/2024 | 30/08/2024
TO-24-CRO-KBY-1-05 | 110kV FEEDER - COOLROE 110-KILBARRY 110-1 | 5 | 5 | 5 | Scheduled | 26/08/2024 | 30/08/2024
TO-24-COR-PST-02 | TRANSFORMER - CORRACLASSY 110-ENNISKILLEN 110-PST | 12 | 10 |  | Scheduled | 26/08/2024 | 06/09/2024
TO-24-COR-GWE-1-03 | 110kV FEEDER - CORRACLASSY 110-GORTAWEE 110-1 | 12 | 10 |  | Scheduled | 26/08/2024 | 06/09/2024
TO-24-110 kV A2 @ FIN GIS-03 | BUSBAR SECTION - FINGLAS GIS 110-FINGLAS GIS 110-110A2 | 5 | 5 | 5 | Scheduled | 26/08/2024 | 30/08/2024
TO-24-110 kV B2 @ FIN GIS-03 | BUSBAR SECTION - FINGLAS GIS 110-FINGLAS GIS 110-110B2 | 5 | 5 | 5 | Scheduled | 26/08/2024 | 30/08/2024
TO-24-FIN GIS-110K2-04 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110K2 | 5 | 5 | 5 | Scheduled | 26/08/2024 | 30/08/2024
TO-24-FIN GIS-110SA1-2CB-04 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110SA1-2CB | 5 | 5 | 5 | Scheduled | 26/08/2024 | 30/08/2024
TO-24-FIN GIS-110SA2-4CB-05 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110SA2-4CB | 5 | 5 | 5 | Scheduled | 26/08/2024 | 30/08/2024
TO-24-FIN GIS-110SB1-2CB-04 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110SB1-2CB | 5 | 5 | 5 | Scheduled | 26/08/2024 | 30/08/2024
TO-24-FIN GIS-110SB2-4CB-06 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110SB2-4CB | 5 | 5 | 5 | Scheduled | 26/08/2024 | 30/08/2024
TO-24-GLR-110SA1-2CB-03 | COUPLER/SECTIONALISING CB - GLENREE 110-GLENREE 110-110SA1-2CB | 5 | 5 | 5 | Scheduled | 26/08/2024 | 30/08/2024
TO-24-GLR-T121-01 | DISTRIBUTION TRANSFORMER - GLENREE 110-GLENREE 38-T121 | 5 | 5 | 5 | Reference | 26/08/2024 | 30/08/2024
TO-24-MOY-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - MOY 110-MOY 110-110SA1-2CB | 5 | 5 | 5 | Scheduled | 26/08/2024 | 30/08/2024
TO-24-MOY-CAP1-01 | CAPACITOR/SVC/REACTOR - MOY 110-MOY 110-CAP1 | 12 | 10 | 10 | Scheduled | 26/08/2024 | 06/09/2024
TO-24-MOY-T141-01 | DISTRIBUTION TRANSFORMER - MOY 110-MOY 38-T141 | 5 | 5 | 5 | Reference | 26/08/2024 | 30/08/2024
TO-24-MOY-TAW-1-04 | 110kV FEEDER - MOY 110-TAWNAGHMORE 110-1 | 12 | 10 | 10 | Scheduled | 26/08/2024 | 06/09/2024
TO-24-ROP-T131-02 | GENERATOR TRANSFORMER - ROSSPILE 110-ROSSPILE 33-T131 | 1 | 1 | 1 | Scheduled | 26/08/2024 | 26/08/2024
TO-24-WOO-T4204-01 | TRANSFORMER - WOODLAND 400-WOODLAND 220-T4204 | 26 | 20 | 20 | Scheduled | 26/08/2024 | 20/09/2024
TO-24-CHA-GLE-1-03 | 110kV FEEDER - CHARLEVILLE 110-GLENLARA 110-1 | 8 | 6 |  | Scheduled | 27/08/2024 | 03/09/2024
TO-24-GLE-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - GLENLARA 110-GLENLARA 110-110SA1-2CB | 8 | 6 | 6 | Scheduled | 27/08/2024 | 03/09/2024
TO-24-MAY-TEN-1-01 | 110kV FEEDER - MAYNOOTH 110-TIMAHOE 110-1 | 34 | 24 | 24 | Scheduled | 29/08/2024 | 01/10/2024
TO-24-SHL-T2015-01 | GENERATOR TRANSFORMER - SHELLYBANKS 220-SHELLYBANKS G5-T2015 | 27 | 20 | 20 | Scheduled | 01/09/2024 | 27/09/2024
TO-24-BRY-RAF-2-01 | 110kV FEEDER - BARNAHELY 110-RAFFEEN 110-2 | 121 | 84 | 84 | Reference | 02/09/2024 | 31/12/2024
TO-24-BDA-T101-01 | TSO CUSTOMER TRANSFORMER - BARODA 110-BARODA 10-T101 | 9 | 7 | 7 | Scheduled | 02/09/2024 | 10/09/2024
TO-24-BIN-110SA1-2CB-02 | COUPLER/SECTIONALISING CB - BINBANE 110-BINBANE 110-110SA1-2CB | 3 | 3 | 3 | Scheduled | 02/09/2024 | 04/09/2024
TO-24-BIN-T142-03 | DISTRIBUTION TRANSFORMER - BINBANE 110-BINBANE 38-T142 | 3 | 3 | 3 | Reference | 02/09/2024 | 04/09/2024
TO-24-CLH-TRL-1-01 | 110kV FEEDER - CLAHANE 110-TRALEE 110-1 | 40 | 30 | 30 | Scheduled | 02/09/2024 | 11/10/2024
TO-24-DRY-LOU-1-02 | 110kV FEEDER - DRYBRIDGE 110-LOUTH 110-1 | 3 | 3 | 3 | Scheduled | 02/09/2024 | 04/09/2024
TO-24-GLR-MOY-1-01 | 110kV FEEDER - GLENREE 110-MOY 110-1 | 61 | 44 | 44 | Scheduled | 02/09/2024 | 01/11/2024
TO-24-MP GIS-T121-01 | GENERATOR TRANSFORMER - MONEYPOINT GIS 110-MONEYPOINT GIS 20-T121 | 5 | 5 | 5 | Scheduled | 02/09/2024 | 06/09/2024
TO-24-MP GIS-T2102-01 | TRANSFORMER - MONEYPOINT GIS 220-MONEYPOINT GIS 110-T2102 | 5 | 5 | 5 | Scheduled | 02/09/2024 | 06/09/2024
TO-24-MP GIS-T4202-02 | TRANSFORMER - MONEYPOINT GIS 400-MONEYPOINT GIS 220-T4202 | 5 | 5 |  | Scheduled | 02/09/2024 | 06/09/2024
TO-24-RNW-T121-01 | TSO CUSTOMER TRANSFORMER - RINAWADE 110-RINAWADE 20-T121 | 5 | 5 | 5 | Scheduled | 02/09/2024 | 06/09/2024
TO-24-110 kV A1 @ SNU-04 | BUSBAR SECTION - SNUGBOROUGH 110-SNUGBOROUGH 110-110A1 | 5 | 5 | 5 | Scheduled | 02/09/2024 | 06/09/2024
TO-24-110 kV B1 @ SNU-04 | BUSBAR SECTION - SNUGBOROUGH 110-SNUGBOROUGH 110-110B1 | 5 | 5 | 5 | Scheduled | 02/09/2024 | 06/09/2024
TO-24-SNU-110K1-04 | COUPLER/SECTIONALISING CB - SNUGBOROUGH 110-SNUGBOROUGH 110-110K1 | 5 | 5 | 5 | Scheduled | 02/09/2024 | 06/09/2024
TO-24-SNU-110SA1-2CB-08 | COUPLER/SECTIONALISING CB - SNUGBOROUGH 110-SNUGBOROUGH 110-110SA1-2CB | 5 | 5 | 5 | Scheduled | 02/09/2024 | 06/09/2024
TO-24-SNU-110SB1-2CB-09 | COUPLER/SECTIONALISING CB - SNUGBOROUGH 110-SNUGBOROUGH 110-110SB1-2CB | 5 | 5 | 5 | Scheduled | 02/09/2024 | 06/09/2024
TO-24-BAN-BRI-1-02 | 110kV FEEDER - BANDON 110-BRINNY 110-1 | 1 | 1 | 1 | Scheduled | 03/09/2024 | 03/09/2024
TO-24-BRI-T101-03 | TSO CUSTOMER TRANSFORMER - BRINNY 110-BRINNY 10-T101 | 1 | 1 | 1 | Scheduled | 03/09/2024 | 03/09/2024
TO-24-110 kV A3 @ KPG-01 | BUSBAR SECTION - KILPADDOGE 110-KILPADDOGE 110-110A3 | 11 | 9 | 9 | Scheduled | 03/09/2024 | 13/09/2024
TO-24-110 kV B3 @ KPG-01 | BUSBAR SECTION - KILPADDOGE 110-KILPADDOGE 110-110B3 | 11 | 9 | 9 | Scheduled | 03/09/2024 | 13/09/2024
TO-24-KPG-110K3-01 | COUPLER/SECTIONALISING CB - KILPADDOGE 110-KILPADDOGE 110-110K3 | 11 | 9 | 9 | Scheduled | 03/09/2024 | 13/09/2024
TO-24-KPG-110SA1-3CB-02 | COUPLER/SECTIONALISING CB - KILPADDOGE 110-KILPADDOGE 110-110SA1-3CB | 11 | 9 | 9 | Scheduled | 03/09/2024 | 13/09/2024
TO-24-KPG-110SB1-3CB-02 | COUPLER/SECTIONALISING CB - KILPADDOGE 110-KILPADDOGE 110-110SB1-3CB | 11 | 9 | 9 | Scheduled | 03/09/2024 | 13/09/2024
TO-24-KPG-RAT-1-01 | 110kV FEEDER - KILPADDOGE 110-RATHKEALE 110-1 | 11 | 9 | 9 | Scheduled | 03/09/2024 | 13/09/2024
TO-24-MP GIS-400K4-01 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 400-MONEYPOINT GIS 400-400K4 | 1 | 1 | 1 | Scheduled | 04/09/2024 | 04/09/2024
TO-24-CDU-GLN-1-05 | 110kV FEEDER - CORDUFF 110-GALLANSTOWN 110-1 | 3 | 1 | 1 | Scheduled | 06/09/2024 | 08/09/2024
TO-24-AA GIS-T103-01 | GENERATOR TRANSFORMER - ARDNACRUSHA GIS 110-ARDNACRUSHA GIS G3-T103 | 5 | 5 | 5 | Scheduled | 09/09/2024 | 13/09/2024
TO-24-CRA-LWD-1-09 | 110kV FEEDER - CRANE 110-LODGEWOOD 110-1 | 4 | 4 | 4 | Scheduled | 09/09/2024 | 12/09/2024
TO-24-CRY-LWD-1-05 | 110kV FEEDER - CRORY 110-LODGEWOOD 110-1 | 4 | 4 | 4 | Reference | 09/09/2024 | 12/09/2024
TO-24-CRY-T121-05 | DISTRIBUTION TRANSFORMER - CRORY 110-CRORY 20-T121 | 4 | 4 | 4 | Reference | 09/09/2024 | 12/09/2024
TO-24-GGO-T2001-01 | GENERATOR TRANSFORMER - GLANAGOW 220-GLANAGOW G1-T2001 | 9 | 7 | 7 | Scheduled | 09/09/2024 | 17/09/2024
TO-24-110 kV A1 @ GI-02 | BUSBAR SECTION - GREAT ISLAND 110-GREAT ISLAND 110-110A1 | 5 | 5 | 5 | Scheduled | 09/09/2024 | 13/09/2024
TO-24-110 kV A2 @ GI-01 | BUSBAR SECTION - GREAT ISLAND 110-GREAT ISLAND 110-110A2 | 5 | 5 | 5 | Scheduled | 09/09/2024 | 13/09/2024
TO-24-110 kV B1 @ GI-02 | BUSBAR SECTION - GREAT ISLAND 110-GREAT ISLAND 110-110B1 | 5 | 5 | 5 | Scheduled | 09/09/2024 | 13/09/2024
TO-24-110 kV B2 @ GI-01 | BUSBAR SECTION - GREAT ISLAND 110-GREAT ISLAND 110-110B2 | 5 | 5 | 5 | Scheduled | 09/09/2024 | 13/09/2024
TO-24-GI-110K1-2-01 | COUPLER/SECTIONALISING CB - GREAT ISLAND 110-GREAT ISLAND 110-110K1-2 | 5 | 5 |  | Scheduled | 09/09/2024 | 13/09/2024
TO-24-LWD-110SA1-09 | SECTIONALISING DISCONNECT - LODGEWOOD 110-LODGEWOOD 110-110SA1 | 4 | 4 | 4 | Scheduled | 09/09/2024 | 12/09/2024
TO-24-LWD-110SA2-09 | SECTIONALISING DISCONNECT - LODGEWOOD 110-LODGEWOOD 110-110SA2 | 4 | 4 | 4 | Scheduled | 09/09/2024 | 12/09/2024
TO-24-110 kV A2 @ LOU-03 | BUSBAR SECTION - LOUTH 110-LOUTH 110-110A2 | 1 | 1 | 1 | Scheduled | 09/09/2024 | 09/09/2024
TO-24-110 kV B2 @ LOU-03 | BUSBAR SECTION - LOUTH 110-LOUTH 110-110B2 | 1 | 1 | 1 | Scheduled | 09/09/2024 | 09/09/2024
TO-24-LOU-T2104-03 | TRANSFORMER - LOUTH 220-LOUTH 110-T2104 | 1 | 1 | 1 | Scheduled | 09/09/2024 | 09/09/2024
TO-24-110 kV A2 @ SNU-02 | BUSBAR SECTION - SNUGBOROUGH 110-SNUGBOROUGH 110-110A2 | 10 | 8 | 8 | Scheduled | 09/09/2024 | 18/09/2024
TO-24-110 kV B2 @ SNU-02 | BUSBAR SECTION - SNUGBOROUGH 110-SNUGBOROUGH 110-110B2 | 10 | 8 | 8 | Scheduled | 09/09/2024 | 18/09/2024
TO-24-SNU-110K2-01 | COUPLER/SECTIONALISING CB - SNUGBOROUGH 110-SNUGBOROUGH 110-110K2 | 10 | 8 | 8 | Scheduled | 09/09/2024 | 18/09/2024
TO-24-SNU-110SA1-2CB-06 | COUPLER/SECTIONALISING CB - SNUGBOROUGH 110-SNUGBOROUGH 110-110SA1-2CB | 10 | 8 | 8 | Scheduled | 09/09/2024 | 18/09/2024
TO-24-SNU-110SB1-2CB-07 | COUPLER/SECTIONALISING CB - SNUGBOROUGH 110-SNUGBOROUGH 110-110SB1-2CB | 10 | 8 | 8 | Scheduled | 09/09/2024 | 18/09/2024
TO-24-SOM-T142-01 | DISTRIBUTION TRANSFORMER - SOMERSET 110-SOMERSET 38-T142 | 3 | 3 | 3 | Reference | 09/09/2024 | 11/09/2024
TO-24-SOM,T-CSH-1-01 | 110kV FEEDER - SOMERSET tee-CASHLA 110-1 | 66 | 47 | 47 | Proposed | 09/09/2024 | 13/11/2024
TO-24-SOM,T-SH-1-02 | 110kV FEEDER - SOMERSET tee-SHANNONBRIDGE 110-1 | 3 | 3 | 3 | Scheduled | 09/09/2024 | 11/09/2024
TO-24-SOM,T-SOM-1-01 | 110kV FEEDER - SOMERSET tee-SOMERSET 110-1 | 3 | 3 | 3 | Scheduled | 09/09/2024 | 11/09/2024
TO-24-AA GIS-110K2-02 | COUPLER/SECTIONALISING CB - ARDNACRUSHA GIS 110-ARDNACRUSHA GIS 110-110K2 | 1 | 1 | 1 | Scheduled | 10/09/2024 | 10/09/2024
TO-24-BAN-BRI-2-02 | 110kV FEEDER - BANDON 110-BRINNY 110-2 | 7 | 5 | 5 | Scheduled | 10/09/2024 | 16/09/2024
TO-24-BRI-T102-02 | TSO CUSTOMER TRANSFORMER - BRINNY 110-BRINNY 10-T102 | 7 | 5 | 5 | Scheduled | 10/09/2024 | 16/09/2024
TO-24-INC-T2102-01 | TRANSFORMER - INCHICORE 220-INCHICORE 110-T2102 | 2 | 2 | 2 | Reference | 10/09/2024 | 11/09/2024
TO-24-LOU-AT3-01 | TRANSFORMER - LOUTH 220-LOUTH 275-AT3 | 3 | 3 |  | Scheduled | 10/09/2024 | 12/09/2024
TO-24-220 kV A2 @ AD-02 | BUSBAR SECTION - AGHADA 220-AGHADA 220-220A2 | 10 | 8 | 8 | Scheduled | 11/09/2024 | 20/09/2024
TO-24-220 kV B2 @ AD-02 | BUSBAR SECTION - AGHADA 220-AGHADA 220-220B2 | 10 | 8 | 8 | Scheduled | 11/09/2024 | 20/09/2024
TO-24-AD-SA1-2CB-02 | COUPLER/SECTIONALISING CB - AGHADA 220-AGHADA 220-220SA1-2CB | 10 | 8 | 8 | Scheduled | 11/09/2024 | 20/09/2024
TO-24-AD-SB1-2CB-02 | COUPLER/SECTIONALISING CB - AGHADA 220-AGHADA 220-220SB1-2CB | 10 | 8 | 8 | Scheduled | 11/09/2024 | 20/09/2024
TO-24-AD-RAF-1-04 | 220kV FEEDER - AGHADA 220-RAFFEEN 220-1 | 10 | 8 | 8 | Scheduled | 11/09/2024 | 20/09/2024
TO-24-CLA-110K1-2-02 | COUPLER/SECTIONALISING CB - CLASHAVOON 110-CLASHAVOON 110-110K1-2 | 1 | 1 | 1 | Scheduled | 11/09/2024 | 11/09/2024
TO-24-KYT-220K2-01 | COUPLER/SECTIONALISING CB - KELLYSTOWN 220-KELLYSTOWN 220-220K2 | 1 | 1 | 1 | Scheduled | 11/09/2024 | 11/09/2024
TO-24-220 kV A4 @ KRA-01 | BUSBAR SECTION - KNOCKRAHA 220-KNOCKRAHA 220-220A4 | 57 | 40 | 40 | Scheduled | 11/09/2024 | 06/11/2024
TO-24-220 kV B4 @ KRA-01 | BUSBAR SECTION - KNOCKRAHA 220-KNOCKRAHA 220-220B4 | 57 | 40 | 40 | Scheduled | 11/09/2024 | 06/11/2024
TO-24-KRA-220K4-04 | COUPLER/SECTIONALISING CB - KNOCKRAHA 220-KNOCKRAHA 220-220K4 | 57 | 40 | 40 | Scheduled | 11/09/2024 | 06/11/2024
TO-24-KRA-220SA2-4CB-04 | COUPLER/SECTIONALISING CB - KNOCKRAHA 220-KNOCKRAHA 220-220SA2-4CB | 57 | 40 | 40 | Scheduled | 11/09/2024 | 06/11/2024
TO-24-KRA-220SB2-4CB-04 | COUPLER/SECTIONALISING CB - KNOCKRAHA 220-KNOCKRAHA 220-220SB2-4CB | 57 | 40 | 40 | Scheduled | 11/09/2024 | 06/11/2024
TO-24-220 kV A2 @ RAF-02 | BUSBAR SECTION - RAFFEEN 220-RAFFEEN 220-220A2 | 10 | 8 | 8 | Scheduled | 11/09/2024 | 20/09/2024
TO-24-220 kV B2 @ RAF-02 | BUSBAR SECTION - RAFFEEN 220-RAFFEEN 220-220B2 | 10 | 8 | 8 | Scheduled | 11/09/2024 | 20/09/2024
TO-24-110 kV A2 @ CSH-01 | BUSBAR SECTION - CASHLA 110-CASHLA 110-110A2 | 58 | 41 |  | Scheduled | 12/09/2024 | 08/11/2024
TO-24-110 kV B2 @ CSH-01 | BUSBAR SECTION - CASHLA 110-CASHLA 110-110B2 | 58 | 41 |  | Scheduled | 12/09/2024 | 08/11/2024
TO-24-KYT-220K3-01 | COUPLER/SECTIONALISING CB - KELLYSTOWN 220-KELLYSTOWN 220-220K3 | 1 | 1 | 1 | Scheduled | 12/09/2024 | 12/09/2024
TO-24-ATH-SH-1-04 | 110kV FEEDER - ATHLONE 110-SHANNONBRIDGE 110-1 | 1 | 0 | 0 | Scheduled | 14/09/2024 | 14/09/2024
TO-24-AD-WHI-1-01 | 110kV FEEDER - AGHADA 110-WHITEGATE 110-1 | 4 | 4 |  | Scheduled | 16/09/2024 | 19/09/2024
TO-24-BAN-BRI-1-04 | 110kV FEEDER - BANDON 110-BRINNY 110-1 | 5 | 5 | 5 | Scheduled | 16/09/2024 | 20/09/2024
TO-24-BOL-ENN-1-03 | 110kV FEEDER - BOOLTIAGH 110-ENNIS 110-1 | 5 | 5 | 5 | Scheduled | 16/09/2024 | 20/09/2024
TO-24-BRI-T101-04 | TSO CUSTOMER TRANSFORMER - BRINNY 110-BRINNY 10-T101 | 5 | 5 | 5 | Scheduled | 16/09/2024 | 20/09/2024
TO-24-CLW-KLS-2-06 | 110kV FEEDER - CARLOW 110-KELLIS 110-2 | 5 | 5 | 5 | Scheduled | 16/09/2024 | 20/09/2024
TO-24-CLE-T222-02 | TSO CUSTOMER TRANSFORMER - CLONEE 220-CLONEE 20-T222 | 36 | 26 | 26 | Scheduled | 16/09/2024 | 21/10/2024
TO-24-CRO-T122-02 | DISTRIBUTION TRANSFORMER - COOLROE 110-COOLROE 20-T122 | 68 | 49 | 49 | Reference | 16/09/2024 | 22/11/2024
TO-24-CRA-WEX-1-01 | 110kV FEEDER - CRANE 110-WEXFORD 110-1 | 71 | 50 | 50 | Scheduled | 16/09/2024 | 25/11/2024
TO-24-GAR-PLA-1-02 | 110kV FEEDER - GARBALLAGH 110-PLATIN 110-1 | 3 | 3 | 3 | Scheduled | 16/09/2024 | 18/09/2024
TO-24-220 kV B1 @ GI GIS-03 | BUSBAR SECTION - GREAT ISLAND GIS 220-GREAT ISLAND GIS 220-220B1 | 10 | 8 | 8 | Scheduled | 16/09/2024 | 25/09/2024
TO-24-220 kV B2 @ GI GIS-01 | BUSBAR SECTION - GREAT ISLAND GIS 220-GREAT ISLAND GIS 220-220B2 | 10 | 8 | 8 | Scheduled | 16/09/2024 | 25/09/2024
TO-24-GI GIS-220K1-05 | COUPLER/SECTIONALISING CB - GREAT ISLAND GIS 220-GREAT ISLAND GIS 220-220K1 | 10 | 8 | 8 | Scheduled | 16/09/2024 | 25/09/2024
TO-24-GI GIS-220K2-05 | COUPLER/SECTIONALISING CB - GREAT ISLAND GIS 220-GREAT ISLAND GIS 220-220K2 | 10 | 8 | 8 | Scheduled | 16/09/2024 | 25/09/2024
TO-24-GI GIS-220SB1-2CB-02 | COUPLER/SECTIONALISING CB - GREAT ISLAND GIS 220-GREAT ISLAND GIS 220-220SB1-2CB | 10 | 8 | 8 | Scheduled | 16/09/2024 | 25/09/2024
TO-24-110 kV A2 @ KLS-06 | BUSBAR SECTION - KELLIS 110-KELLIS 110-110A2 | 12 | 10 | 10 | Scheduled | 16/09/2024 | 27/09/2024
TO-24-110 kV B2 @ KLS-05 | BUSBAR SECTION - KELLIS 110-KELLIS 110-110B2 | 12 | 10 | 10 | Scheduled | 16/09/2024 | 27/09/2024
TO-24-110 kV A2 @ KLN-02 | BUSBAR SECTION - KILLONAN 110-KILLONAN 110-110A2 | 18 | 14 | 14 | Scheduled | 16/09/2024 | 03/10/2024
TO-24-110 kV B2 @ KLN-03 | BUSBAR SECTION - KILLONAN 110-KILLONAN 110-110B2 | 18 | 14 | 14 | Scheduled | 16/09/2024 | 03/10/2024
TO-24-220 kV A2 @ KLN-03 | BUSBAR SECTION - KILLONAN 220-KILLONAN 220-220A2 | 18 | 14 | 14 | Scheduled | 16/09/2024 | 03/10/2024
TO-24-220 kV B2 @ KLN-02 | BUSBAR SECTION - KILLONAN 220-KILLONAN 220-220B2 | 18 | 14 | 14 | Scheduled | 16/09/2024 | 03/10/2024
TO-24-KLN-T2104-01 | TRANSFORMER - KILLONAN 220-KILLONAN 110-T2104 | 18 | 14 | 14 | Scheduled | 16/09/2024 | 03/10/2024
TO-24-TSB-TEN-1-05 | 110kV FEEDER - THORNSBERRY 110-TIMAHOE 110-1 | 5 | 5 | 5 | Scheduled | 16/09/2024 | 20/09/2024
TO-24-TEN-110K2-01 | COUPLER/SECTIONALISING CB - TIMAHOE 110-TIMAHOE 110-110K2 | 5 | 5 | 5 | Scheduled | 16/09/2024 | 20/09/2024
TO-24-TEN-T132-01 | GENERATOR TRANSFORMER - TIMAHOE 110-TIMAHOE 33-T132 | 5 | 5 | 5 | Scheduled | 16/09/2024 | 20/09/2024
TO-24-220 kV A1 @ TH-02 | BUSBAR SECTION - TURLOUGH HILL 220-TURLOUGH HILL 220-220A1 | 4 | 4 | 4 | Scheduled | 16/09/2024 | 19/09/2024
TO-24-220 kV A2 @ TH-03 | BUSBAR SECTION - TURLOUGH HILL 220-TURLOUGH HILL 220-220A2 | 4 | 4 | 4 | Scheduled | 16/09/2024 | 19/09/2024
TO-24-220 kV B1 @ TH-02 | BUSBAR SECTION - TURLOUGH HILL 220-TURLOUGH HILL 220-220B1 | 4 | 4 | 4 | Scheduled | 16/09/2024 | 19/09/2024
TO-24-220 kV B2 @ TH-01 | BUSBAR SECTION - TURLOUGH HILL 220-TURLOUGH HILL 220-220B2 | 4 | 4 | 4 | Scheduled | 16/09/2024 | 19/09/2024
TO-24-TH-220K1-2-03 | COUPLER/SECTIONALISING CB - TURLOUGH HILL 220-TURLOUGH HILL 220-220K1-2 | 5 | 5 | 5 | Scheduled | 16/09/2024 | 20/09/2024
TO-24-AUG-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - AUGHINISH 110-AUGHINISH 110-110SA1-2CB | 2 | 2 | 2 | Scheduled | 17/09/2024 | 18/09/2024
TO-24-CTN-TIP-1-02 | 110kV FEEDER - CAUTEEN 110-TIPPERARY 110-1 | 2 | 2 | 2 | Scheduled | 17/09/2024 | 18/09/2024
TO-24-GLN-T133-01 | GENERATOR TRANSFORMER - GALLANSTOWN 110-GALLANSTOWN 33-T133 | 1 | 1 | 1 | Scheduled | 17/09/2024 | 17/09/2024
TO-24-110 kV A2 @ LOU-04 | BUSBAR SECTION - LOUTH 110-LOUTH 110-110A2 | 2 | 2 | 2 | Scheduled | 17/09/2024 | 18/09/2024
TO-24-110 kV B2 @ LOU-04 | BUSBAR SECTION - LOUTH 110-LOUTH 110-110B2 | 2 | 2 | 2 | Scheduled | 17/09/2024 | 18/09/2024
TO-24-LOU-T2104-04 | TRANSFORMER - LOUTH 220-LOUTH 110-T2104 | 2 | 2 | 2 | Scheduled | 17/09/2024 | 18/09/2024
TO-24-PB-R2001-06 | CAPACITOR/SVC/REACTOR - POOLBEG 220-POOLBEG 220-R2001 | 2 | 2 | 2 | Scheduled | 17/09/2024 | 18/09/2024
TO-24-BDN-MRK1-01 | TSO CUSTOMER TRANSFORMER - BALLYDINE 110-BALLYDINE 10-MRK1 | 14 | 10 | 10 | Scheduled | 19/09/2024 | 02/10/2024
TO-24-BAL-T121-03 | DISTRIBUTION TRANSFORMER - BALTRASNA 110-BALTRASNA 20-T121 | 2 | 2 | 2 | Reference (Proposed) | 19/09/2024 | 20/09/2024
TO-24-AD-RAF-1-01 | 220kV FEEDER - AGHADA 220-RAFFEEN 220-1 | 6 | 4 | 4 | Scheduled | 21/09/2024 | 26/09/2024
TO-24-CHA-110SA1-2CB-02 | COUPLER/SECTIONALISING CB - CHARLEVILLE 110-CHARLEVILLE 110-110SA1-2CB | 5 | 5 |  | Scheduled | 23/09/2024 | 27/09/2024
TO-24-CHA-MAL-1-03 | 110kV FEEDER - CHARLEVILLE 110-MALLOW 110-1 | 5 | 5 |  | Scheduled | 23/09/2024 | 27/09/2024
TO-24-CHA-T142-02 | DISTRIBUTION TRANSFORMER - CHARLEVILLE 110-CHARLEVILLE 38-T142 | 5 | 5 |  | Reference | 23/09/2024 | 27/09/2024
TO-24-110 kV A1 @ CLG-02 | BUSBAR SECTION - CLOGHRAN 110-CLOGHRAN 110-110A1 | 12 | 10 | 10 | Scheduled | 23/09/2024 | 04/10/2024
TO-24-110 kV B1 @ CLG-02 | BUSBAR SECTION - CLOGHRAN 110-CLOGHRAN 110-110B1 | 12 | 10 | 10 | Scheduled | 23/09/2024 | 04/10/2024
TO-24-CLG-110K1-05 | COUPLER/SECTIONALISING CB - CLOGHRAN 110-CLOGHRAN 110-110K1 | 12 | 10 | 10 | Scheduled | 23/09/2024 | 04/10/2024
TO-24-CLG-110SA1-2CB-03 | COUPLER/SECTIONALISING CB - CLOGHRAN 110-CLOGHRAN 110-110SA1-2CB | 12 | 10 | 10 | Scheduled | 23/09/2024 | 04/10/2024
TO-24-CLG-110SB1-2CB-02 | COUPLER/SECTIONALISING CB - CLOGHRAN 110-CLOGHRAN 110-110SB1-2CB | 12 | 10 | 10 | Scheduled | 23/09/2024 | 04/10/2024
TO-24-CLG-T121-01 | TSO CUSTOMER TRANSFORMER - CLOGHRAN 110-CLOGHRAN 20-T121 | 12 | 10 | 10 | Scheduled | 23/09/2024 | 04/10/2024
TO-24-COW-RAF-1-03 | 110kV FEEDER - COW CROSS 110-RAFFEEN 110-1 | 8 | 6 | 6 | Scheduled | 23/09/2024 | 30/09/2024
TO-24-FIN-T2103-03 | TRANSFORMER - FINGLAS 220-FINGLAS 110-T2103 | 2 | 2 | 2 | Scheduled | 23/09/2024 | 24/09/2024
TO-24-110 kV A3 @ GAL GIS-03 | BUSBAR SECTION - GALWAY GIS 110-GALWAY GIS 110-110A3 | 9 | 7 | 7 | Scheduled | 23/09/2024 | 01/10/2024
TO-24-110 kV B3 @ GAL GIS-01 | BUSBAR SECTION - GALWAY GIS 110-GALWAY GIS 110-110B3 | 9 | 7 | 7 | Scheduled | 23/09/2024 | 01/10/2024
TO-24-GAL GIS-110K3-01 | COUPLER/SECTIONALISING CB - GALWAY GIS 110-GALWAY GIS 110-110K3 | 9 | 7 | 7 | Scheduled | 23/09/2024 | 01/10/2024
TO-24-GAL GIS-110SA1-3CB-03 | COUPLER/SECTIONALISING CB - GALWAY GIS 110-GALWAY GIS 110-110SA1-3CB | 9 | 7 | 7 | Scheduled | 23/09/2024 | 01/10/2024
TO-24-GAL GIS-110SB1-3CB-03 | COUPLER/SECTIONALISING CB - GALWAY GIS 110-GALWAY GIS 110-110SB1-3CB | 9 | 7 | 7 | Scheduled | 23/09/2024 | 01/10/2024
TO-24-LIS-T131-02 | GENERATOR TRANSFORMER - LISDRUM 110-LISDRUM 33-T131 | 2 | 2 | 2 | Scheduled | 23/09/2024 | 24/09/2024
TO-24-ROP-T131-03 | GENERATOR TRANSFORMER - ROSSPILE 110-ROSSPILE 33-T131 | 1 | 1 | 1 | Scheduled | 23/09/2024 | 23/09/2024
TO-24-RYB GIS-T103-01 | TSO CUSTOMER TRANSFORMER - RYEBROOK GIS 110-RYEBROOK 10-T103 | 18 | 14 | 14 | Scheduled | 23/09/2024 | 10/10/2024
TO-24-SHL-D2/CB2-02 | COUPLER/SECTIONALISING CB - SHELLYBANKS 220-SHELLYBANKS 220-D2/CB2 | 5 | 5 | 5 | Scheduled | 23/09/2024 | 27/09/2024
TO-24-SHL-D2/CB3-03 | COUPLER/SECTIONALISING CB - SHELLYBANKS 220-SHELLYBANKS 220-D2/CB3 | 5 | 5 | 5 | Scheduled | 23/09/2024 | 27/09/2024
TO-24-110 kV A1 @ CUL-02 | BUSBAR SECTION - CULLENAGH 110-CULLENAGH 110-110A1 | 1 | 1 | 1 | Scheduled | 24/09/2024 | 24/09/2024
TO-24-110 kV B1 @ CUL-03 | BUSBAR SECTION - CULLENAGH 110-CULLENAGH 110-110B1 | 1 | 1 | 1 | Scheduled | 24/09/2024 | 24/09/2024
TO-24-110 kV A2 @ MAY-02 | BUSBAR SECTION - MAYNOOTH 110-MAYNOOTH 110-110A2 | 2 | 2 | 2 | Scheduled | 24/09/2024 | 25/09/2024
TO-24-110 kV A3 @ MAY-04 | BUSBAR SECTION - MAYNOOTH 110-MAYNOOTH 110-110A3 | 2 | 2 | 2 | Scheduled | 24/09/2024 | 25/09/2024
TO-24-110 kV B2 @ MAY-02 | BUSBAR SECTION - MAYNOOTH 110-MAYNOOTH 110-110B2 | 2 | 2 | 2 | Scheduled | 24/09/2024 | 25/09/2024
TO-24-110 kV B3 @ MAY-04 | BUSBAR SECTION - MAYNOOTH 110-MAYNOOTH 110-110B3 | 2 | 2 | 2 | Scheduled | 24/09/2024 | 25/09/2024
TO-24-MAY-T2102-06 | TRANSFORMER - MAYNOOTH 220-MAYNOOTH 110-T2102 | 2 | 2 | 2 | Scheduled | 24/09/2024 | 25/09/2024
TO-24-MAY-T2103-02 | TRANSFORMER - MAYNOOTH 220-MAYNOOTH 110-T2103 | 2 | 2 | 2 | Scheduled | 24/09/2024 | 25/09/2024
TO-24-CAH-TIP-1-01 | 110kV FEEDER - CAHIR 110-TIPPERARY 110-1 | 57 | 40 | 40 | Scheduled | 25/09/2024 | 20/11/2024
TO-24-CUL-110K1-2-01 | COUPLER/SECTIONALISING CB - CULLENAGH 110-CULLENAGH 110-110K1-2 | 57 | 40 | 40 | Scheduled | 25/09/2024 | 20/11/2024
TO-24-CUL-220K1-2-02 | COUPLER/SECTIONALISING CB - CULLENAGH 220-CULLENAGH 220-220K1-2 | 57 | 40 | 40 | Scheduled | 25/09/2024 | 20/11/2024
TO-24-COS-FLA-2-03 | 110kV FEEDER - CARRICK ON SHANNON 110-FLAGFORD 110-2 | 57 | 40 |  | Scheduled | 30/09/2024 | 25/11/2024
TO-24-CHA-KLN-1-01 | 110kV FEEDER - CHARLEVILLE 110-KILLONAN 110-1 | 5 | 5 | 5 | Scheduled | 30/09/2024 | 04/10/2024
TO-24-CLA-MAC-2-01 | 110kV FEEDER - CLASHAVOON 110-MACROOM 110-2 | 50 | 35 | 35 | Scheduled | 30/09/2024 | 18/11/2024
TO-24-CDU-SNU-1-02 | 110kV FEEDER - CORDUFF 110-SNUGBOROUGH 110-1 | 5 | 5 | 5 | Scheduled | 30/09/2024 | 04/10/2024
TO-24-110 kV A2 @ FLA-01 | BUSBAR SECTION - FLAGFORD 110-FLAGFORD 110-110A2 | 53 | 38 | 38 | Scheduled | 30/09/2024 | 21/11/2024
TO-24-110 kV B2 @ FLA-01 | BUSBAR SECTION - FLAGFORD 110-FLAGFORD 110-110B2 | 53 | 38 | 38 | Scheduled | 30/09/2024 | 21/11/2024
TO-24-ROP-T131-04 | GENERATOR TRANSFORMER - ROSSPILE 110-ROSSPILE 33-T131 | 1 | 1 | 1 | Scheduled | 30/09/2024 | 30/09/2024
TO-24-110 kV A2 @ SNU-03 | BUSBAR SECTION - SNUGBOROUGH 110-SNUGBOROUGH 110-110A2 | 5 | 5 | 5 | Scheduled | 30/09/2024 | 04/10/2024
TO-24-110 kV B2 @ SNU-03 | BUSBAR SECTION - SNUGBOROUGH 110-SNUGBOROUGH 110-110B2 | 5 | 5 | 5 | Scheduled | 30/09/2024 | 04/10/2024
TO-24-SNU-110K2-04 | COUPLER/SECTIONALISING CB - SNUGBOROUGH 110-SNUGBOROUGH 110-110K2 | 5 | 5 | 5 | Scheduled | 30/09/2024 | 04/10/2024
TO-24-SNU-110SA1-2CB-07 | COUPLER/SECTIONALISING CB - SNUGBOROUGH 110-SNUGBOROUGH 110-110SA1-2CB | 5 | 5 | 5 | Scheduled | 30/09/2024 | 04/10/2024
TO-24-SNU-110SB1-2CB-08 | COUPLER/SECTIONALISING CB - SNUGBOROUGH 110-SNUGBOROUGH 110-110SB1-2CB | 5 | 5 | 5 | Scheduled | 30/09/2024 | 04/10/2024
TO-24-ATH-T142-01 | DISTRIBUTION TRANSFORMER - ATHLONE 110-ATHLONE 38-T142 | 2 | 2 | 2 | Reference | 01/10/2024 | 02/10/2024
TO-24-BOG-T122-01 | DISTRIBUTION TRANSFORMER - BANOGE 110-BANOGE 20-T122 | 2 | 2 | 2 | Reference | 01/10/2024 | 02/10/2024
TO-24-TB-T101-02 | GENERATOR TRANSFORMER - TARBERT 110-TARBERT G1-T101 | 2 | 2 | 2 | Scheduled | 01/10/2024 | 02/10/2024
TO-24-BLC-110K1-01 | COUPLER/SECTIONALISING CB - BELCAMP 110-BELCAMP 110-110K1 | 1 | 1 | 1 | Scheduled | 02/10/2024 | 02/10/2024
TO-24-CD-MAC-1-02 | 110kV FEEDER - CARRIGADROHID 110-MACROOM 110-1 | 9 | 7 | 7 | Scheduled | 02/10/2024 | 10/10/2024
TO-24-DGN-110SA1-01 | SECTIONALISING DISCONNECT - DUNGARVAN 110-DUNGARVAN 110-110SA1 | 1 | 1 | 1 | Scheduled | 02/10/2024 | 02/10/2024
TO-24-DGN-110SA2-03 | SECTIONALISING DISCONNECT - DUNGARVAN 110-DUNGARVAN 110-110SA2 | 1 | 1 | 1 | Scheduled | 02/10/2024 | 02/10/2024
TO-24-DGN-T142-01 | DISTRIBUTION TRANSFORMER - DUNGARVAN 110-DUNGARVAN 38-T142 | 1 | 1 | 1 | Reference | 02/10/2024 | 02/10/2024
TO-24-110 kV A1 @ LOU-07 | BUSBAR SECTION - LOUTH 110-LOUTH 110-110A1 | 1 | 1 | 1 | Scheduled | 02/10/2024 | 02/10/2024
TO-24-110 kV A2 @ LOU-05 | BUSBAR SECTION - LOUTH 110-LOUTH 110-110A2 | 1 | 1 | 1 | Scheduled | 02/10/2024 | 02/10/2024
TO-24-110 kV B1 @ LOU-07 | BUSBAR SECTION - LOUTH 110-LOUTH 110-110B1 | 1 | 1 | 1 | Scheduled | 02/10/2024 | 02/10/2024
TO-24-110 kV B2 @ LOU-05 | BUSBAR SECTION - LOUTH 110-LOUTH 110-110B2 | 1 | 1 | 1 | Scheduled | 02/10/2024 | 02/10/2024
TO-24-LOU-T2104-05 | TRANSFORMER - LOUTH 220-LOUTH 110-T2104 | 1 | 1 | 1 | Scheduled | 02/10/2024 | 02/10/2024
TO-24-MAC-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - MACROOM 110-MACROOM 110-110SA1-2CB | 9 | 7 |  | Scheduled | 02/10/2024 | 10/10/2024
TO-24-SHL-D1/CB1-04 | COUPLER/SECTIONALISING CB - SHELLYBANKS 220-SHELLYBANKS 220-D1/CB1 | 1 | 1 | 1 | Scheduled | 02/10/2024 | 02/10/2024
TO-24-SHL-D2/CB1-04 | COUPLER/SECTIONALISING CB - SHELLYBANKS 220-SHELLYBANKS 220-D2/CB1 | 1 | 1 | 1 | Scheduled | 02/10/2024 | 02/10/2024
TO-24-SHL-T2016-01 | GENERATOR TRANSFORMER - SHELLYBANKS 220-SHELLYBANKS G6-T2016 | 30 | 21 |  | Scheduled | 02/10/2024 | 31/10/2024
TO-24-BVK-R2001-01 | CAPACITOR/SVC/REACTOR - BALLYVOUSKILL 220-BALLYVOUSKILL 220-R2001 | 1 | 1 | 1 | Scheduled | 03/10/2024 | 03/10/2024
TO-24-BLC-110K3-01 | COUPLER/SECTIONALISING CB - BELCAMP 110-BELCAMP 110-110K3 | 1 | 1 | 1 | Scheduled | 03/10/2024 | 03/10/2024
TO-24-CDU-HN-1-01 | 220kV FEEDER - CORDUFF 220-HUNTSTOWN 220-1 | 19 | 13 | 13 | Scheduled | 05/10/2024 | 23/10/2024
TO-24-DSN-MP GIS-1-04 | 400kV FEEDER - DUNSTOWN 400-MONEYPOINT GIS 400-1 | 2 | 0 | 0 | Scheduled | 05/10/2024 | 06/10/2024
TO-24-HN-T2002-01 | GENERATOR TRANSFORMER - HUNTSTOWN 220-HUNTSTOWN G2-T2002 | 19 | 13 | 13 | Scheduled | 05/10/2024 | 23/10/2024
TO-24-110 kV A1 @ CLG-03 | BUSBAR SECTION - CLOGHRAN 110-CLOGHRAN 110-110A1 | 13 | 10 | 10 | Scheduled | 06/10/2024 | 18/10/2024
TO-24-110 kV B1 @ CLG-03 | BUSBAR SECTION - CLOGHRAN 110-CLOGHRAN 110-110B1 | 13 | 10 | 10 | Scheduled | 06/10/2024 | 18/10/2024
TO-24-CLG-110K1-06 | COUPLER/SECTIONALISING CB - CLOGHRAN 110-CLOGHRAN 110-110K1 | 13 | 10 | 10 | Scheduled | 06/10/2024 | 18/10/2024
TO-24-CLG-110SA1-2CB-02 | COUPLER/SECTIONALISING CB - CLOGHRAN 110-CLOGHRAN 110-110SA1-2CB | 13 | 10 | 10 | Scheduled | 06/10/2024 | 18/10/2024
TO-24-CLG-110SB1-2CB-03 | COUPLER/SECTIONALISING CB - CLOGHRAN 110-CLOGHRAN 110-110SB1-2CB | 13 | 10 | 10 | Scheduled | 06/10/2024 | 18/10/2024
TO-24-CLG-T123-02 | TSO CUSTOMER TRANSFORMER - CLOGHRAN 110-CLOGHRAN 20-T123 | 13 | 10 | 10 | Scheduled | 06/10/2024 | 18/10/2024
TO-24-AUG-CFM-1-02 | 110kV FEEDER - AUGHINISH 110-CASTLEFARM 110-1 | 5 | 5 | 5 | Scheduled | 07/10/2024 | 11/10/2024
TO-24-110 kV A1 @ AUN-01 | BUSBAR SECTION - AUNGIERSTOWN 110-AUNGIERSTOWN 110-110A1 | 5 | 5 | 5 | Scheduled | 07/10/2024 | 11/10/2024
TO-24-110 kV B1 @ AUN-01 | BUSBAR SECTION - AUNGIERSTOWN 110-AUNGIERSTOWN 110-110B1 | 5 | 5 | 5 | Scheduled | 07/10/2024 | 11/10/2024
TO-24-AUN-110K1-01 | COUPLER/SECTIONALISING CB - AUNGIERSTOWN 110-AUNGIERSTOWN 110-110K1 | 5 | 5 | 5 | Scheduled | 07/10/2024 | 11/10/2024
TO-24-AUN-110SA1-2CB-02 | COUPLER/SECTIONALISING CB - AUNGIERSTOWN 110-AUNGIERSTOWN 110-110SA1-2CB | 5 | 5 | 5 | Scheduled | 07/10/2024 | 11/10/2024
TO-24-AUN-110SB1-2CB-01 | COUPLER/SECTIONALISING CB - AUNGIERSTOWN 110-AUNGIERSTOWN 110-110SB1-2CB | 5 | 5 | 5 | Scheduled | 07/10/2024 | 11/10/2024
TO-24-220 kV A1 @ BVK-01 | BUSBAR SECTION - BALLYVOUSKILL 220-BALLYVOUSKILL 220-220A1 | 5 | 5 | 5 | Scheduled | 07/10/2024 | 11/10/2024
TO-24-220 kV B1 @ BVK-01 | BUSBAR SECTION - BALLYVOUSKILL 220-BALLYVOUSKILL 220-220B1 | 5 | 5 | 5 | Scheduled | 07/10/2024 | 11/10/2024
TO-24-BVK-220K1-01 | COUPLER/SECTIONALISING CB - BALLYVOUSKILL 220-BALLYVOUSKILL 220-220K1 | 5 | 5 | 5 | Scheduled | 07/10/2024 | 11/10/2024
TO-24-BVK-220SA1-2CB-05 | COUPLER/SECTIONALISING CB - BALLYVOUSKILL 220-BALLYVOUSKILL 220-220SA1-2CB | 5 | 5 | 5 | Scheduled | 07/10/2024 | 11/10/2024
TO-24-BVK-220SB1-2CB-05 | COUPLER/SECTIONALISING CB - BALLYVOUSKILL 220-BALLYVOUSKILL 220-220SB1-2CB | 5 | 5 | 5 | Scheduled | 07/10/2024 | 11/10/2024
TO-24-110 kV A4 @ CBT-01 | BUSBAR SECTION - CASTLEBAGOT 110-CASTLEBAGOT 110-110A4 | 5 | 5 | 5 | Scheduled | 07/10/2024 | 11/10/2024
TO-24-110 kV B4 @ CBT-01 | BUSBAR SECTION - CASTLEBAGOT 110-CASTLEBAGOT 110-110B4 | 5 | 5 | 5 | Scheduled | 07/10/2024 | 11/10/2024
TO-24-CBT-110K4-01 | COUPLER/SECTIONALISING CB - CASTLEBAGOT 110-CASTLEBAGOT 110-110K4 | 5 | 5 | 5 | Scheduled | 07/10/2024 | 11/10/2024
TO-24-CBT-110SA2-4CB-01 | COUPLER/SECTIONALISING CB - CASTLEBAGOT 110-CASTLEBAGOT 110-110SA2-4CB | 5 | 5 | 5 | Scheduled | 07/10/2024 | 11/10/2024
TO-24-CBT-110SB2-4CB-01 | COUPLER/SECTIONALISING CB - CASTLEBAGOT 110-CASTLEBAGOT 110-110SB2-4CB | 5 | 5 | 5 | Scheduled | 07/10/2024 | 11/10/2024
TO-24-220 kV A1 @ CBT-03 | BUSBAR SECTION - CASTLEBAGOT 220-CASTLEBAGOT 220-220A1 | 24 | 17 | 17 | Proposed | 07/10/2024 | 30/10/2024
TO-24-220 kV B1 @ CBT-01 | BUSBAR SECTION - CASTLEBAGOT 220-CASTLEBAGOT 220-220B1 | 24 | 17 | 17 | Proposed | 07/10/2024 | 30/10/2024
TO-24-CBT-220K1-02 | COUPLER/SECTIONALISING CB - CASTLEBAGOT 220-CASTLEBAGOT 220-220K1 | 24 | 17 | 17 | Proposed | 07/10/2024 | 30/10/2024
TO-24-CBT-220SA1-2CB-05 | COUPLER/SECTIONALISING CB - CASTLEBAGOT 220-CASTLEBAGOT 220-220SA1-2CB | 24 | 17 | 17 | Proposed | 07/10/2024 | 30/10/2024
TO-24-CBT-220SB1-2CB-05 | COUPLER/SECTIONALISING CB - CASTLEBAGOT 220-CASTLEBAGOT 220-220SB1-2CB | 24 | 17 | 17 | Proposed | 07/10/2024 | 30/10/2024
TO-24-CBT-MAY-1-01 | 220kV FEEDER - CASTLEBAGOT 220-MAYNOOTH 220-1 | 24 | 17 | 17 | Proposed | 07/10/2024 | 30/10/2024
TO-24-CBT-MAY-1-04 | 220kV FEEDER - CASTLEBAGOT 220-MAYNOOTH 220-1 | 24 | 17 | 17 | Scheduled | 07/10/2024 | 30/10/2024
TO-24-CFM-T101-02 | TSO CUSTOMER TRANSFORMER - CASTLEFARM 110-CASTLEFARM 10-T101 | 5 | 5 | 5 | Reference | 07/10/2024 | 11/10/2024
TO-24-110 kV A2 @ CDU-04 | BUSBAR SECTION - CORDUFF 110-CORDUFF 110-110A2 | 19 | 15 |  | Scheduled | 07/10/2024 | 25/10/2024
TO-24-110 kV A4 @ CDU-03 | BUSBAR SECTION - CORDUFF 110-CORDUFF 110-110A4 | 19 | 15 |  | Scheduled | 07/10/2024 | 25/10/2024
TO-24-110 kV B2 @ CDU-03 | BUSBAR SECTION - CORDUFF 110-CORDUFF 110-110B2 | 19 | 15 |  | Scheduled | 07/10/2024 | 25/10/2024
TO-24-110 kV B4 @ CDU-04 | BUSBAR SECTION - CORDUFF 110-CORDUFF 110-110B4 | 19 | 15 |  | Scheduled | 07/10/2024 | 25/10/2024
TO-24-CUS-NEW-1-01 | 110kV FEEDER - CUSHALING 110-NEWBRIDGE 110-1 | 5 | 5 | 5 | Scheduled | 07/10/2024 | 11/10/2024
TO-24-400 kV A1 @ DSN-01 | BUSBAR SECTION - DUNSTOWN 400-DUNSTOWN 400-400A1 | 19 | 15 | 15 | Scheduled | 07/10/2024 | 25/10/2024
TO-24-400 kV B1 @ DSN-01 | BUSBAR SECTION - DUNSTOWN 400-DUNSTOWN 400-400B1 | 19 | 15 | 15 | Scheduled | 07/10/2024 | 25/10/2024
TO-24-DSN-T4201-03 | TRANSFORMER - DUNSTOWN 400-DUNSTOWN 220-T4201 | 19 | 15 | 15 | Scheduled | 07/10/2024 | 25/10/2024
TO-24-GI-KKY-1-02 | 110kV FEEDER - GREAT ISLAND 110-KILKENNY 110-1 | 5 | 5 |  | Scheduled | 07/10/2024 | 11/10/2024
TO-24-GI-WAT-1-05 | 110kV FEEDER - GREAT ISLAND 110-WATERFORD 110-1 | 5 | 5 |  | Scheduled | 07/10/2024 | 11/10/2024
TO-24-INC-MAY-2-03 | 220kV FEEDER - INCHICORE 220-MAYNOOTH 220-2 | 61 | 44 | 44 | Scheduled | 07/10/2024 | 06/12/2024
TO-24-INC-MAY-2-05 | 220kV FEEDER - INCHICORE 220-MAYNOOTH 220-2 | 58 | 41 | 41 | Proposed | 07/10/2024 | 03/12/2024
TO-24-KBY-KRA-1-01 | 110kV FEEDER - KILBARRY 110-KNOCKRAHA 110-1 | 12 | 10 |  | Scheduled | 07/10/2024 | 18/10/2024
TO-24-110 kV A2 @ KLN-03 | BUSBAR SECTION - KILLONAN 110-KILLONAN 110-110A2 | 9 | 7 | 7 | Scheduled | 07/10/2024 | 15/10/2024
TO-24-110 kV B2 @ KLN-04 | BUSBAR SECTION - KILLONAN 110-KILLONAN 110-110B2 | 9 | 7 | 7 | Scheduled | 07/10/2024 | 15/10/2024
TO-24-220 kV A2 @ KLN-04 | BUSBAR SECTION - KILLONAN 220-KILLONAN 220-220A2 | 9 | 7 | 7 | Scheduled | 07/10/2024 | 15/10/2024
TO-24-220 kV B2 @ KLN-03 | BUSBAR SECTION - KILLONAN 220-KILLONAN 220-220B2 | 9 | 7 | 7 | Scheduled | 07/10/2024 | 15/10/2024
TO-24-KLN-T2102-02 | TRANSFORMER - KILLONAN 220-KILLONAN 110-T2102 | 9 | 7 | 7 | Scheduled | 07/10/2024 | 15/10/2024
TO-24-110 kV A1 @ KRA-02 | BUSBAR SECTION - KNOCKRAHA 110-KNOCKRAHA 110-110A1 | 12 | 10 | 10 | Scheduled | 07/10/2024 | 18/10/2024
TO-24-110 kV B1 @ KRA-02 | BUSBAR SECTION - KNOCKRAHA 110-KNOCKRAHA 110-110B1 | 12 | 10 | 10 | Scheduled | 07/10/2024 | 18/10/2024
TO-24-LA-MUL-1-01 | 110kV FEEDER - LANESBORO 110-MULLINGAR 110-1 | 12 | 10 |  | Scheduled | 07/10/2024 | 18/10/2024
TO-24-LIS-110SA1-01 | SECTIONALISING DISCONNECT - LISDRUM 110-LISDRUM 110-110SA1 | 5 | 5 | 5 | Scheduled | 07/10/2024 | 11/10/2024
TO-24-LIS-110SA2-01 | SECTIONALISING DISCONNECT - LISDRUM 110-LISDRUM 110-110SA2 | 5 | 5 | 5 | Scheduled | 07/10/2024 | 11/10/2024
TO-24-LIS-CAP2-02 | CAPACITOR/SVC/REACTOR - LISDRUM 110-LISDRUM 110-CAP2 | 5 | 5 | 5 | Scheduled | 07/10/2024 | 11/10/2024
TO-24-LIS-LSA-1-01 | 110kV FEEDER - LISDRUM 110-LISLEA 110-1 | 5 | 5 | 5 | Scheduled | 07/10/2024 | 11/10/2024
TO-24-LIS-LSA-1-02 | 110kV FEEDER - LISDRUM 110-LISLEA 110-1 | 39 | 28 | 28 | Scheduled | 07/10/2024 | 14/11/2024
TO-24-LIS-T142-01 | DISTRIBUTION TRANSFORMER - LISDRUM 110-LISDRUM 38-T142 | 5 | 5 | 5 | Reference | 07/10/2024 | 11/10/2024
TO-24-110 kV A1 @ LOU-08 | BUSBAR SECTION - LOUTH 110-LOUTH 110-110A1 | 1 | 1 | 1 | Scheduled | 07/10/2024 | 07/10/2024
TO-24-110 kV A2 @ LOU-06 | BUSBAR SECTION - LOUTH 110-LOUTH 110-110A2 | 1 | 1 | 1 | Scheduled | 07/10/2024 | 07/10/2024
TO-24-110 kV B1 @ LOU-08 | BUSBAR SECTION - LOUTH 110-LOUTH 110-110B1 | 1 | 1 | 1 | Scheduled | 07/10/2024 | 07/10/2024
TO-24-110 kV B2 @ LOU-06 | BUSBAR SECTION - LOUTH 110-LOUTH 110-110B2 | 1 | 1 | 1 | Scheduled | 07/10/2024 | 07/10/2024
TO-24-LOU-T2104-06 | TRANSFORMER - LOUTH 220-LOUTH 110-T2104 | 1 | 1 | 1 | Scheduled | 07/10/2024 | 07/10/2024
TO-24-220 kV A1 @ MAY-05 | BUSBAR SECTION - MAYNOOTH 220-MAYNOOTH 220-220A1 | 24 | 17 | 17 | Proposed | 07/10/2024 | 30/10/2024
TO-24-220 kV A2 @ MAY-02 | BUSBAR SECTION - MAYNOOTH 220-MAYNOOTH 220-220A2 | 64 | 45 | 45 | Proposed | 07/10/2024 | 09/12/2024
TO-24-220 kV B1 @ MAY-05 | BUSBAR SECTION - MAYNOOTH 220-MAYNOOTH 220-220B1 | 24 | 17 | 17 | Proposed | 07/10/2024 | 30/10/2024
TO-24-220 kV B2 @ MAY-02 | BUSBAR SECTION - MAYNOOTH 220-MAYNOOTH 220-220B2 | 64 | 45 | 45 | Proposed | 07/10/2024 | 09/12/2024
TO-24-MOY-TAW-2-02 | 110kV FEEDER - MOY 110-TAWNAGHMORE 110-2 | 5 | 5 | 5 | Scheduled | 07/10/2024 | 11/10/2024
TO-24-KPG-MP GIS-1-01 | 220kV FEEDER - KILPADDOGE 220-MONEYPOINT GIS 220-1 | 8 | 6 | 6 | Scheduled | 08/10/2024 | 15/10/2024
TO-24-LLA-110K1-02 | COUPLER/SECTIONALISING CB - LENALEA 110-LENALEA 110-110K1 | 1 | 1 | 1 | Scheduled | 08/10/2024 | 08/10/2024
TO-24-110 kV A2 @ LOU-08 | BUSBAR SECTION - LOUTH 110-LOUTH 110-110A2 | 25 | 18 | 18 | Scheduled | 08/10/2024 | 01/11/2024
TO-24-110 kV B2 @ LOU-08 | BUSBAR SECTION - LOUTH 110-LOUTH 110-110B2 | 25 | 18 | 18 | Scheduled | 08/10/2024 | 01/11/2024
TO-24-220 kV A2 @ LOU-03 | BUSBAR SECTION - LOUTH 220-LOUTH 220-220A2 | 25 | 18 | 18 | Scheduled | 08/10/2024 | 01/11/2024
TO-24-220 kV B2 @ LOU-03 | BUSBAR SECTION - LOUTH 220-LOUTH 220-220B2 | 25 | 18 | 18 | Scheduled | 08/10/2024 | 01/11/2024
TO-24-LOU-T2104-01 | TRANSFORMER - LOUTH 220-LOUTH 110-T2104 | 25 | 18 | 18 | Scheduled | 08/10/2024 | 01/11/2024
TO-24-RYB GIS-110K4-02 | COUPLER/SECTIONALISING CB - RYEBROOK GIS 110-RYEBROOK GIS 110-110K4 | 1 | 1 | 1 | Scheduled | 08/10/2024 | 08/10/2024
TO-24-GAL-T103-01 | DISTRIBUTION TRANSFORMER - GALWAY 110-GALWAY 10-T103 | 84 | 57 | 57 | Scheduled | 09/10/2024 | 31/12/2024
TO-24-CDU-RYB GIS-1-03 | 110kV FEEDER - CORDUFF 110-RYEBROOK GIS 110-1 | 1 | 1 | 1 | Scheduled | 10/10/2024 | 10/10/2024
TO-24-110 kV A1 @ RYB GIS-01 | BUSBAR SECTION - RYEBROOK GIS 110-RYEBROOK GIS 110-110A1 | 1 | 1 | 1 | Scheduled | 10/10/2024 | 10/10/2024
TO-24-110 kV A2 @ RYB GIS-01 | BUSBAR SECTION - RYEBROOK GIS 110-RYEBROOK GIS 110-110A2 | 1 | 1 | 1 | Scheduled | 10/10/2024 | 10/10/2024
TO-24-110 kV A3 @ RYB GIS-01 | BUSBAR SECTION - RYEBROOK GIS 110-RYEBROOK GIS 110-110A3 | 1 | 1 | 1 | Scheduled | 10/10/2024 | 10/10/2024
TO-24-110 kV A4 @ RYB GIS-01 | BUSBAR SECTION - RYEBROOK GIS 110-RYEBROOK GIS 110-110A4 | 1 | 1 | 1 | Scheduled | 10/10/2024 | 10/10/2024
TO-24-RYB GIS-110K3-02 | COUPLER/SECTIONALISING CB - RYEBROOK GIS 110-RYEBROOK GIS 110-110K3 | 1 | 1 | 1 | Scheduled | 10/10/2024 | 10/10/2024
TO-24-RYB GIS-110K4-03 | COUPLER/SECTIONALISING CB - RYEBROOK GIS 110-RYEBROOK GIS 110-110K4 | 1 | 1 | 1 | Scheduled | 10/10/2024 | 10/10/2024
TO-24-RYB GIS-110SA1-2CB-02 | COUPLER/SECTIONALISING CB - RYEBROOK GIS 110-RYEBROOK GIS 110-110SA1-2CB | 1 | 1 | 1 | Scheduled | 10/10/2024 | 10/10/2024
TO-24-RYB GIS-110SA1-3CB-02 | COUPLER/SECTIONALISING CB - RYEBROOK GIS 110-RYEBROOK GIS 110-110SA1-3CB | 1 | 1 | 1 | Scheduled | 10/10/2024 | 10/10/2024
TO-24-RYB GIS-110SA2-4CB-02 | COUPLER/SECTIONALISING CB - RYEBROOK GIS 110-RYEBROOK GIS 110-110SA2-4CB | 1 | 1 | 1 | Scheduled | 10/10/2024 | 10/10/2024
TO-24-220 kV A2 @ BVK-04 | BUSBAR SECTION - BALLYVOUSKILL 220-BALLYVOUSKILL 220-220A2 | 10 | 8 | 8 | Scheduled | 14/10/2024 | 23/10/2024
TO-24-220 kV B2 @ BVK-04 | BUSBAR SECTION - BALLYVOUSKILL 220-BALLYVOUSKILL 220-220B2 | 10 | 8 | 8 | Scheduled | 14/10/2024 | 23/10/2024
TO-24-BVK-220K2-01 | COUPLER/SECTIONALISING CB - BALLYVOUSKILL 220-BALLYVOUSKILL 220-220K2 | 10 | 8 | 8 | Scheduled | 14/10/2024 | 23/10/2024
TO-24-BVK-220SA1-2CB-06 | COUPLER/SECTIONALISING CB - BALLYVOUSKILL 220-BALLYVOUSKILL 220-220SA1-2CB | 10 | 8 | 8 | Scheduled | 14/10/2024 | 23/10/2024
TO-24-BVK-220SB1-2CB-06 | COUPLER/SECTIONALISING CB - BALLYVOUSKILL 220-BALLYVOUSKILL 220-220SB1-2CB | 10 | 8 | 8 | Scheduled | 14/10/2024 | 23/10/2024
TO-24-110 kV A1 @ BAG-01 | BUSBAR SECTION - BARNAGEERAGH 110-BARNAGEERAGH 110-110A1 | 2 | 2 | 2 | Scheduled | 14/10/2024 | 15/10/2024
TO-24-110 kV B1 @ BAG-01 | BUSBAR SECTION - BARNAGEERAGH 110-BARNAGEERAGH 110-110B1 | 2 | 2 | 2 | Scheduled | 14/10/2024 | 15/10/2024
TO-24-BAG-110K1-01 | COUPLER/SECTIONALISING CB - BARNAGEERAGH 110-BARNAGEERAGH 110-110K1 | 2 | 2 | 2 | Scheduled | 14/10/2024 | 15/10/2024
TO-24-BAG-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - BARNAGEERAGH 110-BARNAGEERAGH 110-110SA1-2CB | 2 | 2 | 2 | Scheduled | 14/10/2024 | 15/10/2024
TO-24-BAG-110SB1-2CB-01 | COUPLER/SECTIONALISING CB - BARNAGEERAGH 110-BARNAGEERAGH 110-110SB1-2CB | 2 | 2 | 2 | Scheduled | 14/10/2024 | 15/10/2024
TO-24-CSH-GAL GIS-1-03 | 110kV FEEDER - CASHLA 110-GALWAY GIS 110-1 | 2 | 2 | 2 | Scheduled | 14/10/2024 | 15/10/2024
TO-24-CLA-220K1-2-03 | COUPLER/SECTIONALISING CB - CLASHAVOON 220-CLASHAVOON 220-220K1-2 | 5 | 5 | 5 | Scheduled | 14/10/2024 | 18/10/2024
TO-24-CLA-KRA-1-05 | 220kV FEEDER - CLASHAVOON 220-KNOCKRAHA 220-1 | 5 | 5 | 5 | Scheduled | 14/10/2024 | 18/10/2024
TO-24-CLA-T2102-02 | TRANSFORMER - CLASHAVOON 220-CLASHAVOON 110-T2102 | 5 | 5 | 5 | Scheduled | 14/10/2024 | 18/10/2024
TO-24-COW-WHI-1-04 | 110kV FEEDER - COW CROSS 110-WHITEGATE 110-1 | 12 | 10 | 10 | Scheduled | 14/10/2024 | 25/10/2024
TO-24-DDK-110SA1-01 | SECTIONALISING DISCONNECT - DUNDALK 110-DUNDALK 110-110SA1 | 5 | 5 | 5 | Scheduled | 14/10/2024 | 18/10/2024
TO-24-DDK-110SA2-03 | SECTIONALISING DISCONNECT - DUNDALK 110-DUNDALK 110-110SA2 | 5 | 5 | 5 | Scheduled | 14/10/2024 | 18/10/2024
TO-24-DDK-MLN-1-03 | 110kV FEEDER - DUNDALK 110-MULLAGHARLIN 110-1 | 5 | 5 | 5 | Scheduled | 14/10/2024 | 18/10/2024
TO-24-DDK-T141-02 | DISTRIBUTION TRANSFORMER - DUNDALK 110-DUNDALK 38-T141 | 5 | 5 | 5 | Reference | 14/10/2024 | 18/10/2024
TO-24-110 kV A3 @ GAL GIS-05 | BUSBAR SECTION - GALWAY GIS 110-GALWAY GIS 110-110A3 | 2 | 2 | 2 | Scheduled | 14/10/2024 | 15/10/2024
TO-24-110 kV B3 @ GAL GIS-05 | BUSBAR SECTION - GALWAY GIS 110-GALWAY GIS 110-110B3 | 2 | 2 | 2 | Scheduled | 14/10/2024 | 15/10/2024
TO-24-GAL GIS-110K3-07 | COUPLER/SECTIONALISING CB - GALWAY GIS 110-GALWAY GIS 110-110K3 | 2 | 2 | 2 | Scheduled | 14/10/2024 | 15/10/2024
TO-24-GAL GIS-110SA1-3CB-09 | COUPLER/SECTIONALISING CB - GALWAY GIS 110-GALWAY GIS 110-110SA1-3CB | 2 | 2 | 2 | Scheduled | 14/10/2024 | 15/10/2024
TO-24-GAL GIS-110SB1-3CB-09 | COUPLER/SECTIONALISING CB - GALWAY GIS 110-GALWAY GIS 110-110SB1-3CB | 2 | 2 | 2 | Scheduled | 14/10/2024 | 15/10/2024
TO-24-GAR-PLA-1-04 | 110kV FEEDER - GARBALLAGH 110-PLATIN 110-1 | 5 | 5 | 5 | Scheduled | 14/10/2024 | 18/10/2024
TO-24-MTN-MUN-2-02 | 110kV FEEDER - MONETEEN 110-MUNGRET 110-2 | 3 | 3 | 3 | Scheduled | 14/10/2024 | 16/10/2024
TO-24-MOY-CAP1-02 | CAPACITOR/SVC/REACTOR - MOY 110-MOY 110-CAP1 | 13 | 10 | 10 | Scheduled | 14/10/2024 | 26/10/2024
TO-24-MOY-TAW-1-03 | 110kV FEEDER - MOY 110-TAWNAGHMORE 110-1 | 19 | 14 | 14 | Scheduled | 14/10/2024 | 01/11/2024
TO-24-MUN-T102-01 | TSO CUSTOMER TRANSFORMER - MUNGRET 110-MUNGRET 10-T102 | 3 | 3 | 3 | Reference | 14/10/2024 | 16/10/2024
TO-24-NEW-PLS-1-03 | 110kV FEEDER - NEWBRIDGE 110-PORTLAOISE 110-1 | 12 | 10 | 10 | Scheduled | 14/10/2024 | 25/10/2024
TO-24-110 kV A1 @ PLS-02 | BUSBAR SECTION - PORTLAOISE 110-PORTLAOISE 110-110A1 | 12 | 10 | 10 | Scheduled | 14/10/2024 | 25/10/2024
TO-24-110 kV B1 @ PLS-01 | BUSBAR SECTION - PORTLAOISE 110-PORTLAOISE 110-110B1 | 12 | 10 | 10 | Scheduled | 14/10/2024 | 25/10/2024
TO-24-110 kV A1 @ SNU-03 | BUSBAR SECTION - SNUGBOROUGH 110-SNUGBOROUGH 110-110A1 | 2 | 2 | 2 | Scheduled | 14/10/2024 | 15/10/2024
TO-24-110 kV B1 @ SNU-03 | BUSBAR SECTION - SNUGBOROUGH 110-SNUGBOROUGH 110-110B1 | 2 | 2 | 2 | Scheduled | 14/10/2024 | 15/10/2024
TO-24-SNU-110K1-02 | COUPLER/SECTIONALISING CB - SNUGBOROUGH 110-SNUGBOROUGH 110-110K1 | 2 | 2 | 2 | Scheduled | 14/10/2024 | 15/10/2024
TO-24-SNU-110SA1-2CB-03 | COUPLER/SECTIONALISING CB - SNUGBOROUGH 110-SNUGBOROUGH 110-110SA1-2CB | 2 | 2 | 2 | Scheduled | 14/10/2024 | 15/10/2024
TO-24-SNU-110SB1-2CB-03 | COUPLER/SECTIONALISING CB - SNUGBOROUGH 110-SNUGBOROUGH 110-110SB1-2CB | 2 | 2 | 2 | Scheduled | 14/10/2024 | 15/10/2024
TO-24-TIP-110SA1-02 | SECTIONALISING DISCONNECT - TIPPERARY 110-TIPPERARY 110-110SA1 | 5 | 5 | 5 | Scheduled | 14/10/2024 | 18/10/2024
TO-24-TIP-110SA2-01 | SECTIONALISING DISCONNECT - TIPPERARY 110-TIPPERARY 110-110SA2 | 5 | 5 | 5 | Scheduled | 14/10/2024 | 18/10/2024
TO-24-220 kV A1 @ TB-02 | BUSBAR SECTION - TARBERT 220-TARBERT 220-220A1 | 6 | 4 | 4 | Scheduled | 15/10/2024 | 20/10/2024
TO-24-220 kV B1 @ TB-02 | BUSBAR SECTION - TARBERT 220-TARBERT 220-220B1 | 6 | 4 | 4 | Scheduled | 15/10/2024 | 20/10/2024
TO-24-TB-T102-02 | GENERATOR TRANSFORMER - TARBERT 110-TARBERT G2-T102 | 2 | 2 | 2 | Scheduled | 15/10/2024 | 16/10/2024
TO-24-LSA-T131-01 | GENERATOR TRANSFORMER - LISLEA 110-LISLEA 33-T131 | 1 | 1 | 1 | Scheduled | 16/10/2024 | 16/10/2024
TO-24-MP GIS-400SA2-4CB-01 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 400-MONEYPOINT GIS 400-400SA2-4CB | 1 | 1 | 1 | Scheduled | 16/10/2024 | 16/10/2024
TO-24-MTN-MUN-1-02 | 110kV FEEDER - MONETEEN 110-MUNGRET 110-1 | 2 | 2 | 2 | Scheduled | 17/10/2024 | 18/10/2024
TO-24-MP GIS-400SB1-2CB-01 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 400-MONEYPOINT GIS 400-400SB1-2CB | 1 | 1 | 1 | Scheduled | 17/10/2024 | 17/10/2024
TO-24-MUN-T101-01 | TSO CUSTOMER TRANSFORMER - MUNGRET 110-MUNGRET 10-T101 | 2 | 2 | 2 | Reference | 17/10/2024 | 18/10/2024
TO-24-110 kV A2 @ CF-03 | BUSBAR SECTION - CATHALEENS FALL 110-CATHALEENS FALL 110-110A2 | 1 | 1 | 1 | Scheduled | 18/10/2024 | 18/10/2024
TO-24-CF-SRA-2-02 | 110kV FEEDER - CATHALEENS FALL 110-SRANANAGH 110-2 | 1 | 1 | 1 | Scheduled | 18/10/2024 | 18/10/2024
TO-24-KIN-T1/T2-03 | GENERATOR TRANSFORMER - KINNEGAD 110-RHODE 110-T1/T2 | 4 | 2 | 2 | Scheduled | 18/10/2024 | 21/10/2024
TO-24-RRU-T122-05 | GENERATOR TRANSFORMER - RATRUSSAN 110-RATRUSSAN 20-T122 | 1 | 1 | 1 | Scheduled | 18/10/2024 | 18/10/2024
TO-24-220 kV A2 @ CSH-04 | BUSBAR SECTION - CASHLA 220-CASHLA 220-220A2 | 12 | 9 | 9 | Scheduled | 21/10/2024 | 01/11/2024
TO-24-220 kV B2 @ CSH-06 | BUSBAR SECTION - CASHLA 220-CASHLA 220-220B2 | 12 | 9 | 9 | Scheduled | 21/10/2024 | 01/11/2024
TO-24-CSH-T2102-03 | TRANSFORMER - CASHLA 220-CASHLA 110-T2102 | 12 | 9 | 9 | Scheduled | 21/10/2024 | 01/11/2024
TO-24-110 kV A2 @ CLG-01 | BUSBAR SECTION - CLOGHRAN 110-CLOGHRAN 110-110A2 | 5 | 5 | 5 | Scheduled | 21/10/2024 | 25/10/2024
TO-24-110 kV B2 @ CLG-01 | BUSBAR SECTION - CLOGHRAN 110-CLOGHRAN 110-110B2 | 5 | 5 | 5 | Scheduled | 21/10/2024 | 25/10/2024
TO-24-CLG-110K2-02 | COUPLER/SECTIONALISING CB - CLOGHRAN 110-CLOGHRAN 110-110K2 | 5 | 5 | 5 | Scheduled | 21/10/2024 | 25/10/2024
TO-24-CLG-110SA1-2CB-04 | COUPLER/SECTIONALISING CB - CLOGHRAN 110-CLOGHRAN 110-110SA1-2CB | 5 | 5 | 5 | Scheduled | 21/10/2024 | 25/10/2024
TO-24-CLG-110SB1-2CB-04 | COUPLER/SECTIONALISING CB - CLOGHRAN 110-CLOGHRAN 110-110SB1-2CB | 5 | 5 | 5 | Scheduled | 21/10/2024 | 25/10/2024
TO-24-CLG-T126-02 | TSO CUSTOMER TRANSFORMER - CLOGHRAN 110-CLOGHRAN 20-T126 | 5 | 5 | 5 | Scheduled | 21/10/2024 | 25/10/2024
TO-24-GAL-GAL GIS-1-04 | 110kV FEEDER - GALWAY 110-GALWAY GIS 110-1 | 72 | 49 | 49 | Proposed | 21/10/2024 | 31/12/2024
TO-24-GAL GIS-T142-05 | DISTRIBUTION TRANSFORMER - GALWAY GIS 110-GALWAY 38-T142 | 5 | 5 | 5 | Reference (Proposed) | 21/10/2024 | 25/10/2024
TO-24-KYT-T232-02 | TSO CUSTOMER TRANSFORMER - KELLYSTOWN 220-KELLYSTOWN 34.5-T232 | 19 | 14 | 14 | Scheduled | 21/10/2024 | 08/11/2024
TO-24-KBY-KRA-2-01 | 110kV FEEDER - KILBARRY 110-KNOCKRAHA 110-2 | 5 | 5 | 5 | Scheduled | 21/10/2024 | 25/10/2024
TO-24-KPG-KNR-1-110-01 | 110kV FEEDER - KILPADDOGE 110-KNOCKANURE 110-1-110 | 5 | 5 | 5 | Scheduled | 21/10/2024 | 25/10/2024
TO-24-LIM-RAT-1-04 | 110kV FEEDER - LIMERICK 110-RATHKEALE 110-1 | 5 | 5 | 5 | Scheduled | 21/10/2024 | 25/10/2024
TO-24-MLC-TSB-1-02 | 110kV FEEDER - MOUNTLUCAS 110-THORNSBERRY 110-1 | 22 | 15 | 15 | Proposed | 21/10/2024 | 11/11/2024
TO-24-OBE-PLA-1-04 | 110kV FEEDER - OLDBRIDGE 110-PLATIN 110-1 | 5 | 5 | 5 | Scheduled | 21/10/2024 | 25/10/2024
TO-24-RAT-110SA1-01 | SECTIONALISING DISCONNECT - RATHKEALE 110-RATHKEALE 110-110SA1 | 5 | 5 | 5 | Scheduled | 21/10/2024 | 25/10/2024
TO-24-RAT-110SA2-01 | SECTIONALISING DISCONNECT - RATHKEALE 110-RATHKEALE 110-110SA2 | 5 | 5 | 5 | Scheduled | 21/10/2024 | 25/10/2024
TO-24-RAT-T142-01 | DISTRIBUTION TRANSFORMER - RATHKEALE 110-RATHKEALE 38-T142 | 5 | 5 | 5 | Reference | 21/10/2024 | 25/10/2024
TO-24-110 kV A2 @ SNU-04 | BUSBAR SECTION - SNUGBOROUGH 110-SNUGBOROUGH 110-110A2 | 5 | 5 | 5 | Scheduled | 21/10/2024 | 25/10/2024
TO-24-110 kV B2 @ SNU-05 | BUSBAR SECTION - SNUGBOROUGH 110-SNUGBOROUGH 110-110B2 | 5 | 5 | 5 | Scheduled | 21/10/2024 | 25/10/2024
TO-24-SNU-110K2-06 | COUPLER/SECTIONALISING CB - SNUGBOROUGH 110-SNUGBOROUGH 110-110K2 | 5 | 5 | 5 | Scheduled | 21/10/2024 | 25/10/2024
TO-24-SNU-110SA1-2CB-09 | COUPLER/SECTIONALISING CB - SNUGBOROUGH 110-SNUGBOROUGH 110-110SA1-2CB | 5 | 5 | 5 | Scheduled | 21/10/2024 | 25/10/2024
TO-24-SNU-110SB1-2CB-10 | COUPLER/SECTIONALISING CB - SNUGBOROUGH 110-SNUGBOROUGH 110-110SB1-2CB | 5 | 5 | 5 | Scheduled | 21/10/2024 | 25/10/2024
TO-24-SNU-T102-04 | TSO CUSTOMER TRANSFORMER - SNUGBOROUGH 110-SNUGBOROUGH 10-T102 | 5 | 5 | 5 | Scheduled | 21/10/2024 | 25/10/2024
TO-24-KLN-T2103-01 | TRANSFORMER - KILLONAN 220-KILLONAN 110-T2103 | 3 | 3 | 3 | Scheduled | 22/10/2024 | 24/10/2024
TO-24-KTL-T142-01 | DISTRIBUTION TRANSFORMER - KILTEEL 110-KILTEEL 38-T142 | 2 | 2 | 2 | Reference | 22/10/2024 | 23/10/2024
TO-24-PLS-T142-01 | DISTRIBUTION TRANSFORMER - PORTLAOISE 110-PORTLAOISE 38-T142 | 2 | 2 | 2 | Reference | 22/10/2024 | 23/10/2024
TO-24-FIN GIS-110K1-01 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110K1 | 1 | 1 | 1 | Scheduled | 23/10/2024 | 23/10/2024
TO-24-220 kV A2 @ FLA-06 | BUSBAR SECTION - FLAGFORD 220-FLAGFORD 220-220A2 | 1 | 1 | 1 | Proposed | 23/10/2024 | 23/10/2024
TO-24-220 kV B2 @ FLA-05 | BUSBAR SECTION - FLAGFORD 220-FLAGFORD 220-220B2 | 1 | 1 | 1 | Proposed | 23/10/2024 | 23/10/2024
TO-24-GAL GIS-110K2-01 | COUPLER/SECTIONALISING CB - GALWAY GIS 110-GALWAY GIS 110-110K2 | 1 | 1 | 1 | Scheduled | 23/10/2024 | 23/10/2024
TO-24-KIN-MUL-1-02 | 110kV FEEDER - KINNEGAD 110-MULLINGAR 110-1 | 3 | 3 | 3 | Scheduled | 23/10/2024 | 25/10/2024
TO-24-GAL GIS-110K3-03 | COUPLER/SECTIONALISING CB - GALWAY GIS 110-GALWAY GIS 110-110K3 | 1 | 1 | 1 | Scheduled | 24/10/2024 | 24/10/2024
TO-24-PLS-T141-01 | DISTRIBUTION TRANSFORMER - PORTLAOISE 110-PORTLAOISE 38-T141 | 2 | 2 | 2 | Reference | 24/10/2024 | 25/10/2024
TO-24-GAL GIS-110SA1-3CB-04 | COUPLER/SECTIONALISING CB - GALWAY GIS 110-GALWAY GIS 110-110SA1-3CB | 1 | 1 |  | Scheduled | 25/10/2024 | 25/10/2024
TO-24-CVW-110SA1-01 | SECTIONALISING DISCONNECT - CASTLEVIEW 110-CASTLEVIEW 110-110SA1 | 9 | 6 | 6 | Proposed | 28/10/2024 | 05/11/2024
TO-24-CVW-110SA2-01 | SECTIONALISING DISCONNECT - CASTLEVIEW 110-CASTLEVIEW 110-110SA2 | 9 | 6 | 6 | Proposed | 28/10/2024 | 05/11/2024
TO-24-CVW-COW-1-03 | 110kV FEEDER - CASTLEVIEW 110-COW CROSS 110-1 | 9 | 6 | 6 | Proposed | 28/10/2024 | 05/11/2024
TO-24-CVW-T101-01 | DISTRIBUTION TRANSFORMER - CASTLEVIEW 110-CASTLEVIEW 10-T101 | 9 | 6 | 6 | Reference (Proposed) | 28/10/2024 | 05/11/2024
TO-24-GAL GIS-KNY-1-03 | 110kV FEEDER - GALWAY GIS 110-KNOCKRANNY 110-1 | 5 | 4 | 4 | Proposed | 28/10/2024 | 01/11/2024
TO-24-BAN-DMY-1-04 | 110kV FEEDER - BANDON 110-DUNMANWAY 110-1 | 11 | 9 | 9 | Proposed | 29/10/2024 | 08/11/2024
TO-24-CLA-DMY-1-01 | 110kV FEEDER - CLASHAVOON 110-DUNMANWAY 110-1 | 11 | 9 | 9 | Proposed | 29/10/2024 | 08/11/2024
TO-24-CLG-T122-01 | TSO CUSTOMER TRANSFORMER - CLOGHRAN 110-CLOGHRAN 20-T122 | 2 | 2 | 2 | Proposed | 29/10/2024 | 30/10/2024
TO-24-CDU-MCE-1-04 | 110kV FEEDER - CORDUFF 110-MACETOWN 110-1 | 4 | 4 | 4 | Proposed | 29/10/2024 | 01/11/2024
TO-24-DMY-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - DUNMANWAY 110-DUNMANWAY 110-110SA1-2CB | 11 | 9 | 9 | Proposed | 29/10/2024 | 08/11/2024
TO-24-DMY-CAP2-02 | CAPACITOR/SVC/REACTOR - DUNMANWAY 110-DUNMANWAY 110-CAP2 | 11 | 9 | 9 | Proposed | 29/10/2024 | 08/11/2024
TO-24-DMY-T142-02 | DISTRIBUTION TRANSFORMER - DUNMANWAY 110-DUNMANWAY 38-T142 | 11 | 9 | 9 | Reference (Proposed) | 29/10/2024 | 08/11/2024
TO-24-GAL GIS-110SB1-3CB-04 | COUPLER/SECTIONALISING CB - GALWAY GIS 110-GALWAY GIS 110-110SB1-3CB | 1 | 1 | 1 | Scheduled | 29/10/2024 | 29/10/2024
TO-24-110 kV A1 @ GOR-03 | BUSBAR SECTION - GORMAN 110-GORMAN 110-110A1 | 7 | 5 | 5 | Proposed | 29/10/2024 | 04/11/2024
TO-24-110 kV B1 @ GOR-02 | BUSBAR SECTION - GORMAN 110-GORMAN 110-110B1 | 7 | 5 | 5 | Proposed | 29/10/2024 | 04/11/2024
TO-24-GOR-NAV-3-02 | 110kV FEEDER - GORMAN 110-NAVAN 110-3 | 7 | 5 | 5 | Proposed | 29/10/2024 | 04/11/2024
TO-24-KLN-KRA-1-01 | 220kV FEEDER - KILLONAN 220-KNOCKRAHA 220-1 | 4 | 4 |  | Scheduled | 29/10/2024 | 01/11/2024
TO-24-KTL-MAY-1-02 | 110kV FEEDER - KILTEEL 110-MAYNOOTH 110-1 | 25 | 19 | 19 | Scheduled | 29/10/2024 | 22/11/2024
TO-24-KNR-TRI-2-03 | 110kV FEEDER - KNOCKANURE 110-TRIEN 110-2 | 2 | 2 | 2 | Proposed | 29/10/2024 | 30/10/2024
TO-24-110 kV A2 @ SNU-05 | BUSBAR SECTION - SNUGBOROUGH 110-SNUGBOROUGH 110-110A2 | 11 | 9 | 9 | Scheduled | 29/10/2024 | 08/11/2024
TO-24-110 kV B2 @ SNU-06 | BUSBAR SECTION - SNUGBOROUGH 110-SNUGBOROUGH 110-110B2 | 11 | 9 | 9 | Scheduled | 29/10/2024 | 08/11/2024
TO-24-SNU-110K2-07 | COUPLER/SECTIONALISING CB - SNUGBOROUGH 110-SNUGBOROUGH 110-110K2 | 11 | 9 | 9 | Scheduled | 29/10/2024 | 08/11/2024
TO-24-SNU-110SA1-2CB-10 | COUPLER/SECTIONALISING CB - SNUGBOROUGH 110-SNUGBOROUGH 110-110SA1-2CB | 11 | 9 | 9 | Scheduled | 29/10/2024 | 08/11/2024
TO-24-SNU-110SB1-2CB-11 | COUPLER/SECTIONALISING CB - SNUGBOROUGH 110-SNUGBOROUGH 110-110SB1-2CB | 11 | 9 | 9 | Scheduled | 29/10/2024 | 08/11/2024
TO-24-SNU-T104-01 | TSO CUSTOMER TRANSFORMER - SNUGBOROUGH 110-SNUGBOROUGH 10-T104 | 11 | 9 | 9 | Scheduled | 29/10/2024 | 08/11/2024
TO-24-TRI-110SA1-2CB-02 | COUPLER/SECTIONALISING CB - TRIEN 110-TRIEN 110-110SA1-2CB | 1 | 1 | 1 | Proposed | 29/10/2024 | 29/10/2024
TO-24-TRI-T142-03 | DISTRIBUTION TRANSFORMER - TRIEN 110-TRIEN 38-T142 | 1 | 1 | 1 | Reference (Proposed) | 29/10/2024 | 29/10/2024
TO-24-BAN-BRI-2-01 | 110kV FEEDER - BANDON 110-BRINNY 110-2 | 1 | 1 | 1 | Proposed | 30/10/2024 | 30/10/2024
TO-24-BRI-T102-01 | TSO CUSTOMER TRANSFORMER - BRINNY 110-BRINNY 10-T102 | 1 | 1 | 1 | Proposed | 30/10/2024 | 30/10/2024
TO-24-CBT-CLU-1-01 | 110kV FEEDER - CASTLEBAGOT 110-CLUTTERLAND 110-1 | 3 | 3 | 3 | Scheduled | 30/10/2024 | 01/11/2024
TO-24-CLG-T124-01 | TSO CUSTOMER TRANSFORMER - CLOGHRAN 110-CLOGHRAN 20-T124 | 2 | 2 | 2 | Proposed | 30/10/2024 | 31/10/2024
TO-24-220 kV A1 @ CBT-01 | BUSBAR SECTION - CASTLEBAGOT 220-CASTLEBAGOT 220-220A1 | 26 | 18 | 18 | Proposed | 31/10/2024 | 25/11/2024
TO-24-220 kV B1 @ CBT-03 | BUSBAR SECTION - CASTLEBAGOT 220-CASTLEBAGOT 220-220B1 | 26 | 18 | 18 | Proposed | 31/10/2024 | 25/11/2024
TO-24-CBT-220K1-03 | COUPLER/SECTIONALISING CB - CASTLEBAGOT 220-CASTLEBAGOT 220-220K1 | 26 | 18 | 18 | Proposed | 31/10/2024 | 25/11/2024
TO-24-CBT-220SA1-2CB-06 | COUPLER/SECTIONALISING CB - CASTLEBAGOT 220-CASTLEBAGOT 220-220SA1-2CB | 26 | 18 | 18 | Proposed | 31/10/2024 | 25/11/2024
TO-24-CBT-220SB1-2CB-06 | COUPLER/SECTIONALISING CB - CASTLEBAGOT 220-CASTLEBAGOT 220-220SB1-2CB | 26 | 18 | 18 | Proposed | 31/10/2024 | 25/11/2024
TO-24-CBT-INC-1-03 | 220kV FEEDER - CASTLEBAGOT 220-INCHICORE 220-1 | 21 | 15 | 15 | Proposed | 31/10/2024 | 20/11/2024
TO-24-CBT-INC-1-05 | 220kV FEEDER - CASTLEBAGOT 220-INCHICORE 220-1 | 21 | 15 | 15 | Proposed | 31/10/2024 | 20/11/2024
TO-24-CBT-INC-1-02 | 220kV FEEDER - CASTLEBAGOT 220-INCHICORE 220-1 | 21 | 15 |  | Proposed | 31/10/2024 | 20/11/2024
TO-24-INC-MAY-2-07 | 220kV FEEDER - INCHICORE 220-MAYNOOTH 220-2 | 21 | 15 | 15 | Proposed | 31/10/2024 | 20/11/2024
TO-24-220 kV A1 @ AD-04 | BUSBAR SECTION - AGHADA 220-AGHADA 220-220A1 | 5 | 5 | 5 | Scheduled | 04/11/2024 | 08/11/2024
TO-24-220 kV A2 @ AD-07 | BUSBAR SECTION - AGHADA 220-AGHADA 220-220A2 | 5 | 5 | 5 | Scheduled | 04/11/2024 | 08/11/2024
TO-24-AD-220K1-05 | COUPLER/SECTIONALISING CB - AGHADA 220-AGHADA 220-220K1 | 5 | 5 | 5 | Scheduled | 04/11/2024 | 08/11/2024
TO-24-AD-SA1-2CB-04 | COUPLER/SECTIONALISING CB - AGHADA 220-AGHADA 220-220SA1-2CB | 5 | 5 | 5 | Scheduled | 04/11/2024 | 08/11/2024
TO-24-ATH-110SA1-2CB-05 | COUPLER/SECTIONALISING CB - ATHLONE 110-ATHLONE 110-110SA1-2CB | 5 | 5 | 5 | Scheduled | 04/11/2024 | 08/11/2024
TO-24-ATH-SH-1-06 | 110kV FEEDER - ATHLONE 110-SHANNONBRIDGE 110-1 | 5 | 5 | 5 | Scheduled | 04/11/2024 | 08/11/2024
TO-24-ATH-T142-02 | DISTRIBUTION TRANSFORMER - ATHLONE 110-ATHLONE 38-T142 | 5 | 5 | 5 | Reference | 04/11/2024 | 08/11/2024
TO-24-220 kV A2 @ BYH-04 | BUSBAR SECTION - BALLYNAHULLA 220-BALLYNAHULLA 220-220A2 | 5 | 5 | 5 | Scheduled | 04/11/2024 | 08/11/2024
TO-24-220 kV B2 @ BYH-04 | BUSBAR SECTION - BALLYNAHULLA 220-BALLYNAHULLA 220-220B2 | 5 | 5 | 5 | Scheduled | 04/11/2024 | 08/11/2024
TO-24-BYH-220K2-01 | COUPLER/SECTIONALISING CB - BALLYNAHULLA 220-BALLYNAHULLA 220-220K2 | 5 | 5 | 5 | Scheduled | 04/11/2024 | 08/11/2024
TO-24-BYH-220SA1-2CB-04 | COUPLER/SECTIONALISING CB - BALLYNAHULLA 220-BALLYNAHULLA 220-220SA1-2CB | 5 | 5 | 5 | Scheduled | 04/11/2024 | 08/11/2024
TO-24-BYH-220SB1-2CB-05 | COUPLER/SECTIONALISING CB - BALLYNAHULLA 220-BALLYNAHULLA 220-220SB1-2CB | 5 | 5 | 5 | Scheduled | 04/11/2024 | 08/11/2024
TO-24-BK-110SA1-01 | SECTIONALISING DISCONNECT - BELLACORICK 110-BELLACORICK 110-110SA1 | 4 | 4 | 4 | Proposed | 04/11/2024 | 07/11/2024
TO-24-BK-110SA1-02 | SECTIONALISING DISCONNECT - BELLACORICK 110-BELLACORICK 110-110SA1 | 4 | 4 | 4 | Scheduled | 04/11/2024 | 07/11/2024
TO-24-BK-110SA2-01 | SECTIONALISING DISCONNECT - BELLACORICK 110-BELLACORICK 110-110SA2 | 4 | 4 | 4 | Proposed | 04/11/2024 | 07/11/2024
TO-24-BK-110SA2-04 | SECTIONALISING DISCONNECT - BELLACORICK 110-BELLACORICK 110-110SA2 | 4 | 4 |  | Scheduled | 04/11/2024 | 07/11/2024
TO-24-BK-MOY-1-01 | 110kV FEEDER - BELLACORICK 110-MOY 110-1 | 5 | 5 | 5 | Proposed | 04/11/2024 | 08/11/2024
TO-24-BK-MOY-1-02 | 110kV FEEDER - BELLACORICK 110-MOY 110-1 | 4 | 4 | 4 | Proposed | 04/11/2024 | 07/11/2024
TO-24-BK-MOY-1-04 | 110kV FEEDER - BELLACORICK 110-MOY 110-1 | 9 | 7 | 7 | Scheduled | 04/11/2024 | 12/11/2024
TO-24-BK-T141-01 | DISTRIBUTION TRANSFORMER - BELLACORICK 110-BELLACORICK 38-T141 | 4 | 4 | 4 | Reference (Proposed) | 04/11/2024 | 07/11/2024
TO-24-BK-T141-02 | DISTRIBUTION TRANSFORMER - BELLACORICK 110-BELLACORICK 38-T141 | 4 | 4 | 4 | Reference | 04/11/2024 | 07/11/2024
TO-24-DRU-110SA1-01 | SECTIONALISING DISCONNECT - DRUMLINE 110-DRUMLINE 110-110SA1 | 1 | 1 | 1 | Scheduled | 04/11/2024 | 04/11/2024
TO-24-DRU-110SA2-01 | SECTIONALISING DISCONNECT - DRUMLINE 110-DRUMLINE 110-110SA2 | 1 | 1 | 1 | Scheduled | 04/11/2024 | 04/11/2024
TO-24-DRU-ENN-1-03 | 110kV FEEDER - DRUMLINE 110-ENNIS 110-1 | 1 | 1 |  | Scheduled | 04/11/2024 | 04/11/2024
TO-24-220 kV A1 @ KNR-01 | BUSBAR SECTION - KNOCKANURE 220-KNOCKANURE 220-220A1 | 13 | 10 | 10 | Scheduled | 04/11/2024 | 16/11/2024
TO-24-220 kV B1 @ KNR-01 | BUSBAR SECTION - KNOCKANURE 220-KNOCKANURE 220-220B1 | 13 | 10 | 10 | Scheduled | 04/11/2024 | 16/11/2024
TO-24-KNR-220K1-01 | COUPLER/SECTIONALISING CB - KNOCKANURE 220-KNOCKANURE 220-220K1 | 13 | 10 | 10 | Scheduled | 04/11/2024 | 16/11/2024
TO-24-KNR-220SA1-2CB-03 | COUPLER/SECTIONALISING CB - KNOCKANURE 220-KNOCKANURE 220-220SA1-2CB | 13 | 10 | 10 | Scheduled | 04/11/2024 | 16/11/2024
TO-24-KNR-220SB1-2CB-02 | COUPLER/SECTIONALISING CB - KNOCKANURE 220-KNOCKANURE 220-220SB1-2CB | 13 | 10 | 10 | Scheduled | 04/11/2024 | 16/11/2024
TO-24-PLA-T105-02 | TSO CUSTOMER TRANSFORMER - PLATIN 110-PLATIN 10-T105 | 5 | 5 | 5 | Proposed | 04/11/2024 | 08/11/2024
TO-24-SLI-110SA1-2CB-06 | COUPLER/SECTIONALISING CB - SLIGO 110-SLIGO 110-110SA1-2CB | 5 | 5 | 5 | Proposed | 04/11/2024 | 08/11/2024
TO-24-SLI-T142-03 | DISTRIBUTION TRANSFORMER - SLIGO 110-SLIGO 38-T142 | 5 | 5 | 5 | Reference (Proposed) | 04/11/2024 | 08/11/2024
TO-24-WOO-T4202-03 | TRANSFORMER - WOODLAND 400-WOODLAND 220-T4202 | 12 | 10 | 10 | Scheduled | 04/11/2024 | 15/11/2024
TO-24-BLU-T131-02 | GENERATOR TRANSFORMER - BLUNDELSTOWN 110-BLUNDELSTOWN 33-T131 | 2 | 2 | 2 | Proposed | 05/11/2024 | 06/11/2024
TO-24-CSH-GAL GIS-4-02 | 110kV FEEDER - CASHLA 110-GALWAY GIS 110-4 | 4 | 4 | 4 | Scheduled | 05/11/2024 | 08/11/2024
TO-24-GAR-T131-01 | GENERATOR TRANSFORMER - GARBALLAGH 110-GARBALLAGH 33-T131 | 3 | 3 | 3 | Proposed | 05/11/2024 | 07/11/2024
TO-24-110 kV A2 @ KBY-02 | BUSBAR SECTION - KILBARRY 110-KILBARRY 110-110A2 | 8 | 6 | 6 | Proposed | 05/11/2024 | 12/11/2024
TO-24-110 kV B2 @ KBY-02 | BUSBAR SECTION - KILBARRY 110-KILBARRY 110-110B2 | 8 | 6 | 6 | Proposed | 05/11/2024 | 12/11/2024
TO-24-KBY-MAL-1-01 | 110kV FEEDER - KILBARRY 110-MALLOW 110-1 | 8 | 6 | 6 | Proposed | 05/11/2024 | 12/11/2024
TO-24-KBY-MAL-1-02 | 110kV FEEDER - KILBARRY 110-MALLOW 110-1 | 21 | 15 | 15 | Scheduled | 05/11/2024 | 25/11/2024
TO-24-KPG-KNR-2-01 | 220kV FEEDER - KILPADDOGE 220-KNOCKANURE 220-2 | 4 | 4 | 4 | Scheduled | 05/11/2024 | 08/11/2024
TO-24-MLN-T123-01 | TSO CUSTOMER TRANSFORMER - MULLAGHARLIN 110-MULLAGHARLIN 20-T123 | 9 | 7 | 7 | Scheduled | 05/11/2024 | 13/11/2024
TO-24-CUS-T103/5-02 | GENERATOR TRANSFORMER - CUSHALING 110-CUSHALING G3/5-T103/5 | 1 | 1 | 1 | Scheduled | 06/11/2024 | 06/11/2024
TO-24-220 kV B1 @ AD-05 | BUSBAR SECTION - AGHADA 220-AGHADA 220-220B1 | 5 | 5 | 5 | Scheduled | 11/11/2024 | 15/11/2024
TO-24-220 kV B2 @ AD-07 | BUSBAR SECTION - AGHADA 220-AGHADA 220-220B2 | 5 | 5 | 5 | Scheduled | 11/11/2024 | 15/11/2024
TO-24-AD-220K1-07 | COUPLER/SECTIONALISING CB - AGHADA 220-AGHADA 220-220K1 | 5 | 5 | 5 | Scheduled | 11/11/2024 | 15/11/2024
TO-24-AD-SB1-2CB-04 | COUPLER/SECTIONALISING CB - AGHADA 220-AGHADA 220-220SB1-2CB | 5 | 5 | 5 | Scheduled | 11/11/2024 | 15/11/2024
TO-24-CSH-ENN-1-01 | 110kV FEEDER - CASHLA 110-ENNIS 110-1 | 8 | 6 |  | Scheduled | 11/11/2024 | 18/11/2024
TO-24-CRO-110SA1-04 | SECTIONALISING DISCONNECT - COOLROE 110-COOLROE 110-110SA1 | 12 | 10 | 10 | Scheduled | 11/11/2024 | 22/11/2024
TO-24-CRO-110SA2-04 | SECTIONALISING DISCONNECT - COOLROE 110-COOLROE 110-110SA2 | 12 | 10 | 10 | Scheduled | 11/11/2024 | 22/11/2024
TO-24-CRO-IA-1-06 | 110kV FEEDER - COOLROE 110-INNISCARRA 110-1 | 12 | 10 | 10 | Scheduled | 11/11/2024 | 22/11/2024
TO-24-110 kV A1 @ FIN-01 | BUSBAR SECTION - FINGLAS 110-FINGLAS 110-110A1 | 12 | 10 | 10 | Scheduled | 11/11/2024 | 22/11/2024
TO-24-110 kV A2 @ FIN-04 | BUSBAR SECTION - FINGLAS 110-FINGLAS 110-110A2 | 12 | 10 | 10 | Scheduled | 11/11/2024 | 22/11/2024
TO-24-110 kV B1 @ FIN-01 | BUSBAR SECTION - FINGLAS 110-FINGLAS 110-110B1 | 12 | 10 | 10 | Scheduled | 11/11/2024 | 22/11/2024
TO-24-110 kV B2 @ FIN-04 | BUSBAR SECTION - FINGLAS 110-FINGLAS 110-110B2 | 12 | 10 | 10 | Scheduled | 11/11/2024 | 22/11/2024
TO-24-FIN-110K1-2-01 | COUPLER/SECTIONALISING CB - FINGLAS 110-FINGLAS 110-110K1-2 | 12 | 10 | 10 | Scheduled | 11/11/2024 | 22/11/2024
TO-24-110 kV A1 @ KRA-03 | BUSBAR SECTION - KNOCKRAHA 110-KNOCKRAHA 110-110A1 | 19 | 15 | 15 | Proposed | 11/11/2024 | 29/11/2024
TO-24-110 kV B1 @ KRA-03 | BUSBAR SECTION - KNOCKRAHA 110-KNOCKRAHA 110-110B1 | 19 | 15 | 15 | Proposed | 11/11/2024 | 29/11/2024
TO-24-220 kV A1 @ KRA-03 | BUSBAR SECTION - KNOCKRAHA 220-KNOCKRAHA 220-220A1 | 19 | 15 | 15 | Proposed | 11/11/2024 | 29/11/2024
TO-24-220 kV B1 @ KRA-03 | BUSBAR SECTION - KNOCKRAHA 220-KNOCKRAHA 220-220B1 | 19 | 15 | 15 | Proposed | 11/11/2024 | 29/11/2024
TO-24-KRA-220K1-04 | COUPLER/SECTIONALISING CB - KNOCKRAHA 220-KNOCKRAHA 220-220K1 | 19 | 15 | 15 | Scheduled | 11/11/2024 | 29/11/2024
TO-24-KRA-220SA1-2CB-04 | COUPLER/SECTIONALISING CB - KNOCKRAHA 220-KNOCKRAHA 220-220SA1-2CB | 19 | 15 | 15 | Scheduled | 11/11/2024 | 29/11/2024
TO-24-KRA-220SB1-2CB-04 | COUPLER/SECTIONALISING CB - KNOCKRAHA 220-KNOCKRAHA 220-220SB1-2CB | 19 | 15 | 15 | Scheduled | 11/11/2024 | 29/11/2024
TO-24-KRA-T2101-02 | TRANSFORMER - KNOCKRAHA 220-KNOCKRAHA 110-T2101 | 19 | 15 | 15 | Proposed | 11/11/2024 | 29/11/2024
TO-24-110 kV A1 @ LOU-09 | BUSBAR SECTION - LOUTH 110-LOUTH 110-110A1 | 5 | 5 | 5 | Scheduled | 11/11/2024 | 15/11/2024
TO-24-110 kV A2 @ LOU-07 | BUSBAR SECTION - LOUTH 110-LOUTH 110-110A2 | 5 | 5 | 5 | Scheduled | 11/11/2024 | 15/11/2024
TO-24-110 kV B1 @ LOU-09 | BUSBAR SECTION - LOUTH 110-LOUTH 110-110B1 | 5 | 5 | 5 | Scheduled | 11/11/2024 | 15/11/2024
TO-24-110 kV B2 @ LOU-07 | BUSBAR SECTION - LOUTH 110-LOUTH 110-110B2 | 5 | 5 | 5 | Scheduled | 11/11/2024 | 15/11/2024
TO-24-LOU-110K1-2-06 | COUPLER/SECTIONALISING CB - LOUTH 110-LOUTH 110-110K1-2 | 5 | 5 | 5 | Scheduled | 11/11/2024 | 15/11/2024
TO-24-RYB GIS-T104-03 | TSO CUSTOMER TRANSFORMER - RYEBROOK GIS 110-RYEBROOK 10-T104 | 19 | 15 | 15 | Scheduled | 11/11/2024 | 29/11/2024
TO-24-SOM-T142-02 | DISTRIBUTION TRANSFORMER - SOMERSET 110-SOMERSET 38-T142 | 3 | 3 | 3 | Reference (Proposed) | 11/11/2024 | 13/11/2024
TO-24-SOM,T-SH-1-03 | 110kV FEEDER - SOMERSET tee-SHANNONBRIDGE 110-1 | 3 | 3 | 3 | Proposed | 11/11/2024 | 13/11/2024
TO-24-SOM,T-SOM-1-02 | 110kV FEEDER - SOMERSET tee-SOMERSET 110-1 | 3 | 3 | 3 | Proposed | 11/11/2024 | 13/11/2024
TO-24-110 kV A2 @ CSH-02 | BUSBAR SECTION - CASHLA 110-CASHLA 110-110A2 | 2 | 2 | 2 | Proposed | 12/11/2024 | 13/11/2024
TO-24-110 kV B2 @ CSH-02 | BUSBAR SECTION - CASHLA 110-CASHLA 110-110B2 | 2 | 2 | 2 | Proposed | 12/11/2024 | 13/11/2024
TO-24-CLE-T224-01 | TSO CUSTOMER TRANSFORMER - CLONEE 220-CLONEE 20-T224 | 1 | 1 | 1 | Scheduled | 12/11/2024 | 12/11/2024
TO-24-DGN-WOH-1-04 | 110kV FEEDER - DUNGARVAN 110-WOODHOUSE 110-1 | 1 | 1 | 1 | Trip Testing | 12/11/2024 | 12/11/2024
TO-24-KPG-KNR-1-01 | 220kV FEEDER - KILPADDOGE 220-KNOCKANURE 220-1 | 4 | 4 | 4 | Scheduled | 12/11/2024 | 15/11/2024
TO-24-KRA-WOH-1-04 | 110kV FEEDER - KNOCKRAHA 110-WOODHOUSE 110-1 | 1 | 1 | 1 | Trip Testing | 12/11/2024 | 12/11/2024
TO-24-KKY-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - KILKENNY 110-KILKENNY 110-110SA1-2CB | 1 | 1 | 1 | Proposed | 13/11/2024 | 13/11/2024
TO-24-KKY-T141-01 | DISTRIBUTION TRANSFORMER - KILKENNY 110-KILKENNY 38-T141 | 1 | 1 | 1 | Reference (Proposed) | 13/11/2024 | 13/11/2024
TO-24-LIS-LOU-1-02 | 110kV FEEDER - LISDRUM 110-LOUTH 110-1 | 14 | 10 | 10 | Scheduled | 15/11/2024 | 28/11/2024
TO-24-LIS-LOU-1-01 | 110kV FEEDER - LISDRUM 110-LOUTH 110-1 | Unknown | Unknown | 10 | Planned | November | November
TO-24-LOU-110K1-2-02 | COUPLER/SECTIONALISING CB - LOUTH 110-LOUTH 110-110K1-2 | 14 | 10 | 10 | Proposed | 15/11/2024 | 28/11/2024
TO-24-ATY-110SA1-01 | SECTIONALISING DISCONNECT - ATHY 110-ATHY 110-110SA1 | 5 | 5 | 5 | Proposed | 18/11/2024 | 22/11/2024
TO-24-ATY-110SA2-04 | SECTIONALISING DISCONNECT - ATHY 110-ATHY 110-110SA2 | 5 | 5 | 5 | Proposed | 18/11/2024 | 22/11/2024
TO-24-ATY-CLW-1-08 | 110kV FEEDER - ATHY 110-CARLOW 110-1 | 5 | 5 | 5 | Proposed | 18/11/2024 | 22/11/2024
TO-24-ATY-T101-02 | DISTRIBUTION TRANSFORMER - ATHY 110-ATHY 10-T101 | 5 | 5 | 5 | Reference (Proposed) | 18/11/2024 | 22/11/2024
TO-24-BYH-110K1-01 | COUPLER/SECTIONALISING CB - BALLYNAHULLA 110-BALLYNAHULLA 110-110K1 | 5 | 5 | 5 | Scheduled | 18/11/2024 | 22/11/2024
TO-24-BLU-MUL-1-02 | 110kV FEEDER - BLUNDELSTOWN 110-MULLINGAR 110-1 | 12 | 10 | 10 | Scheduled | 18/11/2024 | 29/11/2024
TO-24-BLU-MUL-1-06 | 110kV FEEDER - BLUNDELSTOWN 110-MULLINGAR 110-1 | 12 | 10 | 10 | Proposed | 18/11/2024 | 29/11/2024
TO-24-CSH-DLT-1-01 | 110kV FEEDER - CASHLA 110-DALTON 110-1 | 10 | 8 | 9 | Scheduled | 18/11/2024 | 27/11/2024
TO-24-110 kV A1 @ GI-01 | BUSBAR SECTION - GREAT ISLAND 110-GREAT ISLAND 110-110A1 | 2 | 2 |  | Scheduled | 18/11/2024 | 19/11/2024
TO-24-110 kV B1 @ GI-01 | BUSBAR SECTION - GREAT ISLAND 110-GREAT ISLAND 110-110B1 | 2 | 2 |  | Scheduled | 18/11/2024 | 19/11/2024
TO-24-GI-WAT-1-02 | 110kV FEEDER - GREAT ISLAND 110-WATERFORD 110-1 | 2 | 2 |  | Scheduled | 18/11/2024 | 19/11/2024
TO-24-PB-T2007/8-04 | GENERATOR TRANSFORMER - POOLBEG 220-POOLBEG G7/8-T2007/8 | 12 | 10 | 10 | Proposed | 18/11/2024 | 29/11/2024
TO-24-110 kV A1 @ RAF-01 | BUSBAR SECTION - RAFFEEN 110-RAFFEEN 110-110A1 | 12 | 10 | 10 | Proposed | 18/11/2024 | 29/11/2024
TO-24-110 kV B1 @ RAF-01 | BUSBAR SECTION - RAFFEEN 110-RAFFEEN 110-110B1 | 12 | 10 | 10 | Proposed | 18/11/2024 | 29/11/2024
TO-24-RAF-TBG-1-01 | 110kV FEEDER - RAFFEEN 110-TRABEG 110-1 | 12 | 10 |  | Proposed | 18/11/2024 | 29/11/2024
TO-24-110 kV A2 @ TBG-01 | BUSBAR SECTION - TRABEG 110-TRABEG 110-110A2 | 12 | 10 |  | Proposed | 18/11/2024 | 29/11/2024
TO-24-110 kV B2 @ TBG-01 | BUSBAR SECTION - TRABEG 110-TRABEG 110-110B2 | 12 | 10 | 10 | Proposed | 18/11/2024 | 29/11/2024
TO-24-BRT-220K2-01 | COUPLER/SECTIONALISING CB - BRACETOWN 220-BRACETOWN 220-220K2 | 1 | 1 | 1 | Proposed | 20/11/2024 | 20/11/2024
TO-24-RAF-110K1-2-03 | COUPLER/SECTIONALISING CB - RAFFEEN 110-RAFFEEN 110-110K1-2 | 3 | 3 | 3 | Scheduled | 20/11/2024 | 22/11/2024
TO-24-BRT-CLE-2-02 | 220kV FEEDER - BRACETOWN 220-CLONEE 220-2 | 1 | 1 | 1 | Proposed | 21/11/2024 | 21/11/2024
TO-24-110 kV A2 @ FLA-02 | BUSBAR SECTION - FLAGFORD 110-FLAGFORD 110-110A2 | 4 | 2 |  | Scheduled | 22/11/2024 | 25/11/2024
TO-24-110 kV B2 @ FLA-02 | BUSBAR SECTION - FLAGFORD 110-FLAGFORD 110-110B2 | 4 | 2 |  | Scheduled | 22/11/2024 | 25/11/2024
TO-24-MCE-T124-04 | TSO CUSTOMER TRANSFORMER - MACETOWN 110-MACETOWN 20-T124 | 9 | 6 | 6 | Scheduled | 22/11/2024 | 30/11/2024
TO-24-110 kV A1 @ AUN-03 | BUSBAR SECTION - AUNGIERSTOWN 110-AUNGIERSTOWN 110-110A1 | 5 | 5 | 5 | Scheduled | 25/11/2024 | 29/11/2024
TO-24-110 kV B1 @ AUN-03 | BUSBAR SECTION - AUNGIERSTOWN 110-AUNGIERSTOWN 110-110B1 | 5 | 5 | 5 | Scheduled | 25/11/2024 | 29/11/2024
TO-24-AUN-110K1-03 | COUPLER/SECTIONALISING CB - AUNGIERSTOWN 110-AUNGIERSTOWN 110-110K1 | 5 | 5 | 5 | Scheduled | 25/11/2024 | 29/11/2024
TO-24-AUN-110SA1-2CB-04 | COUPLER/SECTIONALISING CB - AUNGIERSTOWN 110-AUNGIERSTOWN 110-110SA1-2CB | 5 | 5 | 5 | Scheduled | 25/11/2024 | 29/11/2024
TO-24-AUN-110SB1-2CB-03 | COUPLER/SECTIONALISING CB - AUNGIERSTOWN 110-AUNGIERSTOWN 110-110SB1-2CB | 5 | 5 | 5 | Scheduled | 25/11/2024 | 29/11/2024
TO-24-AUN-CBT-1-01 | 110kV FEEDER - AUNGIERSTOWN 110-CASTLEBAGOT 110-1 | 5 | 5 | 5 | Scheduled | 25/11/2024 | 29/11/2024
TO-24-110 kV A1 @ CBT-01 | BUSBAR SECTION - CASTLEBAGOT 110-CASTLEBAGOT 110-110A1 | 5 | 5 | 5 | Scheduled | 25/11/2024 | 29/11/2024
TO-24-110 kV B1 @ CBT-01 | BUSBAR SECTION - CASTLEBAGOT 110-CASTLEBAGOT 110-110B1 | 5 | 5 | 5 | Scheduled | 25/11/2024 | 29/11/2024
TO-24-CBT-110K1-01 | COUPLER/SECTIONALISING CB - CASTLEBAGOT 110-CASTLEBAGOT 110-110K1 | 5 | 5 | 5 | Scheduled | 25/11/2024 | 29/11/2024
TO-24-CBT-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - CASTLEBAGOT 110-CASTLEBAGOT 110-110SA1-2CB | 5 | 5 | 5 | Scheduled | 25/11/2024 | 29/11/2024
TO-24-CBT-110SB1-2CB-01 | COUPLER/SECTIONALISING CB - CASTLEBAGOT 110-CASTLEBAGOT 110-110SB1-2CB | 5 | 5 | 5 | Scheduled | 25/11/2024 | 29/11/2024
TO-24-220 kV A2 @ CBT-01 | BUSBAR SECTION - CASTLEBAGOT 220-CASTLEBAGOT 220-220A2 | 3 | 3 | 3 | Proposed | 25/11/2024 | 27/11/2024
TO-24-220 kV B2 @ CBT-01 | BUSBAR SECTION - CASTLEBAGOT 220-CASTLEBAGOT 220-220B2 | 3 | 3 | 3 | Proposed | 25/11/2024 | 27/11/2024
TO-24-CBT-220K2-01 | COUPLER/SECTIONALISING CB - CASTLEBAGOT 220-CASTLEBAGOT 220-220K2 | 3 | 3 | 3 | Proposed | 25/11/2024 | 27/11/2024
TO-24-CBT-220SA1-2CB-01 | COUPLER/SECTIONALISING CB - CASTLEBAGOT 220-CASTLEBAGOT 220-220SA1-2CB | 3 | 3 | 3 | Proposed | 25/11/2024 | 27/11/2024
TO-24-CBT-220SB1-2CB-01 | COUPLER/SECTIONALISING CB - CASTLEBAGOT 220-CASTLEBAGOT 220-220SB1-2CB | 3 | 3 | 3 | Proposed | 25/11/2024 | 27/11/2024
TO-24-COW-110SA1-01 | SECTIONALISING DISCONNECT - COW CROSS 110-COW CROSS 110-110SA1 | Unknown | Unknown |  | Planned | November | December
TO-24-COW-110SA2-02 | SECTIONALISING DISCONNECT - COW CROSS 110-COW CROSS 110-110SA2 | Unknown | Unknown |  | Planned | November | December
TO-24-COW-OLD-2-01 | 110kV FEEDER - COW CROSS 110-OLDCOURT 110-2 | Unknown | Unknown |  | Reference (Planned) | November | December
TO-24-COW-OLD-2-02 | 110kV FEEDER - COW CROSS 110-OLDCOURT 110-2 | 15 | 11 | 11 | Reference (Proposed) | 25/11/2024 | 09/12/2024
TO-24-COW-RAF-1-01 | 110kV FEEDER - COW CROSS 110-RAFFEEN 110-1 | Unknown | Unknown |  | Planned | November | December
TO-24-COW-T141-01 | DISTRIBUTION TRANSFORMER - COW CROSS 110-COW CROSS 38-T141 | Unknown | Unknown |  | Reference (Planned) | November | December
TO-24-DDK-LOU-1-01 | 110kV FEEDER - DUNDALK 110-LOUTH 110-1 | Unknown | Unknown | 3 | Planned | November | November
TO-24-DDK-LOU-1-02 | 110kV FEEDER - DUNDALK 110-LOUTH 110-1 | 3 | 3 | 3 | Scheduled | 25/11/2024 | 27/11/2024
TO-24-FLA-T2102-02 | TRANSFORMER - FLAGFORD 220-FLAGFORD 110-T2102 | 1 | 1 | 1 | Scheduled | 25/11/2024 | 25/11/2024
TO-24-KTL-MON-1-01 | 110kV FEEDER - KILTEEL 110-MONREAD 110-1 | 5 | 5 | 5 | Scheduled | 25/11/2024 | 29/11/2024
TO-24-OLD-T102-01 | DISTRIBUTION TRANSFORMER - OLDCOURT 110-OLDCOURT 10-T102 | Unknown | Unknown | 11 | Reference (Planned) | November | December
TO-24-BDN-110SA1-02 | SECTIONALISING DISCONNECT - BALLYDINE 110-BALLYDINE 110-110SA1 | 4 | 4 | 4 | Scheduled | 26/11/2024 | 29/11/2024
TO-24-BDN-110SA2-01 | SECTIONALISING DISCONNECT - BALLYDINE 110-BALLYDINE 110-110SA2 | 4 | 4 | 4 | Scheduled | 26/11/2024 | 29/11/2024
TO-24-BDN-DOO-1-02 | 110kV FEEDER - BALLYDINE 110-DOON 110-1 | 4 | 4 | 4 | Scheduled | 26/11/2024 | 29/11/2024
TO-24-BDN-MRK3-02 | TSO CUSTOMER TRANSFORMER - BALLYDINE 110-BALLYDINE 10-MRK3 | 4 | 4 | 4 | Scheduled | 26/11/2024 | 29/11/2024
TO-24-MLN-T124-01 | TSO CUSTOMER TRANSFORMER - MULLAGHARLIN 110-MULLAGHARLIN 20-T124 | 1 | 1 | 1 | Scheduled | 26/11/2024 | 26/11/2024
TO-24-ROP-WEX-1-02 | 110kV FEEDER - ROSSPILE 110-WEXFORD 110-1 | 4 | 4 | 4 | Proposed | 26/11/2024 | 29/11/2024
TO-24-BAN-RAF-1-03 | 110kV FEEDER - BANDON 110-RAFFEEN 110-1 | 3 | 3 | 3 | Scheduled | 27/11/2024 | 29/11/2024
TO-24-220 kV A2 @ MAY-03 | BUSBAR SECTION - MAYNOOTH 220-MAYNOOTH 220-220A2 | 2 | 2 | 2 | Proposed | 28/11/2024 | 29/11/2024
TO-24-220 kV B2 @ MAY-03 | BUSBAR SECTION - MAYNOOTH 220-MAYNOOTH 220-220B2 | 2 | 2 | 2 | Proposed | 28/11/2024 | 29/11/2024
TO-24-MAY-RYB GIS-1-03 | 110kV FEEDER - MAYNOOTH 110-RYEBROOK GIS 110-1 | 1 | 1 | 1 | Proposed | 29/11/2024 | 29/11/2024
TO-24-ROP-T131-01 | GENERATOR TRANSFORMER - ROSSPILE 110-ROSSPILE 33-T131 | 1 | 1 | 1 | Proposed | 29/11/2024 | 29/11/2024
TO-24-PB-R2001-04 | CAPACITOR/SVC/REACTOR - POOLBEG 220-POOLBEG 220-R2001 | Unknown | Unknown |  | Planned | December | December
TO-24-220 kV A2 @ CBT-02 | BUSBAR SECTION - CASTLEBAGOT 220-CASTLEBAGOT 220-220A2 | 2 | 2 | 2 | Proposed | 05/12/2024 | 06/12/2024
TO-24-220 kV B2 @ CBT-02 | BUSBAR SECTION - CASTLEBAGOT 220-CASTLEBAGOT 220-220B2 | 2 | 2 | 2 | Proposed | 05/12/2024 | 06/12/2024
TO-24-CBT-220K2-02 | COUPLER/SECTIONALISING CB - CASTLEBAGOT 220-CASTLEBAGOT 220-220K2 | 2 | 2 | 2 | Proposed | 05/12/2024 | 06/12/2024
TO-24-CBT-220SA1-2CB-02 | COUPLER/SECTIONALISING CB - CASTLEBAGOT 220-CASTLEBAGOT 220-220SA1-2CB | 2 | 2 | 2 | Proposed | 05/12/2024 | 06/12/2024
TO-24-CBT-220SB1-2CB-02 | COUPLER/SECTIONALISING CB - CASTLEBAGOT 220-CASTLEBAGOT 220-220SB1-2CB | 2 | 2 | 2 | Proposed | 05/12/2024 | 06/12/2024
TO-24-110 kV A3 @ GAL GIS-02 | BUSBAR SECTION - GALWAY GIS 110-GALWAY GIS 110-110A3 | 9 | 7 | 7 | Proposed | 05/12/2024 | 13/12/2024
TO-24-110 kV B3 @ GAL GIS-03 | BUSBAR SECTION - GALWAY GIS 110-GALWAY GIS 110-110B3 | 9 | 7 | 7 | Proposed | 05/12/2024 | 13/12/2024
TO-24-GAL GIS-110K3-05 | COUPLER/SECTIONALISING CB - GALWAY GIS 110-GALWAY GIS 110-110K3 | 9 | 7 | 7 | Proposed | 05/12/2024 | 13/12/2024
TO-24-GAL GIS-110SA1-3CB-07 | COUPLER/SECTIONALISING CB - GALWAY GIS 110-GALWAY GIS 110-110SA1-3CB | 9 | 7 | 7 | Proposed | 05/12/2024 | 13/12/2024
TO-24-GAL GIS-110SB1-3CB-07 | COUPLER/SECTIONALISING CB - GALWAY GIS 110-GALWAY GIS 110-110SB1-3CB | 9 | 7 | 7 | Proposed | 05/12/2024 | 13/12/2024
TO-24-INC-MAY-2-09 | 220kV FEEDER - INCHICORE 220-MAYNOOTH 220-2 | 2 | 2 | 2 | Proposed | 05/12/2024 | 06/12/2024
TO-24-CSH-GAL GIS-1-04 | 110kV FEEDER - CASHLA 110-GALWAY GIS 110-1 | 2 | 2 | 2 | Proposed | 12/12/2024 | 13/12/2024

## GEN_AreaSouthWest
Outage ID | Feeder ID | Calendar Day Duration | Working Day Duration | Work Days | Outage Status | Start | Finish
TO-24-KPG-TB-1-02 | 220kV FEEDER - KILPADDOGE 220-TARBERT 220-1 | 167 | 113 | 113 | Scheduled | 02/01/2024 | 16/06/2024
TO-24-220 kV A2 @ TB-01 | BUSBAR SECTION - TARBERT 220-TARBERT 220-220A2 | 287 | 198 | 198 | Scheduled | 02/01/2024 | 14/10/2024
TO-24-220 kV B2 @ TB-01 | BUSBAR SECTION - TARBERT 220-TARBERT 220-220B2 | 287 | 198 | 198 | Scheduled | 02/01/2024 | 14/10/2024
TO-24-TB-220K1-2-02 | COUPLER/SECTIONALISING CB - TARBERT 220-TARBERT 220-220K1-2 | 167 | 113 | 113 | Scheduled | 02/01/2024 | 16/06/2024
TO-24-TB-T2004-02 | GENERATOR TRANSFORMER - TARBERT 220-TARBERT G4-T2004 | 167 | 113 | 113 | Scheduled | 02/01/2024 | 16/06/2024
TO-24-AUG-CFM-1-01 | 110kV FEEDER - AUGHINISH 110-CASTLEFARM 110-1 | 5 | 5 | 5 | Scheduled | 08/01/2024 | 12/01/2024
TO-24-CFM-T101-01 | TSO CUSTOMER TRANSFORMER - CASTLEFARM 110-CASTLEFARM 10-T101 | 5 | 5 | 5 | Reference | 08/01/2024 | 12/01/2024
TO-24-LIM-MTN-1-02 | 110kV FEEDER - LIMERICK 110-MONETEEN 110-1 | 2 | 2 | 2 | Scheduled | 08/01/2024 | 09/01/2024
TO-24-IKE,T-THU-1-04 | 110kV FEEDER - IKERRIN tee-THURLES 110-1 | 3 | 3 | 3 | Scheduled | 15/01/2024 | 17/01/2024
TO-24-LSN-110SA1-2-02 | SECTIONALISING DISCONNECT - LISHEEN 110-LISHEEN 110-110SA1-2 | 3 | 3 | 3 | Scheduled | 15/01/2024 | 17/01/2024
TO-24-LSN-110SA2-4-02 | SECTIONALISING DISCONNECT - LISHEEN 110-LISHEEN 110-110SA2-4 | 3 | 3 | 3 | Scheduled | 15/01/2024 | 17/01/2024
TO-24-LSN-T122-02 | GENERATOR TRANSFORMER - LISHEEN 110-LISHEEN 20-T122 | 3 | 3 | 3 | Scheduled | 15/01/2024 | 17/01/2024
TO-24-LSN-T131-02 | GENERATOR TRANSFORMER - LISHEEN 110-LISHEEN 33-T131 | 3 | 3 | 3 | Scheduled | 15/01/2024 | 17/01/2024
TO-24-LSN-T142-03 | DISTRIBUTION TRANSFORMER - LISHEEN 110-LISHEEN 38-T142 | 3 | 3 | 3 | Reference | 15/01/2024 | 17/01/2024
TO-24-LSN-THU-1-02 | 110kV FEEDER - LISHEEN 110-THURLES 110-1 | 3 | 3 | 3 | Scheduled | 15/01/2024 | 17/01/2024
TO-24-THU-110SA1-2CB-02 | COUPLER/SECTIONALISING CB - THURLES 110-THURLES 110-110SA1-2CB | 3 | 3 | 3 | Scheduled | 15/01/2024 | 17/01/2024
TO-24-THU-T142-02 | DISTRIBUTION TRANSFORMER - THURLES 110-THURLES 38-T142 | 3 | 3 | 3 | Reference | 15/01/2024 | 17/01/2024
TO-24-CAH-TIP-1-02 | 110kV FEEDER - CAHIR 110-TIPPERARY 110-1 | 2 | 2 | 2 | Scheduled | 31/01/2024 | 01/02/2024
TO-24-IKE,T-SH-1-03 | 110kV FEEDER - IKERRIN tee-SHANNONBRIDGE 110-1 | 3 | 3 | 3 | Scheduled | 06/02/2024 | 08/02/2024
TO-24-KNR-TRI-1-02 | 110kV FEEDER - KNOCKANURE 110-TRIEN 110-1 | 9 | 7 | 7 | Scheduled | 12/02/2024 | 20/02/2024
TO-24-IKE,T-SH-1-04 | 110kV FEEDER - IKERRIN tee-SHANNONBRIDGE 110-1 | 4 | 4 | 4 | Scheduled | 19/02/2024 | 22/02/2024
TO-24-AA GIS-SNG-1-01 | 110kV FEEDER - ARDNACRUSHA GIS 110-SINGLAND 110-1 | 5 | 5 |  | Scheduled | 26/02/2024 | 01/03/2024
TO-24-OST-WOO-1-01 | 400kV FEEDER - OLDSTREET 400-WOODLAND 400-1 | 5 | 5 | 5 | Scheduled | 26/02/2024 | 01/03/2024
TO-24-CKN-KER-1-03 | 110kV FEEDER - CLONKEEN 110-KNOCKEARAGH 110-1 | 1 | 1 | 1 | Scheduled | 27/02/2024 | 27/02/2024
TO-24-KPG-TRL-1-01 | 110kV FEEDER - KILPADDOGE 110-TRALEE 110-1 | 10 | 8 | 8 | Scheduled | 28/02/2024 | 08/03/2024
TO-24-BYH-STATCOM-01 | CAPACITOR/SVC/REACTOR - BALLYNAHULLA 110-BALLYNAHULLA 110-STATCOM | 1 | 1 | 1 | Scheduled | 29/02/2024 | 29/02/2024
TO-24-AGL-ENN-1-01 | 110kV FEEDER - AGANNYGAL 110-ENNIS 110-1 | 22 | 15 | 15 | Scheduled | 04/03/2024 | 25/03/2024
TO-24-BVK-STATCOM-01 | CAPACITOR/SVC/REACTOR - BALLYVOUSKILL 110-BALLYVOUSKILL 110-STATCOM | 1 | 1 | 1 | Scheduled | 05/03/2024 | 05/03/2024
TO-24-BYH-T2101-01 | TRANSFORMER - BALLYNAHULLA 220-BALLYNAHULLA 110-T2101 | 5 | 5 | 5 | Scheduled | 11/03/2024 | 15/03/2024
TO-24-THU-CAP1-03 | CAPACITOR/SVC/REACTOR - THURLES 110-THURLES 110-CAP1 | 1 | 1 | 1 | Scheduled | 14/03/2024 | 14/03/2024
TO-24-THU-STATCOM-02 | CAPACITOR/SVC/REACTOR - THURLES 110-THURLES 110-STATCOM | 1 | 1 | 1 | Scheduled | 14/03/2024 | 14/03/2024
TO-24-BOL-T141-01 | DISTRIBUTION TRANSFORMER - BOOLTIAGH 110-BOOLTIAGH 38-T141 | 154 | 104 | 104 | Reference | 15/03/2024 | 15/08/2024
TO-24-CBA-110SA1-01 | SECTIONALISING DISCONNECT - CLOGHBOOLA 110-CLOGHBOOLA 110-110SA1 | 2 | 2 | 2 | Scheduled | 20/03/2024 | 21/03/2024
TO-24-CBA-110SA2-01 | SECTIONALISING DISCONNECT - CLOGHBOOLA 110-CLOGHBOOLA 110-110SA2 | 2 | 2 | 2 | Scheduled | 20/03/2024 | 21/03/2024
TO-24-CBA-T122-02 | DISTRIBUTION TRANSFORMER - CLOGHBOOLA 110-CLOGHBOOLA 20-T122 | 2 | 2 | 2 | Reference | 20/03/2024 | 21/03/2024
TO-24-CBA-T131-02 | GENERATOR TRANSFORMER - CLOGHBOOLA 110-CLOGHBOOLA 33-T131 | 2 | 2 | 2 | Scheduled | 20/03/2024 | 21/03/2024
TO-24-BYH-T2102-01 | TRANSFORMER - BALLYNAHULLA 220-BALLYNAHULLA 110-T2102 | 4 | 4 | 4 | Scheduled | 25/03/2024 | 28/03/2024
TO-24-DAL,T-SH-1-02 | 110kV FEEDER - DALLOW tee-SHANNONBRIDGE 110-1 | 77 | 51 | 51 | Scheduled | 26/03/2024 | 10/06/2024
TO-24-AUG-KPG-1-01 | 110kV FEEDER - AUGHINISH 110-KILPADDOGE 110-1 | 4 | 4 |  | Scheduled | 02/04/2024 | 05/04/2024
TO-24-BYH-220SB1-2CB-01 | COUPLER/SECTIONALISING CB - BALLYNAHULLA 220-BALLYNAHULLA 220-220SB1-2CB | 1 | 1 | 1 | Scheduled | 04/04/2024 | 04/04/2024
TO-24-BVK-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - BALLYVOUSKILL 110-BALLYVOUSKILL 110-110SA1-2CB | 1 | 1 | 1 | Scheduled | 04/04/2024 | 04/04/2024
TO-24-BVK-110SB1-2CB-01 | COUPLER/SECTIONALISING CB - BALLYVOUSKILL 110-BALLYVOUSKILL 110-110SB1-2CB | 1 | 1 | 1 | Scheduled | 05/04/2024 | 05/04/2024
TO-24-220 kV A1 @ BYH-01 | BUSBAR SECTION - BALLYNAHULLA 220-BALLYNAHULLA 220-220A1 | 5 | 5 | 5 | Scheduled | 08/04/2024 | 12/04/2024
TO-24-220 kV B1 @ BYH-01 | BUSBAR SECTION - BALLYNAHULLA 220-BALLYNAHULLA 220-220B1 | 5 | 5 | 5 | Scheduled | 08/04/2024 | 12/04/2024
TO-24-BYH-220K1-01 | COUPLER/SECTIONALISING CB - BALLYNAHULLA 220-BALLYNAHULLA 220-220K1 | 5 | 5 | 5 | Scheduled | 08/04/2024 | 12/04/2024
TO-24-BYH-220SA1-2CB-01 | COUPLER/SECTIONALISING CB - BALLYNAHULLA 220-BALLYNAHULLA 220-220SA1-2CB | 5 | 5 | 5 | Scheduled | 08/04/2024 | 12/04/2024
TO-24-BYH-220SB1-2CB-02 | COUPLER/SECTIONALISING CB - BALLYNAHULLA 220-BALLYNAHULLA 220-220SB1-2CB | 5 | 5 | 5 | Scheduled | 08/04/2024 | 12/04/2024
TO-24-CTN-TIP-1-01 | 110kV FEEDER - CAUTEEN 110-TIPPERARY 110-1 | 5 | 5 | 5 | Scheduled | 15/04/2024 | 19/04/2024
TO-24-KLN-SH-1-02 | 220kV FEEDER - KILLONAN 220-SHANNONBRIDGE 220-1 | 2 | 2 |  | Scheduled | 15/04/2024 | 16/04/2024
TO-24-KPG-T2101-01 | TRANSFORMER - KILPADDOGE 220-KILPADDOGE 110-T2101 | 5 | 5 | 5 | Scheduled | 15/04/2024 | 19/04/2024
TO-24-MP GIS-220K1-01 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 220-MONEYPOINT GIS 220-220K1 | 1 | 1 | 1 | Scheduled | 16/04/2024 | 16/04/2024
TO-24-MP GIS-220K2-01 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 220-MONEYPOINT GIS 220-220K2 | 1 | 1 | 1 | Scheduled | 17/04/2024 | 17/04/2024
TO-24-AA GIS-T104-04 | GENERATOR TRANSFORMER - ARDNACRUSHA GIS 110-ARDNACRUSHA GIS G4-T104 | 1 | 1 | 1 | Scheduled | 18/04/2024 | 18/04/2024
TO-24-MP GIS-220SA1-2CB-01 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 220-MONEYPOINT GIS 220-220SA1-2CB | 1 | 1 | 1 | Scheduled | 18/04/2024 | 18/04/2024
TO-24-MP GIS-220SB1-2CB-01 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 220-MONEYPOINT GIS 220-220SB1-2CB | 1 | 1 | 1 | Scheduled | 19/04/2024 | 19/04/2024
TO-24-TB-T2102-03 | TRANSFORMER - TARBERT 220-TARBERT 110-T2102 | 3 | 1 | 1 | Scheduled | 19/04/2024 | 21/04/2024
TO-24-LIM-RAT-1-01 | 110kV FEEDER - LIMERICK 110-RATHKEALE 110-1 | 5 | 5 | 5 | Scheduled | 22/04/2024 | 26/04/2024
TO-24-CGL-GAE-1-05 | 110kV FEEDER - COOMAGEARLAHY 110-GLANLEE 110-1 | 2 | 2 | 2 | Scheduled | 23/04/2024 | 24/04/2024
TO-24-GAE-T121-02 | GENERATOR TRANSFORMER - GLANLEE 110-GLANLEE 20-T121 | 2 | 2 | 2 | Scheduled | 23/04/2024 | 24/04/2024
TO-24-KPG-220SB1-3CB-01 | COUPLER/SECTIONALISING CB - KILPADDOGE 220-KILPADDOGE 220-220SB1-3CB | 2 | 2 | 2 | Scheduled | 23/04/2024 | 24/04/2024
TO-24-110 kV A3 @ AA GIS-01 | BUSBAR SECTION - ARDNACRUSHA GIS 110-ARDNACRUSHA GIS 110-110A3 | 1 | 1 | 1 | Scheduled | 25/04/2024 | 25/04/2024
TO-24-AA GIS-T104-02 | GENERATOR TRANSFORMER - ARDNACRUSHA GIS 110-ARDNACRUSHA GIS G4-T104 | 1 | 1 | 1 | Scheduled | 25/04/2024 | 25/04/2024
TO-24-BYH-STATCOM-02 | CAPACITOR/SVC/REACTOR - BALLYNAHULLA 110-BALLYNAHULLA 110-STATCOM | 1 | 1 | 1 | Scheduled | 25/04/2024 | 25/04/2024
TO-24-110 kV A3 @ AA GIS-02 | BUSBAR SECTION - ARDNACRUSHA GIS 110-ARDNACRUSHA GIS 110-110A3 | 5 | 5 | 5 | Scheduled | 29/04/2024 | 03/05/2024
TO-24-110 kV B3 @ AA GIS-01 | BUSBAR SECTION - ARDNACRUSHA GIS 110-ARDNACRUSHA GIS 110-110B3 | 5 | 5 | 5 | Scheduled | 29/04/2024 | 03/05/2024
TO-23-AA GIS-110K3-01 | COUPLER/SECTIONALISING CB - ARDNACRUSHA GIS 110-ARDNACRUSHA GIS 110-110K3 | 5 | 5 | 5 | Scheduled | 29/04/2024 | 03/05/2024
TO-24-AA GIS-110SA1-3CB-01 | COUPLER/SECTIONALISING CB - ARDNACRUSHA GIS 110-ARDNACRUSHA GIS 110-110SA1-3CB | 5 | 5 | 5 | Scheduled | 29/04/2024 | 03/05/2024
TO-24-AA GIS-110SB1-3CB-01 | COUPLER/SECTIONALISING CB - ARDNACRUSHA GIS 110-ARDNACRUSHA GIS 110-110SB1-3CB | 5 | 5 | 5 | Scheduled | 29/04/2024 | 03/05/2024
TO-24-AA GIS-CAP1-01 | CAPACITOR/SVC/REACTOR - ARDNACRUSHA GIS 110-ARDNACRUSHA GIS 110-CAP1 | 5 | 5 | 5 | Scheduled | 29/04/2024 | 03/05/2024
TO-24-CHA-GLE-1-01 | 110kV FEEDER - CHARLEVILLE 110-GLENLARA 110-1 | 3 | 3 | 3 | Scheduled | 30/04/2024 | 02/05/2024
TO-24-AA GIS-T101-01 | GENERATOR TRANSFORMER - ARDNACRUSHA GIS 110-ARDNACRUSHA GIS G1-T101 | 171 | 120 | 120 | Scheduled | 01/05/2024 | 18/10/2024
TO-24-110 kV A2 @ AA GIS-01 | BUSBAR SECTION - ARDNACRUSHA GIS 110-ARDNACRUSHA GIS 110-110A2 | 10 | 8 | 8 | Scheduled | 07/05/2024 | 16/05/2024
TO-24-110 kV B2 @ AA GIS-01 | BUSBAR SECTION - ARDNACRUSHA GIS 110-ARDNACRUSHA GIS 110-110B2 | 10 | 8 | 8 | Scheduled | 07/05/2024 | 16/05/2024
TO-24-AA GIS-110K2-01 | COUPLER/SECTIONALISING CB - ARDNACRUSHA GIS 110-ARDNACRUSHA GIS 110-110K2 | 10 | 8 | 8 | Scheduled | 07/05/2024 | 16/05/2024
TO-24-AA GIS-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - ARDNACRUSHA GIS 110-ARDNACRUSHA GIS 110-110SA1-2CB | 10 | 8 | 8 | Scheduled | 07/05/2024 | 16/05/2024
TO-24-AA GIS-110SB1-2CB-01 | COUPLER/SECTIONALISING CB - ARDNACRUSHA GIS 110-ARDNACRUSHA GIS 110-110SB1-2CB | 10 | 8 | 8 | Scheduled | 07/05/2024 | 16/05/2024
TO-24-AA GIS-ENN-1-04 | 110kV FEEDER - ARDNACRUSHA GIS 110-ENNIS 110-1 | 10 | 8 | 8 | Scheduled | 07/05/2024 | 16/05/2024
TO-24-AA GIS-T104-01 | GENERATOR TRANSFORMER - ARDNACRUSHA GIS 110-ARDNACRUSHA GIS G4-T104 | 14 | 10 | 10 | Scheduled | 09/05/2024 | 22/05/2024
TO-24-CLH-110SA2-01 | SECTIONALISING DISCONNECT - CLAHANE 110-CLAHANE 110-110SA2 | 3 | 3 | 3 | Scheduled | 13/05/2024 | 15/05/2024
TO-24-CLH-T122-01 | GENERATOR TRANSFORMER - CLAHANE 110-CLAHANE 20-T122 | 5 | 5 | 5 | Scheduled | 13/05/2024 | 17/05/2024
TO-24-CLH-TRI-1-01 | 110kV FEEDER - CLAHANE 110-TRIEN 110-1 | 3 | 3 | 3 | Scheduled | 13/05/2024 | 15/05/2024
TO-24-400 kV A1 @ MP GIS-02 | BUSBAR SECTION - MONEYPOINT GIS 400-MONEYPOINT GIS 400-400A1 | 12 | 10 | 10 | Scheduled | 13/05/2024 | 24/05/2024
TO-24-400 kV B1 @ MP GIS-04 | BUSBAR SECTION - MONEYPOINT GIS 400-MONEYPOINT GIS 400-400B1 | 12 | 10 | 10 | Scheduled | 13/05/2024 | 24/05/2024
TO-24-MP GIS-400SA1-2CB-02 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 400-MONEYPOINT GIS 400-400SA1-2CB | 12 | 10 | 10 | Scheduled | 13/05/2024 | 24/05/2024
TO-24-MP GIS-400SB1-2CB-03 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 400-MONEYPOINT GIS 400-400SB1-2CB | 12 | 10 | 10 | Scheduled | 13/05/2024 | 24/05/2024
TO-24-MP GIS-400SB1-3CB-02 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 400-MONEYPOINT GIS 400-400SB1-3CB | 12 | 10 | 10 | Scheduled | 13/05/2024 | 24/05/2024
TO-24-SLC-T122-03 | GENERATOR TRANSFORMER - SLIEVECALLAN 110-SLIEVECALLAN 20-T122 | 1 | 1 | 1 | Scheduled | 16/05/2024 | 16/05/2024
TO-24-BVK-T2101-01 | TRANSFORMER - BALLYVOUSKILL 220-BALLYVOUSKILL 110-T2101 | 15 | 11 |  | Scheduled | 17/05/2024 | 31/05/2024
TO-24-KLN-KPG-1-01 | 220kV FEEDER - KILLONAN 220-KILPADDOGE 220-1 | 12 | 10 | 10 | Scheduled | 20/05/2024 | 31/05/2024
TO-24-220 kV A4 @ KPG-01 | BUSBAR SECTION - KILPADDOGE 220-KILPADDOGE 220-220A4 | 12 | 10 | 10 | Scheduled | 20/05/2024 | 31/05/2024
TO-24-220 kV B4 @ KPG-01 | BUSBAR SECTION - KILPADDOGE 220-KILPADDOGE 220-220B4 | 12 | 10 | 10 | Scheduled | 20/05/2024 | 31/05/2024
TO-24-KPG-220K4-02 | COUPLER/SECTIONALISING CB - KILPADDOGE 220-KILPADDOGE 220-220K4 | 12 | 10 | 10 | Scheduled | 20/05/2024 | 31/05/2024
TO-24-KPG-220SA2-4CB-02 | COUPLER/SECTIONALISING CB - KILPADDOGE 220-KILPADDOGE 220-220SA2-4CB | 12 | 10 | 10 | Scheduled | 20/05/2024 | 31/05/2024
TO-24-KPG-220SB2-4CB-01 | COUPLER/SECTIONALISING CB - KILPADDOGE 220-KILPADDOGE 220-220SB2-4CB | 12 | 10 | 10 | Scheduled | 20/05/2024 | 31/05/2024
TO-24-220 kV A1 @ MP GIS-01 | BUSBAR SECTION - MONEYPOINT GIS 220-MONEYPOINT GIS 220-220A1 | 5 | 5 | 5 | Scheduled | 20/05/2024 | 24/05/2024
TO-24-220 kV B1 @ MP GIS-01 | BUSBAR SECTION - MONEYPOINT GIS 220-MONEYPOINT GIS 220-220B1 | 5 | 5 | 5 | Scheduled | 20/05/2024 | 24/05/2024
TO-24-MP GIS-220K1-02 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 220-MONEYPOINT GIS 220-220K1 | 5 | 5 | 5 | Scheduled | 20/05/2024 | 24/05/2024
TO-24-MP GIS-220SA1-2CB-03 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 220-MONEYPOINT GIS 220-220SA1-2CB | 5 | 5 | 5 | Scheduled | 20/05/2024 | 24/05/2024
TO-24-MP GIS-220SB1-2CB-02 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 220-MONEYPOINT GIS 220-220SB1-2CB | 5 | 5 | 5 | Scheduled | 20/05/2024 | 24/05/2024
TO-24-MP GIS-T4001-01 | GENERATOR TRANSFORMER - MONEYPOINT GIS 400-MONEYPOINT GIS G1-T4001 | 12 | 10 | 10 | Scheduled | 20/05/2024 | 31/05/2024
TO-24-MP GIS-T4201-01 | TRANSFORMER - MONEYPOINT GIS 400-MONEYPOINT GIS 220-T4201 | 5 | 5 | 5 | Scheduled | 20/05/2024 | 24/05/2024
TO-24-BYH-CDL-1-01 | 110kV FEEDER - BALLYNAHULLA 110-CORDAL 110-1 | 4 | 4 | 4 | Scheduled | 27/05/2024 | 30/05/2024
TO-24-CDL-110SA1-01 | SECTIONALISING DISCONNECT - CORDAL 110-CORDAL 110-110SA1 | 4 | 4 | 4 | Scheduled | 27/05/2024 | 30/05/2024
TO-24-CDL-110SA2-01 | SECTIONALISING DISCONNECT - CORDAL 110-CORDAL 110-110SA2 | 4 | 4 | 4 | Scheduled | 27/05/2024 | 30/05/2024
TO-24-CDL-T132-01 | GENERATOR TRANSFORMER - CORDAL 110-CORDAL 33-T132 | 4 | 4 |  | Scheduled | 27/05/2024 | 30/05/2024
TO-24-CDL-T141-01 | DISTRIBUTION TRANSFORMER - CORDAL 110-CORDAL 38-T141 | 4 | 4 | 4 | Reference | 27/05/2024 | 30/05/2024
TO-24-400 kV A2 @ MP GIS-01 | BUSBAR SECTION - MONEYPOINT GIS 400-MONEYPOINT GIS 400-400A2 | 5 | 5 | 5 | Scheduled | 27/05/2024 | 31/05/2024
TO-24-400 kV B2 @ MP GIS-01 | BUSBAR SECTION - MONEYPOINT GIS 400-MONEYPOINT GIS 400-400B2 | 5 | 5 | 5 | Scheduled | 27/05/2024 | 31/05/2024
TO-24-MP GIS-400SA1-2CB-03 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 400-MONEYPOINT GIS 400-400SA1-2CB | 5 | 5 | 5 | Scheduled | 27/05/2024 | 31/05/2024
TO-24-MP GIS-400SA2-4CB-03 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 400-MONEYPOINT GIS 400-400SA2-4CB | 5 | 5 | 5 | Scheduled | 27/05/2024 | 31/05/2024
TO-24-MP GIS-400SB1-2CB-05 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 400-MONEYPOINT GIS 400-400SB1-2CB | 5 | 5 | 5 | Scheduled | 27/05/2024 | 31/05/2024
TO-24-MP GIS-400SB2-4CB-01 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 400-MONEYPOINT GIS 400-400SB2-4CB | 5 | 5 | 5 | Scheduled | 27/05/2024 | 31/05/2024
TO-24-MP GIS-T4002-02 | GENERATOR TRANSFORMER - MONEYPOINT GIS 400-MONEYPOINT GIS G2-T4002 | 5 | 5 | 5 | Scheduled | 27/05/2024 | 31/05/2024
TO-24-GLE-KCR-1-01 | 110kV FEEDER - GLENLARA 110-KNOCKACUMMER 110-1 | 4 | 4 | 4 | Scheduled | 04/06/2024 | 07/06/2024
TO-24-KCR-T121-01 | GENERATOR TRANSFORMER - KNOCKACUMMER 110-KNOCKACUMMER 20-T121 | 4 | 4 | 4 | Scheduled | 04/06/2024 | 07/06/2024
TO-24-AA GIS-LIM-1-01 | 110kV FEEDER - ARDNACRUSHA GIS 110-LIMERICK 110-1 | 3 | 3 | 3 | Scheduled | 05/06/2024 | 07/06/2024
TO-24-BYH-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - BALLYNAHULLA 110-BALLYNAHULLA 110-110SA1-2CB | 1 | 1 | 1 | Scheduled | 05/06/2024 | 05/06/2024
TO-24-DAL-T141-02 | DISTRIBUTION TRANSFORMER - DALLOW 110-DALLOW 38-T141 | 6 | 4 | 4 | Reference | 05/06/2024 | 10/06/2024
TO-24-DAL,T-DAL-1-02 | 110kV FEEDER - DALLOW tee-DALLOW 110-1 | 6 | 4 | 4 | Scheduled | 05/06/2024 | 10/06/2024
TO-24-KLN-T2101-01 | TRANSFORMER - KILLONAN 220-KILLONAN 110-T2101 | 3 | 3 | 3 | Scheduled | 05/06/2024 | 07/06/2024
TO-24-AA GIS-T102-01 | GENERATOR TRANSFORMER - ARDNACRUSHA GIS 110-ARDNACRUSHA GIS G2-T102 | 5 | 5 | 5 | Scheduled | 10/06/2024 | 14/06/2024
TO-24-AUG-CFM-2-01 | 110kV FEEDER - AUGHINISH 110-CASTLEFARM 110-2 | 5 | 5 | 5 | Scheduled | 10/06/2024 | 14/06/2024
TO-24-AUG-SK-3-01 | 110kV FEEDER - AUGHINISH 110-SEALROCK 110-3 | 5 | 5 | 5 | Scheduled | 10/06/2024 | 14/06/2024
TO-24-CFM-T102-01 | TSO CUSTOMER TRANSFORMER - CASTLEFARM 110-CASTLEFARM 10-T102 | 5 | 5 | 5 | Reference | 10/06/2024 | 14/06/2024
TO-24-DRU-ENN-1-02 | 110kV FEEDER - DRUMLINE 110-ENNIS 110-1 | 123 | 88 | 88 | Scheduled | 10/06/2024 | 10/10/2024
TO-24-KPG-TRL-2-02 | 110kV FEEDER - KILPADDOGE 110-TRALEE 110-2 | 8 | 6 | 6 | Scheduled | 10/06/2024 | 17/06/2024
TO-24-SK-T103-01 | GENERATOR TRANSFORMER - SEALROCK 110-SEALROCK G3-T103 | 5 | 5 | 5 | Scheduled | 10/06/2024 | 14/06/2024
TO-24-CHA-MAL-1-01 | 110kV FEEDER - CHARLEVILLE 110-MALLOW 110-1 | 14 | 10 | 10 | Scheduled | 11/06/2024 | 24/06/2024
TO-24-CAH-KHL-1-01 | 110kV FEEDER - CAHIR 110-KILL HILL 110-1 | 2 | 2 | 2 | Scheduled | 12/06/2024 | 13/06/2024
TO-24-ATE-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - ATHEA 110-ATHEA 110-110SA1-2CB | 10 | 8 | 8 | Scheduled | 17/06/2024 | 26/06/2024
TO-24-ATE-DRO-1-01 | 110kV FEEDER - ATHEA 110-DROMADA 110-1 | 10 | 8 | 8 | Scheduled | 17/06/2024 | 26/06/2024
TO-24-ATE-KNR-1-01 | 110kV FEEDER - ATHEA 110-KNOCKANURE 110-1 | 10 | 8 | 8 | Scheduled | 17/06/2024 | 26/06/2024
TO-24-ATE-T121-01 | GENERATOR TRANSFORMER - ATHEA 110-ATHEA 20-T121 | 10 | 8 | 8 | Scheduled | 17/06/2024 | 26/06/2024
TO-24-ATE-TOB-1-02 | 110kV FEEDER - ATHEA 110-TOBERTOREEN 110-1 | 10 | 8 | 8 | Scheduled | 17/06/2024 | 26/06/2024
TO-24-DRO-T121-02 | GENERATOR TRANSFORMER - DROMADA 110-DROMADA 20-T121 | 10 | 8 | 8 | Scheduled | 17/06/2024 | 26/06/2024
TO-24-KPG-TB-2-03 | 220kV FEEDER - KILPADDOGE 220-TARBERT 220-2 | 14 | 10 |  | Scheduled | 17/06/2024 | 30/06/2024
TO-24-400 kV A1 @ MP GIS-03 | BUSBAR SECTION - MONEYPOINT GIS 400-MONEYPOINT GIS 400-400A1 | 5 | 5 | 5 | Scheduled | 17/06/2024 | 21/06/2024
TO-24-400 kV A3 @ MP GIS-01 | BUSBAR SECTION - MONEYPOINT GIS 400-MONEYPOINT GIS 400-400A3 | 5 | 5 | 5 | Scheduled | 17/06/2024 | 21/06/2024
TO-24-MP GIS-400K3-03 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 400-MONEYPOINT GIS 400-400K3 | 5 | 5 | 5 | Scheduled | 17/06/2024 | 21/06/2024
TO-24-MP GIS-400SA1-2CB-04 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 400-MONEYPOINT GIS 400-400SA1-2CB | 5 | 5 | 5 | Scheduled | 17/06/2024 | 21/06/2024
TO-24-MP GIS-400SA1-3CB-01 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 400-MONEYPOINT GIS 400-400SA1-3CB | 5 | 5 | 5 | Scheduled | 17/06/2024 | 21/06/2024
TO-24-220 kV A1/A2 @ TB-02 | BUSBAR SECTION - TARBERT 220-TARBERT 220-220A1-A2 | 14 | 10 |  | Scheduled | 17/06/2024 | 30/06/2024
TO-24-TOB-T132-02 | GENERATOR TRANSFORMER - TOBERTOREEN 110-TOBERTOREEN 33-T132 | 10 | 8 | 8 | Scheduled | 17/06/2024 | 26/06/2024
TO-24-AUG-MTN-1-01 | 110kV FEEDER - AUGHINISH 110-MONETEEN 110-1 | 9 | 7 | 7 | Scheduled | 18/06/2024 | 26/06/2024
TO-24-CTN-KLN-1-01 | 110kV FEEDER - CAUTEEN 110-KILLONAN 110-1 | 4 | 4 | 4 | Scheduled | 25/06/2024 | 28/06/2024
TO-24-CNO-KPG-1-01 | 110kV FEEDER - COOLNANOONAGH 110-KILPADDOGE 110-1 | 2 | 2 | 2 | Scheduled | 27/06/2024 | 28/06/2024
TO-24-CNO-T131-01 | GENERATOR TRANSFORMER - COOLNANOONAGH 110-COOLNANOONAGH 33-T131 | 2 | 2 |  | Scheduled | 27/06/2024 | 28/06/2024
TO-24-BVK-COT-1-01 | 110kV FEEDER - BALLYVOUSKILL 110-COOMATAGGART 110-1 | 9 | 7 |  | Scheduled | 01/07/2024 | 09/07/2024
TO-24-COT-110SA1-01 | SECTIONALISING DISCONNECT - COOMATAGGART 110-COOMATAGGART 110-110SA1 | 9 | 7 | 7 | Scheduled | 01/07/2024 | 09/07/2024
TO-24-COT-110SA2-01 | SECTIONALISING DISCONNECT - COOMATAGGART 110-COOMATAGGART 110-110SA2 | 9 | 7 | 7 | Scheduled | 01/07/2024 | 09/07/2024
TO-24-COT-FILTER1-01 | CAPACITOR/SVC/REACTOR - COOMATAGGART 110-COOMATAGGART 110-FILTER1 | 9 | 7 | 7 | Scheduled | 01/07/2024 | 09/07/2024
TO-24-COT-T132-01 | GENERATOR TRANSFORMER - COOMATAGGART 110-COOMATAGGART 33-T132 | 9 | 7 |  | Scheduled | 01/07/2024 | 09/07/2024
TO-24-COT-T141-01 | DISTRIBUTION TRANSFORMER - COOMATAGGART 110-COOMATAGGART 38-T141 | 9 | 7 | 7 | Reference | 01/07/2024 | 09/07/2024
TO-24-ENN-SLC-1-02 | 110kV FEEDER - ENNIS 110-SLIEVECALLAN 110-1 | 3 | 3 | 3 | Scheduled | 03/07/2024 | 05/07/2024
TO-24-SLC-110SA1-02 | SECTIONALISING DISCONNECT - SLIEVECALLAN 110-SLIEVECALLAN 110-110SA1 | 3 | 3 | 3 | Scheduled | 03/07/2024 | 05/07/2024
TO-24-SLC-110SA2-02 | SECTIONALISING DISCONNECT - SLIEVECALLAN 110-SLIEVECALLAN 110-110SA2 | 3 | 3 | 3 | Scheduled | 03/07/2024 | 05/07/2024
TO-24-SLC-T121-02 | GENERATOR TRANSFORMER - SLIEVECALLAN 110-SLIEVECALLAN 20-T121 | 3 | 3 | 3 | Scheduled | 03/07/2024 | 05/07/2024
TO-24-SLC-T122-02 | GENERATOR TRANSFORMER - SLIEVECALLAN 110-SLIEVECALLAN 20-T122 | 3 | 3 | 3 | Scheduled | 03/07/2024 | 05/07/2024
TO-24-AUG-SK-4-01 | 110kV FEEDER - AUGHINISH 110-SEALROCK 110-4 | 65 | 46 | 46 | Scheduled | 08/07/2024 | 10/09/2024
TO-24-CLA-CKN-1-01 | 110kV FEEDER - CLASHAVOON 110-CLONKEEN 110-1 | 19 | 15 | 15 | Scheduled | 08/07/2024 | 26/07/2024
TO-24-CKN-110SA1-2CB-02 | COUPLER/SECTIONALISING CB - CLONKEEN 110-CLONKEEN 110-110SA1-2CB | 19 | 15 | 15 | Scheduled | 08/07/2024 | 26/07/2024
TO-24-CKN-CGL-1-02 | 110kV FEEDER - CLONKEEN 110-COOMAGEARLAHY 110-1 | 19 | 15 | 15 | Scheduled | 08/07/2024 | 26/07/2024
TO-24-CKN-GRO-1-02 | 110kV FEEDER - CLONKEEN 110-GARROW 110-1 | 19 | 15 | 15 | Scheduled | 08/07/2024 | 26/07/2024
TO-24-CKN-KER-1-02 | 110kV FEEDER - CLONKEEN 110-KNOCKEARAGH 110-1 | 19 | 15 | 15 | Scheduled | 08/07/2024 | 26/07/2024
TO-24-CGL-110SA1-02 | SECTIONALISING DISCONNECT - COOMAGEARLAHY 110-COOMAGEARLAHY 110-110SA1 | 19 | 15 | 15 | Scheduled | 08/07/2024 | 26/07/2024
TO-24-CGL-110SA2-02 | SECTIONALISING DISCONNECT - COOMAGEARLAHY 110-COOMAGEARLAHY 110-110SA2 | 19 | 15 | 15 | Scheduled | 08/07/2024 | 26/07/2024
TO-24-CGL-GAE-1-02 | 110kV FEEDER - COOMAGEARLAHY 110-GLANLEE 110-1 | 19 | 15 | 15 | Scheduled | 08/07/2024 | 26/07/2024
TO-24-CGL-T121-02 | GENERATOR TRANSFORMER - COOMAGEARLAHY 110-COOMAGEARLAHY 20-T121 | 19 | 15 | 15 | Scheduled | 08/07/2024 | 26/07/2024
TO-24-CGL-T122-02 | GENERATOR TRANSFORMER - COOMAGEARLAHY 110-COOMAGEARLAHY 20-T122 | 19 | 15 |  | Scheduled | 08/07/2024 | 26/07/2024
TO-24-GAE-T121-01 | GENERATOR TRANSFORMER - GLANLEE 110-GLANLEE 20-T121 | 19 | 15 | 15 | Scheduled | 08/07/2024 | 26/07/2024
TO-24-SK-T104-01 | GENERATOR TRANSFORMER - SEALROCK 110-SEALROCK G4-T104 | 65 | 46 | 46 | Scheduled | 08/07/2024 | 10/09/2024
TO-24-KPG-TB-1-07 | 220kV FEEDER - KILPADDOGE 220-TARBERT 220-1 | 26 | 18 | 18 | Scheduled | 10/07/2024 | 04/08/2024
TO-24-TB-220K1-2-08 | COUPLER/SECTIONALISING CB - TARBERT 220-TARBERT 220-220K1-2 | 26 | 18 | 18 | Scheduled | 10/07/2024 | 04/08/2024
TO-24-TB-T2004-05 | GENERATOR TRANSFORMER - TARBERT 220-TARBERT G4-T2004 | 26 | 18 | 18 | Scheduled | 10/07/2024 | 04/08/2024
TO-24-CAH-TIP-1-03 | 110kV FEEDER - CAHIR 110-TIPPERARY 110-1 | 5 | 5 | 5 | Scheduled | 15/07/2024 | 19/07/2024
TO-24-GRO-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - GARROW 110-GARROW 110-110SA1-2CB | 5 | 5 | 5 | Scheduled | 15/07/2024 | 19/07/2024
TO-24-GRO-T122-01 | GENERATOR TRANSFORMER - GARROW 110-GARROW 20-T122 | 5 | 5 | 5 | Scheduled | 15/07/2024 | 19/07/2024
TO-24-220 kV A4 @ KPG-02 | BUSBAR SECTION - KILPADDOGE 220-KILPADDOGE 220-220A4 | 5 | 5 | 5 | Scheduled | 15/07/2024 | 19/07/2024
TO-24-220 kV B4 @ KPG-02 | BUSBAR SECTION - KILPADDOGE 220-KILPADDOGE 220-220B4 | 5 | 5 | 5 | Scheduled | 15/07/2024 | 19/07/2024
TO-24-KPG-220K4-03 | COUPLER/SECTIONALISING CB - KILPADDOGE 220-KILPADDOGE 220-220K4 | 5 | 5 | 5 | Scheduled | 15/07/2024 | 19/07/2024
TO-24-KPG-220SA2-4CB-03 | COUPLER/SECTIONALISING CB - KILPADDOGE 220-KILPADDOGE 220-220SA2-4CB | 5 | 5 | 5 | Scheduled | 15/07/2024 | 19/07/2024
TO-24-KPG-220SB2-4CB-02 | COUPLER/SECTIONALISING CB - KILPADDOGE 220-KILPADDOGE 220-220SB2-4CB | 5 | 5 | 5 | Scheduled | 15/07/2024 | 19/07/2024
TO-24-KPG-MP GIS-2-01 | 220kV FEEDER - KILPADDOGE 220-MONEYPOINT GIS 220-2 | 5 | 5 | 5 | Scheduled | 15/07/2024 | 19/07/2024
TO-24-KHL-T131-01 | GENERATOR TRANSFORMER - KILL HILL 110-KILL HILL 33-T131 | 1 | 1 | 1 | Scheduled | 16/07/2024 | 16/07/2024
TO-24-CSH-PRO-1-04 | 220kV FEEDER - CASHLA 220-PROSPECT 220-1 | 1 | 1 |  | Scheduled | 19/07/2024 | 19/07/2024
TO-24-KPG-TB-1-03 | 220kV FEEDER - KILPADDOGE 220-TARBERT 220-1 | 2 | 2 | 2 | Scheduled | 25/07/2024 | 26/07/2024
TO-24-TB-220K1-2-03 | COUPLER/SECTIONALISING CB - TARBERT 220-TARBERT 220-220K1-2 | 2 | 2 | 2 | Scheduled | 25/07/2024 | 26/07/2024
TO-24-TB-T2004-03 | GENERATOR TRANSFORMER - TARBERT 220-TARBERT G4-T2004 | 2 | 2 | 2 | Scheduled | 25/07/2024 | 26/07/2024
TO-24-CBA-110SA1-02 | SECTIONALISING DISCONNECT - CLOGHBOOLA 110-CLOGHBOOLA 110-110SA1 | 5 | 5 | 5 | Scheduled | 29/07/2024 | 02/08/2024
TO-24-CBA-110SA2-02 | SECTIONALISING DISCONNECT - CLOGHBOOLA 110-CLOGHBOOLA 110-110SA2 | 5 | 5 | 5 | Scheduled | 29/07/2024 | 02/08/2024
TO-24-CBA-T122-01 | DISTRIBUTION TRANSFORMER - CLOGHBOOLA 110-CLOGHBOOLA 20-T122 | 5 | 5 | 5 | Reference | 29/07/2024 | 02/08/2024
TO-24-CBA-T131-01 | GENERATOR TRANSFORMER - CLOGHBOOLA 110-CLOGHBOOLA 33-T131 | 5 | 5 | 5 | Scheduled | 29/07/2024 | 02/08/2024
TO-24-CBA-TRI-1-01 | 110kV FEEDER - CLOGHBOOLA 110-TRIEN 110-1 | 5 | 5 |  | Scheduled | 29/07/2024 | 02/08/2024
TO-24-KNR-T2101-02 | TRANSFORMER - KNOCKANURE 220-KNOCKANURE 110-T2101 | 2 | 2 | 2 | Scheduled | 31/07/2024 | 01/08/2024
TO-24-KPG-TB-1-04 | 220kV FEEDER - KILPADDOGE 220-TARBERT 220-1 | 4 | 3 |  | Scheduled | 05/08/2024 | 08/08/2024
TO-24-TB-220K1-2-04 | COUPLER/SECTIONALISING CB - TARBERT 220-TARBERT 220-220K1-2 | 4 | 3 |  | Scheduled | 05/08/2024 | 08/08/2024
TO-24-TB-T2004-04 | GENERATOR TRANSFORMER - TARBERT 220-TARBERT G4-T2004 | 4 | 3 |  | Scheduled | 05/08/2024 | 08/08/2024
TO-24-BVK-T2102-02 | TRANSFORMER - BALLYVOUSKILL 220-BALLYVOUSKILL 110-T2102 | 2 | 2 | 2 | Scheduled | 06/08/2024 | 07/08/2024
TO-24-LSN-110SA1-2-03 | SECTIONALISING DISCONNECT - LISHEEN 110-LISHEEN 110-110SA1-2 | 11 | 9 | 9 | Scheduled | 06/08/2024 | 16/08/2024
TO-24-LSN-110SA2-4-03 | SECTIONALISING DISCONNECT - LISHEEN 110-LISHEEN 110-110SA2-4 | 11 | 9 | 9 | Scheduled | 06/08/2024 | 16/08/2024
TO-24-LSN-T122-03 | GENERATOR TRANSFORMER - LISHEEN 110-LISHEEN 20-T122 | 11 | 9 | 9 | Scheduled | 06/08/2024 | 16/08/2024
TO-24-LSN-T131-03 | GENERATOR TRANSFORMER - LISHEEN 110-LISHEEN 33-T131 | 11 | 9 | 9 | Scheduled | 06/08/2024 | 16/08/2024
TO-24-LSN-T142-02 | DISTRIBUTION TRANSFORMER - LISHEEN 110-LISHEEN 38-T142 | 11 | 9 | 9 | Reference | 06/08/2024 | 16/08/2024
TO-24-LSN-THU-1-03 | 110kV FEEDER - LISHEEN 110-THURLES 110-1 | 11 | 9 | 9 | Scheduled | 06/08/2024 | 16/08/2024
TO-24-REM-110SA1-01 | SECTIONALISING DISCONNECT - REAMORE 110-REAMORE 110-110SA1 | 22 | 16 | 16 | Scheduled | 07/08/2024 | 28/08/2024
TO-24-REM-110SA2-01 | SECTIONALISING DISCONNECT - REAMORE 110-REAMORE 110-110SA2 | 22 | 16 | 16 | Scheduled | 07/08/2024 | 28/08/2024
TO-24-REM-T141-01 | DISTRIBUTION TRANSFORMER - REAMORE 110-REAMORE 38-T141 | 22 | 16 | 16 | Reference | 07/08/2024 | 28/08/2024
TO-24-REM-T142-01 | DISTRIBUTION TRANSFORMER - REAMORE 110-REAMORE 38-T142 | 22 | 16 | 16 | Reference | 07/08/2024 | 28/08/2024
TO-24-REM-TRL-1-01 | 110kV FEEDER - REAMORE 110-TRALEE 110-1 | 22 | 16 | 16 | Scheduled | 07/08/2024 | 28/08/2024
TO-24-KPG-TB-1-08 | 220kV FEEDER - KILPADDOGE 220-TARBERT 220-1 | 73 | 51 | 51 | Scheduled | 09/08/2024 | 20/10/2024
TO-24-TB-220K1-2-09 | COUPLER/SECTIONALISING CB - TARBERT 220-TARBERT 220-220K1-2 | 67 | 47 | 47 | Scheduled | 09/08/2024 | 14/10/2024
TO-24-TB-T2004-06 | GENERATOR TRANSFORMER - TARBERT 220-TARBERT G4-T2004 | 67 | 47 | 47 | Scheduled | 09/08/2024 | 14/10/2024
TO-24-BYH-BVK-1-02 | 220kV FEEDER - BALLYNAHULLA 220-BALLYVOUSKILL 220-1 | 12 | 10 | 10 | Scheduled | 12/08/2024 | 23/08/2024
TO-24-220 kV A2 @ BVK-03 | BUSBAR SECTION - BALLYVOUSKILL 220-BALLYVOUSKILL 220-220A2 | 12 | 10 | 10 | Scheduled | 12/08/2024 | 23/08/2024
TO-24-220 kV B2 @ BVK-03 | BUSBAR SECTION - BALLYVOUSKILL 220-BALLYVOUSKILL 220-220B2 | 12 | 10 | 10 | Scheduled | 12/08/2024 | 23/08/2024
TO-24-BVK-220K2-06 | COUPLER/SECTIONALISING CB - BALLYVOUSKILL 220-BALLYVOUSKILL 220-220K2 | 12 | 10 | 10 | Scheduled | 12/08/2024 | 23/08/2024
TO-24-BVK-220SA1-2CB-04 | COUPLER/SECTIONALISING CB - BALLYVOUSKILL 220-BALLYVOUSKILL 220-220SA1-2CB | 12 | 10 | 10 | Scheduled | 12/08/2024 | 23/08/2024
TO-24-BVK-220SB1-2CB-04 | COUPLER/SECTIONALISING CB - BALLYVOUSKILL 220-BALLYVOUSKILL 220-220SB1-2CB | 12 | 10 | 10 | Scheduled | 12/08/2024 | 23/08/2024
TO-24-DRU-T141-01 | DISTRIBUTION TRANSFORMER - DRUMLINE 110-DRUMLINE 38-T141 | 85 | 60 |  | Reference | 12/08/2024 | 04/11/2024
TO-24-220 kV A2 @ BYH-03 | BUSBAR SECTION - BALLYNAHULLA 220-BALLYNAHULLA 220-220A2 | 11 | 9 | 9 | Scheduled | 13/08/2024 | 23/08/2024
TO-24-220 kV B2 @ BYH-03 | BUSBAR SECTION - BALLYNAHULLA 220-BALLYNAHULLA 220-220B2 | 11 | 9 | 9 | Scheduled | 13/08/2024 | 23/08/2024
TO-24-BYH-220K2-04 | COUPLER/SECTIONALISING CB - BALLYNAHULLA 220-BALLYNAHULLA 220-220K2 | 11 | 9 | 9 | Scheduled | 13/08/2024 | 23/08/2024
TO-24-BYH-220SA1-2CB-05 | COUPLER/SECTIONALISING CB - BALLYNAHULLA 220-BALLYNAHULLA 220-220SA1-2CB | 11 | 9 | 9 | Scheduled | 13/08/2024 | 23/08/2024
TO-24-BYH-220SB1-2CB-06 | COUPLER/SECTIONALISING CB - BALLYNAHULLA 220-BALLYNAHULLA 220-220SB1-2CB | 11 | 9 | 9 | Scheduled | 13/08/2024 | 23/08/2024
TO-24-BOL-110SA1-3CB-02 | COUPLER/SECTIONALISING CB - BOOLTIAGH 110-BOOLTIAGH 110-110SA1-3CB | 2 | 2 | 33 | Proposed | 14/08/2024 | 15/08/2024
TO-24-BOL-ENN-1-02 | 110kV FEEDER - BOOLTIAGH 110-ENNIS 110-1 | 2 | 2 | 2 | Proposed | 14/08/2024 | 15/08/2024
TO-24-BOL-T143-02 | DISTRIBUTION TRANSFORMER - BOOLTIAGH 110-BOOLTIAGH 38-T143 | 2 | 2 | 2 | Reference (Proposed) | 14/08/2024 | 15/08/2024
TO-24-BOL-110SA1-3CB-03 | COUPLER/SECTIONALISING CB - BOOLTIAGH 110-BOOLTIAGH 110-110SA1-3CB | 12 | 10 | 10 | Scheduled | 19/08/2024 | 30/08/2024
TO-24-BOL-T121-01 | GENERATOR TRANSFORMER - BOOLTIAGH 110-BOOLTIAGH 20-T121 | 12 | 10 | 10 | Scheduled | 19/08/2024 | 30/08/2024
TO-24-KHL-THU-1-01 | 110kV FEEDER - KILL HILL 110-THURLES 110-1 | 9 | 7 | 7 | Scheduled | 19/08/2024 | 27/08/2024
TO-24-TBK-T141-01 | DISTRIBUTION TRANSFORMER - TULLABRACK 110-TULLABRACK 38-T141 | 12 | 10 | 10 | Reference | 19/08/2024 | 30/08/2024
TO-24-TBK,T-BOL-1-01 | 110kV FEEDER - TULLABRACK tee-BOOLTIAGH 110-1 | 12 | 10 | 10 | Scheduled | 19/08/2024 | 30/08/2024
TO-24-TBK,T-MP GIS-1-01 | 110kV FEEDER - TULLABRACK tee-MONEYPOINT GIS 110-1 | 12 | 10 | 10 | Scheduled | 19/08/2024 | 30/08/2024
TO-24-TBK,T-TBK-1-01 | 110kV FEEDER - TULLABRACK tee-TULLABRACK 110-1 | 12 | 10 | 10 | Scheduled | 19/08/2024 | 30/08/2024
TO-24-DAL-T141-06 | DISTRIBUTION TRANSFORMER - DALLOW 110-DALLOW 38-T141 | 16 | 12 | 12 | Reference | 20/08/2024 | 04/09/2024
TO-24-DAL,T-DAL-1-08 | 110kV FEEDER - DALLOW tee-DALLOW 110-1 | 16 | 12 | 12 | Scheduled | 20/08/2024 | 04/09/2024
TO-24-DAL,T-SH-1-10 | 110kV FEEDER - DALLOW tee-SHANNONBRIDGE 110-1 | 16 | 12 | 12 | Scheduled | 20/08/2024 | 04/09/2024
TO-24-CHA-GLE-1-03 | 110kV FEEDER - CHARLEVILLE 110-GLENLARA 110-1 | 8 | 6 |  | Scheduled | 27/08/2024 | 03/09/2024
TO-24-GLE-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - GLENLARA 110-GLENLARA 110-110SA1-2CB | 8 | 6 | 6 | Scheduled | 27/08/2024 | 03/09/2024
TO-24-CLH-TRL-1-01 | 110kV FEEDER - CLAHANE 110-TRALEE 110-1 | 40 | 30 | 30 | Scheduled | 02/09/2024 | 11/10/2024
TO-24-MP GIS-T121-01 | GENERATOR TRANSFORMER - MONEYPOINT GIS 110-MONEYPOINT GIS 20-T121 | 5 | 5 | 5 | Scheduled | 02/09/2024 | 06/09/2024
TO-24-MP GIS-T2102-01 | TRANSFORMER - MONEYPOINT GIS 220-MONEYPOINT GIS 110-T2102 | 5 | 5 | 5 | Scheduled | 02/09/2024 | 06/09/2024
TO-24-MP GIS-T4202-02 | TRANSFORMER - MONEYPOINT GIS 400-MONEYPOINT GIS 220-T4202 | 5 | 5 |  | Scheduled | 02/09/2024 | 06/09/2024
TO-24-110 kV A3 @ KPG-01 | BUSBAR SECTION - KILPADDOGE 110-KILPADDOGE 110-110A3 | 11 | 9 | 9 | Scheduled | 03/09/2024 | 13/09/2024
TO-24-110 kV B3 @ KPG-01 | BUSBAR SECTION - KILPADDOGE 110-KILPADDOGE 110-110B3 | 11 | 9 | 9 | Scheduled | 03/09/2024 | 13/09/2024
TO-24-KPG-110K3-01 | COUPLER/SECTIONALISING CB - KILPADDOGE 110-KILPADDOGE 110-110K3 | 11 | 9 | 9 | Scheduled | 03/09/2024 | 13/09/2024
TO-24-KPG-110SA1-3CB-02 | COUPLER/SECTIONALISING CB - KILPADDOGE 110-KILPADDOGE 110-110SA1-3CB | 11 | 9 | 9 | Scheduled | 03/09/2024 | 13/09/2024
TO-24-KPG-110SB1-3CB-02 | COUPLER/SECTIONALISING CB - KILPADDOGE 110-KILPADDOGE 110-110SB1-3CB | 11 | 9 | 9 | Scheduled | 03/09/2024 | 13/09/2024
TO-24-KPG-RAT-1-01 | 110kV FEEDER - KILPADDOGE 110-RATHKEALE 110-1 | 11 | 9 | 9 | Scheduled | 03/09/2024 | 13/09/2024
TO-24-MP GIS-400K4-01 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 400-MONEYPOINT GIS 400-400K4 | 1 | 1 | 1 | Scheduled | 04/09/2024 | 04/09/2024
TO-24-AA GIS-T103-01 | GENERATOR TRANSFORMER - ARDNACRUSHA GIS 110-ARDNACRUSHA GIS G3-T103 | 5 | 5 | 5 | Scheduled | 09/09/2024 | 13/09/2024
TO-24-AA GIS-110K2-02 | COUPLER/SECTIONALISING CB - ARDNACRUSHA GIS 110-ARDNACRUSHA GIS 110-110K2 | 1 | 1 | 1 | Scheduled | 10/09/2024 | 10/09/2024
TO-24-BOL-ENN-1-03 | 110kV FEEDER - BOOLTIAGH 110-ENNIS 110-1 | 5 | 5 | 5 | Scheduled | 16/09/2024 | 20/09/2024
TO-24-110 kV A2 @ KLN-02 | BUSBAR SECTION - KILLONAN 110-KILLONAN 110-110A2 | 18 | 14 | 14 | Scheduled | 16/09/2024 | 03/10/2024
TO-24-110 kV B2 @ KLN-03 | BUSBAR SECTION - KILLONAN 110-KILLONAN 110-110B2 | 18 | 14 | 14 | Scheduled | 16/09/2024 | 03/10/2024
TO-24-220 kV A2 @ KLN-03 | BUSBAR SECTION - KILLONAN 220-KILLONAN 220-220A2 | 18 | 14 | 14 | Scheduled | 16/09/2024 | 03/10/2024
TO-24-220 kV B2 @ KLN-02 | BUSBAR SECTION - KILLONAN 220-KILLONAN 220-220B2 | 18 | 14 | 14 | Scheduled | 16/09/2024 | 03/10/2024
TO-24-KLN-T2104-01 | TRANSFORMER - KILLONAN 220-KILLONAN 110-T2104 | 18 | 14 | 14 | Scheduled | 16/09/2024 | 03/10/2024
TO-24-AUG-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - AUGHINISH 110-AUGHINISH 110-110SA1-2CB | 2 | 2 | 2 | Scheduled | 17/09/2024 | 18/09/2024
TO-24-CTN-TIP-1-02 | 110kV FEEDER - CAUTEEN 110-TIPPERARY 110-1 | 2 | 2 | 2 | Scheduled | 17/09/2024 | 18/09/2024
TO-24-CHA-110SA1-2CB-02 | COUPLER/SECTIONALISING CB - CHARLEVILLE 110-CHARLEVILLE 110-110SA1-2CB | 5 | 5 |  | Scheduled | 23/09/2024 | 27/09/2024
TO-24-CHA-MAL-1-03 | 110kV FEEDER - CHARLEVILLE 110-MALLOW 110-1 | 5 | 5 |  | Scheduled | 23/09/2024 | 27/09/2024
TO-24-CHA-T142-02 | DISTRIBUTION TRANSFORMER - CHARLEVILLE 110-CHARLEVILLE 38-T142 | 5 | 5 |  | Reference | 23/09/2024 | 27/09/2024
TO-24-CAH-TIP-1-01 | 110kV FEEDER - CAHIR 110-TIPPERARY 110-1 | 57 | 40 | 40 | Scheduled | 25/09/2024 | 20/11/2024
TO-24-CHA-KLN-1-01 | 110kV FEEDER - CHARLEVILLE 110-KILLONAN 110-1 | 5 | 5 | 5 | Scheduled | 30/09/2024 | 04/10/2024
TO-24-TB-T101-02 | GENERATOR TRANSFORMER - TARBERT 110-TARBERT G1-T101 | 2 | 2 | 2 | Scheduled | 01/10/2024 | 02/10/2024
TO-24-BVK-R2001-01 | CAPACITOR/SVC/REACTOR - BALLYVOUSKILL 220-BALLYVOUSKILL 220-R2001 | 1 | 1 | 1 | Scheduled | 03/10/2024 | 03/10/2024
TO-24-DSN-MP GIS-1-04 | 400kV FEEDER - DUNSTOWN 400-MONEYPOINT GIS 400-1 | 2 | 0 | 0 | Scheduled | 05/10/2024 | 06/10/2024
TO-24-AUG-CFM-1-02 | 110kV FEEDER - AUGHINISH 110-CASTLEFARM 110-1 | 5 | 5 | 5 | Scheduled | 07/10/2024 | 11/10/2024
TO-24-220 kV A1 @ BVK-01 | BUSBAR SECTION - BALLYVOUSKILL 220-BALLYVOUSKILL 220-220A1 | 5 | 5 | 5 | Scheduled | 07/10/2024 | 11/10/2024
TO-24-220 kV B1 @ BVK-01 | BUSBAR SECTION - BALLYVOUSKILL 220-BALLYVOUSKILL 220-220B1 | 5 | 5 | 5 | Scheduled | 07/10/2024 | 11/10/2024
TO-24-BVK-220K1-01 | COUPLER/SECTIONALISING CB - BALLYVOUSKILL 220-BALLYVOUSKILL 220-220K1 | 5 | 5 | 5 | Scheduled | 07/10/2024 | 11/10/2024
TO-24-BVK-220SA1-2CB-05 | COUPLER/SECTIONALISING CB - BALLYVOUSKILL 220-BALLYVOUSKILL 220-220SA1-2CB | 5 | 5 | 5 | Scheduled | 07/10/2024 | 11/10/2024
TO-24-BVK-220SB1-2CB-05 | COUPLER/SECTIONALISING CB - BALLYVOUSKILL 220-BALLYVOUSKILL 220-220SB1-2CB | 5 | 5 | 5 | Scheduled | 07/10/2024 | 11/10/2024
TO-24-CFM-T101-02 | TSO CUSTOMER TRANSFORMER - CASTLEFARM 110-CASTLEFARM 10-T101 | 5 | 5 | 5 | Reference | 07/10/2024 | 11/10/2024
TO-24-110 kV A2 @ KLN-03 | BUSBAR SECTION - KILLONAN 110-KILLONAN 110-110A2 | 9 | 7 | 7 | Scheduled | 07/10/2024 | 15/10/2024
TO-24-110 kV B2 @ KLN-04 | BUSBAR SECTION - KILLONAN 110-KILLONAN 110-110B2 | 9 | 7 | 7 | Scheduled | 07/10/2024 | 15/10/2024
TO-24-220 kV A2 @ KLN-04 | BUSBAR SECTION - KILLONAN 220-KILLONAN 220-220A2 | 9 | 7 | 7 | Scheduled | 07/10/2024 | 15/10/2024
TO-24-220 kV B2 @ KLN-03 | BUSBAR SECTION - KILLONAN 220-KILLONAN 220-220B2 | 9 | 7 | 7 | Scheduled | 07/10/2024 | 15/10/2024
TO-24-KLN-T2102-02 | TRANSFORMER - KILLONAN 220-KILLONAN 110-T2102 | 9 | 7 | 7 | Scheduled | 07/10/2024 | 15/10/2024
TO-24-KPG-MP GIS-1-01 | 220kV FEEDER - KILPADDOGE 220-MONEYPOINT GIS 220-1 | 8 | 6 | 6 | Scheduled | 08/10/2024 | 15/10/2024
TO-24-220 kV A2 @ BVK-04 | BUSBAR SECTION - BALLYVOUSKILL 220-BALLYVOUSKILL 220-220A2 | 10 | 8 | 8 | Scheduled | 14/10/2024 | 23/10/2024
TO-24-220 kV B2 @ BVK-04 | BUSBAR SECTION - BALLYVOUSKILL 220-BALLYVOUSKILL 220-220B2 | 10 | 8 | 8 | Scheduled | 14/10/2024 | 23/10/2024
TO-24-BVK-220K2-01 | COUPLER/SECTIONALISING CB - BALLYVOUSKILL 220-BALLYVOUSKILL 220-220K2 | 10 | 8 | 8 | Scheduled | 14/10/2024 | 23/10/2024
TO-24-BVK-220SA1-2CB-06 | COUPLER/SECTIONALISING CB - BALLYVOUSKILL 220-BALLYVOUSKILL 220-220SA1-2CB | 10 | 8 | 8 | Scheduled | 14/10/2024 | 23/10/2024
TO-24-BVK-220SB1-2CB-06 | COUPLER/SECTIONALISING CB - BALLYVOUSKILL 220-BALLYVOUSKILL 220-220SB1-2CB | 10 | 8 | 8 | Scheduled | 14/10/2024 | 23/10/2024
TO-24-MTN-MUN-2-02 | 110kV FEEDER - MONETEEN 110-MUNGRET 110-2 | 3 | 3 | 3 | Scheduled | 14/10/2024 | 16/10/2024
TO-24-MUN-T102-01 | TSO CUSTOMER TRANSFORMER - MUNGRET 110-MUNGRET 10-T102 | 3 | 3 | 3 | Reference | 14/10/2024 | 16/10/2024
TO-24-TIP-110SA1-02 | SECTIONALISING DISCONNECT - TIPPERARY 110-TIPPERARY 110-110SA1 | 5 | 5 | 5 | Scheduled | 14/10/2024 | 18/10/2024
TO-24-TIP-110SA2-01 | SECTIONALISING DISCONNECT - TIPPERARY 110-TIPPERARY 110-110SA2 | 5 | 5 | 5 | Scheduled | 14/10/2024 | 18/10/2024
TO-24-220 kV A1 @ TB-02 | BUSBAR SECTION - TARBERT 220-TARBERT 220-220A1 | 6 | 4 | 4 | Scheduled | 15/10/2024 | 20/10/2024
TO-24-220 kV B1 @ TB-02 | BUSBAR SECTION - TARBERT 220-TARBERT 220-220B1 | 6 | 4 | 4 | Scheduled | 15/10/2024 | 20/10/2024
TO-24-TB-T102-02 | GENERATOR TRANSFORMER - TARBERT 110-TARBERT G2-T102 | 2 | 2 | 2 | Scheduled | 15/10/2024 | 16/10/2024
TO-24-MP GIS-400SA2-4CB-01 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 400-MONEYPOINT GIS 400-400SA2-4CB | 1 | 1 | 1 | Scheduled | 16/10/2024 | 16/10/2024
TO-24-MTN-MUN-1-02 | 110kV FEEDER - MONETEEN 110-MUNGRET 110-1 | 2 | 2 | 2 | Scheduled | 17/10/2024 | 18/10/2024
TO-24-MP GIS-400SB1-2CB-01 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 400-MONEYPOINT GIS 400-400SB1-2CB | 1 | 1 | 1 | Scheduled | 17/10/2024 | 17/10/2024
TO-24-MUN-T101-01 | TSO CUSTOMER TRANSFORMER - MUNGRET 110-MUNGRET 10-T101 | 2 | 2 | 2 | Reference | 17/10/2024 | 18/10/2024
TO-24-KPG-KNR-1-110-01 | 110kV FEEDER - KILPADDOGE 110-KNOCKANURE 110-1-110 | 5 | 5 | 5 | Scheduled | 21/10/2024 | 25/10/2024
TO-24-LIM-RAT-1-04 | 110kV FEEDER - LIMERICK 110-RATHKEALE 110-1 | 5 | 5 | 5 | Scheduled | 21/10/2024 | 25/10/2024
TO-24-RAT-110SA1-01 | SECTIONALISING DISCONNECT - RATHKEALE 110-RATHKEALE 110-110SA1 | 5 | 5 | 5 | Scheduled | 21/10/2024 | 25/10/2024
TO-24-RAT-110SA2-01 | SECTIONALISING DISCONNECT - RATHKEALE 110-RATHKEALE 110-110SA2 | 5 | 5 | 5 | Scheduled | 21/10/2024 | 25/10/2024
TO-24-RAT-T142-01 | DISTRIBUTION TRANSFORMER - RATHKEALE 110-RATHKEALE 38-T142 | 5 | 5 | 5 | Reference | 21/10/2024 | 25/10/2024
TO-24-KLN-T2103-01 | TRANSFORMER - KILLONAN 220-KILLONAN 110-T2103 | 3 | 3 | 3 | Scheduled | 22/10/2024 | 24/10/2024
TO-24-KLN-KRA-1-01 | 220kV FEEDER - KILLONAN 220-KNOCKRAHA 220-1 | 4 | 4 |  | Scheduled | 29/10/2024 | 01/11/2024
TO-24-KNR-TRI-2-03 | 110kV FEEDER - KNOCKANURE 110-TRIEN 110-2 | 2 | 2 | 2 | Proposed | 29/10/2024 | 30/10/2024
TO-24-TRI-110SA1-2CB-02 | COUPLER/SECTIONALISING CB - TRIEN 110-TRIEN 110-110SA1-2CB | 1 | 1 | 1 | Proposed | 29/10/2024 | 29/10/2024
TO-24-TRI-T142-03 | DISTRIBUTION TRANSFORMER - TRIEN 110-TRIEN 38-T142 | 1 | 1 | 1 | Reference (Proposed) | 29/10/2024 | 29/10/2024
TO-24-220 kV A2 @ BYH-04 | BUSBAR SECTION - BALLYNAHULLA 220-BALLYNAHULLA 220-220A2 | 5 | 5 | 5 | Scheduled | 04/11/2024 | 08/11/2024
TO-24-220 kV B2 @ BYH-04 | BUSBAR SECTION - BALLYNAHULLA 220-BALLYNAHULLA 220-220B2 | 5 | 5 | 5 | Scheduled | 04/11/2024 | 08/11/2024
TO-24-BYH-220K2-01 | COUPLER/SECTIONALISING CB - BALLYNAHULLA 220-BALLYNAHULLA 220-220K2 | 5 | 5 | 5 | Scheduled | 04/11/2024 | 08/11/2024
TO-24-BYH-220SA1-2CB-04 | COUPLER/SECTIONALISING CB - BALLYNAHULLA 220-BALLYNAHULLA 220-220SA1-2CB | 5 | 5 | 5 | Scheduled | 04/11/2024 | 08/11/2024
TO-24-BYH-220SB1-2CB-05 | COUPLER/SECTIONALISING CB - BALLYNAHULLA 220-BALLYNAHULLA 220-220SB1-2CB | 5 | 5 | 5 | Scheduled | 04/11/2024 | 08/11/2024
TO-24-DRU-110SA1-01 | SECTIONALISING DISCONNECT - DRUMLINE 110-DRUMLINE 110-110SA1 | 1 | 1 | 1 | Scheduled | 04/11/2024 | 04/11/2024
TO-24-DRU-110SA2-01 | SECTIONALISING DISCONNECT - DRUMLINE 110-DRUMLINE 110-110SA2 | 1 | 1 | 1 | Scheduled | 04/11/2024 | 04/11/2024
TO-24-DRU-ENN-1-03 | 110kV FEEDER - DRUMLINE 110-ENNIS 110-1 | 1 | 1 |  | Scheduled | 04/11/2024 | 04/11/2024
TO-24-220 kV A1 @ KNR-01 | BUSBAR SECTION - KNOCKANURE 220-KNOCKANURE 220-220A1 | 13 | 10 | 10 | Scheduled | 04/11/2024 | 16/11/2024
TO-24-220 kV B1 @ KNR-01 | BUSBAR SECTION - KNOCKANURE 220-KNOCKANURE 220-220B1 | 13 | 10 | 10 | Scheduled | 04/11/2024 | 16/11/2024
TO-24-KNR-220K1-01 | COUPLER/SECTIONALISING CB - KNOCKANURE 220-KNOCKANURE 220-220K1 | 13 | 10 | 10 | Scheduled | 04/11/2024 | 16/11/2024
TO-24-KNR-220SA1-2CB-03 | COUPLER/SECTIONALISING CB - KNOCKANURE 220-KNOCKANURE 220-220SA1-2CB | 13 | 10 | 10 | Scheduled | 04/11/2024 | 16/11/2024
TO-24-KNR-220SB1-2CB-02 | COUPLER/SECTIONALISING CB - KNOCKANURE 220-KNOCKANURE 220-220SB1-2CB | 13 | 10 | 10 | Scheduled | 04/11/2024 | 16/11/2024
TO-24-KPG-KNR-2-01 | 220kV FEEDER - KILPADDOGE 220-KNOCKANURE 220-2 | 4 | 4 | 4 | Scheduled | 05/11/2024 | 08/11/2024
TO-24-CSH-ENN-1-01 | 110kV FEEDER - CASHLA 110-ENNIS 110-1 | 8 | 6 |  | Scheduled | 11/11/2024 | 18/11/2024
TO-24-KPG-KNR-1-01 | 220kV FEEDER - KILPADDOGE 220-KNOCKANURE 220-1 | 4 | 4 | 4 | Scheduled | 12/11/2024 | 15/11/2024
TO-24-BYH-110K1-01 | COUPLER/SECTIONALISING CB - BALLYNAHULLA 110-BALLYNAHULLA 110-110K1 | 5 | 5 | 5 | Scheduled | 18/11/2024 | 22/11/2024

## GEN_SouthEast
Outage ID | Feeder ID | Calendar Day Duration | Working Day Duration | Work Days | Outage Status | Start | Finish
TO-24-BOT-MLC-1-01 | 110kV FEEDER - BOGTOWN 110-MOUNTLUCAS 110-1 | 7 | 5 |  | Scheduled | 03/01/2024 | 09/01/2024
TO-24-BOT-T132-01 | GENERATOR TRANSFORMER - BOGTOWN 110-BOGTOWN 33-T132 | 7 | 5 | 5 | Scheduled | 03/01/2024 | 09/01/2024
TO-24-DER-MAY-1-02 | 110kV FEEDER - DERRYIRON 110-MAYNOOTH 110-1 | 5 | 5 | 5 | Scheduled | 15/01/2024 | 19/01/2024
TO-24-GI-T141-03 | DISTRIBUTION TRANSFORMER - GREAT ISLAND 110-GREAT ISLAND 38-T141 | 5 | 5 | 5 | Reference | 15/01/2024 | 19/01/2024
TO-24-KLS-KKY-1-02 | 110kV FEEDER - KELLIS 110-KILKENNY 110-1 | 10 | 7 | 7 | Scheduled | 29/01/2024 | 07/02/2024
TO-24-CUL-WAT-1-02 | 110kV FEEDER - CULLENAGH 110-WATERFORD 110-1 | 3 | 3 | 3 | Scheduled | 30/01/2024 | 01/02/2024
TO-24-CAH-TIP-1-02 | 110kV FEEDER - CAHIR 110-TIPPERARY 110-1 | 2 | 2 | 2 | Scheduled | 31/01/2024 | 01/02/2024
TO-24-DER-MAY-1-03 | 110kV FEEDER - DERRYIRON 110-MAYNOOTH 110-1 | 18 | 14 |  | Scheduled | 06/02/2024 | 23/02/2024
TO-24-CUL-GI GIS-1-04 | 220kV FEEDER - CULLENAGH 220-GREAT ISLAND GIS 220-1 | 2 | 2 | 2 | Scheduled | 19/02/2024 | 20/02/2024
TO-24-110 kV A1 @ ARK-01 | BUSBAR SECTION - ARKLOW 110-ARKLOW 110-110A1 | 12 | 10 | 10 | Scheduled | 26/02/2024 | 08/03/2024
TO-24-110 kV B1 @ ARK-01 | BUSBAR SECTION - ARKLOW 110-ARKLOW 110-110B1 | 12 | 10 | 10 | Scheduled | 26/02/2024 | 08/03/2024
TO-24-ARK-BOG-1-01 | 110kV FEEDER - ARKLOW 110-BANOGE 110-1 | 12 | 10 | 10 | Scheduled | 26/02/2024 | 08/03/2024
TO-24-CAH-DOO-1-03 | 110kV FEEDER - CAHIR 110-DOON 110-1 | 1 | 1 | 1 | Scheduled | 28/02/2024 | 28/02/2024
TO-24-BDN-DOO-1-01 | 110kV FEEDER - BALLYDINE 110-DOON 110-1 | 9 | 7 | 7 | Scheduled | 05/03/2024 | 13/03/2024
TO-24-ARK-BEG-1-01 | 110kV FEEDER - ARKLOW 110-BALLYBEG 110-1 | 12 | 9 |  | Scheduled | 11/03/2024 | 22/03/2024
TO-24-110 kV A1/A2 @ CAH-01 | BUSBAR SECTION - CAHIR 110-CAHIR 110-110A1-A2 | 10 | 8 | 8 | Scheduled | 19/03/2024 | 28/03/2024
TO-24-110 kV B1/B2 @ CAH-01 | BUSBAR SECTION - CAHIR 110-CAHIR 110-110B1-B2 | 10 | 8 | 8 | Scheduled | 19/03/2024 | 28/03/2024
TO-24-CAH-110K1-2-01 | COUPLER/SECTIONALISING CB - CAHIR 110-CAHIR 110-110K1-2 | 10 | 8 | 8 | Scheduled | 19/03/2024 | 28/03/2024
TO-24-CAH-T141-01 | DISTRIBUTION TRANSFORMER - CAHIR 110-CAHIR 38-T141 | 7 | 5 | 5 | Reference | 19/03/2024 | 25/03/2024
TO-24-GI-WAT-2-01 | 110kV FEEDER - GREAT ISLAND 110-WATERFORD 110-2 | 4 | 4 | 4 | Scheduled | 19/03/2024 | 22/03/2024
TO-24-CAH-T142-01 | DISTRIBUTION TRANSFORMER - CAHIR 110-CAHIR 38-T142 | 4 | 4 | 4 | Reference | 25/03/2024 | 28/03/2024
TO-24-DAL,T-SH-1-02 | 110kV FEEDER - DALLOW tee-SHANNONBRIDGE 110-1 | 77 | 51 | 51 | Scheduled | 26/03/2024 | 10/06/2024
TO-24-GI-T141-01 | DISTRIBUTION TRANSFORMER - GREAT ISLAND 110-GREAT ISLAND 38-T141 | 232 | 162 | 162 | Reference | 02/04/2024 | 19/11/2024
TO-24-220 kV A2 @ CUL-02 | BUSBAR SECTION - CULLENAGH 220-CULLENAGH 220-220A2 | 43 | 30 | 30 | Scheduled | 04/04/2024 | 16/05/2024
TO-24-220 kV B2 @ CUL-02 | BUSBAR SECTION - CULLENAGH 220-CULLENAGH 220-220B2 | 43 | 30 | 30 | Scheduled | 04/04/2024 | 16/05/2024
TO-24-CUL-KRA-1-01 | 220kV FEEDER - CULLENAGH 220-KNOCKRAHA 220-1 | 55 | 38 | 38 | Scheduled | 04/04/2024 | 28/05/2024
TO-24-GI-KKY-1-01 | 110kV FEEDER - GREAT ISLAND 110-KILKENNY 110-1 | 9 | 7 | 7 | Scheduled | 04/04/2024 | 12/04/2024
TO-24-GI-WAT-1-01 | 110kV FEEDER - GREAT ISLAND 110-WATERFORD 110-1 | 2 | 2 | 2 | Scheduled | 04/04/2024 | 05/04/2024
TO-24-BGT-110K1-01 | COUPLER/SECTIONALISING CB - BALLYRAGGET 110-BALLYRAGGET 110-110K1 | 3 | 3 | 3 | Scheduled | 15/04/2024 | 17/04/2024
TO-24-BGT-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - BALLYRAGGET 110-BALLYRAGGET 110-110SA1-2CB | 3 | 3 | 3 | Scheduled | 15/04/2024 | 17/04/2024
TO-24-BGT-110SB1-2CB-01 | COUPLER/SECTIONALISING CB - BALLYRAGGET 110-BALLYRAGGET 110-110SB1-2CB | 3 | 3 | 3 | Scheduled | 15/04/2024 | 17/04/2024
TO-24-BGT-KKY-1-01 | 110kV FEEDER - BALLYRAGGET 110-KILKENNY 110-1 | 3 | 3 | 3 | Scheduled | 15/04/2024 | 17/04/2024
TO-24-BGT-141-01 | DISTRIBUTION TRANSFORMER - BALLYRAGGET 110-BALLYRAGGET 38-T141 | 3 | 3 | 3 | Reference | 15/04/2024 | 17/04/2024
TO-24-KTN-WAT-1-01 | 110kV FEEDER - KILLOTERAN 110-WATERFORD 110-1 | 5 | 5 | 5 | Scheduled | 22/04/2024 | 26/04/2024
TO-24-ARK-T2102-01 | TRANSFORMER - ARKLOW 220-ARKLOW 110-T2102 | 5 | 5 | 5 | Scheduled | 29/04/2024 | 03/05/2024
TO-24-BUT-CUL-1-01 | 110kV FEEDER - BUTLERSTOWN 110-CULLENAGH 110-1 | 3 | 3 | 3 | Scheduled | 07/05/2024 | 09/05/2024
TO-24-ROP-110K1-01 | COUPLER/SECTIONALISING CB - ROSSPILE 110-ROSSPILE 110-110K1 | 1 | 1 | 1 | Scheduled | 08/05/2024 | 08/05/2024
TO-24-ARK-T101-01 | DISTRIBUTION TRANSFORMER - ARKLOW 110-ARKLOW 10-T101 | 2 | 2 | 2 | Reference | 09/05/2024 | 10/05/2024
TO-24-WOH-T122-01 | GENERATOR TRANSFORMER - WOODHOUSE 110-WOODHOUSE 20-T122 | 2 | 2 | 2 | Scheduled | 09/05/2024 | 10/05/2024
TO-24-GI-WAT-1-04 | 110kV FEEDER - GREAT ISLAND 110-WATERFORD 110-1 | 5 | 5 | 5 | Scheduled | 13/05/2024 | 17/05/2024
TO-24-KLS-220K1-2-01 | COUPLER/SECTIONALISING CB - KELLIS 220-KELLIS 220-220K1-2 | 57 | 40 | 40 | Scheduled | 13/05/2024 | 08/07/2024
TO-24-CRA-LWD-1-06 | 110kV FEEDER - CRANE 110-LODGEWOOD 110-1 | 4 | 4 | 4 | Scheduled | 14/05/2024 | 17/05/2024
TO-24-220 kV A2 @ GI GIS-01 | BUSBAR SECTION - GREAT ISLAND GIS 220-GREAT ISLAND GIS 220-220A2 | 3 | 3 | 3 | Scheduled | 21/05/2024 | 23/05/2024
TO-24-GI GIS-220K2-01 | COUPLER/SECTIONALISING CB - GREAT ISLAND GIS 220-GREAT ISLAND GIS 220-220K2 | 3 | 3 | 3 | Scheduled | 21/05/2024 | 23/05/2024
TO-24-GI GIS-220SA1-2CB-04 | COUPLER/SECTIONALISING CB - GREAT ISLAND GIS 220-GREAT ISLAND GIS 220-220SA1-2CB | 3 | 3 | 3 | Scheduled | 21/05/2024 | 23/05/2024
TO-24-GI GIS-T2004-02 | GENERATOR TRANSFORMER - GREAT ISLAND GIS 220-GREAT ISLAND GIS G4-T2004 | 11 | 9 | 9 | Scheduled | 21/05/2024 | 31/05/2024
TO-24-BOG-TTU-1-01 | 110kV FEEDER - BANOGE 110-TULLABEG 110-1 | 3 | 3 | 3 | Scheduled | 27/05/2024 | 29/05/2024
TO-24-110 kV A2 @ CAH-03 | BUSBAR SECTION - CAHIR 110-CAHIR 110-110A2 | 12 | 9 | 9 | Scheduled | 27/05/2024 | 07/06/2024
TO-24-110 kV B2 @ CAH-03 | BUSBAR SECTION - CAHIR 110-CAHIR 110-110B2 | 12 | 9 | 9 | Scheduled | 27/05/2024 | 07/06/2024
TO-24-CAH-DOO-1-01 | 110kV FEEDER - CAHIR 110-DOON 110-1 | 12 | 9 | 9 | Scheduled | 27/05/2024 | 07/06/2024
TO-24-DSN-KLS-1-03 | 220kV FEEDER - DUNSTOWN 220-KELLIS 220-1 | 7 | 4 | 4 | Scheduled | 29/05/2024 | 04/06/2024
TO-24-KLS-T2101-05 | TRANSFORMER - KELLIS 220-KELLIS 110-T2101 | 7 | 4 | 4 | Scheduled | 29/05/2024 | 04/06/2024
TO-24-BDA-T102-01 | TSO CUSTOMER TRANSFORMER - BARODA 110-BARODA 10-T102 | 3 | 3 | 3 | Scheduled | 05/06/2024 | 07/06/2024
TO-24-DAL,T-DAL-1-02 | 110kV FEEDER - DALLOW tee-DALLOW 110-1 | 6 | 4 | 4 | Scheduled | 05/06/2024 | 10/06/2024
TO-24-DAL,T-DEY-1-03 | 110kV FEEDER - DALLOW tee-DERRYCARNEY 110-1 | 92 | 65 |  | Scheduled | 05/06/2024 | 04/09/2024
TO-24-DEY-110K2-01 | COUPLER/SECTIONALISING CB - DERRYCARNEY 110-DERRYCARNEY 110-110K2 | 1 | 1 | 1 | Scheduled | 05/06/2024 | 05/06/2024
TO-24-220 kV A1 @ GI GIS-03 | BUSBAR SECTION - GREAT ISLAND GIS 220-GREAT ISLAND GIS 220-220A1 | 13 | 9 | 9 | Scheduled | 05/06/2024 | 17/06/2024
TO-24-220 kV B1 @ GI GIS-02 | BUSBAR SECTION - GREAT ISLAND GIS 220-GREAT ISLAND GIS 220-220B1 | 13 | 9 | 9 | Scheduled | 05/06/2024 | 17/06/2024
TO-24-GI GIS-KLS-1-01 | 220kV FEEDER - GREAT ISLAND GIS 220-KELLIS 220-1 | 13 | 9 | 9 | Scheduled | 05/06/2024 | 17/06/2024
TO-24-KLS-T2102-01 | TRANSFORMER - KELLIS 220-KELLIS 110-T2102 | 7 | 5 | 5 | Scheduled | 05/06/2024 | 11/06/2024
TO-24-CRA-LWD-1-01 | 110kV FEEDER - CRANE 110-LODGEWOOD 110-1 | 5 | 5 | 5 | Scheduled | 10/06/2024 | 14/06/2024
TO-24-CRY-LWD-1-01 | 110kV FEEDER - CRORY 110-LODGEWOOD 110-1 | 5 | 5 | 5 | Reference | 10/06/2024 | 14/06/2024
TO-24-CRY-T121-01 | DISTRIBUTION TRANSFORMER - CRORY 110-CRORY 20-T121 | 5 | 5 | 5 | Reference | 10/06/2024 | 14/06/2024
TO-24-LWD-110SA1-01 | SECTIONALISING DISCONNECT - LODGEWOOD 110-LODGEWOOD 110-110SA1 | 5 | 5 | 5 | Scheduled | 10/06/2024 | 14/06/2024
TO-24-LWD-110SA2-01 | SECTIONALISING DISCONNECT - LODGEWOOD 110-LODGEWOOD 110-110SA2 | 5 | 5 | 5 | Scheduled | 10/06/2024 | 14/06/2024
TO-24-110 kV A1 @ CAH-02 | BUSBAR SECTION - CAHIR 110-CAHIR 110-110A1 | 2 | 2 | 2 | Scheduled | 12/06/2024 | 13/06/2024
TO-24-CAH-KHL-1-01 | 110kV FEEDER - CAHIR 110-KILL HILL 110-1 | 2 | 2 | 2 | Scheduled | 12/06/2024 | 13/06/2024
TO-24-110 kV A1 @ CAH-04 | BUSBAR SECTION - CAHIR 110-CAHIR 110-110A1 | 9 | 7 | 7 | Scheduled | 17/06/2024 | 25/06/2024
TO-24-110 kV B1 @ CAH-03 | BUSBAR SECTION - CAHIR 110-CAHIR 110-110B1 | 9 | 7 | 7 | Scheduled | 17/06/2024 | 25/06/2024
TO-24-CAH-CAP1/3-01 | CAPACITOR/SVC/REACTOR - CAHIR 110-CAHIR 110-CAP1/3 | 9 | 7 | 7 | Scheduled | 17/06/2024 | 25/06/2024
TO-24-CDK-LWD-1-01 | 110kV FEEDER - CASTLEDOCKRELL 110-LODGEWOOD 110-1 | 5 | 5 | 5 | Scheduled | 17/06/2024 | 21/06/2024
TO-24-CDK-T121-01 | GENERATOR TRANSFORMER - CASTLEDOCKRELL 110-CASTLEDOCKRELL 20-T121 | 5 | 5 | 5 | Reference | 17/06/2024 | 21/06/2024
TO-24-KKY-CAP2-01 | CAPACITOR/SVC/REACTOR - KILKENNY 110-KILKENNY 110-CAP2 | 5 | 5 | 5 | Scheduled | 17/06/2024 | 21/06/2024
TO-24-KRA-WOH-1-02 | 110kV FEEDER - KNOCKRAHA 110-WOODHOUSE 110-1 | 12 | 10 | 10 | Scheduled | 17/06/2024 | 28/06/2024
TO-24-LWD-110SA1-02 | SECTIONALISING DISCONNECT - LODGEWOOD 110-LODGEWOOD 110-110SA1 | 5 | 5 | 5 | Scheduled | 17/06/2024 | 21/06/2024
TO-24-LWD-110SA2-02 | SECTIONALISING DISCONNECT - LODGEWOOD 110-LODGEWOOD 110-110SA2 | 5 | 5 | 5 | Scheduled | 17/06/2024 | 21/06/2024
TO-24-LWD-T2102-01 | TRANSFORMER - LODGEWOOD 220-LODGEWOOD 110-T2102 | 5 | 5 | 5 | Scheduled | 17/06/2024 | 21/06/2024
TO-24-CUS-KIR-1-02 | 110kV FEEDER - CUSHALING 110-KILCUMBER 110-1 | 24 | 18 | 18 | Scheduled | 24/06/2024 | 17/07/2024
TO-24-GI-KKY-1-03 | 110kV FEEDER - GREAT ISLAND 110-KILKENNY 110-1 | 8 | 6 |  | Scheduled | 24/06/2024 | 01/07/2024
TO-24-KIR-T131-02 | GENERATOR TRANSFORMER - KILCUMBER 110-KILCUMBER 33-T131 | 24 | 18 | 18 | Scheduled | 24/06/2024 | 17/07/2024
TO-24-KKY-110SA1-2CB-02 | COUPLER/SECTIONALISING CB - KILKENNY 110-KILKENNY 110-110SA1-2CB | 8 | 6 |  | Scheduled | 24/06/2024 | 01/07/2024
TO-24-KKY-CAP2-02 | CAPACITOR/SVC/REACTOR - KILKENNY 110-KILKENNY 110-CAP2 | 8 | 6 |  | Scheduled | 24/06/2024 | 01/07/2024
TO-24-KKY-T142-01 | DISTRIBUTION TRANSFORMER - KILKENNY 110-KILKENNY 38-T142 | 8 | 6 |  | Reference | 24/06/2024 | 01/07/2024
TO-24-110 kV A1 @ KLS-02 | BUSBAR SECTION - KELLIS 110-KELLIS 110-110A1 | 1 | 1 | 1 | Scheduled | 25/06/2024 | 25/06/2024
TO-24-110 kV A2 @ KLS-05 | BUSBAR SECTION - KELLIS 110-KELLIS 110-110A2 | 1 | 1 | 1 | Scheduled | 25/06/2024 | 25/06/2024
TO-24-110 kV B1 @ KLS-02 | BUSBAR SECTION - KELLIS 110-KELLIS 110-110B1 | 1 | 1 | 1 | Scheduled | 25/06/2024 | 25/06/2024
TO-24-110 kV B2 @ KLS-04 | BUSBAR SECTION - KELLIS 110-KELLIS 110-110B2 | 1 | 1 | 1 | Scheduled | 25/06/2024 | 25/06/2024
TO-24-DGN-WOH-1-02 | 110kV FEEDER - DUNGARVAN 110-WOODHOUSE 110-1 | 5 | 5 | 5 | Scheduled | 01/07/2024 | 05/07/2024
TO-24-KLS-KKY-1-03 | 110kV FEEDER - KELLIS 110-KILKENNY 110-1 | 10 | 8 | 8 | Scheduled | 02/07/2024 | 11/07/2024
TO-24-ARK-LWD-1-02 | 220kV FEEDER - ARKLOW 220-LODGEWOOD 220-1 | 10 | 8 | 8 | Scheduled | 08/07/2024 | 17/07/2024
TO-24-CRA-LWD-1-02 | 110kV FEEDER - CRANE 110-LODGEWOOD 110-1 | 5 | 5 | 5 | Scheduled | 08/07/2024 | 12/07/2024
TO-24-CRY-LWD-1-02 | 110kV FEEDER - CRORY 110-LODGEWOOD 110-1 | 5 | 5 | 5 | Reference | 08/07/2024 | 12/07/2024
TO-24-CRY-T121-02 | DISTRIBUTION TRANSFORMER - CRORY 110-CRORY 20-T121 | 5 | 5 | 5 | Reference | 08/07/2024 | 12/07/2024
TO-24-CUL-DGN-1-03 | 110kV FEEDER - CULLENAGH 110-DUNGARVAN 110-1 | 128 | 90 | 90 | Scheduled | 08/07/2024 | 12/11/2024
TO-24-LWD-110SA1-03 | SECTIONALISING DISCONNECT - LODGEWOOD 110-LODGEWOOD 110-110SA1 | 5 | 5 | 5 | Scheduled | 08/07/2024 | 12/07/2024
TO-24-LWD-110SA2-03 | SECTIONALISING DISCONNECT - LODGEWOOD 110-LODGEWOOD 110-110SA2 | 5 | 5 | 5 | Scheduled | 08/07/2024 | 12/07/2024
TO-24-110 kV A1 @ CAH-03 | BUSBAR SECTION - CAHIR 110-CAHIR 110-110A1 | 5 | 5 | 5 | Scheduled | 15/07/2024 | 19/07/2024
TO-24-110 kV B1 @ CAH-02 | BUSBAR SECTION - CAHIR 110-CAHIR 110-110B1 | 5 | 5 | 5 | Scheduled | 15/07/2024 | 19/07/2024
TO-24-CAH-TIP-1-03 | 110kV FEEDER - CAHIR 110-TIPPERARY 110-1 | 5 | 5 | 5 | Scheduled | 15/07/2024 | 19/07/2024
TO-24-CDK-LWD-1-02 | 110kV FEEDER - CASTLEDOCKRELL 110-LODGEWOOD 110-1 | 9 | 7 | 7 | Scheduled | 15/07/2024 | 23/07/2024
TO-24-CDK-T121-02 | GENERATOR TRANSFORMER - CASTLEDOCKRELL 110-CASTLEDOCKRELL 20-T121 | 9 | 7 | 7 | Reference | 15/07/2024 | 23/07/2024
TO-24-LWD-110SA1-04 | SECTIONALISING DISCONNECT - LODGEWOOD 110-LODGEWOOD 110-110SA1 | 9 | 7 | 7 | Scheduled | 15/07/2024 | 23/07/2024
TO-24-LWD-110SA2-04 | SECTIONALISING DISCONNECT - LODGEWOOD 110-LODGEWOOD 110-110SA2 | 9 | 7 | 7 | Scheduled | 15/07/2024 | 23/07/2024
TO-24-LWD-T2102-02 | TRANSFORMER - LODGEWOOD 220-LODGEWOOD 110-T2102 | 9 | 7 | 7 | Scheduled | 15/07/2024 | 23/07/2024
TO-24-CRA-LWD-1-03 | 110kV FEEDER - CRANE 110-LODGEWOOD 110-1 | 7 | 5 | 5 | Scheduled | 24/07/2024 | 30/07/2024
TO-24-CRY-LWD-1-03 | 110kV FEEDER - CRORY 110-LODGEWOOD 110-1 | 7 | 5 | 5 | Reference | 24/07/2024 | 30/07/2024
TO-24-CRY-T121-03 | DISTRIBUTION TRANSFORMER - CRORY 110-CRORY 20-T121 | 7 | 5 | 5 | Reference | 24/07/2024 | 30/07/2024
TO-24-LWD-110SA1-05 | SECTIONALISING DISCONNECT - LODGEWOOD 110-LODGEWOOD 110-110SA1 | 7 | 5 | 5 | Scheduled | 24/07/2024 | 30/07/2024
TO-24-LWD-110SA2-05 | SECTIONALISING DISCONNECT - LODGEWOOD 110-LODGEWOOD 110-110SA2 | 7 | 5 | 5 | Scheduled | 24/07/2024 | 30/07/2024
TO-24-CDK-LWD-1-03 | 110kV FEEDER - CASTLEDOCKRELL 110-LODGEWOOD 110-1 | 8 | 5 | 5 | Scheduled | 31/07/2024 | 07/08/2024
TO-24-CDK-T121-03 | GENERATOR TRANSFORMER - CASTLEDOCKRELL 110-CASTLEDOCKRELL 20-T121 | 8 | 5 | 5 | Reference | 31/07/2024 | 07/08/2024
TO-24-LWD-110SA1-06 | SECTIONALISING DISCONNECT - LODGEWOOD 110-LODGEWOOD 110-110SA1 | 8 | 5 | 5 | Scheduled | 31/07/2024 | 07/08/2024
TO-24-LWD-110SA2-06 | SECTIONALISING DISCONNECT - LODGEWOOD 110-LODGEWOOD 110-110SA2 | 8 | 5 | 5 | Scheduled | 31/07/2024 | 07/08/2024
TO-24-LWD-T2102-03 | TRANSFORMER - LODGEWOOD 220-LODGEWOOD 110-T2102 | 8 | 5 | 5 | Scheduled | 31/07/2024 | 07/08/2024
TO-24-CUS-T101-01 | GENERATOR TRANSFORMER - CUSHALING 110-CUSHALING G1-T101 | 17 | 13 | 13 | Scheduled | 06/08/2024 | 22/08/2024
TO-24-110 kV A2 @ DEY-01 | BUSBAR SECTION - DERRYCARNEY 110-DERRYCARNEY 110-110A2 | 17 | 13 | 13 | Scheduled | 07/08/2024 | 23/08/2024
TO-24-110 kV B2 @ DEY-01 | BUSBAR SECTION - DERRYCARNEY 110-DERRYCARNEY 110-110B2 | 17 | 13 | 13 | Scheduled | 07/08/2024 | 23/08/2024
TO-24-DEY-110K2-03 | COUPLER/SECTIONALISING CB - DERRYCARNEY 110-DERRYCARNEY 110-110K2 | 17 | 13 | 13 | Scheduled | 07/08/2024 | 23/08/2024
TO-24-CRA-LWD-1-04 | 110kV FEEDER - CRANE 110-LODGEWOOD 110-1 | 5 | 5 | 5 | Scheduled | 12/08/2024 | 16/08/2024
TO-24-CRY-LWD-1-04 | 110kV FEEDER - CRORY 110-LODGEWOOD 110-1 | 5 | 5 | 5 | Reference | 12/08/2024 | 16/08/2024
TO-24-CRY-T121-04 | DISTRIBUTION TRANSFORMER - CRORY 110-CRORY 20-T121 | 5 | 5 | 5 | Reference | 12/08/2024 | 16/08/2024
TO-24-LWD-110SA1-07 | SECTIONALISING DISCONNECT - LODGEWOOD 110-LODGEWOOD 110-110SA1 | 5 | 5 | 5 | Scheduled | 12/08/2024 | 16/08/2024
TO-24-LWD-110SA2-07 | SECTIONALISING DISCONNECT - LODGEWOOD 110-LODGEWOOD 110-110SA2 | 5 | 5 |  | Scheduled | 12/08/2024 | 16/08/2024
TO-24-CDK-LWD-1-04 | 110kV FEEDER - CASTLEDOCKRELL 110-LODGEWOOD 110-1 | 19 | 15 |  | Scheduled | 19/08/2024 | 06/09/2024
TO-24-CDK-T121-04 | GENERATOR TRANSFORMER - CASTLEDOCKRELL 110-CASTLEDOCKRELL 20-T121 | 19 | 15 |  | Reference | 19/08/2024 | 06/09/2024
TO-24-LWD-110SA1-08 | SECTIONALISING DISCONNECT - LODGEWOOD 110-LODGEWOOD 110-110SA1 | 19 | 15 |  | Scheduled | 19/08/2024 | 06/09/2024
TO-24-LWD-110SA2-08 | SECTIONALISING DISCONNECT - LODGEWOOD 110-LODGEWOOD 110-110SA2 | 19 | 15 |  | Scheduled | 19/08/2024 | 06/09/2024
TO-24-LWD-T2102-06 | TRANSFORMER - LODGEWOOD 220-LODGEWOOD 110-T2102 | 19 | 15 |  | Scheduled | 19/08/2024 | 06/09/2024
TO-24-DAL,T-DAL-1-08 | 110kV FEEDER - DALLOW tee-DALLOW 110-1 | 16 | 12 | 12 | Scheduled | 20/08/2024 | 04/09/2024
TO-24-DAL,T-SH-1-10 | 110kV FEEDER - DALLOW tee-SHANNONBRIDGE 110-1 | 16 | 12 | 12 | Scheduled | 20/08/2024 | 04/09/2024
TO-24-ROP-T131-02 | GENERATOR TRANSFORMER - ROSSPILE 110-ROSSPILE 33-T131 | 1 | 1 | 1 | Scheduled | 26/08/2024 | 26/08/2024
TO-24-BDA-T101-01 | TSO CUSTOMER TRANSFORMER - BARODA 110-BARODA 10-T101 | 9 | 7 | 7 | Scheduled | 02/09/2024 | 10/09/2024
TO-24-CRA-LWD-1-09 | 110kV FEEDER - CRANE 110-LODGEWOOD 110-1 | 4 | 4 | 4 | Scheduled | 09/09/2024 | 12/09/2024
TO-24-CRY-LWD-1-05 | 110kV FEEDER - CRORY 110-LODGEWOOD 110-1 | 4 | 4 | 4 | Reference | 09/09/2024 | 12/09/2024
TO-24-CRY-T121-05 | DISTRIBUTION TRANSFORMER - CRORY 110-CRORY 20-T121 | 4 | 4 | 4 | Reference | 09/09/2024 | 12/09/2024
TO-24-110 kV A1 @ GI-02 | BUSBAR SECTION - GREAT ISLAND 110-GREAT ISLAND 110-110A1 | 5 | 5 | 5 | Scheduled | 09/09/2024 | 13/09/2024
TO-24-110 kV A2 @ GI-01 | BUSBAR SECTION - GREAT ISLAND 110-GREAT ISLAND 110-110A2 | 5 | 5 | 5 | Scheduled | 09/09/2024 | 13/09/2024
TO-24-110 kV B1 @ GI-02 | BUSBAR SECTION - GREAT ISLAND 110-GREAT ISLAND 110-110B1 | 5 | 5 | 5 | Scheduled | 09/09/2024 | 13/09/2024
TO-24-110 kV B2 @ GI-01 | BUSBAR SECTION - GREAT ISLAND 110-GREAT ISLAND 110-110B2 | 5 | 5 | 5 | Scheduled | 09/09/2024 | 13/09/2024
TO-24-GI-110K1-2-01 | COUPLER/SECTIONALISING CB - GREAT ISLAND 110-GREAT ISLAND 110-110K1-2 | 5 | 5 |  | Scheduled | 09/09/2024 | 13/09/2024
TO-24-LWD-110SA1-09 | SECTIONALISING DISCONNECT - LODGEWOOD 110-LODGEWOOD 110-110SA1 | 4 | 4 | 4 | Scheduled | 09/09/2024 | 12/09/2024
TO-24-LWD-110SA2-09 | SECTIONALISING DISCONNECT - LODGEWOOD 110-LODGEWOOD 110-110SA2 | 4 | 4 | 4 | Scheduled | 09/09/2024 | 12/09/2024
TO-24-CLW-KLS-2-06 | 110kV FEEDER - CARLOW 110-KELLIS 110-2 | 5 | 5 | 5 | Scheduled | 16/09/2024 | 20/09/2024
TO-24-CRA-WEX-1-01 | 110kV FEEDER - CRANE 110-WEXFORD 110-1 | 71 | 50 | 50 | Scheduled | 16/09/2024 | 25/11/2024
TO-24-220 kV B1 @ GI GIS-03 | BUSBAR SECTION - GREAT ISLAND GIS 220-GREAT ISLAND GIS 220-220B1 | 10 | 8 | 8 | Scheduled | 16/09/2024 | 25/09/2024
TO-24-220 kV B2 @ GI GIS-01 | BUSBAR SECTION - GREAT ISLAND GIS 220-GREAT ISLAND GIS 220-220B2 | 10 | 8 | 8 | Scheduled | 16/09/2024 | 25/09/2024
TO-24-GI GIS-220K1-05 | COUPLER/SECTIONALISING CB - GREAT ISLAND GIS 220-GREAT ISLAND GIS 220-220K1 | 10 | 8 | 8 | Scheduled | 16/09/2024 | 25/09/2024
TO-24-GI GIS-220K2-05 | COUPLER/SECTIONALISING CB - GREAT ISLAND GIS 220-GREAT ISLAND GIS 220-220K2 | 10 | 8 | 8 | Scheduled | 16/09/2024 | 25/09/2024
TO-24-GI GIS-220SB1-2CB-02 | COUPLER/SECTIONALISING CB - GREAT ISLAND GIS 220-GREAT ISLAND GIS 220-220SB1-2CB | 10 | 8 | 8 | Scheduled | 16/09/2024 | 25/09/2024
TO-24-110 kV A2 @ KLS-06 | BUSBAR SECTION - KELLIS 110-KELLIS 110-110A2 | 12 | 10 | 10 | Scheduled | 16/09/2024 | 27/09/2024
TO-24-110 kV B2 @ KLS-05 | BUSBAR SECTION - KELLIS 110-KELLIS 110-110B2 | 12 | 10 | 10 | Scheduled | 16/09/2024 | 27/09/2024
TO-24-BDN-MRK1-01 | TSO CUSTOMER TRANSFORMER - BALLYDINE 110-BALLYDINE 10-MRK1 | 14 | 10 | 10 | Scheduled | 19/09/2024 | 02/10/2024
TO-24-ROP-T131-03 | GENERATOR TRANSFORMER - ROSSPILE 110-ROSSPILE 33-T131 | 1 | 1 | 1 | Scheduled | 23/09/2024 | 23/09/2024
TO-24-110 kV A1 @ CUL-02 | BUSBAR SECTION - CULLENAGH 110-CULLENAGH 110-110A1 | 1 | 1 | 1 | Scheduled | 24/09/2024 | 24/09/2024
TO-24-110 kV B1 @ CUL-03 | BUSBAR SECTION - CULLENAGH 110-CULLENAGH 110-110B1 | 1 | 1 | 1 | Scheduled | 24/09/2024 | 24/09/2024
TO-24-CAH-TIP-1-01 | 110kV FEEDER - CAHIR 110-TIPPERARY 110-1 | 57 | 40 | 40 | Scheduled | 25/09/2024 | 20/11/2024
TO-24-CUL-110K1-2-01 | COUPLER/SECTIONALISING CB - CULLENAGH 110-CULLENAGH 110-110K1-2 | 57 | 40 | 40 | Scheduled | 25/09/2024 | 20/11/2024
TO-24-CUL-220K1-2-02 | COUPLER/SECTIONALISING CB - CULLENAGH 220-CULLENAGH 220-220K1-2 | 57 | 40 | 40 | Scheduled | 25/09/2024 | 20/11/2024
TO-24-ROP-T131-04 | GENERATOR TRANSFORMER - ROSSPILE 110-ROSSPILE 33-T131 | 1 | 1 | 1 | Scheduled | 30/09/2024 | 30/09/2024
TO-24-BOG-T122-01 | DISTRIBUTION TRANSFORMER - BANOGE 110-BANOGE 20-T122 | 2 | 2 | 2 | Reference | 01/10/2024 | 02/10/2024
TO-24-DGN-110SA1-01 | SECTIONALISING DISCONNECT - DUNGARVAN 110-DUNGARVAN 110-110SA1 | 1 | 1 | 1 | Scheduled | 02/10/2024 | 02/10/2024
TO-24-DGN-110SA2-03 | SECTIONALISING DISCONNECT - DUNGARVAN 110-DUNGARVAN 110-110SA2 | 1 | 1 | 1 | Scheduled | 02/10/2024 | 02/10/2024
TO-24-DGN-T142-01 | DISTRIBUTION TRANSFORMER - DUNGARVAN 110-DUNGARVAN 38-T142 | 1 | 1 | 1 | Reference | 02/10/2024 | 02/10/2024
TO-24-CUS-NEW-1-01 | 110kV FEEDER - CUSHALING 110-NEWBRIDGE 110-1 | 5 | 5 | 5 | Scheduled | 07/10/2024 | 11/10/2024
TO-24-GI-KKY-1-02 | 110kV FEEDER - GREAT ISLAND 110-KILKENNY 110-1 | 5 | 5 |  | Scheduled | 07/10/2024 | 11/10/2024
TO-24-GI-WAT-1-05 | 110kV FEEDER - GREAT ISLAND 110-WATERFORD 110-1 | 5 | 5 |  | Scheduled | 07/10/2024 | 11/10/2024
TO-24-NEW-PLS-1-03 | 110kV FEEDER - NEWBRIDGE 110-PORTLAOISE 110-1 | 12 | 10 | 10 | Scheduled | 14/10/2024 | 25/10/2024
TO-24-110 kV A1 @ PLS-02 | BUSBAR SECTION - PORTLAOISE 110-PORTLAOISE 110-110A1 | 12 | 10 | 10 | Scheduled | 14/10/2024 | 25/10/2024
TO-24-110 kV B1 @ PLS-01 | BUSBAR SECTION - PORTLAOISE 110-PORTLAOISE 110-110B1 | 12 | 10 | 10 | Scheduled | 14/10/2024 | 25/10/2024
TO-24-PLS-T142-01 | DISTRIBUTION TRANSFORMER - PORTLAOISE 110-PORTLAOISE 38-T142 | 2 | 2 | 2 | Reference | 22/10/2024 | 23/10/2024
TO-24-PLS-T141-01 | DISTRIBUTION TRANSFORMER - PORTLAOISE 110-PORTLAOISE 38-T141 | 2 | 2 | 2 | Reference | 24/10/2024 | 25/10/2024
TO-24-CUS-T103/5-02 | GENERATOR TRANSFORMER - CUSHALING 110-CUSHALING G3/5-T103/5 | 1 | 1 | 1 | Scheduled | 06/11/2024 | 06/11/2024
TO-24-DGN-WOH-1-04 | 110kV FEEDER - DUNGARVAN 110-WOODHOUSE 110-1 | 1 | 1 | 1 | Trip Testing | 12/11/2024 | 12/11/2024
TO-24-KRA-WOH-1-04 | 110kV FEEDER - KNOCKRAHA 110-WOODHOUSE 110-1 | 1 | 1 | 1 | Trip Testing | 12/11/2024 | 12/11/2024
TO-24-KKY-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - KILKENNY 110-KILKENNY 110-110SA1-2CB | 1 | 1 | 1 | Proposed | 13/11/2024 | 13/11/2024
TO-24-KKY-T141-01 | DISTRIBUTION TRANSFORMER - KILKENNY 110-KILKENNY 38-T141 | 1 | 1 | 1 | Reference (Proposed) | 13/11/2024 | 13/11/2024
TO-24-ATY-110SA1-01 | SECTIONALISING DISCONNECT - ATHY 110-ATHY 110-110SA1 | 5 | 5 | 5 | Proposed | 18/11/2024 | 22/11/2024
TO-24-ATY-110SA2-04 | SECTIONALISING DISCONNECT - ATHY 110-ATHY 110-110SA2 | 5 | 5 | 5 | Proposed | 18/11/2024 | 22/11/2024
TO-24-ATY-CLW-1-08 | 110kV FEEDER - ATHY 110-CARLOW 110-1 | 5 | 5 | 5 | Proposed | 18/11/2024 | 22/11/2024
TO-24-ATY-T101-02 | DISTRIBUTION TRANSFORMER - ATHY 110-ATHY 10-T101 | 5 | 5 | 5 | Reference (Proposed) | 18/11/2024 | 22/11/2024
TO-24-110 kV A1 @ GI-01 | BUSBAR SECTION - GREAT ISLAND 110-GREAT ISLAND 110-110A1 | 2 | 2 |  | Scheduled | 18/11/2024 | 19/11/2024
TO-24-110 kV B1 @ GI-01 | BUSBAR SECTION - GREAT ISLAND 110-GREAT ISLAND 110-110B1 | 2 | 2 |  | Scheduled | 18/11/2024 | 19/11/2024
TO-24-GI-WAT-1-02 | 110kV FEEDER - GREAT ISLAND 110-WATERFORD 110-1 | 2 | 2 |  | Scheduled | 18/11/2024 | 19/11/2024
TO-24-BDN-110SA1-02 | SECTIONALISING DISCONNECT - BALLYDINE 110-BALLYDINE 110-110SA1 | 4 | 4 | 4 | Scheduled | 26/11/2024 | 29/11/2024
TO-24-BDN-110SA2-01 | SECTIONALISING DISCONNECT - BALLYDINE 110-BALLYDINE 110-110SA2 | 4 | 4 | 4 | Scheduled | 26/11/2024 | 29/11/2024
TO-24-BDN-DOO-1-02 | 110kV FEEDER - BALLYDINE 110-DOON 110-1 | 4 | 4 | 4 | Scheduled | 26/11/2024 | 29/11/2024
TO-24-BDN-MRK3-02 | TSO CUSTOMER TRANSFORMER - BALLYDINE 110-BALLYDINE 10-MRK3 | 4 | 4 | 4 | Scheduled | 26/11/2024 | 29/11/2024
TO-24-ROP-WEX-1-02 | 110kV FEEDER - ROSSPILE 110-WEXFORD 110-1 | 4 | 4 | 4 | Proposed | 26/11/2024 | 29/11/2024
TO-24-ROP-T131-01 | GENERATOR TRANSFORMER - ROSSPILE 110-ROSSPILE 33-T131 | 1 | 1 | 1 | Proposed | 29/11/2024 | 29/11/2024

## GEN_NorthWest
Outage ID | Feeder ID | Calendar Day Duration | Working Day Duration | Work Days | Outage Status | Start | Finish
TO-24-220 kV A2 @ CSH-01 | BUSBAR SECTION - CASHLA 220-CASHLA 220-220A2 | 5 | 5 | 5 | Scheduled | 08/01/2024 | 12/01/2024
TO-24-220 kV A4 @ CSH-02 | BUSBAR SECTION - CASHLA 220-CASHLA 220-220A4 | 5 | 5 | 5 | Scheduled | 08/01/2024 | 12/01/2024
TO-24-220 kV B2 @ CSH-03 | BUSBAR SECTION - CASHLA 220-CASHLA 220-220B2 | 5 | 5 | 5 | Scheduled | 08/01/2024 | 12/01/2024
TO-24-220 kV B4 @ CSH-01 | BUSBAR SECTION - CASHLA 220-CASHLA 220-220B4 | 5 | 5 | 5 | Scheduled | 08/01/2024 | 12/01/2024
TO-24-CSH-220K2-4-02 | COUPLER/SECTIONALISING CB - CASHLA 220-CASHLA 220-220K2-4 | 5 | 5 | 5 | Scheduled | 08/01/2024 | 12/01/2024
TO-24-CLN-T142-01 | DISTRIBUTION TRANSFORMER - CLOON 110-CLOON 38-T142 | 152 | 104 | 104 | Reference | 15/01/2024 | 14/06/2024
TO-24-CF-T104-02 | GENERATOR TRANSFORMER - CATHALEENS FALL 110-CATHALEENS FALL G4-T104 | 2 | 2 | 2 | Scheduled | 12/02/2024 | 13/02/2024
TO-24-BUF-T131-01 | GENERATOR TRANSFORMER - BUFFY 110-BUFFY 33-T131 | 1 | 1 | 1 | Scheduled | 19/02/2024 | 19/02/2024
TO-24-CLN-110SA1-01 | SECTIONALISING DISCONNECT - CLOON 110-CLOON 110-110SA1 | 12 | 10 | 10 | Scheduled | 19/02/2024 | 01/03/2024
TO-24-CLN-110SA2-01 | SECTIONALISING DISCONNECT - CLOON 110-CLOON 110-110SA2 | 12 | 10 | 10 | Scheduled | 19/02/2024 | 01/03/2024
TO-24-CLN-LA-1-01 | 110kV FEEDER - CLOON 110-LANESBORO 110-1 | 12 | 10 | 10 | Scheduled | 19/02/2024 | 01/03/2024
TO-24-CSH-T2104-02 | TRANSFORMER - CASHLA 220-CASHLA 110-T2104 | 66 | 45 |  | Scheduled | 26/02/2024 | 01/05/2024
TO-24-SKY-T132-01 | GENERATOR TRANSFORMER - SRAHNAKILLY 110-SRAHNAKILLY 33-T132 | 2 | 2 | 2 | Scheduled | 29/02/2024 | 01/03/2024
TO-24-DYN-T121-01 | GENERATOR TRANSFORMER - DERRYBRIEN 110-DERRYBRIEN 20-T121 | 22 | 15 |  | Reference | 04/03/2024 | 25/03/2024
TO-24-FLA-SLB-1-04 | 110kV FEEDER - FLAGFORD 110-SLIABH BAWN 110-1 | 47 | 32 | 32 | Scheduled | 04/03/2024 | 19/04/2024
TO-24-CUN-GLR-1-01 | 110kV FEEDER - CUNGHILL 110-GLENREE 110-1 | 5 | 4 | 4 | Scheduled | 18/03/2024 | 22/03/2024
TO-24-110 kV A2 @ GLR-01 | BUSBAR SECTION - GLENREE 110-GLENREE 110-110A2 | 5 | 4 | 4 | Scheduled | 18/03/2024 | 22/03/2024
TO-24-GLR-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - GLENREE 110-GLENREE 110-110SA1-2CB | 5 | 4 | 4 | Scheduled | 18/03/2024 | 22/03/2024
TO-24-GLR-T142-01 | DISTRIBUTION TRANSFORMER - GLENREE 110-GLENREE 38-T142 | 5 | 4 | 4 | Reference | 18/03/2024 | 22/03/2024
TO-24-BIN-TIV-1-01 | 110kV FEEDER - BINBANE 110-TIEVEBRACK 110-1 | 4 | 4 | 4 | Scheduled | 19/03/2024 | 22/03/2024
TO-24-CBR-DLT-1-03 | 110kV FEEDER - CASTLEBAR 110-DALTON 110-1 | 4 | 4 | 4 | Scheduled | 25/03/2024 | 28/03/2024
TO-24-110 kV A2 @ CF-04 | BUSBAR SECTION - CATHALEENS FALL 110-CATHALEENS FALL 110-110A2 | 4 | 4 | 4 | Scheduled | 25/03/2024 | 28/03/2024
TO-24-110 kV B2 @ CF-01 | BUSBAR SECTION - CATHALEENS FALL 110-CATHALEENS FALL 110-110B2 | 4 | 4 | 4 | Scheduled | 25/03/2024 | 28/03/2024
TO-24-CF-SRA-2-03 | 110kV FEEDER - CATHALEENS FALL 110-SRANANAGH 110-2 | 4 | 4 | 4 | Scheduled | 25/03/2024 | 28/03/2024
TO-24-TAW-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - TAWNAGHMORE 110-TAWNAGHMORE 110-110SA1-2CB | 4 | 4 | 4 | Scheduled | 25/03/2024 | 28/03/2024
TO-24-CBR-SVC-02 | CAPACITOR/SVC/REACTOR - CASTLEBAR 110-CASTLEBAR 110-SVC | 4 | 4 | 4 | Scheduled | 02/04/2024 | 05/04/2024
TO-24-DRM-LET-1-01 | 110kV FEEDER - DRUMKEEN 110-LETTERKENNY 110-1 | 4 | 4 | 4 | Scheduled | 02/04/2024 | 05/04/2024
TO-24-LET-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - LETTERKENNY 110-LETTERKENNY 110-110SA1-2CB | 2 | 2 | 2 | Scheduled | 03/04/2024 | 04/04/2024
TO-24-LET-110SA1-3CB-02 | COUPLER/SECTIONALISING CB - LETTERKENNY 110-LETTERKENNY 110-110SA1-3CB | 2 | 2 | 2 | Scheduled | 03/04/2024 | 04/04/2024
TO-24-LET-M/CAP1-01 | CAPACITOR/SVC/REACTOR - LETTERKENNY 110-LETTERKENNY 110-M/CAP1 | 2 | 2 | 2 | Scheduled | 03/04/2024 | 04/04/2024
TO-24-LET-PST-01 | TRANSFORMER - LETTERKENNY 110-STRABANE 110-PST | 2 | 2 | 2 | Scheduled | 03/04/2024 | 04/04/2024
TO-24-LET-SVC-01 | CAPACITOR/SVC/REACTOR - LETTERKENNY 110-LETTERKENNY 110-SVC | 2 | 2 | 2 | Scheduled | 03/04/2024 | 04/04/2024
TO-24-LET-T141-01 | DISTRIBUTION TRANSFORMER - LETTERKENNY 110-LETTERKENNY 38-T141 | 2 | 2 |  | Reference | 03/04/2024 | 04/04/2024
TO-24-BK-CBR-1-01 | 110kV FEEDER - BELLACORICK 110-CASTLEBAR 110-1 | 12 | 10 | 10 | Scheduled | 08/04/2024 | 19/04/2024
TO-24-BK-SKY-1-01 | 110kV FEEDER - BELLACORICK 110-SRAHNAKILLY 110-1 | 33 | 24 | 24 | Scheduled | 08/04/2024 | 10/05/2024
TO-24-CL-T101-02 | GENERATOR TRANSFORMER - CLIFF 110-CLIFF G1-T101 | 5 | 5 |  | Scheduled | 08/04/2024 | 12/04/2024
TO-24-SKY-110SA1-01 | SECTIONALISING DISCONNECT - SRAHNAKILLY 110-SRAHNAKILLY 110-110SA1 | 33 | 24 | 24 | Scheduled | 08/04/2024 | 10/05/2024
TO-24-SKY-110SA2-01 | SECTIONALISING DISCONNECT - SRAHNAKILLY 110-SRAHNAKILLY 110-110SA2 | 33 | 24 | 24 | Scheduled | 08/04/2024 | 10/05/2024
TO-24-SKY-T131-02 | GENERATOR TRANSFORMER - SRAHNAKILLY 110-SRAHNAKILLY 33-T131 | 33 | 24 | 24 | Scheduled | 08/04/2024 | 10/05/2024
TO-24-SKY-T132-02 | GENERATOR TRANSFORMER - SRAHNAKILLY 110-SRAHNAKILLY 33-T132 | 33 | 24 | 24 | Scheduled | 08/04/2024 | 10/05/2024
TO-24-LLA-T133-01 | GENERATOR TRANSFORMER - LENALEA 110-LENALEA 33-T133 | 1 | 1 | 1 | Scheduled | 09/04/2024 | 09/04/2024
TO-24-BIN-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - BINBANE 110-BINBANE 110-110SA1-2CB | 3 | 3 | 3 | Scheduled | 22/04/2024 | 24/04/2024
TO-24-BIN-CF-1-01 | 110kV FEEDER - BINBANE 110-CATHALEENS FALL 110-1 | 180 | 127 | 127 | Scheduled | 22/04/2024 | 18/10/2024
TO-24-BIN-T142-02 | DISTRIBUTION TRANSFORMER - BINBANE 110-BINBANE 38-T142 | 3 | 3 | 3 | Reference | 22/04/2024 | 24/04/2024
TO-24-COS-FLA-1-03 | 110kV FEEDER - CARRICK ON SHANNON 110-FLAGFORD 110-1 | 58 | 40 |  | Scheduled | 22/04/2024 | 18/06/2024
TO-24-110 kV A2 @ CF-01 | BUSBAR SECTION - CATHALEENS FALL 110-CATHALEENS FALL 110-110A2 | 100 | 70 | 70 | Scheduled | 22/04/2024 | 30/07/2024
TO-24-110 kV A2 @ CLO-02 | BUSBAR SECTION - CLOGHER 110-CLOGHER 110-110A2 | 8 | 6 | 6 | Scheduled | 22/04/2024 | 29/04/2024
TO-24-110 kV B2 @ CLO-02 | BUSBAR SECTION - CLOGHER 110-CLOGHER 110-110B2 | 8 | 6 | 6 | Scheduled | 22/04/2024 | 29/04/2024
TO-24-CLO-MRY-1-01 | 110kV FEEDER - CLOGHER 110-MULREAVY 110-1 | 8 | 6 | 6 | Scheduled | 22/04/2024 | 29/04/2024
TO-24-110 kV A1 @ FLA-04 | BUSBAR SECTION - FLAGFORD 110-FLAGFORD 110-110A1 | 54 | 38 | 38 | Scheduled | 22/04/2024 | 14/06/2024
TO-24-110 kV B1 @ FLA-05 | BUSBAR SECTION - FLAGFORD 110-FLAGFORD 110-110B1 | 54 | 38 | 38 | Scheduled | 22/04/2024 | 14/06/2024
TO-24-MRY-T131-01 | GENERATOR TRANSFORMER - MULREAVY 110-MULREAVY 33-T131 | 8 | 6 | 6 | Scheduled | 22/04/2024 | 29/04/2024
TO-24-UGL-T132-03 | GENERATOR TRANSFORMER - UGGOOL 110-UGGOOL 33-T132 | 5 | 5 | 5 | Scheduled | 22/04/2024 | 26/04/2024
TO-24-UGL-T134-02 | GENERATOR TRANSFORMER - UGGOOL 110-UGGOOL 33-T134 | 5 | 5 | 5 | Scheduled | 22/04/2024 | 26/04/2024
TO-24-BUF-T131-02 | GENERATOR TRANSFORMER - BUFFY 110-BUFFY 33-T131 | 1 | 1 | 1 | Scheduled | 23/04/2024 | 23/04/2024
TO-24-CBR-CAP2-01 | CAPACITOR/SVC/REACTOR - CASTLEBAR 110-CASTLEBAR 110-CAP2 | 4 | 4 | 4 | Scheduled | 07/05/2024 | 10/05/2024
TO-24-MEE-T121-01 | GENERATOR TRANSFORMER - MEENTYCAT 110-MEENTYCAT 20-T121 | 3 | 3 | 3 | Scheduled | 07/05/2024 | 09/05/2024
TO-24-CSH-GAL GIS-2-02 | 110kV FEEDER - CASHLA 110-GALWAY GIS 110-2 | 1 | 1 | 1 | Scheduled | 08/05/2024 | 08/05/2024
TO-24-110 kV A2 @ CSH-04 | BUSBAR SECTION - CASHLA 110-CASHLA 110-110A2 | 72 | 51 | 51 | Scheduled | 09/05/2024 | 19/07/2024
TO-24-110 kV B2 @ CSH-04 | BUSBAR SECTION - CASHLA 110-CASHLA 110-110B2 | 72 | 51 | 51 | Scheduled | 09/05/2024 | 19/07/2024
TO-24-220 kV B2 @ CSH-01 | BUSBAR SECTION - CASHLA 220-CASHLA 220-220B2 | 72 | 51 | 51 | Scheduled | 09/05/2024 | 19/07/2024
TO-24-CSH-220K2-4-03 | COUPLER/SECTIONALISING CB - CASHLA 220-CASHLA 220-220K2-4 | 72 | 51 | 51 | Scheduled | 09/05/2024 | 19/07/2024
TO-24-CSH-T2102-01 | TRANSFORMER - CASHLA 220-CASHLA 110-T2102 | 72 | 51 | 51 | Scheduled | 09/05/2024 | 19/07/2024
TO-24-110 kV A1 @ CSH-06 | BUSBAR SECTION - CASHLA 110-CASHLA 110-110A1 | 6 | 5 | 5 | Scheduled | 13/05/2024 | 18/05/2024
TO-24-110 kV B1 @ CSH-03 | BUSBAR SECTION - CASHLA 110-CASHLA 110-110B1 | 6 | 5 | 5 | Scheduled | 13/05/2024 | 18/05/2024
TO-24-CL-T102-03 | GENERATOR TRANSFORMER - CLIFF 110-CLIFF G2-T102 | 11 | 9 |  | Scheduled | 13/05/2024 | 23/05/2024
TO-24-MOY-CAP2-01 | CAPACITOR/SVC/REACTOR - MOY 110-MOY 110-CAP2 | 2 | 2 | 2 | Scheduled | 14/05/2024 | 15/05/2024
TO-24-110 kV A1 @ CSH-05 | BUSBAR SECTION - CASHLA 110-CASHLA 110-110A1 | 3 | 3 | 3 | Scheduled | 20/05/2024 | 22/05/2024
TO-24-CSH-GAL GIS-1-01 | 110kV FEEDER - CASHLA 110-GALWAY GIS 110-1 | 3 | 3 | 3 | Scheduled | 20/05/2024 | 22/05/2024
TO-24-220 kV A1 @ FLA-02 | BUSBAR SECTION - FLAGFORD 220-FLAGFORD 220-220A1 | 5 | 5 | 5 | Scheduled | 20/05/2024 | 24/05/2024
TO-24-220 kV A2 @ FLA-04 | BUSBAR SECTION - FLAGFORD 220-FLAGFORD 220-220A2 | 5 | 5 | 5 | Scheduled | 20/05/2024 | 24/05/2024
TO-24-220 kV B1 @ FLA-03 | BUSBAR SECTION - FLAGFORD 220-FLAGFORD 220-220B1 | 5 | 5 | 5 | Scheduled | 20/05/2024 | 24/05/2024
TO-24-220 kV B2 @ FLA-03 | BUSBAR SECTION - FLAGFORD 220-FLAGFORD 220-220B2 | 5 | 5 | 5 | Scheduled | 20/05/2024 | 24/05/2024
TO-24-FLA-220K1-2-01 | COUPLER/SECTIONALISING CB - FLAGFORD 220-FLAGFORD 220-220K1-2 | 5 | 5 | 5 | Scheduled | 20/05/2024 | 24/05/2024
TO-24-CF-SRA-1-02 | 110kV FEEDER - CATHALEENS FALL 110-SRANANAGH 110-1 | 70 | 49 | 49 | Scheduled | 05/06/2024 | 13/08/2024
TO-24-CLN-110SA1-02 | SECTIONALISING DISCONNECT - CLOON 110-CLOON 110-110SA1 | 9 | 7 | 7 | Scheduled | 06/06/2024 | 14/06/2024
TO-24-CLN-110SA2-02 | SECTIONALISING DISCONNECT - CLOON 110-CLOON 110-110SA2 | 9 | 7 | 7 | Scheduled | 06/06/2024 | 14/06/2024
TO-24-CLN-LA-1-02 | 110kV FEEDER - CLOON 110-LANESBORO 110-1 | 9 | 7 | 7 | Scheduled | 06/06/2024 | 14/06/2024
TO-24-CF-T103-01 | GENERATOR TRANSFORMER - CATHALEENS FALL 110-CATHALEENS FALL G3-T103 | 5 | 5 | 5 | Scheduled | 10/06/2024 | 14/06/2024
TO-24-110 kV A1 @ GAL GIS-01 | BUSBAR SECTION - GALWAY GIS 110-GALWAY GIS 110-110A1 | 7 | 5 | 5 | Scheduled | 10/06/2024 | 16/06/2024
TO-24-110 kV B1 @ GAL GIS-01 | BUSBAR SECTION - GALWAY GIS 110-GALWAY GIS 110-110B1 | 7 | 5 | 5 | Scheduled | 10/06/2024 | 16/06/2024
TO-24-GAL GIS-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - GALWAY GIS 110-GALWAY GIS 110-110SA1-2CB | 7 | 5 | 5 | Scheduled | 10/06/2024 | 16/06/2024
TO-24-GAL GIS-110SA1-3CB-01 | COUPLER/SECTIONALISING CB - GALWAY GIS 110-GALWAY GIS 110-110SA1-3CB | 7 | 5 | 5 | Scheduled | 10/06/2024 | 16/06/2024
TO-24-GAL GIS-110SB1-2CB-01 | COUPLER/SECTIONALISING CB - GALWAY GIS 110-GALWAY GIS 110-110SB1-2CB | 7 | 5 | 5 | Scheduled | 10/06/2024 | 16/06/2024
TO-24-GAL GIS-110SB1-3CB-01 | COUPLER/SECTIONALISING CB - GALWAY GIS 110-GALWAY GIS 110-110SB1-3CB | 7 | 5 | 5 | Scheduled | 10/06/2024 | 16/06/2024
TO-24-CUN-T121-01 | GENERATOR TRANSFORMER - CUNGHILL 110-CUNGHILL 20-T121 | 5 | 5 | 5 | Scheduled | 17/06/2024 | 21/06/2024
TO-24-110 kV A1 @ FLA-05 | BUSBAR SECTION - FLAGFORD 110-FLAGFORD 110-110A1 | 2 | 2 |  | Scheduled | 17/06/2024 | 18/06/2024
TO-24-110 kV B1 @ FLA-06 | BUSBAR SECTION - FLAGFORD 110-FLAGFORD 110-110B1 | 2 | 2 |  | Scheduled | 17/06/2024 | 18/06/2024
TO-24-CLO-CRD-1-01 | 110kV FEEDER - CLOGHER 110-CROAGHONAGH 110-1 | 4 | 4 | 4 | Scheduled | 18/06/2024 | 21/06/2024
TO-24-CRD-T131-01 | GENERATOR TRANSFORMER - CROAGHONAGH 110-CROAGHONAGH 33-T131 | 4 | 4 | 4 | Scheduled | 18/06/2024 | 21/06/2024
TO-24-FLA-T2101-01 | TRANSFORMER - FLAGFORD 220-FLAGFORD 110-T2101 | 1 | 1 |  | Scheduled | 18/06/2024 | 18/06/2024
TO-24-DYN-T121-03 | GENERATOR TRANSFORMER - DERRYBRIEN 110-DERRYBRIEN 20-T121 | 3 | 3 | 3 | Reference | 24/06/2024 | 26/06/2024
TO-24-110 kV A1 @ GAL GIS-02 | BUSBAR SECTION - GALWAY GIS 110-GALWAY GIS 110-110A1 | 2 | 2 | 2 | Scheduled | 24/06/2024 | 25/06/2024
TO-24-110 kV B1 @ GAL GIS-02 | BUSBAR SECTION - GALWAY GIS 110-GALWAY GIS 110-110B1 | 2 | 2 | 2 | Scheduled | 24/06/2024 | 25/06/2024
TO-24-GAL GIS-110SA1-2CB-02 | COUPLER/SECTIONALISING CB - GALWAY GIS 110-GALWAY GIS 110-110SA1-2CB | 2 | 2 | 2 | Scheduled | 24/06/2024 | 25/06/2024
TO-24-GAL GIS-110SA1-3CB-02 | COUPLER/SECTIONALISING CB - GALWAY GIS 110-GALWAY GIS 110-110SA1-3CB | 2 | 2 | 2 | Scheduled | 24/06/2024 | 25/06/2024
TO-24-GAL GIS-110SB1-2CB-02 | COUPLER/SECTIONALISING CB - GALWAY GIS 110-GALWAY GIS 110-110SB1-2CB | 2 | 2 | 2 | Scheduled | 24/06/2024 | 25/06/2024
TO-24-GAL GIS-110SB1-3CB-02 | COUPLER/SECTIONALISING CB - GALWAY GIS 110-GALWAY GIS 110-110SB1-3CB | 2 | 2 | 2 | Scheduled | 24/06/2024 | 25/06/2024
TO-24-GAL GIS-SAL-1-01 | 110kV FEEDER - GALWAY GIS 110-SALTHILL 110-1 | 2 | 2 | 2 | Scheduled | 24/06/2024 | 25/06/2024
TO-24-GAL GIS-T142-04 | DISTRIBUTION TRANSFORMER - GALWAY GIS 110-GALWAY 38-T142 | 14 | 10 | 10 | Reference | 26/06/2024 | 09/07/2024
TO-24-110 kV A2 @ FLA-04 | BUSBAR SECTION - FLAGFORD 110-FLAGFORD 110-110A2 | 12 | 10 | 10 | Scheduled | 01/07/2024 | 12/07/2024
TO-24-110 kV B2 @ FLA-04 | BUSBAR SECTION - FLAGFORD 110-FLAGFORD 110-110B2 | 12 | 10 | 10 | Scheduled | 01/07/2024 | 12/07/2024
TO-24-220 kV A2 @ FLA-05 | BUSBAR SECTION - FLAGFORD 220-FLAGFORD 220-220A2 | 12 | 10 | 10 | Scheduled | 01/07/2024 | 12/07/2024
TO-24-220 kV B2 @ FLA-04 | BUSBAR SECTION - FLAGFORD 220-FLAGFORD 220-220B2 | 12 | 10 | 10 | Scheduled | 01/07/2024 | 12/07/2024
TO-24-FLA-T2102-01 | TRANSFORMER - FLAGFORD 220-FLAGFORD 110-T2102 | 12 | 10 | 10 | Scheduled | 01/07/2024 | 12/07/2024
TO-24-ARI,T-CDY-1-01 | 110kV FEEDER - ARIGNA tee-CORDERRY 110-1 | 1 | 1 | 1 | Scheduled | 02/07/2024 | 02/07/2024
TO-24-TAW-T1/T2-01 | GENERATOR TRANSFORMER - TAWNAGHMORE 110-TAWNAGHMORE 10-T1/T2 | 12 | 10 | 10 | Scheduled | 08/07/2024 | 19/07/2024
TO-24-TAW-T3-01 | GENERATOR TRANSFORMER - TAWNAGHMORE 110-TAWNAGHMORE 10-T3 | 12 | 10 | 10 | Scheduled | 08/07/2024 | 19/07/2024
TO-24-GAL-GAL GIS-2-02 | 110kV FEEDER - GALWAY 110-GALWAY GIS 110-2 | 174 | 120 | 120 | Scheduled | 11/07/2024 | 31/12/2024
TO-24-GAL-T141-02 | DISTRIBUTION TRANSFORMER - GALWAY 110-GALWAY 38-T141 | 97 | 68 | 68 | Reference | 11/07/2024 | 15/10/2024
TO-24-CDY-GRV-1-01 | 110kV FEEDER - CORDERRY 110-GARVAGH 110-1 | 2 | 2 | 2 | Scheduled | 15/07/2024 | 16/07/2024
TO-24-GRV-110K1-01 | COUPLER/SECTIONALISING CB - GARVAGH 110-GARVAGH 110-110K1 | 2 | 2 | 2 | Scheduled | 15/07/2024 | 16/07/2024
TO-24-GRV-T121-01 | GENERATOR TRANSFORMER - GARVAGH 110-GARVAGH 20-T121 | 9 | 7 | 7 | Scheduled | 15/07/2024 | 23/07/2024
TO-24-GRV-T141-02 | DISTRIBUTION TRANSFORMER - GARVAGH 110-GARVAGH 20-T141 | 2 | 2 | 2 | Reference | 15/07/2024 | 16/07/2024
TO-24-220 kV B2/B4 @ CSH-01 | BUSBAR SECTION - CASHLA 220-CASHLA 220-220B2-B4 | 1 | 1 |  | Scheduled | 19/07/2024 | 19/07/2024
TO-24-CSH-PRO-1-04 | 220kV FEEDER - CASHLA 220-PROSPECT 220-1 | 1 | 1 |  | Scheduled | 19/07/2024 | 19/07/2024
TO-24-BK-CBR-1-03 | 110kV FEEDER - BELLACORICK 110-CASTLEBAR 110-1 | 10 | 8 | 8 | Scheduled | 22/07/2024 | 31/07/2024
TO-24-TON-T142-02 | DISTRIBUTION TRANSFORMER - TONROE 110-TONROE 38-T142 | 2 | 2 | 2 | Reference | 23/07/2024 | 24/07/2024
TO-24-CSH-T2101-01 | TRANSFORMER - CASHLA 220-CASHLA 110-T2101 | 75 | 52 | 52 | Scheduled | 25/07/2024 | 07/10/2024
TO-24-110 kV A1 @ FLA-06 | BUSBAR SECTION - FLAGFORD 110-FLAGFORD 110-110A1 | 5 | 5 | 5 | Scheduled | 29/07/2024 | 02/08/2024
TO-24-110 kV B1 @ FLA-07 | BUSBAR SECTION - FLAGFORD 110-FLAGFORD 110-110B1 | 5 | 5 | 5 | Scheduled | 29/07/2024 | 02/08/2024
TO-24-FLA-GIL-1-01 | 110kV FEEDER - FLAGFORD 110-GILRA 110-1 | 5 | 5 | 5 | Scheduled | 29/07/2024 | 02/08/2024
TO-24-GIL-T121-02 | TSO CUSTOMER TRANSFORMER - GILRA 110-GILRA 20-T121 | 5 | 5 | 5 | Reference | 29/07/2024 | 02/08/2024
TO-24-CBR-CLN-1-04 | 110kV FEEDER - CASTLEBAR 110-CLOON 110-1 | 4 | 4 | 4 | Scheduled | 06/08/2024 | 09/08/2024
TO-24-CUN-110SA1-03 | SECTIONALISING DISCONNECT - CUNGHILL 110-CUNGHILL 110-110SA1 | 3 | 3 | 3 | Scheduled | 13/08/2024 | 15/08/2024
TO-24-CUN-110SA2-01 | SECTIONALISING DISCONNECT - CUNGHILL 110-CUNGHILL 110-110SA2 | 3 | 3 | 3 | Scheduled | 13/08/2024 | 15/08/2024
TO-24-CUN-SLI-1-03 | 110kV FEEDER - CUNGHILL 110-SLIGO 110-1 | 3 | 3 | 3 | Scheduled | 13/08/2024 | 15/08/2024
TO-24-CUN-T121-02 | GENERATOR TRANSFORMER - CUNGHILL 110-CUNGHILL 20-T121 | 3 | 3 | 3 | Scheduled | 13/08/2024 | 15/08/2024
TO-24-GOL-T101-03 | GENERATOR TRANSFORMER - GOLAGH 110-GOLAGH 10-T101 | 4 | 4 | 4 | Scheduled | 19/08/2024 | 22/08/2024
TO-24-UGL-T131-02 | GENERATOR TRANSFORMER - UGGOOL 110-UGGOOL 33-T131 | 5 | 5 | 5 | Scheduled | 19/08/2024 | 23/08/2024
TO-24-UGL-T132-04 | GENERATOR TRANSFORMER - UGGOOL 110-UGGOOL 33-T132 | 10 | 8 | 8 | Scheduled | 19/08/2024 | 28/08/2024
TO-24-UGL-T134-03 | GENERATOR TRANSFORMER - UGGOOL 110-UGGOOL 33-T134 | 10 | 8 | 8 | Scheduled | 19/08/2024 | 28/08/2024
TO-24-110 kV B1 @ CF-04 | BUSBAR SECTION - CATHALEENS FALL 110-CATHALEENS FALL 110-110B1 | 1 | 1 | 1 | Proposed | 22/08/2024 | 22/08/2024
TO-24-CF-CL-1-02 | 110kV FEEDER - CATHALEENS FALL 110-CLIFF 110-1 | 2 | 2 | 2 | Proposed | 22/08/2024 | 23/08/2024
TO-24-CL-T101-04 | GENERATOR TRANSFORMER - CLIFF 110-CLIFF G1-T101 | 1 | 1 | 1 | Proposed | 22/08/2024 | 22/08/2024
TO-24-CL-T102-06 | GENERATOR TRANSFORMER - CLIFF 110-CLIFF G2-T102 | 1 | 1 | 1 | Proposed | 22/08/2024 | 22/08/2024
TO-24-110 kV A1 @ CF-04 | BUSBAR SECTION - CATHALEENS FALL 110-CATHALEENS FALL 110-110A1 | 12 | 10 | 10 | Scheduled | 26/08/2024 | 06/09/2024
TO-24-110 kV A2 @ CF-02 | BUSBAR SECTION - CATHALEENS FALL 110-CATHALEENS FALL 110-110A2 | 5 | 5 | 5 | Scheduled | 26/08/2024 | 30/08/2024
TO-24-110 kV B1 @ CF-03 | BUSBAR SECTION - CATHALEENS FALL 110-CATHALEENS FALL 110-110B1 | 12 | 10 | 10 | Scheduled | 26/08/2024 | 06/09/2024
TO-24-CF-COR-1-01 | 110kV FEEDER - CATHALEENS FALL 110-CORRACLASSY 110-1 | 12 | 10 |  | Scheduled | 26/08/2024 | 06/09/2024
TO-24-GLR-110SA1-2CB-03 | COUPLER/SECTIONALISING CB - GLENREE 110-GLENREE 110-110SA1-2CB | 5 | 5 | 5 | Scheduled | 26/08/2024 | 30/08/2024
TO-24-GLR-T121-01 | DISTRIBUTION TRANSFORMER - GLENREE 110-GLENREE 38-T121 | 5 | 5 | 5 | Reference | 26/08/2024 | 30/08/2024
TO-24-MOY-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - MOY 110-MOY 110-110SA1-2CB | 5 | 5 | 5 | Scheduled | 26/08/2024 | 30/08/2024
TO-24-MOY-CAP1-01 | CAPACITOR/SVC/REACTOR - MOY 110-MOY 110-CAP1 | 12 | 10 | 10 | Scheduled | 26/08/2024 | 06/09/2024
TO-24-MOY-T141-01 | DISTRIBUTION TRANSFORMER - MOY 110-MOY 38-T141 | 5 | 5 | 5 | Reference | 26/08/2024 | 30/08/2024
TO-24-MOY-TAW-1-04 | 110kV FEEDER - MOY 110-TAWNAGHMORE 110-1 | 12 | 10 | 10 | Scheduled | 26/08/2024 | 06/09/2024
TO-24-BIN-110SA1-2CB-02 | COUPLER/SECTIONALISING CB - BINBANE 110-BINBANE 110-110SA1-2CB | 3 | 3 | 3 | Scheduled | 02/09/2024 | 04/09/2024
TO-24-BIN-T142-03 | DISTRIBUTION TRANSFORMER - BINBANE 110-BINBANE 38-T142 | 3 | 3 | 3 | Reference | 02/09/2024 | 04/09/2024
TO-24-GLR-MOY-1-01 | 110kV FEEDER - GLENREE 110-MOY 110-1 | 61 | 44 | 44 | Scheduled | 02/09/2024 | 01/11/2024
TO-24-SOM,T-CSH-1-01 | 110kV FEEDER - SOMERSET tee-CASHLA 110-1 | 66 | 47 | 47 | Proposed | 09/09/2024 | 13/11/2024
TO-24-110 kV A2 @ CSH-01 | BUSBAR SECTION - CASHLA 110-CASHLA 110-110A2 | 58 | 41 |  | Scheduled | 12/09/2024 | 08/11/2024
TO-24-110 kV B2 @ CSH-01 | BUSBAR SECTION - CASHLA 110-CASHLA 110-110B2 | 58 | 41 |  | Scheduled | 12/09/2024 | 08/11/2024
TO-24-110 kV A3 @ GAL GIS-03 | BUSBAR SECTION - GALWAY GIS 110-GALWAY GIS 110-110A3 | 9 | 7 | 7 | Scheduled | 23/09/2024 | 01/10/2024
TO-24-110 kV B3 @ GAL GIS-01 | BUSBAR SECTION - GALWAY GIS 110-GALWAY GIS 110-110B3 | 9 | 7 | 7 | Scheduled | 23/09/2024 | 01/10/2024
TO-24-GAL GIS-110K3-01 | COUPLER/SECTIONALISING CB - GALWAY GIS 110-GALWAY GIS 110-110K3 | 9 | 7 | 7 | Scheduled | 23/09/2024 | 01/10/2024
TO-24-GAL GIS-110SA1-3CB-03 | COUPLER/SECTIONALISING CB - GALWAY GIS 110-GALWAY GIS 110-110SA1-3CB | 9 | 7 | 7 | Scheduled | 23/09/2024 | 01/10/2024
TO-24-GAL GIS-110SB1-3CB-03 | COUPLER/SECTIONALISING CB - GALWAY GIS 110-GALWAY GIS 110-110SB1-3CB | 9 | 7 | 7 | Scheduled | 23/09/2024 | 01/10/2024
TO-24-COS-FLA-2-03 | 110kV FEEDER - CARRICK ON SHANNON 110-FLAGFORD 110-2 | 57 | 40 |  | Scheduled | 30/09/2024 | 25/11/2024
TO-24-110 kV A2 @ FLA-01 | BUSBAR SECTION - FLAGFORD 110-FLAGFORD 110-110A2 | 53 | 38 | 38 | Scheduled | 30/09/2024 | 21/11/2024
TO-24-110 kV B2 @ FLA-01 | BUSBAR SECTION - FLAGFORD 110-FLAGFORD 110-110B2 | 53 | 38 | 38 | Scheduled | 30/09/2024 | 21/11/2024
TO-24-MOY-TAW-2-02 | 110kV FEEDER - MOY 110-TAWNAGHMORE 110-2 | 5 | 5 | 5 | Scheduled | 07/10/2024 | 11/10/2024
TO-24-LLA-110K1-02 | COUPLER/SECTIONALISING CB - LENALEA 110-LENALEA 110-110K1 | 1 | 1 | 1 | Scheduled | 08/10/2024 | 08/10/2024
TO-24-GAL-T103-01 | DISTRIBUTION TRANSFORMER - GALWAY 110-GALWAY 10-T103 | 84 | 57 | 57 | Scheduled | 09/10/2024 | 31/12/2024
TO-24-CSH-GAL GIS-1-03 | 110kV FEEDER - CASHLA 110-GALWAY GIS 110-1 | 2 | 2 | 2 | Scheduled | 14/10/2024 | 15/10/2024
TO-24-110 kV A3 @ GAL GIS-05 | BUSBAR SECTION - GALWAY GIS 110-GALWAY GIS 110-110A3 | 2 | 2 | 2 | Scheduled | 14/10/2024 | 15/10/2024
TO-24-110 kV B3 @ GAL GIS-05 | BUSBAR SECTION - GALWAY GIS 110-GALWAY GIS 110-110B3 | 2 | 2 | 2 | Scheduled | 14/10/2024 | 15/10/2024
TO-24-GAL GIS-110K3-07 | COUPLER/SECTIONALISING CB - GALWAY GIS 110-GALWAY GIS 110-110K3 | 2 | 2 | 2 | Scheduled | 14/10/2024 | 15/10/2024
TO-24-GAL GIS-110SA1-3CB-09 | COUPLER/SECTIONALISING CB - GALWAY GIS 110-GALWAY GIS 110-110SA1-3CB | 2 | 2 | 2 | Scheduled | 14/10/2024 | 15/10/2024
TO-24-GAL GIS-110SB1-3CB-09 | COUPLER/SECTIONALISING CB - GALWAY GIS 110-GALWAY GIS 110-110SB1-3CB | 2 | 2 | 2 | Scheduled | 14/10/2024 | 15/10/2024
TO-24-MOY-CAP1-02 | CAPACITOR/SVC/REACTOR - MOY 110-MOY 110-CAP1 | 13 | 10 | 10 | Scheduled | 14/10/2024 | 26/10/2024
TO-24-MOY-TAW-1-03 | 110kV FEEDER - MOY 110-TAWNAGHMORE 110-1 | 19 | 14 | 14 | Scheduled | 14/10/2024 | 01/11/2024
TO-24-110 kV A2 @ CF-03 | BUSBAR SECTION - CATHALEENS FALL 110-CATHALEENS FALL 110-110A2 | 1 | 1 | 1 | Scheduled | 18/10/2024 | 18/10/2024
TO-24-CF-SRA-2-02 | 110kV FEEDER - CATHALEENS FALL 110-SRANANAGH 110-2 | 1 | 1 | 1 | Scheduled | 18/10/2024 | 18/10/2024
TO-24-220 kV A2 @ CSH-04 | BUSBAR SECTION - CASHLA 220-CASHLA 220-220A2 | 12 | 9 | 9 | Scheduled | 21/10/2024 | 01/11/2024
TO-24-220 kV B2 @ CSH-06 | BUSBAR SECTION - CASHLA 220-CASHLA 220-220B2 | 12 | 9 | 9 | Scheduled | 21/10/2024 | 01/11/2024
TO-24-CSH-T2102-03 | TRANSFORMER - CASHLA 220-CASHLA 110-T2102 | 12 | 9 | 9 | Scheduled | 21/10/2024 | 01/11/2024
TO-24-GAL-GAL GIS-1-04 | 110kV FEEDER - GALWAY 110-GALWAY GIS 110-1 | 72 | 49 | 49 | Proposed | 21/10/2024 | 31/12/2024
TO-24-GAL GIS-T142-05 | DISTRIBUTION TRANSFORMER - GALWAY GIS 110-GALWAY 38-T142 | 5 | 5 | 5 | Reference (Proposed) | 21/10/2024 | 25/10/2024
TO-24-220 kV A2 @ FLA-06 | BUSBAR SECTION - FLAGFORD 220-FLAGFORD 220-220A2 | 1 | 1 | 1 | Proposed | 23/10/2024 | 23/10/2024
TO-24-220 kV B2 @ FLA-05 | BUSBAR SECTION - FLAGFORD 220-FLAGFORD 220-220B2 | 1 | 1 | 1 | Proposed | 23/10/2024 | 23/10/2024
TO-24-GAL GIS-110K2-01 | COUPLER/SECTIONALISING CB - GALWAY GIS 110-GALWAY GIS 110-110K2 | 1 | 1 | 1 | Scheduled | 23/10/2024 | 23/10/2024
TO-24-GAL GIS-110K3-03 | COUPLER/SECTIONALISING CB - GALWAY GIS 110-GALWAY GIS 110-110K3 | 1 | 1 | 1 | Scheduled | 24/10/2024 | 24/10/2024
TO-24-GAL GIS-110SA1-3CB-04 | COUPLER/SECTIONALISING CB - GALWAY GIS 110-GALWAY GIS 110-110SA1-3CB | 1 | 1 |  | Scheduled | 25/10/2024 | 25/10/2024
TO-24-GAL GIS-KNY-1-03 | 110kV FEEDER - GALWAY GIS 110-KNOCKRANNY 110-1 | 5 | 4 | 4 | Proposed | 28/10/2024 | 01/11/2024
TO-24-GAL GIS-110SB1-3CB-04 | COUPLER/SECTIONALISING CB - GALWAY GIS 110-GALWAY GIS 110-110SB1-3CB | 1 | 1 | 1 | Scheduled | 29/10/2024 | 29/10/2024
TO-24-BK-110SA1-01 | SECTIONALISING DISCONNECT - BELLACORICK 110-BELLACORICK 110-110SA1 | 4 | 4 | 4 | Proposed | 04/11/2024 | 07/11/2024
TO-24-BK-110SA1-02 | SECTIONALISING DISCONNECT - BELLACORICK 110-BELLACORICK 110-110SA1 | 4 | 4 | 4 | Scheduled | 04/11/2024 | 07/11/2024
TO-24-BK-110SA2-01 | SECTIONALISING DISCONNECT - BELLACORICK 110-BELLACORICK 110-110SA2 | 4 | 4 | 4 | Proposed | 04/11/2024 | 07/11/2024
TO-24-BK-110SA2-04 | SECTIONALISING DISCONNECT - BELLACORICK 110-BELLACORICK 110-110SA2 | 4 | 4 |  | Scheduled | 04/11/2024 | 07/11/2024
TO-24-BK-MOY-1-01 | 110kV FEEDER - BELLACORICK 110-MOY 110-1 | 5 | 5 | 5 | Proposed | 04/11/2024 | 08/11/2024
TO-24-BK-MOY-1-02 | 110kV FEEDER - BELLACORICK 110-MOY 110-1 | 4 | 4 | 4 | Proposed | 04/11/2024 | 07/11/2024
TO-24-BK-MOY-1-04 | 110kV FEEDER - BELLACORICK 110-MOY 110-1 | 9 | 7 | 7 | Scheduled | 04/11/2024 | 12/11/2024
TO-24-BK-T141-01 | DISTRIBUTION TRANSFORMER - BELLACORICK 110-BELLACORICK 38-T141 | 4 | 4 | 4 | Reference (Proposed) | 04/11/2024 | 07/11/2024
TO-24-BK-T141-02 | DISTRIBUTION TRANSFORMER - BELLACORICK 110-BELLACORICK 38-T141 | 4 | 4 | 4 | Reference | 04/11/2024 | 07/11/2024
TO-24-SLI-110SA1-2CB-06 | COUPLER/SECTIONALISING CB - SLIGO 110-SLIGO 110-110SA1-2CB | 5 | 5 | 5 | Proposed | 04/11/2024 | 08/11/2024
TO-24-SLI-T142-03 | DISTRIBUTION TRANSFORMER - SLIGO 110-SLIGO 38-T142 | 5 | 5 | 5 | Reference (Proposed) | 04/11/2024 | 08/11/2024
TO-24-CSH-GAL GIS-4-02 | 110kV FEEDER - CASHLA 110-GALWAY GIS 110-4 | 4 | 4 | 4 | Scheduled | 05/11/2024 | 08/11/2024
TO-24-CSH-ENN-1-01 | 110kV FEEDER - CASHLA 110-ENNIS 110-1 | 8 | 6 |  | Scheduled | 11/11/2024 | 18/11/2024
TO-24-110 kV A2 @ CSH-02 | BUSBAR SECTION - CASHLA 110-CASHLA 110-110A2 | 2 | 2 | 2 | Proposed | 12/11/2024 | 13/11/2024
TO-24-110 kV B2 @ CSH-02 | BUSBAR SECTION - CASHLA 110-CASHLA 110-110B2 | 2 | 2 | 2 | Proposed | 12/11/2024 | 13/11/2024
TO-24-CSH-DLT-1-01 | 110kV FEEDER - CASHLA 110-DALTON 110-1 | 10 | 8 | 9 | Scheduled | 18/11/2024 | 27/11/2024
TO-24-110 kV A2 @ FLA-02 | BUSBAR SECTION - FLAGFORD 110-FLAGFORD 110-110A2 | 4 | 2 |  | Scheduled | 22/11/2024 | 25/11/2024
TO-24-110 kV B2 @ FLA-02 | BUSBAR SECTION - FLAGFORD 110-FLAGFORD 110-110B2 | 4 | 2 |  | Scheduled | 22/11/2024 | 25/11/2024
TO-24-FLA-T2102-02 | TRANSFORMER - FLAGFORD 220-FLAGFORD 110-T2102 | 1 | 1 | 1 | Scheduled | 25/11/2024 | 25/11/2024
TO-24-110 kV A3 @ GAL GIS-02 | BUSBAR SECTION - GALWAY GIS 110-GALWAY GIS 110-110A3 | 9 | 7 | 7 | Proposed | 05/12/2024 | 13/12/2024
TO-24-110 kV B3 @ GAL GIS-03 | BUSBAR SECTION - GALWAY GIS 110-GALWAY GIS 110-110B3 | 9 | 7 | 7 | Proposed | 05/12/2024 | 13/12/2024
TO-24-GAL GIS-110K3-05 | COUPLER/SECTIONALISING CB - GALWAY GIS 110-GALWAY GIS 110-110K3 | 9 | 7 | 7 | Proposed | 05/12/2024 | 13/12/2024
TO-24-GAL GIS-110SA1-3CB-07 | COUPLER/SECTIONALISING CB - GALWAY GIS 110-GALWAY GIS 110-110SA1-3CB | 9 | 7 | 7 | Proposed | 05/12/2024 | 13/12/2024
TO-24-GAL GIS-110SB1-3CB-07 | COUPLER/SECTIONALISING CB - GALWAY GIS 110-GALWAY GIS 110-110SB1-3CB | 9 | 7 | 7 | Proposed | 05/12/2024 | 13/12/2024
TO-24-CSH-GAL GIS-1-04 | 110kV FEEDER - CASHLA 110-GALWAY GIS 110-1 | 2 | 2 | 2 | Proposed | 12/12/2024 | 13/12/2024

## GEN_NorthEast
Outage ID | Feeder ID | Calendar Day Duration | Working Day Duration | Work Days | Outage Status | Start | Finish
TO-24-110 kV A1 @ SH-01 | BUSBAR SECTION - SHANNONBRIDGE 110-SHANNONBRIDGE 110-110A1 | 23 | 17 | 17 | Scheduled | 02/01/2024 | 24/01/2024
TO-24-110 kV B1 @ SH-01 | BUSBAR SECTION - SHANNONBRIDGE 110-SHANNONBRIDGE 110-110B1 | 23 | 17 | 17 | Scheduled | 02/01/2024 | 24/01/2024
TO-24-MLC-110SA1-01 | SECTIONALISING DISCONNECT - MOUNTLUCAS 110-MOUNTLUCAS 110-110SA1 | 7 | 5 | 5 | Scheduled | 03/01/2024 | 09/01/2024
TO-24-MLC-110SA2-01 | SECTIONALISING DISCONNECT - MOUNTLUCAS 110-MOUNTLUCAS 110-110SA2 | 7 | 5 | 5 | Scheduled | 03/01/2024 | 09/01/2024
TO-24-MLC-TSB-1-01 | 110kV FEEDER - MOUNTLUCAS 110-THORNSBERRY 110-1 | 7 | 5 | 5 | Scheduled | 03/01/2024 | 09/01/2024
TO-24-110 kV A1 @ LOU-02 | BUSBAR SECTION - LOUTH 110-LOUTH 110-110A1 | 12 | 10 | 10 | Scheduled | 08/01/2024 | 19/01/2024
TO-24-110 kV B1 @ LOU-02 | BUSBAR SECTION - LOUTH 110-LOUTH 110-110B1 | 12 | 10 | 10 | Scheduled | 08/01/2024 | 19/01/2024
TO-24-DER-TSB-1-01 | 110kV FEEDER - DERRYIRON 110-THORNSBERRY 110-1 | 5 | 5 | 5 | Scheduled | 15/01/2024 | 19/01/2024
TO-24-220 kV A2 @ SH-01 | BUSBAR SECTION - SHANNONBRIDGE 220-SHANNONBRIDGE 220-220A2 | 89 | 61 |  | Scheduled | 15/01/2024 | 12/04/2024
TO-24-220 kV B2 @ SH-01 | BUSBAR SECTION - SHANNONBRIDGE 220-SHANNONBRIDGE 220-220B2 | 89 | 61 |  | Scheduled | 15/01/2024 | 12/04/2024
TO-24-AGL-SH-1-05 | 110kV FEEDER - AGANNYGAL 110-SHANNONBRIDGE 110-1 | 2 | 2 | 2 | Scheduled | 25/01/2024 | 26/01/2024
TO-24-110 kV A2 @ SH-01 | BUSBAR SECTION - SHANNONBRIDGE 110-SHANNONBRIDGE 110-110A2 | 2 | 2 | 2 | Scheduled | 25/01/2024 | 26/01/2024
TO-24-110 kV B2 @ SH-01 | BUSBAR SECTION - SHANNONBRIDGE 110-SHANNONBRIDGE 110-110B2 | 2 | 2 | 2 | Scheduled | 25/01/2024 | 26/01/2024
TO-24-DER-KIN-1-01 | 110kV FEEDER - DERRYIRON 110-KINNEGAD 110-1 | 5 | 5 | 5 | Scheduled | 29/01/2024 | 02/02/2024
TO-24-DER-T1/T2-01 | GENERATOR TRANSFORMER - DERRYIRON 110-RHODE 110-T1/T2 | 5 | 5 | 5 | Scheduled | 29/01/2024 | 02/02/2024
TO-24-OBE-PLA-1-01 | 110kV FEEDER - OLDBRIDGE 110-PLATIN 110-1 | 5 | 4 | 4 | Scheduled | 30/01/2024 | 03/02/2024
TO-24-PLA-110SA1-02 | SECTIONALISING DISCONNECT - PLATIN 110-PLATIN 110-110SA1 | 5 | 4 | 4 | Scheduled | 30/01/2024 | 03/02/2024
TO-24-PLA-110SA2-02 | SECTIONALISING DISCONNECT - PLATIN 110-PLATIN 110-110SA2 | 5 | 4 | 4 | Scheduled | 30/01/2024 | 03/02/2024
TO-24-PLA-T101/2/3/4-01 | TSO CUSTOMER TRANSFORMER - PLATIN 110-PLATIN 10-T101/2/3/4 | 72 | 48 | 48 | Scheduled | 30/01/2024 | 10/04/2024
TO-24-DRY-LOU-1-03 | 110kV FEEDER - DRYBRIDGE 110-LOUTH 110-1 | 12 | 9 |  | Scheduled | 05/02/2024 | 16/02/2024
TO-24-110 kV A1 @ LOU-04 | BUSBAR SECTION - LOUTH 110-LOUTH 110-110A1 | 12 | 9 | 9 | Scheduled | 05/02/2024 | 16/02/2024
TO-24-110 kV B1 @ LOU-03 | BUSBAR SECTION - LOUTH 110-LOUTH 110-110B1 | 12 | 9 |  | Scheduled | 05/02/2024 | 16/02/2024
TO-24-LOU-RRU-1-03 | 110kV FEEDER - LOUTH 110-RATRUSSAN 110-1 | 12 | 9 | 9 | Scheduled | 05/02/2024 | 16/02/2024
TO-24-DER-TSB-1-02 | 110kV FEEDER - DERRYIRON 110-THORNSBERRY 110-1 | 18 | 14 |  | Scheduled | 06/02/2024 | 23/02/2024
TO-24-IKE,T-SH-1-03 | 110kV FEEDER - IKERRIN tee-SHANNONBRIDGE 110-1 | 3 | 3 | 3 | Scheduled | 06/02/2024 | 08/02/2024
TO-24-110 kV B1 @ SH-02 | BUSBAR SECTION - SHANNONBRIDGE 110-SHANNONBRIDGE 110-110B1 | 3 | 3 |  | Scheduled | 06/02/2024 | 08/02/2024
TO-24-SH-T2101-01 | TRANSFORMER - SHANNONBRIDGE 220-SHANNONBRIDGE 110-T2101 | 1 | 1 |  | Scheduled | 08/02/2024 | 08/02/2024
TO-24-ARV-SKL-1-02 | 110kV FEEDER - ARVA 110-SHANKILL 110-1 | 75 | 50 | 50 | Scheduled | 09/02/2024 | 23/04/2024
TO-24-110 kV A1 @ ATH-01 | BUSBAR SECTION - ATHLONE 110-ATHLONE 110-110A1 | 2 | 2 | 2 | Proposed | 14/02/2024 | 15/02/2024
TO-24-CLN-LA-1-01 | 110kV FEEDER - CLOON 110-LANESBORO 110-1 | 12 | 10 | 10 | Scheduled | 19/02/2024 | 01/03/2024
TO-24-IKE,T-SH-1-04 | 110kV FEEDER - IKERRIN tee-SHANNONBRIDGE 110-1 | 4 | 4 | 4 | Scheduled | 19/02/2024 | 22/02/2024
TO-24-110 kV A1 @ SH-02 | BUSBAR SECTION - SHANNONBRIDGE 110-SHANNONBRIDGE 110-110A1 | 5 | 5 | 5 | Scheduled | 19/02/2024 | 23/02/2024
TO-24-TSB-110SA1-01 | SECTIONALISING DISCONNECT - THORNSBERRY 110-THORNSBERRY 110-110SA1 | 3 | 3 |  | Scheduled | 20/02/2024 | 22/02/2024
TO-24-TSB-110SA2-01 | SECTIONALISING DISCONNECT - THORNSBERRY 110-THORNSBERRY 110-110SA2 | 3 | 3 |  | Scheduled | 20/02/2024 | 22/02/2024
TO-24-TSB-T142-01 | DISTRIBUTION TRANSFORMER - THORNSBERRY 110-THORNSBERRY 38-T142 | 3 | 3 |  | Reference | 20/02/2024 | 22/02/2024
TO-24-SH-T2101-05 | TRANSFORMER - SHANNONBRIDGE 220-SHANNONBRIDGE 110-T2101 | 1 | 1 | 1 | Scheduled | 23/02/2024 | 23/02/2024
TO-24-ATH-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - ATHLONE 110-ATHLONE 110-110SA1-2CB | 2 | 2 | 2 | Scheduled | 26/02/2024 | 27/02/2024
TO-24-ATH-CAP3-02 | CAPACITOR/SVC/REACTOR - ATHLONE 110-ATHLONE 110-CAP3 | 2 | 2 | 2 | Scheduled | 26/02/2024 | 27/02/2024
TO-24-ATH-LA-1-01 | 110kV FEEDER - ATHLONE 110-LANESBORO 110-1 | 2 | 2 | 2 | Scheduled | 26/02/2024 | 27/02/2024
TO-24-ATH-T141-01 | DISTRIBUTION TRANSFORMER - ATHLONE 110-ATHLONE 38-T141 | 2 | 2 | 2 | Reference | 26/02/2024 | 27/02/2024
TO-24-220 kV B1/B2 @ LOU-01 | BUSBAR SECTION - LOUTH 220-LOUTH 220-220B1-B2 | 73 | 49 |  | Scheduled | 26/02/2024 | 08/05/2024
TO-24-LOU-220K1-2-01 | COUPLER/SECTIONALISING CB - LOUTH 220-LOUTH 220-220K1-2 | 73 | 49 |  | Scheduled | 26/02/2024 | 08/05/2024
TO-24-OST-WOO-1-01 | 400kV FEEDER - OLDSTREET 400-WOODLAND 400-1 | 5 | 5 | 5 | Scheduled | 26/02/2024 | 01/03/2024
TO-24-ATH-110SA1-2CB-04 | COUPLER/SECTIONALISING CB - ATHLONE 110-ATHLONE 110-110SA1-2CB | 2 | 2 | 2 | Scheduled | 29/02/2024 | 01/03/2024
TO-24-ATH-CAP3-05 | CAPACITOR/SVC/REACTOR - ATHLONE 110-ATHLONE 110-CAP3 | 2 | 2 | 2 | Scheduled | 29/02/2024 | 01/03/2024
TO-24-ATH-LA-1-04 | 110kV FEEDER - ATHLONE 110-LANESBORO 110-1 | 2 | 2 | 2 | Scheduled | 29/02/2024 | 01/03/2024
TO-24-ATH-T141-02 | DISTRIBUTION TRANSFORMER - ATHLONE 110-ATHLONE 38-T141 | 2 | 2 | 2 | Reference | 29/02/2024 | 01/03/2024
TO-24-AGL-110SA1-01 | SECTIONALISING DISCONNECT - AGANNYGAL 110-AGANNYGAL 110-110SA1 | 22 | 15 |  | Scheduled | 04/03/2024 | 25/03/2024
TO-24-AGL-110SA2-01 | SECTIONALISING DISCONNECT - AGANNYGAL 110-AGANNYGAL 110-110SA2 | 22 | 15 |  | Scheduled | 04/03/2024 | 25/03/2024
TO-24-AGL-DYN-1-01 | 110kV FEEDER - AGANNYGAL 110-DERRYBRIEN 110-1 | 22 | 15 |  | Scheduled | 04/03/2024 | 25/03/2024
TO-24-AGL-ENN-1-01 | 110kV FEEDER - AGANNYGAL 110-ENNIS 110-1 | 22 | 15 | 15 | Scheduled | 04/03/2024 | 25/03/2024
TO-24-AGL-SH-1-01 | 110kV FEEDER - AGANNYGAL 110-SHANNONBRIDGE 110-1 | 22 | 15 | 15 | Scheduled | 04/03/2024 | 25/03/2024
TO-24-FLA-SLB-1-04 | 110kV FEEDER - FLAGFORD 110-SLIABH BAWN 110-1 | 47 | 32 | 32 | Scheduled | 04/03/2024 | 19/04/2024
TO-24-DER-110SA1-01 | SECTIONALISING DISCONNECT - DERRYIRON 110-DERRYIRON 110-110SA1 | 23 | 15 | 15 | Scheduled | 19/03/2024 | 10/04/2024
TO-24-DER-110SA2-01 | SECTIONALISING DISCONNECT - DERRYIRON 110-DERRYIRON 110-110SA2 | 23 | 15 | 15 | Scheduled | 19/03/2024 | 10/04/2024
TO-24-DER-KIN-1-02 | 110kV FEEDER - DERRYIRON 110-KINNEGAD 110-1 | 23 | 15 | 15 | Scheduled | 19/03/2024 | 10/04/2024
TO-24-DER-T1/T2-02 | GENERATOR TRANSFORMER - DERRYIRON 110-RHODE 110-T1/T2 | 23 | 15 | 15 | Scheduled | 19/03/2024 | 10/04/2024
TO-24-NAV-T141-01 | DISTRIBUTION TRANSFORMER - NAVAN 110-NAVAN 38-T141 | 81 | 55 |  | Reference | 19/03/2024 | 07/06/2024
TO-24-DEY-T134-02 | GENERATOR TRANSFORMER - DERRYCARNEY 110-DERRYCARNEY 33-T134 | 2 | 2 | 2 | Scheduled | 20/03/2024 | 21/03/2024
TO-24-110 kV A1 @ GOR-02 | BUSBAR SECTION - GORMAN 110-GORMAN 110-110A1 | 9 | 7 | 7 | Scheduled | 20/03/2024 | 28/03/2024
TO-24-110 kV B1 @ GOR-01 | BUSBAR SECTION - GORMAN 110-GORMAN 110-110B1 | 9 | 7 | 7 | Scheduled | 20/03/2024 | 28/03/2024
TO-24-110 kV A1 @ SH-03 | BUSBAR SECTION - SHANNONBRIDGE 110-SHANNONBRIDGE 110-110A1 | 2 | 2 |  | Scheduled | 21/03/2024 | 22/03/2024
TO-24-SH-T2101-02 | TRANSFORMER - SHANNONBRIDGE 220-SHANNONBRIDGE 110-T2101 | 2 | 2 |  | Scheduled | 21/03/2024 | 22/03/2024
TO-24-DAL,T-SH-1-02 | 110kV FEEDER - DALLOW tee-SHANNONBRIDGE 110-1 | 77 | 51 | 51 | Scheduled | 26/03/2024 | 10/06/2024
TO-24-OBE-PLA-1-02 | 110kV FEEDER - OLDBRIDGE 110-PLATIN 110-1 | 9 | 7 |  | Scheduled | 02/04/2024 | 10/04/2024
TO-24-PLA-110SA1-03 | SECTIONALISING DISCONNECT - PLATIN 110-PLATIN 110-110SA1 | 9 | 7 |  | Scheduled | 02/04/2024 | 10/04/2024
TO-24-PLA-110SA2-03 | SECTIONALISING DISCONNECT - PLATIN 110-PLATIN 110-110SA2 | 9 | 7 |  | Scheduled | 02/04/2024 | 10/04/2024
TO-24-GAR-110K1-01 | COUPLER/SECTIONALISING CB - GARBALLAGH 110-GARBALLAGH 110-110K1 | 1 | 1 | 1 | Scheduled | 03/04/2024 | 03/04/2024
TO-24-GAR-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - GARBALLAGH 110-GARBALLAGH 110-110SA1-2CB | 1 | 1 | 1 | Scheduled | 04/04/2024 | 04/04/2024
TO-24-GAR-110SB1-2CB-01 | COUPLER/SECTIONALISING CB - GARBALLAGH 110-GARBALLAGH 110-110SB1-2CB | 1 | 1 | 1 | Scheduled | 05/04/2024 | 05/04/2024
TO-24-110 kV A2 @ SLB-01 | BUSBAR SECTION - SLIABH BAWN 110-SLIABH BAWN 110-110A2 | 5 | 5 | 5 | Scheduled | 08/04/2024 | 12/04/2024
TO-24-110 kV B2 @ SLB-01 | BUSBAR SECTION - SLIABH BAWN 110-SLIABH BAWN 110-110B2 | 5 | 5 | 5 | Scheduled | 08/04/2024 | 12/04/2024
TO-24-GOR-220K1-2-01 | COUPLER/SECTIONALISING CB - GORMAN 220-GORMAN 220-220K1-2 | 1 | 1 | 1 | Scheduled | 12/04/2024 | 12/04/2024
TO-24-COR-PST-03 | TRANSFORMER - CORRACLASSY 110-ENNISKILLEN 110-PST | 19 | 15 | 15 | Scheduled | 15/04/2024 | 03/05/2024
TO-24-KLN-SH-1-02 | 220kV FEEDER - KILLONAN 220-SHANNONBRIDGE 220-1 | 2 | 2 |  | Scheduled | 15/04/2024 | 16/04/2024
TO-24-SH-220K1-2-02 | COUPLER/SECTIONALISING CB - SHANNONBRIDGE 220-SHANNONBRIDGE 220-220K1-2 | 2 | 2 |  | Scheduled | 17/04/2024 | 18/04/2024
TO-24-SH-110K1-2-02 | COUPLER/SECTIONALISING CB - SHANNONBRIDGE 110-SHANNONBRIDGE 110-110K1-2 | 4 | 2 | 2 | Scheduled | 19/04/2024 | 22/04/2024
TO-24-110 kV A1 @ ARV-01 | BUSBAR SECTION - ARVA 110-ARVA 110-110A1 | 1 | 1 | 1 | Scheduled | 23/04/2024 | 23/04/2024
TO-24-ARV-NAV-1-01 | 110kV FEEDER - ARVA 110-NAVAN 110-1 | 1 | 1 | 1 | Scheduled | 23/04/2024 | 23/04/2024
TO-24-SH-T2101-03 | TRANSFORMER - SHANNONBRIDGE 220-SHANNONBRIDGE 110-T2101 | 2 | 2 |  | Scheduled | 23/04/2024 | 24/04/2024
TO-24-110 kV A1 @ LOU-01 | BUSBAR SECTION - LOUTH 110-LOUTH 110-110A1 | 160 | 111 | 111 | Scheduled | 24/04/2024 | 30/09/2024
TO-24-110 kV B1 @ LOU-01 | BUSBAR SECTION - LOUTH 110-LOUTH 110-110B1 | 160 | 111 | 111 | Scheduled | 24/04/2024 | 30/09/2024
TO-24-LOU-RRU-1-01 | 110kV FEEDER - LOUTH 110-RATRUSSAN 110-1 | 156 | 109 | 109 | Scheduled | 24/04/2024 | 26/09/2024
TO-24-RRU-110SA1-03 | SECTIONALISING DISCONNECT - RATRUSSAN 110-RATRUSSAN 110-110SA1 | 29 | 20 |  | Scheduled | 24/04/2024 | 22/05/2024
TO-24-RRU-110SA2-03 | SECTIONALISING DISCONNECT - RATRUSSAN 110-RATRUSSAN 110-110SA2 | 29 | 20 |  | Scheduled | 24/04/2024 | 22/05/2024
TO-24-RRU-SKL-1-03 | 110kV FEEDER - RATRUSSAN 110-SHANKILL 110-1 | 29 | 20 |  | Scheduled | 24/04/2024 | 22/05/2024
TO-24-RRU-T121-03 | GENERATOR TRANSFORMER - RATRUSSAN 110-RATRUSSAN 20-T121 | 29 | 20 |  | Scheduled | 24/04/2024 | 22/05/2024
TO-24-RRU-T122-01 | GENERATOR TRANSFORMER - RATRUSSAN 110-RATRUSSAN 20-T122 | 29 | 20 |  | Scheduled | 24/04/2024 | 22/05/2024
TO-24-AGL-SH-1-02 | 110kV FEEDER - AGANNYGAL 110-SHANNONBRIDGE 110-1 | 2 | 2 |  | Scheduled | 25/04/2024 | 26/04/2024
TO-24-LOU-T2104-02 | TRANSFORMER - LOUTH 220-LOUTH 110-T2104 | 1 | 1 | 1 | Scheduled | 25/04/2024 | 25/04/2024
TO-24-110 kV A2 @ SH-03 | BUSBAR SECTION - SHANNONBRIDGE 110-SHANNONBRIDGE 110-110A2 | 14 | 9 | 9 | Scheduled | 26/04/2024 | 09/05/2024
TO-24-110 kV B2 @ SH-03 | BUSBAR SECTION - SHANNONBRIDGE 110-SHANNONBRIDGE 110-110B2 | 14 | 9 | 9 | Scheduled | 26/04/2024 | 09/05/2024
TO-24-ATH-LA-1-02 | 110kV FEEDER - ATHLONE 110-LANESBORO 110-1 | 18 | 13 | 13 | Scheduled | 30/04/2024 | 17/05/2024
TO-24-MAY-TSB-1-02 | 110kV FEEDER - MAYNOOTH 110-THORNSBERRY 110-1 | 120 | 83 | 83 | Scheduled | 02/05/2024 | 29/08/2024
TO-24-GOR-LOU-1-01 | 220kV FEEDER - GORMAN 220-LOUTH 220-1 | 1 | 1 |  | Scheduled | 08/05/2024 | 08/05/2024
TO-24-LIS-T131-01 | GENERATOR TRANSFORMER - LISDRUM 110-LISDRUM 33-T131 | 1 | 1 | 1 | Scheduled | 08/05/2024 | 08/05/2024
TO-24-BAL-DRY-1-05 | 110kV FEEDER - BALTRASNA 110-DRYBRIDGE 110-1 | 197 | 138 | 138 | Scheduled | 13/05/2024 | 25/11/2024
TO-24-110 kV A2 @ LOU-01 | BUSBAR SECTION - LOUTH 110-LOUTH 110-110A2 | 5 | 5 | 5 | Scheduled | 13/05/2024 | 17/05/2024
TO-24-110 kV B2 @ LOU-01 | BUSBAR SECTION - LOUTH 110-LOUTH 110-110B2 | 5 | 5 | 5 | Scheduled | 13/05/2024 | 17/05/2024
TO-24-LOU-MTH-1-01 | 110kV FEEDER - LOUTH 110-MEATH HILL 110-1 | 9 | 7 | 7 | Scheduled | 13/05/2024 | 21/05/2024
TO-24-LOU-MLN-1-01 | 110kV FEEDER - LOUTH 110-MULLAGHARLIN 110-1 | 146 | 102 | 102 | Scheduled | 15/05/2024 | 07/10/2024
TO-24-LIS-CAP2-01 | CAPACITOR/SVC/REACTOR - LISDRUM 110-LISDRUM 110-CAP2 | 4 | 4 | 4 | Scheduled | 21/05/2024 | 24/05/2024
TO-24-DEY-T134-03 | GENERATOR TRANSFORMER - DERRYCARNEY 110-DERRYCARNEY 33-T134 | 1 | 1 | 1 | Scheduled | 28/05/2024 | 28/05/2024
TO-24-MLC-T121-01 | GENERATOR TRANSFORMER - MOUNTLUCAS 110-MOUNTLUCAS 20-T121 | 1 | 1 | 1 | Scheduled | 29/05/2024 | 29/05/2024
TO-24-LOU-T2101-04 | TRANSFORMER - LOUTH 220-LOUTH 110-T2101 | 15 | 10 | 10 | Scheduled | 30/05/2024 | 13/06/2024
TO-24-ARV-NAV-1-04 | 110kV FEEDER - ARVA 110-NAVAN 110-1 | 2 | 0 |  | Scheduled | 01/06/2024 | 02/06/2024
TO-24-GOR-NAV-2-05 | 110kV FEEDER - GORMAN 110-NAVAN 110-2 | 2 | 0 |  | Scheduled | 01/06/2024 | 02/06/2024
TO-24-NAV-110SA1-2CB-04 | COUPLER/SECTIONALISING CB - NAVAN 110-NAVAN 110-110SA1-2CB | 2 | 0 |  | Scheduled | 01/06/2024 | 02/06/2024
TO-24-NAV-M/CAP1-03 | CAPACITOR/SVC/REACTOR - NAVAN 110-NAVAN 110-M/CAP1 | 2 | 0 |  | Scheduled | 01/06/2024 | 02/06/2024
TO-24-GOR-NAV-2-02 | 110kV FEEDER - GORMAN 110-NAVAN 110-2 | 77 | 54 | 54 | Scheduled | 04/06/2024 | 19/08/2024
TO-24-DAL,T-DAL-1-02 | 110kV FEEDER - DALLOW tee-DALLOW 110-1 | 6 | 4 | 4 | Scheduled | 05/06/2024 | 10/06/2024
TO-24-CLN-LA-1-02 | 110kV FEEDER - CLOON 110-LANESBORO 110-1 | 9 | 7 | 7 | Scheduled | 06/06/2024 | 14/06/2024
TO-24-SLB-T132-01 | GENERATOR TRANSFORMER - SLIABH BAWN 110-SLIABH BAWN 33-T132 | 3 | 3 | 3 | Scheduled | 12/06/2024 | 14/06/2024
TO-24-AGL-DYN-1-04 | 110kV FEEDER - AGANNYGAL 110-DERRYBRIEN 110-1 | 2 | 2 | 2 | Scheduled | 13/06/2024 | 14/06/2024
TO-24-ATH-SH-1-02 | 110kV FEEDER - ATHLONE 110-SHANNONBRIDGE 110-1 | 12 | 10 | 10 | Scheduled | 17/06/2024 | 28/06/2024
TO-24-110 kV A1 @ SH-05 | BUSBAR SECTION - SHANNONBRIDGE 110-SHANNONBRIDGE 110-110A1 | 12 | 10 | 10 | Scheduled | 17/06/2024 | 28/06/2024
TO-24-110 kV B1 @ SH-05 | BUSBAR SECTION - SHANNONBRIDGE 110-SHANNONBRIDGE 110-110B1 | 12 | 10 | 10 | Scheduled | 17/06/2024 | 28/06/2024
TO-24-GOR-T122-01 | GENERATOR TRANSFORMER - GORMAN 110-GORMAN 20-T122 | 2 | 2 | 2 | Proposed | 19/06/2024 | 20/06/2024
TO-24-TY-T2001/2-04 | GENERATOR TRANSFORMER - TYNAGH 220-TYNAGH G1/2-T2001/2 | 7 | 5 | 5 | Scheduled | 23/06/2024 | 29/06/2024
TO-24-OBE-T123-01 | TSO CUSTOMER TRANSFORMER - OLDBRIDGE 110-OLDBRIDGE 20-T123 | 2 | 2 | 2 | Scheduled | 24/06/2024 | 25/06/2024
TO-24-220 kV A1 @ SH-03 | BUSBAR SECTION - SHANNONBRIDGE 220-SHANNONBRIDGE 220-220A1 | 12 | 10 | 10 | Scheduled | 24/06/2024 | 05/07/2024
TO-24-220 kV A2 @ SH-02 | BUSBAR SECTION - SHANNONBRIDGE 220-SHANNONBRIDGE 220-220A2 | 12 | 10 | 10 | Scheduled | 24/06/2024 | 05/07/2024
TO-24-220 kV B1 @ SH-03 | BUSBAR SECTION - SHANNONBRIDGE 220-SHANNONBRIDGE 220-220B1 | 12 | 10 | 10 | Scheduled | 24/06/2024 | 05/07/2024
TO-24-220 kV B2 @ SH-03 | BUSBAR SECTION - SHANNONBRIDGE 220-SHANNONBRIDGE 220-220B2 | 12 | 10 | 10 | Scheduled | 24/06/2024 | 05/07/2024
TO-24-SH-220K1-2-01 | COUPLER/SECTIONALISING CB - SHANNONBRIDGE 220-SHANNONBRIDGE 220-220K1-2 | 12 | 10 | 10 | Scheduled | 24/06/2024 | 05/07/2024
TO-24-TY-T2001/2-02 | GENERATOR TRANSFORMER - TYNAGH 220-TYNAGH G1/2-T2001/2 | 1 | 1 | 1 | Scheduled | 26/06/2024 | 26/06/2024
TO-24-220 kV A2 @ LOU-01 | BUSBAR SECTION - LOUTH 220-LOUTH 220-220A2 | 12 | 10 | 10 | Scheduled | 01/07/2024 | 12/07/2024
TO-24-220 kV B2 @ LOU-01 | BUSBAR SECTION - LOUTH 220-LOUTH 220-220B2 | 12 | 10 | 10 | Scheduled | 01/07/2024 | 12/07/2024
TO-24-LOU-AT1-01 | TRANSFORMER - LOUTH 220-LOUTH 275-AT1 | 12 | 10 | 10 | Scheduled | 01/07/2024 | 12/07/2024
TO-24-LOU-AT3-02 | TRANSFORMER - LOUTH 220-LOUTH 275-AT3 | 12 | 10 | 10 | Scheduled | 01/07/2024 | 12/07/2024
TO-24-LOU-TAN-1-01 | 275kV FEEDER - LOUTH 275-TANDRAGEE 275-1 | 12 | 10 | 10 | Scheduled | 01/07/2024 | 12/07/2024
TO-24-CFN-SH-1-01 | 220kV FEEDER - CLONIFFEEN 220-SHANNONBRIDGE 220-1 | 2 | 2 | 2 | Scheduled | 08/07/2024 | 09/07/2024
TO-24-CFN-T232-01 | GENERATOR TRANSFORMER - CLONIFFEEN 220-CLONIFFEEN 33-T232 | 2 | 2 | 2 | Scheduled | 08/07/2024 | 09/07/2024
TO-24-KIN-T101-02 | TSO CUSTOMER TRANSFORMER - KINNEGAD 110-KINNEGAD 10-T101 | 12 | 10 | 10 | Scheduled | 15/07/2024 | 26/07/2024
TO-24-DER-TSB-1-05 | 110kV FEEDER - DERRYIRON 110-THORNSBERRY 110-1 | 3 | 3 |  | Scheduled | 17/07/2024 | 19/07/2024
TO-24-TSB-110SA1-02 | SECTIONALISING DISCONNECT - THORNSBERRY 110-THORNSBERRY 110-110SA1 | 3 | 3 | 3 | Scheduled | 17/07/2024 | 19/07/2024
TO-24-TSB-110SA2-02 | SECTIONALISING DISCONNECT - THORNSBERRY 110-THORNSBERRY 110-110SA2 | 3 | 3 | 3 | Scheduled | 17/07/2024 | 19/07/2024
TO-24-TSB-T142-02 | DISTRIBUTION TRANSFORMER - THORNSBERRY 110-THORNSBERRY 38-T142 | 3 | 3 | 3 | Reference | 17/07/2024 | 19/07/2024
TO-24-TSB-TEN-1-01 | 110kV FEEDER - THORNSBERRY 110-TIMAHOE 110-1 | 3 | 3 | 3 | Scheduled | 17/07/2024 | 19/07/2024
TO-24-OBE-T121-01 | TSO CUSTOMER TRANSFORMER - OLDBRIDGE 110-OLDBRIDGE 20-T121 | 2 | 2 | 2 | Scheduled | 18/07/2024 | 19/07/2024
TO-24-KIN-MUL-1-01 | 110kV FEEDER - KINNEGAD 110-MULLINGAR 110-1 | 2 | 0 | 0 | Scheduled | 20/07/2024 | 21/07/2024
TO-24-LA-MUL-1-02 | 110kV FEEDER - LANESBORO 110-MULLINGAR 110-1 | 2 | 0 | 0 | Scheduled | 20/07/2024 | 21/07/2024
TO-24-MUL-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - MULLINGAR 110-MULLINGAR 110-110SA1-2CB | 2 | 0 | 0 | Scheduled | 20/07/2024 | 21/07/2024
TO-24-MUL-T101-01 | DISTRIBUTION TRANSFORMER - MULLINGAR 110-MULLINGAR 10-T101 | 2 | 0 | 0 | Reference | 20/07/2024 | 21/07/2024
TO-24-MUL-T141-01 | DISTRIBUTION TRANSFORMER - MULLINGAR 110-MULLINGAR 38-T141 | 2 | 0 | 0 | Reference | 20/07/2024 | 21/07/2024
TO-24-ARV-NAV-1-05 | 110kV FEEDER - ARVA 110-NAVAN 110-1 | 1 | 1 | 1 | Scheduled | 22/07/2024 | 22/07/2024
TO-24-DEY-T132-01 | GENERATOR TRANSFORMER - DERRYCARNEY 110-DERRYCARNEY 33-T132 | 2 | 2 | 2 | Scheduled | 22/07/2024 | 23/07/2024
TO-24-GOR-NAV-2-06 | 110kV FEEDER - GORMAN 110-NAVAN 110-2 | 1 | 1 | 1 | Scheduled | 22/07/2024 | 22/07/2024
TO-24-LOU-AT2-01 | TRANSFORMER - LOUTH 220-LOUTH 275-AT2 | 5 | 5 | 5 | Scheduled | 22/07/2024 | 26/07/2024
TO-24-LOU-TAN-2-01 | 275kV FEEDER - LOUTH 275-TANDRAGEE 275-2 | 5 | 5 | 5 | Scheduled | 22/07/2024 | 26/07/2024
TO-24-NAV-110SA1-2CB-03 | COUPLER/SECTIONALISING CB - NAVAN 110-NAVAN 110-110SA1-2CB | 1 | 1 | 1 | Scheduled | 22/07/2024 | 22/07/2024
TO-24-NAV-M/CAP1-02 | CAPACITOR/SVC/REACTOR - NAVAN 110-NAVAN 110-M/CAP1 | 1 | 1 | 1 | Scheduled | 22/07/2024 | 22/07/2024
TO-24-NAV-T141-03 | DISTRIBUTION TRANSFORMER - NAVAN 110-NAVAN 38-T141 | 1 | 1 | 1 | Reference | 22/07/2024 | 22/07/2024
TO-24-GOR-MTH-1-03 | 110kV FEEDER - GORMAN 110-MEATH HILL 110-1 | 3 | 3 | 3 | Scheduled | 30/07/2024 | 01/08/2024
TO-24-PLA-T101/2/3/4-05 | TSO CUSTOMER TRANSFORMER - PLATIN 110-PLATIN 10-T101/2/3/4 | 9 | 6 | 6 | Scheduled | 31/07/2024 | 08/08/2024
TO-24-TSB-TEN-1-03 | 110kV FEEDER - THORNSBERRY 110-TIMAHOE 110-1 | 9 | 6 | 6 | Scheduled | 01/08/2024 | 09/08/2024
TO-24-MLN-T124-02 | TSO CUSTOMER TRANSFORMER - MULLAGHARLIN 110-MULLAGHARLIN 20-T124 | 2 | 2 | 2 | Scheduled | 06/08/2024 | 07/08/2024
TO-24-MLN-T123-03 | TSO CUSTOMER TRANSFORMER - MULLAGHARLIN 110-MULLAGHARLIN 20-T123 | 2 | 2 | 2 | Scheduled | 08/08/2024 | 09/08/2024
TO-24-GAR-T131-02 | GENERATOR TRANSFORMER - GARBALLAGH 110-GARBALLAGH 33-T131 | 1 | 1 | 1 | Scheduled | 09/08/2024 | 09/08/2024
TO-24-DRY-LOU-1-01 | 110kV FEEDER - DRYBRIDGE 110-LOUTH 110-1 | 5 | 5 | 5 | Scheduled | 12/08/2024 | 16/08/2024
TO-24-LOU-110K1-2-01 | COUPLER/SECTIONALISING CB - LOUTH 110-LOUTH 110-110K1-2 | 5 | 5 |  | Scheduled | 12/08/2024 | 16/08/2024
TO-24-LOU-CAP1-03 | CAPACITOR/SVC/REACTOR - LOUTH 110-LOUTH 110-CAP1 | 5 | 5 | 5 | Scheduled | 12/08/2024 | 16/08/2024
TO-24-LOU-T2101-01 | TRANSFORMER - LOUTH 220-LOUTH 110-T2101 | 5 | 5 |  | Scheduled | 12/08/2024 | 16/08/2024
TO-24-LOU-T2103-01 | TRANSFORMER - LOUTH 220-LOUTH 110-T2103 | 5 | 5 |  | Scheduled | 12/08/2024 | 16/08/2024
TO-24-GAR-T131-03 | GENERATOR TRANSFORMER - GARBALLAGH 110-GARBALLAGH 33-T131 | 1 | 1 | 1 | Scheduled | 15/08/2024 | 15/08/2024
TO-24-110 kV A1 @ ARV-02 | BUSBAR SECTION - ARVA 110-ARVA 110-110A1 | 5 | 5 | 5 | Scheduled | 19/08/2024 | 23/08/2024
TO-24-110 kV A2 @ ARV-01 | BUSBAR SECTION - ARVA 110-ARVA 110-110A2 | 5 | 5 | 5 | Scheduled | 19/08/2024 | 23/08/2024
TO-24-110 kV B1 @ ARV-01 | BUSBAR SECTION - ARVA 110-ARVA 110-110B1 | 5 | 5 | 5 | Scheduled | 19/08/2024 | 23/08/2024
TO-24-110 kV B2 @ ARV-01 | BUSBAR SECTION - ARVA 110-ARVA 110-110B2 | 5 | 5 | 5 | Scheduled | 19/08/2024 | 23/08/2024
TO-24-ARV-110K1-2-01 | COUPLER/SECTIONALISING CB - ARVA 110-ARVA 110-110K1-2 | 5 | 5 | 5 | Scheduled | 19/08/2024 | 23/08/2024
TO-24-110 kV A2 @ GOR-01 | BUSBAR SECTION - GORMAN 110-GORMAN 110-110A2 | 1 | 1 | 1 | Scheduled | 19/08/2024 | 19/08/2024
TO-24-GOR-MTH-1-01 | 110kV FEEDER - GORMAN 110-MEATH HILL 110-1 | 1 | 1 | 1 | Scheduled | 19/08/2024 | 19/08/2024
TO-24-DAL,T-DAL-1-08 | 110kV FEEDER - DALLOW tee-DALLOW 110-1 | 16 | 12 | 12 | Scheduled | 20/08/2024 | 04/09/2024
TO-24-DAL,T-SH-1-10 | 110kV FEEDER - DALLOW tee-SHANNONBRIDGE 110-1 | 16 | 12 | 12 | Scheduled | 20/08/2024 | 04/09/2024
TO-24-GOR-NAV-1-01 | 110kV FEEDER - GORMAN 110-NAVAN 110-1 | 70 | 49 | 49 | Scheduled | 20/08/2024 | 28/10/2024
TO-24-110 kV A2 @ SH-05 | BUSBAR SECTION - SHANNONBRIDGE 110-SHANNONBRIDGE 110-110A2 | 1 | 1 | 1 | Scheduled | 20/08/2024 | 20/08/2024
TO-24-110 kV B2 @ SH-05 | BUSBAR SECTION - SHANNONBRIDGE 110-SHANNONBRIDGE 110-110B2 | 1 | 1 | 1 | Scheduled | 20/08/2024 | 20/08/2024
TO-24-CF-COR-1-01 | 110kV FEEDER - CATHALEENS FALL 110-CORRACLASSY 110-1 | 12 | 10 |  | Scheduled | 26/08/2024 | 06/09/2024
TO-24-COR-PST-02 | TRANSFORMER - CORRACLASSY 110-ENNISKILLEN 110-PST | 12 | 10 |  | Scheduled | 26/08/2024 | 06/09/2024
TO-24-COR-GWE-1-03 | 110kV FEEDER - CORRACLASSY 110-GORTAWEE 110-1 | 12 | 10 |  | Scheduled | 26/08/2024 | 06/09/2024
TO-24-MAY-TEN-1-01 | 110kV FEEDER - MAYNOOTH 110-TIMAHOE 110-1 | 34 | 24 | 24 | Scheduled | 29/08/2024 | 01/10/2024
TO-24-DRY-LOU-1-02 | 110kV FEEDER - DRYBRIDGE 110-LOUTH 110-1 | 3 | 3 | 3 | Scheduled | 02/09/2024 | 04/09/2024
TO-24-110 kV A2 @ LOU-03 | BUSBAR SECTION - LOUTH 110-LOUTH 110-110A2 | 1 | 1 | 1 | Scheduled | 09/09/2024 | 09/09/2024
TO-24-110 kV B2 @ LOU-03 | BUSBAR SECTION - LOUTH 110-LOUTH 110-110B2 | 1 | 1 | 1 | Scheduled | 09/09/2024 | 09/09/2024
TO-24-LOU-T2104-03 | TRANSFORMER - LOUTH 220-LOUTH 110-T2104 | 1 | 1 | 1 | Scheduled | 09/09/2024 | 09/09/2024
TO-24-SOM-T142-01 | DISTRIBUTION TRANSFORMER - SOMERSET 110-SOMERSET 38-T142 | 3 | 3 | 3 | Reference | 09/09/2024 | 11/09/2024
TO-24-SOM,T-CSH-1-01 | 110kV FEEDER - SOMERSET tee-CASHLA 110-1 | 66 | 47 | 47 | Proposed | 09/09/2024 | 13/11/2024
TO-24-SOM,T-SH-1-02 | 110kV FEEDER - SOMERSET tee-SHANNONBRIDGE 110-1 | 3 | 3 | 3 | Scheduled | 09/09/2024 | 11/09/2024
TO-24-SOM,T-SOM-1-01 | 110kV FEEDER - SOMERSET tee-SOMERSET 110-1 | 3 | 3 | 3 | Scheduled | 09/09/2024 | 11/09/2024
TO-24-LOU-AT3-01 | TRANSFORMER - LOUTH 220-LOUTH 275-AT3 | 3 | 3 |  | Scheduled | 10/09/2024 | 12/09/2024
TO-24-ATH-SH-1-04 | 110kV FEEDER - ATHLONE 110-SHANNONBRIDGE 110-1 | 1 | 0 | 0 | Scheduled | 14/09/2024 | 14/09/2024
TO-24-GAR-PLA-1-02 | 110kV FEEDER - GARBALLAGH 110-PLATIN 110-1 | 3 | 3 | 3 | Scheduled | 16/09/2024 | 18/09/2024
TO-24-TSB-TEN-1-05 | 110kV FEEDER - THORNSBERRY 110-TIMAHOE 110-1 | 5 | 5 | 5 | Scheduled | 16/09/2024 | 20/09/2024
TO-24-TEN-110K2-01 | COUPLER/SECTIONALISING CB - TIMAHOE 110-TIMAHOE 110-110K2 | 5 | 5 | 5 | Scheduled | 16/09/2024 | 20/09/2024
TO-24-TEN-T132-01 | GENERATOR TRANSFORMER - TIMAHOE 110-TIMAHOE 33-T132 | 5 | 5 | 5 | Scheduled | 16/09/2024 | 20/09/2024
TO-24-110 kV A2 @ LOU-04 | BUSBAR SECTION - LOUTH 110-LOUTH 110-110A2 | 2 | 2 | 2 | Scheduled | 17/09/2024 | 18/09/2024
TO-24-110 kV B2 @ LOU-04 | BUSBAR SECTION - LOUTH 110-LOUTH 110-110B2 | 2 | 2 | 2 | Scheduled | 17/09/2024 | 18/09/2024
TO-24-LOU-T2104-04 | TRANSFORMER - LOUTH 220-LOUTH 110-T2104 | 2 | 2 | 2 | Scheduled | 17/09/2024 | 18/09/2024
TO-24-LIS-T131-02 | GENERATOR TRANSFORMER - LISDRUM 110-LISDRUM 33-T131 | 2 | 2 | 2 | Scheduled | 23/09/2024 | 24/09/2024
TO-24-ATH-T142-01 | DISTRIBUTION TRANSFORMER - ATHLONE 110-ATHLONE 38-T142 | 2 | 2 | 2 | Reference | 01/10/2024 | 02/10/2024
TO-24-110 kV A1 @ LOU-07 | BUSBAR SECTION - LOUTH 110-LOUTH 110-110A1 | 1 | 1 | 1 | Scheduled | 02/10/2024 | 02/10/2024
TO-24-110 kV A2 @ LOU-05 | BUSBAR SECTION - LOUTH 110-LOUTH 110-110A2 | 1 | 1 | 1 | Scheduled | 02/10/2024 | 02/10/2024
TO-24-110 kV B1 @ LOU-07 | BUSBAR SECTION - LOUTH 110-LOUTH 110-110B1 | 1 | 1 | 1 | Scheduled | 02/10/2024 | 02/10/2024
TO-24-110 kV B2 @ LOU-05 | BUSBAR SECTION - LOUTH 110-LOUTH 110-110B2 | 1 | 1 | 1 | Scheduled | 02/10/2024 | 02/10/2024
TO-24-LOU-T2104-05 | TRANSFORMER - LOUTH 220-LOUTH 110-T2104 | 1 | 1 | 1 | Scheduled | 02/10/2024 | 02/10/2024
TO-24-LA-MUL-1-01 | 110kV FEEDER - LANESBORO 110-MULLINGAR 110-1 | 12 | 10 |  | Scheduled | 07/10/2024 | 18/10/2024
TO-24-LIS-110SA1-01 | SECTIONALISING DISCONNECT - LISDRUM 110-LISDRUM 110-110SA1 | 5 | 5 | 5 | Scheduled | 07/10/2024 | 11/10/2024
TO-24-LIS-110SA2-01 | SECTIONALISING DISCONNECT - LISDRUM 110-LISDRUM 110-110SA2 | 5 | 5 | 5 | Scheduled | 07/10/2024 | 11/10/2024
TO-24-LIS-CAP2-02 | CAPACITOR/SVC/REACTOR - LISDRUM 110-LISDRUM 110-CAP2 | 5 | 5 | 5 | Scheduled | 07/10/2024 | 11/10/2024
TO-24-LIS-LSA-1-01 | 110kV FEEDER - LISDRUM 110-LISLEA 110-1 | 5 | 5 | 5 | Scheduled | 07/10/2024 | 11/10/2024
TO-24-LIS-LSA-1-02 | 110kV FEEDER - LISDRUM 110-LISLEA 110-1 | 39 | 28 | 28 | Scheduled | 07/10/2024 | 14/11/2024
TO-24-LIS-T142-01 | DISTRIBUTION TRANSFORMER - LISDRUM 110-LISDRUM 38-T142 | 5 | 5 | 5 | Reference | 07/10/2024 | 11/10/2024
TO-24-110 kV A1 @ LOU-08 | BUSBAR SECTION - LOUTH 110-LOUTH 110-110A1 | 1 | 1 | 1 | Scheduled | 07/10/2024 | 07/10/2024
TO-24-110 kV A2 @ LOU-06 | BUSBAR SECTION - LOUTH 110-LOUTH 110-110A2 | 1 | 1 | 1 | Scheduled | 07/10/2024 | 07/10/2024
TO-24-110 kV B1 @ LOU-08 | BUSBAR SECTION - LOUTH 110-LOUTH 110-110B1 | 1 | 1 | 1 | Scheduled | 07/10/2024 | 07/10/2024
TO-24-110 kV B2 @ LOU-06 | BUSBAR SECTION - LOUTH 110-LOUTH 110-110B2 | 1 | 1 | 1 | Scheduled | 07/10/2024 | 07/10/2024
TO-24-LOU-T2104-06 | TRANSFORMER - LOUTH 220-LOUTH 110-T2104 | 1 | 1 | 1 | Scheduled | 07/10/2024 | 07/10/2024
TO-24-110 kV A2 @ LOU-08 | BUSBAR SECTION - LOUTH 110-LOUTH 110-110A2 | 25 | 18 | 18 | Scheduled | 08/10/2024 | 01/11/2024
TO-24-110 kV B2 @ LOU-08 | BUSBAR SECTION - LOUTH 110-LOUTH 110-110B2 | 25 | 18 | 18 | Scheduled | 08/10/2024 | 01/11/2024
TO-24-220 kV A2 @ LOU-03 | BUSBAR SECTION - LOUTH 220-LOUTH 220-220A2 | 25 | 18 | 18 | Scheduled | 08/10/2024 | 01/11/2024
TO-24-220 kV B2 @ LOU-03 | BUSBAR SECTION - LOUTH 220-LOUTH 220-220B2 | 25 | 18 | 18 | Scheduled | 08/10/2024 | 01/11/2024
TO-24-LOU-T2104-01 | TRANSFORMER - LOUTH 220-LOUTH 110-T2104 | 25 | 18 | 18 | Scheduled | 08/10/2024 | 01/11/2024
TO-24-DDK-110SA1-01 | SECTIONALISING DISCONNECT - DUNDALK 110-DUNDALK 110-110SA1 | 5 | 5 | 5 | Scheduled | 14/10/2024 | 18/10/2024
TO-24-DDK-110SA2-03 | SECTIONALISING DISCONNECT - DUNDALK 110-DUNDALK 110-110SA2 | 5 | 5 | 5 | Scheduled | 14/10/2024 | 18/10/2024
TO-24-DDK-MLN-1-03 | 110kV FEEDER - DUNDALK 110-MULLAGHARLIN 110-1 | 5 | 5 | 5 | Scheduled | 14/10/2024 | 18/10/2024
TO-24-DDK-T141-02 | DISTRIBUTION TRANSFORMER - DUNDALK 110-DUNDALK 38-T141 | 5 | 5 | 5 | Reference | 14/10/2024 | 18/10/2024
TO-24-GAR-PLA-1-04 | 110kV FEEDER - GARBALLAGH 110-PLATIN 110-1 | 5 | 5 | 5 | Scheduled | 14/10/2024 | 18/10/2024
TO-24-LSA-T131-01 | GENERATOR TRANSFORMER - LISLEA 110-LISLEA 33-T131 | 1 | 1 | 1 | Scheduled | 16/10/2024 | 16/10/2024
TO-24-KIN-T1/T2-03 | GENERATOR TRANSFORMER - KINNEGAD 110-RHODE 110-T1/T2 | 4 | 2 | 2 | Scheduled | 18/10/2024 | 21/10/2024
TO-24-RRU-T122-05 | GENERATOR TRANSFORMER - RATRUSSAN 110-RATRUSSAN 20-T122 | 1 | 1 | 1 | Scheduled | 18/10/2024 | 18/10/2024
TO-24-MLC-TSB-1-02 | 110kV FEEDER - MOUNTLUCAS 110-THORNSBERRY 110-1 | 22 | 15 | 15 | Proposed | 21/10/2024 | 11/11/2024
TO-24-OBE-PLA-1-04 | 110kV FEEDER - OLDBRIDGE 110-PLATIN 110-1 | 5 | 5 | 5 | Scheduled | 21/10/2024 | 25/10/2024
TO-24-KIN-MUL-1-02 | 110kV FEEDER - KINNEGAD 110-MULLINGAR 110-1 | 3 | 3 | 3 | Scheduled | 23/10/2024 | 25/10/2024
TO-24-110 kV A1 @ GOR-03 | BUSBAR SECTION - GORMAN 110-GORMAN 110-110A1 | 7 | 5 | 5 | Proposed | 29/10/2024 | 04/11/2024
TO-24-110 kV B1 @ GOR-02 | BUSBAR SECTION - GORMAN 110-GORMAN 110-110B1 | 7 | 5 | 5 | Proposed | 29/10/2024 | 04/11/2024
TO-24-GOR-NAV-3-02 | 110kV FEEDER - GORMAN 110-NAVAN 110-3 | 7 | 5 | 5 | Proposed | 29/10/2024 | 04/11/2024
TO-24-ATH-110SA1-2CB-05 | COUPLER/SECTIONALISING CB - ATHLONE 110-ATHLONE 110-110SA1-2CB | 5 | 5 | 5 | Scheduled | 04/11/2024 | 08/11/2024
TO-24-ATH-SH-1-06 | 110kV FEEDER - ATHLONE 110-SHANNONBRIDGE 110-1 | 5 | 5 | 5 | Scheduled | 04/11/2024 | 08/11/2024
TO-24-ATH-T142-02 | DISTRIBUTION TRANSFORMER - ATHLONE 110-ATHLONE 38-T142 | 5 | 5 | 5 | Reference | 04/11/2024 | 08/11/2024
TO-24-PLA-T105-02 | TSO CUSTOMER TRANSFORMER - PLATIN 110-PLATIN 10-T105 | 5 | 5 | 5 | Proposed | 04/11/2024 | 08/11/2024
TO-24-GAR-T131-01 | GENERATOR TRANSFORMER - GARBALLAGH 110-GARBALLAGH 33-T131 | 3 | 3 | 3 | Proposed | 05/11/2024 | 07/11/2024
TO-24-MLN-T123-01 | TSO CUSTOMER TRANSFORMER - MULLAGHARLIN 110-MULLAGHARLIN 20-T123 | 9 | 7 | 7 | Scheduled | 05/11/2024 | 13/11/2024
TO-24-110 kV A1 @ LOU-09 | BUSBAR SECTION - LOUTH 110-LOUTH 110-110A1 | 5 | 5 | 5 | Scheduled | 11/11/2024 | 15/11/2024
TO-24-110 kV A2 @ LOU-07 | BUSBAR SECTION - LOUTH 110-LOUTH 110-110A2 | 5 | 5 | 5 | Scheduled | 11/11/2024 | 15/11/2024
TO-24-110 kV B1 @ LOU-09 | BUSBAR SECTION - LOUTH 110-LOUTH 110-110B1 | 5 | 5 | 5 | Scheduled | 11/11/2024 | 15/11/2024
TO-24-110 kV B2 @ LOU-07 | BUSBAR SECTION - LOUTH 110-LOUTH 110-110B2 | 5 | 5 | 5 | Scheduled | 11/11/2024 | 15/11/2024
TO-24-LOU-110K1-2-06 | COUPLER/SECTIONALISING CB - LOUTH 110-LOUTH 110-110K1-2 | 5 | 5 | 5 | Scheduled | 11/11/2024 | 15/11/2024
TO-24-SOM-T142-02 | DISTRIBUTION TRANSFORMER - SOMERSET 110-SOMERSET 38-T142 | 3 | 3 | 3 | Reference (Proposed) | 11/11/2024 | 13/11/2024
TO-24-SOM,T-SH-1-03 | 110kV FEEDER - SOMERSET tee-SHANNONBRIDGE 110-1 | 3 | 3 | 3 | Proposed | 11/11/2024 | 13/11/2024
TO-24-SOM,T-SOM-1-02 | 110kV FEEDER - SOMERSET tee-SOMERSET 110-1 | 3 | 3 | 3 | Proposed | 11/11/2024 | 13/11/2024
TO-24-LIS-LOU-1-01 | 110kV FEEDER - LISDRUM 110-LOUTH 110-1 | Unknown | Unknown | 10 | Planned | November | November
TO-24-LIS-LOU-1-02 | 110kV FEEDER - LISDRUM 110-LOUTH 110-1 | 14 | 10 | 10 | Scheduled | 15/11/2024 | 28/11/2024
TO-24-LOU-110K1-2-02 | COUPLER/SECTIONALISING CB - LOUTH 110-LOUTH 110-110K1-2 | 14 | 10 | 10 | Proposed | 15/11/2024 | 28/11/2024
TO-24-BLU-MUL-1-02 | 110kV FEEDER - BLUNDELSTOWN 110-MULLINGAR 110-1 | 12 | 10 | 10 | Scheduled | 18/11/2024 | 29/11/2024
TO-24-BLU-MUL-1-06 | 110kV FEEDER - BLUNDELSTOWN 110-MULLINGAR 110-1 | 12 | 10 | 10 | Proposed | 18/11/2024 | 29/11/2024
TO-24-DDK-LOU-1-01 | 110kV FEEDER - DUNDALK 110-LOUTH 110-1 | Unknown | Unknown | 3 | Planned | November | November
TO-24-DDK-LOU-1-02 | 110kV FEEDER - DUNDALK 110-LOUTH 110-1 | 3 | 3 | 3 | Scheduled | 25/11/2024 | 27/11/2024
TO-24-MLN-T124-01 | TSO CUSTOMER TRANSFORMER - MULLAGHARLIN 110-MULLAGHARLIN 20-T124 | 1 | 1 | 1 | Scheduled | 26/11/2024 | 26/11/2024

## GEN_Dublin
Outage ID | Feeder ID | Calendar Day Duration | Working Day Duration | Work Days | Outage Status | Start | Finish
TO-24-220 kV A1 @ MAY-01 | BUSBAR SECTION - MAYNOOTH 220-MAYNOOTH 220-220A1 | 12 | 10 | 10 | Proposed | 08/01/2024 | 19/01/2024
TO-24-220 kV B1 @ MAY-01 | BUSBAR SECTION - MAYNOOTH 220-MAYNOOTH 220-220B1 | 12 | 10 | 10 | Proposed | 08/01/2024 | 19/01/2024
TO-24-220 kV A3 @ PB-01 | BUSBAR SECTION - POOLBEG 220-POOLBEG 220-220A3 | 12 | 10 | 10 | Scheduled | 08/01/2024 | 19/01/2024
TO-24-220 kV A4 @ PB-02 | BUSBAR SECTION - POOLBEG 220-POOLBEG 220-220A4 | 12 | 10 | 10 | Scheduled | 08/01/2024 | 19/01/2024
TO-24-220 kV B3 @ PB-01 | BUSBAR SECTION - POOLBEG 220-POOLBEG 220-220B3 | 12 | 10 | 10 | Scheduled | 08/01/2024 | 19/01/2024
TO-24-220 kV B4 @ PB-01 | BUSBAR SECTION - POOLBEG 220-POOLBEG 220-220B4 | 12 | 10 | 10 | Scheduled | 08/01/2024 | 19/01/2024
TO-24-PB-R223-4-01 | CAPACITOR/SVC/REACTOR - POOLBEG 220-POOLBEG 220-R223-4 | 12 | 10 | 10 | Scheduled | 08/01/2024 | 19/01/2024
TO-24-DER-MAY-1-02 | 110kV FEEDER - DERRYIRON 110-MAYNOOTH 110-1 | 5 | 5 | 5 | Scheduled | 15/01/2024 | 19/01/2024
TO-24-AUN-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - AUNGIERSTOWN 110-AUNGIERSTOWN 110-110SA1-2CB | 3 | 3 |  | Scheduled | 22/01/2024 | 24/01/2024
TO-24-AUN-T123-01 | TSO CUSTOMER TRANSFORMER - AUNGIERSTOWN 110-AUNGIERSTOWN 20-T123 | 2 | 2 |  | Scheduled | 22/01/2024 | 23/01/2024
TO-24-RYB GIS-T108-01 | TSO CUSTOMER TRANSFORMER - RYEBROOK GIS 110-RYEBROOK 10-T108 | 5 | 5 | 5 | Scheduled | 22/01/2024 | 26/01/2024
TO-24-AUN-T121-01 | TSO CUSTOMER TRANSFORMER - AUNGIERSTOWN 110-AUNGIERSTOWN 20-T121 | 1 | 1 |  | Scheduled | 24/01/2024 | 24/01/2024
TO-24-BAL-CDU-1-03 | 110kV FEEDER - BALTRASNA 110-CORDUFF 110-1 | 3 | 3 | 3 | Scheduled | 24/01/2024 | 26/01/2024
TO-24-BLU-CDU-1-03 | 110kV FEEDER - BLUNDELSTOWN 110-CORDUFF 110-1 | 3 | 3 | 3 | Scheduled | 24/01/2024 | 26/01/2024
TO-24-110 kV B2/B4 @ CDU-01 | BUSBAR SECTION - CORDUFF 110-CORDUFF 110-110B2-B4 | 3 | 3 | 3 | Scheduled | 24/01/2024 | 26/01/2024
TO-24-BAL-CDU-1-04 | 110kV FEEDER - BALTRASNA 110-CORDUFF 110-1 | 2 | 2 |  | Scheduled | 29/01/2024 | 30/01/2024
TO-24-220 kV A4 @ CKM GIS-01 | BUSBAR SECTION - CARRICKMINES GIS 220-CARRICKMINES GIS 220-220A4 | 3 | 3 | 3 | Scheduled | 29/01/2024 | 31/01/2024
TO-24-220 kV B4 @ CKM GIS-01 | BUSBAR SECTION - CARRICKMINES GIS 220-CARRICKMINES GIS 220-220B4 | 3 | 3 | 3 | Scheduled | 29/01/2024 | 31/01/2024
TO-24-CKM GIS-220K4-01 | COUPLER/SECTIONALISING CB - CARRICKMINES GIS 220-CARRICKMINES GIS 220-220K4 | 3 | 3 | 3 | Scheduled | 29/01/2024 | 31/01/2024
TO-24-CKM GIS-220SA2-4CB-01 | COUPLER/SECTIONALISING CB - CARRICKMINES GIS 220-CARRICKMINES GIS 220-22SA2-4CB | 3 | 3 | 3 | Scheduled | 29/01/2024 | 31/01/2024
TO-24-CKM GIS-220SB2-4CB-01 | COUPLER/SECTIONALISING CB - CARRICKMINES GIS 220-CARRICKMINES GIS 220-22SB2-4CB | 3 | 3 | 3 | Scheduled | 29/01/2024 | 31/01/2024
TO-24-CKM GIS-DSN-1-02 | 220kV FEEDER - CARRICKMINES GIS 220-DUNSTOWN 220-1 | 3 | 3 | 3 | Scheduled | 29/01/2024 | 31/01/2024
TO-24-CKM GIS-T2104-01 | TRANSFORMER - CARRICKMINES GIS 220-CARRICKMINES GIS 110-T2104 | 3 | 3 | 3 | Reference | 29/01/2024 | 31/01/2024
TO-24-CDU-110SB2-4-02 | SECTIONALISING DISCONNECT - CORDUFF 110-CORDUFF 110-110SB2-4 | 2 | 2 |  | Scheduled | 29/01/2024 | 30/01/2024
TO-24-CDU-MCE-1-03 | 110kV FEEDER - CORDUFF 110-MACETOWN 110-1 | 2 | 2 |  | Scheduled | 29/01/2024 | 30/01/2024
TO-24-WOO-220K1-2-02 | COUPLER/SECTIONALISING CB - WOODLAND 220-WOODLAND 220-220K1-2 | 2 | 2 | 2 | Scheduled | 31/01/2024 | 01/02/2024
TO-24-PB-T2007/8-01 | GENERATOR TRANSFORMER - POOLBEG 220-POOLBEG G7/8-T2007/8 | 3 | 2 | 2 | Scheduled | 01/02/2024 | 03/02/2024
TO-24-220 kV A1 @ CKM-01 | BUSBAR SECTION - CARRICKMINES 220-CARRICKMINES 220-220A1 | 5 | 4 | 4 | Scheduled | 06/02/2024 | 10/02/2024
TO-24-CKM-CKM GIS-1-01 | 220kV FEEDER - CARRICKMINES 220-CARRICKMINES GIS 220-1 | 5 | 4 | 4 | Scheduled | 06/02/2024 | 10/02/2024
TO-24-CKM-PB-1-02 | 220kV FEEDER - CARRICKMINES 220-POOLBEG 220-1 | 5 | 4 | 4 | Scheduled | 06/02/2024 | 10/02/2024
TO-24-CKM-PST2201-01 | TRANSFORMER - CARRICKMINES 220-CARRICKMINES 220-PST2201 | 5 | 4 | 4 | Scheduled | 06/02/2024 | 10/02/2024
TO-24-DER-MAY-1-03 | 110kV FEEDER - DERRYIRON 110-MAYNOOTH 110-1 | 18 | 14 |  | Scheduled | 06/02/2024 | 23/02/2024
TO-24-RYB GIS-T109-01 | TSO CUSTOMER TRANSFORMER - RYEBROOK GIS 110-RYEBROOK 10-T109 | 4 | 4 | 4 | Scheduled | 06/02/2024 | 09/02/2024
TO-24-BRT-CLE-4-01 | 220kV FEEDER - BRACETOWN 220-CLONEE 220-4 | 1 | 1 | 1 | Scheduled | 08/02/2024 | 08/02/2024
TO-24-BRT-T222-01 | TSO CUSTOMER TRANSFORMER - BRACETOWN 220-BRACETOWN 20-T222 | 38 | 27 | 27 | Scheduled | 12/02/2024 | 20/03/2024
TO-24-CKM GIS-T2103-01 | TRANSFORMER - CARRICKMINES GIS 220-CARRICKMINES GIS 110-T2103 | 5 | 5 | 5 | Reference | 12/02/2024 | 16/02/2024
TO-24-DND-T121-01 | TSO CUSTOMER TRANSFORMER - DARNDALE 110-DARNDALE 20-T121 | 324 | 223 | 223 | Scheduled | 12/02/2024 | 31/12/2024
TO-24-DSN-T4201-02 | TRANSFORMER - DUNSTOWN 400-DUNSTOWN 220-T4201 | 19 | 15 | 15 | Scheduled | 12/02/2024 | 01/03/2024
TO-24-GLN-T133-03 | GENERATOR TRANSFORMER - GALLANSTOWN 110-GALLANSTOWN 33-T133 | 26 | 20 | 20 | Scheduled | 12/02/2024 | 08/03/2024
TO-24-110 kV A4 @ CBT-02 | BUSBAR SECTION - CASTLEBAGOT 110-CASTLEBAGOT 110-110A4 | 5 | 5 | 5 | Scheduled | 19/02/2024 | 23/02/2024
TO-24-110 kV B4 @ CBT-02 | BUSBAR SECTION - CASTLEBAGOT 110-CASTLEBAGOT 110-110B4 | 5 | 5 | 5 | Scheduled | 19/02/2024 | 23/02/2024
TO-24-CBT-CKG-2-03 | 110kV FEEDER - CASTLEBAGOT 110-CORKAGH 110-2 | 5 | 5 | 5 | Scheduled | 19/02/2024 | 23/02/2024
TO-24-110 kV B2 @ MAY-03 | BUSBAR SECTION - MAYNOOTH 110-MAYNOOTH 110-110B2 | 3 | 3 |  | Scheduled | 20/02/2024 | 22/02/2024
TO-24-110 kV A1 @ CDU-01 | BUSBAR SECTION - CORDUFF 110-CORDUFF 110-110A1 | 4 | 4 | 4 | Scheduled | 26/02/2024 | 29/02/2024
TO-24-110 kV A2 @ CDU-01 | BUSBAR SECTION - CORDUFF 110-CORDUFF 110-110A2 | 4 | 4 | 4 | Scheduled | 26/02/2024 | 29/02/2024
TO-24-110 kV A3 @ CDU-01 | BUSBAR SECTION - CORDUFF 110-CORDUFF 110-110A3 | 4 | 4 | 4 | Scheduled | 26/02/2024 | 29/02/2024
TO-24-110 kV A4 @ CDU-01 | BUSBAR SECTION - CORDUFF 110-CORDUFF 110-110A4 | 4 | 4 | 4 | Scheduled | 26/02/2024 | 29/02/2024
TO-24-110 kV B1 @ CDU-01 | BUSBAR SECTION - CORDUFF 110-CORDUFF 110-110B1 | 4 | 4 | 4 | Scheduled | 26/02/2024 | 29/02/2024
TO-24-110 kV B2 @ CDU-01 | BUSBAR SECTION - CORDUFF 110-CORDUFF 110-110B2 | 4 | 4 | 4 | Scheduled | 26/02/2024 | 29/02/2024
TO-24-110 kV B3 @ CDU-01 | BUSBAR SECTION - CORDUFF 110-CORDUFF 110-110B3 | 4 | 4 | 4 | Scheduled | 26/02/2024 | 29/02/2024
TO-24-110 kV B4 @ CDU-01 | BUSBAR SECTION - CORDUFF 110-CORDUFF 110-110B4 | 4 | 4 | 4 | Scheduled | 26/02/2024 | 29/02/2024
TO-24-OST-WOO-1-01 | 400kV FEEDER - OLDSTREET 400-WOODLAND 400-1 | 5 | 5 | 5 | Scheduled | 26/02/2024 | 01/03/2024
TO-24-110 kV A2 @ CBT-01 | BUSBAR SECTION - CASTLEBAGOT 110-CASTLEBAGOT 110-110A2 | 2 | 2 | 2 | Scheduled | 27/02/2024 | 28/02/2024
TO-24-110 kV B2 @ CBT-01 | BUSBAR SECTION - CASTLEBAGOT 110-CASTLEBAGOT 110-110B2 | 2 | 2 | 2 | Scheduled | 27/02/2024 | 28/02/2024
TO-24-CBT-110SA1-2CB-02 | COUPLER/SECTIONALISING CB - CASTLEBAGOT 110-CASTLEBAGOT 110-110SA1-2CB | 2 | 2 | 2 | Scheduled | 27/02/2024 | 28/02/2024
TO-24-CBT-110SA2-4CB-02 | COUPLER/SECTIONALISING CB - CASTLEBAGOT 110-CASTLEBAGOT 110-110SA2-4CB | 2 | 2 | 2 | Scheduled | 27/02/2024 | 28/02/2024
TO-24-CBT-110SB1-2CB-02 | COUPLER/SECTIONALISING CB - CASTLEBAGOT 110-CASTLEBAGOT 110-110SB1-2CB | 2 | 2 | 2 | Scheduled | 27/02/2024 | 28/02/2024
TO-24-CBT-110SB2-4CB-02 | COUPLER/SECTIONALISING CB - CASTLEBAGOT 110-CASTLEBAGOT 110-110SB2-4CB | 2 | 2 | 2 | Scheduled | 27/02/2024 | 28/02/2024
TO-24-CBT-T2101-01 | TRANSFORMER - CASTLEBAGOT 220-CASTLEBAGOT 110-T2101 | 2 | 2 | 2 | Scheduled | 27/02/2024 | 28/02/2024
TO-24-110 kV A1 @ GLN-01 | BUSBAR SECTION - GALLANSTOWN 110-GALLANSTOWN 110-110A1 | 2 | 2 | 2 | Scheduled | 27/02/2024 | 28/02/2024
TO-24-GLN-110K1-02 | COUPLER/SECTIONALISING CB - GALLANSTOWN 110-GALLANSTOWN 110-110K1 | 2 | 2 | 2 | Scheduled | 27/02/2024 | 28/02/2024
TO-24-TH-T2001/2-03 | GENERATOR TRANSFORMER - TURLOUGH HILL 220-TURLOUGH HILL G1-T2001/2 | 1 | 0 | 0 | Scheduled | 03/03/2024 | 03/03/2024
TO-24-TH-T2003/4-02 | GENERATOR TRANSFORMER - TURLOUGH HILL 220-TURLOUGH HILL G1-T2003/4 | 4 | 3 | 3 | Scheduled | 03/03/2024 | 06/03/2024
TO-24-BAG-T103-01 | TSO CUSTOMER TRANSFORMER - BARNAGEERAGH 110-BARNAGEERAGH 11-T103 | 2 | 2 | 2 | Scheduled | 04/03/2024 | 05/03/2024
TO-24-110 kV A1 @ CBT-02 | BUSBAR SECTION - CASTLEBAGOT 110-CASTLEBAGOT 110-110A1 | 5 | 5 | 5 | Scheduled | 04/03/2024 | 08/03/2024
TO-24-110 kV B1 @ CBT-02 | BUSBAR SECTION - CASTLEBAGOT 110-CASTLEBAGOT 110-110B1 | 5 | 5 | 5 | Scheduled | 04/03/2024 | 08/03/2024
TO-24-CBT-110K1-04 | COUPLER/SECTIONALISING CB - CASTLEBAGOT 110-CASTLEBAGOT 110-110K1 | 5 | 5 | 5 | Scheduled | 04/03/2024 | 08/03/2024
TO-24-CBT-110SA1-2CB-04 | COUPLER/SECTIONALISING CB - CASTLEBAGOT 110-CASTLEBAGOT 110-110SA1-2CB | 5 | 5 | 5 | Scheduled | 04/03/2024 | 08/03/2024
TO-24-CBT-110SB1-2CB-04 | COUPLER/SECTIONALISING CB - CASTLEBAGOT 110-CASTLEBAGOT 110-110SB1-2CB | 5 | 5 | 5 | Scheduled | 04/03/2024 | 08/03/2024
TO-24-CBT-CKG-1-03 | 110kV FEEDER - CASTLEBAGOT 110-CORKAGH 110-1 | 5 | 5 | 5 | Scheduled | 04/03/2024 | 08/03/2024
TO-24-220 kV A1 @ DSN-01 | BUSBAR SECTION - DUNSTOWN 220-DUNSTOWN 220-220A1 | 12 | 10 | 10 | Scheduled | 04/03/2024 | 15/03/2024
TO-24-220 kV B1 @ DSN-01 | BUSBAR SECTION - DUNSTOWN 220-DUNSTOWN 220-220B1 | 12 | 10 | 10 | Scheduled | 04/03/2024 | 15/03/2024
TO-24-DSN-TH-1-01 | 220kV FEEDER - DUNSTOWN 220-TURLOUGH HILL 220-1 | 12 | 10 |  | Scheduled | 04/03/2024 | 15/03/2024
TO-24-PB-R2001-01 | CAPACITOR/SVC/REACTOR - POOLBEG 220-POOLBEG 220-R2001 | 5 | 5 | 5 | Scheduled | 04/03/2024 | 08/03/2024
TO-24-220 kV A1 @ TH-01 | BUSBAR SECTION - TURLOUGH HILL 220-TURLOUGH HILL 220-220A1 | 12 | 10 | 10 | Scheduled | 04/03/2024 | 15/03/2024
TO-24-220 kV B1 @ TH-01 | BUSBAR SECTION - TURLOUGH HILL 220-TURLOUGH HILL 220-220B1 | 12 | 10 | 10 | Scheduled | 04/03/2024 | 15/03/2024
TO-24-110 kV A1 @ GLN-02 | BUSBAR SECTION - GALLANSTOWN 110-GALLANSTOWN 110-110A1 | 1 | 1 | 1 | Scheduled | 06/03/2024 | 06/03/2024
TO-24-GLN-110K1-05 | COUPLER/SECTIONALISING CB - GALLANSTOWN 110-GALLANSTOWN 110-110K1 | 1 | 1 | 1 | Scheduled | 06/03/2024 | 06/03/2024
TO-24-GLN-T133-06 | GENERATOR TRANSFORMER - GALLANSTOWN 110-GALLANSTOWN 33-T133 | 1 | 1 | 1 | Scheduled | 06/03/2024 | 06/03/2024
TO-24-ISH-T2002/3-01 | GENERATOR TRANSFORMER - IRISHTOWN 220-IRISHTOWN G2/3-T2002/3 | 2 | 2 | 2 | Scheduled | 06/03/2024 | 07/03/2024
TO-24-TH-T2001/2-02 | GENERATOR TRANSFORMER - TURLOUGH HILL 220-TURLOUGH HILL G1-T2001/2 | 4 | 3 | 3 | Scheduled | 10/03/2024 | 13/03/2024
TO-24-220 kV A2 @ CBT-03 | BUSBAR SECTION - CASTLEBAGOT 220-CASTLEBAGOT 220-220A2 | 12 | 9 | 9 | Scheduled | 11/03/2024 | 22/03/2024
TO-24-220 kV B2 @ CBT-03 | BUSBAR SECTION - CASTLEBAGOT 220-CASTLEBAGOT 220-220B2 | 12 | 9 | 9 | Scheduled | 11/03/2024 | 22/03/2024
TO-24-CBT-220K2-04 | COUPLER/SECTIONALISING CB - CASTLEBAGOT 220-CASTLEBAGOT 220-220K2 | 12 | 9 | 9 | Scheduled | 11/03/2024 | 22/03/2024
TO-24-CBT-220SA1-2CB-03 | COUPLER/SECTIONALISING CB - CASTLEBAGOT 220-CASTLEBAGOT 220-220SA1-2CB | 12 | 9 | 9 | Scheduled | 11/03/2024 | 22/03/2024
TO-24-CBT-220SB1-2CB-04 | COUPLER/SECTIONALISING CB - CASTLEBAGOT 220-CASTLEBAGOT 220-220SB1-2CB | 12 | 9 | 9 | Scheduled | 11/03/2024 | 22/03/2024
TO-24-220 kV B2/B4 @ CDU-01 | BUSBAR SECTION - CORDUFF 220-CORDUFF 220-220B2-B4 | 5 | 5 | 5 | Scheduled | 11/03/2024 | 15/03/2024
TO-24-CDU-WOO-1-02 | 220kV FEEDER - CORDUFF 220-WOODLAND 220-1 | 5 | 5 | 5 | Scheduled | 11/03/2024 | 15/03/2024
TO-24-BAG-T101-01 | TSO CUSTOMER TRANSFORMER - BARNAGEERAGH 110-BARNAGEERAGH 11-T101 | 2 | 2 | 2 | Scheduled | 12/03/2024 | 13/03/2024
TO-24-110 kV A1 @ CBT-03 | BUSBAR SECTION - CASTLEBAGOT 110-CASTLEBAGOT 110-110A1 | 3 | 3 | 3 | Scheduled | 12/03/2024 | 14/03/2024
TO-24-110 kV A2 @ CBT-02 | BUSBAR SECTION - CASTLEBAGOT 110-CASTLEBAGOT 110-110A2 | 3 | 3 | 3 | Scheduled | 12/03/2024 | 14/03/2024
TO-24-CBT-110SA1-2CB-03 | COUPLER/SECTIONALISING CB - CASTLEBAGOT 110-CASTLEBAGOT 110-110SA1-2CB | 3 | 3 | 3 | Scheduled | 12/03/2024 | 14/03/2024
TO-24-CKM GIS-T2104-02 | TRANSFORMER - CARRICKMINES GIS 220-CARRICKMINES GIS 110-T2104 | 11 | 8 | 8 | Reference | 18/03/2024 | 28/03/2024
TO-24-KYT-MAY-1-01 | 220kV FEEDER - KELLYSTOWN 220-MAYNOOTH 220-1 | 10 | 8 | 8 | Scheduled | 19/03/2024 | 28/03/2024
TO-24-WOO-400K1-2-01 | COUPLER/SECTIONALISING CB - WOODLAND 400-WOODLAND 400-400K1-2 | 4 | 4 | 4 | Scheduled | 19/03/2024 | 22/03/2024
TO-24-220 kV A1 @ CDU-01 | BUSBAR SECTION - CORDUFF 220-CORDUFF 220-220A1 | 4 | 4 | 4 | Scheduled | 25/03/2024 | 28/03/2024
TO-24-220 kV A2 @ CDU-01 | BUSBAR SECTION - CORDUFF 220-CORDUFF 220-220A2 | 4 | 4 | 4 | Scheduled | 25/03/2024 | 28/03/2024
TO-24-220 kV A3 @ CDU-01 | BUSBAR SECTION - CORDUFF 220-CORDUFF 220-220A3 | 4 | 4 | 4 | Scheduled | 25/03/2024 | 28/03/2024
TO-24-220 kV A4 @ CDU-01 | BUSBAR SECTION - CORDUFF 220-CORDUFF 220-220A4 | 4 | 4 | 4 | Scheduled | 25/03/2024 | 28/03/2024
TO-24-220 kV B1 @ CDU-01 | BUSBAR SECTION - CORDUFF 220-CORDUFF 220-220B1 | 4 | 4 | 4 | Scheduled | 25/03/2024 | 28/03/2024
TO-24-220 kV B2 @ CDU-01 | BUSBAR SECTION - CORDUFF 220-CORDUFF 220-220B2 | 4 | 4 | 4 | Scheduled | 25/03/2024 | 28/03/2024
TO-24-220 kV B3 @ CDU-01 | BUSBAR SECTION - CORDUFF 220-CORDUFF 220-220B3 | 4 | 4 | 4 | Scheduled | 25/03/2024 | 28/03/2024
TO-24-220 kV B4 @ CDU-01 | BUSBAR SECTION - CORDUFF 220-CORDUFF 220-220B4 | 4 | 4 | 4 | Scheduled | 25/03/2024 | 28/03/2024
TO-24-CKM GIS-R2001-01 | CAPACITOR/SVC/REACTOR - CARRICKMINES GIS 220-CARRICKMINES GIS 220-R2001 | 18 | 12 |  | Scheduled | 26/03/2024 | 12/04/2024
TO-24-220 kV A2 @ CDU-03 | BUSBAR SECTION - CORDUFF 220-CORDUFF 220-220A2 | 25 | 19 | 19 | Scheduled | 02/04/2024 | 26/04/2024
TO-24-220 kV A4 @ CDU-02 | BUSBAR SECTION - CORDUFF 220-CORDUFF 220-220A4 | 11 | 9 | 9 | Scheduled | 02/04/2024 | 12/04/2024
TO-24-220 kV B2 @ CDU-03 | BUSBAR SECTION - CORDUFF 220-CORDUFF 220-220B2 | 25 | 19 | 19 | Scheduled | 02/04/2024 | 26/04/2024
TO-24-220 kV B4 @ CDU-02 | BUSBAR SECTION - CORDUFF 220-CORDUFF 220-220B4 | 11 | 9 | 9 | Scheduled | 02/04/2024 | 12/04/2024
TO-24-BLU-110K1-01 | COUPLER/SECTIONALISING CB - BLUNDELSTOWN 110-BLUNDELSTOWN 110-110K1 | 1 | 1 | 1 | Scheduled | 03/04/2024 | 03/04/2024
TO-24-CKM GIS-220SB1-3CB-01 | COUPLER/SECTIONALISING CB - CARRICKMINES GIS 220-CARRICKMINES GIS 220-22SB1-3CB | 1 | 1 | 1 | Scheduled | 04/04/2024 | 04/04/2024
TO-24-110 kV A4 @ CBT-03 | BUSBAR SECTION - CASTLEBAGOT 110-CASTLEBAGOT 110-110A4 | 5 | 5 | 5 | Scheduled | 08/04/2024 | 12/04/2024
TO-24-110 kV B4 @ CBT-03 | BUSBAR SECTION - CASTLEBAGOT 110-CASTLEBAGOT 110-110B4 | 5 | 5 | 5 | Scheduled | 08/04/2024 | 12/04/2024
TO-24-CBT-110K4-02 | COUPLER/SECTIONALISING CB - CASTLEBAGOT 110-CASTLEBAGOT 110-110K4 | 5 | 5 | 5 | Scheduled | 08/04/2024 | 12/04/2024
TO-24-CBT-110SA2-4CB-04 | COUPLER/SECTIONALISING CB - CASTLEBAGOT 110-CASTLEBAGOT 110-110SA2-4CB | 5 | 5 | 5 | Scheduled | 08/04/2024 | 12/04/2024
TO-24-CBT-110SB2-4CB-04 | COUPLER/SECTIONALISING CB - CASTLEBAGOT 110-CASTLEBAGOT 110-110SB2-4CB | 5 | 5 | 5 | Scheduled | 08/04/2024 | 12/04/2024
TO-24-CBT-MAY-1-02 | 220kV FEEDER - CASTLEBAGOT 220-MAYNOOTH 220-1 | 4 | 4 | 4 | Scheduled | 09/04/2024 | 12/04/2024
TO-24-INC-MAY-2-01 | 220kV FEEDER - INCHICORE 220-MAYNOOTH 220-2 | 4 | 4 | 4 | Scheduled | 09/04/2024 | 12/04/2024
TO-24-BAL-CDU-1-05 | 110kV FEEDER - BALTRASNA 110-CORDUFF 110-1 | 9 | 7 |  | Scheduled | 11/04/2024 | 19/04/2024
TO-24-CDU-110SA2-4-01 | SECTIONALISING DISCONNECT - CORDUFF 110-CORDUFF 110-110SA2-4 | 9 | 7 |  | Scheduled | 11/04/2024 | 19/04/2024
TO-24-CDU-110SB2-4-01 | SECTIONALISING DISCONNECT - CORDUFF 110-CORDUFF 110-110SB2-4 | 9 | 7 |  | Scheduled | 11/04/2024 | 19/04/2024
TO-24-CDU-MCE-1-02 | 110kV FEEDER - CORDUFF 110-MACETOWN 110-1 | 9 | 7 |  | Scheduled | 11/04/2024 | 19/04/2024
TO-24-CDU-T102-01 | GENERATOR TRANSFORMER - CORDUFF 110-CORDUFF 10.5-T102 | 9 | 7 |  | Scheduled | 11/04/2024 | 19/04/2024
TO-24-110 kV A2 @ FIN GIS-02 | BUSBAR SECTION - FINGLAS GIS 110-FINGLAS GIS 110-110A2 | 7 | 5 | 5 | Scheduled | 11/04/2024 | 17/04/2024
TO-24-110 kV B2 @ FIN GIS-02 | BUSBAR SECTION - FINGLAS GIS 110-FINGLAS GIS 110-110B2 | 7 | 5 | 5 | Scheduled | 11/04/2024 | 17/04/2024
TO-24-CDU-WOO-1-03 | 220kV FEEDER - CORDUFF 220-WOODLAND 220-1 | 7 | 5 | 5 | Scheduled | 13/04/2024 | 19/04/2024
TO-24-220 kV B2 @ CKM GIS-01 | BUSBAR SECTION - CARRICKMINES GIS 220-CARRICKMINES GIS 220-220B2 | 9 | 7 | 7 | Scheduled | 15/04/2024 | 23/04/2024
TO-24-220 kV B4 @ CKM GIS-02 | BUSBAR SECTION - CARRICKMINES GIS 220-CARRICKMINES GIS 220-220B4 | 9 | 7 | 7 | Scheduled | 15/04/2024 | 23/04/2024
TO-24-CKM GIS-220SB2-4CB-02 | COUPLER/SECTIONALISING CB - CARRICKMINES GIS 220-CARRICKMINES GIS 220-22SB2-4CB | 9 | 7 | 7 | Scheduled | 15/04/2024 | 23/04/2024
TO-24-CDU-220SA2-4-01 | SECTIONALISING DISCONNECT - CORDUFF 220-CORDUFF 220-220SA2-4 | 5 | 5 | 5 | Scheduled | 15/04/2024 | 19/04/2024
TO-24-CDU-220SB2-4-01 | SECTIONALISING DISCONNECT - CORDUFF 220-CORDUFF 220-220SB2-4 | 5 | 5 | 5 | Scheduled | 15/04/2024 | 19/04/2024
TO-24-PRN-T4301-01 | TRANSFORMER - PORTAN 400-PORTAN 260-T4301 | 1 | 1 | 1 | Scheduled | 15/04/2024 | 15/04/2024
TO-24-PRN-WOO-1-04 | 400kV FEEDER - PORTAN 400-WOODLAND 400-1 | 1 | 1 | 1 | Scheduled | 15/04/2024 | 15/04/2024
TO-24-400 kV A1 @ WOO-01 | BUSBAR SECTION - WOODLAND 400-WOODLAND 400-400A1 | 1 | 1 | 1 | Scheduled | 15/04/2024 | 15/04/2024
TO-24-PRN-WOO-1-01 | 400kV FEEDER - PORTAN 400-WOODLAND 400-1 | 4 | 4 | 4 | Scheduled | 16/04/2024 | 19/04/2024
TO-24-220 kV A2 @ CRU-01 | BUSBAR SECTION - CRUISERATH 220-CRUISERATH 220-220A2 | 9 | 7 | 7 | Scheduled | 22/04/2024 | 30/04/2024
TO-24-220 kV B2 @ CRU-01 | BUSBAR SECTION - CRUISERATH 220-CRUISERATH 220-220B2 | 9 | 7 | 7 | Scheduled | 22/04/2024 | 30/04/2024
TO-24-CRU-220K2-01 | COUPLER/SECTIONALISING CB - CRUISERATH 220-CRUISERATH 220-220K2 | 9 | 7 | 7 | Scheduled | 22/04/2024 | 30/04/2024
TO-24-CRU-SA1-2CB-01 | COUPLER/SECTIONALISING CB - CRUISERATH 220-CRUISERATH 220-220SA1-2CB | 9 | 7 | 7 | Scheduled | 22/04/2024 | 30/04/2024
TO-24-CRU-SB1-2CB-01 | COUPLER/SECTIONALISING CB - CRUISERATH 220-CRUISERATH 220-220SB1-2CB | 9 | 7 | 7 | Scheduled | 22/04/2024 | 30/04/2024
TO-24-WOO-T4201-03 | TRANSFORMER - WOODLAND 400-WOODLAND 220-T4201 | 5 | 5 | 5 | Scheduled | 22/04/2024 | 26/04/2024
TO-24-220 kV A1 @ FIN-02 | BUSBAR SECTION - FINGLAS 220-FINGLAS 220-220A1 | 12 | 7 | 7 | Scheduled | 27/04/2024 | 08/05/2024
TO-24-220 kV B1 @ FIN-02 | BUSBAR SECTION - FINGLAS 220-FINGLAS 220-220B1 | 12 | 7 | 7 | Scheduled | 27/04/2024 | 08/05/2024
TO-24-FIN-220K1-03 | COUPLER/SECTIONALISING CB - FINGLAS 220-FINGLAS 220-220K1 | 12 | 7 | 7 | Scheduled | 27/04/2024 | 08/05/2024
TO-24-FIN-220SA1-2CB-02 | COUPLER/SECTIONALISING CB - FINGLAS 220-FINGLAS 220-220SA1-2CB | 12 | 7 | 7 | Scheduled | 27/04/2024 | 08/05/2024
TO-24-FIN-220SB1-2CB-03 | COUPLER/SECTIONALISING CB - FINGLAS 220-FINGLAS 220-220SB1-2CB | 12 | 7 | 7 | Scheduled | 27/04/2024 | 08/05/2024
TO-24-FIN-HN-1-01 | 220kV FEEDER - FINGLAS 220-HUNTSTOWN 220-1 | 12 | 7 | 7 | Scheduled | 27/04/2024 | 08/05/2024
TO-24-HN-T2010/11-01 | GENERATOR TRANSFORMER - HUNTSTOWN 220-HUNTSTOWN G10/11-T2010/11 | 12 | 7 | 7 | Scheduled | 27/04/2024 | 08/05/2024
TO-24-MCE-T124-03 | TSO CUSTOMER TRANSFORMER - MACETOWN 110-MACETOWN 20-T124 | 3 | 3 | 3 | Scheduled | 29/04/2024 | 01/05/2024
TO-24-MAY-TSB-1-02 | 110kV FEEDER - MAYNOOTH 110-THORNSBERRY 110-1 | 120 | 83 | 83 | Scheduled | 02/05/2024 | 29/08/2024
TO-24-INC-MAY-2-02 | 220kV FEEDER - INCHICORE 220-MAYNOOTH 220-2 | 9 | 7 |  | Scheduled | 07/05/2024 | 15/05/2024
TO-24-KTL-T131-01 | GENERATOR TRANSFORMER - KILTEEL 110-KILTEEL 33-T131 | 1 | 1 | 1 | Scheduled | 07/05/2024 | 07/05/2024
TO-24-BLC-110SA1-3CB-01 | COUPLER/SECTIONALISING CB - BELCAMP 110-BELCAMP 110-110SA1-3CB | 1 | 1 | 1 | Scheduled | 09/05/2024 | 09/05/2024
TO-24-BLC-110SB1-3CB-01 | COUPLER/SECTIONALISING CB - BELCAMP 110-BELCAMP 110-110SB1-3CB | 1 | 1 | 1 | Scheduled | 10/05/2024 | 10/05/2024
TO-24-BAL-DRY-1-05 | 110kV FEEDER - BALTRASNA 110-DRYBRIDGE 110-1 | 197 | 138 | 138 | Scheduled | 13/05/2024 | 25/11/2024
TO-24-400 kV A1 @ DSN-02 | BUSBAR SECTION - DUNSTOWN 400-DUNSTOWN 400-400A1 | 12 | 10 | 10 | Scheduled | 13/05/2024 | 24/05/2024
TO-24-400 kV A2 @ DSN-01 | BUSBAR SECTION - DUNSTOWN 400-DUNSTOWN 400-400A2 | 12 | 10 | 10 | Scheduled | 13/05/2024 | 24/05/2024
TO-24-400 kV B1 @ DSN-02 | BUSBAR SECTION - DUNSTOWN 400-DUNSTOWN 400-400B1 | 12 | 10 | 10 | Scheduled | 13/05/2024 | 24/05/2024
TO-24-400 kV B2 @ DSN-01 | BUSBAR SECTION - DUNSTOWN 400-DUNSTOWN 400-400B2 | 12 | 10 | 10 | Scheduled | 13/05/2024 | 24/05/2024
TO-24-DSN-400K1-2-01 | COUPLER/SECTIONALISING CB - DUNSTOWN 400-DUNSTOWN 400-400K1-2 | 12 | 10 | 10 | Scheduled | 13/05/2024 | 24/05/2024
TO-24-220 kV A2 @ CRU-03 | BUSBAR SECTION - CRUISERATH 220-CRUISERATH 220-220A2 | 2 | 2 | 2 | Scheduled | 16/05/2024 | 17/05/2024
TO-24-220 kV B2 @ CRU-03 | BUSBAR SECTION - CRUISERATH 220-CRUISERATH 220-220B2 | 2 | 2 | 2 | Scheduled | 16/05/2024 | 17/05/2024
TO-24-CRU-220K2-05 | COUPLER/SECTIONALISING CB - CRUISERATH 220-CRUISERATH 220-220K2 | 2 | 2 | 2 | Scheduled | 16/05/2024 | 17/05/2024
TO-24-CRU-SA1-2CB-05 | COUPLER/SECTIONALISING CB - CRUISERATH 220-CRUISERATH 220-220SA1-2CB | 2 | 2 | 2 | Scheduled | 16/05/2024 | 17/05/2024
TO-24-CRU-SB1-2CB-05 | COUPLER/SECTIONALISING CB - CRUISERATH 220-CRUISERATH 220-220SB1-2CB | 2 | 2 | 2 | Scheduled | 16/05/2024 | 17/05/2024
TO-24-CLE-WOO-1-01 | 220kV FEEDER - CLONEE 220-WOODLAND 220-1 | 141 | 99 | 99 | Scheduled | 17/05/2024 | 04/10/2024
TO-24-KYT-WOO-1-01 | 220kV FEEDER - KELLYSTOWN 220-WOODLAND 220-1 | 141 | 99 | 99 | Scheduled | 17/05/2024 | 04/10/2024
TO-24-220 kV A2 @ CDU-04 | BUSBAR SECTION - CORDUFF 220-CORDUFF 220-220A2 | 43 | 30 | 30 | Scheduled | 20/05/2024 | 01/07/2024
TO-24-220 kV A4 @ CDU-04 | BUSBAR SECTION - CORDUFF 220-CORDUFF 220-220A4 | 43 | 30 |  | Scheduled | 20/05/2024 | 01/07/2024
TO-24-220 kV B2 @ CDU-04 | BUSBAR SECTION - CORDUFF 220-CORDUFF 220-220B2 | 43 | 30 | 30 | Scheduled | 20/05/2024 | 01/07/2024
TO-24-220 kV B4 @ CDU-04 | BUSBAR SECTION - CORDUFF 220-CORDUFF 220-220B4 | 43 | 30 |  | Scheduled | 20/05/2024 | 01/07/2024
TO-24-220 kV A2 @ CRU-02 | BUSBAR SECTION - CRUISERATH 220-CRUISERATH 220-220A2 | 2 | 2 | 2 | Scheduled | 20/05/2024 | 21/05/2024
TO-24-220 kV B2 @ CRU-02 | BUSBAR SECTION - CRUISERATH 220-CRUISERATH 220-220B2 | 2 | 2 | 2 | Scheduled | 20/05/2024 | 21/05/2024
TO-24-CRU-220K2-02 | COUPLER/SECTIONALISING CB - CRUISERATH 220-CRUISERATH 220-220K2 | 2 | 2 | 2 | Scheduled | 20/05/2024 | 21/05/2024
TO-24-CRU-SA1-2CB-02 | COUPLER/SECTIONALISING CB - CRUISERATH 220-CRUISERATH 220-220SA1-2CB | 2 | 2 | 2 | Scheduled | 20/05/2024 | 21/05/2024
TO-24-CRU-SB1-2CB-02 | COUPLER/SECTIONALISING CB - CRUISERATH 220-CRUISERATH 220-220SB1-2CB | 2 | 2 | 2 | Scheduled | 20/05/2024 | 21/05/2024
TO-24-BNK-T122-02 | TSO CUSTOMER TRANSFORMER - BARNAKYLE 110-BARNAKYLE 20-T122 | 5 | 5 | 5 | Scheduled | 27/05/2024 | 31/05/2024
TO-24-DND-T122-01 | TSO CUSTOMER TRANSFORMER - DARNDALE 110-DARNDALE 20-T122 | 5 | 5 | 5 | Scheduled | 27/05/2024 | 31/05/2024
TO-24-110 kV A2 @ FIN-03 | BUSBAR SECTION - FINGLAS 110-FINGLAS 110-110A2 | 3 | 3 | 3 | Scheduled | 28/05/2024 | 30/05/2024
TO-24-110 kV B2 @ FIN-03 | BUSBAR SECTION - FINGLAS 110-FINGLAS 110-110B2 | 3 | 3 | 3 | Scheduled | 28/05/2024 | 30/05/2024
TO-24-110 kV A2 @ CDU-03 | BUSBAR SECTION - CORDUFF 110-CORDUFF 110-110A2 | 57 | 40 | 40 | Scheduled | 29/05/2024 | 24/07/2024
TO-24-110 kV A4 @ CDU-02 | BUSBAR SECTION - CORDUFF 110-CORDUFF 110-110A4 | 57 | 40 | 40 | Scheduled | 29/05/2024 | 24/07/2024
TO-24-110 kV B2 @ CDU-04 | BUSBAR SECTION - CORDUFF 110-CORDUFF 110-110B2 | 57 | 40 | 40 | Scheduled | 29/05/2024 | 24/07/2024
TO-24-110 kV B4 @ CDU-02 | BUSBAR SECTION - CORDUFF 110-CORDUFF 110-110B4 | 57 | 40 | 40 | Scheduled | 29/05/2024 | 24/07/2024
TO-24-DSN-KLS-1-03 | 220kV FEEDER - DUNSTOWN 220-KELLIS 220-1 | 7 | 4 | 4 | Scheduled | 29/05/2024 | 04/06/2024
TO-24-PA-T101-04 | GENERATOR TRANSFORMER - POLLAPHUCA 110-POLLAPHUCA G1-T101 | 8 | 6 | 6 | Scheduled | 04/06/2024 | 11/06/2024
TO-24-CDU-110K1-3-01 | COUPLER/SECTIONALISING CB - CORDUFF 110-CORDUFF 110-110K1-3 | 1 | 1 | 1 | Scheduled | 05/06/2024 | 05/06/2024
TO-24-CKG-110K2-02 | COUPLER/SECTIONALISING CB - CORKAGH 110-CORKAGH 110-110K2 | 1 | 1 | 1 | Scheduled | 05/06/2024 | 05/06/2024
TO-24-CKM GIS-220SA1-3CB-01 | COUPLER/SECTIONALISING CB - CARRICKMINES GIS 220-CARRICKMINES GIS 220-22SA1-3CB | 2 | 2 | 2 | Scheduled | 06/06/2024 | 07/06/2024
TO-24-CDU-220K1-3-01 | COUPLER/SECTIONALISING CB - CORDUFF 220-CORDUFF 220-220K1-3 | 1 | 1 | 1 | Proposed | 07/06/2024 | 07/06/2024
TO-24-110 kV A1 @ DND-01 | BUSBAR SECTION - DARNDALE 110-DARNDALE 110-110A1 | 5 | 5 | 5 | Scheduled | 10/06/2024 | 14/06/2024
TO-24-110 kV B1 @ DND-01 | BUSBAR SECTION - DARNDALE 110-DARNDALE 110-110B1 | 5 | 5 | 5 | Scheduled | 10/06/2024 | 14/06/2024
TO-24-DND-110K1-01 | COUPLER/SECTIONALISING CB - DARNDALE 110-DARNDALE 110-110K1 | 5 | 5 | 5 | Scheduled | 10/06/2024 | 14/06/2024
TO-24-DND-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - DARNDALE 110-DARNDALE 110-110SA1-2CB | 5 | 5 | 5 | Scheduled | 10/06/2024 | 14/06/2024
TO-24-DND-110SB1-2CB-01 | COUPLER/SECTIONALISING CB - DARNDALE 110-DARNDALE 110-110SB1-2CB | 5 | 5 | 5 | Scheduled | 10/06/2024 | 14/06/2024
TO-24-BNK-T121-01 | TSO CUSTOMER TRANSFORMER - BARNAKYLE 110-BARNAKYLE 20-T121 | 2 | 2 | 2 | Scheduled | 11/06/2024 | 12/06/2024
TO-24-BLC-DND-1-01 | 110kV FEEDER - BELCAMP 110-DARNDALE 110-1 | 2 | 2 | 2 | Scheduled | 17/06/2024 | 18/06/2024
TO-24-110 kV A1 @ DND-02 | BUSBAR SECTION - DARNDALE 110-DARNDALE 110-110A1 | 2 | 2 | 2 | Scheduled | 17/06/2024 | 18/06/2024
TO-24-110 kV B1 @ DND-02 | BUSBAR SECTION - DARNDALE 110-DARNDALE 110-110B1 | 2 | 2 | 2 | Scheduled | 17/06/2024 | 18/06/2024
TO-24-DND-110K1-02 | COUPLER/SECTIONALISING CB - DARNDALE 110-DARNDALE 110-110K1 | 2 | 2 | 2 | Scheduled | 17/06/2024 | 18/06/2024
TO-24-DND-110SA1-2CB-02 | COUPLER/SECTIONALISING CB - DARNDALE 110-DARNDALE 110-110SA1-2CB | 2 | 2 | 2 | Scheduled | 17/06/2024 | 18/06/2024
TO-24-DND-110SB1-2CB-02 | COUPLER/SECTIONALISING CB - DARNDALE 110-DARNDALE 110-110SB1-2CB | 2 | 2 | 2 | Scheduled | 17/06/2024 | 18/06/2024
TO-24-110 kV B2 @ DND-01 | BUSBAR SECTION - DARNDALE 110-DARNDALE 110-110B2 | 1 | 1 | 1 | Scheduled | 19/06/2024 | 19/06/2024
TO-24-DND-110K2-03 | COUPLER/SECTIONALISING CB - DARNDALE 110-DARNDALE 110-110K2 | 1 | 1 | 1 | Scheduled | 19/06/2024 | 19/06/2024
TO-24-DND-110SB1-2CB-04 | COUPLER/SECTIONALISING CB - DARNDALE 110-DARNDALE 110-110SB1-2CB | 1 | 1 | 1 | Scheduled | 19/06/2024 | 19/06/2024
TO-24-DND-T126-01 | TSO CUSTOMER TRANSFORMER - DARNDALE 110-DARNDALE 20-T126 | 1 | 1 | 1 | Scheduled | 19/06/2024 | 19/06/2024
TO-24-220 kV B2 @ CRU-04 | BUSBAR SECTION - CRUISERATH 220-CRUISERATH 220-220B2 | 2 | 2 | 2 | Scheduled | 20/06/2024 | 21/06/2024
TO-24-CRU-220K2-06 | COUPLER/SECTIONALISING CB - CRUISERATH 220-CRUISERATH 220-220K2 | 2 | 2 | 2 | Scheduled | 20/06/2024 | 21/06/2024
TO-24-CRU-SB1-2CB-06 | COUPLER/SECTIONALISING CB - CRUISERATH 220-CRUISERATH 220-220SB1-2CB | 2 | 2 | 2 | Scheduled | 20/06/2024 | 21/06/2024
TO-24-CRU-T222-01 | TSO CUSTOMER TRANSFORMER - CRUISERATH 220-CRUISERATH 20-T222 | 2 | 2 | 2 | Scheduled | 20/06/2024 | 21/06/2024
TO-24-220 kV A4 @ PB-01 | BUSBAR SECTION - POOLBEG 220-POOLBEG 220-220A4 | 5 | 5 | 5 | Scheduled | 24/06/2024 | 28/06/2024
TO-24-220 kV B4 @ PB-02 | BUSBAR SECTION - POOLBEG 220-POOLBEG 220-220B4 | 5 | 5 | 5 | Scheduled | 24/06/2024 | 28/06/2024
TO-24-110 kV A2 @ MAY-01 | BUSBAR SECTION - MAYNOOTH 110-MAYNOOTH 110-110A2 | 61 | 44 | 44 | Scheduled | 08/07/2024 | 06/09/2024
TO-24-110 kV A3 @ MAY-03 | BUSBAR SECTION - MAYNOOTH 110-MAYNOOTH 110-110A3 | 61 | 44 | 44 | Scheduled | 08/07/2024 | 06/09/2024
TO-24-110 kV B2 @ MAY-01 | BUSBAR SECTION - MAYNOOTH 110-MAYNOOTH 110-110B2 | 61 | 44 | 44 | Scheduled | 08/07/2024 | 06/09/2024
TO-24-110 kV B3 @ MAY-03 | BUSBAR SECTION - MAYNOOTH 110-MAYNOOTH 110-110B3 | 61 | 44 | 44 | Scheduled | 08/07/2024 | 06/09/2024
TO-24-PB-R2001-03 | CAPACITOR/SVC/REACTOR - POOLBEG 220-POOLBEG 220-R2001 | 5 | 5 | 5 | Scheduled | 08/07/2024 | 12/07/2024
TO-24-DSN-T4202-01 | TRANSFORMER - DUNSTOWN 400-DUNSTOWN 220-T4202 | 1 | 1 | 1 | Scheduled | 10/07/2024 | 10/07/2024
TO-24-PB-T2007/8-03 | GENERATOR TRANSFORMER - POOLBEG 220-POOLBEG G7/8-T2007/8 | 3 | 3 | 3 | Scheduled | 10/07/2024 | 12/07/2024
TO-24-BLC-DND-1-03 | 110kV FEEDER - BELCAMP 110-DARNDALE 110-1 | 4 | 4 | 4 | Scheduled | 16/07/2024 | 19/07/2024
TO-24-CKM GIS-DSN-1-06 | 220kV FEEDER - CARRICKMINES GIS 220-DUNSTOWN 220-1 | 2 | 0 | 0 | Scheduled | 20/07/2024 | 21/07/2024
TO-24-BLC-DND-3-01 | 110kV FEEDER - BELCAMP 110-DARNDALE 110-3 | 4 | 4 | 4 | Scheduled | 23/07/2024 | 26/07/2024
TO-24-220 kV A2 @ FIN-05 | BUSBAR SECTION - FINGLAS 220-FINGLAS 220-220A2 | 9 | 7 | 7 | Scheduled | 25/07/2024 | 02/08/2024
TO-24-CKM GIS-DSN-1-07 | 220kV FEEDER - CARRICKMINES GIS 220-DUNSTOWN 220-1 | 2 | 0 | 0 | Scheduled | 27/07/2024 | 28/07/2024
TO-24-BNK-CBT-1-01 | 110kV FEEDER - BARNAKYLE 110-CASTLEBAGOT 110-1 | 2 | 2 | 2 | Scheduled | 30/07/2024 | 31/07/2024
TO-24-CKM GIS-DSN-1-08 | 220kV FEEDER - CARRICKMINES GIS 220-DUNSTOWN 220-1 | 2 | 0 | 0 | Scheduled | 03/08/2024 | 04/08/2024
TO-24-BLU-CDU-1-01 | 110kV FEEDER - BLUNDELSTOWN 110-CORDUFF 110-1 | 58 | 42 | 42 | Scheduled | 08/08/2024 | 04/10/2024
TO-24-ISH-T2001-01 | GENERATOR TRANSFORMER - IRISHTOWN 220-IRISHTOWN G1-T2001 | 20 | 15 | 15 | Scheduled | 11/08/2024 | 30/08/2024
TO-24-AUN-CBT-3-01 | 110kV FEEDER - AUNGIERSTOWN 110-CASTLEBAGOT 110-3 | 99 | 70 |  | Scheduled | 15/08/2024 | 21/11/2024
TO-24-CDU-220SB2-4-02 | SECTIONALISING DISCONNECT - CORDUFF 220-CORDUFF 220-220SB2-4 | 3 | 3 |  | Scheduled | 19/08/2024 | 21/08/2024
TO-24-RNW-T122-01 | TSO CUSTOMER TRANSFORMER - RINAWADE 110-RINAWADE 20-T122 | 5 | 5 | 5 | Proposed | 19/08/2024 | 23/08/2024
TO-24-220 kV A6 @ INC-01 | BUSBAR SECTION - INCHICORE 220-INCHICORE 220-220A6 | 4 | 4 | 4 | Scheduled | 20/08/2024 | 23/08/2024
TO-24-220 kV B6 @ INC-01 | BUSBAR SECTION - INCHICORE 220-INCHICORE 220-220B6 | 4 | 4 | 4 | Scheduled | 20/08/2024 | 23/08/2024
TO-24-INC-T2106-02 | TRANSFORMER - INCHICORE 220-INCHICORE 110-T2106 | 4 | 4 | 4 | Reference | 20/08/2024 | 23/08/2024
TO-24-110 kV A2 @ FIN GIS-03 | BUSBAR SECTION - FINGLAS GIS 110-FINGLAS GIS 110-110A2 | 5 | 5 | 5 | Scheduled | 26/08/2024 | 30/08/2024
TO-24-110 kV B2 @ FIN GIS-03 | BUSBAR SECTION - FINGLAS GIS 110-FINGLAS GIS 110-110B2 | 5 | 5 | 5 | Scheduled | 26/08/2024 | 30/08/2024
TO-24-FIN GIS-110K2-04 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110K2 | 5 | 5 | 5 | Scheduled | 26/08/2024 | 30/08/2024
TO-24-FIN GIS-110SA1-2CB-04 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110SA1-2CB | 5 | 5 | 5 | Scheduled | 26/08/2024 | 30/08/2024
TO-24-FIN GIS-110SA2-4CB-05 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110SA2-4CB | 5 | 5 | 5 | Scheduled | 26/08/2024 | 30/08/2024
TO-24-FIN GIS-110SB1-2CB-04 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110SB1-2CB | 5 | 5 | 5 | Scheduled | 26/08/2024 | 30/08/2024
TO-24-FIN GIS-110SB2-4CB-06 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110SB2-4CB | 5 | 5 | 5 | Scheduled | 26/08/2024 | 30/08/2024
TO-24-WOO-T4204-01 | TRANSFORMER - WOODLAND 400-WOODLAND 220-T4204 | 26 | 20 | 20 | Scheduled | 26/08/2024 | 20/09/2024
TO-24-MAY-TEN-1-01 | 110kV FEEDER - MAYNOOTH 110-TIMAHOE 110-1 | 34 | 24 | 24 | Scheduled | 29/08/2024 | 01/10/2024
TO-24-SHL-T2015-01 | GENERATOR TRANSFORMER - SHELLYBANKS 220-SHELLYBANKS G5-T2015 | 27 | 20 | 20 | Scheduled | 01/09/2024 | 27/09/2024
TO-24-RNW-T121-01 | TSO CUSTOMER TRANSFORMER - RINAWADE 110-RINAWADE 20-T121 | 5 | 5 | 5 | Scheduled | 02/09/2024 | 06/09/2024
TO-24-110 kV A1 @ SNU-04 | BUSBAR SECTION - SNUGBOROUGH 110-SNUGBOROUGH 110-110A1 | 5 | 5 | 5 | Scheduled | 02/09/2024 | 06/09/2024
TO-24-110 kV B1 @ SNU-04 | BUSBAR SECTION - SNUGBOROUGH 110-SNUGBOROUGH 110-110B1 | 5 | 5 | 5 | Scheduled | 02/09/2024 | 06/09/2024
TO-24-SNU-110K1-04 | COUPLER/SECTIONALISING CB - SNUGBOROUGH 110-SNUGBOROUGH 110-110K1 | 5 | 5 | 5 | Scheduled | 02/09/2024 | 06/09/2024
TO-24-SNU-110SA1-2CB-08 | COUPLER/SECTIONALISING CB - SNUGBOROUGH 110-SNUGBOROUGH 110-110SA1-2CB | 5 | 5 | 5 | Scheduled | 02/09/2024 | 06/09/2024
TO-24-SNU-110SB1-2CB-09 | COUPLER/SECTIONALISING CB - SNUGBOROUGH 110-SNUGBOROUGH 110-110SB1-2CB | 5 | 5 | 5 | Scheduled | 02/09/2024 | 06/09/2024
TO-24-CDU-GLN-1-05 | 110kV FEEDER - CORDUFF 110-GALLANSTOWN 110-1 | 3 | 1 | 1 | Scheduled | 06/09/2024 | 08/09/2024
TO-24-110 kV A2 @ SNU-02 | BUSBAR SECTION - SNUGBOROUGH 110-SNUGBOROUGH 110-110A2 | 10 | 8 | 8 | Scheduled | 09/09/2024 | 18/09/2024
TO-24-110 kV B2 @ SNU-02 | BUSBAR SECTION - SNUGBOROUGH 110-SNUGBOROUGH 110-110B2 | 10 | 8 | 8 | Scheduled | 09/09/2024 | 18/09/2024
TO-24-SNU-110K2-01 | COUPLER/SECTIONALISING CB - SNUGBOROUGH 110-SNUGBOROUGH 110-110K2 | 10 | 8 | 8 | Scheduled | 09/09/2024 | 18/09/2024
TO-24-SNU-110SA1-2CB-06 | COUPLER/SECTIONALISING CB - SNUGBOROUGH 110-SNUGBOROUGH 110-110SA1-2CB | 10 | 8 | 8 | Scheduled | 09/09/2024 | 18/09/2024
TO-24-SNU-110SB1-2CB-07 | COUPLER/SECTIONALISING CB - SNUGBOROUGH 110-SNUGBOROUGH 110-110SB1-2CB | 10 | 8 | 8 | Scheduled | 09/09/2024 | 18/09/2024
TO-24-INC-T2102-01 | TRANSFORMER - INCHICORE 220-INCHICORE 110-T2102 | 2 | 2 | 2 | Reference | 10/09/2024 | 11/09/2024
TO-24-KYT-220K2-01 | COUPLER/SECTIONALISING CB - KELLYSTOWN 220-KELLYSTOWN 220-220K2 | 1 | 1 | 1 | Scheduled | 11/09/2024 | 11/09/2024
TO-24-KYT-220K3-01 | COUPLER/SECTIONALISING CB - KELLYSTOWN 220-KELLYSTOWN 220-220K3 | 1 | 1 | 1 | Scheduled | 12/09/2024 | 12/09/2024
TO-24-CLE-T222-02 | TSO CUSTOMER TRANSFORMER - CLONEE 220-CLONEE 20-T222 | 36 | 26 | 26 | Scheduled | 16/09/2024 | 21/10/2024
TO-24-220 kV A1 @ TH-02 | BUSBAR SECTION - TURLOUGH HILL 220-TURLOUGH HILL 220-220A1 | 4 | 4 | 4 | Scheduled | 16/09/2024 | 19/09/2024
TO-24-220 kV A2 @ TH-03 | BUSBAR SECTION - TURLOUGH HILL 220-TURLOUGH HILL 220-220A2 | 4 | 4 | 4 | Scheduled | 16/09/2024 | 19/09/2024
TO-24-220 kV B1 @ TH-02 | BUSBAR SECTION - TURLOUGH HILL 220-TURLOUGH HILL 220-220B1 | 4 | 4 | 4 | Scheduled | 16/09/2024 | 19/09/2024
TO-24-220 kV B2 @ TH-01 | BUSBAR SECTION - TURLOUGH HILL 220-TURLOUGH HILL 220-220B2 | 4 | 4 | 4 | Scheduled | 16/09/2024 | 19/09/2024
TO-24-TH-220K1-2-03 | COUPLER/SECTIONALISING CB - TURLOUGH HILL 220-TURLOUGH HILL 220-220K1-2 | 5 | 5 | 5 | Scheduled | 16/09/2024 | 20/09/2024
TO-24-GLN-T133-01 | GENERATOR TRANSFORMER - GALLANSTOWN 110-GALLANSTOWN 33-T133 | 1 | 1 | 1 | Scheduled | 17/09/2024 | 17/09/2024
TO-24-PB-R2001-06 | CAPACITOR/SVC/REACTOR - POOLBEG 220-POOLBEG 220-R2001 | 2 | 2 | 2 | Scheduled | 17/09/2024 | 18/09/2024
TO-24-BAL-T121-03 | DISTRIBUTION TRANSFORMER - BALTRASNA 110-BALTRASNA 20-T121 | 2 | 2 | 2 | Reference (Proposed) | 19/09/2024 | 20/09/2024
TO-24-110 kV A1 @ CLG-02 | BUSBAR SECTION - CLOGHRAN 110-CLOGHRAN 110-110A1 | 12 | 10 | 10 | Scheduled | 23/09/2024 | 04/10/2024
TO-24-110 kV B1 @ CLG-02 | BUSBAR SECTION - CLOGHRAN 110-CLOGHRAN 110-110B1 | 12 | 10 | 10 | Scheduled | 23/09/2024 | 04/10/2024
TO-24-CLG-110K1-05 | COUPLER/SECTIONALISING CB - CLOGHRAN 110-CLOGHRAN 110-110K1 | 12 | 10 | 10 | Scheduled | 23/09/2024 | 04/10/2024
TO-24-CLG-110SA1-2CB-03 | COUPLER/SECTIONALISING CB - CLOGHRAN 110-CLOGHRAN 110-110SA1-2CB | 12 | 10 | 10 | Scheduled | 23/09/2024 | 04/10/2024
TO-24-CLG-110SB1-2CB-02 | COUPLER/SECTIONALISING CB - CLOGHRAN 110-CLOGHRAN 110-110SB1-2CB | 12 | 10 | 10 | Scheduled | 23/09/2024 | 04/10/2024
TO-24-CLG-T121-01 | TSO CUSTOMER TRANSFORMER - CLOGHRAN 110-CLOGHRAN 20-T121 | 12 | 10 | 10 | Scheduled | 23/09/2024 | 04/10/2024
TO-24-FIN-T2103-03 | TRANSFORMER - FINGLAS 220-FINGLAS 110-T2103 | 2 | 2 | 2 | Scheduled | 23/09/2024 | 24/09/2024
TO-24-RYB GIS-T103-01 | TSO CUSTOMER TRANSFORMER - RYEBROOK GIS 110-RYEBROOK 10-T103 | 18 | 14 | 14 | Scheduled | 23/09/2024 | 10/10/2024
TO-24-SHL-D2/CB2-02 | COUPLER/SECTIONALISING CB - SHELLYBANKS 220-SHELLYBANKS 220-D2/CB2 | 5 | 5 | 5 | Scheduled | 23/09/2024 | 27/09/2024
TO-24-SHL-D2/CB3-03 | COUPLER/SECTIONALISING CB - SHELLYBANKS 220-SHELLYBANKS 220-D2/CB3 | 5 | 5 | 5 | Scheduled | 23/09/2024 | 27/09/2024
TO-24-110 kV A2 @ MAY-02 | BUSBAR SECTION - MAYNOOTH 110-MAYNOOTH 110-110A2 | 2 | 2 | 2 | Scheduled | 24/09/2024 | 25/09/2024
TO-24-110 kV A3 @ MAY-04 | BUSBAR SECTION - MAYNOOTH 110-MAYNOOTH 110-110A3 | 2 | 2 | 2 | Scheduled | 24/09/2024 | 25/09/2024
TO-24-110 kV B2 @ MAY-02 | BUSBAR SECTION - MAYNOOTH 110-MAYNOOTH 110-110B2 | 2 | 2 | 2 | Scheduled | 24/09/2024 | 25/09/2024
TO-24-110 kV B3 @ MAY-04 | BUSBAR SECTION - MAYNOOTH 110-MAYNOOTH 110-110B3 | 2 | 2 | 2 | Scheduled | 24/09/2024 | 25/09/2024
TO-24-MAY-T2102-06 | TRANSFORMER - MAYNOOTH 220-MAYNOOTH 110-T2102 | 2 | 2 | 2 | Scheduled | 24/09/2024 | 25/09/2024
TO-24-MAY-T2103-02 | TRANSFORMER - MAYNOOTH 220-MAYNOOTH 110-T2103 | 2 | 2 | 2 | Scheduled | 24/09/2024 | 25/09/2024
TO-24-CDU-SNU-1-02 | 110kV FEEDER - CORDUFF 110-SNUGBOROUGH 110-1 | 5 | 5 | 5 | Scheduled | 30/09/2024 | 04/10/2024
TO-24-110 kV A2 @ SNU-03 | BUSBAR SECTION - SNUGBOROUGH 110-SNUGBOROUGH 110-110A2 | 5 | 5 | 5 | Scheduled | 30/09/2024 | 04/10/2024
TO-24-110 kV B2 @ SNU-03 | BUSBAR SECTION - SNUGBOROUGH 110-SNUGBOROUGH 110-110B2 | 5 | 5 | 5 | Scheduled | 30/09/2024 | 04/10/2024
TO-24-SNU-110K2-04 | COUPLER/SECTIONALISING CB - SNUGBOROUGH 110-SNUGBOROUGH 110-110K2 | 5 | 5 | 5 | Scheduled | 30/09/2024 | 04/10/2024
TO-24-SNU-110SA1-2CB-07 | COUPLER/SECTIONALISING CB - SNUGBOROUGH 110-SNUGBOROUGH 110-110SA1-2CB | 5 | 5 | 5 | Scheduled | 30/09/2024 | 04/10/2024
TO-24-SNU-110SB1-2CB-08 | COUPLER/SECTIONALISING CB - SNUGBOROUGH 110-SNUGBOROUGH 110-110SB1-2CB | 5 | 5 | 5 | Scheduled | 30/09/2024 | 04/10/2024
TO-24-BLC-110K1-01 | COUPLER/SECTIONALISING CB - BELCAMP 110-BELCAMP 110-110K1 | 1 | 1 | 1 | Scheduled | 02/10/2024 | 02/10/2024
TO-24-SHL-D1/CB1-04 | COUPLER/SECTIONALISING CB - SHELLYBANKS 220-SHELLYBANKS 220-D1/CB1 | 1 | 1 | 1 | Scheduled | 02/10/2024 | 02/10/2024
TO-24-SHL-D2/CB1-04 | COUPLER/SECTIONALISING CB - SHELLYBANKS 220-SHELLYBANKS 220-D2/CB1 | 1 | 1 | 1 | Scheduled | 02/10/2024 | 02/10/2024
TO-24-SHL-T2016-01 | GENERATOR TRANSFORMER - SHELLYBANKS 220-SHELLYBANKS G6-T2016 | 30 | 21 |  | Scheduled | 02/10/2024 | 31/10/2024
TO-24-BLC-110K3-01 | COUPLER/SECTIONALISING CB - BELCAMP 110-BELCAMP 110-110K3 | 1 | 1 | 1 | Scheduled | 03/10/2024 | 03/10/2024
TO-24-CDU-HN-1-01 | 220kV FEEDER - CORDUFF 220-HUNTSTOWN 220-1 | 19 | 13 | 13 | Scheduled | 05/10/2024 | 23/10/2024
TO-24-DSN-MP GIS-1-04 | 400kV FEEDER - DUNSTOWN 400-MONEYPOINT GIS 400-1 | 2 | 0 | 0 | Scheduled | 05/10/2024 | 06/10/2024
TO-24-HN-T2002-01 | GENERATOR TRANSFORMER - HUNTSTOWN 220-HUNTSTOWN G2-T2002 | 19 | 13 | 13 | Scheduled | 05/10/2024 | 23/10/2024
TO-24-110 kV A1 @ CLG-03 | BUSBAR SECTION - CLOGHRAN 110-CLOGHRAN 110-110A1 | 13 | 10 | 10 | Scheduled | 06/10/2024 | 18/10/2024
TO-24-110 kV B1 @ CLG-03 | BUSBAR SECTION - CLOGHRAN 110-CLOGHRAN 110-110B1 | 13 | 10 | 10 | Scheduled | 06/10/2024 | 18/10/2024
TO-24-CLG-110K1-06 | COUPLER/SECTIONALISING CB - CLOGHRAN 110-CLOGHRAN 110-110K1 | 13 | 10 | 10 | Scheduled | 06/10/2024 | 18/10/2024
TO-24-CLG-110SA1-2CB-02 | COUPLER/SECTIONALISING CB - CLOGHRAN 110-CLOGHRAN 110-110SA1-2CB | 13 | 10 | 10 | Scheduled | 06/10/2024 | 18/10/2024
TO-24-CLG-110SB1-2CB-03 | COUPLER/SECTIONALISING CB - CLOGHRAN 110-CLOGHRAN 110-110SB1-2CB | 13 | 10 | 10 | Scheduled | 06/10/2024 | 18/10/2024
TO-24-CLG-T123-02 | TSO CUSTOMER TRANSFORMER - CLOGHRAN 110-CLOGHRAN 20-T123 | 13 | 10 | 10 | Scheduled | 06/10/2024 | 18/10/2024
TO-24-110 kV A1 @ AUN-01 | BUSBAR SECTION - AUNGIERSTOWN 110-AUNGIERSTOWN 110-110A1 | 5 | 5 | 5 | Scheduled | 07/10/2024 | 11/10/2024
TO-24-110 kV B1 @ AUN-01 | BUSBAR SECTION - AUNGIERSTOWN 110-AUNGIERSTOWN 110-110B1 | 5 | 5 | 5 | Scheduled | 07/10/2024 | 11/10/2024
TO-24-AUN-110K1-01 | COUPLER/SECTIONALISING CB - AUNGIERSTOWN 110-AUNGIERSTOWN 110-110K1 | 5 | 5 | 5 | Scheduled | 07/10/2024 | 11/10/2024
TO-24-AUN-110SA1-2CB-02 | COUPLER/SECTIONALISING CB - AUNGIERSTOWN 110-AUNGIERSTOWN 110-110SA1-2CB | 5 | 5 | 5 | Scheduled | 07/10/2024 | 11/10/2024
TO-24-AUN-110SB1-2CB-01 | COUPLER/SECTIONALISING CB - AUNGIERSTOWN 110-AUNGIERSTOWN 110-110SB1-2CB | 5 | 5 | 5 | Scheduled | 07/10/2024 | 11/10/2024
TO-24-110 kV A4 @ CBT-01 | BUSBAR SECTION - CASTLEBAGOT 110-CASTLEBAGOT 110-110A4 | 5 | 5 | 5 | Scheduled | 07/10/2024 | 11/10/2024
TO-24-110 kV B4 @ CBT-01 | BUSBAR SECTION - CASTLEBAGOT 110-CASTLEBAGOT 110-110B4 | 5 | 5 | 5 | Scheduled | 07/10/2024 | 11/10/2024
TO-24-CBT-110K4-01 | COUPLER/SECTIONALISING CB - CASTLEBAGOT 110-CASTLEBAGOT 110-110K4 | 5 | 5 | 5 | Scheduled | 07/10/2024 | 11/10/2024
TO-24-CBT-110SA2-4CB-01 | COUPLER/SECTIONALISING CB - CASTLEBAGOT 110-CASTLEBAGOT 110-110SA2-4CB | 5 | 5 | 5 | Scheduled | 07/10/2024 | 11/10/2024
TO-24-CBT-110SB2-4CB-01 | COUPLER/SECTIONALISING CB - CASTLEBAGOT 110-CASTLEBAGOT 110-110SB2-4CB | 5 | 5 | 5 | Scheduled | 07/10/2024 | 11/10/2024
TO-24-220 kV A1 @ CBT-03 | BUSBAR SECTION - CASTLEBAGOT 220-CASTLEBAGOT 220-220A1 | 24 | 17 | 17 | Proposed | 07/10/2024 | 30/10/2024
TO-24-220 kV B1 @ CBT-01 | BUSBAR SECTION - CASTLEBAGOT 220-CASTLEBAGOT 220-220B1 | 24 | 17 | 17 | Proposed | 07/10/2024 | 30/10/2024
TO-24-CBT-220K1-02 | COUPLER/SECTIONALISING CB - CASTLEBAGOT 220-CASTLEBAGOT 220-220K1 | 24 | 17 | 17 | Proposed | 07/10/2024 | 30/10/2024
TO-24-CBT-220SA1-2CB-05 | COUPLER/SECTIONALISING CB - CASTLEBAGOT 220-CASTLEBAGOT 220-220SA1-2CB | 24 | 17 | 17 | Proposed | 07/10/2024 | 30/10/2024
TO-24-CBT-220SB1-2CB-05 | COUPLER/SECTIONALISING CB - CASTLEBAGOT 220-CASTLEBAGOT 220-220SB1-2CB | 24 | 17 | 17 | Proposed | 07/10/2024 | 30/10/2024
TO-24-CBT-MAY-1-01 | 220kV FEEDER - CASTLEBAGOT 220-MAYNOOTH 220-1 | 24 | 17 | 17 | Proposed | 07/10/2024 | 30/10/2024
TO-24-CBT-MAY-1-04 | 220kV FEEDER - CASTLEBAGOT 220-MAYNOOTH 220-1 | 24 | 17 | 17 | Scheduled | 07/10/2024 | 30/10/2024
TO-24-110 kV A2 @ CDU-04 | BUSBAR SECTION - CORDUFF 110-CORDUFF 110-110A2 | 19 | 15 |  | Scheduled | 07/10/2024 | 25/10/2024
TO-24-110 kV A4 @ CDU-03 | BUSBAR SECTION - CORDUFF 110-CORDUFF 110-110A4 | 19 | 15 |  | Scheduled | 07/10/2024 | 25/10/2024
TO-24-110 kV B2 @ CDU-03 | BUSBAR SECTION - CORDUFF 110-CORDUFF 110-110B2 | 19 | 15 |  | Scheduled | 07/10/2024 | 25/10/2024
TO-24-110 kV B4 @ CDU-04 | BUSBAR SECTION - CORDUFF 110-CORDUFF 110-110B4 | 19 | 15 |  | Scheduled | 07/10/2024 | 25/10/2024
TO-24-400 kV A1 @ DSN-01 | BUSBAR SECTION - DUNSTOWN 400-DUNSTOWN 400-400A1 | 19 | 15 | 15 | Scheduled | 07/10/2024 | 25/10/2024
TO-24-400 kV B1 @ DSN-01 | BUSBAR SECTION - DUNSTOWN 400-DUNSTOWN 400-400B1 | 19 | 15 | 15 | Scheduled | 07/10/2024 | 25/10/2024
TO-24-DSN-T4201-03 | TRANSFORMER - DUNSTOWN 400-DUNSTOWN 220-T4201 | 19 | 15 | 15 | Scheduled | 07/10/2024 | 25/10/2024
TO-24-INC-MAY-2-03 | 220kV FEEDER - INCHICORE 220-MAYNOOTH 220-2 | 61 | 44 | 44 | Scheduled | 07/10/2024 | 06/12/2024
TO-24-INC-MAY-2-05 | 220kV FEEDER - INCHICORE 220-MAYNOOTH 220-2 | 58 | 41 | 41 | Proposed | 07/10/2024 | 03/12/2024
TO-24-220 kV A1 @ MAY-05 | BUSBAR SECTION - MAYNOOTH 220-MAYNOOTH 220-220A1 | 24 | 17 | 17 | Proposed | 07/10/2024 | 30/10/2024
TO-24-220 kV A2 @ MAY-02 | BUSBAR SECTION - MAYNOOTH 220-MAYNOOTH 220-220A2 | 64 | 45 | 45 | Proposed | 07/10/2024 | 09/12/2024
TO-24-220 kV B1 @ MAY-05 | BUSBAR SECTION - MAYNOOTH 220-MAYNOOTH 220-220B1 | 24 | 17 | 17 | Proposed | 07/10/2024 | 30/10/2024
TO-24-220 kV B2 @ MAY-02 | BUSBAR SECTION - MAYNOOTH 220-MAYNOOTH 220-220B2 | 64 | 45 | 45 | Proposed | 07/10/2024 | 09/12/2024
TO-24-RYB GIS-110K4-02 | COUPLER/SECTIONALISING CB - RYEBROOK GIS 110-RYEBROOK GIS 110-110K4 | 1 | 1 | 1 | Scheduled | 08/10/2024 | 08/10/2024
TO-24-CDU-RYB GIS-1-03 | 110kV FEEDER - CORDUFF 110-RYEBROOK GIS 110-1 | 1 | 1 | 1 | Scheduled | 10/10/2024 | 10/10/2024
TO-24-110 kV A1 @ RYB GIS-01 | BUSBAR SECTION - RYEBROOK GIS 110-RYEBROOK GIS 110-110A1 | 1 | 1 | 1 | Scheduled | 10/10/2024 | 10/10/2024
TO-24-110 kV A2 @ RYB GIS-01 | BUSBAR SECTION - RYEBROOK GIS 110-RYEBROOK GIS 110-110A2 | 1 | 1 | 1 | Scheduled | 10/10/2024 | 10/10/2024
TO-24-110 kV A3 @ RYB GIS-01 | BUSBAR SECTION - RYEBROOK GIS 110-RYEBROOK GIS 110-110A3 | 1 | 1 | 1 | Scheduled | 10/10/2024 | 10/10/2024
TO-24-110 kV A4 @ RYB GIS-01 | BUSBAR SECTION - RYEBROOK GIS 110-RYEBROOK GIS 110-110A4 | 1 | 1 | 1 | Scheduled | 10/10/2024 | 10/10/2024
TO-24-RYB GIS-110K3-02 | COUPLER/SECTIONALISING CB - RYEBROOK GIS 110-RYEBROOK GIS 110-110K3 | 1 | 1 | 1 | Scheduled | 10/10/2024 | 10/10/2024
TO-24-RYB GIS-110K4-03 | COUPLER/SECTIONALISING CB - RYEBROOK GIS 110-RYEBROOK GIS 110-110K4 | 1 | 1 | 1 | Scheduled | 10/10/2024 | 10/10/2024
TO-24-RYB GIS-110SA1-2CB-02 | COUPLER/SECTIONALISING CB - RYEBROOK GIS 110-RYEBROOK GIS 110-110SA1-2CB | 1 | 1 | 1 | Scheduled | 10/10/2024 | 10/10/2024
TO-24-RYB GIS-110SA1-3CB-02 | COUPLER/SECTIONALISING CB - RYEBROOK GIS 110-RYEBROOK GIS 110-110SA1-3CB | 1 | 1 | 1 | Scheduled | 10/10/2024 | 10/10/2024
TO-24-RYB GIS-110SA2-4CB-02 | COUPLER/SECTIONALISING CB - RYEBROOK GIS 110-RYEBROOK GIS 110-110SA2-4CB | 1 | 1 | 1 | Scheduled | 10/10/2024 | 10/10/2024
TO-24-110 kV A1 @ BAG-01 | BUSBAR SECTION - BARNAGEERAGH 110-BARNAGEERAGH 110-110A1 | 2 | 2 | 2 | Scheduled | 14/10/2024 | 15/10/2024
TO-24-110 kV B1 @ BAG-01 | BUSBAR SECTION - BARNAGEERAGH 110-BARNAGEERAGH 110-110B1 | 2 | 2 | 2 | Scheduled | 14/10/2024 | 15/10/2024
TO-24-BAG-110K1-01 | COUPLER/SECTIONALISING CB - BARNAGEERAGH 110-BARNAGEERAGH 110-110K1 | 2 | 2 | 2 | Scheduled | 14/10/2024 | 15/10/2024
TO-24-BAG-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - BARNAGEERAGH 110-BARNAGEERAGH 110-110SA1-2CB | 2 | 2 | 2 | Scheduled | 14/10/2024 | 15/10/2024
TO-24-BAG-110SB1-2CB-01 | COUPLER/SECTIONALISING CB - BARNAGEERAGH 110-BARNAGEERAGH 110-110SB1-2CB | 2 | 2 | 2 | Scheduled | 14/10/2024 | 15/10/2024
TO-24-110 kV A1 @ SNU-03 | BUSBAR SECTION - SNUGBOROUGH 110-SNUGBOROUGH 110-110A1 | 2 | 2 | 2 | Scheduled | 14/10/2024 | 15/10/2024
TO-24-110 kV B1 @ SNU-03 | BUSBAR SECTION - SNUGBOROUGH 110-SNUGBOROUGH 110-110B1 | 2 | 2 | 2 | Scheduled | 14/10/2024 | 15/10/2024
TO-24-SNU-110K1-02 | COUPLER/SECTIONALISING CB - SNUGBOROUGH 110-SNUGBOROUGH 110-110K1 | 2 | 2 | 2 | Scheduled | 14/10/2024 | 15/10/2024
TO-24-SNU-110SA1-2CB-03 | COUPLER/SECTIONALISING CB - SNUGBOROUGH 110-SNUGBOROUGH 110-110SA1-2CB | 2 | 2 | 2 | Scheduled | 14/10/2024 | 15/10/2024
TO-24-SNU-110SB1-2CB-03 | COUPLER/SECTIONALISING CB - SNUGBOROUGH 110-SNUGBOROUGH 110-110SB1-2CB | 2 | 2 | 2 | Scheduled | 14/10/2024 | 15/10/2024
TO-24-110 kV A2 @ CLG-01 | BUSBAR SECTION - CLOGHRAN 110-CLOGHRAN 110-110A2 | 5 | 5 | 5 | Scheduled | 21/10/2024 | 25/10/2024
TO-24-110 kV B2 @ CLG-01 | BUSBAR SECTION - CLOGHRAN 110-CLOGHRAN 110-110B2 | 5 | 5 | 5 | Scheduled | 21/10/2024 | 25/10/2024
TO-24-CLG-110K2-02 | COUPLER/SECTIONALISING CB - CLOGHRAN 110-CLOGHRAN 110-110K2 | 5 | 5 | 5 | Scheduled | 21/10/2024 | 25/10/2024
TO-24-CLG-110SA1-2CB-04 | COUPLER/SECTIONALISING CB - CLOGHRAN 110-CLOGHRAN 110-110SA1-2CB | 5 | 5 | 5 | Scheduled | 21/10/2024 | 25/10/2024
TO-24-CLG-110SB1-2CB-04 | COUPLER/SECTIONALISING CB - CLOGHRAN 110-CLOGHRAN 110-110SB1-2CB | 5 | 5 | 5 | Scheduled | 21/10/2024 | 25/10/2024
TO-24-CLG-T126-02 | TSO CUSTOMER TRANSFORMER - CLOGHRAN 110-CLOGHRAN 20-T126 | 5 | 5 | 5 | Scheduled | 21/10/2024 | 25/10/2024
TO-24-KYT-T232-02 | TSO CUSTOMER TRANSFORMER - KELLYSTOWN 220-KELLYSTOWN 34.5-T232 | 19 | 14 | 14 | Scheduled | 21/10/2024 | 08/11/2024
TO-24-110 kV A2 @ SNU-04 | BUSBAR SECTION - SNUGBOROUGH 110-SNUGBOROUGH 110-110A2 | 5 | 5 | 5 | Scheduled | 21/10/2024 | 25/10/2024
TO-24-110 kV B2 @ SNU-05 | BUSBAR SECTION - SNUGBOROUGH 110-SNUGBOROUGH 110-110B2 | 5 | 5 | 5 | Scheduled | 21/10/2024 | 25/10/2024
TO-24-SNU-110K2-06 | COUPLER/SECTIONALISING CB - SNUGBOROUGH 110-SNUGBOROUGH 110-110K2 | 5 | 5 | 5 | Scheduled | 21/10/2024 | 25/10/2024
TO-24-SNU-110SA1-2CB-09 | COUPLER/SECTIONALISING CB - SNUGBOROUGH 110-SNUGBOROUGH 110-110SA1-2CB | 5 | 5 | 5 | Scheduled | 21/10/2024 | 25/10/2024
TO-24-SNU-110SB1-2CB-10 | COUPLER/SECTIONALISING CB - SNUGBOROUGH 110-SNUGBOROUGH 110-110SB1-2CB | 5 | 5 | 5 | Scheduled | 21/10/2024 | 25/10/2024
TO-24-SNU-T102-04 | TSO CUSTOMER TRANSFORMER - SNUGBOROUGH 110-SNUGBOROUGH 10-T102 | 5 | 5 | 5 | Scheduled | 21/10/2024 | 25/10/2024
TO-24-KTL-T142-01 | DISTRIBUTION TRANSFORMER - KILTEEL 110-KILTEEL 38-T142 | 2 | 2 | 2 | Reference | 22/10/2024 | 23/10/2024
TO-24-FIN GIS-110K1-01 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110K1 | 1 | 1 | 1 | Scheduled | 23/10/2024 | 23/10/2024
TO-24-CLG-T122-01 | TSO CUSTOMER TRANSFORMER - CLOGHRAN 110-CLOGHRAN 20-T122 | 2 | 2 | 2 | Proposed | 29/10/2024 | 30/10/2024
TO-24-CDU-MCE-1-04 | 110kV FEEDER - CORDUFF 110-MACETOWN 110-1 | 4 | 4 | 4 | Proposed | 29/10/2024 | 01/11/2024
TO-24-KTL-MAY-1-02 | 110kV FEEDER - KILTEEL 110-MAYNOOTH 110-1 | 25 | 19 | 19 | Scheduled | 29/10/2024 | 22/11/2024
TO-24-110 kV A2 @ SNU-05 | BUSBAR SECTION - SNUGBOROUGH 110-SNUGBOROUGH 110-110A2 | 11 | 9 | 9 | Scheduled | 29/10/2024 | 08/11/2024
TO-24-110 kV B2 @ SNU-06 | BUSBAR SECTION - SNUGBOROUGH 110-SNUGBOROUGH 110-110B2 | 11 | 9 | 9 | Scheduled | 29/10/2024 | 08/11/2024
TO-24-SNU-110K2-07 | COUPLER/SECTIONALISING CB - SNUGBOROUGH 110-SNUGBOROUGH 110-110K2 | 11 | 9 | 9 | Scheduled | 29/10/2024 | 08/11/2024
TO-24-SNU-110SA1-2CB-10 | COUPLER/SECTIONALISING CB - SNUGBOROUGH 110-SNUGBOROUGH 110-110SA1-2CB | 11 | 9 | 9 | Scheduled | 29/10/2024 | 08/11/2024
TO-24-SNU-110SB1-2CB-11 | COUPLER/SECTIONALISING CB - SNUGBOROUGH 110-SNUGBOROUGH 110-110SB1-2CB | 11 | 9 | 9 | Scheduled | 29/10/2024 | 08/11/2024
TO-24-SNU-T104-01 | TSO CUSTOMER TRANSFORMER - SNUGBOROUGH 110-SNUGBOROUGH 10-T104 | 11 | 9 | 9 | Scheduled | 29/10/2024 | 08/11/2024
TO-24-CBT-CLU-1-01 | 110kV FEEDER - CASTLEBAGOT 110-CLUTTERLAND 110-1 | 3 | 3 | 3 | Scheduled | 30/10/2024 | 01/11/2024
TO-24-CLG-T124-01 | TSO CUSTOMER TRANSFORMER - CLOGHRAN 110-CLOGHRAN 20-T124 | 2 | 2 | 2 | Proposed | 30/10/2024 | 31/10/2024
TO-24-220 kV A1 @ CBT-01 | BUSBAR SECTION - CASTLEBAGOT 220-CASTLEBAGOT 220-220A1 | 26 | 18 | 18 | Proposed | 31/10/2024 | 25/11/2024
TO-24-220 kV B1 @ CBT-03 | BUSBAR SECTION - CASTLEBAGOT 220-CASTLEBAGOT 220-220B1 | 26 | 18 | 18 | Proposed | 31/10/2024 | 25/11/2024
TO-24-CBT-220K1-03 | COUPLER/SECTIONALISING CB - CASTLEBAGOT 220-CASTLEBAGOT 220-220K1 | 26 | 18 | 18 | Proposed | 31/10/2024 | 25/11/2024
TO-24-CBT-220SA1-2CB-06 | COUPLER/SECTIONALISING CB - CASTLEBAGOT 220-CASTLEBAGOT 220-220SA1-2CB | 26 | 18 | 18 | Proposed | 31/10/2024 | 25/11/2024
TO-24-CBT-220SB1-2CB-06 | COUPLER/SECTIONALISING CB - CASTLEBAGOT 220-CASTLEBAGOT 220-220SB1-2CB | 26 | 18 | 18 | Proposed | 31/10/2024 | 25/11/2024
TO-24-CBT-INC-1-05 | 220kV FEEDER - CASTLEBAGOT 220-INCHICORE 220-1 | 21 | 15 | 15 | Proposed | 31/10/2024 | 20/11/2024
TO-24-CBT-INC-1-02 | 220kV FEEDER - CASTLEBAGOT 220-INCHICORE 220-1 | 21 | 15 |  | Proposed | 31/10/2024 | 20/11/2024
TO-24-CBT-INC-1-03 | 220kV FEEDER - CASTLEBAGOT 220-INCHICORE 220-1 | 21 | 15 | 15 | Proposed | 31/10/2024 | 20/11/2024
TO-24-INC-MAY-2-07 | 220kV FEEDER - INCHICORE 220-MAYNOOTH 220-2 | 21 | 15 | 15 | Proposed | 31/10/2024 | 20/11/2024
TO-24-WOO-T4202-03 | TRANSFORMER - WOODLAND 400-WOODLAND 220-T4202 | 12 | 10 | 10 | Scheduled | 04/11/2024 | 15/11/2024
TO-24-BLU-T131-02 | GENERATOR TRANSFORMER - BLUNDELSTOWN 110-BLUNDELSTOWN 33-T131 | 2 | 2 | 2 | Proposed | 05/11/2024 | 06/11/2024
TO-24-110 kV A1 @ FIN-01 | BUSBAR SECTION - FINGLAS 110-FINGLAS 110-110A1 | 12 | 10 | 10 | Scheduled | 11/11/2024 | 22/11/2024
TO-24-110 kV A2 @ FIN-04 | BUSBAR SECTION - FINGLAS 110-FINGLAS 110-110A2 | 12 | 10 | 10 | Scheduled | 11/11/2024 | 22/11/2024
TO-24-110 kV B1 @ FIN-01 | BUSBAR SECTION - FINGLAS 110-FINGLAS 110-110B1 | 12 | 10 | 10 | Scheduled | 11/11/2024 | 22/11/2024
TO-24-110 kV B2 @ FIN-04 | BUSBAR SECTION - FINGLAS 110-FINGLAS 110-110B2 | 12 | 10 | 10 | Scheduled | 11/11/2024 | 22/11/2024
TO-24-FIN-110K1-2-01 | COUPLER/SECTIONALISING CB - FINGLAS 110-FINGLAS 110-110K1-2 | 12 | 10 | 10 | Scheduled | 11/11/2024 | 22/11/2024
TO-24-RYB GIS-T104-03 | TSO CUSTOMER TRANSFORMER - RYEBROOK GIS 110-RYEBROOK 10-T104 | 19 | 15 | 15 | Scheduled | 11/11/2024 | 29/11/2024
TO-24-CLE-T224-01 | TSO CUSTOMER TRANSFORMER - CLONEE 220-CLONEE 20-T224 | 1 | 1 | 1 | Scheduled | 12/11/2024 | 12/11/2024
TO-24-BLU-MUL-1-06 | 110kV FEEDER - BLUNDELSTOWN 110-MULLINGAR 110-1 | 12 | 10 | 10 | Proposed | 18/11/2024 | 29/11/2024
TO-24-BLU-MUL-1-02 | 110kV FEEDER - BLUNDELSTOWN 110-MULLINGAR 110-1 | 12 | 10 | 10 | Scheduled | 18/11/2024 | 29/11/2024
TO-24-PB-T2007/8-04 | GENERATOR TRANSFORMER - POOLBEG 220-POOLBEG G7/8-T2007/8 | 12 | 10 | 10 | Proposed | 18/11/2024 | 29/11/2024
TO-24-BRT-220K2-01 | COUPLER/SECTIONALISING CB - BRACETOWN 220-BRACETOWN 220-220K2 | 1 | 1 | 1 | Proposed | 20/11/2024 | 20/11/2024
TO-24-BRT-CLE-2-02 | 220kV FEEDER - BRACETOWN 220-CLONEE 220-2 | 1 | 1 | 1 | Proposed | 21/11/2024 | 21/11/2024
TO-24-MCE-T124-04 | TSO CUSTOMER TRANSFORMER - MACETOWN 110-MACETOWN 20-T124 | 9 | 6 | 6 | Scheduled | 22/11/2024 | 30/11/2024
TO-24-110 kV A1 @ AUN-03 | BUSBAR SECTION - AUNGIERSTOWN 110-AUNGIERSTOWN 110-110A1 | 5 | 5 | 5 | Scheduled | 25/11/2024 | 29/11/2024
TO-24-110 kV B1 @ AUN-03 | BUSBAR SECTION - AUNGIERSTOWN 110-AUNGIERSTOWN 110-110B1 | 5 | 5 | 5 | Scheduled | 25/11/2024 | 29/11/2024
TO-24-AUN-110K1-03 | COUPLER/SECTIONALISING CB - AUNGIERSTOWN 110-AUNGIERSTOWN 110-110K1 | 5 | 5 | 5 | Scheduled | 25/11/2024 | 29/11/2024
TO-24-AUN-110SA1-2CB-04 | COUPLER/SECTIONALISING CB - AUNGIERSTOWN 110-AUNGIERSTOWN 110-110SA1-2CB | 5 | 5 | 5 | Scheduled | 25/11/2024 | 29/11/2024
TO-24-AUN-110SB1-2CB-03 | COUPLER/SECTIONALISING CB - AUNGIERSTOWN 110-AUNGIERSTOWN 110-110SB1-2CB | 5 | 5 | 5 | Scheduled | 25/11/2024 | 29/11/2024
TO-24-AUN-CBT-1-01 | 110kV FEEDER - AUNGIERSTOWN 110-CASTLEBAGOT 110-1 | 5 | 5 | 5 | Scheduled | 25/11/2024 | 29/11/2024
TO-24-110 kV A1 @ CBT-01 | BUSBAR SECTION - CASTLEBAGOT 110-CASTLEBAGOT 110-110A1 | 5 | 5 | 5 | Scheduled | 25/11/2024 | 29/11/2024
TO-24-110 kV B1 @ CBT-01 | BUSBAR SECTION - CASTLEBAGOT 110-CASTLEBAGOT 110-110B1 | 5 | 5 | 5 | Scheduled | 25/11/2024 | 29/11/2024
TO-24-CBT-110K1-01 | COUPLER/SECTIONALISING CB - CASTLEBAGOT 110-CASTLEBAGOT 110-110K1 | 5 | 5 | 5 | Scheduled | 25/11/2024 | 29/11/2024
TO-24-CBT-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - CASTLEBAGOT 110-CASTLEBAGOT 110-110SA1-2CB | 5 | 5 | 5 | Scheduled | 25/11/2024 | 29/11/2024
TO-24-CBT-110SB1-2CB-01 | COUPLER/SECTIONALISING CB - CASTLEBAGOT 110-CASTLEBAGOT 110-110SB1-2CB | 5 | 5 | 5 | Scheduled | 25/11/2024 | 29/11/2024
TO-24-220 kV A2 @ CBT-01 | BUSBAR SECTION - CASTLEBAGOT 220-CASTLEBAGOT 220-220A2 | 3 | 3 | 3 | Proposed | 25/11/2024 | 27/11/2024
TO-24-220 kV B2 @ CBT-01 | BUSBAR SECTION - CASTLEBAGOT 220-CASTLEBAGOT 220-220B2 | 3 | 3 | 3 | Proposed | 25/11/2024 | 27/11/2024
TO-24-CBT-220K2-01 | COUPLER/SECTIONALISING CB - CASTLEBAGOT 220-CASTLEBAGOT 220-220K2 | 3 | 3 | 3 | Proposed | 25/11/2024 | 27/11/2024
TO-24-CBT-220SA1-2CB-01 | COUPLER/SECTIONALISING CB - CASTLEBAGOT 220-CASTLEBAGOT 220-220SA1-2CB | 3 | 3 | 3 | Proposed | 25/11/2024 | 27/11/2024
TO-24-CBT-220SB1-2CB-01 | COUPLER/SECTIONALISING CB - CASTLEBAGOT 220-CASTLEBAGOT 220-220SB1-2CB | 3 | 3 | 3 | Proposed | 25/11/2024 | 27/11/2024
TO-24-KTL-MON-1-01 | 110kV FEEDER - KILTEEL 110-MONREAD 110-1 | 5 | 5 | 5 | Scheduled | 25/11/2024 | 29/11/2024
TO-24-220 kV A2 @ MAY-03 | BUSBAR SECTION - MAYNOOTH 220-MAYNOOTH 220-220A2 | 2 | 2 | 2 | Proposed | 28/11/2024 | 29/11/2024
TO-24-220 kV B2 @ MAY-03 | BUSBAR SECTION - MAYNOOTH 220-MAYNOOTH 220-220B2 | 2 | 2 | 2 | Proposed | 28/11/2024 | 29/11/2024
TO-24-MAY-RYB GIS-1-03 | 110kV FEEDER - MAYNOOTH 110-RYEBROOK GIS 110-1 | 1 | 1 | 1 | Proposed | 29/11/2024 | 29/11/2024
TO-24-PB-R2001-04 | CAPACITOR/SVC/REACTOR - POOLBEG 220-POOLBEG 220-R2001 | Unknown | Unknown |  | Planned | December | December
TO-24-220 kV A2 @ CBT-02 | BUSBAR SECTION - CASTLEBAGOT 220-CASTLEBAGOT 220-220A2 | 2 | 2 | 2 | Proposed | 05/12/2024 | 06/12/2024
TO-24-220 kV B2 @ CBT-02 | BUSBAR SECTION - CASTLEBAGOT 220-CASTLEBAGOT 220-220B2 | 2 | 2 | 2 | Proposed | 05/12/2024 | 06/12/2024
TO-24-CBT-220K2-02 | COUPLER/SECTIONALISING CB - CASTLEBAGOT 220-CASTLEBAGOT 220-220K2 | 2 | 2 | 2 | Proposed | 05/12/2024 | 06/12/2024
TO-24-CBT-220SA1-2CB-02 | COUPLER/SECTIONALISING CB - CASTLEBAGOT 220-CASTLEBAGOT 220-220SA1-2CB | 2 | 2 | 2 | Proposed | 05/12/2024 | 06/12/2024
TO-24-CBT-220SB1-2CB-02 | COUPLER/SECTIONALISING CB - CASTLEBAGOT 220-CASTLEBAGOT 220-220SB1-2CB | 2 | 2 | 2 | Proposed | 05/12/2024 | 06/12/2024
TO-24-INC-MAY-2-09 | 220kV FEEDER - INCHICORE 220-MAYNOOTH 220-2 | 2 | 2 | 2 | Proposed | 05/12/2024 | 06/12/2024

## GEN_Cork
Outage ID | Feeder ID | Calendar Day Duration | Working Day Duration | Work Days | Outage Status | Start | Finish
TO-24-KRA-220SA2-4CB-01 | COUPLER/SECTIONALISING CB - KNOCKRAHA 220-KNOCKRAHA 220-220SA2-4CB | 1 | 1 | 1 | Scheduled | 07/02/2024 | 07/02/2024
TO-24-KRA-220K4-01 | COUPLER/SECTIONALISING CB - KNOCKRAHA 220-KNOCKRAHA 220-220K4 | 1 | 1 | 1 | Scheduled | 09/02/2024 | 09/02/2024
TO-24-COW-WHI-1-03 | 110kV FEEDER - COW CROSS 110-WHITEGATE 110-1 | 5 | 5 | 5 | Scheduled | 12/02/2024 | 16/02/2024
TO-24-LYT-T132-01 | GENERATOR TRANSFORMER - LYSAGHTSTOWN 110-LYSAGHTSTOWN 33-T132 | 1 | 1 | 1 | Scheduled | 19/02/2024 | 19/02/2024
TO-24-RAF-TBG-2-02 | 110kV FEEDER - RAFFEEN 110-TRABEG 110-2 | 5 | 5 | 5 | Scheduled | 19/02/2024 | 23/02/2024
TO-24-KRA-110K1-2-01 | COUPLER/SECTIONALISING CB - KNOCKRAHA 110-KNOCKRAHA 110-110K1-2 | 1 | 1 | 1 | Scheduled | 20/02/2024 | 20/02/2024
TO-24-AD-LPT-1-01 | 220kV FEEDER - AGHADA 220-LONG POINT 220-1 | 78 | 52 | 52 | Scheduled | 26/02/2024 | 13/05/2024
TO-24-CVW-COW-1-01 | 110kV FEEDER - CASTLEVIEW 110-COW CROSS 110-1 | 5 | 5 | 5 | Scheduled | 26/02/2024 | 01/03/2024
TO-24-LPT-T2002-02 | GENERATOR TRANSFORMER - LONG POINT 220-LONG POINT G1-T2002 | 100 | 67 | 67 | Scheduled | 26/02/2024 | 04/06/2024
TO-24-110 kV A1 @ RAF-02 | BUSBAR SECTION - RAFFEEN 110-RAFFEEN 110-110A1 | 5 | 5 | 5 | Scheduled | 26/02/2024 | 01/03/2024
TO-24-110 kV B1 @ RAF-02 | BUSBAR SECTION - RAFFEEN 110-RAFFEEN 110-110B1 | 5 | 5 | 5 | Scheduled | 26/02/2024 | 01/03/2024
TO-24-220 kV A1 @ RAF-02 | BUSBAR SECTION - RAFFEEN 220-RAFFEEN 220-220A1 | 5 | 5 | 5 | Scheduled | 26/02/2024 | 01/03/2024
TO-24-220 kV B1 @ RAF-02 | BUSBAR SECTION - RAFFEEN 220-RAFFEEN 220-220B1 | 5 | 5 | 5 | Scheduled | 26/02/2024 | 01/03/2024
TO-24-220 kV A2 @ AD-04 | BUSBAR SECTION - AGHADA 220-AGHADA 220-220A2 | 12 | 10 | 10 | Scheduled | 04/03/2024 | 15/03/2024
TO-24-220 kV B2 @ AD-04 | BUSBAR SECTION - AGHADA 220-AGHADA 220-220B2 | 12 | 10 | 10 | Scheduled | 04/03/2024 | 15/03/2024
TO-24-AD-SA1-2CB-06 | COUPLER/SECTIONALISING CB - AGHADA 220-AGHADA 220-220SA1-2CB | 12 | 10 | 10 | Scheduled | 04/03/2024 | 15/03/2024
TO-24-AD-SB1-2CB-06 | COUPLER/SECTIONALISING CB - AGHADA 220-AGHADA 220-220SB1-2CB | 12 | 10 | 10 | Scheduled | 04/03/2024 | 15/03/2024
TO-24-AD-KRA-2-01 | 220kV FEEDER - AGHADA 220-KNOCKRAHA 220-2 | 12 | 10 |  | Scheduled | 04/03/2024 | 15/03/2024
TO-24-COW-WHI-1-01 | 110kV FEEDER - COW CROSS 110-WHITEGATE 110-1 | 5 | 5 | 5 | Scheduled | 04/03/2024 | 08/03/2024
TO-24-220 kV A1 @ KRA-02 | BUSBAR SECTION - KNOCKRAHA 220-KNOCKRAHA 220-220A1 | 12 | 10 | 10 | Scheduled | 04/03/2024 | 15/03/2024
TO-24-220 kV B1 @ KRA-02 | BUSBAR SECTION - KNOCKRAHA 220-KNOCKRAHA 220-220B1 | 12 | 10 | 10 | Scheduled | 04/03/2024 | 15/03/2024
TO-24-KRA-220K1-03 | COUPLER/SECTIONALISING CB - KNOCKRAHA 220-KNOCKRAHA 220-220K1 | 12 | 10 | 10 | Scheduled | 04/03/2024 | 15/03/2024
TO-24-KRA-220SA1-2CB-03 | COUPLER/SECTIONALISING CB - KNOCKRAHA 220-KNOCKRAHA 220-220SA1-2CB | 12 | 10 | 10 | Scheduled | 04/03/2024 | 15/03/2024
TO-24-KRA-220SB1-2CB-03 | COUPLER/SECTIONALISING CB - KNOCKRAHA 220-KNOCKRAHA 220-220SB1-2CB | 12 | 10 | 10 | Scheduled | 04/03/2024 | 15/03/2024
TO-24-RAF-RSY-1-01 | 110kV FEEDER - RAFFEEN 110-RINGASKIDDY 110-1 | 12 | 10 |  | Reference | 04/03/2024 | 15/03/2024
TO-24-KRA-220K4-02 | COUPLER/SECTIONALISING CB - KNOCKRAHA 220-KNOCKRAHA 220-220K4 | 85 | 57 | 57 | Scheduled | 05/03/2024 | 28/05/2024
TO-24-KRA-220SA2-4CB-02 | COUPLER/SECTIONALISING CB - KNOCKRAHA 220-KNOCKRAHA 220-220SA2-4CB | 85 | 57 | 57 | Scheduled | 05/03/2024 | 28/05/2024
TO-24-KRA-220SB2-4CB-01 | COUPLER/SECTIONALISING CB - KNOCKRAHA 220-KNOCKRAHA 220-220SB2-4CB | 85 | 57 | 57 | Scheduled | 05/03/2024 | 28/05/2024
TO-24-220 kV A1 @ AD-03 | BUSBAR SECTION - AGHADA 220-AGHADA 220-220A1 | 5 | 5 | 5 | Scheduled | 11/03/2024 | 15/03/2024
TO-24-220 kV B1 @ AD-02 | BUSBAR SECTION - AGHADA 220-AGHADA 220-220B1 | 5 | 5 | 5 | Scheduled | 11/03/2024 | 15/03/2024
TO-24-AD-220K1-04 | COUPLER/SECTIONALISING CB - AGHADA 220-AGHADA 220-220K1 | 5 | 5 | 5 | Scheduled | 11/03/2024 | 15/03/2024
TO-24-AD-SA1-2CB-03 | COUPLER/SECTIONALISING CB - AGHADA 220-AGHADA 220-220SA1-2CB | 5 | 5 | 5 | Scheduled | 11/03/2024 | 15/03/2024
TO-24-AD-SB1-2CB-03 | COUPLER/SECTIONALISING CB - AGHADA 220-AGHADA 220-220SB1-2CB | 5 | 5 | 5 | Scheduled | 11/03/2024 | 15/03/2024
TO-24-COW-RAF-1-02 | 110kV FEEDER - COW CROSS 110-RAFFEEN 110-1 | 5 | 5 | 5 | Scheduled | 11/03/2024 | 15/03/2024
TO-24-LPT-T2002-01 | GENERATOR TRANSFORMER - LONG POINT 220-LONG POINT G1-T2002 | 5 | 5 | 5 | Scheduled | 11/03/2024 | 15/03/2024
TO-24-BAN-110SA1-01 | SECTIONALISING DISCONNECT - BANDON 110-BANDON 110-110SA1 | 15 | 10 | 10 | Scheduled | 14/03/2024 | 28/03/2024
TO-24-BAN-110SA2-02 | SECTIONALISING DISCONNECT - BANDON 110-BANDON 110-110SA2 | 15 | 10 | 10 | Scheduled | 14/03/2024 | 28/03/2024
TO-24-BAN-BRI-1-01 | 110kV FEEDER - BANDON 110-BRINNY 110-1 | 15 | 10 | 10 | Scheduled | 14/03/2024 | 28/03/2024
TO-24-BAN-CAP1-02 | CAPACITOR/SVC/REACTOR - BANDON 110-BANDON 110-CAP1 | 15 | 10 | 10 | Scheduled | 14/03/2024 | 28/03/2024
TO-24-BAN-DMY-1-02 | 110kV FEEDER - BANDON 110-DUNMANWAY 110-1 | 15 | 10 | 10 | Scheduled | 14/03/2024 | 28/03/2024
TO-24-BAN-T101-01 | DISTRIBUTION TRANSFORMER - BANDON 110-BANDON 10-T101 | 15 | 10 | 10 | Reference | 14/03/2024 | 28/03/2024
TO-24-BAN-T141-01 | DISTRIBUTION TRANSFORMER - BANDON 110-BANDON 38-T141 | 15 | 10 | 10 | Reference | 14/03/2024 | 28/03/2024
TO-24-BRI-T101-02 | TSO CUSTOMER TRANSFORMER - BRINNY 110-BRINNY 10-T101 | 15 | 10 | 10 | Scheduled | 14/03/2024 | 28/03/2024
TO-24-220 kV A1 @ AD-02 | BUSBAR SECTION - AGHADA 220-AGHADA 220-220A1 | 16 | 10 | 10 | Scheduled | 19/03/2024 | 03/04/2024
TO-24-220 kV A2 @ AD-01 | BUSBAR SECTION - AGHADA 220-AGHADA 220-220A2 | 16 | 10 | 10 | Scheduled | 19/03/2024 | 03/04/2024
TO-24-220 kV B1 @ AD-01 | BUSBAR SECTION - AGHADA 220-AGHADA 220-220B1 | 16 | 10 | 10 | Scheduled | 19/03/2024 | 03/04/2024
TO-24-220 kV B2 @ AD-01 | BUSBAR SECTION - AGHADA 220-AGHADA 220-220B2 | 16 | 10 | 10 | Scheduled | 19/03/2024 | 03/04/2024
TO-24-AD-220K1-03 | COUPLER/SECTIONALISING CB - AGHADA 220-AGHADA 220-220K1 | 16 | 10 | 10 | Scheduled | 19/03/2024 | 03/04/2024
TO-24-AD-SA1-2CB-01 | COUPLER/SECTIONALISING CB - AGHADA 220-AGHADA 220-220SA1-2CB | 16 | 10 | 10 | Scheduled | 19/03/2024 | 03/04/2024
TO-24-AD-SB1-2CB-01 | COUPLER/SECTIONALISING CB - AGHADA 220-AGHADA 220-220SB1-2CB | 16 | 10 | 10 | Scheduled | 19/03/2024 | 03/04/2024
TO-24-AD-KRA-1-01 | 220kV FEEDER - AGHADA 220-KNOCKRAHA 220-1 | 16 | 10 |  | Scheduled | 19/03/2024 | 03/04/2024
TO-24-AD-T2102-01 | TRANSFORMER - AGHADA 220-AGHADA 110-T2102 | 16 | 10 | 10 | Scheduled | 19/03/2024 | 03/04/2024
TO-24-CGG-DMY-1-01 | 110kV FEEDER - CARRIGDANGAN 110-DUNMANWAY 110-1 | 7 | 5 | 5 | Scheduled | 19/03/2024 | 25/03/2024
TO-24-CGG-T131-01 | GENERATOR TRANSFORMER - CARRIGDANGAN 110-CARRIGDANGAN 33-T131 | 7 | 5 | 5 | Scheduled | 19/03/2024 | 25/03/2024
TO-24-110 kV A2 @ CLA-01 | BUSBAR SECTION - CLASHAVOON 110-CLASHAVOON 110-110A2 | 10 | 8 | 8 | Scheduled | 19/03/2024 | 28/03/2024
TO-24-110 kV B2 @ CLA-01 | BUSBAR SECTION - CLASHAVOON 110-CLASHAVOON 110-110B2 | 10 | 8 | 8 | Scheduled | 19/03/2024 | 28/03/2024
TO-24-CLA-MAC-2-03 | 110kV FEEDER - CLASHAVOON 110-MACROOM 110-2 | 10 | 8 | 8 | Scheduled | 19/03/2024 | 28/03/2024
TO-24-220 kV A2 @ KRA-02 | BUSBAR SECTION - KNOCKRAHA 220-KNOCKRAHA 220-220A2 | 16 | 10 | 10 | Scheduled | 19/03/2024 | 03/04/2024
TO-24-220 kV B2 @ KRA-02 | BUSBAR SECTION - KNOCKRAHA 220-KNOCKRAHA 220-220B2 | 16 | 10 | 10 | Scheduled | 19/03/2024 | 03/04/2024
TO-24-KRA-220SA1-2CB-02 | COUPLER/SECTIONALISING CB - KNOCKRAHA 220-KNOCKRAHA 220-220SA1-2CB | 16 | 10 | 10 | Scheduled | 19/03/2024 | 03/04/2024
TO-24-KRA-220SB1-2CB-02 | COUPLER/SECTIONALISING CB - KNOCKRAHA 220-KNOCKRAHA 220-220SB1-2CB | 16 | 10 | 10 | Scheduled | 19/03/2024 | 03/04/2024
TO-24-CUL-KRA-1-01 | 220kV FEEDER - CULLENAGH 220-KNOCKRAHA 220-1 | 55 | 38 | 38 | Scheduled | 04/04/2024 | 28/05/2024
TO-24-220 kV A2 @ KRA-01 | BUSBAR SECTION - KNOCKRAHA 220-KNOCKRAHA 220-220A2 | 55 | 38 | 38 | Scheduled | 04/04/2024 | 28/05/2024
TO-24-220 kV B2 @ KRA-01 | BUSBAR SECTION - KNOCKRAHA 220-KNOCKRAHA 220-220B2 | 55 | 38 | 38 | Scheduled | 04/04/2024 | 28/05/2024
TO-24-KRA-220SA1-2CB-01 | COUPLER/SECTIONALISING CB - KNOCKRAHA 220-KNOCKRAHA 220-220SA1-2CB | 55 | 38 | 38 | Scheduled | 04/04/2024 | 28/05/2024
TO-24-KRA-220SB1-2CB-01 | COUPLER/SECTIONALISING CB - KNOCKRAHA 220-KNOCKRAHA 220-220SB1-2CB | 55 | 38 | 38 | Scheduled | 04/04/2024 | 28/05/2024
TO-24-KRA-RAF-1-01 | 220kV FEEDER - KNOCKRAHA 220-RAFFEEN 220-1 | 55 | 38 | 38 | Scheduled | 04/04/2024 | 28/05/2024
TO-24-CRO-110SA1-01 | SECTIONALISING DISCONNECT - COOLROE 110-COOLROE 110-110SA1 | 5 | 5 | 5 | Scheduled | 08/04/2024 | 12/04/2024
TO-24-CRO-110SA2-02 | SECTIONALISING DISCONNECT - COOLROE 110-COOLROE 110-110SA2 | 5 | 5 | 5 | Scheduled | 08/04/2024 | 12/04/2024
TO-24-CRO-KBY-1-01 | 110kV FEEDER - COOLROE 110-KILBARRY 110-1 | 5 | 5 |  | Scheduled | 08/04/2024 | 12/04/2024
TO-24-CRO-T121-01 | DISTRIBUTION TRANSFORMER - COOLROE 110-COOLROE 20-T121 | 5 | 5 | 5 | Reference | 08/04/2024 | 12/04/2024
TO-24-220 kV A1 @ RAF-03 | BUSBAR SECTION - RAFFEEN 220-RAFFEEN 220-220A1 | 5 | 5 | 5 | Scheduled | 08/04/2024 | 12/04/2024
TO-24-220 kV B1 @ RAF-03 | BUSBAR SECTION - RAFFEEN 220-RAFFEEN 220-220B1 | 5 | 5 | 5 | Scheduled | 08/04/2024 | 12/04/2024
TO-24-BGH-T132-02 | GENERATOR TRANSFORMER - BOGGERAGH 110-BOGGERAGH 33-T132 | 2 | 2 | 2 | Scheduled | 15/04/2024 | 16/04/2024
TO-24-CRO-110SA1-02 | SECTIONALISING DISCONNECT - COOLROE 110-COOLROE 110-110SA1 | 5 | 5 | 5 | Scheduled | 15/04/2024 | 19/04/2024
TO-24-CRO-110SA2-01 | SECTIONALISING DISCONNECT - COOLROE 110-COOLROE 110-110SA2 | 5 | 5 | 5 | Scheduled | 15/04/2024 | 19/04/2024
TO-24-CRO-IA-1-01 | 110kV FEEDER - COOLROE 110-INNISCARRA 110-1 | 5 | 5 | 5 | Scheduled | 15/04/2024 | 19/04/2024
TO-24-CRO-T122-01 | DISTRIBUTION TRANSFORMER - COOLROE 110-COOLROE 20-T122 | 5 | 5 | 5 | Reference | 15/04/2024 | 19/04/2024
TO-24-AD-ST101-01 | GENERATOR TRANSFORMER - AGHADA 110-AGHADA 10-ST101 | 10 | 8 | 8 | Scheduled | 22/04/2024 | 01/05/2024
TO-24-AD-WHI-1-03 | 110kV FEEDER - AGHADA 110-WHITEGATE 110-1 | 5 | 5 | 5 | Scheduled | 22/04/2024 | 26/04/2024
TO-24-CD-KBY-1-01 | 110kV FEEDER - CARRIGADROHID 110-KILBARRY 110-1 | 12 | 10 | 10 | Scheduled | 22/04/2024 | 03/05/2024
TO-24-110 kV A2 @ RAF-02 | BUSBAR SECTION - RAFFEEN 110-RAFFEEN 110-110A2 | 215 | 151 | 151 | Scheduled | 29/04/2024 | 29/11/2024
TO-24-110 kV B2 @ RAF-02 | BUSBAR SECTION - RAFFEEN 110-RAFFEEN 110-110B2 | 215 | 151 | 151 | Scheduled | 29/04/2024 | 29/11/2024
TO-24-CRO-IA-1-04 | 110kV FEEDER - COOLROE 110-INNISCARRA 110-1 | 1 | 1 | 1 | Scheduled | 30/04/2024 | 30/04/2024
TO-24-110 kV A1 @ IA-02 | BUSBAR SECTION - INNISCARRA 110-INNISCARRA 110-110A1 | 1 | 1 | 1 | Scheduled | 30/04/2024 | 30/04/2024
TO-24-IA-MAC-1-04 | 110kV FEEDER - INNISCARRA 110-MACROOM 110-1 | 1 | 1 | 1 | Scheduled | 30/04/2024 | 30/04/2024
TO-24-IA-T101-04 | GENERATOR TRANSFORMER - INNISCARRA 110-INNISCARRA G1-T101 | 1 | 1 | 1 | Scheduled | 30/04/2024 | 30/04/2024
TO-24-AD-220K1-02 | COUPLER/SECTIONALISING CB - AGHADA 220-AGHADA 220-220K1 | 1 | 1 | 1 | Scheduled | 08/05/2024 | 08/05/2024
TO-24-RAF-110K1-2-01 | COUPLER/SECTIONALISING CB - RAFFEEN 110-RAFFEEN 110-110K1-2 | 3 | 3 | 3 | Scheduled | 13/05/2024 | 15/05/2024
TO-24-CRO-IA-1-02 | 110kV FEEDER - COOLROE 110-INNISCARRA 110-1 | 7 | 5 | 5 | Scheduled | 14/05/2024 | 20/05/2024
TO-24-IA-MAC-1-01 | 110kV FEEDER - INNISCARRA 110-MACROOM 110-1 | 7 | 5 | 5 | Scheduled | 14/05/2024 | 20/05/2024
TO-24-IA-T101-01 | GENERATOR TRANSFORMER - INNISCARRA 110-INNISCARRA G1-T101 | 10 | 8 | 8 | Scheduled | 14/05/2024 | 23/05/2024
TO-24-CRO-T121-02 | DISTRIBUTION TRANSFORMER - COOLROE 110-COOLROE 20-T121 | 117 | 83 | 83 | Reference | 20/05/2024 | 13/09/2024
TO-24-KBY-MR-1-02 | 110kV FEEDER - KILBARRY 110-MARINA 110-1 | 107 | 75 | 75 | Scheduled | 27/05/2024 | 10/09/2024
TO-24-KBY-MR-2-02 | 110kV FEEDER - KILBARRY 110-MARINA 110-2 | 107 | 75 | 75 | Scheduled | 27/05/2024 | 10/09/2024
TO-24-CLA-MAC-1-02 | 110kV FEEDER - CLASHAVOON 110-MACROOM 110-1 | 5 | 5 | 5 | Scheduled | 10/06/2024 | 14/06/2024
TO-24-CHA-MAL-1-01 | 110kV FEEDER - CHARLEVILLE 110-MALLOW 110-1 | 14 | 10 | 10 | Scheduled | 11/06/2024 | 24/06/2024
TO-24-KRA-WOH-1-02 | 110kV FEEDER - KNOCKRAHA 110-WOODHOUSE 110-1 | 12 | 10 | 10 | Scheduled | 17/06/2024 | 28/06/2024
TO-24-220 kV B1 @ AD-03 | BUSBAR SECTION - AGHADA 220-AGHADA 220-220B1 | 1 | 1 | 1 | Scheduled | 20/06/2024 | 20/06/2024
TO-24-AD-T2011/12-03 | GENERATOR TRANSFORMER - AGHADA 220-AGHADA G11/12-T2011/12 | 1 | 1 | 1 | Scheduled | 20/06/2024 | 20/06/2024
TO-24-DMY-MAC-1-03 | 110kV FEEDER - DUNMANWAY 110-MACROOM 110-1 | 5 | 5 | 5 | Scheduled | 24/06/2024 | 28/06/2024
TO-24-110 kV A2 @ KBY-01 | BUSBAR SECTION - KILBARRY 110-KILBARRY 110-110A2 | 19 | 15 | 15 | Scheduled | 24/06/2024 | 12/07/2024
TO-24-110 kV B2 @ KBY-01 | BUSBAR SECTION - KILBARRY 110-KILBARRY 110-110B2 | 19 | 15 | 15 | Scheduled | 24/06/2024 | 12/07/2024
TO-24-MID-110SA1-03 | SECTIONALISING DISCONNECT - MIDLETON 110-MIDLETON 110-110SA1 | 12 | 10 | 10 | Scheduled | 01/07/2024 | 12/07/2024
TO-24-MID-110SA2-01 | SECTIONALISING DISCONNECT - MIDLETON 110-MIDLETON 110-110SA2 | 12 | 10 | 10 | Scheduled | 01/07/2024 | 12/07/2024
TO-24-MID-T102-01 | DISTRIBUTION TRANSFORMER - MIDLETON 110-MIDLETON 10-T102 | 12 | 10 | 10 | Reference | 01/07/2024 | 12/07/2024
TO-24-MID-WHI-1-01 | 110kV FEEDER - MIDLETON 110-WHITEGATE 110-1 | 12 | 10 | 10 | Scheduled | 01/07/2024 | 12/07/2024
TO-24-CRO-110SA1-03 | SECTIONALISING DISCONNECT - COOLROE 110-COOLROE 110-110SA1 | 10 | 8 | 8 | Scheduled | 03/07/2024 | 12/07/2024
TO-24-CRO-110SA2-03 | SECTIONALISING DISCONNECT - COOLROE 110-COOLROE 110-110SA2 | 10 | 8 | 8 | Scheduled | 03/07/2024 | 12/07/2024
TO-24-CRO-KBY-1-04 | 110kV FEEDER - COOLROE 110-KILBARRY 110-1 | 10 | 8 | 8 | Scheduled | 03/07/2024 | 12/07/2024
TO-24-CRO-T121-04 | DISTRIBUTION TRANSFORMER - COOLROE 110-COOLROE 20-T121 | 10 | 8 | 8 | Reference | 03/07/2024 | 12/07/2024
TO-24-CLA-CKN-1-01 | 110kV FEEDER - CLASHAVOON 110-CLONKEEN 110-1 | 19 | 15 | 15 | Scheduled | 08/07/2024 | 26/07/2024
TO-24-CLA-220K1-2-02 | COUPLER/SECTIONALISING CB - CLASHAVOON 220-CLASHAVOON 220-220K1-2 | 45 | 32 | 32 | Scheduled | 17/07/2024 | 30/08/2024
TO-24-RAF-T2102-01 | TRANSFORMER - RAFFEEN 220-RAFFEEN 110-T2102 | 8 | 6 | 6 | Scheduled | 22/07/2024 | 29/07/2024
TO-24-WHI-CKB-T101-01 | TSO CUSTOMER TRANSFORMER - WHITEGATE 110-WHITEGATE 10-CKB-T101 | 5 | 5 | 5 | Scheduled | 22/07/2024 | 26/07/2024
TO-24-WHI-CKB-T102-01 | TSO CUSTOMER TRANSFORMER - WHITEGATE 110-WHITEGATE 10-CKB-T102 | 10 | 7 | 7 | Scheduled | 29/07/2024 | 07/08/2024
TO-24-AD-KRA-1-04 | 220kV FEEDER - AGHADA 220-KNOCKRAHA 220-1 | 3 | 3 | 3 | Proposed | 30/07/2024 | 01/08/2024
TO-24-BAN-DMY-1-03 | 110kV FEEDER - BANDON 110-DUNMANWAY 110-1 | 3 | 3 | 3 | Scheduled | 14/08/2024 | 16/08/2024
TO-24-BAN-RAF-1-02 | 110kV FEEDER - BANDON 110-RAFFEEN 110-1 | 5 | 5 | 5 | Scheduled | 19/08/2024 | 23/08/2024
TO-24-BGH-110SA1-01 | SECTIONALISING DISCONNECT - BOGGERAGH 110-BOGGERAGH 110-110SA1 | 12 | 10 | 10 | Scheduled | 19/08/2024 | 30/08/2024
TO-24-BGH-110SA2-01 | SECTIONALISING DISCONNECT - BOGGERAGH 110-BOGGERAGH 110-110SA2 | 12 | 10 | 10 | Scheduled | 19/08/2024 | 30/08/2024
TO-24-BGH-CLA-1-01 | 110kV FEEDER - BOGGERAGH 110-CLASHAVOON 110-1 | 12 | 10 | 10 | Scheduled | 19/08/2024 | 30/08/2024
TO-24-BGH-T121-01 | GENERATOR TRANSFORMER - BOGGERAGH 110-BOGGERAGH 20-T121 | 12 | 10 | 10 | Scheduled | 19/08/2024 | 30/08/2024
TO-24-BGH-T132-01 | GENERATOR TRANSFORMER - BOGGERAGH 110-BOGGERAGH 33-T132 | 12 | 10 | 10 | Scheduled | 19/08/2024 | 30/08/2024
TO-24-BGH-T142-01 | DISTRIBUTION TRANSFORMER - BOGGERAGH 110-BOGGERAGH 38-T142 | 12 | 10 | 10 | Reference | 19/08/2024 | 30/08/2024
TO-24-110 kV A1 @ CLA-01 | BUSBAR SECTION - CLASHAVOON 110-CLASHAVOON 110-110A1 | 12 | 10 | 10 | Scheduled | 19/08/2024 | 30/08/2024
TO-24-110 kV B1 @ CLA-01 | BUSBAR SECTION - CLASHAVOON 110-CLASHAVOON 110-110B1 | 12 | 10 | 10 | Scheduled | 19/08/2024 | 30/08/2024
TO-24-220 kV A1 @ AD-06 | BUSBAR SECTION - AGHADA 220-AGHADA 220-220A1 | 1 | 1 | 1 | Proposed | 20/08/2024 | 20/08/2024
TO-24-AD-T2011/12-06 | GENERATOR TRANSFORMER - AGHADA 220-AGHADA G11/12-T2011/12 | 1 | 1 | 1 | Proposed | 20/08/2024 | 20/08/2024
TO-24-220 kV A1 @ AD-05 | BUSBAR SECTION - AGHADA 220-AGHADA 220-220A1 | 8 | 6 | 6 | Scheduled | 21/08/2024 | 28/08/2024
TO-24-220 kV B1 @ AD-04 | BUSBAR SECTION - AGHADA 220-AGHADA 220-220B1 | 8 | 6 | 6 | Scheduled | 21/08/2024 | 28/08/2024
TO-24-AD-220K1-06 | COUPLER/SECTIONALISING CB - AGHADA 220-AGHADA 220-220K1 | 8 | 6 | 6 | Scheduled | 21/08/2024 | 28/08/2024
TO-24-AD-SA1-2CB-08 | COUPLER/SECTIONALISING CB - AGHADA 220-AGHADA 220-220SA1-2CB | 8 | 6 | 6 | Scheduled | 21/08/2024 | 28/08/2024
TO-24-AD-SB1-2CB-08 | COUPLER/SECTIONALISING CB - AGHADA 220-AGHADA 220-220SB1-2CB | 8 | 6 | 6 | Scheduled | 21/08/2024 | 28/08/2024
TO-24-AD-T2011/12-02 | GENERATOR TRANSFORMER - AGHADA 220-AGHADA G11/12-T2011/12 | 8 | 6 | 6 | Scheduled | 21/08/2024 | 28/08/2024
TO-24-AD-T2014-02 | GENERATOR TRANSFORMER - AGHADA 220-AGHADA G14-T2014 | 8 | 6 | 6 | Scheduled | 21/08/2024 | 28/08/2024
TO-24-CRO-110SA1-05 | SECTIONALISING DISCONNECT - COOLROE 110-COOLROE 110-110SA1 | 5 | 5 | 5 | Scheduled | 26/08/2024 | 30/08/2024
TO-24-CRO-110SA2-05 | SECTIONALISING DISCONNECT - COOLROE 110-COOLROE 110-110SA2 | 5 | 5 | 5 | Scheduled | 26/08/2024 | 30/08/2024
TO-24-CRO-KBY-1-05 | 110kV FEEDER - COOLROE 110-KILBARRY 110-1 | 5 | 5 | 5 | Scheduled | 26/08/2024 | 30/08/2024
TO-24-BRY-RAF-2-01 | 110kV FEEDER - BARNAHELY 110-RAFFEEN 110-2 | 121 | 84 | 84 | Reference | 02/09/2024 | 31/12/2024
TO-24-BAN-BRI-1-02 | 110kV FEEDER - BANDON 110-BRINNY 110-1 | 1 | 1 | 1 | Scheduled | 03/09/2024 | 03/09/2024
TO-24-BRI-T101-03 | TSO CUSTOMER TRANSFORMER - BRINNY 110-BRINNY 10-T101 | 1 | 1 | 1 | Scheduled | 03/09/2024 | 03/09/2024
TO-24-GGO-T2001-01 | GENERATOR TRANSFORMER - GLANAGOW 220-GLANAGOW G1-T2001 | 9 | 7 | 7 | Scheduled | 09/09/2024 | 17/09/2024
TO-24-BAN-BRI-2-02 | 110kV FEEDER - BANDON 110-BRINNY 110-2 | 7 | 5 | 5 | Scheduled | 10/09/2024 | 16/09/2024
TO-24-BRI-T102-02 | TSO CUSTOMER TRANSFORMER - BRINNY 110-BRINNY 10-T102 | 7 | 5 | 5 | Scheduled | 10/09/2024 | 16/09/2024
TO-24-220 kV A2 @ AD-02 | BUSBAR SECTION - AGHADA 220-AGHADA 220-220A2 | 10 | 8 | 8 | Scheduled | 11/09/2024 | 20/09/2024
TO-24-220 kV B2 @ AD-02 | BUSBAR SECTION - AGHADA 220-AGHADA 220-220B2 | 10 | 8 | 8 | Scheduled | 11/09/2024 | 20/09/2024
TO-24-AD-SA1-2CB-02 | COUPLER/SECTIONALISING CB - AGHADA 220-AGHADA 220-220SA1-2CB | 10 | 8 | 8 | Scheduled | 11/09/2024 | 20/09/2024
TO-24-AD-SB1-2CB-02 | COUPLER/SECTIONALISING CB - AGHADA 220-AGHADA 220-220SB1-2CB | 10 | 8 | 8 | Scheduled | 11/09/2024 | 20/09/2024
TO-24-AD-RAF-1-04 | 220kV FEEDER - AGHADA 220-RAFFEEN 220-1 | 10 | 8 | 8 | Scheduled | 11/09/2024 | 20/09/2024
TO-24-CLA-110K1-2-02 | COUPLER/SECTIONALISING CB - CLASHAVOON 110-CLASHAVOON 110-110K1-2 | 1 | 1 | 1 | Scheduled | 11/09/2024 | 11/09/2024
TO-24-220 kV A4 @ KRA-01 | BUSBAR SECTION - KNOCKRAHA 220-KNOCKRAHA 220-220A4 | 57 | 40 | 40 | Scheduled | 11/09/2024 | 06/11/2024
TO-24-220 kV B4 @ KRA-01 | BUSBAR SECTION - KNOCKRAHA 220-KNOCKRAHA 220-220B4 | 57 | 40 | 40 | Scheduled | 11/09/2024 | 06/11/2024
TO-24-KRA-220K4-04 | COUPLER/SECTIONALISING CB - KNOCKRAHA 220-KNOCKRAHA 220-220K4 | 57 | 40 | 40 | Scheduled | 11/09/2024 | 06/11/2024
TO-24-KRA-220SA2-4CB-04 | COUPLER/SECTIONALISING CB - KNOCKRAHA 220-KNOCKRAHA 220-220SA2-4CB | 57 | 40 | 40 | Scheduled | 11/09/2024 | 06/11/2024
TO-24-KRA-220SB2-4CB-04 | COUPLER/SECTIONALISING CB - KNOCKRAHA 220-KNOCKRAHA 220-220SB2-4CB | 57 | 40 | 40 | Scheduled | 11/09/2024 | 06/11/2024
TO-24-220 kV A2 @ RAF-02 | BUSBAR SECTION - RAFFEEN 220-RAFFEEN 220-220A2 | 10 | 8 | 8 | Scheduled | 11/09/2024 | 20/09/2024
TO-24-220 kV B2 @ RAF-02 | BUSBAR SECTION - RAFFEEN 220-RAFFEEN 220-220B2 | 10 | 8 | 8 | Scheduled | 11/09/2024 | 20/09/2024
TO-24-AD-WHI-1-01 | 110kV FEEDER - AGHADA 110-WHITEGATE 110-1 | 4 | 4 |  | Scheduled | 16/09/2024 | 19/09/2024
TO-24-BAN-BRI-1-04 | 110kV FEEDER - BANDON 110-BRINNY 110-1 | 5 | 5 | 5 | Scheduled | 16/09/2024 | 20/09/2024
TO-24-BRI-T101-04 | TSO CUSTOMER TRANSFORMER - BRINNY 110-BRINNY 10-T101 | 5 | 5 | 5 | Scheduled | 16/09/2024 | 20/09/2024
TO-24-CRO-T122-02 | DISTRIBUTION TRANSFORMER - COOLROE 110-COOLROE 20-T122 | 68 | 49 | 49 | Reference | 16/09/2024 | 22/11/2024
TO-24-AD-RAF-1-01 | 220kV FEEDER - AGHADA 220-RAFFEEN 220-1 | 6 | 4 | 4 | Scheduled | 21/09/2024 | 26/09/2024
TO-24-CHA-MAL-1-03 | 110kV FEEDER - CHARLEVILLE 110-MALLOW 110-1 | 5 | 5 |  | Scheduled | 23/09/2024 | 27/09/2024
TO-24-COW-RAF-1-03 | 110kV FEEDER - COW CROSS 110-RAFFEEN 110-1 | 8 | 6 | 6 | Scheduled | 23/09/2024 | 30/09/2024
TO-24-CLA-MAC-2-01 | 110kV FEEDER - CLASHAVOON 110-MACROOM 110-2 | 50 | 35 | 35 | Scheduled | 30/09/2024 | 18/11/2024
TO-24-CD-MAC-1-02 | 110kV FEEDER - CARRIGADROHID 110-MACROOM 110-1 | 9 | 7 | 7 | Scheduled | 02/10/2024 | 10/10/2024
TO-24-MAC-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - MACROOM 110-MACROOM 110-110SA1-2CB | 9 | 7 |  | Scheduled | 02/10/2024 | 10/10/2024
TO-24-KBY-KRA-1-01 | 110kV FEEDER - KILBARRY 110-KNOCKRAHA 110-1 | 12 | 10 |  | Scheduled | 07/10/2024 | 18/10/2024
TO-24-110 kV A1 @ KRA-02 | BUSBAR SECTION - KNOCKRAHA 110-KNOCKRAHA 110-110A1 | 12 | 10 | 10 | Scheduled | 07/10/2024 | 18/10/2024
TO-24-110 kV B1 @ KRA-02 | BUSBAR SECTION - KNOCKRAHA 110-KNOCKRAHA 110-110B1 | 12 | 10 | 10 | Scheduled | 07/10/2024 | 18/10/2024
TO-24-CLA-220K1-2-03 | COUPLER/SECTIONALISING CB - CLASHAVOON 220-CLASHAVOON 220-220K1-2 | 5 | 5 | 5 | Scheduled | 14/10/2024 | 18/10/2024
TO-24-CLA-KRA-1-05 | 220kV FEEDER - CLASHAVOON 220-KNOCKRAHA 220-1 | 5 | 5 | 5 | Scheduled | 14/10/2024 | 18/10/2024
TO-24-CLA-T2102-02 | TRANSFORMER - CLASHAVOON 220-CLASHAVOON 110-T2102 | 5 | 5 | 5 | Scheduled | 14/10/2024 | 18/10/2024
TO-24-COW-WHI-1-04 | 110kV FEEDER - COW CROSS 110-WHITEGATE 110-1 | 12 | 10 | 10 | Scheduled | 14/10/2024 | 25/10/2024
TO-24-KBY-KRA-2-01 | 110kV FEEDER - KILBARRY 110-KNOCKRAHA 110-2 | 5 | 5 | 5 | Scheduled | 21/10/2024 | 25/10/2024
TO-24-CVW-110SA1-01 | SECTIONALISING DISCONNECT - CASTLEVIEW 110-CASTLEVIEW 110-110SA1 | 9 | 6 | 6 | Proposed | 28/10/2024 | 05/11/2024
TO-24-CVW-110SA2-01 | SECTIONALISING DISCONNECT - CASTLEVIEW 110-CASTLEVIEW 110-110SA2 | 9 | 6 | 6 | Proposed | 28/10/2024 | 05/11/2024
TO-24-CVW-COW-1-03 | 110kV FEEDER - CASTLEVIEW 110-COW CROSS 110-1 | 9 | 6 | 6 | Proposed | 28/10/2024 | 05/11/2024
TO-24-CVW-T101-01 | DISTRIBUTION TRANSFORMER - CASTLEVIEW 110-CASTLEVIEW 10-T101 | 9 | 6 | 6 | Reference (Proposed) | 28/10/2024 | 05/11/2024
TO-24-BAN-DMY-1-04 | 110kV FEEDER - BANDON 110-DUNMANWAY 110-1 | 11 | 9 | 9 | Proposed | 29/10/2024 | 08/11/2024
TO-24-CLA-DMY-1-01 | 110kV FEEDER - CLASHAVOON 110-DUNMANWAY 110-1 | 11 | 9 | 9 | Proposed | 29/10/2024 | 08/11/2024
TO-24-DMY-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - DUNMANWAY 110-DUNMANWAY 110-110SA1-2CB | 11 | 9 | 9 | Proposed | 29/10/2024 | 08/11/2024
TO-24-DMY-CAP2-02 | CAPACITOR/SVC/REACTOR - DUNMANWAY 110-DUNMANWAY 110-CAP2 | 11 | 9 | 9 | Proposed | 29/10/2024 | 08/11/2024
TO-24-DMY-T142-02 | DISTRIBUTION TRANSFORMER - DUNMANWAY 110-DUNMANWAY 38-T142 | 11 | 9 | 9 | Reference (Proposed) | 29/10/2024 | 08/11/2024
TO-24-KLN-KRA-1-01 | 220kV FEEDER - KILLONAN 220-KNOCKRAHA 220-1 | 4 | 4 |  | Scheduled | 29/10/2024 | 01/11/2024
TO-24-BAN-BRI-2-01 | 110kV FEEDER - BANDON 110-BRINNY 110-2 | 1 | 1 | 1 | Proposed | 30/10/2024 | 30/10/2024
TO-24-BRI-T102-01 | TSO CUSTOMER TRANSFORMER - BRINNY 110-BRINNY 10-T102 | 1 | 1 | 1 | Proposed | 30/10/2024 | 30/10/2024
TO-24-220 kV A1 @ AD-04 | BUSBAR SECTION - AGHADA 220-AGHADA 220-220A1 | 5 | 5 | 5 | Scheduled | 04/11/2024 | 08/11/2024
TO-24-220 kV A2 @ AD-07 | BUSBAR SECTION - AGHADA 220-AGHADA 220-220A2 | 5 | 5 | 5 | Scheduled | 04/11/2024 | 08/11/2024
TO-24-AD-220K1-05 | COUPLER/SECTIONALISING CB - AGHADA 220-AGHADA 220-220K1 | 5 | 5 | 5 | Scheduled | 04/11/2024 | 08/11/2024
TO-24-AD-SA1-2CB-04 | COUPLER/SECTIONALISING CB - AGHADA 220-AGHADA 220-220SA1-2CB | 5 | 5 | 5 | Scheduled | 04/11/2024 | 08/11/2024
TO-24-110 kV A2 @ KBY-02 | BUSBAR SECTION - KILBARRY 110-KILBARRY 110-110A2 | 8 | 6 | 6 | Proposed | 05/11/2024 | 12/11/2024
TO-24-110 kV B2 @ KBY-02 | BUSBAR SECTION - KILBARRY 110-KILBARRY 110-110B2 | 8 | 6 | 6 | Proposed | 05/11/2024 | 12/11/2024
TO-24-KBY-MAL-1-01 | 110kV FEEDER - KILBARRY 110-MALLOW 110-1 | 8 | 6 | 6 | Proposed | 05/11/2024 | 12/11/2024
TO-24-KBY-MAL-1-02 | 110kV FEEDER - KILBARRY 110-MALLOW 110-1 | 21 | 15 | 15 | Scheduled | 05/11/2024 | 25/11/2024
TO-24-220 kV B1 @ AD-05 | BUSBAR SECTION - AGHADA 220-AGHADA 220-220B1 | 5 | 5 | 5 | Scheduled | 11/11/2024 | 15/11/2024
TO-24-220 kV B2 @ AD-07 | BUSBAR SECTION - AGHADA 220-AGHADA 220-220B2 | 5 | 5 | 5 | Scheduled | 11/11/2024 | 15/11/2024
TO-24-AD-220K1-07 | COUPLER/SECTIONALISING CB - AGHADA 220-AGHADA 220-220K1 | 5 | 5 | 5 | Scheduled | 11/11/2024 | 15/11/2024
TO-24-AD-SB1-2CB-04 | COUPLER/SECTIONALISING CB - AGHADA 220-AGHADA 220-220SB1-2CB | 5 | 5 | 5 | Scheduled | 11/11/2024 | 15/11/2024
TO-24-CRO-110SA1-04 | SECTIONALISING DISCONNECT - COOLROE 110-COOLROE 110-110SA1 | 12 | 10 | 10 | Scheduled | 11/11/2024 | 22/11/2024
TO-24-CRO-110SA2-04 | SECTIONALISING DISCONNECT - COOLROE 110-COOLROE 110-110SA2 | 12 | 10 | 10 | Scheduled | 11/11/2024 | 22/11/2024
TO-24-CRO-IA-1-06 | 110kV FEEDER - COOLROE 110-INNISCARRA 110-1 | 12 | 10 | 10 | Scheduled | 11/11/2024 | 22/11/2024
TO-24-110 kV A1 @ KRA-03 | BUSBAR SECTION - KNOCKRAHA 110-KNOCKRAHA 110-110A1 | 19 | 15 | 15 | Proposed | 11/11/2024 | 29/11/2024
TO-24-110 kV B1 @ KRA-03 | BUSBAR SECTION - KNOCKRAHA 110-KNOCKRAHA 110-110B1 | 19 | 15 | 15 | Proposed | 11/11/2024 | 29/11/2024
TO-24-220 kV A1 @ KRA-03 | BUSBAR SECTION - KNOCKRAHA 220-KNOCKRAHA 220-220A1 | 19 | 15 | 15 | Proposed | 11/11/2024 | 29/11/2024
TO-24-220 kV B1 @ KRA-03 | BUSBAR SECTION - KNOCKRAHA 220-KNOCKRAHA 220-220B1 | 19 | 15 | 15 | Proposed | 11/11/2024 | 29/11/2024
TO-24-KRA-220K1-04 | COUPLER/SECTIONALISING CB - KNOCKRAHA 220-KNOCKRAHA 220-220K1 | 19 | 15 | 15 | Scheduled | 11/11/2024 | 29/11/2024
TO-24-KRA-220SA1-2CB-04 | COUPLER/SECTIONALISING CB - KNOCKRAHA 220-KNOCKRAHA 220-220SA1-2CB | 19 | 15 | 15 | Scheduled | 11/11/2024 | 29/11/2024
TO-24-KRA-220SB1-2CB-04 | COUPLER/SECTIONALISING CB - KNOCKRAHA 220-KNOCKRAHA 220-220SB1-2CB | 19 | 15 | 15 | Scheduled | 11/11/2024 | 29/11/2024
TO-24-KRA-T2101-02 | TRANSFORMER - KNOCKRAHA 220-KNOCKRAHA 110-T2101 | 19 | 15 | 15 | Proposed | 11/11/2024 | 29/11/2024
TO-24-KRA-WOH-1-04 | 110kV FEEDER - KNOCKRAHA 110-WOODHOUSE 110-1 | 1 | 1 | 1 | Trip Testing | 12/11/2024 | 12/11/2024
TO-24-110 kV A1 @ RAF-01 | BUSBAR SECTION - RAFFEEN 110-RAFFEEN 110-110A1 | 12 | 10 | 10 | Proposed | 18/11/2024 | 29/11/2024
TO-24-110 kV B1 @ RAF-01 | BUSBAR SECTION - RAFFEEN 110-RAFFEEN 110-110B1 | 12 | 10 | 10 | Proposed | 18/11/2024 | 29/11/2024
TO-24-RAF-TBG-1-01 | 110kV FEEDER - RAFFEEN 110-TRABEG 110-1 | 12 | 10 |  | Proposed | 18/11/2024 | 29/11/2024
TO-24-110 kV A2 @ TBG-01 | BUSBAR SECTION - TRABEG 110-TRABEG 110-110A2 | 12 | 10 |  | Proposed | 18/11/2024 | 29/11/2024
TO-24-110 kV B2 @ TBG-01 | BUSBAR SECTION - TRABEG 110-TRABEG 110-110B2 | 12 | 10 | 10 | Proposed | 18/11/2024 | 29/11/2024
TO-24-RAF-110K1-2-03 | COUPLER/SECTIONALISING CB - RAFFEEN 110-RAFFEEN 110-110K1-2 | 3 | 3 | 3 | Scheduled | 20/11/2024 | 22/11/2024
TO-24-COW-110SA1-01 | SECTIONALISING DISCONNECT - COW CROSS 110-COW CROSS 110-110SA1 | Unknown | Unknown |  | Planned | November | December
TO-24-COW-110SA2-02 | SECTIONALISING DISCONNECT - COW CROSS 110-COW CROSS 110-110SA2 | Unknown | Unknown |  | Planned | November | December
TO-24-COW-OLD-2-01 | 110kV FEEDER - COW CROSS 110-OLDCOURT 110-2 | Unknown | Unknown |  | Reference (Planned) | November | December
TO-24-COW-OLD-2-02 | 110kV FEEDER - COW CROSS 110-OLDCOURT 110-2 | 15 | 11 | 11 | Reference (Proposed) | 25/11/2024 | 09/12/2024
TO-24-COW-RAF-1-01 | 110kV FEEDER - COW CROSS 110-RAFFEEN 110-1 | Unknown | Unknown |  | Planned | November | December
TO-24-COW-T141-01 | DISTRIBUTION TRANSFORMER - COW CROSS 110-COW CROSS 38-T141 | Unknown | Unknown |  | Reference (Planned) | November | December
TO-24-OLD-T102-01 | DISTRIBUTION TRANSFORMER - OLDCOURT 110-OLDCOURT 10-T102 | Unknown | Unknown | 11 | Reference (Planned) | November | December
TO-24-BAN-RAF-1-03 | 110kV FEEDER - BANDON 110-RAFFEEN 110-1 | 3 | 3 | 3 | Scheduled | 27/11/2024 | 29/11/2024