## GEN_ALL
Outage ID | Feeder ID | Calendar Day Duration | Working Day Duration | Work Days | Outage Status | Start | Finish
TO-24-AUG-CFM-1-01 | 110kV FEEDER - AUGHINISH 110-CASTLEFARM 110-1 | 5 | 5 | 5 | Scheduled | 08/01/2024 | 12/01/2024
TO-24-220 kV A2 @ CSH-01 | BUSBAR SECTION - CASHLA 220-CASHLA 220-220A2 | 5 | 5 | 5 | Scheduled | 08/01/2024 | 12/01/2024
TO-24-220 kV A4 @ CSH-02 | BUSBAR SECTION - CASHLA 220-CASHLA 220-220A4 | 5 | 5 | 5 | Scheduled | 08/01/2024 | 12/01/2024
TO-24-220 kV B2 @ CSH-03 | BUSBAR SECTION - CASHLA 220-CASHLA 220-220B2 | 5 | 5 | 5 | Scheduled | 08/01/2024 | 12/01/2024
TO-24-220 kV B4 @ CSH-01 | BUSBAR SECTION - CASHLA 220-CASHLA 220-220B4 | 5 | 5 | 5 | Scheduled | 08/01/2024 | 12/01/2024
TO-24-CSH-220K2-4-02 | COUPLER/SECTIONALISING CB - CASHLA 220-CASHLA 220-220K2-4 | 5 | 5 | 5 | Scheduled | 08/01/2024 | 12/01/2024
TO-24-CFM-T101-01 | TSO CUSTOMER TRANSFORMER - CASTLEFARM 110-CASTLEFARM 10-T101 | 5 | 5 | 5 | Reference | 08/01/2024 | 12/01/2024
TO-24-LIM-MTN-1-02 | 110kV FEEDER - LIMERICK 110-MONETEEN 110-1 | 2 | 2 | 2 | Scheduled | 08/01/2024 | 09/01/2024
TO-24-110 kV A1 @ LOU-02 | BUSBAR SECTION - LOUTH 110-LOUTH 110-110A1 | 12 | 10 | 10 | Scheduled | 08/01/2024 | 19/01/2024
TO-24-110 kV B1 @ LOU-02 | BUSBAR SECTION - LOUTH 110-LOUTH 110-110B1 | 12 | 10 | 10 | Scheduled | 08/01/2024 | 19/01/2024
TO-24-220 kV A1 @ MAY-01 | BUSBAR SECTION - MAYNOOTH 220-MAYNOOTH 220-220A1 | 12 | 10 | 10 | Proposed | 08/01/2024 | 19/01/2024
TO-24-220 kV B1 @ MAY-01 | BUSBAR SECTION - MAYNOOTH 220-MAYNOOTH 220-220B1 | 12 | 10 | 10 | Proposed | 08/01/2024 | 19/01/2024
TO-24-220 kV A3 @ PB-01 | BUSBAR SECTION - POOLBEG 220-POOLBEG 220-220A3 | 12 | 10 | 10 | Scheduled | 08/01/2024 | 19/01/2024
TO-24-220 kV A4 @ PB-02 | BUSBAR SECTION - POOLBEG 220-POOLBEG 220-220A4 | 12 | 10 | 10 | Scheduled | 08/01/2024 | 19/01/2024
TO-24-220 kV B3 @ PB-01 | BUSBAR SECTION - POOLBEG 220-POOLBEG 220-220B3 | 12 | 10 | 10 | Scheduled | 08/01/2024 | 19/01/2024
TO-24-220 kV B4 @ PB-01 | BUSBAR SECTION - POOLBEG 220-POOLBEG 220-220B4 | 12 | 10 | 10 | Scheduled | 08/01/2024 | 19/01/2024
TO-24-PB-R223-4-01 | CAPACITOR/SVC/REACTOR - POOLBEG 220-POOLBEG 220-R223-4 | 12 | 10 | 10 | Scheduled | 08/01/2024 | 19/01/2024
TO-24-CRA-LWD-1-07 | 110kV FEEDER - CRANE 110-LODGEWOOD 110-1 | 2 | 2 | 2 | Scheduled | 15/01/2024 | 16/01/2024
TO-24-GI-T141-03 | DISTRIBUTION TRANSFORMER - GREAT ISLAND 110-GREAT ISLAND 38-T141 | 5 | 5 | 5 | Reference | 15/01/2024 | 19/01/2024
TO-24-RYB GIS-T108-01 | TSO CUSTOMER TRANSFORMER - RYEBROOK GIS 110-RYEBROOK 10-T108 | 5 | 5 | 5 | Scheduled | 22/01/2024 | 26/01/2024
TO-24-220 kV A4 @ CKM GIS-01 | BUSBAR SECTION - CARRICKMINES GIS 220-CARRICKMINES GIS 220-220A4 | 3 | 3 | 3 | Scheduled | 29/01/2024 | 31/01/2024
TO-24-220 kV B4 @ CKM GIS-01 | BUSBAR SECTION - CARRICKMINES GIS 220-CARRICKMINES GIS 220-220B4 | 3 | 3 | 3 | Scheduled | 29/01/2024 | 31/01/2024
TO-24-CKM GIS-220K4-01 | COUPLER/SECTIONALISING CB - CARRICKMINES GIS 220-CARRICKMINES GIS 220-220K4 | 3 | 3 | 3 | Scheduled | 29/01/2024 | 31/01/2024
TO-24-CKM GIS-220SA2-4CB-01 | COUPLER/SECTIONALISING CB - CARRICKMINES GIS 220-CARRICKMINES GIS 220-22SA2-4CB | 3 | 3 | 3 | Scheduled | 29/01/2024 | 31/01/2024
TO-24-CKM GIS-220SB2-4CB-01 | COUPLER/SECTIONALISING CB - CARRICKMINES GIS 220-CARRICKMINES GIS 220-22SB2-4CB | 3 | 3 | 3 | Scheduled | 29/01/2024 | 31/01/2024
TO-24-CKM GIS-DSN-1-02 | 220kV FEEDER - CARRICKMINES GIS 220-DUNSTOWN 220-1 | 3 | 3 | 3 | Scheduled | 29/01/2024 | 31/01/2024
TO-24-CKM GIS-T2104-01 | TRANSFORMER - CARRICKMINES GIS 220-CARRICKMINES GIS 110-T2104 | 3 | 3 | 3 | Reference | 29/01/2024 | 31/01/2024
TO-24-KLS-KKY-1-02 | 110kV FEEDER - KELLIS 110-KILKENNY 110-1 | 10 | 7 | 7 | Scheduled | 29/01/2024 | 07/02/2024
TO-24-CUL-WAT-1-02 | 110kV FEEDER - CULLENAGH 110-WATERFORD 110-1 | 3 | 3 | 3 | Scheduled | 30/01/2024 | 01/02/2024
TO-24-CAH-TIP-1-02 | 110kV FEEDER - CAHIR 110-TIPPERARY 110-1 | 2 | 2 | 2 | Scheduled | 31/01/2024 | 01/02/2024
TO-24-WOO-220K1-2-02 | COUPLER/SECTIONALISING CB - WOODLAND 220-WOODLAND 220-220K1-2 | 2 | 2 | 2 | Scheduled | 31/01/2024 | 01/02/2024
TO-24-PB-T2007/8-01 | GENERATOR TRANSFORMER - POOLBEG 220-POOLBEG G7/8-T2007/8 | 3 | 2 | 2 | Scheduled | 01/02/2024 | 03/02/2024
TO-24-220 kV A1 @ CKM-01 | BUSBAR SECTION - CARRICKMINES 220-CARRICKMINES 220-220A1 | 5 | 4 | 4 | Scheduled | 06/02/2024 | 10/02/2024
TO-24-CKM-CKM GIS-1-01 | 220kV FEEDER - CARRICKMINES 220-CARRICKMINES GIS 220-1 | 5 | 4 | 4 | Scheduled | 06/02/2024 | 10/02/2024
TO-24-CKM-PB-1-02 | 220kV FEEDER - CARRICKMINES 220-POOLBEG 220-1 | 5 | 4 | 4 | Scheduled | 06/02/2024 | 10/02/2024
TO-24-CKM-PST2201-01 | TRANSFORMER - CARRICKMINES 220-CARRICKMINES 220-PST2201 | 5 | 4 | 4 | Scheduled | 06/02/2024 | 10/02/2024
TO-24-RYB GIS-T109-01 | TSO CUSTOMER TRANSFORMER - RYEBROOK GIS 110-RYEBROOK 10-T109 | 4 | 4 | 4 | Scheduled | 06/02/2024 | 09/02/2024
TO-24-BRT-CLE-2-01 | 220kV FEEDER - BRACETOWN 220-CLONEE 220-2 | 1 | 1 | 1 | Scheduled | 07/02/2024 | 07/02/2024
TO-24-KRA-220SA2-4CB-01 | COUPLER/SECTIONALISING CB - KNOCKRAHA 220-KNOCKRAHA 220-220SA2-4CB | 1 | 1 | 1 | Scheduled | 07/02/2024 | 07/02/2024
TO-24-BRT-CLE-4-01 | 220kV FEEDER - BRACETOWN 220-CLONEE 220-4 | 1 | 1 | 1 | Scheduled | 08/02/2024 | 08/02/2024
TO-24-KRA-220K4-01 | COUPLER/SECTIONALISING CB - KNOCKRAHA 220-KNOCKRAHA 220-220K4 | 1 | 1 | 1 | Scheduled | 09/02/2024 | 09/02/2024
TO-24-BRT-T222-01 | TSO CUSTOMER TRANSFORMER - BRACETOWN 220-BRACETOWN 20-T222 | 38 | 27 | 27 | Scheduled | 12/02/2024 | 20/03/2024
TO-24-CKM GIS-T2103-01 | TRANSFORMER - CARRICKMINES GIS 220-CARRICKMINES GIS 110-T2103 | 5 | 5 | 5 | Reference | 12/02/2024 | 16/02/2024
TO-24-CF-T104-02 | GENERATOR TRANSFORMER - CATHALEENS FALL 110-CATHALEENS FALL G4-T104 | 2 | 2 | 2 | Scheduled | 12/02/2024 | 13/02/2024
TO-24-COW-WHI-1-03 | 110kV FEEDER - COW CROSS 110-WHITEGATE 110-1 | 5 | 5 | 5 | Scheduled | 12/02/2024 | 16/02/2024
TO-24-400 kV A1 @ DSN-01 | BUSBAR SECTION - DUNSTOWN 400-DUNSTOWN 400-400A1 | 19 | 15 | 15 | Scheduled | 12/02/2024 | 01/03/2024
TO-24-400 kV B1 @ DSN-01 | BUSBAR SECTION - DUNSTOWN 400-DUNSTOWN 400-400B1 | 19 | 15 | 15 | Scheduled | 12/02/2024 | 01/03/2024
TO-24-DSN-T4201-02 | TRANSFORMER - DUNSTOWN 400-DUNSTOWN 220-T4201 | 19 | 15 | 15 | Scheduled | 12/02/2024 | 01/03/2024
TO-24-GLN-T133-03 | GENERATOR TRANSFORMER - GALLANSTOWN 110-GALLANSTOWN 33-T133 | 26 | 20 | 20 | Scheduled | 12/02/2024 | 08/03/2024
TO-24-KNR-TRI-1-02 | 110kV FEEDER - KNOCKANURE 110-TRIEN 110-1 | 9 | 7 | 7 | Scheduled | 12/02/2024 | 20/02/2024
TO-24-110 kV A1 @ ATH-01 | BUSBAR SECTION - ATHLONE 110-ATHLONE 110-110A1 | 2 | 2 | 2 | Proposed | 14/02/2024 | 15/02/2024
TO-24-BUF-T131-01 | GENERATOR TRANSFORMER - BUFFY 110-BUFFY 33-T131 | 1 | 1 | 1 | Scheduled | 19/02/2024 | 19/02/2024
TO-24-110 kV A4 @ CBT-02 | BUSBAR SECTION - CASTLEBAGOT 110-CASTLEBAGOT 110-110A4 | 5 | 5 | 5 | Scheduled | 19/02/2024 | 23/02/2024
TO-24-110 kV B4 @ CBT-02 | BUSBAR SECTION - CASTLEBAGOT 110-CASTLEBAGOT 110-110B4 | 5 | 5 | 5 | Scheduled | 19/02/2024 | 23/02/2024
TO-24-CBT-CKG-2-03 | 110kV FEEDER - CASTLEBAGOT 110-CORKAGH 110-2 | 5 | 5 | 5 | Scheduled | 19/02/2024 | 23/02/2024
TO-24-CLN-LA-1-01 | 110kV FEEDER - CLOON 110-LANESBORO 110-1 | 12 | 10 | 10 | Scheduled | 19/02/2024 | 01/03/2024
TO-24-CUL-GI GIS-1-04 | 220kV FEEDER - CULLENAGH 220-GREAT ISLAND GIS 220-1 | 2 | 2 | 2 | Scheduled | 19/02/2024 | 20/02/2024
TO-24-LYT-T132-01 | GENERATOR TRANSFORMER - LYSAGHTSTOWN 110-LYSAGHTSTOWN 33-T132 | 1 | 1 | 1 | Scheduled | 19/02/2024 | 19/02/2024
TO-24-RAF-TBG-2-02 | 110kV FEEDER - RAFFEEN 110-TRABEG 110-2 | 5 | 5 | 5 | Scheduled | 19/02/2024 | 23/02/2024
TO-24-KRA-110K1-2-01 | COUPLER/SECTIONALISING CB - KNOCKRAHA 110-KNOCKRAHA 110-110K1-2 | 1 | 1 | 1 | Scheduled | 20/02/2024 | 20/02/2024
TO-24-AD-LPT-1-01 | 220kV FEEDER - AGHADA 220-LONG POINT 220-1 | 78 | 52 | 52 | Scheduled | 26/02/2024 | 13/05/2024
TO-24-AA GIS-SNG-1-01 | 110kV FEEDER - ARDNACRUSHA GIS 110-SINGLAND 110-1 | 5 | 5 |  | Scheduled | 26/02/2024 | 01/03/2024
TO-24-110 kV A1 @ ARK-01 | BUSBAR SECTION - ARKLOW 110-ARKLOW 110-110A1 | 12 | 10 | 10 | Scheduled | 26/02/2024 | 08/03/2024
TO-24-110 kV B1 @ ARK-01 | BUSBAR SECTION - ARKLOW 110-ARKLOW 110-110B1 | 12 | 10 | 10 | Scheduled | 26/02/2024 | 08/03/2024
TO-24-ARK-BOG-1-01 | 110kV FEEDER - ARKLOW 110-BANOGE 110-1 | 12 | 10 | 10 | Scheduled | 26/02/2024 | 08/03/2024
TO-24-ATH-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - ATHLONE 110-ATHLONE 110-110SA1-2CB | 2 | 2 | 2 | Scheduled | 26/02/2024 | 27/02/2024
TO-24-ATH-CAP3-02 | CAPACITOR/SVC/REACTOR - ATHLONE 110-ATHLONE 110-CAP3 | 2 | 2 | 2 | Scheduled | 26/02/2024 | 27/02/2024
TO-24-ATH-LA-1-01 | 110kV FEEDER - ATHLONE 110-LANESBORO 110-1 | 2 | 2 | 2 | Scheduled | 26/02/2024 | 27/02/2024
TO-24-ATH-T141-01 | DISTRIBUTION TRANSFORMER - ATHLONE 110-ATHLONE 38-T141 | 2 | 2 | 2 | Reference | 26/02/2024 | 27/02/2024
TO-24-CSH-T2104-02 | TRANSFORMER - CASHLA 220-CASHLA 110-T2104 | 66 | 45 |  | Scheduled | 26/02/2024 | 01/05/2024
TO-24-LPT-T2002-02 | GENERATOR TRANSFORMER - LONG POINT 220-LONG POINT G1-T2002 | 78 | 52 | 52 | Scheduled | 26/02/2024 | 13/05/2024
TO-24-OST-WOO-1-01 | 400kV FEEDER - OLDSTREET 400-WOODLAND 400-1 | 5 | 5 | 5 | Scheduled | 26/02/2024 | 01/03/2024
TO-24-110 kV A1 @ RAF-02 | BUSBAR SECTION - RAFFEEN 110-RAFFEEN 110-110A1 | 5 | 5 | 5 | Scheduled | 26/02/2024 | 01/03/2024
TO-24-110 kV B1 @ RAF-02 | BUSBAR SECTION - RAFFEEN 110-RAFFEEN 110-110B1 | 5 | 5 | 5 | Scheduled | 26/02/2024 | 01/03/2024
TO-24-220 kV A1 @ RAF-02 | BUSBAR SECTION - RAFFEEN 220-RAFFEEN 220-220A1 | 5 | 5 | 5 | Scheduled | 26/02/2024 | 01/03/2024
TO-24-220 kV B1 @ RAF-02 | BUSBAR SECTION - RAFFEEN 220-RAFFEEN 220-220B1 | 5 | 5 | 5 | Scheduled | 26/02/2024 | 01/03/2024
TO-24-KPG-TRL-1-01 | 110kV FEEDER - KILPADDOGE 110-TRALEE 110-1 | 10 | 8 | 8 | Scheduled | 28/02/2024 | 08/03/2024
TO-24-ATH-110SA1-2CB-04 | COUPLER/SECTIONALISING CB - ATHLONE 110-ATHLONE 110-110SA1-2CB | 2 | 2 | 2 | Scheduled | 29/02/2024 | 01/03/2024
TO-24-ATH-CAP3-05 | CAPACITOR/SVC/REACTOR - ATHLONE 110-ATHLONE 110-CAP3 | 2 | 2 | 2 | Scheduled | 29/02/2024 | 01/03/2024
TO-24-ATH-LA-1-04 | 110kV FEEDER - ATHLONE 110-LANESBORO 110-1 | 2 | 2 | 2 | Scheduled | 29/02/2024 | 01/03/2024
TO-24-ATH-T141-02 | DISTRIBUTION TRANSFORMER - ATHLONE 110-ATHLONE 38-T141 | 2 | 2 | 2 | Reference | 29/02/2024 | 01/03/2024
TO-24-SKY-T132-01 | GENERATOR TRANSFORMER - SRAHNAKILLY 110-SRAHNAKILLY 33-T132 | 2 | 2 | 2 | Scheduled | 29/02/2024 | 01/03/2024
TO-24-TH-T2001/2-03 | GENERATOR TRANSFORMER - TURLOUGH HILL 220-TURLOUGH HILL G1-T2001/2 | 1 | 0 | 0 | Scheduled | 03/03/2024 | 03/03/2024
TO-24-TH-T2003/4-02 | GENERATOR TRANSFORMER - TURLOUGH HILL 220-TURLOUGH HILL G1-T2003/4 | 4 | 3 | 3 | Scheduled | 03/03/2024 | 06/03/2024
TO-24-AGL-DYN-1-01 | 110kV FEEDER - AGANNYGAL 110-DERRYBRIEN 110-1 | 22 | 15 |  | Scheduled | 04/03/2024 | 25/03/2024
TO-24-AGL-ENN-1-01 | 110kV FEEDER - AGANNYGAL 110-ENNIS 110-1 | 22 | 15 | 15 | Scheduled | 04/03/2024 | 25/03/2024
TO-24-AGL-SH-1-01 | 110kV FEEDER - AGANNYGAL 110-SHANNONBRIDGE 110-1 | 22 | 15 | 15 | Scheduled | 04/03/2024 | 25/03/2024
TO-24-220 kV A2 @ AD-04 | BUSBAR SECTION - AGHADA 220-AGHADA 220-220A2 | 12 | 10 | 10 | Scheduled | 04/03/2024 | 15/03/2024
TO-24-220 kV B2 @ AD-04 | BUSBAR SECTION - AGHADA 220-AGHADA 220-220B2 | 12 | 10 | 10 | Scheduled | 04/03/2024 | 15/03/2024
TO-24-AD-SA1-2CB-06 | COUPLER/SECTIONALISING CB - AGHADA 220-AGHADA 220-220SA1-2CB | 12 | 10 | 10 | Scheduled | 04/03/2024 | 15/03/2024
TO-24-AD-SB1-2CB-06 | COUPLER/SECTIONALISING CB - AGHADA 220-AGHADA 220-220SB1-2CB | 12 | 10 | 10 | Scheduled | 04/03/2024 | 15/03/2024
TO-24-AD-KRA-2-01 | 220kV FEEDER - AGHADA 220-KNOCKRAHA 220-2 | 12 | 10 |  | Scheduled | 04/03/2024 | 15/03/2024
TO-24-BAG-T103-01 | TSO CUSTOMER TRANSFORMER - BARNAGEERAGH 110-BARNAGEERAGH 11-T103 | 2 | 2 | 2 | Scheduled | 04/03/2024 | 05/03/2024
TO-24-110 kV A1 @ CBT-02 | BUSBAR SECTION - CASTLEBAGOT 110-CASTLEBAGOT 110-110A1 | 5 | 5 | 5 | Scheduled | 04/03/2024 | 08/03/2024
TO-24-110 kV B1 @ CBT-02 | BUSBAR SECTION - CASTLEBAGOT 110-CASTLEBAGOT 110-110B1 | 5 | 5 | 5 | Scheduled | 04/03/2024 | 08/03/2024
TO-24-CBT-110K1-04 | COUPLER/SECTIONALISING CB - CASTLEBAGOT 110-CASTLEBAGOT 110-110K1 | 5 | 5 | 5 | Scheduled | 04/03/2024 | 08/03/2024
TO-24-CBT-110SA1-2CB-04 | COUPLER/SECTIONALISING CB - CASTLEBAGOT 110-CASTLEBAGOT 110-110SA1-2CB | 5 | 5 | 5 | Scheduled | 04/03/2024 | 08/03/2024
TO-24-CBT-110SB1-2CB-04 | COUPLER/SECTIONALISING CB - CASTLEBAGOT 110-CASTLEBAGOT 110-110SB1-2CB | 5 | 5 | 5 | Scheduled | 04/03/2024 | 08/03/2024
TO-24-CBT-CKG-1-03 | 110kV FEEDER - CASTLEBAGOT 110-CORKAGH 110-1 | 5 | 5 | 5 | Scheduled | 04/03/2024 | 08/03/2024
TO-24-DYN-T121-01 | GENERATOR TRANSFORMER - DERRYBRIEN 110-DERRYBRIEN 20-T121 | 22 | 15 |  | Reference | 04/03/2024 | 25/03/2024
TO-24-220 kV A1 @ DSN-01 | BUSBAR SECTION - DUNSTOWN 220-DUNSTOWN 220-220A1 | 12 | 10 | 10 | Scheduled | 04/03/2024 | 15/03/2024
TO-24-220 kV B1 @ DSN-01 | BUSBAR SECTION - DUNSTOWN 220-DUNSTOWN 220-220B1 | 12 | 10 | 10 | Scheduled | 04/03/2024 | 15/03/2024
TO-24-DSN-TH-1-01 | 220kV FEEDER - DUNSTOWN 220-TURLOUGH HILL 220-1 | 12 | 10 |  | Scheduled | 04/03/2024 | 15/03/2024
TO-24-FLA-SLB-1-04 | 110kV FEEDER - FLAGFORD 110-SLIABH BAWN 110-1 | 47 | 32 | 32 | Scheduled | 04/03/2024 | 19/04/2024
TO-24-220 kV A1 @ KRA-02 | BUSBAR SECTION - KNOCKRAHA 220-KNOCKRAHA 220-220A1 | 12 | 10 | 10 | Scheduled | 04/03/2024 | 15/03/2024
TO-24-220 kV B1 @ KRA-02 | BUSBAR SECTION - KNOCKRAHA 220-KNOCKRAHA 220-220B1 | 12 | 10 | 10 | Scheduled | 04/03/2024 | 15/03/2024
TO-24-KRA-220K1-03 | COUPLER/SECTIONALISING CB - KNOCKRAHA 220-KNOCKRAHA 220-220K1 | 12 | 10 | 10 | Scheduled | 04/03/2024 | 15/03/2024
TO-24-KRA-220SA1-2CB-03 | COUPLER/SECTIONALISING CB - KNOCKRAHA 220-KNOCKRAHA 220-220SA1-2CB | 12 | 10 | 10 | Scheduled | 04/03/2024 | 15/03/2024
TO-24-KRA-220SB1-2CB-03 | COUPLER/SECTIONALISING CB - KNOCKRAHA 220-KNOCKRAHA 220-220SB1-2CB | 12 | 10 | 10 | Scheduled | 04/03/2024 | 15/03/2024
TO-24-PB-R2001-01 | CAPACITOR/SVC/REACTOR - POOLBEG 220-POOLBEG 220-R2001 | 5 | 5 | 5 | Scheduled | 04/03/2024 | 08/03/2024
TO-24-RAF-RSY-1-01 | 110kV FEEDER - RAFFEEN 110-RINGASKIDDY 110-1 | 12 | 10 |  | Reference | 04/03/2024 | 15/03/2024
TO-24-220 kV A1 @ TH-01 | BUSBAR SECTION - TURLOUGH HILL 220-TURLOUGH HILL 220-220A1 | 12 | 10 | 10 | Scheduled | 04/03/2024 | 15/03/2024
TO-24-220 kV B1 @ TH-01 | BUSBAR SECTION - TURLOUGH HILL 220-TURLOUGH HILL 220-220B1 | 12 | 10 | 10 | Scheduled | 04/03/2024 | 15/03/2024
TO-24-BDN-DOO-1-01 | 110kV FEEDER - BALLYDINE 110-DOON 110-1 | 9 | 7 | 7 | Scheduled | 05/03/2024 | 13/03/2024
TO-24-KRA-220SA2-4CB-02 | COUPLER/SECTIONALISING CB - KNOCKRAHA 220-KNOCKRAHA 220-220SA2-4CB | 73 | 49 |  | Scheduled | 05/03/2024 | 16/05/2024
TO-24-KRA-220SB2-4CB-01 | COUPLER/SECTIONALISING CB - KNOCKRAHA 220-KNOCKRAHA 220-220SB2-4CB | 73 | 49 |  | Scheduled | 05/03/2024 | 16/05/2024
TO-24-ISH-T2002/3-01 | GENERATOR TRANSFORMER - IRISHTOWN 220-IRISHTOWN G2/3-T2002/3 | 2 | 2 | 2 | Scheduled | 06/03/2024 | 07/03/2024
TO-24-TH-T2001/2-02 | GENERATOR TRANSFORMER - TURLOUGH HILL 220-TURLOUGH HILL G1-T2001/2 | 4 | 3 | 3 | Scheduled | 10/03/2024 | 13/03/2024
TO-24-220 kV A1 @ AD-03 | BUSBAR SECTION - AGHADA 220-AGHADA 220-220A1 | 5 | 5 | 5 | Scheduled | 11/03/2024 | 15/03/2024
TO-24-220 kV B1 @ AD-02 | BUSBAR SECTION - AGHADA 220-AGHADA 220-220B1 | 5 | 5 | 5 | Scheduled | 11/03/2024 | 15/03/2024
TO-24-AD-220K1-04 | COUPLER/SECTIONALISING CB - AGHADA 220-AGHADA 220-220K1 | 5 | 5 | 5 | Scheduled | 11/03/2024 | 15/03/2024
TO-24-AD-SA1-2CB-03 | COUPLER/SECTIONALISING CB - AGHADA 220-AGHADA 220-220SA1-2CB | 5 | 5 | 5 | Scheduled | 11/03/2024 | 15/03/2024
TO-24-AD-SB1-2CB-03 | COUPLER/SECTIONALISING CB - AGHADA 220-AGHADA 220-220SB1-2CB | 5 | 5 | 5 | Scheduled | 11/03/2024 | 15/03/2024
TO-24-ARK-BEG-1-01 | 110kV FEEDER - ARKLOW 110-BALLYBEG 110-1 | 12 | 9 |  | Scheduled | 11/03/2024 | 22/03/2024
TO-24-BYH-T2101-01 | TRANSFORMER - BALLYNAHULLA 220-BALLYNAHULLA 110-T2101 | 5 | 5 | 5 | Scheduled | 11/03/2024 | 15/03/2024
TO-24-220 kV A2 @ CBT-03 | BUSBAR SECTION - CASTLEBAGOT 220-CASTLEBAGOT 220-220A2 | 12 | 9 | 9 | Scheduled | 11/03/2024 | 22/03/2024
TO-24-220 kV B2 @ CBT-03 | BUSBAR SECTION - CASTLEBAGOT 220-CASTLEBAGOT 220-220B2 | 12 | 9 | 9 | Scheduled | 11/03/2024 | 22/03/2024
TO-24-CBT-220K2-04 | COUPLER/SECTIONALISING CB - CASTLEBAGOT 220-CASTLEBAGOT 220-220K2 | 12 | 9 | 9 | Scheduled | 11/03/2024 | 22/03/2024
TO-24-CBT-220SA1-2CB-03 | COUPLER/SECTIONALISING CB - CASTLEBAGOT 220-CASTLEBAGOT 220-220SA1-2CB | 12 | 9 | 9 | Scheduled | 11/03/2024 | 22/03/2024
TO-24-CBT-220SB1-2CB-04 | COUPLER/SECTIONALISING CB - CASTLEBAGOT 220-CASTLEBAGOT 220-220SB1-2CB | 12 | 9 | 9 | Scheduled | 11/03/2024 | 22/03/2024
TO-24-LPT-T2002-01 | GENERATOR TRANSFORMER - LONG POINT 220-LONG POINT G1-T2002 | 5 | 5 | 5 | Scheduled | 11/03/2024 | 15/03/2024
TO-24-BAG-T101-01 | TSO CUSTOMER TRANSFORMER - BARNAGEERAGH 110-BARNAGEERAGH 11-T101 | 2 | 2 | 2 | Scheduled | 12/03/2024 | 13/03/2024
TO-24-110 kV A1 @ CBT-03 | BUSBAR SECTION - CASTLEBAGOT 110-CASTLEBAGOT 110-110A1 | 3 | 3 | 3 | Scheduled | 12/03/2024 | 14/03/2024
TO-24-110 kV A2 @ CBT-02 | BUSBAR SECTION - CASTLEBAGOT 110-CASTLEBAGOT 110-110A2 | 3 | 3 | 3 | Scheduled | 12/03/2024 | 14/03/2024
TO-24-CBT-110SA1-2CB-03 | COUPLER/SECTIONALISING CB - CASTLEBAGOT 110-CASTLEBAGOT 110-110SA1-2CB | 3 | 3 | 3 | Scheduled | 12/03/2024 | 14/03/2024
TO-24-BAN-110SA1-01 | SECTIONALISING DISCONNECT - BANDON 110-BANDON 110-110SA1 | 15 | 10 | 10 | Scheduled | 14/03/2024 | 28/03/2024
TO-24-BAN-110SA2-02 | SECTIONALISING DISCONNECT - BANDON 110-BANDON 110-110SA2 | 15 | 10 | 10 | Scheduled | 14/03/2024 | 28/03/2024
TO-24-BAN-BRI-1-01 | 110kV FEEDER - BANDON 110-BRINNY 110-1 | 15 | 10 | 10 | Scheduled | 14/03/2024 | 28/03/2024
TO-24-BAN-CAP1-02 | CAPACITOR/SVC/REACTOR - BANDON 110-BANDON 110-CAP1 | 15 | 10 | 10 | Scheduled | 14/03/2024 | 28/03/2024
TO-24-BAN-DMY-1-02 | 110kV FEEDER - BANDON 110-DUNMANWAY 110-1 | 15 | 10 | 10 | Scheduled | 14/03/2024 | 28/03/2024
TO-24-BAN-T101-01 | DISTRIBUTION TRANSFORMER - BANDON 110-BANDON 10-T101 | 15 | 10 | 10 | Reference | 14/03/2024 | 28/03/2024
TO-24-BAN-T141-01 | DISTRIBUTION TRANSFORMER - BANDON 110-BANDON 38-T141 | 15 | 10 | 10 | Reference | 14/03/2024 | 28/03/2024
TO-24-BRI-T101-02 | TSO CUSTOMER TRANSFORMER - BRINNY 110-BRINNY 10-T101 | 15 | 10 | 10 | Scheduled | 14/03/2024 | 28/03/2024
TO-24-BOL-T141-01 | DISTRIBUTION TRANSFORMER - BOOLTIAGH 110-BOOLTIAGH 38-T141 | 85 | 56 | 56 | Reference | 15/03/2024 | 07/06/2024
TO-24-CKM GIS-T2104-02 | TRANSFORMER - CARRICKMINES GIS 220-CARRICKMINES GIS 110-T2104 | 11 | 8 | 8 | Reference | 18/03/2024 | 28/03/2024
TO-24-CUN-GLR-1-01 | 110kV FEEDER - CUNGHILL 110-GLENREE 110-1 | 5 | 4 | 4 | Scheduled | 18/03/2024 | 22/03/2024
TO-24-110 kV A2 @ GLR-01 | BUSBAR SECTION - GLENREE 110-GLENREE 110-110A2 | 5 | 4 | 4 | Scheduled | 18/03/2024 | 22/03/2024
TO-24-GLR-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - GLENREE 110-GLENREE 110-110SA1-2CB | 5 | 4 | 4 | Scheduled | 18/03/2024 | 22/03/2024
TO-24-GLR-T142-01 | DISTRIBUTION TRANSFORMER - GLENREE 110-GLENREE 38-T142 | 5 | 4 | 4 | Reference | 18/03/2024 | 22/03/2024
TO-24-220 kV A1 @ AD-02 | BUSBAR SECTION - AGHADA 220-AGHADA 220-220A1 | 16 | 10 | 10 | Scheduled | 19/03/2024 | 03/04/2024
TO-24-220 kV A2 @ AD-01 | BUSBAR SECTION - AGHADA 220-AGHADA 220-220A2 | 16 | 10 | 10 | Scheduled | 19/03/2024 | 03/04/2024
TO-24-220 kV B1 @ AD-01 | BUSBAR SECTION - AGHADA 220-AGHADA 220-220B1 | 16 | 10 | 10 | Scheduled | 19/03/2024 | 03/04/2024
TO-24-220 kV B2 @ AD-01 | BUSBAR SECTION - AGHADA 220-AGHADA 220-220B2 | 16 | 10 | 10 | Scheduled | 19/03/2024 | 03/04/2024
TO-24-AD-220K1-03 | COUPLER/SECTIONALISING CB - AGHADA 220-AGHADA 220-220K1 | 16 | 10 | 10 | Scheduled | 19/03/2024 | 03/04/2024
TO-24-AD-SA1-2CB-01 | COUPLER/SECTIONALISING CB - AGHADA 220-AGHADA 220-220SA1-2CB | 16 | 10 | 10 | Scheduled | 19/03/2024 | 03/04/2024
TO-24-AD-SB1-2CB-01 | COUPLER/SECTIONALISING CB - AGHADA 220-AGHADA 220-220SB1-2CB | 16 | 10 | 10 | Scheduled | 19/03/2024 | 03/04/2024
TO-24-AD-KRA-1-01 | 220kV FEEDER - AGHADA 220-KNOCKRAHA 220-1 | 16 | 10 |  | Scheduled | 19/03/2024 | 03/04/2024
TO-24-AD-T2102-01 | TRANSFORMER - AGHADA 220-AGHADA 110-T2102 | 16 | 10 | 10 | Scheduled | 19/03/2024 | 03/04/2024
TO-24-BIN-TIV-1-01 | 110kV FEEDER - BINBANE 110-TIEVEBRACK 110-1 | 4 | 4 | 4 | Scheduled | 19/03/2024 | 22/03/2024
TO-24-110 kV A1/A2 @ CAH-01 | BUSBAR SECTION - CAHIR 110-CAHIR 110-110A1-A2 | 10 | 8 | 8 | Scheduled | 19/03/2024 | 28/03/2024
TO-24-110 kV B1/B2 @ CAH-01 | BUSBAR SECTION - CAHIR 110-CAHIR 110-110B1-B2 | 10 | 8 | 8 | Scheduled | 19/03/2024 | 28/03/2024
TO-24-CAH-110K1-2-01 | COUPLER/SECTIONALISING CB - CAHIR 110-CAHIR 110-110K1-2 | 10 | 8 | 8 | Scheduled | 19/03/2024 | 28/03/2024
TO-24-CAH-T141-01 | DISTRIBUTION TRANSFORMER - CAHIR 110-CAHIR 38-T141 | 7 | 5 | 5 | Reference | 19/03/2024 | 25/03/2024
TO-24-CGG-DMY-1-01 | 110kV FEEDER - CARRIGDANGAN 110-DUNMANWAY 110-1 | 7 | 5 | 5 | Scheduled | 19/03/2024 | 25/03/2024
TO-24-CGG-T131-01 | GENERATOR TRANSFORMER - CARRIGDANGAN 110-CARRIGDANGAN 33-T131 | 7 | 5 | 5 | Scheduled | 19/03/2024 | 25/03/2024
TO-24-110 kV A2 @ CLA-01 | BUSBAR SECTION - CLASHAVOON 110-CLASHAVOON 110-110A2 | 10 | 8 | 8 | Scheduled | 19/03/2024 | 28/03/2024
TO-24-110 kV B2 @ CLA-01 | BUSBAR SECTION - CLASHAVOON 110-CLASHAVOON 110-110B2 | 10 | 8 | 8 | Scheduled | 19/03/2024 | 28/03/2024
TO-24-CLA-MAC-2-03 | 110kV FEEDER - CLASHAVOON 110-MACROOM 110-2 | 10 | 8 | 8 | Scheduled | 19/03/2024 | 28/03/2024
TO-24-DER-KIN-1-02 | 110kV FEEDER - DERRYIRON 110-KINNEGAD 110-1 | 23 | 15 | 15 | Scheduled | 19/03/2024 | 10/04/2024
TO-24-DER-T1/T2-02 | GENERATOR TRANSFORMER - DERRYIRON 110-RHODE 110-T1/T2 | 23 | 15 | 15 | Scheduled | 19/03/2024 | 10/04/2024
TO-24-GI-WAT-2-01 | 110kV FEEDER - GREAT ISLAND 110-WATERFORD 110-2 | 4 | 4 | 4 | Scheduled | 19/03/2024 | 22/03/2024
TO-24-KYT-MAY-1-01 | 220kV FEEDER - KELLYSTOWN 220-MAYNOOTH 220-1 | 10 | 8 | 8 | Scheduled | 19/03/2024 | 28/03/2024
TO-24-220 kV A2 @ KRA-02 | BUSBAR SECTION - KNOCKRAHA 220-KNOCKRAHA 220-220A2 | 16 | 10 | 10 | Scheduled | 19/03/2024 | 03/04/2024
TO-24-220 kV B2 @ KRA-02 | BUSBAR SECTION - KNOCKRAHA 220-KNOCKRAHA 220-220B2 | 16 | 10 | 10 | Scheduled | 19/03/2024 | 03/04/2024
TO-24-KRA-220SA1-2CB-02 | COUPLER/SECTIONALISING CB - KNOCKRAHA 220-KNOCKRAHA 220-220SA1-2CB | 16 | 10 | 10 | Scheduled | 19/03/2024 | 03/04/2024
TO-24-KRA-220SB1-2CB-02 | COUPLER/SECTIONALISING CB - KNOCKRAHA 220-KNOCKRAHA 220-220SB1-2CB | 16 | 10 | 10 | Scheduled | 19/03/2024 | 03/04/2024
TO-24-WOO-400K1-2-01 | COUPLER/SECTIONALISING CB - WOODLAND 400-WOODLAND 400-400K1-2 | 4 | 4 | 4 | Scheduled | 19/03/2024 | 22/03/2024
TO-24-CBA-110SA1-01 | SECTIONALISING DISCONNECT - CLOGHBOOLA 110-CLOGHBOOLA 110-110SA1 | 2 | 2 | 2 | Scheduled | 20/03/2024 | 21/03/2024
TO-24-CBA-110SA2-01 | SECTIONALISING DISCONNECT - CLOGHBOOLA 110-CLOGHBOOLA 110-110SA2 | 2 | 2 | 2 | Scheduled | 20/03/2024 | 21/03/2024
TO-24-CBA-T122-02 | DISTRIBUTION TRANSFORMER - CLOGHBOOLA 110-CLOGHBOOLA 20-T122 | 2 | 2 | 2 | Reference | 20/03/2024 | 21/03/2024
TO-24-CBA-T131-02 | GENERATOR TRANSFORMER - CLOGHBOOLA 110-CLOGHBOOLA 33-T131 | 2 | 2 | 2 | Scheduled | 20/03/2024 | 21/03/2024
TO-24-CBA-TRI-1-02 | 110kV FEEDER - CLOGHBOOLA 110-TRIEN 110-1 | 2 | 2 |  | Scheduled | 20/03/2024 | 21/03/2024
TO-24-DEY-T134-02 | GENERATOR TRANSFORMER - DERRYCARNEY 110-DERRYCARNEY 33-T134 | 2 | 2 | 2 | Scheduled | 20/03/2024 | 21/03/2024
TO-24-110 kV A1 @ GOR-02 | BUSBAR SECTION - GORMAN 110-GORMAN 110-110A1 | 9 | 7 | 7 | Scheduled | 20/03/2024 | 28/03/2024
TO-24-110 kV B1 @ GOR-01 | BUSBAR SECTION - GORMAN 110-GORMAN 110-110B1 | 9 | 7 | 7 | Scheduled | 20/03/2024 | 28/03/2024
TO-24-BYH-T2102-01 | TRANSFORMER - BALLYNAHULLA 220-BALLYNAHULLA 110-T2102 | 4 | 4 | 4 | Scheduled | 25/03/2024 | 28/03/2024
TO-24-CAH-T142-01 | DISTRIBUTION TRANSFORMER - CAHIR 110-CAHIR 38-T142 | 4 | 4 | 4 | Reference | 25/03/2024 | 28/03/2024
TO-24-CBR-DLT-1-03 | 110kV FEEDER - CASTLEBAR 110-DALTON 110-1 | 4 | 4 | 4 | Scheduled | 25/03/2024 | 28/03/2024
TO-24-110 kV A2 @ CF-04 | BUSBAR SECTION - CATHALEENS FALL 110-CATHALEENS FALL 110-110A2 | 4 | 4 | 4 | Scheduled | 25/03/2024 | 28/03/2024
TO-24-110 kV B2 @ CF-01 | BUSBAR SECTION - CATHALEENS FALL 110-CATHALEENS FALL 110-110B2 | 4 | 4 | 4 | Scheduled | 25/03/2024 | 28/03/2024
TO-24-CF-SRA-2-03 | 110kV FEEDER - CATHALEENS FALL 110-SRANANAGH 110-2 | 4 | 4 | 4 | Scheduled | 25/03/2024 | 28/03/2024
TO-24-TAW-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - TAWNAGHMORE 110-TAWNAGHMORE 110-110SA1-2CB | 4 | 4 | 4 | Scheduled | 25/03/2024 | 28/03/2024
TO-24-CKM GIS-R2001-01 | CAPACITOR/SVC/REACTOR - CARRICKMINES GIS 220-CARRICKMINES GIS 220-R2001 | 18 | 12 |  | Scheduled | 26/03/2024 | 12/04/2024
TO-24-AUG-KPG-1-01 | 110kV FEEDER - AUGHINISH 110-KILPADDOGE 110-1 | 4 | 4 |  | Scheduled | 02/04/2024 | 05/04/2024
TO-24-220 kV A1 @ CBT-01 | BUSBAR SECTION - CASTLEBAGOT 220-CASTLEBAGOT 220-220A1 | 9 | 7 | 7 | Scheduled | 02/04/2024 | 10/04/2024
TO-24-220 kV B1 @ CBT-01 | BUSBAR SECTION - CASTLEBAGOT 220-CASTLEBAGOT 220-220B1 | 9 | 7 | 7 | Scheduled | 02/04/2024 | 10/04/2024
TO-24-CBT-220K1-02 | COUPLER/SECTIONALISING CB - CASTLEBAGOT 220-CASTLEBAGOT 220-220K1 | 9 | 7 | 7 | Scheduled | 02/04/2024 | 10/04/2024
TO-24-CBT-220SA1-2CB-05 | COUPLER/SECTIONALISING CB - CASTLEBAGOT 220-CASTLEBAGOT 220-220SA1-2CB | 9 | 7 | 7 | Scheduled | 02/04/2024 | 10/04/2024
TO-24-CBT-220SB1-2CB-05 | COUPLER/SECTIONALISING CB - CASTLEBAGOT 220-CASTLEBAGOT 220-220SB1-2CB | 9 | 7 | 7 | Scheduled | 02/04/2024 | 10/04/2024
TO-24-CBT-MAY-1-01 | 220kV FEEDER - CASTLEBAGOT 220-MAYNOOTH 220-1 | 9 | 7 | 7 | Scheduled | 02/04/2024 | 10/04/2024
TO-24-CBR-SVC-02 | CAPACITOR/SVC/REACTOR - CASTLEBAR 110-CASTLEBAR 110-SVC | 4 | 4 | 4 | Scheduled | 02/04/2024 | 05/04/2024
TO-24-DRM-LET-1-01 | 110kV FEEDER - DRUMKEEN 110-LETTERKENNY 110-1 | 4 | 4 | 4 | Scheduled | 02/04/2024 | 05/04/2024
TO-24-BLU-110K1-01 | COUPLER/SECTIONALISING CB - BLUNDELSTOWN 110-BLUNDELSTOWN 110-110K1 | 1 | 1 | 1 | Scheduled | 03/04/2024 | 03/04/2024
TO-24-GAR-110K1-01 | COUPLER/SECTIONALISING CB - GARBALLAGH 110-GARBALLAGH 110-110K1 | 1 | 1 | 1 | Scheduled | 03/04/2024 | 03/04/2024
TO-24-LET-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - LETTERKENNY 110-LETTERKENNY 110-110SA1-2CB | 2 | 2 | 2 | Scheduled | 03/04/2024 | 04/04/2024
TO-24-LET-110SA1-3CB-02 | COUPLER/SECTIONALISING CB - LETTERKENNY 110-LETTERKENNY 110-110SA1-3CB | 2 | 2 | 2 | Scheduled | 03/04/2024 | 04/04/2024
TO-24-LET-M/CAP1-01 | CAPACITOR/SVC/REACTOR - LETTERKENNY 110-LETTERKENNY 110-M/CAP1 | 2 | 2 | 2 | Scheduled | 03/04/2024 | 04/04/2024
TO-24-LET-PST-01 | TRANSFORMER - LETTERKENNY 110-STRABANE 110-PST | 2 | 2 | 2 | Scheduled | 03/04/2024 | 04/04/2024
TO-24-LET-SVC-01 | CAPACITOR/SVC/REACTOR - LETTERKENNY 110-LETTERKENNY 110-SVC | 2 | 2 | 2 | Scheduled | 03/04/2024 | 04/04/2024
TO-24-LET-T141-01 | DISTRIBUTION TRANSFORMER - LETTERKENNY 110-LETTERKENNY 38-T141 | 2 | 2 |  | Reference | 03/04/2024 | 04/04/2024
TO-24-BYH-220SB1-2CB-01 | COUPLER/SECTIONALISING CB - BALLYNAHULLA 220-BALLYNAHULLA 220-220SB1-2CB | 1 | 1 | 1 | Scheduled | 04/04/2024 | 04/04/2024
TO-24-BVK-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - BALLYVOUSKILL 110-BALLYVOUSKILL 110-110SA1-2CB | 1 | 1 | 1 | Scheduled | 04/04/2024 | 04/04/2024
TO-24-CKM GIS-220SB1-3CB-01 | COUPLER/SECTIONALISING CB - CARRICKMINES GIS 220-CARRICKMINES GIS 220-22SB1-3CB | 1 | 1 | 1 | Scheduled | 04/04/2024 | 04/04/2024
TO-24-220 kV A2 @ CUL-02 | BUSBAR SECTION - CULLENAGH 220-CULLENAGH 220-220A2 | 43 | 30 | 30 | Scheduled | 04/04/2024 | 16/05/2024
TO-24-220 kV B2 @ CUL-02 | BUSBAR SECTION - CULLENAGH 220-CULLENAGH 220-220B2 | 43 | 30 | 30 | Scheduled | 04/04/2024 | 16/05/2024
TO-24-CUL-KRA-1-01 | 220kV FEEDER - CULLENAGH 220-KNOCKRAHA 220-1 | 43 | 30 |  | Scheduled | 04/04/2024 | 16/05/2024
TO-24-GAR-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - GARBALLAGH 110-GARBALLAGH 110-110SA1-2CB | 1 | 1 | 1 | Scheduled | 04/04/2024 | 04/04/2024
TO-24-GI-KKY-1-01 | 110kV FEEDER - GREAT ISLAND 110-KILKENNY 110-1 | 9 | 7 | 7 | Scheduled | 04/04/2024 | 12/04/2024
TO-24-GI-WAT-1-01 | 110kV FEEDER - GREAT ISLAND 110-WATERFORD 110-1 | 9 | 7 | 7 | Scheduled | 04/04/2024 | 12/04/2024
TO-24-220 kV A2 @ KRA-01 | BUSBAR SECTION - KNOCKRAHA 220-KNOCKRAHA 220-220A2 | 43 | 30 | 30 | Scheduled | 04/04/2024 | 16/05/2024
TO-24-220 kV B2 @ KRA-01 | BUSBAR SECTION - KNOCKRAHA 220-KNOCKRAHA 220-220B2 | 43 | 30 | 30 | Scheduled | 04/04/2024 | 16/05/2024
TO-24-KRA-220SA1-2CB-01 | COUPLER/SECTIONALISING CB - KNOCKRAHA 220-KNOCKRAHA 220-220SA1-2CB | 43 | 30 | 30 | Scheduled | 04/04/2024 | 16/05/2024
TO-24-KRA-220SB1-2CB-01 | COUPLER/SECTIONALISING CB - KNOCKRAHA 220-KNOCKRAHA 220-220SB1-2CB | 43 | 30 | 30 | Scheduled | 04/04/2024 | 16/05/2024
TO-24-KRA-RAF-1-01 | 220kV FEEDER - KNOCKRAHA 220-RAFFEEN 220-1 | 43 | 30 |  | Scheduled | 04/04/2024 | 16/05/2024
TO-24-BVK-110SB1-2CB-01 | COUPLER/SECTIONALISING CB - BALLYVOUSKILL 110-BALLYVOUSKILL 110-110SB1-2CB | 1 | 1 | 1 | Scheduled | 05/04/2024 | 05/04/2024
TO-24-GAR-110SB1-2CB-01 | COUPLER/SECTIONALISING CB - GARBALLAGH 110-GARBALLAGH 110-110SB1-2CB | 1 | 1 | 1 | Scheduled | 05/04/2024 | 05/04/2024
TO-24-220 kV A1 @ BYH-01 | BUSBAR SECTION - BALLYNAHULLA 220-BALLYNAHULLA 220-220A1 | 5 | 5 | 5 | Scheduled | 08/04/2024 | 12/04/2024
TO-24-220 kV B1 @ BYH-01 | BUSBAR SECTION - BALLYNAHULLA 220-BALLYNAHULLA 220-220B1 | 5 | 5 | 5 | Scheduled | 08/04/2024 | 12/04/2024
TO-24-BYH-220K1-01 | COUPLER/SECTIONALISING CB - BALLYNAHULLA 220-BALLYNAHULLA 220-220K1 | 5 | 5 | 5 | Scheduled | 08/04/2024 | 12/04/2024
TO-24-BYH-220SA1-2CB-01 | COUPLER/SECTIONALISING CB - BALLYNAHULLA 220-BALLYNAHULLA 220-220SA1-2CB | 5 | 5 | 5 | Scheduled | 08/04/2024 | 12/04/2024
TO-24-BYH-220SB1-2CB-02 | COUPLER/SECTIONALISING CB - BALLYNAHULLA 220-BALLYNAHULLA 220-220SB1-2CB | 5 | 5 | 5 | Scheduled | 08/04/2024 | 12/04/2024
TO-24-BK-CBR-1-01 | 110kV FEEDER - BELLACORICK 110-CASTLEBAR 110-1 | 12 | 10 | 10 | Scheduled | 08/04/2024 | 19/04/2024
TO-24-BK-SKY-1-01 | 110kV FEEDER - BELLACORICK 110-SRAHNAKILLY 110-1 | 19 | 15 | 15 | Scheduled | 08/04/2024 | 26/04/2024
TO-24-110 kV A4 @ CBT-03 | BUSBAR SECTION - CASTLEBAGOT 110-CASTLEBAGOT 110-110A4 | 5 | 5 | 5 | Scheduled | 08/04/2024 | 12/04/2024
TO-24-110 kV B4 @ CBT-03 | BUSBAR SECTION - CASTLEBAGOT 110-CASTLEBAGOT 110-110B4 | 5 | 5 | 5 | Scheduled | 08/04/2024 | 12/04/2024
TO-24-CBT-110K4-02 | COUPLER/SECTIONALISING CB - CASTLEBAGOT 110-CASTLEBAGOT 110-110K4 | 5 | 5 | 5 | Scheduled | 08/04/2024 | 12/04/2024
TO-24-CBT-110SA2-4CB-04 | COUPLER/SECTIONALISING CB - CASTLEBAGOT 110-CASTLEBAGOT 110-110SA2-4CB | 5 | 5 | 5 | Scheduled | 08/04/2024 | 12/04/2024
TO-24-CBT-110SB2-4CB-04 | COUPLER/SECTIONALISING CB - CASTLEBAGOT 110-CASTLEBAGOT 110-110SB2-4CB | 5 | 5 | 5 | Scheduled | 08/04/2024 | 12/04/2024
TO-24-CL-T101-02 | GENERATOR TRANSFORMER - CLIFF 110-CLIFF G1-T101 | 5 | 5 |  | Scheduled | 08/04/2024 | 12/04/2024
TO-24-CRO-KBY-1-01 | 110kV FEEDER - COOLROE 110-KILBARRY 110-1 | 5 | 5 |  | Scheduled | 08/04/2024 | 12/04/2024
TO-24-110 kV A2 @ FIN-02 | BUSBAR SECTION - FINGLAS 110-FINGLAS 110-110A2 | 3 | 3 | 3 | Scheduled | 08/04/2024 | 10/04/2024
TO-24-110 kV B2 @ FIN-02 | BUSBAR SECTION - FINGLAS 110-FINGLAS 110-110B2 | 3 | 3 | 3 | Scheduled | 08/04/2024 | 10/04/2024
TO-24-220 kV A1 @ RAF-03 | BUSBAR SECTION - RAFFEEN 220-RAFFEEN 220-220A1 | 5 | 5 | 5 | Scheduled | 08/04/2024 | 12/04/2024
TO-24-220 kV B1 @ RAF-03 | BUSBAR SECTION - RAFFEEN 220-RAFFEEN 220-220B1 | 5 | 5 | 5 | Scheduled | 08/04/2024 | 12/04/2024
TO-24-110 kV A2 @ SLB-01 | BUSBAR SECTION - SLIABH BAWN 110-SLIABH BAWN 110-110A2 | 5 | 5 | 5 | Scheduled | 08/04/2024 | 12/04/2024
TO-24-110 kV B2 @ SLB-01 | BUSBAR SECTION - SLIABH BAWN 110-SLIABH BAWN 110-110B2 | 5 | 5 | 5 | Scheduled | 08/04/2024 | 12/04/2024
TO-24-SKY-110SA1-01 | SECTIONALISING DISCONNECT - SRAHNAKILLY 110-SRAHNAKILLY 110-110SA1 | 19 | 15 | 15 | Scheduled | 08/04/2024 | 26/04/2024
TO-24-SKY-110SA2-01 | SECTIONALISING DISCONNECT - SRAHNAKILLY 110-SRAHNAKILLY 110-110SA2 | 19 | 15 | 15 | Scheduled | 08/04/2024 | 26/04/2024
TO-24-SKY-T131-02 | GENERATOR TRANSFORMER - SRAHNAKILLY 110-SRAHNAKILLY 33-T131 | 19 | 15 | 15 | Scheduled | 08/04/2024 | 26/04/2024
TO-24-SKY-T132-02 | GENERATOR TRANSFORMER - SRAHNAKILLY 110-SRAHNAKILLY 33-T132 | 19 | 15 | 15 | Scheduled | 08/04/2024 | 26/04/2024
TO-24-LLA-T133-01 | GENERATOR TRANSFORMER - LENALEA 110-LENALEA 33-T133 | 1 | 1 | 1 | Scheduled | 09/04/2024 | 09/04/2024
TO-24-CF-CL-1-02 | 110kV FEEDER - CATHALEENS FALL 110-CLIFF 110-1 | 2 | 2 | 2 | Scheduled | 10/04/2024 | 11/04/2024
TO-24-CL-T102-02 | GENERATOR TRANSFORMER - CLIFF 110-CLIFF G2-T102 | 2 | 2 | 2 | Scheduled | 10/04/2024 | 11/04/2024
TO-24-110 kV A2 @ FIN GIS-02 | BUSBAR SECTION - FINGLAS GIS 110-FINGLAS GIS 110-110A2 | 7 | 5 | 5 | Scheduled | 11/04/2024 | 17/04/2024
TO-24-110 kV B2 @ FIN GIS-02 | BUSBAR SECTION - FINGLAS GIS 110-FINGLAS GIS 110-110B2 | 7 | 5 | 5 | Scheduled | 11/04/2024 | 17/04/2024
TO-24-FIN GIS-110K2-03 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110K2 | 7 | 5 | 5 | Scheduled | 11/04/2024 | 17/04/2024
TO-24-FIN GIS-110SA1-2CB-03 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110SA1-2CB | 7 | 5 | 5 | Scheduled | 11/04/2024 | 17/04/2024
TO-24-FIN GIS-110SA2-4CB-04 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110SA2-4CB | 7 | 5 | 5 | Scheduled | 11/04/2024 | 17/04/2024
TO-24-FIN GIS-110SB1-2CB-03 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110SB1-2CB | 7 | 5 | 5 | Scheduled | 11/04/2024 | 17/04/2024
TO-24-FIN GIS-110SB2-4CB-05 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110SB2-4CB | 7 | 5 | 5 | Scheduled | 11/04/2024 | 17/04/2024
TO-24-GOR-220K1-2-01 | COUPLER/SECTIONALISING CB - GORMAN 220-GORMAN 220-220K1-2 | 1 | 1 | 1 | Scheduled | 12/04/2024 | 12/04/2024
TO-24-CDU-WOO-1-03 | 220kV FEEDER - CORDUFF 220-WOODLAND 220-1 | 7 | 5 | 5 | Scheduled | 13/04/2024 | 19/04/2024
TO-24-BGT-110K1-01 | COUPLER/SECTIONALISING CB - BALLYRAGGET 110-BALLYRAGGET 110-110K1 | 3 | 3 | 3 | Scheduled | 15/04/2024 | 17/04/2024
TO-24-BGT-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - BALLYRAGGET 110-BALLYRAGGET 110-110SA1-2CB | 3 | 3 | 3 | Scheduled | 15/04/2024 | 17/04/2024
TO-24-BGT-110SB1-2CB-01 | COUPLER/SECTIONALISING CB - BALLYRAGGET 110-BALLYRAGGET 110-110SB1-2CB | 3 | 3 | 3 | Scheduled | 15/04/2024 | 17/04/2024
TO-24-BGT-KKY-1-01 | 110kV FEEDER - BALLYRAGGET 110-KILKENNY 110-1 | 3 | 3 | 3 | Scheduled | 15/04/2024 | 17/04/2024
TO-24-BGT-141-01 | DISTRIBUTION TRANSFORMER - BALLYRAGGET 110-BALLYRAGGET 38-T141 | 3 | 3 | 3 | Reference | 15/04/2024 | 17/04/2024
TO-24-BGH-T132-02 | GENERATOR TRANSFORMER - BOGGERAGH 110-BOGGERAGH 33-T132 | 2 | 2 | 2 | Scheduled | 15/04/2024 | 16/04/2024
TO-24-220 kV B2 @ CKM GIS-01 | BUSBAR SECTION - CARRICKMINES GIS 220-CARRICKMINES GIS 220-220B2 | 9 | 7 | 7 | Scheduled | 15/04/2024 | 23/04/2024
TO-24-220 kV B4 @ CKM GIS-02 | BUSBAR SECTION - CARRICKMINES GIS 220-CARRICKMINES GIS 220-220B4 | 9 | 7 | 7 | Scheduled | 15/04/2024 | 23/04/2024
TO-24-CKM GIS-220SB2-4CB-02 | COUPLER/SECTIONALISING CB - CARRICKMINES GIS 220-CARRICKMINES GIS 220-22SB2-4CB | 9 | 7 | 7 | Scheduled | 15/04/2024 | 23/04/2024
TO-24-CTN-TIP-1-01 | 110kV FEEDER - CAUTEEN 110-TIPPERARY 110-1 | 5 | 5 | 5 | Scheduled | 15/04/2024 | 19/04/2024
TO-24-CRO-110SA2-01 | SECTIONALISING DISCONNECT - COOLROE 110-COOLROE 110-110SA2 | 5 | 5 | 5 | Scheduled | 15/04/2024 | 19/04/2024
TO-24-CRO-IA-1-01 | 110kV FEEDER - COOLROE 110-INNISCARRA 110-1 | 5 | 5 | 5 | Scheduled | 15/04/2024 | 19/04/2024
TO-24-CRA-110SA1-02 | SECTIONALISING DISCONNECT - CRANE 110-CRANE 110-110SA1 | 5 | 5 | 5 | Scheduled | 15/04/2024 | 19/04/2024
TO-24-CRA-110SA2-04 | SECTIONALISING DISCONNECT - CRANE 110-CRANE 110-110SA2 | 5 | 5 | 5 | Scheduled | 15/04/2024 | 19/04/2024
TO-24-CRA-T141-01 | DISTRIBUTION TRANSFORMER - CRANE 110-CRANE 38-T141 | 5 | 5 | 5 | Reference | 15/04/2024 | 19/04/2024
TO-24-CRA-TTU-1-01 | 110kV FEEDER - CRANE 110-TULLABEG 110-1 | 5 | 5 | 5 | Scheduled | 15/04/2024 | 19/04/2024
TO-24-KPG-T2101-01 | TRANSFORMER - KILPADDOGE 220-KILPADDOGE 110-T2101 | 5 | 5 | 5 | Scheduled | 15/04/2024 | 19/04/2024
TO-24-PRN-T4301-01 | TRANSFORMER - PORTAN 400-PORTAN 260-T4301 | 1 | 1 | 1 | Scheduled | 15/04/2024 | 15/04/2024
TO-24-PRN-WOO-1-04 | 400kV FEEDER - PORTAN 400-WOODLAND 400-1 | 1 | 1 | 1 | Scheduled | 15/04/2024 | 15/04/2024
TO-24-400 kV A1 @ WOO-01 | BUSBAR SECTION - WOODLAND 400-WOODLAND 400-400A1 | 1 | 1 | 1 | Scheduled | 15/04/2024 | 15/04/2024
TO-24-MP GIS-220K1-01 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 220-MONEYPOINT GIS 220-220K1 | 1 | 1 | 1 | Scheduled | 16/04/2024 | 16/04/2024
TO-24-PRN-WOO-1-01 | 400kV FEEDER - PORTAN 400-WOODLAND 400-1 | 4 | 4 | 4 | Scheduled | 16/04/2024 | 19/04/2024
TO-24-BGH-T121-02 | GENERATOR TRANSFORMER - BOGGERAGH 110-BOGGERAGH 20-T121 | 1 | 1 | 1 | Scheduled | 17/04/2024 | 17/04/2024
TO-24-MP GIS-220K2-01 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 220-MONEYPOINT GIS 220-220K2 | 1 | 1 | 1 | Scheduled | 17/04/2024 | 17/04/2024
TO-24-AA GIS-T104-04 | GENERATOR TRANSFORMER - ARDNACRUSHA GIS 110-ARDNACRUSHA GIS G4-T104 | 1 | 1 | 1 | Scheduled | 18/04/2024 | 18/04/2024
TO-24-110 kV A1 @ FIN GIS-01 | BUSBAR SECTION - FINGLAS GIS 110-FINGLAS GIS 110-110A1 | 2 | 2 | 2 | Scheduled | 18/04/2024 | 19/04/2024
TO-24-110 kV A2 @ FIN GIS-03 | BUSBAR SECTION - FINGLAS GIS 110-FINGLAS GIS 110-110A2 | 2 | 2 | 2 | Scheduled | 18/04/2024 | 19/04/2024
TO-24-110 kV A3 @ FIN GIS-01 | BUSBAR SECTION - FINGLAS GIS 110-FINGLAS GIS 110-110A3 | 2 | 2 | 2 | Scheduled | 18/04/2024 | 19/04/2024
TO-24-110 kV B1 @ FIN GIS-01 | BUSBAR SECTION - FINGLAS GIS 110-FINGLAS GIS 110-110B1 | 2 | 2 | 2 | Scheduled | 18/04/2024 | 19/04/2024
TO-24-110 kV B2 @ FIN GIS-03 | BUSBAR SECTION - FINGLAS GIS 110-FINGLAS GIS 110-110B2 | 2 | 2 | 2 | Scheduled | 18/04/2024 | 19/04/2024
TO-24-110 kV B3 @ FIN GIS-01 | BUSBAR SECTION - FINGLAS GIS 110-FINGLAS GIS 110-110B3 | 2 | 2 | 2 | Scheduled | 18/04/2024 | 19/04/2024
TO-24-FIN GIS-110K1-03 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110K1 | 2 | 2 | 2 | Scheduled | 18/04/2024 | 19/04/2024
TO-24-FIN GIS-110K2-04 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110K2 | 2 | 2 | 2 | Scheduled | 18/04/2024 | 19/04/2024
TO-24-FIN GIS-110SA1-2CB-04 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110SA1-2CB | 2 | 2 | 2 | Scheduled | 18/04/2024 | 19/04/2024
TO-24-FIN GIS-110SA1-3CB-02 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110SA1-3CB | 2 | 2 | 2 | Scheduled | 18/04/2024 | 19/04/2024
TO-24-FIN GIS-110SA2-4CB-05 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110SA2-4CB | 2 | 2 | 2 | Scheduled | 18/04/2024 | 19/04/2024
TO-24-FIN GIS-110SA3-5CB-02 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110SA3-5CB | 2 | 2 | 2 | Scheduled | 18/04/2024 | 19/04/2024
TO-24-FIN GIS-110SB1-2CB-04 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110SB1-2CB | 1 | 1 |  | Scheduled | 18/04/2024 | 18/04/2024
TO-24-FIN GIS-110SB1-3CB-02 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110SB1-3CB | 2 | 2 | 2 | Scheduled | 18/04/2024 | 19/04/2024
TO-24-FIN GIS-110SB2-4CB-06 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110SB2-4CB | 2 | 2 | 2 | Scheduled | 18/04/2024 | 19/04/2024
TO-24-FIN GIS-110SB3-5CB-02 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110SB3-5CB | 2 | 2 | 2 | Scheduled | 18/04/2024 | 19/04/2024
TO-24-FIN GIS-T2106-04 | TRANSFORMER - FINGLAS 220-FINGLAS GIS 110-T2106 | 2 | 2 | 2 | Scheduled | 18/04/2024 | 19/04/2024
TO-24-MP GIS-220SA1-2CB-01 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 220-MONEYPOINT GIS 220-220SA1-2CB | 1 | 1 | 1 | Scheduled | 18/04/2024 | 18/04/2024
TO-24-MP GIS-220SB1-2CB-01 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 220-MONEYPOINT GIS 220-220SB1-2CB | 1 | 1 | 1 | Scheduled | 19/04/2024 | 19/04/2024
TO-24-TB-T2102-03 | TRANSFORMER - TARBERT 220-TARBERT 110-T2102 | 3 | 1 | 1 | Scheduled | 19/04/2024 | 21/04/2024
TO-24-AD-ST101-01 | GENERATOR TRANSFORMER - AGHADA 110-AGHADA 10-ST101 | 5 | 5 | 5 | Scheduled | 22/04/2024 | 26/04/2024
TO-24-BAL-DRY-1-05 | 110kV FEEDER - BALTRASNA 110-DRYBRIDGE 110-1 | 150 | 105 | 105 | Scheduled | 22/04/2024 | 18/09/2024
TO-24-BIN-CF-1-01 | 110kV FEEDER - BINBANE 110-CATHALEENS FALL 110-1 | 143 | 100 | 100 | Scheduled | 22/04/2024 | 11/09/2024
TO-24-COS-FLA-1-03 | 110kV FEEDER - CARRICK ON SHANNON 110-FLAGFORD 110-1 | 58 | 40 |  | Scheduled | 22/04/2024 | 18/06/2024
TO-24-CD-KBY-1-01 | 110kV FEEDER - CARRIGADROHID 110-KILBARRY 110-1 | 12 | 10 | 10 | Scheduled | 22/04/2024 | 03/05/2024
TO-24-110 kV A2 @ CLO-02 | BUSBAR SECTION - CLOGHER 110-CLOGHER 110-110A2 | 8 | 6 | 6 | Scheduled | 22/04/2024 | 29/04/2024
TO-24-110 kV B2 @ CLO-02 | BUSBAR SECTION - CLOGHER 110-CLOGHER 110-110B2 | 8 | 6 | 6 | Scheduled | 22/04/2024 | 29/04/2024
TO-24-CLO-MRY-1-01 | 110kV FEEDER - CLOGHER 110-MULREAVY 110-1 | 8 | 6 | 6 | Scheduled | 22/04/2024 | 29/04/2024
TO-24-110 kV A1 @ FLA-06 | BUSBAR SECTION - FLAGFORD 110-FLAGFORD 110-110A1 | 54 | 38 | 38 | Proposed | 22/04/2024 | 14/06/2024
TO-24-110 kV B1 @ FLA-07 | BUSBAR SECTION - FLAGFORD 110-FLAGFORD 110-110B1 | 54 | 38 | 38 | Proposed | 22/04/2024 | 14/06/2024
TO-24-KTN-WAT-1-01 | 110kV FEEDER - KILLOTERAN 110-WATERFORD 110-1 | 5 | 5 | 5 | Scheduled | 22/04/2024 | 26/04/2024
TO-24-LIM-RAT-1-01 | 110kV FEEDER - LIMERICK 110-RATHKEALE 110-1 | 5 | 5 | 5 | Scheduled | 22/04/2024 | 26/04/2024
TO-24-MRY-T131-01 | GENERATOR TRANSFORMER - MULREAVY 110-MULREAVY 33-T131 | 8 | 6 | 6 | Scheduled | 22/04/2024 | 29/04/2024
TO-24-ROP-WEX-1-02 | 110kV FEEDER - ROSSPILE 110-WEXFORD 110-1 | 5 | 5 |  | Scheduled | 22/04/2024 | 26/04/2024
TO-24-UGL-T132-03 | GENERATOR TRANSFORMER - UGGOOL 110-UGGOOL 33-T132 | 4 | 4 | 4 | Scheduled | 22/04/2024 | 25/04/2024
TO-24-UGL-T134-02 | GENERATOR TRANSFORMER - UGGOOL 110-UGGOOL 33-T134 | 4 | 4 | 4 | Scheduled | 22/04/2024 | 25/04/2024
TO-24-WEX-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - WEXFORD 110-WEXFORD 110-110SA1-2CB | 5 | 5 |  | Scheduled | 22/04/2024 | 26/04/2024
TO-24-WEX-T121-01 | DISTRIBUTION TRANSFORMER - WEXFORD 110-WEXFORD 20-T121 | 5 | 5 | 5 | Reference | 22/04/2024 | 26/04/2024
TO-24-WEX-T141-01 | DISTRIBUTION TRANSFORMER - WEXFORD 110-WEXFORD 38-T141 | 5 | 5 | 5 | Reference | 22/04/2024 | 26/04/2024
TO-24-GAE-T121-02 | GENERATOR TRANSFORMER - GLANLEE 110-GLANLEE 20-T121 | 2 | 2 | 2 | Scheduled | 23/04/2024 | 24/04/2024
TO-24-KPG-220SB1-3CB-01 | COUPLER/SECTIONALISING CB - KILPADDOGE 220-KILPADDOGE 220-220SB1-3CB | 2 | 2 | 2 | Scheduled | 23/04/2024 | 24/04/2024
TO-24-BNK-T122-02 | TSO CUSTOMER TRANSFORMER - BARNAKYLE 110-BARNAKYLE 20-T122 | 8 | 6 | 6 | Scheduled | 24/04/2024 | 01/05/2024
TO-24-LOU-RRU-1-13 | 110kV FEEDER - LOUTH 110-RATRUSSAN 110-1 | 140 | 97 | 97 | Proposed | 24/04/2024 | 10/09/2024
TO-24-RRU-110SA1-05 | SECTIONALISING DISCONNECT - RATRUSSAN 110-RATRUSSAN 110-110SA1 | 8 | 6 | 6 | Scheduled | 24/04/2024 | 01/05/2024
TO-24-RRU-110SA2-05 | SECTIONALISING DISCONNECT - RATRUSSAN 110-RATRUSSAN 110-110SA2 | 7 | 5 | 5 | Proposed | 24/04/2024 | 30/04/2024
TO-24-RRU-SKL-1-03 | 110kV FEEDER - RATRUSSAN 110-SHANKILL 110-1 | 29 | 20 | 20 | Scheduled | 24/04/2024 | 22/05/2024
TO-24-RRU-T121-05 | GENERATOR TRANSFORMER - RATRUSSAN 110-RATRUSSAN 20-T121 | 29 | 20 | 20 | Scheduled | 24/04/2024 | 22/05/2024
TO-24-RRU-T122-05 | GENERATOR TRANSFORMER - RATRUSSAN 110-RATRUSSAN 20-T122 | 29 | 20 | 20 | Scheduled | 24/04/2024 | 22/05/2024
TO-24-110 kV A3 @ AA GIS-01 | BUSBAR SECTION - ARDNACRUSHA GIS 110-ARDNACRUSHA GIS 110-110A3 | 1 | 1 | 1 | Scheduled | 25/04/2024 | 25/04/2024
TO-24-AA GIS-T104-02 | GENERATOR TRANSFORMER - ARDNACRUSHA GIS 110-ARDNACRUSHA GIS G4-T104 | 1 | 1 | 1 | Scheduled | 25/04/2024 | 25/04/2024
TO-24-220 kV A1 @ FIN-02 | BUSBAR SECTION - FINGLAS 220-FINGLAS 220-220A1 | 12 | 7 | 7 | Scheduled | 27/04/2024 | 08/05/2024
TO-24-220 kV B1 @ FIN-02 | BUSBAR SECTION - FINGLAS 220-FINGLAS 220-220B1 | 12 | 7 | 7 | Scheduled | 27/04/2024 | 08/05/2024
TO-24-FIN-HN-1-01 | 220kV FEEDER - FINGLAS 220-HUNTSTOWN 220-1 | 12 | 7 | 7 | Scheduled | 27/04/2024 | 08/05/2024
TO-24-HN-T2010/11-01 | GENERATOR TRANSFORMER - HUNTSTOWN 220-HUNTSTOWN G10/11-T2010/11 | 12 | 7 | 7 | Scheduled | 27/04/2024 | 08/05/2024
TO-24-220 kV A1 @ AD-04 | BUSBAR SECTION - AGHADA 220-AGHADA 220-220A1 | 5 | 5 | 5 | Scheduled | 29/04/2024 | 03/05/2024
TO-24-220 kV A2 @ AD-07 | BUSBAR SECTION - AGHADA 220-AGHADA 220-220A2 | 5 | 5 | 5 | Scheduled | 29/04/2024 | 03/05/2024
TO-24-AD-SA1-2CB-04 | COUPLER/SECTIONALISING CB - AGHADA 220-AGHADA 220-220SA1-2CB | 5 | 5 | 5 | Scheduled | 29/04/2024 | 03/05/2024
TO-24-110 kV A3 @ AA GIS-02 | BUSBAR SECTION - ARDNACRUSHA GIS 110-ARDNACRUSHA GIS 110-110A3 | 5 | 5 | 5 | Scheduled | 29/04/2024 | 03/05/2024
TO-24-110 kV B3 @ AA GIS-01 | BUSBAR SECTION - ARDNACRUSHA GIS 110-ARDNACRUSHA GIS 110-110B3 | 5 | 5 | 5 | Scheduled | 29/04/2024 | 03/05/2024
TO-24-AA GIS-CAP1-01 | CAPACITOR/SVC/REACTOR - ARDNACRUSHA GIS 110-ARDNACRUSHA GIS 110-CAP1 | 5 | 5 | 5 | Scheduled | 29/04/2024 | 03/05/2024
TO-24-ARK-T2102-01 | TRANSFORMER - ARKLOW 220-ARKLOW 110-T2102 | 5 | 5 | 5 | Scheduled | 29/04/2024 | 03/05/2024
TO-24-ATH-LA-1-02 | 110kV FEEDER - ATHLONE 110-LANESBORO 110-1 | 15 | 10 | 10 | Scheduled | 29/04/2024 | 13/05/2024
TO-24-ATY-CLW-1-07 | 110kV FEEDER - ATHY 110-CARLOW 110-1 | 15 | 10 | 10 | Proposed | 29/04/2024 | 13/05/2024
TO-24-CL-T102-05 | GENERATOR TRANSFORMER - CLIFF 110-CLIFF G2-T102 | 5 | 5 | 5 | Proposed | 29/04/2024 | 03/05/2024
TO-24-MCE-T124-03 | TSO CUSTOMER TRANSFORMER - MACETOWN 110-MACETOWN 20-T124 | 10 | 7 | 7 | Proposed | 29/04/2024 | 08/05/2024
TO-24-BNK-CBT-2-02 | 110kV FEEDER - BARNAKYLE 110-CASTLEBAGOT 110-2 | 2 | 2 | 2 | Proposed | 30/04/2024 | 01/05/2024
TO-24-CBT-110K1-03 | COUPLER/SECTIONALISING CB - CASTLEBAGOT 110-CASTLEBAGOT 110-110K1 | 3 | 3 | 3 | Proposed | 30/04/2024 | 02/05/2024
TO-24-CHA-GLE-1-01 | 110kV FEEDER - CHARLEVILLE 110-GLENLARA 110-1 | 2 | 2 | 2 | Proposed | 30/04/2024 | 01/05/2024
TO-24-CRO-IA-1-04 | 110kV FEEDER - COOLROE 110-INNISCARRA 110-1 | 1 | 1 | 1 | Proposed | 30/04/2024 | 30/04/2024
TO-24-GOR-T122-01 | GENERATOR TRANSFORMER - GORMAN 110-GORMAN 20-T122 | 1 | 1 | 1 | Scheduled | 30/04/2024 | 30/04/2024
TO-24-110 kV A1 @ IA-02 | BUSBAR SECTION - INNISCARRA 110-INNISCARRA 110-110A1 | 1 | 1 | 1 | Proposed | 30/04/2024 | 30/04/2024
TO-24-IA-MAC-1-04 | 110kV FEEDER - INNISCARRA 110-MACROOM 110-1 | 1 | 1 | 1 | Proposed | 30/04/2024 | 30/04/2024
TO-24-IA-T101-04 | GENERATOR TRANSFORMER - INNISCARRA 110-INNISCARRA G1-T101 | 1 | 1 | 1 | Proposed | 30/04/2024 | 30/04/2024
TO-24-AA GIS-T101-01 | GENERATOR TRANSFORMER - ARDNACRUSHA GIS 110-ARDNACRUSHA GIS G1-T101 | 136 | 95 | 95 | Scheduled | 01/05/2024 | 13/09/2024
TO-24-CSH-T2102-01 | TRANSFORMER - CASHLA 220-CASHLA 110-T2102 | 79 | 55 | 55 | Proposed | 02/05/2024 | 19/07/2024
TO-24-DER-TSB-1-06 | 110kV FEEDER - DERRYIRON 110-THORNSBERRY 110-1 | 86 | 60 | 60 | Proposed | 02/05/2024 | 26/07/2024
TO-24-HN-T2010/11-02 | GENERATOR TRANSFORMER - HUNTSTOWN 220-HUNTSTOWN G10/11-T2010/11 | 3 | 2 | 2 | Scheduled | 06/05/2024 | 08/05/2024
TO-24-WOH-T122-01 | GENERATOR TRANSFORMER - WOODHOUSE 110-WOODHOUSE 20-T122 | 5 | 4 | 4 | Scheduled | 06/05/2024 | 10/05/2024
TO-24-110 kV A2 @ AA GIS-01 | BUSBAR SECTION - ARDNACRUSHA GIS 110-ARDNACRUSHA GIS 110-110A2 | 10 | 8 | 8 | Scheduled | 07/05/2024 | 16/05/2024
TO-24-110 kV B2 @ AA GIS-01 | BUSBAR SECTION - ARDNACRUSHA GIS 110-ARDNACRUSHA GIS 110-110B2 | 10 | 8 | 8 | Scheduled | 07/05/2024 | 16/05/2024
TO-24-AA GIS-ENN-1-04 | 110kV FEEDER - ARDNACRUSHA GIS 110-ENNIS 110-1 | 10 | 8 | 8 | Scheduled | 07/05/2024 | 16/05/2024
TO-24-BLC-110K1-01 | COUPLER/SECTIONALISING CB - BELCAMP 110-BELCAMP 110-110K1 | 1 | 1 | 1 | Scheduled | 07/05/2024 | 07/05/2024
TO-24-BUT-CUL-1-01 | 110kV FEEDER - BUTLERSTOWN 110-CULLENAGH 110-1 | 3 | 3 | 3 | Scheduled | 07/05/2024 | 09/05/2024
TO-24-CBT-MAY-1-05 | 220kV FEEDER - CASTLEBAGOT 220-MAYNOOTH 220-1 | 9 | 7 | 7 | Proposed | 07/05/2024 | 15/05/2024
TO-24-CBR-CAP2-01 | CAPACITOR/SVC/REACTOR - CASTLEBAR 110-CASTLEBAR 110-CAP2 | 4 | 4 | 4 | Scheduled | 07/05/2024 | 10/05/2024
TO-24-110 kV A2 @ CF-05 | BUSBAR SECTION - CATHALEENS FALL 110-CATHALEENS FALL 110-110A2 | 1 | 1 | 1 | Proposed | 07/05/2024 | 07/05/2024
TO-24-CF-T104-04 | GENERATOR TRANSFORMER - CATHALEENS FALL 110-CATHALEENS FALL G4-T104 | 1 | 1 | 1 | Proposed | 07/05/2024 | 07/05/2024
TO-24-CLO-DRM-1-01 | 110kV FEEDER - CLOGHER 110-DRUMKEEN 110-1 | 11 | 9 | 9 | Proposed | 07/05/2024 | 17/05/2024
TO-24-KTL-T131-01 | GENERATOR TRANSFORMER - KILTEEL 110-KILTEEL 33-T131 | 1 | 1 | 1 | Scheduled | 07/05/2024 | 07/05/2024
TO-24-AD-220K1-02 | COUPLER/SECTIONALISING CB - AGHADA 220-AGHADA 220-220K1 | 1 | 1 | 1 | Scheduled | 08/05/2024 | 08/05/2024
TO-24-BLC-110K3-01 | COUPLER/SECTIONALISING CB - BELCAMP 110-BELCAMP 110-110K3 | 1 | 1 | 1 | Scheduled | 08/05/2024 | 08/05/2024
TO-24-CSH-GAL GIS-2-02 | 110kV FEEDER - CASHLA 110-GALWAY GIS 110-2 | 1 | 1 | 1 | Scheduled | 08/05/2024 | 08/05/2024
TO-24-LIS-T131-01 | GENERATOR TRANSFORMER - LISDRUM 110-LISDRUM 33-T131 | 1 | 1 | 1 | Scheduled | 08/05/2024 | 08/05/2024
TO-24-ROP-110K1-01 | COUPLER/SECTIONALISING CB - ROSSPILE 110-ROSSPILE 110-110K1 | 1 | 1 | 1 | Proposed | 08/05/2024 | 08/05/2024
TO-24-220 kV A1 @ AD-01 | BUSBAR SECTION - AGHADA 220-AGHADA 220-220A1 | 1 | 1 | 1 | Proposed | 09/05/2024 | 09/05/2024
TO-24-220 kV A2 @ AD-06 | BUSBAR SECTION - AGHADA 220-AGHADA 220-220A2 | 1 | 1 | 1 | Proposed | 09/05/2024 | 09/05/2024
TO-24-220 kV B1 @ AD-03 | BUSBAR SECTION - AGHADA 220-AGHADA 220-220B1 | 1 | 1 | 1 | Proposed | 09/05/2024 | 09/05/2024
TO-24-220 kV B2 @ AD-05 | BUSBAR SECTION - AGHADA 220-AGHADA 220-220B2 | 1 | 1 | 1 | Proposed | 09/05/2024 | 09/05/2024
TO-24-AD-T2011/12-03 | GENERATOR TRANSFORMER - AGHADA 220-AGHADA G11/12-T2011/12 | 1 | 1 | 1 | Proposed | 09/05/2024 | 09/05/2024
TO-24-AA GIS-T104-01 | GENERATOR TRANSFORMER - ARDNACRUSHA GIS 110-ARDNACRUSHA GIS G4-T104 | 14 | 10 | 10 | Proposed | 09/05/2024 | 22/05/2024
TO-24-ARK-T101-01 | DISTRIBUTION TRANSFORMER - ARKLOW 110-ARKLOW 10-T101 | 2 | 2 | 2 | Reference (Proposed) | 09/05/2024 | 10/05/2024
TO-24-BLC-110SA1-3CB-01 | COUPLER/SECTIONALISING CB - BELCAMP 110-BELCAMP 110-110SA1-3CB | 1 | 1 | 1 | Scheduled | 09/05/2024 | 09/05/2024
TO-24-BLC-110SB1-3CB-01 | COUPLER/SECTIONALISING CB - BELCAMP 110-BELCAMP 110-110SB1-3CB | 1 | 1 | 1 | Scheduled | 10/05/2024 | 10/05/2024
TO-24-CSH-CLN-1-01 | 110kV FEEDER - CASHLA 110-CLOON 110-1 | 6 | 5 | 5 | Proposed | 13/05/2024 | 18/05/2024
TO-24-CLH-T122-01 | GENERATOR TRANSFORMER - CLAHANE 110-CLAHANE 20-T122 | 5 | 5 | 5 | Scheduled | 13/05/2024 | 17/05/2024
TO-24-CL-T102-03 | GENERATOR TRANSFORMER - CLIFF 110-CLIFF G2-T102 | 11 | 9 |  | Proposed | 13/05/2024 | 23/05/2024
TO-24-CRA-LWD-1-06 | 110kV FEEDER - CRANE 110-LODGEWOOD 110-1 | 5 | 5 | 5 | Proposed | 13/05/2024 | 17/05/2024
TO-24-400 kV A1 @ DSN-02 | BUSBAR SECTION - DUNSTOWN 400-DUNSTOWN 400-400A1 | 12 | 10 | 10 | Proposed | 13/05/2024 | 24/05/2024
TO-24-400 kV A2 @ DSN-01 | BUSBAR SECTION - DUNSTOWN 400-DUNSTOWN 400-400A2 | 12 | 10 | 10 | Proposed | 13/05/2024 | 24/05/2024
TO-24-400 kV B1 @ DSN-02 | BUSBAR SECTION - DUNSTOWN 400-DUNSTOWN 400-400B1 | 12 | 10 | 10 | Proposed | 13/05/2024 | 24/05/2024
TO-24-400 kV B2 @ DSN-01 | BUSBAR SECTION - DUNSTOWN 400-DUNSTOWN 400-400B2 | 12 | 10 | 10 | Proposed | 13/05/2024 | 24/05/2024
TO-24-DSN-400K1-2-01 | COUPLER/SECTIONALISING CB - DUNSTOWN 400-DUNSTOWN 400-400K1-2 | 12 | 10 | 10 | Proposed | 13/05/2024 | 24/05/2024
TO-24-IA-MAC-1-03 | 110kV FEEDER - INNISCARRA 110-MACROOM 110-1 | 5 | 5 | 5 | Proposed | 13/05/2024 | 17/05/2024
TO-24-KLS-220K1-2-04 | COUPLER/SECTIONALISING CB - KELLIS 220-KELLIS 220-220K1-2 | 57 | 40 | 40 | Scheduled | 13/05/2024 | 08/07/2024
TO-24-LOU-MTH-1-01 | 110kV FEEDER - LOUTH 110-MEATH HILL 110-1 | 5 | 5 |  | Proposed | 13/05/2024 | 17/05/2024
TO-24-MP GIS-T4001-01 | GENERATOR TRANSFORMER - MONEYPOINT GIS 400-MONEYPOINT GIS G1-T4001 | 9 | 7 | 7 | Proposed | 13/05/2024 | 21/05/2024
TO-24-DAL,T-DAL-1-01 | 110kV FEEDER - DALLOW tee-DALLOW 110-1 | 7 | 5 | 5 | Proposed | 14/05/2024 | 20/05/2024
TO-24-IA-T101-02 | GENERATOR TRANSFORMER - INNISCARRA 110-INNISCARRA G1-T101 | 10 | 8 | 8 | Proposed | 14/05/2024 | 23/05/2024
TO-24-MOY-CAP2-01 | CAPACITOR/SVC/REACTOR - MOY 110-MOY 110-CAP2 | 2 | 2 | 2 | Proposed | 14/05/2024 | 15/05/2024
TO-24-LOU-MLN-1-01 | 110kV FEEDER - LOUTH 110-MULLAGHARLIN 110-1 | 139 | 97 | 97 | Scheduled | 15/05/2024 | 30/09/2024
TO-24-ROP-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - ROSSPILE 110-ROSSPILE 110-110SA1-2CB | 1 | 1 | 1 | Proposed | 15/05/2024 | 15/05/2024
TO-24-ROP-110SB1-2CB-01 | COUPLER/SECTIONALISING CB - ROSSPILE 110-ROSSPILE 110-110SB1-2CB | 1 | 1 | 1 | Proposed | 16/05/2024 | 16/05/2024
TO-24-SLC-T122-03 | GENERATOR TRANSFORMER - SLIEVECALLAN 110-SLIEVECALLAN 20-T122 | 1 | 1 | 1 | Proposed | 16/05/2024 | 16/05/2024
TO-24-BVK-T2101-01 | TRANSFORMER - BALLYVOUSKILL 220-BALLYVOUSKILL 110-T2101 | 15 | 11 |  | Proposed | 17/05/2024 | 31/05/2024
TO-24-CLE-WOO-1-01 | 220kV FEEDER - CLONEE 220-WOODLAND 220-1 | 116 | 80 | 80 | Scheduled | 17/05/2024 | 09/09/2024
TO-24-KYT-WOO-1-01 | 220kV FEEDER - KELLYSTOWN 220-WOODLAND 220-1 | 116 | 80 | 80 | Scheduled | 17/05/2024 | 09/09/2024
TO-24-CSH-GAL GIS-1-01 | 110kV FEEDER - CASHLA 110-GALWAY GIS 110-1 | 3 | 3 | 3 | Proposed | 20/05/2024 | 22/05/2024
TO-24-CBT-T2103-01 | TRANSFORMER - CASTLEBAGOT 220-CASTLEBAGOT 110-T2103 | 12 | 10 |  | Scheduled | 20/05/2024 | 31/05/2024
TO-24-CUL-T2101-03 | TRANSFORMER - CULLENAGH 220-CULLENAGH 110-T2101 | 2 | 2 | 2 | Proposed | 20/05/2024 | 21/05/2024
TO-24-FIN-FIN GIS-2-01 | 110kV FEEDER - FINGLAS 110-FINGLAS GIS 110-2 | 226 | 158 | 158 | Proposed | 20/05/2024 | 31/12/2024
TO-24-FIN-T2104-01 | TRANSFORMER - FINGLAS 220-FINGLAS 110-T2104 | 115 | 81 | 81 | Proposed | 20/05/2024 | 11/09/2024
TO-24-FIN-T2104-03 | TRANSFORMER - FINGLAS 220-FINGLAS 110-T2104 | 12 | 10 | 10 | Scheduled | 20/05/2024 | 31/05/2024
TO-24-FLA-220K1-2-01 | COUPLER/SECTIONALISING CB - FLAGFORD 220-FLAGFORD 220-220K1-2 | 5 | 5 | 5 | Proposed | 20/05/2024 | 24/05/2024
TO-24-GI GIS-220K1-03 | COUPLER/SECTIONALISING CB - GREAT ISLAND GIS 220-GREAT ISLAND GIS 220-220K1 | 12 | 10 | 10 | Proposed | 20/05/2024 | 31/05/2024
TO-24-GI GIS-220SA1-2CB-04 | COUPLER/SECTIONALISING CB - GREAT ISLAND GIS 220-GREAT ISLAND GIS 220-220SA1-2CB | 12 | 10 | 10 | Proposed | 20/05/2024 | 31/05/2024
TO-24-GI GIS-220SB1-2CB-02 | COUPLER/SECTIONALISING CB - GREAT ISLAND GIS 220-GREAT ISLAND GIS 220-220SB1-2CB | 12 | 10 | 10 | Proposed | 20/05/2024 | 31/05/2024
TO-24-KLN-KPG-1-01 | 220kV FEEDER - KILLONAN 220-KILPADDOGE 220-1 | 12 | 10 | 10 | Proposed | 20/05/2024 | 31/05/2024
TO-24-220 kV A4 @ KPG-01 | BUSBAR SECTION - KILPADDOGE 220-KILPADDOGE 220-220A4 | 12 | 10 | 10 | Proposed | 20/05/2024 | 31/05/2024
TO-24-220 kV B4 @ KPG-01 | BUSBAR SECTION - KILPADDOGE 220-KILPADDOGE 220-220B4 | 12 | 10 | 10 | Proposed | 20/05/2024 | 31/05/2024
TO-24-MP GIS-T4201-01 | TRANSFORMER - MONEYPOINT GIS 400-MONEYPOINT GIS 220-T4201 | 5 | 5 | 5 | Scheduled | 20/05/2024 | 24/05/2024
TO-24-110 kV A2 @ RAF-01 | BUSBAR SECTION - RAFFEEN 110-RAFFEEN 110-110A2 | 5 | 5 | 5 | Proposed | 20/05/2024 | 24/05/2024
TO-24-110 kV B2 @ RAF-01 | BUSBAR SECTION - RAFFEEN 110-RAFFEEN 110-110B2 | 5 | 5 | 5 | Proposed | 20/05/2024 | 24/05/2024
TO-24-RAF-CAP2-01 | CAPACITOR/SVC/REACTOR - RAFFEEN 110-RAFFEEN 110-CAP2 | 5 | 5 | 5 | Proposed | 20/05/2024 | 24/05/2024
TO-24-DAL,T-DEY-1-01 | 110kV FEEDER - DALLOW tee-DERRYCARNEY 110-1 | 86 | 60 | 60 | Proposed | 21/05/2024 | 14/08/2024
TO-24-GI GIS-T2004-02 | GENERATOR TRANSFORMER - GREAT ISLAND GIS 220-GREAT ISLAND GIS G4-T2004 | 11 | 9 | 9 | Proposed | 21/05/2024 | 31/05/2024
TO-24-LIS-CAP2-01 | CAPACITOR/SVC/REACTOR - LISDRUM 110-LISDRUM 110-CAP2 | 4 | 4 | 4 | Proposed | 21/05/2024 | 24/05/2024
TO-24-CUL-GI GIS-1-01 | 220kV FEEDER - CULLENAGH 220-GREAT ISLAND GIS 220-1 | 3 | 3 | 3 | Proposed | 22/05/2024 | 24/05/2024
TO-24-CLN-110SA1-04 | SECTIONALISING DISCONNECT - CLOON 110-CLOON 110-110SA1 | 9 | 7 | 7 | Proposed | 23/05/2024 | 31/05/2024
TO-24-CLN-LA-1-04 | 110kV FEEDER - CLOON 110-LANESBORO 110-1 | 9 | 7 | 7 | Proposed | 23/05/2024 | 31/05/2024
TO-24-BYH-CDL-1-01 | 110kV FEEDER - BALLYNAHULLA 110-CORDAL 110-1 | 4 | 4 | 4 | Scheduled | 27/05/2024 | 30/05/2024
TO-24-CAH-DOO-1-01 | 110kV FEEDER - CAHIR 110-DOON 110-1 | 12 | 9 | 9 | Scheduled | 27/05/2024 | 07/06/2024
TO-24-CSH-GAL GIS-4-02 | 110kV FEEDER - CASHLA 110-GALWAY GIS 110-4 | 5 | 5 | 5 | Proposed | 27/05/2024 | 31/05/2024
TO-24-CDL-110SA1-01 | SECTIONALISING DISCONNECT - CORDAL 110-CORDAL 110-110SA1 | 4 | 4 | 4 | Scheduled | 27/05/2024 | 30/05/2024
TO-24-CDL-110SA2-01 | SECTIONALISING DISCONNECT - CORDAL 110-CORDAL 110-110SA2 | 4 | 4 | 4 | Scheduled | 27/05/2024 | 30/05/2024
TO-24-CDL-T132-01 | GENERATOR TRANSFORMER - CORDAL 110-CORDAL 33-T132 | 4 | 4 |  | Scheduled | 27/05/2024 | 30/05/2024
TO-24-CDL-T141-01 | DISTRIBUTION TRANSFORMER - CORDAL 110-CORDAL 38-T141 | 4 | 4 | 4 | Reference | 27/05/2024 | 30/05/2024
TO-24-CDL-T141-02 | DISTRIBUTION TRANSFORMER - CORDAL 110-CORDAL 38-T141 | 1 | 1 | 1 | Reference (Proposed) | 27/05/2024 | 27/05/2024
TO-24-COW-110SA1-03 | SECTIONALISING DISCONNECT - COW CROSS 110-COW CROSS 110-110SA1 | 15 | 10 | 10 | Proposed | 27/05/2024 | 10/06/2024
TO-24-COW-OLD-2-02 | 110kV FEEDER - COW CROSS 110-OLDCOURT 110-2 | 15 | 10 | 10 | Reference (Proposed) | 27/05/2024 | 10/06/2024
TO-24-COW-RAF-1-03 | 110kV FEEDER - COW CROSS 110-RAFFEEN 110-1 | 15 | 10 | 10 | Proposed | 27/05/2024 | 10/06/2024
TO-24-DND-T122-01 | TSO CUSTOMER TRANSFORMER - DARNDALE 110-DARNDALE 20-T122 | 5 | 5 | 5 | Scheduled | 27/05/2024 | 31/05/2024
TO-24-KLS-T2101-05 | TRANSFORMER - KELLIS 220-KELLIS 110-T2101 | 5 | 5 | 5 | Scheduled | 27/05/2024 | 31/05/2024
TO-24-KBY-MR-1-02 | 110kV FEEDER - KILBARRY 110-MARINA 110-1 | 107 | 75 | 75 | Proposed | 27/05/2024 | 10/09/2024
TO-24-KBY-MR-2-02 | 110kV FEEDER - KILBARRY 110-MARINA 110-2 | 107 | 75 | 75 | Proposed | 27/05/2024 | 10/09/2024
TO-24-MP GIS-T4002-02 | GENERATOR TRANSFORMER - MONEYPOINT GIS 400-MONEYPOINT GIS G2-T4002 | 5 | 5 | 5 | Proposed | 27/05/2024 | 31/05/2024
TO-24-CUL-220K1-2-01 | COUPLER/SECTIONALISING CB - CULLENAGH 220-CULLENAGH 220-220K1-2 | 2 | 2 | 2 | Proposed | 28/05/2024 | 29/05/2024
TO-24-DEY-T134-03 | GENERATOR TRANSFORMER - DERRYCARNEY 110-DERRYCARNEY 33-T134 | 2 | 2 | 2 | Proposed | 28/05/2024 | 29/05/2024
TO-24-KBY-MR-1-01 | 110kV FEEDER - KILBARRY 110-MARINA 110-1 | 10 | 7 |  | Scheduled | 28/05/2024 | 06/06/2024
TO-24-KBY-MR-2-01 | 110kV FEEDER - KILBARRY 110-MARINA 110-2 | 4 | 4 | 4 | Scheduled | 28/05/2024 | 31/05/2024
TO-24-MLC-T121-01 | GENERATOR TRANSFORMER - MOUNTLUCAS 110-MOUNTLUCAS 20-T121 | 2 | 2 | 2 | Proposed | 29/05/2024 | 30/05/2024
TO-24-GLE-KCR-1-01 | 110kV FEEDER - GLENLARA 110-KNOCKACUMMER 110-1 | Unknown | Unknown | 4 | Planned | June | June
TO-24-KCR-T121-01 | GENERATOR TRANSFORMER - KNOCKACUMMER 110-KNOCKACUMMER 20-T121 | Unknown | Unknown | 4 | Planned | June | June
TO-24-BYH-KNR-1-01 | 220kV FEEDER - BALLYNAHULLA 220-KNOCKANURE 220-1 | Unknown | Unknown | 4 | Planned | June | June
TO-24-CKM GIS-220SA1-2CB-01 | COUPLER/SECTIONALISING CB - CARRICKMINES GIS 220-CARRICKMINES GIS 220-22SA1-2CB | 2 | 2 | 2 | Proposed | 04/06/2024 | 05/06/2024
TO-24-CSH-DLT-1-01 | 110kV FEEDER - CASHLA 110-DALTON 110-1 | 11 | 9 | 9 | Proposed | 04/06/2024 | 14/06/2024
TO-24-CBT-220K1-01 | COUPLER/SECTIONALISING CB - CASTLEBAGOT 220-CASTLEBAGOT 220-220K1 | 4 | 4 | 4 | Proposed | 04/06/2024 | 07/06/2024
TO-24-GOR-NAV-2-02 | 110kV FEEDER - GORMAN 110-NAVAN 110-2 | Unknown | Unknown | 40 | Planned | June | July
TO-24-GI GIS-KLS-1-01 | 220kV FEEDER - GREAT ISLAND GIS 220-KELLIS 220-1 | Unknown | Unknown | 6 | Planned | June | June
TO-24-KNY-SAL-1-01 | 110kV FEEDER - KNOCKRANNY 110-SALTHILL 110-1 | 4 | 4 | 4 | Proposed | 04/06/2024 | 07/06/2024
TO-24-PA-110SA1-04 | SECTIONALISING DISCONNECT - POLLAPHUCA 110-POLLAPHUCA 110-110SA1 | Unknown | Unknown | 9 | Planned | June | June
TO-24-PA-110SA2-04 | SECTIONALISING DISCONNECT - POLLAPHUCA 110-POLLAPHUCA 110-110SA2 | Unknown | Unknown | 9 | Planned | June | June
TO-24-PA-T101-04 | GENERATOR TRANSFORMER - POLLAPHUCA 110-POLLAPHUCA G1-T101 | Unknown | Unknown | 9 | Planned | June | June
TO-24-STR-T141-04 | DISTRIBUTION TRANSFORMER - STRATFORD 110-STRATFORD 38-T141 | Unknown | Unknown | 9 | Reference (Planned) | June | June
TO-24-STR,T-CLW-1-04 | 110kV FEEDER - STRATFORD tee-CARLOW 110-1 | Unknown | Unknown | 9 | Planned | June | June
TO-24-STR,T-PA-1-04 | 110kV FEEDER - STRATFORD tee-POLLAPHUCA 110-1 | Unknown | Unknown | 9 | Planned | June | June
TO-24-STR,T-STR-1-04 | 110kV FEEDER - STRATFORD tee-STRATFORD 110-1 | Unknown | Unknown | 9 | Planned | June | June
TO-24-AA GIS-LIM-1-01 | 110kV FEEDER - ARDNACRUSHA GIS 110-LIMERICK 110-1 | 3 | 3 | 3 | Proposed | 05/06/2024 | 07/06/2024
TO-24-BAG-110K1-02 | COUPLER/SECTIONALISING CB - BARNAGEERAGH 110-BARNAGEERAGH 110-110K1 | 1 | 1 | 1 | Proposed | 05/06/2024 | 05/06/2024
TO-24-BNK-CBT-1-01 | 110kV FEEDER - BARNAKYLE 110-CASTLEBAGOT 110-1 | 2 | 2 | 2 | Proposed | 05/06/2024 | 06/06/2024
TO-24-BDA-T102-01 | TSO CUSTOMER TRANSFORMER - BARODA 110-BARODA 10-T102 | 3 | 3 | 3 | Proposed | 05/06/2024 | 07/06/2024
TO-24-CBT-CLU-1-01 | 110kV FEEDER - CASTLEBAGOT 110-CLUTTERLAND 110-1 | 3 | 3 | 3 | Proposed | 05/06/2024 | 07/06/2024
TO-24-CF-SRA-1-04 | 110kV FEEDER - CATHALEENS FALL 110-SRANANAGH 110-1 | 56 | 40 | 40 | Proposed | 05/06/2024 | 30/07/2024
TO-24-CDU-110K1-3-01 | COUPLER/SECTIONALISING CB - CORDUFF 110-CORDUFF 110-110K1-3 | 1 | 1 | 1 | Proposed | 05/06/2024 | 05/06/2024
TO-24-CKG-110K2-02 | COUPLER/SECTIONALISING CB - CORKAGH 110-CORKAGH 110-110K2 | 1 | 1 | 1 | Proposed | 05/06/2024 | 05/06/2024
TO-24-DEY-110K2-01 | COUPLER/SECTIONALISING CB - DERRYCARNEY 110-DERRYCARNEY 110-110K2 | 1 | 1 | 1 | Proposed | 05/06/2024 | 05/06/2024
TO-24-KLN-T2101-01 | TRANSFORMER - KILLONAN 220-KILLONAN 110-T2101 | 3 | 3 | 3 | Proposed | 05/06/2024 | 07/06/2024
TO-24-RYB GIS-T103-01 | TSO CUSTOMER TRANSFORMER - RYEBROOK GIS 110-RYEBROOK 10-T103 | 2 | 2 | 2 | Proposed | 05/06/2024 | 06/06/2024
TO-24-CKM GIS-220SA1-3CB-01 | COUPLER/SECTIONALISING CB - CARRICKMINES GIS 220-CARRICKMINES GIS 220-22SA1-3CB | 2 | 2 | 2 | Proposed | 06/06/2024 | 07/06/2024
TO-24-CKG-T121-01 | TSO CUSTOMER TRANSFORMER - CORKAGH 110-CORKAGH 20-T121 | 2 | 2 | 2 | Proposed | 06/06/2024 | 07/06/2024
TO-24-CRU-T221-01 | TSO CUSTOMER TRANSFORMER - CRUISERATH 220-CRUISERATH 20-T221 | 2 | 2 | 2 | Proposed | 06/06/2024 | 07/06/2024
TO-24-MP GIS-400K4-01 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 400-MONEYPOINT GIS 400-400K4 | 1 | 1 | 1 | Proposed | 06/06/2024 | 06/06/2024
TO-24-CDU-220K1-3-01 | COUPLER/SECTIONALISING CB - CORDUFF 220-CORDUFF 220-220K1-3 | 1 | 1 | 1 | Proposed | 07/06/2024 | 07/06/2024
TO-24-RYB GIS-T104-01 | TSO CUSTOMER TRANSFORMER - RYEBROOK GIS 110-RYEBROOK 10-T104 | 1 | 1 | 1 | Proposed | 07/06/2024 | 07/06/2024
TO-24-ATE-TOB-1-01 | 110kV FEEDER - ATHEA 110-TOBERTOREEN 110-1 | Unknown | Unknown | 5 | Planned | June | June
TO-24-AUG-CFM-2-01 | 110kV FEEDER - AUGHINISH 110-CASTLEFARM 110-2 | Unknown | Unknown | 5 | Planned | June | June
TO-24-AUG-SK-3-01 | 110kV FEEDER - AUGHINISH 110-SEALROCK 110-3 | Unknown | Unknown | 10 | Planned | June | June
TO-24-BDA-MON-1-01 | 110kV FEEDER - BARODA 110-MONREAD 110-1 | 5 | 5 | 5 | Proposed | 10/06/2024 | 14/06/2024
TO-24-CSH-220K1-2-01 | COUPLER/SECTIONALISING CB - CASHLA 220-CASHLA 220-220K1-2 | 5 | 5 | 5 | Proposed | 10/06/2024 | 14/06/2024
TO-24-CBT-110SA2-4CB-03 | COUPLER/SECTIONALISING CB - CASTLEBAGOT 110-CASTLEBAGOT 110-110SA2-4CB | 5 | 5 | 5 | Proposed | 10/06/2024 | 14/06/2024
TO-24-CBT-T2104-01 | TRANSFORMER - CASTLEBAGOT 220-CASTLEBAGOT 110-T2104 | Unknown | Unknown | 10 | Planned | June | June
TO-24-CFM-T102-01 | TSO CUSTOMER TRANSFORMER - CASTLEFARM 110-CASTLEFARM 10-T102 | 5 | 5 | 5 | Reference (Proposed) | 10/06/2024 | 14/06/2024
TO-24-CF-T103-01 | GENERATOR TRANSFORMER - CATHALEENS FALL 110-CATHALEENS FALL G3-T103 | Unknown | Unknown | 7 | Planned | June | June
TO-24-CHA-MAL-1-01 | 110kV FEEDER - CHARLEVILLE 110-MALLOW 110-1 | Unknown | Unknown | 10 | Planned | June | June
TO-24-CDU-220K1-2-01 | COUPLER/SECTIONALISING CB - CORDUFF 220-CORDUFF 220-220K1-2 | 12 | 10 | 10 | Proposed | 10/06/2024 | 21/06/2024
TO-24-DRO-T121-01 | GENERATOR TRANSFORMER - DROMADA 110-DROMADA 20-T121 | Unknown | Unknown | 5 | Planned | June | June
TO-24-DRU-ENN-1-05 | 110kV FEEDER - DRUMLINE 110-ENNIS 110-1 | 64 | 45 | 45 | Proposed | 10/06/2024 | 12/08/2024
TO-24-GAL GIS-KNY-1-02 | 110kV FEEDER - GALWAY GIS 110-KNOCKRANNY 110-1 | 5 | 5 | 5 | Proposed | 10/06/2024 | 14/06/2024
TO-24-KTL-CAP1-01 | CAPACITOR/SVC/REACTOR - KILTEEL 110-KILTEEL 110-CAP1 | 5 | 5 | 5 | Proposed | 10/06/2024 | 14/06/2024
TO-24-MAY-T2103-01 | TRANSFORMER - MAYNOOTH 220-MAYNOOTH 110-T2103 | Unknown | Unknown |  | Planned | June | June
TO-24-PB-R2001-02 | CAPACITOR/SVC/REACTOR - POOLBEG 220-POOLBEG 220-R2001 | Unknown | Unknown | 5 | Planned | June | June
TO-24-SK-T103-01 | GENERATOR TRANSFORMER - SEALROCK 110-SEALROCK G3-T103 | Unknown | Unknown | 10 | Planned | June | June
TO-24-TOB-T132-01 | GENERATOR TRANSFORMER - TOBERTOREEN 110-TOBERTOREEN 33-T132 | Unknown | Unknown | 5 | Planned | June | June
TO-24-WOO-220K1-2-01 | COUPLER/SECTIONALISING CB - WOODLAND 220-WOODLAND 220-220K1-2 | Unknown | Unknown | 15 | Planned | June | June
TO-24-BNK-T121-01 | TSO CUSTOMER TRANSFORMER - BARNAKYLE 110-BARNAKYLE 20-T121 | 2 | 2 | 2 | Proposed | 11/06/2024 | 12/06/2024
TO-24-BRT-220K2-01 | COUPLER/SECTIONALISING CB - BRACETOWN 220-BRACETOWN 220-220K2 | 1 | 1 | 1 | Proposed | 11/06/2024 | 11/06/2024
TO-24-COW-110SA2-01 | SECTIONALISING DISCONNECT - COW CROSS 110-COW CROSS 110-110SA2 | Unknown | Unknown | 12 | Planned | June | June
TO-24-CRU-220K1-01 | COUPLER/SECTIONALISING CB - CRUISERATH 220-CRUISERATH 220-220K1 | 1 | 1 | 1 | Proposed | 11/06/2024 | 11/06/2024
TO-24-MP GIS-400SA1-2CB-01 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 400-MONEYPOINT GIS 400-400SA1-2CB | 1 | 1 | 1 | Proposed | 11/06/2024 | 11/06/2024
TO-24-RYB GIS-T106-01 | TSO CUSTOMER TRANSFORMER - RYEBROOK GIS 110-RYEBROOK 10-T106 | 2 | 2 | 2 | Proposed | 11/06/2024 | 12/06/2024
TO-24-AA GIS-T102-01 | GENERATOR TRANSFORMER - ARDNACRUSHA GIS 110-ARDNACRUSHA GIS G2-T102 | Unknown | Unknown | 3 | Planned | June | June
TO-24-BDN-CUL-1-01 | 110kV FEEDER - BALLYDINE 110-CULLENAGH 110-1 | 2 | 2 | 2 | Proposed | 12/06/2024 | 13/06/2024
TO-24-110 kV A1 @ CAH-02 | BUSBAR SECTION - CAHIR 110-CAHIR 110-110A1 | 2 | 2 | 2 | Proposed | 12/06/2024 | 13/06/2024
TO-24-CAH-KHL-1-01 | 110kV FEEDER - CAHIR 110-KILL HILL 110-1 | 2 | 2 | 2 | Proposed | 12/06/2024 | 13/06/2024
TO-24-CLG-T122-01 | TSO CUSTOMER TRANSFORMER - CLOGHRAN 110-CLOGHRAN 20-T122 | 2 | 2 | 2 | Proposed | 12/06/2024 | 13/06/2024
TO-24-CRU-220K2-03 | COUPLER/SECTIONALISING CB - CRUISERATH 220-CRUISERATH 220-220K2 | 1 | 1 | 1 | Proposed | 12/06/2024 | 12/06/2024
TO-24-KLS-KKY-1-03 | 110kV FEEDER - KELLIS 110-KILKENNY 110-1 | 10 | 8 | 8 | Proposed | 12/06/2024 | 21/06/2024
TO-24-KLN-T2103-01 | TRANSFORMER - KILLONAN 220-KILLONAN 110-T2103 | 2 | 2 | 2 | Proposed | 12/06/2024 | 13/06/2024
TO-24-MP GIS-400SA2-4CB-01 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 400-MONEYPOINT GIS 400-400SA2-4CB | 1 | 1 | 1 | Proposed | 12/06/2024 | 12/06/2024
TO-24-SLB-T132-01 | GENERATOR TRANSFORMER - SLIABH BAWN 110-SLIABH BAWN 33-T132 | Unknown | Unknown | 3 | Planned | June | June
TO-24-AGL-DYN-1-04 | 110kV FEEDER - AGANNYGAL 110-DERRYBRIEN 110-1 | Unknown | Unknown | 2 | Planned | June | June
TO-24-CRU-SA1-2CB-03 | COUPLER/SECTIONALISING CB - CRUISERATH 220-CRUISERATH 220-220SA1-2CB | 1 | 1 | 1 | Proposed | 13/06/2024 | 13/06/2024
TO-24-DND-T121-02 | TSO CUSTOMER TRANSFORMER - DARNDALE 110-DARNDALE 20-T121 | 2 | 2 | 2 | Proposed | 13/06/2024 | 14/06/2024
TO-24-DYN-T121-03 | GENERATOR TRANSFORMER - DERRYBRIEN 110-DERRYBRIEN 20-T121 | Unknown | Unknown | 2 | Reference (Planned) | June | June
TO-24-MP GIS-400SB1-2CB-01 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 400-MONEYPOINT GIS 400-400SB1-2CB | 1 | 1 | 1 | Proposed | 13/06/2024 | 13/06/2024
TO-24-RYB GIS-T107-01 | TSO CUSTOMER TRANSFORMER - RYEBROOK GIS 110-RYEBROOK 10-T107 | 2 | 2 | 2 | Proposed | 13/06/2024 | 14/06/2024
TO-24-CLG-T124-01 | TSO CUSTOMER TRANSFORMER - CLOGHRAN 110-CLOGHRAN 20-T124 | 1 | 1 | 1 | Proposed | 14/06/2024 | 14/06/2024
TO-24-CRU-SB1-2CB-03 | COUPLER/SECTIONALISING CB - CRUISERATH 220-CRUISERATH 220-220SB1-2CB | 1 | 1 | 1 | Proposed | 14/06/2024 | 14/06/2024
TO-24-TH-T2001/2-01 | GENERATOR TRANSFORMER - TURLOUGH HILL 220-TURLOUGH HILL G1-T2001/2 | Unknown | Unknown | 0 | Planned | June | June
TO-24-TH-T2003/4-01 | GENERATOR TRANSFORMER - TURLOUGH HILL 220-TURLOUGH HILL G1-T2003/4 | Unknown | Unknown | 0 | Planned | June | June
TO-24-ATE-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - ATHEA 110-ATHEA 110-110SA1-2CB | Unknown | Unknown | 5 | Planned | June | June
TO-24-ATE-DRO-1-01 | 110kV FEEDER - ATHEA 110-DROMADA 110-1 | Unknown | Unknown | 5 | Planned | June | June
TO-24-ATE-KNR-1-01 | 110kV FEEDER - ATHEA 110-KNOCKANURE 110-1 | Unknown | Unknown | 5 | Planned | June | June
TO-24-ATE-T121-01 | GENERATOR TRANSFORMER - ATHEA 110-ATHEA 20-T121 | Unknown | Unknown | 5 | Planned | June | June
TO-24-ATE-TOB-1-02 | 110kV FEEDER - ATHEA 110-TOBERTOREEN 110-1 | Unknown | Unknown | 5 | Planned | June | June
TO-24-ATH-CAP3-01 | CAPACITOR/SVC/REACTOR - ATHLONE 110-ATHLONE 110-CAP3 | Unknown | Unknown | 5 | Planned | June | June
TO-24-ATH-SH-1-02 | 110kV FEEDER - ATHLONE 110-SHANNONBRIDGE 110-1 | 12 | 10 | 10 | Proposed | 17/06/2024 | 28/06/2024
TO-24-CKM GIS-DSN-1-01 | 220kV FEEDER - CARRICKMINES GIS 220-DUNSTOWN 220-1 | 10 | 8 | 8 | Proposed | 17/06/2024 | 26/06/2024
TO-24-CBT-110SB1-2CB-03 | COUPLER/SECTIONALISING CB - CASTLEBAGOT 110-CASTLEBAGOT 110-110SB1-2CB | 5 | 5 | 5 | Proposed | 17/06/2024 | 21/06/2024
TO-24-CLE-220K1-01 | COUPLER/SECTIONALISING CB - CLONEE 220-CLONEE 220-220K1 | 5 | 5 | 5 | Proposed | 17/06/2024 | 21/06/2024
TO-24-KKY-CAP2-01 | CAPACITOR/SVC/REACTOR - KILKENNY 110-KILKENNY 110-CAP2 | 5 | 5 | 5 | Proposed | 17/06/2024 | 21/06/2024
TO-24-KPG-MP GIS-2-01 | 220kV FEEDER - KILPADDOGE 220-MONEYPOINT GIS 220-2 | 5 | 5 | 5 | Proposed | 17/06/2024 | 21/06/2024
TO-24-LET-SVC-02 | CAPACITOR/SVC/REACTOR - LETTERKENNY 110-LETTERKENNY 110-SVC | 5 | 5 | 5 | Proposed | 17/06/2024 | 21/06/2024
TO-24-MP GIS-400SA1-3CB-01 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 400-MONEYPOINT GIS 400-400SA1-3CB | 5 | 5 | 5 | Proposed | 17/06/2024 | 21/06/2024
TO-24-TOB-T132-02 | GENERATOR TRANSFORMER - TOBERTOREEN 110-TOBERTOREEN 33-T132 | Unknown | Unknown | 5 | Planned | June | June
TO-24-AUG-MTN-1-01 | 110kV FEEDER - AUGHINISH 110-MONETEEN 110-1 | 9 | 7 | 7 | Proposed | 18/06/2024 | 26/06/2024
TO-24-CKM GIS-220SA2-4CB-02 | COUPLER/SECTIONALISING CB - CARRICKMINES GIS 220-CARRICKMINES GIS 220-22SA2-4CB | 2 | 2 | 2 | Proposed | 18/06/2024 | 19/06/2024
TO-24-CLO-CRD-1-01 | 110kV FEEDER - CLOGHER 110-CROAGHONAGH 110-1 | 4 | 4 | 4 | Proposed | 18/06/2024 | 21/06/2024
TO-24-CRU-CDU-1-02 | 220kV FEEDER - CRUISERATH 220-CORDUFF 220-1 | 4 | 4 | 4 | Proposed | 18/06/2024 | 21/06/2024
TO-24-MAY-TH-1-01 | 220kV FEEDER - MAYNOOTH 220-TURLOUGH HILL 220-1 | 4 | 4 | 4 | Proposed | 18/06/2024 | 21/06/2024
TO-24-RYB GIS-T109-02 | TSO CUSTOMER TRANSFORMER - RYEBROOK GIS 110-RYEBROOK 10-T109 | 1 | 1 | 1 | Proposed | 18/06/2024 | 18/06/2024
TO-24-CDL-T141-03 | DISTRIBUTION TRANSFORMER - CORDAL 110-CORDAL 38-T141 | 1 | 1 | 1 | Reference (Proposed) | 19/06/2024 | 19/06/2024
TO-24-RYB GIS-T108-02 | TSO CUSTOMER TRANSFORMER - RYEBROOK GIS 110-RYEBROOK 10-T108 | 2 | 2 | 2 | Proposed | 19/06/2024 | 20/06/2024
TO-24-CSH-TY-1-05 | 220kV FEEDER - CASHLA 220-TYNAGH 220-1 | Unknown | Unknown | 45 | Planned | June | August
TO-24-BLU-CDU-1-02 | 110kV FEEDER - BLUNDELSTOWN 110-CORDUFF 110-1 | Unknown | Unknown | 25 | Planned | June | July
TO-24-CBT-110SB2-4CB-03 | COUPLER/SECTIONALISING CB - CASTLEBAGOT 110-CASTLEBAGOT 110-110SB2-4CB | 5 | 5 | 5 | Proposed | 24/06/2024 | 28/06/2024
TO-24-CF-CAP2-01 | CAPACITOR/SVC/REACTOR - CATHALEENS FALL 110-CATHALEENS FALL 110-CAP2 | 5 | 5 | 5 | Proposed | 24/06/2024 | 28/06/2024
TO-24-CLG-T126-02 | TSO CUSTOMER TRANSFORMER - CLOGHRAN 110-CLOGHRAN 20-T126 | 5 | 5 | 5 | Proposed | 24/06/2024 | 28/06/2024
TO-24-SH-220K1-2-01 | COUPLER/SECTIONALISING CB - SHANNONBRIDGE 220-SHANNONBRIDGE 220-220K1-2 | Unknown | Unknown |  | Planned | June | July
TO-24-CTN-KLN-1-01 | 110kV FEEDER - CAUTEEN 110-KILLONAN 110-1 | 4 | 4 | 4 | Proposed | 25/06/2024 | 28/06/2024
TO-24-CLU-110K1-01 | COUPLER/SECTIONALISING CB - CLUTTERLAND 110-CLUTTERLAND 110-110K1 | 1 | 1 | 1 | Proposed | 25/06/2024 | 25/06/2024
TO-24-CKG-T122-01 | TSO CUSTOMER TRANSFORMER - CORKAGH 110-CORKAGH 20-T122 | 2 | 2 | 2 | Proposed | 25/06/2024 | 26/06/2024
TO-24-CLU-110K2-01 | COUPLER/SECTIONALISING CB - CLUTTERLAND 110-CLUTTERLAND 110-110K2 | 1 | 1 | 1 | Proposed | 26/06/2024 | 26/06/2024
TO-24-TY-T2001/2-02 | GENERATOR TRANSFORMER - TYNAGH 220-TYNAGH G1/2-T2001/2 | Unknown | Unknown | 1 | Planned | June | June
TO-24-CLU-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - CLUTTERLAND 110-CLUTTERLAND 110-110SA1-2CB | 1 | 1 | 1 | Proposed | 27/06/2024 | 27/06/2024
TO-24-CNO-KPG-1-01 | 110kV FEEDER - COOLNANOONAGH 110-KILPADDOGE 110-1 | Unknown | Unknown | 2 | Planned | June | June
TO-24-CNO-T131-01 | GENERATOR TRANSFORMER - COOLNANOONAGH 110-COOLNANOONAGH 33-T131 | Unknown | Unknown | 2 | Planned | June | June
TO-24-CKG-T123-01 | TSO CUSTOMER TRANSFORMER - CORKAGH 110-CORKAGH 20-T123 | 2 | 2 | 2 | Proposed | 27/06/2024 | 28/06/2024
TO-24-CLU-T121-01 | TSO CUSTOMER TRANSFORMER - CLUTTERLAND 110-CLUTTERLAND 20-T121 | 1 | 1 | 1 | Proposed | 28/06/2024 | 28/06/2024
TO-24-BVK-COT-1-01 | 110kV FEEDER - BALLYVOUSKILL 110-COOMATAGGART 110-1 | Unknown | Unknown | 5 | Planned | July | July
TO-24-COT-110SA1-01 | SECTIONALISING DISCONNECT - COOMATAGGART 110-COOMATAGGART 110-110SA1 | Unknown | Unknown | 5 | Planned | July | July
TO-24-COT-110SA2-01 | SECTIONALISING DISCONNECT - COOMATAGGART 110-COOMATAGGART 110-110SA2 | Unknown | Unknown | 5 | Planned | July | July
TO-24-COT-FILTER1-01 | CAPACITOR/SVC/REACTOR - COOMATAGGART 110-COOMATAGGART 110-FILTER1 | Unknown | Unknown | 5 | Planned | July | July
TO-24-COT-T132-01 | GENERATOR TRANSFORMER - COOMATAGGART 110-COOMATAGGART 33-T132 | Unknown | Unknown | 5 | Planned | July | July
TO-24-COT-T141-01 | DISTRIBUTION TRANSFORMER - COOMATAGGART 110-COOMATAGGART 38-T141 | Unknown | Unknown | 5 | Reference (Planned) | July | July
TO-24-MID-110SA2-01 | SECTIONALISING DISCONNECT - MIDLETON 110-MIDLETON 110-110SA2 | Unknown | Unknown | 5 | Planned | July | July
TO-24-MID-T102-01 | DISTRIBUTION TRANSFORMER - MIDLETON 110-MIDLETON 10-T102 | Unknown | Unknown | 5 | Reference (Planned) | July | July
TO-24-MID-WHI-1-01 | 110kV FEEDER - MIDLETON 110-WHITEGATE 110-1 | Unknown | Unknown |  | Planned | July | July
TO-24-TAW-T1/T2-01 | GENERATOR TRANSFORMER - TAWNAGHMORE 110-TAWNAGHMORE 10-T1/T2 | Unknown | Unknown | 3 | Planned | July | July
TO-24-WOO-T4201-01 | TRANSFORMER - WOODLAND 400-WOODLAND 220-T4201 | Unknown | Unknown |  | Planned | July | July
TO-24-ENN-SLC-1-02 | 110kV FEEDER - ENNIS 110-SLIEVECALLAN 110-1 | Unknown | Unknown | 3 | Planned | July | July
TO-24-KLH-KNY-1-01 | 110kV FEEDER - KNOCKALOUGH 110-KNOCKRANNY 110-1 | Unknown | Unknown | 3 | Planned | July | July
TO-24-KLH-T121-01 | GENERATOR TRANSFORMER - KNOCKALOUGH 110-KNOCKALOUGH 20-T121 | Unknown | Unknown | 3 | Planned | July | July
TO-24-SLC-110SA1-02 | SECTIONALISING DISCONNECT - SLIEVECALLAN 110-SLIEVECALLAN 110-110SA1 | Unknown | Unknown | 3 | Planned | July | July
TO-24-SLC-110SA2-02 | SECTIONALISING DISCONNECT - SLIEVECALLAN 110-SLIEVECALLAN 110-110SA2 | Unknown | Unknown | 3 | Planned | July | July
TO-24-SLC-T121-02 | GENERATOR TRANSFORMER - SLIEVECALLAN 110-SLIEVECALLAN 20-T121 | Unknown | Unknown | 3 | Planned | July | July
TO-24-SLC-T122-02 | GENERATOR TRANSFORMER - SLIEVECALLAN 110-SLIEVECALLAN 20-T122 | Unknown | Unknown | 3 | Planned | July | July
TO-24-AUG-SK-4-01 | 110kV FEEDER - AUGHINISH 110-SEALROCK 110-4 | Unknown | Unknown | 44 | Planned | July | September
TO-24-CFN-SH-1-01 | 220kV FEEDER - CLONIFFEEN 220-SHANNONBRIDGE 220-1 | Unknown | Unknown | 1 | Planned | July | July
TO-24-CFN-T232-01 | GENERATOR TRANSFORMER - CLONIFFEEN 220-CLONIFFEEN 33-T232 | Unknown | Unknown | 1 | Planned | July | July
TO-24-KNY-UGL-1-01 | 110kV FEEDER - KNOCKRANNY 110-UGGOOL 110-1 | Unknown | Unknown | 2 | Planned | July | July
TO-24-LET-CAP2-01 | CAPACITOR/SVC/REACTOR - LETTERKENNY 110-LETTERKENNY 110-CAP2 | Unknown | Unknown | 10 | Planned | July | July
TO-24-SK-T104-01 | GENERATOR TRANSFORMER - SEALROCK 110-SEALROCK G4-T104 | Unknown | Unknown | 44 | Planned | July | September
TO-24-TAW-T3-01 | GENERATOR TRANSFORMER - TAWNAGHMORE 110-TAWNAGHMORE 10-T3 | Unknown | Unknown | 1 | Planned | July | July
TO-24-UGL-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - UGGOOL 110-UGGOOL 110-110SA1-2CB | Unknown | Unknown | 2 | Planned | July | July
TO-24-UGL-T131-01 | GENERATOR TRANSFORMER - UGGOOL 110-UGGOOL 33-T131 | Unknown | Unknown |  | Planned | July | July
TO-24-UGL-T132-02 | GENERATOR TRANSFORMER - UGGOOL 110-UGGOOL 33-T132 | Unknown | Unknown | 2 | Planned | July | July
TO-24-UGL-T134-01 | GENERATOR TRANSFORMER - UGGOOL 110-UGGOOL 33-T134 | Unknown | Unknown | 2 | Planned | July | July
TO-24-220 kV A2 @ TH-02 | BUSBAR SECTION - TURLOUGH HILL 220-TURLOUGH HILL 220-220A2 | 1 | 1 | 1 | Proposed | 11/07/2024 | 11/07/2024
TO-24-TH-T2003/4-04 | GENERATOR TRANSFORMER - TURLOUGH HILL 220-TURLOUGH HILL G1-T2003/4 | 1 | 1 | 1 | Proposed | 11/07/2024 | 11/07/2024
TO-24-CDY-GRV-1-01 | 110kV FEEDER - CORDERRY 110-GARVAGH 110-1 | Unknown | Unknown | 1 | Planned | July | July
TO-24-GRO-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - GARROW 110-GARROW 110-110SA1-2CB | Unknown | Unknown | 5 | Planned | July | July
TO-24-GRO-T122-01 | GENERATOR TRANSFORMER - GARROW 110-GARROW 20-T122 | Unknown | Unknown | 5 | Planned | July | July
TO-24-GRV-T121-01 | GENERATOR TRANSFORMER - GARVAGH 110-GARVAGH 20-T121 | Unknown | Unknown | 7 | Planned | July | July
TO-24-GRV-T141-02 | DISTRIBUTION TRANSFORMER - GARVAGH 110-GARVAGH 20-T141 | 1 | 1 | 1 | Reference (Proposed) | 15/07/2024 | 15/07/2024
TO-24-RRU-T122-04 | GENERATOR TRANSFORMER - RATRUSSAN 110-RATRUSSAN 20-T122 | Unknown | Unknown | 4 | Planned | July | July
TO-24-KHL-T131-01 | GENERATOR TRANSFORMER - KILL HILL 110-KILL HILL 33-T131 | Unknown | Unknown | 1 | Planned | July | July
TO-24-NW-T2004/5-01 | GENERATOR TRANSFORMER - NORTH WALL 220-NORTH WALL G4/5-T2004/5 | Unknown | Unknown | 2 | Planned | July | July
TO-24-BAR-T141-02 | DISTRIBUTION TRANSFORMER - BARRYMORE 110-BARRYMORE 38-T141 | Unknown | Unknown | 10 | Reference (Planned) | July | August
TO-24-BAR,T-BAR-1-02 | 110kV FEEDER - BARRYMORE tee-BARRYMORE 110-1 | Unknown | Unknown | 10 | Planned | July | August
TO-24-BAR,T-CAH-1-01 | 110kV FEEDER - BARRYMORE tee-CAHIR 110-1 | Unknown | Unknown | 10 | Planned | July | August
TO-24-BAR,T-KRA-1-01 | 110kV FEEDER - BARRYMORE tee-KNOCKRAHA 110-1 | Unknown | Unknown |  | Planned | July | August
TO-24-110 kV A2 @ CAH-02 | BUSBAR SECTION - CAHIR 110-CAHIR 110-110A2 | 12 | 10 | 10 | Proposed | 22/07/2024 | 02/08/2024
TO-24-110 kV B2 @ CAH-02 | BUSBAR SECTION - CAHIR 110-CAHIR 110-110B2 | 12 | 10 | 10 | Proposed | 22/07/2024 | 02/08/2024
TO-24-CSH-T2101-01 | TRANSFORMER - CASHLA 220-CASHLA 110-T2101 | Unknown | Unknown | 45 | Planned | July | September
TO-24-CBA-110SA1-02 | SECTIONALISING DISCONNECT - CLOGHBOOLA 110-CLOGHBOOLA 110-110SA1 | Unknown | Unknown | 5 | Planned | July | July
TO-24-CBA-110SA2-02 | SECTIONALISING DISCONNECT - CLOGHBOOLA 110-CLOGHBOOLA 110-110SA2 | Unknown | Unknown | 5 | Planned | July | July
TO-24-CBA-T122-01 | DISTRIBUTION TRANSFORMER - CLOGHBOOLA 110-CLOGHBOOLA 20-T122 | Unknown | Unknown | 5 | Reference (Planned) | July | July
TO-24-CBA-T131-01 | GENERATOR TRANSFORMER - CLOGHBOOLA 110-CLOGHBOOLA 33-T131 | Unknown | Unknown |  | Planned | July | July
TO-24-CBA-TRI-1-01 | 110kV FEEDER - CLOGHBOOLA 110-TRIEN 110-1 | Unknown | Unknown | 5 | Planned | July | July
TO-24-CUS-T103/5-01 | GENERATOR TRANSFORMER - CUSHALING 110-CUSHALING G3/5-T103/5 | Unknown | Unknown | 10 | Planned | July | August
TO-24-DEY-T132-01 | GENERATOR TRANSFORMER - DERRYCARNEY 110-DERRYCARNEY 33-T132 | Unknown | Unknown | 2 | Planned | July | July
TO-24-110 kV A1 @ KRA-01 | BUSBAR SECTION - KNOCKRAHA 110-KNOCKRAHA 110-110A1 | Unknown | Unknown | 10 | Planned | July | August
TO-24-110 kV B1 @ KRA-01 | BUSBAR SECTION - KNOCKRAHA 110-KNOCKRAHA 110-110B1 | Unknown | Unknown | 10 | Planned | July | August
TO-24-WHI-CKB-T101-01 | TSO CUSTOMER TRANSFORMER - WHITEGATE 110-WHITEGATE 10-CKB-T101 | 5 | 5 | 5 | Proposed | 22/07/2024 | 26/07/2024
TO-24-WOO-T4204-01 | TRANSFORMER - WOODLAND 400-WOODLAND 220-T4204 | Unknown | Unknown | 20 | Planned | July | August
TO-24-CRO-T122-03 | DISTRIBUTION TRANSFORMER - COOLROE 110-COOLROE 20-T122 | 2 | 2 | 2 | Reference (Proposed) | 23/07/2024 | 24/07/2024
TO-24-OUG-T141-01 | DISTRIBUTION TRANSFORMER - OUGHTRAGH 110-OUGHTRAGH 38-T141 | Unknown | Unknown | 1 | Reference (Planned) | July | July
TO-24-OUG,T-KER-1-01 | 110kV FEEDER - OUGHTRAGH tee-KNOCKEARAGH 110-1 | Unknown | Unknown | 1 | Planned | July | July
TO-24-OUG,T-OUG-1-01 | 110kV FEEDER - OUGHTRAGH tee-OUGHTRAGH 110-1 | Unknown | Unknown | 1 | Planned | July | July
TO-24-OUG,T-TRL-1-01 | 110kV FEEDER - OUGHTRAGH tee-TRALEE 110-1 | Unknown | Unknown | 1 | Planned | July | July
TO-24-110 kV A1 @ FLA-08 | BUSBAR SECTION - FLAGFORD 110-FLAGFORD 110-110A1 | 5 | 5 | 5 | Proposed | 29/07/2024 | 02/08/2024
TO-24-110 kV B1 @ FLA-09 | BUSBAR SECTION - FLAGFORD 110-FLAGFORD 110-110B1 | 5 | 5 | 5 | Proposed | 29/07/2024 | 02/08/2024
TO-24-FLA-GIL-1-01 | 110kV FEEDER - FLAGFORD 110-GILRA 110-1 | 5 | 5 | 5 | Proposed | 29/07/2024 | 02/08/2024
TO-24-WHI-CKB-T102-01 | TSO CUSTOMER TRANSFORMER - WHITEGATE 110-WHITEGATE 10-CKB-T102 | 5 | 5 | 5 | Proposed | 29/07/2024 | 02/08/2024
TO-24-CUS-KIR-1-01 | 110kV FEEDER - CUSHALING 110-KILCUMBER 110-1 | Unknown | Unknown | 2 | Planned | July | July
TO-24-KIR-T131-01 | GENERATOR TRANSFORMER - KILCUMBER 110-KILCUMBER 33-T131 | Unknown | Unknown | 2 | Planned | July | July
TO-24-110 kV A2 @ CF-06 | BUSBAR SECTION - CATHALEENS FALL 110-CATHALEENS FALL 110-110A2 | 11 | 9 | 9 | Proposed | 06/08/2024 | 16/08/2024
TO-24-110 kV B2 @ CF-02 | BUSBAR SECTION - CATHALEENS FALL 110-CATHALEENS FALL 110-110B2 | 11 | 9 | 9 | Proposed | 06/08/2024 | 16/08/2024
TO-24-CUS-T101-01 | GENERATOR TRANSFORMER - CUSHALING 110-CUSHALING G1-T101 | Unknown | Unknown | 1 | Planned | August | August
TO-24-GOR-NAV-1-02 | 110kV FEEDER - GORMAN 110-NAVAN 110-1 | Unknown | Unknown | 40 | Planned | August | September
TO-24-LSN-110SA1-2-03 | SECTIONALISING DISCONNECT - LISHEEN 110-LISHEEN 110-110SA1-2 | Unknown | Unknown | 9 | Planned | August | August
TO-24-LSN-110SA2-4-03 | SECTIONALISING DISCONNECT - LISHEEN 110-LISHEEN 110-110SA2-4 | Unknown | Unknown | 9 | Planned | August | August
TO-24-LSN-T122-03 | GENERATOR TRANSFORMER - LISHEEN 110-LISHEEN 20-T122 | Unknown | Unknown | 9 | Planned | August | August
TO-24-LSN-T131-03 | GENERATOR TRANSFORMER - LISHEEN 110-LISHEEN 33-T131 | Unknown | Unknown | 9 | Planned | August | August
TO-24-LSN-T142-02 | DISTRIBUTION TRANSFORMER - LISHEEN 110-LISHEEN 38-T142 | Unknown | Unknown | 9 | Reference (Planned) | August | August
TO-24-LSN-THU-1-03 | 110kV FEEDER - LISHEEN 110-THURLES 110-1 | Unknown | Unknown | 9 | Planned | August | August
TO-24-REM-110SA1-01 | SECTIONALISING DISCONNECT - REAMORE 110-REAMORE 110-110SA1 | Unknown | Unknown | 8 | Planned | August | August
TO-24-REM-110SA2-01 | SECTIONALISING DISCONNECT - REAMORE 110-REAMORE 110-110SA2 | Unknown | Unknown | 8 | Planned | August | August
TO-24-REM-T141-01 | DISTRIBUTION TRANSFORMER - REAMORE 110-REAMORE 38-T141 | Unknown | Unknown | 8 | Reference (Planned) | August | August
TO-24-REM-T142-01 | DISTRIBUTION TRANSFORMER - REAMORE 110-REAMORE 38-T142 | Unknown | Unknown | 8 | Reference (Planned) | August | August
TO-24-REM-TRL-1-01 | 110kV FEEDER - REAMORE 110-TRALEE 110-1 | Unknown | Unknown | 8 | Planned | August | August
TO-24-110 kV B4 @ FIN GIS-01 | BUSBAR SECTION - FINGLAS GIS 110-FINGLAS GIS 110-110B4 | 3 | 3 |  | Proposed | 12/08/2024 | 14/08/2024
TO-24-FIN GIS-110SB2-4CB-01 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110SB2-4CB | 3 | 3 |  | Proposed | 12/08/2024 | 14/08/2024
TO-24-FIN GIS-110SB4-6CB-01 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110SB4-6CB | 3 | 3 |  | Proposed | 12/08/2024 | 14/08/2024
TO-24-ISH-T2001-01 | GENERATOR TRANSFORMER - IRISHTOWN 220-IRISHTOWN G1-T2001 | Unknown | Unknown | 1 | Planned | August | August
TO-24-BGH-110SA1-01 | SECTIONALISING DISCONNECT - BOGGERAGH 110-BOGGERAGH 110-110SA1 | Unknown | Unknown | 7 | Planned | August | August
TO-24-BGH-110SA2-01 | SECTIONALISING DISCONNECT - BOGGERAGH 110-BOGGERAGH 110-110SA2 | Unknown | Unknown | 7 | Planned | August | August
TO-24-BGH-CLA-1-01 | 110kV FEEDER - BOGGERAGH 110-CLASHAVOON 110-1 | Unknown | Unknown | 7 | Planned | August | August
TO-24-BGH-T121-01 | GENERATOR TRANSFORMER - BOGGERAGH 110-BOGGERAGH 20-T121 | Unknown | Unknown | 7 | Planned | August | August
TO-24-BGH-T132-01 | GENERATOR TRANSFORMER - BOGGERAGH 110-BOGGERAGH 33-T132 | Unknown | Unknown | 7 | Planned | August | August
TO-24-BGH-T142-01 | DISTRIBUTION TRANSFORMER - BOGGERAGH 110-BOGGERAGH 38-T142 | Unknown | Unknown | 7 | Reference (Planned) | August | August
TO-24-BOL-110SA1-3CB-03 | COUPLER/SECTIONALISING CB - BOOLTIAGH 110-BOOLTIAGH 110-110SA1-3CB | Unknown | Unknown | 10 | Planned | August | August
TO-24-BOL-T121-01 | GENERATOR TRANSFORMER - BOOLTIAGH 110-BOOLTIAGH 20-T121 | Unknown | Unknown | 10 | Planned | August | August
TO-24-MP GIS-ST101-01 | GENERATOR TRANSFORMER - MONEYPOINT GIS 110-MONEYPOINT GIS 10-ST101 | Unknown | Unknown | 10 | Planned | August | August
TO-24-MP GIS-T121-01 | GENERATOR TRANSFORMER - MONEYPOINT GIS 110-MONEYPOINT GIS 20-T121 | Unknown | Unknown | 10 | Planned | August | August
TO-24-MP GIS-T2102-01 | TRANSFORMER - MONEYPOINT GIS 220-MONEYPOINT GIS 110-T2102 | Unknown | Unknown |  | Planned | August | August
TO-24-TBK-T141-01 | DISTRIBUTION TRANSFORMER - TULLABRACK 110-TULLABRACK 38-T141 | Unknown | Unknown | 10 | Reference (Planned) | August | August
TO-24-TBK,T-BOL-1-01 | 110kV FEEDER - TULLABRACK tee-BOOLTIAGH 110-1 | Unknown | Unknown | 10 | Planned | August | August
TO-24-TBK,T-MP GIS-1-01 | 110kV FEEDER - TULLABRACK tee-MONEYPOINT GIS 110-1 | Unknown | Unknown | 10 | Planned | August | August
TO-24-TBK,T-TBK-1-01 | 110kV FEEDER - TULLABRACK tee-TULLABRACK 110-1 | Unknown | Unknown | 10 | Planned | August | August
TO-24-CF-COR-1-01 | 110kV FEEDER - CATHALEENS FALL 110-CORRACLASSY 110-1 | Unknown | Unknown | 10 | Planned | August | September
TO-24-COR-PST-02 | TRANSFORMER - CORRACLASSY 110-ENNISKILLEN 110-PST | Unknown | Unknown | 10 | Planned | August | September
TO-24-COR-GWE-1-03 | 110kV FEEDER - CORRACLASSY 110-GORTAWEE 110-1 | Unknown | Unknown | 10 | Planned | August | September
TO-24-GLR-MOY-1-01 | 110kV FEEDER - GLENREE 110-MOY 110-1 | Unknown | Unknown | 35 | Planned | August | October
TO-24-GLR-MOY-1-05 | 110kV FEEDER - GLENREE 110-MOY 110-1 | Unknown | Unknown | 35 | Planned | August | October
TO-24-MOY-TAW-1-04 | 110kV FEEDER - MOY 110-TAWNAGHMORE 110-1 | Unknown | Unknown | 10 | Planned | August | September
TO-24-BOL-T121-03 | GENERATOR TRANSFORMER - BOOLTIAGH 110-BOOLTIAGH 20-T121 | 2 | 2 | 2 | Proposed | 28/08/2024 | 29/08/2024
TO-24-BDA-T101-01 | TSO CUSTOMER TRANSFORMER - BARODA 110-BARODA 10-T101 | 9 | 7 | 7 | Proposed | 02/09/2024 | 10/09/2024
TO-24-BDA-T101-02 | TSO CUSTOMER TRANSFORMER - BARODA 110-BARODA 10-T101 | 9 | 7 | 7 | Proposed | 02/09/2024 | 10/09/2024
TO-24-CLH-TRL-1-01 | 110kV FEEDER - CLAHANE 110-TRALEE 110-1 | 10 | 8 | 8 | Proposed | 02/09/2024 | 11/09/2024
TO-24-220 kV A2 @ FIN-01 | BUSBAR SECTION - FINGLAS 220-FINGLAS 220-220A2 | 5 | 5 |  | Proposed | 02/09/2024 | 06/09/2024
TO-24-220 kV B2 @ FIN-01 | BUSBAR SECTION - FINGLAS 220-FINGLAS 220-220B2 | 5 | 5 |  | Proposed | 02/09/2024 | 06/09/2024
TO-24-FIN-220K2-01 | COUPLER/SECTIONALISING CB - FINGLAS 220-FINGLAS 220-220K2 | 5 | 5 |  | Proposed | 02/09/2024 | 06/09/2024
TO-24-FIN-220SB1-2CB-01 | COUPLER/SECTIONALISING CB - FINGLAS 220-FINGLAS 220-220SB1-2CB | 5 | 5 |  | Proposed | 02/09/2024 | 06/09/2024
TO-24-110 kV A4 @ FIN GIS-01 | BUSBAR SECTION - FINGLAS GIS 110-FINGLAS GIS 110-110A4 | 5 | 5 |  | Proposed | 02/09/2024 | 06/09/2024
TO-24-110 kV B4 @ FIN GIS-02 | BUSBAR SECTION - FINGLAS GIS 110-FINGLAS GIS 110-110B4 | 5 | 5 |  | Proposed | 02/09/2024 | 06/09/2024
TO-24-FIN GIS-110SA2-4CB-01 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110SA2-4CB | 5 | 5 |  | Proposed | 02/09/2024 | 06/09/2024
TO-24-FIN GIS-110SA4-6CB-01 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110SA4-6CB | 5 | 5 |  | Proposed | 02/09/2024 | 06/09/2024
TO-24-FIN GIS-110SB2-4CB-02 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110SB2-4CB | 5 | 5 |  | Proposed | 02/09/2024 | 06/09/2024
TO-24-FIN GIS-110SB4-6CB-02 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110SB4-6CB | 5 | 5 |  | Proposed | 02/09/2024 | 06/09/2024
TO-24-IKE-T141-03 | DISTRIBUTION TRANSFORMER - IKERRIN 110-IKERRIN 38-T141 | Unknown | Unknown | 7 | Reference (Planned) | September | September
TO-24-IKE,T-IKE-1-03 | 110kV FEEDER - IKERRIN tee-IKERRIN 110-1 | Unknown | Unknown | 7 | Planned | September | September
TO-24-IKE,T-SH-1-05 | 110kV FEEDER - IKERRIN tee-SHANNONBRIDGE 110-1 | Unknown | Unknown | 7 | Planned | September | September
TO-24-IKE,T-THU-1-05 | 110kV FEEDER - IKERRIN tee-THURLES 110-1 | Unknown | Unknown | 7 | Planned | September | September
TO-24-CF-T104-01 | GENERATOR TRANSFORMER - CATHALEENS FALL 110-CATHALEENS FALL G4-T104 | Unknown | Unknown | 7 | Planned | September | September
TO-24-SHL-D2/CB2-04 | COUPLER/SECTIONALISING CB - SHELLYBANKS 220-SHELLYBANKS 220-D2/CB2 | Unknown | Unknown | 5 | Planned | September | September
TO-24-SHL-T2015-01 | GENERATOR TRANSFORMER - SHELLYBANKS 220-SHELLYBANKS G5-T2015 | Unknown | Unknown | 5 | Planned | September | September
TO-24-AA GIS-T103-01 | GENERATOR TRANSFORMER - ARDNACRUSHA GIS 110-ARDNACRUSHA GIS G3-T103 | Unknown | Unknown | 4 | Planned | September | September
TO-24-220 kV A2 @ FIN-02 | BUSBAR SECTION - FINGLAS 220-FINGLAS 220-220A2 | 2 | 2 |  | Proposed | 10/09/2024 | 11/09/2024
TO-24-FIN-220K2-02 | COUPLER/SECTIONALISING CB - FINGLAS 220-FINGLAS 220-220K2 | 2 | 2 |  | Proposed | 10/09/2024 | 11/09/2024
TO-24-FIN-NW-1-03 | 220kV FEEDER - FINGLAS 220-NORTH WALL 220-1 | 2 | 2 |  | Proposed | 10/09/2024 | 11/09/2024
TO-24-GGO-T2001-01 | GENERATOR TRANSFORMER - GLANAGOW 220-GLANAGOW G1-T2001 | Unknown | Unknown | 2 | Planned | September | September
TO-24-INC-MAY-2-05 | 220kV FEEDER - INCHICORE 220-MAYNOOTH 220-2 | 64 | 45 | 45 | Proposed | 10/09/2024 | 12/11/2024
TO-24-LOU-AT3-01 | TRANSFORMER - LOUTH 220-LOUTH 275-AT3 | Unknown | Unknown | 3 | Planned | September | September
TO-24-MP GIS-T4003-02 | GENERATOR TRANSFORMER - MONEYPOINT GIS 400-MONEYPOINT GIS G3-T4003 | Unknown | Unknown | 2 | Planned | September | September
TO-24-220 kV A2 @ AD-02 | BUSBAR SECTION - AGHADA 220-AGHADA 220-220A2 | Unknown | Unknown | 5 | Planned | September | September
TO-24-220 kV B2 @ AD-02 | BUSBAR SECTION - AGHADA 220-AGHADA 220-220B2 | Unknown | Unknown | 5 | Planned | September | September
TO-24-AD-SA1-2CB-02 | COUPLER/SECTIONALISING CB - AGHADA 220-AGHADA 220-220SA1-2CB | Unknown | Unknown | 5 | Planned | September | September
TO-24-AD-SB1-2CB-02 | COUPLER/SECTIONALISING CB - AGHADA 220-AGHADA 220-220SB1-2CB | Unknown | Unknown | 5 | Planned | September | September
TO-24-AD-KRA-2-02 | 220kV FEEDER - AGHADA 220-KNOCKRAHA 220-2 | Unknown | Unknown | 5 | Planned | September | September
TO-24-AD-RAF-1-01 | 220kV FEEDER - AGHADA 220-RAFFEEN 220-1 | Unknown | Unknown | 5 | Planned | September | September
TO-24-LIS-LSA-1-02 | 110kV FEEDER - LISDRUM 110-LISLEA 110-1 | Unknown | Unknown | 40 | Planned | September | November
TO-24-AD-T2011/12-02 | GENERATOR TRANSFORMER - AGHADA 220-AGHADA G11/12-T2011/12 | Unknown | Unknown | 5 | Planned | September | September
TO-24-CRA-WEX-1-01 | 110kV FEEDER - CRANE 110-WEXFORD 110-1 | Unknown | Unknown |  | Planned | September | September
TO-24-220 kV A1 @ KRA-01 | BUSBAR SECTION - KNOCKRAHA 220-KNOCKRAHA 220-220A1 | Unknown | Unknown | 10 | Planned | September | September
TO-24-220 kV B1 @ KRA-01 | BUSBAR SECTION - KNOCKRAHA 220-KNOCKRAHA 220-220B1 | Unknown | Unknown | 10 | Planned | September | September
TO-24-AD-T2014-02 | GENERATOR TRANSFORMER - AGHADA 220-AGHADA G14-T2014 | Unknown | Unknown | 5 | Planned | September | September
TO-24-CLG-T121-01 | TSO CUSTOMER TRANSFORMER - CLOGHRAN 110-CLOGHRAN 20-T121 | 5 | 5 | 5 | Proposed | 23/09/2024 | 27/09/2024
TO-24-PB-R2001-03 | CAPACITOR/SVC/REACTOR - POOLBEG 220-POOLBEG 220-R2001 | Unknown | Unknown |  | Planned | September | September
TO-24-COS-FLA-2-03 | 110kV FEEDER - CARRICK ON SHANNON 110-FLAGFORD 110-2 | Unknown | Unknown | 40 | Planned | September | November
TO-24-CLG-T123-01 | TSO CUSTOMER TRANSFORMER - CLOGHRAN 110-CLOGHRAN 20-T123 | 5 | 5 | 5 | Proposed | 30/09/2024 | 04/10/2024
TO-24-AUG-CFM-1-02 | 110kV FEEDER - AUGHINISH 110-CASTLEFARM 110-1 | Unknown | Unknown | 5 | Planned | October | October
TO-24-CSH-SAL-1-01 | 110kV FEEDER - CASHLA 110-SALTHILL 110-1 | Unknown | Unknown |  | Planned | October | October
TO-24-CFM-T101-02 | TSO CUSTOMER TRANSFORMER - CASTLEFARM 110-CASTLEFARM 10-T101 | 5 | 5 | 5 | Reference (Proposed) | 07/10/2024 | 11/10/2024
TO-24-CF-110K1-2-01 | COUPLER/SECTIONALISING CB - CATHALEENS FALL 110-CATHALEENS FALL 110-110K1-2 | Unknown | Unknown | 10 | Planned | October | October
TO-24-KBY-KRA-1-01 | 110kV FEEDER - KILBARRY 110-KNOCKRAHA 110-1 | Unknown | Unknown | 10 | Planned | October | October
TO-24-LOU-T2104-01 | TRANSFORMER - LOUTH 220-LOUTH 110-T2104 | Unknown | Unknown | 19 | Planned | October | November
TO-24-MOY-TAW-2-01 | 110kV FEEDER - MOY 110-TAWNAGHMORE 110-2 | Unknown | Unknown | 5 | Planned | October | October
TO-24-MOY-TAW-2-02 | 110kV FEEDER - MOY 110-TAWNAGHMORE 110-2 | Unknown | Unknown | 5 | Planned | October | October
TO-24-220 kV A1 @ RAF-01 | BUSBAR SECTION - RAFFEEN 220-RAFFEEN 220-220A1 | Unknown | Unknown | 10 | Planned | October | October
TO-24-220 kV B1 @ RAF-01 | BUSBAR SECTION - RAFFEEN 220-RAFFEEN 220-220B1 | Unknown | Unknown | 10 | Planned | October | October
TO-24-KPG-MP GIS-1-01 | 220kV FEEDER - KILPADDOGE 220-MONEYPOINT GIS 220-1 | Unknown | Unknown |  | Planned | October | October
TO-24-CDU-HN-1-01 | 220kV FEEDER - CORDUFF 220-HUNTSTOWN 220-1 | Unknown | Unknown | 5 | Planned | October | October
TO-24-GAR-PLA-1-04 | 110kV FEEDER - GARBALLAGH 110-PLATIN 110-1 | Unknown | Unknown | 5 | Planned | October | October
TO-24-HN-T2002-01 | GENERATOR TRANSFORMER - HUNTSTOWN 220-HUNTSTOWN G2-T2002 | Unknown | Unknown | 5 | Planned | October | October
TO-24-MOY-TAW-1-01 | 110kV FEEDER - MOY 110-TAWNAGHMORE 110-1 | Unknown | Unknown | 5 | Planned | October | October
TO-24-SHL-T2016-01 | GENERATOR TRANSFORMER - SHELLYBANKS 220-SHELLYBANKS G6-T2016 | Unknown | Unknown | 5 | Planned | October | October
TO-24-KBY-KRA-2-01 | 110kV FEEDER - KILBARRY 110-KNOCKRAHA 110-2 | Unknown | Unknown | 10 | Planned | October | November
TO-24-OBE-PLA-1-04 | 110kV FEEDER - OLDBRIDGE 110-PLATIN 110-1 | 5 | 5 | 5 | Proposed | 21/10/2024 | 25/10/2024
TO-24-CDU-FIN-2-01 | 220kV FEEDER - CORDUFF 220-FINGLAS 220-2 | Unknown | Unknown |  | Planned | October | November
TO-24-KLN-KRA-1-01 | 220kV FEEDER - KILLONAN 220-KNOCKRAHA 220-1 | Unknown | Unknown | 4 | Planned | October | November
TO-24-BK-110SA1-02 | SECTIONALISING DISCONNECT - BELLACORICK 110-BELLACORICK 110-110SA1 | Unknown | Unknown | 4 | Planned | November | November
TO-24-BK-110SA2-04 | SECTIONALISING DISCONNECT - BELLACORICK 110-BELLACORICK 110-110SA2 | Unknown | Unknown | 4 | Planned | November | November
TO-24-BK-MOY-1-04 | 110kV FEEDER - BELLACORICK 110-MOY 110-1 | Unknown | Unknown | 5 | Planned | November | November
TO-24-BK-MOY-1-01 | 110kV FEEDER - BELLACORICK 110-MOY 110-1 | Unknown | Unknown | 5 | Planned | November | November
TO-24-CSH-ENN-1-01 | 110kV FEEDER - CASHLA 110-ENNIS 110-1 | Unknown | Unknown | 6 | Planned | November | November
TO-24-GOR-MAY-1-01 | 220kV FEEDER - GORMAN 220-MAYNOOTH 220-1 | Unknown | Unknown |  | Planned | November | November
TO-24-LIS-LOU-1-02 | 110kV FEEDER - LISDRUM 110-LOUTH 110-1 | Unknown | Unknown | 10 | Planned | November | November
TO-24-110 kV A1 @ RAF-01 | BUSBAR SECTION - RAFFEEN 110-RAFFEEN 110-110A1 | Unknown | Unknown | 10 | Planned | November | November
TO-24-110 kV B1 @ RAF-01 | BUSBAR SECTION - RAFFEEN 110-RAFFEEN 110-110B1 | Unknown | Unknown | 10 | Planned | November | November
TO-24-RAF-TBG-1-01 | 110kV FEEDER - RAFFEEN 110-TRABEG 110-1 | Unknown | Unknown | 10 | Planned | November | November
TO-24-ARK-CKM GIS-1-01 | 220kV FEEDER - ARKLOW 220-CARRICKMINES GIS 220-1 | Unknown | Unknown |  | Planned | November | December
TO-24-ROP-T131-01 | GENERATOR TRANSFORMER - ROSSPILE 110-ROSSPILE 33-T131 | Unknown | Unknown | 2 | Planned | November | November
TO-24-PB-R2001-04 | CAPACITOR/SVC/REACTOR - POOLBEG 220-POOLBEG 220-R2001 | Unknown | Unknown |  | Planned | December | December

## GEN_AreaSouthWest
Outage ID | Feeder ID | Calendar Day Duration | Working Day Duration | Work Days | Outage Status | Start | Finish
TO-24-AUG-CFM-1-01 | 110kV FEEDER - AUGHINISH 110-CASTLEFARM 110-1 | 5 | 5 | 5 | Scheduled | 08/01/2024 | 12/01/2024
TO-24-CFM-T101-01 | TSO CUSTOMER TRANSFORMER - CASTLEFARM 110-CASTLEFARM 10-T101 | 5 | 5 | 5 | Reference | 08/01/2024 | 12/01/2024
TO-24-LIM-MTN-1-02 | 110kV FEEDER - LIMERICK 110-MONETEEN 110-1 | 2 | 2 | 2 | Scheduled | 08/01/2024 | 09/01/2024
TO-24-CAH-TIP-1-02 | 110kV FEEDER - CAHIR 110-TIPPERARY 110-1 | 2 | 2 | 2 | Scheduled | 31/01/2024 | 01/02/2024
TO-24-KNR-TRI-1-02 | 110kV FEEDER - KNOCKANURE 110-TRIEN 110-1 | 9 | 7 | 7 | Scheduled | 12/02/2024 | 20/02/2024
TO-24-AA GIS-SNG-1-01 | 110kV FEEDER - ARDNACRUSHA GIS 110-SINGLAND 110-1 | 5 | 5 |  | Scheduled | 26/02/2024 | 01/03/2024
TO-24-OST-WOO-1-01 | 400kV FEEDER - OLDSTREET 400-WOODLAND 400-1 | 5 | 5 | 5 | Scheduled | 26/02/2024 | 01/03/2024
TO-24-KPG-TRL-1-01 | 110kV FEEDER - KILPADDOGE 110-TRALEE 110-1 | 10 | 8 | 8 | Scheduled | 28/02/2024 | 08/03/2024
TO-24-AGL-ENN-1-01 | 110kV FEEDER - AGANNYGAL 110-ENNIS 110-1 | 22 | 15 | 15 | Scheduled | 04/03/2024 | 25/03/2024
TO-24-BYH-T2101-01 | TRANSFORMER - BALLYNAHULLA 220-BALLYNAHULLA 110-T2101 | 5 | 5 | 5 | Scheduled | 11/03/2024 | 15/03/2024
TO-24-BOL-T141-01 | DISTRIBUTION TRANSFORMER - BOOLTIAGH 110-BOOLTIAGH 38-T141 | 85 | 56 | 56 | Reference | 15/03/2024 | 07/06/2024
TO-24-CBA-110SA1-01 | SECTIONALISING DISCONNECT - CLOGHBOOLA 110-CLOGHBOOLA 110-110SA1 | 2 | 2 | 2 | Scheduled | 20/03/2024 | 21/03/2024
TO-24-CBA-110SA2-01 | SECTIONALISING DISCONNECT - CLOGHBOOLA 110-CLOGHBOOLA 110-110SA2 | 2 | 2 | 2 | Scheduled | 20/03/2024 | 21/03/2024
TO-24-CBA-T122-02 | DISTRIBUTION TRANSFORMER - CLOGHBOOLA 110-CLOGHBOOLA 20-T122 | 2 | 2 | 2 | Reference | 20/03/2024 | 21/03/2024
TO-24-CBA-T131-02 | GENERATOR TRANSFORMER - CLOGHBOOLA 110-CLOGHBOOLA 33-T131 | 2 | 2 | 2 | Scheduled | 20/03/2024 | 21/03/2024
TO-24-CBA-TRI-1-02 | 110kV FEEDER - CLOGHBOOLA 110-TRIEN 110-1 | 2 | 2 |  | Scheduled | 20/03/2024 | 21/03/2024
TO-24-BYH-T2102-01 | TRANSFORMER - BALLYNAHULLA 220-BALLYNAHULLA 110-T2102 | 4 | 4 | 4 | Scheduled | 25/03/2024 | 28/03/2024
TO-24-AUG-KPG-1-01 | 110kV FEEDER - AUGHINISH 110-KILPADDOGE 110-1 | 4 | 4 |  | Scheduled | 02/04/2024 | 05/04/2024
TO-24-BYH-220SB1-2CB-01 | COUPLER/SECTIONALISING CB - BALLYNAHULLA 220-BALLYNAHULLA 220-220SB1-2CB | 1 | 1 | 1 | Scheduled | 04/04/2024 | 04/04/2024
TO-24-BVK-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - BALLYVOUSKILL 110-BALLYVOUSKILL 110-110SA1-2CB | 1 | 1 | 1 | Scheduled | 04/04/2024 | 04/04/2024
TO-24-BVK-110SB1-2CB-01 | COUPLER/SECTIONALISING CB - BALLYVOUSKILL 110-BALLYVOUSKILL 110-110SB1-2CB | 1 | 1 | 1 | Scheduled | 05/04/2024 | 05/04/2024
TO-24-220 kV A1 @ BYH-01 | BUSBAR SECTION - BALLYNAHULLA 220-BALLYNAHULLA 220-220A1 | 5 | 5 | 5 | Scheduled | 08/04/2024 | 12/04/2024
TO-24-220 kV B1 @ BYH-01 | BUSBAR SECTION - BALLYNAHULLA 220-BALLYNAHULLA 220-220B1 | 5 | 5 | 5 | Scheduled | 08/04/2024 | 12/04/2024
TO-24-BYH-220K1-01 | COUPLER/SECTIONALISING CB - BALLYNAHULLA 220-BALLYNAHULLA 220-220K1 | 5 | 5 | 5 | Scheduled | 08/04/2024 | 12/04/2024
TO-24-BYH-220SA1-2CB-01 | COUPLER/SECTIONALISING CB - BALLYNAHULLA 220-BALLYNAHULLA 220-220SA1-2CB | 5 | 5 | 5 | Scheduled | 08/04/2024 | 12/04/2024
TO-24-BYH-220SB1-2CB-02 | COUPLER/SECTIONALISING CB - BALLYNAHULLA 220-BALLYNAHULLA 220-220SB1-2CB | 5 | 5 | 5 | Scheduled | 08/04/2024 | 12/04/2024
TO-24-CTN-TIP-1-01 | 110kV FEEDER - CAUTEEN 110-TIPPERARY 110-1 | 5 | 5 | 5 | Scheduled | 15/04/2024 | 19/04/2024
TO-24-KPG-T2101-01 | TRANSFORMER - KILPADDOGE 220-KILPADDOGE 110-T2101 | 5 | 5 | 5 | Scheduled | 15/04/2024 | 19/04/2024
TO-24-MP GIS-220K1-01 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 220-MONEYPOINT GIS 220-220K1 | 1 | 1 | 1 | Scheduled | 16/04/2024 | 16/04/2024
TO-24-MP GIS-220K2-01 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 220-MONEYPOINT GIS 220-220K2 | 1 | 1 | 1 | Scheduled | 17/04/2024 | 17/04/2024
TO-24-AA GIS-T104-04 | GENERATOR TRANSFORMER - ARDNACRUSHA GIS 110-ARDNACRUSHA GIS G4-T104 | 1 | 1 | 1 | Scheduled | 18/04/2024 | 18/04/2024
TO-24-MP GIS-220SA1-2CB-01 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 220-MONEYPOINT GIS 220-220SA1-2CB | 1 | 1 | 1 | Scheduled | 18/04/2024 | 18/04/2024
TO-24-MP GIS-220SB1-2CB-01 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 220-MONEYPOINT GIS 220-220SB1-2CB | 1 | 1 | 1 | Scheduled | 19/04/2024 | 19/04/2024
TO-24-TB-T2102-03 | TRANSFORMER - TARBERT 220-TARBERT 110-T2102 | 3 | 1 | 1 | Scheduled | 19/04/2024 | 21/04/2024
TO-24-LIM-RAT-1-01 | 110kV FEEDER - LIMERICK 110-RATHKEALE 110-1 | 5 | 5 | 5 | Scheduled | 22/04/2024 | 26/04/2024
TO-24-GAE-T121-02 | GENERATOR TRANSFORMER - GLANLEE 110-GLANLEE 20-T121 | 2 | 2 | 2 | Scheduled | 23/04/2024 | 24/04/2024
TO-24-KPG-220SB1-3CB-01 | COUPLER/SECTIONALISING CB - KILPADDOGE 220-KILPADDOGE 220-220SB1-3CB | 2 | 2 | 2 | Scheduled | 23/04/2024 | 24/04/2024
TO-24-110 kV A3 @ AA GIS-01 | BUSBAR SECTION - ARDNACRUSHA GIS 110-ARDNACRUSHA GIS 110-110A3 | 1 | 1 | 1 | Scheduled | 25/04/2024 | 25/04/2024
TO-24-AA GIS-T104-02 | GENERATOR TRANSFORMER - ARDNACRUSHA GIS 110-ARDNACRUSHA GIS G4-T104 | 1 | 1 | 1 | Scheduled | 25/04/2024 | 25/04/2024
TO-24-110 kV A3 @ AA GIS-02 | BUSBAR SECTION - ARDNACRUSHA GIS 110-ARDNACRUSHA GIS 110-110A3 | 5 | 5 | 5 | Scheduled | 29/04/2024 | 03/05/2024
TO-24-110 kV B3 @ AA GIS-01 | BUSBAR SECTION - ARDNACRUSHA GIS 110-ARDNACRUSHA GIS 110-110B3 | 5 | 5 | 5 | Scheduled | 29/04/2024 | 03/05/2024
TO-24-AA GIS-CAP1-01 | CAPACITOR/SVC/REACTOR - ARDNACRUSHA GIS 110-ARDNACRUSHA GIS 110-CAP1 | 5 | 5 | 5 | Scheduled | 29/04/2024 | 03/05/2024
TO-24-CHA-GLE-1-01 | 110kV FEEDER - CHARLEVILLE 110-GLENLARA 110-1 | 2 | 2 | 2 | Proposed | 30/04/2024 | 01/05/2024
TO-24-AA GIS-T101-01 | GENERATOR TRANSFORMER - ARDNACRUSHA GIS 110-ARDNACRUSHA GIS G1-T101 | 136 | 95 | 95 | Scheduled | 01/05/2024 | 13/09/2024
TO-24-110 kV A2 @ AA GIS-01 | BUSBAR SECTION - ARDNACRUSHA GIS 110-ARDNACRUSHA GIS 110-110A2 | 10 | 8 | 8 | Scheduled | 07/05/2024 | 16/05/2024
TO-24-110 kV B2 @ AA GIS-01 | BUSBAR SECTION - ARDNACRUSHA GIS 110-ARDNACRUSHA GIS 110-110B2 | 10 | 8 | 8 | Scheduled | 07/05/2024 | 16/05/2024
TO-24-AA GIS-ENN-1-04 | 110kV FEEDER - ARDNACRUSHA GIS 110-ENNIS 110-1 | 10 | 8 | 8 | Scheduled | 07/05/2024 | 16/05/2024
TO-24-AA GIS-T104-01 | GENERATOR TRANSFORMER - ARDNACRUSHA GIS 110-ARDNACRUSHA GIS G4-T104 | 14 | 10 | 10 | Proposed | 09/05/2024 | 22/05/2024
TO-24-CLH-T122-01 | GENERATOR TRANSFORMER - CLAHANE 110-CLAHANE 20-T122 | 5 | 5 | 5 | Scheduled | 13/05/2024 | 17/05/2024
TO-24-MP GIS-T4001-01 | GENERATOR TRANSFORMER - MONEYPOINT GIS 400-MONEYPOINT GIS G1-T4001 | 9 | 7 | 7 | Proposed | 13/05/2024 | 21/05/2024
TO-24-DAL,T-DAL-1-01 | 110kV FEEDER - DALLOW tee-DALLOW 110-1 | 7 | 5 | 5 | Proposed | 14/05/2024 | 20/05/2024
TO-24-SLC-T122-03 | GENERATOR TRANSFORMER - SLIEVECALLAN 110-SLIEVECALLAN 20-T122 | 1 | 1 | 1 | Proposed | 16/05/2024 | 16/05/2024
TO-24-BVK-T2101-01 | TRANSFORMER - BALLYVOUSKILL 220-BALLYVOUSKILL 110-T2101 | 15 | 11 |  | Proposed | 17/05/2024 | 31/05/2024
TO-24-KLN-KPG-1-01 | 220kV FEEDER - KILLONAN 220-KILPADDOGE 220-1 | 12 | 10 | 10 | Proposed | 20/05/2024 | 31/05/2024
TO-24-220 kV A4 @ KPG-01 | BUSBAR SECTION - KILPADDOGE 220-KILPADDOGE 220-220A4 | 12 | 10 | 10 | Proposed | 20/05/2024 | 31/05/2024
TO-24-220 kV B4 @ KPG-01 | BUSBAR SECTION - KILPADDOGE 220-KILPADDOGE 220-220B4 | 12 | 10 | 10 | Proposed | 20/05/2024 | 31/05/2024
TO-24-MP GIS-T4201-01 | TRANSFORMER - MONEYPOINT GIS 400-MONEYPOINT GIS 220-T4201 | 5 | 5 | 5 | Scheduled | 20/05/2024 | 24/05/2024
TO-24-BYH-CDL-1-01 | 110kV FEEDER - BALLYNAHULLA 110-CORDAL 110-1 | 4 | 4 | 4 | Scheduled | 27/05/2024 | 30/05/2024
TO-24-CDL-110SA1-01 | SECTIONALISING DISCONNECT - CORDAL 110-CORDAL 110-110SA1 | 4 | 4 | 4 | Scheduled | 27/05/2024 | 30/05/2024
TO-24-CDL-110SA2-01 | SECTIONALISING DISCONNECT - CORDAL 110-CORDAL 110-110SA2 | 4 | 4 | 4 | Scheduled | 27/05/2024 | 30/05/2024
TO-24-CDL-T132-01 | GENERATOR TRANSFORMER - CORDAL 110-CORDAL 33-T132 | 4 | 4 |  | Scheduled | 27/05/2024 | 30/05/2024
TO-24-CDL-T141-01 | DISTRIBUTION TRANSFORMER - CORDAL 110-CORDAL 38-T141 | 4 | 4 | 4 | Reference | 27/05/2024 | 30/05/2024
TO-24-CDL-T141-02 | DISTRIBUTION TRANSFORMER - CORDAL 110-CORDAL 38-T141 | 1 | 1 | 1 | Reference (Proposed) | 27/05/2024 | 27/05/2024
TO-24-MP GIS-T4002-02 | GENERATOR TRANSFORMER - MONEYPOINT GIS 400-MONEYPOINT GIS G2-T4002 | 5 | 5 | 5 | Proposed | 27/05/2024 | 31/05/2024
TO-24-GLE-KCR-1-01 | 110kV FEEDER - GLENLARA 110-KNOCKACUMMER 110-1 | Unknown | Unknown | 4 | Planned | June | June
TO-24-KCR-T121-01 | GENERATOR TRANSFORMER - KNOCKACUMMER 110-KNOCKACUMMER 20-T121 | Unknown | Unknown | 4 | Planned | June | June
TO-24-BYH-KNR-1-01 | 220kV FEEDER - BALLYNAHULLA 220-KNOCKANURE 220-1 | Unknown | Unknown | 4 | Planned | June | June
TO-24-AA GIS-LIM-1-01 | 110kV FEEDER - ARDNACRUSHA GIS 110-LIMERICK 110-1 | 3 | 3 | 3 | Proposed | 05/06/2024 | 07/06/2024
TO-24-KLN-T2101-01 | TRANSFORMER - KILLONAN 220-KILLONAN 110-T2101 | 3 | 3 | 3 | Proposed | 05/06/2024 | 07/06/2024
TO-24-MP GIS-400K4-01 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 400-MONEYPOINT GIS 400-400K4 | 1 | 1 | 1 | Proposed | 06/06/2024 | 06/06/2024
TO-24-ATE-TOB-1-01 | 110kV FEEDER - ATHEA 110-TOBERTOREEN 110-1 | Unknown | Unknown | 5 | Planned | June | June
TO-24-AUG-CFM-2-01 | 110kV FEEDER - AUGHINISH 110-CASTLEFARM 110-2 | Unknown | Unknown | 5 | Planned | June | June
TO-24-AUG-SK-3-01 | 110kV FEEDER - AUGHINISH 110-SEALROCK 110-3 | Unknown | Unknown | 10 | Planned | June | June
TO-24-CFM-T102-01 | TSO CUSTOMER TRANSFORMER - CASTLEFARM 110-CASTLEFARM 10-T102 | 5 | 5 | 5 | Reference (Proposed) | 10/06/2024 | 14/06/2024
TO-24-CHA-MAL-1-01 | 110kV FEEDER - CHARLEVILLE 110-MALLOW 110-1 | Unknown | Unknown | 10 | Planned | June | June
TO-24-DRO-T121-01 | GENERATOR TRANSFORMER - DROMADA 110-DROMADA 20-T121 | Unknown | Unknown | 5 | Planned | June | June
TO-24-DRU-ENN-1-05 | 110kV FEEDER - DRUMLINE 110-ENNIS 110-1 | 64 | 45 | 45 | Proposed | 10/06/2024 | 12/08/2024
TO-24-SK-T103-01 | GENERATOR TRANSFORMER - SEALROCK 110-SEALROCK G3-T103 | Unknown | Unknown | 10 | Planned | June | June
TO-24-TOB-T132-01 | GENERATOR TRANSFORMER - TOBERTOREEN 110-TOBERTOREEN 33-T132 | Unknown | Unknown | 5 | Planned | June | June
TO-24-MP GIS-400SA1-2CB-01 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 400-MONEYPOINT GIS 400-400SA1-2CB | 1 | 1 | 1 | Proposed | 11/06/2024 | 11/06/2024
TO-24-AA GIS-T102-01 | GENERATOR TRANSFORMER - ARDNACRUSHA GIS 110-ARDNACRUSHA GIS G2-T102 | Unknown | Unknown | 3 | Planned | June | June
TO-24-CAH-KHL-1-01 | 110kV FEEDER - CAHIR 110-KILL HILL 110-1 | 2 | 2 | 2 | Proposed | 12/06/2024 | 13/06/2024
TO-24-KLN-T2103-01 | TRANSFORMER - KILLONAN 220-KILLONAN 110-T2103 | 2 | 2 | 2 | Proposed | 12/06/2024 | 13/06/2024
TO-24-MP GIS-400SA2-4CB-01 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 400-MONEYPOINT GIS 400-400SA2-4CB | 1 | 1 | 1 | Proposed | 12/06/2024 | 12/06/2024
TO-24-MP GIS-400SB1-2CB-01 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 400-MONEYPOINT GIS 400-400SB1-2CB | 1 | 1 | 1 | Proposed | 13/06/2024 | 13/06/2024
TO-24-ATE-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - ATHEA 110-ATHEA 110-110SA1-2CB | Unknown | Unknown | 5 | Planned | June | June
TO-24-ATE-DRO-1-01 | 110kV FEEDER - ATHEA 110-DROMADA 110-1 | Unknown | Unknown | 5 | Planned | June | June
TO-24-ATE-KNR-1-01 | 110kV FEEDER - ATHEA 110-KNOCKANURE 110-1 | Unknown | Unknown | 5 | Planned | June | June
TO-24-ATE-T121-01 | GENERATOR TRANSFORMER - ATHEA 110-ATHEA 20-T121 | Unknown | Unknown | 5 | Planned | June | June
TO-24-ATE-TOB-1-02 | 110kV FEEDER - ATHEA 110-TOBERTOREEN 110-1 | Unknown | Unknown | 5 | Planned | June | June
TO-24-KPG-MP GIS-2-01 | 220kV FEEDER - KILPADDOGE 220-MONEYPOINT GIS 220-2 | 5 | 5 | 5 | Proposed | 17/06/2024 | 21/06/2024
TO-24-MP GIS-400SA1-3CB-01 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 400-MONEYPOINT GIS 400-400SA1-3CB | 5 | 5 | 5 | Proposed | 17/06/2024 | 21/06/2024
TO-24-TOB-T132-02 | GENERATOR TRANSFORMER - TOBERTOREEN 110-TOBERTOREEN 33-T132 | Unknown | Unknown | 5 | Planned | June | June
TO-24-AUG-MTN-1-01 | 110kV FEEDER - AUGHINISH 110-MONETEEN 110-1 | 9 | 7 | 7 | Proposed | 18/06/2024 | 26/06/2024
TO-24-CDL-T141-03 | DISTRIBUTION TRANSFORMER - CORDAL 110-CORDAL 38-T141 | 1 | 1 | 1 | Reference (Proposed) | 19/06/2024 | 19/06/2024
TO-24-CTN-KLN-1-01 | 110kV FEEDER - CAUTEEN 110-KILLONAN 110-1 | 4 | 4 | 4 | Proposed | 25/06/2024 | 28/06/2024
TO-24-CNO-KPG-1-01 | 110kV FEEDER - COOLNANOONAGH 110-KILPADDOGE 110-1 | Unknown | Unknown | 2 | Planned | June | June
TO-24-CNO-T131-01 | GENERATOR TRANSFORMER - COOLNANOONAGH 110-COOLNANOONAGH 33-T131 | Unknown | Unknown | 2 | Planned | June | June
TO-24-BVK-COT-1-01 | 110kV FEEDER - BALLYVOUSKILL 110-COOMATAGGART 110-1 | Unknown | Unknown | 5 | Planned | July | July
TO-24-COT-110SA1-01 | SECTIONALISING DISCONNECT - COOMATAGGART 110-COOMATAGGART 110-110SA1 | Unknown | Unknown | 5 | Planned | July | July
TO-24-COT-110SA2-01 | SECTIONALISING DISCONNECT - COOMATAGGART 110-COOMATAGGART 110-110SA2 | Unknown | Unknown | 5 | Planned | July | July
TO-24-COT-FILTER1-01 | CAPACITOR/SVC/REACTOR - COOMATAGGART 110-COOMATAGGART 110-FILTER1 | Unknown | Unknown | 5 | Planned | July | July
TO-24-COT-T132-01 | GENERATOR TRANSFORMER - COOMATAGGART 110-COOMATAGGART 33-T132 | Unknown | Unknown | 5 | Planned | July | July
TO-24-COT-T141-01 | DISTRIBUTION TRANSFORMER - COOMATAGGART 110-COOMATAGGART 38-T141 | Unknown | Unknown | 5 | Reference (Planned) | July | July
TO-24-ENN-SLC-1-02 | 110kV FEEDER - ENNIS 110-SLIEVECALLAN 110-1 | Unknown | Unknown | 3 | Planned | July | July
TO-24-SLC-110SA1-02 | SECTIONALISING DISCONNECT - SLIEVECALLAN 110-SLIEVECALLAN 110-110SA1 | Unknown | Unknown | 3 | Planned | July | July
TO-24-SLC-110SA2-02 | SECTIONALISING DISCONNECT - SLIEVECALLAN 110-SLIEVECALLAN 110-110SA2 | Unknown | Unknown | 3 | Planned | July | July
TO-24-SLC-T121-02 | GENERATOR TRANSFORMER - SLIEVECALLAN 110-SLIEVECALLAN 20-T121 | Unknown | Unknown | 3 | Planned | July | July
TO-24-SLC-T122-02 | GENERATOR TRANSFORMER - SLIEVECALLAN 110-SLIEVECALLAN 20-T122 | Unknown | Unknown | 3 | Planned | July | July
TO-24-AUG-SK-4-01 | 110kV FEEDER - AUGHINISH 110-SEALROCK 110-4 | Unknown | Unknown | 44 | Planned | July | September
TO-24-SK-T104-01 | GENERATOR TRANSFORMER - SEALROCK 110-SEALROCK G4-T104 | Unknown | Unknown | 44 | Planned | July | September
TO-24-GRO-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - GARROW 110-GARROW 110-110SA1-2CB | Unknown | Unknown | 5 | Planned | July | July
TO-24-GRO-T122-01 | GENERATOR TRANSFORMER - GARROW 110-GARROW 20-T122 | Unknown | Unknown | 5 | Planned | July | July
TO-24-KHL-T131-01 | GENERATOR TRANSFORMER - KILL HILL 110-KILL HILL 33-T131 | Unknown | Unknown | 1 | Planned | July | July
TO-24-CBA-110SA1-02 | SECTIONALISING DISCONNECT - CLOGHBOOLA 110-CLOGHBOOLA 110-110SA1 | Unknown | Unknown | 5 | Planned | July | July
TO-24-CBA-110SA2-02 | SECTIONALISING DISCONNECT - CLOGHBOOLA 110-CLOGHBOOLA 110-110SA2 | Unknown | Unknown | 5 | Planned | July | July
TO-24-CBA-T122-01 | DISTRIBUTION TRANSFORMER - CLOGHBOOLA 110-CLOGHBOOLA 20-T122 | Unknown | Unknown | 5 | Reference (Planned) | July | July
TO-24-CBA-T131-01 | GENERATOR TRANSFORMER - CLOGHBOOLA 110-CLOGHBOOLA 33-T131 | Unknown | Unknown |  | Planned | July | July
TO-24-CBA-TRI-1-01 | 110kV FEEDER - CLOGHBOOLA 110-TRIEN 110-1 | Unknown | Unknown | 5 | Planned | July | July
TO-24-OUG-T141-01 | DISTRIBUTION TRANSFORMER - OUGHTRAGH 110-OUGHTRAGH 38-T141 | Unknown | Unknown | 1 | Reference (Planned) | July | July
TO-24-OUG,T-KER-1-01 | 110kV FEEDER - OUGHTRAGH tee-KNOCKEARAGH 110-1 | Unknown | Unknown | 1 | Planned | July | July
TO-24-OUG,T-OUG-1-01 | 110kV FEEDER - OUGHTRAGH tee-OUGHTRAGH 110-1 | Unknown | Unknown | 1 | Planned | July | July
TO-24-OUG,T-TRL-1-01 | 110kV FEEDER - OUGHTRAGH tee-TRALEE 110-1 | Unknown | Unknown | 1 | Planned | July | July
TO-24-LSN-110SA1-2-03 | SECTIONALISING DISCONNECT - LISHEEN 110-LISHEEN 110-110SA1-2 | Unknown | Unknown | 9 | Planned | August | August
TO-24-LSN-110SA2-4-03 | SECTIONALISING DISCONNECT - LISHEEN 110-LISHEEN 110-110SA2-4 | Unknown | Unknown | 9 | Planned | August | August
TO-24-LSN-T122-03 | GENERATOR TRANSFORMER - LISHEEN 110-LISHEEN 20-T122 | Unknown | Unknown | 9 | Planned | August | August
TO-24-LSN-T131-03 | GENERATOR TRANSFORMER - LISHEEN 110-LISHEEN 33-T131 | Unknown | Unknown | 9 | Planned | August | August
TO-24-LSN-T142-02 | DISTRIBUTION TRANSFORMER - LISHEEN 110-LISHEEN 38-T142 | Unknown | Unknown | 9 | Reference (Planned) | August | August
TO-24-LSN-THU-1-03 | 110kV FEEDER - LISHEEN 110-THURLES 110-1 | Unknown | Unknown | 9 | Planned | August | August
TO-24-REM-110SA1-01 | SECTIONALISING DISCONNECT - REAMORE 110-REAMORE 110-110SA1 | Unknown | Unknown | 8 | Planned | August | August
TO-24-REM-110SA2-01 | SECTIONALISING DISCONNECT - REAMORE 110-REAMORE 110-110SA2 | Unknown | Unknown | 8 | Planned | August | August
TO-24-REM-T141-01 | DISTRIBUTION TRANSFORMER - REAMORE 110-REAMORE 38-T141 | Unknown | Unknown | 8 | Reference (Planned) | August | August
TO-24-REM-T142-01 | DISTRIBUTION TRANSFORMER - REAMORE 110-REAMORE 38-T142 | Unknown | Unknown | 8 | Reference (Planned) | August | August
TO-24-REM-TRL-1-01 | 110kV FEEDER - REAMORE 110-TRALEE 110-1 | Unknown | Unknown | 8 | Planned | August | August
TO-24-BOL-110SA1-3CB-03 | COUPLER/SECTIONALISING CB - BOOLTIAGH 110-BOOLTIAGH 110-110SA1-3CB | Unknown | Unknown | 10 | Planned | August | August
TO-24-BOL-T121-01 | GENERATOR TRANSFORMER - BOOLTIAGH 110-BOOLTIAGH 20-T121 | Unknown | Unknown | 10 | Planned | August | August
TO-24-MP GIS-ST101-01 | GENERATOR TRANSFORMER - MONEYPOINT GIS 110-MONEYPOINT GIS 10-ST101 | Unknown | Unknown | 10 | Planned | August | August
TO-24-MP GIS-T121-01 | GENERATOR TRANSFORMER - MONEYPOINT GIS 110-MONEYPOINT GIS 20-T121 | Unknown | Unknown | 10 | Planned | August | August
TO-24-MP GIS-T2102-01 | TRANSFORMER - MONEYPOINT GIS 220-MONEYPOINT GIS 110-T2102 | Unknown | Unknown |  | Planned | August | August
TO-24-TBK-T141-01 | DISTRIBUTION TRANSFORMER - TULLABRACK 110-TULLABRACK 38-T141 | Unknown | Unknown | 10 | Reference (Planned) | August | August
TO-24-TBK,T-BOL-1-01 | 110kV FEEDER - TULLABRACK tee-BOOLTIAGH 110-1 | Unknown | Unknown | 10 | Planned | August | August
TO-24-TBK,T-MP GIS-1-01 | 110kV FEEDER - TULLABRACK tee-MONEYPOINT GIS 110-1 | Unknown | Unknown | 10 | Planned | August | August
TO-24-TBK,T-TBK-1-01 | 110kV FEEDER - TULLABRACK tee-TULLABRACK 110-1 | Unknown | Unknown | 10 | Planned | August | August
TO-24-BOL-T121-03 | GENERATOR TRANSFORMER - BOOLTIAGH 110-BOOLTIAGH 20-T121 | 2 | 2 | 2 | Proposed | 28/08/2024 | 29/08/2024
TO-24-CLH-TRL-1-01 | 110kV FEEDER - CLAHANE 110-TRALEE 110-1 | 10 | 8 | 8 | Proposed | 02/09/2024 | 11/09/2024
TO-24-IKE-T141-03 | DISTRIBUTION TRANSFORMER - IKERRIN 110-IKERRIN 38-T141 | Unknown | Unknown | 7 | Reference (Planned) | September | September
TO-24-IKE,T-IKE-1-03 | 110kV FEEDER - IKERRIN tee-IKERRIN 110-1 | Unknown | Unknown | 7 | Planned | September | September
TO-24-IKE,T-SH-1-05 | 110kV FEEDER - IKERRIN tee-SHANNONBRIDGE 110-1 | Unknown | Unknown | 7 | Planned | September | September
TO-24-IKE,T-THU-1-05 | 110kV FEEDER - IKERRIN tee-THURLES 110-1 | Unknown | Unknown | 7 | Planned | September | September
TO-24-AA GIS-T103-01 | GENERATOR TRANSFORMER - ARDNACRUSHA GIS 110-ARDNACRUSHA GIS G3-T103 | Unknown | Unknown | 4 | Planned | September | September
TO-24-MP GIS-T4003-02 | GENERATOR TRANSFORMER - MONEYPOINT GIS 400-MONEYPOINT GIS G3-T4003 | Unknown | Unknown | 2 | Planned | September | September
TO-24-AUG-CFM-1-02 | 110kV FEEDER - AUGHINISH 110-CASTLEFARM 110-1 | Unknown | Unknown | 5 | Planned | October | October
TO-24-CFM-T101-02 | TSO CUSTOMER TRANSFORMER - CASTLEFARM 110-CASTLEFARM 10-T101 | 5 | 5 | 5 | Reference (Proposed) | 07/10/2024 | 11/10/2024
TO-24-KPG-MP GIS-1-01 | 220kV FEEDER - KILPADDOGE 220-MONEYPOINT GIS 220-1 | Unknown | Unknown |  | Planned | October | October
TO-24-KLN-KRA-1-01 | 220kV FEEDER - KILLONAN 220-KNOCKRAHA 220-1 | Unknown | Unknown | 4 | Planned | October | November
TO-24-CSH-ENN-1-01 | 110kV FEEDER - CASHLA 110-ENNIS 110-1 | Unknown | Unknown | 6 | Planned | November | November

## GEN_SouthEast
Outage ID | Feeder ID | Calendar Day Duration | Working Day Duration | Work Days | Outage Status | Start | Finish
TO-24-CRA-LWD-1-07 | 110kV FEEDER - CRANE 110-LODGEWOOD 110-1 | 2 | 2 | 2 | Scheduled | 15/01/2024 | 16/01/2024
TO-24-GI-T141-03 | DISTRIBUTION TRANSFORMER - GREAT ISLAND 110-GREAT ISLAND 38-T141 | 5 | 5 | 5 | Reference | 15/01/2024 | 19/01/2024
TO-24-KLS-KKY-1-02 | 110kV FEEDER - KELLIS 110-KILKENNY 110-1 | 10 | 7 | 7 | Scheduled | 29/01/2024 | 07/02/2024
TO-24-CUL-WAT-1-02 | 110kV FEEDER - CULLENAGH 110-WATERFORD 110-1 | 3 | 3 | 3 | Scheduled | 30/01/2024 | 01/02/2024
TO-24-CAH-TIP-1-02 | 110kV FEEDER - CAHIR 110-TIPPERARY 110-1 | 2 | 2 | 2 | Scheduled | 31/01/2024 | 01/02/2024
TO-24-CUL-GI GIS-1-04 | 220kV FEEDER - CULLENAGH 220-GREAT ISLAND GIS 220-1 | 2 | 2 | 2 | Scheduled | 19/02/2024 | 20/02/2024
TO-24-110 kV A1 @ ARK-01 | BUSBAR SECTION - ARKLOW 110-ARKLOW 110-110A1 | 12 | 10 | 10 | Scheduled | 26/02/2024 | 08/03/2024
TO-24-110 kV B1 @ ARK-01 | BUSBAR SECTION - ARKLOW 110-ARKLOW 110-110B1 | 12 | 10 | 10 | Scheduled | 26/02/2024 | 08/03/2024
TO-24-ARK-BOG-1-01 | 110kV FEEDER - ARKLOW 110-BANOGE 110-1 | 12 | 10 | 10 | Scheduled | 26/02/2024 | 08/03/2024
TO-24-BDN-DOO-1-01 | 110kV FEEDER - BALLYDINE 110-DOON 110-1 | 9 | 7 | 7 | Scheduled | 05/03/2024 | 13/03/2024
TO-24-ARK-BEG-1-01 | 110kV FEEDER - ARKLOW 110-BALLYBEG 110-1 | 12 | 9 |  | Scheduled | 11/03/2024 | 22/03/2024
TO-24-110 kV A1/A2 @ CAH-01 | BUSBAR SECTION - CAHIR 110-CAHIR 110-110A1-A2 | 10 | 8 | 8 | Scheduled | 19/03/2024 | 28/03/2024
TO-24-110 kV B1/B2 @ CAH-01 | BUSBAR SECTION - CAHIR 110-CAHIR 110-110B1-B2 | 10 | 8 | 8 | Scheduled | 19/03/2024 | 28/03/2024
TO-24-CAH-110K1-2-01 | COUPLER/SECTIONALISING CB - CAHIR 110-CAHIR 110-110K1-2 | 10 | 8 | 8 | Scheduled | 19/03/2024 | 28/03/2024
TO-24-CAH-T141-01 | DISTRIBUTION TRANSFORMER - CAHIR 110-CAHIR 38-T141 | 7 | 5 | 5 | Reference | 19/03/2024 | 25/03/2024
TO-24-GI-WAT-2-01 | 110kV FEEDER - GREAT ISLAND 110-WATERFORD 110-2 | 4 | 4 | 4 | Scheduled | 19/03/2024 | 22/03/2024
TO-24-CAH-T142-01 | DISTRIBUTION TRANSFORMER - CAHIR 110-CAHIR 38-T142 | 4 | 4 | 4 | Reference | 25/03/2024 | 28/03/2024
TO-24-220 kV A2 @ CUL-02 | BUSBAR SECTION - CULLENAGH 220-CULLENAGH 220-220A2 | 43 | 30 | 30 | Scheduled | 04/04/2024 | 16/05/2024
TO-24-220 kV B2 @ CUL-02 | BUSBAR SECTION - CULLENAGH 220-CULLENAGH 220-220B2 | 43 | 30 | 30 | Scheduled | 04/04/2024 | 16/05/2024
TO-24-CUL-KRA-1-01 | 220kV FEEDER - CULLENAGH 220-KNOCKRAHA 220-1 | 43 | 30 |  | Scheduled | 04/04/2024 | 16/05/2024
TO-24-GI-KKY-1-01 | 110kV FEEDER - GREAT ISLAND 110-KILKENNY 110-1 | 9 | 7 | 7 | Scheduled | 04/04/2024 | 12/04/2024
TO-24-GI-WAT-1-01 | 110kV FEEDER - GREAT ISLAND 110-WATERFORD 110-1 | 9 | 7 | 7 | Scheduled | 04/04/2024 | 12/04/2024
TO-24-BGT-110K1-01 | COUPLER/SECTIONALISING CB - BALLYRAGGET 110-BALLYRAGGET 110-110K1 | 3 | 3 | 3 | Scheduled | 15/04/2024 | 17/04/2024
TO-24-BGT-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - BALLYRAGGET 110-BALLYRAGGET 110-110SA1-2CB | 3 | 3 | 3 | Scheduled | 15/04/2024 | 17/04/2024
TO-24-BGT-110SB1-2CB-01 | COUPLER/SECTIONALISING CB - BALLYRAGGET 110-BALLYRAGGET 110-110SB1-2CB | 3 | 3 | 3 | Scheduled | 15/04/2024 | 17/04/2024
TO-24-BGT-KKY-1-01 | 110kV FEEDER - BALLYRAGGET 110-KILKENNY 110-1 | 3 | 3 | 3 | Scheduled | 15/04/2024 | 17/04/2024
TO-24-BGT-141-01 | DISTRIBUTION TRANSFORMER - BALLYRAGGET 110-BALLYRAGGET 38-T141 | 3 | 3 | 3 | Reference | 15/04/2024 | 17/04/2024
TO-24-CRA-110SA1-02 | SECTIONALISING DISCONNECT - CRANE 110-CRANE 110-110SA1 | 5 | 5 | 5 | Scheduled | 15/04/2024 | 19/04/2024
TO-24-CRA-110SA2-04 | SECTIONALISING DISCONNECT - CRANE 110-CRANE 110-110SA2 | 5 | 5 | 5 | Scheduled | 15/04/2024 | 19/04/2024
TO-24-CRA-T141-01 | DISTRIBUTION TRANSFORMER - CRANE 110-CRANE 38-T141 | 5 | 5 | 5 | Reference | 15/04/2024 | 19/04/2024
TO-24-CRA-TTU-1-01 | 110kV FEEDER - CRANE 110-TULLABEG 110-1 | 5 | 5 | 5 | Scheduled | 15/04/2024 | 19/04/2024
TO-24-KTN-WAT-1-01 | 110kV FEEDER - KILLOTERAN 110-WATERFORD 110-1 | 5 | 5 | 5 | Scheduled | 22/04/2024 | 26/04/2024
TO-24-ROP-WEX-1-02 | 110kV FEEDER - ROSSPILE 110-WEXFORD 110-1 | 5 | 5 |  | Scheduled | 22/04/2024 | 26/04/2024
TO-24-WEX-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - WEXFORD 110-WEXFORD 110-110SA1-2CB | 5 | 5 |  | Scheduled | 22/04/2024 | 26/04/2024
TO-24-WEX-T121-01 | DISTRIBUTION TRANSFORMER - WEXFORD 110-WEXFORD 20-T121 | 5 | 5 | 5 | Reference | 22/04/2024 | 26/04/2024
TO-24-WEX-T141-01 | DISTRIBUTION TRANSFORMER - WEXFORD 110-WEXFORD 38-T141 | 5 | 5 | 5 | Reference | 22/04/2024 | 26/04/2024
TO-24-ARK-T2102-01 | TRANSFORMER - ARKLOW 220-ARKLOW 110-T2102 | 5 | 5 | 5 | Scheduled | 29/04/2024 | 03/05/2024
TO-24-ATY-CLW-1-07 | 110kV FEEDER - ATHY 110-CARLOW 110-1 | 15 | 10 | 10 | Proposed | 29/04/2024 | 13/05/2024
TO-24-WOH-T122-01 | GENERATOR TRANSFORMER - WOODHOUSE 110-WOODHOUSE 20-T122 | 5 | 4 | 4 | Scheduled | 06/05/2024 | 10/05/2024
TO-24-BUT-CUL-1-01 | 110kV FEEDER - BUTLERSTOWN 110-CULLENAGH 110-1 | 3 | 3 | 3 | Scheduled | 07/05/2024 | 09/05/2024
TO-24-ROP-110K1-01 | COUPLER/SECTIONALISING CB - ROSSPILE 110-ROSSPILE 110-110K1 | 1 | 1 | 1 | Proposed | 08/05/2024 | 08/05/2024
TO-24-ARK-T101-01 | DISTRIBUTION TRANSFORMER - ARKLOW 110-ARKLOW 10-T101 | 2 | 2 | 2 | Reference (Proposed) | 09/05/2024 | 10/05/2024
TO-24-CRA-LWD-1-06 | 110kV FEEDER - CRANE 110-LODGEWOOD 110-1 | 5 | 5 | 5 | Proposed | 13/05/2024 | 17/05/2024
TO-24-KLS-220K1-2-04 | COUPLER/SECTIONALISING CB - KELLIS 220-KELLIS 220-220K1-2 | 57 | 40 | 40 | Scheduled | 13/05/2024 | 08/07/2024
TO-24-DAL,T-DAL-1-01 | 110kV FEEDER - DALLOW tee-DALLOW 110-1 | 7 | 5 | 5 | Proposed | 14/05/2024 | 20/05/2024
TO-24-ROP-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - ROSSPILE 110-ROSSPILE 110-110SA1-2CB | 1 | 1 | 1 | Proposed | 15/05/2024 | 15/05/2024
TO-24-ROP-110SB1-2CB-01 | COUPLER/SECTIONALISING CB - ROSSPILE 110-ROSSPILE 110-110SB1-2CB | 1 | 1 | 1 | Proposed | 16/05/2024 | 16/05/2024
TO-24-CUL-T2101-03 | TRANSFORMER - CULLENAGH 220-CULLENAGH 110-T2101 | 2 | 2 | 2 | Proposed | 20/05/2024 | 21/05/2024
TO-24-GI GIS-220K1-03 | COUPLER/SECTIONALISING CB - GREAT ISLAND GIS 220-GREAT ISLAND GIS 220-220K1 | 12 | 10 | 10 | Proposed | 20/05/2024 | 31/05/2024
TO-24-GI GIS-220SA1-2CB-04 | COUPLER/SECTIONALISING CB - GREAT ISLAND GIS 220-GREAT ISLAND GIS 220-220SA1-2CB | 12 | 10 | 10 | Proposed | 20/05/2024 | 31/05/2024
TO-24-GI GIS-220SB1-2CB-02 | COUPLER/SECTIONALISING CB - GREAT ISLAND GIS 220-GREAT ISLAND GIS 220-220SB1-2CB | 12 | 10 | 10 | Proposed | 20/05/2024 | 31/05/2024
TO-24-DAL,T-DEY-1-01 | 110kV FEEDER - DALLOW tee-DERRYCARNEY 110-1 | 86 | 60 | 60 | Proposed | 21/05/2024 | 14/08/2024
TO-24-GI GIS-T2004-02 | GENERATOR TRANSFORMER - GREAT ISLAND GIS 220-GREAT ISLAND GIS G4-T2004 | 11 | 9 | 9 | Proposed | 21/05/2024 | 31/05/2024
TO-24-CUL-GI GIS-1-01 | 220kV FEEDER - CULLENAGH 220-GREAT ISLAND GIS 220-1 | 3 | 3 | 3 | Proposed | 22/05/2024 | 24/05/2024
TO-24-CAH-DOO-1-01 | 110kV FEEDER - CAHIR 110-DOON 110-1 | 12 | 9 | 9 | Scheduled | 27/05/2024 | 07/06/2024
TO-24-KLS-T2101-05 | TRANSFORMER - KELLIS 220-KELLIS 110-T2101 | 5 | 5 | 5 | Scheduled | 27/05/2024 | 31/05/2024
TO-24-CUL-220K1-2-01 | COUPLER/SECTIONALISING CB - CULLENAGH 220-CULLENAGH 220-220K1-2 | 2 | 2 | 2 | Proposed | 28/05/2024 | 29/05/2024
TO-24-GI GIS-KLS-1-01 | 220kV FEEDER - GREAT ISLAND GIS 220-KELLIS 220-1 | Unknown | Unknown | 6 | Planned | June | June
TO-24-STR-T141-04 | DISTRIBUTION TRANSFORMER - STRATFORD 110-STRATFORD 38-T141 | Unknown | Unknown | 9 | Reference (Planned) | June | June
TO-24-STR,T-CLW-1-04 | 110kV FEEDER - STRATFORD tee-CARLOW 110-1 | Unknown | Unknown | 9 | Planned | June | June
TO-24-STR,T-PA-1-04 | 110kV FEEDER - STRATFORD tee-POLLAPHUCA 110-1 | Unknown | Unknown | 9 | Planned | June | June
TO-24-STR,T-STR-1-04 | 110kV FEEDER - STRATFORD tee-STRATFORD 110-1 | Unknown | Unknown | 9 | Planned | June | June
TO-24-BDA-T102-01 | TSO CUSTOMER TRANSFORMER - BARODA 110-BARODA 10-T102 | 3 | 3 | 3 | Proposed | 05/06/2024 | 07/06/2024
TO-24-DEY-110K2-01 | COUPLER/SECTIONALISING CB - DERRYCARNEY 110-DERRYCARNEY 110-110K2 | 1 | 1 | 1 | Proposed | 05/06/2024 | 05/06/2024
TO-24-BDA-MON-1-01 | 110kV FEEDER - BARODA 110-MONREAD 110-1 | 5 | 5 | 5 | Proposed | 10/06/2024 | 14/06/2024
TO-24-BDN-CUL-1-01 | 110kV FEEDER - BALLYDINE 110-CULLENAGH 110-1 | 2 | 2 | 2 | Proposed | 12/06/2024 | 13/06/2024
TO-24-110 kV A1 @ CAH-02 | BUSBAR SECTION - CAHIR 110-CAHIR 110-110A1 | 2 | 2 | 2 | Proposed | 12/06/2024 | 13/06/2024
TO-24-CAH-KHL-1-01 | 110kV FEEDER - CAHIR 110-KILL HILL 110-1 | 2 | 2 | 2 | Proposed | 12/06/2024 | 13/06/2024
TO-24-KLS-KKY-1-03 | 110kV FEEDER - KELLIS 110-KILKENNY 110-1 | 10 | 8 | 8 | Proposed | 12/06/2024 | 21/06/2024
TO-24-KKY-CAP2-01 | CAPACITOR/SVC/REACTOR - KILKENNY 110-KILKENNY 110-CAP2 | 5 | 5 | 5 | Proposed | 17/06/2024 | 21/06/2024
TO-24-BAR,T-CAH-1-01 | 110kV FEEDER - BARRYMORE tee-CAHIR 110-1 | Unknown | Unknown | 10 | Planned | July | August
TO-24-110 kV A2 @ CAH-02 | BUSBAR SECTION - CAHIR 110-CAHIR 110-110A2 | 12 | 10 | 10 | Proposed | 22/07/2024 | 02/08/2024
TO-24-110 kV B2 @ CAH-02 | BUSBAR SECTION - CAHIR 110-CAHIR 110-110B2 | 12 | 10 | 10 | Proposed | 22/07/2024 | 02/08/2024
TO-24-CUS-T103/5-01 | GENERATOR TRANSFORMER - CUSHALING 110-CUSHALING G3/5-T103/5 | Unknown | Unknown | 10 | Planned | July | August
TO-24-CUS-KIR-1-01 | 110kV FEEDER - CUSHALING 110-KILCUMBER 110-1 | Unknown | Unknown | 2 | Planned | July | July
TO-24-KIR-T131-01 | GENERATOR TRANSFORMER - KILCUMBER 110-KILCUMBER 33-T131 | Unknown | Unknown | 2 | Planned | July | July
TO-24-CUS-T101-01 | GENERATOR TRANSFORMER - CUSHALING 110-CUSHALING G1-T101 | Unknown | Unknown | 1 | Planned | August | August
TO-24-BDA-T101-01 | TSO CUSTOMER TRANSFORMER - BARODA 110-BARODA 10-T101 | 9 | 7 | 7 | Proposed | 02/09/2024 | 10/09/2024
TO-24-BDA-T101-02 | TSO CUSTOMER TRANSFORMER - BARODA 110-BARODA 10-T101 | 9 | 7 | 7 | Proposed | 02/09/2024 | 10/09/2024
TO-24-CRA-WEX-1-01 | 110kV FEEDER - CRANE 110-WEXFORD 110-1 | Unknown | Unknown |  | Planned | September | September
TO-24-ARK-CKM GIS-1-01 | 220kV FEEDER - ARKLOW 220-CARRICKMINES GIS 220-1 | Unknown | Unknown |  | Planned | November | December
TO-24-ROP-T131-01 | GENERATOR TRANSFORMER - ROSSPILE 110-ROSSPILE 33-T131 | Unknown | Unknown | 2 | Planned | November | November

## GEN_NorthWest
Outage ID | Feeder ID | Calendar Day Duration | Working Day Duration | Work Days | Outage Status | Start | Finish
TO-24-220 kV A2 @ CSH-01 | BUSBAR SECTION - CASHLA 220-CASHLA 220-220A2 | 5 | 5 | 5 | Scheduled | 08/01/2024 | 12/01/2024
TO-24-220 kV A4 @ CSH-02 | BUSBAR SECTION - CASHLA 220-CASHLA 220-220A4 | 5 | 5 | 5 | Scheduled | 08/01/2024 | 12/01/2024
TO-24-220 kV B2 @ CSH-03 | BUSBAR SECTION - CASHLA 220-CASHLA 220-220B2 | 5 | 5 | 5 | Scheduled | 08/01/2024 | 12/01/2024
TO-24-220 kV B4 @ CSH-01 | BUSBAR SECTION - CASHLA 220-CASHLA 220-220B4 | 5 | 5 | 5 | Scheduled | 08/01/2024 | 12/01/2024
TO-24-CSH-220K2-4-02 | COUPLER/SECTIONALISING CB - CASHLA 220-CASHLA 220-220K2-4 | 5 | 5 | 5 | Scheduled | 08/01/2024 | 12/01/2024
TO-24-CF-T104-02 | GENERATOR TRANSFORMER - CATHALEENS FALL 110-CATHALEENS FALL G4-T104 | 2 | 2 | 2 | Scheduled | 12/02/2024 | 13/02/2024
TO-24-BUF-T131-01 | GENERATOR TRANSFORMER - BUFFY 110-BUFFY 33-T131 | 1 | 1 | 1 | Scheduled | 19/02/2024 | 19/02/2024
TO-24-CLN-LA-1-01 | 110kV FEEDER - CLOON 110-LANESBORO 110-1 | 12 | 10 | 10 | Scheduled | 19/02/2024 | 01/03/2024
TO-24-CSH-T2104-02 | TRANSFORMER - CASHLA 220-CASHLA 110-T2104 | 66 | 45 |  | Scheduled | 26/02/2024 | 01/05/2024
TO-24-SKY-T132-01 | GENERATOR TRANSFORMER - SRAHNAKILLY 110-SRAHNAKILLY 33-T132 | 2 | 2 | 2 | Scheduled | 29/02/2024 | 01/03/2024
TO-24-DYN-T121-01 | GENERATOR TRANSFORMER - DERRYBRIEN 110-DERRYBRIEN 20-T121 | 22 | 15 |  | Reference | 04/03/2024 | 25/03/2024
TO-24-FLA-SLB-1-04 | 110kV FEEDER - FLAGFORD 110-SLIABH BAWN 110-1 | 47 | 32 | 32 | Scheduled | 04/03/2024 | 19/04/2024
TO-24-CUN-GLR-1-01 | 110kV FEEDER - CUNGHILL 110-GLENREE 110-1 | 5 | 4 | 4 | Scheduled | 18/03/2024 | 22/03/2024
TO-24-110 kV A2 @ GLR-01 | BUSBAR SECTION - GLENREE 110-GLENREE 110-110A2 | 5 | 4 | 4 | Scheduled | 18/03/2024 | 22/03/2024
TO-24-GLR-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - GLENREE 110-GLENREE 110-110SA1-2CB | 5 | 4 | 4 | Scheduled | 18/03/2024 | 22/03/2024
TO-24-GLR-T142-01 | DISTRIBUTION TRANSFORMER - GLENREE 110-GLENREE 38-T142 | 5 | 4 | 4 | Reference | 18/03/2024 | 22/03/2024
TO-24-BIN-TIV-1-01 | 110kV FEEDER - BINBANE 110-TIEVEBRACK 110-1 | 4 | 4 | 4 | Scheduled | 19/03/2024 | 22/03/2024
TO-24-CBR-DLT-1-03 | 110kV FEEDER - CASTLEBAR 110-DALTON 110-1 | 4 | 4 | 4 | Scheduled | 25/03/2024 | 28/03/2024
TO-24-110 kV A2 @ CF-04 | BUSBAR SECTION - CATHALEENS FALL 110-CATHALEENS FALL 110-110A2 | 4 | 4 | 4 | Scheduled | 25/03/2024 | 28/03/2024
TO-24-110 kV B2 @ CF-01 | BUSBAR SECTION - CATHALEENS FALL 110-CATHALEENS FALL 110-110B2 | 4 | 4 | 4 | Scheduled | 25/03/2024 | 28/03/2024
TO-24-CF-SRA-2-03 | 110kV FEEDER - CATHALEENS FALL 110-SRANANAGH 110-2 | 4 | 4 | 4 | Scheduled | 25/03/2024 | 28/03/2024
TO-24-TAW-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - TAWNAGHMORE 110-TAWNAGHMORE 110-110SA1-2CB | 4 | 4 | 4 | Scheduled | 25/03/2024 | 28/03/2024
TO-24-CBR-SVC-02 | CAPACITOR/SVC/REACTOR - CASTLEBAR 110-CASTLEBAR 110-SVC | 4 | 4 | 4 | Scheduled | 02/04/2024 | 05/04/2024
TO-24-DRM-LET-1-01 | 110kV FEEDER - DRUMKEEN 110-LETTERKENNY 110-1 | 4 | 4 | 4 | Scheduled | 02/04/2024 | 05/04/2024
TO-24-LET-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - LETTERKENNY 110-LETTERKENNY 110-110SA1-2CB | 2 | 2 | 2 | Scheduled | 03/04/2024 | 04/04/2024
TO-24-LET-110SA1-3CB-02 | COUPLER/SECTIONALISING CB - LETTERKENNY 110-LETTERKENNY 110-110SA1-3CB | 2 | 2 | 2 | Scheduled | 03/04/2024 | 04/04/2024
TO-24-LET-M/CAP1-01 | CAPACITOR/SVC/REACTOR - LETTERKENNY 110-LETTERKENNY 110-M/CAP1 | 2 | 2 | 2 | Scheduled | 03/04/2024 | 04/04/2024
TO-24-LET-PST-01 | TRANSFORMER - LETTERKENNY 110-STRABANE 110-PST | 2 | 2 | 2 | Scheduled | 03/04/2024 | 04/04/2024
TO-24-LET-SVC-01 | CAPACITOR/SVC/REACTOR - LETTERKENNY 110-LETTERKENNY 110-SVC | 2 | 2 | 2 | Scheduled | 03/04/2024 | 04/04/2024
TO-24-LET-T141-01 | DISTRIBUTION TRANSFORMER - LETTERKENNY 110-LETTERKENNY 38-T141 | 2 | 2 |  | Reference | 03/04/2024 | 04/04/2024
TO-24-BK-CBR-1-01 | 110kV FEEDER - BELLACORICK 110-CASTLEBAR 110-1 | 12 | 10 | 10 | Scheduled | 08/04/2024 | 19/04/2024
TO-24-BK-SKY-1-01 | 110kV FEEDER - BELLACORICK 110-SRAHNAKILLY 110-1 | 19 | 15 | 15 | Scheduled | 08/04/2024 | 26/04/2024
TO-24-CL-T101-02 | GENERATOR TRANSFORMER - CLIFF 110-CLIFF G1-T101 | 5 | 5 |  | Scheduled | 08/04/2024 | 12/04/2024
TO-24-SKY-110SA1-01 | SECTIONALISING DISCONNECT - SRAHNAKILLY 110-SRAHNAKILLY 110-110SA1 | 19 | 15 | 15 | Scheduled | 08/04/2024 | 26/04/2024
TO-24-SKY-110SA2-01 | SECTIONALISING DISCONNECT - SRAHNAKILLY 110-SRAHNAKILLY 110-110SA2 | 19 | 15 | 15 | Scheduled | 08/04/2024 | 26/04/2024
TO-24-SKY-T131-02 | GENERATOR TRANSFORMER - SRAHNAKILLY 110-SRAHNAKILLY 33-T131 | 19 | 15 | 15 | Scheduled | 08/04/2024 | 26/04/2024
TO-24-SKY-T132-02 | GENERATOR TRANSFORMER - SRAHNAKILLY 110-SRAHNAKILLY 33-T132 | 19 | 15 | 15 | Scheduled | 08/04/2024 | 26/04/2024
TO-24-LLA-T133-01 | GENERATOR TRANSFORMER - LENALEA 110-LENALEA 33-T133 | 1 | 1 | 1 | Scheduled | 09/04/2024 | 09/04/2024
TO-24-CF-CL-1-02 | 110kV FEEDER - CATHALEENS FALL 110-CLIFF 110-1 | 2 | 2 | 2 | Scheduled | 10/04/2024 | 11/04/2024
TO-24-CL-T102-02 | GENERATOR TRANSFORMER - CLIFF 110-CLIFF G2-T102 | 2 | 2 | 2 | Scheduled | 10/04/2024 | 11/04/2024
TO-24-BIN-CF-1-01 | 110kV FEEDER - BINBANE 110-CATHALEENS FALL 110-1 | 143 | 100 | 100 | Scheduled | 22/04/2024 | 11/09/2024
TO-24-COS-FLA-1-03 | 110kV FEEDER - CARRICK ON SHANNON 110-FLAGFORD 110-1 | 58 | 40 |  | Scheduled | 22/04/2024 | 18/06/2024
TO-24-110 kV A2 @ CLO-02 | BUSBAR SECTION - CLOGHER 110-CLOGHER 110-110A2 | 8 | 6 | 6 | Scheduled | 22/04/2024 | 29/04/2024
TO-24-110 kV B2 @ CLO-02 | BUSBAR SECTION - CLOGHER 110-CLOGHER 110-110B2 | 8 | 6 | 6 | Scheduled | 22/04/2024 | 29/04/2024
TO-24-CLO-MRY-1-01 | 110kV FEEDER - CLOGHER 110-MULREAVY 110-1 | 8 | 6 | 6 | Scheduled | 22/04/2024 | 29/04/2024
TO-24-110 kV A1 @ FLA-06 | BUSBAR SECTION - FLAGFORD 110-FLAGFORD 110-110A1 | 54 | 38 | 38 | Proposed | 22/04/2024 | 14/06/2024
TO-24-110 kV B1 @ FLA-07 | BUSBAR SECTION - FLAGFORD 110-FLAGFORD 110-110B1 | 54 | 38 | 38 | Proposed | 22/04/2024 | 14/06/2024
TO-24-MRY-T131-01 | GENERATOR TRANSFORMER - MULREAVY 110-MULREAVY 33-T131 | 8 | 6 | 6 | Scheduled | 22/04/2024 | 29/04/2024
TO-24-UGL-T132-03 | GENERATOR TRANSFORMER - UGGOOL 110-UGGOOL 33-T132 | 4 | 4 | 4 | Scheduled | 22/04/2024 | 25/04/2024
TO-24-UGL-T134-02 | GENERATOR TRANSFORMER - UGGOOL 110-UGGOOL 33-T134 | 4 | 4 | 4 | Scheduled | 22/04/2024 | 25/04/2024
TO-24-CL-T102-05 | GENERATOR TRANSFORMER - CLIFF 110-CLIFF G2-T102 | 5 | 5 | 5 | Proposed | 29/04/2024 | 03/05/2024
TO-24-CSH-T2102-01 | TRANSFORMER - CASHLA 220-CASHLA 110-T2102 | 79 | 55 | 55 | Proposed | 02/05/2024 | 19/07/2024
TO-24-CBR-CAP2-01 | CAPACITOR/SVC/REACTOR - CASTLEBAR 110-CASTLEBAR 110-CAP2 | 4 | 4 | 4 | Scheduled | 07/05/2024 | 10/05/2024
TO-24-110 kV A2 @ CF-05 | BUSBAR SECTION - CATHALEENS FALL 110-CATHALEENS FALL 110-110A2 | 1 | 1 | 1 | Proposed | 07/05/2024 | 07/05/2024
TO-24-CF-T104-04 | GENERATOR TRANSFORMER - CATHALEENS FALL 110-CATHALEENS FALL G4-T104 | 1 | 1 | 1 | Proposed | 07/05/2024 | 07/05/2024
TO-24-CLO-DRM-1-01 | 110kV FEEDER - CLOGHER 110-DRUMKEEN 110-1 | 11 | 9 | 9 | Proposed | 07/05/2024 | 17/05/2024
TO-24-CSH-GAL GIS-2-02 | 110kV FEEDER - CASHLA 110-GALWAY GIS 110-2 | 1 | 1 | 1 | Scheduled | 08/05/2024 | 08/05/2024
TO-24-CSH-CLN-1-01 | 110kV FEEDER - CASHLA 110-CLOON 110-1 | 6 | 5 | 5 | Proposed | 13/05/2024 | 18/05/2024
TO-24-CL-T102-03 | GENERATOR TRANSFORMER - CLIFF 110-CLIFF G2-T102 | 11 | 9 |  | Proposed | 13/05/2024 | 23/05/2024
TO-24-MOY-CAP2-01 | CAPACITOR/SVC/REACTOR - MOY 110-MOY 110-CAP2 | 2 | 2 | 2 | Proposed | 14/05/2024 | 15/05/2024
TO-24-CSH-GAL GIS-1-01 | 110kV FEEDER - CASHLA 110-GALWAY GIS 110-1 | 3 | 3 | 3 | Proposed | 20/05/2024 | 22/05/2024
TO-24-FLA-220K1-2-01 | COUPLER/SECTIONALISING CB - FLAGFORD 220-FLAGFORD 220-220K1-2 | 5 | 5 | 5 | Proposed | 20/05/2024 | 24/05/2024
TO-24-CLN-110SA1-04 | SECTIONALISING DISCONNECT - CLOON 110-CLOON 110-110SA1 | 9 | 7 | 7 | Proposed | 23/05/2024 | 31/05/2024
TO-24-CLN-LA-1-04 | 110kV FEEDER - CLOON 110-LANESBORO 110-1 | 9 | 7 | 7 | Proposed | 23/05/2024 | 31/05/2024
TO-24-CSH-GAL GIS-4-02 | 110kV FEEDER - CASHLA 110-GALWAY GIS 110-4 | 5 | 5 | 5 | Proposed | 27/05/2024 | 31/05/2024
TO-24-CSH-DLT-1-01 | 110kV FEEDER - CASHLA 110-DALTON 110-1 | 11 | 9 | 9 | Proposed | 04/06/2024 | 14/06/2024
TO-24-KNY-SAL-1-01 | 110kV FEEDER - KNOCKRANNY 110-SALTHILL 110-1 | 4 | 4 | 4 | Proposed | 04/06/2024 | 07/06/2024
TO-24-CF-SRA-1-04 | 110kV FEEDER - CATHALEENS FALL 110-SRANANAGH 110-1 | 56 | 40 | 40 | Proposed | 05/06/2024 | 30/07/2024
TO-24-CSH-220K1-2-01 | COUPLER/SECTIONALISING CB - CASHLA 220-CASHLA 220-220K1-2 | 5 | 5 | 5 | Proposed | 10/06/2024 | 14/06/2024
TO-24-CF-T103-01 | GENERATOR TRANSFORMER - CATHALEENS FALL 110-CATHALEENS FALL G3-T103 | Unknown | Unknown | 7 | Planned | June | June
TO-24-GAL GIS-KNY-1-02 | 110kV FEEDER - GALWAY GIS 110-KNOCKRANNY 110-1 | 5 | 5 | 5 | Proposed | 10/06/2024 | 14/06/2024
TO-24-DYN-T121-03 | GENERATOR TRANSFORMER - DERRYBRIEN 110-DERRYBRIEN 20-T121 | Unknown | Unknown | 2 | Reference (Planned) | June | June
TO-24-LET-SVC-02 | CAPACITOR/SVC/REACTOR - LETTERKENNY 110-LETTERKENNY 110-SVC | 5 | 5 | 5 | Proposed | 17/06/2024 | 21/06/2024
TO-24-CLO-CRD-1-01 | 110kV FEEDER - CLOGHER 110-CROAGHONAGH 110-1 | 4 | 4 | 4 | Proposed | 18/06/2024 | 21/06/2024
TO-24-CSH-TY-1-05 | 220kV FEEDER - CASHLA 220-TYNAGH 220-1 | Unknown | Unknown | 45 | Planned | June | August
TO-24-CF-CAP2-01 | CAPACITOR/SVC/REACTOR - CATHALEENS FALL 110-CATHALEENS FALL 110-CAP2 | 5 | 5 | 5 | Proposed | 24/06/2024 | 28/06/2024
TO-24-TAW-T1/T2-01 | GENERATOR TRANSFORMER - TAWNAGHMORE 110-TAWNAGHMORE 10-T1/T2 | Unknown | Unknown | 3 | Planned | July | July
TO-24-KLH-KNY-1-01 | 110kV FEEDER - KNOCKALOUGH 110-KNOCKRANNY 110-1 | Unknown | Unknown | 3 | Planned | July | July
TO-24-KLH-T121-01 | GENERATOR TRANSFORMER - KNOCKALOUGH 110-KNOCKALOUGH 20-T121 | Unknown | Unknown | 3 | Planned | July | July
TO-24-KNY-UGL-1-01 | 110kV FEEDER - KNOCKRANNY 110-UGGOOL 110-1 | Unknown | Unknown | 2 | Planned | July | July
TO-24-LET-CAP2-01 | CAPACITOR/SVC/REACTOR - LETTERKENNY 110-LETTERKENNY 110-CAP2 | Unknown | Unknown | 10 | Planned | July | July
TO-24-TAW-T3-01 | GENERATOR TRANSFORMER - TAWNAGHMORE 110-TAWNAGHMORE 10-T3 | Unknown | Unknown | 1 | Planned | July | July
TO-24-UGL-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - UGGOOL 110-UGGOOL 110-110SA1-2CB | Unknown | Unknown | 2 | Planned | July | July
TO-24-UGL-T131-01 | GENERATOR TRANSFORMER - UGGOOL 110-UGGOOL 33-T131 | Unknown | Unknown |  | Planned | July | July
TO-24-UGL-T132-02 | GENERATOR TRANSFORMER - UGGOOL 110-UGGOOL 33-T132 | Unknown | Unknown | 2 | Planned | July | July
TO-24-UGL-T134-01 | GENERATOR TRANSFORMER - UGGOOL 110-UGGOOL 33-T134 | Unknown | Unknown | 2 | Planned | July | July
TO-24-CDY-GRV-1-01 | 110kV FEEDER - CORDERRY 110-GARVAGH 110-1 | Unknown | Unknown | 1 | Planned | July | July
TO-24-GRV-T121-01 | GENERATOR TRANSFORMER - GARVAGH 110-GARVAGH 20-T121 | Unknown | Unknown | 7 | Planned | July | July
TO-24-GRV-T141-02 | DISTRIBUTION TRANSFORMER - GARVAGH 110-GARVAGH 20-T141 | 1 | 1 | 1 | Reference (Proposed) | 15/07/2024 | 15/07/2024
TO-24-CSH-T2101-01 | TRANSFORMER - CASHLA 220-CASHLA 110-T2101 | Unknown | Unknown | 45 | Planned | July | September
TO-24-110 kV A1 @ FLA-08 | BUSBAR SECTION - FLAGFORD 110-FLAGFORD 110-110A1 | 5 | 5 | 5 | Proposed | 29/07/2024 | 02/08/2024
TO-24-110 kV B1 @ FLA-09 | BUSBAR SECTION - FLAGFORD 110-FLAGFORD 110-110B1 | 5 | 5 | 5 | Proposed | 29/07/2024 | 02/08/2024
TO-24-FLA-GIL-1-01 | 110kV FEEDER - FLAGFORD 110-GILRA 110-1 | 5 | 5 | 5 | Proposed | 29/07/2024 | 02/08/2024
TO-24-110 kV A2 @ CF-06 | BUSBAR SECTION - CATHALEENS FALL 110-CATHALEENS FALL 110-110A2 | 11 | 9 | 9 | Proposed | 06/08/2024 | 16/08/2024
TO-24-110 kV B2 @ CF-02 | BUSBAR SECTION - CATHALEENS FALL 110-CATHALEENS FALL 110-110B2 | 11 | 9 | 9 | Proposed | 06/08/2024 | 16/08/2024
TO-24-CF-COR-1-01 | 110kV FEEDER - CATHALEENS FALL 110-CORRACLASSY 110-1 | Unknown | Unknown | 10 | Planned | August | September
TO-24-GLR-MOY-1-01 | 110kV FEEDER - GLENREE 110-MOY 110-1 | Unknown | Unknown | 35 | Planned | August | October
TO-24-GLR-MOY-1-05 | 110kV FEEDER - GLENREE 110-MOY 110-1 | Unknown | Unknown | 35 | Planned | August | October
TO-24-MOY-TAW-1-04 | 110kV FEEDER - MOY 110-TAWNAGHMORE 110-1 | Unknown | Unknown | 10 | Planned | August | September
TO-24-CF-T104-01 | GENERATOR TRANSFORMER - CATHALEENS FALL 110-CATHALEENS FALL G4-T104 | Unknown | Unknown | 7 | Planned | September | September
TO-24-COS-FLA-2-03 | 110kV FEEDER - CARRICK ON SHANNON 110-FLAGFORD 110-2 | Unknown | Unknown | 40 | Planned | September | November
TO-24-CSH-SAL-1-01 | 110kV FEEDER - CASHLA 110-SALTHILL 110-1 | Unknown | Unknown |  | Planned | October | October
TO-24-CF-110K1-2-01 | COUPLER/SECTIONALISING CB - CATHALEENS FALL 110-CATHALEENS FALL 110-110K1-2 | Unknown | Unknown | 10 | Planned | October | October
TO-24-MOY-TAW-2-01 | 110kV FEEDER - MOY 110-TAWNAGHMORE 110-2 | Unknown | Unknown | 5 | Planned | October | October
TO-24-MOY-TAW-2-02 | 110kV FEEDER - MOY 110-TAWNAGHMORE 110-2 | Unknown | Unknown | 5 | Planned | October | October
TO-24-MOY-TAW-1-01 | 110kV FEEDER - MOY 110-TAWNAGHMORE 110-1 | Unknown | Unknown | 5 | Planned | October | October
TO-24-BK-110SA1-02 | SECTIONALISING DISCONNECT - BELLACORICK 110-BELLACORICK 110-110SA1 | Unknown | Unknown | 4 | Planned | November | November
TO-24-BK-110SA2-04 | SECTIONALISING DISCONNECT - BELLACORICK 110-BELLACORICK 110-110SA2 | Unknown | Unknown | 4 | Planned | November | November
TO-24-BK-MOY-1-01 | 110kV FEEDER - BELLACORICK 110-MOY 110-1 | Unknown | Unknown | 5 | Planned | November | November
TO-24-BK-MOY-1-04 | 110kV FEEDER - BELLACORICK 110-MOY 110-1 | Unknown | Unknown | 5 | Planned | November | November
TO-24-CSH-ENN-1-01 | 110kV FEEDER - CASHLA 110-ENNIS 110-1 | Unknown | Unknown | 6 | Planned | November | November

## GEN_NorthEast
Outage ID | Feeder ID | Calendar Day Duration | Working Day Duration | Work Days | Outage Status | Start | Finish
TO-24-110 kV A1 @ LOU-02 | BUSBAR SECTION - LOUTH 110-LOUTH 110-110A1 | 12 | 10 | 10 | Scheduled | 08/01/2024 | 19/01/2024
TO-24-110 kV B1 @ LOU-02 | BUSBAR SECTION - LOUTH 110-LOUTH 110-110B1 | 12 | 10 | 10 | Scheduled | 08/01/2024 | 19/01/2024
TO-24-110 kV A1 @ ATH-01 | BUSBAR SECTION - ATHLONE 110-ATHLONE 110-110A1 | 2 | 2 | 2 | Proposed | 14/02/2024 | 15/02/2024
TO-24-CLN-LA-1-01 | 110kV FEEDER - CLOON 110-LANESBORO 110-1 | 12 | 10 | 10 | Scheduled | 19/02/2024 | 01/03/2024
TO-24-ATH-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - ATHLONE 110-ATHLONE 110-110SA1-2CB | 2 | 2 | 2 | Scheduled | 26/02/2024 | 27/02/2024
TO-24-ATH-CAP3-02 | CAPACITOR/SVC/REACTOR - ATHLONE 110-ATHLONE 110-CAP3 | 2 | 2 | 2 | Scheduled | 26/02/2024 | 27/02/2024
TO-24-ATH-LA-1-01 | 110kV FEEDER - ATHLONE 110-LANESBORO 110-1 | 2 | 2 | 2 | Scheduled | 26/02/2024 | 27/02/2024
TO-24-ATH-T141-01 | DISTRIBUTION TRANSFORMER - ATHLONE 110-ATHLONE 38-T141 | 2 | 2 | 2 | Reference | 26/02/2024 | 27/02/2024
TO-24-OST-WOO-1-01 | 400kV FEEDER - OLDSTREET 400-WOODLAND 400-1 | 5 | 5 | 5 | Scheduled | 26/02/2024 | 01/03/2024
TO-24-ATH-110SA1-2CB-04 | COUPLER/SECTIONALISING CB - ATHLONE 110-ATHLONE 110-110SA1-2CB | 2 | 2 | 2 | Scheduled | 29/02/2024 | 01/03/2024
TO-24-ATH-CAP3-05 | CAPACITOR/SVC/REACTOR - ATHLONE 110-ATHLONE 110-CAP3 | 2 | 2 | 2 | Scheduled | 29/02/2024 | 01/03/2024
TO-24-ATH-LA-1-04 | 110kV FEEDER - ATHLONE 110-LANESBORO 110-1 | 2 | 2 | 2 | Scheduled | 29/02/2024 | 01/03/2024
TO-24-ATH-T141-02 | DISTRIBUTION TRANSFORMER - ATHLONE 110-ATHLONE 38-T141 | 2 | 2 | 2 | Reference | 29/02/2024 | 01/03/2024
TO-24-AGL-DYN-1-01 | 110kV FEEDER - AGANNYGAL 110-DERRYBRIEN 110-1 | 22 | 15 |  | Scheduled | 04/03/2024 | 25/03/2024
TO-24-AGL-ENN-1-01 | 110kV FEEDER - AGANNYGAL 110-ENNIS 110-1 | 22 | 15 | 15 | Scheduled | 04/03/2024 | 25/03/2024
TO-24-AGL-SH-1-01 | 110kV FEEDER - AGANNYGAL 110-SHANNONBRIDGE 110-1 | 22 | 15 | 15 | Scheduled | 04/03/2024 | 25/03/2024
TO-24-FLA-SLB-1-04 | 110kV FEEDER - FLAGFORD 110-SLIABH BAWN 110-1 | 47 | 32 | 32 | Scheduled | 04/03/2024 | 19/04/2024
TO-24-DER-KIN-1-02 | 110kV FEEDER - DERRYIRON 110-KINNEGAD 110-1 | 23 | 15 | 15 | Scheduled | 19/03/2024 | 10/04/2024
TO-24-DER-T1/T2-02 | GENERATOR TRANSFORMER - DERRYIRON 110-RHODE 110-T1/T2 | 23 | 15 | 15 | Scheduled | 19/03/2024 | 10/04/2024
TO-24-DEY-T134-02 | GENERATOR TRANSFORMER - DERRYCARNEY 110-DERRYCARNEY 33-T134 | 2 | 2 | 2 | Scheduled | 20/03/2024 | 21/03/2024
TO-24-110 kV A1 @ GOR-02 | BUSBAR SECTION - GORMAN 110-GORMAN 110-110A1 | 9 | 7 | 7 | Scheduled | 20/03/2024 | 28/03/2024
TO-24-110 kV B1 @ GOR-01 | BUSBAR SECTION - GORMAN 110-GORMAN 110-110B1 | 9 | 7 | 7 | Scheduled | 20/03/2024 | 28/03/2024
TO-24-GAR-110K1-01 | COUPLER/SECTIONALISING CB - GARBALLAGH 110-GARBALLAGH 110-110K1 | 1 | 1 | 1 | Scheduled | 03/04/2024 | 03/04/2024
TO-24-GAR-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - GARBALLAGH 110-GARBALLAGH 110-110SA1-2CB | 1 | 1 | 1 | Scheduled | 04/04/2024 | 04/04/2024
TO-24-GAR-110SB1-2CB-01 | COUPLER/SECTIONALISING CB - GARBALLAGH 110-GARBALLAGH 110-110SB1-2CB | 1 | 1 | 1 | Scheduled | 05/04/2024 | 05/04/2024
TO-24-110 kV A2 @ SLB-01 | BUSBAR SECTION - SLIABH BAWN 110-SLIABH BAWN 110-110A2 | 5 | 5 | 5 | Scheduled | 08/04/2024 | 12/04/2024
TO-24-110 kV B2 @ SLB-01 | BUSBAR SECTION - SLIABH BAWN 110-SLIABH BAWN 110-110B2 | 5 | 5 | 5 | Scheduled | 08/04/2024 | 12/04/2024
TO-24-GOR-220K1-2-01 | COUPLER/SECTIONALISING CB - GORMAN 220-GORMAN 220-220K1-2 | 1 | 1 | 1 | Scheduled | 12/04/2024 | 12/04/2024
TO-24-BAL-DRY-1-05 | 110kV FEEDER - BALTRASNA 110-DRYBRIDGE 110-1 | 150 | 105 | 105 | Scheduled | 22/04/2024 | 18/09/2024
TO-24-LOU-RRU-1-13 | 110kV FEEDER - LOUTH 110-RATRUSSAN 110-1 | 140 | 97 | 97 | Proposed | 24/04/2024 | 10/09/2024
TO-24-RRU-110SA1-05 | SECTIONALISING DISCONNECT - RATRUSSAN 110-RATRUSSAN 110-110SA1 | 8 | 6 | 6 | Scheduled | 24/04/2024 | 01/05/2024
TO-24-RRU-110SA2-05 | SECTIONALISING DISCONNECT - RATRUSSAN 110-RATRUSSAN 110-110SA2 | 7 | 5 | 5 | Proposed | 24/04/2024 | 30/04/2024
TO-24-RRU-SKL-1-03 | 110kV FEEDER - RATRUSSAN 110-SHANKILL 110-1 | 29 | 20 | 20 | Scheduled | 24/04/2024 | 22/05/2024
TO-24-RRU-T121-05 | GENERATOR TRANSFORMER - RATRUSSAN 110-RATRUSSAN 20-T121 | 29 | 20 | 20 | Scheduled | 24/04/2024 | 22/05/2024
TO-24-RRU-T122-05 | GENERATOR TRANSFORMER - RATRUSSAN 110-RATRUSSAN 20-T122 | 29 | 20 | 20 | Scheduled | 24/04/2024 | 22/05/2024
TO-24-ATH-LA-1-02 | 110kV FEEDER - ATHLONE 110-LANESBORO 110-1 | 15 | 10 | 10 | Scheduled | 29/04/2024 | 13/05/2024
TO-24-GOR-T122-01 | GENERATOR TRANSFORMER - GORMAN 110-GORMAN 20-T122 | 1 | 1 | 1 | Scheduled | 30/04/2024 | 30/04/2024
TO-24-DER-TSB-1-06 | 110kV FEEDER - DERRYIRON 110-THORNSBERRY 110-1 | 86 | 60 | 60 | Proposed | 02/05/2024 | 26/07/2024
TO-24-LIS-T131-01 | GENERATOR TRANSFORMER - LISDRUM 110-LISDRUM 33-T131 | 1 | 1 | 1 | Scheduled | 08/05/2024 | 08/05/2024
TO-24-LOU-MTH-1-01 | 110kV FEEDER - LOUTH 110-MEATH HILL 110-1 | 5 | 5 |  | Proposed | 13/05/2024 | 17/05/2024
TO-24-DAL,T-DAL-1-01 | 110kV FEEDER - DALLOW tee-DALLOW 110-1 | 7 | 5 | 5 | Proposed | 14/05/2024 | 20/05/2024
TO-24-LOU-MLN-1-01 | 110kV FEEDER - LOUTH 110-MULLAGHARLIN 110-1 | 139 | 97 | 97 | Scheduled | 15/05/2024 | 30/09/2024
TO-24-LIS-CAP2-01 | CAPACITOR/SVC/REACTOR - LISDRUM 110-LISDRUM 110-CAP2 | 4 | 4 | 4 | Proposed | 21/05/2024 | 24/05/2024
TO-24-CLN-LA-1-04 | 110kV FEEDER - CLOON 110-LANESBORO 110-1 | 9 | 7 | 7 | Proposed | 23/05/2024 | 31/05/2024
TO-24-DEY-T134-03 | GENERATOR TRANSFORMER - DERRYCARNEY 110-DERRYCARNEY 33-T134 | 2 | 2 | 2 | Proposed | 28/05/2024 | 29/05/2024
TO-24-MLC-T121-01 | GENERATOR TRANSFORMER - MOUNTLUCAS 110-MOUNTLUCAS 20-T121 | 2 | 2 | 2 | Proposed | 29/05/2024 | 30/05/2024
TO-24-GOR-NAV-2-02 | 110kV FEEDER - GORMAN 110-NAVAN 110-2 | Unknown | Unknown | 40 | Planned | June | July
TO-24-SLB-T132-01 | GENERATOR TRANSFORMER - SLIABH BAWN 110-SLIABH BAWN 33-T132 | Unknown | Unknown | 3 | Planned | June | June
TO-24-AGL-DYN-1-04 | 110kV FEEDER - AGANNYGAL 110-DERRYBRIEN 110-1 | Unknown | Unknown | 2 | Planned | June | June
TO-24-ATH-CAP3-01 | CAPACITOR/SVC/REACTOR - ATHLONE 110-ATHLONE 110-CAP3 | Unknown | Unknown | 5 | Planned | June | June
TO-24-ATH-SH-1-02 | 110kV FEEDER - ATHLONE 110-SHANNONBRIDGE 110-1 | 12 | 10 | 10 | Proposed | 17/06/2024 | 28/06/2024
TO-24-CSH-TY-1-05 | 220kV FEEDER - CASHLA 220-TYNAGH 220-1 | Unknown | Unknown | 45 | Planned | June | August
TO-24-SH-220K1-2-01 | COUPLER/SECTIONALISING CB - SHANNONBRIDGE 220-SHANNONBRIDGE 220-220K1-2 | Unknown | Unknown |  | Planned | June | July
TO-24-TY-T2001/2-02 | GENERATOR TRANSFORMER - TYNAGH 220-TYNAGH G1/2-T2001/2 | Unknown | Unknown | 1 | Planned | June | June
TO-24-CFN-SH-1-01 | 220kV FEEDER - CLONIFFEEN 220-SHANNONBRIDGE 220-1 | Unknown | Unknown | 1 | Planned | July | July
TO-24-CFN-T232-01 | GENERATOR TRANSFORMER - CLONIFFEEN 220-CLONIFFEEN 33-T232 | Unknown | Unknown | 1 | Planned | July | July
TO-24-RRU-T122-04 | GENERATOR TRANSFORMER - RATRUSSAN 110-RATRUSSAN 20-T122 | Unknown | Unknown | 4 | Planned | July | July
TO-24-DEY-T132-01 | GENERATOR TRANSFORMER - DERRYCARNEY 110-DERRYCARNEY 33-T132 | Unknown | Unknown | 2 | Planned | July | July
TO-24-GOR-NAV-1-02 | 110kV FEEDER - GORMAN 110-NAVAN 110-1 | Unknown | Unknown | 40 | Planned | August | September
TO-24-CF-COR-1-01 | 110kV FEEDER - CATHALEENS FALL 110-CORRACLASSY 110-1 | Unknown | Unknown | 10 | Planned | August | September
TO-24-COR-PST-02 | TRANSFORMER - CORRACLASSY 110-ENNISKILLEN 110-PST | Unknown | Unknown | 10 | Planned | August | September
TO-24-COR-GWE-1-03 | 110kV FEEDER - CORRACLASSY 110-GORTAWEE 110-1 | Unknown | Unknown | 10 | Planned | August | September
TO-24-IKE,T-SH-1-05 | 110kV FEEDER - IKERRIN tee-SHANNONBRIDGE 110-1 | Unknown | Unknown | 7 | Planned | September | September
TO-24-LOU-AT3-01 | TRANSFORMER - LOUTH 220-LOUTH 275-AT3 | Unknown | Unknown | 3 | Planned | September | September
TO-24-LIS-LSA-1-02 | 110kV FEEDER - LISDRUM 110-LISLEA 110-1 | Unknown | Unknown | 40 | Planned | September | November
TO-24-LOU-T2104-01 | TRANSFORMER - LOUTH 220-LOUTH 110-T2104 | Unknown | Unknown | 19 | Planned | October | November
TO-24-GAR-PLA-1-04 | 110kV FEEDER - GARBALLAGH 110-PLATIN 110-1 | Unknown | Unknown | 5 | Planned | October | October
TO-24-OBE-PLA-1-04 | 110kV FEEDER - OLDBRIDGE 110-PLATIN 110-1 | 5 | 5 | 5 | Proposed | 21/10/2024 | 25/10/2024
TO-24-GOR-MAY-1-01 | 220kV FEEDER - GORMAN 220-MAYNOOTH 220-1 | Unknown | Unknown |  | Planned | November | November
TO-24-LIS-LOU-1-02 | 110kV FEEDER - LISDRUM 110-LOUTH 110-1 | Unknown | Unknown | 10 | Planned | November | November

## GEN_Dublin
Outage ID | Feeder ID | Calendar Day Duration | Working Day Duration | Work Days | Outage Status | Start | Finish
TO-24-220 kV A1 @ MAY-01 | BUSBAR SECTION - MAYNOOTH 220-MAYNOOTH 220-220A1 | 12 | 10 | 10 | Proposed | 08/01/2024 | 19/01/2024
TO-24-220 kV B1 @ MAY-01 | BUSBAR SECTION - MAYNOOTH 220-MAYNOOTH 220-220B1 | 12 | 10 | 10 | Proposed | 08/01/2024 | 19/01/2024
TO-24-220 kV A3 @ PB-01 | BUSBAR SECTION - POOLBEG 220-POOLBEG 220-220A3 | 12 | 10 | 10 | Scheduled | 08/01/2024 | 19/01/2024
TO-24-220 kV A4 @ PB-02 | BUSBAR SECTION - POOLBEG 220-POOLBEG 220-220A4 | 12 | 10 | 10 | Scheduled | 08/01/2024 | 19/01/2024
TO-24-220 kV B3 @ PB-01 | BUSBAR SECTION - POOLBEG 220-POOLBEG 220-220B3 | 12 | 10 | 10 | Scheduled | 08/01/2024 | 19/01/2024
TO-24-220 kV B4 @ PB-01 | BUSBAR SECTION - POOLBEG 220-POOLBEG 220-220B4 | 12 | 10 | 10 | Scheduled | 08/01/2024 | 19/01/2024
TO-24-PB-R223-4-01 | CAPACITOR/SVC/REACTOR - POOLBEG 220-POOLBEG 220-R223-4 | 12 | 10 | 10 | Scheduled | 08/01/2024 | 19/01/2024
TO-24-RYB GIS-T108-01 | TSO CUSTOMER TRANSFORMER - RYEBROOK GIS 110-RYEBROOK 10-T108 | 5 | 5 | 5 | Scheduled | 22/01/2024 | 26/01/2024
TO-24-220 kV A4 @ CKM GIS-01 | BUSBAR SECTION - CARRICKMINES GIS 220-CARRICKMINES GIS 220-220A4 | 3 | 3 | 3 | Scheduled | 29/01/2024 | 31/01/2024
TO-24-220 kV B4 @ CKM GIS-01 | BUSBAR SECTION - CARRICKMINES GIS 220-CARRICKMINES GIS 220-220B4 | 3 | 3 | 3 | Scheduled | 29/01/2024 | 31/01/2024
TO-24-CKM GIS-220K4-01 | COUPLER/SECTIONALISING CB - CARRICKMINES GIS 220-CARRICKMINES GIS 220-220K4 | 3 | 3 | 3 | Scheduled | 29/01/2024 | 31/01/2024
TO-24-CKM GIS-220SA2-4CB-01 | COUPLER/SECTIONALISING CB - CARRICKMINES GIS 220-CARRICKMINES GIS 220-22SA2-4CB | 3 | 3 | 3 | Scheduled | 29/01/2024 | 31/01/2024
TO-24-CKM GIS-220SB2-4CB-01 | COUPLER/SECTIONALISING CB - CARRICKMINES GIS 220-CARRICKMINES GIS 220-22SB2-4CB | 3 | 3 | 3 | Scheduled | 29/01/2024 | 31/01/2024
TO-24-CKM GIS-DSN-1-02 | 220kV FEEDER - CARRICKMINES GIS 220-DUNSTOWN 220-1 | 3 | 3 | 3 | Scheduled | 29/01/2024 | 31/01/2024
TO-24-CKM GIS-T2104-01 | TRANSFORMER - CARRICKMINES GIS 220-CARRICKMINES GIS 110-T2104 | 3 | 3 | 3 | Reference | 29/01/2024 | 31/01/2024
TO-24-WOO-220K1-2-02 | COUPLER/SECTIONALISING CB - WOODLAND 220-WOODLAND 220-220K1-2 | 2 | 2 | 2 | Scheduled | 31/01/2024 | 01/02/2024
TO-24-PB-T2007/8-01 | GENERATOR TRANSFORMER - POOLBEG 220-POOLBEG G7/8-T2007/8 | 3 | 2 | 2 | Scheduled | 01/02/2024 | 03/02/2024
TO-24-220 kV A1 @ CKM-01 | BUSBAR SECTION - CARRICKMINES 220-CARRICKMINES 220-220A1 | 5 | 4 | 4 | Scheduled | 06/02/2024 | 10/02/2024
TO-24-CKM-CKM GIS-1-01 | 220kV FEEDER - CARRICKMINES 220-CARRICKMINES GIS 220-1 | 5 | 4 | 4 | Scheduled | 06/02/2024 | 10/02/2024
TO-24-CKM-PB-1-02 | 220kV FEEDER - CARRICKMINES 220-POOLBEG 220-1 | 5 | 4 | 4 | Scheduled | 06/02/2024 | 10/02/2024
TO-24-CKM-PST2201-01 | TRANSFORMER - CARRICKMINES 220-CARRICKMINES 220-PST2201 | 5 | 4 | 4 | Scheduled | 06/02/2024 | 10/02/2024
TO-24-RYB GIS-T109-01 | TSO CUSTOMER TRANSFORMER - RYEBROOK GIS 110-RYEBROOK 10-T109 | 4 | 4 | 4 | Scheduled | 06/02/2024 | 09/02/2024
TO-24-BRT-CLE-2-01 | 220kV FEEDER - BRACETOWN 220-CLONEE 220-2 | 1 | 1 | 1 | Scheduled | 07/02/2024 | 07/02/2024
TO-24-BRT-CLE-4-01 | 220kV FEEDER - BRACETOWN 220-CLONEE 220-4 | 1 | 1 | 1 | Scheduled | 08/02/2024 | 08/02/2024
TO-24-BRT-T222-01 | TSO CUSTOMER TRANSFORMER - BRACETOWN 220-BRACETOWN 20-T222 | 38 | 27 | 27 | Scheduled | 12/02/2024 | 20/03/2024
TO-24-CKM GIS-T2103-01 | TRANSFORMER - CARRICKMINES GIS 220-CARRICKMINES GIS 110-T2103 | 5 | 5 | 5 | Reference | 12/02/2024 | 16/02/2024
TO-24-400 kV A1 @ DSN-01 | BUSBAR SECTION - DUNSTOWN 400-DUNSTOWN 400-400A1 | 19 | 15 | 15 | Scheduled | 12/02/2024 | 01/03/2024
TO-24-400 kV B1 @ DSN-01 | BUSBAR SECTION - DUNSTOWN 400-DUNSTOWN 400-400B1 | 19 | 15 | 15 | Scheduled | 12/02/2024 | 01/03/2024
TO-24-DSN-T4201-02 | TRANSFORMER - DUNSTOWN 400-DUNSTOWN 220-T4201 | 19 | 15 | 15 | Scheduled | 12/02/2024 | 01/03/2024
TO-24-GLN-T133-03 | GENERATOR TRANSFORMER - GALLANSTOWN 110-GALLANSTOWN 33-T133 | 26 | 20 | 20 | Scheduled | 12/02/2024 | 08/03/2024
TO-24-110 kV A4 @ CBT-02 | BUSBAR SECTION - CASTLEBAGOT 110-CASTLEBAGOT 110-110A4 | 5 | 5 | 5 | Scheduled | 19/02/2024 | 23/02/2024
TO-24-110 kV B4 @ CBT-02 | BUSBAR SECTION - CASTLEBAGOT 110-CASTLEBAGOT 110-110B4 | 5 | 5 | 5 | Scheduled | 19/02/2024 | 23/02/2024
TO-24-CBT-CKG-2-03 | 110kV FEEDER - CASTLEBAGOT 110-CORKAGH 110-2 | 5 | 5 | 5 | Scheduled | 19/02/2024 | 23/02/2024
TO-24-OST-WOO-1-01 | 400kV FEEDER - OLDSTREET 400-WOODLAND 400-1 | 5 | 5 | 5 | Scheduled | 26/02/2024 | 01/03/2024
TO-24-TH-T2001/2-03 | GENERATOR TRANSFORMER - TURLOUGH HILL 220-TURLOUGH HILL G1-T2001/2 | 1 | 0 | 0 | Scheduled | 03/03/2024 | 03/03/2024
TO-24-TH-T2003/4-02 | GENERATOR TRANSFORMER - TURLOUGH HILL 220-TURLOUGH HILL G1-T2003/4 | 4 | 3 | 3 | Scheduled | 03/03/2024 | 06/03/2024
TO-24-BAG-T103-01 | TSO CUSTOMER TRANSFORMER - BARNAGEERAGH 110-BARNAGEERAGH 11-T103 | 2 | 2 | 2 | Scheduled | 04/03/2024 | 05/03/2024
TO-24-110 kV A1 @ CBT-02 | BUSBAR SECTION - CASTLEBAGOT 110-CASTLEBAGOT 110-110A1 | 5 | 5 | 5 | Scheduled | 04/03/2024 | 08/03/2024
TO-24-110 kV B1 @ CBT-02 | BUSBAR SECTION - CASTLEBAGOT 110-CASTLEBAGOT 110-110B1 | 5 | 5 | 5 | Scheduled | 04/03/2024 | 08/03/2024
TO-24-CBT-110K1-04 | COUPLER/SECTIONALISING CB - CASTLEBAGOT 110-CASTLEBAGOT 110-110K1 | 5 | 5 | 5 | Scheduled | 04/03/2024 | 08/03/2024
TO-24-CBT-110SA1-2CB-04 | COUPLER/SECTIONALISING CB - CASTLEBAGOT 110-CASTLEBAGOT 110-110SA1-2CB | 5 | 5 | 5 | Scheduled | 04/03/2024 | 08/03/2024
TO-24-CBT-110SB1-2CB-04 | COUPLER/SECTIONALISING CB - CASTLEBAGOT 110-CASTLEBAGOT 110-110SB1-2CB | 5 | 5 | 5 | Scheduled | 04/03/2024 | 08/03/2024
TO-24-CBT-CKG-1-03 | 110kV FEEDER - CASTLEBAGOT 110-CORKAGH 110-1 | 5 | 5 | 5 | Scheduled | 04/03/2024 | 08/03/2024
TO-24-220 kV A1 @ DSN-01 | BUSBAR SECTION - DUNSTOWN 220-DUNSTOWN 220-220A1 | 12 | 10 | 10 | Scheduled | 04/03/2024 | 15/03/2024
TO-24-220 kV B1 @ DSN-01 | BUSBAR SECTION - DUNSTOWN 220-DUNSTOWN 220-220B1 | 12 | 10 | 10 | Scheduled | 04/03/2024 | 15/03/2024
TO-24-DSN-TH-1-01 | 220kV FEEDER - DUNSTOWN 220-TURLOUGH HILL 220-1 | 12 | 10 |  | Scheduled | 04/03/2024 | 15/03/2024
TO-24-PB-R2001-01 | CAPACITOR/SVC/REACTOR - POOLBEG 220-POOLBEG 220-R2001 | 5 | 5 | 5 | Scheduled | 04/03/2024 | 08/03/2024
TO-24-220 kV A1 @ TH-01 | BUSBAR SECTION - TURLOUGH HILL 220-TURLOUGH HILL 220-220A1 | 12 | 10 | 10 | Scheduled | 04/03/2024 | 15/03/2024
TO-24-220 kV B1 @ TH-01 | BUSBAR SECTION - TURLOUGH HILL 220-TURLOUGH HILL 220-220B1 | 12 | 10 | 10 | Scheduled | 04/03/2024 | 15/03/2024
TO-24-ISH-T2002/3-01 | GENERATOR TRANSFORMER - IRISHTOWN 220-IRISHTOWN G2/3-T2002/3 | 2 | 2 | 2 | Scheduled | 06/03/2024 | 07/03/2024
TO-24-TH-T2001/2-02 | GENERATOR TRANSFORMER - TURLOUGH HILL 220-TURLOUGH HILL G1-T2001/2 | 4 | 3 | 3 | Scheduled | 10/03/2024 | 13/03/2024
TO-24-220 kV A2 @ CBT-03 | BUSBAR SECTION - CASTLEBAGOT 220-CASTLEBAGOT 220-220A2 | 12 | 9 | 9 | Scheduled | 11/03/2024 | 22/03/2024
TO-24-220 kV B2 @ CBT-03 | BUSBAR SECTION - CASTLEBAGOT 220-CASTLEBAGOT 220-220B2 | 12 | 9 | 9 | Scheduled | 11/03/2024 | 22/03/2024
TO-24-CBT-220K2-04 | COUPLER/SECTIONALISING CB - CASTLEBAGOT 220-CASTLEBAGOT 220-220K2 | 12 | 9 | 9 | Scheduled | 11/03/2024 | 22/03/2024
TO-24-CBT-220SA1-2CB-03 | COUPLER/SECTIONALISING CB - CASTLEBAGOT 220-CASTLEBAGOT 220-220SA1-2CB | 12 | 9 | 9 | Scheduled | 11/03/2024 | 22/03/2024
TO-24-CBT-220SB1-2CB-04 | COUPLER/SECTIONALISING CB - CASTLEBAGOT 220-CASTLEBAGOT 220-220SB1-2CB | 12 | 9 | 9 | Scheduled | 11/03/2024 | 22/03/2024
TO-24-BAG-T101-01 | TSO CUSTOMER TRANSFORMER - BARNAGEERAGH 110-BARNAGEERAGH 11-T101 | 2 | 2 | 2 | Scheduled | 12/03/2024 | 13/03/2024
TO-24-110 kV A1 @ CBT-03 | BUSBAR SECTION - CASTLEBAGOT 110-CASTLEBAGOT 110-110A1 | 3 | 3 | 3 | Scheduled | 12/03/2024 | 14/03/2024
TO-24-110 kV A2 @ CBT-02 | BUSBAR SECTION - CASTLEBAGOT 110-CASTLEBAGOT 110-110A2 | 3 | 3 | 3 | Scheduled | 12/03/2024 | 14/03/2024
TO-24-CBT-110SA1-2CB-03 | COUPLER/SECTIONALISING CB - CASTLEBAGOT 110-CASTLEBAGOT 110-110SA1-2CB | 3 | 3 | 3 | Scheduled | 12/03/2024 | 14/03/2024
TO-24-CKM GIS-T2104-02 | TRANSFORMER - CARRICKMINES GIS 220-CARRICKMINES GIS 110-T2104 | 11 | 8 | 8 | Reference | 18/03/2024 | 28/03/2024
TO-24-KYT-MAY-1-01 | 220kV FEEDER - KELLYSTOWN 220-MAYNOOTH 220-1 | 10 | 8 | 8 | Scheduled | 19/03/2024 | 28/03/2024
TO-24-WOO-400K1-2-01 | COUPLER/SECTIONALISING CB - WOODLAND 400-WOODLAND 400-400K1-2 | 4 | 4 | 4 | Scheduled | 19/03/2024 | 22/03/2024
TO-24-CKM GIS-R2001-01 | CAPACITOR/SVC/REACTOR - CARRICKMINES GIS 220-CARRICKMINES GIS 220-R2001 | 18 | 12 |  | Scheduled | 26/03/2024 | 12/04/2024
TO-24-220 kV A1 @ CBT-01 | BUSBAR SECTION - CASTLEBAGOT 220-CASTLEBAGOT 220-220A1 | 9 | 7 | 7 | Scheduled | 02/04/2024 | 10/04/2024
TO-24-220 kV B1 @ CBT-01 | BUSBAR SECTION - CASTLEBAGOT 220-CASTLEBAGOT 220-220B1 | 9 | 7 | 7 | Scheduled | 02/04/2024 | 10/04/2024
TO-24-CBT-220K1-02 | COUPLER/SECTIONALISING CB - CASTLEBAGOT 220-CASTLEBAGOT 220-220K1 | 9 | 7 | 7 | Scheduled | 02/04/2024 | 10/04/2024
TO-24-CBT-220SA1-2CB-05 | COUPLER/SECTIONALISING CB - CASTLEBAGOT 220-CASTLEBAGOT 220-220SA1-2CB | 9 | 7 | 7 | Scheduled | 02/04/2024 | 10/04/2024
TO-24-CBT-220SB1-2CB-05 | COUPLER/SECTIONALISING CB - CASTLEBAGOT 220-CASTLEBAGOT 220-220SB1-2CB | 9 | 7 | 7 | Scheduled | 02/04/2024 | 10/04/2024
TO-24-CBT-MAY-1-01 | 220kV FEEDER - CASTLEBAGOT 220-MAYNOOTH 220-1 | 9 | 7 | 7 | Scheduled | 02/04/2024 | 10/04/2024
TO-24-BLU-110K1-01 | COUPLER/SECTIONALISING CB - BLUNDELSTOWN 110-BLUNDELSTOWN 110-110K1 | 1 | 1 | 1 | Scheduled | 03/04/2024 | 03/04/2024
TO-24-CKM GIS-220SB1-3CB-01 | COUPLER/SECTIONALISING CB - CARRICKMINES GIS 220-CARRICKMINES GIS 220-22SB1-3CB | 1 | 1 | 1 | Scheduled | 04/04/2024 | 04/04/2024
TO-24-110 kV A4 @ CBT-03 | BUSBAR SECTION - CASTLEBAGOT 110-CASTLEBAGOT 110-110A4 | 5 | 5 | 5 | Scheduled | 08/04/2024 | 12/04/2024
TO-24-110 kV B4 @ CBT-03 | BUSBAR SECTION - CASTLEBAGOT 110-CASTLEBAGOT 110-110B4 | 5 | 5 | 5 | Scheduled | 08/04/2024 | 12/04/2024
TO-24-CBT-110K4-02 | COUPLER/SECTIONALISING CB - CASTLEBAGOT 110-CASTLEBAGOT 110-110K4 | 5 | 5 | 5 | Scheduled | 08/04/2024 | 12/04/2024
TO-24-CBT-110SA2-4CB-04 | COUPLER/SECTIONALISING CB - CASTLEBAGOT 110-CASTLEBAGOT 110-110SA2-4CB | 5 | 5 | 5 | Scheduled | 08/04/2024 | 12/04/2024
TO-24-CBT-110SB2-4CB-04 | COUPLER/SECTIONALISING CB - CASTLEBAGOT 110-CASTLEBAGOT 110-110SB2-4CB | 5 | 5 | 5 | Scheduled | 08/04/2024 | 12/04/2024
TO-24-110 kV A2 @ FIN-02 | BUSBAR SECTION - FINGLAS 110-FINGLAS 110-110A2 | 3 | 3 | 3 | Scheduled | 08/04/2024 | 10/04/2024
TO-24-110 kV B2 @ FIN-02 | BUSBAR SECTION - FINGLAS 110-FINGLAS 110-110B2 | 3 | 3 | 3 | Scheduled | 08/04/2024 | 10/04/2024
TO-24-110 kV A2 @ FIN GIS-02 | BUSBAR SECTION - FINGLAS GIS 110-FINGLAS GIS 110-110A2 | 7 | 5 | 5 | Scheduled | 11/04/2024 | 17/04/2024
TO-24-110 kV B2 @ FIN GIS-02 | BUSBAR SECTION - FINGLAS GIS 110-FINGLAS GIS 110-110B2 | 7 | 5 | 5 | Scheduled | 11/04/2024 | 17/04/2024
TO-24-FIN GIS-110K2-03 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110K2 | 7 | 5 | 5 | Scheduled | 11/04/2024 | 17/04/2024
TO-24-FIN GIS-110SA1-2CB-03 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110SA1-2CB | 7 | 5 | 5 | Scheduled | 11/04/2024 | 17/04/2024
TO-24-FIN GIS-110SA2-4CB-04 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110SA2-4CB | 7 | 5 | 5 | Scheduled | 11/04/2024 | 17/04/2024
TO-24-FIN GIS-110SB1-2CB-03 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110SB1-2CB | 7 | 5 | 5 | Scheduled | 11/04/2024 | 17/04/2024
TO-24-FIN GIS-110SB2-4CB-05 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110SB2-4CB | 7 | 5 | 5 | Scheduled | 11/04/2024 | 17/04/2024
TO-24-CDU-WOO-1-03 | 220kV FEEDER - CORDUFF 220-WOODLAND 220-1 | 7 | 5 | 5 | Scheduled | 13/04/2024 | 19/04/2024
TO-24-220 kV B2 @ CKM GIS-01 | BUSBAR SECTION - CARRICKMINES GIS 220-CARRICKMINES GIS 220-220B2 | 9 | 7 | 7 | Scheduled | 15/04/2024 | 23/04/2024
TO-24-220 kV B4 @ CKM GIS-02 | BUSBAR SECTION - CARRICKMINES GIS 220-CARRICKMINES GIS 220-220B4 | 9 | 7 | 7 | Scheduled | 15/04/2024 | 23/04/2024
TO-24-CKM GIS-220SB2-4CB-02 | COUPLER/SECTIONALISING CB - CARRICKMINES GIS 220-CARRICKMINES GIS 220-22SB2-4CB | 9 | 7 | 7 | Scheduled | 15/04/2024 | 23/04/2024
TO-24-PRN-T4301-01 | TRANSFORMER - PORTAN 400-PORTAN 260-T4301 | 1 | 1 | 1 | Scheduled | 15/04/2024 | 15/04/2024
TO-24-PRN-WOO-1-04 | 400kV FEEDER - PORTAN 400-WOODLAND 400-1 | 1 | 1 | 1 | Scheduled | 15/04/2024 | 15/04/2024
TO-24-400 kV A1 @ WOO-01 | BUSBAR SECTION - WOODLAND 400-WOODLAND 400-400A1 | 1 | 1 | 1 | Scheduled | 15/04/2024 | 15/04/2024
TO-24-PRN-WOO-1-01 | 400kV FEEDER - PORTAN 400-WOODLAND 400-1 | 4 | 4 | 4 | Scheduled | 16/04/2024 | 19/04/2024
TO-24-110 kV A1 @ FIN GIS-01 | BUSBAR SECTION - FINGLAS GIS 110-FINGLAS GIS 110-110A1 | 2 | 2 | 2 | Scheduled | 18/04/2024 | 19/04/2024
TO-24-110 kV A2 @ FIN GIS-03 | BUSBAR SECTION - FINGLAS GIS 110-FINGLAS GIS 110-110A2 | 2 | 2 | 2 | Scheduled | 18/04/2024 | 19/04/2024
TO-24-110 kV A3 @ FIN GIS-01 | BUSBAR SECTION - FINGLAS GIS 110-FINGLAS GIS 110-110A3 | 2 | 2 | 2 | Scheduled | 18/04/2024 | 19/04/2024
TO-24-110 kV B1 @ FIN GIS-01 | BUSBAR SECTION - FINGLAS GIS 110-FINGLAS GIS 110-110B1 | 2 | 2 | 2 | Scheduled | 18/04/2024 | 19/04/2024
TO-24-110 kV B2 @ FIN GIS-03 | BUSBAR SECTION - FINGLAS GIS 110-FINGLAS GIS 110-110B2 | 2 | 2 | 2 | Scheduled | 18/04/2024 | 19/04/2024
TO-24-110 kV B3 @ FIN GIS-01 | BUSBAR SECTION - FINGLAS GIS 110-FINGLAS GIS 110-110B3 | 2 | 2 | 2 | Scheduled | 18/04/2024 | 19/04/2024
TO-24-FIN GIS-110K1-03 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110K1 | 2 | 2 | 2 | Scheduled | 18/04/2024 | 19/04/2024
TO-24-FIN GIS-110K2-04 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110K2 | 2 | 2 | 2 | Scheduled | 18/04/2024 | 19/04/2024
TO-24-FIN GIS-110SA1-2CB-04 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110SA1-2CB | 2 | 2 | 2 | Scheduled | 18/04/2024 | 19/04/2024
TO-24-FIN GIS-110SA1-3CB-02 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110SA1-3CB | 2 | 2 | 2 | Scheduled | 18/04/2024 | 19/04/2024
TO-24-FIN GIS-110SA2-4CB-05 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110SA2-4CB | 2 | 2 | 2 | Scheduled | 18/04/2024 | 19/04/2024
TO-24-FIN GIS-110SA3-5CB-02 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110SA3-5CB | 2 | 2 | 2 | Scheduled | 18/04/2024 | 19/04/2024
TO-24-FIN GIS-110SB1-2CB-04 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110SB1-2CB | 1 | 1 |  | Scheduled | 18/04/2024 | 18/04/2024
TO-24-FIN GIS-110SB1-3CB-02 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110SB1-3CB | 2 | 2 | 2 | Scheduled | 18/04/2024 | 19/04/2024
TO-24-FIN GIS-110SB2-4CB-06 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110SB2-4CB | 2 | 2 | 2 | Scheduled | 18/04/2024 | 19/04/2024
TO-24-FIN GIS-110SB3-5CB-02 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110SB3-5CB | 2 | 2 | 2 | Scheduled | 18/04/2024 | 19/04/2024
TO-24-FIN GIS-T2106-04 | TRANSFORMER - FINGLAS 220-FINGLAS GIS 110-T2106 | 2 | 2 | 2 | Scheduled | 18/04/2024 | 19/04/2024
TO-24-BAL-DRY-1-05 | 110kV FEEDER - BALTRASNA 110-DRYBRIDGE 110-1 | 150 | 105 | 105 | Scheduled | 22/04/2024 | 18/09/2024
TO-24-BNK-T122-02 | TSO CUSTOMER TRANSFORMER - BARNAKYLE 110-BARNAKYLE 20-T122 | 8 | 6 | 6 | Scheduled | 24/04/2024 | 01/05/2024
TO-24-220 kV A1 @ FIN-02 | BUSBAR SECTION - FINGLAS 220-FINGLAS 220-220A1 | 12 | 7 | 7 | Scheduled | 27/04/2024 | 08/05/2024
TO-24-220 kV B1 @ FIN-02 | BUSBAR SECTION - FINGLAS 220-FINGLAS 220-220B1 | 12 | 7 | 7 | Scheduled | 27/04/2024 | 08/05/2024
TO-24-FIN-HN-1-01 | 220kV FEEDER - FINGLAS 220-HUNTSTOWN 220-1 | 12 | 7 | 7 | Scheduled | 27/04/2024 | 08/05/2024
TO-24-HN-T2010/11-01 | GENERATOR TRANSFORMER - HUNTSTOWN 220-HUNTSTOWN G10/11-T2010/11 | 12 | 7 | 7 | Scheduled | 27/04/2024 | 08/05/2024
TO-24-MCE-T124-03 | TSO CUSTOMER TRANSFORMER - MACETOWN 110-MACETOWN 20-T124 | 10 | 7 | 7 | Proposed | 29/04/2024 | 08/05/2024
TO-24-BNK-CBT-2-02 | 110kV FEEDER - BARNAKYLE 110-CASTLEBAGOT 110-2 | 2 | 2 | 2 | Proposed | 30/04/2024 | 01/05/2024
TO-24-CBT-110K1-03 | COUPLER/SECTIONALISING CB - CASTLEBAGOT 110-CASTLEBAGOT 110-110K1 | 3 | 3 | 3 | Proposed | 30/04/2024 | 02/05/2024
TO-24-HN-T2010/11-02 | GENERATOR TRANSFORMER - HUNTSTOWN 220-HUNTSTOWN G10/11-T2010/11 | 3 | 2 | 2 | Scheduled | 06/05/2024 | 08/05/2024
TO-24-BLC-110K1-01 | COUPLER/SECTIONALISING CB - BELCAMP 110-BELCAMP 110-110K1 | 1 | 1 | 1 | Scheduled | 07/05/2024 | 07/05/2024
TO-24-CBT-MAY-1-05 | 220kV FEEDER - CASTLEBAGOT 220-MAYNOOTH 220-1 | 9 | 7 | 7 | Proposed | 07/05/2024 | 15/05/2024
TO-24-KTL-T131-01 | GENERATOR TRANSFORMER - KILTEEL 110-KILTEEL 33-T131 | 1 | 1 | 1 | Scheduled | 07/05/2024 | 07/05/2024
TO-24-BLC-110K3-01 | COUPLER/SECTIONALISING CB - BELCAMP 110-BELCAMP 110-110K3 | 1 | 1 | 1 | Scheduled | 08/05/2024 | 08/05/2024
TO-24-BLC-110SA1-3CB-01 | COUPLER/SECTIONALISING CB - BELCAMP 110-BELCAMP 110-110SA1-3CB | 1 | 1 | 1 | Scheduled | 09/05/2024 | 09/05/2024
TO-24-BLC-110SB1-3CB-01 | COUPLER/SECTIONALISING CB - BELCAMP 110-BELCAMP 110-110SB1-3CB | 1 | 1 | 1 | Scheduled | 10/05/2024 | 10/05/2024
TO-24-400 kV A1 @ DSN-02 | BUSBAR SECTION - DUNSTOWN 400-DUNSTOWN 400-400A1 | 12 | 10 | 10 | Proposed | 13/05/2024 | 24/05/2024
TO-24-400 kV A2 @ DSN-01 | BUSBAR SECTION - DUNSTOWN 400-DUNSTOWN 400-400A2 | 12 | 10 | 10 | Proposed | 13/05/2024 | 24/05/2024
TO-24-400 kV B1 @ DSN-02 | BUSBAR SECTION - DUNSTOWN 400-DUNSTOWN 400-400B1 | 12 | 10 | 10 | Proposed | 13/05/2024 | 24/05/2024
TO-24-400 kV B2 @ DSN-01 | BUSBAR SECTION - DUNSTOWN 400-DUNSTOWN 400-400B2 | 12 | 10 | 10 | Proposed | 13/05/2024 | 24/05/2024
TO-24-DSN-400K1-2-01 | COUPLER/SECTIONALISING CB - DUNSTOWN 400-DUNSTOWN 400-400K1-2 | 12 | 10 | 10 | Proposed | 13/05/2024 | 24/05/2024
TO-24-CLE-WOO-1-01 | 220kV FEEDER - CLONEE 220-WOODLAND 220-1 | 116 | 80 | 80 | Scheduled | 17/05/2024 | 09/09/2024
TO-24-KYT-WOO-1-01 | 220kV FEEDER - KELLYSTOWN 220-WOODLAND 220-1 | 116 | 80 | 80 | Scheduled | 17/05/2024 | 09/09/2024
TO-24-CBT-T2103-01 | TRANSFORMER - CASTLEBAGOT 220-CASTLEBAGOT 110-T2103 | 12 | 10 |  | Scheduled | 20/05/2024 | 31/05/2024
TO-24-FIN-FIN GIS-2-01 | 110kV FEEDER - FINGLAS 110-FINGLAS GIS 110-2 | 226 | 158 | 158 | Proposed | 20/05/2024 | 31/12/2024
TO-24-FIN-T2104-01 | TRANSFORMER - FINGLAS 220-FINGLAS 110-T2104 | 115 | 81 | 81 | Proposed | 20/05/2024 | 11/09/2024
TO-24-FIN-T2104-03 | TRANSFORMER - FINGLAS 220-FINGLAS 110-T2104 | 12 | 10 | 10 | Scheduled | 20/05/2024 | 31/05/2024
TO-24-DND-T122-01 | TSO CUSTOMER TRANSFORMER - DARNDALE 110-DARNDALE 20-T122 | 5 | 5 | 5 | Scheduled | 27/05/2024 | 31/05/2024
TO-24-CKM GIS-220SA1-2CB-01 | COUPLER/SECTIONALISING CB - CARRICKMINES GIS 220-CARRICKMINES GIS 220-22SA1-2CB | 2 | 2 | 2 | Proposed | 04/06/2024 | 05/06/2024
TO-24-CBT-220K1-01 | COUPLER/SECTIONALISING CB - CASTLEBAGOT 220-CASTLEBAGOT 220-220K1 | 4 | 4 | 4 | Proposed | 04/06/2024 | 07/06/2024
TO-24-PA-110SA1-04 | SECTIONALISING DISCONNECT - POLLAPHUCA 110-POLLAPHUCA 110-110SA1 | Unknown | Unknown | 9 | Planned | June | June
TO-24-PA-110SA2-04 | SECTIONALISING DISCONNECT - POLLAPHUCA 110-POLLAPHUCA 110-110SA2 | Unknown | Unknown | 9 | Planned | June | June
TO-24-PA-T101-04 | GENERATOR TRANSFORMER - POLLAPHUCA 110-POLLAPHUCA G1-T101 | Unknown | Unknown | 9 | Planned | June | June
TO-24-BAG-110K1-02 | COUPLER/SECTIONALISING CB - BARNAGEERAGH 110-BARNAGEERAGH 110-110K1 | 1 | 1 | 1 | Proposed | 05/06/2024 | 05/06/2024
TO-24-BNK-CBT-1-01 | 110kV FEEDER - BARNAKYLE 110-CASTLEBAGOT 110-1 | 2 | 2 | 2 | Proposed | 05/06/2024 | 06/06/2024
TO-24-CBT-CLU-1-01 | 110kV FEEDER - CASTLEBAGOT 110-CLUTTERLAND 110-1 | 3 | 3 | 3 | Proposed | 05/06/2024 | 07/06/2024
TO-24-CDU-110K1-3-01 | COUPLER/SECTIONALISING CB - CORDUFF 110-CORDUFF 110-110K1-3 | 1 | 1 | 1 | Proposed | 05/06/2024 | 05/06/2024
TO-24-CKG-110K2-02 | COUPLER/SECTIONALISING CB - CORKAGH 110-CORKAGH 110-110K2 | 1 | 1 | 1 | Proposed | 05/06/2024 | 05/06/2024
TO-24-RYB GIS-T103-01 | TSO CUSTOMER TRANSFORMER - RYEBROOK GIS 110-RYEBROOK 10-T103 | 2 | 2 | 2 | Proposed | 05/06/2024 | 06/06/2024
TO-24-CKM GIS-220SA1-3CB-01 | COUPLER/SECTIONALISING CB - CARRICKMINES GIS 220-CARRICKMINES GIS 220-22SA1-3CB | 2 | 2 | 2 | Proposed | 06/06/2024 | 07/06/2024
TO-24-CKG-T121-01 | TSO CUSTOMER TRANSFORMER - CORKAGH 110-CORKAGH 20-T121 | 2 | 2 | 2 | Proposed | 06/06/2024 | 07/06/2024
TO-24-CRU-T221-01 | TSO CUSTOMER TRANSFORMER - CRUISERATH 220-CRUISERATH 20-T221 | 2 | 2 | 2 | Proposed | 06/06/2024 | 07/06/2024
TO-24-CDU-220K1-3-01 | COUPLER/SECTIONALISING CB - CORDUFF 220-CORDUFF 220-220K1-3 | 1 | 1 | 1 | Proposed | 07/06/2024 | 07/06/2024
TO-24-RYB GIS-T104-01 | TSO CUSTOMER TRANSFORMER - RYEBROOK GIS 110-RYEBROOK 10-T104 | 1 | 1 | 1 | Proposed | 07/06/2024 | 07/06/2024
TO-24-CBT-110SA2-4CB-03 | COUPLER/SECTIONALISING CB - CASTLEBAGOT 110-CASTLEBAGOT 110-110SA2-4CB | 5 | 5 | 5 | Proposed | 10/06/2024 | 14/06/2024
TO-24-CBT-T2104-01 | TRANSFORMER - CASTLEBAGOT 220-CASTLEBAGOT 110-T2104 | Unknown | Unknown | 10 | Planned | June | June
TO-24-CDU-220K1-2-01 | COUPLER/SECTIONALISING CB - CORDUFF 220-CORDUFF 220-220K1-2 | 12 | 10 | 10 | Proposed | 10/06/2024 | 21/06/2024
TO-24-KTL-CAP1-01 | CAPACITOR/SVC/REACTOR - KILTEEL 110-KILTEEL 110-CAP1 | 5 | 5 | 5 | Proposed | 10/06/2024 | 14/06/2024
TO-24-MAY-T2103-01 | TRANSFORMER - MAYNOOTH 220-MAYNOOTH 110-T2103 | Unknown | Unknown |  | Planned | June | June
TO-24-PB-R2001-02 | CAPACITOR/SVC/REACTOR - POOLBEG 220-POOLBEG 220-R2001 | Unknown | Unknown | 5 | Planned | June | June
TO-24-WOO-220K1-2-01 | COUPLER/SECTIONALISING CB - WOODLAND 220-WOODLAND 220-220K1-2 | Unknown | Unknown | 15 | Planned | June | June
TO-24-BNK-T121-01 | TSO CUSTOMER TRANSFORMER - BARNAKYLE 110-BARNAKYLE 20-T121 | 2 | 2 | 2 | Proposed | 11/06/2024 | 12/06/2024
TO-24-BRT-220K2-01 | COUPLER/SECTIONALISING CB - BRACETOWN 220-BRACETOWN 220-220K2 | 1 | 1 | 1 | Proposed | 11/06/2024 | 11/06/2024
TO-24-CRU-220K1-01 | COUPLER/SECTIONALISING CB - CRUISERATH 220-CRUISERATH 220-220K1 | 1 | 1 | 1 | Proposed | 11/06/2024 | 11/06/2024
TO-24-RYB GIS-T106-01 | TSO CUSTOMER TRANSFORMER - RYEBROOK GIS 110-RYEBROOK 10-T106 | 2 | 2 | 2 | Proposed | 11/06/2024 | 12/06/2024
TO-24-CLG-T122-01 | TSO CUSTOMER TRANSFORMER - CLOGHRAN 110-CLOGHRAN 20-T122 | 2 | 2 | 2 | Proposed | 12/06/2024 | 13/06/2024
TO-24-CRU-220K2-03 | COUPLER/SECTIONALISING CB - CRUISERATH 220-CRUISERATH 220-220K2 | 1 | 1 | 1 | Proposed | 12/06/2024 | 12/06/2024
TO-24-CRU-SA1-2CB-03 | COUPLER/SECTIONALISING CB - CRUISERATH 220-CRUISERATH 220-220SA1-2CB | 1 | 1 | 1 | Proposed | 13/06/2024 | 13/06/2024
TO-24-DND-T121-02 | TSO CUSTOMER TRANSFORMER - DARNDALE 110-DARNDALE 20-T121 | 2 | 2 | 2 | Proposed | 13/06/2024 | 14/06/2024
TO-24-RYB GIS-T107-01 | TSO CUSTOMER TRANSFORMER - RYEBROOK GIS 110-RYEBROOK 10-T107 | 2 | 2 | 2 | Proposed | 13/06/2024 | 14/06/2024
TO-24-CLG-T124-01 | TSO CUSTOMER TRANSFORMER - CLOGHRAN 110-CLOGHRAN 20-T124 | 1 | 1 | 1 | Proposed | 14/06/2024 | 14/06/2024
TO-24-CRU-SB1-2CB-03 | COUPLER/SECTIONALISING CB - CRUISERATH 220-CRUISERATH 220-220SB1-2CB | 1 | 1 | 1 | Proposed | 14/06/2024 | 14/06/2024
TO-24-TH-T2001/2-01 | GENERATOR TRANSFORMER - TURLOUGH HILL 220-TURLOUGH HILL G1-T2001/2 | Unknown | Unknown | 0 | Planned | June | June
TO-24-TH-T2003/4-01 | GENERATOR TRANSFORMER - TURLOUGH HILL 220-TURLOUGH HILL G1-T2003/4 | Unknown | Unknown | 0 | Planned | June | June
TO-24-CKM GIS-DSN-1-01 | 220kV FEEDER - CARRICKMINES GIS 220-DUNSTOWN 220-1 | 10 | 8 | 8 | Proposed | 17/06/2024 | 26/06/2024
TO-24-CBT-110SB1-2CB-03 | COUPLER/SECTIONALISING CB - CASTLEBAGOT 110-CASTLEBAGOT 110-110SB1-2CB | 5 | 5 | 5 | Proposed | 17/06/2024 | 21/06/2024
TO-24-CLE-220K1-01 | COUPLER/SECTIONALISING CB - CLONEE 220-CLONEE 220-220K1 | 5 | 5 | 5 | Proposed | 17/06/2024 | 21/06/2024
TO-24-CKM GIS-220SA2-4CB-02 | COUPLER/SECTIONALISING CB - CARRICKMINES GIS 220-CARRICKMINES GIS 220-22SA2-4CB | 2 | 2 | 2 | Proposed | 18/06/2024 | 19/06/2024
TO-24-CRU-CDU-1-02 | 220kV FEEDER - CRUISERATH 220-CORDUFF 220-1 | 4 | 4 | 4 | Proposed | 18/06/2024 | 21/06/2024
TO-24-MAY-TH-1-01 | 220kV FEEDER - MAYNOOTH 220-TURLOUGH HILL 220-1 | 4 | 4 | 4 | Proposed | 18/06/2024 | 21/06/2024
TO-24-RYB GIS-T109-02 | TSO CUSTOMER TRANSFORMER - RYEBROOK GIS 110-RYEBROOK 10-T109 | 1 | 1 | 1 | Proposed | 18/06/2024 | 18/06/2024
TO-24-RYB GIS-T108-02 | TSO CUSTOMER TRANSFORMER - RYEBROOK GIS 110-RYEBROOK 10-T108 | 2 | 2 | 2 | Proposed | 19/06/2024 | 20/06/2024
TO-24-BLU-CDU-1-02 | 110kV FEEDER - BLUNDELSTOWN 110-CORDUFF 110-1 | Unknown | Unknown | 25 | Planned | June | July
TO-24-CBT-110SB2-4CB-03 | COUPLER/SECTIONALISING CB - CASTLEBAGOT 110-CASTLEBAGOT 110-110SB2-4CB | 5 | 5 | 5 | Proposed | 24/06/2024 | 28/06/2024
TO-24-CLG-T126-02 | TSO CUSTOMER TRANSFORMER - CLOGHRAN 110-CLOGHRAN 20-T126 | 5 | 5 | 5 | Proposed | 24/06/2024 | 28/06/2024
TO-24-CLU-110K1-01 | COUPLER/SECTIONALISING CB - CLUTTERLAND 110-CLUTTERLAND 110-110K1 | 1 | 1 | 1 | Proposed | 25/06/2024 | 25/06/2024
TO-24-CKG-T122-01 | TSO CUSTOMER TRANSFORMER - CORKAGH 110-CORKAGH 20-T122 | 2 | 2 | 2 | Proposed | 25/06/2024 | 26/06/2024
TO-24-CLU-110K2-01 | COUPLER/SECTIONALISING CB - CLUTTERLAND 110-CLUTTERLAND 110-110K2 | 1 | 1 | 1 | Proposed | 26/06/2024 | 26/06/2024
TO-24-CLU-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - CLUTTERLAND 110-CLUTTERLAND 110-110SA1-2CB | 1 | 1 | 1 | Proposed | 27/06/2024 | 27/06/2024
TO-24-CKG-T123-01 | TSO CUSTOMER TRANSFORMER - CORKAGH 110-CORKAGH 20-T123 | 2 | 2 | 2 | Proposed | 27/06/2024 | 28/06/2024
TO-24-CLU-T121-01 | TSO CUSTOMER TRANSFORMER - CLUTTERLAND 110-CLUTTERLAND 20-T121 | 1 | 1 | 1 | Proposed | 28/06/2024 | 28/06/2024
TO-24-WOO-T4201-01 | TRANSFORMER - WOODLAND 400-WOODLAND 220-T4201 | Unknown | Unknown |  | Planned | July | July
TO-24-220 kV A2 @ TH-02 | BUSBAR SECTION - TURLOUGH HILL 220-TURLOUGH HILL 220-220A2 | 1 | 1 | 1 | Proposed | 11/07/2024 | 11/07/2024
TO-24-TH-T2003/4-04 | GENERATOR TRANSFORMER - TURLOUGH HILL 220-TURLOUGH HILL G1-T2003/4 | 1 | 1 | 1 | Proposed | 11/07/2024 | 11/07/2024
TO-24-NW-T2004/5-01 | GENERATOR TRANSFORMER - NORTH WALL 220-NORTH WALL G4/5-T2004/5 | Unknown | Unknown | 2 | Planned | July | July
TO-24-WOO-T4204-01 | TRANSFORMER - WOODLAND 400-WOODLAND 220-T4204 | Unknown | Unknown | 20 | Planned | July | August
TO-24-110 kV B4 @ FIN GIS-01 | BUSBAR SECTION - FINGLAS GIS 110-FINGLAS GIS 110-110B4 | 3 | 3 |  | Proposed | 12/08/2024 | 14/08/2024
TO-24-FIN GIS-110SB2-4CB-01 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110SB2-4CB | 3 | 3 |  | Proposed | 12/08/2024 | 14/08/2024
TO-24-FIN GIS-110SB4-6CB-01 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110SB4-6CB | 3 | 3 |  | Proposed | 12/08/2024 | 14/08/2024
TO-24-ISH-T2001-01 | GENERATOR TRANSFORMER - IRISHTOWN 220-IRISHTOWN G1-T2001 | Unknown | Unknown | 1 | Planned | August | August
TO-24-220 kV A2 @ FIN-01 | BUSBAR SECTION - FINGLAS 220-FINGLAS 220-220A2 | 5 | 5 |  | Proposed | 02/09/2024 | 06/09/2024
TO-24-220 kV B2 @ FIN-01 | BUSBAR SECTION - FINGLAS 220-FINGLAS 220-220B2 | 5 | 5 |  | Proposed | 02/09/2024 | 06/09/2024
TO-24-FIN-220K2-01 | COUPLER/SECTIONALISING CB - FINGLAS 220-FINGLAS 220-220K2 | 5 | 5 |  | Proposed | 02/09/2024 | 06/09/2024
TO-24-FIN-220SB1-2CB-01 | COUPLER/SECTIONALISING CB - FINGLAS 220-FINGLAS 220-220SB1-2CB | 5 | 5 |  | Proposed | 02/09/2024 | 06/09/2024
TO-24-110 kV A4 @ FIN GIS-01 | BUSBAR SECTION - FINGLAS GIS 110-FINGLAS GIS 110-110A4 | 5 | 5 |  | Proposed | 02/09/2024 | 06/09/2024
TO-24-110 kV B4 @ FIN GIS-02 | BUSBAR SECTION - FINGLAS GIS 110-FINGLAS GIS 110-110B4 | 5 | 5 |  | Proposed | 02/09/2024 | 06/09/2024
TO-24-FIN GIS-110SA2-4CB-01 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110SA2-4CB | 5 | 5 |  | Proposed | 02/09/2024 | 06/09/2024
TO-24-FIN GIS-110SA4-6CB-01 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110SA4-6CB | 5 | 5 |  | Proposed | 02/09/2024 | 06/09/2024
TO-24-FIN GIS-110SB2-4CB-02 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110SB2-4CB | 5 | 5 |  | Proposed | 02/09/2024 | 06/09/2024
TO-24-FIN GIS-110SB4-6CB-02 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110SB4-6CB | 5 | 5 |  | Proposed | 02/09/2024 | 06/09/2024
TO-24-SHL-D2/CB2-04 | COUPLER/SECTIONALISING CB - SHELLYBANKS 220-SHELLYBANKS 220-D2/CB2 | Unknown | Unknown | 5 | Planned | September | September
TO-24-SHL-T2015-01 | GENERATOR TRANSFORMER - SHELLYBANKS 220-SHELLYBANKS G5-T2015 | Unknown | Unknown | 5 | Planned | September | September
TO-24-220 kV A2 @ FIN-02 | BUSBAR SECTION - FINGLAS 220-FINGLAS 220-220A2 | 2 | 2 |  | Proposed | 10/09/2024 | 11/09/2024
TO-24-FIN-220K2-02 | COUPLER/SECTIONALISING CB - FINGLAS 220-FINGLAS 220-220K2 | 2 | 2 |  | Proposed | 10/09/2024 | 11/09/2024
TO-24-FIN-NW-1-03 | 220kV FEEDER - FINGLAS 220-NORTH WALL 220-1 | 2 | 2 |  | Proposed | 10/09/2024 | 11/09/2024
TO-24-INC-MAY-2-05 | 220kV FEEDER - INCHICORE 220-MAYNOOTH 220-2 | 64 | 45 | 45 | Proposed | 10/09/2024 | 12/11/2024
TO-24-CLG-T121-01 | TSO CUSTOMER TRANSFORMER - CLOGHRAN 110-CLOGHRAN 20-T121 | 5 | 5 | 5 | Proposed | 23/09/2024 | 27/09/2024
TO-24-PB-R2001-03 | CAPACITOR/SVC/REACTOR - POOLBEG 220-POOLBEG 220-R2001 | Unknown | Unknown |  | Planned | September | September
TO-24-CLG-T123-01 | TSO CUSTOMER TRANSFORMER - CLOGHRAN 110-CLOGHRAN 20-T123 | 5 | 5 | 5 | Proposed | 30/09/2024 | 04/10/2024
TO-24-CDU-HN-1-01 | 220kV FEEDER - CORDUFF 220-HUNTSTOWN 220-1 | Unknown | Unknown | 5 | Planned | October | October
TO-24-HN-T2002-01 | GENERATOR TRANSFORMER - HUNTSTOWN 220-HUNTSTOWN G2-T2002 | Unknown | Unknown | 5 | Planned | October | October
TO-24-SHL-T2016-01 | GENERATOR TRANSFORMER - SHELLYBANKS 220-SHELLYBANKS G6-T2016 | Unknown | Unknown | 5 | Planned | October | October
TO-24-CDU-FIN-2-01 | 220kV FEEDER - CORDUFF 220-FINGLAS 220-2 | Unknown | Unknown |  | Planned | October | November
TO-24-GOR-MAY-1-01 | 220kV FEEDER - GORMAN 220-MAYNOOTH 220-1 | Unknown | Unknown |  | Planned | November | November
TO-24-ARK-CKM GIS-1-01 | 220kV FEEDER - ARKLOW 220-CARRICKMINES GIS 220-1 | Unknown | Unknown |  | Planned | November | December
TO-24-PB-R2001-04 | CAPACITOR/SVC/REACTOR - POOLBEG 220-POOLBEG 220-R2001 | Unknown | Unknown |  | Planned | December | December

## GEN_Cork
Outage ID | Feeder ID | Calendar Day Duration | Working Day Duration | Work Days | Outage Status | Start | Finish
TO-24-KRA-220SA2-4CB-01 | COUPLER/SECTIONALISING CB - KNOCKRAHA 220-KNOCKRAHA 220-220SA2-4CB | 1 | 1 | 1 | Scheduled | 07/02/2024 | 07/02/2024
TO-24-KRA-220K4-01 | COUPLER/SECTIONALISING CB - KNOCKRAHA 220-KNOCKRAHA 220-220K4 | 1 | 1 | 1 | Scheduled | 09/02/2024 | 09/02/2024
TO-24-COW-WHI-1-03 | 110kV FEEDER - COW CROSS 110-WHITEGATE 110-1 | 5 | 5 | 5 | Scheduled | 12/02/2024 | 16/02/2024
TO-24-LYT-T132-01 | GENERATOR TRANSFORMER - LYSAGHTSTOWN 110-LYSAGHTSTOWN 33-T132 | 1 | 1 | 1 | Scheduled | 19/02/2024 | 19/02/2024
TO-24-RAF-TBG-2-02 | 110kV FEEDER - RAFFEEN 110-TRABEG 110-2 | 5 | 5 | 5 | Scheduled | 19/02/2024 | 23/02/2024
TO-24-KRA-110K1-2-01 | COUPLER/SECTIONALISING CB - KNOCKRAHA 110-KNOCKRAHA 110-110K1-2 | 1 | 1 | 1 | Scheduled | 20/02/2024 | 20/02/2024
TO-24-AD-LPT-1-01 | 220kV FEEDER - AGHADA 220-LONG POINT 220-1 | 78 | 52 | 52 | Scheduled | 26/02/2024 | 13/05/2024
TO-24-LPT-T2002-02 | GENERATOR TRANSFORMER - LONG POINT 220-LONG POINT G1-T2002 | 78 | 52 | 52 | Scheduled | 26/02/2024 | 13/05/2024
TO-24-110 kV A1 @ RAF-02 | BUSBAR SECTION - RAFFEEN 110-RAFFEEN 110-110A1 | 5 | 5 | 5 | Scheduled | 26/02/2024 | 01/03/2024
TO-24-110 kV B1 @ RAF-02 | BUSBAR SECTION - RAFFEEN 110-RAFFEEN 110-110B1 | 5 | 5 | 5 | Scheduled | 26/02/2024 | 01/03/2024
TO-24-220 kV A1 @ RAF-02 | BUSBAR SECTION - RAFFEEN 220-RAFFEEN 220-220A1 | 5 | 5 | 5 | Scheduled | 26/02/2024 | 01/03/2024
TO-24-220 kV B1 @ RAF-02 | BUSBAR SECTION - RAFFEEN 220-RAFFEEN 220-220B1 | 5 | 5 | 5 | Scheduled | 26/02/2024 | 01/03/2024
TO-24-220 kV A2 @ AD-04 | BUSBAR SECTION - AGHADA 220-AGHADA 220-220A2 | 12 | 10 | 10 | Scheduled | 04/03/2024 | 15/03/2024
TO-24-220 kV B2 @ AD-04 | BUSBAR SECTION - AGHADA 220-AGHADA 220-220B2 | 12 | 10 | 10 | Scheduled | 04/03/2024 | 15/03/2024
TO-24-AD-SA1-2CB-06 | COUPLER/SECTIONALISING CB - AGHADA 220-AGHADA 220-220SA1-2CB | 12 | 10 | 10 | Scheduled | 04/03/2024 | 15/03/2024
TO-24-AD-SB1-2CB-06 | COUPLER/SECTIONALISING CB - AGHADA 220-AGHADA 220-220SB1-2CB | 12 | 10 | 10 | Scheduled | 04/03/2024 | 15/03/2024
TO-24-AD-KRA-2-01 | 220kV FEEDER - AGHADA 220-KNOCKRAHA 220-2 | 12 | 10 |  | Scheduled | 04/03/2024 | 15/03/2024
TO-24-220 kV A1 @ KRA-02 | BUSBAR SECTION - KNOCKRAHA 220-KNOCKRAHA 220-220A1 | 12 | 10 | 10 | Scheduled | 04/03/2024 | 15/03/2024
TO-24-220 kV B1 @ KRA-02 | BUSBAR SECTION - KNOCKRAHA 220-KNOCKRAHA 220-220B1 | 12 | 10 | 10 | Scheduled | 04/03/2024 | 15/03/2024
TO-24-KRA-220K1-03 | COUPLER/SECTIONALISING CB - KNOCKRAHA 220-KNOCKRAHA 220-220K1 | 12 | 10 | 10 | Scheduled | 04/03/2024 | 15/03/2024
TO-24-KRA-220SA1-2CB-03 | COUPLER/SECTIONALISING CB - KNOCKRAHA 220-KNOCKRAHA 220-220SA1-2CB | 12 | 10 | 10 | Scheduled | 04/03/2024 | 15/03/2024
TO-24-KRA-220SB1-2CB-03 | COUPLER/SECTIONALISING CB - KNOCKRAHA 220-KNOCKRAHA 220-220SB1-2CB | 12 | 10 | 10 | Scheduled | 04/03/2024 | 15/03/2024
TO-24-RAF-RSY-1-01 | 110kV FEEDER - RAFFEEN 110-RINGASKIDDY 110-1 | 12 | 10 |  | Reference | 04/03/2024 | 15/03/2024
TO-24-KRA-220SA2-4CB-02 | COUPLER/SECTIONALISING CB - KNOCKRAHA 220-KNOCKRAHA 220-220SA2-4CB | 73 | 49 |  | Scheduled | 05/03/2024 | 16/05/2024
TO-24-KRA-220SB2-4CB-01 | COUPLER/SECTIONALISING CB - KNOCKRAHA 220-KNOCKRAHA 220-220SB2-4CB | 73 | 49 |  | Scheduled | 05/03/2024 | 16/05/2024
TO-24-220 kV A1 @ AD-03 | BUSBAR SECTION - AGHADA 220-AGHADA 220-220A1 | 5 | 5 | 5 | Scheduled | 11/03/2024 | 15/03/2024
TO-24-220 kV B1 @ AD-02 | BUSBAR SECTION - AGHADA 220-AGHADA 220-220B1 | 5 | 5 | 5 | Scheduled | 11/03/2024 | 15/03/2024
TO-24-AD-220K1-04 | COUPLER/SECTIONALISING CB - AGHADA 220-AGHADA 220-220K1 | 5 | 5 | 5 | Scheduled | 11/03/2024 | 15/03/2024
TO-24-AD-SA1-2CB-03 | COUPLER/SECTIONALISING CB - AGHADA 220-AGHADA 220-220SA1-2CB | 5 | 5 | 5 | Scheduled | 11/03/2024 | 15/03/2024
TO-24-AD-SB1-2CB-03 | COUPLER/SECTIONALISING CB - AGHADA 220-AGHADA 220-220SB1-2CB | 5 | 5 | 5 | Scheduled | 11/03/2024 | 15/03/2024
TO-24-LPT-T2002-01 | GENERATOR TRANSFORMER - LONG POINT 220-LONG POINT G1-T2002 | 5 | 5 | 5 | Scheduled | 11/03/2024 | 15/03/2024
TO-24-BAN-110SA1-01 | SECTIONALISING DISCONNECT - BANDON 110-BANDON 110-110SA1 | 15 | 10 | 10 | Scheduled | 14/03/2024 | 28/03/2024
TO-24-BAN-110SA2-02 | SECTIONALISING DISCONNECT - BANDON 110-BANDON 110-110SA2 | 15 | 10 | 10 | Scheduled | 14/03/2024 | 28/03/2024
TO-24-BAN-BRI-1-01 | 110kV FEEDER - BANDON 110-BRINNY 110-1 | 15 | 10 | 10 | Scheduled | 14/03/2024 | 28/03/2024
TO-24-BAN-CAP1-02 | CAPACITOR/SVC/REACTOR - BANDON 110-BANDON 110-CAP1 | 15 | 10 | 10 | Scheduled | 14/03/2024 | 28/03/2024
TO-24-BAN-DMY-1-02 | 110kV FEEDER - BANDON 110-DUNMANWAY 110-1 | 15 | 10 | 10 | Scheduled | 14/03/2024 | 28/03/2024
TO-24-BAN-T101-01 | DISTRIBUTION TRANSFORMER - BANDON 110-BANDON 10-T101 | 15 | 10 | 10 | Reference | 14/03/2024 | 28/03/2024
TO-24-BAN-T141-01 | DISTRIBUTION TRANSFORMER - BANDON 110-BANDON 38-T141 | 15 | 10 | 10 | Reference | 14/03/2024 | 28/03/2024
TO-24-BRI-T101-02 | TSO CUSTOMER TRANSFORMER - BRINNY 110-BRINNY 10-T101 | 15 | 10 | 10 | Scheduled | 14/03/2024 | 28/03/2024
TO-24-220 kV A1 @ AD-02 | BUSBAR SECTION - AGHADA 220-AGHADA 220-220A1 | 16 | 10 | 10 | Scheduled | 19/03/2024 | 03/04/2024
TO-24-220 kV A2 @ AD-01 | BUSBAR SECTION - AGHADA 220-AGHADA 220-220A2 | 16 | 10 | 10 | Scheduled | 19/03/2024 | 03/04/2024
TO-24-220 kV B1 @ AD-01 | BUSBAR SECTION - AGHADA 220-AGHADA 220-220B1 | 16 | 10 | 10 | Scheduled | 19/03/2024 | 03/04/2024
TO-24-220 kV B2 @ AD-01 | BUSBAR SECTION - AGHADA 220-AGHADA 220-220B2 | 16 | 10 | 10 | Scheduled | 19/03/2024 | 03/04/2024
TO-24-AD-220K1-03 | COUPLER/SECTIONALISING CB - AGHADA 220-AGHADA 220-220K1 | 16 | 10 | 10 | Scheduled | 19/03/2024 | 03/04/2024
TO-24-AD-SA1-2CB-01 | COUPLER/SECTIONALISING CB - AGHADA 220-AGHADA 220-220SA1-2CB | 16 | 10 | 10 | Scheduled | 19/03/2024 | 03/04/2024
TO-24-AD-SB1-2CB-01 | COUPLER/SECTIONALISING CB - AGHADA 220-AGHADA 220-220SB1-2CB | 16 | 10 | 10 | Scheduled | 19/03/2024 | 03/04/2024
TO-24-AD-KRA-1-01 | 220kV FEEDER - AGHADA 220-KNOCKRAHA 220-1 | 16 | 10 |  | Scheduled | 19/03/2024 | 03/04/2024
TO-24-AD-T2102-01 | TRANSFORMER - AGHADA 220-AGHADA 110-T2102 | 16 | 10 | 10 | Scheduled | 19/03/2024 | 03/04/2024
TO-24-CGG-DMY-1-01 | 110kV FEEDER - CARRIGDANGAN 110-DUNMANWAY 110-1 | 7 | 5 | 5 | Scheduled | 19/03/2024 | 25/03/2024
TO-24-CGG-T131-01 | GENERATOR TRANSFORMER - CARRIGDANGAN 110-CARRIGDANGAN 33-T131 | 7 | 5 | 5 | Scheduled | 19/03/2024 | 25/03/2024
TO-24-110 kV A2 @ CLA-01 | BUSBAR SECTION - CLASHAVOON 110-CLASHAVOON 110-110A2 | 10 | 8 | 8 | Scheduled | 19/03/2024 | 28/03/2024
TO-24-110 kV B2 @ CLA-01 | BUSBAR SECTION - CLASHAVOON 110-CLASHAVOON 110-110B2 | 10 | 8 | 8 | Scheduled | 19/03/2024 | 28/03/2024
TO-24-CLA-MAC-2-03 | 110kV FEEDER - CLASHAVOON 110-MACROOM 110-2 | 10 | 8 | 8 | Scheduled | 19/03/2024 | 28/03/2024
TO-24-220 kV A2 @ KRA-02 | BUSBAR SECTION - KNOCKRAHA 220-KNOCKRAHA 220-220A2 | 16 | 10 | 10 | Scheduled | 19/03/2024 | 03/04/2024
TO-24-220 kV B2 @ KRA-02 | BUSBAR SECTION - KNOCKRAHA 220-KNOCKRAHA 220-220B2 | 16 | 10 | 10 | Scheduled | 19/03/2024 | 03/04/2024
TO-24-KRA-220SA1-2CB-02 | COUPLER/SECTIONALISING CB - KNOCKRAHA 220-KNOCKRAHA 220-220SA1-2CB | 16 | 10 | 10 | Scheduled | 19/03/2024 | 03/04/2024
TO-24-KRA-220SB1-2CB-02 | COUPLER/SECTIONALISING CB - KNOCKRAHA 220-KNOCKRAHA 220-220SB1-2CB | 16 | 10 | 10 | Scheduled | 19/03/2024 | 03/04/2024
TO-24-CUL-KRA-1-01 | 220kV FEEDER - CULLENAGH 220-KNOCKRAHA 220-1 | 43 | 30 |  | Scheduled | 04/04/2024 | 16/05/2024
TO-24-220 kV A2 @ KRA-01 | BUSBAR SECTION - KNOCKRAHA 220-KNOCKRAHA 220-220A2 | 43 | 30 | 30 | Scheduled | 04/04/2024 | 16/05/2024
TO-24-220 kV B2 @ KRA-01 | BUSBAR SECTION - KNOCKRAHA 220-KNOCKRAHA 220-220B2 | 43 | 30 | 30 | Scheduled | 04/04/2024 | 16/05/2024
TO-24-KRA-220SA1-2CB-01 | COUPLER/SECTIONALISING CB - KNOCKRAHA 220-KNOCKRAHA 220-220SA1-2CB | 43 | 30 | 30 | Scheduled | 04/04/2024 | 16/05/2024
TO-24-KRA-220SB1-2CB-01 | COUPLER/SECTIONALISING CB - KNOCKRAHA 220-KNOCKRAHA 220-220SB1-2CB | 43 | 30 | 30 | Scheduled | 04/04/2024 | 16/05/2024
TO-24-KRA-RAF-1-01 | 220kV FEEDER - KNOCKRAHA 220-RAFFEEN 220-1 | 43 | 30 |  | Scheduled | 04/04/2024 | 16/05/2024
TO-24-CRO-KBY-1-01 | 110kV FEEDER - COOLROE 110-KILBARRY 110-1 | 5 | 5 |  | Scheduled | 08/04/2024 | 12/04/2024
TO-24-220 kV A1 @ RAF-03 | BUSBAR SECTION - RAFFEEN 220-RAFFEEN 220-220A1 | 5 | 5 | 5 | Scheduled | 08/04/2024 | 12/04/2024
TO-24-220 kV B1 @ RAF-03 | BUSBAR SECTION - RAFFEEN 220-RAFFEEN 220-220B1 | 5 | 5 | 5 | Scheduled | 08/04/2024 | 12/04/2024
TO-24-BGH-T132-02 | GENERATOR TRANSFORMER - BOGGERAGH 110-BOGGERAGH 33-T132 | 2 | 2 | 2 | Scheduled | 15/04/2024 | 16/04/2024
TO-24-CRO-110SA2-01 | SECTIONALISING DISCONNECT - COOLROE 110-COOLROE 110-110SA2 | 5 | 5 | 5 | Scheduled | 15/04/2024 | 19/04/2024
TO-24-CRO-IA-1-01 | 110kV FEEDER - COOLROE 110-INNISCARRA 110-1 | 5 | 5 | 5 | Scheduled | 15/04/2024 | 19/04/2024
TO-24-BGH-T121-02 | GENERATOR TRANSFORMER - BOGGERAGH 110-BOGGERAGH 20-T121 | 1 | 1 | 1 | Scheduled | 17/04/2024 | 17/04/2024
TO-24-AD-ST101-01 | GENERATOR TRANSFORMER - AGHADA 110-AGHADA 10-ST101 | 5 | 5 | 5 | Scheduled | 22/04/2024 | 26/04/2024
TO-24-CD-KBY-1-01 | 110kV FEEDER - CARRIGADROHID 110-KILBARRY 110-1 | 12 | 10 | 10 | Scheduled | 22/04/2024 | 03/05/2024
TO-24-220 kV A1 @ AD-04 | BUSBAR SECTION - AGHADA 220-AGHADA 220-220A1 | 5 | 5 | 5 | Scheduled | 29/04/2024 | 03/05/2024
TO-24-220 kV A2 @ AD-07 | BUSBAR SECTION - AGHADA 220-AGHADA 220-220A2 | 5 | 5 | 5 | Scheduled | 29/04/2024 | 03/05/2024
TO-24-AD-SA1-2CB-04 | COUPLER/SECTIONALISING CB - AGHADA 220-AGHADA 220-220SA1-2CB | 5 | 5 | 5 | Scheduled | 29/04/2024 | 03/05/2024
TO-24-CRO-IA-1-04 | 110kV FEEDER - COOLROE 110-INNISCARRA 110-1 | 1 | 1 | 1 | Proposed | 30/04/2024 | 30/04/2024
TO-24-110 kV A1 @ IA-02 | BUSBAR SECTION - INNISCARRA 110-INNISCARRA 110-110A1 | 1 | 1 | 1 | Proposed | 30/04/2024 | 30/04/2024
TO-24-IA-MAC-1-04 | 110kV FEEDER - INNISCARRA 110-MACROOM 110-1 | 1 | 1 | 1 | Proposed | 30/04/2024 | 30/04/2024
TO-24-IA-T101-04 | GENERATOR TRANSFORMER - INNISCARRA 110-INNISCARRA G1-T101 | 1 | 1 | 1 | Proposed | 30/04/2024 | 30/04/2024
TO-24-AD-220K1-02 | COUPLER/SECTIONALISING CB - AGHADA 220-AGHADA 220-220K1 | 1 | 1 | 1 | Scheduled | 08/05/2024 | 08/05/2024
TO-24-220 kV A1 @ AD-01 | BUSBAR SECTION - AGHADA 220-AGHADA 220-220A1 | 1 | 1 | 1 | Proposed | 09/05/2024 | 09/05/2024
TO-24-220 kV A2 @ AD-06 | BUSBAR SECTION - AGHADA 220-AGHADA 220-220A2 | 1 | 1 | 1 | Proposed | 09/05/2024 | 09/05/2024
TO-24-220 kV B1 @ AD-03 | BUSBAR SECTION - AGHADA 220-AGHADA 220-220B1 | 1 | 1 | 1 | Proposed | 09/05/2024 | 09/05/2024
TO-24-220 kV B2 @ AD-05 | BUSBAR SECTION - AGHADA 220-AGHADA 220-220B2 | 1 | 1 | 1 | Proposed | 09/05/2024 | 09/05/2024
TO-24-AD-T2011/12-03 | GENERATOR TRANSFORMER - AGHADA 220-AGHADA G11/12-T2011/12 | 1 | 1 | 1 | Proposed | 09/05/2024 | 09/05/2024
TO-24-IA-MAC-1-03 | 110kV FEEDER - INNISCARRA 110-MACROOM 110-1 | 5 | 5 | 5 | Proposed | 13/05/2024 | 17/05/2024
TO-24-IA-T101-02 | GENERATOR TRANSFORMER - INNISCARRA 110-INNISCARRA G1-T101 | 10 | 8 | 8 | Proposed | 14/05/2024 | 23/05/2024
TO-24-110 kV A2 @ RAF-01 | BUSBAR SECTION - RAFFEEN 110-RAFFEEN 110-110A2 | 5 | 5 | 5 | Proposed | 20/05/2024 | 24/05/2024
TO-24-110 kV B2 @ RAF-01 | BUSBAR SECTION - RAFFEEN 110-RAFFEEN 110-110B2 | 5 | 5 | 5 | Proposed | 20/05/2024 | 24/05/2024
TO-24-RAF-CAP2-01 | CAPACITOR/SVC/REACTOR - RAFFEEN 110-RAFFEEN 110-CAP2 | 5 | 5 | 5 | Proposed | 20/05/2024 | 24/05/2024
TO-24-COW-110SA1-03 | SECTIONALISING DISCONNECT - COW CROSS 110-COW CROSS 110-110SA1 | 15 | 10 | 10 | Proposed | 27/05/2024 | 10/06/2024
TO-24-COW-OLD-2-02 | 110kV FEEDER - COW CROSS 110-OLDCOURT 110-2 | 15 | 10 | 10 | Reference (Proposed) | 27/05/2024 | 10/06/2024
TO-24-COW-RAF-1-03 | 110kV FEEDER - COW CROSS 110-RAFFEEN 110-1 | 15 | 10 | 10 | Proposed | 27/05/2024 | 10/06/2024
TO-24-KBY-MR-1-02 | 110kV FEEDER - KILBARRY 110-MARINA 110-1 | 107 | 75 | 75 | Proposed | 27/05/2024 | 10/09/2024
TO-24-KBY-MR-2-02 | 110kV FEEDER - KILBARRY 110-MARINA 110-2 | 107 | 75 | 75 | Proposed | 27/05/2024 | 10/09/2024
TO-24-KBY-MR-1-01 | 110kV FEEDER - KILBARRY 110-MARINA 110-1 | 10 | 7 |  | Scheduled | 28/05/2024 | 06/06/2024
TO-24-KBY-MR-2-01 | 110kV FEEDER - KILBARRY 110-MARINA 110-2 | 4 | 4 | 4 | Scheduled | 28/05/2024 | 31/05/2024
TO-24-CHA-MAL-1-01 | 110kV FEEDER - CHARLEVILLE 110-MALLOW 110-1 | Unknown | Unknown | 10 | Planned | June | June
TO-24-COW-110SA2-01 | SECTIONALISING DISCONNECT - COW CROSS 110-COW CROSS 110-110SA2 | Unknown | Unknown | 12 | Planned | June | June
TO-24-MID-110SA2-01 | SECTIONALISING DISCONNECT - MIDLETON 110-MIDLETON 110-110SA2 | Unknown | Unknown | 5 | Planned | July | July
TO-24-MID-T102-01 | DISTRIBUTION TRANSFORMER - MIDLETON 110-MIDLETON 10-T102 | Unknown | Unknown | 5 | Reference (Planned) | July | July
TO-24-MID-WHI-1-01 | 110kV FEEDER - MIDLETON 110-WHITEGATE 110-1 | Unknown | Unknown |  | Planned | July | July
TO-24-BAR-T141-02 | DISTRIBUTION TRANSFORMER - BARRYMORE 110-BARRYMORE 38-T141 | Unknown | Unknown | 10 | Reference (Planned) | July | August
TO-24-BAR,T-BAR-1-02 | 110kV FEEDER - BARRYMORE tee-BARRYMORE 110-1 | Unknown | Unknown | 10 | Planned | July | August
TO-24-BAR,T-CAH-1-01 | 110kV FEEDER - BARRYMORE tee-CAHIR 110-1 | Unknown | Unknown | 10 | Planned | July | August
TO-24-BAR,T-KRA-1-01 | 110kV FEEDER - BARRYMORE tee-KNOCKRAHA 110-1 | Unknown | Unknown |  | Planned | July | August
TO-24-110 kV A1 @ KRA-01 | BUSBAR SECTION - KNOCKRAHA 110-KNOCKRAHA 110-110A1 | Unknown | Unknown | 10 | Planned | July | August
TO-24-110 kV B1 @ KRA-01 | BUSBAR SECTION - KNOCKRAHA 110-KNOCKRAHA 110-110B1 | Unknown | Unknown | 10 | Planned | July | August
TO-24-WHI-CKB-T101-01 | TSO CUSTOMER TRANSFORMER - WHITEGATE 110-WHITEGATE 10-CKB-T101 | 5 | 5 | 5 | Proposed | 22/07/2024 | 26/07/2024
TO-24-CRO-T122-03 | DISTRIBUTION TRANSFORMER - COOLROE 110-COOLROE 20-T122 | 2 | 2 | 2 | Reference (Proposed) | 23/07/2024 | 24/07/2024
TO-24-WHI-CKB-T102-01 | TSO CUSTOMER TRANSFORMER - WHITEGATE 110-WHITEGATE 10-CKB-T102 | 5 | 5 | 5 | Proposed | 29/07/2024 | 02/08/2024
TO-24-BGH-110SA1-01 | SECTIONALISING DISCONNECT - BOGGERAGH 110-BOGGERAGH 110-110SA1 | Unknown | Unknown | 7 | Planned | August | August
TO-24-BGH-110SA2-01 | SECTIONALISING DISCONNECT - BOGGERAGH 110-BOGGERAGH 110-110SA2 | Unknown | Unknown | 7 | Planned | August | August
TO-24-BGH-CLA-1-01 | 110kV FEEDER - BOGGERAGH 110-CLASHAVOON 110-1 | Unknown | Unknown | 7 | Planned | August | August
TO-24-BGH-T121-01 | GENERATOR TRANSFORMER - BOGGERAGH 110-BOGGERAGH 20-T121 | Unknown | Unknown | 7 | Planned | August | August
TO-24-BGH-T132-01 | GENERATOR TRANSFORMER - BOGGERAGH 110-BOGGERAGH 33-T132 | Unknown | Unknown | 7 | Planned | August | August
TO-24-BGH-T142-01 | DISTRIBUTION TRANSFORMER - BOGGERAGH 110-BOGGERAGH 38-T142 | Unknown | Unknown | 7 | Reference (Planned) | August | August
TO-24-GGO-T2001-01 | GENERATOR TRANSFORMER - GLANAGOW 220-GLANAGOW G1-T2001 | Unknown | Unknown | 2 | Planned | September | September
TO-24-220 kV A2 @ AD-02 | BUSBAR SECTION - AGHADA 220-AGHADA 220-220A2 | Unknown | Unknown | 5 | Planned | September | September
TO-24-220 kV B2 @ AD-02 | BUSBAR SECTION - AGHADA 220-AGHADA 220-220B2 | Unknown | Unknown | 5 | Planned | September | September
TO-24-AD-SA1-2CB-02 | COUPLER/SECTIONALISING CB - AGHADA 220-AGHADA 220-220SA1-2CB | Unknown | Unknown | 5 | Planned | September | September
TO-24-AD-SB1-2CB-02 | COUPLER/SECTIONALISING CB - AGHADA 220-AGHADA 220-220SB1-2CB | Unknown | Unknown | 5 | Planned | September | September
TO-24-AD-KRA-2-02 | 220kV FEEDER - AGHADA 220-KNOCKRAHA 220-2 | Unknown | Unknown | 5 | Planned | September | September
TO-24-AD-RAF-1-01 | 220kV FEEDER - AGHADA 220-RAFFEEN 220-1 | Unknown | Unknown | 5 | Planned | September | September
TO-24-AD-T2011/12-02 | GENERATOR TRANSFORMER - AGHADA 220-AGHADA G11/12-T2011/12 | Unknown | Unknown | 5 | Planned | September | September
TO-24-220 kV A1 @ KRA-01 | BUSBAR SECTION - KNOCKRAHA 220-KNOCKRAHA 220-220A1 | Unknown | Unknown | 10 | Planned | September | September
TO-24-220 kV B1 @ KRA-01 | BUSBAR SECTION - KNOCKRAHA 220-KNOCKRAHA 220-220B1 | Unknown | Unknown | 10 | Planned | September | September
TO-24-AD-T2014-02 | GENERATOR TRANSFORMER - AGHADA 220-AGHADA G14-T2014 | Unknown | Unknown | 5 | Planned | September | September
TO-24-KBY-KRA-1-01 | 110kV FEEDER - KILBARRY 110-KNOCKRAHA 110-1 | Unknown | Unknown | 10 | Planned | October | October
TO-24-220 kV A1 @ RAF-01 | BUSBAR SECTION - RAFFEEN 220-RAFFEEN 220-220A1 | Unknown | Unknown | 10 | Planned | October | October
TO-24-220 kV B1 @ RAF-01 | BUSBAR SECTION - RAFFEEN 220-RAFFEEN 220-220B1 | Unknown | Unknown | 10 | Planned | October | October
TO-24-KBY-KRA-2-01 | 110kV FEEDER - KILBARRY 110-KNOCKRAHA 110-2 | Unknown | Unknown | 10 | Planned | October | November
TO-24-KLN-KRA-1-01 | 220kV FEEDER - KILLONAN 220-KNOCKRAHA 220-1 | Unknown | Unknown | 4 | Planned | October | November
TO-24-110 kV A1 @ RAF-01 | BUSBAR SECTION - RAFFEEN 110-RAFFEEN 110-110A1 | Unknown | Unknown | 10 | Planned | November | November
TO-24-110 kV B1 @ RAF-01 | BUSBAR SECTION - RAFFEEN 110-RAFFEEN 110-110B1 | Unknown | Unknown | 10 | Planned | November | November
TO-24-RAF-TBG-1-01 | 110kV FEEDER - RAFFEEN 110-TRABEG 110-1 | Unknown | Unknown | 10 | Planned | November | November