## GEN_ALL
Outage ID | Feeder ID | Calendar Day Duration | Working Day Duration | Work Days | Outage Status | Start | Finish
TO-25-DND-T121-01 | TSO CUSTOMER TRANSFORMER - DARNDALE 110-DARNDALE 20-T121 | 474 | 334 | 334 | Scheduled | 12/02/2024 | 30/05/2025
TO-25-GI-T141-01 | DISTRIBUTION TRANSFORMER - GREAT ISLAND 110-GREAT ISLAND 38-T141 | 639 | 446 | 446 | Reference | 02/04/2024 | 31/12/2025
TO-25-BAL-DRY-1-03 | 110kV FEEDER - BALTRASNA 110-DRYBRIDGE 110-1 | 283 | 201 | 201 | Scheduled | 13/05/2024 | 19/02/2025
TO-25-CUS-PLS-1-01 | 110kV FEEDER - CUSHALING 110-PORTLAOISE 110-1 | 128 | 89 |  | Scheduled | 11/12/2024 | 17/04/2025
TO-25-110 kV A2 @ PLS-01 | BUSBAR SECTION - PORTLAOISE 110-PORTLAOISE 110-110A2 | 128 | 89 |  | Scheduled | 11/12/2024 | 17/04/2025
TO-25-110 kV B2 @ PLS-01 | BUSBAR SECTION - PORTLAOISE 110-PORTLAOISE 110-110B2 | 128 | 89 |  | Scheduled | 11/12/2024 | 17/04/2025
TO-25-ARK-SHE-2-01 | 110kV FEEDER - ARKLOW 110-SHELTON ABBEY 110-2 | 15 | 10 | 10 | Scheduled | 23/12/2024 | 06/01/2025
TO-25-SHE-T102-01 | TSO CUSTOMER TRANSFORMER - SHELTON ABBEY 110-SHELTON ABBEY 10-T102 | 15 | 10 | 10 | Scheduled | 23/12/2024 | 06/01/2025
TO-25-KIN-T101-02 | TSO CUSTOMER TRANSFORMER - KINNEGAD 110-KINNEGAD 10-T101 | 26 | 18 | 18 | Scheduled | 03/01/2025 | 28/01/2025
TO-25-110 kV B2/B4 @ CDU-01 | BUSBAR SECTION - CORDUFF 110-CORDUFF 110-110B2-B4 | 8 | 6 | 6 | Scheduled | 06/01/2025 | 13/01/2025
TO-25-CDU-110SB2-4-01 | SECTIONALISING DISCONNECT - CORDUFF 110-CORDUFF 110-110SB2-4 | 8 | 6 | 6 | Scheduled | 06/01/2025 | 13/01/2025
TO-25-220 kV A2 @ SH-01 | BUSBAR SECTION - SHANNONBRIDGE 220-SHANNONBRIDGE 220-220A2 | 50 | 35 | 35 | Scheduled | 06/01/2025 | 24/02/2025
TO-25-220 kV B2 @ SH-01 | BUSBAR SECTION - SHANNONBRIDGE 220-SHANNONBRIDGE 220-220B2 | 50 | 35 | 35 | Scheduled | 06/01/2025 | 24/02/2025
TO-25-CHA-MAL-1-03 | 110kV FEEDER - CHARLEVILLE 110-MALLOW 110-1 | 4 | 4 | 4 | Scheduled | 07/01/2025 | 10/01/2025
TO-25-FIN-220K1-04 | COUPLER/SECTIONALISING CB - FINGLAS 220-FINGLAS 220-220K1 | 2 | 2 | 2 | Scheduled | 08/01/2025 | 09/01/2025
TO-25-FIN-220K2-05 | COUPLER/SECTIONALISING CB - FINGLAS 220-FINGLAS 220-220K2 | 2 | 2 | 2 | Scheduled | 08/01/2025 | 09/01/2025
TO-25-FIN-220SA1-2CB-08 | COUPLER/SECTIONALISING CB - FINGLAS 220-FINGLAS 220-220SA1-2CB | 2 | 2 | 2 | Scheduled | 08/01/2025 | 09/01/2025
TO-25-AA GIS-DRU-1-01 | 110kV FEEDER - ARDNACRUSHA GIS 110-DRUMLINE 110-1 | 2 | 2 | 2 | Scheduled | 09/01/2025 | 10/01/2025
TO-25-CDU-T2102-02 | TRANSFORMER - CORDUFF 220-CORDUFF 110-T2102 | 1 | 1 | 1 | Scheduled | 13/01/2025 | 13/01/2025
TO-25-110 kV A2 @ LOU-05 | BUSBAR SECTION - LOUTH 110-LOUTH 110-110A2 | 12 | 10 | 10 | Scheduled | 13/01/2025 | 24/01/2025
TO-25-110 kV B2 @ LOU-05 | BUSBAR SECTION - LOUTH 110-LOUTH 110-110B2 | 12 | 10 | 10 | Scheduled | 13/01/2025 | 24/01/2025
TO-25-220 kV A2 @ LOU-07 | BUSBAR SECTION - LOUTH 220-LOUTH 220-220A2 | 12 | 10 | 10 | Scheduled | 13/01/2025 | 24/01/2025
TO-25-220 kV B2 @ LOU-06 | BUSBAR SECTION - LOUTH 220-LOUTH 220-220B2 | 12 | 10 | 10 | Scheduled | 13/01/2025 | 24/01/2025
TO-25-LOU-T2102-01 | TRANSFORMER - LOUTH 220-LOUTH 110-T2102 | 12 | 10 | 10 | Scheduled | 13/01/2025 | 24/01/2025
TO-25-220 kV B1 @ CBT-02 | BUSBAR SECTION - CASTLEBAGOT 220-CASTLEBAGOT 220-220B1 | 9 | 7 | 7 | Scheduled | 14/01/2025 | 22/01/2025
TO-25-220 kV B2 @ CBT-01 | BUSBAR SECTION - CASTLEBAGOT 220-CASTLEBAGOT 220-220B2 | 9 | 7 | 7 | Scheduled | 14/01/2025 | 22/01/2025
TO-25-CBT-220K1-04 | COUPLER/SECTIONALISING CB - CASTLEBAGOT 220-CASTLEBAGOT 220-220K1 | 9 | 7 | 7 | Scheduled | 14/01/2025 | 22/01/2025
TO-25-CBT-220K2-02 | COUPLER/SECTIONALISING CB - CASTLEBAGOT 220-CASTLEBAGOT 220-220K2 | 9 | 7 | 7 | Scheduled | 14/01/2025 | 22/01/2025
TO-25-CBT-220SB1-2CB-01 | COUPLER/SECTIONALISING CB - CASTLEBAGOT 220-CASTLEBAGOT 220-220SB1-2CB | 9 | 7 | 7 | Scheduled | 14/01/2025 | 22/01/2025
TO-25-COW-110SA1-01 | SECTIONALISING DISCONNECT - COW CROSS 110-COW CROSS 110-110SA1 | 10 | 8 | 8 | Scheduled | 14/01/2025 | 23/01/2025
TO-25-COW-110SA2-01 | SECTIONALISING DISCONNECT - COW CROSS 110-COW CROSS 110-110SA2 | 10 | 8 | 8 | Scheduled | 14/01/2025 | 23/01/2025
TO-25-COW-OLD-2-01 | 110kV FEEDER - COW CROSS 110-OLDCOURT 110-2 | 10 | 8 | 8 | Reference | 14/01/2025 | 23/01/2025
TO-25-COW-RAF-1-01 | 110kV FEEDER - COW CROSS 110-RAFFEEN 110-1 | 10 | 8 | 8 | Scheduled | 14/01/2025 | 23/01/2025
TO-25-COW-T141-01 | DISTRIBUTION TRANSFORMER - COW CROSS 110-COW CROSS 38-T141 | 10 | 8 | 8 | Reference | 14/01/2025 | 23/01/2025
TO-25-CUS-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - CUSHALING 110-CUSHALING 110-110SA1-2CB | 1 | 1 | 1 | Scheduled | 14/01/2025 | 14/01/2025
TO-25-CUS-KIR-1-01 | 110kV FEEDER - CUSHALING 110-KILCUMBER 110-1 | 1 | 1 | 1 | Scheduled | 14/01/2025 | 14/01/2025
TO-25-CUS-MLC-1-01 | 110kV FEEDER - CUSHALING 110-MOUNTLUCAS 110-1 | 1 | 1 | 1 | Scheduled | 14/01/2025 | 14/01/2025
TO-25-CUS-T101-01 | GENERATOR TRANSFORMER - CUSHALING 110-CUSHALING G1-T101 | 1 | 1 | 1 | Scheduled | 14/01/2025 | 14/01/2025
TO-25-KIR-T131-02 | GENERATOR TRANSFORMER - KILCUMBER 110-KILCUMBER 33-T131 | 1 | 1 | 1 | Scheduled | 14/01/2025 | 14/01/2025
TO-25-OLD-T102-01 | DISTRIBUTION TRANSFORMER - OLDCOURT 110-OLDCOURT 10-T102 | 10 | 8 | 8 | Reference | 14/01/2025 | 23/01/2025
TO-25-CSH-DLT-1-01 | 110kV FEEDER - CASHLA 110-DALTON 110-1 | 3 | 3 | 3 | Scheduled | 15/01/2025 | 17/01/2025
TO-25-GWE-T101-03 | TSO CUSTOMER TRANSFORMER - GORTAWEE 110-GORTAWEE 10-T101 | 16 | 12 | 12 | Scheduled | 15/01/2025 | 30/01/2025
TO-25-WOO-220K1-2-05 | COUPLER/SECTIONALISING CB - WOODLAND 220-WOODLAND 220-220K1-2 | 2 | 2 | 2 | Scheduled | 15/01/2025 | 16/01/2025
TO-25-BNK-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - BARNAKYLE 110-BARNAKYLE 110-110SA1-2CB | 67 | 45 | 45 | Scheduled | 17/01/2025 | 24/03/2025
TO-25-BNK-CBT-2-01 | 110kV FEEDER - BARNAKYLE 110-CASTLEBAGOT 110-2 | 67 | 45 | 45 | Scheduled | 17/01/2025 | 24/03/2025
TO-25-BNK-T122-01 | TSO CUSTOMER TRANSFORMER - BARNAKYLE 110-BARNAKYLE 20-T122 | 67 | 45 | 45 | Scheduled | 17/01/2025 | 24/03/2025
TO-25-DSN-MAY-2-03 | 220kV FEEDER - DUNSTOWN 220-MAYNOOTH 220-2 | 11 | 9 |  | Scheduled | 20/01/2025 | 30/01/2025
TO-25-KPG-110K4-01 | COUPLER/SECTIONALISING CB - KILPADDOGE 110-KILPADDOGE 110-110K4 | 1 | 1 |  | Scheduled | 21/01/2025 | 21/01/2025
TO-25-INC-PB-1-01 | 220kV FEEDER - INCHICORE 220-POOLBEG 220-1 | 43 | 30 | 30 | Scheduled | 27/01/2025 | 10/03/2025
TO-25-220 kV A2 @ KLN-01 | BUSBAR SECTION - KILLONAN 220-KILLONAN 220-220A2 | 5 | 5 | 5 | Scheduled | 27/01/2025 | 31/01/2025
TO-25-220 kV B2 @ KLN-01 | BUSBAR SECTION - KILLONAN 220-KILLONAN 220-220B2 | 5 | 5 | 5 | Scheduled | 27/01/2025 | 31/01/2025
TO-25-KLN-KPG-1-01 | 220kV FEEDER - KILLONAN 220-KILPADDOGE 220-1 | 43 | 30 | 30 | Scheduled | 27/01/2025 | 10/03/2025
TO-25-220 kV A2 @ TB-01 | BUSBAR SECTION - TARBERT 220-TARBERT 220-220A2 | 15 | 10 | 10 | Scheduled | 27/01/2025 | 10/02/2025
TO-25-220 kV B2 @ TB-01 | BUSBAR SECTION - TARBERT 220-TARBERT 220-220B2 | 15 | 10 | 10 | Scheduled | 27/01/2025 | 10/02/2025
TO-25-LOU-T2101-03 | TRANSFORMER - LOUTH 220-LOUTH 110-T2101 | 16 | 11 | 11 | Scheduled | 29/01/2025 | 13/02/2025
TO-25-CHA-KLN-1-01 | 110kV FEEDER - CHARLEVILLE 110-KILLONAN 110-1 | 43 | 30 | 30 | Scheduled | 04/02/2025 | 18/03/2025
TO-25-220 kV A2 @ FIN-05 | BUSBAR SECTION - FINGLAS 220-FINGLAS 220-220A2 | 11 | 9 | 9 | Scheduled | 04/02/2025 | 14/02/2025
TO-25-FIN-220K2-08 | COUPLER/SECTIONALISING CB - FINGLAS 220-FINGLAS 220-220K2 | 11 | 9 | 9 | Scheduled | 04/02/2025 | 14/02/2025
TO-25-FIN-220SA1-2CB-09 | COUPLER/SECTIONALISING CB - FINGLAS 220-FINGLAS 220-220SA1-2CB | 11 | 9 | 9 | Scheduled | 04/02/2025 | 14/02/2025
TO-25-FIN-SHL-1-01 | 220kV FEEDER - FINGLAS 220-SHELLYBANKS 220-1 | 25 | 19 | 19 | Scheduled | 04/02/2025 | 28/02/2025
TO-25-SHL-T2016-01 | GENERATOR TRANSFORMER - SHELLYBANKS 220-SHELLYBANKS G6-T2016 | 1 | 1 | 1 | Scheduled | 04/02/2025 | 04/02/2025
TO-25-RRU-SKL-1-01 | 110kV FEEDER - RATRUSSAN 110-SHANKILL 110-1 | 57 | 40 | 40 | Scheduled | 05/02/2025 | 02/04/2025
TO-25-BAR-T141-01 | DISTRIBUTION TRANSFORMER - BARRYMORE 110-BARRYMORE 38-T141 | 3 | 3 | 3 | Reference | 10/02/2025 | 12/02/2025
TO-25-BAR,T-BAR-1-01 | 110kV FEEDER - BARRYMORE tee-BARRYMORE 110-1 | 3 | 3 | 3 | Scheduled | 10/02/2025 | 12/02/2025
TO-25-BAR,T-CAH-1-01 | 110kV FEEDER - BARRYMORE tee-CAHIR 110-1 | 19 | 15 | 15 | Scheduled | 10/02/2025 | 28/02/2025
TO-25-BAR,T-KRA-1-02 | 110kV FEEDER - BARRYMORE tee-KNOCKRAHA 110-1 | 3 | 3 | 3 | Scheduled | 10/02/2025 | 12/02/2025
TO-25-110 kV A2 @ CDU-02 | BUSBAR SECTION - CORDUFF 110-CORDUFF 110-110A2 | 5 | 5 | 5 | Scheduled | 10/02/2025 | 14/02/2025
TO-25-110 kV A4 @ CDU-02 | BUSBAR SECTION - CORDUFF 110-CORDUFF 110-110A4 | 5 | 5 | 5 | Scheduled | 10/02/2025 | 14/02/2025
TO-25-110 kV B2 @ CDU-02 | BUSBAR SECTION - CORDUFF 110-CORDUFF 110-110B2 | 5 | 5 | 5 | Scheduled | 10/02/2025 | 14/02/2025
TO-25-110 kV B4 @ CDU-02 | BUSBAR SECTION - CORDUFF 110-CORDUFF 110-110B4 | 5 | 5 | 5 | Scheduled | 10/02/2025 | 14/02/2025
TO-25-FLA-SLB-1-01 | 110kV FEEDER - FLAGFORD 110-SLIABH BAWN 110-1 | 19 | 15 | 15 | Scheduled | 10/02/2025 | 28/02/2025
TO-25-SH-T2101-03 | TRANSFORMER - SHANNONBRIDGE 220-SHANNONBRIDGE 110-T2101 | 80 | 55 |  | Scheduled | 10/02/2025 | 30/04/2025
TO-25-110 kV A2 @ SLB-01 | BUSBAR SECTION - SLIABH BAWN 110-SLIABH BAWN 110-110A2 | 19 | 15 | 15 | Scheduled | 10/02/2025 | 28/02/2025
TO-25-110 kV B2 @ SLB-01 | BUSBAR SECTION - SLIABH BAWN 110-SLIABH BAWN 110-110B2 | 19 | 15 | 15 | Scheduled | 10/02/2025 | 28/02/2025
TO-25-SLB-110K2-01 | COUPLER/SECTIONALISING CB - SLIABH BAWN 110-SLIABH BAWN 110-110K2 | 19 | 15 | 15 | Scheduled | 10/02/2025 | 28/02/2025
TO-25-AUN-CBT-1-01 | 110kV FEEDER - AUNGIERSTOWN 110-CASTLEBAGOT 110-1 | 2 | 2 | 2 | Scheduled | 11/02/2025 | 12/02/2025
TO-25-ROP-WEX-1-01 | 110kV FEEDER - ROSSPILE 110-WEXFORD 110-1 | 7 | 5 |  | Scheduled | 12/02/2025 | 18/02/2025
TO-25-WEX-110SA1-2CB-03 | COUPLER/SECTIONALISING CB - WEXFORD 110-WEXFORD 110-110SA1-2CB | 7 | 5 |  | Scheduled | 12/02/2025 | 18/02/2025
TO-25-WEX-T121-01 | DISTRIBUTION TRANSFORMER - WEXFORD 110-WEXFORD 20-T121 | 7 | 5 | 5 | Reference | 12/02/2025 | 18/02/2025
TO-25-WEX-T141-01 | DISTRIBUTION TRANSFORMER - WEXFORD 110-WEXFORD 38-T141 | 7 | 5 | 5 | Reference | 12/02/2025 | 18/02/2025
TO-25-AUN-T121-01 | TSO CUSTOMER TRANSFORMER - AUNGIERSTOWN 110-AUNGIERSTOWN 20-T121 | 2 | 2 | 2 | Scheduled | 13/02/2025 | 14/02/2025
TO-25-110 kV A2 @ CAH-01 | BUSBAR SECTION - CAHIR 110-CAHIR 110-110A2 | 12 | 10 | 10 | Scheduled | 17/02/2025 | 28/02/2025
TO-25-110 kV B2 @ CAH-01 | BUSBAR SECTION - CAHIR 110-CAHIR 110-110B2 | 12 | 10 | 10 | Scheduled | 17/02/2025 | 28/02/2025
TO-25-110 kV A2 @ CSH-03 | BUSBAR SECTION - CASHLA 110-CASHLA 110-110A2 | 12 | 10 | 10 | Scheduled | 17/02/2025 | 28/02/2025
TO-25-110 kV B2 @ CSH-05 | BUSBAR SECTION - CASHLA 110-CASHLA 110-110B2 | 12 | 10 | 10 | Scheduled | 17/02/2025 | 28/02/2025
TO-25-220 kV A4 @ CSH-02 | BUSBAR SECTION - CASHLA 220-CASHLA 220-220A4 | 12 | 10 | 10 | Scheduled | 17/02/2025 | 28/02/2025
TO-25-220 kV B4 @ CSH-02 | BUSBAR SECTION - CASHLA 220-CASHLA 220-220B4 | 12 | 10 | 10 | Scheduled | 17/02/2025 | 28/02/2025
TO-25-CSH-T2104-01 | TRANSFORMER - CASHLA 220-CASHLA 110-T2104 | 26 | 20 |  | Scheduled | 17/02/2025 | 14/03/2025
TO-25-CUN-GLR-1-01 | 110kV FEEDER - CUNGHILL 110-GLENREE 110-1 | 12 | 10 |  | Scheduled | 17/02/2025 | 28/02/2025
TO-25-DEN-DRY-1-03 | 110kV FEEDER - DEENES 110-DRYBRIDGE 110-1 | 3 | 3 | 3 | Scheduled | 17/02/2025 | 19/02/2025
TO-25-DRY-110SA1-02 | SECTIONALISING DISCONNECT - DRYBRIDGE 110-DRYBRIDGE 110-110SA1 | 3 | 3 | 3 | Scheduled | 17/02/2025 | 19/02/2025
TO-25-DRY-110SA2-02 | SECTIONALISING DISCONNECT - DRYBRIDGE 110-DRYBRIDGE 110-110SA2 | 3 | 3 | 3 | Scheduled | 17/02/2025 | 19/02/2025
TO-25-DRY-GOR-1-03 | 110kV FEEDER - DRYBRIDGE 110-GORMAN 110-1 | 3 | 3 | 3 | Scheduled | 17/02/2025 | 19/02/2025
TO-25-DRY-T142-02 | DISTRIBUTION TRANSFORMER - DRYBRIDGE 110-DRYBRIDGE 38-T142 | 3 | 3 | 3 | Reference | 17/02/2025 | 19/02/2025
TO-25-PLA-T101/2/3/4-02 | TSO CUSTOMER TRANSFORMER - PLATIN 110-PLATIN 10-T101/2/3/4 | 5 | 5 | 5 | Proposed | 17/02/2025 | 21/02/2025
TO-25-CVW-COW-1-01 | 110kV FEEDER - CASTLEVIEW 110-COW CROSS 110-1 | 16 | 12 | 12 | Scheduled | 18/02/2025 | 05/03/2025
TO-25-COW-110SA1-02 | SECTIONALISING DISCONNECT - COW CROSS 110-COW CROSS 110-110SA1 | 16 | 12 | 12 | Scheduled | 18/02/2025 | 05/03/2025
TO-25-COW-110SA2-02 | SECTIONALISING DISCONNECT - COW CROSS 110-COW CROSS 110-110SA2 | 16 | 12 | 12 | Scheduled | 18/02/2025 | 05/03/2025
TO-25-COW-OLD-1-01 | 110kV FEEDER - COW CROSS 110-OLDCOURT 110-1 | 16 | 12 | 12 | Reference | 18/02/2025 | 05/03/2025
TO-25-COW-WHI-1-01 | 110kV FEEDER - COW CROSS 110-WHITEGATE 110-1 | 16 | 12 |  | Scheduled | 18/02/2025 | 05/03/2025
TO-25-OLD-T101-01 | DISTRIBUTION TRANSFORMER - OLDCOURT 110-OLDCOURT 10-T101 | 16 | 12 | 12 | Reference | 18/02/2025 | 05/03/2025
TO-25-AUN-T123-01 | TSO CUSTOMER TRANSFORMER - AUNGIERSTOWN 110-AUNGIERSTOWN 20-T123 | 2 | 2 | 2 | Scheduled | 19/02/2025 | 20/02/2025
TO-25-110 kV A2 @ GI-03 | BUSBAR SECTION - GREAT ISLAND 110-GREAT ISLAND 110-110A2 | 10 | 8 | 8 | Scheduled | 19/02/2025 | 28/02/2025
TO-25-110 kV B2 @ GI-02 | BUSBAR SECTION - GREAT ISLAND 110-GREAT ISLAND 110-110B2 | 10 | 8 | 8 | Scheduled | 19/02/2025 | 28/02/2025
TO-25-GI-ROP-1-01 | 110kV FEEDER - GREAT ISLAND 110-ROSSPILE 110-1 | 10 | 8 |  | Scheduled | 19/02/2025 | 28/02/2025
TO-25-AUN-KSG-1-01 | 110kV FEEDER - AUNGIERSTOWN 110-KISHOGE 110-1 | 4 | 2 | 2 | Scheduled | 21/02/2025 | 24/02/2025
TO-25-BAL-CDU-1-02 | 110kV FEEDER - BALTRASNA 110-CORDUFF 110-1 | 6 | 5 |  | Scheduled | 24/02/2025 | 01/03/2025
TO-25-BAR-T141-03 | DISTRIBUTION TRANSFORMER - BARRYMORE 110-BARRYMORE 38-T141 | 5 | 5 | 5 | Reference | 24/02/2025 | 28/02/2025
TO-25-BAR,T-BAR-1-03 | 110kV FEEDER - BARRYMORE tee-BARRYMORE 110-1 | 5 | 5 | 5 | Scheduled | 24/02/2025 | 28/02/2025
TO-25-BAR,T-KRA-1-01 | 110kV FEEDER - BARRYMORE tee-KNOCKRAHA 110-1 | 19 | 15 | 15 | Scheduled | 24/02/2025 | 14/03/2025
TO-25-CLA-DMY-1-01 | 110kV FEEDER - CLASHAVOON 110-DUNMANWAY 110-1 | 5 | 5 |  | Scheduled | 24/02/2025 | 28/02/2025
TO-25-110 kV A4 @ CDU-01 | BUSBAR SECTION - CORDUFF 110-CORDUFF 110-110A4 | 6 | 5 | 5 | Scheduled | 24/02/2025 | 01/03/2025
TO-25-110 kV B4 @ CDU-01 | BUSBAR SECTION - CORDUFF 110-CORDUFF 110-110B4 | 6 | 5 | 5 | Scheduled | 24/02/2025 | 01/03/2025
TO-25-CDU-110SA2-4CB-01 | COUPLER/SECTIONALISING CB - CORDUFF 110-CORDUFF 110-110SA2-4CB | 6 | 5 | 5 | Scheduled | 24/02/2025 | 01/03/2025
TO-25-CDU-110SB2-4CB-01 | COUPLER/SECTIONALISING CB - CORDUFF 110-CORDUFF 110-110SB2-4CB | 6 | 5 | 5 | Scheduled | 24/02/2025 | 01/03/2025
TO-25-110 kV A1 @ KRA-01 | BUSBAR SECTION - KNOCKRAHA 110-KNOCKRAHA 110-110A1 | 19 | 15 | 15 | Scheduled | 24/02/2025 | 14/03/2025
TO-25-110 kV B1 @ KRA-01 | BUSBAR SECTION - KNOCKRAHA 110-KNOCKRAHA 110-110B1 | 19 | 15 | 15 | Scheduled | 24/02/2025 | 14/03/2025
TO-25-220 kV B2 @ LOU-08 | BUSBAR SECTION - LOUTH 220-LOUTH 220-220B2 | 9 | 7 | 7 | Scheduled | 24/02/2025 | 04/03/2025
TO-25-LOU-T2104-04 | TRANSFORMER - LOUTH 220-LOUTH 110-T2104 | 9 | 7 | 7 | Scheduled | 24/02/2025 | 04/03/2025
TO-25-FIN GIS-T2101-01 | TRANSFORMER - FINGLAS 220-FINGLAS GIS 110-T2101 | 3 | 3 | 3 | Scheduled | 25/02/2025 | 27/02/2025
TO-25-110 kV A1 @ CF-04 | BUSBAR SECTION - CATHALEENS FALL 110-CATHALEENS FALL 110-110A1 | 43 | 30 | 30 | Scheduled | 26/02/2025 | 09/04/2025
TO-25-110 kV A2 @ CF-02 | BUSBAR SECTION - CATHALEENS FALL 110-CATHALEENS FALL 110-110A2 | 43 | 30 | 30 | Scheduled | 26/02/2025 | 09/04/2025
TO-25-110 kV B1 @ CF-03 | BUSBAR SECTION - CATHALEENS FALL 110-CATHALEENS FALL 110-110B1 | 43 | 30 | 30 | Scheduled | 26/02/2025 | 09/04/2025
TO-25-110 kV B2 @ CF-01 | BUSBAR SECTION - CATHALEENS FALL 110-CATHALEENS FALL 110-110B2 | 43 | 30 | 30 | Scheduled | 26/02/2025 | 09/04/2025
TO-25-CF-110K1-2-01 | COUPLER/SECTIONALISING CB - CATHALEENS FALL 110-CATHALEENS FALL 110-110K1-2 | 43 | 30 | 30 | Scheduled | 26/02/2025 | 09/04/2025
TO-25-110 kV B2 @ DEN-01 | BUSBAR SECTION - DEENES 110-DEENES 110-110B2 | 2 | 2 | 2 | Scheduled | 26/02/2025 | 27/02/2025
TO-25-DEN-110K2-02 | COUPLER/SECTIONALISING CB - DEENES 110-DEENES 110-110K2 | 2 | 2 | 2 | Scheduled | 26/02/2025 | 27/02/2025
TO-25-DEY-T134-01 | GENERATOR TRANSFORMER - DERRYCARNEY 110-DERRYCARNEY 33-T134 | 1 | 1 | 1 | Scheduled | 27/02/2025 | 27/02/2025
TO-25-ATH-110SA1-2CB-02 | COUPLER/SECTIONALISING CB - ATHLONE 110-ATHLONE 110-110SA1-2CB | 12 | 10 |  | Scheduled | 03/03/2025 | 14/03/2025
TO-25-ATH-110SA1-2CB-06 | COUPLER/SECTIONALISING CB - ATHLONE 110-ATHLONE 110-110SA1-2CB | 12 | 10 |  | Proposed | 03/03/2025 | 14/03/2025
TO-25-ATH-SH-1-02 | 110kV FEEDER - ATHLONE 110-SHANNONBRIDGE 110-1 | 12 | 10 | 10 | Scheduled | 03/03/2025 | 14/03/2025
TO-25-ATH-SH-1-06 | 110kV FEEDER - ATHLONE 110-SHANNONBRIDGE 110-1 | 12 | 10 | 10 | Proposed | 03/03/2025 | 14/03/2025
TO-25-ATH-T142-02 | DISTRIBUTION TRANSFORMER - ATHLONE 110-ATHLONE 38-T142 | 12 | 10 |  | Reference | 03/03/2025 | 14/03/2025
TO-25-ATH-T142-06 | DISTRIBUTION TRANSFORMER - ATHLONE 110-ATHLONE 38-T142 | 12 | 10 | 10 | Reference (Proposed) | 03/03/2025 | 14/03/2025
TO-25-BAG-T101-01 | TSO CUSTOMER TRANSFORMER - BARNAGEERAGH 110-BARNAGEERAGH 11-T101 | 5 | 5 | 5 | Proposed | 03/03/2025 | 07/03/2025
TO-25-BOT-MLC-1-02 | 110kV FEEDER - BOGTOWN 110-MOUNTLUCAS 110-1 | 12 | 10 | 10 | Proposed | 03/03/2025 | 14/03/2025
TO-25-BOT-MLC-1-01 | 110kV FEEDER - BOGTOWN 110-MOUNTLUCAS 110-1 | 12 | 10 | 10 | Scheduled | 03/03/2025 | 14/03/2025
TO-25-BOT-T132-01 | GENERATOR TRANSFORMER - BOGTOWN 110-BOGTOWN 33-T132 | 12 | 10 | 10 | Scheduled | 03/03/2025 | 14/03/2025
TO-25-220 kV A1 @ CSH-01 | BUSBAR SECTION - CASHLA 220-CASHLA 220-220A1 | 12 | 10 | 10 | Proposed | 03/03/2025 | 14/03/2025
TO-25-220 kV A2 @ CSH-01 | BUSBAR SECTION - CASHLA 220-CASHLA 220-220A2 | 12 | 10 | 10 | Proposed | 03/03/2025 | 14/03/2025
TO-25-220 kV B1 @ CSH-01 | BUSBAR SECTION - CASHLA 220-CASHLA 220-220B1 | 12 | 10 | 10 | Proposed | 03/03/2025 | 14/03/2025
TO-25-220 kV B2 @ CSH-01 | BUSBAR SECTION - CASHLA 220-CASHLA 220-220B2 | 12 | 10 | 10 | Proposed | 03/03/2025 | 14/03/2025
TO-25-CSH-220K1-2-01 | COUPLER/SECTIONALISING CB - CASHLA 220-CASHLA 220-220K1-2 | 12 | 10 | 10 | Proposed | 03/03/2025 | 14/03/2025
TO-25-CSH-T2104-02 | TRANSFORMER - CASHLA 220-CASHLA 110-T2104 | 8 | 6 | 6 | Proposed | 03/03/2025 | 10/03/2025
TO-25-CBT-CKG-1-02 | 110kV FEEDER - CASTLEBAGOT 110-CORKAGH 110-1 | 5 | 5 | 5 | Proposed | 03/03/2025 | 07/03/2025
TO-25-110 kV A1 @ CLA-01 | BUSBAR SECTION - CLASHAVOON 110-CLASHAVOON 110-110A1 | 13 | 10 |  | Proposed | 03/03/2025 | 15/03/2025
TO-25-110 kV B1 @ CLA-01 | BUSBAR SECTION - CLASHAVOON 110-CLASHAVOON 110-110B1 | 13 | 10 |  | Proposed | 03/03/2025 | 15/03/2025
TO-25-220 kV A3 @ CDU-02 | BUSBAR SECTION - CORDUFF 220-CORDUFF 220-220A3 | 12 | 10 | 10 | Proposed | 03/03/2025 | 14/03/2025
TO-25-220 kV B3 @ CDU-02 | BUSBAR SECTION - CORDUFF 220-CORDUFF 220-220B3 | 12 | 10 | 10 | Proposed | 03/03/2025 | 14/03/2025
TO-25-CDU-FIN-1-03 | 220kV FEEDER - CORDUFF 220-FINGLAS 220-1 | 12 | 10 | 10 | Proposed | 03/03/2025 | 14/03/2025
TO-25-CDU-FIN-1-02 | 220kV FEEDER - CORDUFF 220-FINGLAS 220-1 | 12 | 10 |  | Proposed | 03/03/2025 | 14/03/2025
TO-25-CDU-GLN-1-01 | 110kV FEEDER - CORDUFF 110-GALLANSTOWN 110-1 | 1 | 1 | 1 | Proposed | 03/03/2025 | 03/03/2025
TO-25-CDU-GLN-1-02 | 110kV FEEDER - CORDUFF 110-GALLANSTOWN 110-1 | 12 | 10 | 10 | Proposed | 03/03/2025 | 14/03/2025
TO-25-110 kV A3 @ CKG-02 | BUSBAR SECTION - CORKAGH 110-CORKAGH 110-110A3 | 5 | 5 | 5 | Proposed | 03/03/2025 | 07/03/2025
TO-25-110 kV B3 @ CKG-02 | BUSBAR SECTION - CORKAGH 110-CORKAGH 110-110B3 | 5 | 5 | 5 | Proposed | 03/03/2025 | 07/03/2025
TO-25-CKG-110K3-02 | COUPLER/SECTIONALISING CB - CORKAGH 110-CORKAGH 110-110K3 | 5 | 5 | 5 | Proposed | 03/03/2025 | 07/03/2025
TO-25-CKG-110SA1-3CB-03 | COUPLER/SECTIONALISING CB - CORKAGH 110-CORKAGH 110-110SA1-3CB | 5 | 5 | 5 | Proposed | 03/03/2025 | 07/03/2025
TO-25-CKG-110SB1-3CB-03 | COUPLER/SECTIONALISING CB - CORKAGH 110-CORKAGH 110-110SB1-3CB | 5 | 5 | 5 | Proposed | 03/03/2025 | 07/03/2025
TO-25-220 kV A1 @ FIN-03 | BUSBAR SECTION - FINGLAS 220-FINGLAS 220-220A1 | 12 | 10 | 10 | Proposed | 03/03/2025 | 14/03/2025
TO-25-220 kV A1 @ FIN-04 | BUSBAR SECTION - FINGLAS 220-FINGLAS 220-220A1 | 16 | 11 | 11 | Proposed | 03/03/2025 | 18/03/2025
TO-25-220 kV A1 @ FIN-05 | BUSBAR SECTION - FINGLAS 220-FINGLAS 220-220A1 | 12 | 10 | 10 | Proposed | 03/03/2025 | 14/03/2025
TO-25-220 kV B1 @ FIN-02 | BUSBAR SECTION - FINGLAS 220-FINGLAS 220-220B1 | 12 | 10 | 10 | Proposed | 03/03/2025 | 14/03/2025
TO-25-220 kV B1 @ FIN-04 | BUSBAR SECTION - FINGLAS 220-FINGLAS 220-220B1 | 16 | 11 | 11 | Proposed | 03/03/2025 | 18/03/2025
TO-25-220 kV B1 @ FIN-03 | BUSBAR SECTION - FINGLAS 220-FINGLAS 220-220B1 | 12 | 10 |  | Proposed | 03/03/2025 | 14/03/2025
TO-25-FIN-220K1-03 | COUPLER/SECTIONALISING CB - FINGLAS 220-FINGLAS 220-220K1 | 12 | 10 |  | Proposed | 03/03/2025 | 14/03/2025
TO-25-FIN-220K1-05 | COUPLER/SECTIONALISING CB - FINGLAS 220-FINGLAS 220-220K1 | 16 | 11 | 11 | Proposed | 03/03/2025 | 18/03/2025
TO-25-FIN-220K1-07 | COUPLER/SECTIONALISING CB - FINGLAS 220-FINGLAS 220-220K1 | 12 | 10 | 10 | Proposed | 03/03/2025 | 14/03/2025
TO-25-FIN-220SA1-2CB-05 | COUPLER/SECTIONALISING CB - FINGLAS 220-FINGLAS 220-220SA1-2CB | 12 | 10 | 10 | Proposed | 03/03/2025 | 14/03/2025
TO-25-FIN-220SA1-2CB-07 | COUPLER/SECTIONALISING CB - FINGLAS 220-FINGLAS 220-220SA1-2CB | 16 | 11 | 11 | Proposed | 03/03/2025 | 18/03/2025
TO-25-FIN-220SA1-2CB-10 | COUPLER/SECTIONALISING CB - FINGLAS 220-FINGLAS 220-220SA1-2CB | 12 | 10 | 10 | Proposed | 03/03/2025 | 14/03/2025
TO-25-FIN-220SB1-2CB-02 | COUPLER/SECTIONALISING CB - FINGLAS 220-FINGLAS 220-220SB1-2CB | 12 | 10 |  | Proposed | 03/03/2025 | 14/03/2025
TO-25-FIN-220SB1-2CB-06 | COUPLER/SECTIONALISING CB - FINGLAS 220-FINGLAS 220-220SB1-2CB | 16 | 11 | 11 | Proposed | 03/03/2025 | 18/03/2025
TO-25-FIN-220SB1-2CB-08 | COUPLER/SECTIONALISING CB - FINGLAS 220-FINGLAS 220-220SB1-2CB | 12 | 10 | 10 | Proposed | 03/03/2025 | 14/03/2025
TO-25-FIN-T2103-02 | TRANSFORMER - FINGLAS 220-FINGLAS 110-T2103 | 16 | 11 | 11 | Proposed | 03/03/2025 | 18/03/2025
TO-25-RRU-SKL-1-03 | 110kV FEEDER - RATRUSSAN 110-SHANKILL 110-1 | 12 | 10 | 10 | Proposed | 03/03/2025 | 14/03/2025
TO-25-BGT-141-01 | DISTRIBUTION TRANSFORMER - BALLYRAGGET 110-BALLYRAGGET 38-T141 | 43 | 30 | 30 | Reference (Proposed) | 04/03/2025 | 15/04/2025
TO-25-BLU-T131-02 | GENERATOR TRANSFORMER - BLUNDELSTOWN 110-BLUNDELSTOWN 33-T131 | 2 | 2 | 2 | Proposed | 04/03/2025 | 05/03/2025
TO-25-BLU-T131-01 | GENERATOR TRANSFORMER - BLUNDELSTOWN 110-BLUNDELSTOWN 33-T131 | 1 | 1 | 1 | Proposed | 04/03/2025 | 04/03/2025
TO-25-CVW-COW-1-04 | 110kV FEEDER - CASTLEVIEW 110-COW CROSS 110-1 | 1 | 1 | 1 | Proposed | 04/03/2025 | 04/03/2025
TO-25-FLA-SLI-1-02 | 110kV FEEDER - FLAGFORD 110-SLIGO 110-1 | 1 | 1 |  | Proposed | 04/03/2025 | 04/03/2025
TO-25-220 kV A2 @ KLN-02 | BUSBAR SECTION - KILLONAN 220-KILLONAN 220-220A2 | 7 | 5 | 5 | Scheduled | 04/03/2025 | 10/03/2025
TO-25-220 kV B2 @ KLN-02 | BUSBAR SECTION - KILLONAN 220-KILLONAN 220-220B2 | 7 | 5 | 5 | Scheduled | 04/03/2025 | 10/03/2025
TO-25-DND-T121-02 | TSO CUSTOMER TRANSFORMER - DARNDALE 110-DARNDALE 20-T121 | 2 | 2 | 2 | Proposed | 05/03/2025 | 06/03/2025
TO-25-220 kV A2 @ LOU-01 | BUSBAR SECTION - LOUTH 220-LOUTH 220-220A2 | 17 | 12 | 12 | Proposed | 05/03/2025 | 21/03/2025
TO-25-220 kV B2 @ LOU-01 | BUSBAR SECTION - LOUTH 220-LOUTH 220-220B2 | 17 | 12 | 12 | Proposed | 05/03/2025 | 21/03/2025
TO-25-BAG-T103-01 | TSO CUSTOMER TRANSFORMER - BARNAGEERAGH 110-BARNAGEERAGH 11-T103 | 5 | 5 | 5 | Scheduled | 10/03/2025 | 14/03/2025
TO-25-BAG-T103-02 | TSO CUSTOMER TRANSFORMER - BARNAGEERAGH 110-BARNAGEERAGH 11-T103 | 5 | 5 | 5 | Proposed | 10/03/2025 | 14/03/2025
TO-25-110 kV A1 @ CDU-01 | BUSBAR SECTION - CORDUFF 110-CORDUFF 110-110A1 | 12 | 9 | 9 | Proposed | 10/03/2025 | 21/03/2025
TO-25-110 kV A2 @ CDU-01 | BUSBAR SECTION - CORDUFF 110-CORDUFF 110-110A2 | 12 | 9 | 9 | Proposed | 10/03/2025 | 21/03/2025
TO-25-110 kV B1 @ CDU-01 | BUSBAR SECTION - CORDUFF 110-CORDUFF 110-110B1 | 12 | 9 | 9 | Proposed | 10/03/2025 | 21/03/2025
TO-25-110 kV B2 @ CDU-01 | BUSBAR SECTION - CORDUFF 110-CORDUFF 110-110B2 | 12 | 9 | 9 | Proposed | 10/03/2025 | 21/03/2025
TO-25-CDU-110K1-2-01 | COUPLER/SECTIONALISING CB - CORDUFF 110-CORDUFF 110-110K1-2 | 12 | 9 |  | Proposed | 10/03/2025 | 21/03/2025
TO-25-LOU-AT3-01 | TRANSFORMER - LOUTH 220-LOUTH 275-AT3 | 12 | 9 | 9 | Proposed | 10/03/2025 | 21/03/2025
TO-25-400 kV A1 @ DSN-01 | BUSBAR SECTION - DUNSTOWN 400-DUNSTOWN 400-400A1 | 38 | 27 | 27 | Scheduled | 11/03/2025 | 17/04/2025
TO-25-400 kV B1 @ DSN-01 | BUSBAR SECTION - DUNSTOWN 400-DUNSTOWN 400-400B1 | 38 | 27 | 27 | Scheduled | 11/03/2025 | 17/04/2025
TO-25-DSN-MP GIS-1-01 | 400kV FEEDER - DUNSTOWN 400-MONEYPOINT GIS 400-1 | 38 | 27 |  | Scheduled | 11/03/2025 | 17/04/2025
TO-25-INC-PB-2-02 | 220kV FEEDER - INCHICORE 220-POOLBEG 220-2 | 22 | 15 |  | Scheduled | 11/03/2025 | 01/04/2025
TO-25-KLN-KRA-1-03 | 220kV FEEDER - KILLONAN 220-KNOCKRAHA 220-1 | 4 | 4 | 4 | Scheduled | 11/03/2025 | 14/03/2025
TO-25-LYT-T132-01 | GENERATOR TRANSFORMER - LYSAGHTSTOWN 110-LYSAGHTSTOWN 33-T132 | 1 | 1 | 1 | Proposed | 11/03/2025 | 11/03/2025
TO-25-400 kV A4 @ MP GIS-01 | BUSBAR SECTION - MONEYPOINT GIS 400-MONEYPOINT GIS 400-400A4 | 38 | 27 | 27 | Proposed | 11/03/2025 | 17/04/2025
TO-25-400 kV B4 @ MP GIS-01 | BUSBAR SECTION - MONEYPOINT GIS 400-MONEYPOINT GIS 400-400B4 | 38 | 27 | 27 | Proposed | 11/03/2025 | 17/04/2025
TO-25-MP GIS-400K4-01 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 400-MONEYPOINT GIS 400-400K4 | 38 | 27 | 27 | Proposed | 11/03/2025 | 17/04/2025
TO-25-MP GIS-400SA2-4CB-01 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 400-MONEYPOINT GIS 400-400SA2-4CB | 38 | 27 | 27 | Proposed | 11/03/2025 | 17/04/2025
TO-25-MP GIS-400SB2-4CB-01 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 400-MONEYPOINT GIS 400-400SB2-4CB | 38 | 27 | 27 | Proposed | 11/03/2025 | 17/04/2025
TO-25-BAR-T141-04 | DISTRIBUTION TRANSFORMER - BARRYMORE 110-BARRYMORE 38-T141 | 3 | 3 | 3 | Reference | 12/03/2025 | 14/03/2025
TO-25-BAR,T-BAR-1-04 | 110kV FEEDER - BARRYMORE tee-BARRYMORE 110-1 | 3 | 3 | 3 | Scheduled | 12/03/2025 | 14/03/2025
TO-25-BAR,T-CAH-1-03 | 110kV FEEDER - BARRYMORE tee-CAHIR 110-1 | 3 | 3 | 3 | Scheduled | 12/03/2025 | 14/03/2025
TO-25-CDU-CRU-2-02 | 220kV FEEDER - CORDUFF 220-CRUISERATH 220-2 | 2 | 2 | 2 | Proposed | 13/03/2025 | 14/03/2025
TO-25-UGL-T134-01 | GENERATOR TRANSFORMER - UGGOOL 110-UGGOOL 33-T134 | 64 | 42 | 42 | Proposed | 13/03/2025 | 15/05/2025
TO-25-220 kV A2 @ CSH-02 | BUSBAR SECTION - CASHLA 220-CASHLA 220-220A2 | 11 | 9 | 9 | Proposed | 18/03/2025 | 28/03/2025
TO-25-220 kV A4 @ CSH-01 | BUSBAR SECTION - CASHLA 220-CASHLA 220-220A4 | 11 | 9 | 9 | Proposed | 18/03/2025 | 28/03/2025
TO-25-220 kV B2 @ CSH-02 | BUSBAR SECTION - CASHLA 220-CASHLA 220-220B2 | 11 | 9 | 9 | Proposed | 18/03/2025 | 28/03/2025
TO-25-220 kV B4 @ CSH-01 | BUSBAR SECTION - CASHLA 220-CASHLA 220-220B4 | 11 | 9 | 9 | Proposed | 18/03/2025 | 28/03/2025
TO-25-CSH-220K2-4-01 | COUPLER/SECTIONALISING CB - CASHLA 220-CASHLA 220-220K2-4 | 11 | 9 | 9 | Proposed | 18/03/2025 | 28/03/2025
TO-25-CLA-110K1-2-01 | COUPLER/SECTIONALISING CB - CLASHAVOON 110-CLASHAVOON 110-110K1-2 | 44 | 30 |  | Proposed | 18/03/2025 | 30/04/2025
TO-25-110 kV A1 @ FLA-01 | BUSBAR SECTION - FLAGFORD 110-FLAGFORD 110-110A1 | Unknown | Unknown | 40 | Planned | March | May
TO-25-110 kV B1 @ FLA-01 | BUSBAR SECTION - FLAGFORD 110-FLAGFORD 110-110B1 | Unknown | Unknown | 40 | Planned | March | May
TO-25-FLA-SLB-1-02 | 110kV FEEDER - FLAGFORD 110-SLIABH BAWN 110-1 | Unknown | Unknown | 40 | Planned | March | May
TO-25-FLA-SLB-1-04 | 110kV FEEDER - FLAGFORD 110-SLIABH BAWN 110-1 | 59 | 40 | 40 | Proposed | 18/03/2025 | 15/05/2025
TO-25-KBY-MR-1-01 | 110kV FEEDER - KILBARRY 110-MARINA 110-1 | 189 | 130 | 130 | Scheduled | 18/03/2025 | 22/09/2025
TO-25-KBY-MR-1-03 | 110kV FEEDER - KILBARRY 110-MARINA 110-1 | 189 | 130 | 130 | Proposed | 18/03/2025 | 22/09/2025
TO-25-KBY-MR-2-01 | 110kV FEEDER - KILBARRY 110-MARINA 110-2 | 189 | 130 | 130 | Scheduled | 18/03/2025 | 22/09/2025
TO-25-KBY-MR-2-03 | 110kV FEEDER - KILBARRY 110-MARINA 110-2 | 189 | 130 | 130 | Proposed | 18/03/2025 | 22/09/2025
TO-25-KTN-T102-01 | DISTRIBUTION TRANSFORMER - KILLOTERAN 110-KILLOTERAN 10-T102 | 59 | 40 | 40 | Reference | 18/03/2025 | 15/05/2025
TO-25-KTN-WAT-1-01 | 110kV FEEDER - KILLOTERAN 110-WATERFORD 110-1 | 59 | 40 |  | Scheduled | 18/03/2025 | 15/05/2025
TO-25-KTN-WAT-1-03 | 110kV FEEDER - KILLOTERAN 110-WATERFORD 110-1 | 59 | 40 | 40 | Proposed | 18/03/2025 | 15/05/2025
TO-25-KRA-WOH-1-03 | 110kV FEEDER - KNOCKRAHA 110-WOODHOUSE 110-1 | 3 | 3 | 3 | Proposed | 18/03/2025 | 20/03/2025
TO-25-220 kV A1 @ LOU-01 | BUSBAR SECTION - LOUTH 220-LOUTH 220-220A1 | Unknown | Unknown | 20 | Planned | March | April
TO-25-220 kV B1 @ LOU-01 | BUSBAR SECTION - LOUTH 220-LOUTH 220-220B1 | Unknown | Unknown | 20 | Planned | March | April
TO-25-110 kV A2 @ CSH-02 | BUSBAR SECTION - CASHLA 110-CASHLA 110-110A2 | 10 | 8 | 8 | Scheduled | 19/03/2025 | 28/03/2025
TO-25-110 kV B2 @ CSH-04 | BUSBAR SECTION - CASHLA 110-CASHLA 110-110B2 | 10 | 8 | 8 | Scheduled | 19/03/2025 | 28/03/2025
TO-25-CSH-ENN-1-01 | 110kV FEEDER - CASHLA 110-ENNIS 110-1 | 59 | 40 |  | Scheduled | 19/03/2025 | 16/05/2025
TO-25-CSH-ENN-1-02 | 110kV FEEDER - CASHLA 110-ENNIS 110-1 | 59 | 40 |  | Scheduled | 19/03/2025 | 16/05/2025
TO-25-220 kV A2 @ CDU-03 | BUSBAR SECTION - CORDUFF 220-CORDUFF 220-220A2 | 14 | 10 | 10 | Proposed | 19/03/2025 | 01/04/2025
TO-25-220 kV B2 @ CDU-03 | BUSBAR SECTION - CORDUFF 220-CORDUFF 220-220B2 | 14 | 10 | 10 | Proposed | 19/03/2025 | 01/04/2025
TO-25-CDU-FIN-2-03 | 220kV FEEDER - CORDUFF 220-FINGLAS 220-2 | 14 | 10 |  | Proposed | 19/03/2025 | 01/04/2025
TO-25-CDU-FIN-2-05 | 220kV FEEDER - CORDUFF 220-FINGLAS 220-2 | 14 | 10 |  | Proposed | 19/03/2025 | 01/04/2025
TO-25-DRY-GOR-1-04 | 110kV FEEDER - DRYBRIDGE 110-GORMAN 110-1 | 3 | 3 |  | Scheduled | 19/03/2025 | 21/03/2025
TO-25-220 kV A2 @ FIN-03 | BUSBAR SECTION - FINGLAS 220-FINGLAS 220-220A2 | 14 | 10 |  | Proposed | 19/03/2025 | 01/04/2025
TO-25-220 kV A2 @ FIN-06 | BUSBAR SECTION - FINGLAS 220-FINGLAS 220-220A2 | 14 | 10 | 10 | Proposed | 19/03/2025 | 01/04/2025
TO-25-220 kV B2 @ FIN-03 | BUSBAR SECTION - FINGLAS 220-FINGLAS 220-220B2 | 14 | 10 |  | Proposed | 19/03/2025 | 01/04/2025
TO-25-FIN-220K2-07 | COUPLER/SECTIONALISING CB - FINGLAS 220-FINGLAS 220-220K2 | 14 | 10 | 10 | Proposed | 19/03/2025 | 01/04/2025
TO-25-FIN-220K2-03 | COUPLER/SECTIONALISING CB - FINGLAS 220-FINGLAS 220-220K2 | 14 | 10 |  | Proposed | 19/03/2025 | 01/04/2025
TO-25-FIN-220SA1-2CB-06 | COUPLER/SECTIONALISING CB - FINGLAS 220-FINGLAS 220-220SA1-2CB | 14 | 10 | 10 | Proposed | 19/03/2025 | 01/04/2025
TO-25-FIN-220SA1-2CB-11 | COUPLER/SECTIONALISING CB - FINGLAS 220-FINGLAS 220-220SA1-2CB | 14 | 10 | 10 | Proposed | 19/03/2025 | 01/04/2025
TO-25-FIN-220SB1-2CB-03 | COUPLER/SECTIONALISING CB - FINGLAS 220-FINGLAS 220-220SB1-2CB | 14 | 10 |  | Proposed | 19/03/2025 | 01/04/2025
TO-25-TH-T2001/2-01 | GENERATOR TRANSFORMER - TURLOUGH HILL 220-TURLOUGH HILL G1-T2001/2 | 10 | 7 | 7 | Scheduled | 23/03/2025 | 01/04/2025
TO-25-TH-T2001/2-02 | GENERATOR TRANSFORMER - TURLOUGH HILL 220-TURLOUGH HILL G1-T2001/2 | 10 | 7 | 7 | Proposed | 23/03/2025 | 01/04/2025
TO-25-AD-T2011/12-01 | GENERATOR TRANSFORMER - AGHADA 220-AGHADA G11/12-T2011/12 | 9 | 7 | 7 | Proposed | 24/03/2025 | 01/04/2025
TO-25-AD-T2011/12-02 | GENERATOR TRANSFORMER - AGHADA 220-AGHADA G11/12-T2011/12 | 9 | 7 | 7 | Proposed | 24/03/2025 | 01/04/2025
TO-25-CBT-CLU-1-02 | 110kV FEEDER - CASTLEBAGOT 110-CLUTTERLAND 110-1 | 5 | 5 | 5 | Scheduled | 24/03/2025 | 28/03/2025
TO-25-CLG-T122-01 | TSO CUSTOMER TRANSFORMER - CLOGHRAN 110-CLOGHRAN 20-T122 | 5 | 5 | 5 | Scheduled | 24/03/2025 | 28/03/2025
TO-25-CLG-T122-02 | TSO CUSTOMER TRANSFORMER - CLOGHRAN 110-CLOGHRAN 20-T122 | 5 | 5 | 5 | Proposed | 24/03/2025 | 28/03/2025
TO-25-DRY-110SA1-03 | SECTIONALISING DISCONNECT - DRYBRIDGE 110-DRYBRIDGE 110-110SA1 | 5 | 5 | 5 | Scheduled | 24/03/2025 | 28/03/2025
TO-25-DRY-110SA2-03 | SECTIONALISING DISCONNECT - DRYBRIDGE 110-DRYBRIDGE 110-110SA2 | 5 | 5 |  | Scheduled | 24/03/2025 | 28/03/2025
TO-25-DRY-LOU-1-02 | 110kV FEEDER - DRYBRIDGE 110-LOUTH 110-1 | 5 | 5 |  | Scheduled | 24/03/2025 | 28/03/2025
TO-25-DRY-OBE-1-03 | 110kV FEEDER - DRYBRIDGE 110-OLDBRIDGE 110-1 | 74 | 50 | 50 | Proposed | 24/03/2025 | 05/06/2025
TO-25-DRY-OBE-1-01 | 110kV FEEDER - DRYBRIDGE 110-OLDBRIDGE 110-1 | 74 | 50 |  | Proposed | 24/03/2025 | 05/06/2025
TO-25-DRY-OBE-1-02 | 110kV FEEDER - DRYBRIDGE 110-OLDBRIDGE 110-1 | 74 | 50 | 50 | Scheduled | 24/03/2025 | 05/06/2025
TO-25-DRY-T141-01 | DISTRIBUTION TRANSFORMER - DRYBRIDGE 110-DRYBRIDGE 38-T141 | 5 | 5 | 5 | Reference | 24/03/2025 | 28/03/2025
TO-25-220 kV A2 @ FIN-07 | BUSBAR SECTION - FINGLAS 220-FINGLAS 220-220A2 | 12 | 10 | 10 | Proposed | 24/03/2025 | 04/04/2025
TO-25-FIN-220K2-09 | COUPLER/SECTIONALISING CB - FINGLAS 220-FINGLAS 220-220K2 | 12 | 10 | 10 | Proposed | 24/03/2025 | 04/04/2025
TO-25-FIN-220SA1-2CB-12 | COUPLER/SECTIONALISING CB - FINGLAS 220-FINGLAS 220-220SA1-2CB | 12 | 10 | 10 | Proposed | 24/03/2025 | 04/04/2025
TO-25-FIN GIS-T2106-02 | TRANSFORMER - FINGLAS 220-FINGLAS GIS 110-T2106 | 12 | 10 | 10 | Proposed | 24/03/2025 | 04/04/2025
TO-25-GLN-T133-01 | GENERATOR TRANSFORMER - GALLANSTOWN 110-GALLANSTOWN 33-T133 | 5 | 5 | 5 | Proposed | 24/03/2025 | 28/03/2025
TO-25-GLN-T133-02 | GENERATOR TRANSFORMER - GALLANSTOWN 110-GALLANSTOWN 33-T133 | 5 | 5 | 5 | Proposed | 24/03/2025 | 28/03/2025
TO-25-ISH-T2001-01 | GENERATOR TRANSFORMER - IRISHTOWN 220-IRISHTOWN G1-T2001 | 4 | 4 | 4 | Proposed | 24/03/2025 | 27/03/2025
TO-25-220 kV A4 @ KRA-01 | BUSBAR SECTION - KNOCKRAHA 220-KNOCKRAHA 220-220A4 | 75 | 51 | 51 | Proposed | 24/03/2025 | 06/06/2025
TO-25-220 kV B4 @ KRA-01 | BUSBAR SECTION - KNOCKRAHA 220-KNOCKRAHA 220-220B4 | 75 | 51 | 51 | Proposed | 24/03/2025 | 06/06/2025
TO-25-KRA-220K4-01 | COUPLER/SECTIONALISING CB - KNOCKRAHA 220-KNOCKRAHA 220-220K4 | 75 | 51 | 51 | Proposed | 24/03/2025 | 06/06/2025
TO-25-KRA-220K4-02 | COUPLER/SECTIONALISING CB - KNOCKRAHA 220-KNOCKRAHA 220-220K4 | 75 | 51 | 51 | Proposed | 24/03/2025 | 06/06/2025
TO-25-KRA-220SA2-4CB-02 | COUPLER/SECTIONALISING CB - KNOCKRAHA 220-KNOCKRAHA 220-220SA2-4CB | 75 | 51 | 51 | Proposed | 24/03/2025 | 06/06/2025
TO-25-KRA-220SB2-4CB-02 | COUPLER/SECTIONALISING CB - KNOCKRAHA 220-KNOCKRAHA 220-220SB2-4CB | 75 | 51 | 51 | Proposed | 24/03/2025 | 06/06/2025
TO-25-110 kV A2 @ CLU-01 | BUSBAR SECTION - CLUTTERLAND 110-CLUTTERLAND 110-110A2 | 9 | 7 | 7 | Proposed | 27/03/2025 | 04/04/2025
TO-25-110 kV B2 @ CLU-01 | BUSBAR SECTION - CLUTTERLAND 110-CLUTTERLAND 110-110B2 | 9 | 7 | 7 | Proposed | 27/03/2025 | 04/04/2025
TO-25-CLU-110K2-01 | COUPLER/SECTIONALISING CB - CLUTTERLAND 110-CLUTTERLAND 110-110K2 | 9 | 7 | 7 | Proposed | 27/03/2025 | 04/04/2025
TO-25-CLU-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - CLUTTERLAND 110-CLUTTERLAND 110-110SA1-2CB | 9 | 7 | 7 | Proposed | 27/03/2025 | 04/04/2025
TO-25-CLU-110SB1-2CB-01 | COUPLER/SECTIONALISING CB - CLUTTERLAND 110-CLUTTERLAND 110-110SB1-2CB | 9 | 7 | 7 | Proposed | 27/03/2025 | 04/04/2025
TO-25-GLE-KCR-1-01 | 110kV FEEDER - GLENLARA 110-KNOCKACUMMER 110-1 | 13 | 10 | 10 | Proposed | 30/03/2025 | 11/04/2025
TO-25-KCR-T121-01 | GENERATOR TRANSFORMER - KNOCKACUMMER 110-KNOCKACUMMER 20-T121 | 13 | 10 | 10 | Proposed | 30/03/2025 | 11/04/2025
TO-25-CLO-CRD-1-01 | 110kV FEEDER - CLOGHER 110-CROAGHONAGH 110-1 | 5 | 5 | 5 | Proposed | 31/03/2025 | 04/04/2025
TO-25-CRD-T131-01 | GENERATOR TRANSFORMER - CROAGHONAGH 110-CROAGHONAGH 33-T131 | 5 | 5 | 5 | Proposed | 31/03/2025 | 04/04/2025
TO-25-MAY-RYB GIS-1-01 | 110kV FEEDER - MAYNOOTH 110-RYEBROOK GIS 110-1 | Unknown | Unknown | 5 | Planned | March | April
TO-25-WOH-T122-01 | GENERATOR TRANSFORMER - WOODHOUSE 110-WOODHOUSE 20-T122 | Unknown | Unknown | 3 | Planned | March | April
TO-25-WOH-T122-02 | GENERATOR TRANSFORMER - WOODHOUSE 110-WOODHOUSE 20-T122 | 4 | 4 | 4 | Proposed | 31/03/2025 | 03/04/2025
TO-25-AD-T2014-01 | GENERATOR TRANSFORMER - AGHADA 220-AGHADA G14-T2014 | 8 | 6 | 6 | Proposed | 01/04/2025 | 08/04/2025
TO-25-AD-T2014-02 | GENERATOR TRANSFORMER - AGHADA 220-AGHADA G14-T2014 | 8 | 6 | 6 | Proposed | 01/04/2025 | 08/04/2025
TO-25-GOR-T122-01 | GENERATOR TRANSFORMER - GORMAN 110-GORMAN 20-T122 | 1 | 1 | 1 | Proposed | 02/04/2025 | 02/04/2025
TO-25-NAV-T142-01 | DISTRIBUTION TRANSFORMER - NAVAN 110-NAVAN 38-T142 | Unknown | Unknown | 40 | Reference (Planned) | April | May
TO-25-TH-T2003/4-01 | GENERATOR TRANSFORMER - TURLOUGH HILL 220-TURLOUGH HILL G1-T2003/4 | 10 | 8 | 8 | Proposed | 02/04/2025 | 11/04/2025
TO-25-CBT-CLU-1-01 | 110kV FEEDER - CASTLEBAGOT 110-CLUTTERLAND 110-1 | 2 | 2 | 2 | Proposed | 03/04/2025 | 04/04/2025
TO-25-FIN-SHL-1-03 | 220kV FEEDER - FINGLAS 220-SHELLYBANKS 220-1 | Unknown | Unknown | 15 | Planned | April | April
TO-25-TEN-T132-02 | GENERATOR TRANSFORMER - TIMAHOE 110-TIMAHOE 33-T132 | 1 | 1 | 1 | Proposed | 03/04/2025 | 03/04/2025
TO-25-AD-ST101-01 | GENERATOR TRANSFORMER - AGHADA 110-AGHADA 10-ST101 | 8 | 6 | 6 | Proposed | 07/04/2025 | 14/04/2025
TO-25-AD-T2102-01 | TRANSFORMER - AGHADA 220-AGHADA 110-T2102 | 16 | 10 | 10 | Proposed | 07/04/2025 | 22/04/2025
TO-25-AD-WHI-1-01 | 110kV FEEDER - AGHADA 110-WHITEGATE 110-1 | 8 | 6 |  | Proposed | 07/04/2025 | 14/04/2025
TO-25-CF-CL-1-02 | 110kV FEEDER - CATHALEENS FALL 110-CLIFF 110-1 | 4 | 4 | 4 | Proposed | 07/04/2025 | 10/04/2025
TO-25-CL-T101-03 | GENERATOR TRANSFORMER - CLIFF 110-CLIFF G1-T101 | 4 | 4 | 4 | Proposed | 07/04/2025 | 10/04/2025
TO-25-CL-T102-01 | GENERATOR TRANSFORMER - CLIFF 110-CLIFF G2-T102 | 9 | 7 | 7 | Proposed | 07/04/2025 | 15/04/2025
TO-25-DEY-T132-01 | GENERATOR TRANSFORMER - DERRYCARNEY 110-DERRYCARNEY 33-T132 | Unknown | Unknown | 5 | Planned | April | April
TO-25-110 kV A2 @ RAF-01 | BUSBAR SECTION - RAFFEEN 110-RAFFEEN 110-110A2 | Unknown | Unknown |  | Planned | April | August
TO-25-110 kV B2 @ RAF-01 | BUSBAR SECTION - RAFFEEN 110-RAFFEEN 110-110B2 | Unknown | Unknown |  | Planned | April | August
TO-25-BGT-110K1-02 | COUPLER/SECTIONALISING CB - BALLYRAGGET 110-BALLYRAGGET 110-110K1 | 3 | 3 | 3 | Proposed | 09/04/2025 | 11/04/2025
TO-25-BGT-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - BALLYRAGGET 110-BALLYRAGGET 110-110SA1-2CB | 3 | 3 | 3 | Proposed | 09/04/2025 | 11/04/2025
TO-25-BGT-110SB1-2CB-02 | COUPLER/SECTIONALISING CB - BALLYRAGGET 110-BALLYRAGGET 110-110SB1-2CB | 3 | 3 | 3 | Proposed | 09/04/2025 | 11/04/2025
TO-25-BGT-KKY-1-02 | 110kV FEEDER - BALLYRAGGET 110-KILKENNY 110-1 | 3 | 3 | 3 | Proposed | 09/04/2025 | 11/04/2025
TO-25-BGT-141-02 | DISTRIBUTION TRANSFORMER - BALLYRAGGET 110-BALLYRAGGET 38-T141 | 3 | 3 | 3 | Reference (Proposed) | 09/04/2025 | 11/04/2025
TO-25-220 kV A2 @ SH-03 | BUSBAR SECTION - SHANNONBRIDGE 220-SHANNONBRIDGE 220-220A2 | Unknown | Unknown | 2 | Planned | April | April
TO-25-220 kV B2 @ SH-03 | BUSBAR SECTION - SHANNONBRIDGE 220-SHANNONBRIDGE 220-220B2 | Unknown | Unknown | 2 | Planned | April | April
TO-25-SH-220K1-2-01 | COUPLER/SECTIONALISING CB - SHANNONBRIDGE 220-SHANNONBRIDGE 220-220K1-2 | Unknown | Unknown |  | Planned | April | April
TO-25-BRT-T224-01 | TSO CUSTOMER TRANSFORMER - BRACETOWN 220-BRACETOWN 20-T224 | Unknown | Unknown | 33 | Planned | April | May
TO-25-KLN-SH-1-01 | 220kV FEEDER - KILLONAN 220-SHANNONBRIDGE 220-1 | Unknown | Unknown |  | Planned | April | April
TO-25-BGT-110K1-01 | COUPLER/SECTIONALISING CB - BALLYRAGGET 110-BALLYRAGGET 110-110K1 | 2 | 2 |  | Proposed | 14/04/2025 | 15/04/2025
TO-25-110kV B1 @ BGT-01 | BUSBAR SECTION - BALLYRAGGET 110-BALLYRAGGET 110-110B1 | 2 | 2 | 2 | Proposed | 14/04/2025 | 15/04/2025
TO-25-BGT-110SB1-2CB-01 | COUPLER/SECTIONALISING CB - BALLYRAGGET 110-BALLYRAGGET 110-110SB1-2CB | 2 | 2 |  | Proposed | 14/04/2025 | 15/04/2025
TO-25-BGT-KKY-1-01 | 110kV FEEDER - BALLYRAGGET 110-KILKENNY 110-1 | 2 | 2 |  | Proposed | 14/04/2025 | 15/04/2025
TO-25-CHA-GLE-1-01 | 110kV FEEDER - CHARLEVILLE 110-GLENLARA 110-1 | Unknown | Unknown | 30 | Planned | April | May
TO-25-RRU-T122-01 | GENERATOR TRANSFORMER - RATRUSSAN 110-RATRUSSAN 20-T122 | 5 | 4 | 4 | Proposed | 14/04/2025 | 18/04/2025
TO-25-RRU-T122-02 | GENERATOR TRANSFORMER - RATRUSSAN 110-RATRUSSAN 20-T122 | 5 | 4 | 4 | Proposed | 14/04/2025 | 18/04/2025
TO-25-PRN-T4301-01 | TRANSFORMER - PORTAN 400-PORTAN 260-T4301 | Unknown | Unknown | 3 | Planned | April | April
TO-25-PRN-T4301-02 | TRANSFORMER - PORTAN 400-PORTAN 260-T4301 | 4 | 3 | 3 | Proposed | 15/04/2025 | 18/04/2025
TO-25-PRN-WOO-1-01 | 400kV FEEDER - PORTAN 400-WOODLAND 400-1 | Unknown | Unknown | 3 | Planned | April | April
TO-25-PRN-WOO-1-02 | 400kV FEEDER - PORTAN 400-WOODLAND 400-1 | 4 | 3 | 3 | Proposed | 15/04/2025 | 18/04/2025
TO-25-WOO-400K1-2-01 | COUPLER/SECTIONALISING CB - WOODLAND 400-WOODLAND 400-400K1-2 | Unknown | Unknown | 3 | Planned | April | April
TO-25-WOO-T4201-02 | TRANSFORMER - WOODLAND 400-WOODLAND 220-T4201 | Unknown | Unknown | 3 | Planned | April | April
TO-25-KTN-WAT-1-02 | 110kV FEEDER - KILLOTERAN 110-WATERFORD 110-1 | Unknown | Unknown | 20 | Planned | April | May
TO-25-220 kV A1 @ SH-01 | BUSBAR SECTION - SHANNONBRIDGE 220-SHANNONBRIDGE 220-220A1 | Unknown | Unknown |  | Planned | April | April
TO-25-220 kV A2 @ SH-02 | BUSBAR SECTION - SHANNONBRIDGE 220-SHANNONBRIDGE 220-220A2 | Unknown | Unknown |  | Planned | April | April
TO-25-220 kV B1 @ SH-01 | BUSBAR SECTION - SHANNONBRIDGE 220-SHANNONBRIDGE 220-220B1 | Unknown | Unknown |  | Planned | April | April
TO-25-220 kV B2 @ SH-02 | BUSBAR SECTION - SHANNONBRIDGE 220-SHANNONBRIDGE 220-220B2 | Unknown | Unknown |  | Planned | April | April
TO-25-CLW-KLS-1-02 | 110kV FEEDER - CARLOW 110-KELLIS 110-1 | Unknown | Unknown | 40 | Planned | April | June
TO-25-CLW-KLS-1-05 | 110kV FEEDER - CARLOW 110-KELLIS 110-1 | Unknown | Unknown | 11 | Planned | April | May
TO-25-CDK-LWD-1-01 | 110kV FEEDER - CASTLEDOCKRELL 110-LODGEWOOD 110-1 | Unknown | Unknown | 5 | Planned | April | April
TO-25-CDK-T121-01 | GENERATOR TRANSFORMER - CASTLEDOCKRELL 110-CASTLEDOCKRELL 20-T121 | Unknown | Unknown | 5 | Reference (Planned) | April | April
TO-25-LWD-110K1-2-01 | COUPLER/SECTIONALISING CB - LODGEWOOD 110-LODGEWOOD 110-110K1-2 | Unknown | Unknown | 5 | Planned | April | April
TO-25-LWD-T2102-01 | TRANSFORMER - LODGEWOOD 220-LODGEWOOD 110-T2102 | Unknown | Unknown | 5 | Planned | April | April
TO-25-220 kV B2 @ MAY-01 | BUSBAR SECTION - MAYNOOTH 220-MAYNOOTH 220-220B2 | Unknown | Unknown |  | Planned | April | June
TO-25-MAY-SH-1-01 | 220kV FEEDER - MAYNOOTH 220-SHANNONBRIDGE 220-1 | Unknown | Unknown |  | Planned | April | September
TO-25-AUN-110K1-01 | COUPLER/SECTIONALISING CB - AUNGIERSTOWN 110-AUNGIERSTOWN 110-110K1 | 3 | 3 | 3 | Proposed | 23/04/2025 | 25/04/2025
TO-25-AUN-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - AUNGIERSTOWN 110-AUNGIERSTOWN 110-110SA1-2CB | 3 | 3 | 3 | Proposed | 23/04/2025 | 25/04/2025
TO-25-AUN-110SB1-2CB-01 | COUPLER/SECTIONALISING CB - AUNGIERSTOWN 110-AUNGIERSTOWN 110-110SB1-2CB | 3 | 3 | 3 | Proposed | 23/04/2025 | 25/04/2025
TO-25-GOR-LOU-1-02 | 220kV FEEDER - GORMAN 220-LOUTH 220-1 | Unknown | Unknown | 10 | Planned | April | May
TO-25-ROP-T131-01 | GENERATOR TRANSFORMER - ROSSPILE 110-ROSSPILE 33-T131 | 1 | 1 | 1 | Proposed | 23/04/2025 | 23/04/2025
TO-25-ROP-T131-02 | GENERATOR TRANSFORMER - ROSSPILE 110-ROSSPILE 33-T131 | 1 | 1 | 1 | Proposed | 23/04/2025 | 23/04/2025
TO-25-CD-T103-02 | GENERATOR TRANSFORMER - CARRIGADROHID 110-CARRIGADROHID G3-T103 | 6 | 4 | 4 | Proposed | 24/04/2025 | 29/04/2025
TO-25-CF-T104-01 | GENERATOR TRANSFORMER - CATHALEENS FALL 110-CATHALEENS FALL G4-T104 | 14 | 9 | 9 | Proposed | 24/04/2025 | 07/05/2025
TO-25-110 kV A1 @ CKG-01 | BUSBAR SECTION - CORKAGH 110-CORKAGH 110-110A1 | Unknown | Unknown | 10 | Planned | April | May
TO-25-110 kV B1 @ CKG-01 | BUSBAR SECTION - CORKAGH 110-CORKAGH 110-110B1 | Unknown | Unknown | 10 | Planned | April | May
TO-25-CKG-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - CORKAGH 110-CORKAGH 110-110SA1-2CB | Unknown | Unknown | 10 | Planned | April | May
TO-25-CKG-110SA1-3CB-01 | COUPLER/SECTIONALISING CB - CORKAGH 110-CORKAGH 110-110SA1-3CB | Unknown | Unknown | 10 | Planned | April | May
TO-25-CKG-110SB1-2CB-01 | COUPLER/SECTIONALISING CB - CORKAGH 110-CORKAGH 110-110SB1-2CB | Unknown | Unknown | 10 | Planned | April | May
TO-25-CKG-110SB1-3CB-01 | COUPLER/SECTIONALISING CB - CORKAGH 110-CORKAGH 110-110SB1-3CB | Unknown | Unknown | 10 | Planned | April | May
TO-25-CAH-110K1-2-01 | COUPLER/SECTIONALISING CB - CAHIR 110-CAHIR 110-110K1-2 | Unknown | Unknown | 30 | Planned | April | June
TO-25-CKM GIS-ISH-1-01 | 220kV FEEDER - CARRICKMINES GIS 220-IRISHTOWN 220-1 | Unknown | Unknown | 14 | Planned | April | May
TO-25-CRA-WEX-1-02 | 110kV FEEDER - CRANE 110-WEXFORD 110-1 | Unknown | Unknown |  | Planned | April | September
TO-25-CD-KBY-1-01 | 110kV FEEDER - CARRIGADROHID 110-KILBARRY 110-1 | Unknown | Unknown |  | Planned | May | May
TO-25-CD-KBY-1-02 | 110kV FEEDER - CARRIGADROHID 110-KILBARRY 110-1 | Unknown | Unknown | 10 | Planned | May | May
TO-25-CD-MAC-1-01 | 110kV FEEDER - CARRIGADROHID 110-MACROOM 110-1 | Unknown | Unknown | 45 | Planned | May | July
TO-25-CD-T103-01 | GENERATOR TRANSFORMER - CARRIGADROHID 110-CARRIGADROHID G3-T103 | Unknown | Unknown |  | Planned | May | May
TO-25-CF-SRA-2-01 | 110kV FEEDER - CATHALEENS FALL 110-SRANANAGH 110-2 | Unknown | Unknown |  | Planned | May | July
TO-25-BUF-KNY-1-01 | 110kV FEEDER - BUFFY 110-KNOCKRANNY 110-1 | Unknown | Unknown | 3 | Planned | May | May
TO-25-BUF-T131-01 | GENERATOR TRANSFORMER - BUFFY 110-BUFFY 33-T131 | Unknown | Unknown | 3 | Planned | May | May
TO-25-CGG-DMY-1-01 | 110kV FEEDER - CARRIGDANGAN 110-DUNMANWAY 110-1 | Unknown | Unknown | 7 | Planned | May | May
TO-25-CGG-T131-01 | GENERATOR TRANSFORMER - CARRIGDANGAN 110-CARRIGDANGAN 33-T131 | Unknown | Unknown | 7 | Planned | May | May
TO-25-CBT-CKG-2-01 | 110kV FEEDER - CASTLEBAGOT 110-CORKAGH 110-2 | Unknown | Unknown | 2 | Planned | May | May
TO-25-LIS-T131-01 | GENERATOR TRANSFORMER - LISDRUM 110-LISDRUM 33-T131 | Unknown | Unknown | 8 | Planned | May | May
TO-25-BK-SKY-1-01 | 110kV FEEDER - BELLACORICK 110-SRAHNAKILLY 110-1 | Unknown | Unknown | 11 | Planned | May | May
TO-25-SKY-110SA1-01 | SECTIONALISING DISCONNECT - SRAHNAKILLY 110-SRAHNAKILLY 110-110SA1 | Unknown | Unknown | 11 | Planned | May | May
TO-25-SKY-110SA2-01 | SECTIONALISING DISCONNECT - SRAHNAKILLY 110-SRAHNAKILLY 110-110SA2 | Unknown | Unknown | 11 | Planned | May | May
TO-25-SKY-T131-02 | GENERATOR TRANSFORMER - SRAHNAKILLY 110-SRAHNAKILLY 33-T131 | Unknown | Unknown | 11 | Planned | May | May
TO-25-SKY-T132-02 | GENERATOR TRANSFORMER - SRAHNAKILLY 110-SRAHNAKILLY 33-T132 | Unknown | Unknown | 11 | Planned | May | May
TO-25-KTN-110SA1-01 | SECTIONALISING DISCONNECT - KILLOTERAN 110-KILLOTERAN 110-110SA1 | 7 | 5 |  | Scheduled | 09/05/2025 | 15/05/2025
TO-25-KTN-110SA1-02 | SECTIONALISING DISCONNECT - KILLOTERAN 110-KILLOTERAN 110-110SA1 | Unknown | Unknown | 6 | Planned | May | May
TO-25-KTN-110SA2-01 | SECTIONALISING DISCONNECT - KILLOTERAN 110-KILLOTERAN 110-110SA2 | 7 | 5 | 5 | Scheduled | 09/05/2025 | 15/05/2025
TO-25-KTN-110SA2-02 | SECTIONALISING DISCONNECT - KILLOTERAN 110-KILLOTERAN 110-110SA2 | Unknown | Unknown | 6 | Planned | May | May
TO-25-KTN-T102-02 | DISTRIBUTION TRANSFORMER - KILLOTERAN 110-KILLOTERAN 10-T102 | Unknown | Unknown | 6 | Reference (Planned) | May | May
TO-25-WAT-110SA1-02 | SECTIONALISING DISCONNECT - WATERFORD 110-WATERFORD 110-110SA1 | Unknown | Unknown | 6 | Planned | May | May
TO-25-WAT-110SA2-02 | SECTIONALISING DISCONNECT - WATERFORD 110-WATERFORD 110-110SA2 | Unknown | Unknown | 6 | Planned | May | May
TO-25-WAT-T141-01 | DISTRIBUTION TRANSFORMER - WATERFORD 110-WATERFORD 38-T141 | Unknown | Unknown | 6 | Reference (Planned) | May | May
TO-25-BIN-T141-01 | DISTRIBUTION TRANSFORMER - BINBANE 110-BINBANE 38-T141 | Unknown | Unknown |  | Reference (Planned) | May | August
TO-25-BGH-110SA1-01 | SECTIONALISING DISCONNECT - BOGGERAGH 110-BOGGERAGH 110-110SA1 | Unknown | Unknown | 10 | Planned | May | May
TO-25-BGH-110SA2-01 | SECTIONALISING DISCONNECT - BOGGERAGH 110-BOGGERAGH 110-110SA2 | Unknown | Unknown | 10 | Planned | May | May
TO-25-BGH-CLA-1-01 | 110kV FEEDER - BOGGERAGH 110-CLASHAVOON 110-1 | Unknown | Unknown | 10 | Planned | May | May
TO-25-BGH-T121-02 | GENERATOR TRANSFORMER - BOGGERAGH 110-BOGGERAGH 20-T121 | Unknown | Unknown | 10 | Planned | May | May
TO-25-BGH-T132-01 | GENERATOR TRANSFORMER - BOGGERAGH 110-BOGGERAGH 33-T132 | Unknown | Unknown | 10 | Planned | May | May
TO-25-BGH-T142-01 | DISTRIBUTION TRANSFORMER - BOGGERAGH 110-BOGGERAGH 38-T142 | Unknown | Unknown | 10 | Reference (Planned) | May | May
TO-25-GRO-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - GARROW 110-GARROW 110-110SA1-2CB | Unknown | Unknown | 5 | Planned | May | May
TO-25-GRO-T122-01 | GENERATOR TRANSFORMER - GARROW 110-GARROW 20-T122 | Unknown | Unknown | 5 | Planned | May | May
TO-25-GOR-MTH-1-01 | 110kV FEEDER - GORMAN 110-MEATH HILL 110-1 | Unknown | Unknown | 15 | Planned | May | May
TO-25-PA-110SA1-02 | SECTIONALISING DISCONNECT - POLLAPHUCA 110-POLLAPHUCA 110-110SA1 | Unknown | Unknown | 15 | Planned | May | May
TO-25-PA-110SA2-02 | SECTIONALISING DISCONNECT - POLLAPHUCA 110-POLLAPHUCA 110-110SA2 | Unknown | Unknown | 15 | Planned | May | May
TO-25-PA-T101-02 | GENERATOR TRANSFORMER - POLLAPHUCA 110-POLLAPHUCA G1-T101 | Unknown | Unknown | 15 | Planned | May | May
TO-25-SKY-T131-01 | GENERATOR TRANSFORMER - SRAHNAKILLY 110-SRAHNAKILLY 33-T131 | Unknown | Unknown | 5 | Planned | May | May
TO-25-SKY-T132-01 | GENERATOR TRANSFORMER - SRAHNAKILLY 110-SRAHNAKILLY 33-T132 | Unknown | Unknown | 5 | Planned | May | May
TO-25-STR-T141-02 | DISTRIBUTION TRANSFORMER - STRATFORD 110-STRATFORD 38-T141 | Unknown | Unknown | 15 | Reference (Planned) | May | May
TO-25-STR,T-CLW-1-02 | 110kV FEEDER - STRATFORD tee-CARLOW 110-1 | Unknown | Unknown | 15 | Planned | May | May
TO-25-STR,T-PA-1-02 | 110kV FEEDER - STRATFORD tee-POLLAPHUCA 110-1 | Unknown | Unknown | 15 | Planned | May | May
TO-25-STR,T-STR-1-02 | 110kV FEEDER - STRATFORD tee-STRATFORD 110-1 | Unknown | Unknown | 15 | Planned | May | May
TO-25-CLH-T122-01 | GENERATOR TRANSFORMER - CLAHANE 110-CLAHANE 20-T122 | Unknown | Unknown | 1 | Planned | May | May
TO-25-KNY-UGL-1-01 | 110kV FEEDER - KNOCKRANNY 110-UGGOOL 110-1 | Unknown | Unknown | 3 | Planned | May | May
TO-25-UGL-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - UGGOOL 110-UGGOOL 110-110SA1-2CB | 3 | 3 | 3 | Proposed | 13/05/2025 | 15/05/2025
TO-25-UGL-T131-01 | GENERATOR TRANSFORMER - UGGOOL 110-UGGOOL 33-T131 | Unknown | Unknown | 8 | Planned | May | May
TO-25-UGL-T132-01 | GENERATOR TRANSFORMER - UGGOOL 110-UGGOOL 33-T132 | 3 | 3 | 3 | Proposed | 13/05/2025 | 15/05/2025
TO-25-CL-T101-02 | GENERATOR TRANSFORMER - CLIFF 110-CLIFF G1-T101 | Unknown | Unknown | 8 | Planned | May | May
TO-25-MLC-T121-01 | GENERATOR TRANSFORMER - MOUNTLUCAS 110-MOUNTLUCAS 20-T121 | Unknown | Unknown | 1 | Planned | May | May
TO-25-MLC-T121-02 | GENERATOR TRANSFORMER - MOUNTLUCAS 110-MOUNTLUCAS 20-T121 | Unknown | Unknown | 2 | Planned | May | May
TO-25-GAL-GAL GIS-1-01 | 110kV FEEDER - GALWAY 110-GALWAY GIS 110-1 | Unknown | Unknown | 160 | Planned | May | December
TO-25-GAL-T103-01 | DISTRIBUTION TRANSFORMER - GALWAY 110-GALWAY 10-T103 | Unknown | Unknown | 46 | Planned | May | July
TO-25-ATH-110SA1-2CB-03 | COUPLER/SECTIONALISING CB - ATHLONE 110-ATHLONE 110-110SA1-2CB | Unknown | Unknown |  | Planned | May | June
TO-25-ATH-SH-1-03 | 110kV FEEDER - ATHLONE 110-SHANNONBRIDGE 110-1 | Unknown | Unknown |  | Planned | May | June
TO-25-ATH-T142-03 | DISTRIBUTION TRANSFORMER - ATHLONE 110-ATHLONE 38-T142 | Unknown | Unknown |  | Reference (Planned) | May | June
TO-25-AUG-CFM-2-01 | 110kV FEEDER - AUGHINISH 110-CASTLEFARM 110-2 | Unknown | Unknown | 10 | Planned | May | May
TO-25-BUT-KTN-1-03 | 110kV FEEDER - BUTLERSTOWN 110-KILLOTERAN 110-1 | Unknown | Unknown | 40 | Planned | May | July
TO-25-CFM-T102-01 | TSO CUSTOMER TRANSFORMER - CASTLEFARM 110-CASTLEFARM 10-T102 | Unknown | Unknown | 10 | Reference (Planned) | May | May
TO-25-GLE-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - GLENLARA 110-GLENLARA 110-110SA1-2CB | Unknown | Unknown | 5 | Planned | May | May
TO-25-GLE-T142-01 | DISTRIBUTION TRANSFORMER - GLENLARA 110-GLENLARA 38-T142 | Unknown | Unknown | 5 | Reference (Planned) | May | May
TO-25-LSN-T131-01 | GENERATOR TRANSFORMER - LISHEEN 110-LISHEEN 33-T131 | Unknown | Unknown |  | Planned | May | May
TO-25-RYB GIS-T105-02 | TSO CUSTOMER TRANSFORMER - RYEBROOK GIS 110-RYEBROOK 10-T105 | 12 | 10 | 10 | Proposed | 19/05/2025 | 30/05/2025
TO-25-FIN-SHL-1-02 | 220kV FEEDER - FINGLAS 220-SHELLYBANKS 220-1 | Unknown | Unknown | 50 | Planned | May | July
TO-25-KLH-KNY-1-01 | 110kV FEEDER - KNOCKALOUGH 110-KNOCKRANNY 110-1 | Unknown | Unknown | 3 | Planned | May | May
TO-25-KLH-T121-01 | GENERATOR TRANSFORMER - KNOCKALOUGH 110-KNOCKALOUGH 20-T121 | Unknown | Unknown | 3 | Planned | May | May
TO-25-LSA-T131-01 | GENERATOR TRANSFORMER - LISLEA 110-LISLEA 33-T131 | Unknown | Unknown | 3 | Planned | May | May
TO-25-REM-110SA1-01 | SECTIONALISING DISCONNECT - REAMORE 110-REAMORE 110-110SA1 | Unknown | Unknown | 8 | Planned | May | May
TO-25-REM-110SA2-01 | SECTIONALISING DISCONNECT - REAMORE 110-REAMORE 110-110SA2 | Unknown | Unknown | 8 | Planned | May | May
TO-25-REM-T141-01 | DISTRIBUTION TRANSFORMER - REAMORE 110-REAMORE 38-T141 | Unknown | Unknown | 8 | Reference (Planned) | May | May
TO-25-REM-T142-01 | DISTRIBUTION TRANSFORMER - REAMORE 110-REAMORE 38-T142 | Unknown | Unknown | 8 | Reference (Planned) | May | May
TO-25-REM-TRL-1-01 | 110kV FEEDER - REAMORE 110-TRALEE 110-1 | Unknown | Unknown | 8 | Planned | May | May
TO-25-BWR-CRA-1-01 | 110kV FEEDER - BALLYWATER 110-CRANE 110-1 | Unknown | Unknown |  | Planned | May | June
TO-25-BWR-T124-01 | GENERATOR TRANSFORMER - BALLYWATER 110-BALLYWATER 20-T124 | Unknown | Unknown |  | Reference (Planned) | May | June
TO-25-CRA-110SA1-01 | SECTIONALISING DISCONNECT - CRANE 110-CRANE 110-110SA1 | Unknown | Unknown |  | Planned | May | June
TO-25-CRA-110SA2-01 | SECTIONALISING DISCONNECT - CRANE 110-CRANE 110-110SA2 | Unknown | Unknown |  | Planned | May | June
TO-25-CRA-LWD-1-01 | 110kV FEEDER - CRANE 110-LODGEWOOD 110-1 | Unknown | Unknown |  | Planned | May | June
TO-25-CRA-T122-01 | DISTRIBUTION TRANSFORMER - CRANE 110-CRANE 20-T122 | Unknown | Unknown |  | Reference (Planned) | May | June
TO-25-CLO-MRY-1-01 | 110kV FEEDER - CLOGHER 110-MULREAVY 110-1 | Unknown | Unknown | 5 | Planned | May | May
TO-25-MRY-T131-01 | GENERATOR TRANSFORMER - MULREAVY 110-MULREAVY 33-T131 | Unknown | Unknown | 5 | Planned | May | May
TO-25-220 kV A2 @ WOO-05 | BUSBAR SECTION - WOODLAND 220-WOODLAND 220-220A2 | Unknown | Unknown | 10 | Planned | May | June
TO-25-WOO-220K1-2-02 | COUPLER/SECTIONALISING CB - WOODLAND 220-WOODLAND 220-220K1-2 | Unknown | Unknown | 33 | Planned | May | July
TO-25-BLC-DND-1-01 | 110kV FEEDER - BELCAMP 110-DARNDALE 110-1 | 2 | 2 | 2 | Scheduled | 29/05/2025 | 30/05/2025
TO-25-110 kV A1 @ DND-01 | BUSBAR SECTION - DARNDALE 110-DARNDALE 110-110A1 | 2 | 2 | 2 | Scheduled | 29/05/2025 | 30/05/2025
TO-25-DND-110K1-01 | COUPLER/SECTIONALISING CB - DARNDALE 110-DARNDALE 110-110K1 | 2 | 2 | 2 | Scheduled | 29/05/2025 | 30/05/2025
TO-25-DND-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - DARNDALE 110-DARNDALE 110-110SA1-2CB | 2 | 2 | 2 | Scheduled | 29/05/2025 | 30/05/2025
TO-25-FIN-FIN GIS-2-01 | 110kV FEEDER - FINGLAS 110-FINGLAS GIS 110-2 | Unknown | Unknown | 150 | Planned | May | December
TO-25-FIN-T2104-01 | TRANSFORMER - FINGLAS 220-FINGLAS 110-T2104 | Unknown | Unknown |  | Planned | May | September
TO-25-RYB GIS-T106-02 | TSO CUSTOMER TRANSFORMER - RYEBROOK GIS 110-RYEBROOK 10-T106 | 12 | 9 | 9 | Proposed | 02/06/2025 | 13/06/2025
TO-25-CDK-LWD-1-02 | 110kV FEEDER - CASTLEDOCKRELL 110-LODGEWOOD 110-1 | Unknown | Unknown | 4 | Planned | June | June
TO-25-CDK-T121-02 | GENERATOR TRANSFORMER - CASTLEDOCKRELL 110-CASTLEDOCKRELL 20-T121 | Unknown | Unknown | 4 | Reference (Planned) | June | June
TO-25-DRM-MEE-1-01 | 110kV FEEDER - DRUMKEEN 110-MEENTYCAT 110-1 | Unknown | Unknown | 9 | Planned | June | June
TO-25-MEE-T121-01 | GENERATOR TRANSFORMER - MEENTYCAT 110-MEENTYCAT 20-T121 | Unknown | Unknown | 9 | Planned | June | June
TO-25-CUN-T121-02 | GENERATOR TRANSFORMER - CUNGHILL 110-CUNGHILL 20-T121 | Unknown | Unknown | 6 | Planned | June | June
TO-25-RRU-T121-01 | GENERATOR TRANSFORMER - RATRUSSAN 110-RATRUSSAN 20-T121 | Unknown | Unknown | 3 | Planned | June | June
TO-25-WOO-T4202-02 | TRANSFORMER - WOODLAND 400-WOODLAND 220-T4202 | Unknown | Unknown | 2 | Planned | June | June
TO-25-ATH-SH-1-04 | 110kV FEEDER - ATHLONE 110-SHANNONBRIDGE 110-1 | Unknown | Unknown | 10 | Planned | June | June
TO-25-IA-T101-02 | GENERATOR TRANSFORMER - INNISCARRA 110-INNISCARRA G1-T101 | Unknown | Unknown | 4 | Planned | June | June
TO-25-AGL-DYN-1-01 | 110kV FEEDER - AGANNYGAL 110-DERRYBRIEN 110-1 | Unknown | Unknown | 3 | Planned | June | June
TO-25-ATE-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - ATHEA 110-ATHEA 110-110SA1-2CB | Unknown | Unknown | 5 | Planned | June | June
TO-25-ATE-DRO-1-01 | 110kV FEEDER - ATHEA 110-DROMADA 110-1 | Unknown | Unknown | 5 | Planned | June | June
TO-25-ATE-KNR-1-01 | 110kV FEEDER - ATHEA 110-KNOCKANURE 110-1 | Unknown | Unknown | 5 | Planned | June | June
TO-25-ATE-T121-01 | GENERATOR TRANSFORMER - ATHEA 110-ATHEA 20-T121 | Unknown | Unknown | 5 | Planned | June | June
TO-25-ATE-TOB-1-01 | 110kV FEEDER - ATHEA 110-TOBERTOREEN 110-1 | Unknown | Unknown | 5 | Planned | June | June
TO-25-AUG-SK-4-01 | 110kV FEEDER - AUGHINISH 110-SEALROCK 110-4 | Unknown | Unknown | 5 | Planned | June | June
TO-25-110 kV A1 @ CF-02 | BUSBAR SECTION - CATHALEENS FALL 110-CATHALEENS FALL 110-110A1 | 12 | 10 | 10 | Proposed | 09/06/2025 | 20/06/2025
TO-25-110 kV B1 @ CF-01 | BUSBAR SECTION - CATHALEENS FALL 110-CATHALEENS FALL 110-110B1 | 12 | 10 | 10 | Proposed | 09/06/2025 | 20/06/2025
TO-25-CF-CLO-1-02 | 110kV FEEDER - CATHALEENS FALL 110-CLOGHER 110-1 | 12 | 10 | 10 | Proposed | 09/06/2025 | 20/06/2025
TO-25-110 kV A1 @ CLO-01 | BUSBAR SECTION - CLOGHER 110-CLOGHER 110-110A1 | 12 | 10 | 10 | Proposed | 09/06/2025 | 20/06/2025
TO-25-110 kV B1 @ CLO-01 | BUSBAR SECTION - CLOGHER 110-CLOGHER 110-110B1 | 12 | 10 | 10 | Proposed | 09/06/2025 | 20/06/2025
TO-25-DYN-T121-01 | GENERATOR TRANSFORMER - DERRYBRIEN 110-DERRYBRIEN 20-T121 | Unknown | Unknown | 3 | Reference (Planned) | June | June
TO-25-DER-KIN-1-03 | 110kV FEEDER - DERRYIRON 110-KINNEGAD 110-1 | Unknown | Unknown | 15 | Planned | June | June
TO-25-DER-T1/T2-02 | GENERATOR TRANSFORMER - DERRYIRON 110-RHODE 110-T1/T2 | Unknown | Unknown | 15 | Planned | June | June
TO-25-DRO-T121-01 | GENERATOR TRANSFORMER - DROMADA 110-DROMADA 20-T121 | Unknown | Unknown | 5 | Planned | June | June
TO-25-220 kV A2 @ DSN-01 | BUSBAR SECTION - DUNSTOWN 220-DUNSTOWN 220-220A2 | Unknown | Unknown |  | Planned | June | June
TO-25-GOR-MTH-1-02 | 110kV FEEDER - GORMAN 110-MEATH HILL 110-1 | Unknown | Unknown | 15 | Planned | June | June
TO-25-LIM-RAT-1-01 | 110kV FEEDER - LIMERICK 110-RATHKEALE 110-1 | Unknown | Unknown |  | Planned | June | June
TO-25-MTH-110SA1-02 | SECTIONALISING DISCONNECT - MEATH HILL 110-MEATH HILL 110-110SA1 | Unknown | Unknown | 15 | Planned | June | June
TO-25-MTH-110SA2-01 | SECTIONALISING DISCONNECT - MEATH HILL 110-MEATH HILL 110-110SA2 | Unknown | Unknown | 15 | Planned | June | June
TO-25-MTH-T142-01 | DISTRIBUTION TRANSFORMER - MEATH HILL 110-MEATH HILL 38-T142 | Unknown | Unknown | 15 | Reference (Planned) | June | June
TO-25-OBE-PLA-1-01 | 110kV FEEDER - OLDBRIDGE 110-PLATIN 110-1 | Unknown | Unknown |  | Planned | June | August
TO-25-SK-T104-01 | GENERATOR TRANSFORMER - SEALROCK 110-SEALROCK G4-T104 | Unknown | Unknown | 5 | Planned | June | June
TO-25-TOB-T132-01 | GENERATOR TRANSFORMER - TOBERTOREEN 110-TOBERTOREEN 33-T132 | Unknown | Unknown | 5 | Planned | June | June
TO-25-SLB-T132-01 | GENERATOR TRANSFORMER - SLIABH BAWN 110-SLIABH BAWN 33-T132 | Unknown | Unknown | 1 | Planned | June | June
TO-25-SLB-T132-02 | GENERATOR TRANSFORMER - SLIABH BAWN 110-SLIABH BAWN 33-T132 | Unknown | Unknown | 2 | Planned | June | June
TO-25-110 kV B1 @ CSH-02 | BUSBAR SECTION - CASHLA 110-CASHLA 110-110B1 | Unknown | Unknown |  | Planned | June | June
TO-25-MP GIS-T121-01 | GENERATOR TRANSFORMER - MONEYPOINT GIS 110-MONEYPOINT GIS 20-T121 | Unknown | Unknown | 5 | Planned | June | June
TO-25-RYB GIS-T107-02 | TSO CUSTOMER TRANSFORMER - RYEBROOK GIS 110-RYEBROOK 10-T107 | 12 | 10 | 10 | Proposed | 16/06/2025 | 27/06/2025
TO-25-CNO-KPG-1-01 | 110kV FEEDER - COOLNANOONAGH 110-KILPADDOGE 110-1 | Unknown | Unknown | 2 | Planned | June | June
TO-25-CNO-T131-01 | GENERATOR TRANSFORMER - COOLNANOONAGH 110-COOLNANOONAGH 33-T131 | Unknown | Unknown | 2 | Planned | June | June
TO-25-LLA-T133-01 | GENERATOR TRANSFORMER - LENALEA 110-LENALEA 33-T133 | Unknown | Unknown | 3 | Planned | June | June
TO-25-ATY-CLW-1-03 | 110kV FEEDER - ATHY 110-CARLOW 110-1 | Unknown | Unknown |  | Planned | June | June
TO-25-CLW-110SA1-02 | SECTIONALISING DISCONNECT - CARLOW 110-CARLOW 110-110SA1 | Unknown | Unknown |  | Planned | June | June
TO-25-CLW-110SA2-02 | SECTIONALISING DISCONNECT - CARLOW 110-CARLOW 110-110SA2 | Unknown | Unknown |  | Planned | June | June
TO-25-CLW-KLS-1-06 | 110kV FEEDER - CARLOW 110-KELLIS 110-1 | Unknown | Unknown |  | Planned | June | June
TO-25-CLW-T141-02 | DISTRIBUTION TRANSFORMER - CARLOW 110-CARLOW 38-T141 | Unknown | Unknown |  | Reference (Planned) | June | June
TO-25-BWR-CRA-1-02 | 110kV FEEDER - BALLYWATER 110-CRANE 110-1 | Unknown | Unknown |  | Planned | June | July
TO-25-BWR-T124-02 | GENERATOR TRANSFORMER - BALLYWATER 110-BALLYWATER 20-T124 | Unknown | Unknown |  | Reference (Planned) | June | July
TO-25-CKN-CGL-1-01 | 110kV FEEDER - CLONKEEN 110-COOMAGEARLAHY 110-1 | Unknown | Unknown | 6 | Planned | June | June
TO-25-CGL-110SA1-01 | SECTIONALISING DISCONNECT - COOMAGEARLAHY 110-COOMAGEARLAHY 110-110SA1 | Unknown | Unknown | 6 | Planned | June | June
TO-25-CGL-110SA2-01 | SECTIONALISING DISCONNECT - COOMAGEARLAHY 110-COOMAGEARLAHY 110-110SA2 | Unknown | Unknown | 6 | Planned | June | June
TO-25-CGL-GAE-1-01 | 110kV FEEDER - COOMAGEARLAHY 110-GLANLEE 110-1 | Unknown | Unknown | 6 | Planned | June | June
TO-25-CGL-T121-01 | GENERATOR TRANSFORMER - COOMAGEARLAHY 110-COOMAGEARLAHY 20-T121 | Unknown | Unknown | 6 | Planned | June | June
TO-25-CGL-T122-01 | GENERATOR TRANSFORMER - COOMAGEARLAHY 110-COOMAGEARLAHY 20-T122 | Unknown | Unknown | 6 | Planned | June | June
TO-25-CRA-110SA1-02 | SECTIONALISING DISCONNECT - CRANE 110-CRANE 110-110SA1 | Unknown | Unknown |  | Planned | June | July
TO-25-CRA-110SA2-02 | SECTIONALISING DISCONNECT - CRANE 110-CRANE 110-110SA2 | Unknown | Unknown |  | Planned | June | July
TO-25-CRA-LWD-1-02 | 110kV FEEDER - CRANE 110-LODGEWOOD 110-1 | Unknown | Unknown |  | Planned | June | July
TO-25-CRA-T122-02 | DISTRIBUTION TRANSFORMER - CRANE 110-CRANE 20-T122 | Unknown | Unknown |  | Reference (Planned) | June | July
TO-25-GAE-T121-01 | GENERATOR TRANSFORMER - GLANLEE 110-GLANLEE 20-T121 | Unknown | Unknown | 6 | Planned | June | June
TO-25-ATH-LA-1-02 | 110kV FEEDER - ATHLONE 110-LANESBORO 110-1 | Unknown | Unknown |  | Planned | June | July
TO-25-ATY-PLS-1-02 | 110kV FEEDER - ATHY 110-PORTLAOISE 110-1 | Unknown | Unknown | 50 | Planned | June | September
TO-25-220 kV B2 @ DSN-01 | BUSBAR SECTION - DUNSTOWN 220-DUNSTOWN 220-220B2 | Unknown | Unknown |  | Planned | June | July
TO-25-220 kV A1 @ LOU-02 | BUSBAR SECTION - LOUTH 220-LOUTH 220-220A1 | Unknown | Unknown | 20 | Planned | June | July
TO-25-220 kV B1 @ LOU-02 | BUSBAR SECTION - LOUTH 220-LOUTH 220-220B1 | Unknown | Unknown | 20 | Planned | June | July
TO-25-CF-T103-01 | GENERATOR TRANSFORMER - CATHALEENS FALL 110-CATHALEENS FALL G3-T103 | Unknown | Unknown | 9 | Planned | June | July
TO-25-ATY-PLS-1-01 | 110kV FEEDER - ATHY 110-PORTLAOISE 110-1 | Unknown | Unknown | 8 | Planned | June | July
TO-25-CUS-KIR-1-03 | 110kV FEEDER - CUSHALING 110-KILCUMBER 110-1 | Unknown | Unknown | 2 | Planned | June | June
TO-25-KIR-T131-04 | GENERATOR TRANSFORMER - KILCUMBER 110-KILCUMBER 33-T131 | Unknown | Unknown | 2 | Planned | June | June
TO-25-KIR-T131-01 | GENERATOR TRANSFORMER - KILCUMBER 110-KILCUMBER 33-T131 | Unknown | Unknown | 1 | Planned | June | June
TO-25-220 kV A2 @ WOO-06 | BUSBAR SECTION - WOODLAND 220-WOODLAND 220-220A2 | Unknown | Unknown | 2 | Planned | June | June
TO-25-WOO-220K1-2-03 | COUPLER/SECTIONALISING CB - WOODLAND 220-WOODLAND 220-220K1-2 | Unknown | Unknown | 11 | Planned | June | July
TO-25-WOO-T4202-03 | TRANSFORMER - WOODLAND 400-WOODLAND 220-T4202 | Unknown | Unknown | 2 | Planned | June | June
TO-25-BVK-COT-1-01 | 110kV FEEDER - BALLYVOUSKILL 110-COOMATAGGART 110-1 | Unknown | Unknown | 10 | Planned | June | July
TO-25-110 kV A1 @ CSH-02 | BUSBAR SECTION - CASHLA 110-CASHLA 110-110A1 | Unknown | Unknown |  | Planned | June | July
TO-25-CLU-T121-01 | TSO CUSTOMER TRANSFORMER - CLUTTERLAND 110-CLUTTERLAND 20-T121 | 5 | 5 | 5 | Proposed | 30/06/2025 | 04/07/2025
TO-25-COT-110SA1-01 | SECTIONALISING DISCONNECT - COOMATAGGART 110-COOMATAGGART 110-110SA1 | Unknown | Unknown | 10 | Planned | June | July
TO-25-COT-110SA2-01 | SECTIONALISING DISCONNECT - COOMATAGGART 110-COOMATAGGART 110-110SA2 | Unknown | Unknown | 10 | Planned | June | July
TO-25-COT-FILTER1-01 | CAPACITOR/SVC/REACTOR - COOMATAGGART 110-COOMATAGGART 110-FILTER1 | Unknown | Unknown | 10 | Planned | June | July
TO-25-COT-T132-01 | GENERATOR TRANSFORMER - COOMATAGGART 110-COOMATAGGART 33-T132 | Unknown | Unknown | 10 | Planned | June | July
TO-25-COT-T141-01 | DISTRIBUTION TRANSFORMER - COOMATAGGART 110-COOMATAGGART 38-T141 | Unknown | Unknown | 10 | Reference (Planned) | June | July
TO-25-LOU-AT3-02 | TRANSFORMER - LOUTH 220-LOUTH 275-AT3 | Unknown | Unknown |  | Planned | June | October
TO-25-LOU-MTH-1-01 | 110kV FEEDER - LOUTH 110-MEATH HILL 110-1 | Unknown | Unknown | 15 | Planned | June | July
TO-25-MTH-110SA1-01 | SECTIONALISING DISCONNECT - MEATH HILL 110-MEATH HILL 110-110SA1 | Unknown | Unknown | 15 | Planned | June | July
TO-25-MTH-110SA2-02 | SECTIONALISING DISCONNECT - MEATH HILL 110-MEATH HILL 110-110SA2 | Unknown | Unknown | 15 | Planned | June | July
TO-25-MTH-T141-01 | DISTRIBUTION TRANSFORMER - MEATH HILL 110-MEATH HILL 38-T141 | Unknown | Unknown | 15 | Reference (Planned) | June | July
TO-25-CUS-T101-03 | GENERATOR TRANSFORMER - CUSHALING 110-CUSHALING G1-T101 | Unknown | Unknown | 1 | Planned | July | July
TO-25-220 kV A1 @ LOU-06 | BUSBAR SECTION - LOUTH 220-LOUTH 220-220A1 | Unknown | Unknown | 9 | Planned | July | July
TO-25-220 kV B1 @ LOU-06 | BUSBAR SECTION - LOUTH 220-LOUTH 220-220B1 | Unknown | Unknown | 29 | Planned | July | August
TO-25-BWR-CRA-1-03 | 110kV FEEDER - BALLYWATER 110-CRANE 110-1 | Unknown | Unknown |  | Planned | July | July
TO-25-BWR-T124-03 | GENERATOR TRANSFORMER - BALLYWATER 110-BALLYWATER 20-T124 | Unknown | Unknown |  | Reference (Planned) | July | July
TO-25-CRA-110SA1-04 | SECTIONALISING DISCONNECT - CRANE 110-CRANE 110-110SA1 | Unknown | Unknown | 1 | Planned | July | July
TO-25-CRA-110SA2-03 | SECTIONALISING DISCONNECT - CRANE 110-CRANE 110-110SA2 | Unknown | Unknown |  | Planned | July | July
TO-25-CRA-LWD-1-03 | 110kV FEEDER - CRANE 110-LODGEWOOD 110-1 | Unknown | Unknown |  | Planned | July | July
TO-25-CRA-T122-03 | DISTRIBUTION TRANSFORMER - CRANE 110-CRANE 20-T122 | Unknown | Unknown |  | Reference (Planned) | July | July
TO-25-ATH-T142-04 | DISTRIBUTION TRANSFORMER - ATHLONE 110-ATHLONE 38-T142 | Unknown | Unknown |  | Reference (Planned) | July | July
TO-25-ATY-110SA1-01 | SECTIONALISING DISCONNECT - ATHY 110-ATHY 110-110SA1 | Unknown | Unknown |  | Planned | July | July
TO-25-ATY-110SA2-02 | SECTIONALISING DISCONNECT - ATHY 110-ATHY 110-110SA2 | Unknown | Unknown | 10 | Planned | July | July
TO-25-ATY-PLS-1-03 | 110kV FEEDER - ATHY 110-PORTLAOISE 110-1 | Unknown | Unknown | 10 | Planned | July | July
TO-25-ATY-T102-01 | DISTRIBUTION TRANSFORMER - ATHY 110-ATHY 10-T102 | Unknown | Unknown | 10 | Reference (Planned) | July | July
TO-25-BAN-110SA1-03 | SECTIONALISING DISCONNECT - BANDON 110-BANDON 110-110SA1 | Unknown | Unknown | 10 | Planned | July | July
TO-25-BAN-110SA2-03 | SECTIONALISING DISCONNECT - BANDON 110-BANDON 110-110SA2 | Unknown | Unknown | 10 | Planned | July | July
TO-25-BAN-BRI-2-01 | 110kV FEEDER - BANDON 110-BRINNY 110-2 | Unknown | Unknown | 10 | Planned | July | July
TO-25-BAN-BRI-2-02 | 110kV FEEDER - BANDON 110-BRINNY 110-2 | Unknown | Unknown | 10 | Planned | July | July
TO-25-BAN-CAP1-01 | CAPACITOR/SVC/REACTOR - BANDON 110-BANDON 110-CAP1 | Unknown | Unknown | 15 | Planned | July | July
TO-25-BAN-RAF-1-02 | 110kV FEEDER - BANDON 110-RAFFEEN 110-1 | Unknown | Unknown | 10 | Planned | July | July
TO-25-BAN-T142-01 | DISTRIBUTION TRANSFORMER - BANDON 110-BANDON 38-T142 | Unknown | Unknown | 10 | Reference (Planned) | July | July
TO-25-BRI-T102-01 | TSO CUSTOMER TRANSFORMER - BRINNY 110-BRINNY 10-T102 | Unknown | Unknown | 10 | Planned | July | July
TO-25-BRI-T102-02 | TSO CUSTOMER TRANSFORMER - BRINNY 110-BRINNY 10-T102 | Unknown | Unknown | 10 | Planned | July | July
TO-25-CLU-T122-01 | TSO CUSTOMER TRANSFORMER - CLUTTERLAND 110-CLUTTERLAND 20-T122 | 5 | 5 | 5 | Proposed | 07/07/2025 | 11/07/2025
TO-25-CRA-WEX-1-01 | 110kV FEEDER - CRANE 110-WEXFORD 110-1 | Unknown | Unknown | 5 | Planned | July | July
TO-25-400 kV A2 @ DSN-03 | BUSBAR SECTION - DUNSTOWN 400-DUNSTOWN 400-400A2 | Unknown | Unknown |  | Planned | July | July
TO-25-KDN-T131-01 | GENERATOR TRANSFORMER - KNOCKDRIN 110-KNOCKDRIN 33-T131 | Unknown | Unknown | 15 | Planned | July | July
TO-25-KDN,T-KDN-1-01 | 110kV FEEDER - KNOCKDRIN tee-KNOCKDRIN 110-1 | Unknown | Unknown | 15 | Planned | July | July
TO-25-KDN,T-TSB-1-01 | 110kV FEEDER - KNOCKDRIN tee-THORNSBERRY 110-1 | Unknown | Unknown | 15 | Planned | July | July
TO-25-KDN,T-TEN-1-01 | 110kV FEEDER - KNOCKDRIN tee-TIMAHOE 110-1 | Unknown | Unknown | 15 | Planned | July | July
TO-25-SH-T2102-01 | TRANSFORMER - SHANNONBRIDGE 220-SHANNONBRIDGE 110-T2102 | Unknown | Unknown | 55 | Planned | July | September
TO-25-SLI-110SA1-2CB-02 | COUPLER/SECTIONALISING CB - SLIGO 110-SLIGO 110-110SA1-2CB | Unknown | Unknown | 15 | Planned | July | July
TO-25-SLI-CAP1-01 | CAPACITOR/SVC/REACTOR - SLIGO 110-SLIGO 110-CAP1 | Unknown | Unknown | 15 | Planned | July | July
TO-25-SLI-SRA-1-01 | 110kV FEEDER - SLIGO 110-SRANANAGH 110-1 | Unknown | Unknown | 40 | Planned | July | September
TO-25-SLI-SRA-1-02 | 110kV FEEDER - SLIGO 110-SRANANAGH 110-1 | Unknown | Unknown |  | Planned | July | October
TO-25-SLI-T141-02 | DISTRIBUTION TRANSFORMER - SLIGO 110-SLIGO 38-T141 | Unknown | Unknown | 15 | Reference (Planned) | July | July
TO-25-WEX-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - WEXFORD 110-WEXFORD 110-110SA1-2CB | Unknown | Unknown | 5 | Planned | July | July
TO-25-WEX-CAP2-01 | CAPACITOR/SVC/REACTOR - WEXFORD 110-WEXFORD 110-CAP2 | Unknown | Unknown | 5 | Planned | July | July
TO-25-WEX-CAP4-01 | CAPACITOR/SVC/REACTOR - WEXFORD 110-WEXFORD 110-CAP4 | Unknown | Unknown | 5 | Planned | July | July
TO-25-WEX-T122-01 | DISTRIBUTION TRANSFORMER - WEXFORD 110-WEXFORD 20-T122 | Unknown | Unknown | 5 | Reference (Planned) | July | July
TO-25-WEX-T142-01 | DISTRIBUTION TRANSFORMER - WEXFORD 110-WEXFORD 38-T142 | Unknown | Unknown | 5 | Reference (Planned) | July | July
TO-25-GLR-MOY-1-01 | 110kV FEEDER - GLENREE 110-MOY 110-1 | Unknown | Unknown |  | Planned | July | September
TO-25-110 kV A3 @ GAL GIS-01 | BUSBAR SECTION - GALWAY GIS 110-GALWAY GIS 110-110A3 | Unknown | Unknown | 7 | Planned | July | July
TO-25-110 kV B3 @ GAL GIS-01 | BUSBAR SECTION - GALWAY GIS 110-GALWAY GIS 110-110B3 | Unknown | Unknown | 7 | Planned | July | July
TO-25-GAL GIS-110K3-01 | COUPLER/SECTIONALISING CB - GALWAY GIS 110-GALWAY GIS 110-110K3 | Unknown | Unknown | 7 | Planned | July | July
TO-25-GAL GIS-110SA1-3CB-01 | COUPLER/SECTIONALISING CB - GALWAY GIS 110-GALWAY GIS 110-110SA1-3CB | Unknown | Unknown | 7 | Planned | July | July
TO-25-GAL GIS-110SB1-3CB-01 | COUPLER/SECTIONALISING CB - GALWAY GIS 110-GALWAY GIS 110-110SB1-3CB | Unknown | Unknown | 7 | Planned | July | July
TO-25-220 kV A1 @ WOO-01 | BUSBAR SECTION - WOODLAND 220-WOODLAND 220-220A1 | Unknown | Unknown | 1 | Planned | July | July
TO-25-WOO-T4201-01 | TRANSFORMER - WOODLAND 400-WOODLAND 220-T4201 | Unknown | Unknown | 1 | Planned | July | July
TO-25-GRV-T121-02 | GENERATOR TRANSFORMER - GARVAGH 110-GARVAGH 20-T121 | Unknown | Unknown | 6 | Planned | July | July
TO-25-AUG-SK-3-01 | 110kV FEEDER - AUGHINISH 110-SEALROCK 110-3 | Unknown | Unknown | 15 | Planned | July | August
TO-25-CDY-GRV-1-01 | 110kV FEEDER - CORDERRY 110-GARVAGH 110-1 | Unknown | Unknown | 5 | Planned | July | July
TO-25-GRV-110K1-01 | COUPLER/SECTIONALISING CB - GARVAGH 110-GARVAGH 110-110K1 | Unknown | Unknown | 5 | Planned | July | July
TO-25-GRV-T121-01 | GENERATOR TRANSFORMER - GARVAGH 110-GARVAGH 20-T121 | Unknown | Unknown | 3 | Planned | July | July
TO-25-GRV-T141-01 | DISTRIBUTION TRANSFORMER - GARVAGH 110-GARVAGH 20-T141 | Unknown | Unknown | 5 | Reference (Planned) | July | July
TO-25-SK-T103-01 | GENERATOR TRANSFORMER - SEALROCK 110-SEALROCK G3-T103 | Unknown | Unknown | 15 | Planned | July | August
TO-25-TSB-110SA1-01 | SECTIONALISING DISCONNECT - THORNSBERRY 110-THORNSBERRY 110-110SA1 | Unknown | Unknown | 5 | Planned | July | July
TO-25-TSB-110SA2-01 | SECTIONALISING DISCONNECT - THORNSBERRY 110-THORNSBERRY 110-110SA2 | Unknown | Unknown | 5 | Planned | July | July
TO-25-TSB-T142-01 | DISTRIBUTION TRANSFORMER - THORNSBERRY 110-THORNSBERRY 38-T142 | Unknown | Unknown | 5 | Reference (Planned) | July | July
TO-25-110 kV A2 @ TEN-01 | BUSBAR SECTION - TIMAHOE 110-TIMAHOE 110-110A2 | Unknown | Unknown | 5 | Planned | July | July
TO-25-110 kV B2 @ TEN-01 | BUSBAR SECTION - TIMAHOE 110-TIMAHOE 110-110B2 | Unknown | Unknown | 5 | Planned | July | July
TO-25-TEN-110K2-01 | COUPLER/SECTIONALISING CB - TIMAHOE 110-TIMAHOE 110-110K2 | Unknown | Unknown | 5 | Planned | July | July
TO-25-CBA-110SA1-01 | SECTIONALISING DISCONNECT - CLOGHBOOLA 110-CLOGHBOOLA 110-110SA1 | Unknown | Unknown | 12 | Planned | July | July
TO-25-CBA-110SA2-01 | SECTIONALISING DISCONNECT - CLOGHBOOLA 110-CLOGHBOOLA 110-110SA2 | Unknown | Unknown | 12 | Planned | July | July
TO-25-CBA-T122-01 | DISTRIBUTION TRANSFORMER - CLOGHBOOLA 110-CLOGHBOOLA 20-T122 | Unknown | Unknown | 12 | Reference (Planned) | July | July
TO-25-CBA-T131-01 | GENERATOR TRANSFORMER - CLOGHBOOLA 110-CLOGHBOOLA 33-T131 | Unknown | Unknown | 12 | Planned | July | July
TO-25-CBA-TRI-1-01 | 110kV FEEDER - CLOGHBOOLA 110-TRIEN 110-1 | Unknown | Unknown | 12 | Planned | July | July
TO-25-STN-T131-01 | GENERATOR TRANSFORMER - STONESTOWN 110-STONESTOWN 33-T131 | Unknown | Unknown | 1 | Planned | July | July
TO-25-ATH-T141-02 | DISTRIBUTION TRANSFORMER - ATHLONE 110-ATHLONE 38-T141 | Unknown | Unknown |  | Reference (Planned) | July | August
TO-25-ATY-T102-02 | DISTRIBUTION TRANSFORMER - ATHY 110-ATHY 10-T102 | Unknown | Unknown | 8 | Reference (Planned) | July | July
TO-25-BAN-110SA1-01 | SECTIONALISING DISCONNECT - BANDON 110-BANDON 110-110SA1 | Unknown | Unknown | 5 | Planned | July | July
TO-25-BAN-110SA1-02 | SECTIONALISING DISCONNECT - BANDON 110-BANDON 110-110SA1 | Unknown | Unknown | 10 | Planned | July | August
TO-25-BAN-110SA2-01 | SECTIONALISING DISCONNECT - BANDON 110-BANDON 110-110SA2 | Unknown | Unknown | 5 | Planned | July | July
TO-25-BAN-110SA2-02 | SECTIONALISING DISCONNECT - BANDON 110-BANDON 110-110SA2 | Unknown | Unknown | 10 | Planned | July | August
TO-25-BAN-BRI-1-01 | 110kV FEEDER - BANDON 110-BRINNY 110-1 | Unknown | Unknown | 5 | Planned | July | July
TO-25-BAN-BRI-1-02 | 110kV FEEDER - BANDON 110-BRINNY 110-1 | Unknown | Unknown | 10 | Planned | July | August
TO-25-BAN-CAP1-02 | CAPACITOR/SVC/REACTOR - BANDON 110-BANDON 110-CAP1 | Unknown | Unknown | 10 | Planned | July | August
TO-25-BAN-DMY-1-02 | 110kV FEEDER - BANDON 110-DUNMANWAY 110-1 | Unknown | Unknown | 5 | Planned | July | July
TO-25-BAN-DMY-1-03 | 110kV FEEDER - BANDON 110-DUNMANWAY 110-1 | Unknown | Unknown | 10 | Planned | July | August
TO-25-BAN-T101-02 | DISTRIBUTION TRANSFORMER - BANDON 110-BANDON 10-T101 | Unknown | Unknown | 10 | Reference (Planned) | July | August
TO-25-BAN-T101-01 | DISTRIBUTION TRANSFORMER - BANDON 110-BANDON 10-T101 | Unknown | Unknown | 5 | Reference (Planned) | July | July
TO-25-BAN-T141-01 | DISTRIBUTION TRANSFORMER - BANDON 110-BANDON 38-T141 | Unknown | Unknown | 5 | Reference (Planned) | July | July
TO-25-BAN-T141-02 | DISTRIBUTION TRANSFORMER - BANDON 110-BANDON 38-T141 | Unknown | Unknown | 10 | Reference (Planned) | July | August
TO-25-BRI-T101-01 | TSO CUSTOMER TRANSFORMER - BRINNY 110-BRINNY 10-T101 | Unknown | Unknown | 5 | Planned | July | July
TO-25-BRI-T101-02 | TSO CUSTOMER TRANSFORMER - BRINNY 110-BRINNY 10-T101 | Unknown | Unknown | 10 | Planned | July | August
TO-25-110 kV B1 @ CSH-03 | BUSBAR SECTION - CASHLA 110-CASHLA 110-110B1 | Unknown | Unknown |  | Planned | July | August
TO-25-CRU-T221-01 | TSO CUSTOMER TRANSFORMER - CRUISERATH 220-CRUISERATH 20-T221 | 5 | 5 | 5 | Proposed | 21/07/2025 | 25/07/2025
TO-25-400 kV B2 @ DSN-01 | BUSBAR SECTION - DUNSTOWN 400-DUNSTOWN 400-400B2 | Unknown | Unknown |  | Planned | July | August
TO-25-GOR-T2101-01 | TRANSFORMER - GORMAN 220-GORMAN 110-T2101 | Unknown | Unknown | 40 | Planned | July | September
TO-25-DER-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - DERRYIRON 110-DERRYIRON 110-110SA1-2CB | Unknown | Unknown | 4 | Planned | July | July
TO-25-DER-KIN-1-04 | 110kV FEEDER - DERRYIRON 110-KINNEGAD 110-1 | Unknown | Unknown | 4 | Planned | July | July
TO-25-DER-T1/T2-03 | GENERATOR TRANSFORMER - DERRYIRON 110-RHODE 110-T1/T2 | Unknown | Unknown | 4 | Planned | July | July
TO-25-CRU-T223-01 | TSO CUSTOMER TRANSFORMER - CRUISERATH 220-CRUISERATH 20-T223 | 5 | 5 | 5 | Proposed | 28/07/2025 | 01/08/2025
TO-25-ISH-SHL-1-02 | 220kV FEEDER - IRISHTOWN 220-SHELLYBANKS 220-1 | Unknown | Unknown | 2 | Planned | July | July
TO-25-CUS-T103/5-03 | GENERATOR TRANSFORMER - CUSHALING 110-CUSHALING G3/5-T103/5 | Unknown | Unknown | 10 | Planned | July | August
TO-25-BLC-FIN-1-01 | 220kV FEEDER - BELCAMP 220-FINGLAS 220-1 | Unknown | Unknown | 30 | Planned | July | September
TO-25-BLC-T2103-01 | TRANSFORMER - BELCAMP 220-BELCAMP 110-T2103 | Unknown | Unknown | 80 | Planned | July | November
TO-25-KIN-MUL-1-01 | 110kV FEEDER - KINNEGAD 110-MULLINGAR 110-1 | Unknown | Unknown | 70 | Planned | July | November
TO-25-ATH-CAP3-02 | CAPACITOR/SVC/REACTOR - ATHLONE 110-ATHLONE 110-CAP3 | Unknown | Unknown |  | Planned | August | August
TO-25-CLW-KLS-2-01 | 110kV FEEDER - CARLOW 110-KELLIS 110-2 | Unknown | Unknown |  | Planned | August | August
TO-25-KLS-110K1-2-01 | COUPLER/SECTIONALISING CB - KELLIS 110-KELLIS 110-110K1-2 | Unknown | Unknown |  | Planned | August | August
TO-25-KLS-KKY-1-01 | 110kV FEEDER - KELLIS 110-KILKENNY 110-1 | Unknown | Unknown |  | Planned | August | August
TO-25-KLS-T2102-01 | TRANSFORMER - KELLIS 220-KELLIS 110-T2102 | Unknown | Unknown |  | Planned | August | August
TO-25-220 kV A1 @ LOU-07 | BUSBAR SECTION - LOUTH 220-LOUTH 220-220A1 | Unknown | Unknown | 9 | Planned | August | August
TO-25-220 kV B1 @ LOU-07 | BUSBAR SECTION - LOUTH 220-LOUTH 220-220B1 | Unknown | Unknown | 9 | Planned | August | August
TO-25-MLN-T124-01 | TSO CUSTOMER TRANSFORMER - MULLAGHARLIN 110-MULLAGHARLIN 20-T124 | Unknown | Unknown | 2 | Planned | August | August
TO-25-CUS-T103/5-01 | GENERATOR TRANSFORMER - CUSHALING 110-CUSHALING G3/5-T103/5 | Unknown | Unknown | 6 | Planned | August | August
TO-25-110 kV A2 @ KLS-01 | BUSBAR SECTION - KELLIS 110-KELLIS 110-110A2 | Unknown | Unknown |  | Planned | August | August
TO-25-110 kV B2 @ KLS-01 | BUSBAR SECTION - KELLIS 110-KELLIS 110-110B2 | Unknown | Unknown |  | Planned | August | August
TO-25-MLN-T123-01 | TSO CUSTOMER TRANSFORMER - MULLAGHARLIN 110-MULLAGHARLIN 20-T123 | Unknown | Unknown | 2 | Planned | August | August
TO-25-BYH-CDL-1-01 | 110kV FEEDER - BALLYNAHULLA 110-CORDAL 110-1 | Unknown | Unknown | 15 | Planned | August | August
TO-25-CDL-110SA1-01 | SECTIONALISING DISCONNECT - CORDAL 110-CORDAL 110-110SA1 | Unknown | Unknown | 15 | Planned | August | August
TO-25-CDL-110SA2-01 | SECTIONALISING DISCONNECT - CORDAL 110-CORDAL 110-110SA2 | Unknown | Unknown | 15 | Planned | August | August
TO-25-CDL-T132-01 | GENERATOR TRANSFORMER - CORDAL 110-CORDAL 33-T132 | Unknown | Unknown | 15 | Planned | August | August
TO-25-CRA-WEX-1-03 | 110kV FEEDER - CRANE 110-WEXFORD 110-1 | Unknown | Unknown |  | Planned | August | August
TO-25-DFR-T122-03 | DISTRIBUTION TRANSFORMER - DUNFIRTH 110-DUNFIRTH 20-T122 | Unknown | Unknown | 4 | Reference (Planned) | August | August
TO-25-DFR,T-DFR-1-03 | 110kV FEEDER - DUNFIRTH tee-DUNFIRTH 110-1 | Unknown | Unknown | 4 | Planned | August | August
TO-25-DFR,T-RNW-1-02 | 110kV FEEDER - DUNFIRTH tee-RINAWADE 110-1 | Unknown | Unknown | 7 | Planned | August | August
TO-25-110 kV B4 @ FIN GIS-01 | BUSBAR SECTION - FINGLAS GIS 110-FINGLAS GIS 110-110B4 | Unknown | Unknown | 3 | Planned | August | August
TO-25-FIN GIS-110SB2-4CB-01 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110SB2-4CB | Unknown | Unknown | 5 | Planned | August | August
TO-25-FIN GIS-110SB4-6CB-01 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110SB4-6CB | Unknown | Unknown | 3 | Planned | August | August
TO-25-110 kV A2 @ LOU-01 | BUSBAR SECTION - LOUTH 110-LOUTH 110-110A2 | Unknown | Unknown | 10 | Planned | August | August
TO-25-220 kV A2 @ MAY-01 | BUSBAR SECTION - MAYNOOTH 220-MAYNOOTH 220-220A2 | Unknown | Unknown |  | Planned | August | August
TO-25-220 kV B2 @ MAY-02 | BUSBAR SECTION - MAYNOOTH 220-MAYNOOTH 220-220B2 | Unknown | Unknown |  | Planned | August | August
TO-25-WEX-110SA1-2CB-02 | COUPLER/SECTIONALISING CB - WEXFORD 110-WEXFORD 110-110SA1-2CB | Unknown | Unknown |  | Planned | August | August
TO-25-WEX-CAP2-02 | CAPACITOR/SVC/REACTOR - WEXFORD 110-WEXFORD 110-CAP2 | Unknown | Unknown |  | Planned | August | August
TO-25-WEX-CAP4-02 | CAPACITOR/SVC/REACTOR - WEXFORD 110-WEXFORD 110-CAP4 | Unknown | Unknown |  | Planned | August | August
TO-25-WEX-T122-02 | DISTRIBUTION TRANSFORMER - WEXFORD 110-WEXFORD 20-T122 | Unknown | Unknown |  | Reference (Planned) | August | August
TO-25-WEX-T142-02 | DISTRIBUTION TRANSFORMER - WEXFORD 110-WEXFORD 38-T142 | Unknown | Unknown |  | Reference (Planned) | August | August
TO-25-KLS-110K1-2-02 | COUPLER/SECTIONALISING CB - KELLIS 110-KELLIS 110-110K1-2 | Unknown | Unknown |  | Planned | August | August
TO-25-220 kV A2 @ WOO-01 | BUSBAR SECTION - WOODLAND 220-WOODLAND 220-220A2 | Unknown | Unknown | 15 | Planned | August | September
TO-25-220 kV B2 @ WOO-01 | BUSBAR SECTION - WOODLAND 220-WOODLAND 220-220B2 | Unknown | Unknown | 15 | Planned | August | September
TO-25-110 kV A1 @ CSH-03 | BUSBAR SECTION - CASHLA 110-CASHLA 110-110A1 | Unknown | Unknown |  | Planned | August | September
TO-25-110 kV A3 @ CKG-01 | BUSBAR SECTION - CORKAGH 110-CORKAGH 110-110A3 | Unknown | Unknown | 10 | Planned | August | August
TO-25-110 kV B3 @ CKG-01 | BUSBAR SECTION - CORKAGH 110-CORKAGH 110-110B3 | Unknown | Unknown | 10 | Planned | August | August
TO-25-CKG-110K3-01 | COUPLER/SECTIONALISING CB - CORKAGH 110-CORKAGH 110-110K3 | Unknown | Unknown | 10 | Planned | August | August
TO-25-CKG-110SA1-3CB-02 | COUPLER/SECTIONALISING CB - CORKAGH 110-CORKAGH 110-110SA1-3CB | Unknown | Unknown | 10 | Planned | August | August
TO-25-CKG-110SB1-3CB-02 | COUPLER/SECTIONALISING CB - CORKAGH 110-CORKAGH 110-110SB1-3CB | Unknown | Unknown | 10 | Planned | August | August
TO-25-220 kV A1 @ SH-02 | BUSBAR SECTION - SHANNONBRIDGE 220-SHANNONBRIDGE 220-220A1 | Unknown | Unknown |  | Planned | August | August
TO-25-220 kV B1 @ SH-02 | BUSBAR SECTION - SHANNONBRIDGE 220-SHANNONBRIDGE 220-220B1 | Unknown | Unknown |  | Planned | August | August
TO-25-ATH-M/CAP1-02 | CAPACITOR/SVC/REACTOR - ATHLONE 110-ATHLONE 110-M/CAP1 | Unknown | Unknown |  | Planned | August | September
TO-25-220 kV A2 @ DSN-02 | BUSBAR SECTION - DUNSTOWN 220-DUNSTOWN 220-220A2 | Unknown | Unknown |  | Planned | August | September
TO-25-KLS-KKY-1-02 | 110kV FEEDER - KELLIS 110-KILKENNY 110-1 | Unknown | Unknown |  | Planned | August | August
TO-25-110 kV A2 @ KLS-02 | BUSBAR SECTION - KELLIS 110-KELLIS 110-110A2 | Unknown | Unknown | 2 | Planned | August | August
TO-25-110 kV B2 @ KLS-02 | BUSBAR SECTION - KELLIS 110-KELLIS 110-110B2 | Unknown | Unknown | 2 | Planned | August | August
TO-25-KLS-T2102-02 | TRANSFORMER - KELLIS 220-KELLIS 110-T2102 | Unknown | Unknown |  | Planned | August | August
TO-25-CHA-MAL-1-01 | 110kV FEEDER - CHARLEVILLE 110-MALLOW 110-1 | Unknown | Unknown | 13 | Planned | August | September
TO-25-110 kV B2 @ LOU-01 | BUSBAR SECTION - LOUTH 110-LOUTH 110-110B2 | Unknown | Unknown |  | Planned | August | September
TO-25-CBT-CKG-1-01 | 110kV FEEDER - CASTLEBAGOT 110-CORKAGH 110-1 | Unknown | Unknown | 2 | Planned | August | August
TO-25-220 kV A2 @ FIN-01 | BUSBAR SECTION - FINGLAS 220-FINGLAS 220-220A2 | Unknown | Unknown | 5 | Planned | September | September
TO-25-220 kV B2 @ FIN-01 | BUSBAR SECTION - FINGLAS 220-FINGLAS 220-220B2 | Unknown | Unknown | 5 | Planned | September | September
TO-25-FIN-220K2-01 | COUPLER/SECTIONALISING CB - FINGLAS 220-FINGLAS 220-220K2 | Unknown | Unknown | 5 | Planned | September | September
TO-25-FIN-220SA1-2CB-02 | COUPLER/SECTIONALISING CB - FINGLAS 220-FINGLAS 220-220SA1-2CB | Unknown | Unknown | 5 | Planned | September | September
TO-25-FIN-220SB1-2CB-01 | COUPLER/SECTIONALISING CB - FINGLAS 220-FINGLAS 220-220SB1-2CB | Unknown | Unknown | 5 | Planned | September | September
TO-25-110 kV A4 @ FIN GIS-01 | BUSBAR SECTION - FINGLAS GIS 110-FINGLAS GIS 110-110A4 | Unknown | Unknown | 5 | Planned | September | September
TO-25-110 kV B4 @ FIN GIS-02 | BUSBAR SECTION - FINGLAS GIS 110-FINGLAS GIS 110-110B4 | Unknown | Unknown | 5 | Planned | September | September
TO-25-FIN GIS-110SA2-4CB-01 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110SA2-4CB | Unknown | Unknown | 5 | Planned | September | September
TO-25-FIN GIS-110SA4-6CB-01 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110SA4-6CB | Unknown | Unknown | 5 | Planned | September | September
TO-25-FIN GIS-110SB2-4CB-02 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110SB2-4CB | Unknown | Unknown | 5 | Planned | September | September
TO-25-FIN GIS-110SB4-6CB-02 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110SB4-6CB | Unknown | Unknown | 5 | Planned | September | September
TO-25-WHI-CKB-T101-01 | TSO CUSTOMER TRANSFORMER - WHITEGATE 110-WHITEGATE 10-CKB-T101 | Unknown | Unknown | 5 | Planned | September | September
TO-25-GGO-T2001-01 | GENERATOR TRANSFORMER - GLANAGOW 220-GLANAGOW G1-T2001 | Unknown | Unknown | 4 | Planned | September | September
TO-25-110 kV A1 @ RAF-02 | BUSBAR SECTION - RAFFEEN 110-RAFFEEN 110-110A1 | Unknown | Unknown | 3 | Planned | September | September
TO-25-110 kV B1 @ RAF-02 | BUSBAR SECTION - RAFFEEN 110-RAFFEEN 110-110B1 | Unknown | Unknown | 3 | Planned | September | September
TO-25-LOU-RRU-1-01 | 110kV FEEDER - LOUTH 110-RATRUSSAN 110-1 | Unknown | Unknown | 15 | Planned | September | September
TO-25-LOU-RRU-1-02 | 110kV FEEDER - LOUTH 110-RATRUSSAN 110-1 | Unknown | Unknown |  | Planned | September | October
TO-25-NEW-PLS-1-01 | 110kV FEEDER - NEWBRIDGE 110-PORTLAOISE 110-1 | Unknown | Unknown | 55 | Planned | September | November
TO-25-DSN-MAY-2-01 | 220kV FEEDER - DUNSTOWN 220-MAYNOOTH 220-2 | Unknown | Unknown |  | Planned | September | September
TO-25-220 kV A2 @ MAY-02 | BUSBAR SECTION - MAYNOOTH 220-MAYNOOTH 220-220A2 | Unknown | Unknown |  | Planned | September | September
TO-25-110 kV A2 @ KRA-01 | BUSBAR SECTION - KNOCKRAHA 110-KNOCKRAHA 110-110A2 | Unknown | Unknown | 60 | Planned | September | November
TO-25-110 kV B2 @ KRA-01 | BUSBAR SECTION - KNOCKRAHA 110-KNOCKRAHA 110-110B2 | Unknown | Unknown | 60 | Planned | September | November
TO-25-ATH-110SA1-2CB-05 | COUPLER/SECTIONALISING CB - ATHLONE 110-ATHLONE 110-110SA1-2CB | Unknown | Unknown |  | Planned | September | September
TO-25-ATH-CAP3-03 | CAPACITOR/SVC/REACTOR - ATHLONE 110-ATHLONE 110-CAP3 | Unknown | Unknown |  | Planned | September | September
TO-25-ATH-LA-1-03 | 110kV FEEDER - ATHLONE 110-LANESBORO 110-1 | Unknown | Unknown |  | Planned | September | September
TO-25-ATH-M/CAP1-03 | CAPACITOR/SVC/REACTOR - ATHLONE 110-ATHLONE 110-M/CAP1 | Unknown | Unknown |  | Planned | September | September
TO-25-ATH-T141-03 | DISTRIBUTION TRANSFORMER - ATHLONE 110-ATHLONE 38-T141 | Unknown | Unknown |  | Reference (Planned) | September | September
TO-25-AUG-CFM-1-01 | 110kV FEEDER - AUGHINISH 110-CASTLEFARM 110-1 | Unknown | Unknown | 10 | Planned | September | September
TO-25-BDA-T102-01 | TSO CUSTOMER TRANSFORMER - BARODA 110-BARODA 10-T102 | Unknown | Unknown | 7 | Planned | September | September
TO-25-CFM-T101-01 | TSO CUSTOMER TRANSFORMER - CASTLEFARM 110-CASTLEFARM 10-T101 | Unknown | Unknown | 10 | Reference (Planned) | September | September
TO-25-220 kV A1 @ LOU-03 | BUSBAR SECTION - LOUTH 220-LOUTH 220-220A1 | Unknown | Unknown | 4 | Planned | September | September
TO-25-220 kV B1 @ LOU-03 | BUSBAR SECTION - LOUTH 220-LOUTH 220-220B1 | Unknown | Unknown | 4 | Planned | September | September
TO-25-LOU-WOO-1-01 | 220kV FEEDER - LOUTH 220-WOODLAND 220-1 | Unknown | Unknown | 25 | Planned | September | October
TO-25-LOU-WOO-1-02 | 220kV FEEDER - LOUTH 220-WOODLAND 220-1 | Unknown | Unknown | 25 | Planned | September | October
TO-25-MAY-T2102-01 | TRANSFORMER - MAYNOOTH 220-MAYNOOTH 110-T2102 | Unknown | Unknown | 10 | Planned | September | September
TO-25-WHI-CKB-T102-01 | TSO CUSTOMER TRANSFORMER - WHITEGATE 110-WHITEGATE 10-CKB-T102 | Unknown | Unknown | 5 | Planned | September | September
TO-25-220 kV A2 @ WOO-02 | BUSBAR SECTION - WOODLAND 220-WOODLAND 220-220A2 | Unknown | Unknown | 5 | Planned | September | September
TO-25-220 kV B2 @ WOO-02 | BUSBAR SECTION - WOODLAND 220-WOODLAND 220-220B2 | Unknown | Unknown |  | Planned | September | September
TO-25-WOO-220K1-2-01 | COUPLER/SECTIONALISING CB - WOODLAND 220-WOODLAND 220-220K1-2 | Unknown | Unknown | 5 | Planned | September | September
TO-25-CDU-FIN-2-04 | 220kV FEEDER - CORDUFF 220-FINGLAS 220-2 | Unknown | Unknown | 2 | Planned | September | September
TO-25-220 kV A2 @ DSN-03 | BUSBAR SECTION - DUNSTOWN 220-DUNSTOWN 220-220A2 | Unknown | Unknown |  | Planned | September | September
TO-25-220 kV A2 @ FIN-04 | BUSBAR SECTION - FINGLAS 220-FINGLAS 220-220A2 | Unknown | Unknown | 2 | Planned | September | September
TO-25-FIN-220K2-04 | COUPLER/SECTIONALISING CB - FINGLAS 220-FINGLAS 220-220K2 | Unknown | Unknown | 2 | Planned | September | September
TO-25-FIN-220SA1-2CB-01 | COUPLER/SECTIONALISING CB - FINGLAS 220-FINGLAS 220-220SA1-2CB | Unknown | Unknown | 2 | Planned | September | September
TO-25-BWR-CRA-1-04 | 110kV FEEDER - BALLYWATER 110-CRANE 110-1 | Unknown | Unknown | 5 | Planned | September | September
TO-25-BWR-T124-04 | GENERATOR TRANSFORMER - BALLYWATER 110-BALLYWATER 20-T124 | Unknown | Unknown | 5 | Reference (Planned) | September | September
TO-25-CLA-KRA-1-01 | 220kV FEEDER - CLASHAVOON 220-KNOCKRAHA 220-1 | Unknown | Unknown | 7 | Planned | September | September
TO-25-CDU-WOO-1-01 | 220kV FEEDER - CORDUFF 220-WOODLAND 220-1 | Unknown | Unknown |  | Planned | September | September
TO-25-CRA-110SA1-03 | SECTIONALISING DISCONNECT - CRANE 110-CRANE 110-110SA1 | Unknown | Unknown | 5 | Planned | September | September
TO-25-CRA-110SA2-04 | SECTIONALISING DISCONNECT - CRANE 110-CRANE 110-110SA2 | Unknown | Unknown | 5 | Planned | September | September
TO-25-CRA-LWD-1-04 | 110kV FEEDER - CRANE 110-LODGEWOOD 110-1 | Unknown | Unknown | 5 | Planned | September | September
TO-25-CRA-T122-04 | DISTRIBUTION TRANSFORMER - CRANE 110-CRANE 20-T122 | Unknown | Unknown | 5 | Reference (Planned) | September | September
TO-25-220 kV A1 @ KRA-01 | BUSBAR SECTION - KNOCKRAHA 220-KNOCKRAHA 220-220A1 | Unknown | Unknown | 7 | Planned | September | September
TO-25-220 kV B1 @ KRA-01 | BUSBAR SECTION - KNOCKRAHA 220-KNOCKRAHA 220-220B1 | Unknown | Unknown | 7 | Planned | September | September
TO-25-KRA-220K1-01 | COUPLER/SECTIONALISING CB - KNOCKRAHA 220-KNOCKRAHA 220-220K1 | Unknown | Unknown | 7 | Planned | September | September
TO-25-KRA-220SA1-2CB-01 | COUPLER/SECTIONALISING CB - KNOCKRAHA 220-KNOCKRAHA 220-220SA1-2CB | Unknown | Unknown | 7 | Planned | September | September
TO-25-KRA-220SB1-2CB-01 | COUPLER/SECTIONALISING CB - KNOCKRAHA 220-KNOCKRAHA 220-220SB1-2CB | Unknown | Unknown | 7 | Planned | September | September
TO-25-KRA-T2101-01 | TRANSFORMER - KNOCKRAHA 220-KNOCKRAHA 110-T2101 | Unknown | Unknown | 7 | Planned | September | September
TO-25-110 kV A2 @ LOU-02 | BUSBAR SECTION - LOUTH 110-LOUTH 110-110A2 | Unknown | Unknown | 18 | Planned | September | October
TO-25-220 kV A2 @ WOO-03 | BUSBAR SECTION - WOODLAND 220-WOODLAND 220-220A2 | Unknown | Unknown | 6 | Planned | September | September
TO-25-220 kV B2 @ DSN-02 | BUSBAR SECTION - DUNSTOWN 220-DUNSTOWN 220-220B2 | Unknown | Unknown | 5 | Planned | September | September
TO-25-TEN-T132-01 | GENERATOR TRANSFORMER - TIMAHOE 110-TIMAHOE 33-T132 | Unknown | Unknown | 1 | Planned | September | September
TO-25-220 kV A1/A2 @ FIN-01 | BUSBAR SECTION - FINGLAS 220-FINGLAS 220-220A1-A2 | Unknown | Unknown | 0 | Planned | September | September
TO-25-FIN-220K1-02 | COUPLER/SECTIONALISING CB - FINGLAS 220-FINGLAS 220-220K1 | Unknown | Unknown | 0 | Planned | September | September
TO-25-FIN-220K2-02 | COUPLER/SECTIONALISING CB - FINGLAS 220-FINGLAS 220-220K2 | Unknown | Unknown | 0 | Planned | September | September
TO-25-FIN-220SA1-2CB-03 | COUPLER/SECTIONALISING CB - FINGLAS 220-FINGLAS 220-220SA1-2CB | Unknown | Unknown | 0 | Planned | September | September
TO-25-FIN-NW-1-01 | 220kV FEEDER - FINGLAS 220-NORTH WALL 220-1 | Unknown | Unknown | 0 | Planned | September | September
TO-25-AD-HWL-1-01 | 220kV FEEDER - AGHADA 220-HADWELL 220-1 | Unknown | Unknown | 2 | Planned | September | September
TO-25-110 kV A1 @ CSH-04 | BUSBAR SECTION - CASHLA 110-CASHLA 110-110A1 | Unknown | Unknown |  | Planned | September | September
TO-25-110 kV B1 @ CSH-04 | BUSBAR SECTION - CASHLA 110-CASHLA 110-110B1 | Unknown | Unknown |  | Planned | September | September
TO-25-CDU-WOO-1-02 | 220kV FEEDER - CORDUFF 220-WOODLAND 220-1 | Unknown | Unknown |  | Planned | September | September
TO-25-DER-110SA1-2CB-02 | COUPLER/SECTIONALISING CB - DERRYIRON 110-DERRYIRON 110-110SA1-2CB | Unknown | Unknown | 7 | Planned | September | September
TO-25-DER-KIN-1-01 | 110kV FEEDER - DERRYIRON 110-KINNEGAD 110-1 | Unknown | Unknown | 7 | Planned | September | September
TO-25-INC-PB-2-01 | 220kV FEEDER - INCHICORE 220-POOLBEG 220-2 | Unknown | Unknown | 10 | Planned | September | October
TO-25-220 kV A1 @ LOU-04 | BUSBAR SECTION - LOUTH 220-LOUTH 220-220A1 | Unknown | Unknown |  | Planned | September | September
TO-25-220 kV B1 @ LOU-04 | BUSBAR SECTION - LOUTH 220-LOUTH 220-220B1 | Unknown | Unknown |  | Planned | September | September
TO-25-LOU-220K1-2-02 | COUPLER/SECTIONALISING CB - LOUTH 220-LOUTH 220-220K1-2 | Unknown | Unknown |  | Planned | September | September
TO-25-MAY-T2103-01 | TRANSFORMER - MAYNOOTH 220-MAYNOOTH 110-T2103 | Unknown | Unknown | 10 | Planned | September | October
TO-25-WOO-220K1-2-04 | COUPLER/SECTIONALISING CB - WOODLAND 220-WOODLAND 220-220K1-2 | Unknown | Unknown |  | Planned | September | September
TO-25-400 kV B2 @ WOO-01 | BUSBAR SECTION - WOODLAND 400-WOODLAND 400-400B2 | Unknown | Unknown | 15 | Planned | September | October
TO-25-WOO-T4202-01 | TRANSFORMER - WOODLAND 400-WOODLAND 220-T4202 | Unknown | Unknown |  | Planned | September | September
TO-25-WOO-T4204-01 | TRANSFORMER - WOODLAND 400-WOODLAND 220-T4204 | Unknown | Unknown |  | Planned | September | September
TO-25-400 kV A2 @ DSN-02 | BUSBAR SECTION - DUNSTOWN 400-DUNSTOWN 400-400A2 | Unknown | Unknown |  | Planned | September | September
TO-25-AD-KRA-1-01 | 220kV FEEDER - AGHADA 220-KNOCKRAHA 220-1 | Unknown | Unknown | 15 | Planned | September | October
TO-25-AD-KRA-1-03 | 220kV FEEDER - AGHADA 220-KNOCKRAHA 220-1 | Unknown | Unknown | 15 | Planned | September | October
TO-25-AD-KRA-2-01 | 220kV FEEDER - AGHADA 220-KNOCKRAHA 220-2 | Unknown | Unknown | 15 | Planned | September | October
TO-25-AD-KRA-2-03 | 220kV FEEDER - AGHADA 220-KNOCKRAHA 220-2 | Unknown | Unknown | 15 | Planned | September | October
TO-25-110 kV A2 @ CSH-01 | BUSBAR SECTION - CASHLA 110-CASHLA 110-110A2 | Unknown | Unknown |  | Planned | September | September
TO-25-110 kV B2 @ CSH-01 | BUSBAR SECTION - CASHLA 110-CASHLA 110-110B2 | Unknown | Unknown |  | Planned | September | September
TO-25-CSH-110K1-2-01 | COUPLER/SECTIONALISING CB - CASHLA 110-CASHLA 110-110K1-2 | Unknown | Unknown |  | Planned | September | September
TO-25-CSH-T2102-01 | TRANSFORMER - CASHLA 220-CASHLA 110-T2102 | Unknown | Unknown |  | Planned | September | September
TO-25-220 kV A1 @ KRA-02 | BUSBAR SECTION - KNOCKRAHA 220-KNOCKRAHA 220-220A1 | Unknown | Unknown | 15 | Planned | September | October
TO-25-220 kV A2 @ KRA-01 | BUSBAR SECTION - KNOCKRAHA 220-KNOCKRAHA 220-220A2 | Unknown | Unknown | 15 | Planned | September | October
TO-25-220 kV B1 @ KRA-02 | BUSBAR SECTION - KNOCKRAHA 220-KNOCKRAHA 220-220B1 | Unknown | Unknown | 15 | Planned | September | October
TO-25-220 kV B2 @ KRA-01 | BUSBAR SECTION - KNOCKRAHA 220-KNOCKRAHA 220-220B2 | Unknown | Unknown | 15 | Planned | September | October
TO-25-KRA-220K1-02 | COUPLER/SECTIONALISING CB - KNOCKRAHA 220-KNOCKRAHA 220-220K1 | Unknown | Unknown | 15 | Planned | September | October
TO-25-KRA-220SA1-2CB-02 | COUPLER/SECTIONALISING CB - KNOCKRAHA 220-KNOCKRAHA 220-220SA1-2CB | Unknown | Unknown | 15 | Planned | September | October
TO-25-KRA-220SA1-2CB-03 | COUPLER/SECTIONALISING CB - KNOCKRAHA 220-KNOCKRAHA 220-220SA1-2CB | Unknown | Unknown | 15 | Planned | September | October
TO-25-KRA-220SA2-4CB-01 | COUPLER/SECTIONALISING CB - KNOCKRAHA 220-KNOCKRAHA 220-220SA2-4CB | Unknown | Unknown | 15 | Planned | September | October
TO-25-KRA-220SB1-2CB-02 | COUPLER/SECTIONALISING CB - KNOCKRAHA 220-KNOCKRAHA 220-220SB1-2CB | Unknown | Unknown | 15 | Planned | September | October
TO-25-KRA-220SB1-2CB-03 | COUPLER/SECTIONALISING CB - KNOCKRAHA 220-KNOCKRAHA 220-220SB1-2CB | Unknown | Unknown | 15 | Planned | September | October
TO-25-KRA-220SB2-4CB-01 | COUPLER/SECTIONALISING CB - KNOCKRAHA 220-KNOCKRAHA 220-220SB2-4CB | Unknown | Unknown | 15 | Planned | September | October
TO-25-KRA-T2102-01 | TRANSFORMER - KNOCKRAHA 220-KNOCKRAHA 110-T2102 | Unknown | Unknown | 15 | Planned | September | October
TO-25-AD-KRA-1-02 | 220kV FEEDER - AGHADA 220-KNOCKRAHA 220-1 | Unknown | Unknown | 10 | Planned | September | October
TO-25-AD-KRA-2-02 | 220kV FEEDER - AGHADA 220-KNOCKRAHA 220-2 | Unknown | Unknown | 10 | Planned | September | October
TO-25-ATH-110SA1-2CB-04 | COUPLER/SECTIONALISING CB - ATHLONE 110-ATHLONE 110-110SA1-2CB | Unknown | Unknown |  | Planned | September | October
TO-25-ATH-SH-1-05 | 110kV FEEDER - ATHLONE 110-SHANNONBRIDGE 110-1 | Unknown | Unknown |  | Planned | September | October
TO-25-ATH-T142-05 | DISTRIBUTION TRANSFORMER - ATHLONE 110-ATHLONE 38-T142 | Unknown | Unknown |  | Reference (Planned) | September | October
TO-25-LOU-220K1-2-01 | COUPLER/SECTIONALISING CB - LOUTH 220-LOUTH 220-220K1-2 | Unknown | Unknown | 5 | Planned | September | October
TO-25-LOU-AT2-01 | TRANSFORMER - LOUTH 220-LOUTH 275-AT2 | Unknown | Unknown | 5 | Planned | September | October
TO-25-LOU-T2101-01 | TRANSFORMER - LOUTH 220-LOUTH 110-T2101 | Unknown | Unknown | 5 | Planned | September | October
TO-25-LOU-T2103-01 | TRANSFORMER - LOUTH 220-LOUTH 110-T2103 | Unknown | Unknown | 5 | Planned | September | October
TO-25-LOU-TAN-2-01 | 275kV FEEDER - LOUTH 275-TANDRAGEE 275-2 | Unknown | Unknown | 5 | Planned | September | October
TO-25-110 kV B1 @ CSH-05 | BUSBAR SECTION - CASHLA 110-CASHLA 110-110B1 | Unknown | Unknown | 2 | Planned | October | October
TO-25-CSH-T2101-01 | TRANSFORMER - CASHLA 220-CASHLA 110-T2101 | Unknown | Unknown |  | Planned | October | October
TO-25-110 kV A1 @ CSH-05 | BUSBAR SECTION - CASHLA 110-CASHLA 110-110A1 | Unknown | Unknown |  | Planned | October | October
TO-25-400 kV A2 @ DSN-01 | BUSBAR SECTION - DUNSTOWN 400-DUNSTOWN 400-400A2 | Unknown | Unknown |  | Planned | October | October
TO-25-INC-ISH-1-01 | 220kV FEEDER - INCHICORE 220-IRISHTOWN 220-1 | Unknown | Unknown | 10 | Planned | October | October
TO-25-MAY-T2104-01 | TRANSFORMER - MAYNOOTH 220-MAYNOOTH 110-T2104 | Unknown | Unknown | 10 | Planned | October | October
TO-25-SLI-110SA1-2CB-03 | COUPLER/SECTIONALISING CB - SLIGO 110-SLIGO 110-110SA1-2CB | Unknown | Unknown | 15 | Planned | October | October
TO-25-SLI-CAP1-02 | CAPACITOR/SVC/REACTOR - SLIGO 110-SLIGO 110-CAP1 | Unknown | Unknown | 15 | Planned | October | October
TO-25-SLI-T141-01 | DISTRIBUTION TRANSFORMER - SLIGO 110-SLIGO 38-T141 | Unknown | Unknown | 15 | Reference (Planned) | October | October
TO-25-CSH-T2101-02 | TRANSFORMER - CASHLA 220-CASHLA 110-T2101 | Unknown | Unknown |  | Planned | October | October
TO-25-DER-110SA1-2CB-03 | COUPLER/SECTIONALISING CB - DERRYIRON 110-DERRYIRON 110-110SA1-2CB | Unknown | Unknown | 7 | Planned | October | October
TO-25-DER-T1/T2-01 | GENERATOR TRANSFORMER - DERRYIRON 110-RHODE 110-T1/T2 | Unknown | Unknown | 7 | Planned | October | October
TO-25-DER-TSB-1-01 | 110kV FEEDER - DERRYIRON 110-THORNSBERRY 110-1 | Unknown | Unknown | 7 | Planned | October | October
TO-25-DER-TEN-1-01 | 110kV FEEDER - DERRYIRON 110-TIMAHOE 110-1 | Unknown | Unknown | 7 | Planned | October | October
TO-25-110 kV B2 @ LOU-02 | BUSBAR SECTION - LOUTH 110-LOUTH 110-110B2 | Unknown | Unknown |  | Planned | October | November
TO-25-220 kV A1 @ LOU-05 | BUSBAR SECTION - LOUTH 220-LOUTH 220-220A1 | Unknown | Unknown | 2 | Planned | October | October
TO-25-220 kV B1 @ LOU-05 | BUSBAR SECTION - LOUTH 220-LOUTH 220-220B1 | Unknown | Unknown | 2 | Planned | October | October
TO-25-220 kV A2 @ WOO-04 | BUSBAR SECTION - WOODLAND 220-WOODLAND 220-220A2 | Unknown | Unknown | 2 | Planned | October | October
TO-25-220 kV B2 @ WOO-03 | BUSBAR SECTION - WOODLAND 220-WOODLAND 220-220B2 | Unknown | Unknown | 2 | Planned | October | October
TO-25-WOO-T4204-02 | TRANSFORMER - WOODLAND 400-WOODLAND 220-T4204 | Unknown | Unknown | 2 | Planned | October | October
TO-25-DRY-GOR-1-01 | 110kV FEEDER - DRYBRIDGE 110-GORMAN 110-1 | Unknown | Unknown | 40 | Planned | October | December
TO-25-DRY-GOR-1-05 | 110kV FEEDER - DRYBRIDGE 110-GORMAN 110-1 | Unknown | Unknown | 40 | Planned | October | December
TO-25-400 kV B2 @ DSN-02 | BUSBAR SECTION - DUNSTOWN 400-DUNSTOWN 400-400B2 | Unknown | Unknown |  | Planned | October | October
TO-25-GOR-LOU-1-01 | 220kV FEEDER - GORMAN 220-LOUTH 220-1 | Unknown | Unknown |  | Planned | October | October
TO-25-220 kV A2 @ LOU-05 | BUSBAR SECTION - LOUTH 220-LOUTH 220-220A2 | Unknown | Unknown |  | Planned | October | October
TO-25-220 kV B2 @ LOU-05 | BUSBAR SECTION - LOUTH 220-LOUTH 220-220B2 | Unknown | Unknown | 2 | Planned | October | October
TO-25-DSN-MAY-1-01 | 220kV FEEDER - DUNSTOWN 220-MAYNOOTH 220-1 | Unknown | Unknown | 5 | Planned | October | October
TO-25-KYT-T233-01 | TSO CUSTOMER TRANSFORMER - KELLYSTOWN 220-KELLYSTOWN 34.5-T233 | 19 | 14 | 14 | Proposed | 20/10/2025 | 07/11/2025
TO-25-KBY-MR-1-02 | 110kV FEEDER - KILBARRY 110-MARINA 110-1 | Unknown | Unknown | 35 | Planned | October | December
TO-25-KBY-MR-2-02 | 110kV FEEDER - KILBARRY 110-MARINA 110-2 | Unknown | Unknown | 35 | Planned | October | December
TO-25-LA-MUL-1-02 | 110kV FEEDER - LANESBORO 110-MULLINGAR 110-1 | Unknown | Unknown | 2 | Planned | October | October
TO-25-MAY-TH-1-01 | 220kV FEEDER - MAYNOOTH 220-TURLOUGH HILL 220-1 | Unknown | Unknown |  | Planned | October | November
TO-25-MAY-TH-1-03 | 220kV FEEDER - MAYNOOTH 220-TURLOUGH HILL 220-1 | Unknown | Unknown | 5 | Planned | October | October
TO-25-MUL-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - MULLINGAR 110-MULLINGAR 110-110SA1-2CB | Unknown | Unknown | 2 | Planned | October | October
TO-25-MUL-CAP1-01 | CAPACITOR/SVC/REACTOR - MULLINGAR 110-MULLINGAR 110-CAP1 | Unknown | Unknown | 2 | Planned | October | October
TO-25-MUL-T101-01 | DISTRIBUTION TRANSFORMER - MULLINGAR 110-MULLINGAR 10-T101 | Unknown | Unknown | 2 | Reference (Planned) | October | October
TO-25-MUL-T141-01 | DISTRIBUTION TRANSFORMER - MULLINGAR 110-MULLINGAR 38-T141 | Unknown | Unknown | 2 | Reference (Planned) | October | October
TO-25-PB-SHL-1-01 | 220kV FEEDER - POOLBEG 220-SHELLYBANKS 220-1 | Unknown | Unknown | 5 | Planned | October | October
TO-25-CF-SRA-1-01 | 110kV FEEDER - CATHALEENS FALL 110-SRANANAGH 110-1 | Unknown | Unknown |  | Planned | October | October
TO-25-110 kV A1 @ SRA-01 | BUSBAR SECTION - SRANANAGH 110-SRANANAGH 110-110A1 | Unknown | Unknown |  | Planned | October | October
TO-25-220 kV B2/B4 @ CDU-01 | BUSBAR SECTION - CORDUFF 220-CORDUFF 220-220B2-B4 | Unknown | Unknown | 5 | Planned | November | November
TO-25-CDU-CRU-2-01 | 220kV FEEDER - CORDUFF 220-CRUISERATH 220-2 | Unknown | Unknown | 5 | Planned | November | November
TO-25-CDU-WOO-1-03 | 220kV FEEDER - CORDUFF 220-WOODLAND 220-1 | Unknown | Unknown | 5 | Planned | November | November
TO-25-DER-KIN-1-02 | 110kV FEEDER - DERRYIRON 110-KINNEGAD 110-1 | Unknown | Unknown |  | Planned | November | November
TO-25-KIN-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - KINNEGAD 110-KINNEGAD 110-110SA1-2CB | Unknown | Unknown |  | Planned | November | November
TO-25-KIN-T101-01 | TSO CUSTOMER TRANSFORMER - KINNEGAD 110-KINNEGAD 10-T101 | Unknown | Unknown |  | Planned | November | November
TO-25-220 kV A1 @ MAY-01 | BUSBAR SECTION - MAYNOOTH 220-MAYNOOTH 220-220A1 | Unknown | Unknown |  | Planned | November | November
TO-25-220 kV B1 @ MAY-01 | BUSBAR SECTION - MAYNOOTH 220-MAYNOOTH 220-220B1 | Unknown | Unknown |  | Planned | November | November
TO-25-NW-PB-1-01 | 220kV FEEDER - NORTH WALL 220-POOLBEG 220-1 | Unknown | Unknown | 10 | Planned | November | November
TO-25-TTU-131-01 | GENERATOR TRANSFORMER - TULLABEG 110-TULLABEG 33-T131 | Unknown | Unknown | 2 | Planned | November | November
TO-25-110 kV A2 @ KRA-02 | BUSBAR SECTION - KNOCKRAHA 110-KNOCKRAHA 110-110A2 | Unknown | Unknown | 10 | Planned | November | November
TO-25-110 kV B2 @ KRA-02 | BUSBAR SECTION - KNOCKRAHA 110-KNOCKRAHA 110-110B2 | Unknown | Unknown | 10 | Planned | November | November
TO-25-KRA-WOH-1-01 | 110kV FEEDER - KNOCKRAHA 110-WOODHOUSE 110-1 | Unknown | Unknown |  | Planned | November | November
TO-25-KRA-WOH-1-02 | 110kV FEEDER - KNOCKRAHA 110-WOODHOUSE 110-1 | Unknown | Unknown | 10 | Planned | November | November
TO-25-CHA-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - CHARLEVILLE 110-CHARLEVILLE 110-110SA1-2CB | Unknown | Unknown | 5 | Planned | November | November
TO-25-CHA-MAL-1-02 | 110kV FEEDER - CHARLEVILLE 110-MALLOW 110-1 | Unknown | Unknown | 5 | Planned | November | November
TO-25-CHA-T142-01 | DISTRIBUTION TRANSFORMER - CHARLEVILLE 110-CHARLEVILLE 38-T142 | Unknown | Unknown | 5 | Reference (Planned) | November | November
TO-25-220 kV A3 @ BLC-01 | BUSBAR SECTION - BELCAMP 220-BELCAMP 220-220A3 | Unknown | Unknown | 2 | Planned | November | November
TO-25-BLC-220K3-01 | COUPLER/SECTIONALISING CB - BELCAMP 220-BELCAMP 220-220K3 | Unknown | Unknown | 2 | Planned | November | November
TO-25-BLC-220SA1-3CB-01 | COUPLER/SECTIONALISING CB - BELCAMP 220-BELCAMP 220-220SA1-3CB | Unknown | Unknown | 2 | Planned | November | November
TO-25-BLC-FIN-1-02 | 220kV FEEDER - BELCAMP 220-FINGLAS 220-1 | Unknown | Unknown | 2 | Planned | November | November
TO-25-110 kV A2 @ LOU-03 | BUSBAR SECTION - LOUTH 110-LOUTH 110-110A2 | Unknown | Unknown | 3 | Planned | November | November
TO-25-110 kV B2 @ LOU-03 | BUSBAR SECTION - LOUTH 110-LOUTH 110-110B2 | Unknown | Unknown |  | Planned | November | November
TO-25-110 kV A1 @ LOU-02 | BUSBAR SECTION - LOUTH 110-LOUTH 110-110A1 | Unknown | Unknown |  | Planned | November | November
TO-25-110 kV B1 @ LOU-02 | BUSBAR SECTION - LOUTH 110-LOUTH 110-110B1 | Unknown | Unknown |  | Planned | November | November
TO-25-LOU-110K1-2-02 | COUPLER/SECTIONALISING CB - LOUTH 110-LOUTH 110-110K1-2 | Unknown | Unknown |  | Planned | November | November
TO-25-LOU-T2103-03 | TRANSFORMER - LOUTH 220-LOUTH 110-T2103 | Unknown | Unknown |  | Planned | November | November
TO-25-DDK-LOU-1-01 | 110kV FEEDER - DUNDALK 110-LOUTH 110-1 | Unknown | Unknown |  | Planned | December | December
TO-25-DSN-MAY-2-02 | 220kV FEEDER - DUNSTOWN 220-MAYNOOTH 220-2 | Unknown | Unknown | 5 | Planned | December | December
TO-25-LIS-LOU-1-01 | 110kV FEEDER - LISDRUM 110-LOUTH 110-1 | Unknown | Unknown |  | Planned | December | December
TO-25-110 kV A2 @ LOU-04 | BUSBAR SECTION - LOUTH 110-LOUTH 110-110A2 | Unknown | Unknown | 2 | Planned | December | December
TO-25-LOU-T2104-02 | TRANSFORMER - LOUTH 220-LOUTH 110-T2104 | Unknown | Unknown |  | Planned | December | December
TO-25-110 kV B2 @ LOU-04 | BUSBAR SECTION - LOUTH 110-LOUTH 110-110B2 | Unknown | Unknown |  | Planned | December | December
TO-25-LOU-T2104-01 | TRANSFORMER - LOUTH 220-LOUTH 110-T2104 | Unknown | Unknown |  | Planned | December | December

## GEN_AreaSouthWest
Outage ID | Feeder ID | Calendar Day Duration | Working Day Duration | Work Days | Outage Status | Start | Finish
TO-25-CHA-MAL-1-03 | 110kV FEEDER - CHARLEVILLE 110-MALLOW 110-1 | 4 | 4 | 4 | Scheduled | 07/01/2025 | 10/01/2025
TO-25-AA GIS-DRU-1-01 | 110kV FEEDER - ARDNACRUSHA GIS 110-DRUMLINE 110-1 | 2 | 2 | 2 | Scheduled | 09/01/2025 | 10/01/2025
TO-25-KPG-110K4-01 | COUPLER/SECTIONALISING CB - KILPADDOGE 110-KILPADDOGE 110-110K4 | 1 | 1 |  | Scheduled | 21/01/2025 | 21/01/2025
TO-25-220 kV A2 @ KLN-01 | BUSBAR SECTION - KILLONAN 220-KILLONAN 220-220A2 | 5 | 5 | 5 | Scheduled | 27/01/2025 | 31/01/2025
TO-25-220 kV B2 @ KLN-01 | BUSBAR SECTION - KILLONAN 220-KILLONAN 220-220B2 | 5 | 5 | 5 | Scheduled | 27/01/2025 | 31/01/2025
TO-25-KLN-KPG-1-01 | 220kV FEEDER - KILLONAN 220-KILPADDOGE 220-1 | 43 | 30 | 30 | Scheduled | 27/01/2025 | 10/03/2025
TO-25-220 kV A2 @ TB-01 | BUSBAR SECTION - TARBERT 220-TARBERT 220-220A2 | 15 | 10 | 10 | Scheduled | 27/01/2025 | 10/02/2025
TO-25-220 kV B2 @ TB-01 | BUSBAR SECTION - TARBERT 220-TARBERT 220-220B2 | 15 | 10 | 10 | Scheduled | 27/01/2025 | 10/02/2025
TO-25-CHA-KLN-1-01 | 110kV FEEDER - CHARLEVILLE 110-KILLONAN 110-1 | 43 | 30 | 30 | Scheduled | 04/02/2025 | 18/03/2025
TO-25-220 kV A2 @ KLN-02 | BUSBAR SECTION - KILLONAN 220-KILLONAN 220-220A2 | 7 | 5 | 5 | Scheduled | 04/03/2025 | 10/03/2025
TO-25-220 kV B2 @ KLN-02 | BUSBAR SECTION - KILLONAN 220-KILLONAN 220-220B2 | 7 | 5 | 5 | Scheduled | 04/03/2025 | 10/03/2025
TO-25-DSN-MP GIS-1-01 | 400kV FEEDER - DUNSTOWN 400-MONEYPOINT GIS 400-1 | 38 | 27 |  | Scheduled | 11/03/2025 | 17/04/2025
TO-25-KLN-KRA-1-03 | 220kV FEEDER - KILLONAN 220-KNOCKRAHA 220-1 | 4 | 4 | 4 | Scheduled | 11/03/2025 | 14/03/2025
TO-25-400 kV A4 @ MP GIS-01 | BUSBAR SECTION - MONEYPOINT GIS 400-MONEYPOINT GIS 400-400A4 | 38 | 27 | 27 | Proposed | 11/03/2025 | 17/04/2025
TO-25-400 kV B4 @ MP GIS-01 | BUSBAR SECTION - MONEYPOINT GIS 400-MONEYPOINT GIS 400-400B4 | 38 | 27 | 27 | Proposed | 11/03/2025 | 17/04/2025
TO-25-MP GIS-400K4-01 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 400-MONEYPOINT GIS 400-400K4 | 38 | 27 | 27 | Proposed | 11/03/2025 | 17/04/2025
TO-25-MP GIS-400SA2-4CB-01 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 400-MONEYPOINT GIS 400-400SA2-4CB | 38 | 27 | 27 | Proposed | 11/03/2025 | 17/04/2025
TO-25-MP GIS-400SB2-4CB-01 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 400-MONEYPOINT GIS 400-400SB2-4CB | 38 | 27 | 27 | Proposed | 11/03/2025 | 17/04/2025
TO-25-CSH-ENN-1-01 | 110kV FEEDER - CASHLA 110-ENNIS 110-1 | 59 | 40 |  | Scheduled | 19/03/2025 | 16/05/2025
TO-25-CSH-ENN-1-02 | 110kV FEEDER - CASHLA 110-ENNIS 110-1 | 59 | 40 |  | Scheduled | 19/03/2025 | 16/05/2025
TO-25-GLE-KCR-1-01 | 110kV FEEDER - GLENLARA 110-KNOCKACUMMER 110-1 | 13 | 10 | 10 | Proposed | 30/03/2025 | 11/04/2025
TO-25-KCR-T121-01 | GENERATOR TRANSFORMER - KNOCKACUMMER 110-KNOCKACUMMER 20-T121 | 13 | 10 | 10 | Proposed | 30/03/2025 | 11/04/2025
TO-25-KLN-SH-1-01 | 220kV FEEDER - KILLONAN 220-SHANNONBRIDGE 220-1 | Unknown | Unknown |  | Planned | April | April
TO-25-CHA-GLE-1-01 | 110kV FEEDER - CHARLEVILLE 110-GLENLARA 110-1 | Unknown | Unknown | 30 | Planned | April | May
TO-25-GRO-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - GARROW 110-GARROW 110-110SA1-2CB | Unknown | Unknown | 5 | Planned | May | May
TO-25-GRO-T122-01 | GENERATOR TRANSFORMER - GARROW 110-GARROW 20-T122 | Unknown | Unknown | 5 | Planned | May | May
TO-25-CLH-T122-01 | GENERATOR TRANSFORMER - CLAHANE 110-CLAHANE 20-T122 | Unknown | Unknown | 1 | Planned | May | May
TO-25-AUG-CFM-2-01 | 110kV FEEDER - AUGHINISH 110-CASTLEFARM 110-2 | Unknown | Unknown | 10 | Planned | May | May
TO-25-CFM-T102-01 | TSO CUSTOMER TRANSFORMER - CASTLEFARM 110-CASTLEFARM 10-T102 | Unknown | Unknown | 10 | Reference (Planned) | May | May
TO-25-GLE-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - GLENLARA 110-GLENLARA 110-110SA1-2CB | Unknown | Unknown | 5 | Planned | May | May
TO-25-GLE-T142-01 | DISTRIBUTION TRANSFORMER - GLENLARA 110-GLENLARA 38-T142 | Unknown | Unknown | 5 | Reference (Planned) | May | May
TO-25-LSN-T131-01 | GENERATOR TRANSFORMER - LISHEEN 110-LISHEEN 33-T131 | Unknown | Unknown |  | Planned | May | May
TO-25-REM-110SA1-01 | SECTIONALISING DISCONNECT - REAMORE 110-REAMORE 110-110SA1 | Unknown | Unknown | 8 | Planned | May | May
TO-25-REM-110SA2-01 | SECTIONALISING DISCONNECT - REAMORE 110-REAMORE 110-110SA2 | Unknown | Unknown | 8 | Planned | May | May
TO-25-REM-T141-01 | DISTRIBUTION TRANSFORMER - REAMORE 110-REAMORE 38-T141 | Unknown | Unknown | 8 | Reference (Planned) | May | May
TO-25-REM-T142-01 | DISTRIBUTION TRANSFORMER - REAMORE 110-REAMORE 38-T142 | Unknown | Unknown | 8 | Reference (Planned) | May | May
TO-25-REM-TRL-1-01 | 110kV FEEDER - REAMORE 110-TRALEE 110-1 | Unknown | Unknown | 8 | Planned | May | May
TO-25-ATE-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - ATHEA 110-ATHEA 110-110SA1-2CB | Unknown | Unknown | 5 | Planned | June | June
TO-25-ATE-DRO-1-01 | 110kV FEEDER - ATHEA 110-DROMADA 110-1 | Unknown | Unknown | 5 | Planned | June | June
TO-25-ATE-KNR-1-01 | 110kV FEEDER - ATHEA 110-KNOCKANURE 110-1 | Unknown | Unknown | 5 | Planned | June | June
TO-25-ATE-T121-01 | GENERATOR TRANSFORMER - ATHEA 110-ATHEA 20-T121 | Unknown | Unknown | 5 | Planned | June | June
TO-25-ATE-TOB-1-01 | 110kV FEEDER - ATHEA 110-TOBERTOREEN 110-1 | Unknown | Unknown | 5 | Planned | June | June
TO-25-AUG-SK-4-01 | 110kV FEEDER - AUGHINISH 110-SEALROCK 110-4 | Unknown | Unknown | 5 | Planned | June | June
TO-25-DRO-T121-01 | GENERATOR TRANSFORMER - DROMADA 110-DROMADA 20-T121 | Unknown | Unknown | 5 | Planned | June | June
TO-25-LIM-RAT-1-01 | 110kV FEEDER - LIMERICK 110-RATHKEALE 110-1 | Unknown | Unknown |  | Planned | June | June
TO-25-SK-T104-01 | GENERATOR TRANSFORMER - SEALROCK 110-SEALROCK G4-T104 | Unknown | Unknown | 5 | Planned | June | June
TO-25-TOB-T132-01 | GENERATOR TRANSFORMER - TOBERTOREEN 110-TOBERTOREEN 33-T132 | Unknown | Unknown | 5 | Planned | June | June
TO-25-MP GIS-T121-01 | GENERATOR TRANSFORMER - MONEYPOINT GIS 110-MONEYPOINT GIS 20-T121 | Unknown | Unknown | 5 | Planned | June | June
TO-25-CNO-KPG-1-01 | 110kV FEEDER - COOLNANOONAGH 110-KILPADDOGE 110-1 | Unknown | Unknown | 2 | Planned | June | June
TO-25-CNO-T131-01 | GENERATOR TRANSFORMER - COOLNANOONAGH 110-COOLNANOONAGH 33-T131 | Unknown | Unknown | 2 | Planned | June | June
TO-25-CKN-CGL-1-01 | 110kV FEEDER - CLONKEEN 110-COOMAGEARLAHY 110-1 | Unknown | Unknown | 6 | Planned | June | June
TO-25-CGL-110SA1-01 | SECTIONALISING DISCONNECT - COOMAGEARLAHY 110-COOMAGEARLAHY 110-110SA1 | Unknown | Unknown | 6 | Planned | June | June
TO-25-CGL-110SA2-01 | SECTIONALISING DISCONNECT - COOMAGEARLAHY 110-COOMAGEARLAHY 110-110SA2 | Unknown | Unknown | 6 | Planned | June | June
TO-25-CGL-GAE-1-01 | 110kV FEEDER - COOMAGEARLAHY 110-GLANLEE 110-1 | Unknown | Unknown | 6 | Planned | June | June
TO-25-CGL-T121-01 | GENERATOR TRANSFORMER - COOMAGEARLAHY 110-COOMAGEARLAHY 20-T121 | Unknown | Unknown | 6 | Planned | June | June
TO-25-CGL-T122-01 | GENERATOR TRANSFORMER - COOMAGEARLAHY 110-COOMAGEARLAHY 20-T122 | Unknown | Unknown | 6 | Planned | June | June
TO-25-GAE-T121-01 | GENERATOR TRANSFORMER - GLANLEE 110-GLANLEE 20-T121 | Unknown | Unknown | 6 | Planned | June | June
TO-25-BVK-COT-1-01 | 110kV FEEDER - BALLYVOUSKILL 110-COOMATAGGART 110-1 | Unknown | Unknown | 10 | Planned | June | July
TO-25-COT-110SA1-01 | SECTIONALISING DISCONNECT - COOMATAGGART 110-COOMATAGGART 110-110SA1 | Unknown | Unknown | 10 | Planned | June | July
TO-25-COT-110SA2-01 | SECTIONALISING DISCONNECT - COOMATAGGART 110-COOMATAGGART 110-110SA2 | Unknown | Unknown | 10 | Planned | June | July
TO-25-COT-FILTER1-01 | CAPACITOR/SVC/REACTOR - COOMATAGGART 110-COOMATAGGART 110-FILTER1 | Unknown | Unknown | 10 | Planned | June | July
TO-25-COT-T132-01 | GENERATOR TRANSFORMER - COOMATAGGART 110-COOMATAGGART 33-T132 | Unknown | Unknown | 10 | Planned | June | July
TO-25-COT-T141-01 | DISTRIBUTION TRANSFORMER - COOMATAGGART 110-COOMATAGGART 38-T141 | Unknown | Unknown | 10 | Reference (Planned) | June | July
TO-25-AUG-SK-3-01 | 110kV FEEDER - AUGHINISH 110-SEALROCK 110-3 | Unknown | Unknown | 15 | Planned | July | August
TO-25-SK-T103-01 | GENERATOR TRANSFORMER - SEALROCK 110-SEALROCK G3-T103 | Unknown | Unknown | 15 | Planned | July | August
TO-25-CBA-110SA1-01 | SECTIONALISING DISCONNECT - CLOGHBOOLA 110-CLOGHBOOLA 110-110SA1 | Unknown | Unknown | 12 | Planned | July | July
TO-25-CBA-110SA2-01 | SECTIONALISING DISCONNECT - CLOGHBOOLA 110-CLOGHBOOLA 110-110SA2 | Unknown | Unknown | 12 | Planned | July | July
TO-25-CBA-T122-01 | DISTRIBUTION TRANSFORMER - CLOGHBOOLA 110-CLOGHBOOLA 20-T122 | Unknown | Unknown | 12 | Reference (Planned) | July | July
TO-25-CBA-T131-01 | GENERATOR TRANSFORMER - CLOGHBOOLA 110-CLOGHBOOLA 33-T131 | Unknown | Unknown | 12 | Planned | July | July
TO-25-CBA-TRI-1-01 | 110kV FEEDER - CLOGHBOOLA 110-TRIEN 110-1 | Unknown | Unknown | 12 | Planned | July | July
TO-25-BYH-CDL-1-01 | 110kV FEEDER - BALLYNAHULLA 110-CORDAL 110-1 | Unknown | Unknown | 15 | Planned | August | August
TO-25-CDL-110SA1-01 | SECTIONALISING DISCONNECT - CORDAL 110-CORDAL 110-110SA1 | Unknown | Unknown | 15 | Planned | August | August
TO-25-CDL-110SA2-01 | SECTIONALISING DISCONNECT - CORDAL 110-CORDAL 110-110SA2 | Unknown | Unknown | 15 | Planned | August | August
TO-25-CDL-T132-01 | GENERATOR TRANSFORMER - CORDAL 110-CORDAL 33-T132 | Unknown | Unknown | 15 | Planned | August | August
TO-25-CHA-MAL-1-01 | 110kV FEEDER - CHARLEVILLE 110-MALLOW 110-1 | Unknown | Unknown | 13 | Planned | August | September
TO-25-AUG-CFM-1-01 | 110kV FEEDER - AUGHINISH 110-CASTLEFARM 110-1 | Unknown | Unknown | 10 | Planned | September | September
TO-25-CFM-T101-01 | TSO CUSTOMER TRANSFORMER - CASTLEFARM 110-CASTLEFARM 10-T101 | Unknown | Unknown | 10 | Reference (Planned) | September | September
TO-25-CHA-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - CHARLEVILLE 110-CHARLEVILLE 110-110SA1-2CB | Unknown | Unknown | 5 | Planned | November | November
TO-25-CHA-MAL-1-02 | 110kV FEEDER - CHARLEVILLE 110-MALLOW 110-1 | Unknown | Unknown | 5 | Planned | November | November
TO-25-CHA-T142-01 | DISTRIBUTION TRANSFORMER - CHARLEVILLE 110-CHARLEVILLE 38-T142 | Unknown | Unknown | 5 | Reference (Planned) | November | November

## GEN_SouthEast
Outage ID | Feeder ID | Calendar Day Duration | Working Day Duration | Work Days | Outage Status | Start | Finish
TO-25-GI-T141-01 | DISTRIBUTION TRANSFORMER - GREAT ISLAND 110-GREAT ISLAND 38-T141 | 639 | 446 | 446 | Reference | 02/04/2024 | 31/12/2025
TO-25-CUS-PLS-1-01 | 110kV FEEDER - CUSHALING 110-PORTLAOISE 110-1 | 128 | 89 |  | Scheduled | 11/12/2024 | 17/04/2025
TO-25-110 kV A2 @ PLS-01 | BUSBAR SECTION - PORTLAOISE 110-PORTLAOISE 110-110A2 | 128 | 89 |  | Scheduled | 11/12/2024 | 17/04/2025
TO-25-110 kV B2 @ PLS-01 | BUSBAR SECTION - PORTLAOISE 110-PORTLAOISE 110-110B2 | 128 | 89 |  | Scheduled | 11/12/2024 | 17/04/2025
TO-25-ARK-SHE-2-01 | 110kV FEEDER - ARKLOW 110-SHELTON ABBEY 110-2 | 15 | 10 | 10 | Scheduled | 23/12/2024 | 06/01/2025
TO-25-SHE-T102-01 | TSO CUSTOMER TRANSFORMER - SHELTON ABBEY 110-SHELTON ABBEY 10-T102 | 15 | 10 | 10 | Scheduled | 23/12/2024 | 06/01/2025
TO-25-CUS-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - CUSHALING 110-CUSHALING 110-110SA1-2CB | 1 | 1 | 1 | Scheduled | 14/01/2025 | 14/01/2025
TO-25-CUS-KIR-1-01 | 110kV FEEDER - CUSHALING 110-KILCUMBER 110-1 | 1 | 1 | 1 | Scheduled | 14/01/2025 | 14/01/2025
TO-25-CUS-MLC-1-01 | 110kV FEEDER - CUSHALING 110-MOUNTLUCAS 110-1 | 1 | 1 | 1 | Scheduled | 14/01/2025 | 14/01/2025
TO-25-CUS-T101-01 | GENERATOR TRANSFORMER - CUSHALING 110-CUSHALING G1-T101 | 1 | 1 | 1 | Scheduled | 14/01/2025 | 14/01/2025
TO-25-KIR-T131-02 | GENERATOR TRANSFORMER - KILCUMBER 110-KILCUMBER 33-T131 | 1 | 1 | 1 | Scheduled | 14/01/2025 | 14/01/2025
TO-25-BAR,T-CAH-1-01 | 110kV FEEDER - BARRYMORE tee-CAHIR 110-1 | 19 | 15 | 15 | Scheduled | 10/02/2025 | 28/02/2025
TO-25-ROP-WEX-1-01 | 110kV FEEDER - ROSSPILE 110-WEXFORD 110-1 | 7 | 5 |  | Scheduled | 12/02/2025 | 18/02/2025
TO-25-WEX-110SA1-2CB-03 | COUPLER/SECTIONALISING CB - WEXFORD 110-WEXFORD 110-110SA1-2CB | 7 | 5 |  | Scheduled | 12/02/2025 | 18/02/2025
TO-25-WEX-T121-01 | DISTRIBUTION TRANSFORMER - WEXFORD 110-WEXFORD 20-T121 | 7 | 5 | 5 | Reference | 12/02/2025 | 18/02/2025
TO-25-WEX-T141-01 | DISTRIBUTION TRANSFORMER - WEXFORD 110-WEXFORD 38-T141 | 7 | 5 | 5 | Reference | 12/02/2025 | 18/02/2025
TO-25-110 kV A2 @ CAH-01 | BUSBAR SECTION - CAHIR 110-CAHIR 110-110A2 | 12 | 10 | 10 | Scheduled | 17/02/2025 | 28/02/2025
TO-25-110 kV B2 @ CAH-01 | BUSBAR SECTION - CAHIR 110-CAHIR 110-110B2 | 12 | 10 | 10 | Scheduled | 17/02/2025 | 28/02/2025
TO-25-110 kV A2 @ GI-03 | BUSBAR SECTION - GREAT ISLAND 110-GREAT ISLAND 110-110A2 | 10 | 8 | 8 | Scheduled | 19/02/2025 | 28/02/2025
TO-25-110 kV B2 @ GI-02 | BUSBAR SECTION - GREAT ISLAND 110-GREAT ISLAND 110-110B2 | 10 | 8 | 8 | Scheduled | 19/02/2025 | 28/02/2025
TO-25-GI-ROP-1-01 | 110kV FEEDER - GREAT ISLAND 110-ROSSPILE 110-1 | 10 | 8 |  | Scheduled | 19/02/2025 | 28/02/2025
TO-25-BOT-MLC-1-02 | 110kV FEEDER - BOGTOWN 110-MOUNTLUCAS 110-1 | 12 | 10 | 10 | Proposed | 03/03/2025 | 14/03/2025
TO-25-BOT-MLC-1-01 | 110kV FEEDER - BOGTOWN 110-MOUNTLUCAS 110-1 | 12 | 10 | 10 | Scheduled | 03/03/2025 | 14/03/2025
TO-25-BOT-T132-01 | GENERATOR TRANSFORMER - BOGTOWN 110-BOGTOWN 33-T132 | 12 | 10 | 10 | Scheduled | 03/03/2025 | 14/03/2025
TO-25-BGT-141-01 | DISTRIBUTION TRANSFORMER - BALLYRAGGET 110-BALLYRAGGET 38-T141 | 43 | 30 | 30 | Reference (Proposed) | 04/03/2025 | 15/04/2025
TO-25-BAR,T-CAH-1-03 | 110kV FEEDER - BARRYMORE tee-CAHIR 110-1 | 3 | 3 | 3 | Scheduled | 12/03/2025 | 14/03/2025
TO-25-KTN-T102-01 | DISTRIBUTION TRANSFORMER - KILLOTERAN 110-KILLOTERAN 10-T102 | 59 | 40 | 40 | Reference | 18/03/2025 | 15/05/2025
TO-25-KTN-WAT-1-01 | 110kV FEEDER - KILLOTERAN 110-WATERFORD 110-1 | 59 | 40 |  | Scheduled | 18/03/2025 | 15/05/2025
TO-25-KTN-WAT-1-03 | 110kV FEEDER - KILLOTERAN 110-WATERFORD 110-1 | 59 | 40 | 40 | Proposed | 18/03/2025 | 15/05/2025
TO-25-KRA-WOH-1-03 | 110kV FEEDER - KNOCKRAHA 110-WOODHOUSE 110-1 | 3 | 3 | 3 | Proposed | 18/03/2025 | 20/03/2025
TO-25-WOH-T122-01 | GENERATOR TRANSFORMER - WOODHOUSE 110-WOODHOUSE 20-T122 | Unknown | Unknown | 3 | Planned | March | April
TO-25-WOH-T122-02 | GENERATOR TRANSFORMER - WOODHOUSE 110-WOODHOUSE 20-T122 | 4 | 4 | 4 | Proposed | 31/03/2025 | 03/04/2025
TO-25-BGT-110K1-02 | COUPLER/SECTIONALISING CB - BALLYRAGGET 110-BALLYRAGGET 110-110K1 | 3 | 3 | 3 | Proposed | 09/04/2025 | 11/04/2025
TO-25-BGT-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - BALLYRAGGET 110-BALLYRAGGET 110-110SA1-2CB | 3 | 3 | 3 | Proposed | 09/04/2025 | 11/04/2025
TO-25-BGT-110SB1-2CB-02 | COUPLER/SECTIONALISING CB - BALLYRAGGET 110-BALLYRAGGET 110-110SB1-2CB | 3 | 3 | 3 | Proposed | 09/04/2025 | 11/04/2025
TO-25-BGT-KKY-1-02 | 110kV FEEDER - BALLYRAGGET 110-KILKENNY 110-1 | 3 | 3 | 3 | Proposed | 09/04/2025 | 11/04/2025
TO-25-BGT-141-02 | DISTRIBUTION TRANSFORMER - BALLYRAGGET 110-BALLYRAGGET 38-T141 | 3 | 3 | 3 | Reference (Proposed) | 09/04/2025 | 11/04/2025
TO-25-BGT-110K1-01 | COUPLER/SECTIONALISING CB - BALLYRAGGET 110-BALLYRAGGET 110-110K1 | 2 | 2 |  | Proposed | 14/04/2025 | 15/04/2025
TO-25-110kV B1 @ BGT-01 | BUSBAR SECTION - BALLYRAGGET 110-BALLYRAGGET 110-110B1 | 2 | 2 | 2 | Proposed | 14/04/2025 | 15/04/2025
TO-25-BGT-110SB1-2CB-01 | COUPLER/SECTIONALISING CB - BALLYRAGGET 110-BALLYRAGGET 110-110SB1-2CB | 2 | 2 |  | Proposed | 14/04/2025 | 15/04/2025
TO-25-BGT-KKY-1-01 | 110kV FEEDER - BALLYRAGGET 110-KILKENNY 110-1 | 2 | 2 |  | Proposed | 14/04/2025 | 15/04/2025
TO-25-KTN-WAT-1-02 | 110kV FEEDER - KILLOTERAN 110-WATERFORD 110-1 | Unknown | Unknown | 20 | Planned | April | May
TO-25-CLW-KLS-1-02 | 110kV FEEDER - CARLOW 110-KELLIS 110-1 | Unknown | Unknown | 40 | Planned | April | June
TO-25-CLW-KLS-1-05 | 110kV FEEDER - CARLOW 110-KELLIS 110-1 | Unknown | Unknown | 11 | Planned | April | May
TO-25-CDK-LWD-1-01 | 110kV FEEDER - CASTLEDOCKRELL 110-LODGEWOOD 110-1 | Unknown | Unknown | 5 | Planned | April | April
TO-25-CDK-T121-01 | GENERATOR TRANSFORMER - CASTLEDOCKRELL 110-CASTLEDOCKRELL 20-T121 | Unknown | Unknown | 5 | Reference (Planned) | April | April
TO-25-LWD-110K1-2-01 | COUPLER/SECTIONALISING CB - LODGEWOOD 110-LODGEWOOD 110-110K1-2 | Unknown | Unknown | 5 | Planned | April | April
TO-25-LWD-T2102-01 | TRANSFORMER - LODGEWOOD 220-LODGEWOOD 110-T2102 | Unknown | Unknown | 5 | Planned | April | April
TO-25-MAY-SH-1-01 | 220kV FEEDER - MAYNOOTH 220-SHANNONBRIDGE 220-1 | Unknown | Unknown |  | Planned | April | September
TO-25-ROP-T131-02 | GENERATOR TRANSFORMER - ROSSPILE 110-ROSSPILE 33-T131 | 1 | 1 | 1 | Proposed | 23/04/2025 | 23/04/2025
TO-25-ROP-T131-01 | GENERATOR TRANSFORMER - ROSSPILE 110-ROSSPILE 33-T131 | 1 | 1 | 1 | Proposed | 23/04/2025 | 23/04/2025
TO-25-CAH-110K1-2-01 | COUPLER/SECTIONALISING CB - CAHIR 110-CAHIR 110-110K1-2 | Unknown | Unknown | 30 | Planned | April | June
TO-25-CRA-WEX-1-02 | 110kV FEEDER - CRANE 110-WEXFORD 110-1 | Unknown | Unknown |  | Planned | April | September
TO-25-KTN-110SA1-01 | SECTIONALISING DISCONNECT - KILLOTERAN 110-KILLOTERAN 110-110SA1 | 7 | 5 |  | Scheduled | 09/05/2025 | 15/05/2025
TO-25-KTN-110SA1-02 | SECTIONALISING DISCONNECT - KILLOTERAN 110-KILLOTERAN 110-110SA1 | Unknown | Unknown | 6 | Planned | May | May
TO-25-KTN-110SA2-01 | SECTIONALISING DISCONNECT - KILLOTERAN 110-KILLOTERAN 110-110SA2 | 7 | 5 | 5 | Scheduled | 09/05/2025 | 15/05/2025
TO-25-KTN-110SA2-02 | SECTIONALISING DISCONNECT - KILLOTERAN 110-KILLOTERAN 110-110SA2 | Unknown | Unknown | 6 | Planned | May | May
TO-25-KTN-T102-02 | DISTRIBUTION TRANSFORMER - KILLOTERAN 110-KILLOTERAN 10-T102 | Unknown | Unknown | 6 | Reference (Planned) | May | May
TO-25-WAT-110SA1-02 | SECTIONALISING DISCONNECT - WATERFORD 110-WATERFORD 110-110SA1 | Unknown | Unknown | 6 | Planned | May | May
TO-25-WAT-110SA2-02 | SECTIONALISING DISCONNECT - WATERFORD 110-WATERFORD 110-110SA2 | Unknown | Unknown | 6 | Planned | May | May
TO-25-WAT-T141-01 | DISTRIBUTION TRANSFORMER - WATERFORD 110-WATERFORD 38-T141 | Unknown | Unknown | 6 | Reference (Planned) | May | May
TO-25-STR-T141-02 | DISTRIBUTION TRANSFORMER - STRATFORD 110-STRATFORD 38-T141 | Unknown | Unknown | 15 | Reference (Planned) | May | May
TO-25-STR,T-CLW-1-02 | 110kV FEEDER - STRATFORD tee-CARLOW 110-1 | Unknown | Unknown | 15 | Planned | May | May
TO-25-STR,T-PA-1-02 | 110kV FEEDER - STRATFORD tee-POLLAPHUCA 110-1 | Unknown | Unknown | 15 | Planned | May | May
TO-25-STR,T-STR-1-02 | 110kV FEEDER - STRATFORD tee-STRATFORD 110-1 | Unknown | Unknown | 15 | Planned | May | May
TO-25-BUT-KTN-1-03 | 110kV FEEDER - BUTLERSTOWN 110-KILLOTERAN 110-1 | Unknown | Unknown | 40 | Planned | May | July
TO-25-BWR-CRA-1-01 | 110kV FEEDER - BALLYWATER 110-CRANE 110-1 | Unknown | Unknown |  | Planned | May | June
TO-25-BWR-T124-01 | GENERATOR TRANSFORMER - BALLYWATER 110-BALLYWATER 20-T124 | Unknown | Unknown |  | Reference (Planned) | May | June
TO-25-CRA-110SA1-01 | SECTIONALISING DISCONNECT - CRANE 110-CRANE 110-110SA1 | Unknown | Unknown |  | Planned | May | June
TO-25-CRA-110SA2-01 | SECTIONALISING DISCONNECT - CRANE 110-CRANE 110-110SA2 | Unknown | Unknown |  | Planned | May | June
TO-25-CRA-LWD-1-01 | 110kV FEEDER - CRANE 110-LODGEWOOD 110-1 | Unknown | Unknown |  | Planned | May | June
TO-25-CRA-T122-01 | DISTRIBUTION TRANSFORMER - CRANE 110-CRANE 20-T122 | Unknown | Unknown |  | Reference (Planned) | May | June
TO-25-CDK-LWD-1-02 | 110kV FEEDER - CASTLEDOCKRELL 110-LODGEWOOD 110-1 | Unknown | Unknown | 4 | Planned | June | June
TO-25-CDK-T121-02 | GENERATOR TRANSFORMER - CASTLEDOCKRELL 110-CASTLEDOCKRELL 20-T121 | Unknown | Unknown | 4 | Reference (Planned) | June | June
TO-25-ATY-CLW-1-03 | 110kV FEEDER - ATHY 110-CARLOW 110-1 | Unknown | Unknown |  | Planned | June | June
TO-25-CLW-110SA1-02 | SECTIONALISING DISCONNECT - CARLOW 110-CARLOW 110-110SA1 | Unknown | Unknown |  | Planned | June | June
TO-25-CLW-110SA2-02 | SECTIONALISING DISCONNECT - CARLOW 110-CARLOW 110-110SA2 | Unknown | Unknown |  | Planned | June | June
TO-25-CLW-KLS-1-06 | 110kV FEEDER - CARLOW 110-KELLIS 110-1 | Unknown | Unknown |  | Planned | June | June
TO-25-CLW-T141-02 | DISTRIBUTION TRANSFORMER - CARLOW 110-CARLOW 38-T141 | Unknown | Unknown |  | Reference (Planned) | June | June
TO-25-BWR-CRA-1-02 | 110kV FEEDER - BALLYWATER 110-CRANE 110-1 | Unknown | Unknown |  | Planned | June | July
TO-25-BWR-T124-02 | GENERATOR TRANSFORMER - BALLYWATER 110-BALLYWATER 20-T124 | Unknown | Unknown |  | Reference (Planned) | June | July
TO-25-CRA-110SA1-02 | SECTIONALISING DISCONNECT - CRANE 110-CRANE 110-110SA1 | Unknown | Unknown |  | Planned | June | July
TO-25-CRA-110SA2-02 | SECTIONALISING DISCONNECT - CRANE 110-CRANE 110-110SA2 | Unknown | Unknown |  | Planned | June | July
TO-25-CRA-LWD-1-02 | 110kV FEEDER - CRANE 110-LODGEWOOD 110-1 | Unknown | Unknown |  | Planned | June | July
TO-25-CRA-T122-02 | DISTRIBUTION TRANSFORMER - CRANE 110-CRANE 20-T122 | Unknown | Unknown |  | Reference (Planned) | June | July
TO-25-ATY-PLS-1-02 | 110kV FEEDER - ATHY 110-PORTLAOISE 110-1 | Unknown | Unknown | 50 | Planned | June | September
TO-25-ATY-PLS-1-01 | 110kV FEEDER - ATHY 110-PORTLAOISE 110-1 | Unknown | Unknown | 8 | Planned | June | July
TO-25-CUS-KIR-1-03 | 110kV FEEDER - CUSHALING 110-KILCUMBER 110-1 | Unknown | Unknown | 2 | Planned | June | June
TO-25-KIR-T131-01 | GENERATOR TRANSFORMER - KILCUMBER 110-KILCUMBER 33-T131 | Unknown | Unknown | 1 | Planned | June | June
TO-25-KIR-T131-04 | GENERATOR TRANSFORMER - KILCUMBER 110-KILCUMBER 33-T131 | Unknown | Unknown | 2 | Planned | June | June
TO-25-CUS-T101-03 | GENERATOR TRANSFORMER - CUSHALING 110-CUSHALING G1-T101 | Unknown | Unknown | 1 | Planned | July | July
TO-25-BWR-CRA-1-03 | 110kV FEEDER - BALLYWATER 110-CRANE 110-1 | Unknown | Unknown |  | Planned | July | July
TO-25-BWR-T124-03 | GENERATOR TRANSFORMER - BALLYWATER 110-BALLYWATER 20-T124 | Unknown | Unknown |  | Reference (Planned) | July | July
TO-25-CRA-110SA1-04 | SECTIONALISING DISCONNECT - CRANE 110-CRANE 110-110SA1 | Unknown | Unknown | 1 | Planned | July | July
TO-25-CRA-110SA2-03 | SECTIONALISING DISCONNECT - CRANE 110-CRANE 110-110SA2 | Unknown | Unknown |  | Planned | July | July
TO-25-CRA-LWD-1-03 | 110kV FEEDER - CRANE 110-LODGEWOOD 110-1 | Unknown | Unknown |  | Planned | July | July
TO-25-CRA-T122-03 | DISTRIBUTION TRANSFORMER - CRANE 110-CRANE 20-T122 | Unknown | Unknown |  | Reference (Planned) | July | July
TO-25-ATY-110SA1-01 | SECTIONALISING DISCONNECT - ATHY 110-ATHY 110-110SA1 | Unknown | Unknown |  | Planned | July | July
TO-25-ATY-110SA2-02 | SECTIONALISING DISCONNECT - ATHY 110-ATHY 110-110SA2 | Unknown | Unknown | 10 | Planned | July | July
TO-25-ATY-PLS-1-03 | 110kV FEEDER - ATHY 110-PORTLAOISE 110-1 | Unknown | Unknown | 10 | Planned | July | July
TO-25-ATY-T102-01 | DISTRIBUTION TRANSFORMER - ATHY 110-ATHY 10-T102 | Unknown | Unknown | 10 | Reference (Planned) | July | July
TO-25-CRA-WEX-1-01 | 110kV FEEDER - CRANE 110-WEXFORD 110-1 | Unknown | Unknown | 5 | Planned | July | July
TO-25-WEX-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - WEXFORD 110-WEXFORD 110-110SA1-2CB | Unknown | Unknown | 5 | Planned | July | July
TO-25-WEX-CAP2-01 | CAPACITOR/SVC/REACTOR - WEXFORD 110-WEXFORD 110-CAP2 | Unknown | Unknown | 5 | Planned | July | July
TO-25-WEX-CAP4-01 | CAPACITOR/SVC/REACTOR - WEXFORD 110-WEXFORD 110-CAP4 | Unknown | Unknown | 5 | Planned | July | July
TO-25-WEX-T122-01 | DISTRIBUTION TRANSFORMER - WEXFORD 110-WEXFORD 20-T122 | Unknown | Unknown | 5 | Reference (Planned) | July | July
TO-25-WEX-T142-01 | DISTRIBUTION TRANSFORMER - WEXFORD 110-WEXFORD 38-T142 | Unknown | Unknown | 5 | Reference (Planned) | July | July
TO-25-STN-T131-01 | GENERATOR TRANSFORMER - STONESTOWN 110-STONESTOWN 33-T131 | Unknown | Unknown | 1 | Planned | July | July
TO-25-ATY-T102-02 | DISTRIBUTION TRANSFORMER - ATHY 110-ATHY 10-T102 | Unknown | Unknown | 8 | Reference (Planned) | July | July
TO-25-CUS-T103/5-03 | GENERATOR TRANSFORMER - CUSHALING 110-CUSHALING G3/5-T103/5 | Unknown | Unknown | 10 | Planned | July | August
TO-25-CLW-KLS-2-01 | 110kV FEEDER - CARLOW 110-KELLIS 110-2 | Unknown | Unknown |  | Planned | August | August
TO-25-KLS-110K1-2-01 | COUPLER/SECTIONALISING CB - KELLIS 110-KELLIS 110-110K1-2 | Unknown | Unknown |  | Planned | August | August
TO-25-KLS-KKY-1-01 | 110kV FEEDER - KELLIS 110-KILKENNY 110-1 | Unknown | Unknown |  | Planned | August | August
TO-25-KLS-T2102-01 | TRANSFORMER - KELLIS 220-KELLIS 110-T2102 | Unknown | Unknown |  | Planned | August | August
TO-25-CUS-T103/5-01 | GENERATOR TRANSFORMER - CUSHALING 110-CUSHALING G3/5-T103/5 | Unknown | Unknown | 6 | Planned | August | August
TO-25-110 kV A2 @ KLS-01 | BUSBAR SECTION - KELLIS 110-KELLIS 110-110A2 | Unknown | Unknown |  | Planned | August | August
TO-25-110 kV B2 @ KLS-01 | BUSBAR SECTION - KELLIS 110-KELLIS 110-110B2 | Unknown | Unknown |  | Planned | August | August
TO-25-CRA-WEX-1-03 | 110kV FEEDER - CRANE 110-WEXFORD 110-1 | Unknown | Unknown |  | Planned | August | August
TO-25-WEX-110SA1-2CB-02 | COUPLER/SECTIONALISING CB - WEXFORD 110-WEXFORD 110-110SA1-2CB | Unknown | Unknown |  | Planned | August | August
TO-25-WEX-CAP2-02 | CAPACITOR/SVC/REACTOR - WEXFORD 110-WEXFORD 110-CAP2 | Unknown | Unknown |  | Planned | August | August
TO-25-WEX-CAP4-02 | CAPACITOR/SVC/REACTOR - WEXFORD 110-WEXFORD 110-CAP4 | Unknown | Unknown |  | Planned | August | August
TO-25-WEX-T122-02 | DISTRIBUTION TRANSFORMER - WEXFORD 110-WEXFORD 20-T122 | Unknown | Unknown |  | Reference (Planned) | August | August
TO-25-WEX-T142-02 | DISTRIBUTION TRANSFORMER - WEXFORD 110-WEXFORD 38-T142 | Unknown | Unknown |  | Reference (Planned) | August | August
TO-25-KLS-110K1-2-02 | COUPLER/SECTIONALISING CB - KELLIS 110-KELLIS 110-110K1-2 | Unknown | Unknown |  | Planned | August | August
TO-25-KLS-KKY-1-02 | 110kV FEEDER - KELLIS 110-KILKENNY 110-1 | Unknown | Unknown |  | Planned | August | August
TO-25-110 kV A2 @ KLS-02 | BUSBAR SECTION - KELLIS 110-KELLIS 110-110A2 | Unknown | Unknown | 2 | Planned | August | August
TO-25-110 kV B2 @ KLS-02 | BUSBAR SECTION - KELLIS 110-KELLIS 110-110B2 | Unknown | Unknown | 2 | Planned | August | August
TO-25-KLS-T2102-02 | TRANSFORMER - KELLIS 220-KELLIS 110-T2102 | Unknown | Unknown |  | Planned | August | August
TO-25-NEW-PLS-1-01 | 110kV FEEDER - NEWBRIDGE 110-PORTLAOISE 110-1 | Unknown | Unknown | 55 | Planned | September | November
TO-25-BDA-T102-01 | TSO CUSTOMER TRANSFORMER - BARODA 110-BARODA 10-T102 | Unknown | Unknown | 7 | Planned | September | September
TO-25-BWR-CRA-1-04 | 110kV FEEDER - BALLYWATER 110-CRANE 110-1 | Unknown | Unknown | 5 | Planned | September | September
TO-25-BWR-T124-04 | GENERATOR TRANSFORMER - BALLYWATER 110-BALLYWATER 20-T124 | Unknown | Unknown | 5 | Reference (Planned) | September | September
TO-25-CRA-110SA1-03 | SECTIONALISING DISCONNECT - CRANE 110-CRANE 110-110SA1 | Unknown | Unknown | 5 | Planned | September | September
TO-25-CRA-110SA2-04 | SECTIONALISING DISCONNECT - CRANE 110-CRANE 110-110SA2 | Unknown | Unknown | 5 | Planned | September | September
TO-25-CRA-LWD-1-04 | 110kV FEEDER - CRANE 110-LODGEWOOD 110-1 | Unknown | Unknown | 5 | Planned | September | September
TO-25-CRA-T122-04 | DISTRIBUTION TRANSFORMER - CRANE 110-CRANE 20-T122 | Unknown | Unknown | 5 | Reference (Planned) | September | September
TO-25-TTU-131-01 | GENERATOR TRANSFORMER - TULLABEG 110-TULLABEG 33-T131 | Unknown | Unknown | 2 | Planned | November | November
TO-25-KRA-WOH-1-01 | 110kV FEEDER - KNOCKRAHA 110-WOODHOUSE 110-1 | Unknown | Unknown |  | Planned | November | November
TO-25-KRA-WOH-1-02 | 110kV FEEDER - KNOCKRAHA 110-WOODHOUSE 110-1 | Unknown | Unknown | 10 | Planned | November | November

## GEN_NorthWest
Outage ID | Feeder ID | Calendar Day Duration | Working Day Duration | Work Days | Outage Status | Start | Finish
TO-25-CSH-DLT-1-01 | 110kV FEEDER - CASHLA 110-DALTON 110-1 | 3 | 3 | 3 | Scheduled | 15/01/2025 | 17/01/2025
TO-25-FLA-SLB-1-01 | 110kV FEEDER - FLAGFORD 110-SLIABH BAWN 110-1 | 19 | 15 | 15 | Scheduled | 10/02/2025 | 28/02/2025
TO-25-110 kV A2 @ CSH-03 | BUSBAR SECTION - CASHLA 110-CASHLA 110-110A2 | 12 | 10 | 10 | Scheduled | 17/02/2025 | 28/02/2025
TO-25-110 kV B2 @ CSH-05 | BUSBAR SECTION - CASHLA 110-CASHLA 110-110B2 | 12 | 10 | 10 | Scheduled | 17/02/2025 | 28/02/2025
TO-25-220 kV A4 @ CSH-02 | BUSBAR SECTION - CASHLA 220-CASHLA 220-220A4 | 12 | 10 | 10 | Scheduled | 17/02/2025 | 28/02/2025
TO-25-220 kV B4 @ CSH-02 | BUSBAR SECTION - CASHLA 220-CASHLA 220-220B4 | 12 | 10 | 10 | Scheduled | 17/02/2025 | 28/02/2025
TO-25-CSH-T2104-01 | TRANSFORMER - CASHLA 220-CASHLA 110-T2104 | 26 | 20 |  | Scheduled | 17/02/2025 | 14/03/2025
TO-25-CUN-GLR-1-01 | 110kV FEEDER - CUNGHILL 110-GLENREE 110-1 | 12 | 10 |  | Scheduled | 17/02/2025 | 28/02/2025
TO-25-110 kV A1 @ CF-04 | BUSBAR SECTION - CATHALEENS FALL 110-CATHALEENS FALL 110-110A1 | 43 | 30 | 30 | Scheduled | 26/02/2025 | 09/04/2025
TO-25-110 kV A2 @ CF-02 | BUSBAR SECTION - CATHALEENS FALL 110-CATHALEENS FALL 110-110A2 | 43 | 30 | 30 | Scheduled | 26/02/2025 | 09/04/2025
TO-25-110 kV B1 @ CF-03 | BUSBAR SECTION - CATHALEENS FALL 110-CATHALEENS FALL 110-110B1 | 43 | 30 | 30 | Scheduled | 26/02/2025 | 09/04/2025
TO-25-110 kV B2 @ CF-01 | BUSBAR SECTION - CATHALEENS FALL 110-CATHALEENS FALL 110-110B2 | 43 | 30 | 30 | Scheduled | 26/02/2025 | 09/04/2025
TO-25-CF-110K1-2-01 | COUPLER/SECTIONALISING CB - CATHALEENS FALL 110-CATHALEENS FALL 110-110K1-2 | 43 | 30 | 30 | Scheduled | 26/02/2025 | 09/04/2025
TO-25-220 kV A1 @ CSH-01 | BUSBAR SECTION - CASHLA 220-CASHLA 220-220A1 | 12 | 10 | 10 | Proposed | 03/03/2025 | 14/03/2025
TO-25-220 kV A2 @ CSH-01 | BUSBAR SECTION - CASHLA 220-CASHLA 220-220A2 | 12 | 10 | 10 | Proposed | 03/03/2025 | 14/03/2025
TO-25-220 kV B1 @ CSH-01 | BUSBAR SECTION - CASHLA 220-CASHLA 220-220B1 | 12 | 10 | 10 | Proposed | 03/03/2025 | 14/03/2025
TO-25-220 kV B2 @ CSH-01 | BUSBAR SECTION - CASHLA 220-CASHLA 220-220B2 | 12 | 10 | 10 | Proposed | 03/03/2025 | 14/03/2025
TO-25-CSH-220K1-2-01 | COUPLER/SECTIONALISING CB - CASHLA 220-CASHLA 220-220K1-2 | 12 | 10 | 10 | Proposed | 03/03/2025 | 14/03/2025
TO-25-CSH-T2104-02 | TRANSFORMER - CASHLA 220-CASHLA 110-T2104 | 8 | 6 | 6 | Proposed | 03/03/2025 | 10/03/2025
TO-25-FLA-SLI-1-02 | 110kV FEEDER - FLAGFORD 110-SLIGO 110-1 | 1 | 1 |  | Proposed | 04/03/2025 | 04/03/2025
TO-25-UGL-T134-01 | GENERATOR TRANSFORMER - UGGOOL 110-UGGOOL 33-T134 | 64 | 42 | 42 | Proposed | 13/03/2025 | 15/05/2025
TO-25-220 kV A2 @ CSH-02 | BUSBAR SECTION - CASHLA 220-CASHLA 220-220A2 | 11 | 9 | 9 | Proposed | 18/03/2025 | 28/03/2025
TO-25-220 kV A4 @ CSH-01 | BUSBAR SECTION - CASHLA 220-CASHLA 220-220A4 | 11 | 9 | 9 | Proposed | 18/03/2025 | 28/03/2025
TO-25-220 kV B2 @ CSH-02 | BUSBAR SECTION - CASHLA 220-CASHLA 220-220B2 | 11 | 9 | 9 | Proposed | 18/03/2025 | 28/03/2025
TO-25-220 kV B4 @ CSH-01 | BUSBAR SECTION - CASHLA 220-CASHLA 220-220B4 | 11 | 9 | 9 | Proposed | 18/03/2025 | 28/03/2025
TO-25-CSH-220K2-4-01 | COUPLER/SECTIONALISING CB - CASHLA 220-CASHLA 220-220K2-4 | 11 | 9 | 9 | Proposed | 18/03/2025 | 28/03/2025
TO-25-110 kV A1 @ FLA-01 | BUSBAR SECTION - FLAGFORD 110-FLAGFORD 110-110A1 | Unknown | Unknown | 40 | Planned | March | May
TO-25-110 kV B1 @ FLA-01 | BUSBAR SECTION - FLAGFORD 110-FLAGFORD 110-110B1 | Unknown | Unknown | 40 | Planned | March | May
TO-25-FLA-SLB-1-02 | 110kV FEEDER - FLAGFORD 110-SLIABH BAWN 110-1 | Unknown | Unknown | 40 | Planned | March | May
TO-25-FLA-SLB-1-04 | 110kV FEEDER - FLAGFORD 110-SLIABH BAWN 110-1 | 59 | 40 | 40 | Proposed | 18/03/2025 | 15/05/2025
TO-25-110 kV A2 @ CSH-02 | BUSBAR SECTION - CASHLA 110-CASHLA 110-110A2 | 10 | 8 | 8 | Scheduled | 19/03/2025 | 28/03/2025
TO-25-110 kV B2 @ CSH-04 | BUSBAR SECTION - CASHLA 110-CASHLA 110-110B2 | 10 | 8 | 8 | Scheduled | 19/03/2025 | 28/03/2025
TO-25-CSH-ENN-1-02 | 110kV FEEDER - CASHLA 110-ENNIS 110-1 | 59 | 40 |  | Scheduled | 19/03/2025 | 16/05/2025
TO-25-CSH-ENN-1-01 | 110kV FEEDER - CASHLA 110-ENNIS 110-1 | 59 | 40 |  | Scheduled | 19/03/2025 | 16/05/2025
TO-25-CLO-CRD-1-01 | 110kV FEEDER - CLOGHER 110-CROAGHONAGH 110-1 | 5 | 5 | 5 | Proposed | 31/03/2025 | 04/04/2025
TO-25-CRD-T131-01 | GENERATOR TRANSFORMER - CROAGHONAGH 110-CROAGHONAGH 33-T131 | 5 | 5 | 5 | Proposed | 31/03/2025 | 04/04/2025
TO-25-CF-CL-1-02 | 110kV FEEDER - CATHALEENS FALL 110-CLIFF 110-1 | 4 | 4 | 4 | Proposed | 07/04/2025 | 10/04/2025
TO-25-CL-T101-03 | GENERATOR TRANSFORMER - CLIFF 110-CLIFF G1-T101 | 4 | 4 | 4 | Proposed | 07/04/2025 | 10/04/2025
TO-25-CL-T102-01 | GENERATOR TRANSFORMER - CLIFF 110-CLIFF G2-T102 | 9 | 7 | 7 | Proposed | 07/04/2025 | 15/04/2025
TO-25-CF-T104-01 | GENERATOR TRANSFORMER - CATHALEENS FALL 110-CATHALEENS FALL G4-T104 | 14 | 9 | 9 | Proposed | 24/04/2025 | 07/05/2025
TO-25-CF-SRA-2-01 | 110kV FEEDER - CATHALEENS FALL 110-SRANANAGH 110-2 | Unknown | Unknown |  | Planned | May | July
TO-25-BUF-KNY-1-01 | 110kV FEEDER - BUFFY 110-KNOCKRANNY 110-1 | Unknown | Unknown | 3 | Planned | May | May
TO-25-BUF-T131-01 | GENERATOR TRANSFORMER - BUFFY 110-BUFFY 33-T131 | Unknown | Unknown | 3 | Planned | May | May
TO-25-BK-SKY-1-01 | 110kV FEEDER - BELLACORICK 110-SRAHNAKILLY 110-1 | Unknown | Unknown | 11 | Planned | May | May
TO-25-SKY-110SA1-01 | SECTIONALISING DISCONNECT - SRAHNAKILLY 110-SRAHNAKILLY 110-110SA1 | Unknown | Unknown | 11 | Planned | May | May
TO-25-SKY-110SA2-01 | SECTIONALISING DISCONNECT - SRAHNAKILLY 110-SRAHNAKILLY 110-110SA2 | Unknown | Unknown | 11 | Planned | May | May
TO-25-SKY-T131-02 | GENERATOR TRANSFORMER - SRAHNAKILLY 110-SRAHNAKILLY 33-T131 | Unknown | Unknown | 11 | Planned | May | May
TO-25-SKY-T132-02 | GENERATOR TRANSFORMER - SRAHNAKILLY 110-SRAHNAKILLY 33-T132 | Unknown | Unknown | 11 | Planned | May | May
TO-25-BIN-T141-01 | DISTRIBUTION TRANSFORMER - BINBANE 110-BINBANE 38-T141 | Unknown | Unknown |  | Reference (Planned) | May | August
TO-25-SKY-T131-01 | GENERATOR TRANSFORMER - SRAHNAKILLY 110-SRAHNAKILLY 33-T131 | Unknown | Unknown | 5 | Planned | May | May
TO-25-SKY-T132-01 | GENERATOR TRANSFORMER - SRAHNAKILLY 110-SRAHNAKILLY 33-T132 | Unknown | Unknown | 5 | Planned | May | May
TO-25-KNY-UGL-1-01 | 110kV FEEDER - KNOCKRANNY 110-UGGOOL 110-1 | Unknown | Unknown | 3 | Planned | May | May
TO-25-UGL-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - UGGOOL 110-UGGOOL 110-110SA1-2CB | 3 | 3 | 3 | Proposed | 13/05/2025 | 15/05/2025
TO-25-UGL-T131-01 | GENERATOR TRANSFORMER - UGGOOL 110-UGGOOL 33-T131 | Unknown | Unknown | 8 | Planned | May | May
TO-25-UGL-T132-01 | GENERATOR TRANSFORMER - UGGOOL 110-UGGOOL 33-T132 | 3 | 3 | 3 | Proposed | 13/05/2025 | 15/05/2025
TO-25-CL-T101-02 | GENERATOR TRANSFORMER - CLIFF 110-CLIFF G1-T101 | Unknown | Unknown | 8 | Planned | May | May
TO-25-GAL-GAL GIS-1-01 | 110kV FEEDER - GALWAY 110-GALWAY GIS 110-1 | Unknown | Unknown | 160 | Planned | May | December
TO-25-GAL-T103-01 | DISTRIBUTION TRANSFORMER - GALWAY 110-GALWAY 10-T103 | Unknown | Unknown | 46 | Planned | May | July
TO-25-KLH-KNY-1-01 | 110kV FEEDER - KNOCKALOUGH 110-KNOCKRANNY 110-1 | Unknown | Unknown | 3 | Planned | May | May
TO-25-KLH-T121-01 | GENERATOR TRANSFORMER - KNOCKALOUGH 110-KNOCKALOUGH 20-T121 | Unknown | Unknown | 3 | Planned | May | May
TO-25-CLO-MRY-1-01 | 110kV FEEDER - CLOGHER 110-MULREAVY 110-1 | Unknown | Unknown | 5 | Planned | May | May
TO-25-MRY-T131-01 | GENERATOR TRANSFORMER - MULREAVY 110-MULREAVY 33-T131 | Unknown | Unknown | 5 | Planned | May | May
TO-25-DRM-MEE-1-01 | 110kV FEEDER - DRUMKEEN 110-MEENTYCAT 110-1 | Unknown | Unknown | 9 | Planned | June | June
TO-25-MEE-T121-01 | GENERATOR TRANSFORMER - MEENTYCAT 110-MEENTYCAT 20-T121 | Unknown | Unknown | 9 | Planned | June | June
TO-25-CUN-T121-02 | GENERATOR TRANSFORMER - CUNGHILL 110-CUNGHILL 20-T121 | Unknown | Unknown | 6 | Planned | June | June
TO-25-110 kV A1 @ CF-02 | BUSBAR SECTION - CATHALEENS FALL 110-CATHALEENS FALL 110-110A1 | 12 | 10 | 10 | Proposed | 09/06/2025 | 20/06/2025
TO-25-110 kV B1 @ CF-01 | BUSBAR SECTION - CATHALEENS FALL 110-CATHALEENS FALL 110-110B1 | 12 | 10 | 10 | Proposed | 09/06/2025 | 20/06/2025
TO-25-CF-CLO-1-02 | 110kV FEEDER - CATHALEENS FALL 110-CLOGHER 110-1 | 12 | 10 | 10 | Proposed | 09/06/2025 | 20/06/2025
TO-25-110 kV A1 @ CLO-01 | BUSBAR SECTION - CLOGHER 110-CLOGHER 110-110A1 | 12 | 10 | 10 | Proposed | 09/06/2025 | 20/06/2025
TO-25-110 kV B1 @ CLO-01 | BUSBAR SECTION - CLOGHER 110-CLOGHER 110-110B1 | 12 | 10 | 10 | Proposed | 09/06/2025 | 20/06/2025
TO-25-DYN-T121-01 | GENERATOR TRANSFORMER - DERRYBRIEN 110-DERRYBRIEN 20-T121 | Unknown | Unknown | 3 | Reference (Planned) | June | June
TO-25-110 kV B1 @ CSH-02 | BUSBAR SECTION - CASHLA 110-CASHLA 110-110B1 | Unknown | Unknown |  | Planned | June | June
TO-25-LLA-T133-01 | GENERATOR TRANSFORMER - LENALEA 110-LENALEA 33-T133 | Unknown | Unknown | 3 | Planned | June | June
TO-25-CF-T103-01 | GENERATOR TRANSFORMER - CATHALEENS FALL 110-CATHALEENS FALL G3-T103 | Unknown | Unknown | 9 | Planned | June | July
TO-25-110 kV A1 @ CSH-02 | BUSBAR SECTION - CASHLA 110-CASHLA 110-110A1 | Unknown | Unknown |  | Planned | June | July
TO-25-SLI-110SA1-2CB-02 | COUPLER/SECTIONALISING CB - SLIGO 110-SLIGO 110-110SA1-2CB | Unknown | Unknown | 15 | Planned | July | July
TO-25-SLI-CAP1-01 | CAPACITOR/SVC/REACTOR - SLIGO 110-SLIGO 110-CAP1 | Unknown | Unknown | 15 | Planned | July | July
TO-25-SLI-SRA-1-01 | 110kV FEEDER - SLIGO 110-SRANANAGH 110-1 | Unknown | Unknown | 40 | Planned | July | September
TO-25-SLI-SRA-1-02 | 110kV FEEDER - SLIGO 110-SRANANAGH 110-1 | Unknown | Unknown |  | Planned | July | October
TO-25-SLI-T141-02 | DISTRIBUTION TRANSFORMER - SLIGO 110-SLIGO 38-T141 | Unknown | Unknown | 15 | Reference (Planned) | July | July
TO-25-GLR-MOY-1-01 | 110kV FEEDER - GLENREE 110-MOY 110-1 | Unknown | Unknown |  | Planned | July | September
TO-25-110 kV A3 @ GAL GIS-01 | BUSBAR SECTION - GALWAY GIS 110-GALWAY GIS 110-110A3 | Unknown | Unknown | 7 | Planned | July | July
TO-25-110 kV B3 @ GAL GIS-01 | BUSBAR SECTION - GALWAY GIS 110-GALWAY GIS 110-110B3 | Unknown | Unknown | 7 | Planned | July | July
TO-25-GAL GIS-110K3-01 | COUPLER/SECTIONALISING CB - GALWAY GIS 110-GALWAY GIS 110-110K3 | Unknown | Unknown | 7 | Planned | July | July
TO-25-GAL GIS-110SA1-3CB-01 | COUPLER/SECTIONALISING CB - GALWAY GIS 110-GALWAY GIS 110-110SA1-3CB | Unknown | Unknown | 7 | Planned | July | July
TO-25-GAL GIS-110SB1-3CB-01 | COUPLER/SECTIONALISING CB - GALWAY GIS 110-GALWAY GIS 110-110SB1-3CB | Unknown | Unknown | 7 | Planned | July | July
TO-25-GRV-T121-02 | GENERATOR TRANSFORMER - GARVAGH 110-GARVAGH 20-T121 | Unknown | Unknown | 6 | Planned | July | July
TO-25-CDY-GRV-1-01 | 110kV FEEDER - CORDERRY 110-GARVAGH 110-1 | Unknown | Unknown | 5 | Planned | July | July
TO-25-GRV-110K1-01 | COUPLER/SECTIONALISING CB - GARVAGH 110-GARVAGH 110-110K1 | Unknown | Unknown | 5 | Planned | July | July
TO-25-GRV-T121-01 | GENERATOR TRANSFORMER - GARVAGH 110-GARVAGH 20-T121 | Unknown | Unknown | 3 | Planned | July | July
TO-25-GRV-T141-01 | DISTRIBUTION TRANSFORMER - GARVAGH 110-GARVAGH 20-T141 | Unknown | Unknown | 5 | Reference (Planned) | July | July
TO-25-110 kV B1 @ CSH-03 | BUSBAR SECTION - CASHLA 110-CASHLA 110-110B1 | Unknown | Unknown |  | Planned | July | August
TO-25-110 kV A1 @ CSH-03 | BUSBAR SECTION - CASHLA 110-CASHLA 110-110A1 | Unknown | Unknown |  | Planned | August | September
TO-25-110 kV A1 @ CSH-04 | BUSBAR SECTION - CASHLA 110-CASHLA 110-110A1 | Unknown | Unknown |  | Planned | September | September
TO-25-110 kV B1 @ CSH-04 | BUSBAR SECTION - CASHLA 110-CASHLA 110-110B1 | Unknown | Unknown |  | Planned | September | September
TO-25-110 kV A2 @ CSH-01 | BUSBAR SECTION - CASHLA 110-CASHLA 110-110A2 | Unknown | Unknown |  | Planned | September | September
TO-25-110 kV B2 @ CSH-01 | BUSBAR SECTION - CASHLA 110-CASHLA 110-110B2 | Unknown | Unknown |  | Planned | September | September
TO-25-CSH-110K1-2-01 | COUPLER/SECTIONALISING CB - CASHLA 110-CASHLA 110-110K1-2 | Unknown | Unknown |  | Planned | September | September
TO-25-CSH-T2102-01 | TRANSFORMER - CASHLA 220-CASHLA 110-T2102 | Unknown | Unknown |  | Planned | September | September
TO-25-110 kV B1 @ CSH-05 | BUSBAR SECTION - CASHLA 110-CASHLA 110-110B1 | Unknown | Unknown | 2 | Planned | October | October
TO-25-CSH-T2101-01 | TRANSFORMER - CASHLA 220-CASHLA 110-T2101 | Unknown | Unknown |  | Planned | October | October
TO-25-110 kV A1 @ CSH-05 | BUSBAR SECTION - CASHLA 110-CASHLA 110-110A1 | Unknown | Unknown |  | Planned | October | October
TO-25-SLI-110SA1-2CB-03 | COUPLER/SECTIONALISING CB - SLIGO 110-SLIGO 110-110SA1-2CB | Unknown | Unknown | 15 | Planned | October | October
TO-25-SLI-CAP1-02 | CAPACITOR/SVC/REACTOR - SLIGO 110-SLIGO 110-CAP1 | Unknown | Unknown | 15 | Planned | October | October
TO-25-SLI-T141-01 | DISTRIBUTION TRANSFORMER - SLIGO 110-SLIGO 38-T141 | Unknown | Unknown | 15 | Reference (Planned) | October | October
TO-25-CSH-T2101-02 | TRANSFORMER - CASHLA 220-CASHLA 110-T2101 | Unknown | Unknown |  | Planned | October | October
TO-25-CF-SRA-1-01 | 110kV FEEDER - CATHALEENS FALL 110-SRANANAGH 110-1 | Unknown | Unknown |  | Planned | October | October
TO-25-110 kV A1 @ SRA-01 | BUSBAR SECTION - SRANANAGH 110-SRANANAGH 110-110A1 | Unknown | Unknown |  | Planned | October | October

## GEN_NorthEast
Outage ID | Feeder ID | Calendar Day Duration | Working Day Duration | Work Days | Outage Status | Start | Finish
TO-25-BAL-DRY-1-03 | 110kV FEEDER - BALTRASNA 110-DRYBRIDGE 110-1 | 283 | 201 | 201 | Scheduled | 13/05/2024 | 19/02/2025
TO-25-KIN-T101-02 | TSO CUSTOMER TRANSFORMER - KINNEGAD 110-KINNEGAD 10-T101 | 26 | 18 | 18 | Scheduled | 03/01/2025 | 28/01/2025
TO-25-220 kV A2 @ SH-01 | BUSBAR SECTION - SHANNONBRIDGE 220-SHANNONBRIDGE 220-220A2 | 50 | 35 | 35 | Scheduled | 06/01/2025 | 24/02/2025
TO-25-220 kV B2 @ SH-01 | BUSBAR SECTION - SHANNONBRIDGE 220-SHANNONBRIDGE 220-220B2 | 50 | 35 | 35 | Scheduled | 06/01/2025 | 24/02/2025
TO-25-110 kV A2 @ LOU-05 | BUSBAR SECTION - LOUTH 110-LOUTH 110-110A2 | 12 | 10 | 10 | Scheduled | 13/01/2025 | 24/01/2025
TO-25-110 kV B2 @ LOU-05 | BUSBAR SECTION - LOUTH 110-LOUTH 110-110B2 | 12 | 10 | 10 | Scheduled | 13/01/2025 | 24/01/2025
TO-25-220 kV A2 @ LOU-07 | BUSBAR SECTION - LOUTH 220-LOUTH 220-220A2 | 12 | 10 | 10 | Scheduled | 13/01/2025 | 24/01/2025
TO-25-220 kV B2 @ LOU-06 | BUSBAR SECTION - LOUTH 220-LOUTH 220-220B2 | 12 | 10 | 10 | Scheduled | 13/01/2025 | 24/01/2025
TO-25-LOU-T2102-01 | TRANSFORMER - LOUTH 220-LOUTH 110-T2102 | 12 | 10 | 10 | Scheduled | 13/01/2025 | 24/01/2025
TO-25-CUS-MLC-1-01 | 110kV FEEDER - CUSHALING 110-MOUNTLUCAS 110-1 | 1 | 1 | 1 | Scheduled | 14/01/2025 | 14/01/2025
TO-25-GWE-T101-03 | TSO CUSTOMER TRANSFORMER - GORTAWEE 110-GORTAWEE 10-T101 | 16 | 12 | 12 | Scheduled | 15/01/2025 | 30/01/2025
TO-25-LOU-T2101-03 | TRANSFORMER - LOUTH 220-LOUTH 110-T2101 | 16 | 11 | 11 | Scheduled | 29/01/2025 | 13/02/2025
TO-25-RRU-SKL-1-01 | 110kV FEEDER - RATRUSSAN 110-SHANKILL 110-1 | 57 | 40 | 40 | Scheduled | 05/02/2025 | 02/04/2025
TO-25-FLA-SLB-1-01 | 110kV FEEDER - FLAGFORD 110-SLIABH BAWN 110-1 | 19 | 15 | 15 | Scheduled | 10/02/2025 | 28/02/2025
TO-25-SH-T2101-03 | TRANSFORMER - SHANNONBRIDGE 220-SHANNONBRIDGE 110-T2101 | 80 | 55 |  | Scheduled | 10/02/2025 | 30/04/2025
TO-25-110 kV A2 @ SLB-01 | BUSBAR SECTION - SLIABH BAWN 110-SLIABH BAWN 110-110A2 | 19 | 15 | 15 | Scheduled | 10/02/2025 | 28/02/2025
TO-25-110 kV B2 @ SLB-01 | BUSBAR SECTION - SLIABH BAWN 110-SLIABH BAWN 110-110B2 | 19 | 15 | 15 | Scheduled | 10/02/2025 | 28/02/2025
TO-25-SLB-110K2-01 | COUPLER/SECTIONALISING CB - SLIABH BAWN 110-SLIABH BAWN 110-110K2 | 19 | 15 | 15 | Scheduled | 10/02/2025 | 28/02/2025
TO-25-DEN-DRY-1-03 | 110kV FEEDER - DEENES 110-DRYBRIDGE 110-1 | 3 | 3 | 3 | Scheduled | 17/02/2025 | 19/02/2025
TO-25-DRY-110SA1-02 | SECTIONALISING DISCONNECT - DRYBRIDGE 110-DRYBRIDGE 110-110SA1 | 3 | 3 | 3 | Scheduled | 17/02/2025 | 19/02/2025
TO-25-DRY-110SA2-02 | SECTIONALISING DISCONNECT - DRYBRIDGE 110-DRYBRIDGE 110-110SA2 | 3 | 3 | 3 | Scheduled | 17/02/2025 | 19/02/2025
TO-25-DRY-GOR-1-03 | 110kV FEEDER - DRYBRIDGE 110-GORMAN 110-1 | 3 | 3 | 3 | Scheduled | 17/02/2025 | 19/02/2025
TO-25-DRY-T142-02 | DISTRIBUTION TRANSFORMER - DRYBRIDGE 110-DRYBRIDGE 38-T142 | 3 | 3 | 3 | Reference | 17/02/2025 | 19/02/2025
TO-25-PLA-T101/2/3/4-02 | TSO CUSTOMER TRANSFORMER - PLATIN 110-PLATIN 10-T101/2/3/4 | 5 | 5 | 5 | Proposed | 17/02/2025 | 21/02/2025
TO-25-220 kV B2 @ LOU-08 | BUSBAR SECTION - LOUTH 220-LOUTH 220-220B2 | 9 | 7 | 7 | Scheduled | 24/02/2025 | 04/03/2025
TO-25-LOU-T2104-04 | TRANSFORMER - LOUTH 220-LOUTH 110-T2104 | 9 | 7 | 7 | Scheduled | 24/02/2025 | 04/03/2025
TO-25-110 kV B2 @ DEN-01 | BUSBAR SECTION - DEENES 110-DEENES 110-110B2 | 2 | 2 | 2 | Scheduled | 26/02/2025 | 27/02/2025
TO-25-DEN-110K2-02 | COUPLER/SECTIONALISING CB - DEENES 110-DEENES 110-110K2 | 2 | 2 | 2 | Scheduled | 26/02/2025 | 27/02/2025
TO-25-DEY-T134-01 | GENERATOR TRANSFORMER - DERRYCARNEY 110-DERRYCARNEY 33-T134 | 1 | 1 | 1 | Scheduled | 27/02/2025 | 27/02/2025
TO-25-ATH-110SA1-2CB-02 | COUPLER/SECTIONALISING CB - ATHLONE 110-ATHLONE 110-110SA1-2CB | 12 | 10 |  | Scheduled | 03/03/2025 | 14/03/2025
TO-25-ATH-110SA1-2CB-06 | COUPLER/SECTIONALISING CB - ATHLONE 110-ATHLONE 110-110SA1-2CB | 12 | 10 |  | Proposed | 03/03/2025 | 14/03/2025
TO-25-ATH-SH-1-02 | 110kV FEEDER - ATHLONE 110-SHANNONBRIDGE 110-1 | 12 | 10 | 10 | Scheduled | 03/03/2025 | 14/03/2025
TO-25-ATH-SH-1-06 | 110kV FEEDER - ATHLONE 110-SHANNONBRIDGE 110-1 | 12 | 10 | 10 | Proposed | 03/03/2025 | 14/03/2025
TO-25-ATH-T142-02 | DISTRIBUTION TRANSFORMER - ATHLONE 110-ATHLONE 38-T142 | 12 | 10 |  | Reference | 03/03/2025 | 14/03/2025
TO-25-ATH-T142-06 | DISTRIBUTION TRANSFORMER - ATHLONE 110-ATHLONE 38-T142 | 12 | 10 | 10 | Reference (Proposed) | 03/03/2025 | 14/03/2025
TO-25-RRU-SKL-1-03 | 110kV FEEDER - RATRUSSAN 110-SHANKILL 110-1 | 12 | 10 | 10 | Proposed | 03/03/2025 | 14/03/2025
TO-25-220 kV A2 @ LOU-01 | BUSBAR SECTION - LOUTH 220-LOUTH 220-220A2 | 17 | 12 | 12 | Proposed | 05/03/2025 | 21/03/2025
TO-25-220 kV B2 @ LOU-01 | BUSBAR SECTION - LOUTH 220-LOUTH 220-220B2 | 17 | 12 | 12 | Proposed | 05/03/2025 | 21/03/2025
TO-25-LOU-AT3-01 | TRANSFORMER - LOUTH 220-LOUTH 275-AT3 | 12 | 9 | 9 | Proposed | 10/03/2025 | 21/03/2025
TO-25-FLA-SLB-1-02 | 110kV FEEDER - FLAGFORD 110-SLIABH BAWN 110-1 | Unknown | Unknown | 40 | Planned | March | May
TO-25-FLA-SLB-1-04 | 110kV FEEDER - FLAGFORD 110-SLIABH BAWN 110-1 | 59 | 40 | 40 | Proposed | 18/03/2025 | 15/05/2025
TO-25-220 kV A1 @ LOU-01 | BUSBAR SECTION - LOUTH 220-LOUTH 220-220A1 | Unknown | Unknown | 20 | Planned | March | April
TO-25-220 kV B1 @ LOU-01 | BUSBAR SECTION - LOUTH 220-LOUTH 220-220B1 | Unknown | Unknown | 20 | Planned | March | April
TO-25-DRY-GOR-1-04 | 110kV FEEDER - DRYBRIDGE 110-GORMAN 110-1 | 3 | 3 |  | Scheduled | 19/03/2025 | 21/03/2025
TO-25-DRY-110SA1-03 | SECTIONALISING DISCONNECT - DRYBRIDGE 110-DRYBRIDGE 110-110SA1 | 5 | 5 | 5 | Scheduled | 24/03/2025 | 28/03/2025
TO-25-DRY-110SA2-03 | SECTIONALISING DISCONNECT - DRYBRIDGE 110-DRYBRIDGE 110-110SA2 | 5 | 5 |  | Scheduled | 24/03/2025 | 28/03/2025
TO-25-DRY-LOU-1-02 | 110kV FEEDER - DRYBRIDGE 110-LOUTH 110-1 | 5 | 5 |  | Scheduled | 24/03/2025 | 28/03/2025
TO-25-DRY-OBE-1-01 | 110kV FEEDER - DRYBRIDGE 110-OLDBRIDGE 110-1 | 74 | 50 |  | Proposed | 24/03/2025 | 05/06/2025
TO-25-DRY-OBE-1-02 | 110kV FEEDER - DRYBRIDGE 110-OLDBRIDGE 110-1 | 74 | 50 | 50 | Scheduled | 24/03/2025 | 05/06/2025
TO-25-DRY-OBE-1-03 | 110kV FEEDER - DRYBRIDGE 110-OLDBRIDGE 110-1 | 74 | 50 | 50 | Proposed | 24/03/2025 | 05/06/2025
TO-25-DRY-T141-01 | DISTRIBUTION TRANSFORMER - DRYBRIDGE 110-DRYBRIDGE 38-T141 | 5 | 5 | 5 | Reference | 24/03/2025 | 28/03/2025
TO-25-GOR-T122-01 | GENERATOR TRANSFORMER - GORMAN 110-GORMAN 20-T122 | 1 | 1 | 1 | Proposed | 02/04/2025 | 02/04/2025
TO-25-NAV-T142-01 | DISTRIBUTION TRANSFORMER - NAVAN 110-NAVAN 38-T142 | Unknown | Unknown | 40 | Reference (Planned) | April | May
TO-25-TEN-T132-02 | GENERATOR TRANSFORMER - TIMAHOE 110-TIMAHOE 33-T132 | 1 | 1 | 1 | Proposed | 03/04/2025 | 03/04/2025
TO-25-DEY-T132-01 | GENERATOR TRANSFORMER - DERRYCARNEY 110-DERRYCARNEY 33-T132 | Unknown | Unknown | 5 | Planned | April | April
TO-25-220 kV A2 @ SH-03 | BUSBAR SECTION - SHANNONBRIDGE 220-SHANNONBRIDGE 220-220A2 | Unknown | Unknown | 2 | Planned | April | April
TO-25-220 kV B2 @ SH-03 | BUSBAR SECTION - SHANNONBRIDGE 220-SHANNONBRIDGE 220-220B2 | Unknown | Unknown | 2 | Planned | April | April
TO-25-SH-220K1-2-01 | COUPLER/SECTIONALISING CB - SHANNONBRIDGE 220-SHANNONBRIDGE 220-220K1-2 | Unknown | Unknown |  | Planned | April | April
TO-25-KLN-SH-1-01 | 220kV FEEDER - KILLONAN 220-SHANNONBRIDGE 220-1 | Unknown | Unknown |  | Planned | April | April
TO-25-RRU-T122-01 | GENERATOR TRANSFORMER - RATRUSSAN 110-RATRUSSAN 20-T122 | 5 | 4 | 4 | Proposed | 14/04/2025 | 18/04/2025
TO-25-RRU-T122-02 | GENERATOR TRANSFORMER - RATRUSSAN 110-RATRUSSAN 20-T122 | 5 | 4 | 4 | Proposed | 14/04/2025 | 18/04/2025
TO-25-220 kV A1 @ SH-01 | BUSBAR SECTION - SHANNONBRIDGE 220-SHANNONBRIDGE 220-220A1 | Unknown | Unknown |  | Planned | April | April
TO-25-220 kV A2 @ SH-02 | BUSBAR SECTION - SHANNONBRIDGE 220-SHANNONBRIDGE 220-220A2 | Unknown | Unknown |  | Planned | April | April
TO-25-220 kV B1 @ SH-01 | BUSBAR SECTION - SHANNONBRIDGE 220-SHANNONBRIDGE 220-220B1 | Unknown | Unknown |  | Planned | April | April
TO-25-220 kV B2 @ SH-02 | BUSBAR SECTION - SHANNONBRIDGE 220-SHANNONBRIDGE 220-220B2 | Unknown | Unknown |  | Planned | April | April
TO-25-MAY-SH-1-01 | 220kV FEEDER - MAYNOOTH 220-SHANNONBRIDGE 220-1 | Unknown | Unknown |  | Planned | April | September
TO-25-GOR-LOU-1-02 | 220kV FEEDER - GORMAN 220-LOUTH 220-1 | Unknown | Unknown | 10 | Planned | April | May
TO-25-LIS-T131-01 | GENERATOR TRANSFORMER - LISDRUM 110-LISDRUM 33-T131 | Unknown | Unknown | 8 | Planned | May | May
TO-25-GOR-MTH-1-01 | 110kV FEEDER - GORMAN 110-MEATH HILL 110-1 | Unknown | Unknown | 15 | Planned | May | May
TO-25-MLC-T121-01 | GENERATOR TRANSFORMER - MOUNTLUCAS 110-MOUNTLUCAS 20-T121 | Unknown | Unknown | 1 | Planned | May | May
TO-25-MLC-T121-02 | GENERATOR TRANSFORMER - MOUNTLUCAS 110-MOUNTLUCAS 20-T121 | Unknown | Unknown | 2 | Planned | May | May
TO-25-ATH-110SA1-2CB-03 | COUPLER/SECTIONALISING CB - ATHLONE 110-ATHLONE 110-110SA1-2CB | Unknown | Unknown |  | Planned | May | June
TO-25-ATH-SH-1-03 | 110kV FEEDER - ATHLONE 110-SHANNONBRIDGE 110-1 | Unknown | Unknown |  | Planned | May | June
TO-25-ATH-T142-03 | DISTRIBUTION TRANSFORMER - ATHLONE 110-ATHLONE 38-T142 | Unknown | Unknown |  | Reference (Planned) | May | June
TO-25-LSA-T131-01 | GENERATOR TRANSFORMER - LISLEA 110-LISLEA 33-T131 | Unknown | Unknown | 3 | Planned | May | May
TO-25-RRU-T121-01 | GENERATOR TRANSFORMER - RATRUSSAN 110-RATRUSSAN 20-T121 | Unknown | Unknown | 3 | Planned | June | June
TO-25-ATH-SH-1-04 | 110kV FEEDER - ATHLONE 110-SHANNONBRIDGE 110-1 | Unknown | Unknown | 10 | Planned | June | June
TO-25-AGL-DYN-1-01 | 110kV FEEDER - AGANNYGAL 110-DERRYBRIEN 110-1 | Unknown | Unknown | 3 | Planned | June | June
TO-25-DER-KIN-1-03 | 110kV FEEDER - DERRYIRON 110-KINNEGAD 110-1 | Unknown | Unknown | 15 | Planned | June | June
TO-25-DER-T1/T2-02 | GENERATOR TRANSFORMER - DERRYIRON 110-RHODE 110-T1/T2 | Unknown | Unknown | 15 | Planned | June | June
TO-25-GOR-MTH-1-02 | 110kV FEEDER - GORMAN 110-MEATH HILL 110-1 | Unknown | Unknown | 15 | Planned | June | June
TO-25-MTH-110SA1-02 | SECTIONALISING DISCONNECT - MEATH HILL 110-MEATH HILL 110-110SA1 | Unknown | Unknown | 15 | Planned | June | June
TO-25-MTH-110SA2-01 | SECTIONALISING DISCONNECT - MEATH HILL 110-MEATH HILL 110-110SA2 | Unknown | Unknown | 15 | Planned | June | June
TO-25-MTH-T142-01 | DISTRIBUTION TRANSFORMER - MEATH HILL 110-MEATH HILL 38-T142 | Unknown | Unknown | 15 | Reference (Planned) | June | June
TO-25-OBE-PLA-1-01 | 110kV FEEDER - OLDBRIDGE 110-PLATIN 110-1 | Unknown | Unknown |  | Planned | June | August
TO-25-SLB-T132-01 | GENERATOR TRANSFORMER - SLIABH BAWN 110-SLIABH BAWN 33-T132 | Unknown | Unknown | 1 | Planned | June | June
TO-25-SLB-T132-02 | GENERATOR TRANSFORMER - SLIABH BAWN 110-SLIABH BAWN 33-T132 | Unknown | Unknown | 2 | Planned | June | June
TO-25-ATH-LA-1-02 | 110kV FEEDER - ATHLONE 110-LANESBORO 110-1 | Unknown | Unknown |  | Planned | June | July
TO-25-220 kV A1 @ LOU-02 | BUSBAR SECTION - LOUTH 220-LOUTH 220-220A1 | Unknown | Unknown | 20 | Planned | June | July
TO-25-220 kV B1 @ LOU-02 | BUSBAR SECTION - LOUTH 220-LOUTH 220-220B1 | Unknown | Unknown | 20 | Planned | June | July
TO-25-LOU-AT3-02 | TRANSFORMER - LOUTH 220-LOUTH 275-AT3 | Unknown | Unknown |  | Planned | June | October
TO-25-LOU-MTH-1-01 | 110kV FEEDER - LOUTH 110-MEATH HILL 110-1 | Unknown | Unknown | 15 | Planned | June | July
TO-25-MTH-110SA1-01 | SECTIONALISING DISCONNECT - MEATH HILL 110-MEATH HILL 110-110SA1 | Unknown | Unknown | 15 | Planned | June | July
TO-25-MTH-110SA2-02 | SECTIONALISING DISCONNECT - MEATH HILL 110-MEATH HILL 110-110SA2 | Unknown | Unknown | 15 | Planned | June | July
TO-25-MTH-T141-01 | DISTRIBUTION TRANSFORMER - MEATH HILL 110-MEATH HILL 38-T141 | Unknown | Unknown | 15 | Reference (Planned) | June | July
TO-25-220 kV A1 @ LOU-06 | BUSBAR SECTION - LOUTH 220-LOUTH 220-220A1 | Unknown | Unknown | 9 | Planned | July | July
TO-25-220 kV B1 @ LOU-06 | BUSBAR SECTION - LOUTH 220-LOUTH 220-220B1 | Unknown | Unknown | 29 | Planned | July | August
TO-25-ATH-T142-04 | DISTRIBUTION TRANSFORMER - ATHLONE 110-ATHLONE 38-T142 | Unknown | Unknown |  | Reference (Planned) | July | July
TO-25-KDN-T131-01 | GENERATOR TRANSFORMER - KNOCKDRIN 110-KNOCKDRIN 33-T131 | Unknown | Unknown | 15 | Planned | July | July
TO-25-KDN,T-KDN-1-01 | 110kV FEEDER - KNOCKDRIN tee-KNOCKDRIN 110-1 | Unknown | Unknown | 15 | Planned | July | July
TO-25-KDN,T-TSB-1-01 | 110kV FEEDER - KNOCKDRIN tee-THORNSBERRY 110-1 | Unknown | Unknown | 15 | Planned | July | July
TO-25-KDN,T-TEN-1-01 | 110kV FEEDER - KNOCKDRIN tee-TIMAHOE 110-1 | Unknown | Unknown | 15 | Planned | July | July
TO-25-SH-T2102-01 | TRANSFORMER - SHANNONBRIDGE 220-SHANNONBRIDGE 110-T2102 | Unknown | Unknown | 55 | Planned | July | September
TO-25-TSB-110SA1-01 | SECTIONALISING DISCONNECT - THORNSBERRY 110-THORNSBERRY 110-110SA1 | Unknown | Unknown | 5 | Planned | July | July
TO-25-TSB-110SA2-01 | SECTIONALISING DISCONNECT - THORNSBERRY 110-THORNSBERRY 110-110SA2 | Unknown | Unknown | 5 | Planned | July | July
TO-25-TSB-T142-01 | DISTRIBUTION TRANSFORMER - THORNSBERRY 110-THORNSBERRY 38-T142 | Unknown | Unknown | 5 | Reference (Planned) | July | July
TO-25-110 kV A2 @ TEN-01 | BUSBAR SECTION - TIMAHOE 110-TIMAHOE 110-110A2 | Unknown | Unknown | 5 | Planned | July | July
TO-25-110 kV B2 @ TEN-01 | BUSBAR SECTION - TIMAHOE 110-TIMAHOE 110-110B2 | Unknown | Unknown | 5 | Planned | July | July
TO-25-TEN-110K2-01 | COUPLER/SECTIONALISING CB - TIMAHOE 110-TIMAHOE 110-110K2 | Unknown | Unknown | 5 | Planned | July | July
TO-25-ATH-T141-02 | DISTRIBUTION TRANSFORMER - ATHLONE 110-ATHLONE 38-T141 | Unknown | Unknown |  | Reference (Planned) | July | August
TO-25-GOR-T2101-01 | TRANSFORMER - GORMAN 220-GORMAN 110-T2101 | Unknown | Unknown | 40 | Planned | July | September
TO-25-DER-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - DERRYIRON 110-DERRYIRON 110-110SA1-2CB | Unknown | Unknown | 4 | Planned | July | July
TO-25-DER-KIN-1-04 | 110kV FEEDER - DERRYIRON 110-KINNEGAD 110-1 | Unknown | Unknown | 4 | Planned | July | July
TO-25-DER-T1/T2-03 | GENERATOR TRANSFORMER - DERRYIRON 110-RHODE 110-T1/T2 | Unknown | Unknown | 4 | Planned | July | July
TO-25-KIN-MUL-1-01 | 110kV FEEDER - KINNEGAD 110-MULLINGAR 110-1 | Unknown | Unknown | 70 | Planned | July | November
TO-25-ATH-CAP3-02 | CAPACITOR/SVC/REACTOR - ATHLONE 110-ATHLONE 110-CAP3 | Unknown | Unknown |  | Planned | August | August
TO-25-220 kV A1 @ LOU-07 | BUSBAR SECTION - LOUTH 220-LOUTH 220-220A1 | Unknown | Unknown | 9 | Planned | August | August
TO-25-220 kV B1 @ LOU-07 | BUSBAR SECTION - LOUTH 220-LOUTH 220-220B1 | Unknown | Unknown | 9 | Planned | August | August
TO-25-MLN-T124-01 | TSO CUSTOMER TRANSFORMER - MULLAGHARLIN 110-MULLAGHARLIN 20-T124 | Unknown | Unknown | 2 | Planned | August | August
TO-25-MLN-T123-01 | TSO CUSTOMER TRANSFORMER - MULLAGHARLIN 110-MULLAGHARLIN 20-T123 | Unknown | Unknown | 2 | Planned | August | August
TO-25-DFR-T122-03 | DISTRIBUTION TRANSFORMER - DUNFIRTH 110-DUNFIRTH 20-T122 | Unknown | Unknown | 4 | Reference (Planned) | August | August
TO-25-DFR,T-DFR-1-03 | 110kV FEEDER - DUNFIRTH tee-DUNFIRTH 110-1 | Unknown | Unknown | 4 | Planned | August | August
TO-25-DFR,T-RNW-1-02 | 110kV FEEDER - DUNFIRTH tee-RINAWADE 110-1 | Unknown | Unknown | 7 | Planned | August | August
TO-25-110 kV A2 @ LOU-01 | BUSBAR SECTION - LOUTH 110-LOUTH 110-110A2 | Unknown | Unknown | 10 | Planned | August | August
TO-25-220 kV A1 @ SH-02 | BUSBAR SECTION - SHANNONBRIDGE 220-SHANNONBRIDGE 220-220A1 | Unknown | Unknown |  | Planned | August | August
TO-25-220 kV B1 @ SH-02 | BUSBAR SECTION - SHANNONBRIDGE 220-SHANNONBRIDGE 220-220B1 | Unknown | Unknown |  | Planned | August | August
TO-25-ATH-M/CAP1-02 | CAPACITOR/SVC/REACTOR - ATHLONE 110-ATHLONE 110-M/CAP1 | Unknown | Unknown |  | Planned | August | September
TO-25-110 kV B2 @ LOU-01 | BUSBAR SECTION - LOUTH 110-LOUTH 110-110B2 | Unknown | Unknown |  | Planned | August | September
TO-25-LOU-RRU-1-01 | 110kV FEEDER - LOUTH 110-RATRUSSAN 110-1 | Unknown | Unknown | 15 | Planned | September | September
TO-25-LOU-RRU-1-02 | 110kV FEEDER - LOUTH 110-RATRUSSAN 110-1 | Unknown | Unknown |  | Planned | September | October
TO-25-ATH-110SA1-2CB-05 | COUPLER/SECTIONALISING CB - ATHLONE 110-ATHLONE 110-110SA1-2CB | Unknown | Unknown |  | Planned | September | September
TO-25-ATH-CAP3-03 | CAPACITOR/SVC/REACTOR - ATHLONE 110-ATHLONE 110-CAP3 | Unknown | Unknown |  | Planned | September | September
TO-25-ATH-LA-1-03 | 110kV FEEDER - ATHLONE 110-LANESBORO 110-1 | Unknown | Unknown |  | Planned | September | September
TO-25-ATH-M/CAP1-03 | CAPACITOR/SVC/REACTOR - ATHLONE 110-ATHLONE 110-M/CAP1 | Unknown | Unknown |  | Planned | September | September
TO-25-ATH-T141-03 | DISTRIBUTION TRANSFORMER - ATHLONE 110-ATHLONE 38-T141 | Unknown | Unknown |  | Reference (Planned) | September | September
TO-25-220 kV A1 @ LOU-03 | BUSBAR SECTION - LOUTH 220-LOUTH 220-220A1 | Unknown | Unknown | 4 | Planned | September | September
TO-25-220 kV B1 @ LOU-03 | BUSBAR SECTION - LOUTH 220-LOUTH 220-220B1 | Unknown | Unknown | 4 | Planned | September | September
TO-25-LOU-WOO-1-01 | 220kV FEEDER - LOUTH 220-WOODLAND 220-1 | Unknown | Unknown | 25 | Planned | September | October
TO-25-LOU-WOO-1-02 | 220kV FEEDER - LOUTH 220-WOODLAND 220-1 | Unknown | Unknown | 25 | Planned | September | October
TO-25-110 kV A2 @ LOU-02 | BUSBAR SECTION - LOUTH 110-LOUTH 110-110A2 | Unknown | Unknown | 18 | Planned | September | October
TO-25-TEN-T132-01 | GENERATOR TRANSFORMER - TIMAHOE 110-TIMAHOE 33-T132 | Unknown | Unknown | 1 | Planned | September | September
TO-25-DER-110SA1-2CB-02 | COUPLER/SECTIONALISING CB - DERRYIRON 110-DERRYIRON 110-110SA1-2CB | Unknown | Unknown | 7 | Planned | September | September
TO-25-DER-KIN-1-01 | 110kV FEEDER - DERRYIRON 110-KINNEGAD 110-1 | Unknown | Unknown | 7 | Planned | September | September
TO-25-220 kV A1 @ LOU-04 | BUSBAR SECTION - LOUTH 220-LOUTH 220-220A1 | Unknown | Unknown |  | Planned | September | September
TO-25-220 kV B1 @ LOU-04 | BUSBAR SECTION - LOUTH 220-LOUTH 220-220B1 | Unknown | Unknown |  | Planned | September | September
TO-25-LOU-220K1-2-02 | COUPLER/SECTIONALISING CB - LOUTH 220-LOUTH 220-220K1-2 | Unknown | Unknown |  | Planned | September | September
TO-25-ATH-110SA1-2CB-04 | COUPLER/SECTIONALISING CB - ATHLONE 110-ATHLONE 110-110SA1-2CB | Unknown | Unknown |  | Planned | September | October
TO-25-ATH-SH-1-05 | 110kV FEEDER - ATHLONE 110-SHANNONBRIDGE 110-1 | Unknown | Unknown |  | Planned | September | October
TO-25-ATH-T142-05 | DISTRIBUTION TRANSFORMER - ATHLONE 110-ATHLONE 38-T142 | Unknown | Unknown |  | Reference (Planned) | September | October
TO-25-LOU-220K1-2-01 | COUPLER/SECTIONALISING CB - LOUTH 220-LOUTH 220-220K1-2 | Unknown | Unknown | 5 | Planned | September | October
TO-25-LOU-AT2-01 | TRANSFORMER - LOUTH 220-LOUTH 275-AT2 | Unknown | Unknown | 5 | Planned | September | October
TO-25-LOU-T2101-01 | TRANSFORMER - LOUTH 220-LOUTH 110-T2101 | Unknown | Unknown | 5 | Planned | September | October
TO-25-LOU-T2103-01 | TRANSFORMER - LOUTH 220-LOUTH 110-T2103 | Unknown | Unknown | 5 | Planned | September | October
TO-25-LOU-TAN-2-01 | 275kV FEEDER - LOUTH 275-TANDRAGEE 275-2 | Unknown | Unknown | 5 | Planned | September | October
TO-25-DER-110SA1-2CB-03 | COUPLER/SECTIONALISING CB - DERRYIRON 110-DERRYIRON 110-110SA1-2CB | Unknown | Unknown | 7 | Planned | October | October
TO-25-DER-T1/T2-01 | GENERATOR TRANSFORMER - DERRYIRON 110-RHODE 110-T1/T2 | Unknown | Unknown | 7 | Planned | October | October
TO-25-DER-TSB-1-01 | 110kV FEEDER - DERRYIRON 110-THORNSBERRY 110-1 | Unknown | Unknown | 7 | Planned | October | October
TO-25-DER-TEN-1-01 | 110kV FEEDER - DERRYIRON 110-TIMAHOE 110-1 | Unknown | Unknown | 7 | Planned | October | October
TO-25-110 kV B2 @ LOU-02 | BUSBAR SECTION - LOUTH 110-LOUTH 110-110B2 | Unknown | Unknown |  | Planned | October | November
TO-25-220 kV A1 @ LOU-05 | BUSBAR SECTION - LOUTH 220-LOUTH 220-220A1 | Unknown | Unknown | 2 | Planned | October | October
TO-25-220 kV B1 @ LOU-05 | BUSBAR SECTION - LOUTH 220-LOUTH 220-220B1 | Unknown | Unknown | 2 | Planned | October | October
TO-25-DRY-GOR-1-01 | 110kV FEEDER - DRYBRIDGE 110-GORMAN 110-1 | Unknown | Unknown | 40 | Planned | October | December
TO-25-DRY-GOR-1-05 | 110kV FEEDER - DRYBRIDGE 110-GORMAN 110-1 | Unknown | Unknown | 40 | Planned | October | December
TO-25-GOR-LOU-1-01 | 220kV FEEDER - GORMAN 220-LOUTH 220-1 | Unknown | Unknown |  | Planned | October | October
TO-25-220 kV A2 @ LOU-05 | BUSBAR SECTION - LOUTH 220-LOUTH 220-220A2 | Unknown | Unknown |  | Planned | October | October
TO-25-220 kV B2 @ LOU-05 | BUSBAR SECTION - LOUTH 220-LOUTH 220-220B2 | Unknown | Unknown | 2 | Planned | October | October
TO-25-LA-MUL-1-02 | 110kV FEEDER - LANESBORO 110-MULLINGAR 110-1 | Unknown | Unknown | 2 | Planned | October | October
TO-25-MUL-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - MULLINGAR 110-MULLINGAR 110-110SA1-2CB | Unknown | Unknown | 2 | Planned | October | October
TO-25-MUL-CAP1-01 | CAPACITOR/SVC/REACTOR - MULLINGAR 110-MULLINGAR 110-CAP1 | Unknown | Unknown | 2 | Planned | October | October
TO-25-MUL-T101-01 | DISTRIBUTION TRANSFORMER - MULLINGAR 110-MULLINGAR 10-T101 | Unknown | Unknown | 2 | Reference (Planned) | October | October
TO-25-MUL-T141-01 | DISTRIBUTION TRANSFORMER - MULLINGAR 110-MULLINGAR 38-T141 | Unknown | Unknown | 2 | Reference (Planned) | October | October
TO-25-DER-KIN-1-02 | 110kV FEEDER - DERRYIRON 110-KINNEGAD 110-1 | Unknown | Unknown |  | Planned | November | November
TO-25-KIN-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - KINNEGAD 110-KINNEGAD 110-110SA1-2CB | Unknown | Unknown |  | Planned | November | November
TO-25-KIN-T101-01 | TSO CUSTOMER TRANSFORMER - KINNEGAD 110-KINNEGAD 10-T101 | Unknown | Unknown |  | Planned | November | November
TO-25-110 kV A2 @ LOU-03 | BUSBAR SECTION - LOUTH 110-LOUTH 110-110A2 | Unknown | Unknown | 3 | Planned | November | November
TO-25-110 kV B2 @ LOU-03 | BUSBAR SECTION - LOUTH 110-LOUTH 110-110B2 | Unknown | Unknown |  | Planned | November | November
TO-25-110 kV A1 @ LOU-02 | BUSBAR SECTION - LOUTH 110-LOUTH 110-110A1 | Unknown | Unknown |  | Planned | November | November
TO-25-110 kV B1 @ LOU-02 | BUSBAR SECTION - LOUTH 110-LOUTH 110-110B1 | Unknown | Unknown |  | Planned | November | November
TO-25-LOU-110K1-2-02 | COUPLER/SECTIONALISING CB - LOUTH 110-LOUTH 110-110K1-2 | Unknown | Unknown |  | Planned | November | November
TO-25-LOU-T2103-03 | TRANSFORMER - LOUTH 220-LOUTH 110-T2103 | Unknown | Unknown |  | Planned | November | November
TO-25-DDK-LOU-1-01 | 110kV FEEDER - DUNDALK 110-LOUTH 110-1 | Unknown | Unknown |  | Planned | December | December
TO-25-LIS-LOU-1-01 | 110kV FEEDER - LISDRUM 110-LOUTH 110-1 | Unknown | Unknown |  | Planned | December | December
TO-25-110 kV A2 @ LOU-04 | BUSBAR SECTION - LOUTH 110-LOUTH 110-110A2 | Unknown | Unknown | 2 | Planned | December | December
TO-25-LOU-T2104-02 | TRANSFORMER - LOUTH 220-LOUTH 110-T2104 | Unknown | Unknown |  | Planned | December | December
TO-25-110 kV B2 @ LOU-04 | BUSBAR SECTION - LOUTH 110-LOUTH 110-110B2 | Unknown | Unknown |  | Planned | December | December
TO-25-LOU-T2104-01 | TRANSFORMER - LOUTH 220-LOUTH 110-T2104 | Unknown | Unknown |  | Planned | December | December

## GEN_Dublin
Outage ID | Feeder ID | Calendar Day Duration | Working Day Duration | Work Days | Outage Status | Start | Finish
TO-25-DND-T121-01 | TSO CUSTOMER TRANSFORMER - DARNDALE 110-DARNDALE 20-T121 | 474 | 334 | 334 | Scheduled | 12/02/2024 | 30/05/2025
TO-25-BAL-DRY-1-03 | 110kV FEEDER - BALTRASNA 110-DRYBRIDGE 110-1 | 283 | 201 | 201 | Scheduled | 13/05/2024 | 19/02/2025
TO-25-110 kV B2/B4 @ CDU-01 | BUSBAR SECTION - CORDUFF 110-CORDUFF 110-110B2-B4 | 8 | 6 | 6 | Scheduled | 06/01/2025 | 13/01/2025
TO-25-CDU-110SB2-4-01 | SECTIONALISING DISCONNECT - CORDUFF 110-CORDUFF 110-110SB2-4 | 8 | 6 | 6 | Scheduled | 06/01/2025 | 13/01/2025
TO-25-FIN-220K1-04 | COUPLER/SECTIONALISING CB - FINGLAS 220-FINGLAS 220-220K1 | 2 | 2 | 2 | Scheduled | 08/01/2025 | 09/01/2025
TO-25-FIN-220K2-05 | COUPLER/SECTIONALISING CB - FINGLAS 220-FINGLAS 220-220K2 | 2 | 2 | 2 | Scheduled | 08/01/2025 | 09/01/2025
TO-25-FIN-220SA1-2CB-08 | COUPLER/SECTIONALISING CB - FINGLAS 220-FINGLAS 220-220SA1-2CB | 2 | 2 | 2 | Scheduled | 08/01/2025 | 09/01/2025
TO-25-CDU-T2102-02 | TRANSFORMER - CORDUFF 220-CORDUFF 110-T2102 | 1 | 1 | 1 | Scheduled | 13/01/2025 | 13/01/2025
TO-25-220 kV B1 @ CBT-02 | BUSBAR SECTION - CASTLEBAGOT 220-CASTLEBAGOT 220-220B1 | 9 | 7 | 7 | Scheduled | 14/01/2025 | 22/01/2025
TO-25-220 kV B2 @ CBT-01 | BUSBAR SECTION - CASTLEBAGOT 220-CASTLEBAGOT 220-220B2 | 9 | 7 | 7 | Scheduled | 14/01/2025 | 22/01/2025
TO-25-CBT-220K1-04 | COUPLER/SECTIONALISING CB - CASTLEBAGOT 220-CASTLEBAGOT 220-220K1 | 9 | 7 | 7 | Scheduled | 14/01/2025 | 22/01/2025
TO-25-CBT-220K2-02 | COUPLER/SECTIONALISING CB - CASTLEBAGOT 220-CASTLEBAGOT 220-220K2 | 9 | 7 | 7 | Scheduled | 14/01/2025 | 22/01/2025
TO-25-CBT-220SB1-2CB-01 | COUPLER/SECTIONALISING CB - CASTLEBAGOT 220-CASTLEBAGOT 220-220SB1-2CB | 9 | 7 | 7 | Scheduled | 14/01/2025 | 22/01/2025
TO-25-WOO-220K1-2-05 | COUPLER/SECTIONALISING CB - WOODLAND 220-WOODLAND 220-220K1-2 | 2 | 2 | 2 | Scheduled | 15/01/2025 | 16/01/2025
TO-25-BNK-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - BARNAKYLE 110-BARNAKYLE 110-110SA1-2CB | 67 | 45 | 45 | Scheduled | 17/01/2025 | 24/03/2025
TO-25-BNK-CBT-2-01 | 110kV FEEDER - BARNAKYLE 110-CASTLEBAGOT 110-2 | 67 | 45 | 45 | Scheduled | 17/01/2025 | 24/03/2025
TO-25-BNK-T122-01 | TSO CUSTOMER TRANSFORMER - BARNAKYLE 110-BARNAKYLE 20-T122 | 67 | 45 | 45 | Scheduled | 17/01/2025 | 24/03/2025
TO-25-DSN-MAY-2-03 | 220kV FEEDER - DUNSTOWN 220-MAYNOOTH 220-2 | 11 | 9 |  | Scheduled | 20/01/2025 | 30/01/2025
TO-25-INC-PB-1-01 | 220kV FEEDER - INCHICORE 220-POOLBEG 220-1 | 43 | 30 | 30 | Scheduled | 27/01/2025 | 10/03/2025
TO-25-220 kV A2 @ FIN-05 | BUSBAR SECTION - FINGLAS 220-FINGLAS 220-220A2 | 11 | 9 | 9 | Scheduled | 04/02/2025 | 14/02/2025
TO-25-FIN-220K2-08 | COUPLER/SECTIONALISING CB - FINGLAS 220-FINGLAS 220-220K2 | 11 | 9 | 9 | Scheduled | 04/02/2025 | 14/02/2025
TO-25-FIN-220SA1-2CB-09 | COUPLER/SECTIONALISING CB - FINGLAS 220-FINGLAS 220-220SA1-2CB | 11 | 9 | 9 | Scheduled | 04/02/2025 | 14/02/2025
TO-25-FIN-SHL-1-01 | 220kV FEEDER - FINGLAS 220-SHELLYBANKS 220-1 | 25 | 19 | 19 | Scheduled | 04/02/2025 | 28/02/2025
TO-25-SHL-T2016-01 | GENERATOR TRANSFORMER - SHELLYBANKS 220-SHELLYBANKS G6-T2016 | 1 | 1 | 1 | Scheduled | 04/02/2025 | 04/02/2025
TO-25-110 kV A2 @ CDU-02 | BUSBAR SECTION - CORDUFF 110-CORDUFF 110-110A2 | 5 | 5 | 5 | Scheduled | 10/02/2025 | 14/02/2025
TO-25-110 kV A4 @ CDU-02 | BUSBAR SECTION - CORDUFF 110-CORDUFF 110-110A4 | 5 | 5 | 5 | Scheduled | 10/02/2025 | 14/02/2025
TO-25-110 kV B2 @ CDU-02 | BUSBAR SECTION - CORDUFF 110-CORDUFF 110-110B2 | 5 | 5 | 5 | Scheduled | 10/02/2025 | 14/02/2025
TO-25-110 kV B4 @ CDU-02 | BUSBAR SECTION - CORDUFF 110-CORDUFF 110-110B4 | 5 | 5 | 5 | Scheduled | 10/02/2025 | 14/02/2025
TO-25-AUN-CBT-1-01 | 110kV FEEDER - AUNGIERSTOWN 110-CASTLEBAGOT 110-1 | 2 | 2 | 2 | Scheduled | 11/02/2025 | 12/02/2025
TO-25-AUN-T121-01 | TSO CUSTOMER TRANSFORMER - AUNGIERSTOWN 110-AUNGIERSTOWN 20-T121 | 2 | 2 | 2 | Scheduled | 13/02/2025 | 14/02/2025
TO-25-AUN-T123-01 | TSO CUSTOMER TRANSFORMER - AUNGIERSTOWN 110-AUNGIERSTOWN 20-T123 | 2 | 2 | 2 | Scheduled | 19/02/2025 | 20/02/2025
TO-25-AUN-KSG-1-01 | 110kV FEEDER - AUNGIERSTOWN 110-KISHOGE 110-1 | 4 | 2 | 2 | Scheduled | 21/02/2025 | 24/02/2025
TO-25-BAL-CDU-1-02 | 110kV FEEDER - BALTRASNA 110-CORDUFF 110-1 | 6 | 5 |  | Scheduled | 24/02/2025 | 01/03/2025
TO-25-110 kV A4 @ CDU-01 | BUSBAR SECTION - CORDUFF 110-CORDUFF 110-110A4 | 6 | 5 | 5 | Scheduled | 24/02/2025 | 01/03/2025
TO-25-110 kV B4 @ CDU-01 | BUSBAR SECTION - CORDUFF 110-CORDUFF 110-110B4 | 6 | 5 | 5 | Scheduled | 24/02/2025 | 01/03/2025
TO-25-CDU-110SA2-4CB-01 | COUPLER/SECTIONALISING CB - CORDUFF 110-CORDUFF 110-110SA2-4CB | 6 | 5 | 5 | Scheduled | 24/02/2025 | 01/03/2025
TO-25-CDU-110SB2-4CB-01 | COUPLER/SECTIONALISING CB - CORDUFF 110-CORDUFF 110-110SB2-4CB | 6 | 5 | 5 | Scheduled | 24/02/2025 | 01/03/2025
TO-25-FIN GIS-T2101-01 | TRANSFORMER - FINGLAS 220-FINGLAS GIS 110-T2101 | 3 | 3 | 3 | Scheduled | 25/02/2025 | 27/02/2025
TO-25-BAG-T101-01 | TSO CUSTOMER TRANSFORMER - BARNAGEERAGH 110-BARNAGEERAGH 11-T101 | 5 | 5 | 5 | Proposed | 03/03/2025 | 07/03/2025
TO-25-CBT-CKG-1-02 | 110kV FEEDER - CASTLEBAGOT 110-CORKAGH 110-1 | 5 | 5 | 5 | Proposed | 03/03/2025 | 07/03/2025
TO-25-220 kV A3 @ CDU-02 | BUSBAR SECTION - CORDUFF 220-CORDUFF 220-220A3 | 12 | 10 | 10 | Proposed | 03/03/2025 | 14/03/2025
TO-25-220 kV B3 @ CDU-02 | BUSBAR SECTION - CORDUFF 220-CORDUFF 220-220B3 | 12 | 10 | 10 | Proposed | 03/03/2025 | 14/03/2025
TO-25-CDU-FIN-1-02 | 220kV FEEDER - CORDUFF 220-FINGLAS 220-1 | 12 | 10 |  | Proposed | 03/03/2025 | 14/03/2025
TO-25-CDU-FIN-1-03 | 220kV FEEDER - CORDUFF 220-FINGLAS 220-1 | 12 | 10 | 10 | Proposed | 03/03/2025 | 14/03/2025
TO-25-CDU-GLN-1-01 | 110kV FEEDER - CORDUFF 110-GALLANSTOWN 110-1 | 1 | 1 | 1 | Proposed | 03/03/2025 | 03/03/2025
TO-25-CDU-GLN-1-02 | 110kV FEEDER - CORDUFF 110-GALLANSTOWN 110-1 | 12 | 10 | 10 | Proposed | 03/03/2025 | 14/03/2025
TO-25-110 kV A3 @ CKG-02 | BUSBAR SECTION - CORKAGH 110-CORKAGH 110-110A3 | 5 | 5 | 5 | Proposed | 03/03/2025 | 07/03/2025
TO-25-110 kV B3 @ CKG-02 | BUSBAR SECTION - CORKAGH 110-CORKAGH 110-110B3 | 5 | 5 | 5 | Proposed | 03/03/2025 | 07/03/2025
TO-25-CKG-110K3-02 | COUPLER/SECTIONALISING CB - CORKAGH 110-CORKAGH 110-110K3 | 5 | 5 | 5 | Proposed | 03/03/2025 | 07/03/2025
TO-25-CKG-110SA1-3CB-03 | COUPLER/SECTIONALISING CB - CORKAGH 110-CORKAGH 110-110SA1-3CB | 5 | 5 | 5 | Proposed | 03/03/2025 | 07/03/2025
TO-25-CKG-110SB1-3CB-03 | COUPLER/SECTIONALISING CB - CORKAGH 110-CORKAGH 110-110SB1-3CB | 5 | 5 | 5 | Proposed | 03/03/2025 | 07/03/2025
TO-25-220 kV A1 @ FIN-03 | BUSBAR SECTION - FINGLAS 220-FINGLAS 220-220A1 | 12 | 10 | 10 | Proposed | 03/03/2025 | 14/03/2025
TO-25-220 kV A1 @ FIN-04 | BUSBAR SECTION - FINGLAS 220-FINGLAS 220-220A1 | 16 | 11 | 11 | Proposed | 03/03/2025 | 18/03/2025
TO-25-220 kV A1 @ FIN-05 | BUSBAR SECTION - FINGLAS 220-FINGLAS 220-220A1 | 12 | 10 | 10 | Proposed | 03/03/2025 | 14/03/2025
TO-25-220 kV B1 @ FIN-02 | BUSBAR SECTION - FINGLAS 220-FINGLAS 220-220B1 | 12 | 10 | 10 | Proposed | 03/03/2025 | 14/03/2025
TO-25-220 kV B1 @ FIN-03 | BUSBAR SECTION - FINGLAS 220-FINGLAS 220-220B1 | 12 | 10 |  | Proposed | 03/03/2025 | 14/03/2025
TO-25-220 kV B1 @ FIN-04 | BUSBAR SECTION - FINGLAS 220-FINGLAS 220-220B1 | 16 | 11 | 11 | Proposed | 03/03/2025 | 18/03/2025
TO-25-FIN-220K1-03 | COUPLER/SECTIONALISING CB - FINGLAS 220-FINGLAS 220-220K1 | 12 | 10 |  | Proposed | 03/03/2025 | 14/03/2025
TO-25-FIN-220K1-05 | COUPLER/SECTIONALISING CB - FINGLAS 220-FINGLAS 220-220K1 | 16 | 11 | 11 | Proposed | 03/03/2025 | 18/03/2025
TO-25-FIN-220K1-07 | COUPLER/SECTIONALISING CB - FINGLAS 220-FINGLAS 220-220K1 | 12 | 10 | 10 | Proposed | 03/03/2025 | 14/03/2025
TO-25-FIN-220SA1-2CB-10 | COUPLER/SECTIONALISING CB - FINGLAS 220-FINGLAS 220-220SA1-2CB | 12 | 10 | 10 | Proposed | 03/03/2025 | 14/03/2025
TO-25-FIN-220SA1-2CB-05 | COUPLER/SECTIONALISING CB - FINGLAS 220-FINGLAS 220-220SA1-2CB | 12 | 10 | 10 | Proposed | 03/03/2025 | 14/03/2025
TO-25-FIN-220SA1-2CB-07 | COUPLER/SECTIONALISING CB - FINGLAS 220-FINGLAS 220-220SA1-2CB | 16 | 11 | 11 | Proposed | 03/03/2025 | 18/03/2025
TO-25-FIN-220SB1-2CB-08 | COUPLER/SECTIONALISING CB - FINGLAS 220-FINGLAS 220-220SB1-2CB | 12 | 10 | 10 | Proposed | 03/03/2025 | 14/03/2025
TO-25-FIN-220SB1-2CB-06 | COUPLER/SECTIONALISING CB - FINGLAS 220-FINGLAS 220-220SB1-2CB | 16 | 11 | 11 | Proposed | 03/03/2025 | 18/03/2025
TO-25-FIN-220SB1-2CB-02 | COUPLER/SECTIONALISING CB - FINGLAS 220-FINGLAS 220-220SB1-2CB | 12 | 10 |  | Proposed | 03/03/2025 | 14/03/2025
TO-25-FIN-T2103-02 | TRANSFORMER - FINGLAS 220-FINGLAS 110-T2103 | 16 | 11 | 11 | Proposed | 03/03/2025 | 18/03/2025
TO-25-BLU-T131-01 | GENERATOR TRANSFORMER - BLUNDELSTOWN 110-BLUNDELSTOWN 33-T131 | 1 | 1 | 1 | Proposed | 04/03/2025 | 04/03/2025
TO-25-BLU-T131-02 | GENERATOR TRANSFORMER - BLUNDELSTOWN 110-BLUNDELSTOWN 33-T131 | 2 | 2 | 2 | Proposed | 04/03/2025 | 05/03/2025
TO-25-DND-T121-02 | TSO CUSTOMER TRANSFORMER - DARNDALE 110-DARNDALE 20-T121 | 2 | 2 | 2 | Proposed | 05/03/2025 | 06/03/2025
TO-25-BAG-T103-01 | TSO CUSTOMER TRANSFORMER - BARNAGEERAGH 110-BARNAGEERAGH 11-T103 | 5 | 5 | 5 | Scheduled | 10/03/2025 | 14/03/2025
TO-25-BAG-T103-02 | TSO CUSTOMER TRANSFORMER - BARNAGEERAGH 110-BARNAGEERAGH 11-T103 | 5 | 5 | 5 | Proposed | 10/03/2025 | 14/03/2025
TO-25-110 kV A1 @ CDU-01 | BUSBAR SECTION - CORDUFF 110-CORDUFF 110-110A1 | 12 | 9 | 9 | Proposed | 10/03/2025 | 21/03/2025
TO-25-110 kV A2 @ CDU-01 | BUSBAR SECTION - CORDUFF 110-CORDUFF 110-110A2 | 12 | 9 | 9 | Proposed | 10/03/2025 | 21/03/2025
TO-25-110 kV B1 @ CDU-01 | BUSBAR SECTION - CORDUFF 110-CORDUFF 110-110B1 | 12 | 9 | 9 | Proposed | 10/03/2025 | 21/03/2025
TO-25-110 kV B2 @ CDU-01 | BUSBAR SECTION - CORDUFF 110-CORDUFF 110-110B2 | 12 | 9 | 9 | Proposed | 10/03/2025 | 21/03/2025
TO-25-CDU-110K1-2-01 | COUPLER/SECTIONALISING CB - CORDUFF 110-CORDUFF 110-110K1-2 | 12 | 9 |  | Proposed | 10/03/2025 | 21/03/2025
TO-25-400 kV A1 @ DSN-01 | BUSBAR SECTION - DUNSTOWN 400-DUNSTOWN 400-400A1 | 38 | 27 | 27 | Scheduled | 11/03/2025 | 17/04/2025
TO-25-400 kV B1 @ DSN-01 | BUSBAR SECTION - DUNSTOWN 400-DUNSTOWN 400-400B1 | 38 | 27 | 27 | Scheduled | 11/03/2025 | 17/04/2025
TO-25-DSN-MP GIS-1-01 | 400kV FEEDER - DUNSTOWN 400-MONEYPOINT GIS 400-1 | 38 | 27 |  | Scheduled | 11/03/2025 | 17/04/2025
TO-25-INC-PB-2-02 | 220kV FEEDER - INCHICORE 220-POOLBEG 220-2 | 22 | 15 |  | Scheduled | 11/03/2025 | 01/04/2025
TO-25-CDU-CRU-2-02 | 220kV FEEDER - CORDUFF 220-CRUISERATH 220-2 | 2 | 2 | 2 | Proposed | 13/03/2025 | 14/03/2025
TO-25-220 kV A2 @ CDU-03 | BUSBAR SECTION - CORDUFF 220-CORDUFF 220-220A2 | 14 | 10 | 10 | Proposed | 19/03/2025 | 01/04/2025
TO-25-220 kV B2 @ CDU-03 | BUSBAR SECTION - CORDUFF 220-CORDUFF 220-220B2 | 14 | 10 | 10 | Proposed | 19/03/2025 | 01/04/2025
TO-25-CDU-FIN-2-03 | 220kV FEEDER - CORDUFF 220-FINGLAS 220-2 | 14 | 10 |  | Proposed | 19/03/2025 | 01/04/2025
TO-25-CDU-FIN-2-05 | 220kV FEEDER - CORDUFF 220-FINGLAS 220-2 | 14 | 10 |  | Proposed | 19/03/2025 | 01/04/2025
TO-25-220 kV A2 @ FIN-03 | BUSBAR SECTION - FINGLAS 220-FINGLAS 220-220A2 | 14 | 10 |  | Proposed | 19/03/2025 | 01/04/2025
TO-25-220 kV A2 @ FIN-06 | BUSBAR SECTION - FINGLAS 220-FINGLAS 220-220A2 | 14 | 10 | 10 | Proposed | 19/03/2025 | 01/04/2025
TO-25-220 kV B2 @ FIN-03 | BUSBAR SECTION - FINGLAS 220-FINGLAS 220-220B2 | 14 | 10 |  | Proposed | 19/03/2025 | 01/04/2025
TO-25-FIN-220K2-07 | COUPLER/SECTIONALISING CB - FINGLAS 220-FINGLAS 220-220K2 | 14 | 10 | 10 | Proposed | 19/03/2025 | 01/04/2025
TO-25-FIN-220K2-03 | COUPLER/SECTIONALISING CB - FINGLAS 220-FINGLAS 220-220K2 | 14 | 10 |  | Proposed | 19/03/2025 | 01/04/2025
TO-25-FIN-220SA1-2CB-11 | COUPLER/SECTIONALISING CB - FINGLAS 220-FINGLAS 220-220SA1-2CB | 14 | 10 | 10 | Proposed | 19/03/2025 | 01/04/2025
TO-25-FIN-220SA1-2CB-06 | COUPLER/SECTIONALISING CB - FINGLAS 220-FINGLAS 220-220SA1-2CB | 14 | 10 | 10 | Proposed | 19/03/2025 | 01/04/2025
TO-25-FIN-220SB1-2CB-03 | COUPLER/SECTIONALISING CB - FINGLAS 220-FINGLAS 220-220SB1-2CB | 14 | 10 |  | Proposed | 19/03/2025 | 01/04/2025
TO-25-TH-T2001/2-01 | GENERATOR TRANSFORMER - TURLOUGH HILL 220-TURLOUGH HILL G1-T2001/2 | 10 | 7 | 7 | Scheduled | 23/03/2025 | 01/04/2025
TO-25-TH-T2001/2-02 | GENERATOR TRANSFORMER - TURLOUGH HILL 220-TURLOUGH HILL G1-T2001/2 | 10 | 7 | 7 | Proposed | 23/03/2025 | 01/04/2025
TO-25-CBT-CLU-1-02 | 110kV FEEDER - CASTLEBAGOT 110-CLUTTERLAND 110-1 | 5 | 5 | 5 | Scheduled | 24/03/2025 | 28/03/2025
TO-25-CLG-T122-01 | TSO CUSTOMER TRANSFORMER - CLOGHRAN 110-CLOGHRAN 20-T122 | 5 | 5 | 5 | Scheduled | 24/03/2025 | 28/03/2025
TO-25-CLG-T122-02 | TSO CUSTOMER TRANSFORMER - CLOGHRAN 110-CLOGHRAN 20-T122 | 5 | 5 | 5 | Proposed | 24/03/2025 | 28/03/2025
TO-25-220 kV A2 @ FIN-07 | BUSBAR SECTION - FINGLAS 220-FINGLAS 220-220A2 | 12 | 10 | 10 | Proposed | 24/03/2025 | 04/04/2025
TO-25-FIN-220K2-09 | COUPLER/SECTIONALISING CB - FINGLAS 220-FINGLAS 220-220K2 | 12 | 10 | 10 | Proposed | 24/03/2025 | 04/04/2025
TO-25-FIN-220SA1-2CB-12 | COUPLER/SECTIONALISING CB - FINGLAS 220-FINGLAS 220-220SA1-2CB | 12 | 10 | 10 | Proposed | 24/03/2025 | 04/04/2025
TO-25-FIN GIS-T2106-02 | TRANSFORMER - FINGLAS 220-FINGLAS GIS 110-T2106 | 12 | 10 | 10 | Proposed | 24/03/2025 | 04/04/2025
TO-25-GLN-T133-01 | GENERATOR TRANSFORMER - GALLANSTOWN 110-GALLANSTOWN 33-T133 | 5 | 5 | 5 | Proposed | 24/03/2025 | 28/03/2025
TO-25-GLN-T133-02 | GENERATOR TRANSFORMER - GALLANSTOWN 110-GALLANSTOWN 33-T133 | 5 | 5 | 5 | Proposed | 24/03/2025 | 28/03/2025
TO-25-ISH-T2001-01 | GENERATOR TRANSFORMER - IRISHTOWN 220-IRISHTOWN G1-T2001 | 4 | 4 | 4 | Proposed | 24/03/2025 | 27/03/2025
TO-25-110 kV A2 @ CLU-01 | BUSBAR SECTION - CLUTTERLAND 110-CLUTTERLAND 110-110A2 | 9 | 7 | 7 | Proposed | 27/03/2025 | 04/04/2025
TO-25-110 kV B2 @ CLU-01 | BUSBAR SECTION - CLUTTERLAND 110-CLUTTERLAND 110-110B2 | 9 | 7 | 7 | Proposed | 27/03/2025 | 04/04/2025
TO-25-CLU-110K2-01 | COUPLER/SECTIONALISING CB - CLUTTERLAND 110-CLUTTERLAND 110-110K2 | 9 | 7 | 7 | Proposed | 27/03/2025 | 04/04/2025
TO-25-CLU-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - CLUTTERLAND 110-CLUTTERLAND 110-110SA1-2CB | 9 | 7 | 7 | Proposed | 27/03/2025 | 04/04/2025
TO-25-CLU-110SB1-2CB-01 | COUPLER/SECTIONALISING CB - CLUTTERLAND 110-CLUTTERLAND 110-110SB1-2CB | 9 | 7 | 7 | Proposed | 27/03/2025 | 04/04/2025
TO-25-MAY-RYB GIS-1-01 | 110kV FEEDER - MAYNOOTH 110-RYEBROOK GIS 110-1 | Unknown | Unknown | 5 | Planned | March | April
TO-25-TH-T2003/4-01 | GENERATOR TRANSFORMER - TURLOUGH HILL 220-TURLOUGH HILL G1-T2003/4 | 10 | 8 | 8 | Proposed | 02/04/2025 | 11/04/2025
TO-25-CBT-CLU-1-01 | 110kV FEEDER - CASTLEBAGOT 110-CLUTTERLAND 110-1 | 2 | 2 | 2 | Proposed | 03/04/2025 | 04/04/2025
TO-25-FIN-SHL-1-03 | 220kV FEEDER - FINGLAS 220-SHELLYBANKS 220-1 | Unknown | Unknown | 15 | Planned | April | April
TO-25-BRT-T224-01 | TSO CUSTOMER TRANSFORMER - BRACETOWN 220-BRACETOWN 20-T224 | Unknown | Unknown | 33 | Planned | April | May
TO-25-PRN-T4301-02 | TRANSFORMER - PORTAN 400-PORTAN 260-T4301 | 4 | 3 | 3 | Proposed | 15/04/2025 | 18/04/2025
TO-25-PRN-T4301-01 | TRANSFORMER - PORTAN 400-PORTAN 260-T4301 | Unknown | Unknown | 3 | Planned | April | April
TO-25-PRN-WOO-1-02 | 400kV FEEDER - PORTAN 400-WOODLAND 400-1 | 4 | 3 | 3 | Proposed | 15/04/2025 | 18/04/2025
TO-25-PRN-WOO-1-01 | 400kV FEEDER - PORTAN 400-WOODLAND 400-1 | Unknown | Unknown | 3 | Planned | April | April
TO-25-WOO-400K1-2-01 | COUPLER/SECTIONALISING CB - WOODLAND 400-WOODLAND 400-400K1-2 | Unknown | Unknown | 3 | Planned | April | April
TO-25-WOO-T4201-02 | TRANSFORMER - WOODLAND 400-WOODLAND 220-T4201 | Unknown | Unknown | 3 | Planned | April | April
TO-25-220 kV B2 @ MAY-01 | BUSBAR SECTION - MAYNOOTH 220-MAYNOOTH 220-220B2 | Unknown | Unknown |  | Planned | April | June
TO-25-MAY-SH-1-01 | 220kV FEEDER - MAYNOOTH 220-SHANNONBRIDGE 220-1 | Unknown | Unknown |  | Planned | April | September
TO-25-AUN-110K1-01 | COUPLER/SECTIONALISING CB - AUNGIERSTOWN 110-AUNGIERSTOWN 110-110K1 | 3 | 3 | 3 | Proposed | 23/04/2025 | 25/04/2025
TO-25-AUN-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - AUNGIERSTOWN 110-AUNGIERSTOWN 110-110SA1-2CB | 3 | 3 | 3 | Proposed | 23/04/2025 | 25/04/2025
TO-25-AUN-110SB1-2CB-01 | COUPLER/SECTIONALISING CB - AUNGIERSTOWN 110-AUNGIERSTOWN 110-110SB1-2CB | 3 | 3 | 3 | Proposed | 23/04/2025 | 25/04/2025
TO-25-110 kV A1 @ CKG-01 | BUSBAR SECTION - CORKAGH 110-CORKAGH 110-110A1 | Unknown | Unknown | 10 | Planned | April | May
TO-25-110 kV B1 @ CKG-01 | BUSBAR SECTION - CORKAGH 110-CORKAGH 110-110B1 | Unknown | Unknown | 10 | Planned | April | May
TO-25-CKG-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - CORKAGH 110-CORKAGH 110-110SA1-2CB | Unknown | Unknown | 10 | Planned | April | May
TO-25-CKG-110SA1-3CB-01 | COUPLER/SECTIONALISING CB - CORKAGH 110-CORKAGH 110-110SA1-3CB | Unknown | Unknown | 10 | Planned | April | May
TO-25-CKG-110SB1-2CB-01 | COUPLER/SECTIONALISING CB - CORKAGH 110-CORKAGH 110-110SB1-2CB | Unknown | Unknown | 10 | Planned | April | May
TO-25-CKG-110SB1-3CB-01 | COUPLER/SECTIONALISING CB - CORKAGH 110-CORKAGH 110-110SB1-3CB | Unknown | Unknown | 10 | Planned | April | May
TO-25-CKM GIS-ISH-1-01 | 220kV FEEDER - CARRICKMINES GIS 220-IRISHTOWN 220-1 | Unknown | Unknown | 14 | Planned | April | May
TO-25-CBT-CKG-2-01 | 110kV FEEDER - CASTLEBAGOT 110-CORKAGH 110-2 | Unknown | Unknown | 2 | Planned | May | May
TO-25-PA-110SA1-02 | SECTIONALISING DISCONNECT - POLLAPHUCA 110-POLLAPHUCA 110-110SA1 | Unknown | Unknown | 15 | Planned | May | May
TO-25-PA-110SA2-02 | SECTIONALISING DISCONNECT - POLLAPHUCA 110-POLLAPHUCA 110-110SA2 | Unknown | Unknown | 15 | Planned | May | May
TO-25-PA-T101-02 | GENERATOR TRANSFORMER - POLLAPHUCA 110-POLLAPHUCA G1-T101 | Unknown | Unknown | 15 | Planned | May | May
TO-25-RYB GIS-T105-02 | TSO CUSTOMER TRANSFORMER - RYEBROOK GIS 110-RYEBROOK 10-T105 | 12 | 10 | 10 | Proposed | 19/05/2025 | 30/05/2025
TO-25-FIN-SHL-1-02 | 220kV FEEDER - FINGLAS 220-SHELLYBANKS 220-1 | Unknown | Unknown | 50 | Planned | May | July
TO-25-220 kV A2 @ WOO-05 | BUSBAR SECTION - WOODLAND 220-WOODLAND 220-220A2 | Unknown | Unknown | 10 | Planned | May | June
TO-25-WOO-220K1-2-02 | COUPLER/SECTIONALISING CB - WOODLAND 220-WOODLAND 220-220K1-2 | Unknown | Unknown | 33 | Planned | May | July
TO-25-BLC-DND-1-01 | 110kV FEEDER - BELCAMP 110-DARNDALE 110-1 | 2 | 2 | 2 | Scheduled | 29/05/2025 | 30/05/2025
TO-25-110 kV A1 @ DND-01 | BUSBAR SECTION - DARNDALE 110-DARNDALE 110-110A1 | 2 | 2 | 2 | Scheduled | 29/05/2025 | 30/05/2025
TO-25-DND-110K1-01 | COUPLER/SECTIONALISING CB - DARNDALE 110-DARNDALE 110-110K1 | 2 | 2 | 2 | Scheduled | 29/05/2025 | 30/05/2025
TO-25-DND-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - DARNDALE 110-DARNDALE 110-110SA1-2CB | 2 | 2 | 2 | Scheduled | 29/05/2025 | 30/05/2025
TO-25-FIN-FIN GIS-2-01 | 110kV FEEDER - FINGLAS 110-FINGLAS GIS 110-2 | Unknown | Unknown | 150 | Planned | May | December
TO-25-FIN-T2104-01 | TRANSFORMER - FINGLAS 220-FINGLAS 110-T2104 | Unknown | Unknown |  | Planned | May | September
TO-25-RYB GIS-T106-02 | TSO CUSTOMER TRANSFORMER - RYEBROOK GIS 110-RYEBROOK 10-T106 | 12 | 9 | 9 | Proposed | 02/06/2025 | 13/06/2025
TO-25-WOO-T4202-02 | TRANSFORMER - WOODLAND 400-WOODLAND 220-T4202 | Unknown | Unknown | 2 | Planned | June | June
TO-25-220 kV A2 @ DSN-01 | BUSBAR SECTION - DUNSTOWN 220-DUNSTOWN 220-220A2 | Unknown | Unknown |  | Planned | June | June
TO-25-RYB GIS-T107-02 | TSO CUSTOMER TRANSFORMER - RYEBROOK GIS 110-RYEBROOK 10-T107 | 12 | 10 | 10 | Proposed | 16/06/2025 | 27/06/2025
TO-25-220 kV B2 @ DSN-01 | BUSBAR SECTION - DUNSTOWN 220-DUNSTOWN 220-220B2 | Unknown | Unknown |  | Planned | June | July
TO-25-220 kV A2 @ WOO-06 | BUSBAR SECTION - WOODLAND 220-WOODLAND 220-220A2 | Unknown | Unknown | 2 | Planned | June | June
TO-25-WOO-220K1-2-03 | COUPLER/SECTIONALISING CB - WOODLAND 220-WOODLAND 220-220K1-2 | Unknown | Unknown | 11 | Planned | June | July
TO-25-WOO-T4202-03 | TRANSFORMER - WOODLAND 400-WOODLAND 220-T4202 | Unknown | Unknown | 2 | Planned | June | June
TO-25-CLU-T121-01 | TSO CUSTOMER TRANSFORMER - CLUTTERLAND 110-CLUTTERLAND 20-T121 | 5 | 5 | 5 | Proposed | 30/06/2025 | 04/07/2025
TO-25-CLU-T122-01 | TSO CUSTOMER TRANSFORMER - CLUTTERLAND 110-CLUTTERLAND 20-T122 | 5 | 5 | 5 | Proposed | 07/07/2025 | 11/07/2025
TO-25-400 kV A2 @ DSN-03 | BUSBAR SECTION - DUNSTOWN 400-DUNSTOWN 400-400A2 | Unknown | Unknown |  | Planned | July | July
TO-25-220 kV A1 @ WOO-01 | BUSBAR SECTION - WOODLAND 220-WOODLAND 220-220A1 | Unknown | Unknown | 1 | Planned | July | July
TO-25-WOO-T4201-01 | TRANSFORMER - WOODLAND 400-WOODLAND 220-T4201 | Unknown | Unknown | 1 | Planned | July | July
TO-25-CRU-T221-01 | TSO CUSTOMER TRANSFORMER - CRUISERATH 220-CRUISERATH 20-T221 | 5 | 5 | 5 | Proposed | 21/07/2025 | 25/07/2025
TO-25-400 kV B2 @ DSN-01 | BUSBAR SECTION - DUNSTOWN 400-DUNSTOWN 400-400B2 | Unknown | Unknown |  | Planned | July | August
TO-25-CRU-T223-01 | TSO CUSTOMER TRANSFORMER - CRUISERATH 220-CRUISERATH 20-T223 | 5 | 5 | 5 | Proposed | 28/07/2025 | 01/08/2025
TO-25-ISH-SHL-1-02 | 220kV FEEDER - IRISHTOWN 220-SHELLYBANKS 220-1 | Unknown | Unknown | 2 | Planned | July | July
TO-25-BLC-FIN-1-01 | 220kV FEEDER - BELCAMP 220-FINGLAS 220-1 | Unknown | Unknown | 30 | Planned | July | September
TO-25-BLC-T2103-01 | TRANSFORMER - BELCAMP 220-BELCAMP 110-T2103 | Unknown | Unknown | 80 | Planned | July | November
TO-25-DFR,T-RNW-1-02 | 110kV FEEDER - DUNFIRTH tee-RINAWADE 110-1 | Unknown | Unknown | 7 | Planned | August | August
TO-25-110 kV B4 @ FIN GIS-01 | BUSBAR SECTION - FINGLAS GIS 110-FINGLAS GIS 110-110B4 | Unknown | Unknown | 3 | Planned | August | August
TO-25-FIN GIS-110SB2-4CB-01 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110SB2-4CB | Unknown | Unknown | 5 | Planned | August | August
TO-25-FIN GIS-110SB4-6CB-01 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110SB4-6CB | Unknown | Unknown | 3 | Planned | August | August
TO-25-220 kV A2 @ MAY-01 | BUSBAR SECTION - MAYNOOTH 220-MAYNOOTH 220-220A2 | Unknown | Unknown |  | Planned | August | August
TO-25-220 kV B2 @ MAY-02 | BUSBAR SECTION - MAYNOOTH 220-MAYNOOTH 220-220B2 | Unknown | Unknown |  | Planned | August | August
TO-25-220 kV A2 @ WOO-01 | BUSBAR SECTION - WOODLAND 220-WOODLAND 220-220A2 | Unknown | Unknown | 15 | Planned | August | September
TO-25-220 kV B2 @ WOO-01 | BUSBAR SECTION - WOODLAND 220-WOODLAND 220-220B2 | Unknown | Unknown | 15 | Planned | August | September
TO-25-110 kV A3 @ CKG-01 | BUSBAR SECTION - CORKAGH 110-CORKAGH 110-110A3 | Unknown | Unknown | 10 | Planned | August | August
TO-25-110 kV B3 @ CKG-01 | BUSBAR SECTION - CORKAGH 110-CORKAGH 110-110B3 | Unknown | Unknown | 10 | Planned | August | August
TO-25-CKG-110K3-01 | COUPLER/SECTIONALISING CB - CORKAGH 110-CORKAGH 110-110K3 | Unknown | Unknown | 10 | Planned | August | August
TO-25-CKG-110SA1-3CB-02 | COUPLER/SECTIONALISING CB - CORKAGH 110-CORKAGH 110-110SA1-3CB | Unknown | Unknown | 10 | Planned | August | August
TO-25-CKG-110SB1-3CB-02 | COUPLER/SECTIONALISING CB - CORKAGH 110-CORKAGH 110-110SB1-3CB | Unknown | Unknown | 10 | Planned | August | August
TO-25-220 kV A2 @ DSN-02 | BUSBAR SECTION - DUNSTOWN 220-DUNSTOWN 220-220A2 | Unknown | Unknown |  | Planned | August | September
TO-25-CBT-CKG-1-01 | 110kV FEEDER - CASTLEBAGOT 110-CORKAGH 110-1 | Unknown | Unknown | 2 | Planned | August | August
TO-25-220 kV A2 @ FIN-01 | BUSBAR SECTION - FINGLAS 220-FINGLAS 220-220A2 | Unknown | Unknown | 5 | Planned | September | September
TO-25-220 kV B2 @ FIN-01 | BUSBAR SECTION - FINGLAS 220-FINGLAS 220-220B2 | Unknown | Unknown | 5 | Planned | September | September
TO-25-FIN-220K2-01 | COUPLER/SECTIONALISING CB - FINGLAS 220-FINGLAS 220-220K2 | Unknown | Unknown | 5 | Planned | September | September
TO-25-FIN-220SA1-2CB-02 | COUPLER/SECTIONALISING CB - FINGLAS 220-FINGLAS 220-220SA1-2CB | Unknown | Unknown | 5 | Planned | September | September
TO-25-FIN-220SB1-2CB-01 | COUPLER/SECTIONALISING CB - FINGLAS 220-FINGLAS 220-220SB1-2CB | Unknown | Unknown | 5 | Planned | September | September
TO-25-110 kV A4 @ FIN GIS-01 | BUSBAR SECTION - FINGLAS GIS 110-FINGLAS GIS 110-110A4 | Unknown | Unknown | 5 | Planned | September | September
TO-25-110 kV B4 @ FIN GIS-02 | BUSBAR SECTION - FINGLAS GIS 110-FINGLAS GIS 110-110B4 | Unknown | Unknown | 5 | Planned | September | September
TO-25-FIN GIS-110SA2-4CB-01 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110SA2-4CB | Unknown | Unknown | 5 | Planned | September | September
TO-25-FIN GIS-110SA4-6CB-01 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110SA4-6CB | Unknown | Unknown | 5 | Planned | September | September
TO-25-FIN GIS-110SB2-4CB-02 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110SB2-4CB | Unknown | Unknown | 5 | Planned | September | September
TO-25-FIN GIS-110SB4-6CB-02 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110SB4-6CB | Unknown | Unknown | 5 | Planned | September | September
TO-25-DSN-MAY-2-01 | 220kV FEEDER - DUNSTOWN 220-MAYNOOTH 220-2 | Unknown | Unknown |  | Planned | September | September
TO-25-220 kV A2 @ MAY-02 | BUSBAR SECTION - MAYNOOTH 220-MAYNOOTH 220-220A2 | Unknown | Unknown |  | Planned | September | September
TO-25-LOU-WOO-1-01 | 220kV FEEDER - LOUTH 220-WOODLAND 220-1 | Unknown | Unknown | 25 | Planned | September | October
TO-25-LOU-WOO-1-02 | 220kV FEEDER - LOUTH 220-WOODLAND 220-1 | Unknown | Unknown | 25 | Planned | September | October
TO-25-MAY-T2102-01 | TRANSFORMER - MAYNOOTH 220-MAYNOOTH 110-T2102 | Unknown | Unknown | 10 | Planned | September | September
TO-25-220 kV A2 @ WOO-02 | BUSBAR SECTION - WOODLAND 220-WOODLAND 220-220A2 | Unknown | Unknown | 5 | Planned | September | September
TO-25-220 kV B2 @ WOO-02 | BUSBAR SECTION - WOODLAND 220-WOODLAND 220-220B2 | Unknown | Unknown |  | Planned | September | September
TO-25-WOO-220K1-2-01 | COUPLER/SECTIONALISING CB - WOODLAND 220-WOODLAND 220-220K1-2 | Unknown | Unknown | 5 | Planned | September | September
TO-25-CDU-FIN-2-04 | 220kV FEEDER - CORDUFF 220-FINGLAS 220-2 | Unknown | Unknown | 2 | Planned | September | September
TO-25-220 kV A2 @ DSN-03 | BUSBAR SECTION - DUNSTOWN 220-DUNSTOWN 220-220A2 | Unknown | Unknown |  | Planned | September | September
TO-25-220 kV A2 @ FIN-04 | BUSBAR SECTION - FINGLAS 220-FINGLAS 220-220A2 | Unknown | Unknown | 2 | Planned | September | September
TO-25-FIN-220K2-04 | COUPLER/SECTIONALISING CB - FINGLAS 220-FINGLAS 220-220K2 | Unknown | Unknown | 2 | Planned | September | September
TO-25-FIN-220SA1-2CB-01 | COUPLER/SECTIONALISING CB - FINGLAS 220-FINGLAS 220-220SA1-2CB | Unknown | Unknown | 2 | Planned | September | September
TO-25-CDU-WOO-1-01 | 220kV FEEDER - CORDUFF 220-WOODLAND 220-1 | Unknown | Unknown |  | Planned | September | September
TO-25-220 kV A2 @ WOO-03 | BUSBAR SECTION - WOODLAND 220-WOODLAND 220-220A2 | Unknown | Unknown | 6 | Planned | September | September
TO-25-220 kV B2 @ DSN-02 | BUSBAR SECTION - DUNSTOWN 220-DUNSTOWN 220-220B2 | Unknown | Unknown | 5 | Planned | September | September
TO-25-220 kV A1/A2 @ FIN-01 | BUSBAR SECTION - FINGLAS 220-FINGLAS 220-220A1-A2 | Unknown | Unknown | 0 | Planned | September | September
TO-25-FIN-220K1-02 | COUPLER/SECTIONALISING CB - FINGLAS 220-FINGLAS 220-220K1 | Unknown | Unknown | 0 | Planned | September | September
TO-25-FIN-220K2-02 | COUPLER/SECTIONALISING CB - FINGLAS 220-FINGLAS 220-220K2 | Unknown | Unknown | 0 | Planned | September | September
TO-25-FIN-220SA1-2CB-03 | COUPLER/SECTIONALISING CB - FINGLAS 220-FINGLAS 220-220SA1-2CB | Unknown | Unknown | 0 | Planned | September | September
TO-25-FIN-NW-1-01 | 220kV FEEDER - FINGLAS 220-NORTH WALL 220-1 | Unknown | Unknown | 0 | Planned | September | September
TO-25-CDU-WOO-1-02 | 220kV FEEDER - CORDUFF 220-WOODLAND 220-1 | Unknown | Unknown |  | Planned | September | September
TO-25-INC-PB-2-01 | 220kV FEEDER - INCHICORE 220-POOLBEG 220-2 | Unknown | Unknown | 10 | Planned | September | October
TO-25-MAY-T2103-01 | TRANSFORMER - MAYNOOTH 220-MAYNOOTH 110-T2103 | Unknown | Unknown | 10 | Planned | September | October
TO-25-WOO-220K1-2-04 | COUPLER/SECTIONALISING CB - WOODLAND 220-WOODLAND 220-220K1-2 | Unknown | Unknown |  | Planned | September | September
TO-25-400 kV B2 @ WOO-01 | BUSBAR SECTION - WOODLAND 400-WOODLAND 400-400B2 | Unknown | Unknown | 15 | Planned | September | October
TO-25-WOO-T4202-01 | TRANSFORMER - WOODLAND 400-WOODLAND 220-T4202 | Unknown | Unknown |  | Planned | September | September
TO-25-WOO-T4204-01 | TRANSFORMER - WOODLAND 400-WOODLAND 220-T4204 | Unknown | Unknown |  | Planned | September | September
TO-25-400 kV A2 @ DSN-02 | BUSBAR SECTION - DUNSTOWN 400-DUNSTOWN 400-400A2 | Unknown | Unknown |  | Planned | September | September
TO-25-400 kV A2 @ DSN-01 | BUSBAR SECTION - DUNSTOWN 400-DUNSTOWN 400-400A2 | Unknown | Unknown |  | Planned | October | October
TO-25-INC-ISH-1-01 | 220kV FEEDER - INCHICORE 220-IRISHTOWN 220-1 | Unknown | Unknown | 10 | Planned | October | October
TO-25-MAY-T2104-01 | TRANSFORMER - MAYNOOTH 220-MAYNOOTH 110-T2104 | Unknown | Unknown | 10 | Planned | October | October
TO-25-220 kV A2 @ WOO-04 | BUSBAR SECTION - WOODLAND 220-WOODLAND 220-220A2 | Unknown | Unknown | 2 | Planned | October | October
TO-25-220 kV B2 @ WOO-03 | BUSBAR SECTION - WOODLAND 220-WOODLAND 220-220B2 | Unknown | Unknown | 2 | Planned | October | October
TO-25-WOO-T4204-02 | TRANSFORMER - WOODLAND 400-WOODLAND 220-T4204 | Unknown | Unknown | 2 | Planned | October | October
TO-25-400 kV B2 @ DSN-02 | BUSBAR SECTION - DUNSTOWN 400-DUNSTOWN 400-400B2 | Unknown | Unknown |  | Planned | October | October
TO-25-DSN-MAY-1-01 | 220kV FEEDER - DUNSTOWN 220-MAYNOOTH 220-1 | Unknown | Unknown | 5 | Planned | October | October
TO-25-KYT-T233-01 | TSO CUSTOMER TRANSFORMER - KELLYSTOWN 220-KELLYSTOWN 34.5-T233 | 19 | 14 | 14 | Proposed | 20/10/2025 | 07/11/2025
TO-25-MAY-TH-1-01 | 220kV FEEDER - MAYNOOTH 220-TURLOUGH HILL 220-1 | Unknown | Unknown |  | Planned | October | November
TO-25-MAY-TH-1-03 | 220kV FEEDER - MAYNOOTH 220-TURLOUGH HILL 220-1 | Unknown | Unknown | 5 | Planned | October | October
TO-25-PB-SHL-1-01 | 220kV FEEDER - POOLBEG 220-SHELLYBANKS 220-1 | Unknown | Unknown | 5 | Planned | October | October
TO-25-220 kV B2/B4 @ CDU-01 | BUSBAR SECTION - CORDUFF 220-CORDUFF 220-220B2-B4 | Unknown | Unknown | 5 | Planned | November | November
TO-25-CDU-CRU-2-01 | 220kV FEEDER - CORDUFF 220-CRUISERATH 220-2 | Unknown | Unknown | 5 | Planned | November | November
TO-25-CDU-WOO-1-03 | 220kV FEEDER - CORDUFF 220-WOODLAND 220-1 | Unknown | Unknown | 5 | Planned | November | November
TO-25-220 kV A1 @ MAY-01 | BUSBAR SECTION - MAYNOOTH 220-MAYNOOTH 220-220A1 | Unknown | Unknown |  | Planned | November | November
TO-25-220 kV B1 @ MAY-01 | BUSBAR SECTION - MAYNOOTH 220-MAYNOOTH 220-220B1 | Unknown | Unknown |  | Planned | November | November
TO-25-NW-PB-1-01 | 220kV FEEDER - NORTH WALL 220-POOLBEG 220-1 | Unknown | Unknown | 10 | Planned | November | November
TO-25-220 kV A3 @ BLC-01 | BUSBAR SECTION - BELCAMP 220-BELCAMP 220-220A3 | Unknown | Unknown | 2 | Planned | November | November
TO-25-BLC-220K3-01 | COUPLER/SECTIONALISING CB - BELCAMP 220-BELCAMP 220-220K3 | Unknown | Unknown | 2 | Planned | November | November
TO-25-BLC-220SA1-3CB-01 | COUPLER/SECTIONALISING CB - BELCAMP 220-BELCAMP 220-220SA1-3CB | Unknown | Unknown | 2 | Planned | November | November
TO-25-BLC-FIN-1-02 | 220kV FEEDER - BELCAMP 220-FINGLAS 220-1 | Unknown | Unknown | 2 | Planned | November | November
TO-25-DSN-MAY-2-02 | 220kV FEEDER - DUNSTOWN 220-MAYNOOTH 220-2 | Unknown | Unknown | 5 | Planned | December | December

## GEN_Cork
Outage ID | Feeder ID | Calendar Day Duration | Working Day Duration | Work Days | Outage Status | Start | Finish
TO-25-CHA-MAL-1-03 | 110kV FEEDER - CHARLEVILLE 110-MALLOW 110-1 | 4 | 4 | 4 | Scheduled | 07/01/2025 | 10/01/2025
TO-25-COW-110SA1-01 | SECTIONALISING DISCONNECT - COW CROSS 110-COW CROSS 110-110SA1 | 10 | 8 | 8 | Scheduled | 14/01/2025 | 23/01/2025
TO-25-COW-110SA2-01 | SECTIONALISING DISCONNECT - COW CROSS 110-COW CROSS 110-110SA2 | 10 | 8 | 8 | Scheduled | 14/01/2025 | 23/01/2025
TO-25-COW-OLD-2-01 | 110kV FEEDER - COW CROSS 110-OLDCOURT 110-2 | 10 | 8 | 8 | Reference | 14/01/2025 | 23/01/2025
TO-25-COW-RAF-1-01 | 110kV FEEDER - COW CROSS 110-RAFFEEN 110-1 | 10 | 8 | 8 | Scheduled | 14/01/2025 | 23/01/2025
TO-25-COW-T141-01 | DISTRIBUTION TRANSFORMER - COW CROSS 110-COW CROSS 38-T141 | 10 | 8 | 8 | Reference | 14/01/2025 | 23/01/2025
TO-25-OLD-T102-01 | DISTRIBUTION TRANSFORMER - OLDCOURT 110-OLDCOURT 10-T102 | 10 | 8 | 8 | Reference | 14/01/2025 | 23/01/2025
TO-25-BAR-T141-01 | DISTRIBUTION TRANSFORMER - BARRYMORE 110-BARRYMORE 38-T141 | 3 | 3 | 3 | Reference | 10/02/2025 | 12/02/2025
TO-25-BAR,T-BAR-1-01 | 110kV FEEDER - BARRYMORE tee-BARRYMORE 110-1 | 3 | 3 | 3 | Scheduled | 10/02/2025 | 12/02/2025
TO-25-BAR,T-CAH-1-01 | 110kV FEEDER - BARRYMORE tee-CAHIR 110-1 | 19 | 15 | 15 | Scheduled | 10/02/2025 | 28/02/2025
TO-25-BAR,T-KRA-1-02 | 110kV FEEDER - BARRYMORE tee-KNOCKRAHA 110-1 | 3 | 3 | 3 | Scheduled | 10/02/2025 | 12/02/2025
TO-25-CVW-COW-1-01 | 110kV FEEDER - CASTLEVIEW 110-COW CROSS 110-1 | 16 | 12 | 12 | Scheduled | 18/02/2025 | 05/03/2025
TO-25-COW-110SA1-02 | SECTIONALISING DISCONNECT - COW CROSS 110-COW CROSS 110-110SA1 | 16 | 12 | 12 | Scheduled | 18/02/2025 | 05/03/2025
TO-25-COW-110SA2-02 | SECTIONALISING DISCONNECT - COW CROSS 110-COW CROSS 110-110SA2 | 16 | 12 | 12 | Scheduled | 18/02/2025 | 05/03/2025
TO-25-COW-OLD-1-01 | 110kV FEEDER - COW CROSS 110-OLDCOURT 110-1 | 16 | 12 | 12 | Reference | 18/02/2025 | 05/03/2025
TO-25-COW-WHI-1-01 | 110kV FEEDER - COW CROSS 110-WHITEGATE 110-1 | 16 | 12 |  | Scheduled | 18/02/2025 | 05/03/2025
TO-25-OLD-T101-01 | DISTRIBUTION TRANSFORMER - OLDCOURT 110-OLDCOURT 10-T101 | 16 | 12 | 12 | Reference | 18/02/2025 | 05/03/2025
TO-25-BAR-T141-03 | DISTRIBUTION TRANSFORMER - BARRYMORE 110-BARRYMORE 38-T141 | 5 | 5 | 5 | Reference | 24/02/2025 | 28/02/2025
TO-25-BAR,T-BAR-1-03 | 110kV FEEDER - BARRYMORE tee-BARRYMORE 110-1 | 5 | 5 | 5 | Scheduled | 24/02/2025 | 28/02/2025
TO-25-BAR,T-KRA-1-01 | 110kV FEEDER - BARRYMORE tee-KNOCKRAHA 110-1 | 19 | 15 | 15 | Scheduled | 24/02/2025 | 14/03/2025
TO-25-CLA-DMY-1-01 | 110kV FEEDER - CLASHAVOON 110-DUNMANWAY 110-1 | 5 | 5 |  | Scheduled | 24/02/2025 | 28/02/2025
TO-25-110 kV A1 @ KRA-01 | BUSBAR SECTION - KNOCKRAHA 110-KNOCKRAHA 110-110A1 | 19 | 15 | 15 | Scheduled | 24/02/2025 | 14/03/2025
TO-25-110 kV B1 @ KRA-01 | BUSBAR SECTION - KNOCKRAHA 110-KNOCKRAHA 110-110B1 | 19 | 15 | 15 | Scheduled | 24/02/2025 | 14/03/2025
TO-25-110 kV A1 @ CLA-01 | BUSBAR SECTION - CLASHAVOON 110-CLASHAVOON 110-110A1 | 13 | 10 |  | Proposed | 03/03/2025 | 15/03/2025
TO-25-110 kV B1 @ CLA-01 | BUSBAR SECTION - CLASHAVOON 110-CLASHAVOON 110-110B1 | 13 | 10 |  | Proposed | 03/03/2025 | 15/03/2025
TO-25-CVW-COW-1-04 | 110kV FEEDER - CASTLEVIEW 110-COW CROSS 110-1 | 1 | 1 | 1 | Proposed | 04/03/2025 | 04/03/2025
TO-25-KLN-KRA-1-03 | 220kV FEEDER - KILLONAN 220-KNOCKRAHA 220-1 | 4 | 4 | 4 | Scheduled | 11/03/2025 | 14/03/2025
TO-25-LYT-T132-01 | GENERATOR TRANSFORMER - LYSAGHTSTOWN 110-LYSAGHTSTOWN 33-T132 | 1 | 1 | 1 | Proposed | 11/03/2025 | 11/03/2025
TO-25-BAR-T141-04 | DISTRIBUTION TRANSFORMER - BARRYMORE 110-BARRYMORE 38-T141 | 3 | 3 | 3 | Reference | 12/03/2025 | 14/03/2025
TO-25-BAR,T-BAR-1-04 | 110kV FEEDER - BARRYMORE tee-BARRYMORE 110-1 | 3 | 3 | 3 | Scheduled | 12/03/2025 | 14/03/2025
TO-25-BAR,T-CAH-1-03 | 110kV FEEDER - BARRYMORE tee-CAHIR 110-1 | 3 | 3 | 3 | Scheduled | 12/03/2025 | 14/03/2025
TO-25-CLA-110K1-2-01 | COUPLER/SECTIONALISING CB - CLASHAVOON 110-CLASHAVOON 110-110K1-2 | 44 | 30 |  | Proposed | 18/03/2025 | 30/04/2025
TO-25-KBY-MR-1-01 | 110kV FEEDER - KILBARRY 110-MARINA 110-1 | 189 | 130 | 130 | Scheduled | 18/03/2025 | 22/09/2025
TO-25-KBY-MR-1-03 | 110kV FEEDER - KILBARRY 110-MARINA 110-1 | 189 | 130 | 130 | Proposed | 18/03/2025 | 22/09/2025
TO-25-KBY-MR-2-01 | 110kV FEEDER - KILBARRY 110-MARINA 110-2 | 189 | 130 | 130 | Scheduled | 18/03/2025 | 22/09/2025
TO-25-KBY-MR-2-03 | 110kV FEEDER - KILBARRY 110-MARINA 110-2 | 189 | 130 | 130 | Proposed | 18/03/2025 | 22/09/2025
TO-25-KRA-WOH-1-03 | 110kV FEEDER - KNOCKRAHA 110-WOODHOUSE 110-1 | 3 | 3 | 3 | Proposed | 18/03/2025 | 20/03/2025
TO-25-AD-T2011/12-01 | GENERATOR TRANSFORMER - AGHADA 220-AGHADA G11/12-T2011/12 | 9 | 7 | 7 | Proposed | 24/03/2025 | 01/04/2025
TO-25-AD-T2011/12-02 | GENERATOR TRANSFORMER - AGHADA 220-AGHADA G11/12-T2011/12 | 9 | 7 | 7 | Proposed | 24/03/2025 | 01/04/2025
TO-25-220 kV A4 @ KRA-01 | BUSBAR SECTION - KNOCKRAHA 220-KNOCKRAHA 220-220A4 | 75 | 51 | 51 | Proposed | 24/03/2025 | 06/06/2025
TO-25-220 kV B4 @ KRA-01 | BUSBAR SECTION - KNOCKRAHA 220-KNOCKRAHA 220-220B4 | 75 | 51 | 51 | Proposed | 24/03/2025 | 06/06/2025
TO-25-KRA-220K4-01 | COUPLER/SECTIONALISING CB - KNOCKRAHA 220-KNOCKRAHA 220-220K4 | 75 | 51 | 51 | Proposed | 24/03/2025 | 06/06/2025
TO-25-KRA-220K4-02 | COUPLER/SECTIONALISING CB - KNOCKRAHA 220-KNOCKRAHA 220-220K4 | 75 | 51 | 51 | Proposed | 24/03/2025 | 06/06/2025
TO-25-KRA-220SA2-4CB-02 | COUPLER/SECTIONALISING CB - KNOCKRAHA 220-KNOCKRAHA 220-220SA2-4CB | 75 | 51 | 51 | Proposed | 24/03/2025 | 06/06/2025
TO-25-KRA-220SB2-4CB-02 | COUPLER/SECTIONALISING CB - KNOCKRAHA 220-KNOCKRAHA 220-220SB2-4CB | 75 | 51 | 51 | Proposed | 24/03/2025 | 06/06/2025
TO-25-AD-T2014-01 | GENERATOR TRANSFORMER - AGHADA 220-AGHADA G14-T2014 | 8 | 6 | 6 | Proposed | 01/04/2025 | 08/04/2025
TO-25-AD-T2014-02 | GENERATOR TRANSFORMER - AGHADA 220-AGHADA G14-T2014 | 8 | 6 | 6 | Proposed | 01/04/2025 | 08/04/2025
TO-25-AD-ST101-01 | GENERATOR TRANSFORMER - AGHADA 110-AGHADA 10-ST101 | 8 | 6 | 6 | Proposed | 07/04/2025 | 14/04/2025
TO-25-AD-T2102-01 | TRANSFORMER - AGHADA 220-AGHADA 110-T2102 | 16 | 10 | 10 | Proposed | 07/04/2025 | 22/04/2025
TO-25-AD-WHI-1-01 | 110kV FEEDER - AGHADA 110-WHITEGATE 110-1 | 8 | 6 |  | Proposed | 07/04/2025 | 14/04/2025
TO-25-110 kV A2 @ RAF-01 | BUSBAR SECTION - RAFFEEN 110-RAFFEEN 110-110A2 | Unknown | Unknown |  | Planned | April | August
TO-25-110 kV B2 @ RAF-01 | BUSBAR SECTION - RAFFEEN 110-RAFFEEN 110-110B2 | Unknown | Unknown |  | Planned | April | August
TO-25-CD-T103-02 | GENERATOR TRANSFORMER - CARRIGADROHID 110-CARRIGADROHID G3-T103 | 6 | 4 | 4 | Proposed | 24/04/2025 | 29/04/2025
TO-25-CD-KBY-1-02 | 110kV FEEDER - CARRIGADROHID 110-KILBARRY 110-1 | Unknown | Unknown | 10 | Planned | May | May
TO-25-CD-KBY-1-01 | 110kV FEEDER - CARRIGADROHID 110-KILBARRY 110-1 | Unknown | Unknown |  | Planned | May | May
TO-25-CD-MAC-1-01 | 110kV FEEDER - CARRIGADROHID 110-MACROOM 110-1 | Unknown | Unknown | 45 | Planned | May | July
TO-25-CD-T103-01 | GENERATOR TRANSFORMER - CARRIGADROHID 110-CARRIGADROHID G3-T103 | Unknown | Unknown |  | Planned | May | May
TO-25-CGG-DMY-1-01 | 110kV FEEDER - CARRIGDANGAN 110-DUNMANWAY 110-1 | Unknown | Unknown | 7 | Planned | May | May
TO-25-CGG-T131-01 | GENERATOR TRANSFORMER - CARRIGDANGAN 110-CARRIGDANGAN 33-T131 | Unknown | Unknown | 7 | Planned | May | May
TO-25-BGH-110SA1-01 | SECTIONALISING DISCONNECT - BOGGERAGH 110-BOGGERAGH 110-110SA1 | Unknown | Unknown | 10 | Planned | May | May
TO-25-BGH-110SA2-01 | SECTIONALISING DISCONNECT - BOGGERAGH 110-BOGGERAGH 110-110SA2 | Unknown | Unknown | 10 | Planned | May | May
TO-25-BGH-CLA-1-01 | 110kV FEEDER - BOGGERAGH 110-CLASHAVOON 110-1 | Unknown | Unknown | 10 | Planned | May | May
TO-25-BGH-T121-02 | GENERATOR TRANSFORMER - BOGGERAGH 110-BOGGERAGH 20-T121 | Unknown | Unknown | 10 | Planned | May | May
TO-25-BGH-T132-01 | GENERATOR TRANSFORMER - BOGGERAGH 110-BOGGERAGH 33-T132 | Unknown | Unknown | 10 | Planned | May | May
TO-25-BGH-T142-01 | DISTRIBUTION TRANSFORMER - BOGGERAGH 110-BOGGERAGH 38-T142 | Unknown | Unknown | 10 | Reference (Planned) | May | May
TO-25-IA-T101-02 | GENERATOR TRANSFORMER - INNISCARRA 110-INNISCARRA G1-T101 | Unknown | Unknown | 4 | Planned | June | June
TO-25-BAN-110SA1-03 | SECTIONALISING DISCONNECT - BANDON 110-BANDON 110-110SA1 | Unknown | Unknown | 10 | Planned | July | July
TO-25-BAN-110SA2-03 | SECTIONALISING DISCONNECT - BANDON 110-BANDON 110-110SA2 | Unknown | Unknown | 10 | Planned | July | July
TO-25-BAN-BRI-2-01 | 110kV FEEDER - BANDON 110-BRINNY 110-2 | Unknown | Unknown | 10 | Planned | July | July
TO-25-BAN-BRI-2-02 | 110kV FEEDER - BANDON 110-BRINNY 110-2 | Unknown | Unknown | 10 | Planned | July | July
TO-25-BAN-CAP1-01 | CAPACITOR/SVC/REACTOR - BANDON 110-BANDON 110-CAP1 | Unknown | Unknown | 15 | Planned | July | July
TO-25-BAN-RAF-1-02 | 110kV FEEDER - BANDON 110-RAFFEEN 110-1 | Unknown | Unknown | 10 | Planned | July | July
TO-25-BAN-T142-01 | DISTRIBUTION TRANSFORMER - BANDON 110-BANDON 38-T142 | Unknown | Unknown | 10 | Reference (Planned) | July | July
TO-25-BRI-T102-01 | TSO CUSTOMER TRANSFORMER - BRINNY 110-BRINNY 10-T102 | Unknown | Unknown | 10 | Planned | July | July
TO-25-BRI-T102-02 | TSO CUSTOMER TRANSFORMER - BRINNY 110-BRINNY 10-T102 | Unknown | Unknown | 10 | Planned | July | July
TO-25-BAN-110SA1-01 | SECTIONALISING DISCONNECT - BANDON 110-BANDON 110-110SA1 | Unknown | Unknown | 5 | Planned | July | July
TO-25-BAN-110SA1-02 | SECTIONALISING DISCONNECT - BANDON 110-BANDON 110-110SA1 | Unknown | Unknown | 10 | Planned | July | August
TO-25-BAN-110SA2-01 | SECTIONALISING DISCONNECT - BANDON 110-BANDON 110-110SA2 | Unknown | Unknown | 5 | Planned | July | July
TO-25-BAN-110SA2-02 | SECTIONALISING DISCONNECT - BANDON 110-BANDON 110-110SA2 | Unknown | Unknown | 10 | Planned | July | August
TO-25-BAN-BRI-1-01 | 110kV FEEDER - BANDON 110-BRINNY 110-1 | Unknown | Unknown | 5 | Planned | July | July
TO-25-BAN-BRI-1-02 | 110kV FEEDER - BANDON 110-BRINNY 110-1 | Unknown | Unknown | 10 | Planned | July | August
TO-25-BAN-CAP1-02 | CAPACITOR/SVC/REACTOR - BANDON 110-BANDON 110-CAP1 | Unknown | Unknown | 10 | Planned | July | August
TO-25-BAN-DMY-1-02 | 110kV FEEDER - BANDON 110-DUNMANWAY 110-1 | Unknown | Unknown | 5 | Planned | July | July
TO-25-BAN-DMY-1-03 | 110kV FEEDER - BANDON 110-DUNMANWAY 110-1 | Unknown | Unknown | 10 | Planned | July | August
TO-25-BAN-T101-01 | DISTRIBUTION TRANSFORMER - BANDON 110-BANDON 10-T101 | Unknown | Unknown | 5 | Reference (Planned) | July | July
TO-25-BAN-T101-02 | DISTRIBUTION TRANSFORMER - BANDON 110-BANDON 10-T101 | Unknown | Unknown | 10 | Reference (Planned) | July | August
TO-25-BAN-T141-01 | DISTRIBUTION TRANSFORMER - BANDON 110-BANDON 38-T141 | Unknown | Unknown | 5 | Reference (Planned) | July | July
TO-25-BAN-T141-02 | DISTRIBUTION TRANSFORMER - BANDON 110-BANDON 38-T141 | Unknown | Unknown | 10 | Reference (Planned) | July | August
TO-25-BRI-T101-01 | TSO CUSTOMER TRANSFORMER - BRINNY 110-BRINNY 10-T101 | Unknown | Unknown | 5 | Planned | July | July
TO-25-BRI-T101-02 | TSO CUSTOMER TRANSFORMER - BRINNY 110-BRINNY 10-T101 | Unknown | Unknown | 10 | Planned | July | August
TO-25-CHA-MAL-1-01 | 110kV FEEDER - CHARLEVILLE 110-MALLOW 110-1 | Unknown | Unknown | 13 | Planned | August | September
TO-25-WHI-CKB-T101-01 | TSO CUSTOMER TRANSFORMER - WHITEGATE 110-WHITEGATE 10-CKB-T101 | Unknown | Unknown | 5 | Planned | September | September
TO-25-GGO-T2001-01 | GENERATOR TRANSFORMER - GLANAGOW 220-GLANAGOW G1-T2001 | Unknown | Unknown | 4 | Planned | September | September
TO-25-110 kV A1 @ RAF-02 | BUSBAR SECTION - RAFFEEN 110-RAFFEEN 110-110A1 | Unknown | Unknown | 3 | Planned | September | September
TO-25-110 kV B1 @ RAF-02 | BUSBAR SECTION - RAFFEEN 110-RAFFEEN 110-110B1 | Unknown | Unknown | 3 | Planned | September | September
TO-25-110 kV A2 @ KRA-01 | BUSBAR SECTION - KNOCKRAHA 110-KNOCKRAHA 110-110A2 | Unknown | Unknown | 60 | Planned | September | November
TO-25-110 kV B2 @ KRA-01 | BUSBAR SECTION - KNOCKRAHA 110-KNOCKRAHA 110-110B2 | Unknown | Unknown | 60 | Planned | September | November
TO-25-WHI-CKB-T102-01 | TSO CUSTOMER TRANSFORMER - WHITEGATE 110-WHITEGATE 10-CKB-T102 | Unknown | Unknown | 5 | Planned | September | September
TO-25-CLA-KRA-1-01 | 220kV FEEDER - CLASHAVOON 220-KNOCKRAHA 220-1 | Unknown | Unknown | 7 | Planned | September | September
TO-25-220 kV A1 @ KRA-01 | BUSBAR SECTION - KNOCKRAHA 220-KNOCKRAHA 220-220A1 | Unknown | Unknown | 7 | Planned | September | September
TO-25-220 kV B1 @ KRA-01 | BUSBAR SECTION - KNOCKRAHA 220-KNOCKRAHA 220-220B1 | Unknown | Unknown | 7 | Planned | September | September
TO-25-KRA-220K1-01 | COUPLER/SECTIONALISING CB - KNOCKRAHA 220-KNOCKRAHA 220-220K1 | Unknown | Unknown | 7 | Planned | September | September
TO-25-KRA-220SA1-2CB-01 | COUPLER/SECTIONALISING CB - KNOCKRAHA 220-KNOCKRAHA 220-220SA1-2CB | Unknown | Unknown | 7 | Planned | September | September
TO-25-KRA-220SB1-2CB-01 | COUPLER/SECTIONALISING CB - KNOCKRAHA 220-KNOCKRAHA 220-220SB1-2CB | Unknown | Unknown | 7 | Planned | September | September
TO-25-KRA-T2101-01 | TRANSFORMER - KNOCKRAHA 220-KNOCKRAHA 110-T2101 | Unknown | Unknown | 7 | Planned | September | September
TO-25-AD-HWL-1-01 | 220kV FEEDER - AGHADA 220-HADWELL 220-1 | Unknown | Unknown | 2 | Planned | September | September
TO-25-AD-KRA-1-01 | 220kV FEEDER - AGHADA 220-KNOCKRAHA 220-1 | Unknown | Unknown | 15 | Planned | September | October
TO-25-AD-KRA-1-03 | 220kV FEEDER - AGHADA 220-KNOCKRAHA 220-1 | Unknown | Unknown | 15 | Planned | September | October
TO-25-AD-KRA-2-01 | 220kV FEEDER - AGHADA 220-KNOCKRAHA 220-2 | Unknown | Unknown | 15 | Planned | September | October
TO-25-AD-KRA-2-03 | 220kV FEEDER - AGHADA 220-KNOCKRAHA 220-2 | Unknown | Unknown | 15 | Planned | September | October
TO-25-220 kV A1 @ KRA-02 | BUSBAR SECTION - KNOCKRAHA 220-KNOCKRAHA 220-220A1 | Unknown | Unknown | 15 | Planned | September | October
TO-25-220 kV A2 @ KRA-01 | BUSBAR SECTION - KNOCKRAHA 220-KNOCKRAHA 220-220A2 | Unknown | Unknown | 15 | Planned | September | October
TO-25-220 kV B1 @ KRA-02 | BUSBAR SECTION - KNOCKRAHA 220-KNOCKRAHA 220-220B1 | Unknown | Unknown | 15 | Planned | September | October
TO-25-220 kV B2 @ KRA-01 | BUSBAR SECTION - KNOCKRAHA 220-KNOCKRAHA 220-220B2 | Unknown | Unknown | 15 | Planned | September | October
TO-25-KRA-220K1-02 | COUPLER/SECTIONALISING CB - KNOCKRAHA 220-KNOCKRAHA 220-220K1 | Unknown | Unknown | 15 | Planned | September | October
TO-25-KRA-220SA1-2CB-02 | COUPLER/SECTIONALISING CB - KNOCKRAHA 220-KNOCKRAHA 220-220SA1-2CB | Unknown | Unknown | 15 | Planned | September | October
TO-25-KRA-220SA1-2CB-03 | COUPLER/SECTIONALISING CB - KNOCKRAHA 220-KNOCKRAHA 220-220SA1-2CB | Unknown | Unknown | 15 | Planned | September | October
TO-25-KRA-220SA2-4CB-01 | COUPLER/SECTIONALISING CB - KNOCKRAHA 220-KNOCKRAHA 220-220SA2-4CB | Unknown | Unknown | 15 | Planned | September | October
TO-25-KRA-220SB1-2CB-02 | COUPLER/SECTIONALISING CB - KNOCKRAHA 220-KNOCKRAHA 220-220SB1-2CB | Unknown | Unknown | 15 | Planned | September | October
TO-25-KRA-220SB1-2CB-03 | COUPLER/SECTIONALISING CB - KNOCKRAHA 220-KNOCKRAHA 220-220SB1-2CB | Unknown | Unknown | 15 | Planned | September | October
TO-25-KRA-220SB2-4CB-01 | COUPLER/SECTIONALISING CB - KNOCKRAHA 220-KNOCKRAHA 220-220SB2-4CB | Unknown | Unknown | 15 | Planned | September | October
TO-25-KRA-T2102-01 | TRANSFORMER - KNOCKRAHA 220-KNOCKRAHA 110-T2102 | Unknown | Unknown | 15 | Planned | September | October
TO-25-AD-KRA-1-02 | 220kV FEEDER - AGHADA 220-KNOCKRAHA 220-1 | Unknown | Unknown | 10 | Planned | September | October
TO-25-AD-KRA-2-02 | 220kV FEEDER - AGHADA 220-KNOCKRAHA 220-2 | Unknown | Unknown | 10 | Planned | September | October
TO-25-KBY-MR-1-02 | 110kV FEEDER - KILBARRY 110-MARINA 110-1 | Unknown | Unknown | 35 | Planned | October | December
TO-25-KBY-MR-2-02 | 110kV FEEDER - KILBARRY 110-MARINA 110-2 | Unknown | Unknown | 35 | Planned | October | December
TO-25-110 kV A2 @ KRA-02 | BUSBAR SECTION - KNOCKRAHA 110-KNOCKRAHA 110-110A2 | Unknown | Unknown | 10 | Planned | November | November
TO-25-110 kV B2 @ KRA-02 | BUSBAR SECTION - KNOCKRAHA 110-KNOCKRAHA 110-110B2 | Unknown | Unknown | 10 | Planned | November | November
TO-25-KRA-WOH-1-01 | 110kV FEEDER - KNOCKRAHA 110-WOODHOUSE 110-1 | Unknown | Unknown |  | Planned | November | November
TO-25-KRA-WOH-1-02 | 110kV FEEDER - KNOCKRAHA 110-WOODHOUSE 110-1 | Unknown | Unknown | 10 | Planned | November | November
TO-25-CHA-MAL-1-02 | 110kV FEEDER - CHARLEVILLE 110-MALLOW 110-1 | Unknown | Unknown | 5 | Planned | November | November