## GEN_ALL
Outage ID | Feeder ID | Calendar Day Duration | Working Day Duration | Work Days | Outage Status | Start | Finish
TO-25-DND-T121-01 | TSO CUSTOMER TRANSFORMER - DARNDALE 110-DARNDALE 20-T121 | 689 | 482 | 482 | Scheduled | 12/02/2024 | 31/12/2025
TO-25-GI-T141-01 | DISTRIBUTION TRANSFORMER - GREAT ISLAND 110-GREAT ISLAND 38-T141 | 639 | 446 | 446 | Reference | 02/04/2024 | 31/12/2025
TO-25-BAL-DRY-1-03 | 110kV FEEDER - BALTRASNA 110-DRYBRIDGE 110-1 | 283 | 201 | 201 | Scheduled | 13/05/2024 | 19/02/2025
TO-25-CUS-PLS-1-01 | 110kV FEEDER - CUSHALING 110-PORTLAOISE 110-1 | 222 | 151 | 151 | Scheduled | 11/12/2024 | 20/07/2025
TO-25-110 kV A2 @ PLS-01 | BUSBAR SECTION - PORTLAOISE 110-PORTLAOISE 110-110A2 | 128 | 89 |  | Scheduled | 11/12/2024 | 17/04/2025
TO-25-110 kV B2 @ PLS-01 | BUSBAR SECTION - PORTLAOISE 110-PORTLAOISE 110-110B2 | 128 | 89 |  | Scheduled | 11/12/2024 | 17/04/2025
TO-25-ARK-SHE-2-01 | 110kV FEEDER - ARKLOW 110-SHELTON ABBEY 110-2 | 15 | 10 | 10 | Scheduled | 23/12/2024 | 06/01/2025
TO-25-SHE-T102-01 | TSO CUSTOMER TRANSFORMER - SHELTON ABBEY 110-SHELTON ABBEY 10-T102 | 15 | 10 | 10 | Scheduled | 23/12/2024 | 06/01/2025
TO-25-KIN-T101-02 | TSO CUSTOMER TRANSFORMER - KINNEGAD 110-KINNEGAD 10-T101 | 26 | 18 | 18 | Scheduled | 03/01/2025 | 28/01/2025
TO-25-110 kV B2/B4 @ CDU-01 | BUSBAR SECTION - CORDUFF 110-CORDUFF 110-110B2-B4 | 8 | 6 | 6 | Scheduled | 06/01/2025 | 13/01/2025
TO-25-CDU-110SB2-4-01 | SECTIONALISING DISCONNECT - CORDUFF 110-CORDUFF 110-110SB2-4 | 8 | 6 | 6 | Scheduled | 06/01/2025 | 13/01/2025
TO-25-CDU-110SB2-4CB-04 | COUPLER/SECTIONALISING CB - CORDUFF 110-CORDUFF 110-110SB2-4CB | 8 | 6 | 6 | Scheduled | 06/01/2025 | 13/01/2025
TO-25-220 kV A2 @ SH-01 | BUSBAR SECTION - SHANNONBRIDGE 220-SHANNONBRIDGE 220-220A2 | 50 | 35 | 35 | Scheduled | 06/01/2025 | 24/02/2025
TO-25-220 kV B2 @ SH-01 | BUSBAR SECTION - SHANNONBRIDGE 220-SHANNONBRIDGE 220-220B2 | 50 | 35 | 35 | Scheduled | 06/01/2025 | 24/02/2025
TO-25-CHA-MAL-1-03 | 110kV FEEDER - CHARLEVILLE 110-MALLOW 110-1 | 4 | 4 | 4 | Scheduled | 07/01/2025 | 10/01/2025
TO-25-FIN-220K1-04 | COUPLER/SECTIONALISING CB - FINGLAS 220-FINGLAS 220-220K1 | 2 | 2 | 2 | Scheduled | 08/01/2025 | 09/01/2025
TO-25-FIN-220K2-05 | COUPLER/SECTIONALISING CB - FINGLAS 220-FINGLAS 220-220K2 | 2 | 2 | 2 | Scheduled | 08/01/2025 | 09/01/2025
TO-25-FIN-220SA1-2CB-08 | COUPLER/SECTIONALISING CB - FINGLAS 220-FINGLAS 220-220SA1-2CB | 2 | 2 | 2 | Scheduled | 08/01/2025 | 09/01/2025
TO-25-GI GIS-220K1-01 | COUPLER/SECTIONALISING CB - GREAT ISLAND GIS 220-GREAT ISLAND GIS 220-220K1 | 1 | 1 | 1 | Scheduled | 08/01/2025 | 08/01/2025
TO-25-AA GIS-DRU-1-01 | 110kV FEEDER - ARDNACRUSHA GIS 110-DRUMLINE 110-1 | 2 | 2 | 2 | Scheduled | 09/01/2025 | 10/01/2025
TO-25-CDU-T2102-02 | TRANSFORMER - CORDUFF 220-CORDUFF 110-T2102 | 1 | 1 | 1 | Scheduled | 13/01/2025 | 13/01/2025
TO-25-110 kV A2 @ LOU-05 | BUSBAR SECTION - LOUTH 110-LOUTH 110-110A2 | 12 | 10 | 10 | Scheduled | 13/01/2025 | 24/01/2025
TO-25-110 kV B2 @ LOU-05 | BUSBAR SECTION - LOUTH 110-LOUTH 110-110B2 | 12 | 10 | 10 | Scheduled | 13/01/2025 | 24/01/2025
TO-25-220 kV A2 @ LOU-07 | BUSBAR SECTION - LOUTH 220-LOUTH 220-220A2 | 12 | 10 | 10 | Scheduled | 13/01/2025 | 24/01/2025
TO-25-220 kV B2 @ LOU-06 | BUSBAR SECTION - LOUTH 220-LOUTH 220-220B2 | 12 | 10 | 10 | Scheduled | 13/01/2025 | 24/01/2025
TO-25-LOU-T2102-01 | TRANSFORMER - LOUTH 220-LOUTH 110-T2102 | 12 | 10 | 10 | Scheduled | 13/01/2025 | 24/01/2025
TO-25-220 kV B1 @ CBT-02 | BUSBAR SECTION - CASTLEBAGOT 220-CASTLEBAGOT 220-220B1 | 9 | 7 | 7 | Scheduled | 14/01/2025 | 22/01/2025
TO-25-220 kV B2 @ CBT-01 | BUSBAR SECTION - CASTLEBAGOT 220-CASTLEBAGOT 220-220B2 | 9 | 7 | 7 | Scheduled | 14/01/2025 | 22/01/2025
TO-25-CBT-220K1-04 | COUPLER/SECTIONALISING CB - CASTLEBAGOT 220-CASTLEBAGOT 220-220K1 | 9 | 7 | 7 | Scheduled | 14/01/2025 | 22/01/2025
TO-25-CBT-220K2-02 | COUPLER/SECTIONALISING CB - CASTLEBAGOT 220-CASTLEBAGOT 220-220K2 | 9 | 7 | 7 | Scheduled | 14/01/2025 | 22/01/2025
TO-25-CBT-220SB1-2CB-01 | COUPLER/SECTIONALISING CB - CASTLEBAGOT 220-CASTLEBAGOT 220-220SB1-2CB | 9 | 7 | 7 | Scheduled | 14/01/2025 | 22/01/2025
TO-25-COW-110SA1-01 | SECTIONALISING DISCONNECT - COW CROSS 110-COW CROSS 110-110SA1 | 10 | 8 | 8 | Scheduled | 14/01/2025 | 23/01/2025
TO-25-COW-110SA2-01 | SECTIONALISING DISCONNECT - COW CROSS 110-COW CROSS 110-110SA2 | 10 | 8 | 8 | Scheduled | 14/01/2025 | 23/01/2025
TO-25-COW-OLD-2-01 | 110kV FEEDER - COW CROSS 110-OLDCOURT 110-2 | 10 | 8 | 8 | Reference | 14/01/2025 | 23/01/2025
TO-25-COW-RAF-1-01 | 110kV FEEDER - COW CROSS 110-RAFFEEN 110-1 | 10 | 8 | 8 | Scheduled | 14/01/2025 | 23/01/2025
TO-25-COW-T141-01 | DISTRIBUTION TRANSFORMER - COW CROSS 110-COW CROSS 38-T141 | 10 | 8 | 8 | Reference | 14/01/2025 | 23/01/2025
TO-25-CUS-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - CUSHALING 110-CUSHALING 110-110SA1-2CB | 1 | 1 | 1 | Scheduled | 14/01/2025 | 14/01/2025
TO-25-CUS-KIR-1-01 | 110kV FEEDER - CUSHALING 110-KILCUMBER 110-1 | 1 | 1 | 1 | Scheduled | 14/01/2025 | 14/01/2025
TO-25-CUS-MLC-1-01 | 110kV FEEDER - CUSHALING 110-MOUNTLUCAS 110-1 | 1 | 1 | 1 | Scheduled | 14/01/2025 | 14/01/2025
TO-25-CUS-T101-01 | GENERATOR TRANSFORMER - CUSHALING 110-CUSHALING G1-T101 | 1 | 1 | 1 | Scheduled | 14/01/2025 | 14/01/2025
TO-25-KIR-T131-02 | GENERATOR TRANSFORMER - KILCUMBER 110-KILCUMBER 33-T131 | 1 | 1 | 1 | Scheduled | 14/01/2025 | 14/01/2025
TO-25-OLD-T102-01 | DISTRIBUTION TRANSFORMER - OLDCOURT 110-OLDCOURT 10-T102 | 10 | 8 | 8 | Reference | 14/01/2025 | 23/01/2025
TO-25-CSH-DLT-1-01 | 110kV FEEDER - CASHLA 110-DALTON 110-1 | 3 | 3 | 3 | Scheduled | 15/01/2025 | 17/01/2025
TO-25-GWE-T101-03 | TSO CUSTOMER TRANSFORMER - GORTAWEE 110-GORTAWEE 10-T101 | 16 | 12 | 12 | Scheduled | 15/01/2025 | 30/01/2025
TO-25-BNK-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - BARNAKYLE 110-BARNAKYLE 110-110SA1-2CB | 151 | 101 | 101 | Scheduled | 17/01/2025 | 16/06/2025
TO-25-BNK-CBT-2-01 | 110kV FEEDER - BARNAKYLE 110-CASTLEBAGOT 110-2 | 151 | 101 | 101 | Scheduled | 17/01/2025 | 16/06/2025
TO-25-BNK-T122-01 | TSO CUSTOMER TRANSFORMER - BARNAKYLE 110-BARNAKYLE 20-T122 | 151 | 101 | 101 | Scheduled | 17/01/2025 | 16/06/2025
TO-25-DSN-MAY-2-03 | 220kV FEEDER - DUNSTOWN 220-MAYNOOTH 220-2 | 11 | 9 |  | Scheduled | 20/01/2025 | 30/01/2025
TO-25-KPG-110K4-01 | COUPLER/SECTIONALISING CB - KILPADDOGE 110-KILPADDOGE 110-110K4 | 1 | 1 |  | Scheduled | 21/01/2025 | 21/01/2025
TO-25-INC-PB-1-01 | 220kV FEEDER - INCHICORE 220-POOLBEG 220-1 | 43 | 30 | 30 | Scheduled | 27/01/2025 | 10/03/2025
TO-25-220 kV A2 @ KLN-01 | BUSBAR SECTION - KILLONAN 220-KILLONAN 220-220A2 | 5 | 5 | 5 | Scheduled | 27/01/2025 | 31/01/2025
TO-25-220 kV B2 @ KLN-01 | BUSBAR SECTION - KILLONAN 220-KILLONAN 220-220B2 | 5 | 5 | 5 | Scheduled | 27/01/2025 | 31/01/2025
TO-25-KLN-KPG-1-01 | 220kV FEEDER - KILLONAN 220-KILPADDOGE 220-1 | 43 | 30 | 30 | Scheduled | 27/01/2025 | 10/03/2025
TO-25-220 kV A2 @ TB-01 | BUSBAR SECTION - TARBERT 220-TARBERT 220-220A2 | 15 | 10 | 10 | Scheduled | 27/01/2025 | 10/02/2025
TO-25-220 kV B2 @ TB-01 | BUSBAR SECTION - TARBERT 220-TARBERT 220-220B2 | 15 | 10 | 10 | Scheduled | 27/01/2025 | 10/02/2025
TO-25-LOU-T2101-03 | TRANSFORMER - LOUTH 220-LOUTH 110-T2101 | 16 | 11 | 11 | Scheduled | 29/01/2025 | 13/02/2025
TO-25-CHA-KLN-1-01 | 110kV FEEDER - CHARLEVILLE 110-KILLONAN 110-1 | 43 | 30 | 30 | Scheduled | 04/02/2025 | 18/03/2025
TO-25-220 kV A2 @ FIN-05 | BUSBAR SECTION - FINGLAS 220-FINGLAS 220-220A2 | 11 | 9 | 9 | Scheduled | 04/02/2025 | 14/02/2025
TO-25-FIN-220K2-08 | COUPLER/SECTIONALISING CB - FINGLAS 220-FINGLAS 220-220K2 | 11 | 9 | 9 | Scheduled | 04/02/2025 | 14/02/2025
TO-25-FIN-220SA1-2CB-09 | COUPLER/SECTIONALISING CB - FINGLAS 220-FINGLAS 220-220SA1-2CB | 11 | 9 | 9 | Scheduled | 04/02/2025 | 14/02/2025
TO-25-FIN-SHL-1-01 | 220kV FEEDER - FINGLAS 220-SHELLYBANKS 220-1 | 25 | 19 | 19 | Scheduled | 04/02/2025 | 28/02/2025
TO-25-SHL-T2016-01 | GENERATOR TRANSFORMER - SHELLYBANKS 220-SHELLYBANKS G6-T2016 | 1 | 1 | 1 | Scheduled | 04/02/2025 | 04/02/2025
TO-25-RRU-SKL-1-01 | 110kV FEEDER - RATRUSSAN 110-SHANKILL 110-1 | 80 | 55 | 55 | Scheduled | 05/02/2025 | 25/04/2025
TO-25-BAR-T141-01 | DISTRIBUTION TRANSFORMER - BARRYMORE 110-BARRYMORE 38-T141 | 3 | 3 | 3 | Reference | 10/02/2025 | 12/02/2025
TO-25-BAR,T-BAR-1-01 | 110kV FEEDER - BARRYMORE tee-BARRYMORE 110-1 | 3 | 3 | 3 | Scheduled | 10/02/2025 | 12/02/2025
TO-25-BAR,T-CAH-1-01 | 110kV FEEDER - BARRYMORE tee-CAHIR 110-1 | 19 | 15 | 15 | Scheduled | 10/02/2025 | 28/02/2025
TO-25-BAR,T-CAH-1-02 | 110kV FEEDER - BARRYMORE tee-CAHIR 110-1 | 19 | 15 | 15 | Proposed | 10/02/2025 | 28/02/2025
TO-25-BAR,T-KRA-1-02 | 110kV FEEDER - BARRYMORE tee-KNOCKRAHA 110-1 | 3 | 3 | 3 | Scheduled | 10/02/2025 | 12/02/2025
TO-25-110 kV A4 @ CDU-02 | BUSBAR SECTION - CORDUFF 110-CORDUFF 110-110A4 | 5 | 5 |  | Scheduled | 10/02/2025 | 14/02/2025
TO-25-110 kV B2 @ CDU-02 | BUSBAR SECTION - CORDUFF 110-CORDUFF 110-110B2 | 5 | 5 |  | Scheduled | 10/02/2025 | 14/02/2025
TO-25-110 kV B4 @ CDU-02 | BUSBAR SECTION - CORDUFF 110-CORDUFF 110-110B4 | 5 | 5 |  | Scheduled | 10/02/2025 | 14/02/2025
TO-25-220 kV A1 @ SH-03 | BUSBAR SECTION - SHANNONBRIDGE 220-SHANNONBRIDGE 220-220A1 | 68 | 48 | 48 | Scheduled | 10/02/2025 | 18/04/2025
TO-25-220 kV B1 @ SH-03 | BUSBAR SECTION - SHANNONBRIDGE 220-SHANNONBRIDGE 220-220B1 | 68 | 48 | 48 | Scheduled | 10/02/2025 | 18/04/2025
TO-25-SH-T2101-03 | TRANSFORMER - SHANNONBRIDGE 220-SHANNONBRIDGE 110-T2101 | 135 | 92 | 92 | Scheduled | 10/02/2025 | 24/06/2025
TO-25-AUN-CBT-1-01 | 110kV FEEDER - AUNGIERSTOWN 110-CASTLEBAGOT 110-1 | 2 | 2 | 2 | Scheduled | 11/02/2025 | 12/02/2025
TO-25-ROP-WEX-1-01 | 110kV FEEDER - ROSSPILE 110-WEXFORD 110-1 | 7 | 5 |  | Scheduled | 12/02/2025 | 18/02/2025
TO-25-WEX-110SA1-2CB-03 | COUPLER/SECTIONALISING CB - WEXFORD 110-WEXFORD 110-110SA1-2CB | 7 | 5 |  | Scheduled | 12/02/2025 | 18/02/2025
TO-25-WEX-T121-01 | DISTRIBUTION TRANSFORMER - WEXFORD 110-WEXFORD 20-T121 | 7 | 5 | 5 | Reference | 12/02/2025 | 18/02/2025
TO-25-WEX-T141-01 | DISTRIBUTION TRANSFORMER - WEXFORD 110-WEXFORD 38-T141 | 7 | 5 | 5 | Reference | 12/02/2025 | 18/02/2025
TO-25-AUN-T121-01 | TSO CUSTOMER TRANSFORMER - AUNGIERSTOWN 110-AUNGIERSTOWN 20-T121 | 2 | 2 | 2 | Scheduled | 13/02/2025 | 14/02/2025
TO-25-PLA-T105-03 | TSO CUSTOMER TRANSFORMER - PLATIN 110-PLATIN 10-T105 | 8 | 6 | 6 | Proposed | 14/02/2025 | 21/02/2025
TO-25-110 kV B2 @ CAH-01 | BUSBAR SECTION - CAHIR 110-CAHIR 110-110B2 | 12 | 10 | 10 | Scheduled | 17/02/2025 | 28/02/2025
TO-25-CSH-T2104-01 | TRANSFORMER - CASHLA 220-CASHLA 110-T2104 | 68 | 47 | 47 | Scheduled | 17/02/2025 | 25/04/2025
TO-25-CSH-T2104-04 | TRANSFORMER - CASHLA 220-CASHLA 110-T2104 | 61 | 43 | 43 | Proposed | 17/02/2025 | 18/04/2025
TO-25-DEN-DRY-1-03 | 110kV FEEDER - DEENES 110-DRYBRIDGE 110-1 | 3 | 3 | 3 | Scheduled | 17/02/2025 | 19/02/2025
TO-25-DRY-110SA1-02 | SECTIONALISING DISCONNECT - DRYBRIDGE 110-DRYBRIDGE 110-110SA1 | 3 | 3 | 3 | Scheduled | 17/02/2025 | 19/02/2025
TO-25-DRY-110SA2-02 | SECTIONALISING DISCONNECT - DRYBRIDGE 110-DRYBRIDGE 110-110SA2 | 3 | 3 | 3 | Scheduled | 17/02/2025 | 19/02/2025
TO-25-DRY-GOR-1-03 | 110kV FEEDER - DRYBRIDGE 110-GORMAN 110-1 | 3 | 3 | 3 | Scheduled | 17/02/2025 | 19/02/2025
TO-25-DRY-T142-02 | DISTRIBUTION TRANSFORMER - DRYBRIDGE 110-DRYBRIDGE 38-T142 | 3 | 3 | 3 | Reference | 17/02/2025 | 19/02/2025
TO-25-FLA-SLB-1-01 | 110kV FEEDER - FLAGFORD 110-SLIABH BAWN 110-1 | 12 | 10 | 10 | Scheduled | 17/02/2025 | 28/02/2025
TO-25-CVW-COW-1-01 | 110kV FEEDER - CASTLEVIEW 110-COW CROSS 110-1 | 16 | 12 | 12 | Scheduled | 18/02/2025 | 05/03/2025
TO-25-COW-110SA1-02 | SECTIONALISING DISCONNECT - COW CROSS 110-COW CROSS 110-110SA1 | 16 | 12 | 12 | Scheduled | 18/02/2025 | 05/03/2025
TO-25-COW-110SA2-02 | SECTIONALISING DISCONNECT - COW CROSS 110-COW CROSS 110-110SA2 | 16 | 12 | 12 | Scheduled | 18/02/2025 | 05/03/2025
TO-25-COW-OLD-1-01 | 110kV FEEDER - COW CROSS 110-OLDCOURT 110-1 | 16 | 12 | 12 | Reference | 18/02/2025 | 05/03/2025
TO-25-COW-WHI-1-01 | 110kV FEEDER - COW CROSS 110-WHITEGATE 110-1 | 16 | 12 |  | Scheduled | 18/02/2025 | 05/03/2025
TO-25-OLD-T101-01 | DISTRIBUTION TRANSFORMER - OLDCOURT 110-OLDCOURT 10-T101 | 16 | 12 | 12 | Reference | 18/02/2025 | 05/03/2025
TO-25-AUN-T123-01 | TSO CUSTOMER TRANSFORMER - AUNGIERSTOWN 110-AUNGIERSTOWN 20-T123 | 2 | 2 | 2 | Scheduled | 19/02/2025 | 20/02/2025
TO-25-110 kV B2 @ GI-02 | BUSBAR SECTION - GREAT ISLAND 110-GREAT ISLAND 110-110B2 | 10 | 8 | 8 | Scheduled | 19/02/2025 | 28/02/2025
TO-25-GI-ROP-1-01 | 110kV FEEDER - GREAT ISLAND 110-ROSSPILE 110-1 | 10 | 8 |  | Scheduled | 19/02/2025 | 28/02/2025
TO-25-AUN-KSG-1-01 | 110kV FEEDER - AUNGIERSTOWN 110-KISHOGE 110-1 | 4 | 2 | 2 | Scheduled | 21/02/2025 | 24/02/2025
TO-25-BAL-CDU-1-02 | 110kV FEEDER - BALTRASNA 110-CORDUFF 110-1 | 6 | 5 |  | Scheduled | 24/02/2025 | 01/03/2025
TO-25-BAR-T141-03 | DISTRIBUTION TRANSFORMER - BARRYMORE 110-BARRYMORE 38-T141 | 5 | 5 | 5 | Reference | 24/02/2025 | 28/02/2025
TO-25-BAR,T-BAR-1-03 | 110kV FEEDER - BARRYMORE tee-BARRYMORE 110-1 | 5 | 5 | 5 | Scheduled | 24/02/2025 | 28/02/2025
TO-25-BAR,T-KRA-1-01 | 110kV FEEDER - BARRYMORE tee-KNOCKRAHA 110-1 | 19 | 15 | 15 | Scheduled | 24/02/2025 | 14/03/2025
TO-25-CLA-DMY-1-01 | 110kV FEEDER - CLASHAVOON 110-DUNMANWAY 110-1 | 5 | 5 |  | Scheduled | 24/02/2025 | 28/02/2025
TO-25-110 kV A4 @ CDU-01 | BUSBAR SECTION - CORDUFF 110-CORDUFF 110-110A4 | 6 | 5 | 5 | Scheduled | 24/02/2025 | 01/03/2025
TO-25-110 kV B4 @ CDU-01 | BUSBAR SECTION - CORDUFF 110-CORDUFF 110-110B4 | 6 | 5 | 5 | Scheduled | 24/02/2025 | 01/03/2025
TO-25-CDU-110SA2-4CB-01 | COUPLER/SECTIONALISING CB - CORDUFF 110-CORDUFF 110-110SA2-4CB | 6 | 5 | 5 | Scheduled | 24/02/2025 | 01/03/2025
TO-25-CDU-110SB2-4CB-01 | COUPLER/SECTIONALISING CB - CORDUFF 110-CORDUFF 110-110SB2-4CB | 6 | 5 | 5 | Scheduled | 24/02/2025 | 01/03/2025
TO-25-110 kV B1 @ KRA-01 | BUSBAR SECTION - KNOCKRAHA 110-KNOCKRAHA 110-110B1 | 19 | 15 | 15 | Scheduled | 24/02/2025 | 14/03/2025
TO-25-110 kV B2 @ DEN-01 | BUSBAR SECTION - DEENES 110-DEENES 110-110B2 | 2 | 2 | 2 | Scheduled | 26/02/2025 | 27/02/2025
TO-25-DEN-110K2-02 | COUPLER/SECTIONALISING CB - DEENES 110-DEENES 110-110K2 | 2 | 2 | 2 | Scheduled | 26/02/2025 | 27/02/2025
TO-25-DEY-T134-01 | GENERATOR TRANSFORMER - DERRYCARNEY 110-DERRYCARNEY 33-T134 | 1 | 1 | 1 | Scheduled | 27/02/2025 | 27/02/2025
TO-25-110 kV B2 @ CSH-05 | BUSBAR SECTION - CASHLA 110-CASHLA 110-110B2 | 57 | 38 | 38 | Scheduled | 28/02/2025 | 25/04/2025
TO-25-220 kV A4 @ CSH-02 | BUSBAR SECTION - CASHLA 220-CASHLA 220-220A4 | 57 | 38 | 38 | Scheduled | 28/02/2025 | 25/04/2025
TO-25-220 kV B4 @ CSH-02 | BUSBAR SECTION - CASHLA 220-CASHLA 220-220B4 | 57 | 38 | 38 | Scheduled | 28/02/2025 | 25/04/2025
TO-25-ATH-110SA1-2CB-02 | COUPLER/SECTIONALISING CB - ATHLONE 110-ATHLONE 110-110SA1-2CB | 12 | 10 | 10 | Scheduled | 03/03/2025 | 14/03/2025
TO-25-ATH-SH-1-06 | 110kV FEEDER - ATHLONE 110-SHANNONBRIDGE 110-1 | 12 | 10 | 10 | Scheduled | 03/03/2025 | 14/03/2025
TO-25-CBT-CKG-1-02 | 110kV FEEDER - CASTLEBAGOT 110-CORKAGH 110-1 | 5 | 5 | 5 | Scheduled | 03/03/2025 | 07/03/2025
TO-25-110 kV B1 @ CLA-01 | BUSBAR SECTION - CLASHAVOON 110-CLASHAVOON 110-110B1 | 13 | 10 |  | Scheduled | 03/03/2025 | 15/03/2025
TO-25-CDU-GLN-1-01 | 110kV FEEDER - CORDUFF 110-GALLANSTOWN 110-1 | 12 | 10 | 10 | Scheduled | 03/03/2025 | 14/03/2025
TO-25-110 kV A3 @ CKG-02 | BUSBAR SECTION - CORKAGH 110-CORKAGH 110-110A3 | 5 | 5 | 5 | Scheduled | 03/03/2025 | 07/03/2025
TO-25-110 kV B3 @ CKG-02 | BUSBAR SECTION - CORKAGH 110-CORKAGH 110-110B3 | 5 | 5 | 5 | Scheduled | 03/03/2025 | 07/03/2025
TO-25-CKG-110K3-02 | COUPLER/SECTIONALISING CB - CORKAGH 110-CORKAGH 110-110K3 | 5 | 5 | 5 | Scheduled | 03/03/2025 | 07/03/2025
TO-25-CKG-110SA1-3CB-03 | COUPLER/SECTIONALISING CB - CORKAGH 110-CORKAGH 110-110SA1-3CB | 5 | 5 | 5 | Scheduled | 03/03/2025 | 07/03/2025
TO-25-CKG-110SB1-3CB-03 | COUPLER/SECTIONALISING CB - CORKAGH 110-CORKAGH 110-110SB1-3CB | 5 | 5 | 5 | Scheduled | 03/03/2025 | 07/03/2025
TO-25-FIN-220SB1-2CB-07 | COUPLER/SECTIONALISING CB - FINGLAS 220-FINGLAS 220-220SB1-2CB | 22 | 15 | 15 | Scheduled | 03/03/2025 | 24/03/2025
TO-25-FIN GIS-T2101-01 | TRANSFORMER - FINGLAS 220-FINGLAS GIS 110-T2101 | 22 | 15 | 15 | Scheduled | 03/03/2025 | 24/03/2025
TO-25-110 kV A3 @ KPG-01 | BUSBAR SECTION - KILPADDOGE 110-KILPADDOGE 110-110A3 | 5 | 5 | 5 | Scheduled | 03/03/2025 | 07/03/2025
TO-25-110 kV B3 @ KPG-01 | BUSBAR SECTION - KILPADDOGE 110-KILPADDOGE 110-110B3 | 5 | 5 | 5 | Scheduled | 03/03/2025 | 07/03/2025
TO-25-KPG-110K3-02 | COUPLER/SECTIONALISING CB - KILPADDOGE 110-KILPADDOGE 110-110K3 | 5 | 5 | 5 | Scheduled | 03/03/2025 | 07/03/2025
TO-25-KPG-110SA1-3CB-02 | COUPLER/SECTIONALISING CB - KILPADDOGE 110-KILPADDOGE 110-110SA1-3CB | 5 | 5 | 5 | Scheduled | 03/03/2025 | 07/03/2025
TO-25-KPG-110SB1-3CB-02 | COUPLER/SECTIONALISING CB - KILPADDOGE 110-KILPADDOGE 110-110SB1-3CB | 5 | 5 | 5 | Scheduled | 03/03/2025 | 07/03/2025
TO-25-BAG-T101-01 | TSO CUSTOMER TRANSFORMER - BARNAGEERAGH 110-BARNAGEERAGH 11-T101 | 4 | 4 | 4 | Scheduled | 04/03/2025 | 07/03/2025
TO-25-BLU-T131-02 | GENERATOR TRANSFORMER - BLUNDELSTOWN 110-BLUNDELSTOWN 33-T131 | 1 | 1 | 1 | Scheduled | 04/03/2025 | 04/03/2025
TO-25-BRI-T101-04 | TSO CUSTOMER TRANSFORMER - BRINNY 110-BRINNY 10-T101 | 4 | 4 | 4 | Scheduled | 04/03/2025 | 07/03/2025
TO-25-220 kV A2 @ KLN-02 | BUSBAR SECTION - KILLONAN 220-KILLONAN 220-220A2 | 7 | 5 | 5 | Scheduled | 04/03/2025 | 10/03/2025
TO-25-220 kV B2 @ KLN-02 | BUSBAR SECTION - KILLONAN 220-KILLONAN 220-220B2 | 7 | 5 | 5 | Scheduled | 04/03/2025 | 10/03/2025
TO-25-220 kV B2 @ LOU-08 | BUSBAR SECTION - LOUTH 220-LOUTH 220-220B2 | 7 | 5 | 5 | Scheduled | 05/03/2025 | 11/03/2025
TO-25-LOU-T2104-04 | TRANSFORMER - LOUTH 220-LOUTH 110-T2104 | 10 | 8 |  | Scheduled | 05/03/2025 | 14/03/2025
TO-25-BAG-T103-01 | TSO CUSTOMER TRANSFORMER - BARNAGEERAGH 110-BARNAGEERAGH 11-T103 | 5 | 5 | 5 | Scheduled | 10/03/2025 | 14/03/2025
TO-25-CBR-DLT-1-03 | 110kV FEEDER - CASTLEBAR 110-DALTON 110-1 | 5 | 5 | 5 | Scheduled | 10/03/2025 | 14/03/2025
TO-25-CLG-FIN GIS-1-02 | 110kV FEEDER - CLOGHRAN 110-FINGLAS GIS 110-1 | 15 | 10 | 10 | Scheduled | 10/03/2025 | 24/03/2025
TO-25-COL-FIN GIS-1-02 | 110kV FEEDER - COLLEGE PARK 110-FINGLAS GIS 110-1 | 15 | 10 | 10 | Scheduled | 10/03/2025 | 24/03/2025
TO-25-110 kV A5 @ FIN GIS-01 | BUSBAR SECTION - FINGLAS GIS 110-FINGLAS GIS 110-110A5 | 15 | 10 | 10 | Scheduled | 10/03/2025 | 24/03/2025
TO-25-110 kV B5 @ FIN GIS-01 | BUSBAR SECTION - FINGLAS GIS 110-FINGLAS GIS 110-110B5 | 15 | 10 | 10 | Scheduled | 10/03/2025 | 24/03/2025
TO-25-FIN GIS-110K5-02 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110K5 | 15 | 10 | 10 | Scheduled | 10/03/2025 | 24/03/2025
TO-25-FIN GIS-110SA3-5CB-03 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110SA3-5CB | 15 | 10 | 10 | Scheduled | 10/03/2025 | 24/03/2025
TO-25-FIN GIS-110SB3-5CB-02 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110SB3-5CB | 15 | 10 | 10 | Scheduled | 10/03/2025 | 24/03/2025
TO-25-BRI-T102-03 | TSO CUSTOMER TRANSFORMER - BRINNY 110-BRINNY 10-T102 | 4 | 4 | 4 | Scheduled | 11/03/2025 | 14/03/2025
TO-25-400 kV A1 @ DSN-01 | BUSBAR SECTION - DUNSTOWN 400-DUNSTOWN 400-400A1 | 38 | 27 | 27 | Scheduled | 11/03/2025 | 17/04/2025
TO-25-400 kV B1 @ DSN-01 | BUSBAR SECTION - DUNSTOWN 400-DUNSTOWN 400-400B1 | 38 | 27 | 27 | Scheduled | 11/03/2025 | 17/04/2025
TO-25-DSN-MP GIS-1-01 | 400kV FEEDER - DUNSTOWN 400-MONEYPOINT GIS 400-1 | 46 | 31 | 31 | Scheduled | 11/03/2025 | 25/04/2025
TO-25-INC-PB-2-02 | 220kV FEEDER - INCHICORE 220-POOLBEG 220-2 | 36 | 25 | 25 | Scheduled | 11/03/2025 | 15/04/2025
TO-25-KLN-KRA-1-04 | 220kV FEEDER - KILLONAN 220-KNOCKRAHA 220-1 | 4 | 4 | 4 | Scheduled | 11/03/2025 | 14/03/2025
TO-25-LYT-T132-01 | GENERATOR TRANSFORMER - LYSAGHTSTOWN 110-LYSAGHTSTOWN 33-T132 | 1 | 1 | 1 | Scheduled | 11/03/2025 | 11/03/2025
TO-25-400 kV A4 @ MP GIS-01 | BUSBAR SECTION - MONEYPOINT GIS 400-MONEYPOINT GIS 400-400A4 | 38 | 27 | 27 | Scheduled | 11/03/2025 | 17/04/2025
TO-25-400 kV B4 @ MP GIS-01 | BUSBAR SECTION - MONEYPOINT GIS 400-MONEYPOINT GIS 400-400B4 | 38 | 27 | 27 | Scheduled | 11/03/2025 | 17/04/2025
TO-25-MP GIS-400K4-01 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 400-MONEYPOINT GIS 400-400K4 | 38 | 27 | 27 | Scheduled | 11/03/2025 | 17/04/2025
TO-25-MP GIS-400SA2-4CB-01 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 400-MONEYPOINT GIS 400-400SA2-4CB | 38 | 27 | 27 | Scheduled | 11/03/2025 | 17/04/2025
TO-25-MP GIS-400SB2-4CB-01 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 400-MONEYPOINT GIS 400-400SB2-4CB | 38 | 27 | 27 | Scheduled | 11/03/2025 | 17/04/2025
TO-25-BAR-T141-04 | DISTRIBUTION TRANSFORMER - BARRYMORE 110-BARRYMORE 38-T141 | 3 | 3 | 3 | Reference | 12/03/2025 | 14/03/2025
TO-25-BAR,T-BAR-1-04 | 110kV FEEDER - BARRYMORE tee-BARRYMORE 110-1 | 3 | 3 | 3 | Scheduled | 12/03/2025 | 14/03/2025
TO-25-BAR,T-CAH-1-03 | 110kV FEEDER - BARRYMORE tee-CAHIR 110-1 | 3 | 3 | 3 | Scheduled | 12/03/2025 | 14/03/2025
TO-25-KPG-TB-2-02 | 220kV FEEDER - KILPADDOGE 220-TARBERT 220-2 | 2 | 2 | 2 | Scheduled | 12/03/2025 | 13/03/2025
TO-25-LYT-110K2-01 | COUPLER/SECTIONALISING CB - LYSAGHTSTOWN 110-LYSAGHTSTOWN 110-110K2 | 1 | 1 | 1 | Scheduled | 12/03/2025 | 12/03/2025
TO-25-SKL-M/CAP2-02 | CAPACITOR/SVC/REACTOR - SHANKILL 110-SHANKILL 110-M/CAP2 | 1 | 1 | 1 | Scheduled | 12/03/2025 | 12/03/2025
TO-25-220 kV A2 @ TB-02 | BUSBAR SECTION - TARBERT 220-TARBERT 220-220A2 | 2 | 2 | 2 | Scheduled | 12/03/2025 | 13/03/2025
TO-25-220 kV B2 @ TB-02 | BUSBAR SECTION - TARBERT 220-TARBERT 220-220B2 | 2 | 2 | 2 | Scheduled | 12/03/2025 | 13/03/2025
TO-25-220 kV A2 @ LOU-01 | BUSBAR SECTION - LOUTH 220-LOUTH 220-220A2 | 16 | 11 |  | Scheduled | 13/03/2025 | 28/03/2025
TO-25-220 kV B2 @ LOU-01 | BUSBAR SECTION - LOUTH 220-LOUTH 220-220B2 | 16 | 11 |  | Scheduled | 13/03/2025 | 28/03/2025
TO-25-220 kV A1 @ AD-01 | BUSBAR SECTION - AGHADA 220-AGHADA 220-220A1 | 11 | 9 | 9 | Scheduled | 18/03/2025 | 28/03/2025
TO-25-220 kV A2 @ AD-02 | BUSBAR SECTION - AGHADA 220-AGHADA 220-220A2 | 11 | 9 | 9 | Scheduled | 18/03/2025 | 28/03/2025
TO-25-220 kV B1 @ AD-02 | BUSBAR SECTION - AGHADA 220-AGHADA 220-220B1 | 11 | 9 | 9 | Scheduled | 18/03/2025 | 28/03/2025
TO-25-220 kV B2 @ AD-02 | BUSBAR SECTION - AGHADA 220-AGHADA 220-220B2 | 11 | 9 | 9 | Scheduled | 18/03/2025 | 28/03/2025
TO-25-AD-220K1-01 | COUPLER/SECTIONALISING CB - AGHADA 220-AGHADA 220-220K1 | 11 | 9 | 9 | Scheduled | 18/03/2025 | 28/03/2025
TO-25-AD-SA1-2CB-03 | COUPLER/SECTIONALISING CB - AGHADA 220-AGHADA 220-220SA1-2CB | 11 | 9 | 9 | Scheduled | 18/03/2025 | 28/03/2025
TO-25-AD-SB1-2CB-03 | COUPLER/SECTIONALISING CB - AGHADA 220-AGHADA 220-220SB1-2CB | 11 | 9 | 9 | Scheduled | 18/03/2025 | 28/03/2025
TO-25-220 kV A2 @ CSH-02 | BUSBAR SECTION - CASHLA 220-CASHLA 220-220A2 | 11 | 9 | 9 | Scheduled | 18/03/2025 | 28/03/2025
TO-25-220 kV A4 @ CSH-01 | BUSBAR SECTION - CASHLA 220-CASHLA 220-220A4 | 11 | 9 | 9 | Scheduled | 18/03/2025 | 28/03/2025
TO-25-220 kV B2 @ CSH-02 | BUSBAR SECTION - CASHLA 220-CASHLA 220-220B2 | 11 | 9 | 9 | Scheduled | 18/03/2025 | 28/03/2025
TO-25-220 kV B4 @ CSH-01 | BUSBAR SECTION - CASHLA 220-CASHLA 220-220B4 | 11 | 9 | 9 | Scheduled | 18/03/2025 | 28/03/2025
TO-25-CSH-220K2-4-01 | COUPLER/SECTIONALISING CB - CASHLA 220-CASHLA 220-220K2-4 | 11 | 9 | 9 | Scheduled | 18/03/2025 | 28/03/2025
TO-25-CLA-110K1-2-01 | COUPLER/SECTIONALISING CB - CLASHAVOON 110-CLASHAVOON 110-110K1-2 | 44 | 30 |  | Scheduled | 18/03/2025 | 30/04/2025
TO-25-110 kV B1 @ FLA-01 | BUSBAR SECTION - FLAGFORD 110-FLAGFORD 110-110B1 | 95 | 65 | 65 | Scheduled | 18/03/2025 | 20/06/2025
TO-25-FLA-SLB-1-03 | 110kV FEEDER - FLAGFORD 110-SLIABH BAWN 110-1 | 95 | 65 | 65 | Scheduled | 18/03/2025 | 20/06/2025
TO-25-KBY-MR-1-03 | 110kV FEEDER - KILBARRY 110-MARINA 110-1 | 186 | 129 | 129 | Scheduled | 18/03/2025 | 19/09/2025
TO-25-KBY-MR-2-03 | 110kV FEEDER - KILBARRY 110-MARINA 110-2 | 186 | 129 | 129 | Scheduled | 18/03/2025 | 19/09/2025
TO-25-KTN-110SA1-01 | SECTIONALISING DISCONNECT - KILLOTERAN 110-KILLOTERAN 110-110SA1 | 74 | 51 | 51 | Scheduled | 18/03/2025 | 30/05/2025
TO-25-KTN-110SA2-01 | SECTIONALISING DISCONNECT - KILLOTERAN 110-KILLOTERAN 110-110SA2 | 74 | 51 | 51 | Scheduled | 18/03/2025 | 30/05/2025
TO-25-KTN-T102-01 | DISTRIBUTION TRANSFORMER - KILLOTERAN 110-KILLOTERAN 10-T102 | 74 | 51 | 51 | Reference | 18/03/2025 | 30/05/2025
TO-25-KTN-WAT-1-03 | 110kV FEEDER - KILLOTERAN 110-WATERFORD 110-1 | 74 | 51 | 51 | Scheduled | 18/03/2025 | 30/05/2025
TO-25-KRA-WOH-1-03 | 110kV FEEDER - KNOCKRAHA 110-WOODHOUSE 110-1 | 3 | 3 | 3 | Scheduled | 18/03/2025 | 20/03/2025
TO-25-110 kV A2 @ SLB-01 | BUSBAR SECTION - SLIABH BAWN 110-SLIABH BAWN 110-110A2 | 14 | 10 | 10 | Scheduled | 18/03/2025 | 31/03/2025
TO-25-110 kV B2 @ SLB-01 | BUSBAR SECTION - SLIABH BAWN 110-SLIABH BAWN 110-110B2 | 14 | 10 | 10 | Scheduled | 18/03/2025 | 31/03/2025
TO-25-SLB-110K2-01 | COUPLER/SECTIONALISING CB - SLIABH BAWN 110-SLIABH BAWN 110-110K2 | 14 | 10 | 10 | Scheduled | 18/03/2025 | 31/03/2025
TO-25-110 kV B2 @ CSH-04 | BUSBAR SECTION - CASHLA 110-CASHLA 110-110B2 | 10 | 8 | 8 | Scheduled | 19/03/2025 | 28/03/2025
TO-25-CSH-ENN-1-02 | 110kV FEEDER - CASHLA 110-ENNIS 110-1 | 72 | 49 | 49 | Scheduled | 19/03/2025 | 29/05/2025
TO-25-GI GIS-KLS-1-02 | 220kV FEEDER - GREAT ISLAND GIS 220-KELLIS 220-1 | 2 | 0 | 0 | Scheduled | 22/03/2025 | 23/03/2025
TO-25-220 kV A1 @ TH-01 | BUSBAR SECTION - TURLOUGH HILL 220-TURLOUGH HILL 220-220A1 | 10 | 7 | 7 | Scheduled | 23/03/2025 | 01/04/2025
TO-25-220 kV B1 @ TH-01 | BUSBAR SECTION - TURLOUGH HILL 220-TURLOUGH HILL 220-220B1 | 10 | 7 | 7 | Scheduled | 23/03/2025 | 01/04/2025
TO-25-TH-T2001/2-01 | GENERATOR TRANSFORMER - TURLOUGH HILL 220-TURLOUGH HILL G1-T2001/2 | 10 | 7 | 7 | Scheduled | 23/03/2025 | 01/04/2025
TO-25-AD-T2011/12-02 | GENERATOR TRANSFORMER - AGHADA 220-AGHADA G11/12-T2011/12 | 9 | 7 | 7 | Scheduled | 24/03/2025 | 01/04/2025
TO-25-CLG-T122-01 | TSO CUSTOMER TRANSFORMER - CLOGHRAN 110-CLOGHRAN 20-T122 | 5 | 5 | 5 | Scheduled | 24/03/2025 | 28/03/2025
TO-25-220 kV A4 @ KRA-01 | BUSBAR SECTION - KNOCKRAHA 220-KNOCKRAHA 220-220A4 | 75 | 51 | 51 | Scheduled | 24/03/2025 | 06/06/2025
TO-25-220 kV B4 @ KRA-01 | BUSBAR SECTION - KNOCKRAHA 220-KNOCKRAHA 220-220B4 | 75 | 51 | 51 | Scheduled | 24/03/2025 | 06/06/2025
TO-25-KRA-220K4-01 | COUPLER/SECTIONALISING CB - KNOCKRAHA 220-KNOCKRAHA 220-220K4 | 75 | 51 | 51 | Scheduled | 24/03/2025 | 06/06/2025
TO-25-KRA-220SA2-4CB-02 | COUPLER/SECTIONALISING CB - KNOCKRAHA 220-KNOCKRAHA 220-220SA2-4CB | 75 | 51 | 51 | Scheduled | 24/03/2025 | 06/06/2025
TO-25-KRA-220SB2-4CB-02 | COUPLER/SECTIONALISING CB - KNOCKRAHA 220-KNOCKRAHA 220-220SB2-4CB | 75 | 51 | 51 | Scheduled | 24/03/2025 | 06/06/2025
TO-25-THU-STATCOM-03 | CAPACITOR/SVC/REACTOR - THURLES 110-THURLES 110-STATCOM | 5 | 5 | 5 | Scheduled | 24/03/2025 | 28/03/2025
TO-25-AUG-KPG-1-01 | 110kV FEEDER - AUGHINISH 110-KILPADDOGE 110-1 | 3 | 3 | 3 | Scheduled | 25/03/2025 | 27/03/2025
TO-25-GLN-T133-02 | GENERATOR TRANSFORMER - GALLANSTOWN 110-GALLANSTOWN 33-T133 | 3 | 3 | 3 | Scheduled | 25/03/2025 | 27/03/2025
TO-25-ISH-T2001-01 | GENERATOR TRANSFORMER - IRISHTOWN 220-IRISHTOWN G1-T2001 | 3 | 3 | 3 | Scheduled | 25/03/2025 | 27/03/2025
TO-25-DRY-GOR-1-04 | 110kV FEEDER - DRYBRIDGE 110-GORMAN 110-1 | 3 | 3 | 3 | Scheduled | 26/03/2025 | 28/03/2025
TO-25-KIN-T102-03 | TSO CUSTOMER TRANSFORMER - KINNEGAD 110-KINNEGAD 10-T102 | 3 | 3 | 3 | Scheduled | 26/03/2025 | 28/03/2025
TO-25-AD-T2014-01 | GENERATOR TRANSFORMER - AGHADA 220-AGHADA G14-T2014 | 9 | 7 | 7 | Scheduled | 31/03/2025 | 08/04/2025
TO-25-BYH-GLE-1-01 | 110kV FEEDER - BALLYNAHULLA 110-GLENLARA 110-1 | 12 | 10 | 10 | Scheduled | 31/03/2025 | 11/04/2025
TO-25-BYH-STATCOM-01 | CAPACITOR/SVC/REACTOR - BALLYNAHULLA 110-BALLYNAHULLA 110-STATCOM | 5 | 5 | 5 | Scheduled | 31/03/2025 | 04/04/2025
TO-25-110 kV B1 @ BLC-01 | BUSBAR SECTION - BELCAMP 110-BELCAMP 110-110B1 | 5 | 5 | 5 | Scheduled | 31/03/2025 | 04/04/2025
TO-25-BLC-110K1-02 | COUPLER/SECTIONALISING CB - BELCAMP 110-BELCAMP 110-110K1 | 5 | 5 | 5 | Scheduled | 31/03/2025 | 04/04/2025
TO-25-BLC-110SA1-3CB-03 | COUPLER/SECTIONALISING CB - BELCAMP 110-BELCAMP 110-110SA1-3CB | 5 | 5 | 5 | Scheduled | 31/03/2025 | 04/04/2025
TO-25-BLC-110SB1-3CB-03 | COUPLER/SECTIONALISING CB - BELCAMP 110-BELCAMP 110-110SB1-3CB | 5 | 5 | 5 | Scheduled | 31/03/2025 | 04/04/2025
TO-25-BLC-DND-1-02 | 110kV FEEDER - BELCAMP 110-DARNDALE 110-1 | 5 | 5 | 5 | Scheduled | 31/03/2025 | 04/04/2025
TO-25-110 kV B1 @ DND-02 | BUSBAR SECTION - DARNDALE 110-DARNDALE 110-110B1 | 5 | 5 | 5 | Scheduled | 31/03/2025 | 04/04/2025
TO-25-DND-110K1-04 | COUPLER/SECTIONALISING CB - DARNDALE 110-DARNDALE 110-110K1 | 5 | 5 | 5 | Scheduled | 31/03/2025 | 04/04/2025
TO-25-DND-110SA1-2CB-06 | COUPLER/SECTIONALISING CB - DARNDALE 110-DARNDALE 110-110SA1-2CB | 5 | 5 | 5 | Scheduled | 31/03/2025 | 04/04/2025
TO-25-DND-110SB1-2CB-05 | COUPLER/SECTIONALISING CB - DARNDALE 110-DARNDALE 110-110SB1-2CB | 5 | 5 | 5 | Scheduled | 31/03/2025 | 04/04/2025
TO-25-DRY-OBE-1-01 | 110kV FEEDER - DRYBRIDGE 110-OLDBRIDGE 110-1 | 67 | 45 | 45 | Scheduled | 31/03/2025 | 05/06/2025
TO-25-GLE-KCR-1-01 | 110kV FEEDER - GLENLARA 110-KNOCKACUMMER 110-1 | 12 | 10 | 10 | Scheduled | 31/03/2025 | 11/04/2025
TO-25-KCR-T121-01 | GENERATOR TRANSFORMER - KNOCKACUMMER 110-KNOCKACUMMER 20-T121 | 12 | 10 | 10 | Scheduled | 31/03/2025 | 11/04/2025
TO-25-220 kV A1 @ LOU-01 | BUSBAR SECTION - LOUTH 220-LOUTH 220-220A1 | 38 | 25 | 25 | Scheduled | 31/03/2025 | 07/05/2025
TO-25-220 kV A1 @ LOU-08 | BUSBAR SECTION - LOUTH 220-LOUTH 220-220A1 | 4 | 4 | 4 | Scheduled | 31/03/2025 | 03/04/2025
TO-25-220 kV B1 @ LOU-01 | BUSBAR SECTION - LOUTH 220-LOUTH 220-220B1 | 38 | 25 | 25 | Scheduled | 31/03/2025 | 07/05/2025
TO-25-LOU-AT2-03 | TRANSFORMER - LOUTH 220-LOUTH 275-AT2 | 4 | 4 | 4 | Scheduled | 31/03/2025 | 03/04/2025
TO-25-LOU-TAN-2-03 | 275kV FEEDER - LOUTH 275-TANDRAGEE 275-2 | 4 | 4 | 4 | Scheduled | 31/03/2025 | 03/04/2025
TO-25-MOY-TAW-1-01 | 110kV FEEDER - MOY 110-TAWNAGHMORE 110-1 | 12 | 10 | 10 | Scheduled | 31/03/2025 | 11/04/2025
TO-25-WOH-T122-01 | GENERATOR TRANSFORMER - WOODHOUSE 110-WOODHOUSE 20-T122 | 5 | 5 | 5 | Scheduled | 31/03/2025 | 04/04/2025
TO-25-AA GIS-LIM-1-01 | 110kV FEEDER - ARDNACRUSHA GIS 110-LIMERICK 110-1 | 3 | 3 | 3 | Scheduled | 01/04/2025 | 03/04/2025
TO-25-BYH-110K1-02 | COUPLER/SECTIONALISING CB - BALLYNAHULLA 110-BALLYNAHULLA 110-110K1 | 2 | 2 | 2 | Scheduled | 01/04/2025 | 02/04/2025
TO-25-BYH-110SB1-2CB-01 | COUPLER/SECTIONALISING CB - BALLYNAHULLA 110-BALLYNAHULLA 110-110SB1-2CB | 2 | 2 | 2 | Scheduled | 01/04/2025 | 02/04/2025
TO-25-SLB-110K2-02 | COUPLER/SECTIONALISING CB - SLIABH BAWN 110-SLIABH BAWN 110-110K2 | 2 | 2 | 2 | Scheduled | 01/04/2025 | 02/04/2025
TO-25-SNU-T102-01 | TSO CUSTOMER TRANSFORMER - SNUGBOROUGH 110-SNUGBOROUGH 10-T102 | 2 | 2 | 2 | Scheduled | 01/04/2025 | 02/04/2025
TO-25-KTL-T131-01 | GENERATOR TRANSFORMER - KILTEEL 110-KILTEEL 33-T131 | 1 | 1 | 1 | Scheduled | 02/04/2025 | 02/04/2025
TO-25-LET-PST-02 | TRANSFORMER - LETTERKENNY 110-STRABANE 110-PST | 16 | 12 | 12 | Scheduled | 02/04/2025 | 17/04/2025
TO-25-ROP-110K1-01 | COUPLER/SECTIONALISING CB - ROSSPILE 110-ROSSPILE 110-110K1 | 1 | 1 | 1 | Scheduled | 02/04/2025 | 02/04/2025
TO-25-220 kV A2 @ TH-01 | BUSBAR SECTION - TURLOUGH HILL 220-TURLOUGH HILL 220-220A2 | 10 | 8 | 8 | Scheduled | 02/04/2025 | 11/04/2025
TO-25-220 kV B2 @ TH-01 | BUSBAR SECTION - TURLOUGH HILL 220-TURLOUGH HILL 220-220B2 | 10 | 8 | 8 | Scheduled | 02/04/2025 | 11/04/2025
TO-25-TH-T2003/4-02 | GENERATOR TRANSFORMER - TURLOUGH HILL 220-TURLOUGH HILL G1-T2003/4 | 10 | 8 | 8 | Scheduled | 02/04/2025 | 11/04/2025
TO-25-TEN-T132-02 | GENERATOR TRANSFORMER - TIMAHOE 110-TIMAHOE 33-T132 | 1 | 1 | 1 | Scheduled | 04/04/2025 | 04/04/2025
TO-25-BVK-STATCOM-01 | CAPACITOR/SVC/REACTOR - BALLYVOUSKILL 110-BALLYVOUSKILL 110-STATCOM | 5 | 5 | 5 | Scheduled | 07/04/2025 | 11/04/2025
TO-25-110 kV A3 @ BLC-01 | BUSBAR SECTION - BELCAMP 110-BELCAMP 110-110A3 | 5 | 5 | 5 | Scheduled | 07/04/2025 | 11/04/2025
TO-25-110 kV B3 @ BLC-01 | BUSBAR SECTION - BELCAMP 110-BELCAMP 110-110B3 | 5 | 5 | 5 | Scheduled | 07/04/2025 | 11/04/2025
TO-25-BLC-110K3-02 | COUPLER/SECTIONALISING CB - BELCAMP 110-BELCAMP 110-110K3 | 5 | 5 | 5 | Scheduled | 07/04/2025 | 11/04/2025
TO-25-BLC-110SA1-3CB-02 | COUPLER/SECTIONALISING CB - BELCAMP 110-BELCAMP 110-110SA1-3CB | 5 | 5 | 5 | Scheduled | 07/04/2025 | 11/04/2025
TO-25-BLC-110SB1-3CB-02 | COUPLER/SECTIONALISING CB - BELCAMP 110-BELCAMP 110-110SB1-3CB | 5 | 5 | 5 | Scheduled | 07/04/2025 | 11/04/2025
TO-25-BLC-DND-3-01 | 110kV FEEDER - BELCAMP 110-DARNDALE 110-3 | 5 | 5 | 5 | Scheduled | 07/04/2025 | 11/04/2025
TO-25-CF-CL-1-02 | 110kV FEEDER - CATHALEENS FALL 110-CLIFF 110-1 | 4 | 4 | 4 | Scheduled | 07/04/2025 | 10/04/2025
TO-25-CL-T101-03 | GENERATOR TRANSFORMER - CLIFF 110-CLIFF G1-T101 | 4 | 4 | 4 | Scheduled | 07/04/2025 | 10/04/2025
TO-25-CL-T102-01 | GENERATOR TRANSFORMER - CLIFF 110-CLIFF G2-T102 | 9 | 7 | 7 | Scheduled | 07/04/2025 | 15/04/2025
TO-25-220 kV A1 @ CDU-01 | BUSBAR SECTION - CORDUFF 220-CORDUFF 220-220A1 | 5 | 5 | 5 | Scheduled | 07/04/2025 | 11/04/2025
TO-25-220 kV A2 @ CDU-01 | BUSBAR SECTION - CORDUFF 220-CORDUFF 220-220A2 | 5 | 5 | 5 | Scheduled | 07/04/2025 | 11/04/2025
TO-25-220 kV A3 @ CDU-01 | BUSBAR SECTION - CORDUFF 220-CORDUFF 220-220A3 | 5 | 5 | 5 | Scheduled | 07/04/2025 | 11/04/2025
TO-25-220 kV A4 @ CDU-01 | BUSBAR SECTION - CORDUFF 220-CORDUFF 220-220A4 | 5 | 5 | 5 | Scheduled | 07/04/2025 | 11/04/2025
TO-25-220 kV B1 @ CDU-01 | BUSBAR SECTION - CORDUFF 220-CORDUFF 220-220B1 | 5 | 5 | 5 | Scheduled | 07/04/2025 | 11/04/2025
TO-25-220 kV B2 @ CDU-01 | BUSBAR SECTION - CORDUFF 220-CORDUFF 220-220B2 | 5 | 5 | 5 | Scheduled | 07/04/2025 | 11/04/2025
TO-25-220 kV B3 @ CDU-01 | BUSBAR SECTION - CORDUFF 220-CORDUFF 220-220B3 | 5 | 5 | 5 | Scheduled | 07/04/2025 | 11/04/2025
TO-25-220 kV B4 @ CDU-01 | BUSBAR SECTION - CORDUFF 220-CORDUFF 220-220B4 | 5 | 5 | 5 | Scheduled | 07/04/2025 | 11/04/2025
TO-25-CDU-CRU-1-01 | 220kV FEEDER - CORDUFF 220-CRUISERATH 220-1 | 5 | 5 | 5 | Scheduled | 07/04/2025 | 11/04/2025
TO-25-CDU-T2104-01 | TRANSFORMER - CORDUFF 220-CORDUFF 110-T2104 | 5 | 5 | 5 | Scheduled | 07/04/2025 | 11/04/2025
TO-25-110 kV B2 @ DND-01 | BUSBAR SECTION - DARNDALE 110-DARNDALE 110-110B2 | 5 | 5 | 5 | Scheduled | 07/04/2025 | 11/04/2025
TO-25-DND-110K2-02 | COUPLER/SECTIONALISING CB - DARNDALE 110-DARNDALE 110-110K2 | 5 | 5 | 5 | Scheduled | 07/04/2025 | 11/04/2025
TO-25-DND-110SA1-2CB-03 | COUPLER/SECTIONALISING CB - DARNDALE 110-DARNDALE 110-110SA1-2CB | 5 | 5 | 5 | Scheduled | 07/04/2025 | 11/04/2025
TO-25-DND-110SB1-2CB-02 | COUPLER/SECTIONALISING CB - DARNDALE 110-DARNDALE 110-110SB1-2CB | 5 | 5 | 5 | Scheduled | 07/04/2025 | 11/04/2025
TO-25-LYT-T132-02 | GENERATOR TRANSFORMER - LYSAGHTSTOWN 110-LYSAGHTSTOWN 33-T132 | 1 | 1 | 1 | Scheduled | 07/04/2025 | 07/04/2025
TO-25-220 kV A1 @ MP GIS-01 | BUSBAR SECTION - MONEYPOINT GIS 220-MONEYPOINT GIS 220-220A1 | 9 | 7 | 7 | Scheduled | 07/04/2025 | 15/04/2025
TO-25-220 kV B1 @ MP GIS-01 | BUSBAR SECTION - MONEYPOINT GIS 220-MONEYPOINT GIS 220-220B1 | 9 | 7 | 7 | Scheduled | 07/04/2025 | 15/04/2025
TO-25-MP GIS-220K1-01 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 220-MONEYPOINT GIS 220-220K1 | 9 | 7 | 7 | Scheduled | 07/04/2025 | 15/04/2025
TO-25-MP GIS-220SA1-2CB-02 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 220-MONEYPOINT GIS 220-220SA1-2CB | 9 | 7 | 7 | Scheduled | 07/04/2025 | 15/04/2025
TO-25-MP GIS-220SB1-2CB-02 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 220-MONEYPOINT GIS 220-220SB1-2CB | 9 | 7 | 7 | Scheduled | 07/04/2025 | 15/04/2025
TO-25-NAV-T142-01 | DISTRIBUTION TRANSFORMER - NAVAN 110-NAVAN 38-T142 | 99 | 67 |  | Reference | 07/04/2025 | 14/07/2025
TO-25-AA GIS-SNG-1-01 | 110kV FEEDER - ARDNACRUSHA GIS 110-SINGLAND 110-1 | 3 | 3 | 3 | Scheduled | 08/04/2025 | 10/04/2025
TO-25-BOG-TTU-1-01 | 110kV FEEDER - BANOGE 110-TULLABEG 110-1 | 4 | 4 | 4 | Scheduled | 08/04/2025 | 11/04/2025
TO-25-BLU-T131-01 | GENERATOR TRANSFORMER - BLUNDELSTOWN 110-BLUNDELSTOWN 33-T131 | 2 | 2 | 2 | Scheduled | 08/04/2025 | 09/04/2025
TO-25-110 kV B2 @ CLU-01 | BUSBAR SECTION - CLUTTERLAND 110-CLUTTERLAND 110-110B2 | 32 | 21 | 21 | Scheduled | 08/04/2025 | 09/05/2025
TO-25-CLU-110K2-01 | COUPLER/SECTIONALISING CB - CLUTTERLAND 110-CLUTTERLAND 110-110K2 | 32 | 21 | 21 | Scheduled | 08/04/2025 | 09/05/2025
TO-25-CLU-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - CLUTTERLAND 110-CLUTTERLAND 110-110SA1-2CB | 32 | 21 | 21 | Scheduled | 08/04/2025 | 09/05/2025
TO-25-CLU-110SB1-2CB-01 | COUPLER/SECTIONALISING CB - CLUTTERLAND 110-CLUTTERLAND 110-110SB1-2CB | 32 | 21 | 21 | Scheduled | 08/04/2025 | 09/05/2025
TO-25-GI GIS-LON-1-01 | 220kV FEEDER - GREAT ISLAND GIS 220-LOUGHTOWN 220-1 | 3 | 3 | 3 | Scheduled | 08/04/2025 | 10/04/2025
TO-25-LON-T2401-01 | TRANSFORMER - LOUGHTOWN 400-LOUGHTOWN 220-T2401 | 3 | 3 | 3 | Scheduled | 08/04/2025 | 10/04/2025
TO-25-TTU-131-02 | GENERATOR TRANSFORMER - TULLABEG 110-TULLABEG 33-T131 | 1 | 1 | 1 | Scheduled | 08/04/2025 | 08/04/2025
TO-25-BLU-110K1-02 | COUPLER/SECTIONALISING CB - BLUNDELSTOWN 110-BLUNDELSTOWN 110-110K1 | 1 | 1 | 1 | Scheduled | 09/04/2025 | 09/04/2025
TO-25-BLU-MUL-1-05 | 110kV FEEDER - BLUNDELSTOWN 110-MULLINGAR 110-1 | 1 | 1 | 1 | Scheduled | 09/04/2025 | 09/04/2025
TO-25-BRT-T224-01 | TSO CUSTOMER TRANSFORMER - BRACETOWN 220-BRACETOWN 20-T224 | 57 | 37 | 37 | Scheduled | 11/04/2025 | 06/06/2025
TO-25-220 kV A1 @ BYH-01 | BUSBAR SECTION - BALLYNAHULLA 220-BALLYNAHULLA 220-220A1 | 4 | 4 | 4 | Scheduled | 14/04/2025 | 17/04/2025
TO-25-220 kV A2 @ BYH-01 | BUSBAR SECTION - BALLYNAHULLA 220-BALLYNAHULLA 220-220A2 | 4 | 4 | 4 | Scheduled | 14/04/2025 | 17/04/2025
TO-25-BYH-220K1-02 | COUPLER/SECTIONALISING CB - BALLYNAHULLA 220-BALLYNAHULLA 220-220K1 | 4 | 4 | 4 | Scheduled | 14/04/2025 | 17/04/2025
TO-25-BYH-220K2-01 | COUPLER/SECTIONALISING CB - BALLYNAHULLA 220-BALLYNAHULLA 220-220K2 | 4 | 4 | 4 | Scheduled | 14/04/2025 | 17/04/2025
TO-25-BYH-220SA1-2CB-01 | COUPLER/SECTIONALISING CB - BALLYNAHULLA 220-BALLYNAHULLA 220-220SA1-2CB | 4 | 4 | 4 | Scheduled | 14/04/2025 | 17/04/2025
TO-25-BUF-KNY-1-01 | 110kV FEEDER - BUFFY 110-KNOCKRANNY 110-1 | 2 | 2 | 2 | Scheduled | 14/04/2025 | 15/04/2025
TO-25-BUF-T131-01 | GENERATOR TRANSFORMER - BUFFY 110-BUFFY 33-T131 | 2 | 2 | 2 | Scheduled | 14/04/2025 | 15/04/2025
TO-25-CHA-MAL-1-06 | 110kV FEEDER - CHARLEVILLE 110-MALLOW 110-1 | 3 | 3 | 3 | Scheduled | 14/04/2025 | 16/04/2025
TO-25-KPG-TRL-2-02 | 110kV FEEDER - KILPADDOGE 110-TRALEE 110-2 | 138 | 95 | 95 | Scheduled | 14/04/2025 | 29/08/2025
TO-25-PRN-T4301-01 | TRANSFORMER - PORTAN 400-PORTAN 260-T4301 | 5 | 4 | 4 | Scheduled | 14/04/2025 | 18/04/2025
TO-25-PRN-WOO-1-01 | 400kV FEEDER - PORTAN 400-WOODLAND 400-1 | 5 | 4 | 4 | Scheduled | 14/04/2025 | 18/04/2025
TO-25-400 kV A1 @ WOO-02 | BUSBAR SECTION - WOODLAND 400-WOODLAND 400-400A1 | 1 | 1 | 1 | Scheduled | 14/04/2025 | 14/04/2025
TO-25-CDY-GRV-1-02 | 110kV FEEDER - CORDERRY 110-GARVAGH 110-1 | 3 | 3 | 3 | Scheduled | 15/04/2025 | 17/04/2025
TO-25-GRV-110K1-02 | COUPLER/SECTIONALISING CB - GARVAGH 110-GARVAGH 110-110K1 | 3 | 3 | 3 | Scheduled | 15/04/2025 | 17/04/2025
TO-25-GRV-T121-03 | GENERATOR TRANSFORMER - GARVAGH 110-GARVAGH 20-T121 | 3 | 3 | 3 | Scheduled | 15/04/2025 | 17/04/2025
TO-25-GRV-T141-02 | DISTRIBUTION TRANSFORMER - GARVAGH 110-GARVAGH 20-T141 | 3 | 3 | 3 | Reference | 15/04/2025 | 17/04/2025
TO-25-110 kV B1 @ LOU-04 | BUSBAR SECTION - LOUTH 110-LOUTH 110-110B1 | 1 | 1 | 1 | Scheduled | 15/04/2025 | 15/04/2025
TO-25-MOY-TAW-2-01 | 110kV FEEDER - MOY 110-TAWNAGHMORE 110-2 | 3 | 3 | 3 | Scheduled | 15/04/2025 | 17/04/2025
TO-25-400 kV B1 @ WOO-02 | BUSBAR SECTION - WOODLAND 400-WOODLAND 400-400B1 | 4 | 3 | 3 | Scheduled | 15/04/2025 | 18/04/2025
TO-25-WOO-400K1-2-01 | COUPLER/SECTIONALISING CB - WOODLAND 400-WOODLAND 400-400K1-2 | 4 | 3 | 3 | Scheduled | 15/04/2025 | 18/04/2025
TO-25-WOO-T4201-02 | TRANSFORMER - WOODLAND 400-WOODLAND 220-T4201 | 4 | 3 | 3 | Scheduled | 15/04/2025 | 18/04/2025
TO-25-LOU-T2101-08 | TRANSFORMER - LOUTH 220-LOUTH 110-T2101 | 2 | 2 | 2 | Scheduled | 16/04/2025 | 17/04/2025
TO-25-220 kV A2 @ MP GIS-01 | BUSBAR SECTION - MONEYPOINT GIS 220-MONEYPOINT GIS 220-220A2 | 13 | 7 | 7 | Scheduled | 16/04/2025 | 28/04/2025
TO-25-220 kV B2 @ MP GIS-01 | BUSBAR SECTION - MONEYPOINT GIS 220-MONEYPOINT GIS 220-220B2 | 13 | 7 | 7 | Scheduled | 16/04/2025 | 28/04/2025
TO-25-MP GIS-220K2-01 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 220-MONEYPOINT GIS 220-220K2 | 13 | 7 | 7 | Scheduled | 16/04/2025 | 28/04/2025
TO-25-MP GIS-220SA1-2CB-03 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 220-MONEYPOINT GIS 220-220SA1-2CB | 13 | 7 | 7 | Scheduled | 16/04/2025 | 28/04/2025
TO-25-MP GIS-220SB1-2CB-03 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 220-MONEYPOINT GIS 220-220SB1-2CB | 13 | 7 | 7 | Scheduled | 16/04/2025 | 28/04/2025
TO-25-CHA-GLE-1-01 | 110kV FEEDER - CHARLEVILLE 110-GLENLARA 110-1 | 62 | 40 | 40 | Scheduled | 17/04/2025 | 17/06/2025
TO-25-ARV-COS-1-03 | 110kV FEEDER - ARVA 110-CARRICK ON SHANNON 110-1 | 4 | 0 | 0 | Scheduled | 18/04/2025 | 21/04/2025
TO-25-220 kV A1 @ ARK-01 | BUSBAR SECTION - ARKLOW 220-ARKLOW 220-220A1 | 4 | 4 | 4 | Scheduled | 22/04/2025 | 25/04/2025
TO-25-220 kV A2 @ ARK-01 | BUSBAR SECTION - ARKLOW 220-ARKLOW 220-220A2 | 4 | 4 | 4 | Scheduled | 22/04/2025 | 25/04/2025
TO-25-220 kV B1 @ ARK-01 | BUSBAR SECTION - ARKLOW 220-ARKLOW 220-220B1 | 4 | 4 | 4 | Scheduled | 22/04/2025 | 25/04/2025
TO-25-220 kV B2 @ ARK-01 | BUSBAR SECTION - ARKLOW 220-ARKLOW 220-220B2 | 4 | 4 | 4 | Scheduled | 22/04/2025 | 25/04/2025
TO-25-ARK-220K1-2-01 | COUPLER/SECTIONALISING CB - ARKLOW 220-ARKLOW 220-220K1-2 | 4 | 4 | 4 | Scheduled | 22/04/2025 | 25/04/2025
TO-25-AUG-MTN-1-01 | 110kV FEEDER - AUGHINISH 110-MONETEEN 110-1 | 3 | 3 | 3 | Scheduled | 22/04/2025 | 24/04/2025
TO-25-220 kV A2 @ SH-02 | BUSBAR SECTION - SHANNONBRIDGE 220-SHANNONBRIDGE 220-220A2 | 46 | 32 | 32 | Scheduled | 22/04/2025 | 06/06/2025
TO-25-220 kV B2 @ SH-02 | BUSBAR SECTION - SHANNONBRIDGE 220-SHANNONBRIDGE 220-220B2 | 46 | 32 | 32 | Scheduled | 22/04/2025 | 06/06/2025
TO-25-CD-T103-02 | GENERATOR TRANSFORMER - CARRIGADROHID 110-CARRIGADROHID G3-T103 | 8 | 6 | 6 | Scheduled | 23/04/2025 | 30/04/2025
TO-25-110 kV B2 @ DND-02 | BUSBAR SECTION - DARNDALE 110-DARNDALE 110-110B2 | 7 | 5 | 5 | Scheduled | 23/04/2025 | 29/04/2025
TO-25-DND-110K2-01 | COUPLER/SECTIONALISING CB - DARNDALE 110-DARNDALE 110-110K2 | 7 | 5 | 5 | Scheduled | 23/04/2025 | 29/04/2025
TO-25-DND-110SA1-2CB-05 | COUPLER/SECTIONALISING CB - DARNDALE 110-DARNDALE 110-110SA1-2CB | 7 | 5 | 5 | Scheduled | 23/04/2025 | 29/04/2025
TO-25-DND-110SB1-2CB-04 | COUPLER/SECTIONALISING CB - DARNDALE 110-DARNDALE 110-110SB1-2CB | 7 | 5 | 5 | Scheduled | 23/04/2025 | 29/04/2025
TO-25-FLA-220K1-2-01 | COUPLER/SECTIONALISING CB - FLAGFORD 220-FLAGFORD 220-220K1-2 | 1 | 1 | 1 | Scheduled | 23/04/2025 | 23/04/2025
TO-25-MR-T106-01 | DISTRIBUTION TRANSFORMER - MARINA 110-MARINA 10-T106 | 2 | 2 | 2 | Reference | 23/04/2025 | 24/04/2025
TO-25-ROP-T131-01 | GENERATOR TRANSFORMER - ROSSPILE 110-ROSSPILE 33-T131 | 1 | 1 | 1 | Scheduled | 23/04/2025 | 23/04/2025
TO-25-110 kV B2 @ CF-02 | BUSBAR SECTION - CATHALEENS FALL 110-CATHALEENS FALL 110-110B2 | 14 | 9 | 9 | Scheduled | 24/04/2025 | 07/05/2025
TO-25-CF-T104-01 | GENERATOR TRANSFORMER - CATHALEENS FALL 110-CATHALEENS FALL G4-T104 | 14 | 9 | 9 | Scheduled | 24/04/2025 | 07/05/2025
TO-25-220 kV A2/A4 @ CDU-01 | BUSBAR SECTION - CORDUFF 220-CORDUFF 220-220A2-A4 | 8 | 6 | 6 | Scheduled | 24/04/2025 | 01/05/2025
TO-25-CDU-220SA2-4CB-01 | COUPLER/SECTIONALISING CB - CORDUFF 220-CORDUFF 220-220SA2-4CB | 8 | 6 | 6 | Scheduled | 24/04/2025 | 01/05/2025
TO-25-IKE-T141-01 | DISTRIBUTION TRANSFORMER - IKERRIN 110-IKERRIN 38-T141 | 2 | 2 | 2 | Reference | 24/04/2025 | 25/04/2025
TO-25-IKE,T-IKE-1-01 | 110kV FEEDER - IKERRIN tee-IKERRIN 110-1 | 2 | 2 | 2 | Scheduled | 24/04/2025 | 25/04/2025
TO-25-IKE,T-SH-1-01 | 110kV FEEDER - IKERRIN tee-SHANNONBRIDGE 110-1 | 2 | 2 | 2 | Scheduled | 24/04/2025 | 25/04/2025
TO-25-IKE,T-THU-1-05 | 110kV FEEDER - IKERRIN tee-THURLES 110-1 | 63 | 43 | 43 | Scheduled | 24/04/2025 | 25/06/2025
TO-25-KLS-220K1-2-01 | COUPLER/SECTIONALISING CB - KELLIS 220-KELLIS 220-220K1-2 | 1 | 1 | 1 | Scheduled | 24/04/2025 | 24/04/2025
TO-25-STN-T131-02 | GENERATOR TRANSFORMER - STONESTOWN 110-STONESTOWN 33-T131 | 1 | 1 | 1 | Scheduled | 24/04/2025 | 24/04/2025
TO-25-FIN-HN-1-01 | 220kV FEEDER - FINGLAS 220-HUNTSTOWN 220-1 | 14 | 9 | 9 | Scheduled | 26/04/2025 | 09/05/2025
TO-25-HN-T2010/11-01 | GENERATOR TRANSFORMER - HUNTSTOWN 220-HUNTSTOWN G10/11-T2010/11 | 14 | 9 | 9 | Scheduled | 26/04/2025 | 09/05/2025
TO-25-110 kV B2 @ AA GIS-01 | BUSBAR SECTION - ARDNACRUSHA GIS 110-ARDNACRUSHA GIS 110-110B2 | 5 | 5 | 5 | Scheduled | 28/04/2025 | 02/05/2025
TO-25-AA GIS-110K2-02 | COUPLER/SECTIONALISING CB - ARDNACRUSHA GIS 110-ARDNACRUSHA GIS 110-110K2 | 5 | 5 | 5 | Scheduled | 28/04/2025 | 02/05/2025
TO-25-AA GIS-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - ARDNACRUSHA GIS 110-ARDNACRUSHA GIS 110-110SA1-2CB | 5 | 5 | 5 | Scheduled | 28/04/2025 | 02/05/2025
TO-25-AA GIS-110SB1-2CB-01 | COUPLER/SECTIONALISING CB - ARDNACRUSHA GIS 110-ARDNACRUSHA GIS 110-110SB1-2CB | 5 | 5 | 5 | Scheduled | 28/04/2025 | 02/05/2025
TO-25-AA GIS-T102-02 | GENERATOR TRANSFORMER - ARDNACRUSHA GIS 110-ARDNACRUSHA GIS G2-T102 | 145 | 102 | 102 | Scheduled | 28/04/2025 | 19/09/2025
TO-25-BVK-110K2-01 | COUPLER/SECTIONALISING CB - BALLYVOUSKILL 110-BALLYVOUSKILL 110-110K2 | 2 | 2 | 2 | Scheduled | 28/04/2025 | 29/04/2025
TO-25-220 kV A1 @ BVK-01 | BUSBAR SECTION - BALLYVOUSKILL 220-BALLYVOUSKILL 220-220A1 | 5 | 5 | 5 | Scheduled | 28/04/2025 | 02/05/2025
TO-25-220 kV B1 @ BVK-01 | BUSBAR SECTION - BALLYVOUSKILL 220-BALLYVOUSKILL 220-220B1 | 5 | 5 | 5 | Scheduled | 28/04/2025 | 02/05/2025
TO-25-BVK-220K1-02 | COUPLER/SECTIONALISING CB - BALLYVOUSKILL 220-BALLYVOUSKILL 220-220K1 | 5 | 5 | 5 | Scheduled | 28/04/2025 | 02/05/2025
TO-25-BVK-220SA1-2CB-03 | COUPLER/SECTIONALISING CB - BALLYVOUSKILL 220-BALLYVOUSKILL 220-220SA1-2CB | 5 | 5 | 5 | Scheduled | 28/04/2025 | 02/05/2025
TO-25-BVK-220SB1-2CB-04 | COUPLER/SECTIONALISING CB - BALLYVOUSKILL 220-BALLYVOUSKILL 220-220SB1-2CB | 5 | 5 | 5 | Scheduled | 28/04/2025 | 02/05/2025
TO-25-BVK-R2001-01 | CAPACITOR/SVC/REACTOR - BALLYVOUSKILL 220-BALLYVOUSKILL 220-R2001 | 5 | 5 | 5 | Scheduled | 28/04/2025 | 02/05/2025
TO-25-CAH-110K1-2-01 | COUPLER/SECTIONALISING CB - CAHIR 110-CAHIR 110-110K1-2 | 79 | 55 | 55 | Scheduled | 28/04/2025 | 15/07/2025
TO-25-CBT-T2103-01 | TRANSFORMER - CASTLEBAGOT 220-CASTLEBAGOT 110-T2103 | 18 | 13 |  | Scheduled | 28/04/2025 | 15/05/2025
TO-25-220 kV A1 @ FIN-06 | BUSBAR SECTION - FINGLAS 220-FINGLAS 220-220A1 | 12 | 9 | 9 | Scheduled | 28/04/2025 | 09/05/2025
TO-25-220 kV B1 @ FIN-05 | BUSBAR SECTION - FINGLAS 220-FINGLAS 220-220B1 | 12 | 9 | 9 | Scheduled | 28/04/2025 | 09/05/2025
TO-25-FIN-220K1-09 | COUPLER/SECTIONALISING CB - FINGLAS 220-FINGLAS 220-220K1 | 12 | 9 | 9 | Scheduled | 28/04/2025 | 09/05/2025
TO-25-FIN-220SA1-2CB-13 | COUPLER/SECTIONALISING CB - FINGLAS 220-FINGLAS 220-220SA1-2CB | 12 | 9 | 9 | Scheduled | 28/04/2025 | 09/05/2025
TO-25-FIN-220SB1-2CB-10 | COUPLER/SECTIONALISING CB - FINGLAS 220-FINGLAS 220-220SB1-2CB | 12 | 9 | 9 | Scheduled | 28/04/2025 | 09/05/2025
TO-25-GAR-110K1-01 | COUPLER/SECTIONALISING CB - GARBALLAGH 110-GARBALLAGH 110-110K1 | 5 | 5 | 5 | Scheduled | 28/04/2025 | 02/05/2025
TO-25-GAR-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - GARBALLAGH 110-GARBALLAGH 110-110SA1-2CB | 5 | 5 | 5 | Scheduled | 28/04/2025 | 02/05/2025
TO-25-GAR-110SB1-2CB-01 | COUPLER/SECTIONALISING CB - GARBALLAGH 110-GARBALLAGH 110-110SB1-2CB | 5 | 5 | 5 | Scheduled | 28/04/2025 | 02/05/2025
TO-25-LLA-110K1-01 | COUPLER/SECTIONALISING CB - LENALEA 110-LENALEA 110-110K1 | 2 | 2 | 2 | Scheduled | 28/04/2025 | 29/04/2025
TO-25-LLA-T133-02 | GENERATOR TRANSFORMER - LENALEA 110-LENALEA 33-T133 | 3 | 3 |  | Scheduled | 28/04/2025 | 30/04/2025
TO-25-LSA-SKL-1-02 | 110kV FEEDER - LISLEA 110-SHANKILL 110-1 | 12 | 9 | 9 | Scheduled | 28/04/2025 | 09/05/2025
TO-25-DSN-MP GIS-1-04 | 400kV FEEDER - DUNSTOWN 400-MONEYPOINT GIS 400-1 | 25 | 18 | 18 | Scheduled | 29/04/2025 | 23/05/2025
TO-25-PLA-T101/2/3/4-02 | TSO CUSTOMER TRANSFORMER - PLATIN 110-PLATIN 10-T101/2/3/4 | 14 | 9 | 9 | Scheduled | 29/04/2025 | 12/05/2025
TO-25-COW-OLD-2-02 | 110kV FEEDER - COW CROSS 110-OLDCOURT 110-2 | 2 | 2 | 2 | Reference | 30/04/2025 | 01/05/2025
TO-25-CRA-WEX-1-02 | 110kV FEEDER - CRANE 110-WEXFORD 110-1 | 143 | 100 | 100 | Scheduled | 30/04/2025 | 19/09/2025
TO-25-DND-110K1-03 | COUPLER/SECTIONALISING CB - DARNDALE 110-DARNDALE 110-110K1 | 8 | 5 | 5 | Scheduled | 30/04/2025 | 07/05/2025
TO-25-DND-110K2-03 | COUPLER/SECTIONALISING CB - DARNDALE 110-DARNDALE 110-110K2 | 8 | 5 | 5 | Scheduled | 30/04/2025 | 07/05/2025
TO-25-DND-110SA1-2CB-02 | COUPLER/SECTIONALISING CB - DARNDALE 110-DARNDALE 110-110SA1-2CB | 8 | 5 | 5 | Scheduled | 30/04/2025 | 07/05/2025
TO-25-OLD-T102-02 | DISTRIBUTION TRANSFORMER - OLDCOURT 110-OLDCOURT 10-T102 | 2 | 2 |  | Reference | 30/04/2025 | 01/05/2025
TO-25-CD-MAC-1-01 | 110kV FEEDER - CARRIGADROHID 110-MACROOM 110-1 | 100 | 69 | 69 | Scheduled | 01/05/2025 | 08/08/2025
TO-25-CDU-CRU-2-04 | 220kV FEEDER - CORDUFF 220-CRUISERATH 220-2 | 1 | 1 | 1 | Scheduled | 01/05/2025 | 01/05/2025
TO-25-220 kV B2/B4 @ CDU-02 | BUSBAR SECTION - CORDUFF 220-CORDUFF 220-220B2-B4 | 8 | 5 | 5 | Scheduled | 02/05/2025 | 09/05/2025
TO-25-CDU-220SB2-4CB-01 | COUPLER/SECTIONALISING CB - CORDUFF 220-CORDUFF 220-220SB2-4CB | 8 | 5 | 5 | Scheduled | 02/05/2025 | 09/05/2025
TO-25-BLU-MUL-1-02 | 110kV FEEDER - BLUNDELSTOWN 110-MULLINGAR 110-1 | 11 | 9 | 9 | Scheduled | 06/05/2025 | 16/05/2025
TO-25-CF-SRA-2-01 | 110kV FEEDER - CATHALEENS FALL 110-SRANANAGH 110-2 | 66 | 47 | 47 | Scheduled | 06/05/2025 | 10/07/2025
TO-25-GAL-GAL GIS-1-01 | 110kV FEEDER - GALWAY 110-GALWAY GIS 110-1 | 240 | 167 | 167 | Scheduled | 06/05/2025 | 31/12/2025
TO-25-GAL-T103-01 | DISTRIBUTION TRANSFORMER - GALWAY 110-GALWAY 10-T103 | 81 | 58 |  | Scheduled | 06/05/2025 | 25/07/2025
TO-25-220 kV A3 @ KPG-01 | BUSBAR SECTION - KILPADDOGE 220-KILPADDOGE 220-220A3 | 14 | 10 | 10 | Scheduled | 06/05/2025 | 19/05/2025
TO-25-220 kV B3 @ KPG-01 | BUSBAR SECTION - KILPADDOGE 220-KILPADDOGE 220-220B3 | 14 | 10 | 10 | Scheduled | 06/05/2025 | 19/05/2025
TO-25-KPG-220K3-02 | COUPLER/SECTIONALISING CB - KILPADDOGE 220-KILPADDOGE 220-220K3 | 14 | 10 | 10 | Scheduled | 06/05/2025 | 19/05/2025
TO-25-KPG-220SA1-3CB-02 | COUPLER/SECTIONALISING CB - KILPADDOGE 220-KILPADDOGE 220-220SA1-3CB | 14 | 10 | 10 | Scheduled | 06/05/2025 | 19/05/2025
TO-25-KPG-220SB1-3CB-02 | COUPLER/SECTIONALISING CB - KILPADDOGE 220-KILPADDOGE 220-220SB1-3CB | 14 | 10 | 10 | Scheduled | 06/05/2025 | 19/05/2025
TO-25-KPG-TB-1-01 | 220kV FEEDER - KILPADDOGE 220-TARBERT 220-1 | 14 | 10 | 10 | Scheduled | 06/05/2025 | 19/05/2025
TO-25-220 kV A2 @ LOU-02 | BUSBAR SECTION - LOUTH 220-LOUTH 220-220A2 | 25 | 19 | 19 | Scheduled | 06/05/2025 | 30/05/2025
TO-25-MP GIS-T4001-03 | GENERATOR TRANSFORMER - MONEYPOINT GIS 400-MONEYPOINT GIS G1-T4001 | 86 | 61 | 61 | Scheduled | 06/05/2025 | 30/07/2025
TO-25-220 kV A1 @ TB-01 | BUSBAR SECTION - TARBERT 220-TARBERT 220-220A1 | 14 | 10 | 10 | Scheduled | 06/05/2025 | 19/05/2025
TO-25-220 kV B1 @ TB-01 | BUSBAR SECTION - TARBERT 220-TARBERT 220-220B1 | 14 | 10 | 10 | Scheduled | 06/05/2025 | 19/05/2025
TO-25-CGG-DMY-1-01 | 110kV FEEDER - CARRIGDANGAN 110-DUNMANWAY 110-1 | 9 | 7 |  | Scheduled | 07/05/2025 | 15/05/2025
TO-25-CGG-T131-01 | GENERATOR TRANSFORMER - CARRIGDANGAN 110-CARRIGDANGAN 33-T131 | 9 | 7 | 7 | Scheduled | 07/05/2025 | 15/05/2025
TO-25-220 kV A1 @ CSH-01 | BUSBAR SECTION - CASHLA 220-CASHLA 220-220A1 | 9 | 7 | 7 | Scheduled | 07/05/2025 | 15/05/2025
TO-25-220 kV A2 @ CSH-01 | BUSBAR SECTION - CASHLA 220-CASHLA 220-220A2 | 9 | 7 | 7 | Scheduled | 07/05/2025 | 15/05/2025
TO-25-220 kV B1 @ CSH-01 | BUSBAR SECTION - CASHLA 220-CASHLA 220-220B1 | 9 | 7 |  | Scheduled | 07/05/2025 | 15/05/2025
TO-25-220 kV B2 @ CSH-01 | BUSBAR SECTION - CASHLA 220-CASHLA 220-220B2 | 9 | 7 | 7 | Scheduled | 07/05/2025 | 15/05/2025
TO-25-CSH-220K1-2-01 | COUPLER/SECTIONALISING CB - CASHLA 220-CASHLA 220-220K1-2 | 9 | 7 | 7 | Scheduled | 07/05/2025 | 15/05/2025
TO-25-GI GIS-220K2-02 | COUPLER/SECTIONALISING CB - GREAT ISLAND GIS 220-GREAT ISLAND GIS 220-220K2 | 2 | 2 | 2 | Scheduled | 07/05/2025 | 08/05/2025
TO-25-GI GIS-220SA1-2CB-01 | COUPLER/SECTIONALISING CB - GREAT ISLAND GIS 220-GREAT ISLAND GIS 220-220SA1-2CB | 2 | 2 | 2 | Scheduled | 07/05/2025 | 08/05/2025
TO-25-220 kV A2 @ KNR-01 | BUSBAR SECTION - KNOCKANURE 220-KNOCKANURE 220-220A2 | 6 | 4 | 4 | Scheduled | 07/05/2025 | 12/05/2025
TO-25-220 kV B2 @ KNR-01 | BUSBAR SECTION - KNOCKANURE 220-KNOCKANURE 220-220B2 | 6 | 4 | 4 | Scheduled | 07/05/2025 | 12/05/2025
TO-25-KNR-220K2-02 | COUPLER/SECTIONALISING CB - KNOCKANURE 220-KNOCKANURE 220-220K2 | 6 | 4 | 4 | Scheduled | 07/05/2025 | 12/05/2025
TO-25-KNR-220SA1-2CB-02 | COUPLER/SECTIONALISING CB - KNOCKANURE 220-KNOCKANURE 220-220SA1-2CB | 6 | 4 | 4 | Scheduled | 07/05/2025 | 12/05/2025
TO-25-KNR-220SB1-2CB-02 | COUPLER/SECTIONALISING CB - KNOCKANURE 220-KNOCKANURE 220-220SB1-2CB | 6 | 4 | 4 | Scheduled | 07/05/2025 | 12/05/2025
TO-25-KNR-R2002-01 | CAPACITOR/SVC/REACTOR - KNOCKANURE 220-KNOCKANURE 220-R2002 | 6 | 4 | 4 | Scheduled | 07/05/2025 | 12/05/2025
TO-25-LOU-MLN-1-01 | 110kV FEEDER - LOUTH 110-MULLAGHARLIN 110-1 | 10 | 8 | 8 | Scheduled | 07/05/2025 | 16/05/2025
TO-25-CBT-CLU-1-01 | 110kV FEEDER - CASTLEBAGOT 110-CLUTTERLAND 110-1 | 2 | 2 | 2 | Scheduled | 08/05/2025 | 09/05/2025
TO-25-110 kV B2 @ CF-03 | BUSBAR SECTION - CATHALEENS FALL 110-CATHALEENS FALL 110-110B2 | 12 | 8 | 8 | Scheduled | 08/05/2025 | 19/05/2025
TO-25-CDU-CRU-2-05 | 220kV FEEDER - CORDUFF 220-CRUISERATH 220-2 | 1 | 1 | 1 | Scheduled | 09/05/2025 | 09/05/2025
TO-25-AA GIS-T103-01 | GENERATOR TRANSFORMER - ARDNACRUSHA GIS 110-ARDNACRUSHA GIS G3-T103 | 5 | 5 | 5 | Scheduled | 12/05/2025 | 16/05/2025
TO-25-BDA-T101-01 | TSO CUSTOMER TRANSFORMER - BARODA 110-BARODA 10-T101 | 5 | 5 | 5 | Scheduled | 12/05/2025 | 16/05/2025
TO-25-BK-SKY-1-01 | 110kV FEEDER - BELLACORICK 110-SRAHNAKILLY 110-1 | 5 | 5 | 5 | Scheduled | 12/05/2025 | 16/05/2025
TO-25-BIN-T141-01 | DISTRIBUTION TRANSFORMER - BINBANE 110-BINBANE 38-T141 | 100 | 70 | 70 | Reference | 12/05/2025 | 19/08/2025
TO-25-CSH-GAL GIS-4-01 | 110kV FEEDER - CASHLA 110-GALWAY GIS 110-4 | 5 | 5 | 5 | Scheduled | 12/05/2025 | 16/05/2025
TO-25-CRA-LWD-1-05 | 110kV FEEDER - CRANE 110-LODGEWOOD 110-1 | 19 | 15 | 15 | Scheduled | 12/05/2025 | 30/05/2025
TO-25-GOR-MTH-1-01 | 110kV FEEDER - GORMAN 110-MEATH HILL 110-1 | 19 | 15 | 15 | Scheduled | 12/05/2025 | 30/05/2025
TO-25-PLS-T141-01 | DISTRIBUTION TRANSFORMER - PORTLAOISE 110-PORTLAOISE 38-T141 | 40 | 29 | 29 | Reference | 12/05/2025 | 20/06/2025
TO-25-RRU-T121-02 | GENERATOR TRANSFORMER - RATRUSSAN 110-RATRUSSAN 20-T121 | 3 | 3 | 3 | Scheduled | 12/05/2025 | 14/05/2025
TO-25-SNU-T104-02 | TSO CUSTOMER TRANSFORMER - SNUGBOROUGH 110-SNUGBOROUGH 10-T104 | 5 | 5 | 5 | Scheduled | 12/05/2025 | 16/05/2025
TO-25-SKY-110SA1-01 | SECTIONALISING DISCONNECT - SRAHNAKILLY 110-SRAHNAKILLY 110-110SA1 | 5 | 5 | 5 | Scheduled | 12/05/2025 | 16/05/2025
TO-25-SKY-110SA2-01 | SECTIONALISING DISCONNECT - SRAHNAKILLY 110-SRAHNAKILLY 110-110SA2 | 5 | 5 | 5 | Scheduled | 12/05/2025 | 16/05/2025
TO-25-SKY-T131-01 | GENERATOR TRANSFORMER - SRAHNAKILLY 110-SRAHNAKILLY 33-T131 | 5 | 5 | 5 | Scheduled | 12/05/2025 | 16/05/2025
TO-25-SKY-T132-01 | GENERATOR TRANSFORMER - SRAHNAKILLY 110-SRAHNAKILLY 33-T132 | 5 | 5 | 5 | Scheduled | 12/05/2025 | 16/05/2025
TO-25-BAL-CDU-1-04 | 110kV FEEDER - BALTRASNA 110-CORDUFF 110-1 | 2 | 2 | 2 | Scheduled | 13/05/2025 | 14/05/2025
TO-25-CLH-T122-01 | GENERATOR TRANSFORMER - CLAHANE 110-CLAHANE 20-T122 | 3 | 3 | 3 | Scheduled | 13/05/2025 | 15/05/2025
TO-25-110 kV B4 @ CDU-03 | BUSBAR SECTION - CORDUFF 110-CORDUFF 110-110B4 | 2 | 2 | 2 | Scheduled | 13/05/2025 | 14/05/2025
TO-25-CL-T101-02 | GENERATOR TRANSFORMER - CLIFF 110-CLIFF G1-T101 | 10 | 8 | 8 | Scheduled | 14/05/2025 | 23/05/2025
TO-25-GOR-T122-01 | GENERATOR TRANSFORMER - GORMAN 110-GORMAN 20-T122 | 2 | 2 | 2 | Scheduled | 14/05/2025 | 15/05/2025
TO-25-MLC-T121-02 | GENERATOR TRANSFORMER - MOUNTLUCAS 110-MOUNTLUCAS 20-T121 | 2 | 2 | 2 | Scheduled | 14/05/2025 | 15/05/2025
TO-25-DSN-KLS-1-03 | 220kV FEEDER - DUNSTOWN 220-KELLIS 220-1 | 2 | 2 | 2 | Scheduled | 15/05/2025 | 16/05/2025
TO-25-LSA-T131-02 | GENERATOR TRANSFORMER - LISLEA 110-LISLEA 33-T131 | 1 | 1 | 1 | Scheduled | 15/05/2025 | 15/05/2025
TO-25-GI-WAT-2-04 | 110kV FEEDER - GREAT ISLAND 110-WATERFORD 110-2 | 15 | 11 | 11 | Scheduled | 16/05/2025 | 30/05/2025
TO-25-KIN-T1/T2-02 | GENERATOR TRANSFORMER - KINNEGAD 110-RHODE 110-T1/T2 | 19 | 12 | 12 | Scheduled | 16/05/2025 | 03/06/2025
TO-25-WAT-110SA1-02 | SECTIONALISING DISCONNECT - WATERFORD 110-WATERFORD 110-110SA1 | 15 | 11 | 11 | Scheduled | 16/05/2025 | 30/05/2025
TO-25-WAT-110SA2-02 | SECTIONALISING DISCONNECT - WATERFORD 110-WATERFORD 110-110SA2 | 15 | 11 | 11 | Scheduled | 16/05/2025 | 30/05/2025
TO-25-WAT-T141-01 | DISTRIBUTION TRANSFORMER - WATERFORD 110-WATERFORD 38-T141 | 15 | 11 | 11 | Reference | 16/05/2025 | 30/05/2025
TO-25-AUG-CFM-2-01 | 110kV FEEDER - AUGHINISH 110-CASTLEFARM 110-2 | 12 | 10 | 10 | Scheduled | 19/05/2025 | 30/05/2025
TO-25-BOT-MLC-1-01 | 110kV FEEDER - BOGTOWN 110-MOUNTLUCAS 110-1 | 22 | 15 | 15 | Scheduled | 19/05/2025 | 09/06/2025
TO-25-BOT-T132-01 | GENERATOR TRANSFORMER - BOGTOWN 110-BOGTOWN 33-T132 | 22 | 15 | 15 | Scheduled | 19/05/2025 | 09/06/2025
TO-25-CFM-T102-01 | TSO CUSTOMER TRANSFORMER - CASTLEFARM 110-CASTLEFARM 10-T102 | 12 | 10 | 10 | Reference | 19/05/2025 | 30/05/2025
TO-25-110 kV B2 @ CLO-01 | BUSBAR SECTION - CLOGHER 110-CLOGHER 110-110B2 | 12 | 10 | 10 | Scheduled | 19/05/2025 | 30/05/2025
TO-25-FIN-110K2-3-04 | COUPLER/SECTIONALISING CB - FINGLAS 110-FINGLAS 110-110K2-3 | 227 | 158 | 158 | Scheduled | 19/05/2025 | 31/12/2025
TO-25-GLE-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - GLENLARA 110-GLENLARA 110-110SA1-2CB | 5 | 5 | 5 | Scheduled | 19/05/2025 | 23/05/2025
TO-25-GLE-T142-01 | DISTRIBUTION TRANSFORMER - GLENLARA 110-GLENLARA 38-T142 | 5 | 5 | 5 | Reference | 19/05/2025 | 23/05/2025
TO-25-GOL-T101-01 | GENERATOR TRANSFORMER - GOLAGH 110-GOLAGH 10-T101 | 12 | 10 | 10 | Scheduled | 19/05/2025 | 30/05/2025
TO-25-GOL,T-CLO-1-01 | 110kV FEEDER - GOLAGH tee-CLOGHER 110-1 | 12 | 10 | 10 | Scheduled | 19/05/2025 | 30/05/2025
TO-25-GOL,T-GOL-1-01 | 110kV FEEDER - GOLAGH tee-GOLAGH 110-1 | 12 | 10 | 10 | Scheduled | 19/05/2025 | 30/05/2025
TO-25-GOL,T-LET-1-01 | 110kV FEEDER - GOLAGH tee-LETTERKENNY 110-1 | 12 | 10 | 10 | Scheduled | 19/05/2025 | 30/05/2025
TO-25-ISH-T2002/3-01 | GENERATOR TRANSFORMER - IRISHTOWN 220-IRISHTOWN G2/3-T2002/3 | 5 | 5 | 5 | Scheduled | 19/05/2025 | 23/05/2025
TO-25-LSN-110SA1-2-03 | SECTIONALISING DISCONNECT - LISHEEN 110-LISHEEN 110-110SA1-2 | 5 | 5 | 5 | Scheduled | 19/05/2025 | 23/05/2025
TO-25-LSN-110SA2-4-03 | SECTIONALISING DISCONNECT - LISHEEN 110-LISHEEN 110-110SA2-4 | 5 | 5 | 5 | Scheduled | 19/05/2025 | 23/05/2025
TO-25-LSN-T122-03 | GENERATOR TRANSFORMER - LISHEEN 110-LISHEEN 20-T122 | 5 | 5 | 5 | Scheduled | 19/05/2025 | 23/05/2025
TO-25-LSN-T131-04 | GENERATOR TRANSFORMER - LISHEEN 110-LISHEEN 33-T131 | 5 | 5 | 5 | Scheduled | 19/05/2025 | 23/05/2025
TO-25-LSN-T142-03 | DISTRIBUTION TRANSFORMER - LISHEEN 110-LISHEEN 38-T142 | 5 | 5 | 5 | Reference | 19/05/2025 | 23/05/2025
TO-25-LSN-THU-1-03 | 110kV FEEDER - LISHEEN 110-THURLES 110-1 | 5 | 5 | 5 | Scheduled | 19/05/2025 | 23/05/2025
TO-25-RYB GIS-T105-01 | TSO CUSTOMER TRANSFORMER - RYEBROOK GIS 110-RYEBROOK 10-T105 | 12 | 10 | 10 | Scheduled | 19/05/2025 | 30/05/2025
TO-25-WEX-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - WEXFORD 110-WEXFORD 110-110SA1-2CB | 12 | 10 | 10 | Scheduled | 19/05/2025 | 30/05/2025
TO-25-WEX-CAP2-01 | CAPACITOR/SVC/REACTOR - WEXFORD 110-WEXFORD 110-CAP2 | 12 | 10 | 10 | Scheduled | 19/05/2025 | 30/05/2025
TO-25-WEX-CAP4-01 | CAPACITOR/SVC/REACTOR - WEXFORD 110-WEXFORD 110-CAP4 | 12 | 10 | 10 | Scheduled | 19/05/2025 | 30/05/2025
TO-25-WEX-T122-01 | DISTRIBUTION TRANSFORMER - WEXFORD 110-WEXFORD 20-T122 | 12 | 10 | 10 | Reference | 19/05/2025 | 30/05/2025
TO-25-WEX-T142-01 | DISTRIBUTION TRANSFORMER - WEXFORD 110-WEXFORD 38-T142 | 12 | 10 | 10 | Reference | 19/05/2025 | 30/05/2025
TO-25-BDA-MON-1-01 | 110kV FEEDER - BARODA 110-MONREAD 110-1 | 3 | 3 | 3 | Scheduled | 20/05/2025 | 22/05/2025
TO-25-220 kV A4 @ CSH-03 | BUSBAR SECTION - CASHLA 220-CASHLA 220-220A4 | 2 | 2 | 2 | Scheduled | 20/05/2025 | 21/05/2025
TO-25-CSH-PRO-1-03 | 220kV FEEDER - CASHLA 220-PROSPECT 220-1 | 2 | 2 | 2 | Scheduled | 20/05/2025 | 21/05/2025
TO-25-KLN-LIM-1-03 | 110kV FEEDER - KILLONAN 110-LIMERICK 110-1 | 18 | 13 | 13 | Scheduled | 20/05/2025 | 06/06/2025
TO-25-LSA-T131-01 | GENERATOR TRANSFORMER - LISLEA 110-LISLEA 33-T131 | 3 | 3 | 3 | Scheduled | 20/05/2025 | 22/05/2025
TO-25-CKM-PB-1-06 | 220kV FEEDER - CARRICKMINES 220-POOLBEG 220-1 | 2 | 0 | 0 | Scheduled | 24/05/2025 | 25/05/2025
TO-25-BGH-110SA1-01 | SECTIONALISING DISCONNECT - BOGGERAGH 110-BOGGERAGH 110-110SA1 | 17 | 12 | 12 | Scheduled | 26/05/2025 | 11/06/2025
TO-25-BGH-110SA2-01 | SECTIONALISING DISCONNECT - BOGGERAGH 110-BOGGERAGH 110-110SA2 | 17 | 12 | 12 | Scheduled | 26/05/2025 | 11/06/2025
TO-25-BGH-CLA-1-01 | 110kV FEEDER - BOGGERAGH 110-CLASHAVOON 110-1 | 17 | 12 | 12 | Scheduled | 26/05/2025 | 11/06/2025
TO-25-BGH-T121-02 | GENERATOR TRANSFORMER - BOGGERAGH 110-BOGGERAGH 20-T121 | 17 | 12 | 12 | Scheduled | 26/05/2025 | 11/06/2025
TO-25-BGH-T132-01 | GENERATOR TRANSFORMER - BOGGERAGH 110-BOGGERAGH 33-T132 | 17 | 12 | 12 | Scheduled | 26/05/2025 | 11/06/2025
TO-25-BGH-T142-01 | DISTRIBUTION TRANSFORMER - BOGGERAGH 110-BOGGERAGH 38-T142 | 17 | 12 | 12 | Reference | 26/05/2025 | 11/06/2025
TO-25-CSH-CLN-1-03 | 110kV FEEDER - CASHLA 110-CLOON 110-1 | 12 | 9 | 9 | Scheduled | 26/05/2025 | 06/06/2025
TO-25-110 kV B1 @ CLA-02 | BUSBAR SECTION - CLASHAVOON 110-CLASHAVOON 110-110B1 | 17 | 12 | 12 | Scheduled | 26/05/2025 | 11/06/2025
TO-25-DEY-T134-02 | GENERATOR TRANSFORMER - DERRYCARNEY 110-DERRYCARNEY 33-T134 | 1 | 1 | 1 | Scheduled | 26/05/2025 | 26/05/2025
TO-25-KPG-T2102-02 | TRANSFORMER - KILPADDOGE 220-KILPADDOGE 110-T2102 | 5 | 5 | 5 | Scheduled | 26/05/2025 | 30/05/2025
TO-25-KTL-CAP1-01 | CAPACITOR/SVC/REACTOR - KILTEEL 110-KILTEEL 110-CAP1 | 5 | 5 | 5 | Scheduled | 26/05/2025 | 30/05/2025
TO-25-LIM-MTN-1-03 | 110kV FEEDER - LIMERICK 110-MONETEEN 110-1 | 5 | 5 | 5 | Scheduled | 26/05/2025 | 30/05/2025
TO-25-110 kV B1 @ CSH-06 | BUSBAR SECTION - CASHLA 110-CASHLA 110-110B1 | 12 | 8 | 8 | Scheduled | 27/05/2025 | 07/06/2025
TO-25-220 kV A1 @ WOO-04 | BUSBAR SECTION - WOODLAND 220-WOODLAND 220-220A1 | 4 | 4 | 4 | Scheduled | 27/05/2025 | 30/05/2025
TO-25-WOO-T4201-05 | TRANSFORMER - WOODLAND 400-WOODLAND 220-T4201 | 4 | 4 | 4 | Scheduled | 27/05/2025 | 30/05/2025
TO-25-DDK-110SA1-02 | SECTIONALISING DISCONNECT - DUNDALK 110-DUNDALK 110-110SA1 | 9 | 6 | 6 | Scheduled | 29/05/2025 | 06/06/2025
TO-25-DDK-110SA2-01 | SECTIONALISING DISCONNECT - DUNDALK 110-DUNDALK 110-110SA2 | 9 | 6 | 6 | Scheduled | 29/05/2025 | 06/06/2025
TO-25-DDK-LOU-1-03 | 110kV FEEDER - DUNDALK 110-LOUTH 110-1 | 9 | 6 | 6 | Scheduled | 29/05/2025 | 06/06/2025
TO-25-DDK-T142-01 | DISTRIBUTION TRANSFORMER - DUNDALK 110-DUNDALK 38-T142 | 9 | 6 | 6 | Reference | 29/05/2025 | 06/06/2025
TO-25-220 kV A2 @ FIN-08 | BUSBAR SECTION - FINGLAS 220-FINGLAS 220-220A2 | 37 | 26 | 26 | Scheduled | 29/05/2025 | 04/07/2025
TO-25-220 kV B2 @ FIN-05 | BUSBAR SECTION - FINGLAS 220-FINGLAS 220-220B2 | 37 | 26 | 26 | Scheduled | 29/05/2025 | 04/07/2025
TO-25-FIN-220K2-10 | COUPLER/SECTIONALISING CB - FINGLAS 220-FINGLAS 220-220K2 | 37 | 26 | 26 | Scheduled | 29/05/2025 | 04/07/2025
TO-25-FIN-220SA1-2CB-14 | COUPLER/SECTIONALISING CB - FINGLAS 220-FINGLAS 220-220SA1-2CB | 37 | 26 | 26 | Scheduled | 29/05/2025 | 04/07/2025
TO-25-FIN-220SB1-2CB-11 | COUPLER/SECTIONALISING CB - FINGLAS 220-FINGLAS 220-220SB1-2CB | 37 | 26 | 26 | Scheduled | 29/05/2025 | 04/07/2025
TO-25-FIN-FIN GIS-2-03 | 110kV FEEDER - FINGLAS 110-FINGLAS GIS 110-2 | 37 | 26 | 26 | Scheduled | 29/05/2025 | 04/07/2025
TO-25-FIN-T2104-03 | TRANSFORMER - FINGLAS 220-FINGLAS 110-T2104 | 37 | 26 | 26 | Scheduled | 29/05/2025 | 04/07/2025
TO-25-TTU-131-03 | GENERATOR TRANSFORMER - TULLABEG 110-TULLABEG 33-T131 | 1 | 1 | 1 | Scheduled | 29/05/2025 | 29/05/2025
TO-25-BUT-KTN-1-04 | 110kV FEEDER - BUTLERSTOWN 110-KILLOTERAN 110-1 | 71 | 50 | 50 | Scheduled | 03/06/2025 | 12/08/2025
TO-25-CSH-GAL GIS-2-01 | 110kV FEEDER - CASHLA 110-GALWAY GIS 110-2 | 7 | 5 | 5 | Scheduled | 03/06/2025 | 09/06/2025
TO-25-CDK-LWD-1-02 | 110kV FEEDER - CASTLEDOCKRELL 110-LODGEWOOD 110-1 | 4 | 4 | 4 | Scheduled | 03/06/2025 | 06/06/2025
TO-25-CDK-T121-02 | GENERATOR TRANSFORMER - CASTLEDOCKRELL 110-CASTLEDOCKRELL 20-T121 | 4 | 4 | 4 | Reference | 03/06/2025 | 06/06/2025
TO-25-GOR-NAV-3-01 | 110kV FEEDER - GORMAN 110-NAVAN 110-3 | 4 | 4 | 4 | Scheduled | 03/06/2025 | 06/06/2025
TO-25-KTN-110SA1-02 | SECTIONALISING DISCONNECT - KILLOTERAN 110-KILLOTERAN 110-110SA1 | 71 | 50 | 50 | Scheduled | 03/06/2025 | 12/08/2025
TO-25-KTN-110SA2-02 | SECTIONALISING DISCONNECT - KILLOTERAN 110-KILLOTERAN 110-110SA2 | 71 | 50 | 50 | Scheduled | 03/06/2025 | 12/08/2025
TO-25-KTN-T101-01 | DISTRIBUTION TRANSFORMER - KILLOTERAN 110-KILLOTERAN 10-T101 | 71 | 50 | 50 | Reference | 03/06/2025 | 12/08/2025
TO-25-OUG-T141-01 | DISTRIBUTION TRANSFORMER - OUGHTRAGH 110-OUGHTRAGH 38-T141 | 10 | 8 | 8 | Reference | 03/06/2025 | 12/06/2025
TO-25-OUG,T-KER-1-02 | 110kV FEEDER - OUGHTRAGH tee-KNOCKEARAGH 110-1 | 10 | 8 | 8 | Scheduled | 03/06/2025 | 12/06/2025
TO-25-OUG,T-OUG-1-01 | 110kV FEEDER - OUGHTRAGH tee-OUGHTRAGH 110-1 | 10 | 8 | 8 | Scheduled | 03/06/2025 | 12/06/2025
TO-25-OUG,T-TRL-1-04 | 110kV FEEDER - OUGHTRAGH tee-TRALEE 110-1 | 10 | 8 | 8 | Scheduled | 03/06/2025 | 12/06/2025
TO-25-110 kV A3 @ RYB GIS-01 | BUSBAR SECTION - RYEBROOK GIS 110-RYEBROOK GIS 110-110A3 | 11 | 9 | 9 | Scheduled | 03/06/2025 | 13/06/2025
TO-25-110 kV B3 @ RYB GIS-01 | BUSBAR SECTION - RYEBROOK GIS 110-RYEBROOK GIS 110-110B3 | 11 | 9 | 9 | Scheduled | 03/06/2025 | 13/06/2025
TO-25-RYB GIS-110K3-02 | COUPLER/SECTIONALISING CB - RYEBROOK GIS 110-RYEBROOK GIS 110-110K3 | 11 | 9 | 9 | Scheduled | 03/06/2025 | 13/06/2025
TO-25-RYB GIS-110SA1-3CB-02 | COUPLER/SECTIONALISING CB - RYEBROOK GIS 110-RYEBROOK GIS 110-110SA1-3CB | 11 | 9 | 9 | Scheduled | 03/06/2025 | 13/06/2025
TO-25-RYB GIS-110SB1-3CB-03 | COUPLER/SECTIONALISING CB - RYEBROOK GIS 110-RYEBROOK GIS 110-110SB1-3CB | 11 | 9 | 9 | Scheduled | 03/06/2025 | 13/06/2025
TO-25-RYB GIS-T106-01 | TSO CUSTOMER TRANSFORMER - RYEBROOK GIS 110-RYEBROOK 10-T106 | 14 | 10 | 10 | Scheduled | 03/06/2025 | 16/06/2025
TO-25-BRT-CLE-2-01 | 220kV FEEDER - BRACETOWN 220-CLONEE 220-2 | 9 | 7 | 7 | Scheduled | 04/06/2025 | 12/06/2025
TO-25-220 kV A1 @ CLE-02 | BUSBAR SECTION - CLONEE 220-CLONEE 220-220A1 | 9 | 7 | 7 | Scheduled | 04/06/2025 | 12/06/2025
TO-25-220 kV B1 @ CLE-02 | BUSBAR SECTION - CLONEE 220-CLONEE 220-220B1 | 9 | 7 | 7 | Scheduled | 04/06/2025 | 12/06/2025
TO-25-CLE-220K1-02 | COUPLER/SECTIONALISING CB - CLONEE 220-CLONEE 220-220K1 | 9 | 7 | 7 | Scheduled | 04/06/2025 | 12/06/2025
TO-25-CLE-220SA1-2CB-03 | COUPLER/SECTIONALISING CB - CLONEE 220-CLONEE 220-220SA1-2CB | 9 | 7 | 7 | Scheduled | 04/06/2025 | 12/06/2025
TO-25-CLE-220SB1-2CB-03 | COUPLER/SECTIONALISING CB - CLONEE 220-CLONEE 220-220SB1-2CB | 9 | 7 | 7 | Scheduled | 04/06/2025 | 12/06/2025
TO-25-IA-T101-05 | GENERATOR TRANSFORMER - INNISCARRA 110-INNISCARRA G1-T101 | 9 | 7 | 7 | Scheduled | 04/06/2025 | 12/06/2025
TO-25-BLU-MUL-1-01 | 110kV FEEDER - BLUNDELSTOWN 110-MULLINGAR 110-1 | 2 | 2 | 2 | Scheduled | 05/06/2025 | 06/06/2025
TO-25-CUS-110SA1-2CB-02 | COUPLER/SECTIONALISING CB - CUSHALING 110-CUSHALING 110-110SA1-2CB | 2 | 2 | 2 | Scheduled | 05/06/2025 | 06/06/2025
TO-25-CUS-KIR-1-02 | 110kV FEEDER - CUSHALING 110-KILCUMBER 110-1 | 2 | 2 | 2 | Scheduled | 05/06/2025 | 06/06/2025
TO-25-CUS-MLC-1-02 | 110kV FEEDER - CUSHALING 110-MOUNTLUCAS 110-1 | 2 | 2 | 2 | Scheduled | 05/06/2025 | 06/06/2025
TO-25-CUS-T101-02 | GENERATOR TRANSFORMER - CUSHALING 110-CUSHALING G1-T101 | 2 | 2 | 2 | Scheduled | 05/06/2025 | 06/06/2025
TO-25-KIR-T131-03 | GENERATOR TRANSFORMER - KILCUMBER 110-KILCUMBER 33-T131 | 2 | 2 | 2 | Scheduled | 05/06/2025 | 06/06/2025
TO-25-MOY-CAP1-01 | CAPACITOR/SVC/REACTOR - MOY 110-MOY 110-CAP1 | 7 | 5 | 5 | Scheduled | 05/06/2025 | 11/06/2025
TO-25-MUL-110SA1-2CB-02 | COUPLER/SECTIONALISING CB - MULLINGAR 110-MULLINGAR 110-110SA1-2CB | 2 | 2 | 2 | Scheduled | 05/06/2025 | 06/06/2025
TO-25-MUL-CAP2-02 | CAPACITOR/SVC/REACTOR - MULLINGAR 110-MULLINGAR 110-CAP2 | 2 | 2 | 2 | Scheduled | 05/06/2025 | 06/06/2025
TO-25-MUL-T102-01 | DISTRIBUTION TRANSFORMER - MULLINGAR 110-MULLINGAR 10-T102 | 2 | 2 | 2 | Reference | 05/06/2025 | 06/06/2025
TO-25-MUL-T142-01 | DISTRIBUTION TRANSFORMER - MULLINGAR 110-MULLINGAR 38-T142 | 2 | 2 | 2 | Reference | 05/06/2025 | 06/06/2025
TO-25-SH-220K1-2-01 | COUPLER/SECTIONALISING CB - SHANNONBRIDGE 220-SHANNONBRIDGE 220-220K1-2 | 2 | 2 | 2 | Scheduled | 05/06/2025 | 06/06/2025
TO-25-AA GIS-T101-01 | GENERATOR TRANSFORMER - ARDNACRUSHA GIS 110-ARDNACRUSHA GIS G1-T101 | 5 | 5 | 5 | Scheduled | 09/06/2025 | 13/06/2025
TO-25-AUG-SK-4-01 | 110kV FEEDER - AUGHINISH 110-SEALROCK 110-4 | 5 | 5 | 5 | Scheduled | 09/06/2025 | 13/06/2025
TO-25-BOT-T132-03 | GENERATOR TRANSFORMER - BOGTOWN 110-BOGTOWN 33-T132 | 1 | 1 | 1 | Scheduled | 09/06/2025 | 09/06/2025
TO-25-220 kV A1/A2/A3/A4 @ CKM GIS-01 | BUSBAR SECTION - CARRICKMINES GIS 220-CARRICKMINES GIS 220-220A1-A2-A3-A4 | 5 | 5 | 5 | Scheduled | 09/06/2025 | 13/06/2025
TO-25-CKM GIS-220K3-01 | COUPLER/SECTIONALISING CB - CARRICKMINES GIS 220-CARRICKMINES GIS 220-220K3 | 5 | 5 | 5 | Scheduled | 09/06/2025 | 13/06/2025
TO-25-CKM GIS-220K4-01 | COUPLER/SECTIONALISING CB - CARRICKMINES GIS 220-CARRICKMINES GIS 220-220K4 | 5 | 5 | 5 | Scheduled | 09/06/2025 | 13/06/2025
TO-25-CKM GIS-220SA1-2CB-01 | COUPLER/SECTIONALISING CB - CARRICKMINES GIS 220-CARRICKMINES GIS 220-22SA1-2CB | 5 | 5 | 5 | Scheduled | 09/06/2025 | 13/06/2025
TO-25-CKM GIS-220SA1-3CB-02 | COUPLER/SECTIONALISING CB - CARRICKMINES GIS 220-CARRICKMINES GIS 220-22SA1-3CB | 5 | 5 | 5 | Scheduled | 09/06/2025 | 13/06/2025
TO-25-CKM GIS-220SA2-4CB-02 | COUPLER/SECTIONALISING CB - CARRICKMINES GIS 220-CARRICKMINES GIS 220-22SA2-4CB | 5 | 5 | 5 | Scheduled | 09/06/2025 | 13/06/2025
TO-25-220 kV A2 @ CDU-02 | BUSBAR SECTION - CORDUFF 220-CORDUFF 220-220A2 | 5 | 5 | 5 | Scheduled | 09/06/2025 | 13/06/2025
TO-25-220 kV A4 @ CDU-02 | BUSBAR SECTION - CORDUFF 220-CORDUFF 220-220A4 | 5 | 5 | 5 | Scheduled | 09/06/2025 | 13/06/2025
TO-25-220 kV B2 @ CDU-02 | BUSBAR SECTION - CORDUFF 220-CORDUFF 220-220B2 | 5 | 5 | 5 | Scheduled | 09/06/2025 | 13/06/2025
TO-25-220 kV B4 @ CDU-02 | BUSBAR SECTION - CORDUFF 220-CORDUFF 220-220B4 | 5 | 5 | 5 | Scheduled | 09/06/2025 | 13/06/2025
TO-25-CDU-220SA2-4CB-02 | COUPLER/SECTIONALISING CB - CORDUFF 220-CORDUFF 220-220SA2-4CB | 5 | 5 | 5 | Scheduled | 09/06/2025 | 13/06/2025
TO-25-CDU-220SB2-4CB-02 | COUPLER/SECTIONALISING CB - CORDUFF 220-CORDUFF 220-220SB2-4CB | 5 | 5 | 5 | Scheduled | 09/06/2025 | 13/06/2025
TO-25-220 kV B1 @ CUL-01 | BUSBAR SECTION - CULLENAGH 220-CULLENAGH 220-220B1 | 3 | 3 | 3 | Scheduled | 09/06/2025 | 11/06/2025
TO-25-CUL-GI GIS-1-01 | 220kV FEEDER - CULLENAGH 220-GREAT ISLAND GIS 220-1 | 3 | 3 | 3 | Scheduled | 09/06/2025 | 11/06/2025
TO-25-CUN-110SA1-01 | SECTIONALISING DISCONNECT - CUNGHILL 110-CUNGHILL 110-110SA1 | 5 | 5 | 5 | Scheduled | 09/06/2025 | 13/06/2025
TO-25-CUN-110SA2-01 | SECTIONALISING DISCONNECT - CUNGHILL 110-CUNGHILL 110-110SA2 | 5 | 5 | 5 | Scheduled | 09/06/2025 | 13/06/2025
TO-25-CUN-SLI-1-05 | 110kV FEEDER - CUNGHILL 110-SLIGO 110-1 | 5 | 5 |  | Scheduled | 09/06/2025 | 13/06/2025
TO-25-CUN-T121-02 | GENERATOR TRANSFORMER - CUNGHILL 110-CUNGHILL 20-T121 | 5 | 5 | 5 | Scheduled | 09/06/2025 | 13/06/2025
TO-25-CUS-NEW-1-05 | 110kV FEEDER - CUSHALING 110-NEWBRIDGE 110-1 | 3 | 3 | 3 | Scheduled | 09/06/2025 | 11/06/2025
TO-25-LIM-RAT-1-02 | 110kV FEEDER - LIMERICK 110-RATHKEALE 110-1 | 5 | 5 | 5 | Scheduled | 09/06/2025 | 13/06/2025
TO-25-OBE-PLA-1-02 | 110kV FEEDER - OLDBRIDGE 110-PLATIN 110-1 | 71 | 50 | 50 | Scheduled | 09/06/2025 | 18/08/2025
TO-25-SK-T104-01 | GENERATOR TRANSFORMER - SEALROCK 110-SEALROCK G4-T104 | 5 | 5 | 5 | Scheduled | 09/06/2025 | 13/06/2025
TO-25-SHL-D1/CB2-02 | COUPLER/SECTIONALISING CB - SHELLYBANKS 220-SHELLYBANKS 220-D1/CB2 | 5 | 5 | 5 | Scheduled | 09/06/2025 | 13/06/2025
TO-25-SHL-D1/CB3-02 | COUPLER/SECTIONALISING CB - SHELLYBANKS 220-SHELLYBANKS 220-D1/CB3 | 5 | 5 | 5 | Scheduled | 09/06/2025 | 13/06/2025
TO-25-SHL-T2014-01 | GENERATOR TRANSFORMER - SHELLYBANKS 220-SHELLYBANKS G4-T2014 | 5 | 5 | 5 | Scheduled | 09/06/2025 | 13/06/2025
TO-25-SLB-T132-02 | GENERATOR TRANSFORMER - SLIABH BAWN 110-SLIABH BAWN 33-T132 | 2 | 2 | 2 | Scheduled | 11/06/2025 | 12/06/2025
TO-25-110 kV B1 @ CF-05 | BUSBAR SECTION - CATHALEENS FALL 110-CATHALEENS FALL 110-110B1 | 1 | 1 | 1 | Scheduled | 12/06/2025 | 12/06/2025
TO-25-CL-T101-05 | GENERATOR TRANSFORMER - CLIFF 110-CLIFF G1-T101 | 1 | 1 | 1 | Scheduled | 12/06/2025 | 12/06/2025
TO-25-CL-T102-03 | GENERATOR TRANSFORMER - CLIFF 110-CLIFF G2-T102 | 1 | 1 | 1 | Scheduled | 12/06/2025 | 12/06/2025
TO-25-220 kV A1 @ CUL-01 | BUSBAR SECTION - CULLENAGH 220-CULLENAGH 220-220A1 | 2 | 2 | 2 | Scheduled | 12/06/2025 | 13/06/2025
TO-25-CUL-T2101-03 | TRANSFORMER - CULLENAGH 220-CULLENAGH 110-T2101 | 2 | 2 | 2 | Scheduled | 12/06/2025 | 13/06/2025
TO-25-TAW-T1/T2-01 | GENERATOR TRANSFORMER - TAWNAGHMORE 110-TAWNAGHMORE 10-T1/T2 | 15 | 11 | 11 | Scheduled | 13/06/2025 | 27/06/2025
TO-25-TAW-T3-01 | GENERATOR TRANSFORMER - TAWNAGHMORE 110-TAWNAGHMORE 10-T3 | 15 | 11 | 11 | Scheduled | 13/06/2025 | 27/06/2025
TO-25-CKM-PB-1-03 | 220kV FEEDER - CARRICKMINES 220-POOLBEG 220-1 | 2 | 0 | 0 | Scheduled | 14/06/2025 | 15/06/2025
TO-25-BK-CBR-1-01 | 110kV FEEDER - BELLACORICK 110-CASTLEBAR 110-1 | 5 | 5 | 5 | Scheduled | 16/06/2025 | 20/06/2025
TO-25-BRT-CLE-4-01 | 220kV FEEDER - BRACETOWN 220-CLONEE 220-4 | 5 | 5 | 5 | Scheduled | 16/06/2025 | 20/06/2025
TO-25-CBR-110SA1-2CB-03 | COUPLER/SECTIONALISING CB - CASTLEBAR 110-CASTLEBAR 110-110SA1-2CB | 5 | 5 | 5 | Scheduled | 16/06/2025 | 20/06/2025
TO-25-CBR-CLN-1-02 | 110kV FEEDER - CASTLEBAR 110-CLOON 110-1 | 5 | 5 | 5 | Scheduled | 16/06/2025 | 20/06/2025
TO-25-CBR-SVC-04 | CAPACITOR/SVC/REACTOR - CASTLEBAR 110-CASTLEBAR 110-SVC | 5 | 5 | 5 | Scheduled | 16/06/2025 | 20/06/2025
TO-25-CBR-T141-01 | DISTRIBUTION TRANSFORMER - CASTLEBAR 110-CASTLEBAR 38-T141 | 5 | 5 | 5 | Reference | 16/06/2025 | 20/06/2025
TO-25-110 kV B2 @ CLO-02 | BUSBAR SECTION - CLOGHER 110-CLOGHER 110-110B2 | 4 | 4 | 4 | Scheduled | 16/06/2025 | 19/06/2025
TO-25-CLO-MRY-1-01 | 110kV FEEDER - CLOGHER 110-MULREAVY 110-1 | 4 | 4 | 4 | Scheduled | 16/06/2025 | 19/06/2025
TO-25-220 kV A1 @ CLE-03 | BUSBAR SECTION - CLONEE 220-CLONEE 220-220A1 | 5 | 5 | 5 | Scheduled | 16/06/2025 | 20/06/2025
TO-25-220 kV B1 @ CLE-03 | BUSBAR SECTION - CLONEE 220-CLONEE 220-220B1 | 5 | 5 | 5 | Scheduled | 16/06/2025 | 20/06/2025
TO-25-CLE-220K1-03 | COUPLER/SECTIONALISING CB - CLONEE 220-CLONEE 220-220K1 | 5 | 5 | 5 | Scheduled | 16/06/2025 | 20/06/2025
TO-25-CLE-220SA1-2CB-04 | COUPLER/SECTIONALISING CB - CLONEE 220-CLONEE 220-220SA1-2CB | 5 | 5 | 5 | Scheduled | 16/06/2025 | 20/06/2025
TO-25-CLE-220SB1-2CB-04 | COUPLER/SECTIONALISING CB - CLONEE 220-CLONEE 220-220SB1-2CB | 5 | 5 | 5 | Scheduled | 16/06/2025 | 20/06/2025
TO-25-GAL GIS-SAL-1-02 | 110kV FEEDER - GALWAY GIS 110-SALTHILL 110-1 | 12 | 10 | 10 | Scheduled | 16/06/2025 | 27/06/2025
TO-25-KPG-RAT-1-02 | 110kV FEEDER - KILPADDOGE 110-RATHKEALE 110-1 | 5 | 5 | 5 | Scheduled | 16/06/2025 | 20/06/2025
TO-25-MP GIS-T4002-03 | GENERATOR TRANSFORMER - MONEYPOINT GIS 400-MONEYPOINT GIS G2-T4002 | 4 | 4 | 4 | Scheduled | 16/06/2025 | 19/06/2025
TO-25-MRY-T131-01 | GENERATOR TRANSFORMER - MULREAVY 110-MULREAVY 33-T131 | 4 | 4 | 4 | Scheduled | 16/06/2025 | 19/06/2025
TO-25-RYB GIS-T107-01 | TSO CUSTOMER TRANSFORMER - RYEBROOK GIS 110-RYEBROOK 10-T107 | 12 | 10 | 10 | Scheduled | 16/06/2025 | 27/06/2025
TO-25-SAL-110SA1-2CB-02 | COUPLER/SECTIONALISING CB - SALTHILL 110-SALTHILL 110-110SA1-2CB | 12 | 10 | 10 | Scheduled | 16/06/2025 | 27/06/2025
TO-25-SAL-T101-01 | DISTRIBUTION TRANSFORMER - SALTHILL 110-SALTHILL 10-T101 | 12 | 10 | 10 | Reference | 16/06/2025 | 27/06/2025
TO-25-SAL-T141-01 | DISTRIBUTION TRANSFORMER - SALTHILL 110-SALTHILL 38-T141 | 12 | 10 | 10 | Reference | 16/06/2025 | 27/06/2025
TO-25-220 kV A1 @ AD-03 | BUSBAR SECTION - AGHADA 220-AGHADA 220-220A1 | 1 | 1 | 1 | Scheduled | 17/06/2025 | 17/06/2025
TO-25-220 kV A2 @ AD-03 | BUSBAR SECTION - AGHADA 220-AGHADA 220-220A2 | 1 | 1 | 1 | Scheduled | 17/06/2025 | 17/06/2025
TO-25-AD-220K1-02 | COUPLER/SECTIONALISING CB - AGHADA 220-AGHADA 220-220K1 | 1 | 1 | 1 | Scheduled | 17/06/2025 | 17/06/2025
TO-25-AD-T2011/12-03 | GENERATOR TRANSFORMER - AGHADA 220-AGHADA G11/12-T2011/12 | 1 | 1 | 1 | Scheduled | 17/06/2025 | 17/06/2025
TO-25-DGY-FIN GIS-1-01 | 110kV FEEDER - DUNSOGHLY 110-FINGLAS GIS 110-1 | 3 | 3 | 3 | Scheduled | 17/06/2025 | 19/06/2025
TO-25-DGY-T101-01 | GENERATOR TRANSFORMER - DUNSOGHLY 110-DUNSOGHLY 11-T101 | 3 | 3 | 3 | Scheduled | 17/06/2025 | 19/06/2025
TO-25-110 kV B2 @ KBY-01 | BUSBAR SECTION - KILBARRY 110-KILBARRY 110-110B2 | 8 | 6 | 6 | Scheduled | 17/06/2025 | 24/06/2025
TO-25-KBY-MAL-1-01 | 110kV FEEDER - KILBARRY 110-MALLOW 110-1 | 8 | 6 | 6 | Scheduled | 17/06/2025 | 24/06/2025
TO-25-LOU-WOO-1-04 | 220kV FEEDER - LOUTH 220-WOODLAND 220-1 | 3 | 3 | 3 | Scheduled | 17/06/2025 | 19/06/2025
TO-25-SHL-D2/CB2-02 | COUPLER/SECTIONALISING CB - SHELLYBANKS 220-SHELLYBANKS 220-D2/CB2 | 12 | 9 | 9 | Scheduled | 17/06/2025 | 28/06/2025
TO-25-SHL-D2/CB3-02 | COUPLER/SECTIONALISING CB - SHELLYBANKS 220-SHELLYBANKS 220-D2/CB3 | 12 | 9 | 9 | Scheduled | 17/06/2025 | 28/06/2025
TO-25-SHL-T2015-01 | GENERATOR TRANSFORMER - SHELLYBANKS 220-SHELLYBANKS G5-T2015 | 12 | 9 | 9 | Scheduled | 17/06/2025 | 28/06/2025
TO-25-220 kV A2 @ WOO-07 | BUSBAR SECTION - WOODLAND 220-WOODLAND 220-220A2 | 3 | 3 | 3 | Scheduled | 17/06/2025 | 19/06/2025
TO-25-KLN-SH-1-04 | 220kV FEEDER - KILLONAN 220-SHANNONBRIDGE 220-1 | 3 | 3 | 3 | Scheduled | 18/06/2025 | 20/06/2025
TO-25-CKM-PB-1-04 | 220kV FEEDER - CARRICKMINES 220-POOLBEG 220-1 | 2 | 0 | 0 | Scheduled | 21/06/2025 | 22/06/2025
TO-25-ATE-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - ATHEA 110-ATHEA 110-110SA1-2CB | 5 | 5 | 5 | Scheduled | 23/06/2025 | 27/06/2025
TO-25-ATE-DRO-1-01 | 110kV FEEDER - ATHEA 110-DROMADA 110-1 | 5 | 5 | 5 | Scheduled | 23/06/2025 | 27/06/2025
TO-25-ATE-KNR-1-01 | 110kV FEEDER - ATHEA 110-KNOCKANURE 110-1 | 5 | 5 | 5 | Scheduled | 23/06/2025 | 27/06/2025
TO-25-ATE-T121-01 | GENERATOR TRANSFORMER - ATHEA 110-ATHEA 20-T121 | 5 | 5 | 5 | Scheduled | 23/06/2025 | 27/06/2025
TO-25-ATE-TOB-1-01 | 110kV FEEDER - ATHEA 110-TOBERTOREEN 110-1 | 5 | 5 | 5 | Scheduled | 23/06/2025 | 27/06/2025
TO-25-CSH-110K1-2-03 | COUPLER/SECTIONALISING CB - CASHLA 110-CASHLA 110-110K1-2 | 8 | 6 | 6 | Scheduled | 23/06/2025 | 30/06/2025
TO-25-CSH-DLT-1-02 | 110kV FEEDER - CASHLA 110-DALTON 110-1 | 12 | 10 | 10 | Scheduled | 23/06/2025 | 04/07/2025
TO-25-110 kV B1 @ CF-01 | BUSBAR SECTION - CATHALEENS FALL 110-CATHALEENS FALL 110-110B1 | 9 | 7 | 7 | Scheduled | 23/06/2025 | 01/07/2025
TO-25-CF-CLO-1-02 | 110kV FEEDER - CATHALEENS FALL 110-CLOGHER 110-1 | 9 | 7 | 7 | Scheduled | 23/06/2025 | 01/07/2025
TO-25-CF-T103-01 | GENERATOR TRANSFORMER - CATHALEENS FALL 110-CATHALEENS FALL G3-T103 | 12 | 10 | 10 | Scheduled | 23/06/2025 | 04/07/2025
TO-25-110 kV B1 @ CLO-01 | BUSBAR SECTION - CLOGHER 110-CLOGHER 110-110B1 | 12 | 10 | 10 | Scheduled | 23/06/2025 | 04/07/2025
TO-25-DRO-T121-01 | GENERATOR TRANSFORMER - DROMADA 110-DROMADA 20-T121 | 5 | 5 | 5 | Scheduled | 23/06/2025 | 27/06/2025
TO-25-KLN-SH-1-01 | 220kV FEEDER - KILLONAN 220-SHANNONBRIDGE 220-1 | 5 | 5 | 5 | Scheduled | 23/06/2025 | 27/06/2025
TO-25-110 kV B1 @ KNR-01 | BUSBAR SECTION - KNOCKANURE 110-KNOCKANURE 110-110B1 | 5 | 5 | 5 | Scheduled | 23/06/2025 | 27/06/2025
TO-25-KNR-110K1-01 | COUPLER/SECTIONALISING CB - KNOCKANURE 110-KNOCKANURE 110-110K1 | 5 | 5 | 5 | Scheduled | 23/06/2025 | 27/06/2025
TO-25-KNR-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - KNOCKANURE 110-KNOCKANURE 110-110SA1-2CB | 5 | 5 | 5 | Scheduled | 23/06/2025 | 27/06/2025
TO-25-KNR-110SB1-2CB-01 | COUPLER/SECTIONALISING CB - KNOCKANURE 110-KNOCKANURE 110-110SB1-2CB | 5 | 5 | 5 | Scheduled | 23/06/2025 | 27/06/2025
TO-25-220 kV A1 @ LOU-02 | BUSBAR SECTION - LOUTH 220-LOUTH 220-220A1 | 47 | 34 |  | Scheduled | 23/06/2025 | 08/08/2025
TO-25-220 kV A2 @ LOU-03 | BUSBAR SECTION - LOUTH 220-LOUTH 220-220A2 | 47 | 34 |  | Scheduled | 23/06/2025 | 08/08/2025
TO-25-220 kV B1 @ LOU-02 | BUSBAR SECTION - LOUTH 220-LOUTH 220-220B1 | 47 | 34 |  | Scheduled | 23/06/2025 | 08/08/2025
TO-25-220 kV B2 @ LOU-02 | BUSBAR SECTION - LOUTH 220-LOUTH 220-220B2 | 47 | 34 |  | Scheduled | 23/06/2025 | 08/08/2025
TO-25-MP GIS-T121-01 | GENERATOR TRANSFORMER - MONEYPOINT GIS 110-MONEYPOINT GIS 20-T121 | 5 | 5 | 5 | Scheduled | 23/06/2025 | 27/06/2025
TO-25-110 kV B1 @ SH-03 | BUSBAR SECTION - SHANNONBRIDGE 110-SHANNONBRIDGE 110-110B1 | 2 | 2 | 2 | Scheduled | 23/06/2025 | 24/06/2025
TO-25-SH-110K1-2-02 | COUPLER/SECTIONALISING CB - SHANNONBRIDGE 110-SHANNONBRIDGE 110-110K1-2 | 2 | 2 | 2 | Scheduled | 23/06/2025 | 24/06/2025
TO-25-SHL-D1/CB1-03 | COUPLER/SECTIONALISING CB - SHELLYBANKS 220-SHELLYBANKS 220-D1/CB1 | 1 | 1 | 1 | Scheduled | 23/06/2025 | 23/06/2025
TO-25-SHL-D2/CB1-02 | COUPLER/SECTIONALISING CB - SHELLYBANKS 220-SHELLYBANKS 220-D2/CB1 | 1 | 1 | 1 | Scheduled | 23/06/2025 | 23/06/2025
TO-25-SHL-T2016-03 | GENERATOR TRANSFORMER - SHELLYBANKS 220-SHELLYBANKS G6-T2016 | 5 | 5 | 5 | Scheduled | 23/06/2025 | 27/06/2025
TO-25-TOB-T132-01 | GENERATOR TRANSFORMER - TOBERTOREEN 110-TOBERTOREEN 33-T132 | 5 | 5 | 5 | Scheduled | 23/06/2025 | 27/06/2025
TO-25-IKE-T141-02 | DISTRIBUTION TRANSFORMER - IKERRIN 110-IKERRIN 38-T141 | 14 | 10 |  | Reference | 25/06/2025 | 08/07/2025
TO-25-IKE,T-IKE-1-02 | 110kV FEEDER - IKERRIN tee-IKERRIN 110-1 | 14 | 10 |  | Scheduled | 25/06/2025 | 08/07/2025
TO-25-IKE,T-SH-1-02 | 110kV FEEDER - IKERRIN tee-SHANNONBRIDGE 110-1 | 14 | 10 |  | Scheduled | 25/06/2025 | 08/07/2025
TO-25-IKE,T-THU-1-02 | 110kV FEEDER - IKERRIN tee-THURLES 110-1 | 14 | 10 |  | Scheduled | 25/06/2025 | 08/07/2025
TO-25-KIR-T131-04 | GENERATOR TRANSFORMER - KILCUMBER 110-KILCUMBER 33-T131 | 2 | 2 | 2 | Scheduled | 25/06/2025 | 26/06/2025
TO-25-SHL-D1/CB1-04 | COUPLER/SECTIONALISING CB - SHELLYBANKS 220-SHELLYBANKS 220-D1/CB1 | 1 | 1 | 1 | Scheduled | 27/06/2025 | 27/06/2025
TO-25-SHL-D2/CB1-03 | COUPLER/SECTIONALISING CB - SHELLYBANKS 220-SHELLYBANKS 220-D2/CB1 | 1 | 1 | 1 | Scheduled | 27/06/2025 | 27/06/2025
TO-25-110 kV B2 @ BVK-01 | BUSBAR SECTION - BALLYVOUSKILL 110-BALLYVOUSKILL 110-110B2 | 12 | 10 | 10 | Scheduled | 30/06/2025 | 11/07/2025
TO-25-BVK-110K2-02 | COUPLER/SECTIONALISING CB - BALLYVOUSKILL 110-BALLYVOUSKILL 110-110K2 | 12 | 10 | 10 | Scheduled | 30/06/2025 | 11/07/2025
TO-25-BVK-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - BALLYVOUSKILL 110-BALLYVOUSKILL 110-110SA1-2CB | 12 | 10 | 10 | Scheduled | 30/06/2025 | 11/07/2025
TO-25-BVK-110SB1-2CB-01 | COUPLER/SECTIONALISING CB - BALLYVOUSKILL 110-BALLYVOUSKILL 110-110SB1-2CB | 12 | 10 | 10 | Scheduled | 30/06/2025 | 11/07/2025
TO-25-BVK-COT-1-01 | 110kV FEEDER - BALLYVOUSKILL 110-COOMATAGGART 110-1 | 12 | 10 | 10 | Scheduled | 30/06/2025 | 11/07/2025
TO-25-CLU-T121-01 | TSO CUSTOMER TRANSFORMER - CLUTTERLAND 110-CLUTTERLAND 20-T121 | 5 | 5 | 5 | Scheduled | 30/06/2025 | 04/07/2025
TO-25-COT-110SA1-01 | SECTIONALISING DISCONNECT - COOMATAGGART 110-COOMATAGGART 110-110SA1 | 12 | 10 | 10 | Scheduled | 30/06/2025 | 11/07/2025
TO-25-COT-110SA2-01 | SECTIONALISING DISCONNECT - COOMATAGGART 110-COOMATAGGART 110-110SA2 | 12 | 10 | 10 | Scheduled | 30/06/2025 | 11/07/2025
TO-25-COT-FILTER1-01 | CAPACITOR/SVC/REACTOR - COOMATAGGART 110-COOMATAGGART 110-FILTER1 | 12 | 10 | 10 | Scheduled | 30/06/2025 | 11/07/2025
TO-25-COT-T132-01 | GENERATOR TRANSFORMER - COOMATAGGART 110-COOMATAGGART 33-T132 | 12 | 10 |  | Scheduled | 30/06/2025 | 11/07/2025
TO-25-COT-T141-01 | DISTRIBUTION TRANSFORMER - COOMATAGGART 110-COOMATAGGART 38-T141 | 12 | 10 | 10 | Reference | 30/06/2025 | 11/07/2025
TO-25-110 kV B4 @ CDU-05 | BUSBAR SECTION - CORDUFF 110-CORDUFF 110-110B4 | 3 | 3 | 3 | Scheduled | 30/06/2025 | 02/07/2025
TO-25-CDU-110SB2-4CB-05 | COUPLER/SECTIONALISING CB - CORDUFF 110-CORDUFF 110-110SB2-4CB | 3 | 3 | 3 | Scheduled | 30/06/2025 | 02/07/2025
TO-25-220 kV A4 @ CDU-03 | BUSBAR SECTION - CORDUFF 220-CORDUFF 220-220A4 | 3 | 3 | 3 | Scheduled | 30/06/2025 | 02/07/2025
TO-25-CDU-220SA2-4CB-03 | COUPLER/SECTIONALISING CB - CORDUFF 220-CORDUFF 220-220SA2-4CB | 3 | 3 | 3 | Scheduled | 30/06/2025 | 02/07/2025
TO-25-GRO-T122-01 | GENERATOR TRANSFORMER - GARROW 110-GARROW 20-T122 | 5 | 5 |  | Scheduled | 30/06/2025 | 04/07/2025
TO-25-KLS-110K1-2-05 | COUPLER/SECTIONALISING CB - KELLIS 110-KELLIS 110-110K1-2 | 9 | 7 | 7 | Scheduled | 30/06/2025 | 08/07/2025
TO-25-KLN-SH-1-05 | 220kV FEEDER - KILLONAN 220-SHANNONBRIDGE 220-1 | 2 | 2 | 2 | Scheduled | 30/06/2025 | 01/07/2025
TO-25-LOU-AT3-02 | TRANSFORMER - LOUTH 220-LOUTH 275-AT3 | 60 | 43 |  | Scheduled | 30/06/2025 | 28/08/2025
TO-25-RRU-T122-01 | GENERATOR TRANSFORMER - RATRUSSAN 110-RATRUSSAN 20-T122 | 5 | 5 | 5 | Scheduled | 30/06/2025 | 04/07/2025
TO-25-220 kV A1 @ SH-01 | BUSBAR SECTION - SHANNONBRIDGE 220-SHANNONBRIDGE 220-220A1 | 2 | 2 | 2 | Scheduled | 30/06/2025 | 01/07/2025
TO-25-220 kV A2 @ SH-03 | BUSBAR SECTION - SHANNONBRIDGE 220-SHANNONBRIDGE 220-220A2 | 2 | 2 | 2 | Scheduled | 30/06/2025 | 01/07/2025
TO-25-220 kV B1 @ SH-01 | BUSBAR SECTION - SHANNONBRIDGE 220-SHANNONBRIDGE 220-220B1 | 2 | 2 | 2 | Scheduled | 30/06/2025 | 01/07/2025
TO-25-220 kV B2 @ SH-03 | BUSBAR SECTION - SHANNONBRIDGE 220-SHANNONBRIDGE 220-220B2 | 2 | 2 | 2 | Scheduled | 30/06/2025 | 01/07/2025
TO-25-SH-T102/4-01 | GENERATOR TRANSFORMER - SHANNONBRIDGE 110-SHANNONBRIDGE G2/4-T102/4 | 38 | 27 | 27 | Scheduled | 30/06/2025 | 06/08/2025
TO-25-110 kV B1 @ CSH-07 | BUSBAR SECTION - CASHLA 110-CASHLA 110-110B1 | 4 | 4 | 4 | Scheduled | 01/07/2025 | 04/07/2025
TO-25-220 kV A1 @ CBT-02 | BUSBAR SECTION - CASTLEBAGOT 220-CASTLEBAGOT 220-220A1 | 9 | 7 | 7 | Scheduled | 01/07/2025 | 09/07/2025
TO-25-220 kV B1 @ CBT-03 | BUSBAR SECTION - CASTLEBAGOT 220-CASTLEBAGOT 220-220B1 | 9 | 7 | 7 | Scheduled | 01/07/2025 | 09/07/2025
TO-25-CBT-220K1-05 | COUPLER/SECTIONALISING CB - CASTLEBAGOT 220-CASTLEBAGOT 220-220K1 | 9 | 7 | 7 | Scheduled | 01/07/2025 | 09/07/2025
TO-25-CBT-220SA1-2CB-03 | COUPLER/SECTIONALISING CB - CASTLEBAGOT 220-CASTLEBAGOT 220-220SA1-2CB | 9 | 7 | 7 | Scheduled | 01/07/2025 | 09/07/2025
TO-25-CBT-220SB1-2CB-03 | COUPLER/SECTIONALISING CB - CASTLEBAGOT 220-CASTLEBAGOT 220-220SB1-2CB | 9 | 7 | 7 | Scheduled | 01/07/2025 | 09/07/2025
TO-25-110 kV A2 @ LOU-01 | BUSBAR SECTION - LOUTH 110-LOUTH 110-110A2 | 88 | 63 | 63 | Scheduled | 01/07/2025 | 26/09/2025
TO-25-110 kV B2 @ LOU-01 | BUSBAR SECTION - LOUTH 110-LOUTH 110-110B2 | 88 | 63 | 63 | Scheduled | 01/07/2025 | 26/09/2025
TO-25-CF-CLO-2-04 | 110kV FEEDER - CATHALEENS FALL 110-CLOGHER 110-2 | 3 | 3 | 3 | Scheduled | 02/07/2025 | 04/07/2025
TO-25-220 kV B2 @ MAY-01 | BUSBAR SECTION - MAYNOOTH 220-MAYNOOTH 220-220B2 | 57 | 40 | 40 | Scheduled | 02/07/2025 | 27/08/2025
TO-25-MAY-SH-1-03 | 220kV FEEDER - MAYNOOTH 220-SHANNONBRIDGE 220-1 | 136 | 96 | 96 | Scheduled | 02/07/2025 | 14/11/2025
TO-25-FLA-SLI-1-04 | 110kV FEEDER - FLAGFORD 110-SLIGO 110-1 | 2 | 2 | 2 | Scheduled | 03/07/2025 | 04/07/2025
TO-25-220 kV A2 @ FIN-09 | BUSBAR SECTION - FINGLAS 220-FINGLAS 220-220A2 | 8 | 6 | 6 | Scheduled | 04/07/2025 | 11/07/2025
TO-25-220 kV B2 @ FIN-04 | BUSBAR SECTION - FINGLAS 220-FINGLAS 220-220B2 | 8 | 6 | 6 | Scheduled | 04/07/2025 | 11/07/2025
TO-25-FIN-220K2-11 | COUPLER/SECTIONALISING CB - FINGLAS 220-FINGLAS 220-220K2 | 8 | 6 | 6 | Scheduled | 04/07/2025 | 11/07/2025
TO-25-FIN-220SA1-2CB-15 | COUPLER/SECTIONALISING CB - FINGLAS 220-FINGLAS 220-220SA1-2CB | 8 | 6 | 6 | Scheduled | 04/07/2025 | 11/07/2025
TO-25-FIN-220SB1-2CB-12 | COUPLER/SECTIONALISING CB - FINGLAS 220-FINGLAS 220-220SB1-2CB | 8 | 6 | 6 | Scheduled | 04/07/2025 | 11/07/2025
TO-25-110 kV A3 @ FIN GIS-02 | BUSBAR SECTION - FINGLAS GIS 110-FINGLAS GIS 110-110A3 | 8 | 6 | 6 | Scheduled | 04/07/2025 | 11/07/2025
TO-25-110 kV B3 @ FIN GIS-01 | BUSBAR SECTION - FINGLAS GIS 110-FINGLAS GIS 110-110B3 | 8 | 6 | 6 | Scheduled | 04/07/2025 | 11/07/2025
TO-25-FIN GIS-110SA1-3CB-02 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110SA1-3CB | 8 | 6 | 6 | Scheduled | 04/07/2025 | 11/07/2025
TO-25-FIN GIS-110SA3-5CB-04 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110SA3-5CB | 8 | 6 | 6 | Scheduled | 04/07/2025 | 11/07/2025
TO-25-FIN GIS-110SB1-3CB-02 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110SB1-3CB | 8 | 6 | 6 | Scheduled | 04/07/2025 | 11/07/2025
TO-25-FIN GIS-110SB3-5CB-03 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110SB3-5CB | 8 | 6 | 6 | Scheduled | 04/07/2025 | 11/07/2025
TO-25-FIN GIS-T2106-02 | TRANSFORMER - FINGLAS 220-FINGLAS GIS 110-T2106 | 8 | 6 | 6 | Scheduled | 04/07/2025 | 11/07/2025
TO-25-CD-KBY-1-02 | 110kV FEEDER - CARRIGADROHID 110-KILBARRY 110-1 | 12 | 10 | 10 | Scheduled | 07/07/2025 | 18/07/2025
TO-25-CD-T103-04 | GENERATOR TRANSFORMER - CARRIGADROHID 110-CARRIGADROHID G3-T103 | 12 | 10 | 10 | Scheduled | 07/07/2025 | 18/07/2025
TO-25-110 kV B1 @ CSH-01 | BUSBAR SECTION - CASHLA 110-CASHLA 110-110B1 | 8 | 6 | 6 | Scheduled | 07/07/2025 | 14/07/2025
TO-25-CSH-GAL GIS-1-02 | 110kV FEEDER - CASHLA 110-GALWAY GIS 110-1 | 8 | 6 | 6 | Scheduled | 07/07/2025 | 14/07/2025
TO-25-ENN-SLC-1-01 | 110kV FEEDER - ENNIS 110-SLIEVECALLAN 110-1 | 3 | 3 | 3 | Scheduled | 07/07/2025 | 09/07/2025
TO-25-FLA-T2101-01 | TRANSFORMER - FLAGFORD 220-FLAGFORD 110-T2101 | 4 | 4 | 4 | Scheduled | 07/07/2025 | 10/07/2025
TO-25-110 kV B1 @ KBY-01 | BUSBAR SECTION - KILBARRY 110-KILBARRY 110-110B1 | 12 | 10 | 10 | Scheduled | 07/07/2025 | 18/07/2025
TO-25-KPG-220K3-01 | COUPLER/SECTIONALISING CB - KILPADDOGE 220-KILPADDOGE 220-220K3 | 5 | 5 | 5 | Scheduled | 07/07/2025 | 11/07/2025
TO-25-KPG-220SA1-2CB-01 | COUPLER/SECTIONALISING CB - KILPADDOGE 220-KILPADDOGE 220-220SA1-2CB | 5 | 5 | 5 | Scheduled | 07/07/2025 | 11/07/2025
TO-25-KPG-220SA1-3CB-01 | COUPLER/SECTIONALISING CB - KILPADDOGE 220-KILPADDOGE 220-220SA1-3CB | 5 | 5 | 5 | Scheduled | 07/07/2025 | 11/07/2025
TO-25-KPG-220SB1-2CB-01 | COUPLER/SECTIONALISING CB - KILPADDOGE 220-KILPADDOGE 220-220SB1-2CB | 5 | 5 | 5 | Scheduled | 07/07/2025 | 11/07/2025
TO-25-KPG-220SB1-3CB-01 | COUPLER/SECTIONALISING CB - KILPADDOGE 220-KILPADDOGE 220-220SB1-3CB | 5 | 5 | 5 | Scheduled | 07/07/2025 | 11/07/2025
TO-25-NW-T2004/5-02 | GENERATOR TRANSFORMER - NORTH WALL 220-NORTH WALL G4/5-T2004/5 | 2 | 2 | 2 | Scheduled | 07/07/2025 | 08/07/2025
TO-25-110 kV A2 @ SH-01 | BUSBAR SECTION - SHANNONBRIDGE 110-SHANNONBRIDGE 110-110A2 | 12 | 10 | 10 | Scheduled | 07/07/2025 | 18/07/2025
TO-25-110 kV B2 @ SH-01 | BUSBAR SECTION - SHANNONBRIDGE 110-SHANNONBRIDGE 110-110B2 | 12 | 10 | 10 | Scheduled | 07/07/2025 | 18/07/2025
TO-25-220 kV A2 @ SH-06 | BUSBAR SECTION - SHANNONBRIDGE 220-SHANNONBRIDGE 220-220A2 | 12 | 10 | 10 | Scheduled | 07/07/2025 | 18/07/2025
TO-25-220 kV B2 @ SH-06 | BUSBAR SECTION - SHANNONBRIDGE 220-SHANNONBRIDGE 220-220B2 | 12 | 10 | 10 | Scheduled | 07/07/2025 | 18/07/2025
TO-25-SH-T2102-01 | TRANSFORMER - SHANNONBRIDGE 220-SHANNONBRIDGE 110-T2102 | 85 | 60 | 60 | Scheduled | 07/07/2025 | 29/09/2025
TO-25-SLC-110SA1-01 | SECTIONALISING DISCONNECT - SLIEVECALLAN 110-SLIEVECALLAN 110-110SA1 | 3 | 3 | 3 | Scheduled | 07/07/2025 | 09/07/2025
TO-25-SLC-110SA2-01 | SECTIONALISING DISCONNECT - SLIEVECALLAN 110-SLIEVECALLAN 110-110SA2 | 3 | 3 | 3 | Scheduled | 07/07/2025 | 09/07/2025
TO-25-SLC-T121-01 | GENERATOR TRANSFORMER - SLIEVECALLAN 110-SLIEVECALLAN 20-T121 | 3 | 3 | 3 | Scheduled | 07/07/2025 | 09/07/2025
TO-25-SLC-T122-01 | GENERATOR TRANSFORMER - SLIEVECALLAN 110-SLIEVECALLAN 20-T122 | 3 | 3 | 3 | Scheduled | 07/07/2025 | 09/07/2025
TO-25-WEX-110SA1-2CB-02 | COUPLER/SECTIONALISING CB - WEXFORD 110-WEXFORD 110-110SA1-2CB | 12 | 10 | 10 | Scheduled | 07/07/2025 | 18/07/2025
TO-25-WEX-CAP2-02 | CAPACITOR/SVC/REACTOR - WEXFORD 110-WEXFORD 110-CAP2 | 12 | 10 | 10 | Scheduled | 07/07/2025 | 18/07/2025
TO-25-WEX-CAP4-02 | CAPACITOR/SVC/REACTOR - WEXFORD 110-WEXFORD 110-CAP4 | 12 | 10 | 10 | Scheduled | 07/07/2025 | 18/07/2025
TO-25-WEX-T122-02 | DISTRIBUTION TRANSFORMER - WEXFORD 110-WEXFORD 20-T122 | 12 | 10 | 10 | Reference | 07/07/2025 | 18/07/2025
TO-25-WEX-T142-02 | DISTRIBUTION TRANSFORMER - WEXFORD 110-WEXFORD 38-T142 | 12 | 10 | 10 | Reference | 07/07/2025 | 18/07/2025
TO-25-220 kV A1 @ AD-04 | BUSBAR SECTION - AGHADA 220-AGHADA 220-220A1 | 2 | 2 | 2 | Scheduled | 08/07/2025 | 09/07/2025
TO-25-220 kV A2 @ AD-04 | BUSBAR SECTION - AGHADA 220-AGHADA 220-220A2 | 2 | 2 | 2 | Scheduled | 08/07/2025 | 09/07/2025
TO-25-AD-220K1-03 | COUPLER/SECTIONALISING CB - AGHADA 220-AGHADA 220-220K1 | 2 | 2 | 2 | Scheduled | 08/07/2025 | 09/07/2025
TO-25-AD-SA1-2CB-05 | COUPLER/SECTIONALISING CB - AGHADA 220-AGHADA 220-220SA1-2CB | 2 | 2 | 2 | Scheduled | 08/07/2025 | 09/07/2025
TO-25-110 kV B1/B2 @ CLO-01 | BUSBAR SECTION - CLOGHER 110-CLOGHER 110-110B1-B2 | 10 | 8 | 8 | Scheduled | 08/07/2025 | 17/07/2025
TO-25-CLO-110K1-2-02 | COUPLER/SECTIONALISING CB - CLOGHER 110-CLOGHER 110-110K1-2 | 10 | 8 | 8 | Scheduled | 08/07/2025 | 17/07/2025
TO-25-GLR-MOY-1-02 | 110kV FEEDER - GLENREE 110-MOY 110-1 | 85 | 60 | 60 | Scheduled | 08/07/2025 | 30/09/2025
TO-25-IKE,T-SH-1-05 | 110kV FEEDER - IKERRIN tee-SHANNONBRIDGE 110-1 | 58 | 41 | 41 | Scheduled | 08/07/2025 | 03/09/2025
TO-25-KNY-UGL-1-01 | 110kV FEEDER - KNOCKRANNY 110-UGGOOL 110-1 | 4 | 4 | 4 | Scheduled | 08/07/2025 | 11/07/2025
TO-25-UGL-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - UGGOOL 110-UGGOOL 110-110SA1-2CB | 4 | 4 | 4 | Scheduled | 08/07/2025 | 11/07/2025
TO-25-UGL-T131-01 | GENERATOR TRANSFORMER - UGGOOL 110-UGGOOL 33-T131 | 10 | 8 | 8 | Scheduled | 08/07/2025 | 17/07/2025
TO-25-UGL-T132-01 | GENERATOR TRANSFORMER - UGGOOL 110-UGGOOL 33-T132 | 4 | 4 | 4 | Scheduled | 08/07/2025 | 11/07/2025
TO-25-UGL-T134-01 | GENERATOR TRANSFORMER - UGGOOL 110-UGGOOL 33-T134 | 4 | 4 | 4 | Scheduled | 08/07/2025 | 11/07/2025
TO-25-BDN-MRK1-02 | TSO CUSTOMER TRANSFORMER - BALLYDINE 110-BALLYDINE 10-MRK1 | 21 | 15 | 15 | Scheduled | 09/07/2025 | 29/07/2025
TO-25-PLS-110K1-2-03 | COUPLER/SECTIONALISING CB - PORTLAOISE 110-PORTLAOISE 110-110K1-2 | 21 | 15 | 15 | Scheduled | 09/07/2025 | 29/07/2025
TO-25-PLS-T141-02 | DISTRIBUTION TRANSFORMER - PORTLAOISE 110-PORTLAOISE 38-T141 | 52 | 37 | 37 | Reference | 09/07/2025 | 29/08/2025
TO-25-110 kV B1 @ AA GIS-01 | BUSBAR SECTION - ARDNACRUSHA GIS 110-ARDNACRUSHA GIS 110-110B1 | 1 | 1 | 1 | Scheduled | 10/07/2025 | 10/07/2025
TO-25-110 kV B3 @ AA GIS-02 | BUSBAR SECTION - ARDNACRUSHA GIS 110-ARDNACRUSHA GIS 110-110B3 | 1 | 1 | 1 | Scheduled | 10/07/2025 | 10/07/2025
TO-25-AA GIS-110K3-02 | COUPLER/SECTIONALISING CB - ARDNACRUSHA GIS 110-ARDNACRUSHA GIS 110-110K3 | 1 | 1 | 1 | Scheduled | 10/07/2025 | 10/07/2025
TO-25-AA GIS-110SB1-2CB-04 | COUPLER/SECTIONALISING CB - ARDNACRUSHA GIS 110-ARDNACRUSHA GIS 110-110SB1-2CB | 1 | 1 | 1 | Scheduled | 10/07/2025 | 10/07/2025
TO-25-AA GIS-110SB1-3CB-02 | COUPLER/SECTIONALISING CB - ARDNACRUSHA GIS 110-ARDNACRUSHA GIS 110-110SB1-3CB | 1 | 1 | 1 | Scheduled | 10/07/2025 | 10/07/2025
TO-25-AA GIS-T103-02 | GENERATOR TRANSFORMER - ARDNACRUSHA GIS 110-ARDNACRUSHA GIS G3-T103 | 1 | 1 | 1 | Scheduled | 10/07/2025 | 10/07/2025
TO-25-220 kV A2 @ CBT-03 | BUSBAR SECTION - CASTLEBAGOT 220-CASTLEBAGOT 220-220A2 | 9 | 7 | 7 | Scheduled | 10/07/2025 | 18/07/2025
TO-25-220 kV B2 @ CBT-03 | BUSBAR SECTION - CASTLEBAGOT 220-CASTLEBAGOT 220-220B2 | 9 | 7 | 7 | Scheduled | 10/07/2025 | 18/07/2025
TO-25-CBT-220K2-03 | COUPLER/SECTIONALISING CB - CASTLEBAGOT 220-CASTLEBAGOT 220-220K2 | 9 | 7 | 7 | Scheduled | 10/07/2025 | 18/07/2025
TO-25-CBT-220SA1-2CB-05 | COUPLER/SECTIONALISING CB - CASTLEBAGOT 220-CASTLEBAGOT 220-220SA1-2CB | 9 | 7 | 7 | Scheduled | 10/07/2025 | 18/07/2025
TO-25-CBT-220SB1-2CB-05 | COUPLER/SECTIONALISING CB - CASTLEBAGOT 220-CASTLEBAGOT 220-220SB1-2CB | 9 | 7 | 7 | Scheduled | 10/07/2025 | 18/07/2025
TO-25-CUS-T101-04 | GENERATOR TRANSFORMER - CUSHALING 110-CUSHALING G1-T101 | 2 | 2 | 2 | Scheduled | 10/07/2025 | 11/07/2025
TO-25-110 kV A3 @ GAL GIS-01 | BUSBAR SECTION - GALWAY GIS 110-GALWAY GIS 110-110A3 | 7 | 5 | 5 | Scheduled | 10/07/2025 | 16/07/2025
TO-25-110 kV B3 @ GAL GIS-01 | BUSBAR SECTION - GALWAY GIS 110-GALWAY GIS 110-110B3 | 7 | 5 | 5 | Scheduled | 10/07/2025 | 16/07/2025
TO-25-GAL GIS-110K3-01 | COUPLER/SECTIONALISING CB - GALWAY GIS 110-GALWAY GIS 110-110K3 | 7 | 5 | 5 | Scheduled | 10/07/2025 | 16/07/2025
TO-25-GAL GIS-110SA1-3CB-01 | COUPLER/SECTIONALISING CB - GALWAY GIS 110-GALWAY GIS 110-110SA1-3CB | 7 | 5 | 5 | Scheduled | 10/07/2025 | 16/07/2025
TO-25-GAL GIS-110SB1-3CB-01 | COUPLER/SECTIONALISING CB - GALWAY GIS 110-GALWAY GIS 110-110SB1-3CB | 7 | 5 | 5 | Scheduled | 10/07/2025 | 16/07/2025
TO-25-ATH-SH-1-08 | 110kV FEEDER - ATHLONE 110-SHANNONBRIDGE 110-1 | 3 | 1 | 1 | Scheduled | 11/07/2025 | 13/07/2025
TO-25-CDY-GRV-1-01 | 110kV FEEDER - CORDERRY 110-GARVAGH 110-1 | 8 | 6 | 6 | Scheduled | 11/07/2025 | 18/07/2025
TO-25-110 kV B1 @ GRV-01 | BUSBAR SECTION - GARVAGH 110-GARVAGH 110-110B1 | 8 | 6 | 6 | Scheduled | 11/07/2025 | 18/07/2025
TO-25-GRV-110K1-03 | COUPLER/SECTIONALISING CB - GARVAGH 110-GARVAGH 110-110K1 | 8 | 6 | 6 | Scheduled | 11/07/2025 | 18/07/2025
TO-25-GRV-T121-02 | GENERATOR TRANSFORMER - GARVAGH 110-GARVAGH 20-T121 | 8 | 6 | 6 | Scheduled | 11/07/2025 | 18/07/2025
TO-25-GRV-T141-01 | DISTRIBUTION TRANSFORMER - GARVAGH 110-GARVAGH 20-T141 | 8 | 6 | 6 | Reference | 11/07/2025 | 18/07/2025
TO-25-AUG-SK-3-01 | 110kV FEEDER - AUGHINISH 110-SEALROCK 110-3 | 16 | 12 | 12 | Scheduled | 14/07/2025 | 29/07/2025
TO-25-CKN-GRO-1-01 | 110kV FEEDER - CLONKEEN 110-GARROW 110-1 | 19 | 15 | 15 | Scheduled | 14/07/2025 | 01/08/2025
TO-25-110 kV B1/B2/B3 @ FIN-01 | BUSBAR SECTION - FINGLAS 110-FINGLAS 110-110B1-B2-B3 | 171 | 119 | 119 | Scheduled | 14/07/2025 | 31/12/2025
TO-25-FIN-FIN GIS-1-02 | 110kV FEEDER - FINGLAS 110-FINGLAS GIS 110-1 | 171 | 119 | 119 | Scheduled | 14/07/2025 | 31/12/2025
TO-25-PB-R2002-03 | CAPACITOR/SVC/REACTOR - POOLBEG 220-POOLBEG 220-R2002 | 5 | 5 | 5 | Scheduled | 14/07/2025 | 18/07/2025
TO-25-SK-T103-01 | GENERATOR TRANSFORMER - SEALROCK 110-SEALROCK G3-T103 | 16 | 12 | 12 | Scheduled | 14/07/2025 | 29/07/2025
TO-25-KBY-KRA-2-01 | 110kV FEEDER - KILBARRY 110-KNOCKRAHA 110-2 | 1 | 1 | 1 | Scheduled | 15/07/2025 | 15/07/2025
TO-25-LOU-MTH-1-02 | 110kV FEEDER - LOUTH 110-MEATH HILL 110-1 | 3 | 3 | 3 | Scheduled | 15/07/2025 | 17/07/2025
TO-25-CF-T104-02 | GENERATOR TRANSFORMER - CATHALEENS FALL 110-CATHALEENS FALL G4-T104 | 63 | 44 | 44 | Scheduled | 16/07/2025 | 16/09/2025
TO-25-220 kV A2 @ KNR-03 | BUSBAR SECTION - KNOCKANURE 220-KNOCKANURE 220-220A2 | 7 | 5 | 5 | Scheduled | 17/07/2025 | 23/07/2025
TO-25-220 kV B2 @ KNR-03 | BUSBAR SECTION - KNOCKANURE 220-KNOCKANURE 220-220B2 | 7 | 5 | 5 | Scheduled | 17/07/2025 | 23/07/2025
TO-25-KNR-220K2-01 | COUPLER/SECTIONALISING CB - KNOCKANURE 220-KNOCKANURE 220-220K2 | 7 | 5 | 5 | Scheduled | 17/07/2025 | 23/07/2025
TO-25-KNR-220SA1-2CB-04 | COUPLER/SECTIONALISING CB - KNOCKANURE 220-KNOCKANURE 220-220SA1-2CB | 7 | 5 | 5 | Scheduled | 17/07/2025 | 23/07/2025
TO-25-KNR-220SB1-2CB-04 | COUPLER/SECTIONALISING CB - KNOCKANURE 220-KNOCKANURE 220-220SB1-2CB | 7 | 5 | 5 | Scheduled | 17/07/2025 | 23/07/2025
TO-25-PA-110SA1-02 | SECTIONALISING DISCONNECT - POLLAPHUCA 110-POLLAPHUCA 110-110SA1 | 16 | 12 | 12 | Scheduled | 17/07/2025 | 01/08/2025
TO-25-PA-110SA2-02 | SECTIONALISING DISCONNECT - POLLAPHUCA 110-POLLAPHUCA 110-110SA2 | 16 | 12 | 12 | Scheduled | 17/07/2025 | 01/08/2025
TO-25-PA-T101-02 | GENERATOR TRANSFORMER - POLLAPHUCA 110-POLLAPHUCA G1-T101 | 16 | 12 | 12 | Scheduled | 17/07/2025 | 01/08/2025
TO-25-STR-T141-02 | DISTRIBUTION TRANSFORMER - STRATFORD 110-STRATFORD 38-T141 | 16 | 12 | 12 | Reference | 17/07/2025 | 01/08/2025
TO-25-STR,T-CLW-1-02 | 110kV FEEDER - STRATFORD tee-CARLOW 110-1 | 16 | 12 | 12 | Scheduled | 17/07/2025 | 01/08/2025
TO-25-STR,T-PA-1-02 | 110kV FEEDER - STRATFORD tee-POLLAPHUCA 110-1 | 16 | 12 | 12 | Scheduled | 17/07/2025 | 01/08/2025
TO-25-STR,T-STR-1-02 | 110kV FEEDER - STRATFORD tee-STRATFORD 110-1 | 16 | 12 | 12 | Scheduled | 17/07/2025 | 01/08/2025
TO-25-DEY-PLS-1-01 | 110kV FEEDER - DERRYCARNEY 110-PORTLAOISE 110-1 | 3 | 1 | 1 | Scheduled | 18/07/2025 | 20/07/2025
TO-25-FIN-T2103-01 | TRANSFORMER - FINGLAS 220-FINGLAS 110-T2103 | 110 | 76 | 76 | Scheduled | 18/07/2025 | 04/11/2025
TO-25-110 kV A2 @ PLS-05 | BUSBAR SECTION - PORTLAOISE 110-PORTLAOISE 110-110A2 | 3 | 1 | 1 | Scheduled | 18/07/2025 | 20/07/2025
TO-25-ATY-T102-03 | DISTRIBUTION TRANSFORMER - ATHY 110-ATHY 10-T102 | 2 | 2 | 2 | Reference | 21/07/2025 | 22/07/2025
TO-25-ATY-T102-02 | DISTRIBUTION TRANSFORMER - ATHY 110-ATHY 10-T102 | 10 | 8 | 8 | Reference | 21/07/2025 | 30/07/2025
TO-25-BAN-110SA1-03 | SECTIONALISING DISCONNECT - BANDON 110-BANDON 110-110SA1 | 12 | 10 | 10 | Scheduled | 21/07/2025 | 01/08/2025
TO-25-BAN-110SA2-04 | SECTIONALISING DISCONNECT - BANDON 110-BANDON 110-110SA2 | 12 | 10 | 10 | Scheduled | 21/07/2025 | 01/08/2025
TO-25-BAN-BRI-2-02 | 110kV FEEDER - BANDON 110-BRINNY 110-2 | 12 | 10 | 10 | Scheduled | 21/07/2025 | 01/08/2025
TO-25-BAN-RAF-1-04 | 110kV FEEDER - BANDON 110-RAFFEEN 110-1 | 12 | 10 | 10 | Scheduled | 21/07/2025 | 01/08/2025
TO-25-BAN-T142-01 | DISTRIBUTION TRANSFORMER - BANDON 110-BANDON 38-T142 | 12 | 10 | 10 | Reference | 21/07/2025 | 01/08/2025
TO-25-BRI-T102-01 | TSO CUSTOMER TRANSFORMER - BRINNY 110-BRINNY 10-T102 | 12 | 10 | 10 | Scheduled | 21/07/2025 | 01/08/2025
TO-25-CRU-T221-01 | TSO CUSTOMER TRANSFORMER - CRUISERATH 220-CRUISERATH 20-T221 | 5 | 5 | 5 | Scheduled | 21/07/2025 | 25/07/2025
TO-25-DEY-T132-02 | GENERATOR TRANSFORMER - DERRYCARNEY 110-DERRYCARNEY 33-T132 | 2 | 2 | 2 | Scheduled | 21/07/2025 | 22/07/2025
TO-25-KLH-KNY-1-01 | 110kV FEEDER - KNOCKALOUGH 110-KNOCKRANNY 110-1 | 9 | 7 | 7 | Scheduled | 21/07/2025 | 29/07/2025
TO-25-KDN-T131-01 | GENERATOR TRANSFORMER - KNOCKDRIN 110-KNOCKDRIN 33-T131 | 44 | 31 | 31 | Scheduled | 21/07/2025 | 02/09/2025
TO-25-KDN-T131-02 | GENERATOR TRANSFORMER - KNOCKDRIN 110-KNOCKDRIN 33-T131 | 72 | 51 | 51 | Scheduled | 21/07/2025 | 30/09/2025
TO-25-KDN,T-KDN-1-01 | 110kV FEEDER - KNOCKDRIN tee-KNOCKDRIN 110-1 | 44 | 31 | 31 | Scheduled | 21/07/2025 | 02/09/2025
TO-25-KDN,T-KDN-1-02 | 110kV FEEDER - KNOCKDRIN tee-KNOCKDRIN 110-1 | 72 | 51 | 51 | Scheduled | 21/07/2025 | 30/09/2025
TO-25-KDN,T-TSB-1-01 | 110kV FEEDER - KNOCKDRIN tee-THORNSBERRY 110-1 | 44 | 31 | 31 | Scheduled | 21/07/2025 | 02/09/2025
TO-25-KDN,T-TSB-1-03 | 110kV FEEDER - KNOCKDRIN tee-THORNSBERRY 110-1 | 72 | 51 | 51 | Scheduled | 21/07/2025 | 30/09/2025
TO-25-KDN,T-TEN-1-02 | 110kV FEEDER - KNOCKDRIN tee-TIMAHOE 110-1 | 44 | 31 | 31 | Scheduled | 21/07/2025 | 02/09/2025
TO-25-KDN,T-TEN-1-03 | 110kV FEEDER - KNOCKDRIN tee-TIMAHOE 110-1 | 72 | 51 | 51 | Scheduled | 21/07/2025 | 30/09/2025
TO-25-110 kV A2 @ RAF-02 | BUSBAR SECTION - RAFFEEN 110-RAFFEEN 110-110A2 | 10 | 8 | 8 | Scheduled | 21/07/2025 | 30/07/2025
TO-25-110 kV B2 @ RAF-02 | BUSBAR SECTION - RAFFEEN 110-RAFFEEN 110-110B2 | 10 | 8 | 8 | Scheduled | 21/07/2025 | 30/07/2025
TO-25-SH-T101/3-01 | GENERATOR TRANSFORMER - SHANNONBRIDGE 110-SHANNONBRIDGE G1/3-T101/3 | 39 | 28 | 28 | Scheduled | 21/07/2025 | 28/08/2025
TO-25-ATY-PLS-1-02 | 110kV FEEDER - ATHY 110-PORTLAOISE 110-1 | 71 | 50 | 50 | Scheduled | 22/07/2025 | 30/09/2025
TO-25-CSH-PRO-1-05 | 220kV FEEDER - CASHLA 220-PROSPECT 220-1 | 8 | 6 | 6 | Scheduled | 22/07/2025 | 29/07/2025
TO-25-220 kV A1 @ CBT-01 | BUSBAR SECTION - CASTLEBAGOT 220-CASTLEBAGOT 220-220A1 | 3 | 3 | 3 | Scheduled | 22/07/2025 | 24/07/2025
TO-25-220 kV A2 @ CBT-01 | BUSBAR SECTION - CASTLEBAGOT 220-CASTLEBAGOT 220-220A2 | 3 | 3 | 3 | Scheduled | 22/07/2025 | 24/07/2025
TO-25-CBT-220K1-03 | COUPLER/SECTIONALISING CB - CASTLEBAGOT 220-CASTLEBAGOT 220-220K1 | 2 | 2 | 2 | Scheduled | 22/07/2025 | 23/07/2025
TO-25-CBT-220K2-01 | COUPLER/SECTIONALISING CB - CASTLEBAGOT 220-CASTLEBAGOT 220-220K2 | 3 | 3 | 3 | Scheduled | 22/07/2025 | 24/07/2025
TO-25-CBT-220SA1-2CB-02 | COUPLER/SECTIONALISING CB - CASTLEBAGOT 220-CASTLEBAGOT 220-220SA1-2CB | 3 | 3 | 3 | Scheduled | 22/07/2025 | 24/07/2025
TO-25-CKN-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - CLONKEEN 110-CLONKEEN 110-110SA1-2CB | 10 | 8 | 8 | Scheduled | 22/07/2025 | 31/07/2025
TO-25-CKN-CGL-1-01 | 110kV FEEDER - CLONKEEN 110-COOMAGEARLAHY 110-1 | 10 | 8 | 8 | Scheduled | 22/07/2025 | 31/07/2025
TO-25-CGL-110SA1-01 | SECTIONALISING DISCONNECT - COOMAGEARLAHY 110-COOMAGEARLAHY 110-110SA1 | 10 | 8 | 8 | Scheduled | 22/07/2025 | 31/07/2025
TO-25-CGL-110SA2-01 | SECTIONALISING DISCONNECT - COOMAGEARLAHY 110-COOMAGEARLAHY 110-110SA2 | 10 | 8 | 8 | Scheduled | 22/07/2025 | 31/07/2025
TO-25-CGL-GAE-1-01 | 110kV FEEDER - COOMAGEARLAHY 110-GLANLEE 110-1 | 10 | 8 | 8 | Scheduled | 22/07/2025 | 31/07/2025
TO-25-CGL-T121-01 | GENERATOR TRANSFORMER - COOMAGEARLAHY 110-COOMAGEARLAHY 20-T121 | 10 | 8 | 8 | Scheduled | 22/07/2025 | 31/07/2025
TO-25-CGL-T122-01 | GENERATOR TRANSFORMER - COOMAGEARLAHY 110-COOMAGEARLAHY 20-T122 | 10 | 8 | 8 | Scheduled | 22/07/2025 | 31/07/2025
TO-25-GAE-T121-01 | GENERATOR TRANSFORMER - GLANLEE 110-GLANLEE 20-T121 | 10 | 8 | 8 | Scheduled | 22/07/2025 | 31/07/2025
TO-25-KPG-T2101-01 | TRANSFORMER - KILPADDOGE 220-KILPADDOGE 110-T2101 | 2 | 2 | 2 | Scheduled | 22/07/2025 | 23/07/2025
TO-25-220 kV A1 @ MP GIS-02 | BUSBAR SECTION - MONEYPOINT GIS 220-MONEYPOINT GIS 220-220A1 | 8 | 6 | 6 | Scheduled | 22/07/2025 | 29/07/2025
TO-25-220 kV B1 @ MP GIS-02 | BUSBAR SECTION - MONEYPOINT GIS 220-MONEYPOINT GIS 220-220B1 | 8 | 6 | 6 | Scheduled | 22/07/2025 | 29/07/2025
TO-25-MP GIS-220K1-02 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 220-MONEYPOINT GIS 220-220K1 | 8 | 6 | 6 | Scheduled | 22/07/2025 | 29/07/2025
TO-25-MP GIS-220SA1-2CB-04 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 220-MONEYPOINT GIS 220-220SA1-2CB | 8 | 6 | 6 | Scheduled | 22/07/2025 | 29/07/2025
TO-25-MP GIS-220SB1-2CB-04 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 220-MONEYPOINT GIS 220-220SB1-2CB | 8 | 6 | 6 | Scheduled | 22/07/2025 | 29/07/2025
TO-25-MP GIS-PRO-1-01 | 220kV FEEDER - MONEYPOINT GIS 220-PROSPECT 220-1 | 8 | 6 | 6 | Scheduled | 22/07/2025 | 29/07/2025
TO-25-PRO-TB-1-02 | 220kV FEEDER - PROSPECT 220-TARBERT 220-1 | 8 | 6 | 6 | Scheduled | 22/07/2025 | 29/07/2025
TO-25-220 kV A1 @ RAF-02 | BUSBAR SECTION - RAFFEEN 220-RAFFEEN 220-220A1 | 10 | 8 | 8 | Scheduled | 22/07/2025 | 31/07/2025
TO-25-220 kV A2 @ RAF-01 | BUSBAR SECTION - RAFFEEN 220-RAFFEEN 220-220A2 | 10 | 8 | 8 | Scheduled | 22/07/2025 | 31/07/2025
TO-25-220 kV B1 @ RAF-02 | BUSBAR SECTION - RAFFEEN 220-RAFFEEN 220-220B1 | 10 | 8 | 8 | Scheduled | 22/07/2025 | 31/07/2025
TO-25-220 kV B2 @ RAF-01 | BUSBAR SECTION - RAFFEEN 220-RAFFEEN 220-220B2 | 10 | 8 | 8 | Scheduled | 22/07/2025 | 31/07/2025
TO-25-RAF-220K1-2-01 | COUPLER/SECTIONALISING CB - RAFFEEN 220-RAFFEEN 220-220K1-2 | 10 | 8 | 8 | Scheduled | 22/07/2025 | 31/07/2025
TO-25-ROP-T131-02 | GENERATOR TRANSFORMER - ROSSPILE 110-ROSSPILE 33-T131 | 2 | 2 | 2 | Scheduled | 22/07/2025 | 23/07/2025
TO-25-220 kV A2 @ TB-04 | BUSBAR SECTION - TARBERT 220-TARBERT 220-220A2 | 8 | 6 | 6 | Scheduled | 22/07/2025 | 29/07/2025
TO-25-220 kV B2 @ TB-04 | BUSBAR SECTION - TARBERT 220-TARBERT 220-220B2 | 8 | 6 | 6 | Scheduled | 22/07/2025 | 29/07/2025
TO-25-110 kV B1 @ LOU-06 | BUSBAR SECTION - LOUTH 110-LOUTH 110-110B1 | 1 | 1 | 1 | Scheduled | 23/07/2025 | 23/07/2025
TO-25-LOU-110K1-2-04 | COUPLER/SECTIONALISING CB - LOUTH 110-LOUTH 110-110K1-2 | 1 | 1 | 1 | Scheduled | 23/07/2025 | 23/07/2025
TO-25-SLI-110SA1-2CB-02 | COUPLER/SECTIONALISING CB - SLIGO 110-SLIGO 110-110SA1-2CB | 31 | 22 | 22 | Scheduled | 23/07/2025 | 22/08/2025
TO-25-SLI-CAP1-01 | CAPACITOR/SVC/REACTOR - SLIGO 110-SLIGO 110-CAP1 | 31 | 22 | 22 | Scheduled | 23/07/2025 | 22/08/2025
TO-25-SLI-SRA-1-02 | 110kV FEEDER - SLIGO 110-SRANANAGH 110-1 | 111 | 77 | 77 | Scheduled | 23/07/2025 | 10/11/2025
TO-25-SLI-T141-02 | DISTRIBUTION TRANSFORMER - SLIGO 110-SLIGO 38-T141 | 31 | 22 | 22 | Reference | 23/07/2025 | 22/08/2025
TO-25-110 kV B1 @ SNU-01 | BUSBAR SECTION - SNUGBOROUGH 110-SNUGBOROUGH 110-110B1 | 10 | 8 | 8 | Scheduled | 23/07/2025 | 01/08/2025
TO-25-110 kV B2 @ SNU-01 | BUSBAR SECTION - SNUGBOROUGH 110-SNUGBOROUGH 110-110B2 | 10 | 8 | 8 | Scheduled | 23/07/2025 | 01/08/2025
TO-25-SNU-110K1-01 | COUPLER/SECTIONALISING CB - SNUGBOROUGH 110-SNUGBOROUGH 110-110K1 | 10 | 8 | 8 | Scheduled | 23/07/2025 | 01/08/2025
TO-25-SNU-110K2-01 | COUPLER/SECTIONALISING CB - SNUGBOROUGH 110-SNUGBOROUGH 110-110K2 | 10 | 8 | 8 | Scheduled | 23/07/2025 | 01/08/2025
TO-25-SNU-110SB1-2CB-01 | COUPLER/SECTIONALISING CB - SNUGBOROUGH 110-SNUGBOROUGH 110-110SB1-2CB | 10 | 8 | 8 | Scheduled | 23/07/2025 | 01/08/2025
TO-25-110 kV B1 @ SRA-01 | BUSBAR SECTION - SRANANAGH 110-SRANANAGH 110-110B1 | 7 | 5 | 5 | Scheduled | 23/07/2025 | 29/07/2025
TO-25-CSH-GAL GIS-1-01 | 110kV FEEDER - CASHLA 110-GALWAY GIS 110-1 | 2 | 2 | 2 | Scheduled | 24/07/2025 | 25/07/2025
TO-25-CF-CLO-2-06 | 110kV FEEDER - CATHALEENS FALL 110-CLOGHER 110-2 | 2 | 2 | 2 | Scheduled | 24/07/2025 | 25/07/2025
TO-25-110 kV A3 @ GAL GIS-02 | BUSBAR SECTION - GALWAY GIS 110-GALWAY GIS 110-110A3 | 2 | 2 | 2 | Scheduled | 24/07/2025 | 25/07/2025
TO-25-110 kV B3 @ GAL GIS-02 | BUSBAR SECTION - GALWAY GIS 110-GALWAY GIS 110-110B3 | 2 | 2 | 2 | Scheduled | 24/07/2025 | 25/07/2025
TO-25-GAL GIS-110K3-03 | COUPLER/SECTIONALISING CB - GALWAY GIS 110-GALWAY GIS 110-110K3 | 2 | 2 | 2 | Scheduled | 24/07/2025 | 25/07/2025
TO-25-GAL GIS-110SA1-3CB-03 | COUPLER/SECTIONALISING CB - GALWAY GIS 110-GALWAY GIS 110-110SA1-3CB | 2 | 2 | 2 | Scheduled | 24/07/2025 | 25/07/2025
TO-25-GAL GIS-110SB1-3CB-03 | COUPLER/SECTIONALISING CB - GALWAY GIS 110-GALWAY GIS 110-110SB1-3CB | 2 | 2 | 2 | Scheduled | 24/07/2025 | 25/07/2025
TO-25-220 kV B1 @ TH-02 | BUSBAR SECTION - TURLOUGH HILL 220-TURLOUGH HILL 220-220B1 | 1 | 1 | 1 | Scheduled | 24/07/2025 | 24/07/2025
TO-25-TH-T2001/2-03 | GENERATOR TRANSFORMER - TURLOUGH HILL 220-TURLOUGH HILL G1-T2001/2 | 1 | 1 | 1 | Scheduled | 24/07/2025 | 24/07/2025
TO-25-TH-T2003/4-03 | GENERATOR TRANSFORMER - TURLOUGH HILL 220-TURLOUGH HILL G1-T2003/4 | 1 | 1 | 1 | Scheduled | 24/07/2025 | 24/07/2025
TO-25-COL-CDU-1-02 | 110kV FEEDER - COLLEGE PARK 110-CORDUFF 110-1 | 2 | 2 | 2 | Scheduled | 28/07/2025 | 29/07/2025
TO-25-CDU-RYB GIS-1-02 | 110kV FEEDER - CORDUFF 110-RYEBROOK GIS 110-1 | 2 | 2 | 2 | Scheduled | 28/07/2025 | 29/07/2025
TO-25-CRU-T223-01 | TSO CUSTOMER TRANSFORMER - CRUISERATH 220-CRUISERATH 20-T223 | 5 | 5 | 5 | Scheduled | 28/07/2025 | 01/08/2025
TO-25-LIS-T142-01 | DISTRIBUTION TRANSFORMER - LISDRUM 110-LISDRUM 38-T142 | 99 | 69 | 69 | Reference | 28/07/2025 | 03/11/2025
TO-25-MTN-MUN-1-01 | 110kV FEEDER - MONETEEN 110-MUNGRET 110-1 | 5 | 5 | 5 | Scheduled | 28/07/2025 | 01/08/2025
TO-25-MP GIS-400K3-02 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 400-MONEYPOINT GIS 400-400K3 | 5 | 5 | 5 | Scheduled | 28/07/2025 | 01/08/2025
TO-25-MUN-T101-01 | TSO CUSTOMER TRANSFORMER - MUNGRET 110-MUNGRET 10-T101 | 5 | 5 | 5 | Reference | 28/07/2025 | 01/08/2025
TO-25-CUS-T103/5-01 | GENERATOR TRANSFORMER - CUSHALING 110-CUSHALING G3/5-T103/5 | 15 | 10 | 10 | Scheduled | 29/07/2025 | 12/08/2025
TO-25-LIS-LOU-1-02 | 110kV FEEDER - LISDRUM 110-LOUTH 110-1 | 23 | 16 | 16 | Scheduled | 29/07/2025 | 20/08/2025
TO-25-400 kV A1 @ WOO-03 | BUSBAR SECTION - WOODLAND 400-WOODLAND 400-400A1 | 15 | 10 | 10 | Scheduled | 29/07/2025 | 12/08/2025
TO-25-400 kV A2 @ WOO-01 | BUSBAR SECTION - WOODLAND 400-WOODLAND 400-400A2 | 15 | 10 | 10 | Scheduled | 29/07/2025 | 12/08/2025
TO-25-400 kV B1 @ WOO-03 | BUSBAR SECTION - WOODLAND 400-WOODLAND 400-400B1 | 15 | 10 | 10 | Scheduled | 29/07/2025 | 12/08/2025
TO-25-400 kV B2 @ WOO-02 | BUSBAR SECTION - WOODLAND 400-WOODLAND 400-400B2 | 15 | 10 | 10 | Scheduled | 29/07/2025 | 12/08/2025
TO-25-WOO-400K1-2-03 | COUPLER/SECTIONALISING CB - WOODLAND 400-WOODLAND 400-400K1-2 | 15 | 10 | 10 | Scheduled | 29/07/2025 | 12/08/2025
TO-25-DFR-T122-01 | DISTRIBUTION TRANSFORMER - DUNFIRTH 110-DUNFIRTH 20-T122 | 20 | 13 | 13 | Reference | 30/07/2025 | 18/08/2025
TO-25-DFR,T-DFR-1-03 | 110kV FEEDER - DUNFIRTH tee-DUNFIRTH 110-1 | 20 | 13 | 13 | Scheduled | 30/07/2025 | 18/08/2025
TO-25-DFR,T-KIN-1-03 | 110kV FEEDER - DUNFIRTH tee-KINNEGAD 110-1 | 20 | 13 | 13 | Scheduled | 30/07/2025 | 18/08/2025
TO-25-DFR,T-RNW-1-02 | 110kV FEEDER - DUNFIRTH tee-RINAWADE 110-1 | 36 | 25 |  | Scheduled | 30/07/2025 | 03/09/2025
TO-25-110 kV A2 @ MAY-01 | BUSBAR SECTION - MAYNOOTH 110-MAYNOOTH 110-110A2 | 15 | 10 | 10 | Scheduled | 30/07/2025 | 13/08/2025
TO-25-110 kV A3 @ MAY-01 | BUSBAR SECTION - MAYNOOTH 110-MAYNOOTH 110-110A3 | 15 | 10 | 10 | Scheduled | 30/07/2025 | 13/08/2025
TO-25-110 kV B2 @ MAY-01 | BUSBAR SECTION - MAYNOOTH 110-MAYNOOTH 110-110B2 | 15 | 10 | 10 | Scheduled | 30/07/2025 | 13/08/2025
TO-25-110 kV B3 @ MAY-01 | BUSBAR SECTION - MAYNOOTH 110-MAYNOOTH 110-110B3 | 15 | 10 | 10 | Scheduled | 30/07/2025 | 13/08/2025
TO-25-MAY-RYB GIS-1-01 | 110kV FEEDER - MAYNOOTH 110-RYEBROOK GIS 110-1 | 36 | 25 | 25 | Scheduled | 30/07/2025 | 03/09/2025
TO-25-MP GIS-T4201-03 | TRANSFORMER - MONEYPOINT GIS 400-MONEYPOINT GIS 220-T4201 | 10 | 7 | 7 | Scheduled | 30/07/2025 | 08/08/2025
TO-25-110 kV A1 @ RYB GIS-01 | BUSBAR SECTION - RYEBROOK GIS 110-RYEBROOK GIS 110-110A1 | 15 | 10 |  | Scheduled | 30/07/2025 | 13/08/2025
TO-25-110 kV B1 @ RYB GIS-01 | BUSBAR SECTION - RYEBROOK GIS 110-RYEBROOK GIS 110-110B1 | 15 | 10 | 10 | Scheduled | 30/07/2025 | 13/08/2025
TO-25-RYB GIS-110SA1-2CB-02 | COUPLER/SECTIONALISING CB - RYEBROOK GIS 110-RYEBROOK GIS 110-110SA1-2CB | 15 | 10 | 10 | Scheduled | 30/07/2025 | 13/08/2025
TO-25-RYB GIS-110SA1-3CB-03 | COUPLER/SECTIONALISING CB - RYEBROOK GIS 110-RYEBROOK GIS 110-110SA1-3CB | 15 | 10 | 10 | Scheduled | 30/07/2025 | 13/08/2025
TO-25-RYB GIS-110SB1-2CB-02 | COUPLER/SECTIONALISING CB - RYEBROOK GIS 110-RYEBROOK GIS 110-110SB1-2CB | 15 | 10 | 10 | Scheduled | 30/07/2025 | 13/08/2025
TO-25-RYB GIS-110SB1-3CB-02 | COUPLER/SECTIONALISING CB - RYEBROOK GIS 110-RYEBROOK GIS 110-110SB1-3CB | 15 | 10 | 10 | Scheduled | 30/07/2025 | 13/08/2025
TO-25-DSN-400K1-2-01 | COUPLER/SECTIONALISING CB - DUNSTOWN 400-DUNSTOWN 400-400K1-2 | 1 | 1 | 1 | Scheduled | 31/07/2025 | 31/07/2025
TO-25-220 kV B1 @ KNR-01 | BUSBAR SECTION - KNOCKANURE 220-KNOCKANURE 220-220B1 | 7 | 4 | 4 | Scheduled | 31/07/2025 | 06/08/2025
TO-25-220 kV B2 @ KNR-04 | BUSBAR SECTION - KNOCKANURE 220-KNOCKANURE 220-220B2 | 7 | 4 | 4 | Scheduled | 31/07/2025 | 06/08/2025
TO-25-KNR-220K1-02 | COUPLER/SECTIONALISING CB - KNOCKANURE 220-KNOCKANURE 220-220K1 | 7 | 4 | 4 | Scheduled | 31/07/2025 | 06/08/2025
TO-25-KNR-220K2-05 | COUPLER/SECTIONALISING CB - KNOCKANURE 220-KNOCKANURE 220-220K2 | 7 | 4 | 4 | Scheduled | 31/07/2025 | 06/08/2025
TO-25-KNR-220SB1-2CB-01 | COUPLER/SECTIONALISING CB - KNOCKANURE 220-KNOCKANURE 220-220SB1-2CB | 7 | 4 | 4 | Scheduled | 31/07/2025 | 06/08/2025
TO-25-220 kV A2 @ AD-01 | BUSBAR SECTION - AGHADA 220-AGHADA 220-220A2 | 4 | 4 | 4 | Scheduled | 05/08/2025 | 08/08/2025
TO-25-220 kV B2 @ AD-01 | BUSBAR SECTION - AGHADA 220-AGHADA 220-220B2 | 4 | 4 | 4 | Scheduled | 05/08/2025 | 08/08/2025
TO-25-AD-GGO-1-01 | 220kV FEEDER - AGHADA 220-GLANAGOW 220-1 | 4 | 4 | 4 | Scheduled | 05/08/2025 | 08/08/2025
TO-25-BVK-CLA-1-01 | 220kV FEEDER - BALLYVOUSKILL 220-CLASHAVOON 220-1 | 11 | 9 | 9 | Scheduled | 05/08/2025 | 15/08/2025
TO-25-CAH-CAP2/4-01 | CAPACITOR/SVC/REACTOR - CAHIR 110-CAHIR 110-CAP2/4 | 4 | 4 | 4 | Scheduled | 05/08/2025 | 08/08/2025
TO-25-CLW-KLS-1-08 | 110kV FEEDER - CARLOW 110-KELLIS 110-1 | 3 | 3 | 3 | Scheduled | 05/08/2025 | 07/08/2025
TO-25-CKM-PB-1-07 | 220kV FEEDER - CARRICKMINES 220-POOLBEG 220-1 | 7 | 5 | 5 | Scheduled | 05/08/2025 | 11/08/2025
TO-25-110 kV A1 @ CLO-02 | BUSBAR SECTION - CLOGHER 110-CLOGHER 110-110A1 | 11 | 9 | 9 | Scheduled | 05/08/2025 | 15/08/2025
TO-25-110 kV B1 @ CLO-02 | BUSBAR SECTION - CLOGHER 110-CLOGHER 110-110B1 | 11 | 9 | 9 | Scheduled | 05/08/2025 | 15/08/2025
TO-25-CLO-DRM-1-01 | 110kV FEEDER - CLOGHER 110-DRUMKEEN 110-1 | 11 | 9 | 9 | Scheduled | 05/08/2025 | 15/08/2025
TO-25-DRM-110SA1-01 | SECTIONALISING DISCONNECT - DRUMKEEN 110-DRUMKEEN 110-110SA1 | 11 | 9 | 9 | Scheduled | 05/08/2025 | 15/08/2025
TO-25-DRM-110SA2-01 | SECTIONALISING DISCONNECT - DRUMKEEN 110-DRUMKEEN 110-110SA2 | 11 | 9 | 9 | Scheduled | 05/08/2025 | 15/08/2025
TO-25-DRM-LET-1-01 | 110kV FEEDER - DRUMKEEN 110-LETTERKENNY 110-1 | 11 | 9 | 9 | Scheduled | 05/08/2025 | 15/08/2025
TO-25-DRM-MEE-1-01 | 110kV FEEDER - DRUMKEEN 110-MEENTYCAT 110-1 | 11 | 9 | 9 | Scheduled | 05/08/2025 | 15/08/2025
TO-25-DMY-T141-01 | DISTRIBUTION TRANSFORMER - DUNMANWAY 110-DUNMANWAY 38-T141 | 2 | 2 | 2 | Reference | 05/08/2025 | 06/08/2025
TO-25-110 kV A1 @ KLS-01 | BUSBAR SECTION - KELLIS 110-KELLIS 110-110A1 | 3 | 3 | 3 | Scheduled | 05/08/2025 | 07/08/2025
TO-25-MEE-T121-01 | GENERATOR TRANSFORMER - MEENTYCAT 110-MEENTYCAT 20-T121 | 11 | 9 | 9 | Scheduled | 05/08/2025 | 15/08/2025
TO-25-MLN-T124-01 | TSO CUSTOMER TRANSFORMER - MULLAGHARLIN 110-MULLAGHARLIN 20-T124 | 2 | 2 | 2 | Scheduled | 05/08/2025 | 06/08/2025
TO-25-220 kV A1 @ PB-01 | BUSBAR SECTION - POOLBEG 220-POOLBEG 220-220A1 | 7 | 5 | 5 | Scheduled | 05/08/2025 | 11/08/2025
TO-25-220 kV A2 @ PB-01 | BUSBAR SECTION - POOLBEG 220-POOLBEG 220-220A2 | 7 | 5 | 5 | Scheduled | 05/08/2025 | 11/08/2025
TO-25-110 kV A1 @ PLS-02 | BUSBAR SECTION - PORTLAOISE 110-PORTLAOISE 110-110A1 | 4 | 4 | 4 | Scheduled | 05/08/2025 | 08/08/2025
TO-25-110 kV B1 @ PLS-01 | BUSBAR SECTION - PORTLAOISE 110-PORTLAOISE 110-110B1 | 4 | 4 | 4 | Scheduled | 05/08/2025 | 08/08/2025
TO-25-110 kV A2 @ TEN-01 | BUSBAR SECTION - TIMAHOE 110-TIMAHOE 110-110A2 | 3 | 3 | 3 | Scheduled | 05/08/2025 | 07/08/2025
TO-25-110 kV B2 @ TEN-01 | BUSBAR SECTION - TIMAHOE 110-TIMAHOE 110-110B2 | 3 | 3 | 3 | Scheduled | 05/08/2025 | 07/08/2025
TO-25-TEN-110K2-01 | COUPLER/SECTIONALISING CB - TIMAHOE 110-TIMAHOE 110-110K2 | 3 | 3 | 3 | Scheduled | 05/08/2025 | 07/08/2025
TO-25-CBA-110SA1-01 | SECTIONALISING DISCONNECT - CLOGHBOOLA 110-CLOGHBOOLA 110-110SA1 | 16 | 12 | 12 | Scheduled | 06/08/2025 | 21/08/2025
TO-25-CBA-110SA2-01 | SECTIONALISING DISCONNECT - CLOGHBOOLA 110-CLOGHBOOLA 110-110SA2 | 16 | 12 | 12 | Scheduled | 06/08/2025 | 21/08/2025
TO-25-CBA-T122-01 | DISTRIBUTION TRANSFORMER - CLOGHBOOLA 110-CLOGHBOOLA 20-T122 | 16 | 12 | 12 | Reference | 06/08/2025 | 21/08/2025
TO-25-CBA-T131-01 | GENERATOR TRANSFORMER - CLOGHBOOLA 110-CLOGHBOOLA 33-T131 | 16 | 12 | 12 | Scheduled | 06/08/2025 | 21/08/2025
TO-25-CBA-TRI-1-01 | 110kV FEEDER - CLOGHBOOLA 110-TRIEN 110-1 | 16 | 12 | 12 | Scheduled | 06/08/2025 | 21/08/2025
TO-25-BOG-T122-01 | DISTRIBUTION TRANSFORMER - BANOGE 110-BANOGE 20-T122 | 2 | 2 | 2 | Reference | 07/08/2025 | 08/08/2025
TO-25-DMY-T142-01 | DISTRIBUTION TRANSFORMER - DUNMANWAY 110-DUNMANWAY 38-T142 | 2 | 2 | 2 | Reference | 07/08/2025 | 08/08/2025
TO-25-MLN-T123-02 | TSO CUSTOMER TRANSFORMER - MULLAGHARLIN 110-MULLAGHARLIN 20-T123 | 2 | 2 | 2 | Scheduled | 07/08/2025 | 08/08/2025
TO-25-ATY-110SA1-01 | SECTIONALISING DISCONNECT - ATHY 110-ATHY 110-110SA1 | 12 | 10 | 10 | Scheduled | 11/08/2025 | 22/08/2025
TO-25-ATY-110SA2-02 | SECTIONALISING DISCONNECT - ATHY 110-ATHY 110-110SA2 | 12 | 10 | 10 | Scheduled | 11/08/2025 | 22/08/2025
TO-25-ATY-PLS-1-06 | 110kV FEEDER - ATHY 110-PORTLAOISE 110-1 | 12 | 10 | 10 | Scheduled | 11/08/2025 | 22/08/2025
TO-25-ATY-T102-01 | DISTRIBUTION TRANSFORMER - ATHY 110-ATHY 10-T102 | 12 | 10 | 10 | Reference | 11/08/2025 | 22/08/2025
TO-25-110 kV A2 @ BYH-01 | BUSBAR SECTION - BALLYNAHULLA 110-BALLYNAHULLA 110-110A2 | 19 | 15 | 15 | Scheduled | 11/08/2025 | 29/08/2025
TO-25-110 kV B2 @ BYH-01 | BUSBAR SECTION - BALLYNAHULLA 110-BALLYNAHULLA 110-110B2 | 19 | 15 | 15 | Scheduled | 11/08/2025 | 29/08/2025
TO-25-BYH-110K2-01 | COUPLER/SECTIONALISING CB - BALLYNAHULLA 110-BALLYNAHULLA 110-110K2 | 19 | 15 | 15 | Scheduled | 11/08/2025 | 29/08/2025
TO-25-BYH-110SA1-2CB-03 | COUPLER/SECTIONALISING CB - BALLYNAHULLA 110-BALLYNAHULLA 110-110SA1-2CB | 19 | 15 | 15 | Scheduled | 11/08/2025 | 29/08/2025
TO-25-BYH-110SB1-2CB-03 | COUPLER/SECTIONALISING CB - BALLYNAHULLA 110-BALLYNAHULLA 110-110SB1-2CB | 19 | 15 | 15 | Scheduled | 11/08/2025 | 29/08/2025
TO-25-220 kV B1 @ BYH-01 | BUSBAR SECTION - BALLYNAHULLA 220-BALLYNAHULLA 220-220B1 | 5 | 5 | 5 | Scheduled | 11/08/2025 | 15/08/2025
TO-25-220 kV B2 @ BYH-01 | BUSBAR SECTION - BALLYNAHULLA 220-BALLYNAHULLA 220-220B2 | 5 | 5 | 5 | Scheduled | 11/08/2025 | 15/08/2025
TO-25-BYH-220K1-03 | COUPLER/SECTIONALISING CB - BALLYNAHULLA 220-BALLYNAHULLA 220-220K1 | 5 | 5 | 5 | Scheduled | 11/08/2025 | 15/08/2025
TO-25-BYH-220K2-02 | COUPLER/SECTIONALISING CB - BALLYNAHULLA 220-BALLYNAHULLA 220-220K2 | 5 | 5 | 5 | Scheduled | 11/08/2025 | 15/08/2025
TO-25-BYH-220SB1-2CB-01 | COUPLER/SECTIONALISING CB - BALLYNAHULLA 220-BALLYNAHULLA 220-220SB1-2CB | 5 | 5 | 5 | Scheduled | 11/08/2025 | 15/08/2025
TO-25-BYH-CDL-1-01 | 110kV FEEDER - BALLYNAHULLA 110-CORDAL 110-1 | 19 | 15 | 15 | Scheduled | 11/08/2025 | 29/08/2025
TO-25-CRO-IA-1-01 | 110kV FEEDER - COOLROE 110-INNISCARRA 110-1 | 12 | 10 | 10 | Scheduled | 11/08/2025 | 22/08/2025
TO-25-CDL-110SA1-01 | SECTIONALISING DISCONNECT - CORDAL 110-CORDAL 110-110SA1 | 19 | 15 | 15 | Scheduled | 11/08/2025 | 29/08/2025
TO-25-CDL-110SA2-01 | SECTIONALISING DISCONNECT - CORDAL 110-CORDAL 110-110SA2 | 19 | 15 | 15 | Scheduled | 11/08/2025 | 29/08/2025
TO-25-CDL-T132-01 | GENERATOR TRANSFORMER - CORDAL 110-CORDAL 33-T132 | 19 | 15 | 15 | Scheduled | 11/08/2025 | 29/08/2025
TO-25-CDL-T141-01 | DISTRIBUTION TRANSFORMER - CORDAL 110-CORDAL 38-T141 | 19 | 15 | 15 | Reference | 11/08/2025 | 29/08/2025
TO-25-FLA-GIL-1-01 | 110kV FEEDER - FLAGFORD 110-GILRA 110-1 | 2 | 2 | 2 | Scheduled | 11/08/2025 | 12/08/2025
TO-25-GIL-T121-01 | TSO CUSTOMER TRANSFORMER - GILRA 110-GILRA 20-T121 | 2 | 2 | 2 | Reference | 11/08/2025 | 12/08/2025
TO-25-220 kV A1 @ GOR-02 | BUSBAR SECTION - GORMAN 220-GORMAN 220-220A1 | 12 | 10 | 10 | Scheduled | 11/08/2025 | 22/08/2025
TO-25-220 kV A2 @ GOR-01 | BUSBAR SECTION - GORMAN 220-GORMAN 220-220A2 | 12 | 10 | 10 | Scheduled | 11/08/2025 | 22/08/2025
TO-25-GOR-LOU-1-02 | 220kV FEEDER - GORMAN 220-LOUTH 220-1 | 12 | 10 | 10 | Scheduled | 11/08/2025 | 22/08/2025
TO-25-IA-MAC-1-03 | 110kV FEEDER - INNISCARRA 110-MACROOM 110-1 | 12 | 10 | 10 | Scheduled | 11/08/2025 | 22/08/2025
TO-25-IA-T101-01 | GENERATOR TRANSFORMER - INNISCARRA 110-INNISCARRA G1-T101 | 12 | 10 | 10 | Scheduled | 11/08/2025 | 22/08/2025
TO-25-IA-T101-02 | GENERATOR TRANSFORMER - INNISCARRA 110-INNISCARRA G1-T101 | 12 | 10 | 10 | Scheduled | 11/08/2025 | 22/08/2025
TO-25-KHL-T131-01 | GENERATOR TRANSFORMER - KILL HILL 110-KILL HILL 33-T131 | 9 | 7 | 7 | Scheduled | 11/08/2025 | 19/08/2025
TO-25-220 kV A2 @ LOU-09 | BUSBAR SECTION - LOUTH 220-LOUTH 220-220A2 | 12 | 10 | 10 | Scheduled | 11/08/2025 | 22/08/2025
TO-25-220 kV B2 @ LOU-09 | BUSBAR SECTION - LOUTH 220-LOUTH 220-220B2 | 12 | 10 | 10 | Scheduled | 11/08/2025 | 22/08/2025
TO-25-400 kV A3 @ MP GIS-01 | BUSBAR SECTION - MONEYPOINT GIS 400-MONEYPOINT GIS 400-400A3 | 5 | 5 | 5 | Scheduled | 11/08/2025 | 15/08/2025
TO-25-400 kV B3 @ MP GIS-01 | BUSBAR SECTION - MONEYPOINT GIS 400-MONEYPOINT GIS 400-400B3 | 5 | 5 | 5 | Scheduled | 11/08/2025 | 15/08/2025
TO-25-MP GIS-400K3-01 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 400-MONEYPOINT GIS 400-400K3 | 5 | 5 | 5 | Scheduled | 11/08/2025 | 15/08/2025
TO-25-MP GIS-400SA1-3CB-02 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 400-MONEYPOINT GIS 400-400SA1-3CB | 5 | 5 | 5 | Scheduled | 11/08/2025 | 15/08/2025
TO-25-MP GIS-400SB1-3CB-02 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 400-MONEYPOINT GIS 400-400SB1-3CB | 5 | 5 | 5 | Scheduled | 11/08/2025 | 15/08/2025
TO-25-SLC-T122-03 | GENERATOR TRANSFORMER - SLIEVECALLAN 110-SLIEVECALLAN 20-T122 | 2 | 2 | 2 | Scheduled | 11/08/2025 | 12/08/2025
TO-25-COL-CDU-1-03 | 110kV FEEDER - COLLEGE PARK 110-CORDUFF 110-1 | 3 | 3 | 3 | Scheduled | 12/08/2025 | 14/08/2025
TO-25-DER-KIN-1-03 | 110kV FEEDER - DERRYIRON 110-KINNEGAD 110-1 | 22 | 16 | 16 | Scheduled | 12/08/2025 | 02/09/2025
TO-25-DER-T1/T2-02 | GENERATOR TRANSFORMER - DERRYIRON 110-RHODE 110-T1/T2 | 22 | 16 | 16 | Scheduled | 12/08/2025 | 02/09/2025
TO-25-KLS-T2101-05 | TRANSFORMER - KELLIS 220-KELLIS 110-T2101 | 3 | 3 | 3 | Scheduled | 12/08/2025 | 14/08/2025
TO-25-BYH-T2102-01 | TRANSFORMER - BALLYNAHULLA 220-BALLYNAHULLA 110-T2102 | 2 | 2 | 8 | Scheduled | 13/08/2025 | 14/08/2025
TO-25-CSH-SAL-1-03 | 110kV FEEDER - CASHLA 110-SALTHILL 110-1 | 16 | 12 | 12 | Scheduled | 13/08/2025 | 28/08/2025
TO-25-KNY-SAL-1-02 | 110kV FEEDER - KNOCKRANNY 110-SALTHILL 110-1 | 14 | 10 | 10 | Scheduled | 13/08/2025 | 26/08/2025
TO-25-SAL-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - SALTHILL 110-SALTHILL 110-110SA1-2CB | 14 | 10 | 10 | Scheduled | 13/08/2025 | 26/08/2025
TO-25-SAL-T102-01 | DISTRIBUTION TRANSFORMER - SALTHILL 110-SALTHILL 10-T102 | 14 | 10 | 10 | Reference | 13/08/2025 | 26/08/2025
TO-25-KTN-WAT-1-04 | 110kV FEEDER - KILLOTERAN 110-WATERFORD 110-1 | 2 | 2 | 2 | Scheduled | 14/08/2025 | 15/08/2025
TO-25-KLH-T121-01 | GENERATOR TRANSFORMER - KNOCKALOUGH 110-KNOCKALOUGH 20-T121 | 1 | 1 | 1 | Scheduled | 14/08/2025 | 14/08/2025
TO-25-CLG-FIN GIS-1-01 | 110kV FEEDER - CLOGHRAN 110-FINGLAS GIS 110-1 | 18 | 12 | 12 | Scheduled | 15/08/2025 | 01/09/2025
TO-25-CLG-FIN GIS-1-03 | 110kV FEEDER - CLOGHRAN 110-FINGLAS GIS 110-1 | 18 | 12 | 12 | Proposed | 15/08/2025 | 01/09/2025
TO-25-MCE-SNU-1-02 | 110kV FEEDER - MACETOWN 110-SNUGBOROUGH 110-1 | 18 | 12 | 12 | Scheduled | 15/08/2025 | 01/09/2025
TO-25-MCE-SNU-1-01 | 110kV FEEDER - MACETOWN 110-SNUGBOROUGH 110-1 | 18 | 12 | 12 | Proposed | 15/08/2025 | 01/09/2025
TO-25-AA GIS-110K3-01 | COUPLER/SECTIONALISING CB - ARDNACRUSHA GIS 110-ARDNACRUSHA GIS 110-110K3 | 5 | 5 | 5 | Proposed | 18/08/2025 | 22/08/2025
TO-25-AA GIS-110SA1-3CB-01 | COUPLER/SECTIONALISING CB - ARDNACRUSHA GIS 110-ARDNACRUSHA GIS 110-110SA1-3CB | 5 | 5 | 5 | Proposed | 18/08/2025 | 22/08/2025
TO-25-AA GIS-110SB1-3CB-01 | COUPLER/SECTIONALISING CB - ARDNACRUSHA GIS 110-ARDNACRUSHA GIS 110-110SB1-3CB | 5 | 5 | 5 | Proposed | 18/08/2025 | 22/08/2025
TO-25-AA GIS-CAP1-01 | CAPACITOR/SVC/REACTOR - ARDNACRUSHA GIS 110-ARDNACRUSHA GIS 110-CAP1 | 5 | 5 | 5 | Proposed | 18/08/2025 | 22/08/2025
TO-25-AA GIS-T104-01 | GENERATOR TRANSFORMER - ARDNACRUSHA GIS 110-ARDNACRUSHA GIS G4-T104 | 5 | 5 | 5 | Proposed | 18/08/2025 | 22/08/2025
TO-25-220 kV A1/A2 @ BVK-01 | BUSBAR SECTION - BALLYVOUSKILL 220-BALLYVOUSKILL 220-220A1-A2 | 9 | 7 | 7 | Scheduled | 18/08/2025 | 26/08/2025
TO-25-220 kV B1/B2 @ BVK-01 | BUSBAR SECTION - BALLYVOUSKILL 220-BALLYVOUSKILL 220-220B1-B2 | 9 | 7 | 7 | Scheduled | 18/08/2025 | 26/08/2025
TO-25-BVK-220K1-01 | COUPLER/SECTIONALISING CB - BALLYVOUSKILL 220-BALLYVOUSKILL 220-220K1 | 9 | 7 | 7 | Scheduled | 18/08/2025 | 26/08/2025
TO-25-BVK-220K2-04 | COUPLER/SECTIONALISING CB - BALLYVOUSKILL 220-BALLYVOUSKILL 220-220K2 | 9 | 7 | 7 | Scheduled | 18/08/2025 | 26/08/2025
TO-25-BVK-220SA1-2CB-02 | COUPLER/SECTIONALISING CB - BALLYVOUSKILL 220-BALLYVOUSKILL 220-220SA1-2CB | 9 | 7 | 7 | Scheduled | 18/08/2025 | 26/08/2025
TO-25-BVK-220SB1-2CB-02 | COUPLER/SECTIONALISING CB - BALLYVOUSKILL 220-BALLYVOUSKILL 220-220SB1-2CB | 9 | 7 | 7 | Scheduled | 18/08/2025 | 26/08/2025
TO-25-110 kV A1 @ BLC-01 | BUSBAR SECTION - BELCAMP 110-BELCAMP 110-110A1 | 5 | 5 | 5 | Scheduled | 18/08/2025 | 22/08/2025
TO-25-110 kV A3 @ BLC-03 | BUSBAR SECTION - BELCAMP 110-BELCAMP 110-110A3 | 5 | 5 | 5 | Scheduled | 18/08/2025 | 22/08/2025
TO-25-BLC-110K1-03 | COUPLER/SECTIONALISING CB - BELCAMP 110-BELCAMP 110-110K1 | 5 | 5 | 5 | Scheduled | 18/08/2025 | 22/08/2025
TO-25-BLC-110K3-03 | COUPLER/SECTIONALISING CB - BELCAMP 110-BELCAMP 110-110K3 | 5 | 5 | 5 | Scheduled | 18/08/2025 | 22/08/2025
TO-25-BLC-110SA1-3CB-01 | COUPLER/SECTIONALISING CB - BELCAMP 110-BELCAMP 110-110SA1-3CB | 5 | 5 | 5 | Scheduled | 18/08/2025 | 22/08/2025
TO-25-BOL-ENN-1-01 | 110kV FEEDER - BOOLTIAGH 110-ENNIS 110-1 | 12 | 10 | 10 | Proposed | 18/08/2025 | 29/08/2025
TO-25-CVW-KRA-1-01 | 110kV FEEDER - CASTLEVIEW 110-KNOCKRAHA 110-1 | 12 | 10 | 10 | Scheduled | 18/08/2025 | 29/08/2025
TO-25-CLA-MAC-1-02 | 110kV FEEDER - CLASHAVOON 110-MACROOM 110-1 | 5 | 5 | 5 | Scheduled | 18/08/2025 | 22/08/2025
TO-25-CLA-MAC-1-04 | 110kV FEEDER - CLASHAVOON 110-MACROOM 110-1 | 5 | 5 | 5 | Proposed | 18/08/2025 | 22/08/2025
TO-25-110 kV A1 @ CLG-01 | BUSBAR SECTION - CLOGHRAN 110-CLOGHRAN 110-110A1 | 2 | 2 | 2 | Scheduled | 18/08/2025 | 19/08/2025
TO-25-110 kV B1 @ CLG-01 | BUSBAR SECTION - CLOGHRAN 110-CLOGHRAN 110-110B1 | 2 | 2 | 2 | Scheduled | 18/08/2025 | 19/08/2025
TO-25-CLG-110K1-03 | COUPLER/SECTIONALISING CB - CLOGHRAN 110-CLOGHRAN 110-110K1 | 2 | 2 | 2 | Scheduled | 18/08/2025 | 19/08/2025
TO-25-CLG-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - CLOGHRAN 110-CLOGHRAN 110-110SA1-2CB | 2 | 2 | 2 | Scheduled | 18/08/2025 | 19/08/2025
TO-25-CLG-110SB1-2CB-01 | COUPLER/SECTIONALISING CB - CLOGHRAN 110-CLOGHRAN 110-110SB1-2CB | 2 | 2 | 2 | Scheduled | 18/08/2025 | 19/08/2025
TO-25-220 kV A2 @ CLE-01 | BUSBAR SECTION - CLONEE 220-CLONEE 220-220A2 | 12 | 10 | 10 | Scheduled | 18/08/2025 | 29/08/2025
TO-25-220 kV B2 @ CLE-01 | BUSBAR SECTION - CLONEE 220-CLONEE 220-220B2 | 12 | 10 | 10 | Scheduled | 18/08/2025 | 29/08/2025
TO-25-CLE-220K2-03 | COUPLER/SECTIONALISING CB - CLONEE 220-CLONEE 220-220K2 | 12 | 10 | 10 | Scheduled | 18/08/2025 | 29/08/2025
TO-25-CLE-220SA1-2CB-05 | COUPLER/SECTIONALISING CB - CLONEE 220-CLONEE 220-220SA1-2CB | 12 | 10 | 10 | Scheduled | 18/08/2025 | 29/08/2025
TO-25-CLE-220SB1-2CB-05 | COUPLER/SECTIONALISING CB - CLONEE 220-CLONEE 220-220SB1-2CB | 12 | 10 | 10 | Scheduled | 18/08/2025 | 29/08/2025
TO-25-CLE-T222-01 | TSO CUSTOMER TRANSFORMER - CLONEE 220-CLONEE 20-T222 | 12 | 10 | 10 | Scheduled | 18/08/2025 | 29/08/2025
TO-25-CNO-KPG-1-01 | 110kV FEEDER - COOLNANOONAGH 110-KILPADDOGE 110-1 | 5 | 5 | 5 | Proposed | 18/08/2025 | 22/08/2025
TO-25-CNO-T131-01 | GENERATOR TRANSFORMER - COOLNANOONAGH 110-COOLNANOONAGH 33-T131 | 5 | 5 | 5 | Proposed | 18/08/2025 | 22/08/2025
TO-25-CDY-GRV-1-04 | 110kV FEEDER - CORDERRY 110-GARVAGH 110-1 | 14 | 10 | 10 | Proposed | 18/08/2025 | 31/08/2025
TO-25-DMY-MAC-1-03 | 110kV FEEDER - DUNMANWAY 110-MACROOM 110-1 | 26 | 20 | 20 | Scheduled | 18/08/2025 | 12/09/2025
TO-25-220 kV A2 @ DSN-01 | BUSBAR SECTION - DUNSTOWN 220-DUNSTOWN 220-220A2 | 15 | 11 | 11 | Scheduled | 18/08/2025 | 01/09/2025
TO-25-DSN-T4201-01 | TRANSFORMER - DUNSTOWN 400-DUNSTOWN 220-T4201 | 12 | 10 | 10 | Proposed | 18/08/2025 | 29/08/2025
TO-25-110 kV A5 @ FIN GIS-02 | BUSBAR SECTION - FINGLAS GIS 110-FINGLAS GIS 110-110A5 | 16 | 12 | 12 | Proposed | 18/08/2025 | 02/09/2025
TO-25-110 kV B5 @ FIN GIS-02 | BUSBAR SECTION - FINGLAS GIS 110-FINGLAS GIS 110-110B5 | 16 | 12 | 12 | Proposed | 18/08/2025 | 02/09/2025
TO-25-FIN GIS-110K5-03 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110K5 | 16 | 12 | 12 | Proposed | 18/08/2025 | 02/09/2025
TO-25-FIN GIS-110SA3-5CB-05 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110SA3-5CB | 16 | 12 | 12 | Proposed | 18/08/2025 | 02/09/2025
TO-25-FIN GIS-110SB3-5CB-04 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110SB3-5CB | 16 | 12 | 12 | Proposed | 18/08/2025 | 02/09/2025
TO-25-GRV-110K1-04 | COUPLER/SECTIONALISING CB - GARVAGH 110-GARVAGH 110-110K1 | 14 | 10 | 10 | Proposed | 18/08/2025 | 31/08/2025
TO-25-GRV-T121-04 | GENERATOR TRANSFORMER - GARVAGH 110-GARVAGH 20-T121 | 14 | 10 | 10 | Proposed | 18/08/2025 | 31/08/2025
TO-25-GRV-T141-03 | DISTRIBUTION TRANSFORMER - GARVAGH 110-GARVAGH 20-T141 | 14 | 10 | 10 | Reference (Proposed) | 18/08/2025 | 31/08/2025
TO-25-110 kV A2 @ KRA-04 | BUSBAR SECTION - KNOCKRAHA 110-KNOCKRAHA 110-110A2 | 12 | 10 | 10 | Scheduled | 18/08/2025 | 29/08/2025
TO-25-110 kV B2 @ KRA-04 | BUSBAR SECTION - KNOCKRAHA 110-KNOCKRAHA 110-110B2 | 12 | 10 | 10 | Scheduled | 18/08/2025 | 29/08/2025
TO-25-LOU-T2103-05 | TRANSFORMER - LOUTH 220-LOUTH 110-T2103 | 21 | 15 | 15 | Proposed | 18/08/2025 | 07/09/2025
TO-25-MCE-110SA1-02 | SECTIONALISING DISCONNECT - MACETOWN 110-MACETOWN 110-110SA1 | 2 | 2 | 2 | Scheduled | 18/08/2025 | 19/08/2025
TO-25-MCE-110SA2-02 | SECTIONALISING DISCONNECT - MACETOWN 110-MACETOWN 110-110SA2 | 2 | 2 | 2 | Scheduled | 18/08/2025 | 19/08/2025
TO-25-MCE-T102-02 | DISTRIBUTION TRANSFORMER - MACETOWN 110-MACETOWN 10-T102 | 2 | 2 | 2 | Reference | 18/08/2025 | 19/08/2025
TO-25-MCE-T124-02 | TSO CUSTOMER TRANSFORMER - MACETOWN 110-MACETOWN 20-T124 | 2 | 2 | 2 | Scheduled | 18/08/2025 | 19/08/2025
TO-25-220 kV B1 @ MP GIS-03 | BUSBAR SECTION - MONEYPOINT GIS 220-MONEYPOINT GIS 220-220B1 | 5 | 5 | 5 | Scheduled | 18/08/2025 | 22/08/2025
TO-25-220 kV B2 @ MP GIS-02 | BUSBAR SECTION - MONEYPOINT GIS 220-MONEYPOINT GIS 220-220B2 | 5 | 5 | 5 | Scheduled | 18/08/2025 | 22/08/2025
TO-25-MP GIS-220K1-04 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 220-MONEYPOINT GIS 220-220K1 | 5 | 5 | 5 | Scheduled | 18/08/2025 | 22/08/2025
TO-25-MP GIS-220K2-03 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 220-MONEYPOINT GIS 220-220K2 | 5 | 5 | 5 | Scheduled | 18/08/2025 | 22/08/2025
TO-25-MP GIS-220SB1-2CB-01 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 220-MONEYPOINT GIS 220-220SB1-2CB | 5 | 5 | 5 | Scheduled | 18/08/2025 | 22/08/2025
TO-25-110 kV A2 @ SNU-01 | BUSBAR SECTION - SNUGBOROUGH 110-SNUGBOROUGH 110-110A2 | 16 | 12 | 12 | Proposed | 18/08/2025 | 02/09/2025
TO-25-110 kV B2 @ SNU-02 | BUSBAR SECTION - SNUGBOROUGH 110-SNUGBOROUGH 110-110B2 | 16 | 12 | 12 | Proposed | 18/08/2025 | 02/09/2025
TO-25-SNU-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - SNUGBOROUGH 110-SNUGBOROUGH 110-110SA1-2CB | 16 | 12 | 12 | Proposed | 18/08/2025 | 02/09/2025
TO-25-SNU-110SB1-2CB-02 | COUPLER/SECTIONALISING CB - SNUGBOROUGH 110-SNUGBOROUGH 110-110SB1-2CB | 16 | 12 | 12 | Proposed | 18/08/2025 | 02/09/2025
TO-25-220 kV A1 @ TB-02 | BUSBAR SECTION - TARBERT 220-TARBERT 220-220A1 | 4 | 4 | 4 | Proposed | 19/08/2025 | 22/08/2025
TO-25-220 kV A2 @ TB-05 | BUSBAR SECTION - TARBERT 220-TARBERT 220-220A2 | 4 | 4 | 4 | Proposed | 19/08/2025 | 22/08/2025
TO-25-220 kV B1 @ TB-02 | BUSBAR SECTION - TARBERT 220-TARBERT 220-220B1 | 4 | 4 | 4 | Proposed | 19/08/2025 | 22/08/2025
TO-25-220 kV B2 @ TB-05 | BUSBAR SECTION - TARBERT 220-TARBERT 220-220B2 | 4 | 4 | 4 | Proposed | 19/08/2025 | 22/08/2025
TO-25-TB-220K1-2-01 | COUPLER/SECTIONALISING CB - TARBERT 220-TARBERT 220-220K1-2 | 4 | 4 | 4 | Proposed | 19/08/2025 | 22/08/2025
TO-25-BYH-T2101-01 | TRANSFORMER - BALLYNAHULLA 220-BALLYNAHULLA 110-T2101 | 2 | 2 | 2 | Scheduled | 20/08/2025 | 21/08/2025
TO-25-CDU-220K1-3-02 | COUPLER/SECTIONALISING CB - CORDUFF 220-CORDUFF 220-220K1-3 | 2 | 2 | 2 | Proposed | 20/08/2025 | 21/08/2025
TO-25-SKY-T131-02 | GENERATOR TRANSFORMER - SRAHNAKILLY 110-SRAHNAKILLY 33-T131 | 1 | 1 | 1 | Scheduled | 20/08/2025 | 20/08/2025
TO-25-CBT-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - CASTLEBAGOT 110-CASTLEBAGOT 110-110SA1-2CB | 1 | 1 | 1 | Scheduled | 25/08/2025 | 25/08/2025
TO-25-CLH-110SA1-01 | SECTIONALISING DISCONNECT - CLAHANE 110-CLAHANE 110-110SA1 | 5 | 5 | 5 | Proposed | 25/08/2025 | 29/08/2025
TO-25-CLH-110SA2-02 | SECTIONALISING DISCONNECT - CLAHANE 110-CLAHANE 110-110SA2 | 5 | 5 | 5 | Proposed | 25/08/2025 | 29/08/2025
TO-25-CLH-TRL-1-01 | 110kV FEEDER - CLAHANE 110-TRALEE 110-1 | 5 | 5 | 5 | Scheduled | 25/08/2025 | 29/08/2025
TO-25-DRU-CAP2-01 | CAPACITOR/SVC/REACTOR - DRUMLINE 110-DRUMLINE 110-CAP2 | 5 | 5 | 5 | Scheduled | 25/08/2025 | 29/08/2025
TO-25-110 kV A2 @ KNR-01 | BUSBAR SECTION - KNOCKANURE 110-KNOCKANURE 110-110A2 | 12 | 10 | 10 | Proposed | 25/08/2025 | 05/09/2025
TO-25-110 kV B2 @ KNR-01 | BUSBAR SECTION - KNOCKANURE 110-KNOCKANURE 110-110B2 | 12 | 10 | 10 | Proposed | 25/08/2025 | 05/09/2025
TO-25-KNR-110SA1-2CB-02 | COUPLER/SECTIONALISING CB - KNOCKANURE 110-KNOCKANURE 110-110SA1-2CB | 12 | 10 | 10 | Proposed | 25/08/2025 | 05/09/2025
TO-25-KNR-110SA2-4CB-01 | COUPLER/SECTIONALISING CB - KNOCKANURE 110-KNOCKANURE 110-110SA2-4CB | 12 | 10 | 10 | Proposed | 25/08/2025 | 05/09/2025
TO-25-KNR-110SB1-2CB-02 | COUPLER/SECTIONALISING CB - KNOCKANURE 110-KNOCKANURE 110-110SB1-2CB | 12 | 10 | 10 | Proposed | 25/08/2025 | 05/09/2025
TO-25-KNR-110SB2-4CB-01 | COUPLER/SECTIONALISING CB - KNOCKANURE 110-KNOCKANURE 110-110SB2-4CB | 12 | 10 | 10 | Proposed | 25/08/2025 | 05/09/2025
TO-25-220 kV A2 @ KNR-04 | BUSBAR SECTION - KNOCKANURE 220-KNOCKANURE 220-220A2 | 12 | 10 | 10 | Proposed | 25/08/2025 | 05/09/2025
TO-25-220 kV B2 @ KNR-05 | BUSBAR SECTION - KNOCKANURE 220-KNOCKANURE 220-220B2 | 12 | 10 | 10 | Proposed | 25/08/2025 | 05/09/2025
TO-25-KNR-220K2-06 | COUPLER/SECTIONALISING CB - KNOCKANURE 220-KNOCKANURE 220-220K2 | 12 | 10 | 10 | Proposed | 25/08/2025 | 05/09/2025
TO-25-KNR-220SA1-2CB-05 | COUPLER/SECTIONALISING CB - KNOCKANURE 220-KNOCKANURE 220-220SA1-2CB | 12 | 10 | 10 | Proposed | 25/08/2025 | 05/09/2025
TO-25-KNR-220SB1-2CB-05 | COUPLER/SECTIONALISING CB - KNOCKANURE 220-KNOCKANURE 220-220SB1-2CB | 12 | 10 | 10 | Proposed | 25/08/2025 | 05/09/2025
TO-25-KNR-T2102-01 | TRANSFORMER - KNOCKANURE 220-KNOCKANURE 110-T2102 | 12 | 10 | 10 | Proposed | 25/08/2025 | 05/09/2025
TO-25-LET-CAP2-02 | CAPACITOR/SVC/REACTOR - LETTERKENNY 110-LETTERKENNY 110-CAP2 | 5 | 5 | 5 | Proposed | 25/08/2025 | 29/08/2025
TO-25-220 kV A2 @ LOU-04 | BUSBAR SECTION - LOUTH 220-LOUTH 220-220A2 | 4 | 4 | 4 | Proposed | 25/08/2025 | 28/08/2025
TO-25-220 kV B2 @ LOU-03 | BUSBAR SECTION - LOUTH 220-LOUTH 220-220B2 | 4 | 4 | 4 | Proposed | 25/08/2025 | 28/08/2025
TO-25-BEG-T101-01 | DISTRIBUTION TRANSFORMER - BALLYBEG 110-BALLYBEG 10-T101 | 2 | 2 | 2 | Reference (Proposed) | 26/08/2025 | 27/08/2025
TO-25-BVK-GRO-1-01 | 110kV FEEDER - BALLYVOUSKILL 110-GARROW 110-1 | 2 | 2 | 2 | Proposed | 26/08/2025 | 27/08/2025
TO-25-RYB GIS-110K3-01 | COUPLER/SECTIONALISING CB - RYEBROOK GIS 110-RYEBROOK GIS 110-110K3 | 2 | 2 | 2 | Proposed | 26/08/2025 | 27/08/2025
TO-25-RYB GIS-T102-01 | TSO CUSTOMER TRANSFORMER - RYEBROOK GIS 110-RYEBROOK 10-T102 | 2 | 2 | 2 | Proposed | 26/08/2025 | 27/08/2025
TO-25-TY-T2001/2-04 | GENERATOR TRANSFORMER - TYNAGH 220-TYNAGH G1/2-T2001/2 | 38 | 28 | 28 | Proposed | 26/08/2025 | 02/10/2025
TO-25-CSH-GAL GIS-1-03 | 110kV FEEDER - CASHLA 110-GALWAY GIS 110-1 | 2 | 2 | 2 | Scheduled | 27/08/2025 | 28/08/2025
TO-25-GOR-LOU-1-01 | 220kV FEEDER - GORMAN 220-LOUTH 220-1 | 2 | 2 |  | Proposed | 27/08/2025 | 28/08/2025
TO-25-IKE,T-SH-1-08 | 110kV FEEDER - IKERRIN tee-SHANNONBRIDGE 110-1 | 2 | 2 | 2 | Proposed | 27/08/2025 | 28/08/2025
TO-25-110 kV A2 @ KPG-01 | BUSBAR SECTION - KILPADDOGE 110-KILPADDOGE 110-110A2 | 3 | 3 | 3 | Proposed | 27/08/2025 | 29/08/2025
TO-25-KPG-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - KILPADDOGE 110-KILPADDOGE 110-110SA1-2CB | 3 | 3 | 3 | Proposed | 27/08/2025 | 29/08/2025
TO-25-KPG-110SA2-4CB-01 | COUPLER/SECTIONALISING CB - KILPADDOGE 110-KILPADDOGE 110-110SA2-4CB | 3 | 3 | 3 | Proposed | 27/08/2025 | 29/08/2025
TO-25-KPG-T2102-01 | TRANSFORMER - KILPADDOGE 220-KILPADDOGE 110-T2102 | 3 | 3 | 3 | Proposed | 27/08/2025 | 29/08/2025
TO-25-220 kV A2 @ LOU-05 | BUSBAR SECTION - LOUTH 220-LOUTH 220-220A2 | 2 | 2 | 2 | Proposed | 27/08/2025 | 28/08/2025
TO-25-220 kV B2 @ LOU-05 | BUSBAR SECTION - LOUTH 220-LOUTH 220-220B2 | 2 | 2 | 2 | Proposed | 27/08/2025 | 28/08/2025
TO-25-110 kV A1 @ SH-03 | BUSBAR SECTION - SHANNONBRIDGE 110-SHANNONBRIDGE 110-110A1 | 2 | 2 |  | Proposed | 27/08/2025 | 28/08/2025
TO-25-110 kV B1 @ SH-04 | BUSBAR SECTION - SHANNONBRIDGE 110-SHANNONBRIDGE 110-110B1 | 2 | 2 | 2 | Proposed | 27/08/2025 | 28/08/2025
TO-25-SH-110K1-2-04 | COUPLER/SECTIONALISING CB - SHANNONBRIDGE 110-SHANNONBRIDGE 110-110K1-2 | 2 | 2 | 2 | Proposed | 27/08/2025 | 28/08/2025
TO-25-TY-T2001/2-01 | GENERATOR TRANSFORMER - TYNAGH 220-TYNAGH G1/2-T2001/2 | 37 | 27 | 27 | Scheduled | 27/08/2025 | 02/10/2025
TO-25-TY-T2001/2-02 | GENERATOR TRANSFORMER - TYNAGH 220-TYNAGH G1/2-T2001/2 | 7 | 5 | 5 | Scheduled | 27/08/2025 | 02/09/2025
TO-25-BYH-BVK-1-01 | 220kV FEEDER - BALLYNAHULLA 220-BALLYVOUSKILL 220-1 | 2 | 2 | 2 | Proposed | 28/08/2025 | 29/08/2025
TO-25-KTL-T142-01 | DISTRIBUTION TRANSFORMER - KILTEEL 110-KILTEEL 38-T142 | 2 | 2 | 2 | Reference (Proposed) | 28/08/2025 | 29/08/2025
TO-25-NEW-PLS-1-04 | 110kV FEEDER - NEWBRIDGE 110-PORTLAOISE 110-1 | 2 | 2 | 2 | Proposed | 28/08/2025 | 29/08/2025
TO-25-RYB GIS-110K4-01 | COUPLER/SECTIONALISING CB - RYEBROOK GIS 110-RYEBROOK GIS 110-110K4 | 2 | 2 | 2 | Proposed | 28/08/2025 | 29/08/2025
TO-25-110 kV A4 @ CBT-01 | BUSBAR SECTION - CASTLEBAGOT 110-CASTLEBAGOT 110-110A4 | 22 | 16 | 16 | Proposed | 29/08/2025 | 19/09/2025
TO-25-110 kV B4 @ CBT-01 | BUSBAR SECTION - CASTLEBAGOT 110-CASTLEBAGOT 110-110B4 | 22 | 16 | 16 | Proposed | 29/08/2025 | 19/09/2025
TO-25-CBT-110K4-02 | COUPLER/SECTIONALISING CB - CASTLEBAGOT 110-CASTLEBAGOT 110-110K4 | 22 | 16 | 16 | Proposed | 29/08/2025 | 19/09/2025
TO-25-CBT-110SA2-4CB-02 | COUPLER/SECTIONALISING CB - CASTLEBAGOT 110-CASTLEBAGOT 110-110SA2-4CB | 22 | 16 | 16 | Proposed | 29/08/2025 | 19/09/2025
TO-25-CBT-110SB2-4CB-02 | COUPLER/SECTIONALISING CB - CASTLEBAGOT 110-CASTLEBAGOT 110-110SB2-4CB | 22 | 16 | 16 | Proposed | 29/08/2025 | 19/09/2025
TO-25-220 kV A2 @ CBT-02 | BUSBAR SECTION - CASTLEBAGOT 220-CASTLEBAGOT 220-220A2 | 22 | 16 | 16 | Proposed | 29/08/2025 | 19/09/2025
TO-25-220 kV B2 @ CBT-02 | BUSBAR SECTION - CASTLEBAGOT 220-CASTLEBAGOT 220-220B2 | 22 | 16 | 16 | Proposed | 29/08/2025 | 19/09/2025
TO-25-CBT-220K2-04 | COUPLER/SECTIONALISING CB - CASTLEBAGOT 220-CASTLEBAGOT 220-220K2 | 22 | 16 | 16 | Proposed | 29/08/2025 | 19/09/2025
TO-25-CBT-220SA1-2CB-04 | COUPLER/SECTIONALISING CB - CASTLEBAGOT 220-CASTLEBAGOT 220-220SA1-2CB | 22 | 16 | 16 | Proposed | 29/08/2025 | 19/09/2025
TO-25-CBT-220SB1-2CB-04 | COUPLER/SECTIONALISING CB - CASTLEBAGOT 220-CASTLEBAGOT 220-220SB1-2CB | 22 | 16 | 16 | Proposed | 29/08/2025 | 19/09/2025
TO-25-CBT-T2104-01 | TRANSFORMER - CASTLEBAGOT 220-CASTLEBAGOT 110-T2104 | 22 | 16 | 16 | Proposed | 29/08/2025 | 19/09/2025
TO-25-TSB-110SA1-01 | SECTIONALISING DISCONNECT - THORNSBERRY 110-THORNSBERRY 110-110SA1 | 2 | 0 | 0 | Scheduled | 30/08/2025 | 31/08/2025
TO-25-TSB-110SA2-01 | SECTIONALISING DISCONNECT - THORNSBERRY 110-THORNSBERRY 110-110SA2 | 2 | 0 | 0 | Scheduled | 30/08/2025 | 31/08/2025
TO-25-TSB-T142-01 | DISTRIBUTION TRANSFORMER - THORNSBERRY 110-THORNSBERRY 38-T142 | 2 | 0 | 0 | Reference | 30/08/2025 | 31/08/2025
TO-25-AHA-KLN-2-01 | 110kV FEEDER - AHANE 110-KILLONAN 110-2 | 2 | 2 | 2 | Reference (Proposed) | 01/09/2025 | 02/09/2025
TO-25-AHA-T102-01 | DISTRIBUTION TRANSFORMER - AHANE 110-AHANE 10-T102 | 2 | 2 | 2 | Reference (Proposed) | 01/09/2025 | 02/09/2025
TO-25-ARI-T121-02 | DISTRIBUTION TRANSFORMER - ARIGNA 110-ARIGNA 20-T121 | 5 | 5 | 5 | Reference (Proposed) | 01/09/2025 | 05/09/2025
TO-25-ARI,T-ARI-1-01 | 110kV FEEDER - ARIGNA tee-ARIGNA 110-1 | 5 | 5 | 5 | Proposed | 01/09/2025 | 05/09/2025
TO-25-ARI,T-COS-1-02 | 110kV FEEDER - ARIGNA tee-CARRICK ON SHANNON 110-1 | 5 | 5 | 5 | Proposed | 01/09/2025 | 05/09/2025
TO-25-ARI,T-CDY-1-02 | 110kV FEEDER - ARIGNA tee-CORDERRY 110-1 | 5 | 5 | 5 | Proposed | 01/09/2025 | 05/09/2025
TO-25-110 kV A1 @ ARK-01 | BUSBAR SECTION - ARKLOW 110-ARKLOW 110-110A1 | 12 | 10 | 10 | Scheduled | 01/09/2025 | 12/09/2025
TO-25-110 kV B1 @ ARK-01 | BUSBAR SECTION - ARKLOW 110-ARKLOW 110-110B1 | 12 | 10 | 10 | Scheduled | 01/09/2025 | 12/09/2025
TO-25-220 kV A1 @ ARK-02 | BUSBAR SECTION - ARKLOW 220-ARKLOW 220-220A1 | 12 | 10 | 10 | Scheduled | 01/09/2025 | 12/09/2025
TO-25-220 kV B1 @ ARK-02 | BUSBAR SECTION - ARKLOW 220-ARKLOW 220-220B1 | 12 | 10 | 10 | Scheduled | 01/09/2025 | 12/09/2025
TO-25-ARK-T2101-01 | TRANSFORMER - ARKLOW 220-ARKLOW 110-T2101 | 12 | 10 | 10 | Scheduled | 01/09/2025 | 12/09/2025
TO-25-220 kV A2 @ BVK-01 | BUSBAR SECTION - BALLYVOUSKILL 220-BALLYVOUSKILL 220-220A2 | 5 | 5 | 5 | Scheduled | 01/09/2025 | 05/09/2025
TO-25-220 kV B2 @ BVK-01 | BUSBAR SECTION - BALLYVOUSKILL 220-BALLYVOUSKILL 220-220B2 | 5 | 5 | 5 | Scheduled | 01/09/2025 | 05/09/2025
TO-25-BVK-220K2-03 | COUPLER/SECTIONALISING CB - BALLYVOUSKILL 220-BALLYVOUSKILL 220-220K2 | 5 | 5 | 5 | Scheduled | 01/09/2025 | 05/09/2025
TO-25-BVK-220SA1-2CB-01 | COUPLER/SECTIONALISING CB - BALLYVOUSKILL 220-BALLYVOUSKILL 220-220SA1-2CB | 5 | 5 | 5 | Scheduled | 01/09/2025 | 05/09/2025
TO-25-BVK-220SB1-2CB-01 | COUPLER/SECTIONALISING CB - BALLYVOUSKILL 220-BALLYVOUSKILL 220-220SB1-2CB | 5 | 5 | 5 | Scheduled | 01/09/2025 | 05/09/2025
TO-25-220 kV A1 @ CSH-02 | BUSBAR SECTION - CASHLA 220-CASHLA 220-220A1 | 5 | 5 | 5 | Scheduled | 01/09/2025 | 05/09/2025
TO-25-220 kV B1 @ CSH-02 | BUSBAR SECTION - CASHLA 220-CASHLA 220-220B1 | 5 | 5 | 5 | Scheduled | 01/09/2025 | 05/09/2025
TO-25-CSH-CLN-1-04 | 110kV FEEDER - CASHLA 110-CLOON 110-1 | 5 | 5 | 5 | Proposed | 01/09/2025 | 05/09/2025
TO-25-CSH-TY-1-02 | 220kV FEEDER - CASHLA 220-TYNAGH 220-1 | 5 | 5 | 5 | Scheduled | 01/09/2025 | 05/09/2025
TO-25-CLA-KRA-1-01 | 220kV FEEDER - CLASHAVOON 220-KNOCKRAHA 220-1 | 9 | 7 | 7 | Proposed | 01/09/2025 | 09/09/2025
TO-25-CLA-KRA-1-02 | 220kV FEEDER - CLASHAVOON 220-KNOCKRAHA 220-1 | 16 | 12 | 12 | Proposed | 01/09/2025 | 16/09/2025
TO-25-CKN-KER-1-01 | 110kV FEEDER - CLONKEEN 110-KNOCKEARAGH 110-1 | 8 | 6 | 6 | Scheduled | 01/09/2025 | 08/09/2025
TO-25-CLU-T122-01 | TSO CUSTOMER TRANSFORMER - CLUTTERLAND 110-CLUTTERLAND 20-T122 | 5 | 5 | 5 | Proposed | 01/09/2025 | 05/09/2025
TO-25-CRO-KBY-1-01 | 110kV FEEDER - COOLROE 110-KILBARRY 110-1 | 8 | 6 | 6 | Scheduled | 01/09/2025 | 08/09/2025
TO-25-CRU-T224-02 | TSO CUSTOMER TRANSFORMER - CRUISERATH 220-CRUISERATH 20-T224 | 40 | 30 | 30 | Proposed | 01/09/2025 | 10/10/2025
TO-25-DLT-CAP1-01 | CAPACITOR/SVC/REACTOR - DALTON 110-DALTON 110-CAP1 | 5 | 5 | 5 | Proposed | 01/09/2025 | 05/09/2025
TO-25-DRU-ENN-1-01 | 110kV FEEDER - DRUMLINE 110-ENNIS 110-1 | 3 | 3 | 3 | Scheduled | 01/09/2025 | 03/09/2025
TO-25-DDK-110SA1-01 | SECTIONALISING DISCONNECT - DUNDALK 110-DUNDALK 110-110SA1 | 5 | 5 | 5 | Scheduled | 01/09/2025 | 05/09/2025
TO-25-DDK-110SA2-02 | SECTIONALISING DISCONNECT - DUNDALK 110-DUNDALK 110-110SA2 | 5 | 5 | 5 | Scheduled | 01/09/2025 | 05/09/2025
TO-25-DDK-MLN-1-01 | 110kV FEEDER - DUNDALK 110-MULLAGHARLIN 110-1 | 5 | 5 | 5 | Scheduled | 01/09/2025 | 05/09/2025
TO-25-DDK-T141-01 | DISTRIBUTION TRANSFORMER - DUNDALK 110-DUNDALK 38-T141 | 5 | 5 | 5 | Reference | 01/09/2025 | 05/09/2025
TO-25-DFR-T122-02 | DISTRIBUTION TRANSFORMER - DUNFIRTH 110-DUNFIRTH 20-T122 | 3 | 3 | 3 | Reference | 01/09/2025 | 03/09/2025
TO-25-DFR,T-DFR-1-02 | 110kV FEEDER - DUNFIRTH tee-DUNFIRTH 110-1 | 3 | 3 | 3 | Scheduled | 01/09/2025 | 03/09/2025
TO-25-DFR,T-KIN-1-02 | 110kV FEEDER - DUNFIRTH tee-KINNEGAD 110-1 | 3 | 3 | 3 | Scheduled | 01/09/2025 | 03/09/2025
TO-25-220 kV A1 @ KRA-04 | BUSBAR SECTION - KNOCKRAHA 220-KNOCKRAHA 220-220A1 | 16 | 12 | 12 | Proposed | 01/09/2025 | 16/09/2025
TO-25-220 kV A1 @ KRA-01 | BUSBAR SECTION - KNOCKRAHA 220-KNOCKRAHA 220-220A1 | 9 | 7 | 7 | Proposed | 01/09/2025 | 09/09/2025
TO-25-220 kV B1 @ KRA-01 | BUSBAR SECTION - KNOCKRAHA 220-KNOCKRAHA 220-220B1 | 9 | 7 | 7 | Proposed | 01/09/2025 | 09/09/2025
TO-25-220 kV B1 @ KRA-04 | BUSBAR SECTION - KNOCKRAHA 220-KNOCKRAHA 220-220B1 | 16 | 12 | 12 | Proposed | 01/09/2025 | 16/09/2025
TO-25-KRA-220K1-01 | COUPLER/SECTIONALISING CB - KNOCKRAHA 220-KNOCKRAHA 220-220K1 | 9 | 7 | 7 | Proposed | 01/09/2025 | 09/09/2025
TO-25-KRA-220K1-04 | COUPLER/SECTIONALISING CB - KNOCKRAHA 220-KNOCKRAHA 220-220K1 | 16 | 12 | 12 | Proposed | 01/09/2025 | 16/09/2025
TO-25-KRA-220SA1-2CB-01 | COUPLER/SECTIONALISING CB - KNOCKRAHA 220-KNOCKRAHA 220-220SA1-2CB | 9 | 7 | 7 | Proposed | 01/09/2025 | 09/09/2025
TO-25-KRA-220SA1-2CB-05 | COUPLER/SECTIONALISING CB - KNOCKRAHA 220-KNOCKRAHA 220-220SA1-2CB | 16 | 12 | 12 | Proposed | 01/09/2025 | 16/09/2025
TO-25-KRA-220SB1-2CB-01 | COUPLER/SECTIONALISING CB - KNOCKRAHA 220-KNOCKRAHA 220-220SB1-2CB | 9 | 7 | 7 | Proposed | 01/09/2025 | 09/09/2025
TO-25-KRA-220SB1-2CB-05 | COUPLER/SECTIONALISING CB - KNOCKRAHA 220-KNOCKRAHA 220-220SB1-2CB | 16 | 12 | 12 | Proposed | 01/09/2025 | 16/09/2025
TO-25-KRA-T2101-01 | TRANSFORMER - KNOCKRAHA 220-KNOCKRAHA 110-T2101 | 9 | 7 | 7 | Proposed | 01/09/2025 | 09/09/2025
TO-25-LIS-CAP2-02 | CAPACITOR/SVC/REACTOR - LISDRUM 110-LISDRUM 110-CAP2 | 5 | 5 | 5 | Scheduled | 01/09/2025 | 05/09/2025
TO-25-220 kV A2 @ MAY-04 | BUSBAR SECTION - MAYNOOTH 220-MAYNOOTH 220-220A2 | 12 | 10 | 10 | Scheduled | 01/09/2025 | 12/09/2025
TO-25-220 kV B2 @ MAY-04 | BUSBAR SECTION - MAYNOOTH 220-MAYNOOTH 220-220B2 | 12 | 10 | 10 | Scheduled | 01/09/2025 | 12/09/2025
TO-25-400 kV A4 @ MP GIS-02 | BUSBAR SECTION - MONEYPOINT GIS 400-MONEYPOINT GIS 400-400A4 | 5 | 5 | 5 | Scheduled | 01/09/2025 | 05/09/2025
TO-25-400 kV B4 @ MP GIS-02 | BUSBAR SECTION - MONEYPOINT GIS 400-MONEYPOINT GIS 400-400B4 | 5 | 5 | 5 | Scheduled | 01/09/2025 | 05/09/2025
TO-25-MP GIS-400K4-02 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 400-MONEYPOINT GIS 400-400K4 | 5 | 5 | 5 | Scheduled | 01/09/2025 | 05/09/2025
TO-25-MP GIS-400SA2-4CB-03 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 400-MONEYPOINT GIS 400-400SA2-4CB | 5 | 5 | 5 | Scheduled | 01/09/2025 | 05/09/2025
TO-25-MP GIS-400SB2-4CB-03 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 400-MONEYPOINT GIS 400-400SB2-4CB | 5 | 5 | 5 | Scheduled | 01/09/2025 | 05/09/2025
TO-25-PB-SHL-1-01 | 220kV FEEDER - POOLBEG 220-SHELLYBANKS 220-1 | 26 | 20 | 20 | Proposed | 01/09/2025 | 26/09/2025
TO-25-PB-SHL-1-03 | 220kV FEEDER - POOLBEG 220-SHELLYBANKS 220-1 | 26 | 20 | 20 | Proposed | 01/09/2025 | 26/09/2025
TO-25-PLS-T142-01 | DISTRIBUTION TRANSFORMER - PORTLAOISE 110-PORTLAOISE 38-T142 | 94 | 67 | 67 | Reference (Proposed) | 01/09/2025 | 03/12/2025
TO-25-SHL-D1/CB3-04 | COUPLER/SECTIONALISING CB - SHELLYBANKS 220-SHELLYBANKS 220-D1/CB3 | 26 | 20 | 20 | Proposed | 01/09/2025 | 26/09/2025
TO-25-SHL-D1/CB3-05 | COUPLER/SECTIONALISING CB - SHELLYBANKS 220-SHELLYBANKS 220-D1/CB3 | 26 | 20 | 20 | Proposed | 01/09/2025 | 26/09/2025
TO-25-SHL-D2/CB3-03 | COUPLER/SECTIONALISING CB - SHELLYBANKS 220-SHELLYBANKS 220-D2/CB3 | 26 | 20 | 20 | Proposed | 01/09/2025 | 26/09/2025
TO-25-SHL-D2/CB3-04 | COUPLER/SECTIONALISING CB - SHELLYBANKS 220-SHELLYBANKS 220-D2/CB3 | 26 | 20 | 20 | Proposed | 01/09/2025 | 26/09/2025
TO-25-WHI-CKB-T101-01 | TSO CUSTOMER TRANSFORMER - WHITEGATE 110-WHITEGATE 10-CKB-T101 | 5 | 5 | 5 | Scheduled | 01/09/2025 | 05/09/2025
TO-25-BYH-GLE-1-03 | 110kV FEEDER - BALLYNAHULLA 110-GLENLARA 110-1 | 2 | 2 | 2 | Proposed | 02/09/2025 | 03/09/2025
TO-25-220 kV B2 @ DSN-01 | BUSBAR SECTION - DUNSTOWN 220-DUNSTOWN 220-220B2 | 15 | 11 | 11 | Scheduled | 02/09/2025 | 16/09/2025
TO-25-DSN-220K1-2-01 | COUPLER/SECTIONALISING CB - DUNSTOWN 220-DUNSTOWN 220-220K1-2 | 2 | 2 | 2 | Scheduled | 02/09/2025 | 03/09/2025
TO-25-GGO-T2001-01 | GENERATOR TRANSFORMER - GLANAGOW 220-GLANAGOW G1-T2001 | 5 | 4 | 4 | Proposed | 02/09/2025 | 06/09/2025
TO-25-GLE-110SA1-2CB-03 | COUPLER/SECTIONALISING CB - GLENLARA 110-GLENLARA 110-110SA1-2CB | 2 | 2 | 2 | Proposed | 02/09/2025 | 03/09/2025
TO-25-GLE-KCR-1-02 | 110kV FEEDER - GLENLARA 110-KNOCKACUMMER 110-1 | 2 | 2 | 2 | Proposed | 02/09/2025 | 03/09/2025
TO-25-GLE-T141-02 | DISTRIBUTION TRANSFORMER - GLENLARA 110-GLENLARA 38-T141 | 2 | 2 | 2 | Reference (Proposed) | 02/09/2025 | 03/09/2025
TO-25-KCR-T121-02 | GENERATOR TRANSFORMER - KNOCKACUMMER 110-KNOCKACUMMER 20-T121 | 2 | 2 | 2 | Proposed | 02/09/2025 | 03/09/2025
TO-25-110 kV B1 @ RAF-02 | BUSBAR SECTION - RAFFEEN 110-RAFFEEN 110-110B1 | 3 | 3 | 3 | Proposed | 02/09/2025 | 04/09/2025
TO-25-BAG 110 - CLG 110 - 1-02 | 110kV FEEDER - BARNAGEERAGH 110-CLOGHRAN 110-1 | 3 | 3 | 3 | Proposed | 03/09/2025 | 05/09/2025
TO-25-DER-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - DERRYIRON 110-DERRYIRON 110-110SA1-2CB | 10 | 8 | 8 | Scheduled | 03/09/2025 | 12/09/2025
TO-25-DER-KIN-1-04 | 110kV FEEDER - DERRYIRON 110-KINNEGAD 110-1 | 10 | 8 | 8 | Scheduled | 03/09/2025 | 12/09/2025
TO-25-FLA-TON-1-01 | 110kV FEEDER - FLAGFORD 110-TONROE 110-1 | 52 | 38 | 38 | Reference | 03/09/2025 | 24/10/2025
TO-25-KLN-110K1-2-01 | COUPLER/SECTIONALISING CB - KILLONAN 110-KILLONAN 110-110K1-2 | 2 | 2 | 2 | Scheduled | 03/09/2025 | 04/09/2025
TO-25-KUD-T101-01 | TSO CUSTOMER TRANSFORMER - KILMAHUD 110-KILMAHUD 10-T101 | 3 | 3 | 3 | Proposed | 03/09/2025 | 05/09/2025
TO-25-KPG-110K3-01 | COUPLER/SECTIONALISING CB - KILPADDOGE 110-KILPADDOGE 110-110K3 | 10 | 8 | 8 | Scheduled | 03/09/2025 | 12/09/2025
TO-25-KPG-110K4-02 | COUPLER/SECTIONALISING CB - KILPADDOGE 110-KILPADDOGE 110-110K4 | 10 | 8 | 8 | Scheduled | 03/09/2025 | 12/09/2025
TO-25-KPG-110SA1-2CB-02 | COUPLER/SECTIONALISING CB - KILPADDOGE 110-KILPADDOGE 110-110SA1-2CB | 10 | 8 | 8 | Scheduled | 03/09/2025 | 12/09/2025
TO-25-KPG-110SA1-3CB-01 | COUPLER/SECTIONALISING CB - KILPADDOGE 110-KILPADDOGE 110-110SA1-3CB | 10 | 8 | 8 | Scheduled | 03/09/2025 | 12/09/2025
TO-25-KPG-110SA2-4CB-02 | COUPLER/SECTIONALISING CB - KILPADDOGE 110-KILPADDOGE 110-110SA2-4CB | 10 | 8 | 8 | Scheduled | 03/09/2025 | 12/09/2025
TO-25-LOU-RRU-1-02 | 110kV FEEDER - LOUTH 110-RATRUSSAN 110-1 | 57 | 40 | 40 | Proposed | 03/09/2025 | 29/10/2025
TO-25-LOU-RRU-1-03 | 110kV FEEDER - LOUTH 110-RATRUSSAN 110-1 | 57 | 40 | 40 | Scheduled | 03/09/2025 | 29/10/2025
TO-25-LOU-RRU-1-01 | 110kV FEEDER - LOUTH 110-RATRUSSAN 110-1 | 21 | 15 | 15 | Proposed | 03/09/2025 | 23/09/2025
TO-25-TON-T142-01 | DISTRIBUTION TRANSFORMER - TONROE 110-TONROE 38-T142 | 52 | 38 | 38 | Reference | 03/09/2025 | 24/10/2025
TO-25-110 kV A2 @ GI-01 | BUSBAR SECTION - GREAT ISLAND 110-GREAT ISLAND 110-110A2 | 9 | 7 | 7 | Scheduled | 04/09/2025 | 12/09/2025
TO-25-110 kV B2 @ GI-03 | BUSBAR SECTION - GREAT ISLAND 110-GREAT ISLAND 110-110B2 | 9 | 7 | 7 | Scheduled | 04/09/2025 | 12/09/2025
TO-25-GI-WAT-2-03 | 110kV FEEDER - GREAT ISLAND 110-WATERFORD 110-2 | 9 | 7 | 7 | Scheduled | 04/09/2025 | 12/09/2025
TO-25-IKE-T141-03 | DISTRIBUTION TRANSFORMER - IKERRIN 110-IKERRIN 38-T141 | 28 | 20 | 20 | Reference (Proposed) | 04/09/2025 | 01/10/2025
TO-25-IKE,T-IKE-1-03 | 110kV FEEDER - IKERRIN tee-IKERRIN 110-1 | 28 | 20 | 20 | Proposed | 04/09/2025 | 01/10/2025
TO-25-IKE,T-SH-1-04 | 110kV FEEDER - IKERRIN tee-SHANNONBRIDGE 110-1 | 28 | 20 |  | Proposed | 04/09/2025 | 01/10/2025
TO-25-IKE,T-THU-1-03 | 110kV FEEDER - IKERRIN tee-THURLES 110-1 | 28 | 20 | 20 | Proposed | 04/09/2025 | 01/10/2025
TO-25-CDU-GLN-1-03 | 110kV FEEDER - CORDUFF 110-GALLANSTOWN 110-1 | 3 | 1 | 1 | Proposed | 05/09/2025 | 07/09/2025
TO-25-AGL-ENN-1-01 | 110kV FEEDER - AGANNYGAL 110-ENNIS 110-1 | 10 | 8 | 8 | Proposed | 08/09/2025 | 17/09/2025
TO-25-AA GIS-ENN-1-01 | 110kV FEEDER - ARDNACRUSHA GIS 110-ENNIS 110-1 | 10 | 8 | 8 | Scheduled | 08/09/2025 | 17/09/2025
TO-25-AUG-CFM-1-01 | 110kV FEEDER - AUGHINISH 110-CASTLEFARM 110-1 | 12 | 10 | 10 | Scheduled | 08/09/2025 | 19/09/2025
TO-25-BDA-T102-01 | TSO CUSTOMER TRANSFORMER - BARODA 110-BARODA 10-T102 | 9 | 7 | 7 | Scheduled | 08/09/2025 | 16/09/2025
TO-25-BDA-T102-02 | TSO CUSTOMER TRANSFORMER - BARODA 110-BARODA 10-T102 | 9 | 7 | 7 | Scheduled | 08/09/2025 | 16/09/2025
TO-25-220 kV A2 @ CSH-03 | BUSBAR SECTION - CASHLA 220-CASHLA 220-220A2 | 15 | 11 | 11 | Scheduled | 08/09/2025 | 22/09/2025
TO-25-CSH-T2102-02 | TRANSFORMER - CASHLA 220-CASHLA 110-T2102 | 15 | 11 | 11 | Scheduled | 08/09/2025 | 22/09/2025
TO-25-CFM-T101-01 | TSO CUSTOMER TRANSFORMER - CASTLEFARM 110-CASTLEFARM 10-T101 | 12 | 10 | 10 | Reference | 08/09/2025 | 19/09/2025
TO-25-110 kV A1 @ CF-01 | BUSBAR SECTION - CATHALEENS FALL 110-CATHALEENS FALL 110-110A1 | 12 | 10 | 10 | Scheduled | 08/09/2025 | 19/09/2025
TO-25-110 kV B1 @ CF-06 | BUSBAR SECTION - CATHALEENS FALL 110-CATHALEENS FALL 110-110B1 | 12 | 10 | 10 | Scheduled | 08/09/2025 | 19/09/2025
TO-25-CF-COR-1-02 | 110kV FEEDER - CATHALEENS FALL 110-CORRACLASSY 110-1 | 5 | 5 | 5 | Proposed | 08/09/2025 | 12/09/2025
TO-25-CF-COR-1-03 | 110kV FEEDER - CATHALEENS FALL 110-CORRACLASSY 110-1 | 12 | 10 | 10 | Scheduled | 08/09/2025 | 19/09/2025
TO-25-CLG-T121-01 | TSO CUSTOMER TRANSFORMER - CLOGHRAN 110-CLOGHRAN 20-T121 | 5 | 5 | 5 | Proposed | 08/09/2025 | 12/09/2025
TO-25-ENN-110SA1-2CB-02 | COUPLER/SECTIONALISING CB - ENNIS 110-ENNIS 110-110SA1-2CB | 10 | 8 | 8 | Scheduled | 08/09/2025 | 17/09/2025
TO-25-ENN-SLC-1-02 | 110kV FEEDER - ENNIS 110-SLIEVECALLAN 110-1 | 10 | 8 | 8 | Scheduled | 08/09/2025 | 17/09/2025
TO-25-ENN-T102-01 | DISTRIBUTION TRANSFORMER - ENNIS 110-ENNIS 10-T102 | 10 | 8 | 8 | Reference | 08/09/2025 | 17/09/2025
TO-25-ENN-T142-01 | DISTRIBUTION TRANSFORMER - ENNIS 110-ENNIS 38-T142 | 10 | 8 | 8 | Reference | 08/09/2025 | 17/09/2025
TO-25-110 kV A1/A2 @ GOR-01 | BUSBAR SECTION - GORMAN 110-GORMAN 110-110A1-A2 | 11 | 9 | 9 | Scheduled | 08/09/2025 | 18/09/2025
TO-25-110 kV B1/B2 @ GOR-01 | BUSBAR SECTION - GORMAN 110-GORMAN 110-110B1-B2 | 11 | 9 | 9 | Scheduled | 08/09/2025 | 18/09/2025
TO-25-GOR-110K1-2-03 | COUPLER/SECTIONALISING CB - GORMAN 110-GORMAN 110-110K1-2 | 11 | 9 | 9 | Scheduled | 08/09/2025 | 18/09/2025
TO-25-220 kV A1 @ GOR-03 | BUSBAR SECTION - GORMAN 220-GORMAN 220-220A1 | 12 | 10 | 10 | Scheduled | 08/09/2025 | 19/09/2025
TO-25-220 kV B1 @ GOR-02 | BUSBAR SECTION - GORMAN 220-GORMAN 220-220B1 | 12 | 10 | 10 | Scheduled | 08/09/2025 | 19/09/2025
TO-25-GOR-MAY-1-01 | 220kV FEEDER - GORMAN 220-MAYNOOTH 220-1 | 12 | 10 | 10 | Scheduled | 08/09/2025 | 19/09/2025
TO-25-GOR-MAY-1-03 | 220kV FEEDER - GORMAN 220-MAYNOOTH 220-1 | 12 | 10 | 10 | Proposed | 08/09/2025 | 19/09/2025
TO-25-KLN-220K1-2-01 | COUPLER/SECTIONALISING CB - KILLONAN 220-KILLONAN 220-220K1-2 | 9 | 7 | 7 | Scheduled | 08/09/2025 | 16/09/2025
TO-25-LA-RIC-2-02 | 110kV FEEDER - LANESBORO 110-RICHMOND 110-2 | 2 | 2 | 2 | Reference (Proposed) | 08/09/2025 | 09/09/2025
TO-25-SLC-110SA1-02 | SECTIONALISING DISCONNECT - SLIEVECALLAN 110-SLIEVECALLAN 110-110SA1 | 10 | 8 | 8 | Scheduled | 08/09/2025 | 17/09/2025
TO-25-SLC-110SA2-02 | SECTIONALISING DISCONNECT - SLIEVECALLAN 110-SLIEVECALLAN 110-110SA2 | 10 | 8 | 8 | Scheduled | 08/09/2025 | 17/09/2025
TO-25-SLC-T121-02 | GENERATOR TRANSFORMER - SLIEVECALLAN 110-SLIEVECALLAN 20-T121 | 10 | 8 | 8 | Scheduled | 08/09/2025 | 17/09/2025
TO-25-SLC-T122-02 | GENERATOR TRANSFORMER - SLIEVECALLAN 110-SLIEVECALLAN 20-T122 | 10 | 8 | 8 | Scheduled | 08/09/2025 | 17/09/2025
TO-25-WHI-CKB-T102-01 | TSO CUSTOMER TRANSFORMER - WHITEGATE 110-WHITEGATE 10-CKB-T102 | 5 | 5 | 5 | Scheduled | 08/09/2025 | 12/09/2025
TO-25-BUT-110SA1-01 | SECTIONALISING DISCONNECT - BUTLERSTOWN 110-BUTLERSTOWN 110-110SA1 | 4 | 4 | 4 | Proposed | 09/09/2025 | 12/09/2025
TO-25-BUT-110SA1-02 | SECTIONALISING DISCONNECT - BUTLERSTOWN 110-BUTLERSTOWN 110-110SA1 | 4 | 4 | 4 | Scheduled | 09/09/2025 | 12/09/2025
TO-25-BUT-110SA2-03 | SECTIONALISING DISCONNECT - BUTLERSTOWN 110-BUTLERSTOWN 110-110SA2 | 4 | 4 | 4 | Scheduled | 09/09/2025 | 12/09/2025
TO-25-BUT-CUL-1-01 | 110kV FEEDER - BUTLERSTOWN 110-CULLENAGH 110-1 | 4 | 4 | 4 | Scheduled | 09/09/2025 | 12/09/2025
TO-25-BUT-T141-01 | DISTRIBUTION TRANSFORMER - BUTLERSTOWN 110-BUTLERSTOWN 38-T141 | 4 | 4 | 4 | Reference | 09/09/2025 | 12/09/2025
TO-25-CLH-110SA1-02 | SECTIONALISING DISCONNECT - CLAHANE 110-CLAHANE 110-110SA1 | 2 | 2 | 2 | Scheduled | 09/09/2025 | 10/09/2025
TO-25-CLH-110SA2-01 | SECTIONALISING DISCONNECT - CLAHANE 110-CLAHANE 110-110SA2 | 2 | 2 | 2 | Scheduled | 09/09/2025 | 10/09/2025
TO-25-CLH-T122-02 | GENERATOR TRANSFORMER - CLAHANE 110-CLAHANE 20-T122 | 2 | 2 | 2 | Scheduled | 09/09/2025 | 10/09/2025
TO-25-CLH-TRI-1-01 | 110kV FEEDER - CLAHANE 110-TRIEN 110-1 | 2 | 2 | 2 | Scheduled | 09/09/2025 | 10/09/2025
TO-25-KUD-T102-01 | TSO CUSTOMER TRANSFORMER - KILMAHUD 110-KILMAHUD 10-T102 | 3 | 3 | 3 | Proposed | 09/09/2025 | 11/09/2025
TO-25-KUD-T103-01 | TSO CUSTOMER TRANSFORMER - KILMAHUD 110-KILMAHUD 10-T103 | 2 | 2 | 2 | Scheduled | 09/09/2025 | 10/09/2025
TO-25-MP GIS-T4001-02 | GENERATOR TRANSFORMER - MONEYPOINT GIS 400-MONEYPOINT GIS G1-T4001 | 3 | 3 | 3 | Proposed | 09/09/2025 | 11/09/2025
TO-25-MOY-CAP2-01 | CAPACITOR/SVC/REACTOR - MOY 110-MOY 110-CAP2 | 2 | 2 | 2 | Scheduled | 09/09/2025 | 10/09/2025
TO-25-110 kV A1 @ SH-02 | BUSBAR SECTION - SHANNONBRIDGE 110-SHANNONBRIDGE 110-110A1 | 2 | 2 |  | Proposed | 09/09/2025 | 10/09/2025
TO-25-110 kV B1 @ SH-01 | BUSBAR SECTION - SHANNONBRIDGE 110-SHANNONBRIDGE 110-110B1 | 2 | 2 | 2 | Proposed | 09/09/2025 | 10/09/2025
TO-25-BVK-T2102-01 | TRANSFORMER - BALLYVOUSKILL 220-BALLYVOUSKILL 110-T2102 | 2 | 2 | 2 | Proposed | 10/09/2025 | 11/09/2025
TO-25-KUD-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - KILMAHUD 110-KILMAHUD 110-110SA1-2CB | 2 | 2 | 2 | Scheduled | 10/09/2025 | 11/09/2025
TO-25-KUD-110SA1-3CB-01 | COUPLER/SECTIONALISING CB - KILMAHUD 110-KILMAHUD 110-110SA1-3CB | 2 | 2 | 2 | Scheduled | 10/09/2025 | 11/09/2025
TO-25-OBE-110K1-01 | COUPLER/SECTIONALISING CB - OLDBRIDGE 110-OLDBRIDGE 110-110K1 | 3 | 3 | 3 | Scheduled | 10/09/2025 | 12/09/2025
TO-25-OBE-110K2-01 | COUPLER/SECTIONALISING CB - OLDBRIDGE 110-OLDBRIDGE 110-110K2 | 3 | 3 | 3 | Scheduled | 10/09/2025 | 12/09/2025
TO-25-OBE-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - OLDBRIDGE 110-OLDBRIDGE 110-110SA1-2CB | 3 | 3 | 3 | Scheduled | 10/09/2025 | 12/09/2025
TO-25-OBE-110SB1-2CB-01 | COUPLER/SECTIONALISING CB - OLDBRIDGE 110-OLDBRIDGE 110-110SB1-2CB | 3 | 3 | 3 | Scheduled | 10/09/2025 | 12/09/2025
TO-25-CHA-KLN-1-03 | 110kV FEEDER - CHARLEVILLE 110-KILLONAN 110-1 | 9 | 7 | 7 | Scheduled | 11/09/2025 | 19/09/2025
TO-25-110 kV A1 @ KLN-02 | BUSBAR SECTION - KILLONAN 110-KILLONAN 110-110A1 | 9 | 7 | 7 | Scheduled | 11/09/2025 | 19/09/2025
TO-25-110 kV B1 @ KLN-02 | BUSBAR SECTION - KILLONAN 110-KILLONAN 110-110B1 | 9 | 7 | 7 | Scheduled | 11/09/2025 | 19/09/2025
TO-25-110 kV A2 @ TB-01 | BUSBAR SECTION - TARBERT 110-TARBERT 110-110A2 | 9 | 7 | 7 | Proposed | 11/09/2025 | 19/09/2025
TO-25-110 kV B2 @ TB-01 | BUSBAR SECTION - TARBERT 110-TARBERT 110-110B2 | 9 | 7 | 7 | Proposed | 11/09/2025 | 19/09/2025
TO-25-220 kV A2 @ TB-03 | BUSBAR SECTION - TARBERT 220-TARBERT 220-220A2 | 9 | 7 | 7 | Proposed | 11/09/2025 | 19/09/2025
TO-25-220 kV B2 @ TB-03 | BUSBAR SECTION - TARBERT 220-TARBERT 220-220B2 | 9 | 7 | 7 | Proposed | 11/09/2025 | 19/09/2025
TO-25-TB-T102-01 | GENERATOR TRANSFORMER - TARBERT 110-TARBERT G2-T102 | 9 | 7 | 7 | Proposed | 11/09/2025 | 19/09/2025
TO-25-TB-T2102-01 | TRANSFORMER - TARBERT 220-TARBERT 110-T2102 | 9 | 7 | 7 | Proposed | 11/09/2025 | 19/09/2025
TO-25-KPG-110K3-03 | COUPLER/SECTIONALISING CB - KILPADDOGE 110-KILPADDOGE 110-110K3 | 12 | 8 | 8 | Scheduled | 13/09/2025 | 24/09/2025
TO-25-KPG-110K4-03 | COUPLER/SECTIONALISING CB - KILPADDOGE 110-KILPADDOGE 110-110K4 | 12 | 8 | 8 | Scheduled | 13/09/2025 | 24/09/2025
TO-25-KPG-110SB1-2CB-01 | COUPLER/SECTIONALISING CB - KILPADDOGE 110-KILPADDOGE 110-110SB1-2CB | 12 | 8 | 8 | Scheduled | 13/09/2025 | 24/09/2025
TO-25-KPG-110SB1-3CB-01 | COUPLER/SECTIONALISING CB - KILPADDOGE 110-KILPADDOGE 110-110SB1-3CB | 12 | 8 | 8 | Scheduled | 13/09/2025 | 24/09/2025
TO-25-KPG-110SB2-4CB-01 | COUPLER/SECTIONALISING CB - KILPADDOGE 110-KILPADDOGE 110-110SB2-4CB | 12 | 8 | 8 | Scheduled | 13/09/2025 | 24/09/2025
TO-25-BWR-CRA-1-02 | 110kV FEEDER - BALLYWATER 110-CRANE 110-1 | 5 | 5 | 5 | Scheduled | 15/09/2025 | 19/09/2025
TO-25-BWR-CRA-1-04 | 110kV FEEDER - BALLYWATER 110-CRANE 110-1 | 2 | 2 | 2 | Scheduled | 15/09/2025 | 16/09/2025
TO-25-BWR-T124-04 | GENERATOR TRANSFORMER - BALLYWATER 110-BALLYWATER 20-T124 | 2 | 2 | 2 | Reference | 15/09/2025 | 16/09/2025
TO-25-BWR-T124-02 | GENERATOR TRANSFORMER - BALLYWATER 110-BALLYWATER 20-T124 | 5 | 5 | 5 | Reference | 15/09/2025 | 19/09/2025
TO-25-BLC-DND-3-02 | 110kV FEEDER - BELCAMP 110-DARNDALE 110-3 | 5 | 5 | 5 | Proposed | 15/09/2025 | 19/09/2025
TO-25-CLW-KLS-1-05 | 110kV FEEDER - CARLOW 110-KELLIS 110-1 | 12 | 10 | 10 | Proposed | 15/09/2025 | 26/09/2025
TO-25-CRA-110SA1-02 | SECTIONALISING DISCONNECT - CRANE 110-CRANE 110-110SA1 | 5 | 5 | 5 | Scheduled | 15/09/2025 | 19/09/2025
TO-25-CRA-110SA1-03 | SECTIONALISING DISCONNECT - CRANE 110-CRANE 110-110SA1 | 2 | 2 | 2 | Scheduled | 15/09/2025 | 16/09/2025
TO-25-CRA-110SA2-02 | SECTIONALISING DISCONNECT - CRANE 110-CRANE 110-110SA2 | 5 | 5 | 5 | Scheduled | 15/09/2025 | 19/09/2025
TO-25-CRA-110SA2-04 | SECTIONALISING DISCONNECT - CRANE 110-CRANE 110-110SA2 | 2 | 2 | 2 | Scheduled | 15/09/2025 | 16/09/2025
TO-25-CRA-LWD-1-02 | 110kV FEEDER - CRANE 110-LODGEWOOD 110-1 | 5 | 5 | 5 | Scheduled | 15/09/2025 | 19/09/2025
TO-25-CRA-LWD-1-04 | 110kV FEEDER - CRANE 110-LODGEWOOD 110-1 | 2 | 2 | 2 | Scheduled | 15/09/2025 | 16/09/2025
TO-25-CRA-T122-02 | DISTRIBUTION TRANSFORMER - CRANE 110-CRANE 20-T122 | 5 | 5 | 5 | Reference | 15/09/2025 | 19/09/2025
TO-25-CRA-T122-04 | DISTRIBUTION TRANSFORMER - CRANE 110-CRANE 20-T122 | 2 | 2 | 2 | Reference | 15/09/2025 | 16/09/2025
TO-25-CRU-220K1-01 | COUPLER/SECTIONALISING CB - CRUISERATH 220-CRUISERATH 220-220K1 | 5 | 5 | 5 | Scheduled | 15/09/2025 | 19/09/2025
TO-25-CRU-220K2-01 | COUPLER/SECTIONALISING CB - CRUISERATH 220-CRUISERATH 220-220K2 | 5 | 5 | 5 | Scheduled | 15/09/2025 | 19/09/2025
TO-25-CRU-SA1-2CB-01 | COUPLER/SECTIONALISING CB - CRUISERATH 220-CRUISERATH 220-220SA1-2CB | 5 | 5 | 5 | Scheduled | 15/09/2025 | 19/09/2025
TO-25-CRU-SB1-2CB-01 | COUPLER/SECTIONALISING CB - CRUISERATH 220-CRUISERATH 220-220SB1-2CB | 5 | 5 | 5 | Scheduled | 15/09/2025 | 19/09/2025
TO-25-110 kV A1 @ KLS-05 | BUSBAR SECTION - KELLIS 110-KELLIS 110-110A1 | 12 | 10 | 10 | Proposed | 15/09/2025 | 26/09/2025
TO-25-110 kV B1 @ KLS-03 | BUSBAR SECTION - KELLIS 110-KELLIS 110-110B1 | 12 | 10 | 10 | Proposed | 15/09/2025 | 26/09/2025
TO-25-KYT-220K2-01 | COUPLER/SECTIONALISING CB - KELLYSTOWN 220-KELLYSTOWN 220-220K2 | 5 | 5 | 5 | Scheduled | 15/09/2025 | 19/09/2025
TO-25-KYT-220K3-01 | COUPLER/SECTIONALISING CB - KELLYSTOWN 220-KELLYSTOWN 220-220K3 | 5 | 5 | 5 | Scheduled | 15/09/2025 | 19/09/2025
TO-25-KYT-220SA1-2CB-01 | COUPLER/SECTIONALISING CB - KELLYSTOWN 220-KELLYSTOWN 220-220SA1-2CB | 5 | 5 | 5 | Scheduled | 15/09/2025 | 19/09/2025
TO-25-KYT-220SA1-3CB-01 | COUPLER/SECTIONALISING CB - KELLYSTOWN 220-KELLYSTOWN 220-220SA1-3CB | 5 | 5 | 5 | Scheduled | 15/09/2025 | 19/09/2025
TO-25-KYT-220SB1-2CB-01 | COUPLER/SECTIONALISING CB - KELLYSTOWN 220-KELLYSTOWN 220-220SB1-2CB | 5 | 5 | 5 | Scheduled | 15/09/2025 | 19/09/2025
TO-25-KYT-220SB1-3CB-01 | COUPLER/SECTIONALISING CB - KELLYSTOWN 220-KELLYSTOWN 220-220SB1-3CB | 5 | 5 | 5 | Scheduled | 15/09/2025 | 19/09/2025
TO-25-KLN-KPG-1-04 | 220kV FEEDER - KILLONAN 220-KILPADDOGE 220-1 | 12 | 10 | 10 | Scheduled | 15/09/2025 | 26/09/2025
TO-25-KLN-KPG-1-03 | 220kV FEEDER - KILLONAN 220-KILPADDOGE 220-1 | 12 | 10 | 10 | Proposed | 15/09/2025 | 26/09/2025
TO-25-MAY-TEN-1-01 | 110kV FEEDER - MAYNOOTH 110-TIMAHOE 110-1 | 87 | 62 | 62 | Scheduled | 15/09/2025 | 10/12/2025
TO-25-MLC-TSB-1-01 | 110kV FEEDER - MOUNTLUCAS 110-THORNSBERRY 110-1 | 5 | 5 | 5 | Proposed | 15/09/2025 | 19/09/2025
TO-25-RYB GIS-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - RYEBROOK GIS 110-RYEBROOK GIS 110-110SA1-2CB | 5 | 5 | 5 | Scheduled | 15/09/2025 | 19/09/2025
TO-25-RYB GIS-110SA1-3CB-01 | COUPLER/SECTIONALISING CB - RYEBROOK GIS 110-RYEBROOK GIS 110-110SA1-3CB | 5 | 5 | 5 | Scheduled | 15/09/2025 | 19/09/2025
TO-25-RYB GIS-110SA2-4CB-01 | COUPLER/SECTIONALISING CB - RYEBROOK GIS 110-RYEBROOK GIS 110-110SA2-4CB | 5 | 5 | 5 | Scheduled | 15/09/2025 | 19/09/2025
TO-25-220 kV A2 @ SH-07 | BUSBAR SECTION - SHANNONBRIDGE 220-SHANNONBRIDGE 220-220A2 | 2 | 2 | 2 | Proposed | 15/09/2025 | 16/09/2025
TO-25-220 kV B2 @ SH-07 | BUSBAR SECTION - SHANNONBRIDGE 220-SHANNONBRIDGE 220-220B2 | 2 | 2 | 2 | Proposed | 15/09/2025 | 16/09/2025
TO-25-SH-220K1-2-03 | COUPLER/SECTIONALISING CB - SHANNONBRIDGE 220-SHANNONBRIDGE 220-220K1-2 | 2 | 2 | 2 | Proposed | 15/09/2025 | 16/09/2025
TO-25-TSB-110SA1-02 | SECTIONALISING DISCONNECT - THORNSBERRY 110-THORNSBERRY 110-110SA1 | 5 | 5 | 5 | Proposed | 15/09/2025 | 19/09/2025
TO-25-TSB-110SA2-02 | SECTIONALISING DISCONNECT - THORNSBERRY 110-THORNSBERRY 110-110SA2 | 5 | 5 | 5 | Proposed | 15/09/2025 | 19/09/2025
TO-25-TSB-T141-01 | DISTRIBUTION TRANSFORMER - THORNSBERRY 110-THORNSBERRY 38-T141 | 5 | 5 | 5 | Reference (Proposed) | 15/09/2025 | 19/09/2025
TO-25-GAL GIS-KNY-1-01 | 110kV FEEDER - GALWAY GIS 110-KNOCKRANNY 110-1 | 2 | 2 | 2 | Proposed | 16/09/2025 | 17/09/2025
TO-25-KIN-MUL-1-02 | 110kV FEEDER - KINNEGAD 110-MULLINGAR 110-1 | 21 | 15 | 15 | Proposed | 16/09/2025 | 06/10/2025
TO-25-220 kV A1/A2 @ KNR-01 | BUSBAR SECTION - KNOCKANURE 220-KNOCKANURE 220-220A1-A2 | 8 | 6 | 6 | Scheduled | 16/09/2025 | 23/09/2025
TO-25-KNR-220K1-01 | COUPLER/SECTIONALISING CB - KNOCKANURE 220-KNOCKANURE 220-220K1 | 8 | 6 | 6 | Scheduled | 16/09/2025 | 23/09/2025
TO-25-KNR-220K2-04 | COUPLER/SECTIONALISING CB - KNOCKANURE 220-KNOCKANURE 220-220K2 | 8 | 6 | 6 | Scheduled | 16/09/2025 | 23/09/2025
TO-25-KNR-220SA1-2CB-01 | COUPLER/SECTIONALISING CB - KNOCKANURE 220-KNOCKANURE 220-220SA1-2CB | 8 | 6 | 6 | Scheduled | 16/09/2025 | 23/09/2025
TO-25-400 kV A2 @ DSN-01 | BUSBAR SECTION - DUNSTOWN 400-DUNSTOWN 400-400A2 | 15 | 11 | 11 | Scheduled | 17/09/2025 | 01/10/2025
TO-25-TEN-T132-01 | GENERATOR TRANSFORMER - TIMAHOE 110-TIMAHOE 33-T132 | 1 | 1 | 1 | Proposed | 17/09/2025 | 17/09/2025
TO-25-TRL-CAP2-03 | CAPACITOR/SVC/REACTOR - TRALEE 110-TRALEE 110-CAP2 | 2 | 2 | 2 | Scheduled | 17/09/2025 | 18/09/2025
TO-25-110 kV A2 @ SH-02 | BUSBAR SECTION - SHANNONBRIDGE 110-SHANNONBRIDGE 110-110A2 | 2 | 2 | 2 | Proposed | 18/09/2025 | 19/09/2025
TO-25-110 kV B2 @ SH-02 | BUSBAR SECTION - SHANNONBRIDGE 110-SHANNONBRIDGE 110-110B2 | 2 | 2 | 2 | Proposed | 18/09/2025 | 19/09/2025
TO-25-SH-110K1-2-03 | COUPLER/SECTIONALISING CB - SHANNONBRIDGE 110-SHANNONBRIDGE 110-110K1-2 | 2 | 2 | 2 | Proposed | 18/09/2025 | 19/09/2025
TO-25-AD-HWL-1-01 | 220kV FEEDER - AGHADA 220-HADWELL 220-1 | 2 | 2 | 2 | Scheduled | 22/09/2025 | 23/09/2025
TO-25-AD-KRA-1-01 | 220kV FEEDER - AGHADA 220-KNOCKRAHA 220-1 | 19 | 15 | 15 | Proposed | 22/09/2025 | 10/10/2025
TO-25-AD-KRA-1-03 | 220kV FEEDER - AGHADA 220-KNOCKRAHA 220-1 | 19 | 15 | 15 | Proposed | 22/09/2025 | 10/10/2025
TO-25-AD-KRA-1-04 | 220kV FEEDER - AGHADA 220-KNOCKRAHA 220-1 | 19 | 15 | 15 | Proposed | 22/09/2025 | 10/10/2025
TO-25-AD-KRA-2-01 | 220kV FEEDER - AGHADA 220-KNOCKRAHA 220-2 | 19 | 15 | 15 | Proposed | 22/09/2025 | 10/10/2025
TO-25-AD-KRA-2-03 | 220kV FEEDER - AGHADA 220-KNOCKRAHA 220-2 | 19 | 15 | 15 | Proposed | 22/09/2025 | 10/10/2025
TO-25-AD-KRA-2-04 | 220kV FEEDER - AGHADA 220-KNOCKRAHA 220-2 | 19 | 15 | 15 | Proposed | 22/09/2025 | 10/10/2025
TO-25-AD-LPT-1-01 | 220kV FEEDER - AGHADA 220-LONG POINT 220-1 | 5 | 5 | 5 | Proposed | 22/09/2025 | 26/09/2025
TO-25-CSH-PRO-1-01 | 220kV FEEDER - CASHLA 220-PROSPECT 220-1 | 57 | 40 | 40 | Proposed | 22/09/2025 | 17/11/2025
TO-25-CSH-PRO-1-02 | 220kV FEEDER - CASHLA 220-PROSPECT 220-1 | Unknown | Unknown | 40 | Planned | September | November
TO-25-110 kV A2 @ CDU-01 | BUSBAR SECTION - CORDUFF 110-CORDUFF 110-110A2 | 12 | 10 | 10 | Proposed | 22/09/2025 | 03/10/2025
TO-25-110 kV A4 @ CDU-05 | BUSBAR SECTION - CORDUFF 110-CORDUFF 110-110A4 | 12 | 10 | 10 | Proposed | 22/09/2025 | 03/10/2025
TO-25-110 kV B2 @ CDU-03 | BUSBAR SECTION - CORDUFF 110-CORDUFF 110-110B2 | 12 | 10 | 10 | Proposed | 22/09/2025 | 03/10/2025
TO-25-110 kV B4 @ CDU-06 | BUSBAR SECTION - CORDUFF 110-CORDUFF 110-110B4 | 12 | 10 | 10 | Proposed | 22/09/2025 | 03/10/2025
TO-25-CDU-110SA2-4CB-03 | COUPLER/SECTIONALISING CB - CORDUFF 110-CORDUFF 110-110SA2-4CB | 12 | 10 | 10 | Proposed | 22/09/2025 | 03/10/2025
TO-25-CDU-110SB2-4CB-06 | COUPLER/SECTIONALISING CB - CORDUFF 110-CORDUFF 110-110SB2-4CB | 12 | 10 | 10 | Proposed | 22/09/2025 | 03/10/2025
TO-25-220 kV A2 @ CDU-04 | BUSBAR SECTION - CORDUFF 220-CORDUFF 220-220A2 | 12 | 10 | 10 | Proposed | 22/09/2025 | 03/10/2025
TO-25-220 kV A4 @ CDU-04 | BUSBAR SECTION - CORDUFF 220-CORDUFF 220-220A4 | 12 | 10 | 10 | Proposed | 22/09/2025 | 03/10/2025
TO-25-220 kV B2 @ CDU-04 | BUSBAR SECTION - CORDUFF 220-CORDUFF 220-220B2 | 12 | 10 | 10 | Proposed | 22/09/2025 | 03/10/2025
TO-25-220 kV B4 @ CDU-03 | BUSBAR SECTION - CORDUFF 220-CORDUFF 220-220B4 | 12 | 10 | 10 | Proposed | 22/09/2025 | 03/10/2025
TO-25-CDU-220SA2-4CB-04 | COUPLER/SECTIONALISING CB - CORDUFF 220-CORDUFF 220-220SA2-4CB | 12 | 10 | 10 | Proposed | 22/09/2025 | 03/10/2025
TO-25-CDU-220SB2-4CB-04 | COUPLER/SECTIONALISING CB - CORDUFF 220-CORDUFF 220-220SB2-4CB | 12 | 10 | 10 | Proposed | 22/09/2025 | 03/10/2025
TO-25-CDU-T2102-03 | TRANSFORMER - CORDUFF 220-CORDUFF 110-T2102 | 12 | 10 | 10 | Proposed | 22/09/2025 | 03/10/2025
TO-25-CRU-T222-01 | TSO CUSTOMER TRANSFORMER - CRUISERATH 220-CRUISERATH 20-T222 | 5 | 5 | 5 | Proposed | 22/09/2025 | 26/09/2025
TO-25-DMY-CAP2-01 | CAPACITOR/SVC/REACTOR - DUNMANWAY 110-DUNMANWAY 110-CAP2 | 4 | 4 | 4 | Scheduled | 22/09/2025 | 25/09/2025
TO-25-HWL-ATA10-01 | GENERATOR TRANSFORMER - HADWELL 220-HADWELL 33-ATA10 | 2 | 2 | 2 | Scheduled | 22/09/2025 | 23/09/2025
TO-25-HWL-ATA20-01 | GENERATOR TRANSFORMER - HADWELL 220-HADWELL 33-ATA20 | 2 | 2 | 2 | Scheduled | 22/09/2025 | 23/09/2025
TO-25-KLN-LIM-2-03 | 110kV FEEDER - KILLONAN 110-LIMERICK 110-2 | 9 | 7 | 7 | Scheduled | 22/09/2025 | 30/09/2025
TO-25-110 kV A2 @ KRA-01 | BUSBAR SECTION - KNOCKRAHA 110-KNOCKRAHA 110-110A2 | Unknown | Unknown | 60 | Planned | September | December
TO-25-110 kV B2 @ KRA-01 | BUSBAR SECTION - KNOCKRAHA 110-KNOCKRAHA 110-110B2 | Unknown | Unknown | 60 | Planned | September | December
TO-25-220 kV A1 @ KRA-02 | BUSBAR SECTION - KNOCKRAHA 220-KNOCKRAHA 220-220A1 | 19 | 15 | 15 | Proposed | 22/09/2025 | 10/10/2025
TO-25-220 kV A2 @ KRA-01 | BUSBAR SECTION - KNOCKRAHA 220-KNOCKRAHA 220-220A2 | 19 | 15 | 15 | Proposed | 22/09/2025 | 10/10/2025
TO-25-220 kV B1 @ KRA-02 | BUSBAR SECTION - KNOCKRAHA 220-KNOCKRAHA 220-220B1 | 19 | 15 | 15 | Proposed | 22/09/2025 | 10/10/2025
TO-25-220 kV B2 @ KRA-01 | BUSBAR SECTION - KNOCKRAHA 220-KNOCKRAHA 220-220B2 | 19 | 15 | 15 | Proposed | 22/09/2025 | 10/10/2025
TO-25-KRA-220K1-02 | COUPLER/SECTIONALISING CB - KNOCKRAHA 220-KNOCKRAHA 220-220K1 | 19 | 15 | 15 | Proposed | 22/09/2025 | 10/10/2025
TO-25-KRA-220SA1-2CB-03 | COUPLER/SECTIONALISING CB - KNOCKRAHA 220-KNOCKRAHA 220-220SA1-2CB | 19 | 15 | 15 | Proposed | 22/09/2025 | 10/10/2025
TO-25-KRA-220SA1-2CB-02 | COUPLER/SECTIONALISING CB - KNOCKRAHA 220-KNOCKRAHA 220-220SA1-2CB | 19 | 15 | 15 | Proposed | 22/09/2025 | 10/10/2025
TO-25-KRA-220SA2-4CB-01 | COUPLER/SECTIONALISING CB - KNOCKRAHA 220-KNOCKRAHA 220-220SA2-4CB | 19 | 15 | 15 | Proposed | 22/09/2025 | 10/10/2025
TO-25-KRA-220SB1-2CB-02 | COUPLER/SECTIONALISING CB - KNOCKRAHA 220-KNOCKRAHA 220-220SB1-2CB | 19 | 15 | 15 | Proposed | 22/09/2025 | 10/10/2025
TO-25-KRA-220SB1-2CB-03 | COUPLER/SECTIONALISING CB - KNOCKRAHA 220-KNOCKRAHA 220-220SB1-2CB | 19 | 15 | 15 | Proposed | 22/09/2025 | 10/10/2025
TO-25-KRA-220SB2-4CB-01 | COUPLER/SECTIONALISING CB - KNOCKRAHA 220-KNOCKRAHA 220-220SB2-4CB | 19 | 15 | 15 | Proposed | 22/09/2025 | 10/10/2025
TO-25-KRA-T2102-01 | TRANSFORMER - KNOCKRAHA 220-KNOCKRAHA 110-T2102 | 19 | 15 | 15 | Proposed | 22/09/2025 | 10/10/2025
TO-25-KRA-T2102-02 | TRANSFORMER - KNOCKRAHA 220-KNOCKRAHA 110-T2102 | Unknown | Unknown | 15 | Planned | September | October
TO-25-LLA-LET-1-01 | 110kV FEEDER - LENALEA 110-LETTERKENNY 110-1 | 10 | 8 | 8 | Scheduled | 22/09/2025 | 01/10/2025
TO-25-LET-M/CAP1-01 | CAPACITOR/SVC/REACTOR - LETTERKENNY 110-LETTERKENNY 110-M/CAP1 | 2 | 2 | 2 | Proposed | 22/09/2025 | 23/09/2025
TO-25-LIS-T131-01 | GENERATOR TRANSFORMER - LISDRUM 110-LISDRUM 33-T131 | 10 | 8 | 8 | Scheduled | 22/09/2025 | 01/10/2025
TO-25-LPT-T2002-01 | GENERATOR TRANSFORMER - LONG POINT 220-LONG POINT G1-T2002 | 5 | 5 | 5 | Proposed | 22/09/2025 | 26/09/2025
TO-25-MAY-T2103-01 | TRANSFORMER - MAYNOOTH 220-MAYNOOTH 110-T2103 | Unknown | Unknown |  | Planned | September | October
TO-25-RYB GIS-110SB1-2CB-01 | COUPLER/SECTIONALISING CB - RYEBROOK GIS 110-RYEBROOK GIS 110-110SB1-2CB | 5 | 5 | 5 | Scheduled | 22/09/2025 | 26/09/2025
TO-25-RYB GIS-110SB1-3CB-01 | COUPLER/SECTIONALISING CB - RYEBROOK GIS 110-RYEBROOK GIS 110-110SB1-3CB | 5 | 5 | 5 | Scheduled | 22/09/2025 | 26/09/2025
TO-25-RYB GIS-110SB2-4CB-01 | COUPLER/SECTIONALISING CB - RYEBROOK GIS 110-RYEBROOK GIS 110-110SB2-4CB | 5 | 5 | 5 | Scheduled | 22/09/2025 | 26/09/2025
TO-25-400 kV B2 @ WOO-01 | BUSBAR SECTION - WOODLAND 400-WOODLAND 400-400B2 | Unknown | Unknown | 15 | Planned | September | October
TO-25-400 kV A3 @ MP GIS-02 | BUSBAR SECTION - MONEYPOINT GIS 400-MONEYPOINT GIS 400-400A3 | 10 | 8 | 8 | Scheduled | 23/09/2025 | 02/10/2025
TO-25-400 kV B3 @ MP GIS-02 | BUSBAR SECTION - MONEYPOINT GIS 400-MONEYPOINT GIS 400-400B3 | 10 | 8 | 8 | Scheduled | 23/09/2025 | 02/10/2025
TO-25-MP GIS-400K3-03 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 400-MONEYPOINT GIS 400-400K3 | 10 | 8 | 8 | Scheduled | 23/09/2025 | 02/10/2025
TO-25-MP GIS-400SA1-3CB-03 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 400-MONEYPOINT GIS 400-400SA1-3CB | 10 | 8 | 8 | Scheduled | 23/09/2025 | 02/10/2025
TO-25-MP GIS-400SB1-3CB-03 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 400-MONEYPOINT GIS 400-400SB1-3CB | 10 | 8 | 8 | Scheduled | 23/09/2025 | 02/10/2025
TO-25-MP GIS-T4003-02 | GENERATOR TRANSFORMER - MONEYPOINT GIS 400-MONEYPOINT GIS G3-T4003 | 10 | 8 | 8 | Scheduled | 23/09/2025 | 02/10/2025
TO-25-110 kV B2 @ CSH-01 | BUSBAR SECTION - CASHLA 110-CASHLA 110-110B2 | Unknown | Unknown |  | Planned | September | September
TO-25-CLE-T221-02 | TSO CUSTOMER TRANSFORMER - CLONEE 220-CLONEE 20-T221 | 39 | 26 | 26 | Proposed | 26/09/2025 | 03/11/2025
TO-25-AD-KRA-1-02 | 220kV FEEDER - AGHADA 220-KNOCKRAHA 220-1 | 12 | 10 | 10 | Proposed | 29/09/2025 | 10/10/2025
TO-25-AD-KRA-2-02 | 220kV FEEDER - AGHADA 220-KNOCKRAHA 220-2 | 12 | 10 | 10 | Proposed | 29/09/2025 | 10/10/2025
TO-25-BLC-110SB1-3CB-01 | COUPLER/SECTIONALISING CB - BELCAMP 110-BELCAMP 110-110SB1-3CB | 5 | 5 | 5 | Proposed | 29/09/2025 | 03/10/2025
TO-25-CBT-INC-2-02 | 220kV FEEDER - CASTLEBAGOT 220-INCHICORE 220-2 | Unknown | Unknown | 20 | Planned | September | October
TO-25-CDU-T102-01 | GENERATOR TRANSFORMER - CORDUFF 110-CORDUFF 10.5-T102 | Unknown | Unknown | 1 | Planned | September | September
TO-25-REM-110SA1-01 | SECTIONALISING DISCONNECT - REAMORE 110-REAMORE 110-110SA1 | 26 | 20 | 20 | Proposed | 29/09/2025 | 24/10/2025
TO-25-REM-110SA2-01 | SECTIONALISING DISCONNECT - REAMORE 110-REAMORE 110-110SA2 | 26 | 20 | 20 | Proposed | 29/09/2025 | 24/10/2025
TO-25-REM-T141-01 | DISTRIBUTION TRANSFORMER - REAMORE 110-REAMORE 38-T141 | 26 | 20 | 20 | Reference (Proposed) | 29/09/2025 | 24/10/2025
TO-25-REM-T142-01 | DISTRIBUTION TRANSFORMER - REAMORE 110-REAMORE 38-T142 | 26 | 20 | 20 | Reference (Proposed) | 29/09/2025 | 24/10/2025
TO-25-REM-TRL-1-01 | 110kV FEEDER - REAMORE 110-TRALEE 110-1 | 26 | 20 | 20 | Proposed | 29/09/2025 | 24/10/2025
TO-25-110 kV A1 @ SH-01 | BUSBAR SECTION - SHANNONBRIDGE 110-SHANNONBRIDGE 110-110A1 | 2 | 2 | 2 | Proposed | 30/09/2025 | 01/10/2025
TO-25-SH-T2101-04 | TRANSFORMER - SHANNONBRIDGE 220-SHANNONBRIDGE 110-T2101 | 2 | 2 | 2 | Proposed | 30/09/2025 | 01/10/2025
TO-25-NEW-PLS-1-01 | 110kV FEEDER - NEWBRIDGE 110-PORTLAOISE 110-1 | Unknown | Unknown | 55 | Planned | October | December
TO-25-NEW-PLS-1-03 | 110kV FEEDER - NEWBRIDGE 110-PORTLAOISE 110-1 | Unknown | Unknown | 10 | Planned | October | October
TO-25-400 kV B2 @ DSN-01 | BUSBAR SECTION - DUNSTOWN 400-DUNSTOWN 400-400B2 | 14 | 10 | 10 | Scheduled | 02/10/2025 | 15/10/2025
TO-25-IKE,T-THU-1-07 | 110kV FEEDER - IKERRIN tee-THURLES 110-1 | 2 | 2 | 2 | Proposed | 02/10/2025 | 03/10/2025
TO-25-LSN-110SA1-2-01 | SECTIONALISING DISCONNECT - LISHEEN 110-LISHEEN 110-110SA1-2 | 2 | 2 | 2 | Proposed | 02/10/2025 | 03/10/2025
TO-25-LSN-110SA2-4-01 | SECTIONALISING DISCONNECT - LISHEEN 110-LISHEEN 110-110SA2-4 | 2 | 2 | 2 | Proposed | 02/10/2025 | 03/10/2025
TO-25-LSN-T122-01 | GENERATOR TRANSFORMER - LISHEEN 110-LISHEEN 20-T122 | 2 | 2 | 2 | Proposed | 02/10/2025 | 03/10/2025
TO-25-LSN-T131-02 | GENERATOR TRANSFORMER - LISHEEN 110-LISHEEN 33-T131 | 2 | 2 | 2 | Proposed | 02/10/2025 | 03/10/2025
TO-25-LSN-T142-01 | DISTRIBUTION TRANSFORMER - LISHEEN 110-LISHEEN 38-T142 | 2 | 2 | 2 | Reference (Proposed) | 02/10/2025 | 03/10/2025
TO-25-LSN-THU-1-01 | 110kV FEEDER - LISHEEN 110-THURLES 110-1 | 2 | 2 | 2 | Proposed | 02/10/2025 | 03/10/2025
TO-25-THU-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - THURLES 110-THURLES 110-110SA1-2CB | 2 | 2 | 2 | Proposed | 02/10/2025 | 03/10/2025
TO-25-THU-STATCOM-01 | CAPACITOR/SVC/REACTOR - THURLES 110-THURLES 110-STATCOM | 2 | 2 | 2 | Proposed | 02/10/2025 | 03/10/2025
TO-25-THU-T142-01 | DISTRIBUTION TRANSFORMER - THURLES 110-THURLES 38-T142 | 2 | 2 | 2 | Reference (Proposed) | 02/10/2025 | 03/10/2025
TO-25-CSH-T2101-01 | TRANSFORMER - CASHLA 220-CASHLA 110-T2101 | Unknown | Unknown |  | Planned | October | October
TO-25-MP GIS-400SA1-2CB-01 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 400-MONEYPOINT GIS 400-400SA1-2CB | Unknown | Unknown | 5 | Planned | October | October
TO-25-CAH-DOO-1-02 | 110kV FEEDER - CAHIR 110-DOON 110-1 | Unknown | Unknown | 40 | Planned | October | December
TO-25-CAH-DOO-1-03 | 110kV FEEDER - CAHIR 110-DOON 110-1 | Unknown | Unknown | 10 | Planned | October | October
TO-25-IKE-T141-05 | DISTRIBUTION TRANSFORMER - IKERRIN 110-IKERRIN 38-T141 | 2 | 2 | 2 | Reference (Proposed) | 06/10/2025 | 07/10/2025
TO-25-IKE,T-IKE-1-05 | 110kV FEEDER - IKERRIN tee-IKERRIN 110-1 | 2 | 2 | 2 | Proposed | 06/10/2025 | 07/10/2025
TO-25-IKE,T-SH-1-07 | 110kV FEEDER - IKERRIN tee-SHANNONBRIDGE 110-1 | 2 | 2 | 2 | Proposed | 06/10/2025 | 07/10/2025
TO-25-IKE,T-THU-1-08 | 110kV FEEDER - IKERRIN tee-THURLES 110-1 | 2 | 2 | 2 | Proposed | 06/10/2025 | 07/10/2025
TO-25-MAY-T2104-01 | TRANSFORMER - MAYNOOTH 220-MAYNOOTH 110-T2104 | Unknown | Unknown |  | Planned | October | October
TO-25-RYB GIS-T108-01 | TSO CUSTOMER TRANSFORMER - RYEBROOK GIS 110-RYEBROOK 10-T108 | 4 | 4 | 4 | Proposed | 06/10/2025 | 09/10/2025
TO-25-CSH-T2101-02 | TRANSFORMER - CASHLA 220-CASHLA 110-T2101 | Unknown | Unknown |  | Planned | October | October
TO-25-DRY-GOR-1-01 | 110kV FEEDER - DRYBRIDGE 110-GORMAN 110-1 | Unknown | Unknown | 40 | Planned | October | December
TO-25-DRY-GOR-1-05 | 110kV FEEDER - DRYBRIDGE 110-GORMAN 110-1 | Unknown | Unknown | 40 | Planned | October | December
TO-25-KBY-MR-1-02 | 110kV FEEDER - KILBARRY 110-MARINA 110-1 | Unknown | Unknown | 40 | Planned | October | December
TO-25-KBY-MR-2-02 | 110kV FEEDER - KILBARRY 110-MARINA 110-2 | Unknown | Unknown | 40 | Planned | October | December
TO-25-MP GIS-400SA1-3CB-01 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 400-MONEYPOINT GIS 400-400SA1-3CB | Unknown | Unknown | 2 | Planned | October | October
TO-25-110 kV A2 @ PLS-03 | BUSBAR SECTION - PORTLAOISE 110-PORTLAOISE 110-110A2 | Unknown | Unknown | 15 | Planned | October | November
TO-25-PLS-110K1-2-04 | COUPLER/SECTIONALISING CB - PORTLAOISE 110-PORTLAOISE 110-110K1-2 | Unknown | Unknown | 15 | Planned | October | November
TO-25-RYB GIS-T109-01 | TSO CUSTOMER TRANSFORMER - RYEBROOK GIS 110-RYEBROOK 10-T109 | 3 | 3 | 3 | Proposed | 13/10/2025 | 15/10/2025
TO-25-MP GIS-400SA2-4CB-02 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 400-MONEYPOINT GIS 400-400SA2-4CB | Unknown | Unknown | 5 | Planned | October | October
TO-25-RYB GIS-T103-01 | TSO CUSTOMER TRANSFORMER - RYEBROOK GIS 110-RYEBROOK 10-T103 | 2 | 2 | 2 | Proposed | 16/10/2025 | 17/10/2025
TO-25-DSN-MAY-1-01 | 220kV FEEDER - DUNSTOWN 220-MAYNOOTH 220-1 | Unknown | Unknown |  | Planned | October | October
TO-25-KYT-T233-01 | TSO CUSTOMER TRANSFORMER - KELLYSTOWN 220-KELLYSTOWN 34.5-T233 | 19 | 14 | 14 | Proposed | 20/10/2025 | 07/11/2025
TO-25-KYT-T233-02 | TSO CUSTOMER TRANSFORMER - KELLYSTOWN 220-KELLYSTOWN 34.5-T233 | 19 | 14 | 14 | Proposed | 20/10/2025 | 07/11/2025
TO-25-220 kV A2 @ MAY-01 | BUSBAR SECTION - MAYNOOTH 220-MAYNOOTH 220-220A2 | 5 | 5 | 5 | Scheduled | 20/10/2025 | 24/10/2025
TO-25-220 kV B2 @ MAY-02 | BUSBAR SECTION - MAYNOOTH 220-MAYNOOTH 220-220B2 | 5 | 5 | 5 | Scheduled | 20/10/2025 | 24/10/2025
TO-25-MAY-220K1-2-02 | COUPLER/SECTIONALISING CB - MAYNOOTH 220-MAYNOOTH 220-220K1-2 | 5 | 5 | 5 | Scheduled | 20/10/2025 | 24/10/2025
TO-25-MAY-TH-1-01 | 220kV FEEDER - MAYNOOTH 220-TURLOUGH HILL 220-1 | Unknown | Unknown |  | Planned | October | November
TO-25-MAY-TH-1-05 | 220kV FEEDER - MAYNOOTH 220-TURLOUGH HILL 220-1 | Unknown | Unknown | 5 | Planned | October | October
TO-25-110 kV A2 @ RYB GIS-01 | BUSBAR SECTION - RYEBROOK GIS 110-RYEBROOK GIS 110-110A2 | 15 | 10 | 10 | Proposed | 20/10/2025 | 03/11/2025
TO-25-110 kV B2 @ RYB GIS-01 | BUSBAR SECTION - RYEBROOK GIS 110-RYEBROOK GIS 110-110B2 | 15 | 10 | 10 | Proposed | 20/10/2025 | 03/11/2025
TO-25-RYB GIS-110SA1-2CB-03 | COUPLER/SECTIONALISING CB - RYEBROOK GIS 110-RYEBROOK GIS 110-110SA1-2CB | 15 | 10 | 10 | Proposed | 20/10/2025 | 03/11/2025
TO-25-RYB GIS-110SA2-4CB-02 | COUPLER/SECTIONALISING CB - RYEBROOK GIS 110-RYEBROOK GIS 110-110SA2-4CB | 15 | 10 | 10 | Proposed | 20/10/2025 | 03/11/2025
TO-25-RYB GIS-110SB1-2CB-03 | COUPLER/SECTIONALISING CB - RYEBROOK GIS 110-RYEBROOK GIS 110-110SB1-2CB | 15 | 10 | 10 | Proposed | 20/10/2025 | 03/11/2025
TO-25-RYB GIS-110SB2-4CB-02 | COUPLER/SECTIONALISING CB - RYEBROOK GIS 110-RYEBROOK GIS 110-110SB2-4CB | 15 | 10 | 10 | Proposed | 20/10/2025 | 03/11/2025
TO-25-RYB GIS-T104-01 | TSO CUSTOMER TRANSFORMER - RYEBROOK GIS 110-RYEBROOK 10-T104 | 15 | 10 | 10 | Proposed | 20/10/2025 | 03/11/2025
TO-25-AGL-SH-1-01 | 110kV FEEDER - AGANNYGAL 110-SHANNONBRIDGE 110-1 | Unknown | Unknown | 4 | Planned | October | October
TO-25-ATH-SH-1-07 | 110kV FEEDER - ATHLONE 110-SHANNONBRIDGE 110-1 | Unknown | Unknown | 4 | Planned | October | October
TO-25-MP GIS-400SB1-2CB-01 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 400-MONEYPOINT GIS 400-400SB1-2CB | Unknown | Unknown | 5 | Planned | October | October
TO-25-AGL-SH-1-02 | 110kV FEEDER - AGANNYGAL 110-SHANNONBRIDGE 110-1 | Unknown | Unknown | 15 | Planned | October | November
TO-25-KNR-TRI-2-01 | 110kV FEEDER - KNOCKANURE 110-TRIEN 110-2 | Unknown | Unknown | 3 | Planned | October | October
TO-25-SLI-110SA1-2CB-03 | COUPLER/SECTIONALISING CB - SLIGO 110-SLIGO 110-110SA1-2CB | 14 | 10 | 10 | Scheduled | 28/10/2025 | 10/11/2025
TO-25-SLI-CAP1-02 | CAPACITOR/SVC/REACTOR - SLIGO 110-SLIGO 110-CAP1 | 14 | 10 | 10 | Scheduled | 28/10/2025 | 10/11/2025
TO-25-SLI-T141-01 | DISTRIBUTION TRANSFORMER - SLIGO 110-SLIGO 38-T141 | 14 | 10 | 10 | Reference | 28/10/2025 | 10/11/2025
TO-25-TRI-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - TRIEN 110-TRIEN 110-110SA1-2CB | Unknown | Unknown | 3 | Planned | October | October
TO-25-TRI-T142-01 | DISTRIBUTION TRANSFORMER - TRIEN 110-TRIEN 38-T142 | Unknown | Unknown | 3 | Reference (Planned) | October | October
TO-25-MP GIS-400SB1-3CB-01 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 400-MONEYPOINT GIS 400-400SB1-3CB | Unknown | Unknown | 5 | Planned | October | November
TO-25-220 kV A1 @ SH-04 | BUSBAR SECTION - SHANNONBRIDGE 220-SHANNONBRIDGE 220-220A1 | 2 | 2 | 2 | Scheduled | 29/10/2025 | 30/10/2025
TO-25-220 kV B1 @ SH-02 | BUSBAR SECTION - SHANNONBRIDGE 220-SHANNONBRIDGE 220-220B1 | 2 | 2 | 2 | Scheduled | 29/10/2025 | 30/10/2025
TO-25-LIS-110SA1-01 | SECTIONALISING DISCONNECT - LISDRUM 110-LISDRUM 110-110SA1 | 1 | 1 | 1 | Scheduled | 03/11/2025 | 03/11/2025
TO-25-LIS-110SA2-01 | SECTIONALISING DISCONNECT - LISDRUM 110-LISDRUM 110-110SA2 | 1 | 1 | 1 | Scheduled | 03/11/2025 | 03/11/2025
TO-25-LIS-CAP2-01 | CAPACITOR/SVC/REACTOR - LISDRUM 110-LISDRUM 110-CAP2 | 1 | 1 | 1 | Scheduled | 03/11/2025 | 03/11/2025
TO-25-LIS-LSA-1-01 | 110kV FEEDER - LISDRUM 110-LISLEA 110-1 | 1 | 1 | 1 | Scheduled | 03/11/2025 | 03/11/2025
TO-25-220 kV A1 @ MAY-01 | BUSBAR SECTION - MAYNOOTH 220-MAYNOOTH 220-220A1 | Unknown | Unknown |  | Planned | November | November
TO-25-220 kV B1 @ MAY-01 | BUSBAR SECTION - MAYNOOTH 220-MAYNOOTH 220-220B1 | Unknown | Unknown |  | Planned | November | November
TO-25-MP GIS-400SB2-4CB-02 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 400-MONEYPOINT GIS 400-400SB2-4CB | Unknown | Unknown | 5 | Planned | November | November
TO-25-CF-SRA-1-01 | 110kV FEEDER - CATHALEENS FALL 110-SRANANAGH 110-1 | 1 | 1 | 1 | Proposed | 10/11/2025 | 10/11/2025
TO-25-KYT-T237-01 | TSO CUSTOMER TRANSFORMER - KELLYSTOWN 220-KELLYSTOWN 34.5-T237 | 3 | 3 | 3 | Proposed | 11/11/2025 | 13/11/2025
TO-25-110 kV A2 @ KRA-02 | BUSBAR SECTION - KNOCKRAHA 110-KNOCKRAHA 110-110A2 | Unknown | Unknown | 10 | Planned | November | November
TO-25-110 kV B2 @ KRA-02 | BUSBAR SECTION - KNOCKRAHA 110-KNOCKRAHA 110-110B2 | Unknown | Unknown | 10 | Planned | November | November
TO-25-DSN-MAY-2-01 | 220kV FEEDER - DUNSTOWN 220-MAYNOOTH 220-2 | 2 | 2 | 2 | Scheduled | 13/11/2025 | 14/11/2025
TO-25-220 kV A2 @ MAY-02 | BUSBAR SECTION - MAYNOOTH 220-MAYNOOTH 220-220A2 | 2 | 2 | 2 | Scheduled | 13/11/2025 | 14/11/2025
TO-25-110 kV A2 @ LOU-03 | BUSBAR SECTION - LOUTH 110-LOUTH 110-110A2 | Unknown | Unknown | 3 | Planned | November | November
TO-25-110 kV B2 @ LOU-03 | BUSBAR SECTION - LOUTH 110-LOUTH 110-110B2 | Unknown | Unknown |  | Planned | November | November
TO-25-110 kV B1 @ LOU-02 | BUSBAR SECTION - LOUTH 110-LOUTH 110-110B1 | Unknown | Unknown |  | Planned | November | November
TO-25-LOU-110K1-2-02 | COUPLER/SECTIONALISING CB - LOUTH 110-LOUTH 110-110K1-2 | Unknown | Unknown |  | Planned | November | November
TO-25-LOU-T2103-03 | TRANSFORMER - LOUTH 220-LOUTH 110-T2103 | Unknown | Unknown |  | Planned | November | November
TO-25-DDK-LOU-1-01 | 110kV FEEDER - DUNDALK 110-LOUTH 110-1 | Unknown | Unknown |  | Planned | December | December
TO-25-DSN-MAY-2-02 | 220kV FEEDER - DUNSTOWN 220-MAYNOOTH 220-2 | Unknown | Unknown |  | Planned | December | December
TO-25-LIS-LOU-1-01 | 110kV FEEDER - LISDRUM 110-LOUTH 110-1 | Unknown | Unknown |  | Planned | December | December
TO-25-DEY-PLS-1-03 | 110kV FEEDER - DERRYCARNEY 110-PORTLAOISE 110-1 | Unknown | Unknown | 2 | Planned | December | December
TO-25-KRA-WOH-1-01 | 110kV FEEDER - KNOCKRAHA 110-WOODHOUSE 110-1 | Unknown | Unknown | 10 | Planned | December | December
TO-25-KRA-WOH-1-02 | 110kV FEEDER - KNOCKRAHA 110-WOODHOUSE 110-1 | Unknown | Unknown | 10 | Planned | December | December
TO-25-110 kV A2 @ PLS-04 | BUSBAR SECTION - PORTLAOISE 110-PORTLAOISE 110-110A2 | Unknown | Unknown | 2 | Planned | December | December
TO-25-110 kV A2 @ LOU-04 | BUSBAR SECTION - LOUTH 110-LOUTH 110-110A2 | Unknown | Unknown | 2 | Planned | December | December
TO-25-LOU-T2104-02 | TRANSFORMER - LOUTH 220-LOUTH 110-T2104 | Unknown | Unknown |  | Planned | December | December
TO-25-110 kV B2 @ LOU-04 | BUSBAR SECTION - LOUTH 110-LOUTH 110-110B2 | Unknown | Unknown |  | Planned | December | December
TO-25-LOU-T2104-01 | TRANSFORMER - LOUTH 220-LOUTH 110-T2104 | Unknown | Unknown |  | Planned | December | December

## GEN_AreaSouthWest
Outage ID | Feeder ID | Calendar Day Duration | Working Day Duration | Work Days | Outage Status | Start | Finish
TO-25-CHA-MAL-1-03 | 110kV FEEDER - CHARLEVILLE 110-MALLOW 110-1 | 4 | 4 | 4 | Scheduled | 07/01/2025 | 10/01/2025
TO-25-AA GIS-DRU-1-01 | 110kV FEEDER - ARDNACRUSHA GIS 110-DRUMLINE 110-1 | 2 | 2 | 2 | Scheduled | 09/01/2025 | 10/01/2025
TO-25-KPG-110K4-01 | COUPLER/SECTIONALISING CB - KILPADDOGE 110-KILPADDOGE 110-110K4 | 1 | 1 |  | Scheduled | 21/01/2025 | 21/01/2025
TO-25-220 kV A2 @ KLN-01 | BUSBAR SECTION - KILLONAN 220-KILLONAN 220-220A2 | 5 | 5 | 5 | Scheduled | 27/01/2025 | 31/01/2025
TO-25-220 kV B2 @ KLN-01 | BUSBAR SECTION - KILLONAN 220-KILLONAN 220-220B2 | 5 | 5 | 5 | Scheduled | 27/01/2025 | 31/01/2025
TO-25-KLN-KPG-1-01 | 220kV FEEDER - KILLONAN 220-KILPADDOGE 220-1 | 43 | 30 | 30 | Scheduled | 27/01/2025 | 10/03/2025
TO-25-220 kV A2 @ TB-01 | BUSBAR SECTION - TARBERT 220-TARBERT 220-220A2 | 15 | 10 | 10 | Scheduled | 27/01/2025 | 10/02/2025
TO-25-220 kV B2 @ TB-01 | BUSBAR SECTION - TARBERT 220-TARBERT 220-220B2 | 15 | 10 | 10 | Scheduled | 27/01/2025 | 10/02/2025
TO-25-CHA-KLN-1-01 | 110kV FEEDER - CHARLEVILLE 110-KILLONAN 110-1 | 43 | 30 | 30 | Scheduled | 04/02/2025 | 18/03/2025
TO-25-110 kV A3 @ KPG-01 | BUSBAR SECTION - KILPADDOGE 110-KILPADDOGE 110-110A3 | 5 | 5 | 5 | Scheduled | 03/03/2025 | 07/03/2025
TO-25-110 kV B3 @ KPG-01 | BUSBAR SECTION - KILPADDOGE 110-KILPADDOGE 110-110B3 | 5 | 5 | 5 | Scheduled | 03/03/2025 | 07/03/2025
TO-25-KPG-110K3-02 | COUPLER/SECTIONALISING CB - KILPADDOGE 110-KILPADDOGE 110-110K3 | 5 | 5 | 5 | Scheduled | 03/03/2025 | 07/03/2025
TO-25-KPG-110SA1-3CB-02 | COUPLER/SECTIONALISING CB - KILPADDOGE 110-KILPADDOGE 110-110SA1-3CB | 5 | 5 | 5 | Scheduled | 03/03/2025 | 07/03/2025
TO-25-KPG-110SB1-3CB-02 | COUPLER/SECTIONALISING CB - KILPADDOGE 110-KILPADDOGE 110-110SB1-3CB | 5 | 5 | 5 | Scheduled | 03/03/2025 | 07/03/2025
TO-25-220 kV A2 @ KLN-02 | BUSBAR SECTION - KILLONAN 220-KILLONAN 220-220A2 | 7 | 5 | 5 | Scheduled | 04/03/2025 | 10/03/2025
TO-25-220 kV B2 @ KLN-02 | BUSBAR SECTION - KILLONAN 220-KILLONAN 220-220B2 | 7 | 5 | 5 | Scheduled | 04/03/2025 | 10/03/2025
TO-25-DSN-MP GIS-1-01 | 400kV FEEDER - DUNSTOWN 400-MONEYPOINT GIS 400-1 | 46 | 31 | 31 | Scheduled | 11/03/2025 | 25/04/2025
TO-25-KLN-KRA-1-04 | 220kV FEEDER - KILLONAN 220-KNOCKRAHA 220-1 | 4 | 4 | 4 | Scheduled | 11/03/2025 | 14/03/2025
TO-25-400 kV A4 @ MP GIS-01 | BUSBAR SECTION - MONEYPOINT GIS 400-MONEYPOINT GIS 400-400A4 | 38 | 27 | 27 | Scheduled | 11/03/2025 | 17/04/2025
TO-25-400 kV B4 @ MP GIS-01 | BUSBAR SECTION - MONEYPOINT GIS 400-MONEYPOINT GIS 400-400B4 | 38 | 27 | 27 | Scheduled | 11/03/2025 | 17/04/2025
TO-25-MP GIS-400K4-01 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 400-MONEYPOINT GIS 400-400K4 | 38 | 27 | 27 | Scheduled | 11/03/2025 | 17/04/2025
TO-25-MP GIS-400SA2-4CB-01 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 400-MONEYPOINT GIS 400-400SA2-4CB | 38 | 27 | 27 | Scheduled | 11/03/2025 | 17/04/2025
TO-25-MP GIS-400SB2-4CB-01 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 400-MONEYPOINT GIS 400-400SB2-4CB | 38 | 27 | 27 | Scheduled | 11/03/2025 | 17/04/2025
TO-25-KPG-TB-2-02 | 220kV FEEDER - KILPADDOGE 220-TARBERT 220-2 | 2 | 2 | 2 | Scheduled | 12/03/2025 | 13/03/2025
TO-25-220 kV A2 @ TB-02 | BUSBAR SECTION - TARBERT 220-TARBERT 220-220A2 | 2 | 2 | 2 | Scheduled | 12/03/2025 | 13/03/2025
TO-25-220 kV B2 @ TB-02 | BUSBAR SECTION - TARBERT 220-TARBERT 220-220B2 | 2 | 2 | 2 | Scheduled | 12/03/2025 | 13/03/2025
TO-25-CSH-ENN-1-02 | 110kV FEEDER - CASHLA 110-ENNIS 110-1 | 72 | 49 | 49 | Scheduled | 19/03/2025 | 29/05/2025
TO-25-THU-STATCOM-03 | CAPACITOR/SVC/REACTOR - THURLES 110-THURLES 110-STATCOM | 5 | 5 | 5 | Scheduled | 24/03/2025 | 28/03/2025
TO-25-AUG-KPG-1-01 | 110kV FEEDER - AUGHINISH 110-KILPADDOGE 110-1 | 3 | 3 | 3 | Scheduled | 25/03/2025 | 27/03/2025
TO-25-BYH-GLE-1-01 | 110kV FEEDER - BALLYNAHULLA 110-GLENLARA 110-1 | 12 | 10 | 10 | Scheduled | 31/03/2025 | 11/04/2025
TO-25-BYH-STATCOM-01 | CAPACITOR/SVC/REACTOR - BALLYNAHULLA 110-BALLYNAHULLA 110-STATCOM | 5 | 5 | 5 | Scheduled | 31/03/2025 | 04/04/2025
TO-25-GLE-KCR-1-01 | 110kV FEEDER - GLENLARA 110-KNOCKACUMMER 110-1 | 12 | 10 | 10 | Scheduled | 31/03/2025 | 11/04/2025
TO-25-KCR-T121-01 | GENERATOR TRANSFORMER - KNOCKACUMMER 110-KNOCKACUMMER 20-T121 | 12 | 10 | 10 | Scheduled | 31/03/2025 | 11/04/2025
TO-25-AA GIS-LIM-1-01 | 110kV FEEDER - ARDNACRUSHA GIS 110-LIMERICK 110-1 | 3 | 3 | 3 | Scheduled | 01/04/2025 | 03/04/2025
TO-25-BYH-110K1-02 | COUPLER/SECTIONALISING CB - BALLYNAHULLA 110-BALLYNAHULLA 110-110K1 | 2 | 2 | 2 | Scheduled | 01/04/2025 | 02/04/2025
TO-25-BYH-110SB1-2CB-01 | COUPLER/SECTIONALISING CB - BALLYNAHULLA 110-BALLYNAHULLA 110-110SB1-2CB | 2 | 2 | 2 | Scheduled | 01/04/2025 | 02/04/2025
TO-25-BVK-STATCOM-01 | CAPACITOR/SVC/REACTOR - BALLYVOUSKILL 110-BALLYVOUSKILL 110-STATCOM | 5 | 5 | 5 | Scheduled | 07/04/2025 | 11/04/2025
TO-25-220 kV A1 @ MP GIS-01 | BUSBAR SECTION - MONEYPOINT GIS 220-MONEYPOINT GIS 220-220A1 | 9 | 7 | 7 | Scheduled | 07/04/2025 | 15/04/2025
TO-25-220 kV B1 @ MP GIS-01 | BUSBAR SECTION - MONEYPOINT GIS 220-MONEYPOINT GIS 220-220B1 | 9 | 7 | 7 | Scheduled | 07/04/2025 | 15/04/2025
TO-25-MP GIS-220K1-01 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 220-MONEYPOINT GIS 220-220K1 | 9 | 7 | 7 | Scheduled | 07/04/2025 | 15/04/2025
TO-25-MP GIS-220SA1-2CB-02 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 220-MONEYPOINT GIS 220-220SA1-2CB | 9 | 7 | 7 | Scheduled | 07/04/2025 | 15/04/2025
TO-25-MP GIS-220SB1-2CB-02 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 220-MONEYPOINT GIS 220-220SB1-2CB | 9 | 7 | 7 | Scheduled | 07/04/2025 | 15/04/2025
TO-25-AA GIS-SNG-1-01 | 110kV FEEDER - ARDNACRUSHA GIS 110-SINGLAND 110-1 | 3 | 3 | 3 | Scheduled | 08/04/2025 | 10/04/2025
TO-25-220 kV A1 @ BYH-01 | BUSBAR SECTION - BALLYNAHULLA 220-BALLYNAHULLA 220-220A1 | 4 | 4 | 4 | Scheduled | 14/04/2025 | 17/04/2025
TO-25-220 kV A2 @ BYH-01 | BUSBAR SECTION - BALLYNAHULLA 220-BALLYNAHULLA 220-220A2 | 4 | 4 | 4 | Scheduled | 14/04/2025 | 17/04/2025
TO-25-BYH-220K1-02 | COUPLER/SECTIONALISING CB - BALLYNAHULLA 220-BALLYNAHULLA 220-220K1 | 4 | 4 | 4 | Scheduled | 14/04/2025 | 17/04/2025
TO-25-BYH-220K2-01 | COUPLER/SECTIONALISING CB - BALLYNAHULLA 220-BALLYNAHULLA 220-220K2 | 4 | 4 | 4 | Scheduled | 14/04/2025 | 17/04/2025
TO-25-BYH-220SA1-2CB-01 | COUPLER/SECTIONALISING CB - BALLYNAHULLA 220-BALLYNAHULLA 220-220SA1-2CB | 4 | 4 | 4 | Scheduled | 14/04/2025 | 17/04/2025
TO-25-CHA-MAL-1-06 | 110kV FEEDER - CHARLEVILLE 110-MALLOW 110-1 | 3 | 3 | 3 | Scheduled | 14/04/2025 | 16/04/2025
TO-25-KPG-TRL-2-02 | 110kV FEEDER - KILPADDOGE 110-TRALEE 110-2 | 138 | 95 | 95 | Scheduled | 14/04/2025 | 29/08/2025
TO-25-220 kV A2 @ MP GIS-01 | BUSBAR SECTION - MONEYPOINT GIS 220-MONEYPOINT GIS 220-220A2 | 13 | 7 | 7 | Scheduled | 16/04/2025 | 28/04/2025
TO-25-220 kV B2 @ MP GIS-01 | BUSBAR SECTION - MONEYPOINT GIS 220-MONEYPOINT GIS 220-220B2 | 13 | 7 | 7 | Scheduled | 16/04/2025 | 28/04/2025
TO-25-MP GIS-220K2-01 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 220-MONEYPOINT GIS 220-220K2 | 13 | 7 | 7 | Scheduled | 16/04/2025 | 28/04/2025
TO-25-MP GIS-220SA1-2CB-03 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 220-MONEYPOINT GIS 220-220SA1-2CB | 13 | 7 | 7 | Scheduled | 16/04/2025 | 28/04/2025
TO-25-MP GIS-220SB1-2CB-03 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 220-MONEYPOINT GIS 220-220SB1-2CB | 13 | 7 | 7 | Scheduled | 16/04/2025 | 28/04/2025
TO-25-CHA-GLE-1-01 | 110kV FEEDER - CHARLEVILLE 110-GLENLARA 110-1 | 62 | 40 | 40 | Scheduled | 17/04/2025 | 17/06/2025
TO-25-AUG-MTN-1-01 | 110kV FEEDER - AUGHINISH 110-MONETEEN 110-1 | 3 | 3 | 3 | Scheduled | 22/04/2025 | 24/04/2025
TO-25-IKE-T141-01 | DISTRIBUTION TRANSFORMER - IKERRIN 110-IKERRIN 38-T141 | 2 | 2 | 2 | Reference | 24/04/2025 | 25/04/2025
TO-25-IKE,T-IKE-1-01 | 110kV FEEDER - IKERRIN tee-IKERRIN 110-1 | 2 | 2 | 2 | Scheduled | 24/04/2025 | 25/04/2025
TO-25-IKE,T-SH-1-01 | 110kV FEEDER - IKERRIN tee-SHANNONBRIDGE 110-1 | 2 | 2 | 2 | Scheduled | 24/04/2025 | 25/04/2025
TO-25-IKE,T-THU-1-05 | 110kV FEEDER - IKERRIN tee-THURLES 110-1 | 63 | 43 | 43 | Scheduled | 24/04/2025 | 25/06/2025
TO-25-110 kV B2 @ AA GIS-01 | BUSBAR SECTION - ARDNACRUSHA GIS 110-ARDNACRUSHA GIS 110-110B2 | 5 | 5 | 5 | Scheduled | 28/04/2025 | 02/05/2025
TO-25-AA GIS-110K2-02 | COUPLER/SECTIONALISING CB - ARDNACRUSHA GIS 110-ARDNACRUSHA GIS 110-110K2 | 5 | 5 | 5 | Scheduled | 28/04/2025 | 02/05/2025
TO-25-AA GIS-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - ARDNACRUSHA GIS 110-ARDNACRUSHA GIS 110-110SA1-2CB | 5 | 5 | 5 | Scheduled | 28/04/2025 | 02/05/2025
TO-25-AA GIS-110SB1-2CB-01 | COUPLER/SECTIONALISING CB - ARDNACRUSHA GIS 110-ARDNACRUSHA GIS 110-110SB1-2CB | 5 | 5 | 5 | Scheduled | 28/04/2025 | 02/05/2025
TO-25-AA GIS-T102-02 | GENERATOR TRANSFORMER - ARDNACRUSHA GIS 110-ARDNACRUSHA GIS G2-T102 | 145 | 102 | 102 | Scheduled | 28/04/2025 | 19/09/2025
TO-25-BVK-110K2-01 | COUPLER/SECTIONALISING CB - BALLYVOUSKILL 110-BALLYVOUSKILL 110-110K2 | 2 | 2 | 2 | Scheduled | 28/04/2025 | 29/04/2025
TO-25-220 kV A1 @ BVK-01 | BUSBAR SECTION - BALLYVOUSKILL 220-BALLYVOUSKILL 220-220A1 | 5 | 5 | 5 | Scheduled | 28/04/2025 | 02/05/2025
TO-25-220 kV B1 @ BVK-01 | BUSBAR SECTION - BALLYVOUSKILL 220-BALLYVOUSKILL 220-220B1 | 5 | 5 | 5 | Scheduled | 28/04/2025 | 02/05/2025
TO-25-BVK-220K1-02 | COUPLER/SECTIONALISING CB - BALLYVOUSKILL 220-BALLYVOUSKILL 220-220K1 | 5 | 5 | 5 | Scheduled | 28/04/2025 | 02/05/2025
TO-25-BVK-220SA1-2CB-03 | COUPLER/SECTIONALISING CB - BALLYVOUSKILL 220-BALLYVOUSKILL 220-220SA1-2CB | 5 | 5 | 5 | Scheduled | 28/04/2025 | 02/05/2025
TO-25-BVK-220SB1-2CB-04 | COUPLER/SECTIONALISING CB - BALLYVOUSKILL 220-BALLYVOUSKILL 220-220SB1-2CB | 5 | 5 | 5 | Scheduled | 28/04/2025 | 02/05/2025
TO-25-BVK-R2001-01 | CAPACITOR/SVC/REACTOR - BALLYVOUSKILL 220-BALLYVOUSKILL 220-R2001 | 5 | 5 | 5 | Scheduled | 28/04/2025 | 02/05/2025
TO-25-DSN-MP GIS-1-04 | 400kV FEEDER - DUNSTOWN 400-MONEYPOINT GIS 400-1 | 25 | 18 | 18 | Scheduled | 29/04/2025 | 23/05/2025
TO-25-220 kV A3 @ KPG-01 | BUSBAR SECTION - KILPADDOGE 220-KILPADDOGE 220-220A3 | 14 | 10 | 10 | Scheduled | 06/05/2025 | 19/05/2025
TO-25-220 kV B3 @ KPG-01 | BUSBAR SECTION - KILPADDOGE 220-KILPADDOGE 220-220B3 | 14 | 10 | 10 | Scheduled | 06/05/2025 | 19/05/2025
TO-25-KPG-220K3-02 | COUPLER/SECTIONALISING CB - KILPADDOGE 220-KILPADDOGE 220-220K3 | 14 | 10 | 10 | Scheduled | 06/05/2025 | 19/05/2025
TO-25-KPG-220SA1-3CB-02 | COUPLER/SECTIONALISING CB - KILPADDOGE 220-KILPADDOGE 220-220SA1-3CB | 14 | 10 | 10 | Scheduled | 06/05/2025 | 19/05/2025
TO-25-KPG-220SB1-3CB-02 | COUPLER/SECTIONALISING CB - KILPADDOGE 220-KILPADDOGE 220-220SB1-3CB | 14 | 10 | 10 | Scheduled | 06/05/2025 | 19/05/2025
TO-25-KPG-TB-1-01 | 220kV FEEDER - KILPADDOGE 220-TARBERT 220-1 | 14 | 10 | 10 | Scheduled | 06/05/2025 | 19/05/2025
TO-25-MP GIS-T4001-03 | GENERATOR TRANSFORMER - MONEYPOINT GIS 400-MONEYPOINT GIS G1-T4001 | 86 | 61 | 61 | Scheduled | 06/05/2025 | 30/07/2025
TO-25-220 kV A1 @ TB-01 | BUSBAR SECTION - TARBERT 220-TARBERT 220-220A1 | 14 | 10 | 10 | Scheduled | 06/05/2025 | 19/05/2025
TO-25-220 kV B1 @ TB-01 | BUSBAR SECTION - TARBERT 220-TARBERT 220-220B1 | 14 | 10 | 10 | Scheduled | 06/05/2025 | 19/05/2025
TO-25-220 kV A2 @ KNR-01 | BUSBAR SECTION - KNOCKANURE 220-KNOCKANURE 220-220A2 | 6 | 4 | 4 | Scheduled | 07/05/2025 | 12/05/2025
TO-25-220 kV B2 @ KNR-01 | BUSBAR SECTION - KNOCKANURE 220-KNOCKANURE 220-220B2 | 6 | 4 | 4 | Scheduled | 07/05/2025 | 12/05/2025
TO-25-KNR-220K2-02 | COUPLER/SECTIONALISING CB - KNOCKANURE 220-KNOCKANURE 220-220K2 | 6 | 4 | 4 | Scheduled | 07/05/2025 | 12/05/2025
TO-25-KNR-220SA1-2CB-02 | COUPLER/SECTIONALISING CB - KNOCKANURE 220-KNOCKANURE 220-220SA1-2CB | 6 | 4 | 4 | Scheduled | 07/05/2025 | 12/05/2025
TO-25-KNR-220SB1-2CB-02 | COUPLER/SECTIONALISING CB - KNOCKANURE 220-KNOCKANURE 220-220SB1-2CB | 6 | 4 | 4 | Scheduled | 07/05/2025 | 12/05/2025
TO-25-KNR-R2002-01 | CAPACITOR/SVC/REACTOR - KNOCKANURE 220-KNOCKANURE 220-R2002 | 6 | 4 | 4 | Scheduled | 07/05/2025 | 12/05/2025
TO-25-AA GIS-T103-01 | GENERATOR TRANSFORMER - ARDNACRUSHA GIS 110-ARDNACRUSHA GIS G3-T103 | 5 | 5 | 5 | Scheduled | 12/05/2025 | 16/05/2025
TO-25-CLH-T122-01 | GENERATOR TRANSFORMER - CLAHANE 110-CLAHANE 20-T122 | 3 | 3 | 3 | Scheduled | 13/05/2025 | 15/05/2025
TO-25-AUG-CFM-2-01 | 110kV FEEDER - AUGHINISH 110-CASTLEFARM 110-2 | 12 | 10 | 10 | Scheduled | 19/05/2025 | 30/05/2025
TO-25-CFM-T102-01 | TSO CUSTOMER TRANSFORMER - CASTLEFARM 110-CASTLEFARM 10-T102 | 12 | 10 | 10 | Reference | 19/05/2025 | 30/05/2025
TO-25-GLE-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - GLENLARA 110-GLENLARA 110-110SA1-2CB | 5 | 5 | 5 | Scheduled | 19/05/2025 | 23/05/2025
TO-25-GLE-T142-01 | DISTRIBUTION TRANSFORMER - GLENLARA 110-GLENLARA 38-T142 | 5 | 5 | 5 | Reference | 19/05/2025 | 23/05/2025
TO-25-LSN-110SA1-2-03 | SECTIONALISING DISCONNECT - LISHEEN 110-LISHEEN 110-110SA1-2 | 5 | 5 | 5 | Scheduled | 19/05/2025 | 23/05/2025
TO-25-LSN-110SA2-4-03 | SECTIONALISING DISCONNECT - LISHEEN 110-LISHEEN 110-110SA2-4 | 5 | 5 | 5 | Scheduled | 19/05/2025 | 23/05/2025
TO-25-LSN-T122-03 | GENERATOR TRANSFORMER - LISHEEN 110-LISHEEN 20-T122 | 5 | 5 | 5 | Scheduled | 19/05/2025 | 23/05/2025
TO-25-LSN-T131-04 | GENERATOR TRANSFORMER - LISHEEN 110-LISHEEN 33-T131 | 5 | 5 | 5 | Scheduled | 19/05/2025 | 23/05/2025
TO-25-LSN-T142-03 | DISTRIBUTION TRANSFORMER - LISHEEN 110-LISHEEN 38-T142 | 5 | 5 | 5 | Reference | 19/05/2025 | 23/05/2025
TO-25-LSN-THU-1-03 | 110kV FEEDER - LISHEEN 110-THURLES 110-1 | 5 | 5 | 5 | Scheduled | 19/05/2025 | 23/05/2025
TO-25-CSH-PRO-1-03 | 220kV FEEDER - CASHLA 220-PROSPECT 220-1 | 2 | 2 | 2 | Scheduled | 20/05/2025 | 21/05/2025
TO-25-KLN-LIM-1-03 | 110kV FEEDER - KILLONAN 110-LIMERICK 110-1 | 18 | 13 | 13 | Scheduled | 20/05/2025 | 06/06/2025
TO-25-KPG-T2102-02 | TRANSFORMER - KILPADDOGE 220-KILPADDOGE 110-T2102 | 5 | 5 | 5 | Scheduled | 26/05/2025 | 30/05/2025
TO-25-LIM-MTN-1-03 | 110kV FEEDER - LIMERICK 110-MONETEEN 110-1 | 5 | 5 | 5 | Scheduled | 26/05/2025 | 30/05/2025
TO-25-OUG-T141-01 | DISTRIBUTION TRANSFORMER - OUGHTRAGH 110-OUGHTRAGH 38-T141 | 10 | 8 | 8 | Reference | 03/06/2025 | 12/06/2025
TO-25-OUG,T-KER-1-02 | 110kV FEEDER - OUGHTRAGH tee-KNOCKEARAGH 110-1 | 10 | 8 | 8 | Scheduled | 03/06/2025 | 12/06/2025
TO-25-OUG,T-OUG-1-01 | 110kV FEEDER - OUGHTRAGH tee-OUGHTRAGH 110-1 | 10 | 8 | 8 | Scheduled | 03/06/2025 | 12/06/2025
TO-25-OUG,T-TRL-1-04 | 110kV FEEDER - OUGHTRAGH tee-TRALEE 110-1 | 10 | 8 | 8 | Scheduled | 03/06/2025 | 12/06/2025
TO-25-AA GIS-T101-01 | GENERATOR TRANSFORMER - ARDNACRUSHA GIS 110-ARDNACRUSHA GIS G1-T101 | 5 | 5 | 5 | Scheduled | 09/06/2025 | 13/06/2025
TO-25-AUG-SK-4-01 | 110kV FEEDER - AUGHINISH 110-SEALROCK 110-4 | 5 | 5 | 5 | Scheduled | 09/06/2025 | 13/06/2025
TO-25-LIM-RAT-1-02 | 110kV FEEDER - LIMERICK 110-RATHKEALE 110-1 | 5 | 5 | 5 | Scheduled | 09/06/2025 | 13/06/2025
TO-25-SK-T104-01 | GENERATOR TRANSFORMER - SEALROCK 110-SEALROCK G4-T104 | 5 | 5 | 5 | Scheduled | 09/06/2025 | 13/06/2025
TO-25-KPG-RAT-1-02 | 110kV FEEDER - KILPADDOGE 110-RATHKEALE 110-1 | 5 | 5 | 5 | Scheduled | 16/06/2025 | 20/06/2025
TO-25-MP GIS-T4002-03 | GENERATOR TRANSFORMER - MONEYPOINT GIS 400-MONEYPOINT GIS G2-T4002 | 4 | 4 | 4 | Scheduled | 16/06/2025 | 19/06/2025
TO-25-KLN-SH-1-04 | 220kV FEEDER - KILLONAN 220-SHANNONBRIDGE 220-1 | 3 | 3 | 3 | Scheduled | 18/06/2025 | 20/06/2025
TO-25-ATE-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - ATHEA 110-ATHEA 110-110SA1-2CB | 5 | 5 | 5 | Scheduled | 23/06/2025 | 27/06/2025
TO-25-ATE-DRO-1-01 | 110kV FEEDER - ATHEA 110-DROMADA 110-1 | 5 | 5 | 5 | Scheduled | 23/06/2025 | 27/06/2025
TO-25-ATE-KNR-1-01 | 110kV FEEDER - ATHEA 110-KNOCKANURE 110-1 | 5 | 5 | 5 | Scheduled | 23/06/2025 | 27/06/2025
TO-25-ATE-T121-01 | GENERATOR TRANSFORMER - ATHEA 110-ATHEA 20-T121 | 5 | 5 | 5 | Scheduled | 23/06/2025 | 27/06/2025
TO-25-ATE-TOB-1-01 | 110kV FEEDER - ATHEA 110-TOBERTOREEN 110-1 | 5 | 5 | 5 | Scheduled | 23/06/2025 | 27/06/2025
TO-25-DRO-T121-01 | GENERATOR TRANSFORMER - DROMADA 110-DROMADA 20-T121 | 5 | 5 | 5 | Scheduled | 23/06/2025 | 27/06/2025
TO-25-KLN-SH-1-01 | 220kV FEEDER - KILLONAN 220-SHANNONBRIDGE 220-1 | 5 | 5 | 5 | Scheduled | 23/06/2025 | 27/06/2025
TO-25-110 kV B1 @ KNR-01 | BUSBAR SECTION - KNOCKANURE 110-KNOCKANURE 110-110B1 | 5 | 5 | 5 | Scheduled | 23/06/2025 | 27/06/2025
TO-25-KNR-110K1-01 | COUPLER/SECTIONALISING CB - KNOCKANURE 110-KNOCKANURE 110-110K1 | 5 | 5 | 5 | Scheduled | 23/06/2025 | 27/06/2025
TO-25-KNR-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - KNOCKANURE 110-KNOCKANURE 110-110SA1-2CB | 5 | 5 | 5 | Scheduled | 23/06/2025 | 27/06/2025
TO-25-KNR-110SB1-2CB-01 | COUPLER/SECTIONALISING CB - KNOCKANURE 110-KNOCKANURE 110-110SB1-2CB | 5 | 5 | 5 | Scheduled | 23/06/2025 | 27/06/2025
TO-25-MP GIS-T121-01 | GENERATOR TRANSFORMER - MONEYPOINT GIS 110-MONEYPOINT GIS 20-T121 | 5 | 5 | 5 | Scheduled | 23/06/2025 | 27/06/2025
TO-25-TOB-T132-01 | GENERATOR TRANSFORMER - TOBERTOREEN 110-TOBERTOREEN 33-T132 | 5 | 5 | 5 | Scheduled | 23/06/2025 | 27/06/2025
TO-25-IKE-T141-02 | DISTRIBUTION TRANSFORMER - IKERRIN 110-IKERRIN 38-T141 | 14 | 10 |  | Reference | 25/06/2025 | 08/07/2025
TO-25-IKE,T-IKE-1-02 | 110kV FEEDER - IKERRIN tee-IKERRIN 110-1 | 14 | 10 |  | Scheduled | 25/06/2025 | 08/07/2025
TO-25-IKE,T-SH-1-02 | 110kV FEEDER - IKERRIN tee-SHANNONBRIDGE 110-1 | 14 | 10 |  | Scheduled | 25/06/2025 | 08/07/2025
TO-25-IKE,T-THU-1-02 | 110kV FEEDER - IKERRIN tee-THURLES 110-1 | 14 | 10 |  | Scheduled | 25/06/2025 | 08/07/2025
TO-25-110 kV B2 @ BVK-01 | BUSBAR SECTION - BALLYVOUSKILL 110-BALLYVOUSKILL 110-110B2 | 12 | 10 | 10 | Scheduled | 30/06/2025 | 11/07/2025
TO-25-BVK-110K2-02 | COUPLER/SECTIONALISING CB - BALLYVOUSKILL 110-BALLYVOUSKILL 110-110K2 | 12 | 10 | 10 | Scheduled | 30/06/2025 | 11/07/2025
TO-25-BVK-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - BALLYVOUSKILL 110-BALLYVOUSKILL 110-110SA1-2CB | 12 | 10 | 10 | Scheduled | 30/06/2025 | 11/07/2025
TO-25-BVK-110SB1-2CB-01 | COUPLER/SECTIONALISING CB - BALLYVOUSKILL 110-BALLYVOUSKILL 110-110SB1-2CB | 12 | 10 | 10 | Scheduled | 30/06/2025 | 11/07/2025
TO-25-BVK-COT-1-01 | 110kV FEEDER - BALLYVOUSKILL 110-COOMATAGGART 110-1 | 12 | 10 | 10 | Scheduled | 30/06/2025 | 11/07/2025
TO-25-COT-110SA1-01 | SECTIONALISING DISCONNECT - COOMATAGGART 110-COOMATAGGART 110-110SA1 | 12 | 10 | 10 | Scheduled | 30/06/2025 | 11/07/2025
TO-25-COT-110SA2-01 | SECTIONALISING DISCONNECT - COOMATAGGART 110-COOMATAGGART 110-110SA2 | 12 | 10 | 10 | Scheduled | 30/06/2025 | 11/07/2025
TO-25-COT-FILTER1-01 | CAPACITOR/SVC/REACTOR - COOMATAGGART 110-COOMATAGGART 110-FILTER1 | 12 | 10 | 10 | Scheduled | 30/06/2025 | 11/07/2025
TO-25-COT-T132-01 | GENERATOR TRANSFORMER - COOMATAGGART 110-COOMATAGGART 33-T132 | 12 | 10 |  | Scheduled | 30/06/2025 | 11/07/2025
TO-25-COT-T141-01 | DISTRIBUTION TRANSFORMER - COOMATAGGART 110-COOMATAGGART 38-T141 | 12 | 10 | 10 | Reference | 30/06/2025 | 11/07/2025
TO-25-GRO-T122-01 | GENERATOR TRANSFORMER - GARROW 110-GARROW 20-T122 | 5 | 5 |  | Scheduled | 30/06/2025 | 04/07/2025
TO-25-KLN-SH-1-05 | 220kV FEEDER - KILLONAN 220-SHANNONBRIDGE 220-1 | 2 | 2 | 2 | Scheduled | 30/06/2025 | 01/07/2025
TO-25-ENN-SLC-1-01 | 110kV FEEDER - ENNIS 110-SLIEVECALLAN 110-1 | 3 | 3 | 3 | Scheduled | 07/07/2025 | 09/07/2025
TO-25-KPG-220K3-01 | COUPLER/SECTIONALISING CB - KILPADDOGE 220-KILPADDOGE 220-220K3 | 5 | 5 | 5 | Scheduled | 07/07/2025 | 11/07/2025
TO-25-KPG-220SA1-2CB-01 | COUPLER/SECTIONALISING CB - KILPADDOGE 220-KILPADDOGE 220-220SA1-2CB | 5 | 5 | 5 | Scheduled | 07/07/2025 | 11/07/2025
TO-25-KPG-220SA1-3CB-01 | COUPLER/SECTIONALISING CB - KILPADDOGE 220-KILPADDOGE 220-220SA1-3CB | 5 | 5 | 5 | Scheduled | 07/07/2025 | 11/07/2025
TO-25-KPG-220SB1-2CB-01 | COUPLER/SECTIONALISING CB - KILPADDOGE 220-KILPADDOGE 220-220SB1-2CB | 5 | 5 | 5 | Scheduled | 07/07/2025 | 11/07/2025
TO-25-KPG-220SB1-3CB-01 | COUPLER/SECTIONALISING CB - KILPADDOGE 220-KILPADDOGE 220-220SB1-3CB | 5 | 5 | 5 | Scheduled | 07/07/2025 | 11/07/2025
TO-25-SLC-110SA1-01 | SECTIONALISING DISCONNECT - SLIEVECALLAN 110-SLIEVECALLAN 110-110SA1 | 3 | 3 | 3 | Scheduled | 07/07/2025 | 09/07/2025
TO-25-SLC-110SA2-01 | SECTIONALISING DISCONNECT - SLIEVECALLAN 110-SLIEVECALLAN 110-110SA2 | 3 | 3 | 3 | Scheduled | 07/07/2025 | 09/07/2025
TO-25-SLC-T121-01 | GENERATOR TRANSFORMER - SLIEVECALLAN 110-SLIEVECALLAN 20-T121 | 3 | 3 | 3 | Scheduled | 07/07/2025 | 09/07/2025
TO-25-SLC-T122-01 | GENERATOR TRANSFORMER - SLIEVECALLAN 110-SLIEVECALLAN 20-T122 | 3 | 3 | 3 | Scheduled | 07/07/2025 | 09/07/2025
TO-25-IKE,T-SH-1-05 | 110kV FEEDER - IKERRIN tee-SHANNONBRIDGE 110-1 | 58 | 41 | 41 | Scheduled | 08/07/2025 | 03/09/2025
TO-25-110 kV B1 @ AA GIS-01 | BUSBAR SECTION - ARDNACRUSHA GIS 110-ARDNACRUSHA GIS 110-110B1 | 1 | 1 | 1 | Scheduled | 10/07/2025 | 10/07/2025
TO-25-110 kV B3 @ AA GIS-02 | BUSBAR SECTION - ARDNACRUSHA GIS 110-ARDNACRUSHA GIS 110-110B3 | 1 | 1 | 1 | Scheduled | 10/07/2025 | 10/07/2025
TO-25-AA GIS-110K3-02 | COUPLER/SECTIONALISING CB - ARDNACRUSHA GIS 110-ARDNACRUSHA GIS 110-110K3 | 1 | 1 | 1 | Scheduled | 10/07/2025 | 10/07/2025
TO-25-AA GIS-110SB1-2CB-04 | COUPLER/SECTIONALISING CB - ARDNACRUSHA GIS 110-ARDNACRUSHA GIS 110-110SB1-2CB | 1 | 1 | 1 | Scheduled | 10/07/2025 | 10/07/2025
TO-25-AA GIS-110SB1-3CB-02 | COUPLER/SECTIONALISING CB - ARDNACRUSHA GIS 110-ARDNACRUSHA GIS 110-110SB1-3CB | 1 | 1 | 1 | Scheduled | 10/07/2025 | 10/07/2025
TO-25-AA GIS-T103-02 | GENERATOR TRANSFORMER - ARDNACRUSHA GIS 110-ARDNACRUSHA GIS G3-T103 | 1 | 1 | 1 | Scheduled | 10/07/2025 | 10/07/2025
TO-25-AUG-SK-3-01 | 110kV FEEDER - AUGHINISH 110-SEALROCK 110-3 | 16 | 12 | 12 | Scheduled | 14/07/2025 | 29/07/2025
TO-25-CKN-GRO-1-01 | 110kV FEEDER - CLONKEEN 110-GARROW 110-1 | 19 | 15 | 15 | Scheduled | 14/07/2025 | 01/08/2025
TO-25-SK-T103-01 | GENERATOR TRANSFORMER - SEALROCK 110-SEALROCK G3-T103 | 16 | 12 | 12 | Scheduled | 14/07/2025 | 29/07/2025
TO-25-220 kV A2 @ KNR-03 | BUSBAR SECTION - KNOCKANURE 220-KNOCKANURE 220-220A2 | 7 | 5 | 5 | Scheduled | 17/07/2025 | 23/07/2025
TO-25-220 kV B2 @ KNR-03 | BUSBAR SECTION - KNOCKANURE 220-KNOCKANURE 220-220B2 | 7 | 5 | 5 | Scheduled | 17/07/2025 | 23/07/2025
TO-25-KNR-220K2-01 | COUPLER/SECTIONALISING CB - KNOCKANURE 220-KNOCKANURE 220-220K2 | 7 | 5 | 5 | Scheduled | 17/07/2025 | 23/07/2025
TO-25-KNR-220SA1-2CB-04 | COUPLER/SECTIONALISING CB - KNOCKANURE 220-KNOCKANURE 220-220SA1-2CB | 7 | 5 | 5 | Scheduled | 17/07/2025 | 23/07/2025
TO-25-KNR-220SB1-2CB-04 | COUPLER/SECTIONALISING CB - KNOCKANURE 220-KNOCKANURE 220-220SB1-2CB | 7 | 5 | 5 | Scheduled | 17/07/2025 | 23/07/2025
TO-25-CSH-PRO-1-05 | 220kV FEEDER - CASHLA 220-PROSPECT 220-1 | 8 | 6 | 6 | Scheduled | 22/07/2025 | 29/07/2025
TO-25-CKN-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - CLONKEEN 110-CLONKEEN 110-110SA1-2CB | 10 | 8 | 8 | Scheduled | 22/07/2025 | 31/07/2025
TO-25-CKN-CGL-1-01 | 110kV FEEDER - CLONKEEN 110-COOMAGEARLAHY 110-1 | 10 | 8 | 8 | Scheduled | 22/07/2025 | 31/07/2025
TO-25-CGL-110SA1-01 | SECTIONALISING DISCONNECT - COOMAGEARLAHY 110-COOMAGEARLAHY 110-110SA1 | 10 | 8 | 8 | Scheduled | 22/07/2025 | 31/07/2025
TO-25-CGL-110SA2-01 | SECTIONALISING DISCONNECT - COOMAGEARLAHY 110-COOMAGEARLAHY 110-110SA2 | 10 | 8 | 8 | Scheduled | 22/07/2025 | 31/07/2025
TO-25-CGL-GAE-1-01 | 110kV FEEDER - COOMAGEARLAHY 110-GLANLEE 110-1 | 10 | 8 | 8 | Scheduled | 22/07/2025 | 31/07/2025
TO-25-CGL-T121-01 | GENERATOR TRANSFORMER - COOMAGEARLAHY 110-COOMAGEARLAHY 20-T121 | 10 | 8 | 8 | Scheduled | 22/07/2025 | 31/07/2025
TO-25-CGL-T122-01 | GENERATOR TRANSFORMER - COOMAGEARLAHY 110-COOMAGEARLAHY 20-T122 | 10 | 8 | 8 | Scheduled | 22/07/2025 | 31/07/2025
TO-25-GAE-T121-01 | GENERATOR TRANSFORMER - GLANLEE 110-GLANLEE 20-T121 | 10 | 8 | 8 | Scheduled | 22/07/2025 | 31/07/2025
TO-25-KPG-T2101-01 | TRANSFORMER - KILPADDOGE 220-KILPADDOGE 110-T2101 | 2 | 2 | 2 | Scheduled | 22/07/2025 | 23/07/2025
TO-25-220 kV A1 @ MP GIS-02 | BUSBAR SECTION - MONEYPOINT GIS 220-MONEYPOINT GIS 220-220A1 | 8 | 6 | 6 | Scheduled | 22/07/2025 | 29/07/2025
TO-25-220 kV B1 @ MP GIS-02 | BUSBAR SECTION - MONEYPOINT GIS 220-MONEYPOINT GIS 220-220B1 | 8 | 6 | 6 | Scheduled | 22/07/2025 | 29/07/2025
TO-25-MP GIS-220K1-02 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 220-MONEYPOINT GIS 220-220K1 | 8 | 6 | 6 | Scheduled | 22/07/2025 | 29/07/2025
TO-25-MP GIS-220SA1-2CB-04 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 220-MONEYPOINT GIS 220-220SA1-2CB | 8 | 6 | 6 | Scheduled | 22/07/2025 | 29/07/2025
TO-25-MP GIS-220SB1-2CB-04 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 220-MONEYPOINT GIS 220-220SB1-2CB | 8 | 6 | 6 | Scheduled | 22/07/2025 | 29/07/2025
TO-25-MP GIS-PRO-1-01 | 220kV FEEDER - MONEYPOINT GIS 220-PROSPECT 220-1 | 8 | 6 | 6 | Scheduled | 22/07/2025 | 29/07/2025
TO-25-PRO-TB-1-02 | 220kV FEEDER - PROSPECT 220-TARBERT 220-1 | 8 | 6 | 6 | Scheduled | 22/07/2025 | 29/07/2025
TO-25-220 kV A2 @ TB-04 | BUSBAR SECTION - TARBERT 220-TARBERT 220-220A2 | 8 | 6 | 6 | Scheduled | 22/07/2025 | 29/07/2025
TO-25-220 kV B2 @ TB-04 | BUSBAR SECTION - TARBERT 220-TARBERT 220-220B2 | 8 | 6 | 6 | Scheduled | 22/07/2025 | 29/07/2025
TO-25-MTN-MUN-1-01 | 110kV FEEDER - MONETEEN 110-MUNGRET 110-1 | 5 | 5 | 5 | Scheduled | 28/07/2025 | 01/08/2025
TO-25-MP GIS-400K3-02 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 400-MONEYPOINT GIS 400-400K3 | 5 | 5 | 5 | Scheduled | 28/07/2025 | 01/08/2025
TO-25-MUN-T101-01 | TSO CUSTOMER TRANSFORMER - MUNGRET 110-MUNGRET 10-T101 | 5 | 5 | 5 | Reference | 28/07/2025 | 01/08/2025
TO-25-MP GIS-T4201-03 | TRANSFORMER - MONEYPOINT GIS 400-MONEYPOINT GIS 220-T4201 | 10 | 7 | 7 | Scheduled | 30/07/2025 | 08/08/2025
TO-25-220 kV B1 @ KNR-01 | BUSBAR SECTION - KNOCKANURE 220-KNOCKANURE 220-220B1 | 7 | 4 | 4 | Scheduled | 31/07/2025 | 06/08/2025
TO-25-220 kV B2 @ KNR-04 | BUSBAR SECTION - KNOCKANURE 220-KNOCKANURE 220-220B2 | 7 | 4 | 4 | Scheduled | 31/07/2025 | 06/08/2025
TO-25-KNR-220K1-02 | COUPLER/SECTIONALISING CB - KNOCKANURE 220-KNOCKANURE 220-220K1 | 7 | 4 | 4 | Scheduled | 31/07/2025 | 06/08/2025
TO-25-KNR-220K2-05 | COUPLER/SECTIONALISING CB - KNOCKANURE 220-KNOCKANURE 220-220K2 | 7 | 4 | 4 | Scheduled | 31/07/2025 | 06/08/2025
TO-25-KNR-220SB1-2CB-01 | COUPLER/SECTIONALISING CB - KNOCKANURE 220-KNOCKANURE 220-220SB1-2CB | 7 | 4 | 4 | Scheduled | 31/07/2025 | 06/08/2025
TO-25-BVK-CLA-1-01 | 220kV FEEDER - BALLYVOUSKILL 220-CLASHAVOON 220-1 | 11 | 9 | 9 | Scheduled | 05/08/2025 | 15/08/2025
TO-25-CBA-110SA1-01 | SECTIONALISING DISCONNECT - CLOGHBOOLA 110-CLOGHBOOLA 110-110SA1 | 16 | 12 | 12 | Scheduled | 06/08/2025 | 21/08/2025
TO-25-CBA-110SA2-01 | SECTIONALISING DISCONNECT - CLOGHBOOLA 110-CLOGHBOOLA 110-110SA2 | 16 | 12 | 12 | Scheduled | 06/08/2025 | 21/08/2025
TO-25-CBA-T122-01 | DISTRIBUTION TRANSFORMER - CLOGHBOOLA 110-CLOGHBOOLA 20-T122 | 16 | 12 | 12 | Reference | 06/08/2025 | 21/08/2025
TO-25-CBA-T131-01 | GENERATOR TRANSFORMER - CLOGHBOOLA 110-CLOGHBOOLA 33-T131 | 16 | 12 | 12 | Scheduled | 06/08/2025 | 21/08/2025
TO-25-CBA-TRI-1-01 | 110kV FEEDER - CLOGHBOOLA 110-TRIEN 110-1 | 16 | 12 | 12 | Scheduled | 06/08/2025 | 21/08/2025
TO-25-110 kV A2 @ BYH-01 | BUSBAR SECTION - BALLYNAHULLA 110-BALLYNAHULLA 110-110A2 | 19 | 15 | 15 | Scheduled | 11/08/2025 | 29/08/2025
TO-25-110 kV B2 @ BYH-01 | BUSBAR SECTION - BALLYNAHULLA 110-BALLYNAHULLA 110-110B2 | 19 | 15 | 15 | Scheduled | 11/08/2025 | 29/08/2025
TO-25-BYH-110K2-01 | COUPLER/SECTIONALISING CB - BALLYNAHULLA 110-BALLYNAHULLA 110-110K2 | 19 | 15 | 15 | Scheduled | 11/08/2025 | 29/08/2025
TO-25-BYH-110SA1-2CB-03 | COUPLER/SECTIONALISING CB - BALLYNAHULLA 110-BALLYNAHULLA 110-110SA1-2CB | 19 | 15 | 15 | Scheduled | 11/08/2025 | 29/08/2025
TO-25-BYH-110SB1-2CB-03 | COUPLER/SECTIONALISING CB - BALLYNAHULLA 110-BALLYNAHULLA 110-110SB1-2CB | 19 | 15 | 15 | Scheduled | 11/08/2025 | 29/08/2025
TO-25-220 kV B1 @ BYH-01 | BUSBAR SECTION - BALLYNAHULLA 220-BALLYNAHULLA 220-220B1 | 5 | 5 | 5 | Scheduled | 11/08/2025 | 15/08/2025
TO-25-220 kV B2 @ BYH-01 | BUSBAR SECTION - BALLYNAHULLA 220-BALLYNAHULLA 220-220B2 | 5 | 5 | 5 | Scheduled | 11/08/2025 | 15/08/2025
TO-25-BYH-220K1-03 | COUPLER/SECTIONALISING CB - BALLYNAHULLA 220-BALLYNAHULLA 220-220K1 | 5 | 5 | 5 | Scheduled | 11/08/2025 | 15/08/2025
TO-25-BYH-220K2-02 | COUPLER/SECTIONALISING CB - BALLYNAHULLA 220-BALLYNAHULLA 220-220K2 | 5 | 5 | 5 | Scheduled | 11/08/2025 | 15/08/2025
TO-25-BYH-220SB1-2CB-01 | COUPLER/SECTIONALISING CB - BALLYNAHULLA 220-BALLYNAHULLA 220-220SB1-2CB | 5 | 5 | 5 | Scheduled | 11/08/2025 | 15/08/2025
TO-25-BYH-CDL-1-01 | 110kV FEEDER - BALLYNAHULLA 110-CORDAL 110-1 | 19 | 15 | 15 | Scheduled | 11/08/2025 | 29/08/2025
TO-25-CDL-110SA1-01 | SECTIONALISING DISCONNECT - CORDAL 110-CORDAL 110-110SA1 | 19 | 15 | 15 | Scheduled | 11/08/2025 | 29/08/2025
TO-25-CDL-110SA2-01 | SECTIONALISING DISCONNECT - CORDAL 110-CORDAL 110-110SA2 | 19 | 15 | 15 | Scheduled | 11/08/2025 | 29/08/2025
TO-25-CDL-T132-01 | GENERATOR TRANSFORMER - CORDAL 110-CORDAL 33-T132 | 19 | 15 | 15 | Scheduled | 11/08/2025 | 29/08/2025
TO-25-CDL-T141-01 | DISTRIBUTION TRANSFORMER - CORDAL 110-CORDAL 38-T141 | 19 | 15 | 15 | Reference | 11/08/2025 | 29/08/2025
TO-25-KHL-T131-01 | GENERATOR TRANSFORMER - KILL HILL 110-KILL HILL 33-T131 | 9 | 7 | 7 | Scheduled | 11/08/2025 | 19/08/2025
TO-25-400 kV A3 @ MP GIS-01 | BUSBAR SECTION - MONEYPOINT GIS 400-MONEYPOINT GIS 400-400A3 | 5 | 5 | 5 | Scheduled | 11/08/2025 | 15/08/2025
TO-25-400 kV B3 @ MP GIS-01 | BUSBAR SECTION - MONEYPOINT GIS 400-MONEYPOINT GIS 400-400B3 | 5 | 5 | 5 | Scheduled | 11/08/2025 | 15/08/2025
TO-25-MP GIS-400K3-01 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 400-MONEYPOINT GIS 400-400K3 | 5 | 5 | 5 | Scheduled | 11/08/2025 | 15/08/2025
TO-25-MP GIS-400SA1-3CB-02 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 400-MONEYPOINT GIS 400-400SA1-3CB | 5 | 5 | 5 | Scheduled | 11/08/2025 | 15/08/2025
TO-25-MP GIS-400SB1-3CB-02 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 400-MONEYPOINT GIS 400-400SB1-3CB | 5 | 5 | 5 | Scheduled | 11/08/2025 | 15/08/2025
TO-25-SLC-T122-03 | GENERATOR TRANSFORMER - SLIEVECALLAN 110-SLIEVECALLAN 20-T122 | 2 | 2 | 2 | Scheduled | 11/08/2025 | 12/08/2025
TO-25-BYH-T2102-01 | TRANSFORMER - BALLYNAHULLA 220-BALLYNAHULLA 110-T2102 | 2 | 2 | 8 | Scheduled | 13/08/2025 | 14/08/2025
TO-25-AA GIS-110K3-01 | COUPLER/SECTIONALISING CB - ARDNACRUSHA GIS 110-ARDNACRUSHA GIS 110-110K3 | 5 | 5 | 5 | Proposed | 18/08/2025 | 22/08/2025
TO-25-AA GIS-110SA1-3CB-01 | COUPLER/SECTIONALISING CB - ARDNACRUSHA GIS 110-ARDNACRUSHA GIS 110-110SA1-3CB | 5 | 5 | 5 | Proposed | 18/08/2025 | 22/08/2025
TO-25-AA GIS-110SB1-3CB-01 | COUPLER/SECTIONALISING CB - ARDNACRUSHA GIS 110-ARDNACRUSHA GIS 110-110SB1-3CB | 5 | 5 | 5 | Proposed | 18/08/2025 | 22/08/2025
TO-25-AA GIS-CAP1-01 | CAPACITOR/SVC/REACTOR - ARDNACRUSHA GIS 110-ARDNACRUSHA GIS 110-CAP1 | 5 | 5 | 5 | Proposed | 18/08/2025 | 22/08/2025
TO-25-AA GIS-T104-01 | GENERATOR TRANSFORMER - ARDNACRUSHA GIS 110-ARDNACRUSHA GIS G4-T104 | 5 | 5 | 5 | Proposed | 18/08/2025 | 22/08/2025
TO-25-220 kV A1/A2 @ BVK-01 | BUSBAR SECTION - BALLYVOUSKILL 220-BALLYVOUSKILL 220-220A1-A2 | 9 | 7 | 7 | Scheduled | 18/08/2025 | 26/08/2025
TO-25-220 kV B1/B2 @ BVK-01 | BUSBAR SECTION - BALLYVOUSKILL 220-BALLYVOUSKILL 220-220B1-B2 | 9 | 7 | 7 | Scheduled | 18/08/2025 | 26/08/2025
TO-25-BVK-220K1-01 | COUPLER/SECTIONALISING CB - BALLYVOUSKILL 220-BALLYVOUSKILL 220-220K1 | 9 | 7 | 7 | Scheduled | 18/08/2025 | 26/08/2025
TO-25-BVK-220K2-04 | COUPLER/SECTIONALISING CB - BALLYVOUSKILL 220-BALLYVOUSKILL 220-220K2 | 9 | 7 | 7 | Scheduled | 18/08/2025 | 26/08/2025
TO-25-BVK-220SA1-2CB-02 | COUPLER/SECTIONALISING CB - BALLYVOUSKILL 220-BALLYVOUSKILL 220-220SA1-2CB | 9 | 7 | 7 | Scheduled | 18/08/2025 | 26/08/2025
TO-25-BVK-220SB1-2CB-02 | COUPLER/SECTIONALISING CB - BALLYVOUSKILL 220-BALLYVOUSKILL 220-220SB1-2CB | 9 | 7 | 7 | Scheduled | 18/08/2025 | 26/08/2025
TO-25-BOL-ENN-1-01 | 110kV FEEDER - BOOLTIAGH 110-ENNIS 110-1 | 12 | 10 | 10 | Proposed | 18/08/2025 | 29/08/2025
TO-25-CNO-KPG-1-01 | 110kV FEEDER - COOLNANOONAGH 110-KILPADDOGE 110-1 | 5 | 5 | 5 | Proposed | 18/08/2025 | 22/08/2025
TO-25-CNO-T131-01 | GENERATOR TRANSFORMER - COOLNANOONAGH 110-COOLNANOONAGH 33-T131 | 5 | 5 | 5 | Proposed | 18/08/2025 | 22/08/2025
TO-25-220 kV B1 @ MP GIS-03 | BUSBAR SECTION - MONEYPOINT GIS 220-MONEYPOINT GIS 220-220B1 | 5 | 5 | 5 | Scheduled | 18/08/2025 | 22/08/2025
TO-25-220 kV B2 @ MP GIS-02 | BUSBAR SECTION - MONEYPOINT GIS 220-MONEYPOINT GIS 220-220B2 | 5 | 5 | 5 | Scheduled | 18/08/2025 | 22/08/2025
TO-25-MP GIS-220K1-04 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 220-MONEYPOINT GIS 220-220K1 | 5 | 5 | 5 | Scheduled | 18/08/2025 | 22/08/2025
TO-25-MP GIS-220K2-03 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 220-MONEYPOINT GIS 220-220K2 | 5 | 5 | 5 | Scheduled | 18/08/2025 | 22/08/2025
TO-25-MP GIS-220SB1-2CB-01 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 220-MONEYPOINT GIS 220-220SB1-2CB | 5 | 5 | 5 | Scheduled | 18/08/2025 | 22/08/2025
TO-25-220 kV A1 @ TB-02 | BUSBAR SECTION - TARBERT 220-TARBERT 220-220A1 | 4 | 4 | 4 | Proposed | 19/08/2025 | 22/08/2025
TO-25-220 kV A2 @ TB-05 | BUSBAR SECTION - TARBERT 220-TARBERT 220-220A2 | 4 | 4 | 4 | Proposed | 19/08/2025 | 22/08/2025
TO-25-220 kV B1 @ TB-02 | BUSBAR SECTION - TARBERT 220-TARBERT 220-220B1 | 4 | 4 | 4 | Proposed | 19/08/2025 | 22/08/2025
TO-25-220 kV B2 @ TB-05 | BUSBAR SECTION - TARBERT 220-TARBERT 220-220B2 | 4 | 4 | 4 | Proposed | 19/08/2025 | 22/08/2025
TO-25-TB-220K1-2-01 | COUPLER/SECTIONALISING CB - TARBERT 220-TARBERT 220-220K1-2 | 4 | 4 | 4 | Proposed | 19/08/2025 | 22/08/2025
TO-25-BYH-T2101-01 | TRANSFORMER - BALLYNAHULLA 220-BALLYNAHULLA 110-T2101 | 2 | 2 | 2 | Scheduled | 20/08/2025 | 21/08/2025
TO-25-CLH-110SA1-01 | SECTIONALISING DISCONNECT - CLAHANE 110-CLAHANE 110-110SA1 | 5 | 5 | 5 | Proposed | 25/08/2025 | 29/08/2025
TO-25-CLH-110SA2-02 | SECTIONALISING DISCONNECT - CLAHANE 110-CLAHANE 110-110SA2 | 5 | 5 | 5 | Proposed | 25/08/2025 | 29/08/2025
TO-25-CLH-TRL-1-01 | 110kV FEEDER - CLAHANE 110-TRALEE 110-1 | 5 | 5 | 5 | Scheduled | 25/08/2025 | 29/08/2025
TO-25-DRU-CAP2-01 | CAPACITOR/SVC/REACTOR - DRUMLINE 110-DRUMLINE 110-CAP2 | 5 | 5 | 5 | Scheduled | 25/08/2025 | 29/08/2025
TO-25-110 kV A2 @ KNR-01 | BUSBAR SECTION - KNOCKANURE 110-KNOCKANURE 110-110A2 | 12 | 10 | 10 | Proposed | 25/08/2025 | 05/09/2025
TO-25-110 kV B2 @ KNR-01 | BUSBAR SECTION - KNOCKANURE 110-KNOCKANURE 110-110B2 | 12 | 10 | 10 | Proposed | 25/08/2025 | 05/09/2025
TO-25-KNR-110SA1-2CB-02 | COUPLER/SECTIONALISING CB - KNOCKANURE 110-KNOCKANURE 110-110SA1-2CB | 12 | 10 | 10 | Proposed | 25/08/2025 | 05/09/2025
TO-25-KNR-110SA2-4CB-01 | COUPLER/SECTIONALISING CB - KNOCKANURE 110-KNOCKANURE 110-110SA2-4CB | 12 | 10 | 10 | Proposed | 25/08/2025 | 05/09/2025
TO-25-KNR-110SB1-2CB-02 | COUPLER/SECTIONALISING CB - KNOCKANURE 110-KNOCKANURE 110-110SB1-2CB | 12 | 10 | 10 | Proposed | 25/08/2025 | 05/09/2025
TO-25-KNR-110SB2-4CB-01 | COUPLER/SECTIONALISING CB - KNOCKANURE 110-KNOCKANURE 110-110SB2-4CB | 12 | 10 | 10 | Proposed | 25/08/2025 | 05/09/2025
TO-25-220 kV A2 @ KNR-04 | BUSBAR SECTION - KNOCKANURE 220-KNOCKANURE 220-220A2 | 12 | 10 | 10 | Proposed | 25/08/2025 | 05/09/2025
TO-25-220 kV B2 @ KNR-05 | BUSBAR SECTION - KNOCKANURE 220-KNOCKANURE 220-220B2 | 12 | 10 | 10 | Proposed | 25/08/2025 | 05/09/2025
TO-25-KNR-220K2-06 | COUPLER/SECTIONALISING CB - KNOCKANURE 220-KNOCKANURE 220-220K2 | 12 | 10 | 10 | Proposed | 25/08/2025 | 05/09/2025
TO-25-KNR-220SA1-2CB-05 | COUPLER/SECTIONALISING CB - KNOCKANURE 220-KNOCKANURE 220-220SA1-2CB | 12 | 10 | 10 | Proposed | 25/08/2025 | 05/09/2025
TO-25-KNR-220SB1-2CB-05 | COUPLER/SECTIONALISING CB - KNOCKANURE 220-KNOCKANURE 220-220SB1-2CB | 12 | 10 | 10 | Proposed | 25/08/2025 | 05/09/2025
TO-25-KNR-T2102-01 | TRANSFORMER - KNOCKANURE 220-KNOCKANURE 110-T2102 | 12 | 10 | 10 | Proposed | 25/08/2025 | 05/09/2025
TO-25-BVK-GRO-1-01 | 110kV FEEDER - BALLYVOUSKILL 110-GARROW 110-1 | 2 | 2 | 2 | Proposed | 26/08/2025 | 27/08/2025
TO-25-IKE,T-SH-1-08 | 110kV FEEDER - IKERRIN tee-SHANNONBRIDGE 110-1 | 2 | 2 | 2 | Proposed | 27/08/2025 | 28/08/2025
TO-25-110 kV A2 @ KPG-01 | BUSBAR SECTION - KILPADDOGE 110-KILPADDOGE 110-110A2 | 3 | 3 | 3 | Proposed | 27/08/2025 | 29/08/2025
TO-25-KPG-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - KILPADDOGE 110-KILPADDOGE 110-110SA1-2CB | 3 | 3 | 3 | Proposed | 27/08/2025 | 29/08/2025
TO-25-KPG-110SA2-4CB-01 | COUPLER/SECTIONALISING CB - KILPADDOGE 110-KILPADDOGE 110-110SA2-4CB | 3 | 3 | 3 | Proposed | 27/08/2025 | 29/08/2025
TO-25-KPG-T2102-01 | TRANSFORMER - KILPADDOGE 220-KILPADDOGE 110-T2102 | 3 | 3 | 3 | Proposed | 27/08/2025 | 29/08/2025
TO-25-BYH-BVK-1-01 | 220kV FEEDER - BALLYNAHULLA 220-BALLYVOUSKILL 220-1 | 2 | 2 | 2 | Proposed | 28/08/2025 | 29/08/2025
TO-25-AHA-KLN-2-01 | 110kV FEEDER - AHANE 110-KILLONAN 110-2 | 2 | 2 | 2 | Reference (Proposed) | 01/09/2025 | 02/09/2025
TO-25-AHA-T102-01 | DISTRIBUTION TRANSFORMER - AHANE 110-AHANE 10-T102 | 2 | 2 | 2 | Reference (Proposed) | 01/09/2025 | 02/09/2025
TO-25-220 kV A2 @ BVK-01 | BUSBAR SECTION - BALLYVOUSKILL 220-BALLYVOUSKILL 220-220A2 | 5 | 5 | 5 | Scheduled | 01/09/2025 | 05/09/2025
TO-25-220 kV B2 @ BVK-01 | BUSBAR SECTION - BALLYVOUSKILL 220-BALLYVOUSKILL 220-220B2 | 5 | 5 | 5 | Scheduled | 01/09/2025 | 05/09/2025
TO-25-BVK-220K2-03 | COUPLER/SECTIONALISING CB - BALLYVOUSKILL 220-BALLYVOUSKILL 220-220K2 | 5 | 5 | 5 | Scheduled | 01/09/2025 | 05/09/2025
TO-25-BVK-220SA1-2CB-01 | COUPLER/SECTIONALISING CB - BALLYVOUSKILL 220-BALLYVOUSKILL 220-220SA1-2CB | 5 | 5 | 5 | Scheduled | 01/09/2025 | 05/09/2025
TO-25-BVK-220SB1-2CB-01 | COUPLER/SECTIONALISING CB - BALLYVOUSKILL 220-BALLYVOUSKILL 220-220SB1-2CB | 5 | 5 | 5 | Scheduled | 01/09/2025 | 05/09/2025
TO-25-CKN-KER-1-01 | 110kV FEEDER - CLONKEEN 110-KNOCKEARAGH 110-1 | 8 | 6 | 6 | Scheduled | 01/09/2025 | 08/09/2025
TO-25-DRU-ENN-1-01 | 110kV FEEDER - DRUMLINE 110-ENNIS 110-1 | 3 | 3 | 3 | Scheduled | 01/09/2025 | 03/09/2025
TO-25-400 kV A4 @ MP GIS-02 | BUSBAR SECTION - MONEYPOINT GIS 400-MONEYPOINT GIS 400-400A4 | 5 | 5 | 5 | Scheduled | 01/09/2025 | 05/09/2025
TO-25-400 kV B4 @ MP GIS-02 | BUSBAR SECTION - MONEYPOINT GIS 400-MONEYPOINT GIS 400-400B4 | 5 | 5 | 5 | Scheduled | 01/09/2025 | 05/09/2025
TO-25-MP GIS-400K4-02 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 400-MONEYPOINT GIS 400-400K4 | 5 | 5 | 5 | Scheduled | 01/09/2025 | 05/09/2025
TO-25-MP GIS-400SA2-4CB-03 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 400-MONEYPOINT GIS 400-400SA2-4CB | 5 | 5 | 5 | Scheduled | 01/09/2025 | 05/09/2025
TO-25-MP GIS-400SB2-4CB-03 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 400-MONEYPOINT GIS 400-400SB2-4CB | 5 | 5 | 5 | Scheduled | 01/09/2025 | 05/09/2025
TO-25-BYH-GLE-1-03 | 110kV FEEDER - BALLYNAHULLA 110-GLENLARA 110-1 | 2 | 2 | 2 | Proposed | 02/09/2025 | 03/09/2025
TO-25-GLE-110SA1-2CB-03 | COUPLER/SECTIONALISING CB - GLENLARA 110-GLENLARA 110-110SA1-2CB | 2 | 2 | 2 | Proposed | 02/09/2025 | 03/09/2025
TO-25-GLE-KCR-1-02 | 110kV FEEDER - GLENLARA 110-KNOCKACUMMER 110-1 | 2 | 2 | 2 | Proposed | 02/09/2025 | 03/09/2025
TO-25-GLE-T141-02 | DISTRIBUTION TRANSFORMER - GLENLARA 110-GLENLARA 38-T141 | 2 | 2 | 2 | Reference (Proposed) | 02/09/2025 | 03/09/2025
TO-25-KCR-T121-02 | GENERATOR TRANSFORMER - KNOCKACUMMER 110-KNOCKACUMMER 20-T121 | 2 | 2 | 2 | Proposed | 02/09/2025 | 03/09/2025
TO-25-KLN-110K1-2-01 | COUPLER/SECTIONALISING CB - KILLONAN 110-KILLONAN 110-110K1-2 | 2 | 2 | 2 | Scheduled | 03/09/2025 | 04/09/2025
TO-25-KPG-110K3-01 | COUPLER/SECTIONALISING CB - KILPADDOGE 110-KILPADDOGE 110-110K3 | 10 | 8 | 8 | Scheduled | 03/09/2025 | 12/09/2025
TO-25-KPG-110K4-02 | COUPLER/SECTIONALISING CB - KILPADDOGE 110-KILPADDOGE 110-110K4 | 10 | 8 | 8 | Scheduled | 03/09/2025 | 12/09/2025
TO-25-KPG-110SA1-2CB-02 | COUPLER/SECTIONALISING CB - KILPADDOGE 110-KILPADDOGE 110-110SA1-2CB | 10 | 8 | 8 | Scheduled | 03/09/2025 | 12/09/2025
TO-25-KPG-110SA1-3CB-01 | COUPLER/SECTIONALISING CB - KILPADDOGE 110-KILPADDOGE 110-110SA1-3CB | 10 | 8 | 8 | Scheduled | 03/09/2025 | 12/09/2025
TO-25-KPG-110SA2-4CB-02 | COUPLER/SECTIONALISING CB - KILPADDOGE 110-KILPADDOGE 110-110SA2-4CB | 10 | 8 | 8 | Scheduled | 03/09/2025 | 12/09/2025
TO-25-IKE-T141-03 | DISTRIBUTION TRANSFORMER - IKERRIN 110-IKERRIN 38-T141 | 28 | 20 | 20 | Reference (Proposed) | 04/09/2025 | 01/10/2025
TO-25-IKE,T-IKE-1-03 | 110kV FEEDER - IKERRIN tee-IKERRIN 110-1 | 28 | 20 | 20 | Proposed | 04/09/2025 | 01/10/2025
TO-25-IKE,T-SH-1-04 | 110kV FEEDER - IKERRIN tee-SHANNONBRIDGE 110-1 | 28 | 20 |  | Proposed | 04/09/2025 | 01/10/2025
TO-25-IKE,T-THU-1-03 | 110kV FEEDER - IKERRIN tee-THURLES 110-1 | 28 | 20 | 20 | Proposed | 04/09/2025 | 01/10/2025
TO-25-AGL-ENN-1-01 | 110kV FEEDER - AGANNYGAL 110-ENNIS 110-1 | 10 | 8 | 8 | Proposed | 08/09/2025 | 17/09/2025
TO-25-AA GIS-ENN-1-01 | 110kV FEEDER - ARDNACRUSHA GIS 110-ENNIS 110-1 | 10 | 8 | 8 | Scheduled | 08/09/2025 | 17/09/2025
TO-25-AUG-CFM-1-01 | 110kV FEEDER - AUGHINISH 110-CASTLEFARM 110-1 | 12 | 10 | 10 | Scheduled | 08/09/2025 | 19/09/2025
TO-25-CFM-T101-01 | TSO CUSTOMER TRANSFORMER - CASTLEFARM 110-CASTLEFARM 10-T101 | 12 | 10 | 10 | Reference | 08/09/2025 | 19/09/2025
TO-25-ENN-110SA1-2CB-02 | COUPLER/SECTIONALISING CB - ENNIS 110-ENNIS 110-110SA1-2CB | 10 | 8 | 8 | Scheduled | 08/09/2025 | 17/09/2025
TO-25-ENN-SLC-1-02 | 110kV FEEDER - ENNIS 110-SLIEVECALLAN 110-1 | 10 | 8 | 8 | Scheduled | 08/09/2025 | 17/09/2025
TO-25-ENN-T102-01 | DISTRIBUTION TRANSFORMER - ENNIS 110-ENNIS 10-T102 | 10 | 8 | 8 | Reference | 08/09/2025 | 17/09/2025
TO-25-ENN-T142-01 | DISTRIBUTION TRANSFORMER - ENNIS 110-ENNIS 38-T142 | 10 | 8 | 8 | Reference | 08/09/2025 | 17/09/2025
TO-25-KLN-220K1-2-01 | COUPLER/SECTIONALISING CB - KILLONAN 220-KILLONAN 220-220K1-2 | 9 | 7 | 7 | Scheduled | 08/09/2025 | 16/09/2025
TO-25-SLC-110SA1-02 | SECTIONALISING DISCONNECT - SLIEVECALLAN 110-SLIEVECALLAN 110-110SA1 | 10 | 8 | 8 | Scheduled | 08/09/2025 | 17/09/2025
TO-25-SLC-110SA2-02 | SECTIONALISING DISCONNECT - SLIEVECALLAN 110-SLIEVECALLAN 110-110SA2 | 10 | 8 | 8 | Scheduled | 08/09/2025 | 17/09/2025
TO-25-SLC-T121-02 | GENERATOR TRANSFORMER - SLIEVECALLAN 110-SLIEVECALLAN 20-T121 | 10 | 8 | 8 | Scheduled | 08/09/2025 | 17/09/2025
TO-25-SLC-T122-02 | GENERATOR TRANSFORMER - SLIEVECALLAN 110-SLIEVECALLAN 20-T122 | 10 | 8 | 8 | Scheduled | 08/09/2025 | 17/09/2025
TO-25-CLH-110SA1-02 | SECTIONALISING DISCONNECT - CLAHANE 110-CLAHANE 110-110SA1 | 2 | 2 | 2 | Scheduled | 09/09/2025 | 10/09/2025
TO-25-CLH-110SA2-01 | SECTIONALISING DISCONNECT - CLAHANE 110-CLAHANE 110-110SA2 | 2 | 2 | 2 | Scheduled | 09/09/2025 | 10/09/2025
TO-25-CLH-T122-02 | GENERATOR TRANSFORMER - CLAHANE 110-CLAHANE 20-T122 | 2 | 2 | 2 | Scheduled | 09/09/2025 | 10/09/2025
TO-25-CLH-TRI-1-01 | 110kV FEEDER - CLAHANE 110-TRIEN 110-1 | 2 | 2 | 2 | Scheduled | 09/09/2025 | 10/09/2025
TO-25-MP GIS-T4001-02 | GENERATOR TRANSFORMER - MONEYPOINT GIS 400-MONEYPOINT GIS G1-T4001 | 3 | 3 | 3 | Proposed | 09/09/2025 | 11/09/2025
TO-25-BVK-T2102-01 | TRANSFORMER - BALLYVOUSKILL 220-BALLYVOUSKILL 110-T2102 | 2 | 2 | 2 | Proposed | 10/09/2025 | 11/09/2025
TO-25-CHA-KLN-1-03 | 110kV FEEDER - CHARLEVILLE 110-KILLONAN 110-1 | 9 | 7 | 7 | Scheduled | 11/09/2025 | 19/09/2025
TO-25-110 kV A1 @ KLN-02 | BUSBAR SECTION - KILLONAN 110-KILLONAN 110-110A1 | 9 | 7 | 7 | Scheduled | 11/09/2025 | 19/09/2025
TO-25-110 kV B1 @ KLN-02 | BUSBAR SECTION - KILLONAN 110-KILLONAN 110-110B1 | 9 | 7 | 7 | Scheduled | 11/09/2025 | 19/09/2025
TO-25-110 kV A2 @ TB-01 | BUSBAR SECTION - TARBERT 110-TARBERT 110-110A2 | 9 | 7 | 7 | Proposed | 11/09/2025 | 19/09/2025
TO-25-110 kV B2 @ TB-01 | BUSBAR SECTION - TARBERT 110-TARBERT 110-110B2 | 9 | 7 | 7 | Proposed | 11/09/2025 | 19/09/2025
TO-25-220 kV A2 @ TB-03 | BUSBAR SECTION - TARBERT 220-TARBERT 220-220A2 | 9 | 7 | 7 | Proposed | 11/09/2025 | 19/09/2025
TO-25-220 kV B2 @ TB-03 | BUSBAR SECTION - TARBERT 220-TARBERT 220-220B2 | 9 | 7 | 7 | Proposed | 11/09/2025 | 19/09/2025
TO-25-TB-T102-01 | GENERATOR TRANSFORMER - TARBERT 110-TARBERT G2-T102 | 9 | 7 | 7 | Proposed | 11/09/2025 | 19/09/2025
TO-25-TB-T2102-01 | TRANSFORMER - TARBERT 220-TARBERT 110-T2102 | 9 | 7 | 7 | Proposed | 11/09/2025 | 19/09/2025
TO-25-KPG-110K3-03 | COUPLER/SECTIONALISING CB - KILPADDOGE 110-KILPADDOGE 110-110K3 | 12 | 8 | 8 | Scheduled | 13/09/2025 | 24/09/2025
TO-25-KPG-110K4-03 | COUPLER/SECTIONALISING CB - KILPADDOGE 110-KILPADDOGE 110-110K4 | 12 | 8 | 8 | Scheduled | 13/09/2025 | 24/09/2025
TO-25-KPG-110SB1-2CB-01 | COUPLER/SECTIONALISING CB - KILPADDOGE 110-KILPADDOGE 110-110SB1-2CB | 12 | 8 | 8 | Scheduled | 13/09/2025 | 24/09/2025
TO-25-KPG-110SB1-3CB-01 | COUPLER/SECTIONALISING CB - KILPADDOGE 110-KILPADDOGE 110-110SB1-3CB | 12 | 8 | 8 | Scheduled | 13/09/2025 | 24/09/2025
TO-25-KPG-110SB2-4CB-01 | COUPLER/SECTIONALISING CB - KILPADDOGE 110-KILPADDOGE 110-110SB2-4CB | 12 | 8 | 8 | Scheduled | 13/09/2025 | 24/09/2025
TO-25-KLN-KPG-1-03 | 220kV FEEDER - KILLONAN 220-KILPADDOGE 220-1 | 12 | 10 | 10 | Proposed | 15/09/2025 | 26/09/2025
TO-25-KLN-KPG-1-04 | 220kV FEEDER - KILLONAN 220-KILPADDOGE 220-1 | 12 | 10 | 10 | Scheduled | 15/09/2025 | 26/09/2025
TO-25-220 kV A1/A2 @ KNR-01 | BUSBAR SECTION - KNOCKANURE 220-KNOCKANURE 220-220A1-A2 | 8 | 6 | 6 | Scheduled | 16/09/2025 | 23/09/2025
TO-25-KNR-220K1-01 | COUPLER/SECTIONALISING CB - KNOCKANURE 220-KNOCKANURE 220-220K1 | 8 | 6 | 6 | Scheduled | 16/09/2025 | 23/09/2025
TO-25-KNR-220K2-04 | COUPLER/SECTIONALISING CB - KNOCKANURE 220-KNOCKANURE 220-220K2 | 8 | 6 | 6 | Scheduled | 16/09/2025 | 23/09/2025
TO-25-KNR-220SA1-2CB-01 | COUPLER/SECTIONALISING CB - KNOCKANURE 220-KNOCKANURE 220-220SA1-2CB | 8 | 6 | 6 | Scheduled | 16/09/2025 | 23/09/2025
TO-25-TRL-CAP2-03 | CAPACITOR/SVC/REACTOR - TRALEE 110-TRALEE 110-CAP2 | 2 | 2 | 2 | Scheduled | 17/09/2025 | 18/09/2025
TO-25-CSH-PRO-1-01 | 220kV FEEDER - CASHLA 220-PROSPECT 220-1 | 57 | 40 | 40 | Proposed | 22/09/2025 | 17/11/2025
TO-25-CSH-PRO-1-02 | 220kV FEEDER - CASHLA 220-PROSPECT 220-1 | Unknown | Unknown | 40 | Planned | September | November
TO-25-KLN-LIM-2-03 | 110kV FEEDER - KILLONAN 110-LIMERICK 110-2 | 9 | 7 | 7 | Scheduled | 22/09/2025 | 30/09/2025
TO-25-400 kV A3 @ MP GIS-02 | BUSBAR SECTION - MONEYPOINT GIS 400-MONEYPOINT GIS 400-400A3 | 10 | 8 | 8 | Scheduled | 23/09/2025 | 02/10/2025
TO-25-400 kV B3 @ MP GIS-02 | BUSBAR SECTION - MONEYPOINT GIS 400-MONEYPOINT GIS 400-400B3 | 10 | 8 | 8 | Scheduled | 23/09/2025 | 02/10/2025
TO-25-MP GIS-400K3-03 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 400-MONEYPOINT GIS 400-400K3 | 10 | 8 | 8 | Scheduled | 23/09/2025 | 02/10/2025
TO-25-MP GIS-400SA1-3CB-03 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 400-MONEYPOINT GIS 400-400SA1-3CB | 10 | 8 | 8 | Scheduled | 23/09/2025 | 02/10/2025
TO-25-MP GIS-400SB1-3CB-03 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 400-MONEYPOINT GIS 400-400SB1-3CB | 10 | 8 | 8 | Scheduled | 23/09/2025 | 02/10/2025
TO-25-MP GIS-T4003-02 | GENERATOR TRANSFORMER - MONEYPOINT GIS 400-MONEYPOINT GIS G3-T4003 | 10 | 8 | 8 | Scheduled | 23/09/2025 | 02/10/2025
TO-25-REM-110SA1-01 | SECTIONALISING DISCONNECT - REAMORE 110-REAMORE 110-110SA1 | 26 | 20 | 20 | Proposed | 29/09/2025 | 24/10/2025
TO-25-REM-110SA2-01 | SECTIONALISING DISCONNECT - REAMORE 110-REAMORE 110-110SA2 | 26 | 20 | 20 | Proposed | 29/09/2025 | 24/10/2025
TO-25-REM-T141-01 | DISTRIBUTION TRANSFORMER - REAMORE 110-REAMORE 38-T141 | 26 | 20 | 20 | Reference (Proposed) | 29/09/2025 | 24/10/2025
TO-25-REM-T142-01 | DISTRIBUTION TRANSFORMER - REAMORE 110-REAMORE 38-T142 | 26 | 20 | 20 | Reference (Proposed) | 29/09/2025 | 24/10/2025
TO-25-REM-TRL-1-01 | 110kV FEEDER - REAMORE 110-TRALEE 110-1 | 26 | 20 | 20 | Proposed | 29/09/2025 | 24/10/2025
TO-25-IKE,T-THU-1-07 | 110kV FEEDER - IKERRIN tee-THURLES 110-1 | 2 | 2 | 2 | Proposed | 02/10/2025 | 03/10/2025
TO-25-LSN-110SA1-2-01 | SECTIONALISING DISCONNECT - LISHEEN 110-LISHEEN 110-110SA1-2 | 2 | 2 | 2 | Proposed | 02/10/2025 | 03/10/2025
TO-25-LSN-110SA2-4-01 | SECTIONALISING DISCONNECT - LISHEEN 110-LISHEEN 110-110SA2-4 | 2 | 2 | 2 | Proposed | 02/10/2025 | 03/10/2025
TO-25-LSN-T122-01 | GENERATOR TRANSFORMER - LISHEEN 110-LISHEEN 20-T122 | 2 | 2 | 2 | Proposed | 02/10/2025 | 03/10/2025
TO-25-LSN-T131-02 | GENERATOR TRANSFORMER - LISHEEN 110-LISHEEN 33-T131 | 2 | 2 | 2 | Proposed | 02/10/2025 | 03/10/2025
TO-25-LSN-T142-01 | DISTRIBUTION TRANSFORMER - LISHEEN 110-LISHEEN 38-T142 | 2 | 2 | 2 | Reference (Proposed) | 02/10/2025 | 03/10/2025
TO-25-LSN-THU-1-01 | 110kV FEEDER - LISHEEN 110-THURLES 110-1 | 2 | 2 | 2 | Proposed | 02/10/2025 | 03/10/2025
TO-25-THU-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - THURLES 110-THURLES 110-110SA1-2CB | 2 | 2 | 2 | Proposed | 02/10/2025 | 03/10/2025
TO-25-THU-STATCOM-01 | CAPACITOR/SVC/REACTOR - THURLES 110-THURLES 110-STATCOM | 2 | 2 | 2 | Proposed | 02/10/2025 | 03/10/2025
TO-25-THU-T142-01 | DISTRIBUTION TRANSFORMER - THURLES 110-THURLES 38-T142 | 2 | 2 | 2 | Reference (Proposed) | 02/10/2025 | 03/10/2025
TO-25-MP GIS-400SA1-2CB-01 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 400-MONEYPOINT GIS 400-400SA1-2CB | Unknown | Unknown | 5 | Planned | October | October
TO-25-IKE-T141-05 | DISTRIBUTION TRANSFORMER - IKERRIN 110-IKERRIN 38-T141 | 2 | 2 | 2 | Reference (Proposed) | 06/10/2025 | 07/10/2025
TO-25-IKE,T-IKE-1-05 | 110kV FEEDER - IKERRIN tee-IKERRIN 110-1 | 2 | 2 | 2 | Proposed | 06/10/2025 | 07/10/2025
TO-25-IKE,T-SH-1-07 | 110kV FEEDER - IKERRIN tee-SHANNONBRIDGE 110-1 | 2 | 2 | 2 | Proposed | 06/10/2025 | 07/10/2025
TO-25-IKE,T-THU-1-08 | 110kV FEEDER - IKERRIN tee-THURLES 110-1 | 2 | 2 | 2 | Proposed | 06/10/2025 | 07/10/2025
TO-25-MP GIS-400SA1-3CB-01 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 400-MONEYPOINT GIS 400-400SA1-3CB | Unknown | Unknown | 2 | Planned | October | October
TO-25-MP GIS-400SA2-4CB-02 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 400-MONEYPOINT GIS 400-400SA2-4CB | Unknown | Unknown | 5 | Planned | October | October
TO-25-MP GIS-400SB1-2CB-01 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 400-MONEYPOINT GIS 400-400SB1-2CB | Unknown | Unknown | 5 | Planned | October | October
TO-25-KNR-TRI-2-01 | 110kV FEEDER - KNOCKANURE 110-TRIEN 110-2 | Unknown | Unknown | 3 | Planned | October | October
TO-25-TRI-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - TRIEN 110-TRIEN 110-110SA1-2CB | Unknown | Unknown | 3 | Planned | October | October
TO-25-TRI-T142-01 | DISTRIBUTION TRANSFORMER - TRIEN 110-TRIEN 38-T142 | Unknown | Unknown | 3 | Reference (Planned) | October | October
TO-25-MP GIS-400SB1-3CB-01 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 400-MONEYPOINT GIS 400-400SB1-3CB | Unknown | Unknown | 5 | Planned | October | November
TO-25-MP GIS-400SB2-4CB-02 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 400-MONEYPOINT GIS 400-400SB2-4CB | Unknown | Unknown | 5 | Planned | November | November

## GEN_SouthEast
Outage ID | Feeder ID | Calendar Day Duration | Working Day Duration | Work Days | Outage Status | Start | Finish
TO-25-GI-T141-01 | DISTRIBUTION TRANSFORMER - GREAT ISLAND 110-GREAT ISLAND 38-T141 | 639 | 446 | 446 | Reference | 02/04/2024 | 31/12/2025
TO-25-CUS-PLS-1-01 | 110kV FEEDER - CUSHALING 110-PORTLAOISE 110-1 | 222 | 151 | 151 | Scheduled | 11/12/2024 | 20/07/2025
TO-25-110 kV A2 @ PLS-01 | BUSBAR SECTION - PORTLAOISE 110-PORTLAOISE 110-110A2 | 128 | 89 |  | Scheduled | 11/12/2024 | 17/04/2025
TO-25-110 kV B2 @ PLS-01 | BUSBAR SECTION - PORTLAOISE 110-PORTLAOISE 110-110B2 | 128 | 89 |  | Scheduled | 11/12/2024 | 17/04/2025
TO-25-ARK-SHE-2-01 | 110kV FEEDER - ARKLOW 110-SHELTON ABBEY 110-2 | 15 | 10 | 10 | Scheduled | 23/12/2024 | 06/01/2025
TO-25-SHE-T102-01 | TSO CUSTOMER TRANSFORMER - SHELTON ABBEY 110-SHELTON ABBEY 10-T102 | 15 | 10 | 10 | Scheduled | 23/12/2024 | 06/01/2025
TO-25-GI GIS-220K1-01 | COUPLER/SECTIONALISING CB - GREAT ISLAND GIS 220-GREAT ISLAND GIS 220-220K1 | 1 | 1 | 1 | Scheduled | 08/01/2025 | 08/01/2025
TO-25-CUS-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - CUSHALING 110-CUSHALING 110-110SA1-2CB | 1 | 1 | 1 | Scheduled | 14/01/2025 | 14/01/2025
TO-25-CUS-KIR-1-01 | 110kV FEEDER - CUSHALING 110-KILCUMBER 110-1 | 1 | 1 | 1 | Scheduled | 14/01/2025 | 14/01/2025
TO-25-CUS-MLC-1-01 | 110kV FEEDER - CUSHALING 110-MOUNTLUCAS 110-1 | 1 | 1 | 1 | Scheduled | 14/01/2025 | 14/01/2025
TO-25-CUS-T101-01 | GENERATOR TRANSFORMER - CUSHALING 110-CUSHALING G1-T101 | 1 | 1 | 1 | Scheduled | 14/01/2025 | 14/01/2025
TO-25-KIR-T131-02 | GENERATOR TRANSFORMER - KILCUMBER 110-KILCUMBER 33-T131 | 1 | 1 | 1 | Scheduled | 14/01/2025 | 14/01/2025
TO-25-BAR,T-CAH-1-01 | 110kV FEEDER - BARRYMORE tee-CAHIR 110-1 | 19 | 15 | 15 | Scheduled | 10/02/2025 | 28/02/2025
TO-25-BAR,T-CAH-1-02 | 110kV FEEDER - BARRYMORE tee-CAHIR 110-1 | 19 | 15 | 15 | Proposed | 10/02/2025 | 28/02/2025
TO-25-ROP-WEX-1-01 | 110kV FEEDER - ROSSPILE 110-WEXFORD 110-1 | 7 | 5 |  | Scheduled | 12/02/2025 | 18/02/2025
TO-25-WEX-110SA1-2CB-03 | COUPLER/SECTIONALISING CB - WEXFORD 110-WEXFORD 110-110SA1-2CB | 7 | 5 |  | Scheduled | 12/02/2025 | 18/02/2025
TO-25-WEX-T121-01 | DISTRIBUTION TRANSFORMER - WEXFORD 110-WEXFORD 20-T121 | 7 | 5 | 5 | Reference | 12/02/2025 | 18/02/2025
TO-25-WEX-T141-01 | DISTRIBUTION TRANSFORMER - WEXFORD 110-WEXFORD 38-T141 | 7 | 5 | 5 | Reference | 12/02/2025 | 18/02/2025
TO-25-110 kV B2 @ CAH-01 | BUSBAR SECTION - CAHIR 110-CAHIR 110-110B2 | 12 | 10 | 10 | Scheduled | 17/02/2025 | 28/02/2025
TO-25-110 kV B2 @ GI-02 | BUSBAR SECTION - GREAT ISLAND 110-GREAT ISLAND 110-110B2 | 10 | 8 | 8 | Scheduled | 19/02/2025 | 28/02/2025
TO-25-GI-ROP-1-01 | 110kV FEEDER - GREAT ISLAND 110-ROSSPILE 110-1 | 10 | 8 |  | Scheduled | 19/02/2025 | 28/02/2025
TO-25-BAR,T-CAH-1-03 | 110kV FEEDER - BARRYMORE tee-CAHIR 110-1 | 3 | 3 | 3 | Scheduled | 12/03/2025 | 14/03/2025
TO-25-KTN-110SA1-01 | SECTIONALISING DISCONNECT - KILLOTERAN 110-KILLOTERAN 110-110SA1 | 74 | 51 | 51 | Scheduled | 18/03/2025 | 30/05/2025
TO-25-KTN-110SA2-01 | SECTIONALISING DISCONNECT - KILLOTERAN 110-KILLOTERAN 110-110SA2 | 74 | 51 | 51 | Scheduled | 18/03/2025 | 30/05/2025
TO-25-KTN-T102-01 | DISTRIBUTION TRANSFORMER - KILLOTERAN 110-KILLOTERAN 10-T102 | 74 | 51 | 51 | Reference | 18/03/2025 | 30/05/2025
TO-25-KTN-WAT-1-03 | 110kV FEEDER - KILLOTERAN 110-WATERFORD 110-1 | 74 | 51 | 51 | Scheduled | 18/03/2025 | 30/05/2025
TO-25-KRA-WOH-1-03 | 110kV FEEDER - KNOCKRAHA 110-WOODHOUSE 110-1 | 3 | 3 | 3 | Scheduled | 18/03/2025 | 20/03/2025
TO-25-GI GIS-KLS-1-02 | 220kV FEEDER - GREAT ISLAND GIS 220-KELLIS 220-1 | 2 | 0 | 0 | Scheduled | 22/03/2025 | 23/03/2025
TO-25-WOH-T122-01 | GENERATOR TRANSFORMER - WOODHOUSE 110-WOODHOUSE 20-T122 | 5 | 5 | 5 | Scheduled | 31/03/2025 | 04/04/2025
TO-25-ROP-110K1-01 | COUPLER/SECTIONALISING CB - ROSSPILE 110-ROSSPILE 110-110K1 | 1 | 1 | 1 | Scheduled | 02/04/2025 | 02/04/2025
TO-25-BOG-TTU-1-01 | 110kV FEEDER - BANOGE 110-TULLABEG 110-1 | 4 | 4 | 4 | Scheduled | 08/04/2025 | 11/04/2025
TO-25-GI GIS-LON-1-01 | 220kV FEEDER - GREAT ISLAND GIS 220-LOUGHTOWN 220-1 | 3 | 3 | 3 | Scheduled | 08/04/2025 | 10/04/2025
TO-25-LON-T2401-01 | TRANSFORMER - LOUGHTOWN 400-LOUGHTOWN 220-T2401 | 3 | 3 | 3 | Scheduled | 08/04/2025 | 10/04/2025
TO-25-TTU-131-02 | GENERATOR TRANSFORMER - TULLABEG 110-TULLABEG 33-T131 | 1 | 1 | 1 | Scheduled | 08/04/2025 | 08/04/2025
TO-25-220 kV A1 @ ARK-01 | BUSBAR SECTION - ARKLOW 220-ARKLOW 220-220A1 | 4 | 4 | 4 | Scheduled | 22/04/2025 | 25/04/2025
TO-25-220 kV A2 @ ARK-01 | BUSBAR SECTION - ARKLOW 220-ARKLOW 220-220A2 | 4 | 4 | 4 | Scheduled | 22/04/2025 | 25/04/2025
TO-25-220 kV B1 @ ARK-01 | BUSBAR SECTION - ARKLOW 220-ARKLOW 220-220B1 | 4 | 4 | 4 | Scheduled | 22/04/2025 | 25/04/2025
TO-25-220 kV B2 @ ARK-01 | BUSBAR SECTION - ARKLOW 220-ARKLOW 220-220B2 | 4 | 4 | 4 | Scheduled | 22/04/2025 | 25/04/2025
TO-25-ARK-220K1-2-01 | COUPLER/SECTIONALISING CB - ARKLOW 220-ARKLOW 220-220K1-2 | 4 | 4 | 4 | Scheduled | 22/04/2025 | 25/04/2025
TO-25-ROP-T131-01 | GENERATOR TRANSFORMER - ROSSPILE 110-ROSSPILE 33-T131 | 1 | 1 | 1 | Scheduled | 23/04/2025 | 23/04/2025
TO-25-KLS-220K1-2-01 | COUPLER/SECTIONALISING CB - KELLIS 220-KELLIS 220-220K1-2 | 1 | 1 | 1 | Scheduled | 24/04/2025 | 24/04/2025
TO-25-STN-T131-02 | GENERATOR TRANSFORMER - STONESTOWN 110-STONESTOWN 33-T131 | 1 | 1 | 1 | Scheduled | 24/04/2025 | 24/04/2025
TO-25-CAH-110K1-2-01 | COUPLER/SECTIONALISING CB - CAHIR 110-CAHIR 110-110K1-2 | 79 | 55 | 55 | Scheduled | 28/04/2025 | 15/07/2025
TO-25-CRA-WEX-1-02 | 110kV FEEDER - CRANE 110-WEXFORD 110-1 | 143 | 100 | 100 | Scheduled | 30/04/2025 | 19/09/2025
TO-25-GI GIS-220K2-02 | COUPLER/SECTIONALISING CB - GREAT ISLAND GIS 220-GREAT ISLAND GIS 220-220K2 | 2 | 2 | 2 | Scheduled | 07/05/2025 | 08/05/2025
TO-25-GI GIS-220SA1-2CB-01 | COUPLER/SECTIONALISING CB - GREAT ISLAND GIS 220-GREAT ISLAND GIS 220-220SA1-2CB | 2 | 2 | 2 | Scheduled | 07/05/2025 | 08/05/2025
TO-25-BDA-T101-01 | TSO CUSTOMER TRANSFORMER - BARODA 110-BARODA 10-T101 | 5 | 5 | 5 | Scheduled | 12/05/2025 | 16/05/2025
TO-25-CRA-LWD-1-05 | 110kV FEEDER - CRANE 110-LODGEWOOD 110-1 | 19 | 15 | 15 | Scheduled | 12/05/2025 | 30/05/2025
TO-25-PLS-T141-01 | DISTRIBUTION TRANSFORMER - PORTLAOISE 110-PORTLAOISE 38-T141 | 40 | 29 | 29 | Reference | 12/05/2025 | 20/06/2025
TO-25-DSN-KLS-1-03 | 220kV FEEDER - DUNSTOWN 220-KELLIS 220-1 | 2 | 2 | 2 | Scheduled | 15/05/2025 | 16/05/2025
TO-25-GI-WAT-2-04 | 110kV FEEDER - GREAT ISLAND 110-WATERFORD 110-2 | 15 | 11 | 11 | Scheduled | 16/05/2025 | 30/05/2025
TO-25-WAT-110SA1-02 | SECTIONALISING DISCONNECT - WATERFORD 110-WATERFORD 110-110SA1 | 15 | 11 | 11 | Scheduled | 16/05/2025 | 30/05/2025
TO-25-WAT-110SA2-02 | SECTIONALISING DISCONNECT - WATERFORD 110-WATERFORD 110-110SA2 | 15 | 11 | 11 | Scheduled | 16/05/2025 | 30/05/2025
TO-25-WAT-T141-01 | DISTRIBUTION TRANSFORMER - WATERFORD 110-WATERFORD 38-T141 | 15 | 11 | 11 | Reference | 16/05/2025 | 30/05/2025
TO-25-BOT-MLC-1-01 | 110kV FEEDER - BOGTOWN 110-MOUNTLUCAS 110-1 | 22 | 15 | 15 | Scheduled | 19/05/2025 | 09/06/2025
TO-25-BOT-T132-01 | GENERATOR TRANSFORMER - BOGTOWN 110-BOGTOWN 33-T132 | 22 | 15 | 15 | Scheduled | 19/05/2025 | 09/06/2025
TO-25-WEX-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - WEXFORD 110-WEXFORD 110-110SA1-2CB | 12 | 10 | 10 | Scheduled | 19/05/2025 | 30/05/2025
TO-25-WEX-CAP2-01 | CAPACITOR/SVC/REACTOR - WEXFORD 110-WEXFORD 110-CAP2 | 12 | 10 | 10 | Scheduled | 19/05/2025 | 30/05/2025
TO-25-WEX-CAP4-01 | CAPACITOR/SVC/REACTOR - WEXFORD 110-WEXFORD 110-CAP4 | 12 | 10 | 10 | Scheduled | 19/05/2025 | 30/05/2025
TO-25-WEX-T122-01 | DISTRIBUTION TRANSFORMER - WEXFORD 110-WEXFORD 20-T122 | 12 | 10 | 10 | Reference | 19/05/2025 | 30/05/2025
TO-25-WEX-T142-01 | DISTRIBUTION TRANSFORMER - WEXFORD 110-WEXFORD 38-T142 | 12 | 10 | 10 | Reference | 19/05/2025 | 30/05/2025
TO-25-BDA-MON-1-01 | 110kV FEEDER - BARODA 110-MONREAD 110-1 | 3 | 3 | 3 | Scheduled | 20/05/2025 | 22/05/2025
TO-25-TTU-131-03 | GENERATOR TRANSFORMER - TULLABEG 110-TULLABEG 33-T131 | 1 | 1 | 1 | Scheduled | 29/05/2025 | 29/05/2025
TO-25-BUT-KTN-1-04 | 110kV FEEDER - BUTLERSTOWN 110-KILLOTERAN 110-1 | 71 | 50 | 50 | Scheduled | 03/06/2025 | 12/08/2025
TO-25-CDK-LWD-1-02 | 110kV FEEDER - CASTLEDOCKRELL 110-LODGEWOOD 110-1 | 4 | 4 | 4 | Scheduled | 03/06/2025 | 06/06/2025
TO-25-CDK-T121-02 | GENERATOR TRANSFORMER - CASTLEDOCKRELL 110-CASTLEDOCKRELL 20-T121 | 4 | 4 | 4 | Reference | 03/06/2025 | 06/06/2025
TO-25-KTN-110SA1-02 | SECTIONALISING DISCONNECT - KILLOTERAN 110-KILLOTERAN 110-110SA1 | 71 | 50 | 50 | Scheduled | 03/06/2025 | 12/08/2025
TO-25-KTN-110SA2-02 | SECTIONALISING DISCONNECT - KILLOTERAN 110-KILLOTERAN 110-110SA2 | 71 | 50 | 50 | Scheduled | 03/06/2025 | 12/08/2025
TO-25-KTN-T101-01 | DISTRIBUTION TRANSFORMER - KILLOTERAN 110-KILLOTERAN 10-T101 | 71 | 50 | 50 | Reference | 03/06/2025 | 12/08/2025
TO-25-CUS-110SA1-2CB-02 | COUPLER/SECTIONALISING CB - CUSHALING 110-CUSHALING 110-110SA1-2CB | 2 | 2 | 2 | Scheduled | 05/06/2025 | 06/06/2025
TO-25-CUS-KIR-1-02 | 110kV FEEDER - CUSHALING 110-KILCUMBER 110-1 | 2 | 2 | 2 | Scheduled | 05/06/2025 | 06/06/2025
TO-25-CUS-MLC-1-02 | 110kV FEEDER - CUSHALING 110-MOUNTLUCAS 110-1 | 2 | 2 | 2 | Scheduled | 05/06/2025 | 06/06/2025
TO-25-CUS-T101-02 | GENERATOR TRANSFORMER - CUSHALING 110-CUSHALING G1-T101 | 2 | 2 | 2 | Scheduled | 05/06/2025 | 06/06/2025
TO-25-KIR-T131-03 | GENERATOR TRANSFORMER - KILCUMBER 110-KILCUMBER 33-T131 | 2 | 2 | 2 | Scheduled | 05/06/2025 | 06/06/2025
TO-25-BOT-T132-03 | GENERATOR TRANSFORMER - BOGTOWN 110-BOGTOWN 33-T132 | 1 | 1 | 1 | Scheduled | 09/06/2025 | 09/06/2025
TO-25-220 kV B1 @ CUL-01 | BUSBAR SECTION - CULLENAGH 220-CULLENAGH 220-220B1 | 3 | 3 | 3 | Scheduled | 09/06/2025 | 11/06/2025
TO-25-CUL-GI GIS-1-01 | 220kV FEEDER - CULLENAGH 220-GREAT ISLAND GIS 220-1 | 3 | 3 | 3 | Scheduled | 09/06/2025 | 11/06/2025
TO-25-CUS-NEW-1-05 | 110kV FEEDER - CUSHALING 110-NEWBRIDGE 110-1 | 3 | 3 | 3 | Scheduled | 09/06/2025 | 11/06/2025
TO-25-220 kV A1 @ CUL-01 | BUSBAR SECTION - CULLENAGH 220-CULLENAGH 220-220A1 | 2 | 2 | 2 | Scheduled | 12/06/2025 | 13/06/2025
TO-25-CUL-T2101-03 | TRANSFORMER - CULLENAGH 220-CULLENAGH 110-T2101 | 2 | 2 | 2 | Scheduled | 12/06/2025 | 13/06/2025
TO-25-KIR-T131-04 | GENERATOR TRANSFORMER - KILCUMBER 110-KILCUMBER 33-T131 | 2 | 2 | 2 | Scheduled | 25/06/2025 | 26/06/2025
TO-25-KLS-110K1-2-05 | COUPLER/SECTIONALISING CB - KELLIS 110-KELLIS 110-110K1-2 | 9 | 7 | 7 | Scheduled | 30/06/2025 | 08/07/2025
TO-25-MAY-SH-1-03 | 220kV FEEDER - MAYNOOTH 220-SHANNONBRIDGE 220-1 | 136 | 96 | 96 | Scheduled | 02/07/2025 | 14/11/2025
TO-25-WEX-110SA1-2CB-02 | COUPLER/SECTIONALISING CB - WEXFORD 110-WEXFORD 110-110SA1-2CB | 12 | 10 | 10 | Scheduled | 07/07/2025 | 18/07/2025
TO-25-WEX-CAP2-02 | CAPACITOR/SVC/REACTOR - WEXFORD 110-WEXFORD 110-CAP2 | 12 | 10 | 10 | Scheduled | 07/07/2025 | 18/07/2025
TO-25-WEX-CAP4-02 | CAPACITOR/SVC/REACTOR - WEXFORD 110-WEXFORD 110-CAP4 | 12 | 10 | 10 | Scheduled | 07/07/2025 | 18/07/2025
TO-25-WEX-T122-02 | DISTRIBUTION TRANSFORMER - WEXFORD 110-WEXFORD 20-T122 | 12 | 10 | 10 | Reference | 07/07/2025 | 18/07/2025
TO-25-WEX-T142-02 | DISTRIBUTION TRANSFORMER - WEXFORD 110-WEXFORD 38-T142 | 12 | 10 | 10 | Reference | 07/07/2025 | 18/07/2025
TO-25-BDN-MRK1-02 | TSO CUSTOMER TRANSFORMER - BALLYDINE 110-BALLYDINE 10-MRK1 | 21 | 15 | 15 | Scheduled | 09/07/2025 | 29/07/2025
TO-25-PLS-110K1-2-03 | COUPLER/SECTIONALISING CB - PORTLAOISE 110-PORTLAOISE 110-110K1-2 | 21 | 15 | 15 | Scheduled | 09/07/2025 | 29/07/2025
TO-25-PLS-T141-02 | DISTRIBUTION TRANSFORMER - PORTLAOISE 110-PORTLAOISE 38-T141 | 52 | 37 | 37 | Reference | 09/07/2025 | 29/08/2025
TO-25-CUS-T101-04 | GENERATOR TRANSFORMER - CUSHALING 110-CUSHALING G1-T101 | 2 | 2 | 2 | Scheduled | 10/07/2025 | 11/07/2025
TO-25-STR-T141-02 | DISTRIBUTION TRANSFORMER - STRATFORD 110-STRATFORD 38-T141 | 16 | 12 | 12 | Reference | 17/07/2025 | 01/08/2025
TO-25-STR,T-CLW-1-02 | 110kV FEEDER - STRATFORD tee-CARLOW 110-1 | 16 | 12 | 12 | Scheduled | 17/07/2025 | 01/08/2025
TO-25-STR,T-PA-1-02 | 110kV FEEDER - STRATFORD tee-POLLAPHUCA 110-1 | 16 | 12 | 12 | Scheduled | 17/07/2025 | 01/08/2025
TO-25-STR,T-STR-1-02 | 110kV FEEDER - STRATFORD tee-STRATFORD 110-1 | 16 | 12 | 12 | Scheduled | 17/07/2025 | 01/08/2025
TO-25-DEY-PLS-1-01 | 110kV FEEDER - DERRYCARNEY 110-PORTLAOISE 110-1 | 3 | 1 | 1 | Scheduled | 18/07/2025 | 20/07/2025
TO-25-110 kV A2 @ PLS-05 | BUSBAR SECTION - PORTLAOISE 110-PORTLAOISE 110-110A2 | 3 | 1 | 1 | Scheduled | 18/07/2025 | 20/07/2025
TO-25-ATY-T102-02 | DISTRIBUTION TRANSFORMER - ATHY 110-ATHY 10-T102 | 10 | 8 | 8 | Reference | 21/07/2025 | 30/07/2025
TO-25-ATY-T102-03 | DISTRIBUTION TRANSFORMER - ATHY 110-ATHY 10-T102 | 2 | 2 | 2 | Reference | 21/07/2025 | 22/07/2025
TO-25-ATY-PLS-1-02 | 110kV FEEDER - ATHY 110-PORTLAOISE 110-1 | 71 | 50 | 50 | Scheduled | 22/07/2025 | 30/09/2025
TO-25-ROP-T131-02 | GENERATOR TRANSFORMER - ROSSPILE 110-ROSSPILE 33-T131 | 2 | 2 | 2 | Scheduled | 22/07/2025 | 23/07/2025
TO-25-CUS-T103/5-01 | GENERATOR TRANSFORMER - CUSHALING 110-CUSHALING G3/5-T103/5 | 15 | 10 | 10 | Scheduled | 29/07/2025 | 12/08/2025
TO-25-CAH-CAP2/4-01 | CAPACITOR/SVC/REACTOR - CAHIR 110-CAHIR 110-CAP2/4 | 4 | 4 | 4 | Scheduled | 05/08/2025 | 08/08/2025
TO-25-CLW-KLS-1-08 | 110kV FEEDER - CARLOW 110-KELLIS 110-1 | 3 | 3 | 3 | Scheduled | 05/08/2025 | 07/08/2025
TO-25-110 kV A1 @ KLS-01 | BUSBAR SECTION - KELLIS 110-KELLIS 110-110A1 | 3 | 3 | 3 | Scheduled | 05/08/2025 | 07/08/2025
TO-25-110 kV A1 @ PLS-02 | BUSBAR SECTION - PORTLAOISE 110-PORTLAOISE 110-110A1 | 4 | 4 | 4 | Scheduled | 05/08/2025 | 08/08/2025
TO-25-110 kV B1 @ PLS-01 | BUSBAR SECTION - PORTLAOISE 110-PORTLAOISE 110-110B1 | 4 | 4 | 4 | Scheduled | 05/08/2025 | 08/08/2025
TO-25-BOG-T122-01 | DISTRIBUTION TRANSFORMER - BANOGE 110-BANOGE 20-T122 | 2 | 2 | 2 | Reference | 07/08/2025 | 08/08/2025
TO-25-ATY-110SA1-01 | SECTIONALISING DISCONNECT - ATHY 110-ATHY 110-110SA1 | 12 | 10 | 10 | Scheduled | 11/08/2025 | 22/08/2025
TO-25-ATY-110SA2-02 | SECTIONALISING DISCONNECT - ATHY 110-ATHY 110-110SA2 | 12 | 10 | 10 | Scheduled | 11/08/2025 | 22/08/2025
TO-25-ATY-PLS-1-06 | 110kV FEEDER - ATHY 110-PORTLAOISE 110-1 | 12 | 10 | 10 | Scheduled | 11/08/2025 | 22/08/2025
TO-25-ATY-T102-01 | DISTRIBUTION TRANSFORMER - ATHY 110-ATHY 10-T102 | 12 | 10 | 10 | Reference | 11/08/2025 | 22/08/2025
TO-25-KLS-T2101-05 | TRANSFORMER - KELLIS 220-KELLIS 110-T2101 | 3 | 3 | 3 | Scheduled | 12/08/2025 | 14/08/2025
TO-25-KTN-WAT-1-04 | 110kV FEEDER - KILLOTERAN 110-WATERFORD 110-1 | 2 | 2 | 2 | Scheduled | 14/08/2025 | 15/08/2025
TO-25-BEG-T101-01 | DISTRIBUTION TRANSFORMER - BALLYBEG 110-BALLYBEG 10-T101 | 2 | 2 | 2 | Reference (Proposed) | 26/08/2025 | 27/08/2025
TO-25-NEW-PLS-1-04 | 110kV FEEDER - NEWBRIDGE 110-PORTLAOISE 110-1 | 2 | 2 | 2 | Proposed | 28/08/2025 | 29/08/2025
TO-25-110 kV A1 @ ARK-01 | BUSBAR SECTION - ARKLOW 110-ARKLOW 110-110A1 | 12 | 10 | 10 | Scheduled | 01/09/2025 | 12/09/2025
TO-25-110 kV B1 @ ARK-01 | BUSBAR SECTION - ARKLOW 110-ARKLOW 110-110B1 | 12 | 10 | 10 | Scheduled | 01/09/2025 | 12/09/2025
TO-25-220 kV A1 @ ARK-02 | BUSBAR SECTION - ARKLOW 220-ARKLOW 220-220A1 | 12 | 10 | 10 | Scheduled | 01/09/2025 | 12/09/2025
TO-25-220 kV B1 @ ARK-02 | BUSBAR SECTION - ARKLOW 220-ARKLOW 220-220B1 | 12 | 10 | 10 | Scheduled | 01/09/2025 | 12/09/2025
TO-25-ARK-T2101-01 | TRANSFORMER - ARKLOW 220-ARKLOW 110-T2101 | 12 | 10 | 10 | Scheduled | 01/09/2025 | 12/09/2025
TO-25-PLS-T142-01 | DISTRIBUTION TRANSFORMER - PORTLAOISE 110-PORTLAOISE 38-T142 | 94 | 67 | 67 | Reference (Proposed) | 01/09/2025 | 03/12/2025
TO-25-110 kV A2 @ GI-01 | BUSBAR SECTION - GREAT ISLAND 110-GREAT ISLAND 110-110A2 | 9 | 7 | 7 | Scheduled | 04/09/2025 | 12/09/2025
TO-25-110 kV B2 @ GI-03 | BUSBAR SECTION - GREAT ISLAND 110-GREAT ISLAND 110-110B2 | 9 | 7 | 7 | Scheduled | 04/09/2025 | 12/09/2025
TO-25-GI-WAT-2-03 | 110kV FEEDER - GREAT ISLAND 110-WATERFORD 110-2 | 9 | 7 | 7 | Scheduled | 04/09/2025 | 12/09/2025
TO-25-BDA-T102-01 | TSO CUSTOMER TRANSFORMER - BARODA 110-BARODA 10-T102 | 9 | 7 | 7 | Scheduled | 08/09/2025 | 16/09/2025
TO-25-BDA-T102-02 | TSO CUSTOMER TRANSFORMER - BARODA 110-BARODA 10-T102 | 9 | 7 | 7 | Scheduled | 08/09/2025 | 16/09/2025
TO-25-BUT-110SA1-01 | SECTIONALISING DISCONNECT - BUTLERSTOWN 110-BUTLERSTOWN 110-110SA1 | 4 | 4 | 4 | Proposed | 09/09/2025 | 12/09/2025
TO-25-BUT-110SA1-02 | SECTIONALISING DISCONNECT - BUTLERSTOWN 110-BUTLERSTOWN 110-110SA1 | 4 | 4 | 4 | Scheduled | 09/09/2025 | 12/09/2025
TO-25-BUT-110SA2-03 | SECTIONALISING DISCONNECT - BUTLERSTOWN 110-BUTLERSTOWN 110-110SA2 | 4 | 4 | 4 | Scheduled | 09/09/2025 | 12/09/2025
TO-25-BUT-CUL-1-01 | 110kV FEEDER - BUTLERSTOWN 110-CULLENAGH 110-1 | 4 | 4 | 4 | Scheduled | 09/09/2025 | 12/09/2025
TO-25-BUT-T141-01 | DISTRIBUTION TRANSFORMER - BUTLERSTOWN 110-BUTLERSTOWN 38-T141 | 4 | 4 | 4 | Reference | 09/09/2025 | 12/09/2025
TO-25-BWR-CRA-1-02 | 110kV FEEDER - BALLYWATER 110-CRANE 110-1 | 5 | 5 | 5 | Scheduled | 15/09/2025 | 19/09/2025
TO-25-BWR-CRA-1-04 | 110kV FEEDER - BALLYWATER 110-CRANE 110-1 | 2 | 2 | 2 | Scheduled | 15/09/2025 | 16/09/2025
TO-25-BWR-T124-02 | GENERATOR TRANSFORMER - BALLYWATER 110-BALLYWATER 20-T124 | 5 | 5 | 5 | Reference | 15/09/2025 | 19/09/2025
TO-25-BWR-T124-04 | GENERATOR TRANSFORMER - BALLYWATER 110-BALLYWATER 20-T124 | 2 | 2 | 2 | Reference | 15/09/2025 | 16/09/2025
TO-25-CLW-KLS-1-05 | 110kV FEEDER - CARLOW 110-KELLIS 110-1 | 12 | 10 | 10 | Proposed | 15/09/2025 | 26/09/2025
TO-25-CRA-110SA1-02 | SECTIONALISING DISCONNECT - CRANE 110-CRANE 110-110SA1 | 5 | 5 | 5 | Scheduled | 15/09/2025 | 19/09/2025
TO-25-CRA-110SA1-03 | SECTIONALISING DISCONNECT - CRANE 110-CRANE 110-110SA1 | 2 | 2 | 2 | Scheduled | 15/09/2025 | 16/09/2025
TO-25-CRA-110SA2-02 | SECTIONALISING DISCONNECT - CRANE 110-CRANE 110-110SA2 | 5 | 5 | 5 | Scheduled | 15/09/2025 | 19/09/2025
TO-25-CRA-110SA2-04 | SECTIONALISING DISCONNECT - CRANE 110-CRANE 110-110SA2 | 2 | 2 | 2 | Scheduled | 15/09/2025 | 16/09/2025
TO-25-CRA-LWD-1-02 | 110kV FEEDER - CRANE 110-LODGEWOOD 110-1 | 5 | 5 | 5 | Scheduled | 15/09/2025 | 19/09/2025
TO-25-CRA-LWD-1-04 | 110kV FEEDER - CRANE 110-LODGEWOOD 110-1 | 2 | 2 | 2 | Scheduled | 15/09/2025 | 16/09/2025
TO-25-CRA-T122-04 | DISTRIBUTION TRANSFORMER - CRANE 110-CRANE 20-T122 | 2 | 2 | 2 | Reference | 15/09/2025 | 16/09/2025
TO-25-CRA-T122-02 | DISTRIBUTION TRANSFORMER - CRANE 110-CRANE 20-T122 | 5 | 5 | 5 | Reference | 15/09/2025 | 19/09/2025
TO-25-110 kV A1 @ KLS-05 | BUSBAR SECTION - KELLIS 110-KELLIS 110-110A1 | 12 | 10 | 10 | Proposed | 15/09/2025 | 26/09/2025
TO-25-110 kV B1 @ KLS-03 | BUSBAR SECTION - KELLIS 110-KELLIS 110-110B1 | 12 | 10 | 10 | Proposed | 15/09/2025 | 26/09/2025
TO-25-NEW-PLS-1-01 | 110kV FEEDER - NEWBRIDGE 110-PORTLAOISE 110-1 | Unknown | Unknown | 55 | Planned | October | December
TO-25-NEW-PLS-1-03 | 110kV FEEDER - NEWBRIDGE 110-PORTLAOISE 110-1 | Unknown | Unknown | 10 | Planned | October | October
TO-25-CAH-DOO-1-02 | 110kV FEEDER - CAHIR 110-DOON 110-1 | Unknown | Unknown | 40 | Planned | October | December
TO-25-CAH-DOO-1-03 | 110kV FEEDER - CAHIR 110-DOON 110-1 | Unknown | Unknown | 10 | Planned | October | October
TO-25-110 kV A2 @ PLS-03 | BUSBAR SECTION - PORTLAOISE 110-PORTLAOISE 110-110A2 | Unknown | Unknown | 15 | Planned | October | November
TO-25-PLS-110K1-2-04 | COUPLER/SECTIONALISING CB - PORTLAOISE 110-PORTLAOISE 110-110K1-2 | Unknown | Unknown | 15 | Planned | October | November
TO-25-DEY-PLS-1-03 | 110kV FEEDER - DERRYCARNEY 110-PORTLAOISE 110-1 | Unknown | Unknown | 2 | Planned | December | December
TO-25-KRA-WOH-1-02 | 110kV FEEDER - KNOCKRAHA 110-WOODHOUSE 110-1 | Unknown | Unknown | 10 | Planned | December | December
TO-25-KRA-WOH-1-01 | 110kV FEEDER - KNOCKRAHA 110-WOODHOUSE 110-1 | Unknown | Unknown | 10 | Planned | December | December
TO-25-110 kV A2 @ PLS-04 | BUSBAR SECTION - PORTLAOISE 110-PORTLAOISE 110-110A2 | Unknown | Unknown | 2 | Planned | December | December

## GEN_NorthWest
Outage ID | Feeder ID | Calendar Day Duration | Working Day Duration | Work Days | Outage Status | Start | Finish
TO-25-CSH-DLT-1-01 | 110kV FEEDER - CASHLA 110-DALTON 110-1 | 3 | 3 | 3 | Scheduled | 15/01/2025 | 17/01/2025
TO-25-CSH-T2104-01 | TRANSFORMER - CASHLA 220-CASHLA 110-T2104 | 68 | 47 | 47 | Scheduled | 17/02/2025 | 25/04/2025
TO-25-CSH-T2104-04 | TRANSFORMER - CASHLA 220-CASHLA 110-T2104 | 61 | 43 | 43 | Proposed | 17/02/2025 | 18/04/2025
TO-25-FLA-SLB-1-01 | 110kV FEEDER - FLAGFORD 110-SLIABH BAWN 110-1 | 12 | 10 | 10 | Scheduled | 17/02/2025 | 28/02/2025
TO-25-110 kV B2 @ CSH-05 | BUSBAR SECTION - CASHLA 110-CASHLA 110-110B2 | 57 | 38 | 38 | Scheduled | 28/02/2025 | 25/04/2025
TO-25-220 kV A4 @ CSH-02 | BUSBAR SECTION - CASHLA 220-CASHLA 220-220A4 | 57 | 38 | 38 | Scheduled | 28/02/2025 | 25/04/2025
TO-25-220 kV B4 @ CSH-02 | BUSBAR SECTION - CASHLA 220-CASHLA 220-220B4 | 57 | 38 | 38 | Scheduled | 28/02/2025 | 25/04/2025
TO-25-CBR-DLT-1-03 | 110kV FEEDER - CASTLEBAR 110-DALTON 110-1 | 5 | 5 | 5 | Scheduled | 10/03/2025 | 14/03/2025
TO-25-220 kV A2 @ CSH-02 | BUSBAR SECTION - CASHLA 220-CASHLA 220-220A2 | 11 | 9 | 9 | Scheduled | 18/03/2025 | 28/03/2025
TO-25-220 kV A4 @ CSH-01 | BUSBAR SECTION - CASHLA 220-CASHLA 220-220A4 | 11 | 9 | 9 | Scheduled | 18/03/2025 | 28/03/2025
TO-25-220 kV B2 @ CSH-02 | BUSBAR SECTION - CASHLA 220-CASHLA 220-220B2 | 11 | 9 | 9 | Scheduled | 18/03/2025 | 28/03/2025
TO-25-220 kV B4 @ CSH-01 | BUSBAR SECTION - CASHLA 220-CASHLA 220-220B4 | 11 | 9 | 9 | Scheduled | 18/03/2025 | 28/03/2025
TO-25-CSH-220K2-4-01 | COUPLER/SECTIONALISING CB - CASHLA 220-CASHLA 220-220K2-4 | 11 | 9 | 9 | Scheduled | 18/03/2025 | 28/03/2025
TO-25-110 kV B1 @ FLA-01 | BUSBAR SECTION - FLAGFORD 110-FLAGFORD 110-110B1 | 95 | 65 | 65 | Scheduled | 18/03/2025 | 20/06/2025
TO-25-FLA-SLB-1-03 | 110kV FEEDER - FLAGFORD 110-SLIABH BAWN 110-1 | 95 | 65 | 65 | Scheduled | 18/03/2025 | 20/06/2025
TO-25-110 kV B2 @ CSH-04 | BUSBAR SECTION - CASHLA 110-CASHLA 110-110B2 | 10 | 8 | 8 | Scheduled | 19/03/2025 | 28/03/2025
TO-25-CSH-ENN-1-02 | 110kV FEEDER - CASHLA 110-ENNIS 110-1 | 72 | 49 | 49 | Scheduled | 19/03/2025 | 29/05/2025
TO-25-MOY-TAW-1-01 | 110kV FEEDER - MOY 110-TAWNAGHMORE 110-1 | 12 | 10 | 10 | Scheduled | 31/03/2025 | 11/04/2025
TO-25-LET-PST-02 | TRANSFORMER - LETTERKENNY 110-STRABANE 110-PST | 16 | 12 | 12 | Scheduled | 02/04/2025 | 17/04/2025
TO-25-CF-CL-1-02 | 110kV FEEDER - CATHALEENS FALL 110-CLIFF 110-1 | 4 | 4 | 4 | Scheduled | 07/04/2025 | 10/04/2025
TO-25-CL-T101-03 | GENERATOR TRANSFORMER - CLIFF 110-CLIFF G1-T101 | 4 | 4 | 4 | Scheduled | 07/04/2025 | 10/04/2025
TO-25-CL-T102-01 | GENERATOR TRANSFORMER - CLIFF 110-CLIFF G2-T102 | 9 | 7 | 7 | Scheduled | 07/04/2025 | 15/04/2025
TO-25-BUF-KNY-1-01 | 110kV FEEDER - BUFFY 110-KNOCKRANNY 110-1 | 2 | 2 | 2 | Scheduled | 14/04/2025 | 15/04/2025
TO-25-BUF-T131-01 | GENERATOR TRANSFORMER - BUFFY 110-BUFFY 33-T131 | 2 | 2 | 2 | Scheduled | 14/04/2025 | 15/04/2025
TO-25-CDY-GRV-1-02 | 110kV FEEDER - CORDERRY 110-GARVAGH 110-1 | 3 | 3 | 3 | Scheduled | 15/04/2025 | 17/04/2025
TO-25-GRV-110K1-02 | COUPLER/SECTIONALISING CB - GARVAGH 110-GARVAGH 110-110K1 | 3 | 3 | 3 | Scheduled | 15/04/2025 | 17/04/2025
TO-25-GRV-T121-03 | GENERATOR TRANSFORMER - GARVAGH 110-GARVAGH 20-T121 | 3 | 3 | 3 | Scheduled | 15/04/2025 | 17/04/2025
TO-25-GRV-T141-02 | DISTRIBUTION TRANSFORMER - GARVAGH 110-GARVAGH 20-T141 | 3 | 3 | 3 | Reference | 15/04/2025 | 17/04/2025
TO-25-MOY-TAW-2-01 | 110kV FEEDER - MOY 110-TAWNAGHMORE 110-2 | 3 | 3 | 3 | Scheduled | 15/04/2025 | 17/04/2025
TO-25-ARV-COS-1-03 | 110kV FEEDER - ARVA 110-CARRICK ON SHANNON 110-1 | 4 | 0 | 0 | Scheduled | 18/04/2025 | 21/04/2025
TO-25-FLA-220K1-2-01 | COUPLER/SECTIONALISING CB - FLAGFORD 220-FLAGFORD 220-220K1-2 | 1 | 1 | 1 | Scheduled | 23/04/2025 | 23/04/2025
TO-25-110 kV B2 @ CF-02 | BUSBAR SECTION - CATHALEENS FALL 110-CATHALEENS FALL 110-110B2 | 14 | 9 | 9 | Scheduled | 24/04/2025 | 07/05/2025
TO-25-CF-T104-01 | GENERATOR TRANSFORMER - CATHALEENS FALL 110-CATHALEENS FALL G4-T104 | 14 | 9 | 9 | Scheduled | 24/04/2025 | 07/05/2025
TO-25-LLA-110K1-01 | COUPLER/SECTIONALISING CB - LENALEA 110-LENALEA 110-110K1 | 2 | 2 | 2 | Scheduled | 28/04/2025 | 29/04/2025
TO-25-LLA-T133-02 | GENERATOR TRANSFORMER - LENALEA 110-LENALEA 33-T133 | 3 | 3 |  | Scheduled | 28/04/2025 | 30/04/2025
TO-25-CF-SRA-2-01 | 110kV FEEDER - CATHALEENS FALL 110-SRANANAGH 110-2 | 66 | 47 | 47 | Scheduled | 06/05/2025 | 10/07/2025
TO-25-GAL-GAL GIS-1-01 | 110kV FEEDER - GALWAY 110-GALWAY GIS 110-1 | 240 | 167 | 167 | Scheduled | 06/05/2025 | 31/12/2025
TO-25-GAL-T103-01 | DISTRIBUTION TRANSFORMER - GALWAY 110-GALWAY 10-T103 | 81 | 58 |  | Scheduled | 06/05/2025 | 25/07/2025
TO-25-220 kV A1 @ CSH-01 | BUSBAR SECTION - CASHLA 220-CASHLA 220-220A1 | 9 | 7 | 7 | Scheduled | 07/05/2025 | 15/05/2025
TO-25-220 kV A2 @ CSH-01 | BUSBAR SECTION - CASHLA 220-CASHLA 220-220A2 | 9 | 7 | 7 | Scheduled | 07/05/2025 | 15/05/2025
TO-25-220 kV B1 @ CSH-01 | BUSBAR SECTION - CASHLA 220-CASHLA 220-220B1 | 9 | 7 |  | Scheduled | 07/05/2025 | 15/05/2025
TO-25-220 kV B2 @ CSH-01 | BUSBAR SECTION - CASHLA 220-CASHLA 220-220B2 | 9 | 7 | 7 | Scheduled | 07/05/2025 | 15/05/2025
TO-25-CSH-220K1-2-01 | COUPLER/SECTIONALISING CB - CASHLA 220-CASHLA 220-220K1-2 | 9 | 7 | 7 | Scheduled | 07/05/2025 | 15/05/2025
TO-25-110 kV B2 @ CF-03 | BUSBAR SECTION - CATHALEENS FALL 110-CATHALEENS FALL 110-110B2 | 12 | 8 | 8 | Scheduled | 08/05/2025 | 19/05/2025
TO-25-BK-SKY-1-01 | 110kV FEEDER - BELLACORICK 110-SRAHNAKILLY 110-1 | 5 | 5 | 5 | Scheduled | 12/05/2025 | 16/05/2025
TO-25-BIN-T141-01 | DISTRIBUTION TRANSFORMER - BINBANE 110-BINBANE 38-T141 | 100 | 70 | 70 | Reference | 12/05/2025 | 19/08/2025
TO-25-CSH-GAL GIS-4-01 | 110kV FEEDER - CASHLA 110-GALWAY GIS 110-4 | 5 | 5 | 5 | Scheduled | 12/05/2025 | 16/05/2025
TO-25-SKY-110SA1-01 | SECTIONALISING DISCONNECT - SRAHNAKILLY 110-SRAHNAKILLY 110-110SA1 | 5 | 5 | 5 | Scheduled | 12/05/2025 | 16/05/2025
TO-25-SKY-110SA2-01 | SECTIONALISING DISCONNECT - SRAHNAKILLY 110-SRAHNAKILLY 110-110SA2 | 5 | 5 | 5 | Scheduled | 12/05/2025 | 16/05/2025
TO-25-SKY-T131-01 | GENERATOR TRANSFORMER - SRAHNAKILLY 110-SRAHNAKILLY 33-T131 | 5 | 5 | 5 | Scheduled | 12/05/2025 | 16/05/2025
TO-25-SKY-T132-01 | GENERATOR TRANSFORMER - SRAHNAKILLY 110-SRAHNAKILLY 33-T132 | 5 | 5 | 5 | Scheduled | 12/05/2025 | 16/05/2025
TO-25-CL-T101-02 | GENERATOR TRANSFORMER - CLIFF 110-CLIFF G1-T101 | 10 | 8 | 8 | Scheduled | 14/05/2025 | 23/05/2025
TO-25-110 kV B2 @ CLO-01 | BUSBAR SECTION - CLOGHER 110-CLOGHER 110-110B2 | 12 | 10 | 10 | Scheduled | 19/05/2025 | 30/05/2025
TO-25-GOL-T101-01 | GENERATOR TRANSFORMER - GOLAGH 110-GOLAGH 10-T101 | 12 | 10 | 10 | Scheduled | 19/05/2025 | 30/05/2025
TO-25-GOL,T-CLO-1-01 | 110kV FEEDER - GOLAGH tee-CLOGHER 110-1 | 12 | 10 | 10 | Scheduled | 19/05/2025 | 30/05/2025
TO-25-GOL,T-GOL-1-01 | 110kV FEEDER - GOLAGH tee-GOLAGH 110-1 | 12 | 10 | 10 | Scheduled | 19/05/2025 | 30/05/2025
TO-25-GOL,T-LET-1-01 | 110kV FEEDER - GOLAGH tee-LETTERKENNY 110-1 | 12 | 10 | 10 | Scheduled | 19/05/2025 | 30/05/2025
TO-25-220 kV A4 @ CSH-03 | BUSBAR SECTION - CASHLA 220-CASHLA 220-220A4 | 2 | 2 | 2 | Scheduled | 20/05/2025 | 21/05/2025
TO-25-CSH-PRO-1-03 | 220kV FEEDER - CASHLA 220-PROSPECT 220-1 | 2 | 2 | 2 | Scheduled | 20/05/2025 | 21/05/2025
TO-25-CSH-CLN-1-03 | 110kV FEEDER - CASHLA 110-CLOON 110-1 | 12 | 9 | 9 | Scheduled | 26/05/2025 | 06/06/2025
TO-25-110 kV B1 @ CSH-06 | BUSBAR SECTION - CASHLA 110-CASHLA 110-110B1 | 12 | 8 | 8 | Scheduled | 27/05/2025 | 07/06/2025
TO-25-CSH-GAL GIS-2-01 | 110kV FEEDER - CASHLA 110-GALWAY GIS 110-2 | 7 | 5 | 5 | Scheduled | 03/06/2025 | 09/06/2025
TO-25-MOY-CAP1-01 | CAPACITOR/SVC/REACTOR - MOY 110-MOY 110-CAP1 | 7 | 5 | 5 | Scheduled | 05/06/2025 | 11/06/2025
TO-25-CUN-110SA1-01 | SECTIONALISING DISCONNECT - CUNGHILL 110-CUNGHILL 110-110SA1 | 5 | 5 | 5 | Scheduled | 09/06/2025 | 13/06/2025
TO-25-CUN-110SA2-01 | SECTIONALISING DISCONNECT - CUNGHILL 110-CUNGHILL 110-110SA2 | 5 | 5 | 5 | Scheduled | 09/06/2025 | 13/06/2025
TO-25-CUN-SLI-1-05 | 110kV FEEDER - CUNGHILL 110-SLIGO 110-1 | 5 | 5 |  | Scheduled | 09/06/2025 | 13/06/2025
TO-25-CUN-T121-02 | GENERATOR TRANSFORMER - CUNGHILL 110-CUNGHILL 20-T121 | 5 | 5 | 5 | Scheduled | 09/06/2025 | 13/06/2025
TO-25-110 kV B1 @ CF-05 | BUSBAR SECTION - CATHALEENS FALL 110-CATHALEENS FALL 110-110B1 | 1 | 1 | 1 | Scheduled | 12/06/2025 | 12/06/2025
TO-25-CL-T101-05 | GENERATOR TRANSFORMER - CLIFF 110-CLIFF G1-T101 | 1 | 1 | 1 | Scheduled | 12/06/2025 | 12/06/2025
TO-25-CL-T102-03 | GENERATOR TRANSFORMER - CLIFF 110-CLIFF G2-T102 | 1 | 1 | 1 | Scheduled | 12/06/2025 | 12/06/2025
TO-25-TAW-T1/T2-01 | GENERATOR TRANSFORMER - TAWNAGHMORE 110-TAWNAGHMORE 10-T1/T2 | 15 | 11 | 11 | Scheduled | 13/06/2025 | 27/06/2025
TO-25-TAW-T3-01 | GENERATOR TRANSFORMER - TAWNAGHMORE 110-TAWNAGHMORE 10-T3 | 15 | 11 | 11 | Scheduled | 13/06/2025 | 27/06/2025
TO-25-BK-CBR-1-01 | 110kV FEEDER - BELLACORICK 110-CASTLEBAR 110-1 | 5 | 5 | 5 | Scheduled | 16/06/2025 | 20/06/2025
TO-25-CBR-110SA1-2CB-03 | COUPLER/SECTIONALISING CB - CASTLEBAR 110-CASTLEBAR 110-110SA1-2CB | 5 | 5 | 5 | Scheduled | 16/06/2025 | 20/06/2025
TO-25-CBR-CLN-1-02 | 110kV FEEDER - CASTLEBAR 110-CLOON 110-1 | 5 | 5 | 5 | Scheduled | 16/06/2025 | 20/06/2025
TO-25-CBR-SVC-04 | CAPACITOR/SVC/REACTOR - CASTLEBAR 110-CASTLEBAR 110-SVC | 5 | 5 | 5 | Scheduled | 16/06/2025 | 20/06/2025
TO-25-CBR-T141-01 | DISTRIBUTION TRANSFORMER - CASTLEBAR 110-CASTLEBAR 38-T141 | 5 | 5 | 5 | Reference | 16/06/2025 | 20/06/2025
TO-25-110 kV B2 @ CLO-02 | BUSBAR SECTION - CLOGHER 110-CLOGHER 110-110B2 | 4 | 4 | 4 | Scheduled | 16/06/2025 | 19/06/2025
TO-25-CLO-MRY-1-01 | 110kV FEEDER - CLOGHER 110-MULREAVY 110-1 | 4 | 4 | 4 | Scheduled | 16/06/2025 | 19/06/2025
TO-25-GAL GIS-SAL-1-02 | 110kV FEEDER - GALWAY GIS 110-SALTHILL 110-1 | 12 | 10 | 10 | Scheduled | 16/06/2025 | 27/06/2025
TO-25-MRY-T131-01 | GENERATOR TRANSFORMER - MULREAVY 110-MULREAVY 33-T131 | 4 | 4 | 4 | Scheduled | 16/06/2025 | 19/06/2025
TO-25-SAL-110SA1-2CB-02 | COUPLER/SECTIONALISING CB - SALTHILL 110-SALTHILL 110-110SA1-2CB | 12 | 10 | 10 | Scheduled | 16/06/2025 | 27/06/2025
TO-25-SAL-T101-01 | DISTRIBUTION TRANSFORMER - SALTHILL 110-SALTHILL 10-T101 | 12 | 10 | 10 | Reference | 16/06/2025 | 27/06/2025
TO-25-SAL-T141-01 | DISTRIBUTION TRANSFORMER - SALTHILL 110-SALTHILL 38-T141 | 12 | 10 | 10 | Reference | 16/06/2025 | 27/06/2025
TO-25-CSH-110K1-2-03 | COUPLER/SECTIONALISING CB - CASHLA 110-CASHLA 110-110K1-2 | 8 | 6 | 6 | Scheduled | 23/06/2025 | 30/06/2025
TO-25-CSH-DLT-1-02 | 110kV FEEDER - CASHLA 110-DALTON 110-1 | 12 | 10 | 10 | Scheduled | 23/06/2025 | 04/07/2025
TO-25-110 kV B1 @ CF-01 | BUSBAR SECTION - CATHALEENS FALL 110-CATHALEENS FALL 110-110B1 | 9 | 7 | 7 | Scheduled | 23/06/2025 | 01/07/2025
TO-25-CF-CLO-1-02 | 110kV FEEDER - CATHALEENS FALL 110-CLOGHER 110-1 | 9 | 7 | 7 | Scheduled | 23/06/2025 | 01/07/2025
TO-25-CF-T103-01 | GENERATOR TRANSFORMER - CATHALEENS FALL 110-CATHALEENS FALL G3-T103 | 12 | 10 | 10 | Scheduled | 23/06/2025 | 04/07/2025
TO-25-110 kV B1 @ CLO-01 | BUSBAR SECTION - CLOGHER 110-CLOGHER 110-110B1 | 12 | 10 | 10 | Scheduled | 23/06/2025 | 04/07/2025
TO-25-110 kV B1 @ CSH-07 | BUSBAR SECTION - CASHLA 110-CASHLA 110-110B1 | 4 | 4 | 4 | Scheduled | 01/07/2025 | 04/07/2025
TO-25-CF-CLO-2-04 | 110kV FEEDER - CATHALEENS FALL 110-CLOGHER 110-2 | 3 | 3 | 3 | Scheduled | 02/07/2025 | 04/07/2025
TO-25-FLA-SLI-1-04 | 110kV FEEDER - FLAGFORD 110-SLIGO 110-1 | 2 | 2 | 2 | Scheduled | 03/07/2025 | 04/07/2025
TO-25-110 kV B1 @ CSH-01 | BUSBAR SECTION - CASHLA 110-CASHLA 110-110B1 | 8 | 6 | 6 | Scheduled | 07/07/2025 | 14/07/2025
TO-25-CSH-GAL GIS-1-02 | 110kV FEEDER - CASHLA 110-GALWAY GIS 110-1 | 8 | 6 | 6 | Scheduled | 07/07/2025 | 14/07/2025
TO-25-FLA-T2101-01 | TRANSFORMER - FLAGFORD 220-FLAGFORD 110-T2101 | 4 | 4 | 4 | Scheduled | 07/07/2025 | 10/07/2025
TO-25-110 kV B1/B2 @ CLO-01 | BUSBAR SECTION - CLOGHER 110-CLOGHER 110-110B1-B2 | 10 | 8 | 8 | Scheduled | 08/07/2025 | 17/07/2025
TO-25-CLO-110K1-2-02 | COUPLER/SECTIONALISING CB - CLOGHER 110-CLOGHER 110-110K1-2 | 10 | 8 | 8 | Scheduled | 08/07/2025 | 17/07/2025
TO-25-GLR-MOY-1-02 | 110kV FEEDER - GLENREE 110-MOY 110-1 | 85 | 60 | 60 | Scheduled | 08/07/2025 | 30/09/2025
TO-25-KNY-UGL-1-01 | 110kV FEEDER - KNOCKRANNY 110-UGGOOL 110-1 | 4 | 4 | 4 | Scheduled | 08/07/2025 | 11/07/2025
TO-25-UGL-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - UGGOOL 110-UGGOOL 110-110SA1-2CB | 4 | 4 | 4 | Scheduled | 08/07/2025 | 11/07/2025
TO-25-UGL-T131-01 | GENERATOR TRANSFORMER - UGGOOL 110-UGGOOL 33-T131 | 10 | 8 | 8 | Scheduled | 08/07/2025 | 17/07/2025
TO-25-UGL-T132-01 | GENERATOR TRANSFORMER - UGGOOL 110-UGGOOL 33-T132 | 4 | 4 | 4 | Scheduled | 08/07/2025 | 11/07/2025
TO-25-UGL-T134-01 | GENERATOR TRANSFORMER - UGGOOL 110-UGGOOL 33-T134 | 4 | 4 | 4 | Scheduled | 08/07/2025 | 11/07/2025
TO-25-110 kV A3 @ GAL GIS-01 | BUSBAR SECTION - GALWAY GIS 110-GALWAY GIS 110-110A3 | 7 | 5 | 5 | Scheduled | 10/07/2025 | 16/07/2025
TO-25-110 kV B3 @ GAL GIS-01 | BUSBAR SECTION - GALWAY GIS 110-GALWAY GIS 110-110B3 | 7 | 5 | 5 | Scheduled | 10/07/2025 | 16/07/2025
TO-25-GAL GIS-110K3-01 | COUPLER/SECTIONALISING CB - GALWAY GIS 110-GALWAY GIS 110-110K3 | 7 | 5 | 5 | Scheduled | 10/07/2025 | 16/07/2025
TO-25-GAL GIS-110SA1-3CB-01 | COUPLER/SECTIONALISING CB - GALWAY GIS 110-GALWAY GIS 110-110SA1-3CB | 7 | 5 | 5 | Scheduled | 10/07/2025 | 16/07/2025
TO-25-GAL GIS-110SB1-3CB-01 | COUPLER/SECTIONALISING CB - GALWAY GIS 110-GALWAY GIS 110-110SB1-3CB | 7 | 5 | 5 | Scheduled | 10/07/2025 | 16/07/2025
TO-25-CDY-GRV-1-01 | 110kV FEEDER - CORDERRY 110-GARVAGH 110-1 | 8 | 6 | 6 | Scheduled | 11/07/2025 | 18/07/2025
TO-25-110 kV B1 @ GRV-01 | BUSBAR SECTION - GARVAGH 110-GARVAGH 110-110B1 | 8 | 6 | 6 | Scheduled | 11/07/2025 | 18/07/2025
TO-25-GRV-110K1-03 | COUPLER/SECTIONALISING CB - GARVAGH 110-GARVAGH 110-110K1 | 8 | 6 | 6 | Scheduled | 11/07/2025 | 18/07/2025
TO-25-GRV-T121-02 | GENERATOR TRANSFORMER - GARVAGH 110-GARVAGH 20-T121 | 8 | 6 | 6 | Scheduled | 11/07/2025 | 18/07/2025
TO-25-GRV-T141-01 | DISTRIBUTION TRANSFORMER - GARVAGH 110-GARVAGH 20-T141 | 8 | 6 | 6 | Reference | 11/07/2025 | 18/07/2025
TO-25-CF-T104-02 | GENERATOR TRANSFORMER - CATHALEENS FALL 110-CATHALEENS FALL G4-T104 | 63 | 44 | 44 | Scheduled | 16/07/2025 | 16/09/2025
TO-25-KLH-KNY-1-01 | 110kV FEEDER - KNOCKALOUGH 110-KNOCKRANNY 110-1 | 9 | 7 | 7 | Scheduled | 21/07/2025 | 29/07/2025
TO-25-CSH-PRO-1-05 | 220kV FEEDER - CASHLA 220-PROSPECT 220-1 | 8 | 6 | 6 | Scheduled | 22/07/2025 | 29/07/2025
TO-25-SLI-110SA1-2CB-02 | COUPLER/SECTIONALISING CB - SLIGO 110-SLIGO 110-110SA1-2CB | 31 | 22 | 22 | Scheduled | 23/07/2025 | 22/08/2025
TO-25-SLI-CAP1-01 | CAPACITOR/SVC/REACTOR - SLIGO 110-SLIGO 110-CAP1 | 31 | 22 | 22 | Scheduled | 23/07/2025 | 22/08/2025
TO-25-SLI-SRA-1-02 | 110kV FEEDER - SLIGO 110-SRANANAGH 110-1 | 111 | 77 | 77 | Scheduled | 23/07/2025 | 10/11/2025
TO-25-SLI-T141-02 | DISTRIBUTION TRANSFORMER - SLIGO 110-SLIGO 38-T141 | 31 | 22 | 22 | Reference | 23/07/2025 | 22/08/2025
TO-25-110 kV B1 @ SRA-01 | BUSBAR SECTION - SRANANAGH 110-SRANANAGH 110-110B1 | 7 | 5 | 5 | Scheduled | 23/07/2025 | 29/07/2025
TO-25-CSH-GAL GIS-1-01 | 110kV FEEDER - CASHLA 110-GALWAY GIS 110-1 | 2 | 2 | 2 | Scheduled | 24/07/2025 | 25/07/2025
TO-25-CF-CLO-2-06 | 110kV FEEDER - CATHALEENS FALL 110-CLOGHER 110-2 | 2 | 2 | 2 | Scheduled | 24/07/2025 | 25/07/2025
TO-25-110 kV A3 @ GAL GIS-02 | BUSBAR SECTION - GALWAY GIS 110-GALWAY GIS 110-110A3 | 2 | 2 | 2 | Scheduled | 24/07/2025 | 25/07/2025
TO-25-110 kV B3 @ GAL GIS-02 | BUSBAR SECTION - GALWAY GIS 110-GALWAY GIS 110-110B3 | 2 | 2 | 2 | Scheduled | 24/07/2025 | 25/07/2025
TO-25-GAL GIS-110K3-03 | COUPLER/SECTIONALISING CB - GALWAY GIS 110-GALWAY GIS 110-110K3 | 2 | 2 | 2 | Scheduled | 24/07/2025 | 25/07/2025
TO-25-GAL GIS-110SA1-3CB-03 | COUPLER/SECTIONALISING CB - GALWAY GIS 110-GALWAY GIS 110-110SA1-3CB | 2 | 2 | 2 | Scheduled | 24/07/2025 | 25/07/2025
TO-25-GAL GIS-110SB1-3CB-03 | COUPLER/SECTIONALISING CB - GALWAY GIS 110-GALWAY GIS 110-110SB1-3CB | 2 | 2 | 2 | Scheduled | 24/07/2025 | 25/07/2025
TO-25-110 kV A1 @ CLO-02 | BUSBAR SECTION - CLOGHER 110-CLOGHER 110-110A1 | 11 | 9 | 9 | Scheduled | 05/08/2025 | 15/08/2025
TO-25-110 kV B1 @ CLO-02 | BUSBAR SECTION - CLOGHER 110-CLOGHER 110-110B1 | 11 | 9 | 9 | Scheduled | 05/08/2025 | 15/08/2025
TO-25-CLO-DRM-1-01 | 110kV FEEDER - CLOGHER 110-DRUMKEEN 110-1 | 11 | 9 | 9 | Scheduled | 05/08/2025 | 15/08/2025
TO-25-DRM-110SA1-01 | SECTIONALISING DISCONNECT - DRUMKEEN 110-DRUMKEEN 110-110SA1 | 11 | 9 | 9 | Scheduled | 05/08/2025 | 15/08/2025
TO-25-DRM-110SA2-01 | SECTIONALISING DISCONNECT - DRUMKEEN 110-DRUMKEEN 110-110SA2 | 11 | 9 | 9 | Scheduled | 05/08/2025 | 15/08/2025
TO-25-DRM-LET-1-01 | 110kV FEEDER - DRUMKEEN 110-LETTERKENNY 110-1 | 11 | 9 | 9 | Scheduled | 05/08/2025 | 15/08/2025
TO-25-DRM-MEE-1-01 | 110kV FEEDER - DRUMKEEN 110-MEENTYCAT 110-1 | 11 | 9 | 9 | Scheduled | 05/08/2025 | 15/08/2025
TO-25-MEE-T121-01 | GENERATOR TRANSFORMER - MEENTYCAT 110-MEENTYCAT 20-T121 | 11 | 9 | 9 | Scheduled | 05/08/2025 | 15/08/2025
TO-25-FLA-GIL-1-01 | 110kV FEEDER - FLAGFORD 110-GILRA 110-1 | 2 | 2 | 2 | Scheduled | 11/08/2025 | 12/08/2025
TO-25-GIL-T121-01 | TSO CUSTOMER TRANSFORMER - GILRA 110-GILRA 20-T121 | 2 | 2 | 2 | Reference | 11/08/2025 | 12/08/2025
TO-25-CSH-SAL-1-03 | 110kV FEEDER - CASHLA 110-SALTHILL 110-1 | 16 | 12 | 12 | Scheduled | 13/08/2025 | 28/08/2025
TO-25-KNY-SAL-1-02 | 110kV FEEDER - KNOCKRANNY 110-SALTHILL 110-1 | 14 | 10 | 10 | Scheduled | 13/08/2025 | 26/08/2025
TO-25-SAL-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - SALTHILL 110-SALTHILL 110-110SA1-2CB | 14 | 10 | 10 | Scheduled | 13/08/2025 | 26/08/2025
TO-25-SAL-T102-01 | DISTRIBUTION TRANSFORMER - SALTHILL 110-SALTHILL 10-T102 | 14 | 10 | 10 | Reference | 13/08/2025 | 26/08/2025
TO-25-KLH-T121-01 | GENERATOR TRANSFORMER - KNOCKALOUGH 110-KNOCKALOUGH 20-T121 | 1 | 1 | 1 | Scheduled | 14/08/2025 | 14/08/2025
TO-25-CDY-GRV-1-04 | 110kV FEEDER - CORDERRY 110-GARVAGH 110-1 | 14 | 10 | 10 | Proposed | 18/08/2025 | 31/08/2025
TO-25-GRV-110K1-04 | COUPLER/SECTIONALISING CB - GARVAGH 110-GARVAGH 110-110K1 | 14 | 10 | 10 | Proposed | 18/08/2025 | 31/08/2025
TO-25-GRV-T121-04 | GENERATOR TRANSFORMER - GARVAGH 110-GARVAGH 20-T121 | 14 | 10 | 10 | Proposed | 18/08/2025 | 31/08/2025
TO-25-GRV-T141-03 | DISTRIBUTION TRANSFORMER - GARVAGH 110-GARVAGH 20-T141 | 14 | 10 | 10 | Reference (Proposed) | 18/08/2025 | 31/08/2025
TO-25-SKY-T131-02 | GENERATOR TRANSFORMER - SRAHNAKILLY 110-SRAHNAKILLY 33-T131 | 1 | 1 | 1 | Scheduled | 20/08/2025 | 20/08/2025
TO-25-LET-CAP2-02 | CAPACITOR/SVC/REACTOR - LETTERKENNY 110-LETTERKENNY 110-CAP2 | 5 | 5 | 5 | Proposed | 25/08/2025 | 29/08/2025
TO-25-CSH-GAL GIS-1-03 | 110kV FEEDER - CASHLA 110-GALWAY GIS 110-1 | 2 | 2 | 2 | Scheduled | 27/08/2025 | 28/08/2025
TO-25-ARI-T121-02 | DISTRIBUTION TRANSFORMER - ARIGNA 110-ARIGNA 20-T121 | 5 | 5 | 5 | Reference (Proposed) | 01/09/2025 | 05/09/2025
TO-25-ARI,T-ARI-1-01 | 110kV FEEDER - ARIGNA tee-ARIGNA 110-1 | 5 | 5 | 5 | Proposed | 01/09/2025 | 05/09/2025
TO-25-ARI,T-COS-1-02 | 110kV FEEDER - ARIGNA tee-CARRICK ON SHANNON 110-1 | 5 | 5 | 5 | Proposed | 01/09/2025 | 05/09/2025
TO-25-ARI,T-CDY-1-02 | 110kV FEEDER - ARIGNA tee-CORDERRY 110-1 | 5 | 5 | 5 | Proposed | 01/09/2025 | 05/09/2025
TO-25-220 kV A1 @ CSH-02 | BUSBAR SECTION - CASHLA 220-CASHLA 220-220A1 | 5 | 5 | 5 | Scheduled | 01/09/2025 | 05/09/2025
TO-25-220 kV B1 @ CSH-02 | BUSBAR SECTION - CASHLA 220-CASHLA 220-220B1 | 5 | 5 | 5 | Scheduled | 01/09/2025 | 05/09/2025
TO-25-CSH-CLN-1-04 | 110kV FEEDER - CASHLA 110-CLOON 110-1 | 5 | 5 | 5 | Proposed | 01/09/2025 | 05/09/2025
TO-25-CSH-TY-1-02 | 220kV FEEDER - CASHLA 220-TYNAGH 220-1 | 5 | 5 | 5 | Scheduled | 01/09/2025 | 05/09/2025
TO-25-DLT-CAP1-01 | CAPACITOR/SVC/REACTOR - DALTON 110-DALTON 110-CAP1 | 5 | 5 | 5 | Proposed | 01/09/2025 | 05/09/2025
TO-25-FLA-TON-1-01 | 110kV FEEDER - FLAGFORD 110-TONROE 110-1 | 52 | 38 | 38 | Reference | 03/09/2025 | 24/10/2025
TO-25-TON-T142-01 | DISTRIBUTION TRANSFORMER - TONROE 110-TONROE 38-T142 | 52 | 38 | 38 | Reference | 03/09/2025 | 24/10/2025
TO-25-220 kV A2 @ CSH-03 | BUSBAR SECTION - CASHLA 220-CASHLA 220-220A2 | 15 | 11 | 11 | Scheduled | 08/09/2025 | 22/09/2025
TO-25-CSH-T2102-02 | TRANSFORMER - CASHLA 220-CASHLA 110-T2102 | 15 | 11 | 11 | Scheduled | 08/09/2025 | 22/09/2025
TO-25-110 kV A1 @ CF-01 | BUSBAR SECTION - CATHALEENS FALL 110-CATHALEENS FALL 110-110A1 | 12 | 10 | 10 | Scheduled | 08/09/2025 | 19/09/2025
TO-25-110 kV B1 @ CF-06 | BUSBAR SECTION - CATHALEENS FALL 110-CATHALEENS FALL 110-110B1 | 12 | 10 | 10 | Scheduled | 08/09/2025 | 19/09/2025
TO-25-CF-COR-1-03 | 110kV FEEDER - CATHALEENS FALL 110-CORRACLASSY 110-1 | 12 | 10 | 10 | Scheduled | 08/09/2025 | 19/09/2025
TO-25-CF-COR-1-02 | 110kV FEEDER - CATHALEENS FALL 110-CORRACLASSY 110-1 | 5 | 5 | 5 | Proposed | 08/09/2025 | 12/09/2025
TO-25-MOY-CAP2-01 | CAPACITOR/SVC/REACTOR - MOY 110-MOY 110-CAP2 | 2 | 2 | 2 | Scheduled | 09/09/2025 | 10/09/2025
TO-25-GAL GIS-KNY-1-01 | 110kV FEEDER - GALWAY GIS 110-KNOCKRANNY 110-1 | 2 | 2 | 2 | Proposed | 16/09/2025 | 17/09/2025
TO-25-CSH-PRO-1-01 | 220kV FEEDER - CASHLA 220-PROSPECT 220-1 | 57 | 40 | 40 | Proposed | 22/09/2025 | 17/11/2025
TO-25-CSH-PRO-1-02 | 220kV FEEDER - CASHLA 220-PROSPECT 220-1 | Unknown | Unknown | 40 | Planned | September | November
TO-25-LLA-LET-1-01 | 110kV FEEDER - LENALEA 110-LETTERKENNY 110-1 | 10 | 8 | 8 | Scheduled | 22/09/2025 | 01/10/2025
TO-25-LET-M/CAP1-01 | CAPACITOR/SVC/REACTOR - LETTERKENNY 110-LETTERKENNY 110-M/CAP1 | 2 | 2 | 2 | Proposed | 22/09/2025 | 23/09/2025
TO-25-110 kV B2 @ CSH-01 | BUSBAR SECTION - CASHLA 110-CASHLA 110-110B2 | Unknown | Unknown |  | Planned | September | September
TO-25-CSH-T2101-01 | TRANSFORMER - CASHLA 220-CASHLA 110-T2101 | Unknown | Unknown |  | Planned | October | October
TO-25-CSH-T2101-02 | TRANSFORMER - CASHLA 220-CASHLA 110-T2101 | Unknown | Unknown |  | Planned | October | October
TO-25-SLI-110SA1-2CB-03 | COUPLER/SECTIONALISING CB - SLIGO 110-SLIGO 110-110SA1-2CB | 14 | 10 | 10 | Scheduled | 28/10/2025 | 10/11/2025
TO-25-SLI-CAP1-02 | CAPACITOR/SVC/REACTOR - SLIGO 110-SLIGO 110-CAP1 | 14 | 10 | 10 | Scheduled | 28/10/2025 | 10/11/2025
TO-25-SLI-T141-01 | DISTRIBUTION TRANSFORMER - SLIGO 110-SLIGO 38-T141 | 14 | 10 | 10 | Reference | 28/10/2025 | 10/11/2025
TO-25-CF-SRA-1-01 | 110kV FEEDER - CATHALEENS FALL 110-SRANANAGH 110-1 | 1 | 1 | 1 | Proposed | 10/11/2025 | 10/11/2025

## GEN_NorthEast
Outage ID | Feeder ID | Calendar Day Duration | Working Day Duration | Work Days | Outage Status | Start | Finish
TO-25-BAL-DRY-1-03 | 110kV FEEDER - BALTRASNA 110-DRYBRIDGE 110-1 | 283 | 201 | 201 | Scheduled | 13/05/2024 | 19/02/2025
TO-25-KIN-T101-02 | TSO CUSTOMER TRANSFORMER - KINNEGAD 110-KINNEGAD 10-T101 | 26 | 18 | 18 | Scheduled | 03/01/2025 | 28/01/2025
TO-25-220 kV A2 @ SH-01 | BUSBAR SECTION - SHANNONBRIDGE 220-SHANNONBRIDGE 220-220A2 | 50 | 35 | 35 | Scheduled | 06/01/2025 | 24/02/2025
TO-25-220 kV B2 @ SH-01 | BUSBAR SECTION - SHANNONBRIDGE 220-SHANNONBRIDGE 220-220B2 | 50 | 35 | 35 | Scheduled | 06/01/2025 | 24/02/2025
TO-25-110 kV A2 @ LOU-05 | BUSBAR SECTION - LOUTH 110-LOUTH 110-110A2 | 12 | 10 | 10 | Scheduled | 13/01/2025 | 24/01/2025
TO-25-110 kV B2 @ LOU-05 | BUSBAR SECTION - LOUTH 110-LOUTH 110-110B2 | 12 | 10 | 10 | Scheduled | 13/01/2025 | 24/01/2025
TO-25-220 kV A2 @ LOU-07 | BUSBAR SECTION - LOUTH 220-LOUTH 220-220A2 | 12 | 10 | 10 | Scheduled | 13/01/2025 | 24/01/2025
TO-25-220 kV B2 @ LOU-06 | BUSBAR SECTION - LOUTH 220-LOUTH 220-220B2 | 12 | 10 | 10 | Scheduled | 13/01/2025 | 24/01/2025
TO-25-LOU-T2102-01 | TRANSFORMER - LOUTH 220-LOUTH 110-T2102 | 12 | 10 | 10 | Scheduled | 13/01/2025 | 24/01/2025
TO-25-CUS-MLC-1-01 | 110kV FEEDER - CUSHALING 110-MOUNTLUCAS 110-1 | 1 | 1 | 1 | Scheduled | 14/01/2025 | 14/01/2025
TO-25-GWE-T101-03 | TSO CUSTOMER TRANSFORMER - GORTAWEE 110-GORTAWEE 10-T101 | 16 | 12 | 12 | Scheduled | 15/01/2025 | 30/01/2025
TO-25-LOU-T2101-03 | TRANSFORMER - LOUTH 220-LOUTH 110-T2101 | 16 | 11 | 11 | Scheduled | 29/01/2025 | 13/02/2025
TO-25-RRU-SKL-1-01 | 110kV FEEDER - RATRUSSAN 110-SHANKILL 110-1 | 80 | 55 | 55 | Scheduled | 05/02/2025 | 25/04/2025
TO-25-220 kV A1 @ SH-03 | BUSBAR SECTION - SHANNONBRIDGE 220-SHANNONBRIDGE 220-220A1 | 68 | 48 | 48 | Scheduled | 10/02/2025 | 18/04/2025
TO-25-220 kV B1 @ SH-03 | BUSBAR SECTION - SHANNONBRIDGE 220-SHANNONBRIDGE 220-220B1 | 68 | 48 | 48 | Scheduled | 10/02/2025 | 18/04/2025
TO-25-SH-T2101-03 | TRANSFORMER - SHANNONBRIDGE 220-SHANNONBRIDGE 110-T2101 | 135 | 92 | 92 | Scheduled | 10/02/2025 | 24/06/2025
TO-25-PLA-T105-03 | TSO CUSTOMER TRANSFORMER - PLATIN 110-PLATIN 10-T105 | 8 | 6 | 6 | Proposed | 14/02/2025 | 21/02/2025
TO-25-DEN-DRY-1-03 | 110kV FEEDER - DEENES 110-DRYBRIDGE 110-1 | 3 | 3 | 3 | Scheduled | 17/02/2025 | 19/02/2025
TO-25-DRY-110SA1-02 | SECTIONALISING DISCONNECT - DRYBRIDGE 110-DRYBRIDGE 110-110SA1 | 3 | 3 | 3 | Scheduled | 17/02/2025 | 19/02/2025
TO-25-DRY-110SA2-02 | SECTIONALISING DISCONNECT - DRYBRIDGE 110-DRYBRIDGE 110-110SA2 | 3 | 3 | 3 | Scheduled | 17/02/2025 | 19/02/2025
TO-25-DRY-GOR-1-03 | 110kV FEEDER - DRYBRIDGE 110-GORMAN 110-1 | 3 | 3 | 3 | Scheduled | 17/02/2025 | 19/02/2025
TO-25-DRY-T142-02 | DISTRIBUTION TRANSFORMER - DRYBRIDGE 110-DRYBRIDGE 38-T142 | 3 | 3 | 3 | Reference | 17/02/2025 | 19/02/2025
TO-25-FLA-SLB-1-01 | 110kV FEEDER - FLAGFORD 110-SLIABH BAWN 110-1 | 12 | 10 | 10 | Scheduled | 17/02/2025 | 28/02/2025
TO-25-110 kV B2 @ DEN-01 | BUSBAR SECTION - DEENES 110-DEENES 110-110B2 | 2 | 2 | 2 | Scheduled | 26/02/2025 | 27/02/2025
TO-25-DEN-110K2-02 | COUPLER/SECTIONALISING CB - DEENES 110-DEENES 110-110K2 | 2 | 2 | 2 | Scheduled | 26/02/2025 | 27/02/2025
TO-25-DEY-T134-01 | GENERATOR TRANSFORMER - DERRYCARNEY 110-DERRYCARNEY 33-T134 | 1 | 1 | 1 | Scheduled | 27/02/2025 | 27/02/2025
TO-25-ATH-110SA1-2CB-02 | COUPLER/SECTIONALISING CB - ATHLONE 110-ATHLONE 110-110SA1-2CB | 12 | 10 | 10 | Scheduled | 03/03/2025 | 14/03/2025
TO-25-ATH-SH-1-06 | 110kV FEEDER - ATHLONE 110-SHANNONBRIDGE 110-1 | 12 | 10 | 10 | Scheduled | 03/03/2025 | 14/03/2025
TO-25-220 kV B2 @ LOU-08 | BUSBAR SECTION - LOUTH 220-LOUTH 220-220B2 | 7 | 5 | 5 | Scheduled | 05/03/2025 | 11/03/2025
TO-25-LOU-T2104-04 | TRANSFORMER - LOUTH 220-LOUTH 110-T2104 | 10 | 8 |  | Scheduled | 05/03/2025 | 14/03/2025
TO-25-SKL-M/CAP2-02 | CAPACITOR/SVC/REACTOR - SHANKILL 110-SHANKILL 110-M/CAP2 | 1 | 1 | 1 | Scheduled | 12/03/2025 | 12/03/2025
TO-25-220 kV A2 @ LOU-01 | BUSBAR SECTION - LOUTH 220-LOUTH 220-220A2 | 16 | 11 |  | Scheduled | 13/03/2025 | 28/03/2025
TO-25-220 kV B2 @ LOU-01 | BUSBAR SECTION - LOUTH 220-LOUTH 220-220B2 | 16 | 11 |  | Scheduled | 13/03/2025 | 28/03/2025
TO-25-FLA-SLB-1-03 | 110kV FEEDER - FLAGFORD 110-SLIABH BAWN 110-1 | 95 | 65 | 65 | Scheduled | 18/03/2025 | 20/06/2025
TO-25-110 kV A2 @ SLB-01 | BUSBAR SECTION - SLIABH BAWN 110-SLIABH BAWN 110-110A2 | 14 | 10 | 10 | Scheduled | 18/03/2025 | 31/03/2025
TO-25-110 kV B2 @ SLB-01 | BUSBAR SECTION - SLIABH BAWN 110-SLIABH BAWN 110-110B2 | 14 | 10 | 10 | Scheduled | 18/03/2025 | 31/03/2025
TO-25-SLB-110K2-01 | COUPLER/SECTIONALISING CB - SLIABH BAWN 110-SLIABH BAWN 110-110K2 | 14 | 10 | 10 | Scheduled | 18/03/2025 | 31/03/2025
TO-25-DRY-GOR-1-04 | 110kV FEEDER - DRYBRIDGE 110-GORMAN 110-1 | 3 | 3 | 3 | Scheduled | 26/03/2025 | 28/03/2025
TO-25-KIN-T102-03 | TSO CUSTOMER TRANSFORMER - KINNEGAD 110-KINNEGAD 10-T102 | 3 | 3 | 3 | Scheduled | 26/03/2025 | 28/03/2025
TO-25-DRY-OBE-1-01 | 110kV FEEDER - DRYBRIDGE 110-OLDBRIDGE 110-1 | 67 | 45 | 45 | Scheduled | 31/03/2025 | 05/06/2025
TO-25-220 kV A1 @ LOU-08 | BUSBAR SECTION - LOUTH 220-LOUTH 220-220A1 | 4 | 4 | 4 | Scheduled | 31/03/2025 | 03/04/2025
TO-25-220 kV A1 @ LOU-01 | BUSBAR SECTION - LOUTH 220-LOUTH 220-220A1 | 38 | 25 | 25 | Scheduled | 31/03/2025 | 07/05/2025
TO-25-220 kV B1 @ LOU-01 | BUSBAR SECTION - LOUTH 220-LOUTH 220-220B1 | 38 | 25 | 25 | Scheduled | 31/03/2025 | 07/05/2025
TO-25-LOU-AT2-03 | TRANSFORMER - LOUTH 220-LOUTH 275-AT2 | 4 | 4 | 4 | Scheduled | 31/03/2025 | 03/04/2025
TO-25-LOU-TAN-2-03 | 275kV FEEDER - LOUTH 275-TANDRAGEE 275-2 | 4 | 4 | 4 | Scheduled | 31/03/2025 | 03/04/2025
TO-25-SLB-110K2-02 | COUPLER/SECTIONALISING CB - SLIABH BAWN 110-SLIABH BAWN 110-110K2 | 2 | 2 | 2 | Scheduled | 01/04/2025 | 02/04/2025
TO-25-TEN-T132-02 | GENERATOR TRANSFORMER - TIMAHOE 110-TIMAHOE 33-T132 | 1 | 1 | 1 | Scheduled | 04/04/2025 | 04/04/2025
TO-25-NAV-T142-01 | DISTRIBUTION TRANSFORMER - NAVAN 110-NAVAN 38-T142 | 99 | 67 |  | Reference | 07/04/2025 | 14/07/2025
TO-25-BLU-MUL-1-05 | 110kV FEEDER - BLUNDELSTOWN 110-MULLINGAR 110-1 | 1 | 1 | 1 | Scheduled | 09/04/2025 | 09/04/2025
TO-25-110 kV B1 @ LOU-04 | BUSBAR SECTION - LOUTH 110-LOUTH 110-110B1 | 1 | 1 | 1 | Scheduled | 15/04/2025 | 15/04/2025
TO-25-LOU-T2101-08 | TRANSFORMER - LOUTH 220-LOUTH 110-T2101 | 2 | 2 | 2 | Scheduled | 16/04/2025 | 17/04/2025
TO-25-ARV-COS-1-03 | 110kV FEEDER - ARVA 110-CARRICK ON SHANNON 110-1 | 4 | 0 | 0 | Scheduled | 18/04/2025 | 21/04/2025
TO-25-220 kV A2 @ SH-02 | BUSBAR SECTION - SHANNONBRIDGE 220-SHANNONBRIDGE 220-220A2 | 46 | 32 | 32 | Scheduled | 22/04/2025 | 06/06/2025
TO-25-220 kV B2 @ SH-02 | BUSBAR SECTION - SHANNONBRIDGE 220-SHANNONBRIDGE 220-220B2 | 46 | 32 | 32 | Scheduled | 22/04/2025 | 06/06/2025
TO-25-IKE,T-SH-1-01 | 110kV FEEDER - IKERRIN tee-SHANNONBRIDGE 110-1 | 2 | 2 | 2 | Scheduled | 24/04/2025 | 25/04/2025
TO-25-GAR-110K1-01 | COUPLER/SECTIONALISING CB - GARBALLAGH 110-GARBALLAGH 110-110K1 | 5 | 5 | 5 | Scheduled | 28/04/2025 | 02/05/2025
TO-25-GAR-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - GARBALLAGH 110-GARBALLAGH 110-110SA1-2CB | 5 | 5 | 5 | Scheduled | 28/04/2025 | 02/05/2025
TO-25-GAR-110SB1-2CB-01 | COUPLER/SECTIONALISING CB - GARBALLAGH 110-GARBALLAGH 110-110SB1-2CB | 5 | 5 | 5 | Scheduled | 28/04/2025 | 02/05/2025
TO-25-LSA-SKL-1-02 | 110kV FEEDER - LISLEA 110-SHANKILL 110-1 | 12 | 9 | 9 | Scheduled | 28/04/2025 | 09/05/2025
TO-25-PLA-T101/2/3/4-02 | TSO CUSTOMER TRANSFORMER - PLATIN 110-PLATIN 10-T101/2/3/4 | 14 | 9 | 9 | Scheduled | 29/04/2025 | 12/05/2025
TO-25-BLU-MUL-1-02 | 110kV FEEDER - BLUNDELSTOWN 110-MULLINGAR 110-1 | 11 | 9 | 9 | Scheduled | 06/05/2025 | 16/05/2025
TO-25-220 kV A2 @ LOU-02 | BUSBAR SECTION - LOUTH 220-LOUTH 220-220A2 | 25 | 19 | 19 | Scheduled | 06/05/2025 | 30/05/2025
TO-25-LOU-MLN-1-01 | 110kV FEEDER - LOUTH 110-MULLAGHARLIN 110-1 | 10 | 8 | 8 | Scheduled | 07/05/2025 | 16/05/2025
TO-25-GOR-MTH-1-01 | 110kV FEEDER - GORMAN 110-MEATH HILL 110-1 | 19 | 15 | 15 | Scheduled | 12/05/2025 | 30/05/2025
TO-25-RRU-T121-02 | GENERATOR TRANSFORMER - RATRUSSAN 110-RATRUSSAN 20-T121 | 3 | 3 | 3 | Scheduled | 12/05/2025 | 14/05/2025
TO-25-GOR-T122-01 | GENERATOR TRANSFORMER - GORMAN 110-GORMAN 20-T122 | 2 | 2 | 2 | Scheduled | 14/05/2025 | 15/05/2025
TO-25-MLC-T121-02 | GENERATOR TRANSFORMER - MOUNTLUCAS 110-MOUNTLUCAS 20-T121 | 2 | 2 | 2 | Scheduled | 14/05/2025 | 15/05/2025
TO-25-LSA-T131-02 | GENERATOR TRANSFORMER - LISLEA 110-LISLEA 33-T131 | 1 | 1 | 1 | Scheduled | 15/05/2025 | 15/05/2025
TO-25-KIN-T1/T2-02 | GENERATOR TRANSFORMER - KINNEGAD 110-RHODE 110-T1/T2 | 19 | 12 | 12 | Scheduled | 16/05/2025 | 03/06/2025
TO-25-LSA-T131-01 | GENERATOR TRANSFORMER - LISLEA 110-LISLEA 33-T131 | 3 | 3 | 3 | Scheduled | 20/05/2025 | 22/05/2025
TO-25-DEY-T134-02 | GENERATOR TRANSFORMER - DERRYCARNEY 110-DERRYCARNEY 33-T134 | 1 | 1 | 1 | Scheduled | 26/05/2025 | 26/05/2025
TO-25-DDK-110SA1-02 | SECTIONALISING DISCONNECT - DUNDALK 110-DUNDALK 110-110SA1 | 9 | 6 | 6 | Scheduled | 29/05/2025 | 06/06/2025
TO-25-DDK-110SA2-01 | SECTIONALISING DISCONNECT - DUNDALK 110-DUNDALK 110-110SA2 | 9 | 6 | 6 | Scheduled | 29/05/2025 | 06/06/2025
TO-25-DDK-LOU-1-03 | 110kV FEEDER - DUNDALK 110-LOUTH 110-1 | 9 | 6 | 6 | Scheduled | 29/05/2025 | 06/06/2025
TO-25-DDK-T142-01 | DISTRIBUTION TRANSFORMER - DUNDALK 110-DUNDALK 38-T142 | 9 | 6 | 6 | Reference | 29/05/2025 | 06/06/2025
TO-25-GOR-NAV-3-01 | 110kV FEEDER - GORMAN 110-NAVAN 110-3 | 4 | 4 | 4 | Scheduled | 03/06/2025 | 06/06/2025
TO-25-BLU-MUL-1-01 | 110kV FEEDER - BLUNDELSTOWN 110-MULLINGAR 110-1 | 2 | 2 | 2 | Scheduled | 05/06/2025 | 06/06/2025
TO-25-CUS-MLC-1-02 | 110kV FEEDER - CUSHALING 110-MOUNTLUCAS 110-1 | 2 | 2 | 2 | Scheduled | 05/06/2025 | 06/06/2025
TO-25-MUL-110SA1-2CB-02 | COUPLER/SECTIONALISING CB - MULLINGAR 110-MULLINGAR 110-110SA1-2CB | 2 | 2 | 2 | Scheduled | 05/06/2025 | 06/06/2025
TO-25-MUL-CAP2-02 | CAPACITOR/SVC/REACTOR - MULLINGAR 110-MULLINGAR 110-CAP2 | 2 | 2 | 2 | Scheduled | 05/06/2025 | 06/06/2025
TO-25-MUL-T102-01 | DISTRIBUTION TRANSFORMER - MULLINGAR 110-MULLINGAR 10-T102 | 2 | 2 | 2 | Reference | 05/06/2025 | 06/06/2025
TO-25-MUL-T142-01 | DISTRIBUTION TRANSFORMER - MULLINGAR 110-MULLINGAR 38-T142 | 2 | 2 | 2 | Reference | 05/06/2025 | 06/06/2025
TO-25-SH-220K1-2-01 | COUPLER/SECTIONALISING CB - SHANNONBRIDGE 220-SHANNONBRIDGE 220-220K1-2 | 2 | 2 | 2 | Scheduled | 05/06/2025 | 06/06/2025
TO-25-OBE-PLA-1-02 | 110kV FEEDER - OLDBRIDGE 110-PLATIN 110-1 | 71 | 50 | 50 | Scheduled | 09/06/2025 | 18/08/2025
TO-25-SLB-T132-02 | GENERATOR TRANSFORMER - SLIABH BAWN 110-SLIABH BAWN 33-T132 | 2 | 2 | 2 | Scheduled | 11/06/2025 | 12/06/2025
TO-25-LOU-WOO-1-04 | 220kV FEEDER - LOUTH 220-WOODLAND 220-1 | 3 | 3 | 3 | Scheduled | 17/06/2025 | 19/06/2025
TO-25-KLN-SH-1-04 | 220kV FEEDER - KILLONAN 220-SHANNONBRIDGE 220-1 | 3 | 3 | 3 | Scheduled | 18/06/2025 | 20/06/2025
TO-25-KLN-SH-1-01 | 220kV FEEDER - KILLONAN 220-SHANNONBRIDGE 220-1 | 5 | 5 | 5 | Scheduled | 23/06/2025 | 27/06/2025
TO-25-220 kV A1 @ LOU-02 | BUSBAR SECTION - LOUTH 220-LOUTH 220-220A1 | 47 | 34 |  | Scheduled | 23/06/2025 | 08/08/2025
TO-25-220 kV A2 @ LOU-03 | BUSBAR SECTION - LOUTH 220-LOUTH 220-220A2 | 47 | 34 |  | Scheduled | 23/06/2025 | 08/08/2025
TO-25-220 kV B1 @ LOU-02 | BUSBAR SECTION - LOUTH 220-LOUTH 220-220B1 | 47 | 34 |  | Scheduled | 23/06/2025 | 08/08/2025
TO-25-220 kV B2 @ LOU-02 | BUSBAR SECTION - LOUTH 220-LOUTH 220-220B2 | 47 | 34 |  | Scheduled | 23/06/2025 | 08/08/2025
TO-25-110 kV B1 @ SH-03 | BUSBAR SECTION - SHANNONBRIDGE 110-SHANNONBRIDGE 110-110B1 | 2 | 2 | 2 | Scheduled | 23/06/2025 | 24/06/2025
TO-25-SH-110K1-2-02 | COUPLER/SECTIONALISING CB - SHANNONBRIDGE 110-SHANNONBRIDGE 110-110K1-2 | 2 | 2 | 2 | Scheduled | 23/06/2025 | 24/06/2025
TO-25-IKE,T-SH-1-02 | 110kV FEEDER - IKERRIN tee-SHANNONBRIDGE 110-1 | 14 | 10 |  | Scheduled | 25/06/2025 | 08/07/2025
TO-25-KLN-SH-1-05 | 220kV FEEDER - KILLONAN 220-SHANNONBRIDGE 220-1 | 2 | 2 | 2 | Scheduled | 30/06/2025 | 01/07/2025
TO-25-LOU-AT3-02 | TRANSFORMER - LOUTH 220-LOUTH 275-AT3 | 60 | 43 |  | Scheduled | 30/06/2025 | 28/08/2025
TO-25-RRU-T122-01 | GENERATOR TRANSFORMER - RATRUSSAN 110-RATRUSSAN 20-T122 | 5 | 5 | 5 | Scheduled | 30/06/2025 | 04/07/2025
TO-25-220 kV A1 @ SH-01 | BUSBAR SECTION - SHANNONBRIDGE 220-SHANNONBRIDGE 220-220A1 | 2 | 2 | 2 | Scheduled | 30/06/2025 | 01/07/2025
TO-25-220 kV A2 @ SH-03 | BUSBAR SECTION - SHANNONBRIDGE 220-SHANNONBRIDGE 220-220A2 | 2 | 2 | 2 | Scheduled | 30/06/2025 | 01/07/2025
TO-25-220 kV B1 @ SH-01 | BUSBAR SECTION - SHANNONBRIDGE 220-SHANNONBRIDGE 220-220B1 | 2 | 2 | 2 | Scheduled | 30/06/2025 | 01/07/2025
TO-25-220 kV B2 @ SH-03 | BUSBAR SECTION - SHANNONBRIDGE 220-SHANNONBRIDGE 220-220B2 | 2 | 2 | 2 | Scheduled | 30/06/2025 | 01/07/2025
TO-25-SH-T102/4-01 | GENERATOR TRANSFORMER - SHANNONBRIDGE 110-SHANNONBRIDGE G2/4-T102/4 | 38 | 27 | 27 | Scheduled | 30/06/2025 | 06/08/2025
TO-25-110 kV A2 @ LOU-01 | BUSBAR SECTION - LOUTH 110-LOUTH 110-110A2 | 88 | 63 | 63 | Scheduled | 01/07/2025 | 26/09/2025
TO-25-110 kV B2 @ LOU-01 | BUSBAR SECTION - LOUTH 110-LOUTH 110-110B2 | 88 | 63 | 63 | Scheduled | 01/07/2025 | 26/09/2025
TO-25-MAY-SH-1-03 | 220kV FEEDER - MAYNOOTH 220-SHANNONBRIDGE 220-1 | 136 | 96 | 96 | Scheduled | 02/07/2025 | 14/11/2025
TO-25-110 kV A2 @ SH-01 | BUSBAR SECTION - SHANNONBRIDGE 110-SHANNONBRIDGE 110-110A2 | 12 | 10 | 10 | Scheduled | 07/07/2025 | 18/07/2025
TO-25-110 kV B2 @ SH-01 | BUSBAR SECTION - SHANNONBRIDGE 110-SHANNONBRIDGE 110-110B2 | 12 | 10 | 10 | Scheduled | 07/07/2025 | 18/07/2025
TO-25-220 kV A2 @ SH-06 | BUSBAR SECTION - SHANNONBRIDGE 220-SHANNONBRIDGE 220-220A2 | 12 | 10 | 10 | Scheduled | 07/07/2025 | 18/07/2025
TO-25-220 kV B2 @ SH-06 | BUSBAR SECTION - SHANNONBRIDGE 220-SHANNONBRIDGE 220-220B2 | 12 | 10 | 10 | Scheduled | 07/07/2025 | 18/07/2025
TO-25-SH-T2102-01 | TRANSFORMER - SHANNONBRIDGE 220-SHANNONBRIDGE 110-T2102 | 85 | 60 | 60 | Scheduled | 07/07/2025 | 29/09/2025
TO-25-IKE,T-SH-1-05 | 110kV FEEDER - IKERRIN tee-SHANNONBRIDGE 110-1 | 58 | 41 | 41 | Scheduled | 08/07/2025 | 03/09/2025
TO-25-ATH-SH-1-08 | 110kV FEEDER - ATHLONE 110-SHANNONBRIDGE 110-1 | 3 | 1 | 1 | Scheduled | 11/07/2025 | 13/07/2025
TO-25-LOU-MTH-1-02 | 110kV FEEDER - LOUTH 110-MEATH HILL 110-1 | 3 | 3 | 3 | Scheduled | 15/07/2025 | 17/07/2025
TO-25-DEY-T132-02 | GENERATOR TRANSFORMER - DERRYCARNEY 110-DERRYCARNEY 33-T132 | 2 | 2 | 2 | Scheduled | 21/07/2025 | 22/07/2025
TO-25-KDN-T131-01 | GENERATOR TRANSFORMER - KNOCKDRIN 110-KNOCKDRIN 33-T131 | 44 | 31 | 31 | Scheduled | 21/07/2025 | 02/09/2025
TO-25-KDN-T131-02 | GENERATOR TRANSFORMER - KNOCKDRIN 110-KNOCKDRIN 33-T131 | 72 | 51 | 51 | Scheduled | 21/07/2025 | 30/09/2025
TO-25-KDN,T-KDN-1-01 | 110kV FEEDER - KNOCKDRIN tee-KNOCKDRIN 110-1 | 44 | 31 | 31 | Scheduled | 21/07/2025 | 02/09/2025
TO-25-KDN,T-KDN-1-02 | 110kV FEEDER - KNOCKDRIN tee-KNOCKDRIN 110-1 | 72 | 51 | 51 | Scheduled | 21/07/2025 | 30/09/2025
TO-25-KDN,T-TSB-1-01 | 110kV FEEDER - KNOCKDRIN tee-THORNSBERRY 110-1 | 44 | 31 | 31 | Scheduled | 21/07/2025 | 02/09/2025
TO-25-KDN,T-TSB-1-03 | 110kV FEEDER - KNOCKDRIN tee-THORNSBERRY 110-1 | 72 | 51 | 51 | Scheduled | 21/07/2025 | 30/09/2025
TO-25-KDN,T-TEN-1-02 | 110kV FEEDER - KNOCKDRIN tee-TIMAHOE 110-1 | 44 | 31 | 31 | Scheduled | 21/07/2025 | 02/09/2025
TO-25-KDN,T-TEN-1-03 | 110kV FEEDER - KNOCKDRIN tee-TIMAHOE 110-1 | 72 | 51 | 51 | Scheduled | 21/07/2025 | 30/09/2025
TO-25-SH-T101/3-01 | GENERATOR TRANSFORMER - SHANNONBRIDGE 110-SHANNONBRIDGE G1/3-T101/3 | 39 | 28 | 28 | Scheduled | 21/07/2025 | 28/08/2025
TO-25-110 kV B1 @ LOU-06 | BUSBAR SECTION - LOUTH 110-LOUTH 110-110B1 | 1 | 1 | 1 | Scheduled | 23/07/2025 | 23/07/2025
TO-25-LOU-110K1-2-04 | COUPLER/SECTIONALISING CB - LOUTH 110-LOUTH 110-110K1-2 | 1 | 1 | 1 | Scheduled | 23/07/2025 | 23/07/2025
TO-25-LIS-T142-01 | DISTRIBUTION TRANSFORMER - LISDRUM 110-LISDRUM 38-T142 | 99 | 69 | 69 | Reference | 28/07/2025 | 03/11/2025
TO-25-LIS-LOU-1-02 | 110kV FEEDER - LISDRUM 110-LOUTH 110-1 | 23 | 16 | 16 | Scheduled | 29/07/2025 | 20/08/2025
TO-25-DFR-T122-01 | DISTRIBUTION TRANSFORMER - DUNFIRTH 110-DUNFIRTH 20-T122 | 20 | 13 | 13 | Reference | 30/07/2025 | 18/08/2025
TO-25-DFR,T-DFR-1-03 | 110kV FEEDER - DUNFIRTH tee-DUNFIRTH 110-1 | 20 | 13 | 13 | Scheduled | 30/07/2025 | 18/08/2025
TO-25-DFR,T-KIN-1-03 | 110kV FEEDER - DUNFIRTH tee-KINNEGAD 110-1 | 20 | 13 | 13 | Scheduled | 30/07/2025 | 18/08/2025
TO-25-DFR,T-RNW-1-02 | 110kV FEEDER - DUNFIRTH tee-RINAWADE 110-1 | 36 | 25 |  | Scheduled | 30/07/2025 | 03/09/2025
TO-25-MLN-T124-01 | TSO CUSTOMER TRANSFORMER - MULLAGHARLIN 110-MULLAGHARLIN 20-T124 | 2 | 2 | 2 | Scheduled | 05/08/2025 | 06/08/2025
TO-25-110 kV A2 @ TEN-01 | BUSBAR SECTION - TIMAHOE 110-TIMAHOE 110-110A2 | 3 | 3 | 3 | Scheduled | 05/08/2025 | 07/08/2025
TO-25-110 kV B2 @ TEN-01 | BUSBAR SECTION - TIMAHOE 110-TIMAHOE 110-110B2 | 3 | 3 | 3 | Scheduled | 05/08/2025 | 07/08/2025
TO-25-TEN-110K2-01 | COUPLER/SECTIONALISING CB - TIMAHOE 110-TIMAHOE 110-110K2 | 3 | 3 | 3 | Scheduled | 05/08/2025 | 07/08/2025
TO-25-MLN-T123-02 | TSO CUSTOMER TRANSFORMER - MULLAGHARLIN 110-MULLAGHARLIN 20-T123 | 2 | 2 | 2 | Scheduled | 07/08/2025 | 08/08/2025
TO-25-220 kV A1 @ GOR-02 | BUSBAR SECTION - GORMAN 220-GORMAN 220-220A1 | 12 | 10 | 10 | Scheduled | 11/08/2025 | 22/08/2025
TO-25-220 kV A2 @ GOR-01 | BUSBAR SECTION - GORMAN 220-GORMAN 220-220A2 | 12 | 10 | 10 | Scheduled | 11/08/2025 | 22/08/2025
TO-25-GOR-LOU-1-02 | 220kV FEEDER - GORMAN 220-LOUTH 220-1 | 12 | 10 | 10 | Scheduled | 11/08/2025 | 22/08/2025
TO-25-220 kV A2 @ LOU-09 | BUSBAR SECTION - LOUTH 220-LOUTH 220-220A2 | 12 | 10 | 10 | Scheduled | 11/08/2025 | 22/08/2025
TO-25-220 kV B2 @ LOU-09 | BUSBAR SECTION - LOUTH 220-LOUTH 220-220B2 | 12 | 10 | 10 | Scheduled | 11/08/2025 | 22/08/2025
TO-25-DER-KIN-1-03 | 110kV FEEDER - DERRYIRON 110-KINNEGAD 110-1 | 22 | 16 | 16 | Scheduled | 12/08/2025 | 02/09/2025
TO-25-DER-T1/T2-02 | GENERATOR TRANSFORMER - DERRYIRON 110-RHODE 110-T1/T2 | 22 | 16 | 16 | Scheduled | 12/08/2025 | 02/09/2025
TO-25-LOU-T2103-05 | TRANSFORMER - LOUTH 220-LOUTH 110-T2103 | 21 | 15 | 15 | Proposed | 18/08/2025 | 07/09/2025
TO-25-220 kV A2 @ LOU-04 | BUSBAR SECTION - LOUTH 220-LOUTH 220-220A2 | 4 | 4 | 4 | Proposed | 25/08/2025 | 28/08/2025
TO-25-220 kV B2 @ LOU-03 | BUSBAR SECTION - LOUTH 220-LOUTH 220-220B2 | 4 | 4 | 4 | Proposed | 25/08/2025 | 28/08/2025
TO-25-TY-T2001/2-04 | GENERATOR TRANSFORMER - TYNAGH 220-TYNAGH G1/2-T2001/2 | 38 | 28 | 28 | Proposed | 26/08/2025 | 02/10/2025
TO-25-GOR-LOU-1-01 | 220kV FEEDER - GORMAN 220-LOUTH 220-1 | 2 | 2 |  | Proposed | 27/08/2025 | 28/08/2025
TO-25-IKE,T-SH-1-08 | 110kV FEEDER - IKERRIN tee-SHANNONBRIDGE 110-1 | 2 | 2 | 2 | Proposed | 27/08/2025 | 28/08/2025
TO-25-220 kV A2 @ LOU-05 | BUSBAR SECTION - LOUTH 220-LOUTH 220-220A2 | 2 | 2 | 2 | Proposed | 27/08/2025 | 28/08/2025
TO-25-220 kV B2 @ LOU-05 | BUSBAR SECTION - LOUTH 220-LOUTH 220-220B2 | 2 | 2 | 2 | Proposed | 27/08/2025 | 28/08/2025
TO-25-110 kV A1 @ SH-03 | BUSBAR SECTION - SHANNONBRIDGE 110-SHANNONBRIDGE 110-110A1 | 2 | 2 |  | Proposed | 27/08/2025 | 28/08/2025
TO-25-110 kV B1 @ SH-04 | BUSBAR SECTION - SHANNONBRIDGE 110-SHANNONBRIDGE 110-110B1 | 2 | 2 | 2 | Proposed | 27/08/2025 | 28/08/2025
TO-25-SH-110K1-2-04 | COUPLER/SECTIONALISING CB - SHANNONBRIDGE 110-SHANNONBRIDGE 110-110K1-2 | 2 | 2 | 2 | Proposed | 27/08/2025 | 28/08/2025
TO-25-TY-T2001/2-01 | GENERATOR TRANSFORMER - TYNAGH 220-TYNAGH G1/2-T2001/2 | 37 | 27 | 27 | Scheduled | 27/08/2025 | 02/10/2025
TO-25-TY-T2001/2-02 | GENERATOR TRANSFORMER - TYNAGH 220-TYNAGH G1/2-T2001/2 | 7 | 5 | 5 | Scheduled | 27/08/2025 | 02/09/2025
TO-25-TSB-110SA1-01 | SECTIONALISING DISCONNECT - THORNSBERRY 110-THORNSBERRY 110-110SA1 | 2 | 0 | 0 | Scheduled | 30/08/2025 | 31/08/2025
TO-25-TSB-110SA2-01 | SECTIONALISING DISCONNECT - THORNSBERRY 110-THORNSBERRY 110-110SA2 | 2 | 0 | 0 | Scheduled | 30/08/2025 | 31/08/2025
TO-25-TSB-T142-01 | DISTRIBUTION TRANSFORMER - THORNSBERRY 110-THORNSBERRY 38-T142 | 2 | 0 | 0 | Reference | 30/08/2025 | 31/08/2025
TO-25-CSH-TY-1-02 | 220kV FEEDER - CASHLA 220-TYNAGH 220-1 | 5 | 5 | 5 | Scheduled | 01/09/2025 | 05/09/2025
TO-25-DDK-110SA1-01 | SECTIONALISING DISCONNECT - DUNDALK 110-DUNDALK 110-110SA1 | 5 | 5 | 5 | Scheduled | 01/09/2025 | 05/09/2025
TO-25-DDK-110SA2-02 | SECTIONALISING DISCONNECT - DUNDALK 110-DUNDALK 110-110SA2 | 5 | 5 | 5 | Scheduled | 01/09/2025 | 05/09/2025
TO-25-DDK-MLN-1-01 | 110kV FEEDER - DUNDALK 110-MULLAGHARLIN 110-1 | 5 | 5 | 5 | Scheduled | 01/09/2025 | 05/09/2025
TO-25-DDK-T141-01 | DISTRIBUTION TRANSFORMER - DUNDALK 110-DUNDALK 38-T141 | 5 | 5 | 5 | Reference | 01/09/2025 | 05/09/2025
TO-25-DFR-T122-02 | DISTRIBUTION TRANSFORMER - DUNFIRTH 110-DUNFIRTH 20-T122 | 3 | 3 | 3 | Reference | 01/09/2025 | 03/09/2025
TO-25-DFR,T-DFR-1-02 | 110kV FEEDER - DUNFIRTH tee-DUNFIRTH 110-1 | 3 | 3 | 3 | Scheduled | 01/09/2025 | 03/09/2025
TO-25-DFR,T-KIN-1-02 | 110kV FEEDER - DUNFIRTH tee-KINNEGAD 110-1 | 3 | 3 | 3 | Scheduled | 01/09/2025 | 03/09/2025
TO-25-LIS-CAP2-02 | CAPACITOR/SVC/REACTOR - LISDRUM 110-LISDRUM 110-CAP2 | 5 | 5 | 5 | Scheduled | 01/09/2025 | 05/09/2025
TO-25-DER-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - DERRYIRON 110-DERRYIRON 110-110SA1-2CB | 10 | 8 | 8 | Scheduled | 03/09/2025 | 12/09/2025
TO-25-DER-KIN-1-04 | 110kV FEEDER - DERRYIRON 110-KINNEGAD 110-1 | 10 | 8 | 8 | Scheduled | 03/09/2025 | 12/09/2025
TO-25-LOU-RRU-1-01 | 110kV FEEDER - LOUTH 110-RATRUSSAN 110-1 | 21 | 15 | 15 | Proposed | 03/09/2025 | 23/09/2025
TO-25-LOU-RRU-1-02 | 110kV FEEDER - LOUTH 110-RATRUSSAN 110-1 | 57 | 40 | 40 | Proposed | 03/09/2025 | 29/10/2025
TO-25-LOU-RRU-1-03 | 110kV FEEDER - LOUTH 110-RATRUSSAN 110-1 | 57 | 40 | 40 | Scheduled | 03/09/2025 | 29/10/2025
TO-25-IKE,T-SH-1-04 | 110kV FEEDER - IKERRIN tee-SHANNONBRIDGE 110-1 | 28 | 20 |  | Proposed | 04/09/2025 | 01/10/2025
TO-25-AGL-ENN-1-01 | 110kV FEEDER - AGANNYGAL 110-ENNIS 110-1 | 10 | 8 | 8 | Proposed | 08/09/2025 | 17/09/2025
TO-25-CF-COR-1-02 | 110kV FEEDER - CATHALEENS FALL 110-CORRACLASSY 110-1 | 5 | 5 | 5 | Proposed | 08/09/2025 | 12/09/2025
TO-25-CF-COR-1-03 | 110kV FEEDER - CATHALEENS FALL 110-CORRACLASSY 110-1 | 12 | 10 | 10 | Scheduled | 08/09/2025 | 19/09/2025
TO-25-110 kV A1/A2 @ GOR-01 | BUSBAR SECTION - GORMAN 110-GORMAN 110-110A1-A2 | 11 | 9 | 9 | Scheduled | 08/09/2025 | 18/09/2025
TO-25-110 kV B1/B2 @ GOR-01 | BUSBAR SECTION - GORMAN 110-GORMAN 110-110B1-B2 | 11 | 9 | 9 | Scheduled | 08/09/2025 | 18/09/2025
TO-25-GOR-110K1-2-03 | COUPLER/SECTIONALISING CB - GORMAN 110-GORMAN 110-110K1-2 | 11 | 9 | 9 | Scheduled | 08/09/2025 | 18/09/2025
TO-25-220 kV A1 @ GOR-03 | BUSBAR SECTION - GORMAN 220-GORMAN 220-220A1 | 12 | 10 | 10 | Scheduled | 08/09/2025 | 19/09/2025
TO-25-220 kV B1 @ GOR-02 | BUSBAR SECTION - GORMAN 220-GORMAN 220-220B1 | 12 | 10 | 10 | Scheduled | 08/09/2025 | 19/09/2025
TO-25-GOR-MAY-1-03 | 220kV FEEDER - GORMAN 220-MAYNOOTH 220-1 | 12 | 10 | 10 | Proposed | 08/09/2025 | 19/09/2025
TO-25-GOR-MAY-1-01 | 220kV FEEDER - GORMAN 220-MAYNOOTH 220-1 | 12 | 10 | 10 | Scheduled | 08/09/2025 | 19/09/2025
TO-25-LA-RIC-2-02 | 110kV FEEDER - LANESBORO 110-RICHMOND 110-2 | 2 | 2 | 2 | Reference (Proposed) | 08/09/2025 | 09/09/2025
TO-25-110 kV A1 @ SH-02 | BUSBAR SECTION - SHANNONBRIDGE 110-SHANNONBRIDGE 110-110A1 | 2 | 2 |  | Proposed | 09/09/2025 | 10/09/2025
TO-25-110 kV B1 @ SH-01 | BUSBAR SECTION - SHANNONBRIDGE 110-SHANNONBRIDGE 110-110B1 | 2 | 2 | 2 | Proposed | 09/09/2025 | 10/09/2025
TO-25-OBE-110K1-01 | COUPLER/SECTIONALISING CB - OLDBRIDGE 110-OLDBRIDGE 110-110K1 | 3 | 3 | 3 | Scheduled | 10/09/2025 | 12/09/2025
TO-25-OBE-110K2-01 | COUPLER/SECTIONALISING CB - OLDBRIDGE 110-OLDBRIDGE 110-110K2 | 3 | 3 | 3 | Scheduled | 10/09/2025 | 12/09/2025
TO-25-OBE-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - OLDBRIDGE 110-OLDBRIDGE 110-110SA1-2CB | 3 | 3 | 3 | Scheduled | 10/09/2025 | 12/09/2025
TO-25-OBE-110SB1-2CB-01 | COUPLER/SECTIONALISING CB - OLDBRIDGE 110-OLDBRIDGE 110-110SB1-2CB | 3 | 3 | 3 | Scheduled | 10/09/2025 | 12/09/2025
TO-25-MAY-TEN-1-01 | 110kV FEEDER - MAYNOOTH 110-TIMAHOE 110-1 | 87 | 62 | 62 | Scheduled | 15/09/2025 | 10/12/2025
TO-25-MLC-TSB-1-01 | 110kV FEEDER - MOUNTLUCAS 110-THORNSBERRY 110-1 | 5 | 5 | 5 | Proposed | 15/09/2025 | 19/09/2025
TO-25-220 kV A2 @ SH-07 | BUSBAR SECTION - SHANNONBRIDGE 220-SHANNONBRIDGE 220-220A2 | 2 | 2 | 2 | Proposed | 15/09/2025 | 16/09/2025
TO-25-220 kV B2 @ SH-07 | BUSBAR SECTION - SHANNONBRIDGE 220-SHANNONBRIDGE 220-220B2 | 2 | 2 | 2 | Proposed | 15/09/2025 | 16/09/2025
TO-25-SH-220K1-2-03 | COUPLER/SECTIONALISING CB - SHANNONBRIDGE 220-SHANNONBRIDGE 220-220K1-2 | 2 | 2 | 2 | Proposed | 15/09/2025 | 16/09/2025
TO-25-TSB-110SA1-02 | SECTIONALISING DISCONNECT - THORNSBERRY 110-THORNSBERRY 110-110SA1 | 5 | 5 | 5 | Proposed | 15/09/2025 | 19/09/2025
TO-25-TSB-110SA2-02 | SECTIONALISING DISCONNECT - THORNSBERRY 110-THORNSBERRY 110-110SA2 | 5 | 5 | 5 | Proposed | 15/09/2025 | 19/09/2025
TO-25-TSB-T141-01 | DISTRIBUTION TRANSFORMER - THORNSBERRY 110-THORNSBERRY 38-T141 | 5 | 5 | 5 | Reference (Proposed) | 15/09/2025 | 19/09/2025
TO-25-KIN-MUL-1-02 | 110kV FEEDER - KINNEGAD 110-MULLINGAR 110-1 | 21 | 15 | 15 | Proposed | 16/09/2025 | 06/10/2025
TO-25-TEN-T132-01 | GENERATOR TRANSFORMER - TIMAHOE 110-TIMAHOE 33-T132 | 1 | 1 | 1 | Proposed | 17/09/2025 | 17/09/2025
TO-25-110 kV A2 @ SH-02 | BUSBAR SECTION - SHANNONBRIDGE 110-SHANNONBRIDGE 110-110A2 | 2 | 2 | 2 | Proposed | 18/09/2025 | 19/09/2025
TO-25-110 kV B2 @ SH-02 | BUSBAR SECTION - SHANNONBRIDGE 110-SHANNONBRIDGE 110-110B2 | 2 | 2 | 2 | Proposed | 18/09/2025 | 19/09/2025
TO-25-SH-110K1-2-03 | COUPLER/SECTIONALISING CB - SHANNONBRIDGE 110-SHANNONBRIDGE 110-110K1-2 | 2 | 2 | 2 | Proposed | 18/09/2025 | 19/09/2025
TO-25-LIS-T131-01 | GENERATOR TRANSFORMER - LISDRUM 110-LISDRUM 33-T131 | 10 | 8 | 8 | Scheduled | 22/09/2025 | 01/10/2025
TO-25-110 kV A1 @ SH-01 | BUSBAR SECTION - SHANNONBRIDGE 110-SHANNONBRIDGE 110-110A1 | 2 | 2 | 2 | Proposed | 30/09/2025 | 01/10/2025
TO-25-SH-T2101-04 | TRANSFORMER - SHANNONBRIDGE 220-SHANNONBRIDGE 110-T2101 | 2 | 2 | 2 | Proposed | 30/09/2025 | 01/10/2025
TO-25-IKE,T-SH-1-07 | 110kV FEEDER - IKERRIN tee-SHANNONBRIDGE 110-1 | 2 | 2 | 2 | Proposed | 06/10/2025 | 07/10/2025
TO-25-DRY-GOR-1-01 | 110kV FEEDER - DRYBRIDGE 110-GORMAN 110-1 | Unknown | Unknown | 40 | Planned | October | December
TO-25-DRY-GOR-1-05 | 110kV FEEDER - DRYBRIDGE 110-GORMAN 110-1 | Unknown | Unknown | 40 | Planned | October | December
TO-25-AGL-SH-1-01 | 110kV FEEDER - AGANNYGAL 110-SHANNONBRIDGE 110-1 | Unknown | Unknown | 4 | Planned | October | October
TO-25-ATH-SH-1-07 | 110kV FEEDER - ATHLONE 110-SHANNONBRIDGE 110-1 | Unknown | Unknown | 4 | Planned | October | October
TO-25-AGL-SH-1-02 | 110kV FEEDER - AGANNYGAL 110-SHANNONBRIDGE 110-1 | Unknown | Unknown | 15 | Planned | October | November
TO-25-220 kV A1 @ SH-04 | BUSBAR SECTION - SHANNONBRIDGE 220-SHANNONBRIDGE 220-220A1 | 2 | 2 | 2 | Scheduled | 29/10/2025 | 30/10/2025
TO-25-220 kV B1 @ SH-02 | BUSBAR SECTION - SHANNONBRIDGE 220-SHANNONBRIDGE 220-220B1 | 2 | 2 | 2 | Scheduled | 29/10/2025 | 30/10/2025
TO-25-LIS-110SA1-01 | SECTIONALISING DISCONNECT - LISDRUM 110-LISDRUM 110-110SA1 | 1 | 1 | 1 | Scheduled | 03/11/2025 | 03/11/2025
TO-25-LIS-110SA2-01 | SECTIONALISING DISCONNECT - LISDRUM 110-LISDRUM 110-110SA2 | 1 | 1 | 1 | Scheduled | 03/11/2025 | 03/11/2025
TO-25-LIS-CAP2-01 | CAPACITOR/SVC/REACTOR - LISDRUM 110-LISDRUM 110-CAP2 | 1 | 1 | 1 | Scheduled | 03/11/2025 | 03/11/2025
TO-25-LIS-LSA-1-01 | 110kV FEEDER - LISDRUM 110-LISLEA 110-1 | 1 | 1 | 1 | Scheduled | 03/11/2025 | 03/11/2025
TO-25-110 kV A2 @ LOU-03 | BUSBAR SECTION - LOUTH 110-LOUTH 110-110A2 | Unknown | Unknown | 3 | Planned | November | November
TO-25-110 kV B2 @ LOU-03 | BUSBAR SECTION - LOUTH 110-LOUTH 110-110B2 | Unknown | Unknown |  | Planned | November | November
TO-25-110 kV B1 @ LOU-02 | BUSBAR SECTION - LOUTH 110-LOUTH 110-110B1 | Unknown | Unknown |  | Planned | November | November
TO-25-LOU-110K1-2-02 | COUPLER/SECTIONALISING CB - LOUTH 110-LOUTH 110-110K1-2 | Unknown | Unknown |  | Planned | November | November
TO-25-LOU-T2103-03 | TRANSFORMER - LOUTH 220-LOUTH 110-T2103 | Unknown | Unknown |  | Planned | November | November
TO-25-DDK-LOU-1-01 | 110kV FEEDER - DUNDALK 110-LOUTH 110-1 | Unknown | Unknown |  | Planned | December | December
TO-25-LIS-LOU-1-01 | 110kV FEEDER - LISDRUM 110-LOUTH 110-1 | Unknown | Unknown |  | Planned | December | December
TO-25-110 kV A2 @ LOU-04 | BUSBAR SECTION - LOUTH 110-LOUTH 110-110A2 | Unknown | Unknown | 2 | Planned | December | December
TO-25-LOU-T2104-02 | TRANSFORMER - LOUTH 220-LOUTH 110-T2104 | Unknown | Unknown |  | Planned | December | December
TO-25-110 kV B2 @ LOU-04 | BUSBAR SECTION - LOUTH 110-LOUTH 110-110B2 | Unknown | Unknown |  | Planned | December | December
TO-25-LOU-T2104-01 | TRANSFORMER - LOUTH 220-LOUTH 110-T2104 | Unknown | Unknown |  | Planned | December | December

## GEN_Dublin
Outage ID | Feeder ID | Calendar Day Duration | Working Day Duration | Work Days | Outage Status | Start | Finish
TO-25-DND-T121-01 | TSO CUSTOMER TRANSFORMER - DARNDALE 110-DARNDALE 20-T121 | 689 | 482 | 482 | Scheduled | 12/02/2024 | 31/12/2025
TO-25-BAL-DRY-1-03 | 110kV FEEDER - BALTRASNA 110-DRYBRIDGE 110-1 | 283 | 201 | 201 | Scheduled | 13/05/2024 | 19/02/2025
TO-25-110 kV B2/B4 @ CDU-01 | BUSBAR SECTION - CORDUFF 110-CORDUFF 110-110B2-B4 | 8 | 6 | 6 | Scheduled | 06/01/2025 | 13/01/2025
TO-25-CDU-110SB2-4-01 | SECTIONALISING DISCONNECT - CORDUFF 110-CORDUFF 110-110SB2-4 | 8 | 6 | 6 | Scheduled | 06/01/2025 | 13/01/2025
TO-25-CDU-110SB2-4CB-04 | COUPLER/SECTIONALISING CB - CORDUFF 110-CORDUFF 110-110SB2-4CB | 8 | 6 | 6 | Scheduled | 06/01/2025 | 13/01/2025
TO-25-FIN-220K1-04 | COUPLER/SECTIONALISING CB - FINGLAS 220-FINGLAS 220-220K1 | 2 | 2 | 2 | Scheduled | 08/01/2025 | 09/01/2025
TO-25-FIN-220K2-05 | COUPLER/SECTIONALISING CB - FINGLAS 220-FINGLAS 220-220K2 | 2 | 2 | 2 | Scheduled | 08/01/2025 | 09/01/2025
TO-25-FIN-220SA1-2CB-08 | COUPLER/SECTIONALISING CB - FINGLAS 220-FINGLAS 220-220SA1-2CB | 2 | 2 | 2 | Scheduled | 08/01/2025 | 09/01/2025
TO-25-CDU-T2102-02 | TRANSFORMER - CORDUFF 220-CORDUFF 110-T2102 | 1 | 1 | 1 | Scheduled | 13/01/2025 | 13/01/2025
TO-25-220 kV B1 @ CBT-02 | BUSBAR SECTION - CASTLEBAGOT 220-CASTLEBAGOT 220-220B1 | 9 | 7 | 7 | Scheduled | 14/01/2025 | 22/01/2025
TO-25-220 kV B2 @ CBT-01 | BUSBAR SECTION - CASTLEBAGOT 220-CASTLEBAGOT 220-220B2 | 9 | 7 | 7 | Scheduled | 14/01/2025 | 22/01/2025
TO-25-CBT-220K1-04 | COUPLER/SECTIONALISING CB - CASTLEBAGOT 220-CASTLEBAGOT 220-220K1 | 9 | 7 | 7 | Scheduled | 14/01/2025 | 22/01/2025
TO-25-CBT-220K2-02 | COUPLER/SECTIONALISING CB - CASTLEBAGOT 220-CASTLEBAGOT 220-220K2 | 9 | 7 | 7 | Scheduled | 14/01/2025 | 22/01/2025
TO-25-CBT-220SB1-2CB-01 | COUPLER/SECTIONALISING CB - CASTLEBAGOT 220-CASTLEBAGOT 220-220SB1-2CB | 9 | 7 | 7 | Scheduled | 14/01/2025 | 22/01/2025
TO-25-BNK-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - BARNAKYLE 110-BARNAKYLE 110-110SA1-2CB | 151 | 101 | 101 | Scheduled | 17/01/2025 | 16/06/2025
TO-25-BNK-CBT-2-01 | 110kV FEEDER - BARNAKYLE 110-CASTLEBAGOT 110-2 | 151 | 101 | 101 | Scheduled | 17/01/2025 | 16/06/2025
TO-25-BNK-T122-01 | TSO CUSTOMER TRANSFORMER - BARNAKYLE 110-BARNAKYLE 20-T122 | 151 | 101 | 101 | Scheduled | 17/01/2025 | 16/06/2025
TO-25-DSN-MAY-2-03 | 220kV FEEDER - DUNSTOWN 220-MAYNOOTH 220-2 | 11 | 9 |  | Scheduled | 20/01/2025 | 30/01/2025
TO-25-INC-PB-1-01 | 220kV FEEDER - INCHICORE 220-POOLBEG 220-1 | 43 | 30 | 30 | Scheduled | 27/01/2025 | 10/03/2025
TO-25-220 kV A2 @ FIN-05 | BUSBAR SECTION - FINGLAS 220-FINGLAS 220-220A2 | 11 | 9 | 9 | Scheduled | 04/02/2025 | 14/02/2025
TO-25-FIN-220K2-08 | COUPLER/SECTIONALISING CB - FINGLAS 220-FINGLAS 220-220K2 | 11 | 9 | 9 | Scheduled | 04/02/2025 | 14/02/2025
TO-25-FIN-220SA1-2CB-09 | COUPLER/SECTIONALISING CB - FINGLAS 220-FINGLAS 220-220SA1-2CB | 11 | 9 | 9 | Scheduled | 04/02/2025 | 14/02/2025
TO-25-FIN-SHL-1-01 | 220kV FEEDER - FINGLAS 220-SHELLYBANKS 220-1 | 25 | 19 | 19 | Scheduled | 04/02/2025 | 28/02/2025
TO-25-SHL-T2016-01 | GENERATOR TRANSFORMER - SHELLYBANKS 220-SHELLYBANKS G6-T2016 | 1 | 1 | 1 | Scheduled | 04/02/2025 | 04/02/2025
TO-25-110 kV A4 @ CDU-02 | BUSBAR SECTION - CORDUFF 110-CORDUFF 110-110A4 | 5 | 5 |  | Scheduled | 10/02/2025 | 14/02/2025
TO-25-110 kV B2 @ CDU-02 | BUSBAR SECTION - CORDUFF 110-CORDUFF 110-110B2 | 5 | 5 |  | Scheduled | 10/02/2025 | 14/02/2025
TO-25-110 kV B4 @ CDU-02 | BUSBAR SECTION - CORDUFF 110-CORDUFF 110-110B4 | 5 | 5 |  | Scheduled | 10/02/2025 | 14/02/2025
TO-25-AUN-CBT-1-01 | 110kV FEEDER - AUNGIERSTOWN 110-CASTLEBAGOT 110-1 | 2 | 2 | 2 | Scheduled | 11/02/2025 | 12/02/2025
TO-25-AUN-T121-01 | TSO CUSTOMER TRANSFORMER - AUNGIERSTOWN 110-AUNGIERSTOWN 20-T121 | 2 | 2 | 2 | Scheduled | 13/02/2025 | 14/02/2025
TO-25-AUN-T123-01 | TSO CUSTOMER TRANSFORMER - AUNGIERSTOWN 110-AUNGIERSTOWN 20-T123 | 2 | 2 | 2 | Scheduled | 19/02/2025 | 20/02/2025
TO-25-AUN-KSG-1-01 | 110kV FEEDER - AUNGIERSTOWN 110-KISHOGE 110-1 | 4 | 2 | 2 | Scheduled | 21/02/2025 | 24/02/2025
TO-25-BAL-CDU-1-02 | 110kV FEEDER - BALTRASNA 110-CORDUFF 110-1 | 6 | 5 |  | Scheduled | 24/02/2025 | 01/03/2025
TO-25-110 kV A4 @ CDU-01 | BUSBAR SECTION - CORDUFF 110-CORDUFF 110-110A4 | 6 | 5 | 5 | Scheduled | 24/02/2025 | 01/03/2025
TO-25-110 kV B4 @ CDU-01 | BUSBAR SECTION - CORDUFF 110-CORDUFF 110-110B4 | 6 | 5 | 5 | Scheduled | 24/02/2025 | 01/03/2025
TO-25-CDU-110SA2-4CB-01 | COUPLER/SECTIONALISING CB - CORDUFF 110-CORDUFF 110-110SA2-4CB | 6 | 5 | 5 | Scheduled | 24/02/2025 | 01/03/2025
TO-25-CDU-110SB2-4CB-01 | COUPLER/SECTIONALISING CB - CORDUFF 110-CORDUFF 110-110SB2-4CB | 6 | 5 | 5 | Scheduled | 24/02/2025 | 01/03/2025
TO-25-CBT-CKG-1-02 | 110kV FEEDER - CASTLEBAGOT 110-CORKAGH 110-1 | 5 | 5 | 5 | Scheduled | 03/03/2025 | 07/03/2025
TO-25-CDU-GLN-1-01 | 110kV FEEDER - CORDUFF 110-GALLANSTOWN 110-1 | 12 | 10 | 10 | Scheduled | 03/03/2025 | 14/03/2025
TO-25-110 kV A3 @ CKG-02 | BUSBAR SECTION - CORKAGH 110-CORKAGH 110-110A3 | 5 | 5 | 5 | Scheduled | 03/03/2025 | 07/03/2025
TO-25-110 kV B3 @ CKG-02 | BUSBAR SECTION - CORKAGH 110-CORKAGH 110-110B3 | 5 | 5 | 5 | Scheduled | 03/03/2025 | 07/03/2025
TO-25-CKG-110K3-02 | COUPLER/SECTIONALISING CB - CORKAGH 110-CORKAGH 110-110K3 | 5 | 5 | 5 | Scheduled | 03/03/2025 | 07/03/2025
TO-25-CKG-110SA1-3CB-03 | COUPLER/SECTIONALISING CB - CORKAGH 110-CORKAGH 110-110SA1-3CB | 5 | 5 | 5 | Scheduled | 03/03/2025 | 07/03/2025
TO-25-CKG-110SB1-3CB-03 | COUPLER/SECTIONALISING CB - CORKAGH 110-CORKAGH 110-110SB1-3CB | 5 | 5 | 5 | Scheduled | 03/03/2025 | 07/03/2025
TO-25-FIN-220SB1-2CB-07 | COUPLER/SECTIONALISING CB - FINGLAS 220-FINGLAS 220-220SB1-2CB | 22 | 15 | 15 | Scheduled | 03/03/2025 | 24/03/2025
TO-25-FIN GIS-T2101-01 | TRANSFORMER - FINGLAS 220-FINGLAS GIS 110-T2101 | 22 | 15 | 15 | Scheduled | 03/03/2025 | 24/03/2025
TO-25-BAG-T101-01 | TSO CUSTOMER TRANSFORMER - BARNAGEERAGH 110-BARNAGEERAGH 11-T101 | 4 | 4 | 4 | Scheduled | 04/03/2025 | 07/03/2025
TO-25-BLU-T131-02 | GENERATOR TRANSFORMER - BLUNDELSTOWN 110-BLUNDELSTOWN 33-T131 | 1 | 1 | 1 | Scheduled | 04/03/2025 | 04/03/2025
TO-25-BAG-T103-01 | TSO CUSTOMER TRANSFORMER - BARNAGEERAGH 110-BARNAGEERAGH 11-T103 | 5 | 5 | 5 | Scheduled | 10/03/2025 | 14/03/2025
TO-25-CLG-FIN GIS-1-02 | 110kV FEEDER - CLOGHRAN 110-FINGLAS GIS 110-1 | 15 | 10 | 10 | Scheduled | 10/03/2025 | 24/03/2025
TO-25-COL-FIN GIS-1-02 | 110kV FEEDER - COLLEGE PARK 110-FINGLAS GIS 110-1 | 15 | 10 | 10 | Scheduled | 10/03/2025 | 24/03/2025
TO-25-110 kV A5 @ FIN GIS-01 | BUSBAR SECTION - FINGLAS GIS 110-FINGLAS GIS 110-110A5 | 15 | 10 | 10 | Scheduled | 10/03/2025 | 24/03/2025
TO-25-110 kV B5 @ FIN GIS-01 | BUSBAR SECTION - FINGLAS GIS 110-FINGLAS GIS 110-110B5 | 15 | 10 | 10 | Scheduled | 10/03/2025 | 24/03/2025
TO-25-FIN GIS-110K5-02 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110K5 | 15 | 10 | 10 | Scheduled | 10/03/2025 | 24/03/2025
TO-25-FIN GIS-110SA3-5CB-03 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110SA3-5CB | 15 | 10 | 10 | Scheduled | 10/03/2025 | 24/03/2025
TO-25-FIN GIS-110SB3-5CB-02 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110SB3-5CB | 15 | 10 | 10 | Scheduled | 10/03/2025 | 24/03/2025
TO-25-400 kV A1 @ DSN-01 | BUSBAR SECTION - DUNSTOWN 400-DUNSTOWN 400-400A1 | 38 | 27 | 27 | Scheduled | 11/03/2025 | 17/04/2025
TO-25-400 kV B1 @ DSN-01 | BUSBAR SECTION - DUNSTOWN 400-DUNSTOWN 400-400B1 | 38 | 27 | 27 | Scheduled | 11/03/2025 | 17/04/2025
TO-25-DSN-MP GIS-1-01 | 400kV FEEDER - DUNSTOWN 400-MONEYPOINT GIS 400-1 | 46 | 31 | 31 | Scheduled | 11/03/2025 | 25/04/2025
TO-25-INC-PB-2-02 | 220kV FEEDER - INCHICORE 220-POOLBEG 220-2 | 36 | 25 | 25 | Scheduled | 11/03/2025 | 15/04/2025
TO-25-220 kV A1 @ TH-01 | BUSBAR SECTION - TURLOUGH HILL 220-TURLOUGH HILL 220-220A1 | 10 | 7 | 7 | Scheduled | 23/03/2025 | 01/04/2025
TO-25-220 kV B1 @ TH-01 | BUSBAR SECTION - TURLOUGH HILL 220-TURLOUGH HILL 220-220B1 | 10 | 7 | 7 | Scheduled | 23/03/2025 | 01/04/2025
TO-25-TH-T2001/2-01 | GENERATOR TRANSFORMER - TURLOUGH HILL 220-TURLOUGH HILL G1-T2001/2 | 10 | 7 | 7 | Scheduled | 23/03/2025 | 01/04/2025
TO-25-CLG-T122-01 | TSO CUSTOMER TRANSFORMER - CLOGHRAN 110-CLOGHRAN 20-T122 | 5 | 5 | 5 | Scheduled | 24/03/2025 | 28/03/2025
TO-25-GLN-T133-02 | GENERATOR TRANSFORMER - GALLANSTOWN 110-GALLANSTOWN 33-T133 | 3 | 3 | 3 | Scheduled | 25/03/2025 | 27/03/2025
TO-25-ISH-T2001-01 | GENERATOR TRANSFORMER - IRISHTOWN 220-IRISHTOWN G1-T2001 | 3 | 3 | 3 | Scheduled | 25/03/2025 | 27/03/2025
TO-25-110 kV B1 @ BLC-01 | BUSBAR SECTION - BELCAMP 110-BELCAMP 110-110B1 | 5 | 5 | 5 | Scheduled | 31/03/2025 | 04/04/2025
TO-25-BLC-110K1-02 | COUPLER/SECTIONALISING CB - BELCAMP 110-BELCAMP 110-110K1 | 5 | 5 | 5 | Scheduled | 31/03/2025 | 04/04/2025
TO-25-BLC-110SA1-3CB-03 | COUPLER/SECTIONALISING CB - BELCAMP 110-BELCAMP 110-110SA1-3CB | 5 | 5 | 5 | Scheduled | 31/03/2025 | 04/04/2025
TO-25-BLC-110SB1-3CB-03 | COUPLER/SECTIONALISING CB - BELCAMP 110-BELCAMP 110-110SB1-3CB | 5 | 5 | 5 | Scheduled | 31/03/2025 | 04/04/2025
TO-25-BLC-DND-1-02 | 110kV FEEDER - BELCAMP 110-DARNDALE 110-1 | 5 | 5 | 5 | Scheduled | 31/03/2025 | 04/04/2025
TO-25-110 kV B1 @ DND-02 | BUSBAR SECTION - DARNDALE 110-DARNDALE 110-110B1 | 5 | 5 | 5 | Scheduled | 31/03/2025 | 04/04/2025
TO-25-DND-110K1-04 | COUPLER/SECTIONALISING CB - DARNDALE 110-DARNDALE 110-110K1 | 5 | 5 | 5 | Scheduled | 31/03/2025 | 04/04/2025
TO-25-DND-110SA1-2CB-06 | COUPLER/SECTIONALISING CB - DARNDALE 110-DARNDALE 110-110SA1-2CB | 5 | 5 | 5 | Scheduled | 31/03/2025 | 04/04/2025
TO-25-DND-110SB1-2CB-05 | COUPLER/SECTIONALISING CB - DARNDALE 110-DARNDALE 110-110SB1-2CB | 5 | 5 | 5 | Scheduled | 31/03/2025 | 04/04/2025
TO-25-SNU-T102-01 | TSO CUSTOMER TRANSFORMER - SNUGBOROUGH 110-SNUGBOROUGH 10-T102 | 2 | 2 | 2 | Scheduled | 01/04/2025 | 02/04/2025
TO-25-KTL-T131-01 | GENERATOR TRANSFORMER - KILTEEL 110-KILTEEL 33-T131 | 1 | 1 | 1 | Scheduled | 02/04/2025 | 02/04/2025
TO-25-220 kV A2 @ TH-01 | BUSBAR SECTION - TURLOUGH HILL 220-TURLOUGH HILL 220-220A2 | 10 | 8 | 8 | Scheduled | 02/04/2025 | 11/04/2025
TO-25-220 kV B2 @ TH-01 | BUSBAR SECTION - TURLOUGH HILL 220-TURLOUGH HILL 220-220B2 | 10 | 8 | 8 | Scheduled | 02/04/2025 | 11/04/2025
TO-25-TH-T2003/4-02 | GENERATOR TRANSFORMER - TURLOUGH HILL 220-TURLOUGH HILL G1-T2003/4 | 10 | 8 | 8 | Scheduled | 02/04/2025 | 11/04/2025
TO-25-110 kV A3 @ BLC-01 | BUSBAR SECTION - BELCAMP 110-BELCAMP 110-110A3 | 5 | 5 | 5 | Scheduled | 07/04/2025 | 11/04/2025
TO-25-110 kV B3 @ BLC-01 | BUSBAR SECTION - BELCAMP 110-BELCAMP 110-110B3 | 5 | 5 | 5 | Scheduled | 07/04/2025 | 11/04/2025
TO-25-BLC-110K3-02 | COUPLER/SECTIONALISING CB - BELCAMP 110-BELCAMP 110-110K3 | 5 | 5 | 5 | Scheduled | 07/04/2025 | 11/04/2025
TO-25-BLC-110SA1-3CB-02 | COUPLER/SECTIONALISING CB - BELCAMP 110-BELCAMP 110-110SA1-3CB | 5 | 5 | 5 | Scheduled | 07/04/2025 | 11/04/2025
TO-25-BLC-110SB1-3CB-02 | COUPLER/SECTIONALISING CB - BELCAMP 110-BELCAMP 110-110SB1-3CB | 5 | 5 | 5 | Scheduled | 07/04/2025 | 11/04/2025
TO-25-BLC-DND-3-01 | 110kV FEEDER - BELCAMP 110-DARNDALE 110-3 | 5 | 5 | 5 | Scheduled | 07/04/2025 | 11/04/2025
TO-25-220 kV A1 @ CDU-01 | BUSBAR SECTION - CORDUFF 220-CORDUFF 220-220A1 | 5 | 5 | 5 | Scheduled | 07/04/2025 | 11/04/2025
TO-25-220 kV A2 @ CDU-01 | BUSBAR SECTION - CORDUFF 220-CORDUFF 220-220A2 | 5 | 5 | 5 | Scheduled | 07/04/2025 | 11/04/2025
TO-25-220 kV A3 @ CDU-01 | BUSBAR SECTION - CORDUFF 220-CORDUFF 220-220A3 | 5 | 5 | 5 | Scheduled | 07/04/2025 | 11/04/2025
TO-25-220 kV A4 @ CDU-01 | BUSBAR SECTION - CORDUFF 220-CORDUFF 220-220A4 | 5 | 5 | 5 | Scheduled | 07/04/2025 | 11/04/2025
TO-25-220 kV B1 @ CDU-01 | BUSBAR SECTION - CORDUFF 220-CORDUFF 220-220B1 | 5 | 5 | 5 | Scheduled | 07/04/2025 | 11/04/2025
TO-25-220 kV B2 @ CDU-01 | BUSBAR SECTION - CORDUFF 220-CORDUFF 220-220B2 | 5 | 5 | 5 | Scheduled | 07/04/2025 | 11/04/2025
TO-25-220 kV B3 @ CDU-01 | BUSBAR SECTION - CORDUFF 220-CORDUFF 220-220B3 | 5 | 5 | 5 | Scheduled | 07/04/2025 | 11/04/2025
TO-25-220 kV B4 @ CDU-01 | BUSBAR SECTION - CORDUFF 220-CORDUFF 220-220B4 | 5 | 5 | 5 | Scheduled | 07/04/2025 | 11/04/2025
TO-25-CDU-CRU-1-01 | 220kV FEEDER - CORDUFF 220-CRUISERATH 220-1 | 5 | 5 | 5 | Scheduled | 07/04/2025 | 11/04/2025
TO-25-CDU-T2104-01 | TRANSFORMER - CORDUFF 220-CORDUFF 110-T2104 | 5 | 5 | 5 | Scheduled | 07/04/2025 | 11/04/2025
TO-25-110 kV B2 @ DND-01 | BUSBAR SECTION - DARNDALE 110-DARNDALE 110-110B2 | 5 | 5 | 5 | Scheduled | 07/04/2025 | 11/04/2025
TO-25-DND-110K2-02 | COUPLER/SECTIONALISING CB - DARNDALE 110-DARNDALE 110-110K2 | 5 | 5 | 5 | Scheduled | 07/04/2025 | 11/04/2025
TO-25-DND-110SA1-2CB-03 | COUPLER/SECTIONALISING CB - DARNDALE 110-DARNDALE 110-110SA1-2CB | 5 | 5 | 5 | Scheduled | 07/04/2025 | 11/04/2025
TO-25-DND-110SB1-2CB-02 | COUPLER/SECTIONALISING CB - DARNDALE 110-DARNDALE 110-110SB1-2CB | 5 | 5 | 5 | Scheduled | 07/04/2025 | 11/04/2025
TO-25-BLU-T131-01 | GENERATOR TRANSFORMER - BLUNDELSTOWN 110-BLUNDELSTOWN 33-T131 | 2 | 2 | 2 | Scheduled | 08/04/2025 | 09/04/2025
TO-25-110 kV B2 @ CLU-01 | BUSBAR SECTION - CLUTTERLAND 110-CLUTTERLAND 110-110B2 | 32 | 21 | 21 | Scheduled | 08/04/2025 | 09/05/2025
TO-25-CLU-110K2-01 | COUPLER/SECTIONALISING CB - CLUTTERLAND 110-CLUTTERLAND 110-110K2 | 32 | 21 | 21 | Scheduled | 08/04/2025 | 09/05/2025
TO-25-CLU-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - CLUTTERLAND 110-CLUTTERLAND 110-110SA1-2CB | 32 | 21 | 21 | Scheduled | 08/04/2025 | 09/05/2025
TO-25-CLU-110SB1-2CB-01 | COUPLER/SECTIONALISING CB - CLUTTERLAND 110-CLUTTERLAND 110-110SB1-2CB | 32 | 21 | 21 | Scheduled | 08/04/2025 | 09/05/2025
TO-25-BLU-110K1-02 | COUPLER/SECTIONALISING CB - BLUNDELSTOWN 110-BLUNDELSTOWN 110-110K1 | 1 | 1 | 1 | Scheduled | 09/04/2025 | 09/04/2025
TO-25-BLU-MUL-1-05 | 110kV FEEDER - BLUNDELSTOWN 110-MULLINGAR 110-1 | 1 | 1 | 1 | Scheduled | 09/04/2025 | 09/04/2025
TO-25-BRT-T224-01 | TSO CUSTOMER TRANSFORMER - BRACETOWN 220-BRACETOWN 20-T224 | 57 | 37 | 37 | Scheduled | 11/04/2025 | 06/06/2025
TO-25-PRN-T4301-01 | TRANSFORMER - PORTAN 400-PORTAN 260-T4301 | 5 | 4 | 4 | Scheduled | 14/04/2025 | 18/04/2025
TO-25-PRN-WOO-1-01 | 400kV FEEDER - PORTAN 400-WOODLAND 400-1 | 5 | 4 | 4 | Scheduled | 14/04/2025 | 18/04/2025
TO-25-400 kV A1 @ WOO-02 | BUSBAR SECTION - WOODLAND 400-WOODLAND 400-400A1 | 1 | 1 | 1 | Scheduled | 14/04/2025 | 14/04/2025
TO-25-400 kV B1 @ WOO-02 | BUSBAR SECTION - WOODLAND 400-WOODLAND 400-400B1 | 4 | 3 | 3 | Scheduled | 15/04/2025 | 18/04/2025
TO-25-WOO-400K1-2-01 | COUPLER/SECTIONALISING CB - WOODLAND 400-WOODLAND 400-400K1-2 | 4 | 3 | 3 | Scheduled | 15/04/2025 | 18/04/2025
TO-25-WOO-T4201-02 | TRANSFORMER - WOODLAND 400-WOODLAND 220-T4201 | 4 | 3 | 3 | Scheduled | 15/04/2025 | 18/04/2025
TO-25-110 kV B2 @ DND-02 | BUSBAR SECTION - DARNDALE 110-DARNDALE 110-110B2 | 7 | 5 | 5 | Scheduled | 23/04/2025 | 29/04/2025
TO-25-DND-110K2-01 | COUPLER/SECTIONALISING CB - DARNDALE 110-DARNDALE 110-110K2 | 7 | 5 | 5 | Scheduled | 23/04/2025 | 29/04/2025
TO-25-DND-110SA1-2CB-05 | COUPLER/SECTIONALISING CB - DARNDALE 110-DARNDALE 110-110SA1-2CB | 7 | 5 | 5 | Scheduled | 23/04/2025 | 29/04/2025
TO-25-DND-110SB1-2CB-04 | COUPLER/SECTIONALISING CB - DARNDALE 110-DARNDALE 110-110SB1-2CB | 7 | 5 | 5 | Scheduled | 23/04/2025 | 29/04/2025
TO-25-220 kV A2/A4 @ CDU-01 | BUSBAR SECTION - CORDUFF 220-CORDUFF 220-220A2-A4 | 8 | 6 | 6 | Scheduled | 24/04/2025 | 01/05/2025
TO-25-CDU-220SA2-4CB-01 | COUPLER/SECTIONALISING CB - CORDUFF 220-CORDUFF 220-220SA2-4CB | 8 | 6 | 6 | Scheduled | 24/04/2025 | 01/05/2025
TO-25-FIN-HN-1-01 | 220kV FEEDER - FINGLAS 220-HUNTSTOWN 220-1 | 14 | 9 | 9 | Scheduled | 26/04/2025 | 09/05/2025
TO-25-HN-T2010/11-01 | GENERATOR TRANSFORMER - HUNTSTOWN 220-HUNTSTOWN G10/11-T2010/11 | 14 | 9 | 9 | Scheduled | 26/04/2025 | 09/05/2025
TO-25-CBT-T2103-01 | TRANSFORMER - CASTLEBAGOT 220-CASTLEBAGOT 110-T2103 | 18 | 13 |  | Scheduled | 28/04/2025 | 15/05/2025
TO-25-220 kV A1 @ FIN-06 | BUSBAR SECTION - FINGLAS 220-FINGLAS 220-220A1 | 12 | 9 | 9 | Scheduled | 28/04/2025 | 09/05/2025
TO-25-220 kV B1 @ FIN-05 | BUSBAR SECTION - FINGLAS 220-FINGLAS 220-220B1 | 12 | 9 | 9 | Scheduled | 28/04/2025 | 09/05/2025
TO-25-FIN-220K1-09 | COUPLER/SECTIONALISING CB - FINGLAS 220-FINGLAS 220-220K1 | 12 | 9 | 9 | Scheduled | 28/04/2025 | 09/05/2025
TO-25-FIN-220SA1-2CB-13 | COUPLER/SECTIONALISING CB - FINGLAS 220-FINGLAS 220-220SA1-2CB | 12 | 9 | 9 | Scheduled | 28/04/2025 | 09/05/2025
TO-25-FIN-220SB1-2CB-10 | COUPLER/SECTIONALISING CB - FINGLAS 220-FINGLAS 220-220SB1-2CB | 12 | 9 | 9 | Scheduled | 28/04/2025 | 09/05/2025
TO-25-DSN-MP GIS-1-04 | 400kV FEEDER - DUNSTOWN 400-MONEYPOINT GIS 400-1 | 25 | 18 | 18 | Scheduled | 29/04/2025 | 23/05/2025
TO-25-DND-110K1-03 | COUPLER/SECTIONALISING CB - DARNDALE 110-DARNDALE 110-110K1 | 8 | 5 | 5 | Scheduled | 30/04/2025 | 07/05/2025
TO-25-DND-110K2-03 | COUPLER/SECTIONALISING CB - DARNDALE 110-DARNDALE 110-110K2 | 8 | 5 | 5 | Scheduled | 30/04/2025 | 07/05/2025
TO-25-DND-110SA1-2CB-02 | COUPLER/SECTIONALISING CB - DARNDALE 110-DARNDALE 110-110SA1-2CB | 8 | 5 | 5 | Scheduled | 30/04/2025 | 07/05/2025
TO-25-CDU-CRU-2-04 | 220kV FEEDER - CORDUFF 220-CRUISERATH 220-2 | 1 | 1 | 1 | Scheduled | 01/05/2025 | 01/05/2025
TO-25-220 kV B2/B4 @ CDU-02 | BUSBAR SECTION - CORDUFF 220-CORDUFF 220-220B2-B4 | 8 | 5 | 5 | Scheduled | 02/05/2025 | 09/05/2025
TO-25-CDU-220SB2-4CB-01 | COUPLER/SECTIONALISING CB - CORDUFF 220-CORDUFF 220-220SB2-4CB | 8 | 5 | 5 | Scheduled | 02/05/2025 | 09/05/2025
TO-25-BLU-MUL-1-02 | 110kV FEEDER - BLUNDELSTOWN 110-MULLINGAR 110-1 | 11 | 9 | 9 | Scheduled | 06/05/2025 | 16/05/2025
TO-25-CBT-CLU-1-01 | 110kV FEEDER - CASTLEBAGOT 110-CLUTTERLAND 110-1 | 2 | 2 | 2 | Scheduled | 08/05/2025 | 09/05/2025
TO-25-CDU-CRU-2-05 | 220kV FEEDER - CORDUFF 220-CRUISERATH 220-2 | 1 | 1 | 1 | Scheduled | 09/05/2025 | 09/05/2025
TO-25-SNU-T104-02 | TSO CUSTOMER TRANSFORMER - SNUGBOROUGH 110-SNUGBOROUGH 10-T104 | 5 | 5 | 5 | Scheduled | 12/05/2025 | 16/05/2025
TO-25-BAL-CDU-1-04 | 110kV FEEDER - BALTRASNA 110-CORDUFF 110-1 | 2 | 2 | 2 | Scheduled | 13/05/2025 | 14/05/2025
TO-25-110 kV B4 @ CDU-03 | BUSBAR SECTION - CORDUFF 110-CORDUFF 110-110B4 | 2 | 2 | 2 | Scheduled | 13/05/2025 | 14/05/2025
TO-25-DSN-KLS-1-03 | 220kV FEEDER - DUNSTOWN 220-KELLIS 220-1 | 2 | 2 | 2 | Scheduled | 15/05/2025 | 16/05/2025
TO-25-FIN-110K2-3-04 | COUPLER/SECTIONALISING CB - FINGLAS 110-FINGLAS 110-110K2-3 | 227 | 158 | 158 | Scheduled | 19/05/2025 | 31/12/2025
TO-25-ISH-T2002/3-01 | GENERATOR TRANSFORMER - IRISHTOWN 220-IRISHTOWN G2/3-T2002/3 | 5 | 5 | 5 | Scheduled | 19/05/2025 | 23/05/2025
TO-25-RYB GIS-T105-01 | TSO CUSTOMER TRANSFORMER - RYEBROOK GIS 110-RYEBROOK 10-T105 | 12 | 10 | 10 | Scheduled | 19/05/2025 | 30/05/2025
TO-25-BDA-MON-1-01 | 110kV FEEDER - BARODA 110-MONREAD 110-1 | 3 | 3 | 3 | Scheduled | 20/05/2025 | 22/05/2025
TO-25-CKM-PB-1-06 | 220kV FEEDER - CARRICKMINES 220-POOLBEG 220-1 | 2 | 0 | 0 | Scheduled | 24/05/2025 | 25/05/2025
TO-25-KTL-CAP1-01 | CAPACITOR/SVC/REACTOR - KILTEEL 110-KILTEEL 110-CAP1 | 5 | 5 | 5 | Scheduled | 26/05/2025 | 30/05/2025
TO-25-220 kV A1 @ WOO-04 | BUSBAR SECTION - WOODLAND 220-WOODLAND 220-220A1 | 4 | 4 | 4 | Scheduled | 27/05/2025 | 30/05/2025
TO-25-WOO-T4201-05 | TRANSFORMER - WOODLAND 400-WOODLAND 220-T4201 | 4 | 4 | 4 | Scheduled | 27/05/2025 | 30/05/2025
TO-25-220 kV A2 @ FIN-08 | BUSBAR SECTION - FINGLAS 220-FINGLAS 220-220A2 | 37 | 26 | 26 | Scheduled | 29/05/2025 | 04/07/2025
TO-25-220 kV B2 @ FIN-05 | BUSBAR SECTION - FINGLAS 220-FINGLAS 220-220B2 | 37 | 26 | 26 | Scheduled | 29/05/2025 | 04/07/2025
TO-25-FIN-220K2-10 | COUPLER/SECTIONALISING CB - FINGLAS 220-FINGLAS 220-220K2 | 37 | 26 | 26 | Scheduled | 29/05/2025 | 04/07/2025
TO-25-FIN-220SA1-2CB-14 | COUPLER/SECTIONALISING CB - FINGLAS 220-FINGLAS 220-220SA1-2CB | 37 | 26 | 26 | Scheduled | 29/05/2025 | 04/07/2025
TO-25-FIN-220SB1-2CB-11 | COUPLER/SECTIONALISING CB - FINGLAS 220-FINGLAS 220-220SB1-2CB | 37 | 26 | 26 | Scheduled | 29/05/2025 | 04/07/2025
TO-25-FIN-FIN GIS-2-03 | 110kV FEEDER - FINGLAS 110-FINGLAS GIS 110-2 | 37 | 26 | 26 | Scheduled | 29/05/2025 | 04/07/2025
TO-25-FIN-T2104-03 | TRANSFORMER - FINGLAS 220-FINGLAS 110-T2104 | 37 | 26 | 26 | Scheduled | 29/05/2025 | 04/07/2025
TO-25-110 kV A3 @ RYB GIS-01 | BUSBAR SECTION - RYEBROOK GIS 110-RYEBROOK GIS 110-110A3 | 11 | 9 | 9 | Scheduled | 03/06/2025 | 13/06/2025
TO-25-110 kV B3 @ RYB GIS-01 | BUSBAR SECTION - RYEBROOK GIS 110-RYEBROOK GIS 110-110B3 | 11 | 9 | 9 | Scheduled | 03/06/2025 | 13/06/2025
TO-25-RYB GIS-110K3-02 | COUPLER/SECTIONALISING CB - RYEBROOK GIS 110-RYEBROOK GIS 110-110K3 | 11 | 9 | 9 | Scheduled | 03/06/2025 | 13/06/2025
TO-25-RYB GIS-110SA1-3CB-02 | COUPLER/SECTIONALISING CB - RYEBROOK GIS 110-RYEBROOK GIS 110-110SA1-3CB | 11 | 9 | 9 | Scheduled | 03/06/2025 | 13/06/2025
TO-25-RYB GIS-110SB1-3CB-03 | COUPLER/SECTIONALISING CB - RYEBROOK GIS 110-RYEBROOK GIS 110-110SB1-3CB | 11 | 9 | 9 | Scheduled | 03/06/2025 | 13/06/2025
TO-25-RYB GIS-T106-01 | TSO CUSTOMER TRANSFORMER - RYEBROOK GIS 110-RYEBROOK 10-T106 | 14 | 10 | 10 | Scheduled | 03/06/2025 | 16/06/2025
TO-25-BRT-CLE-2-01 | 220kV FEEDER - BRACETOWN 220-CLONEE 220-2 | 9 | 7 | 7 | Scheduled | 04/06/2025 | 12/06/2025
TO-25-220 kV A1 @ CLE-02 | BUSBAR SECTION - CLONEE 220-CLONEE 220-220A1 | 9 | 7 | 7 | Scheduled | 04/06/2025 | 12/06/2025
TO-25-220 kV B1 @ CLE-02 | BUSBAR SECTION - CLONEE 220-CLONEE 220-220B1 | 9 | 7 | 7 | Scheduled | 04/06/2025 | 12/06/2025
TO-25-CLE-220K1-02 | COUPLER/SECTIONALISING CB - CLONEE 220-CLONEE 220-220K1 | 9 | 7 | 7 | Scheduled | 04/06/2025 | 12/06/2025
TO-25-CLE-220SA1-2CB-03 | COUPLER/SECTIONALISING CB - CLONEE 220-CLONEE 220-220SA1-2CB | 9 | 7 | 7 | Scheduled | 04/06/2025 | 12/06/2025
TO-25-CLE-220SB1-2CB-03 | COUPLER/SECTIONALISING CB - CLONEE 220-CLONEE 220-220SB1-2CB | 9 | 7 | 7 | Scheduled | 04/06/2025 | 12/06/2025
TO-25-BLU-MUL-1-01 | 110kV FEEDER - BLUNDELSTOWN 110-MULLINGAR 110-1 | 2 | 2 | 2 | Scheduled | 05/06/2025 | 06/06/2025
TO-25-220 kV A1/A2/A3/A4 @ CKM GIS-01 | BUSBAR SECTION - CARRICKMINES GIS 220-CARRICKMINES GIS 220-220A1-A2-A3-A4 | 5 | 5 | 5 | Scheduled | 09/06/2025 | 13/06/2025
TO-25-CKM GIS-220K3-01 | COUPLER/SECTIONALISING CB - CARRICKMINES GIS 220-CARRICKMINES GIS 220-220K3 | 5 | 5 | 5 | Scheduled | 09/06/2025 | 13/06/2025
TO-25-CKM GIS-220K4-01 | COUPLER/SECTIONALISING CB - CARRICKMINES GIS 220-CARRICKMINES GIS 220-220K4 | 5 | 5 | 5 | Scheduled | 09/06/2025 | 13/06/2025
TO-25-CKM GIS-220SA1-2CB-01 | COUPLER/SECTIONALISING CB - CARRICKMINES GIS 220-CARRICKMINES GIS 220-22SA1-2CB | 5 | 5 | 5 | Scheduled | 09/06/2025 | 13/06/2025
TO-25-CKM GIS-220SA1-3CB-02 | COUPLER/SECTIONALISING CB - CARRICKMINES GIS 220-CARRICKMINES GIS 220-22SA1-3CB | 5 | 5 | 5 | Scheduled | 09/06/2025 | 13/06/2025
TO-25-CKM GIS-220SA2-4CB-02 | COUPLER/SECTIONALISING CB - CARRICKMINES GIS 220-CARRICKMINES GIS 220-22SA2-4CB | 5 | 5 | 5 | Scheduled | 09/06/2025 | 13/06/2025
TO-25-220 kV A2 @ CDU-02 | BUSBAR SECTION - CORDUFF 220-CORDUFF 220-220A2 | 5 | 5 | 5 | Scheduled | 09/06/2025 | 13/06/2025
TO-25-220 kV A4 @ CDU-02 | BUSBAR SECTION - CORDUFF 220-CORDUFF 220-220A4 | 5 | 5 | 5 | Scheduled | 09/06/2025 | 13/06/2025
TO-25-220 kV B2 @ CDU-02 | BUSBAR SECTION - CORDUFF 220-CORDUFF 220-220B2 | 5 | 5 | 5 | Scheduled | 09/06/2025 | 13/06/2025
TO-25-220 kV B4 @ CDU-02 | BUSBAR SECTION - CORDUFF 220-CORDUFF 220-220B4 | 5 | 5 | 5 | Scheduled | 09/06/2025 | 13/06/2025
TO-25-CDU-220SA2-4CB-02 | COUPLER/SECTIONALISING CB - CORDUFF 220-CORDUFF 220-220SA2-4CB | 5 | 5 | 5 | Scheduled | 09/06/2025 | 13/06/2025
TO-25-CDU-220SB2-4CB-02 | COUPLER/SECTIONALISING CB - CORDUFF 220-CORDUFF 220-220SB2-4CB | 5 | 5 | 5 | Scheduled | 09/06/2025 | 13/06/2025
TO-25-SHL-D1/CB2-02 | COUPLER/SECTIONALISING CB - SHELLYBANKS 220-SHELLYBANKS 220-D1/CB2 | 5 | 5 | 5 | Scheduled | 09/06/2025 | 13/06/2025
TO-25-SHL-D1/CB3-02 | COUPLER/SECTIONALISING CB - SHELLYBANKS 220-SHELLYBANKS 220-D1/CB3 | 5 | 5 | 5 | Scheduled | 09/06/2025 | 13/06/2025
TO-25-SHL-T2014-01 | GENERATOR TRANSFORMER - SHELLYBANKS 220-SHELLYBANKS G4-T2014 | 5 | 5 | 5 | Scheduled | 09/06/2025 | 13/06/2025
TO-25-CKM-PB-1-03 | 220kV FEEDER - CARRICKMINES 220-POOLBEG 220-1 | 2 | 0 | 0 | Scheduled | 14/06/2025 | 15/06/2025
TO-25-BRT-CLE-4-01 | 220kV FEEDER - BRACETOWN 220-CLONEE 220-4 | 5 | 5 | 5 | Scheduled | 16/06/2025 | 20/06/2025
TO-25-220 kV A1 @ CLE-03 | BUSBAR SECTION - CLONEE 220-CLONEE 220-220A1 | 5 | 5 | 5 | Scheduled | 16/06/2025 | 20/06/2025
TO-25-220 kV B1 @ CLE-03 | BUSBAR SECTION - CLONEE 220-CLONEE 220-220B1 | 5 | 5 | 5 | Scheduled | 16/06/2025 | 20/06/2025
TO-25-CLE-220K1-03 | COUPLER/SECTIONALISING CB - CLONEE 220-CLONEE 220-220K1 | 5 | 5 | 5 | Scheduled | 16/06/2025 | 20/06/2025
TO-25-CLE-220SA1-2CB-04 | COUPLER/SECTIONALISING CB - CLONEE 220-CLONEE 220-220SA1-2CB | 5 | 5 | 5 | Scheduled | 16/06/2025 | 20/06/2025
TO-25-CLE-220SB1-2CB-04 | COUPLER/SECTIONALISING CB - CLONEE 220-CLONEE 220-220SB1-2CB | 5 | 5 | 5 | Scheduled | 16/06/2025 | 20/06/2025
TO-25-RYB GIS-T107-01 | TSO CUSTOMER TRANSFORMER - RYEBROOK GIS 110-RYEBROOK 10-T107 | 12 | 10 | 10 | Scheduled | 16/06/2025 | 27/06/2025
TO-25-DGY-FIN GIS-1-01 | 110kV FEEDER - DUNSOGHLY 110-FINGLAS GIS 110-1 | 3 | 3 | 3 | Scheduled | 17/06/2025 | 19/06/2025
TO-25-DGY-T101-01 | GENERATOR TRANSFORMER - DUNSOGHLY 110-DUNSOGHLY 11-T101 | 3 | 3 | 3 | Scheduled | 17/06/2025 | 19/06/2025
TO-25-LOU-WOO-1-04 | 220kV FEEDER - LOUTH 220-WOODLAND 220-1 | 3 | 3 | 3 | Scheduled | 17/06/2025 | 19/06/2025
TO-25-SHL-D2/CB2-02 | COUPLER/SECTIONALISING CB - SHELLYBANKS 220-SHELLYBANKS 220-D2/CB2 | 12 | 9 | 9 | Scheduled | 17/06/2025 | 28/06/2025
TO-25-SHL-D2/CB3-02 | COUPLER/SECTIONALISING CB - SHELLYBANKS 220-SHELLYBANKS 220-D2/CB3 | 12 | 9 | 9 | Scheduled | 17/06/2025 | 28/06/2025
TO-25-SHL-T2015-01 | GENERATOR TRANSFORMER - SHELLYBANKS 220-SHELLYBANKS G5-T2015 | 12 | 9 | 9 | Scheduled | 17/06/2025 | 28/06/2025
TO-25-220 kV A2 @ WOO-07 | BUSBAR SECTION - WOODLAND 220-WOODLAND 220-220A2 | 3 | 3 | 3 | Scheduled | 17/06/2025 | 19/06/2025
TO-25-CKM-PB-1-04 | 220kV FEEDER - CARRICKMINES 220-POOLBEG 220-1 | 2 | 0 | 0 | Scheduled | 21/06/2025 | 22/06/2025
TO-25-SHL-D1/CB1-03 | COUPLER/SECTIONALISING CB - SHELLYBANKS 220-SHELLYBANKS 220-D1/CB1 | 1 | 1 | 1 | Scheduled | 23/06/2025 | 23/06/2025
TO-25-SHL-D2/CB1-02 | COUPLER/SECTIONALISING CB - SHELLYBANKS 220-SHELLYBANKS 220-D2/CB1 | 1 | 1 | 1 | Scheduled | 23/06/2025 | 23/06/2025
TO-25-SHL-T2016-03 | GENERATOR TRANSFORMER - SHELLYBANKS 220-SHELLYBANKS G6-T2016 | 5 | 5 | 5 | Scheduled | 23/06/2025 | 27/06/2025
TO-25-SHL-D1/CB1-04 | COUPLER/SECTIONALISING CB - SHELLYBANKS 220-SHELLYBANKS 220-D1/CB1 | 1 | 1 | 1 | Scheduled | 27/06/2025 | 27/06/2025
TO-25-SHL-D2/CB1-03 | COUPLER/SECTIONALISING CB - SHELLYBANKS 220-SHELLYBANKS 220-D2/CB1 | 1 | 1 | 1 | Scheduled | 27/06/2025 | 27/06/2025
TO-25-CLU-T121-01 | TSO CUSTOMER TRANSFORMER - CLUTTERLAND 110-CLUTTERLAND 20-T121 | 5 | 5 | 5 | Scheduled | 30/06/2025 | 04/07/2025
TO-25-110 kV B4 @ CDU-05 | BUSBAR SECTION - CORDUFF 110-CORDUFF 110-110B4 | 3 | 3 | 3 | Scheduled | 30/06/2025 | 02/07/2025
TO-25-CDU-110SB2-4CB-05 | COUPLER/SECTIONALISING CB - CORDUFF 110-CORDUFF 110-110SB2-4CB | 3 | 3 | 3 | Scheduled | 30/06/2025 | 02/07/2025
TO-25-220 kV A4 @ CDU-03 | BUSBAR SECTION - CORDUFF 220-CORDUFF 220-220A4 | 3 | 3 | 3 | Scheduled | 30/06/2025 | 02/07/2025
TO-25-CDU-220SA2-4CB-03 | COUPLER/SECTIONALISING CB - CORDUFF 220-CORDUFF 220-220SA2-4CB | 3 | 3 | 3 | Scheduled | 30/06/2025 | 02/07/2025
TO-25-220 kV A1 @ CBT-02 | BUSBAR SECTION - CASTLEBAGOT 220-CASTLEBAGOT 220-220A1 | 9 | 7 | 7 | Scheduled | 01/07/2025 | 09/07/2025
TO-25-220 kV B1 @ CBT-03 | BUSBAR SECTION - CASTLEBAGOT 220-CASTLEBAGOT 220-220B1 | 9 | 7 | 7 | Scheduled | 01/07/2025 | 09/07/2025
TO-25-CBT-220K1-05 | COUPLER/SECTIONALISING CB - CASTLEBAGOT 220-CASTLEBAGOT 220-220K1 | 9 | 7 | 7 | Scheduled | 01/07/2025 | 09/07/2025
TO-25-CBT-220SA1-2CB-03 | COUPLER/SECTIONALISING CB - CASTLEBAGOT 220-CASTLEBAGOT 220-220SA1-2CB | 9 | 7 | 7 | Scheduled | 01/07/2025 | 09/07/2025
TO-25-CBT-220SB1-2CB-03 | COUPLER/SECTIONALISING CB - CASTLEBAGOT 220-CASTLEBAGOT 220-220SB1-2CB | 9 | 7 | 7 | Scheduled | 01/07/2025 | 09/07/2025
TO-25-220 kV B2 @ MAY-01 | BUSBAR SECTION - MAYNOOTH 220-MAYNOOTH 220-220B2 | 57 | 40 | 40 | Scheduled | 02/07/2025 | 27/08/2025
TO-25-MAY-SH-1-03 | 220kV FEEDER - MAYNOOTH 220-SHANNONBRIDGE 220-1 | 136 | 96 | 96 | Scheduled | 02/07/2025 | 14/11/2025
TO-25-220 kV A2 @ FIN-09 | BUSBAR SECTION - FINGLAS 220-FINGLAS 220-220A2 | 8 | 6 | 6 | Scheduled | 04/07/2025 | 11/07/2025
TO-25-220 kV B2 @ FIN-04 | BUSBAR SECTION - FINGLAS 220-FINGLAS 220-220B2 | 8 | 6 | 6 | Scheduled | 04/07/2025 | 11/07/2025
TO-25-FIN-220K2-11 | COUPLER/SECTIONALISING CB - FINGLAS 220-FINGLAS 220-220K2 | 8 | 6 | 6 | Scheduled | 04/07/2025 | 11/07/2025
TO-25-FIN-220SA1-2CB-15 | COUPLER/SECTIONALISING CB - FINGLAS 220-FINGLAS 220-220SA1-2CB | 8 | 6 | 6 | Scheduled | 04/07/2025 | 11/07/2025
TO-25-FIN-220SB1-2CB-12 | COUPLER/SECTIONALISING CB - FINGLAS 220-FINGLAS 220-220SB1-2CB | 8 | 6 | 6 | Scheduled | 04/07/2025 | 11/07/2025
TO-25-110 kV A3 @ FIN GIS-02 | BUSBAR SECTION - FINGLAS GIS 110-FINGLAS GIS 110-110A3 | 8 | 6 | 6 | Scheduled | 04/07/2025 | 11/07/2025
TO-25-110 kV B3 @ FIN GIS-01 | BUSBAR SECTION - FINGLAS GIS 110-FINGLAS GIS 110-110B3 | 8 | 6 | 6 | Scheduled | 04/07/2025 | 11/07/2025
TO-25-FIN GIS-110SA1-3CB-02 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110SA1-3CB | 8 | 6 | 6 | Scheduled | 04/07/2025 | 11/07/2025
TO-25-FIN GIS-110SA3-5CB-04 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110SA3-5CB | 8 | 6 | 6 | Scheduled | 04/07/2025 | 11/07/2025
TO-25-FIN GIS-110SB1-3CB-02 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110SB1-3CB | 8 | 6 | 6 | Scheduled | 04/07/2025 | 11/07/2025
TO-25-FIN GIS-110SB3-5CB-03 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110SB3-5CB | 8 | 6 | 6 | Scheduled | 04/07/2025 | 11/07/2025
TO-25-FIN GIS-T2106-02 | TRANSFORMER - FINGLAS 220-FINGLAS GIS 110-T2106 | 8 | 6 | 6 | Scheduled | 04/07/2025 | 11/07/2025
TO-25-NW-T2004/5-02 | GENERATOR TRANSFORMER - NORTH WALL 220-NORTH WALL G4/5-T2004/5 | 2 | 2 | 2 | Scheduled | 07/07/2025 | 08/07/2025
TO-25-220 kV A2 @ CBT-03 | BUSBAR SECTION - CASTLEBAGOT 220-CASTLEBAGOT 220-220A2 | 9 | 7 | 7 | Scheduled | 10/07/2025 | 18/07/2025
TO-25-220 kV B2 @ CBT-03 | BUSBAR SECTION - CASTLEBAGOT 220-CASTLEBAGOT 220-220B2 | 9 | 7 | 7 | Scheduled | 10/07/2025 | 18/07/2025
TO-25-CBT-220K2-03 | COUPLER/SECTIONALISING CB - CASTLEBAGOT 220-CASTLEBAGOT 220-220K2 | 9 | 7 | 7 | Scheduled | 10/07/2025 | 18/07/2025
TO-25-CBT-220SA1-2CB-05 | COUPLER/SECTIONALISING CB - CASTLEBAGOT 220-CASTLEBAGOT 220-220SA1-2CB | 9 | 7 | 7 | Scheduled | 10/07/2025 | 18/07/2025
TO-25-CBT-220SB1-2CB-05 | COUPLER/SECTIONALISING CB - CASTLEBAGOT 220-CASTLEBAGOT 220-220SB1-2CB | 9 | 7 | 7 | Scheduled | 10/07/2025 | 18/07/2025
TO-25-110 kV B1/B2/B3 @ FIN-01 | BUSBAR SECTION - FINGLAS 110-FINGLAS 110-110B1-B2-B3 | 171 | 119 | 119 | Scheduled | 14/07/2025 | 31/12/2025
TO-25-FIN-FIN GIS-1-02 | 110kV FEEDER - FINGLAS 110-FINGLAS GIS 110-1 | 171 | 119 | 119 | Scheduled | 14/07/2025 | 31/12/2025
TO-25-PB-R2002-03 | CAPACITOR/SVC/REACTOR - POOLBEG 220-POOLBEG 220-R2002 | 5 | 5 | 5 | Scheduled | 14/07/2025 | 18/07/2025
TO-25-PA-110SA1-02 | SECTIONALISING DISCONNECT - POLLAPHUCA 110-POLLAPHUCA 110-110SA1 | 16 | 12 | 12 | Scheduled | 17/07/2025 | 01/08/2025
TO-25-PA-110SA2-02 | SECTIONALISING DISCONNECT - POLLAPHUCA 110-POLLAPHUCA 110-110SA2 | 16 | 12 | 12 | Scheduled | 17/07/2025 | 01/08/2025
TO-25-PA-T101-02 | GENERATOR TRANSFORMER - POLLAPHUCA 110-POLLAPHUCA G1-T101 | 16 | 12 | 12 | Scheduled | 17/07/2025 | 01/08/2025
TO-25-STR,T-PA-1-02 | 110kV FEEDER - STRATFORD tee-POLLAPHUCA 110-1 | 16 | 12 | 12 | Scheduled | 17/07/2025 | 01/08/2025
TO-25-FIN-T2103-01 | TRANSFORMER - FINGLAS 220-FINGLAS 110-T2103 | 110 | 76 | 76 | Scheduled | 18/07/2025 | 04/11/2025
TO-25-CRU-T221-01 | TSO CUSTOMER TRANSFORMER - CRUISERATH 220-CRUISERATH 20-T221 | 5 | 5 | 5 | Scheduled | 21/07/2025 | 25/07/2025
TO-25-220 kV A1 @ CBT-01 | BUSBAR SECTION - CASTLEBAGOT 220-CASTLEBAGOT 220-220A1 | 3 | 3 | 3 | Scheduled | 22/07/2025 | 24/07/2025
TO-25-220 kV A2 @ CBT-01 | BUSBAR SECTION - CASTLEBAGOT 220-CASTLEBAGOT 220-220A2 | 3 | 3 | 3 | Scheduled | 22/07/2025 | 24/07/2025
TO-25-CBT-220K1-03 | COUPLER/SECTIONALISING CB - CASTLEBAGOT 220-CASTLEBAGOT 220-220K1 | 2 | 2 | 2 | Scheduled | 22/07/2025 | 23/07/2025
TO-25-CBT-220K2-01 | COUPLER/SECTIONALISING CB - CASTLEBAGOT 220-CASTLEBAGOT 220-220K2 | 3 | 3 | 3 | Scheduled | 22/07/2025 | 24/07/2025
TO-25-CBT-220SA1-2CB-02 | COUPLER/SECTIONALISING CB - CASTLEBAGOT 220-CASTLEBAGOT 220-220SA1-2CB | 3 | 3 | 3 | Scheduled | 22/07/2025 | 24/07/2025
TO-25-110 kV B1 @ SNU-01 | BUSBAR SECTION - SNUGBOROUGH 110-SNUGBOROUGH 110-110B1 | 10 | 8 | 8 | Scheduled | 23/07/2025 | 01/08/2025
TO-25-110 kV B2 @ SNU-01 | BUSBAR SECTION - SNUGBOROUGH 110-SNUGBOROUGH 110-110B2 | 10 | 8 | 8 | Scheduled | 23/07/2025 | 01/08/2025
TO-25-SNU-110K1-01 | COUPLER/SECTIONALISING CB - SNUGBOROUGH 110-SNUGBOROUGH 110-110K1 | 10 | 8 | 8 | Scheduled | 23/07/2025 | 01/08/2025
TO-25-SNU-110K2-01 | COUPLER/SECTIONALISING CB - SNUGBOROUGH 110-SNUGBOROUGH 110-110K2 | 10 | 8 | 8 | Scheduled | 23/07/2025 | 01/08/2025
TO-25-SNU-110SB1-2CB-01 | COUPLER/SECTIONALISING CB - SNUGBOROUGH 110-SNUGBOROUGH 110-110SB1-2CB | 10 | 8 | 8 | Scheduled | 23/07/2025 | 01/08/2025
TO-25-220 kV B1 @ TH-02 | BUSBAR SECTION - TURLOUGH HILL 220-TURLOUGH HILL 220-220B1 | 1 | 1 | 1 | Scheduled | 24/07/2025 | 24/07/2025
TO-25-TH-T2001/2-03 | GENERATOR TRANSFORMER - TURLOUGH HILL 220-TURLOUGH HILL G1-T2001/2 | 1 | 1 | 1 | Scheduled | 24/07/2025 | 24/07/2025
TO-25-TH-T2003/4-03 | GENERATOR TRANSFORMER - TURLOUGH HILL 220-TURLOUGH HILL G1-T2003/4 | 1 | 1 | 1 | Scheduled | 24/07/2025 | 24/07/2025
TO-25-COL-CDU-1-02 | 110kV FEEDER - COLLEGE PARK 110-CORDUFF 110-1 | 2 | 2 | 2 | Scheduled | 28/07/2025 | 29/07/2025
TO-25-CDU-RYB GIS-1-02 | 110kV FEEDER - CORDUFF 110-RYEBROOK GIS 110-1 | 2 | 2 | 2 | Scheduled | 28/07/2025 | 29/07/2025
TO-25-CRU-T223-01 | TSO CUSTOMER TRANSFORMER - CRUISERATH 220-CRUISERATH 20-T223 | 5 | 5 | 5 | Scheduled | 28/07/2025 | 01/08/2025
TO-25-400 kV A1 @ WOO-03 | BUSBAR SECTION - WOODLAND 400-WOODLAND 400-400A1 | 15 | 10 | 10 | Scheduled | 29/07/2025 | 12/08/2025
TO-25-400 kV A2 @ WOO-01 | BUSBAR SECTION - WOODLAND 400-WOODLAND 400-400A2 | 15 | 10 | 10 | Scheduled | 29/07/2025 | 12/08/2025
TO-25-400 kV B1 @ WOO-03 | BUSBAR SECTION - WOODLAND 400-WOODLAND 400-400B1 | 15 | 10 | 10 | Scheduled | 29/07/2025 | 12/08/2025
TO-25-400 kV B2 @ WOO-02 | BUSBAR SECTION - WOODLAND 400-WOODLAND 400-400B2 | 15 | 10 | 10 | Scheduled | 29/07/2025 | 12/08/2025
TO-25-WOO-400K1-2-03 | COUPLER/SECTIONALISING CB - WOODLAND 400-WOODLAND 400-400K1-2 | 15 | 10 | 10 | Scheduled | 29/07/2025 | 12/08/2025
TO-25-DFR,T-RNW-1-02 | 110kV FEEDER - DUNFIRTH tee-RINAWADE 110-1 | 36 | 25 |  | Scheduled | 30/07/2025 | 03/09/2025
TO-25-110 kV A2 @ MAY-01 | BUSBAR SECTION - MAYNOOTH 110-MAYNOOTH 110-110A2 | 15 | 10 | 10 | Scheduled | 30/07/2025 | 13/08/2025
TO-25-110 kV A3 @ MAY-01 | BUSBAR SECTION - MAYNOOTH 110-MAYNOOTH 110-110A3 | 15 | 10 | 10 | Scheduled | 30/07/2025 | 13/08/2025
TO-25-110 kV B2 @ MAY-01 | BUSBAR SECTION - MAYNOOTH 110-MAYNOOTH 110-110B2 | 15 | 10 | 10 | Scheduled | 30/07/2025 | 13/08/2025
TO-25-110 kV B3 @ MAY-01 | BUSBAR SECTION - MAYNOOTH 110-MAYNOOTH 110-110B3 | 15 | 10 | 10 | Scheduled | 30/07/2025 | 13/08/2025
TO-25-MAY-RYB GIS-1-01 | 110kV FEEDER - MAYNOOTH 110-RYEBROOK GIS 110-1 | 36 | 25 | 25 | Scheduled | 30/07/2025 | 03/09/2025
TO-25-110 kV A1 @ RYB GIS-01 | BUSBAR SECTION - RYEBROOK GIS 110-RYEBROOK GIS 110-110A1 | 15 | 10 |  | Scheduled | 30/07/2025 | 13/08/2025
TO-25-110 kV B1 @ RYB GIS-01 | BUSBAR SECTION - RYEBROOK GIS 110-RYEBROOK GIS 110-110B1 | 15 | 10 | 10 | Scheduled | 30/07/2025 | 13/08/2025
TO-25-RYB GIS-110SA1-2CB-02 | COUPLER/SECTIONALISING CB - RYEBROOK GIS 110-RYEBROOK GIS 110-110SA1-2CB | 15 | 10 | 10 | Scheduled | 30/07/2025 | 13/08/2025
TO-25-RYB GIS-110SA1-3CB-03 | COUPLER/SECTIONALISING CB - RYEBROOK GIS 110-RYEBROOK GIS 110-110SA1-3CB | 15 | 10 | 10 | Scheduled | 30/07/2025 | 13/08/2025
TO-25-RYB GIS-110SB1-2CB-02 | COUPLER/SECTIONALISING CB - RYEBROOK GIS 110-RYEBROOK GIS 110-110SB1-2CB | 15 | 10 | 10 | Scheduled | 30/07/2025 | 13/08/2025
TO-25-RYB GIS-110SB1-3CB-02 | COUPLER/SECTIONALISING CB - RYEBROOK GIS 110-RYEBROOK GIS 110-110SB1-3CB | 15 | 10 | 10 | Scheduled | 30/07/2025 | 13/08/2025
TO-25-DSN-400K1-2-01 | COUPLER/SECTIONALISING CB - DUNSTOWN 400-DUNSTOWN 400-400K1-2 | 1 | 1 | 1 | Scheduled | 31/07/2025 | 31/07/2025
TO-25-CKM-PB-1-07 | 220kV FEEDER - CARRICKMINES 220-POOLBEG 220-1 | 7 | 5 | 5 | Scheduled | 05/08/2025 | 11/08/2025
TO-25-220 kV A1 @ PB-01 | BUSBAR SECTION - POOLBEG 220-POOLBEG 220-220A1 | 7 | 5 | 5 | Scheduled | 05/08/2025 | 11/08/2025
TO-25-220 kV A2 @ PB-01 | BUSBAR SECTION - POOLBEG 220-POOLBEG 220-220A2 | 7 | 5 | 5 | Scheduled | 05/08/2025 | 11/08/2025
TO-25-COL-CDU-1-03 | 110kV FEEDER - COLLEGE PARK 110-CORDUFF 110-1 | 3 | 3 | 3 | Scheduled | 12/08/2025 | 14/08/2025
TO-25-CLG-FIN GIS-1-03 | 110kV FEEDER - CLOGHRAN 110-FINGLAS GIS 110-1 | 18 | 12 | 12 | Proposed | 15/08/2025 | 01/09/2025
TO-25-CLG-FIN GIS-1-01 | 110kV FEEDER - CLOGHRAN 110-FINGLAS GIS 110-1 | 18 | 12 | 12 | Scheduled | 15/08/2025 | 01/09/2025
TO-25-MCE-SNU-1-01 | 110kV FEEDER - MACETOWN 110-SNUGBOROUGH 110-1 | 18 | 12 | 12 | Proposed | 15/08/2025 | 01/09/2025
TO-25-MCE-SNU-1-02 | 110kV FEEDER - MACETOWN 110-SNUGBOROUGH 110-1 | 18 | 12 | 12 | Scheduled | 15/08/2025 | 01/09/2025
TO-25-110 kV A1 @ BLC-01 | BUSBAR SECTION - BELCAMP 110-BELCAMP 110-110A1 | 5 | 5 | 5 | Scheduled | 18/08/2025 | 22/08/2025
TO-25-110 kV A3 @ BLC-03 | BUSBAR SECTION - BELCAMP 110-BELCAMP 110-110A3 | 5 | 5 | 5 | Scheduled | 18/08/2025 | 22/08/2025
TO-25-BLC-110K1-03 | COUPLER/SECTIONALISING CB - BELCAMP 110-BELCAMP 110-110K1 | 5 | 5 | 5 | Scheduled | 18/08/2025 | 22/08/2025
TO-25-BLC-110K3-03 | COUPLER/SECTIONALISING CB - BELCAMP 110-BELCAMP 110-110K3 | 5 | 5 | 5 | Scheduled | 18/08/2025 | 22/08/2025
TO-25-BLC-110SA1-3CB-01 | COUPLER/SECTIONALISING CB - BELCAMP 110-BELCAMP 110-110SA1-3CB | 5 | 5 | 5 | Scheduled | 18/08/2025 | 22/08/2025
TO-25-110 kV A1 @ CLG-01 | BUSBAR SECTION - CLOGHRAN 110-CLOGHRAN 110-110A1 | 2 | 2 | 2 | Scheduled | 18/08/2025 | 19/08/2025
TO-25-110 kV B1 @ CLG-01 | BUSBAR SECTION - CLOGHRAN 110-CLOGHRAN 110-110B1 | 2 | 2 | 2 | Scheduled | 18/08/2025 | 19/08/2025
TO-25-CLG-110K1-03 | COUPLER/SECTIONALISING CB - CLOGHRAN 110-CLOGHRAN 110-110K1 | 2 | 2 | 2 | Scheduled | 18/08/2025 | 19/08/2025
TO-25-CLG-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - CLOGHRAN 110-CLOGHRAN 110-110SA1-2CB | 2 | 2 | 2 | Scheduled | 18/08/2025 | 19/08/2025
TO-25-CLG-110SB1-2CB-01 | COUPLER/SECTIONALISING CB - CLOGHRAN 110-CLOGHRAN 110-110SB1-2CB | 2 | 2 | 2 | Scheduled | 18/08/2025 | 19/08/2025
TO-25-220 kV A2 @ CLE-01 | BUSBAR SECTION - CLONEE 220-CLONEE 220-220A2 | 12 | 10 | 10 | Scheduled | 18/08/2025 | 29/08/2025
TO-25-220 kV B2 @ CLE-01 | BUSBAR SECTION - CLONEE 220-CLONEE 220-220B2 | 12 | 10 | 10 | Scheduled | 18/08/2025 | 29/08/2025
TO-25-CLE-220K2-03 | COUPLER/SECTIONALISING CB - CLONEE 220-CLONEE 220-220K2 | 12 | 10 | 10 | Scheduled | 18/08/2025 | 29/08/2025
TO-25-CLE-220SA1-2CB-05 | COUPLER/SECTIONALISING CB - CLONEE 220-CLONEE 220-220SA1-2CB | 12 | 10 | 10 | Scheduled | 18/08/2025 | 29/08/2025
TO-25-CLE-220SB1-2CB-05 | COUPLER/SECTIONALISING CB - CLONEE 220-CLONEE 220-220SB1-2CB | 12 | 10 | 10 | Scheduled | 18/08/2025 | 29/08/2025
TO-25-CLE-T222-01 | TSO CUSTOMER TRANSFORMER - CLONEE 220-CLONEE 20-T222 | 12 | 10 | 10 | Scheduled | 18/08/2025 | 29/08/2025
TO-25-220 kV A2 @ DSN-01 | BUSBAR SECTION - DUNSTOWN 220-DUNSTOWN 220-220A2 | 15 | 11 | 11 | Scheduled | 18/08/2025 | 01/09/2025
TO-25-DSN-T4201-01 | TRANSFORMER - DUNSTOWN 400-DUNSTOWN 220-T4201 | 12 | 10 | 10 | Proposed | 18/08/2025 | 29/08/2025
TO-25-110 kV A5 @ FIN GIS-02 | BUSBAR SECTION - FINGLAS GIS 110-FINGLAS GIS 110-110A5 | 16 | 12 | 12 | Proposed | 18/08/2025 | 02/09/2025
TO-25-110 kV B5 @ FIN GIS-02 | BUSBAR SECTION - FINGLAS GIS 110-FINGLAS GIS 110-110B5 | 16 | 12 | 12 | Proposed | 18/08/2025 | 02/09/2025
TO-25-FIN GIS-110K5-03 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110K5 | 16 | 12 | 12 | Proposed | 18/08/2025 | 02/09/2025
TO-25-FIN GIS-110SA3-5CB-05 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110SA3-5CB | 16 | 12 | 12 | Proposed | 18/08/2025 | 02/09/2025
TO-25-FIN GIS-110SB3-5CB-04 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110SB3-5CB | 16 | 12 | 12 | Proposed | 18/08/2025 | 02/09/2025
TO-25-MCE-110SA1-02 | SECTIONALISING DISCONNECT - MACETOWN 110-MACETOWN 110-110SA1 | 2 | 2 | 2 | Scheduled | 18/08/2025 | 19/08/2025
TO-25-MCE-110SA2-02 | SECTIONALISING DISCONNECT - MACETOWN 110-MACETOWN 110-110SA2 | 2 | 2 | 2 | Scheduled | 18/08/2025 | 19/08/2025
TO-25-MCE-T102-02 | DISTRIBUTION TRANSFORMER - MACETOWN 110-MACETOWN 10-T102 | 2 | 2 | 2 | Reference | 18/08/2025 | 19/08/2025
TO-25-MCE-T124-02 | TSO CUSTOMER TRANSFORMER - MACETOWN 110-MACETOWN 20-T124 | 2 | 2 | 2 | Scheduled | 18/08/2025 | 19/08/2025
TO-25-110 kV A2 @ SNU-01 | BUSBAR SECTION - SNUGBOROUGH 110-SNUGBOROUGH 110-110A2 | 16 | 12 | 12 | Proposed | 18/08/2025 | 02/09/2025
TO-25-110 kV B2 @ SNU-02 | BUSBAR SECTION - SNUGBOROUGH 110-SNUGBOROUGH 110-110B2 | 16 | 12 | 12 | Proposed | 18/08/2025 | 02/09/2025
TO-25-SNU-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - SNUGBOROUGH 110-SNUGBOROUGH 110-110SA1-2CB | 16 | 12 | 12 | Proposed | 18/08/2025 | 02/09/2025
TO-25-SNU-110SB1-2CB-02 | COUPLER/SECTIONALISING CB - SNUGBOROUGH 110-SNUGBOROUGH 110-110SB1-2CB | 16 | 12 | 12 | Proposed | 18/08/2025 | 02/09/2025
TO-25-CDU-220K1-3-02 | COUPLER/SECTIONALISING CB - CORDUFF 220-CORDUFF 220-220K1-3 | 2 | 2 | 2 | Proposed | 20/08/2025 | 21/08/2025
TO-25-CBT-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - CASTLEBAGOT 110-CASTLEBAGOT 110-110SA1-2CB | 1 | 1 | 1 | Scheduled | 25/08/2025 | 25/08/2025
TO-25-RYB GIS-110K3-01 | COUPLER/SECTIONALISING CB - RYEBROOK GIS 110-RYEBROOK GIS 110-110K3 | 2 | 2 | 2 | Proposed | 26/08/2025 | 27/08/2025
TO-25-RYB GIS-T102-01 | TSO CUSTOMER TRANSFORMER - RYEBROOK GIS 110-RYEBROOK 10-T102 | 2 | 2 | 2 | Proposed | 26/08/2025 | 27/08/2025
TO-25-KTL-T142-01 | DISTRIBUTION TRANSFORMER - KILTEEL 110-KILTEEL 38-T142 | 2 | 2 | 2 | Reference (Proposed) | 28/08/2025 | 29/08/2025
TO-25-RYB GIS-110K4-01 | COUPLER/SECTIONALISING CB - RYEBROOK GIS 110-RYEBROOK GIS 110-110K4 | 2 | 2 | 2 | Proposed | 28/08/2025 | 29/08/2025
TO-25-110 kV A4 @ CBT-01 | BUSBAR SECTION - CASTLEBAGOT 110-CASTLEBAGOT 110-110A4 | 22 | 16 | 16 | Proposed | 29/08/2025 | 19/09/2025
TO-25-110 kV B4 @ CBT-01 | BUSBAR SECTION - CASTLEBAGOT 110-CASTLEBAGOT 110-110B4 | 22 | 16 | 16 | Proposed | 29/08/2025 | 19/09/2025
TO-25-CBT-110K4-02 | COUPLER/SECTIONALISING CB - CASTLEBAGOT 110-CASTLEBAGOT 110-110K4 | 22 | 16 | 16 | Proposed | 29/08/2025 | 19/09/2025
TO-25-CBT-110SA2-4CB-02 | COUPLER/SECTIONALISING CB - CASTLEBAGOT 110-CASTLEBAGOT 110-110SA2-4CB | 22 | 16 | 16 | Proposed | 29/08/2025 | 19/09/2025
TO-25-CBT-110SB2-4CB-02 | COUPLER/SECTIONALISING CB - CASTLEBAGOT 110-CASTLEBAGOT 110-110SB2-4CB | 22 | 16 | 16 | Proposed | 29/08/2025 | 19/09/2025
TO-25-220 kV A2 @ CBT-02 | BUSBAR SECTION - CASTLEBAGOT 220-CASTLEBAGOT 220-220A2 | 22 | 16 | 16 | Proposed | 29/08/2025 | 19/09/2025
TO-25-220 kV B2 @ CBT-02 | BUSBAR SECTION - CASTLEBAGOT 220-CASTLEBAGOT 220-220B2 | 22 | 16 | 16 | Proposed | 29/08/2025 | 19/09/2025
TO-25-CBT-220K2-04 | COUPLER/SECTIONALISING CB - CASTLEBAGOT 220-CASTLEBAGOT 220-220K2 | 22 | 16 | 16 | Proposed | 29/08/2025 | 19/09/2025
TO-25-CBT-220SA1-2CB-04 | COUPLER/SECTIONALISING CB - CASTLEBAGOT 220-CASTLEBAGOT 220-220SA1-2CB | 22 | 16 | 16 | Proposed | 29/08/2025 | 19/09/2025
TO-25-CBT-220SB1-2CB-04 | COUPLER/SECTIONALISING CB - CASTLEBAGOT 220-CASTLEBAGOT 220-220SB1-2CB | 22 | 16 | 16 | Proposed | 29/08/2025 | 19/09/2025
TO-25-CBT-T2104-01 | TRANSFORMER - CASTLEBAGOT 220-CASTLEBAGOT 110-T2104 | 22 | 16 | 16 | Proposed | 29/08/2025 | 19/09/2025
TO-25-CLU-T122-01 | TSO CUSTOMER TRANSFORMER - CLUTTERLAND 110-CLUTTERLAND 20-T122 | 5 | 5 | 5 | Proposed | 01/09/2025 | 05/09/2025
TO-25-CRU-T224-02 | TSO CUSTOMER TRANSFORMER - CRUISERATH 220-CRUISERATH 20-T224 | 40 | 30 | 30 | Proposed | 01/09/2025 | 10/10/2025
TO-25-220 kV A2 @ MAY-04 | BUSBAR SECTION - MAYNOOTH 220-MAYNOOTH 220-220A2 | 12 | 10 | 10 | Scheduled | 01/09/2025 | 12/09/2025
TO-25-220 kV B2 @ MAY-04 | BUSBAR SECTION - MAYNOOTH 220-MAYNOOTH 220-220B2 | 12 | 10 | 10 | Scheduled | 01/09/2025 | 12/09/2025
TO-25-PB-SHL-1-01 | 220kV FEEDER - POOLBEG 220-SHELLYBANKS 220-1 | 26 | 20 | 20 | Proposed | 01/09/2025 | 26/09/2025
TO-25-PB-SHL-1-03 | 220kV FEEDER - POOLBEG 220-SHELLYBANKS 220-1 | 26 | 20 | 20 | Proposed | 01/09/2025 | 26/09/2025
TO-25-SHL-D1/CB3-04 | COUPLER/SECTIONALISING CB - SHELLYBANKS 220-SHELLYBANKS 220-D1/CB3 | 26 | 20 | 20 | Proposed | 01/09/2025 | 26/09/2025
TO-25-SHL-D1/CB3-05 | COUPLER/SECTIONALISING CB - SHELLYBANKS 220-SHELLYBANKS 220-D1/CB3 | 26 | 20 | 20 | Proposed | 01/09/2025 | 26/09/2025
TO-25-SHL-D2/CB3-03 | COUPLER/SECTIONALISING CB - SHELLYBANKS 220-SHELLYBANKS 220-D2/CB3 | 26 | 20 | 20 | Proposed | 01/09/2025 | 26/09/2025
TO-25-SHL-D2/CB3-04 | COUPLER/SECTIONALISING CB - SHELLYBANKS 220-SHELLYBANKS 220-D2/CB3 | 26 | 20 | 20 | Proposed | 01/09/2025 | 26/09/2025
TO-25-220 kV B2 @ DSN-01 | BUSBAR SECTION - DUNSTOWN 220-DUNSTOWN 220-220B2 | 15 | 11 | 11 | Scheduled | 02/09/2025 | 16/09/2025
TO-25-DSN-220K1-2-01 | COUPLER/SECTIONALISING CB - DUNSTOWN 220-DUNSTOWN 220-220K1-2 | 2 | 2 | 2 | Scheduled | 02/09/2025 | 03/09/2025
TO-25-BAG 110 - CLG 110 - 1-02 | 110kV FEEDER - BARNAGEERAGH 110-CLOGHRAN 110-1 | 3 | 3 | 3 | Proposed | 03/09/2025 | 05/09/2025
TO-25-KUD-T101-01 | TSO CUSTOMER TRANSFORMER - KILMAHUD 110-KILMAHUD 10-T101 | 3 | 3 | 3 | Proposed | 03/09/2025 | 05/09/2025
TO-25-CDU-GLN-1-03 | 110kV FEEDER - CORDUFF 110-GALLANSTOWN 110-1 | 3 | 1 | 1 | Proposed | 05/09/2025 | 07/09/2025
TO-25-CLG-T121-01 | TSO CUSTOMER TRANSFORMER - CLOGHRAN 110-CLOGHRAN 20-T121 | 5 | 5 | 5 | Proposed | 08/09/2025 | 12/09/2025
TO-25-GOR-MAY-1-01 | 220kV FEEDER - GORMAN 220-MAYNOOTH 220-1 | 12 | 10 | 10 | Scheduled | 08/09/2025 | 19/09/2025
TO-25-GOR-MAY-1-03 | 220kV FEEDER - GORMAN 220-MAYNOOTH 220-1 | 12 | 10 | 10 | Proposed | 08/09/2025 | 19/09/2025
TO-25-KUD-T102-01 | TSO CUSTOMER TRANSFORMER - KILMAHUD 110-KILMAHUD 10-T102 | 3 | 3 | 3 | Proposed | 09/09/2025 | 11/09/2025
TO-25-KUD-T103-01 | TSO CUSTOMER TRANSFORMER - KILMAHUD 110-KILMAHUD 10-T103 | 2 | 2 | 2 | Scheduled | 09/09/2025 | 10/09/2025
TO-25-KUD-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - KILMAHUD 110-KILMAHUD 110-110SA1-2CB | 2 | 2 | 2 | Scheduled | 10/09/2025 | 11/09/2025
TO-25-KUD-110SA1-3CB-01 | COUPLER/SECTIONALISING CB - KILMAHUD 110-KILMAHUD 110-110SA1-3CB | 2 | 2 | 2 | Scheduled | 10/09/2025 | 11/09/2025
TO-25-BLC-DND-3-02 | 110kV FEEDER - BELCAMP 110-DARNDALE 110-3 | 5 | 5 | 5 | Proposed | 15/09/2025 | 19/09/2025
TO-25-CRU-220K1-01 | COUPLER/SECTIONALISING CB - CRUISERATH 220-CRUISERATH 220-220K1 | 5 | 5 | 5 | Scheduled | 15/09/2025 | 19/09/2025
TO-25-CRU-220K2-01 | COUPLER/SECTIONALISING CB - CRUISERATH 220-CRUISERATH 220-220K2 | 5 | 5 | 5 | Scheduled | 15/09/2025 | 19/09/2025
TO-25-CRU-SA1-2CB-01 | COUPLER/SECTIONALISING CB - CRUISERATH 220-CRUISERATH 220-220SA1-2CB | 5 | 5 | 5 | Scheduled | 15/09/2025 | 19/09/2025
TO-25-CRU-SB1-2CB-01 | COUPLER/SECTIONALISING CB - CRUISERATH 220-CRUISERATH 220-220SB1-2CB | 5 | 5 | 5 | Scheduled | 15/09/2025 | 19/09/2025
TO-25-KYT-220K2-01 | COUPLER/SECTIONALISING CB - KELLYSTOWN 220-KELLYSTOWN 220-220K2 | 5 | 5 | 5 | Scheduled | 15/09/2025 | 19/09/2025
TO-25-KYT-220K3-01 | COUPLER/SECTIONALISING CB - KELLYSTOWN 220-KELLYSTOWN 220-220K3 | 5 | 5 | 5 | Scheduled | 15/09/2025 | 19/09/2025
TO-25-KYT-220SA1-2CB-01 | COUPLER/SECTIONALISING CB - KELLYSTOWN 220-KELLYSTOWN 220-220SA1-2CB | 5 | 5 | 5 | Scheduled | 15/09/2025 | 19/09/2025
TO-25-KYT-220SA1-3CB-01 | COUPLER/SECTIONALISING CB - KELLYSTOWN 220-KELLYSTOWN 220-220SA1-3CB | 5 | 5 | 5 | Scheduled | 15/09/2025 | 19/09/2025
TO-25-KYT-220SB1-2CB-01 | COUPLER/SECTIONALISING CB - KELLYSTOWN 220-KELLYSTOWN 220-220SB1-2CB | 5 | 5 | 5 | Scheduled | 15/09/2025 | 19/09/2025
TO-25-KYT-220SB1-3CB-01 | COUPLER/SECTIONALISING CB - KELLYSTOWN 220-KELLYSTOWN 220-220SB1-3CB | 5 | 5 | 5 | Scheduled | 15/09/2025 | 19/09/2025
TO-25-MAY-TEN-1-01 | 110kV FEEDER - MAYNOOTH 110-TIMAHOE 110-1 | 87 | 62 | 62 | Scheduled | 15/09/2025 | 10/12/2025
TO-25-RYB GIS-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - RYEBROOK GIS 110-RYEBROOK GIS 110-110SA1-2CB | 5 | 5 | 5 | Scheduled | 15/09/2025 | 19/09/2025
TO-25-RYB GIS-110SA1-3CB-01 | COUPLER/SECTIONALISING CB - RYEBROOK GIS 110-RYEBROOK GIS 110-110SA1-3CB | 5 | 5 | 5 | Scheduled | 15/09/2025 | 19/09/2025
TO-25-RYB GIS-110SA2-4CB-01 | COUPLER/SECTIONALISING CB - RYEBROOK GIS 110-RYEBROOK GIS 110-110SA2-4CB | 5 | 5 | 5 | Scheduled | 15/09/2025 | 19/09/2025
TO-25-400 kV A2 @ DSN-01 | BUSBAR SECTION - DUNSTOWN 400-DUNSTOWN 400-400A2 | 15 | 11 | 11 | Scheduled | 17/09/2025 | 01/10/2025
TO-25-110 kV A2 @ CDU-01 | BUSBAR SECTION - CORDUFF 110-CORDUFF 110-110A2 | 12 | 10 | 10 | Proposed | 22/09/2025 | 03/10/2025
TO-25-110 kV A4 @ CDU-05 | BUSBAR SECTION - CORDUFF 110-CORDUFF 110-110A4 | 12 | 10 | 10 | Proposed | 22/09/2025 | 03/10/2025
TO-25-110 kV B2 @ CDU-03 | BUSBAR SECTION - CORDUFF 110-CORDUFF 110-110B2 | 12 | 10 | 10 | Proposed | 22/09/2025 | 03/10/2025
TO-25-110 kV B4 @ CDU-06 | BUSBAR SECTION - CORDUFF 110-CORDUFF 110-110B4 | 12 | 10 | 10 | Proposed | 22/09/2025 | 03/10/2025
TO-25-CDU-110SA2-4CB-03 | COUPLER/SECTIONALISING CB - CORDUFF 110-CORDUFF 110-110SA2-4CB | 12 | 10 | 10 | Proposed | 22/09/2025 | 03/10/2025
TO-25-CDU-110SB2-4CB-06 | COUPLER/SECTIONALISING CB - CORDUFF 110-CORDUFF 110-110SB2-4CB | 12 | 10 | 10 | Proposed | 22/09/2025 | 03/10/2025
TO-25-220 kV A2 @ CDU-04 | BUSBAR SECTION - CORDUFF 220-CORDUFF 220-220A2 | 12 | 10 | 10 | Proposed | 22/09/2025 | 03/10/2025
TO-25-220 kV A4 @ CDU-04 | BUSBAR SECTION - CORDUFF 220-CORDUFF 220-220A4 | 12 | 10 | 10 | Proposed | 22/09/2025 | 03/10/2025
TO-25-220 kV B2 @ CDU-04 | BUSBAR SECTION - CORDUFF 220-CORDUFF 220-220B2 | 12 | 10 | 10 | Proposed | 22/09/2025 | 03/10/2025
TO-25-220 kV B4 @ CDU-03 | BUSBAR SECTION - CORDUFF 220-CORDUFF 220-220B4 | 12 | 10 | 10 | Proposed | 22/09/2025 | 03/10/2025
TO-25-CDU-220SA2-4CB-04 | COUPLER/SECTIONALISING CB - CORDUFF 220-CORDUFF 220-220SA2-4CB | 12 | 10 | 10 | Proposed | 22/09/2025 | 03/10/2025
TO-25-CDU-220SB2-4CB-04 | COUPLER/SECTIONALISING CB - CORDUFF 220-CORDUFF 220-220SB2-4CB | 12 | 10 | 10 | Proposed | 22/09/2025 | 03/10/2025
TO-25-CDU-T2102-03 | TRANSFORMER - CORDUFF 220-CORDUFF 110-T2102 | 12 | 10 | 10 | Proposed | 22/09/2025 | 03/10/2025
TO-25-CRU-T222-01 | TSO CUSTOMER TRANSFORMER - CRUISERATH 220-CRUISERATH 20-T222 | 5 | 5 | 5 | Proposed | 22/09/2025 | 26/09/2025
TO-25-MAY-T2103-01 | TRANSFORMER - MAYNOOTH 220-MAYNOOTH 110-T2103 | Unknown | Unknown |  | Planned | September | October
TO-25-RYB GIS-110SB1-2CB-01 | COUPLER/SECTIONALISING CB - RYEBROOK GIS 110-RYEBROOK GIS 110-110SB1-2CB | 5 | 5 | 5 | Scheduled | 22/09/2025 | 26/09/2025
TO-25-RYB GIS-110SB1-3CB-01 | COUPLER/SECTIONALISING CB - RYEBROOK GIS 110-RYEBROOK GIS 110-110SB1-3CB | 5 | 5 | 5 | Scheduled | 22/09/2025 | 26/09/2025
TO-25-RYB GIS-110SB2-4CB-01 | COUPLER/SECTIONALISING CB - RYEBROOK GIS 110-RYEBROOK GIS 110-110SB2-4CB | 5 | 5 | 5 | Scheduled | 22/09/2025 | 26/09/2025
TO-25-400 kV B2 @ WOO-01 | BUSBAR SECTION - WOODLAND 400-WOODLAND 400-400B2 | Unknown | Unknown | 15 | Planned | September | October
TO-25-CLE-T221-02 | TSO CUSTOMER TRANSFORMER - CLONEE 220-CLONEE 20-T221 | 39 | 26 | 26 | Proposed | 26/09/2025 | 03/11/2025
TO-25-BLC-110SB1-3CB-01 | COUPLER/SECTIONALISING CB - BELCAMP 110-BELCAMP 110-110SB1-3CB | 5 | 5 | 5 | Proposed | 29/09/2025 | 03/10/2025
TO-25-CBT-INC-2-02 | 220kV FEEDER - CASTLEBAGOT 220-INCHICORE 220-2 | Unknown | Unknown | 20 | Planned | September | October
TO-25-CDU-T102-01 | GENERATOR TRANSFORMER - CORDUFF 110-CORDUFF 10.5-T102 | Unknown | Unknown | 1 | Planned | September | September
TO-25-400 kV B2 @ DSN-01 | BUSBAR SECTION - DUNSTOWN 400-DUNSTOWN 400-400B2 | 14 | 10 | 10 | Scheduled | 02/10/2025 | 15/10/2025
TO-25-MAY-T2104-01 | TRANSFORMER - MAYNOOTH 220-MAYNOOTH 110-T2104 | Unknown | Unknown |  | Planned | October | October
TO-25-RYB GIS-T108-01 | TSO CUSTOMER TRANSFORMER - RYEBROOK GIS 110-RYEBROOK 10-T108 | 4 | 4 | 4 | Proposed | 06/10/2025 | 09/10/2025
TO-25-RYB GIS-T109-01 | TSO CUSTOMER TRANSFORMER - RYEBROOK GIS 110-RYEBROOK 10-T109 | 3 | 3 | 3 | Proposed | 13/10/2025 | 15/10/2025
TO-25-RYB GIS-T103-01 | TSO CUSTOMER TRANSFORMER - RYEBROOK GIS 110-RYEBROOK 10-T103 | 2 | 2 | 2 | Proposed | 16/10/2025 | 17/10/2025
TO-25-DSN-MAY-1-01 | 220kV FEEDER - DUNSTOWN 220-MAYNOOTH 220-1 | Unknown | Unknown |  | Planned | October | October
TO-25-KYT-T233-01 | TSO CUSTOMER TRANSFORMER - KELLYSTOWN 220-KELLYSTOWN 34.5-T233 | 19 | 14 | 14 | Proposed | 20/10/2025 | 07/11/2025
TO-25-KYT-T233-02 | TSO CUSTOMER TRANSFORMER - KELLYSTOWN 220-KELLYSTOWN 34.5-T233 | 19 | 14 | 14 | Proposed | 20/10/2025 | 07/11/2025
TO-25-220 kV A2 @ MAY-01 | BUSBAR SECTION - MAYNOOTH 220-MAYNOOTH 220-220A2 | 5 | 5 | 5 | Scheduled | 20/10/2025 | 24/10/2025
TO-25-220 kV B2 @ MAY-02 | BUSBAR SECTION - MAYNOOTH 220-MAYNOOTH 220-220B2 | 5 | 5 | 5 | Scheduled | 20/10/2025 | 24/10/2025
TO-25-MAY-220K1-2-02 | COUPLER/SECTIONALISING CB - MAYNOOTH 220-MAYNOOTH 220-220K1-2 | 5 | 5 | 5 | Scheduled | 20/10/2025 | 24/10/2025
TO-25-MAY-TH-1-01 | 220kV FEEDER - MAYNOOTH 220-TURLOUGH HILL 220-1 | Unknown | Unknown |  | Planned | October | November
TO-25-MAY-TH-1-05 | 220kV FEEDER - MAYNOOTH 220-TURLOUGH HILL 220-1 | Unknown | Unknown | 5 | Planned | October | October
TO-25-110 kV A2 @ RYB GIS-01 | BUSBAR SECTION - RYEBROOK GIS 110-RYEBROOK GIS 110-110A2 | 15 | 10 | 10 | Proposed | 20/10/2025 | 03/11/2025
TO-25-110 kV B2 @ RYB GIS-01 | BUSBAR SECTION - RYEBROOK GIS 110-RYEBROOK GIS 110-110B2 | 15 | 10 | 10 | Proposed | 20/10/2025 | 03/11/2025
TO-25-RYB GIS-110SA1-2CB-03 | COUPLER/SECTIONALISING CB - RYEBROOK GIS 110-RYEBROOK GIS 110-110SA1-2CB | 15 | 10 | 10 | Proposed | 20/10/2025 | 03/11/2025
TO-25-RYB GIS-110SA2-4CB-02 | COUPLER/SECTIONALISING CB - RYEBROOK GIS 110-RYEBROOK GIS 110-110SA2-4CB | 15 | 10 | 10 | Proposed | 20/10/2025 | 03/11/2025
TO-25-RYB GIS-110SB1-2CB-03 | COUPLER/SECTIONALISING CB - RYEBROOK GIS 110-RYEBROOK GIS 110-110SB1-2CB | 15 | 10 | 10 | Proposed | 20/10/2025 | 03/11/2025
TO-25-RYB GIS-110SB2-4CB-02 | COUPLER/SECTIONALISING CB - RYEBROOK GIS 110-RYEBROOK GIS 110-110SB2-4CB | 15 | 10 | 10 | Proposed | 20/10/2025 | 03/11/2025
TO-25-RYB GIS-T104-01 | TSO CUSTOMER TRANSFORMER - RYEBROOK GIS 110-RYEBROOK 10-T104 | 15 | 10 | 10 | Proposed | 20/10/2025 | 03/11/2025
TO-25-220 kV A1 @ MAY-01 | BUSBAR SECTION - MAYNOOTH 220-MAYNOOTH 220-220A1 | Unknown | Unknown |  | Planned | November | November
TO-25-220 kV B1 @ MAY-01 | BUSBAR SECTION - MAYNOOTH 220-MAYNOOTH 220-220B1 | Unknown | Unknown |  | Planned | November | November
TO-25-KYT-T237-01 | TSO CUSTOMER TRANSFORMER - KELLYSTOWN 220-KELLYSTOWN 34.5-T237 | 3 | 3 | 3 | Proposed | 11/11/2025 | 13/11/2025
TO-25-DSN-MAY-2-01 | 220kV FEEDER - DUNSTOWN 220-MAYNOOTH 220-2 | 2 | 2 | 2 | Scheduled | 13/11/2025 | 14/11/2025
TO-25-220 kV A2 @ MAY-02 | BUSBAR SECTION - MAYNOOTH 220-MAYNOOTH 220-220A2 | 2 | 2 | 2 | Scheduled | 13/11/2025 | 14/11/2025
TO-25-DSN-MAY-2-02 | 220kV FEEDER - DUNSTOWN 220-MAYNOOTH 220-2 | Unknown | Unknown |  | Planned | December | December

## GEN_Cork
Outage ID | Feeder ID | Calendar Day Duration | Working Day Duration | Work Days | Outage Status | Start | Finish
TO-25-CHA-MAL-1-03 | 110kV FEEDER - CHARLEVILLE 110-MALLOW 110-1 | 4 | 4 | 4 | Scheduled | 07/01/2025 | 10/01/2025
TO-25-COW-110SA1-01 | SECTIONALISING DISCONNECT - COW CROSS 110-COW CROSS 110-110SA1 | 10 | 8 | 8 | Scheduled | 14/01/2025 | 23/01/2025
TO-25-COW-110SA2-01 | SECTIONALISING DISCONNECT - COW CROSS 110-COW CROSS 110-110SA2 | 10 | 8 | 8 | Scheduled | 14/01/2025 | 23/01/2025
TO-25-COW-OLD-2-01 | 110kV FEEDER - COW CROSS 110-OLDCOURT 110-2 | 10 | 8 | 8 | Reference | 14/01/2025 | 23/01/2025
TO-25-COW-RAF-1-01 | 110kV FEEDER - COW CROSS 110-RAFFEEN 110-1 | 10 | 8 | 8 | Scheduled | 14/01/2025 | 23/01/2025
TO-25-COW-T141-01 | DISTRIBUTION TRANSFORMER - COW CROSS 110-COW CROSS 38-T141 | 10 | 8 | 8 | Reference | 14/01/2025 | 23/01/2025
TO-25-OLD-T102-01 | DISTRIBUTION TRANSFORMER - OLDCOURT 110-OLDCOURT 10-T102 | 10 | 8 | 8 | Reference | 14/01/2025 | 23/01/2025
TO-25-BAR-T141-01 | DISTRIBUTION TRANSFORMER - BARRYMORE 110-BARRYMORE 38-T141 | 3 | 3 | 3 | Reference | 10/02/2025 | 12/02/2025
TO-25-BAR,T-BAR-1-01 | 110kV FEEDER - BARRYMORE tee-BARRYMORE 110-1 | 3 | 3 | 3 | Scheduled | 10/02/2025 | 12/02/2025
TO-25-BAR,T-CAH-1-02 | 110kV FEEDER - BARRYMORE tee-CAHIR 110-1 | 19 | 15 | 15 | Proposed | 10/02/2025 | 28/02/2025
TO-25-BAR,T-CAH-1-01 | 110kV FEEDER - BARRYMORE tee-CAHIR 110-1 | 19 | 15 | 15 | Scheduled | 10/02/2025 | 28/02/2025
TO-25-BAR,T-KRA-1-02 | 110kV FEEDER - BARRYMORE tee-KNOCKRAHA 110-1 | 3 | 3 | 3 | Scheduled | 10/02/2025 | 12/02/2025
TO-25-CVW-COW-1-01 | 110kV FEEDER - CASTLEVIEW 110-COW CROSS 110-1 | 16 | 12 | 12 | Scheduled | 18/02/2025 | 05/03/2025
TO-25-COW-110SA1-02 | SECTIONALISING DISCONNECT - COW CROSS 110-COW CROSS 110-110SA1 | 16 | 12 | 12 | Scheduled | 18/02/2025 | 05/03/2025
TO-25-COW-110SA2-02 | SECTIONALISING DISCONNECT - COW CROSS 110-COW CROSS 110-110SA2 | 16 | 12 | 12 | Scheduled | 18/02/2025 | 05/03/2025
TO-25-COW-OLD-1-01 | 110kV FEEDER - COW CROSS 110-OLDCOURT 110-1 | 16 | 12 | 12 | Reference | 18/02/2025 | 05/03/2025
TO-25-COW-WHI-1-01 | 110kV FEEDER - COW CROSS 110-WHITEGATE 110-1 | 16 | 12 |  | Scheduled | 18/02/2025 | 05/03/2025
TO-25-OLD-T101-01 | DISTRIBUTION TRANSFORMER - OLDCOURT 110-OLDCOURT 10-T101 | 16 | 12 | 12 | Reference | 18/02/2025 | 05/03/2025
TO-25-BAR-T141-03 | DISTRIBUTION TRANSFORMER - BARRYMORE 110-BARRYMORE 38-T141 | 5 | 5 | 5 | Reference | 24/02/2025 | 28/02/2025
TO-25-BAR,T-BAR-1-03 | 110kV FEEDER - BARRYMORE tee-BARRYMORE 110-1 | 5 | 5 | 5 | Scheduled | 24/02/2025 | 28/02/2025
TO-25-BAR,T-KRA-1-01 | 110kV FEEDER - BARRYMORE tee-KNOCKRAHA 110-1 | 19 | 15 | 15 | Scheduled | 24/02/2025 | 14/03/2025
TO-25-CLA-DMY-1-01 | 110kV FEEDER - CLASHAVOON 110-DUNMANWAY 110-1 | 5 | 5 |  | Scheduled | 24/02/2025 | 28/02/2025
TO-25-110 kV B1 @ KRA-01 | BUSBAR SECTION - KNOCKRAHA 110-KNOCKRAHA 110-110B1 | 19 | 15 | 15 | Scheduled | 24/02/2025 | 14/03/2025
TO-25-110 kV B1 @ CLA-01 | BUSBAR SECTION - CLASHAVOON 110-CLASHAVOON 110-110B1 | 13 | 10 |  | Scheduled | 03/03/2025 | 15/03/2025
TO-25-BRI-T101-04 | TSO CUSTOMER TRANSFORMER - BRINNY 110-BRINNY 10-T101 | 4 | 4 | 4 | Scheduled | 04/03/2025 | 07/03/2025
TO-25-BRI-T102-03 | TSO CUSTOMER TRANSFORMER - BRINNY 110-BRINNY 10-T102 | 4 | 4 | 4 | Scheduled | 11/03/2025 | 14/03/2025
TO-25-KLN-KRA-1-04 | 220kV FEEDER - KILLONAN 220-KNOCKRAHA 220-1 | 4 | 4 | 4 | Scheduled | 11/03/2025 | 14/03/2025
TO-25-LYT-T132-01 | GENERATOR TRANSFORMER - LYSAGHTSTOWN 110-LYSAGHTSTOWN 33-T132 | 1 | 1 | 1 | Scheduled | 11/03/2025 | 11/03/2025
TO-25-BAR-T141-04 | DISTRIBUTION TRANSFORMER - BARRYMORE 110-BARRYMORE 38-T141 | 3 | 3 | 3 | Reference | 12/03/2025 | 14/03/2025
TO-25-BAR,T-BAR-1-04 | 110kV FEEDER - BARRYMORE tee-BARRYMORE 110-1 | 3 | 3 | 3 | Scheduled | 12/03/2025 | 14/03/2025
TO-25-BAR,T-CAH-1-03 | 110kV FEEDER - BARRYMORE tee-CAHIR 110-1 | 3 | 3 | 3 | Scheduled | 12/03/2025 | 14/03/2025
TO-25-LYT-110K2-01 | COUPLER/SECTIONALISING CB - LYSAGHTSTOWN 110-LYSAGHTSTOWN 110-110K2 | 1 | 1 | 1 | Scheduled | 12/03/2025 | 12/03/2025
TO-25-220 kV A1 @ AD-01 | BUSBAR SECTION - AGHADA 220-AGHADA 220-220A1 | 11 | 9 | 9 | Scheduled | 18/03/2025 | 28/03/2025
TO-25-220 kV A2 @ AD-02 | BUSBAR SECTION - AGHADA 220-AGHADA 220-220A2 | 11 | 9 | 9 | Scheduled | 18/03/2025 | 28/03/2025
TO-25-220 kV B1 @ AD-02 | BUSBAR SECTION - AGHADA 220-AGHADA 220-220B1 | 11 | 9 | 9 | Scheduled | 18/03/2025 | 28/03/2025
TO-25-220 kV B2 @ AD-02 | BUSBAR SECTION - AGHADA 220-AGHADA 220-220B2 | 11 | 9 | 9 | Scheduled | 18/03/2025 | 28/03/2025
TO-25-AD-220K1-01 | COUPLER/SECTIONALISING CB - AGHADA 220-AGHADA 220-220K1 | 11 | 9 | 9 | Scheduled | 18/03/2025 | 28/03/2025
TO-25-AD-SA1-2CB-03 | COUPLER/SECTIONALISING CB - AGHADA 220-AGHADA 220-220SA1-2CB | 11 | 9 | 9 | Scheduled | 18/03/2025 | 28/03/2025
TO-25-AD-SB1-2CB-03 | COUPLER/SECTIONALISING CB - AGHADA 220-AGHADA 220-220SB1-2CB | 11 | 9 | 9 | Scheduled | 18/03/2025 | 28/03/2025
TO-25-CLA-110K1-2-01 | COUPLER/SECTIONALISING CB - CLASHAVOON 110-CLASHAVOON 110-110K1-2 | 44 | 30 |  | Scheduled | 18/03/2025 | 30/04/2025
TO-25-KBY-MR-1-03 | 110kV FEEDER - KILBARRY 110-MARINA 110-1 | 186 | 129 | 129 | Scheduled | 18/03/2025 | 19/09/2025
TO-25-KBY-MR-2-03 | 110kV FEEDER - KILBARRY 110-MARINA 110-2 | 186 | 129 | 129 | Scheduled | 18/03/2025 | 19/09/2025
TO-25-KRA-WOH-1-03 | 110kV FEEDER - KNOCKRAHA 110-WOODHOUSE 110-1 | 3 | 3 | 3 | Scheduled | 18/03/2025 | 20/03/2025
TO-25-AD-T2011/12-02 | GENERATOR TRANSFORMER - AGHADA 220-AGHADA G11/12-T2011/12 | 9 | 7 | 7 | Scheduled | 24/03/2025 | 01/04/2025
TO-25-220 kV A4 @ KRA-01 | BUSBAR SECTION - KNOCKRAHA 220-KNOCKRAHA 220-220A4 | 75 | 51 | 51 | Scheduled | 24/03/2025 | 06/06/2025
TO-25-220 kV B4 @ KRA-01 | BUSBAR SECTION - KNOCKRAHA 220-KNOCKRAHA 220-220B4 | 75 | 51 | 51 | Scheduled | 24/03/2025 | 06/06/2025
TO-25-KRA-220K4-01 | COUPLER/SECTIONALISING CB - KNOCKRAHA 220-KNOCKRAHA 220-220K4 | 75 | 51 | 51 | Scheduled | 24/03/2025 | 06/06/2025
TO-25-KRA-220SA2-4CB-02 | COUPLER/SECTIONALISING CB - KNOCKRAHA 220-KNOCKRAHA 220-220SA2-4CB | 75 | 51 | 51 | Scheduled | 24/03/2025 | 06/06/2025
TO-25-KRA-220SB2-4CB-02 | COUPLER/SECTIONALISING CB - KNOCKRAHA 220-KNOCKRAHA 220-220SB2-4CB | 75 | 51 | 51 | Scheduled | 24/03/2025 | 06/06/2025
TO-25-AD-T2014-01 | GENERATOR TRANSFORMER - AGHADA 220-AGHADA G14-T2014 | 9 | 7 | 7 | Scheduled | 31/03/2025 | 08/04/2025
TO-25-LYT-T132-02 | GENERATOR TRANSFORMER - LYSAGHTSTOWN 110-LYSAGHTSTOWN 33-T132 | 1 | 1 | 1 | Scheduled | 07/04/2025 | 07/04/2025
TO-25-CHA-MAL-1-06 | 110kV FEEDER - CHARLEVILLE 110-MALLOW 110-1 | 3 | 3 | 3 | Scheduled | 14/04/2025 | 16/04/2025
TO-25-CD-T103-02 | GENERATOR TRANSFORMER - CARRIGADROHID 110-CARRIGADROHID G3-T103 | 8 | 6 | 6 | Scheduled | 23/04/2025 | 30/04/2025
TO-25-MR-T106-01 | DISTRIBUTION TRANSFORMER - MARINA 110-MARINA 10-T106 | 2 | 2 | 2 | Reference | 23/04/2025 | 24/04/2025
TO-25-COW-OLD-2-02 | 110kV FEEDER - COW CROSS 110-OLDCOURT 110-2 | 2 | 2 | 2 | Reference | 30/04/2025 | 01/05/2025
TO-25-OLD-T102-02 | DISTRIBUTION TRANSFORMER - OLDCOURT 110-OLDCOURT 10-T102 | 2 | 2 |  | Reference | 30/04/2025 | 01/05/2025
TO-25-CD-MAC-1-01 | 110kV FEEDER - CARRIGADROHID 110-MACROOM 110-1 | 100 | 69 | 69 | Scheduled | 01/05/2025 | 08/08/2025
TO-25-CGG-DMY-1-01 | 110kV FEEDER - CARRIGDANGAN 110-DUNMANWAY 110-1 | 9 | 7 |  | Scheduled | 07/05/2025 | 15/05/2025
TO-25-CGG-T131-01 | GENERATOR TRANSFORMER - CARRIGDANGAN 110-CARRIGDANGAN 33-T131 | 9 | 7 | 7 | Scheduled | 07/05/2025 | 15/05/2025
TO-25-BGH-110SA1-01 | SECTIONALISING DISCONNECT - BOGGERAGH 110-BOGGERAGH 110-110SA1 | 17 | 12 | 12 | Scheduled | 26/05/2025 | 11/06/2025
TO-25-BGH-110SA2-01 | SECTIONALISING DISCONNECT - BOGGERAGH 110-BOGGERAGH 110-110SA2 | 17 | 12 | 12 | Scheduled | 26/05/2025 | 11/06/2025
TO-25-BGH-CLA-1-01 | 110kV FEEDER - BOGGERAGH 110-CLASHAVOON 110-1 | 17 | 12 | 12 | Scheduled | 26/05/2025 | 11/06/2025
TO-25-BGH-T121-02 | GENERATOR TRANSFORMER - BOGGERAGH 110-BOGGERAGH 20-T121 | 17 | 12 | 12 | Scheduled | 26/05/2025 | 11/06/2025
TO-25-BGH-T132-01 | GENERATOR TRANSFORMER - BOGGERAGH 110-BOGGERAGH 33-T132 | 17 | 12 | 12 | Scheduled | 26/05/2025 | 11/06/2025
TO-25-BGH-T142-01 | DISTRIBUTION TRANSFORMER - BOGGERAGH 110-BOGGERAGH 38-T142 | 17 | 12 | 12 | Reference | 26/05/2025 | 11/06/2025
TO-25-110 kV B1 @ CLA-02 | BUSBAR SECTION - CLASHAVOON 110-CLASHAVOON 110-110B1 | 17 | 12 | 12 | Scheduled | 26/05/2025 | 11/06/2025
TO-25-IA-T101-05 | GENERATOR TRANSFORMER - INNISCARRA 110-INNISCARRA G1-T101 | 9 | 7 | 7 | Scheduled | 04/06/2025 | 12/06/2025
TO-25-220 kV A1 @ AD-03 | BUSBAR SECTION - AGHADA 220-AGHADA 220-220A1 | 1 | 1 | 1 | Scheduled | 17/06/2025 | 17/06/2025
TO-25-220 kV A2 @ AD-03 | BUSBAR SECTION - AGHADA 220-AGHADA 220-220A2 | 1 | 1 | 1 | Scheduled | 17/06/2025 | 17/06/2025
TO-25-AD-220K1-02 | COUPLER/SECTIONALISING CB - AGHADA 220-AGHADA 220-220K1 | 1 | 1 | 1 | Scheduled | 17/06/2025 | 17/06/2025
TO-25-AD-T2011/12-03 | GENERATOR TRANSFORMER - AGHADA 220-AGHADA G11/12-T2011/12 | 1 | 1 | 1 | Scheduled | 17/06/2025 | 17/06/2025
TO-25-110 kV B2 @ KBY-01 | BUSBAR SECTION - KILBARRY 110-KILBARRY 110-110B2 | 8 | 6 | 6 | Scheduled | 17/06/2025 | 24/06/2025
TO-25-KBY-MAL-1-01 | 110kV FEEDER - KILBARRY 110-MALLOW 110-1 | 8 | 6 | 6 | Scheduled | 17/06/2025 | 24/06/2025
TO-25-CD-KBY-1-02 | 110kV FEEDER - CARRIGADROHID 110-KILBARRY 110-1 | 12 | 10 | 10 | Scheduled | 07/07/2025 | 18/07/2025
TO-25-CD-T103-04 | GENERATOR TRANSFORMER - CARRIGADROHID 110-CARRIGADROHID G3-T103 | 12 | 10 | 10 | Scheduled | 07/07/2025 | 18/07/2025
TO-25-110 kV B1 @ KBY-01 | BUSBAR SECTION - KILBARRY 110-KILBARRY 110-110B1 | 12 | 10 | 10 | Scheduled | 07/07/2025 | 18/07/2025
TO-25-220 kV A1 @ AD-04 | BUSBAR SECTION - AGHADA 220-AGHADA 220-220A1 | 2 | 2 | 2 | Scheduled | 08/07/2025 | 09/07/2025
TO-25-220 kV A2 @ AD-04 | BUSBAR SECTION - AGHADA 220-AGHADA 220-220A2 | 2 | 2 | 2 | Scheduled | 08/07/2025 | 09/07/2025
TO-25-AD-220K1-03 | COUPLER/SECTIONALISING CB - AGHADA 220-AGHADA 220-220K1 | 2 | 2 | 2 | Scheduled | 08/07/2025 | 09/07/2025
TO-25-AD-SA1-2CB-05 | COUPLER/SECTIONALISING CB - AGHADA 220-AGHADA 220-220SA1-2CB | 2 | 2 | 2 | Scheduled | 08/07/2025 | 09/07/2025
TO-25-KBY-KRA-2-01 | 110kV FEEDER - KILBARRY 110-KNOCKRAHA 110-2 | 1 | 1 | 1 | Scheduled | 15/07/2025 | 15/07/2025
TO-25-BAN-110SA1-03 | SECTIONALISING DISCONNECT - BANDON 110-BANDON 110-110SA1 | 12 | 10 | 10 | Scheduled | 21/07/2025 | 01/08/2025
TO-25-BAN-110SA2-04 | SECTIONALISING DISCONNECT - BANDON 110-BANDON 110-110SA2 | 12 | 10 | 10 | Scheduled | 21/07/2025 | 01/08/2025
TO-25-BAN-BRI-2-02 | 110kV FEEDER - BANDON 110-BRINNY 110-2 | 12 | 10 | 10 | Scheduled | 21/07/2025 | 01/08/2025
TO-25-BAN-RAF-1-04 | 110kV FEEDER - BANDON 110-RAFFEEN 110-1 | 12 | 10 | 10 | Scheduled | 21/07/2025 | 01/08/2025
TO-25-BAN-T142-01 | DISTRIBUTION TRANSFORMER - BANDON 110-BANDON 38-T142 | 12 | 10 | 10 | Reference | 21/07/2025 | 01/08/2025
TO-25-BRI-T102-01 | TSO CUSTOMER TRANSFORMER - BRINNY 110-BRINNY 10-T102 | 12 | 10 | 10 | Scheduled | 21/07/2025 | 01/08/2025
TO-25-110 kV A2 @ RAF-02 | BUSBAR SECTION - RAFFEEN 110-RAFFEEN 110-110A2 | 10 | 8 | 8 | Scheduled | 21/07/2025 | 30/07/2025
TO-25-110 kV B2 @ RAF-02 | BUSBAR SECTION - RAFFEEN 110-RAFFEEN 110-110B2 | 10 | 8 | 8 | Scheduled | 21/07/2025 | 30/07/2025
TO-25-220 kV A1 @ RAF-02 | BUSBAR SECTION - RAFFEEN 220-RAFFEEN 220-220A1 | 10 | 8 | 8 | Scheduled | 22/07/2025 | 31/07/2025
TO-25-220 kV A2 @ RAF-01 | BUSBAR SECTION - RAFFEEN 220-RAFFEEN 220-220A2 | 10 | 8 | 8 | Scheduled | 22/07/2025 | 31/07/2025
TO-25-220 kV B1 @ RAF-02 | BUSBAR SECTION - RAFFEEN 220-RAFFEEN 220-220B1 | 10 | 8 | 8 | Scheduled | 22/07/2025 | 31/07/2025
TO-25-220 kV B2 @ RAF-01 | BUSBAR SECTION - RAFFEEN 220-RAFFEEN 220-220B2 | 10 | 8 | 8 | Scheduled | 22/07/2025 | 31/07/2025
TO-25-RAF-220K1-2-01 | COUPLER/SECTIONALISING CB - RAFFEEN 220-RAFFEEN 220-220K1-2 | 10 | 8 | 8 | Scheduled | 22/07/2025 | 31/07/2025
TO-25-220 kV A2 @ AD-01 | BUSBAR SECTION - AGHADA 220-AGHADA 220-220A2 | 4 | 4 | 4 | Scheduled | 05/08/2025 | 08/08/2025
TO-25-220 kV B2 @ AD-01 | BUSBAR SECTION - AGHADA 220-AGHADA 220-220B2 | 4 | 4 | 4 | Scheduled | 05/08/2025 | 08/08/2025
TO-25-AD-GGO-1-01 | 220kV FEEDER - AGHADA 220-GLANAGOW 220-1 | 4 | 4 | 4 | Scheduled | 05/08/2025 | 08/08/2025
TO-25-DMY-T141-01 | DISTRIBUTION TRANSFORMER - DUNMANWAY 110-DUNMANWAY 38-T141 | 2 | 2 | 2 | Reference | 05/08/2025 | 06/08/2025
TO-25-DMY-T142-01 | DISTRIBUTION TRANSFORMER - DUNMANWAY 110-DUNMANWAY 38-T142 | 2 | 2 | 2 | Reference | 07/08/2025 | 08/08/2025
TO-25-CRO-IA-1-01 | 110kV FEEDER - COOLROE 110-INNISCARRA 110-1 | 12 | 10 | 10 | Scheduled | 11/08/2025 | 22/08/2025
TO-25-IA-MAC-1-03 | 110kV FEEDER - INNISCARRA 110-MACROOM 110-1 | 12 | 10 | 10 | Scheduled | 11/08/2025 | 22/08/2025
TO-25-IA-T101-01 | GENERATOR TRANSFORMER - INNISCARRA 110-INNISCARRA G1-T101 | 12 | 10 | 10 | Scheduled | 11/08/2025 | 22/08/2025
TO-25-IA-T101-02 | GENERATOR TRANSFORMER - INNISCARRA 110-INNISCARRA G1-T101 | 12 | 10 | 10 | Scheduled | 11/08/2025 | 22/08/2025
TO-25-CVW-KRA-1-01 | 110kV FEEDER - CASTLEVIEW 110-KNOCKRAHA 110-1 | 12 | 10 | 10 | Scheduled | 18/08/2025 | 29/08/2025
TO-25-CLA-MAC-1-02 | 110kV FEEDER - CLASHAVOON 110-MACROOM 110-1 | 5 | 5 | 5 | Scheduled | 18/08/2025 | 22/08/2025
TO-25-CLA-MAC-1-04 | 110kV FEEDER - CLASHAVOON 110-MACROOM 110-1 | 5 | 5 | 5 | Proposed | 18/08/2025 | 22/08/2025
TO-25-DMY-MAC-1-03 | 110kV FEEDER - DUNMANWAY 110-MACROOM 110-1 | 26 | 20 | 20 | Scheduled | 18/08/2025 | 12/09/2025
TO-25-110 kV A2 @ KRA-04 | BUSBAR SECTION - KNOCKRAHA 110-KNOCKRAHA 110-110A2 | 12 | 10 | 10 | Scheduled | 18/08/2025 | 29/08/2025
TO-25-110 kV B2 @ KRA-04 | BUSBAR SECTION - KNOCKRAHA 110-KNOCKRAHA 110-110B2 | 12 | 10 | 10 | Scheduled | 18/08/2025 | 29/08/2025
TO-25-CLA-KRA-1-01 | 220kV FEEDER - CLASHAVOON 220-KNOCKRAHA 220-1 | 9 | 7 | 7 | Proposed | 01/09/2025 | 09/09/2025
TO-25-CLA-KRA-1-02 | 220kV FEEDER - CLASHAVOON 220-KNOCKRAHA 220-1 | 16 | 12 | 12 | Proposed | 01/09/2025 | 16/09/2025
TO-25-CRO-KBY-1-01 | 110kV FEEDER - COOLROE 110-KILBARRY 110-1 | 8 | 6 | 6 | Scheduled | 01/09/2025 | 08/09/2025
TO-25-220 kV A1 @ KRA-01 | BUSBAR SECTION - KNOCKRAHA 220-KNOCKRAHA 220-220A1 | 9 | 7 | 7 | Proposed | 01/09/2025 | 09/09/2025
TO-25-220 kV A1 @ KRA-04 | BUSBAR SECTION - KNOCKRAHA 220-KNOCKRAHA 220-220A1 | 16 | 12 | 12 | Proposed | 01/09/2025 | 16/09/2025
TO-25-220 kV B1 @ KRA-01 | BUSBAR SECTION - KNOCKRAHA 220-KNOCKRAHA 220-220B1 | 9 | 7 | 7 | Proposed | 01/09/2025 | 09/09/2025
TO-25-220 kV B1 @ KRA-04 | BUSBAR SECTION - KNOCKRAHA 220-KNOCKRAHA 220-220B1 | 16 | 12 | 12 | Proposed | 01/09/2025 | 16/09/2025
TO-25-KRA-220K1-01 | COUPLER/SECTIONALISING CB - KNOCKRAHA 220-KNOCKRAHA 220-220K1 | 9 | 7 | 7 | Proposed | 01/09/2025 | 09/09/2025
TO-25-KRA-220K1-04 | COUPLER/SECTIONALISING CB - KNOCKRAHA 220-KNOCKRAHA 220-220K1 | 16 | 12 | 12 | Proposed | 01/09/2025 | 16/09/2025
TO-25-KRA-220SA1-2CB-01 | COUPLER/SECTIONALISING CB - KNOCKRAHA 220-KNOCKRAHA 220-220SA1-2CB | 9 | 7 | 7 | Proposed | 01/09/2025 | 09/09/2025
TO-25-KRA-220SA1-2CB-05 | COUPLER/SECTIONALISING CB - KNOCKRAHA 220-KNOCKRAHA 220-220SA1-2CB | 16 | 12 | 12 | Proposed | 01/09/2025 | 16/09/2025
TO-25-KRA-220SB1-2CB-05 | COUPLER/SECTIONALISING CB - KNOCKRAHA 220-KNOCKRAHA 220-220SB1-2CB | 16 | 12 | 12 | Proposed | 01/09/2025 | 16/09/2025
TO-25-KRA-220SB1-2CB-01 | COUPLER/SECTIONALISING CB - KNOCKRAHA 220-KNOCKRAHA 220-220SB1-2CB | 9 | 7 | 7 | Proposed | 01/09/2025 | 09/09/2025
TO-25-KRA-T2101-01 | TRANSFORMER - KNOCKRAHA 220-KNOCKRAHA 110-T2101 | 9 | 7 | 7 | Proposed | 01/09/2025 | 09/09/2025
TO-25-WHI-CKB-T101-01 | TSO CUSTOMER TRANSFORMER - WHITEGATE 110-WHITEGATE 10-CKB-T101 | 5 | 5 | 5 | Scheduled | 01/09/2025 | 05/09/2025
TO-25-GGO-T2001-01 | GENERATOR TRANSFORMER - GLANAGOW 220-GLANAGOW G1-T2001 | 5 | 4 | 4 | Proposed | 02/09/2025 | 06/09/2025
TO-25-110 kV B1 @ RAF-02 | BUSBAR SECTION - RAFFEEN 110-RAFFEEN 110-110B1 | 3 | 3 | 3 | Proposed | 02/09/2025 | 04/09/2025
TO-25-WHI-CKB-T102-01 | TSO CUSTOMER TRANSFORMER - WHITEGATE 110-WHITEGATE 10-CKB-T102 | 5 | 5 | 5 | Scheduled | 08/09/2025 | 12/09/2025
TO-25-AD-HWL-1-01 | 220kV FEEDER - AGHADA 220-HADWELL 220-1 | 2 | 2 | 2 | Scheduled | 22/09/2025 | 23/09/2025
TO-25-AD-KRA-1-04 | 220kV FEEDER - AGHADA 220-KNOCKRAHA 220-1 | 19 | 15 | 15 | Proposed | 22/09/2025 | 10/10/2025
TO-25-AD-KRA-1-01 | 220kV FEEDER - AGHADA 220-KNOCKRAHA 220-1 | 19 | 15 | 15 | Proposed | 22/09/2025 | 10/10/2025
TO-25-AD-KRA-1-03 | 220kV FEEDER - AGHADA 220-KNOCKRAHA 220-1 | 19 | 15 | 15 | Proposed | 22/09/2025 | 10/10/2025
TO-25-AD-KRA-2-04 | 220kV FEEDER - AGHADA 220-KNOCKRAHA 220-2 | 19 | 15 | 15 | Proposed | 22/09/2025 | 10/10/2025
TO-25-AD-KRA-2-01 | 220kV FEEDER - AGHADA 220-KNOCKRAHA 220-2 | 19 | 15 | 15 | Proposed | 22/09/2025 | 10/10/2025
TO-25-AD-KRA-2-03 | 220kV FEEDER - AGHADA 220-KNOCKRAHA 220-2 | 19 | 15 | 15 | Proposed | 22/09/2025 | 10/10/2025
TO-25-AD-LPT-1-01 | 220kV FEEDER - AGHADA 220-LONG POINT 220-1 | 5 | 5 | 5 | Proposed | 22/09/2025 | 26/09/2025
TO-25-DMY-CAP2-01 | CAPACITOR/SVC/REACTOR - DUNMANWAY 110-DUNMANWAY 110-CAP2 | 4 | 4 | 4 | Scheduled | 22/09/2025 | 25/09/2025
TO-25-HWL-ATA10-01 | GENERATOR TRANSFORMER - HADWELL 220-HADWELL 33-ATA10 | 2 | 2 | 2 | Scheduled | 22/09/2025 | 23/09/2025
TO-25-HWL-ATA20-01 | GENERATOR TRANSFORMER - HADWELL 220-HADWELL 33-ATA20 | 2 | 2 | 2 | Scheduled | 22/09/2025 | 23/09/2025
TO-25-110 kV A2 @ KRA-01 | BUSBAR SECTION - KNOCKRAHA 110-KNOCKRAHA 110-110A2 | Unknown | Unknown | 60 | Planned | September | December
TO-25-110 kV B2 @ KRA-01 | BUSBAR SECTION - KNOCKRAHA 110-KNOCKRAHA 110-110B2 | Unknown | Unknown | 60 | Planned | September | December
TO-25-220 kV A1 @ KRA-02 | BUSBAR SECTION - KNOCKRAHA 220-KNOCKRAHA 220-220A1 | 19 | 15 | 15 | Proposed | 22/09/2025 | 10/10/2025
TO-25-220 kV A2 @ KRA-01 | BUSBAR SECTION - KNOCKRAHA 220-KNOCKRAHA 220-220A2 | 19 | 15 | 15 | Proposed | 22/09/2025 | 10/10/2025
TO-25-220 kV B1 @ KRA-02 | BUSBAR SECTION - KNOCKRAHA 220-KNOCKRAHA 220-220B1 | 19 | 15 | 15 | Proposed | 22/09/2025 | 10/10/2025
TO-25-220 kV B2 @ KRA-01 | BUSBAR SECTION - KNOCKRAHA 220-KNOCKRAHA 220-220B2 | 19 | 15 | 15 | Proposed | 22/09/2025 | 10/10/2025
TO-25-KRA-220K1-02 | COUPLER/SECTIONALISING CB - KNOCKRAHA 220-KNOCKRAHA 220-220K1 | 19 | 15 | 15 | Proposed | 22/09/2025 | 10/10/2025
TO-25-KRA-220SA1-2CB-02 | COUPLER/SECTIONALISING CB - KNOCKRAHA 220-KNOCKRAHA 220-220SA1-2CB | 19 | 15 | 15 | Proposed | 22/09/2025 | 10/10/2025
TO-25-KRA-220SA1-2CB-03 | COUPLER/SECTIONALISING CB - KNOCKRAHA 220-KNOCKRAHA 220-220SA1-2CB | 19 | 15 | 15 | Proposed | 22/09/2025 | 10/10/2025
TO-25-KRA-220SA2-4CB-01 | COUPLER/SECTIONALISING CB - KNOCKRAHA 220-KNOCKRAHA 220-220SA2-4CB | 19 | 15 | 15 | Proposed | 22/09/2025 | 10/10/2025
TO-25-KRA-220SB1-2CB-02 | COUPLER/SECTIONALISING CB - KNOCKRAHA 220-KNOCKRAHA 220-220SB1-2CB | 19 | 15 | 15 | Proposed | 22/09/2025 | 10/10/2025
TO-25-KRA-220SB1-2CB-03 | COUPLER/SECTIONALISING CB - KNOCKRAHA 220-KNOCKRAHA 220-220SB1-2CB | 19 | 15 | 15 | Proposed | 22/09/2025 | 10/10/2025
TO-25-KRA-220SB2-4CB-01 | COUPLER/SECTIONALISING CB - KNOCKRAHA 220-KNOCKRAHA 220-220SB2-4CB | 19 | 15 | 15 | Proposed | 22/09/2025 | 10/10/2025
TO-25-KRA-T2102-01 | TRANSFORMER - KNOCKRAHA 220-KNOCKRAHA 110-T2102 | 19 | 15 | 15 | Proposed | 22/09/2025 | 10/10/2025
TO-25-KRA-T2102-02 | TRANSFORMER - KNOCKRAHA 220-KNOCKRAHA 110-T2102 | Unknown | Unknown | 15 | Planned | September | October
TO-25-LPT-T2002-01 | GENERATOR TRANSFORMER - LONG POINT 220-LONG POINT G1-T2002 | 5 | 5 | 5 | Proposed | 22/09/2025 | 26/09/2025
TO-25-AD-KRA-1-02 | 220kV FEEDER - AGHADA 220-KNOCKRAHA 220-1 | 12 | 10 | 10 | Proposed | 29/09/2025 | 10/10/2025
TO-25-AD-KRA-2-02 | 220kV FEEDER - AGHADA 220-KNOCKRAHA 220-2 | 12 | 10 | 10 | Proposed | 29/09/2025 | 10/10/2025
TO-25-KBY-MR-1-02 | 110kV FEEDER - KILBARRY 110-MARINA 110-1 | Unknown | Unknown | 40 | Planned | October | December
TO-25-KBY-MR-2-02 | 110kV FEEDER - KILBARRY 110-MARINA 110-2 | Unknown | Unknown | 40 | Planned | October | December
TO-25-110 kV A2 @ KRA-02 | BUSBAR SECTION - KNOCKRAHA 110-KNOCKRAHA 110-110A2 | Unknown | Unknown | 10 | Planned | November | November
TO-25-110 kV B2 @ KRA-02 | BUSBAR SECTION - KNOCKRAHA 110-KNOCKRAHA 110-110B2 | Unknown | Unknown | 10 | Planned | November | November
TO-25-KRA-WOH-1-01 | 110kV FEEDER - KNOCKRAHA 110-WOODHOUSE 110-1 | Unknown | Unknown | 10 | Planned | December | December
TO-25-KRA-WOH-1-02 | 110kV FEEDER - KNOCKRAHA 110-WOODHOUSE 110-1 | Unknown | Unknown | 10 | Planned | December | December