## GEN_ALL
Outage ID | Feeder ID | Calendar Day Duration | Working Day Duration | Work Days | Outage Status | Start | Finish
TO-26-CBR-SVC-02 | CAPACITOR/SVC/REACTOR - CASTLEBAR 110-CASTLEBAR 110-SVC | 368 | 253 | 253 | Scheduled | 29/12/2025 | 31/12/2026
TO-26-110 kV A4 @ CBT-01 | BUSBAR SECTION - CASTLEBAGOT 110-CASTLEBAGOT 110-110A4 | 5 | 5 | 5 | Scheduled | 05/01/2026 | 09/01/2026
TO-26-110 kV B4 @ CBT-01 | BUSBAR SECTION - CASTLEBAGOT 110-CASTLEBAGOT 110-110B4 | 5 | 5 | 5 | Scheduled | 05/01/2026 | 09/01/2026
TO-26-CBT-110K4-01 | COUPLER/SECTIONALISING CB - CASTLEBAGOT 110-CASTLEBAGOT 110-110K4 | 5 | 5 |  | Scheduled | 05/01/2026 | 09/01/2026
TO-26-CBT-110SA2-4CB-01 | COUPLER/SECTIONALISING CB - CASTLEBAGOT 110-CASTLEBAGOT 110-110SA2-4CB | 5 | 5 | 5 | Scheduled | 05/01/2026 | 09/01/2026
TO-26-CBT-110SB2-4CB-01 | COUPLER/SECTIONALISING CB - CASTLEBAGOT 110-CASTLEBAGOT 110-110SB2-4CB | 5 | 5 | 5 | Scheduled | 05/01/2026 | 09/01/2026
TO-26-CHA-MAL-1-02 | 110kV FEEDER - CHARLEVILLE 110-MALLOW 110-1 | 5 | 5 | 5 | Scheduled | 05/01/2026 | 09/01/2026
TO-26-220 kV A2 @ FIN-05 | BUSBAR SECTION - FINGLAS 220-FINGLAS 220-220A2 | 5 | 5 | 5 | Scheduled | 05/01/2026 | 09/01/2026
TO-26-220 kV B2 @ FIN-03 | BUSBAR SECTION - FINGLAS 220-FINGLAS 220-220B2 | 5 | 5 | 5 | Scheduled | 05/01/2026 | 09/01/2026
TO-26-FIN-220K2-05 | COUPLER/SECTIONALISING CB - FINGLAS 220-FINGLAS 220-220K2 | 5 | 5 | 5 | Scheduled | 05/01/2026 | 09/01/2026
TO-26-FIN-220SA1-2CB-06 | COUPLER/SECTIONALISING CB - FINGLAS 220-FINGLAS 220-220SA1-2CB | 5 | 5 | 5 | Scheduled | 05/01/2026 | 09/01/2026
TO-26-FIN-220SB1-2CB-04 | COUPLER/SECTIONALISING CB - FINGLAS 220-FINGLAS 220-220SB1-2CB | 5 | 5 | 5 | Scheduled | 05/01/2026 | 09/01/2026
TO-26-GWE-T102-01 | TSO CUSTOMER TRANSFORMER - GORTAWEE 110-GORTAWEE 10-T102 | 5 | 5 |  | Scheduled | 05/01/2026 | 09/01/2026
TO-26-BUT-CUL-1-01 | 110kV FEEDER - BUTLERSTOWN 110-CULLENAGH 110-1 | 2 | 2 | 2 | Scheduled | 06/01/2026 | 07/01/2026
TO-26-GLN-110K1-01 | COUPLER/SECTIONALISING CB - GALLANSTOWN 110-GALLANSTOWN 110-110K1 | 1 | 1 | 1 | Scheduled | 06/01/2026 | 06/01/2026
TO-26-AUN-110K1-01 | COUPLER/SECTIONALISING CB - AUNGIERSTOWN 110-AUNGIERSTOWN 110-110K1 | 3 | 3 | 3 | Scheduled | 07/01/2026 | 09/01/2026
TO-26-AUN-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - AUNGIERSTOWN 110-AUNGIERSTOWN 110-110SA1-2CB | 3 | 3 | 3 | Scheduled | 07/01/2026 | 09/01/2026
TO-26-AUN-110SB1-2CB-01 | COUPLER/SECTIONALISING CB - AUNGIERSTOWN 110-AUNGIERSTOWN 110-110SB1-2CB | 3 | 3 | 3 | Scheduled | 07/01/2026 | 09/01/2026
TO-26-AD-T2014-01 | GENERATOR TRANSFORMER - AGHADA 220-AGHADA G14-T2014 | 49 | 34 | 34 | Scheduled | 11/01/2026 | 28/02/2026
TO-26-110 kV B2 @ CBT-01 | BUSBAR SECTION - CASTLEBAGOT 110-CASTLEBAGOT 110-110B2 | 5 | 5 | 5 | Scheduled | 12/01/2026 | 16/01/2026
TO-26-110 kV B4 @ CBT-02 | BUSBAR SECTION - CASTLEBAGOT 110-CASTLEBAGOT 110-110B4 | 5 | 5 | 5 | Scheduled | 12/01/2026 | 16/01/2026
TO-26-CBT-110K4-02 | COUPLER/SECTIONALISING CB - CASTLEBAGOT 110-CASTLEBAGOT 110-110K4 | 5 | 5 | 5 | Scheduled | 12/01/2026 | 16/01/2026
TO-26-CBT-110SB2-4CB-02 | COUPLER/SECTIONALISING CB - CASTLEBAGOT 110-CASTLEBAGOT 110-110SB2-4CB | 5 | 5 | 5 | Scheduled | 12/01/2026 | 16/01/2026
TO-26-DRY-OBE-1-02 | 110kV FEEDER - DRYBRIDGE 110-OLDBRIDGE 110-1 | 5 | 5 | 5 | Scheduled | 12/01/2026 | 16/01/2026
TO-26-LIS-LSA-1-04 | 110kV FEEDER - LISDRUM 110-LISLEA 110-1 | 10 | 8 |  | Scheduled | 12/01/2026 | 21/01/2026
TO-26-PRO-TB-1-02 | 220kV FEEDER - PROSPECT 220-TARBERT 220-1 | 9 | 7 |  | Scheduled | 12/01/2026 | 20/01/2026
TO-26-220 kV A2 @ TB-01 | BUSBAR SECTION - TARBERT 220-TARBERT 220-220A2 | 9 | 7 | 7 | Scheduled | 12/01/2026 | 20/01/2026
TO-26-220 kV B2 @ TB-01 | BUSBAR SECTION - TARBERT 220-TARBERT 220-220B2 | 9 | 7 | 7 | Scheduled | 12/01/2026 | 20/01/2026
TO-26-TTU-131-01 | GENERATOR TRANSFORMER - TULLABEG 110-TULLABEG 33-T131 | 9 | 7 |  | Scheduled | 12/01/2026 | 20/01/2026
TO-26-CAH-TIP-1-01 | 110kV FEEDER - CAHIR 110-TIPPERARY 110-1 | 1 | 1 | 1 | Scheduled | 14/01/2026 | 14/01/2026
TO-26-DGN-RTH-1-01 | 110kV FEEDER - DUNGARVAN 110-RATHNASKILLOGE 110-1 | 1 | 1 |  | Scheduled | 14/01/2026 | 14/01/2026
TO-26-TIP-110SA1-01 | SECTIONALISING DISCONNECT - TIPPERARY 110-TIPPERARY 110-110SA1 | 1 | 1 | 1 | Scheduled | 14/01/2026 | 14/01/2026
TO-26-TIP-110SA2-01 | SECTIONALISING DISCONNECT - TIPPERARY 110-TIPPERARY 110-110SA2 | 1 | 1 | 1 | Scheduled | 14/01/2026 | 14/01/2026
TO-26-AGL-ENN-1-03 | 110kV FEEDER - AGANNYGAL 110-ENNIS 110-1 | 12 | 10 |  | Scheduled | 19/01/2026 | 30/01/2026
TO-26-BAR-T141-03 | DISTRIBUTION TRANSFORMER - BARRYMORE 110-BARRYMORE 38-T141 | 4 | 4 | 4 | Reference | 19/01/2026 | 22/01/2026
TO-26-BAR,T-BAR-1-03 | 110kV FEEDER - BARRYMORE tee-BARRYMORE 110-1 | 4 | 4 | 4 | Scheduled | 19/01/2026 | 22/01/2026
TO-26-BAR,T-CAH-1-03 | 110kV FEEDER - BARRYMORE tee-CAHIR 110-1 | 4 | 4 | 4 | Scheduled | 19/01/2026 | 22/01/2026
TO-26-BAR,T-KRA-1-03 | 110kV FEEDER - BARRYMORE tee-KNOCKRAHA 110-1 | 4 | 4 | 4 | Scheduled | 19/01/2026 | 22/01/2026
TO-26-BLU-CDU-1-02 | 110kV FEEDER - BLUNDELSTOWN 110-CORDUFF 110-1 | 5 | 5 |  | Scheduled | 19/01/2026 | 23/01/2026
TO-26-110 kV A2 @ CBT-01 | BUSBAR SECTION - CASTLEBAGOT 110-CASTLEBAGOT 110-110A2 | 5 | 5 | 5 | Scheduled | 19/01/2026 | 23/01/2026
TO-26-110 kV A4 @ CBT-02 | BUSBAR SECTION - CASTLEBAGOT 110-CASTLEBAGOT 110-110A4 | 5 | 5 | 5 | Scheduled | 19/01/2026 | 23/01/2026
TO-26-CBT-110K4-03 | COUPLER/SECTIONALISING CB - CASTLEBAGOT 110-CASTLEBAGOT 110-110K4 | 5 | 5 | 5 | Scheduled | 19/01/2026 | 23/01/2026
TO-26-CBT-110SA2-4CB-02 | COUPLER/SECTIONALISING CB - CASTLEBAGOT 110-CASTLEBAGOT 110-110SA2-4CB | 5 | 5 | 5 | Scheduled | 19/01/2026 | 23/01/2026
TO-26-220 kV A1 @ FIN-02 | BUSBAR SECTION - FINGLAS 220-FINGLAS 220-220A1 | 4 | 4 | 4 | Scheduled | 19/01/2026 | 22/01/2026
TO-26-220 kV B1 @ FIN-02 | BUSBAR SECTION - FINGLAS 220-FINGLAS 220-220B1 | 4 | 4 | 4 | Scheduled | 19/01/2026 | 22/01/2026
TO-26-FIN-220K1-02 | COUPLER/SECTIONALISING CB - FINGLAS 220-FINGLAS 220-220K1 | 4 | 4 | 4 | Scheduled | 19/01/2026 | 22/01/2026
TO-26-FIN-220SA1-2CB-07 | COUPLER/SECTIONALISING CB - FINGLAS 220-FINGLAS 220-220SA1-2CB | 4 | 4 | 4 | Scheduled | 19/01/2026 | 22/01/2026
TO-26-FIN-220SB1-2CB-06 | COUPLER/SECTIONALISING CB - FINGLAS 220-FINGLAS 220-220SB1-2CB | 4 | 4 | 4 | Scheduled | 19/01/2026 | 22/01/2026
TO-26-LET-PST-04 | TRANSFORMER - LETTERKENNY 110-STRABANE 110-PST | 64 | 44 | 44 | Scheduled | 19/01/2026 | 23/03/2026
TO-26-LET-SVC-01 | CAPACITOR/SVC/REACTOR - LETTERKENNY 110-LETTERKENNY 110-SVC | 13 | 10 | 10 | Scheduled | 19/01/2026 | 31/01/2026
TO-26-LYT-T132-01 | GENERATOR TRANSFORMER - LYSAGHTSTOWN 110-LYSAGHTSTOWN 33-T132 | 2 | 2 | 2 | Scheduled | 19/01/2026 | 20/01/2026
TO-26-110 kV A2 @ MR-01 | BUSBAR SECTION - MARINA 110-MARINA 110-110A2 | 11 | 9 | 9 | Scheduled | 19/01/2026 | 29/01/2026
TO-26-110 kV B2 @ MR-01 | BUSBAR SECTION - MARINA 110-MARINA 110-110B2 | 11 | 9 | 9 | Scheduled | 19/01/2026 | 29/01/2026
TO-26-MR-TBG-2-02 | 110kV FEEDER - MARINA 110-TRABEG 110-2 | 11 | 9 |  | Scheduled | 19/01/2026 | 29/01/2026
TO-26-SH-T2102-02 | TRANSFORMER - SHANNONBRIDGE 220-SHANNONBRIDGE 110-T2102 | 103 | 71 | 71 | Scheduled | 19/01/2026 | 01/05/2026
TO-26-110 kV A2 @ TBG-01 | BUSBAR SECTION - TRABEG 110-TRABEG 110-110A2 | 11 | 9 | 9 | Scheduled | 19/01/2026 | 29/01/2026
TO-26-110 kV B2 @ TBG-01 | BUSBAR SECTION - TRABEG 110-TRABEG 110-110B2 | 11 | 9 | 9 | Scheduled | 19/01/2026 | 29/01/2026
TO-26-CRU-220K1-01 | COUPLER/SECTIONALISING CB - CRUISERATH 220-CRUISERATH 220-220K1 | 1 | 1 | 1 | Scheduled | 20/01/2026 | 20/01/2026
TO-26-NEW-PLS-1-01 | 110kV FEEDER - NEWBRIDGE 110-PORTLAOISE 110-1 | 128 | 87 | 87 | Scheduled | 20/01/2026 | 27/05/2026
TO-26-CRU-220K2-01 | COUPLER/SECTIONALISING CB - CRUISERATH 220-CRUISERATH 220-220K2 | 1 | 1 | 1 | Scheduled | 21/01/2026 | 21/01/2026
TO-26-KPG-TRL-1-01 | 110kV FEEDER - KILPADDOGE 110-TRALEE 110-1 | 3 | 3 |  | Scheduled | 21/01/2026 | 23/01/2026
TO-26-CRU-SA1-2CB-01 | COUPLER/SECTIONALISING CB - CRUISERATH 220-CRUISERATH 220-220SA1-2CB | 1 | 1 | 1 | Scheduled | 22/01/2026 | 22/01/2026
TO-26-CDU-FIN-2-03 | 220kV FEEDER - CORDUFF 220-FINGLAS 220-2 | 22 | 15 | 15 | Scheduled | 23/01/2026 | 13/02/2026
TO-26-CRU-SB1-2CB-01 | COUPLER/SECTIONALISING CB - CRUISERATH 220-CRUISERATH 220-220SB1-2CB | 1 | 1 | 1 | Scheduled | 23/01/2026 | 23/01/2026
TO-26-ARV-SKL-2-01 | 110kV FEEDER - ARVA 110-SHANKILL 110-2 | 3 | 3 |  | Scheduled | 26/01/2026 | 28/01/2026
TO-26-110 kV B1 @ CBT-01 | BUSBAR SECTION - CASTLEBAGOT 110-CASTLEBAGOT 110-110B1 | 5 | 5 | 5 | Scheduled | 26/01/2026 | 30/01/2026
TO-26-110 kV B2 @ CBT-02 | BUSBAR SECTION - CASTLEBAGOT 110-CASTLEBAGOT 110-110B2 | 5 | 5 | 5 | Scheduled | 26/01/2026 | 30/01/2026
TO-26-CBT-110K1-02 | COUPLER/SECTIONALISING CB - CASTLEBAGOT 110-CASTLEBAGOT 110-110K1 | 5 | 5 | 5 | Scheduled | 26/01/2026 | 30/01/2026
TO-26-CBT-110SB1-2CB-01 | COUPLER/SECTIONALISING CB - CASTLEBAGOT 110-CASTLEBAGOT 110-110SB1-2CB | 5 | 5 |  | Scheduled | 26/01/2026 | 30/01/2026
TO-26-110 kV A1 @ GI-02 | BUSBAR SECTION - GREAT ISLAND 110-GREAT ISLAND 110-110A1 | 5 | 5 | 5 | Scheduled | 26/01/2026 | 30/01/2026
TO-26-110 kV A2 @ GI-03 | BUSBAR SECTION - GREAT ISLAND 110-GREAT ISLAND 110-110A2 | 5 | 5 | 5 | Scheduled | 26/01/2026 | 30/01/2026
TO-26-110 kV B1 @ GI-02 | BUSBAR SECTION - GREAT ISLAND 110-GREAT ISLAND 110-110B1 | 5 | 5 | 5 | Scheduled | 26/01/2026 | 30/01/2026
TO-26-110 kV B2 @ GI-03 | BUSBAR SECTION - GREAT ISLAND 110-GREAT ISLAND 110-110B2 | 5 | 5 | 5 | Scheduled | 26/01/2026 | 30/01/2026
TO-26-GI-110K1-2-01 | COUPLER/SECTIONALISING CB - GREAT ISLAND 110-GREAT ISLAND 110-110K1-2 | 5 | 5 |  | Scheduled | 26/01/2026 | 30/01/2026
TO-26-MID-WHI-1-01 | 110kV FEEDER - MIDLETON 110-WHITEGATE 110-1 | 96 | 66 | 66 | Scheduled | 26/01/2026 | 01/05/2026
TO-26-PA-110SA1-02 | SECTIONALISING DISCONNECT - POLLAPHUCA 110-POLLAPHUCA 110-110SA1 | 5 | 5 | 5 | Scheduled | 26/01/2026 | 30/01/2026
TO-26-PA-110SA2-02 | SECTIONALISING DISCONNECT - POLLAPHUCA 110-POLLAPHUCA 110-110SA2 | 5 | 5 | 5 | Scheduled | 26/01/2026 | 30/01/2026
TO-26-PA-T101-02 | GENERATOR TRANSFORMER - POLLAPHUCA 110-POLLAPHUCA G1-T101 | 5 | 5 | 5 | Scheduled | 26/01/2026 | 30/01/2026
TO-26-PB-R2002-01 | CAPACITOR/SVC/REACTOR - POOLBEG 220-POOLBEG 220-R2002 | 5 | 5 |  | Scheduled | 26/01/2026 | 30/01/2026
TO-26-STR-T141-02 | DISTRIBUTION TRANSFORMER - STRATFORD 110-STRATFORD 38-T141 | 5 | 5 | 5 | Reference | 26/01/2026 | 30/01/2026
TO-26-STR,T-CLW-1-02 | 110kV FEEDER - STRATFORD tee-CARLOW 110-1 | 5 | 5 |  | Scheduled | 26/01/2026 | 30/01/2026
TO-26-STR,T-PA-1-02 | 110kV FEEDER - STRATFORD tee-POLLAPHUCA 110-1 | 5 | 5 | 5 | Scheduled | 26/01/2026 | 30/01/2026
TO-26-STR,T-STR-1-02 | 110kV FEEDER - STRATFORD tee-STRATFORD 110-1 | 5 | 5 | 5 | Scheduled | 26/01/2026 | 30/01/2026
TO-26-CDU-110K1-3-01 | COUPLER/SECTIONALISING CB - CORDUFF 110-CORDUFF 110-110K1-3 | 2 | 2 |  | Scheduled | 28/01/2026 | 29/01/2026
TO-26-BAL-CDU-1-03 | 110kV FEEDER - BALTRASNA 110-CORDUFF 110-1 | 8 | 6 | 6 | Scheduled | 03/02/2026 | 10/02/2026
TO-26-BLU-MUL-1-03 | 110kV FEEDER - BLUNDELSTOWN 110-MULLINGAR 110-1 | 3 | 3 |  | Scheduled | 03/02/2026 | 05/02/2026
TO-26-110 kV A2 @ CDU-01 | BUSBAR SECTION - CORDUFF 110-CORDUFF 110-110A2 | 8 | 6 | 6 | Scheduled | 03/02/2026 | 10/02/2026
TO-26-110 kV A4 @ CDU-02 | BUSBAR SECTION - CORDUFF 110-CORDUFF 110-110A4 | 8 | 6 | 6 | Scheduled | 03/02/2026 | 10/02/2026
TO-26-110 kV B2 @ CDU-01 | BUSBAR SECTION - CORDUFF 110-CORDUFF 110-110B2 | 8 | 6 | 6 | Scheduled | 03/02/2026 | 10/02/2026
TO-26-110 kV B4 @ CDU-01 | BUSBAR SECTION - CORDUFF 110-CORDUFF 110-110B4 | 8 | 6 | 6 | Scheduled | 03/02/2026 | 10/02/2026
TO-26-CDU-110SA2-4CB-01 | COUPLER/SECTIONALISING CB - CORDUFF 110-CORDUFF 110-110SA2-4CB | 8 | 6 | 6 | Scheduled | 03/02/2026 | 10/02/2026
TO-26-CDU-110SB2-4CB-01 | COUPLER/SECTIONALISING CB - CORDUFF 110-CORDUFF 110-110SB2-4CB | 8 | 6 | 6 | Scheduled | 03/02/2026 | 10/02/2026
TO-26-DMY-MAC-1-04 | 110kV FEEDER - DUNMANWAY 110-MACROOM 110-1 | 28 | 20 | 20 | Scheduled | 03/02/2026 | 02/03/2026
TO-26-DSN-MP GIS-1-03 | 400kV FEEDER - DUNSTOWN 400-MONEYPOINT GIS 400-1 | 59 | 42 |  | Scheduled | 03/02/2026 | 02/04/2026
TO-26-220 kV A2 @ INC-01 | BUSBAR SECTION - INCHICORE 220-INCHICORE 220-220A2 | 32 | 24 | 24 | Scheduled | 03/02/2026 | 06/03/2026
TO-26-220 kV B2 @ INC-01 | BUSBAR SECTION - INCHICORE 220-INCHICORE 220-220B2 | 32 | 24 | 24 | Scheduled | 03/02/2026 | 06/03/2026
TO-26-INC-PB-2-02 | 220kV FEEDER - INCHICORE 220-POOLBEG 220-2 | 32 | 24 | 24 | Scheduled | 03/02/2026 | 06/03/2026
TO-26-MUL-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - MULLINGAR 110-MULLINGAR 110-110SA1-2CB | 2 | 2 | 2 | Scheduled | 03/02/2026 | 04/02/2026
TO-26-MUL-T102-01 | DISTRIBUTION TRANSFORMER - MULLINGAR 110-MULLINGAR 10-T102 | 2 | 2 | 2 | Reference | 03/02/2026 | 04/02/2026
TO-26-MUL-T142-01 | DISTRIBUTION TRANSFORMER - MULLINGAR 110-MULLINGAR 38-T142 | 2 | 2 | 2 | Reference | 03/02/2026 | 04/02/2026
TO-26-220 kV A3 @ PB-01 | BUSBAR SECTION - POOLBEG 220-POOLBEG 220-220A3 | 32 | 24 | 24 | Scheduled | 03/02/2026 | 06/03/2026
TO-26-220 kV B3 @ PB-01 | BUSBAR SECTION - POOLBEG 220-POOLBEG 220-220B3 | 32 | 24 | 24 | Scheduled | 03/02/2026 | 06/03/2026
TO-26-ARV-SKL-1-02 | 110kV FEEDER - ARVA 110-SHANKILL 110-1 | 3 | 3 | 3 | Scheduled | 04/02/2026 | 06/02/2026
TO-26-LSN-110SA1-2-02 | SECTIONALISING DISCONNECT - LISHEEN 110-LISHEEN 110-110SA1-2 | 5 | 5 | 5 | Scheduled | 09/02/2026 | 13/02/2026
TO-26-LSN-110SA2-4-02 | SECTIONALISING DISCONNECT - LISHEEN 110-LISHEEN 110-110SA2-4 | 5 | 5 | 5 | Scheduled | 09/02/2026 | 13/02/2026
TO-26-LSN-T122-02 | GENERATOR TRANSFORMER - LISHEEN 110-LISHEEN 20-T122 | 5 | 5 | 5 | Scheduled | 09/02/2026 | 13/02/2026
TO-26-LSN-T131-01 | GENERATOR TRANSFORMER - LISHEEN 110-LISHEEN 33-T131 | 9 | 7 | 7 | Scheduled | 09/02/2026 | 17/02/2026
TO-26-LSN-T142-01 | DISTRIBUTION TRANSFORMER - LISHEEN 110-LISHEEN 38-T142 | 5 | 5 | 5 | Reference | 09/02/2026 | 13/02/2026
TO-26-LSN-THU-1-02 | 110kV FEEDER - LISHEEN 110-THURLES 110-1 | 5 | 5 | 5 | Scheduled | 09/02/2026 | 13/02/2026
TO-26-OBE-PLA-1-01 | 110kV FEEDER - OLDBRIDGE 110-PLATIN 110-1 | 5 | 5 | 5 | Scheduled | 09/02/2026 | 13/02/2026
TO-26-PLA-110SA1-01 | SECTIONALISING DISCONNECT - PLATIN 110-PLATIN 110-110SA1 | 5 | 5 | 5 | Scheduled | 09/02/2026 | 13/02/2026
TO-26-PLA-110SA2-01 | SECTIONALISING DISCONNECT - PLATIN 110-PLATIN 110-110SA2 | 5 | 5 | 5 | Scheduled | 09/02/2026 | 13/02/2026
TO-26-PLA-T101/2/3/4-01 | TSO CUSTOMER TRANSFORMER - PLATIN 110-PLATIN 10-T101/2/3/4 | 5 | 5 | 5 | Scheduled | 09/02/2026 | 13/02/2026
TO-26-CBA-T131-02 | GENERATOR TRANSFORMER - CLOGHBOOLA 110-CLOGHBOOLA 33-T131 | 3 | 3 | 3 | Scheduled | 10/02/2026 | 12/02/2026
TO-26-DJG-KPG-1-03 | 110kV FEEDER - DROMBEG 110-KILPADDOGE 110-1 | 1 | 1 | 1 | Scheduled | 11/02/2026 | 11/02/2026
TO-26-110 kV A2 @ KRA-03 | BUSBAR SECTION - KNOCKRAHA 110-KNOCKRAHA 110-110A2 | 9 | 7 | 7 | Scheduled | 12/02/2026 | 20/02/2026
TO-26-110 kV B2 @ KRA-03 | BUSBAR SECTION - KNOCKRAHA 110-KNOCKRAHA 110-110B2 | 9 | 7 | 7 | Scheduled | 12/02/2026 | 20/02/2026
TO-26-KRA-WOH-1-05 | 110kV FEEDER - KNOCKRAHA 110-WOODHOUSE 110-1 | 9 | 7 | 7 | Scheduled | 12/02/2026 | 20/02/2026
TO-26-110 kV A2 @ CLG-01 | BUSBAR SECTION - CLOGHRAN 110-CLOGHRAN 110-110A2 | 12 | 10 | 10 | Scheduled | 16/02/2026 | 27/02/2026
TO-26-110 kV B2 @ CLG-01 | BUSBAR SECTION - CLOGHRAN 110-CLOGHRAN 110-110B2 | 12 | 10 | 10 | Scheduled | 16/02/2026 | 27/02/2026
TO-26-CLG-110K2-05 | COUPLER/SECTIONALISING CB - CLOGHRAN 110-CLOGHRAN 110-110K2 | 12 | 10 | 10 | Scheduled | 16/02/2026 | 27/02/2026
TO-26-CLG-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - CLOGHRAN 110-CLOGHRAN 110-110SA1-2CB | 12 | 10 | 10 | Scheduled | 16/02/2026 | 27/02/2026
TO-26-CLG-110SB1-2CB-01 | COUPLER/SECTIONALISING CB - CLOGHRAN 110-CLOGHRAN 110-110SB1-2CB | 12 | 10 | 10 | Scheduled | 16/02/2026 | 27/02/2026
TO-26-CLG-CDU-1-01 | 110kV FEEDER - CLOGHRAN 110-CORDUFF 110-1 | 12 | 10 | 10 | Scheduled | 16/02/2026 | 27/02/2026
TO-26-CDU-FIN-1-01 | 220kV FEEDER - CORDUFF 220-FINGLAS 220-1 | 19 | 15 | 15 | Scheduled | 16/02/2026 | 06/03/2026
TO-26-DSN-T4201-01 | TRANSFORMER - DUNSTOWN 400-DUNSTOWN 220-T4201 | 5 | 5 | 5 | Scheduled | 16/02/2026 | 20/02/2026
TO-26-GLN-PLA-1-01 | 110kV FEEDER - GALLANSTOWN 110-PLATIN 110-1 | 19 | 15 |  | Scheduled | 16/02/2026 | 06/03/2026
TO-26-GAR-PLA-1-02 | 110kV FEEDER - GARBALLAGH 110-PLATIN 110-1 | 71 | 48 | 48 | Scheduled | 16/02/2026 | 27/04/2026
TO-26-PLA-T105-01 | TSO CUSTOMER TRANSFORMER - PLATIN 110-PLATIN 10-T105 | 19 | 15 |  | Scheduled | 16/02/2026 | 06/03/2026
TO-26-RAF-110K1-2-02 | COUPLER/SECTIONALISING CB - RAFFEEN 110-RAFFEEN 110-110K1-2 | 3 | 3 | 3 | Scheduled | 16/02/2026 | 18/02/2026
TO-26-BYH-STATCOM-03 | CAPACITOR/SVC/REACTOR - BALLYNAHULLA 110-BALLYNAHULLA 110-STATCOM | 1 | 1 | 1 | Scheduled | 18/02/2026 | 18/02/2026
TO-26-ROP-T131-01 | GENERATOR TRANSFORMER - ROSSPILE 110-ROSSPILE 33-T131 | 2 | 2 | 2 | Scheduled | 19/02/2026 | 20/02/2026
TO-26-220 kV A2 @ ARK-01 | BUSBAR SECTION - ARKLOW 220-ARKLOW 220-220A2 | 16 | 12 | 12 | Scheduled | 23/02/2026 | 10/03/2026
TO-26-220 kV B2 @ ARK-01 | BUSBAR SECTION - ARKLOW 220-ARKLOW 220-220B2 | 16 | 12 | 12 | Scheduled | 23/02/2026 | 10/03/2026
TO-26-ARK-CKM GIS-1-01 | 220kV FEEDER - ARKLOW 220-CARRICKMINES GIS 220-1 | 16 | 12 | 12 | Scheduled | 23/02/2026 | 10/03/2026
TO-26-BEG-CKM GIS-1-01 | 110kV FEEDER - BALLYBEG 110-CARRICKMINES GIS 110-1 | 16 | 12 | 12 | Scheduled | 23/02/2026 | 10/03/2026
TO-26-220 kV A3 @ CKM GIS-01 | BUSBAR SECTION - CARRICKMINES GIS 220-CARRICKMINES GIS 220-220A3 | 16 | 12 | 12 | Scheduled | 23/02/2026 | 10/03/2026
TO-26-220 kV B3 @ CKM GIS-01 | BUSBAR SECTION - CARRICKMINES GIS 220-CARRICKMINES GIS 220-220B3 | 16 | 12 | 12 | Scheduled | 23/02/2026 | 10/03/2026
TO-26-CKM GIS-220K3-02 | COUPLER/SECTIONALISING CB - CARRICKMINES GIS 220-CARRICKMINES GIS 220-220K3 | 16 | 12 | 12 | Scheduled | 23/02/2026 | 10/03/2026
TO-26-CKM GIS-220SA1-3CB-05 | COUPLER/SECTIONALISING CB - CARRICKMINES GIS 220-CARRICKMINES GIS 220-220SA1-3CB | 16 | 12 | 12 | Scheduled | 23/02/2026 | 10/03/2026
TO-26-CKM GIS-220SB1-3CB-03 | COUPLER/SECTIONALISING CB - CARRICKMINES GIS 220-CARRICKMINES GIS 220-220SB1-3CB | 16 | 12 | 12 | Scheduled | 23/02/2026 | 10/03/2026
TO-26-CTN-TIP-1-01 | 110kV FEEDER - CAUTEEN 110-TIPPERARY 110-1 | 8 | 6 | 6 | Scheduled | 23/02/2026 | 02/03/2026
TO-26-CUL-RTH-1-01 | 110kV FEEDER - CULLENAGH 110-RATHNASKILLOGE 110-1 | 9 | 7 | 7 | Scheduled | 23/02/2026 | 03/03/2026
TO-26-DDK-110SA1-01 | SECTIONALISING DISCONNECT - DUNDALK 110-DUNDALK 110-110SA1 | 6 | 5 |  | Scheduled | 23/02/2026 | 28/02/2026
TO-26-DDK-110SA2-01 | SECTIONALISING DISCONNECT - DUNDALK 110-DUNDALK 110-110SA2 | 6 | 5 | 5 | Scheduled | 23/02/2026 | 28/02/2026
TO-26-DDK-MLN-1-01 | 110kV FEEDER - DUNDALK 110-MULLAGHARLIN 110-1 | 6 | 5 | 5 | Scheduled | 23/02/2026 | 28/02/2026
TO-26-DDK-T141-01 | DISTRIBUTION TRANSFORMER - DUNDALK 110-DUNDALK 38-T141 | 6 | 5 | 5 | Reference | 23/02/2026 | 28/02/2026
TO-26-110 kV A1 @ GOR-05 | BUSBAR SECTION - GORMAN 110-GORMAN 110-110A1 | 40 | 28 | 28 | Scheduled | 23/02/2026 | 03/04/2026
TO-26-110 kV A2 @ GOR-01 | BUSBAR SECTION - GORMAN 110-GORMAN 110-110A2 | 40 | 28 | 28 | Scheduled | 23/02/2026 | 03/04/2026
TO-26-KLS-110K1-2-01 | COUPLER/SECTIONALISING CB - KELLIS 110-KELLIS 110-110K1-2 | 52 | 35 | 35 | Scheduled | 23/02/2026 | 15/04/2026
TO-26-KBY-KRA-1-01 | 110kV FEEDER - KILBARRY 110-KNOCKRAHA 110-1 | 5 | 5 | 5 | Scheduled | 23/02/2026 | 27/02/2026
TO-26-220 kV A2 @ KRA-03 | BUSBAR SECTION - KNOCKRAHA 220-KNOCKRAHA 220-220A2 | 5 | 5 | 5 | Scheduled | 23/02/2026 | 27/02/2026
TO-26-220 kV B2 @ KRA-03 | BUSBAR SECTION - KNOCKRAHA 220-KNOCKRAHA 220-220B2 | 5 | 5 | 5 | Scheduled | 23/02/2026 | 27/02/2026
TO-26-110 kV A1 @ BVK-02 | BUSBAR SECTION - BALLYVOUSKILL 110-BALLYVOUSKILL 110-110A1 | 19 | 14 | 14 | Scheduled | 02/03/2026 | 20/03/2026
TO-26-110 kV B1 @ BVK-01 | BUSBAR SECTION - BALLYVOUSKILL 110-BALLYVOUSKILL 110-110B1 | 19 | 14 | 14 | Scheduled | 02/03/2026 | 20/03/2026
TO-26-BVK-110K1-01 | COUPLER/SECTIONALISING CB - BALLYVOUSKILL 110-BALLYVOUSKILL 110-110K1 | 19 | 14 | 14 | Scheduled | 02/03/2026 | 20/03/2026
TO-26-BVK-110SA1-2CB-06 | COUPLER/SECTIONALISING CB - BALLYVOUSKILL 110-BALLYVOUSKILL 110-110SA1-2CB | 19 | 14 | 14 | Scheduled | 02/03/2026 | 20/03/2026
TO-26-BVK-110SB1-2CB-04 | COUPLER/SECTIONALISING CB - BALLYVOUSKILL 110-BALLYVOUSKILL 110-110SB1-2CB | 19 | 14 | 14 | Scheduled | 02/03/2026 | 20/03/2026
TO-26-220 kV A1 @ BVK-01 | BUSBAR SECTION - BALLYVOUSKILL 220-BALLYVOUSKILL 220-220A1 | 19 | 14 | 14 | Scheduled | 02/03/2026 | 20/03/2026
TO-26-220 kV B1 @ BVK-01 | BUSBAR SECTION - BALLYVOUSKILL 220-BALLYVOUSKILL 220-220B1 | 19 | 14 | 14 | Scheduled | 02/03/2026 | 20/03/2026
TO-26-BVK-220K1-01 | COUPLER/SECTIONALISING CB - BALLYVOUSKILL 220-BALLYVOUSKILL 220-220K1 | 19 | 14 | 14 | Scheduled | 02/03/2026 | 20/03/2026
TO-26-BVK-220SA1-2CB-05 | COUPLER/SECTIONALISING CB - BALLYVOUSKILL 220-BALLYVOUSKILL 220-220SA1-2CB | 19 | 14 | 14 | Scheduled | 02/03/2026 | 20/03/2026
TO-26-BVK-220SB1-2CB-05 | COUPLER/SECTIONALISING CB - BALLYVOUSKILL 220-BALLYVOUSKILL 220-220SB1-2CB | 19 | 14 | 14 | Scheduled | 02/03/2026 | 20/03/2026
TO-26-BVK-T2101-02 | TRANSFORMER - BALLYVOUSKILL 220-BALLYVOUSKILL 110-T2101 | 19 | 14 | 14 | Scheduled | 02/03/2026 | 20/03/2026
TO-26-BAG 110 - CLG 110 - 1-02 | 110kV FEEDER - BARNAGEERAGH 110-CLOGHRAN 110-1 | 12 | 10 | 10 | Scheduled | 02/03/2026 | 13/03/2026
TO-26-BAG-T101-01 | TSO CUSTOMER TRANSFORMER - BARNAGEERAGH 110-BARNAGEERAGH 11-T101 | 5 | 5 | 5 | Scheduled | 02/03/2026 | 06/03/2026
TO-26-CLO-CRD-1-01 | 110kV FEEDER - CLOGHER 110-CROAGHONAGH 110-1 | 2 | 2 | 2 | Scheduled | 02/03/2026 | 03/03/2026
TO-26-110 kV A1 @ CLG-01 | BUSBAR SECTION - CLOGHRAN 110-CLOGHRAN 110-110A1 | 12 | 10 | 10 | Scheduled | 02/03/2026 | 13/03/2026
TO-26-110 kV B1 @ CLG-01 | BUSBAR SECTION - CLOGHRAN 110-CLOGHRAN 110-110B1 | 12 | 10 | 10 | Scheduled | 02/03/2026 | 13/03/2026
TO-26-CLG-110K1-04 | COUPLER/SECTIONALISING CB - CLOGHRAN 110-CLOGHRAN 110-110K1 | 12 | 10 | 10 | Scheduled | 02/03/2026 | 13/03/2026
TO-26-CLG-110SA1-2CB-02 | COUPLER/SECTIONALISING CB - CLOGHRAN 110-CLOGHRAN 110-110SA1-2CB | 12 | 10 | 10 | Scheduled | 02/03/2026 | 13/03/2026
TO-26-CLG-110SB1-2CB-02 | COUPLER/SECTIONALISING CB - CLOGHRAN 110-CLOGHRAN 110-110SB1-2CB | 12 | 10 | 10 | Scheduled | 02/03/2026 | 13/03/2026
TO-26-CRD-T131-01 | GENERATOR TRANSFORMER - CROAGHONAGH 110-CROAGHONAGH 33-T131 | 2 | 2 | 2 | Scheduled | 02/03/2026 | 03/03/2026
TO-26-KLN-T2103-01 | TRANSFORMER - KILLONAN 220-KILLONAN 110-T2103 | 12 | 10 | 10 | Scheduled | 02/03/2026 | 13/03/2026
TO-26-220 kV A1 @ MAY-01 | BUSBAR SECTION - MAYNOOTH 220-MAYNOOTH 220-220A1 | 12 | 10 | 10 | Scheduled | 02/03/2026 | 13/03/2026
TO-26-220 kV B1 @ MAY-01 | BUSBAR SECTION - MAYNOOTH 220-MAYNOOTH 220-220B1 | 12 | 10 | 10 | Scheduled | 02/03/2026 | 13/03/2026
TO-26-MAY-TH-1-01 | 220kV FEEDER - MAYNOOTH 220-TURLOUGH HILL 220-1 | 12 | 10 | 10 | Scheduled | 02/03/2026 | 13/03/2026
TO-26-220 kV A2 @ TH-01 | BUSBAR SECTION - TURLOUGH HILL 220-TURLOUGH HILL 220-220A2 | 12 | 10 | 10 | Scheduled | 02/03/2026 | 13/03/2026
TO-26-220 kV B2 @ TH-01 | BUSBAR SECTION - TURLOUGH HILL 220-TURLOUGH HILL 220-220B2 | 12 | 10 | 10 | Scheduled | 02/03/2026 | 13/03/2026
TO-26-AA GIS-DRU-1-03 | 110kV FEEDER - ARDNACRUSHA GIS 110-DRUMLINE 110-1 | 4 | 4 |  | Scheduled | 03/03/2026 | 06/03/2026
TO-26-AUG-CFM-1-01 | 110kV FEEDER - AUGHINISH 110-CASTLEFARM 110-1 | 3 | 3 |  | Scheduled | 03/03/2026 | 05/03/2026
TO-26-CFM-T101-01 | TSO CUSTOMER TRANSFORMER - CASTLEFARM 110-CASTLEFARM 10-T101 | 3 | 3 | 3 | Reference | 03/03/2026 | 05/03/2026
TO-26-GAR-110K1-01 | COUPLER/SECTIONALISING CB - GARBALLAGH 110-GARBALLAGH 110-110K1 | 1 | 1 | 1 | Scheduled | 03/03/2026 | 03/03/2026
TO-26-KPG-KNR-1-01 | 220kV FEEDER - KILPADDOGE 220-KNOCKANURE 220-1 | 1 | 1 | 1 | Scheduled | 04/03/2026 | 04/03/2026
TO-26-RTH-T133-01 | GENERATOR TRANSFORMER - RATHNASKILLOGE 110-RATHNASKILLOGE 33-T133 | 1 | 1 | 1 | Scheduled | 05/03/2026 | 05/03/2026
TO-26-CKG-T121-02 | TSO CUSTOMER TRANSFORMER - CORKAGH 110-CORKAGH 20-T121 | 7 | 5 | 5 | Scheduled | 08/03/2026 | 14/03/2026
TO-26-TH-T2001/2-02 | GENERATOR TRANSFORMER - TURLOUGH HILL 220-TURLOUGH HILL G1-T2001/2 | 4 | 3 | 3 | Scheduled | 08/03/2026 | 11/03/2026
TO-26-TH-T2003/4-03 | GENERATOR TRANSFORMER - TURLOUGH HILL 220-TURLOUGH HILL G1-T2003/4 | 1 | 0 | 0 | Scheduled | 08/03/2026 | 08/03/2026
TO-26-BAG-T103-01 | TSO CUSTOMER TRANSFORMER - BARNAGEERAGH 110-BARNAGEERAGH 11-T103 | 5 | 5 | 5 | Scheduled | 09/03/2026 | 13/03/2026
TO-26-CBT-INC-2-05 | 220kV FEEDER - CASTLEBAGOT 220-INCHICORE 220-2 | 51 | 34 | 34 | Scheduled | 09/03/2026 | 28/04/2026
TO-26-CLE-WOO-1-02 | 220kV FEEDER - CLONEE 220-WOODLAND 220-1 | 81 | 55 | 55 | Scheduled | 09/03/2026 | 28/05/2026
TO-26-110 kV A1 @ CUL-02 | BUSBAR SECTION - CULLENAGH 110-CULLENAGH 110-110A1 | 5 | 5 | 5 | Scheduled | 09/03/2026 | 13/03/2026
TO-26-110 kV A2 @ CUL-01 | BUSBAR SECTION - CULLENAGH 110-CULLENAGH 110-110A2 | 5 | 5 | 5 | Scheduled | 09/03/2026 | 13/03/2026
TO-26-110 kV B1 @ CUL-02 | BUSBAR SECTION - CULLENAGH 110-CULLENAGH 110-110B1 | 5 | 5 | 5 | Scheduled | 09/03/2026 | 13/03/2026
TO-26-110 kV B2 @ CUL-01 | BUSBAR SECTION - CULLENAGH 110-CULLENAGH 110-110B2 | 5 | 5 | 5 | Scheduled | 09/03/2026 | 13/03/2026
TO-26-CUL-110K1-2-01 | COUPLER/SECTIONALISING CB - CULLENAGH 110-CULLENAGH 110-110K1-2 | 5 | 5 | 5 | Scheduled | 09/03/2026 | 13/03/2026
TO-26-DEN-DRY-1-03 | 110kV FEEDER - DEENES 110-DRYBRIDGE 110-1 | 38 | 25 | 25 | Scheduled | 09/03/2026 | 15/04/2026
TO-26-220 kV A6 @ INC-03 | BUSBAR SECTION - INCHICORE 220-INCHICORE 220-220A6 | 51 | 34 | 34 | Scheduled | 09/03/2026 | 28/04/2026
TO-26-220 kV B6 @ INC-03 | BUSBAR SECTION - INCHICORE 220-INCHICORE 220-220B6 | 51 | 34 | 34 | Scheduled | 09/03/2026 | 28/04/2026
TO-26-KPG-KNR-2-01 | 220kV FEEDER - KILPADDOGE 220-KNOCKANURE 220-2 | 5 | 5 | 5 | Scheduled | 09/03/2026 | 13/03/2026
TO-26-LSA-110K1-02 | COUPLER/SECTIONALISING CB - LISLEA 110-LISLEA 110-110K1 | 1 | 1 | 1 | Scheduled | 09/03/2026 | 09/03/2026
TO-26-TEN-T132-01 | GENERATOR TRANSFORMER - TIMAHOE 110-TIMAHOE 33-T132 | 2 | 2 | 2 | Scheduled | 09/03/2026 | 10/03/2026
TO-26-BLC-DND-1-02 | 110kV FEEDER - BELCAMP 110-DARNDALE 110-1 | 3 | 3 |  | Scheduled | 10/03/2026 | 12/03/2026
TO-26-DSN-T4202-07 | TRANSFORMER - DUNSTOWN 400-DUNSTOWN 220-T4202 | 1 | 1 | 1 | Scheduled | 10/03/2026 | 10/03/2026
TO-26-GOR-NAV-1-02 | 110kV FEEDER - GORMAN 110-NAVAN 110-1 | 1 | 1 | 1 | Scheduled | 10/03/2026 | 10/03/2026
TO-26-TB-110K1-2-01 | COUPLER/SECTIONALISING CB - TARBERT 110-TARBERT 110-110K1-2 | 2 | 2 | 2 | Scheduled | 10/03/2026 | 11/03/2026
TO-26-400 kV B2 @ DSN-05 | BUSBAR SECTION - DUNSTOWN 400-DUNSTOWN 400-400B2 | 1 | 1 | 1 | Scheduled | 11/03/2026 | 11/03/2026
TO-26-LIS-LOU-1-06 | 110kV FEEDER - LISDRUM 110-LOUTH 110-1 | 3 | 3 | 3 | Scheduled | 11/03/2026 | 13/03/2026
TO-26-TH-T2003/4-02 | GENERATOR TRANSFORMER - TURLOUGH HILL 220-TURLOUGH HILL G1-T2003/4 | 2 | 2 | 2 | Scheduled | 12/03/2026 | 13/03/2026
TO-26-ATH-110SA1-2CB-08 | COUPLER/SECTIONALISING CB - ATHLONE 110-ATHLONE 110-110SA1-2CB | 1 | 0 | 0 | Scheduled | 14/03/2026 | 14/03/2026
TO-26-ATH-CAP3-08 | CAPACITOR/SVC/REACTOR - ATHLONE 110-ATHLONE 110-CAP3 | 1 | 0 | 0 | Scheduled | 14/03/2026 | 14/03/2026
TO-26-ATH-LA-1-08 | 110kV FEEDER - ATHLONE 110-LANESBORO 110-1 | 1 | 0 | 0 | Scheduled | 14/03/2026 | 14/03/2026
TO-26-ATH-T141-04 | DISTRIBUTION TRANSFORMER - ATHLONE 110-ATHLONE 38-T141 | 1 | 0 | 0 | Reference | 14/03/2026 | 14/03/2026
TO-26-BDN-CUL-1-05 | 110kV FEEDER - BALLYDINE 110-CULLENAGH 110-1 | 6 | 4 | 4 | Scheduled | 16/03/2026 | 21/03/2026
TO-26-220 kV A2 @ CLE-01 | BUSBAR SECTION - CLONEE 220-CLONEE 220-220A2 | 15 | 10 | 10 | Scheduled | 16/03/2026 | 30/03/2026
TO-26-220 kV B2 @ CLE-01 | BUSBAR SECTION - CLONEE 220-CLONEE 220-220B2 | 15 | 10 | 10 | Scheduled | 16/03/2026 | 30/03/2026
TO-26-CLE-220K2-02 | COUPLER/SECTIONALISING CB - CLONEE 220-CLONEE 220-220K2 | 15 | 10 | 10 | Scheduled | 16/03/2026 | 30/03/2026
TO-26-CLE-220SA1-2CB-02 | COUPLER/SECTIONALISING CB - CLONEE 220-CLONEE 220-220SA1-2CB | 15 | 10 | 10 | Scheduled | 16/03/2026 | 30/03/2026
TO-26-CLE-220SB1-2CB-02 | COUPLER/SECTIONALISING CB - CLONEE 220-CLONEE 220-220SB1-2CB | 15 | 10 | 10 | Scheduled | 16/03/2026 | 30/03/2026
TO-26-220 kV A1 @ CDU-04 | BUSBAR SECTION - CORDUFF 220-CORDUFF 220-220A1 | 4 | 3 | 3 | Scheduled | 16/03/2026 | 19/03/2026
TO-26-220 kV A3 @ CDU-02 | BUSBAR SECTION - CORDUFF 220-CORDUFF 220-220A3 | 4 | 3 | 3 | Scheduled | 16/03/2026 | 19/03/2026
TO-26-CDU-220K1-3-01 | COUPLER/SECTIONALISING CB - CORDUFF 220-CORDUFF 220-220K1-3 | 4 | 3 | 3 | Scheduled | 16/03/2026 | 19/03/2026
TO-26-110 kV B2 @ KPG-02 | BUSBAR SECTION - KILPADDOGE 110-KILPADDOGE 110-110B2 | 12 | 9 | 9 | Scheduled | 16/03/2026 | 27/03/2026
TO-26-110 kV B4 @ KPG-01 | BUSBAR SECTION - KILPADDOGE 110-KILPADDOGE 110-110B4 | 12 | 9 |  | Scheduled | 16/03/2026 | 27/03/2026
TO-26-KPG-110K4-02 | COUPLER/SECTIONALISING CB - KILPADDOGE 110-KILPADDOGE 110-110K4 | 12 | 9 | 9 | Scheduled | 16/03/2026 | 27/03/2026
TO-26-LIM-RAT-1-01 | 110kV FEEDER - LIMERICK 110-RATHKEALE 110-1 | 5 | 4 |  | Scheduled | 16/03/2026 | 20/03/2026
TO-26-110 kV A2 @ RAT-01 | BUSBAR SECTION - RATHKEALE 110-RATHKEALE 110-110A2 | 4 | 3 | 3 | Scheduled | 16/03/2026 | 19/03/2026
TO-26-RAT-110SA1-02 | SECTIONALISING DISCONNECT - RATHKEALE 110-RATHKEALE 110-110SA1 | 4 | 3 | 3 | Scheduled | 16/03/2026 | 19/03/2026
TO-26-RAT-110SA2-01 | SECTIONALISING DISCONNECT - RATHKEALE 110-RATHKEALE 110-110SA2 | 4 | 3 | 3 | Scheduled | 16/03/2026 | 19/03/2026
TO-26-RAT-T142-01 | DISTRIBUTION TRANSFORMER - RATHKEALE 110-RATHKEALE 38-T142 | 4 | 3 | 3 | Reference | 16/03/2026 | 19/03/2026
TO-26-SH-220K1-2-02 | COUPLER/SECTIONALISING CB - SHANNONBRIDGE 220-SHANNONBRIDGE 220-220K1-2 | 24 | 15 | 15 | Scheduled | 16/03/2026 | 08/04/2026
TO-26-CKM GIS-220K3-03 | COUPLER/SECTIONALISING CB - CARRICKMINES GIS 220-CARRICKMINES GIS 220-220K3 | 2 | 2 | 2 | Scheduled | 18/03/2026 | 19/03/2026
TO-26-MID-WHI-1-02 | 110kV FEEDER - MIDLETON 110-WHITEGATE 110-1 | 9 | 7 | 7 | Scheduled | 18/03/2026 | 26/03/2026
TO-26-RYB GIS-T105-01 | TSO CUSTOMER TRANSFORMER - RYEBROOK GIS 110-RYEBROOK 10-T105 | 2 | 2 | 2 | Scheduled | 18/03/2026 | 19/03/2026
TO-26-WHI-110SA1-01 | SECTIONALISING DISCONNECT - WHITEGATE 110-WHITEGATE 110-110SA1 | 9 | 7 | 7 | Scheduled | 18/03/2026 | 26/03/2026
TO-26-WHI-110SA2-01 | SECTIONALISING DISCONNECT - WHITEGATE 110-WHITEGATE 110-110SA2 | 9 | 7 | 7 | Scheduled | 18/03/2026 | 26/03/2026
TO-26-WHI-CKB-T101-01 | TSO CUSTOMER TRANSFORMER - WHITEGATE 110-WHITEGATE 10-CKB-T101 | 9 | 7 | 7 | Scheduled | 18/03/2026 | 26/03/2026
TO-26-BVK-CLA-1-02 | 220kV FEEDER - BALLYVOUSKILL 220-CLASHAVOON 220-1 | 1 | 1 | 1 | Scheduled | 20/03/2026 | 20/03/2026
TO-26-220 kV A1 @ CDU-01 | BUSBAR SECTION - CORDUFF 220-CORDUFF 220-220A1 | 12 | 9 | 9 | Scheduled | 23/03/2026 | 03/04/2026
TO-26-220 kV A2 @ CDU-02 | BUSBAR SECTION - CORDUFF 220-CORDUFF 220-220A2 | 12 | 9 | 9 | Scheduled | 23/03/2026 | 03/04/2026
TO-26-220 kV B1 @ CDU-01 | BUSBAR SECTION - CORDUFF 220-CORDUFF 220-220B1 | 12 | 9 | 9 | Scheduled | 23/03/2026 | 03/04/2026
TO-26-220 kV B2 @ CDU-02 | BUSBAR SECTION - CORDUFF 220-CORDUFF 220-220B2 | 12 | 9 | 9 | Scheduled | 23/03/2026 | 03/04/2026
TO-26-CDU-220K1-2-01 | COUPLER/SECTIONALISING CB - CORDUFF 220-CORDUFF 220-220K1-2 | 12 | 9 | 9 | Scheduled | 23/03/2026 | 03/04/2026
TO-26-CDU-220SA2-4CB-02 | COUPLER/SECTIONALISING CB - CORDUFF 220-CORDUFF 220-220SA2-4CB | 12 | 9 | 9 | Scheduled | 23/03/2026 | 03/04/2026
TO-26-CDU-220SB2-4CB-02 | COUPLER/SECTIONALISING CB - CORDUFF 220-CORDUFF 220-220SB2-4CB | 12 | 9 | 9 | Scheduled | 23/03/2026 | 03/04/2026
TO-26-DJG-KPG-1-05 | 110kV FEEDER - DROMBEG 110-KILPADDOGE 110-1 | 5 | 5 | 5 | Scheduled | 23/03/2026 | 27/03/2026
TO-26-DSN-TH-1-02 | 220kV FEEDER - DUNSTOWN 220-TURLOUGH HILL 220-1 | 5 | 5 | 5 | Scheduled | 23/03/2026 | 27/03/2026
TO-26-GLN-T133-01 | GENERATOR TRANSFORMER - GALLANSTOWN 110-GALLANSTOWN 33-T133 | 2 | 2 | 2 | Scheduled | 23/03/2026 | 24/03/2026
TO-26-GOR-NAV-2-02 | 110kV FEEDER - GORMAN 110-NAVAN 110-2 | 5 | 5 | 5 | Scheduled | 23/03/2026 | 27/03/2026
TO-26-GRI-T141-02 | DISTRIBUTION TRANSFORMER - GRIFFINRATH 110-GRIFFINRATH 38-T141 | 12 | 9 | 9 | Reference | 23/03/2026 | 03/04/2026
TO-26-GRI,T-GRI-1-02 | 110kV FEEDER - GRIFFINRATH tee-GRIFFINRATH 110-1 | 12 | 9 | 9 | Scheduled | 23/03/2026 | 03/04/2026
TO-26-GRI,T-MAY-1-03 | 110kV FEEDER - GRIFFINRATH tee-MAYNOOTH 110-1 | 12 | 9 | 9 | Scheduled | 23/03/2026 | 03/04/2026
TO-26-KPG-RAT-1-02 | 110kV FEEDER - KILPADDOGE 110-RATHKEALE 110-1 | 12 | 9 |  | Scheduled | 23/03/2026 | 03/04/2026
TO-26-KRA-WOH-1-07 | 110kV FEEDER - KNOCKRAHA 110-WOODHOUSE 110-1 | 5 | 5 | 5 | Scheduled | 23/03/2026 | 27/03/2026
TO-26-400 kV A3 @ MP GIS-01 | BUSBAR SECTION - MONEYPOINT GIS 400-MONEYPOINT GIS 400-400A3 | 11 | 9 | 9 | Scheduled | 23/03/2026 | 02/04/2026
TO-26-400 kV B3 @ MP GIS-01 | BUSBAR SECTION - MONEYPOINT GIS 400-MONEYPOINT GIS 400-400B3 | 11 | 9 | 9 | Scheduled | 23/03/2026 | 02/04/2026
TO-26-MP GIS-400K3-04 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 400-MONEYPOINT GIS 400-400K3 | 11 | 9 | 9 | Scheduled | 23/03/2026 | 02/04/2026
TO-26-MP GIS-400SA1-3CB-05 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 400-MONEYPOINT GIS 400-400SA1-3CB | 11 | 9 | 9 | Scheduled | 23/03/2026 | 02/04/2026
TO-26-MP GIS-400SB1-3CB-05 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 400-MONEYPOINT GIS 400-400SB1-3CB | 11 | 9 | 9 | Scheduled | 23/03/2026 | 02/04/2026
TO-26-MP GIS-T4003-01 | GENERATOR TRANSFORMER - MONEYPOINT GIS 400-MONEYPOINT GIS G3-T4003 | 11 | 9 | 9 | Scheduled | 23/03/2026 | 02/04/2026
TO-26-OBE-T123-01 | TSO CUSTOMER TRANSFORMER - OLDBRIDGE 110-OLDBRIDGE 20-T123 | 5 | 5 | 5 | Scheduled | 23/03/2026 | 27/03/2026
TO-26-RAT-110SA1-01 | SECTIONALISING DISCONNECT - RATHKEALE 110-RATHKEALE 110-110SA1 | 5 | 5 | 5 | Scheduled | 23/03/2026 | 27/03/2026
TO-26-RAT-110SA2-02 | SECTIONALISING DISCONNECT - RATHKEALE 110-RATHKEALE 110-110SA2 | 5 | 5 | 5 | Scheduled | 23/03/2026 | 27/03/2026
TO-26-RAT-T141-01 | DISTRIBUTION TRANSFORMER - RATHKEALE 110-RATHKEALE 38-T141 | 5 | 5 | 5 | Reference | 23/03/2026 | 27/03/2026
TO-26-BLC-DND-3-01 | 110kV FEEDER - BELCAMP 110-DARNDALE 110-3 | 3 | 3 | 3 | Scheduled | 24/03/2026 | 26/03/2026
TO-26-CLU-T124-01 | TSO CUSTOMER TRANSFORMER - CLUTTERLAND 110-CLUTTERLAND 20-T124 | 2 | 2 | 2 | Scheduled | 24/03/2026 | 25/03/2026
TO-26-110 kV A1 @ KNR-01 | BUSBAR SECTION - KNOCKANURE 110-KNOCKANURE 110-110A1 | 18 | 12 | 12 | Scheduled | 24/03/2026 | 10/04/2026
TO-26-110 kV B1 @ KNR-01 | BUSBAR SECTION - KNOCKANURE 110-KNOCKANURE 110-110B1 | 18 | 12 | 12 | Scheduled | 24/03/2026 | 10/04/2026
TO-26-KNR-110K1-01 | COUPLER/SECTIONALISING CB - KNOCKANURE 110-KNOCKANURE 110-110K1 | 18 | 12 | 12 | Scheduled | 24/03/2026 | 10/04/2026
TO-26-KNR-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - KNOCKANURE 110-KNOCKANURE 110-110SA1-2CB | 18 | 12 | 12 | Scheduled | 24/03/2026 | 10/04/2026
TO-26-KNR-110SB1-2CB-01 | COUPLER/SECTIONALISING CB - KNOCKANURE 110-KNOCKANURE 110-110SB1-2CB | 18 | 12 | 12 | Scheduled | 24/03/2026 | 10/04/2026
TO-26-220 kV A1 @ KNR-01 | BUSBAR SECTION - KNOCKANURE 220-KNOCKANURE 220-220A1 | 18 | 12 | 12 | Scheduled | 24/03/2026 | 10/04/2026
TO-26-220 kV B1 @ KNR-01 | BUSBAR SECTION - KNOCKANURE 220-KNOCKANURE 220-220B1 | 18 | 12 | 12 | Scheduled | 24/03/2026 | 10/04/2026
TO-26-KNR-220K1-01 | COUPLER/SECTIONALISING CB - KNOCKANURE 220-KNOCKANURE 220-220K1 | 18 | 12 | 12 | Scheduled | 24/03/2026 | 10/04/2026
TO-26-KNR-220SA1-2CB-01 | COUPLER/SECTIONALISING CB - KNOCKANURE 220-KNOCKANURE 220-220SA1-2CB | 18 | 12 | 12 | Scheduled | 24/03/2026 | 10/04/2026
TO-26-KNR-220SB1-2CB-01 | COUPLER/SECTIONALISING CB - KNOCKANURE 220-KNOCKANURE 220-220SB1-2CB | 18 | 12 | 12 | Scheduled | 24/03/2026 | 10/04/2026
TO-26-KNR-T2101-01 | TRANSFORMER - KNOCKANURE 220-KNOCKANURE 110-T2101 | 18 | 12 | 12 | Scheduled | 24/03/2026 | 10/04/2026
TO-26-RYB GIS-T104-01 | TSO CUSTOMER TRANSFORMER - RYEBROOK GIS 110-RYEBROOK 10-T104 | 3 | 3 | 3 | Scheduled | 24/03/2026 | 26/03/2026
TO-26-CLA-CKN-1-01 | 110kV FEEDER - CLASHAVOON 110-CLONKEEN 110-1 | 2 | 2 | 2 | Scheduled | 25/03/2026 | 26/03/2026
TO-26-LYT-T132-02 | GENERATOR TRANSFORMER - LYSAGHTSTOWN 110-LYSAGHTSTOWN 33-T132 | 1 | 1 | 1 | Scheduled | 25/03/2026 | 25/03/2026
TO-26-BAN-RAF-1-02 | 110kV FEEDER - BANDON 110-RAFFEEN 110-1 | 119 | 81 |  | Scheduled | 26/03/2026 | 22/07/2026
TO-26-CKG-T123-02 | TSO CUSTOMER TRANSFORMER - CORKAGH 110-CORKAGH 20-T123 | 8 | 5 | 5 | Scheduled | 27/03/2026 | 03/04/2026
TO-26-BDN-DOO-1-02 | 110kV FEEDER - BALLYDINE 110-DOON 110-1 | 4 | 4 | 4 | Scheduled | 30/03/2026 | 02/04/2026
TO-26-220 kV B1 @ BYH-01 | BUSBAR SECTION - BALLYNAHULLA 220-BALLYNAHULLA 220-220B1 | 4 | 4 | 4 | Scheduled | 30/03/2026 | 02/04/2026
TO-26-220 kV B2 @ BYH-01 | BUSBAR SECTION - BALLYNAHULLA 220-BALLYNAHULLA 220-220B2 | 4 | 4 | 4 | Scheduled | 30/03/2026 | 02/04/2026
TO-26-BYH-220K1-01 | COUPLER/SECTIONALISING CB - BALLYNAHULLA 220-BALLYNAHULLA 220-220K1 | 4 | 4 | 4 | Scheduled | 30/03/2026 | 02/04/2026
TO-26-BYH-220K2-01 | COUPLER/SECTIONALISING CB - BALLYNAHULLA 220-BALLYNAHULLA 220-220K2 | 4 | 4 | 4 | Scheduled | 30/03/2026 | 02/04/2026
TO-26-BYH-220SA1-2CB-01 | COUPLER/SECTIONALISING CB - BALLYNAHULLA 220-BALLYNAHULLA 220-220SA1-2CB | 4 | 4 | 4 | Scheduled | 30/03/2026 | 02/04/2026
TO-26-BYH-220SB1-2CB-01 | COUPLER/SECTIONALISING CB - BALLYNAHULLA 220-BALLYNAHULLA 220-220SB1-2CB | 4 | 4 | 4 | Scheduled | 30/03/2026 | 02/04/2026
TO-26-CHA-MAL-1-01 | 110kV FEEDER - CHARLEVILLE 110-MALLOW 110-1 | 30 | 20 | 20 | Scheduled | 30/03/2026 | 28/04/2026
TO-26-CLA-MAC-1-02 | 110kV FEEDER - CLASHAVOON 110-MACROOM 110-1 | 38 | 25 | 25 | Scheduled | 30/03/2026 | 06/05/2026
TO-26-LSA-SKL-1-02 | 110kV FEEDER - LISLEA 110-SHANKILL 110-1 | 3 | 3 | 3 | Scheduled | 30/03/2026 | 01/04/2026
TO-26-OBE-T121-01 | TSO CUSTOMER TRANSFORMER - OLDBRIDGE 110-OLDBRIDGE 20-T121 | 5 | 4 | 4 | Scheduled | 30/03/2026 | 03/04/2026
TO-26-AD-220K1-01 | COUPLER/SECTIONALISING CB - AGHADA 220-AGHADA 220-220K1 | 1 | 1 | 1 | Scheduled | 31/03/2026 | 31/03/2026
TO-26-CLO-DRM-1-01 | 110kV FEEDER - CLOGHER 110-DRUMKEEN 110-1 | 3 | 3 | 3 | Scheduled | 31/03/2026 | 02/04/2026
TO-26-CKN-KER-1-02 | 110kV FEEDER - CLONKEEN 110-KNOCKEARAGH 110-1 | 3 | 3 | 3 | Scheduled | 31/03/2026 | 02/04/2026
TO-26-FIN GIS-T2101-01 | TRANSFORMER - FINGLAS 220-FINGLAS GIS 110-T2101 | 2 | 2 | 2 | Scheduled | 31/03/2026 | 01/04/2026
TO-26-GOL-T101-01 | GENERATOR TRANSFORMER - GOLAGH 110-GOLAGH 10-T101 | 3 | 3 | 3 | Scheduled | 31/03/2026 | 02/04/2026
TO-26-GOL,T-CLO-1-01 | 110kV FEEDER - GOLAGH tee-CLOGHER 110-1 | 3 | 3 | 3 | Scheduled | 31/03/2026 | 02/04/2026
TO-26-GOL,T-GOL-1-03 | 110kV FEEDER - GOLAGH tee-GOLAGH 110-1 | 3 | 3 | 3 | Scheduled | 31/03/2026 | 02/04/2026
TO-26-GOL,T-LET-1-03 | 110kV FEEDER - GOLAGH tee-LETTERKENNY 110-1 | 3 | 3 | 3 | Scheduled | 31/03/2026 | 02/04/2026
TO-26-KPG-T2102-02 | TRANSFORMER - KILPADDOGE 220-KILPADDOGE 110-T2102 | 1 | 1 | 1 | Scheduled | 31/03/2026 | 31/03/2026
TO-26-AD-SA1-2CB-01 | COUPLER/SECTIONALISING CB - AGHADA 220-AGHADA 220-220SA1-2CB | 2 | 2 | 2 | Scheduled | 01/04/2026 | 02/04/2026
TO-26-FLA-110K1-2-01 | COUPLER/SECTIONALISING CB - FLAGFORD 110-FLAGFORD 110-110K1-2 | 1 | 1 | 1 | Scheduled | 01/04/2026 | 01/04/2026
TO-26-220 kV B2 @ KPG-01 | BUSBAR SECTION - KILPADDOGE 220-KILPADDOGE 220-220B2 | 1 | 1 | 1 | Scheduled | 01/04/2026 | 01/04/2026
TO-26-RYB GIS-T107-01 | TSO CUSTOMER TRANSFORMER - RYEBROOK GIS 110-RYEBROOK 10-T107 | 2 | 2 | 2 | Scheduled | 01/04/2026 | 02/04/2026
TO-26-DEN-T132-02 | GENERATOR TRANSFORMER - DEENES 110-DEENES 33-T132 | 1 | 1 | 1 | Scheduled | 02/04/2026 | 02/04/2026
TO-26-AA GIS-ENN-1-03 | 110kV FEEDER - ARDNACRUSHA GIS 110-ENNIS 110-1 | 11 | 9 | 9 | Scheduled | 07/04/2026 | 17/04/2026
TO-26-ARV-GWE-1-04 | 110kV FEEDER - ARVA 110-GORTAWEE 110-1 | 2 | 2 | 2 | Scheduled | 07/04/2026 | 08/04/2026
TO-26-BVK-110SA1-2CB-03 | COUPLER/SECTIONALISING CB - BALLYVOUSKILL 110-BALLYVOUSKILL 110-110SA1-2CB | 2 | 2 | 2 | Scheduled | 07/04/2026 | 08/04/2026
TO-26-BVK-110SB1-2CB-03 | COUPLER/SECTIONALISING CB - BALLYVOUSKILL 110-BALLYVOUSKILL 110-110SB1-2CB | 2 | 2 | 2 | Scheduled | 07/04/2026 | 08/04/2026
TO-26-220 kV A1 @ BVK-02 | BUSBAR SECTION - BALLYVOUSKILL 220-BALLYVOUSKILL 220-220A1 | 4 | 4 | 4 | Scheduled | 07/04/2026 | 10/04/2026
TO-26-BVK-220K1-02 | COUPLER/SECTIONALISING CB - BALLYVOUSKILL 220-BALLYVOUSKILL 220-220K1 | 4 | 4 | 4 | Scheduled | 07/04/2026 | 10/04/2026
TO-26-BVK-T2101-03 | TRANSFORMER - BALLYVOUSKILL 220-BALLYVOUSKILL 110-T2101 | 4 | 4 | 4 | Scheduled | 07/04/2026 | 10/04/2026
TO-26-CAH-DOO-1-01 | 110kV FEEDER - CAHIR 110-DOON 110-1 | 58 | 40 | 40 | Scheduled | 07/04/2026 | 03/06/2026
TO-26-220 kV A2 @ FIN-07 | BUSBAR SECTION - FINGLAS 220-FINGLAS 220-220A2 | 18 | 14 | 14 | Scheduled | 07/04/2026 | 24/04/2026
TO-26-220 kV B2 @ FIN-05 | BUSBAR SECTION - FINGLAS 220-FINGLAS 220-220B2 | 18 | 14 | 14 | Scheduled | 07/04/2026 | 24/04/2026
TO-26-FIN-220K2-10 | COUPLER/SECTIONALISING CB - FINGLAS 220-FINGLAS 220-220K2 | 18 | 14 | 14 | Scheduled | 07/04/2026 | 24/04/2026
TO-26-FIN-220SA1-2CB-13 | COUPLER/SECTIONALISING CB - FINGLAS 220-FINGLAS 220-220SA1-2CB | 18 | 14 | 14 | Scheduled | 07/04/2026 | 24/04/2026
TO-26-FIN-220SB1-2CB-10 | COUPLER/SECTIONALISING CB - FINGLAS 220-FINGLAS 220-220SB1-2CB | 18 | 14 | 14 | Scheduled | 07/04/2026 | 24/04/2026
TO-26-110 kV A3 @ FIN GIS-01 | BUSBAR SECTION - FINGLAS GIS 110-FINGLAS GIS 110-110A3 | 18 | 14 | 14 | Scheduled | 07/04/2026 | 24/04/2026
TO-26-110 kV B3 @ FIN GIS-01 | BUSBAR SECTION - FINGLAS GIS 110-FINGLAS GIS 110-110B3 | 18 | 14 | 14 | Scheduled | 07/04/2026 | 24/04/2026
TO-26-FIN GIS-110SA1-3CB-02 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110SA1-3CB | 18 | 14 | 14 | Scheduled | 07/04/2026 | 24/04/2026
TO-26-FIN GIS-110SA3-5CB-03 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110SA3-5CB | 18 | 14 | 14 | Scheduled | 07/04/2026 | 24/04/2026
TO-26-FIN GIS-110SB1-3CB-01 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110SB1-3CB | 18 | 14 | 14 | Scheduled | 07/04/2026 | 24/04/2026
TO-26-FIN GIS-110SB3-5CB-03 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110SB3-5CB | 18 | 14 | 14 | Scheduled | 07/04/2026 | 24/04/2026
TO-26-FIN GIS-T2106-01 | TRANSFORMER - FINGLAS 220-FINGLAS GIS 110-T2106 | 18 | 14 | 14 | Scheduled | 07/04/2026 | 24/04/2026
TO-26-KPG-KNR-1-110-01 | 110kV FEEDER - KILPADDOGE 110-KNOCKANURE 110-1-110 | 11 | 9 | 9 | Scheduled | 07/04/2026 | 17/04/2026
TO-26-RYB GIS-T108-01 | TSO CUSTOMER TRANSFORMER - RYEBROOK GIS 110-RYEBROOK 10-T108 | 11 | 9 | 9 | Scheduled | 07/04/2026 | 17/04/2026
TO-26-TAW-T1/T2-01 | GENERATOR TRANSFORMER - TAWNAGHMORE 110-TAWNAGHMORE 10-T1/T2 | 163 | 114 | 114 | Scheduled | 07/04/2026 | 16/09/2026
TO-26-TAW-T3-02 | GENERATOR TRANSFORMER - TAWNAGHMORE 110-TAWNAGHMORE 10-T3 | 163 | 114 | 114 | Scheduled | 07/04/2026 | 16/09/2026
TO-26-DND-T121-03 | TSO CUSTOMER TRANSFORMER - DARNDALE 110-DARNDALE 20-T121 | 2 | 2 | 2 | Scheduled | 08/04/2026 | 09/04/2026
TO-26-KLN-KRA-1-06 | 220kV FEEDER - KILLONAN 220-KNOCKRAHA 220-1 | 10 | 8 | 8 | Scheduled | 08/04/2026 | 17/04/2026
TO-26-220 kV A1 @ KRA-03 | BUSBAR SECTION - KNOCKRAHA 220-KNOCKRAHA 220-220A1 | 10 | 8 | 8 | Scheduled | 08/04/2026 | 17/04/2026
TO-26-220 kV B1 @ KRA-03 | BUSBAR SECTION - KNOCKRAHA 220-KNOCKRAHA 220-220B1 | 10 | 8 | 8 | Scheduled | 08/04/2026 | 17/04/2026
TO-26-KRA-220K1-06 | COUPLER/SECTIONALISING CB - KNOCKRAHA 220-KNOCKRAHA 220-220K1 | 10 | 8 | 8 | Scheduled | 08/04/2026 | 17/04/2026
TO-26-KRA-220SA1-2CB-06 | COUPLER/SECTIONALISING CB - KNOCKRAHA 220-KNOCKRAHA 220-220SA1-2CB | 10 | 8 | 8 | Scheduled | 08/04/2026 | 17/04/2026
TO-26-KRA-220SB1-2CB-06 | COUPLER/SECTIONALISING CB - KNOCKRAHA 220-KNOCKRAHA 220-220SB1-2CB | 10 | 8 | 8 | Scheduled | 08/04/2026 | 17/04/2026
TO-26-FLA-LOU-1-06 | 220kV FEEDER - FLAGFORD 220-LOUTH 220-1 | 51 | 36 | 36 | Scheduled | 09/04/2026 | 29/05/2026
TO-26-220 kV A2 @ LOU-06 | BUSBAR SECTION - LOUTH 220-LOUTH 220-220A2 | 9 | 7 | 7 | Scheduled | 09/04/2026 | 17/04/2026
TO-26-220 kV B2 @ LOU-06 | BUSBAR SECTION - LOUTH 220-LOUTH 220-220B2 | 9 | 7 | 7 | Scheduled | 09/04/2026 | 17/04/2026
TO-26-AD-LPT-1-01 | 220kV FEEDER - AGHADA 220-LONG POINT 220-1 | 27 | 18 | 18 | Scheduled | 10/04/2026 | 06/05/2026
TO-26-LPT-T2002-01 | GENERATOR TRANSFORMER - LONG POINT 220-LONG POINT G1-T2002 | 27 | 18 | 18 | Scheduled | 10/04/2026 | 06/05/2026
TO-26-CLE-T224-01 | TSO CUSTOMER TRANSFORMER - CLONEE 220-CLONEE 20-T224 | 47 | 34 |  | Scheduled | 13/04/2026 | 29/05/2026
TO-26-CLE-T224-02 | TSO CUSTOMER TRANSFORMER - CLONEE 220-CLONEE 20-T224 | 5 | 5 | 5 | Scheduled | 13/04/2026 | 17/04/2026
TO-26-110 kV A1 @ DND-02 | BUSBAR SECTION - DARNDALE 110-DARNDALE 110-110A1 | 5 | 5 | 5 | Proposed | 13/04/2026 | 17/04/2026
TO-26-110 kV B1 @ DND-01 | BUSBAR SECTION - DARNDALE 110-DARNDALE 110-110B1 | 5 | 5 | 5 | Proposed | 13/04/2026 | 17/04/2026
TO-26-DND-110K1-06 | COUPLER/SECTIONALISING CB - DARNDALE 110-DARNDALE 110-110K1 | 5 | 5 | 5 | Proposed | 13/04/2026 | 17/04/2026
TO-26-DND-110SA1-2CB-07 | COUPLER/SECTIONALISING CB - DARNDALE 110-DARNDALE 110-110SA1-2CB | 5 | 5 | 5 | Proposed | 13/04/2026 | 17/04/2026
TO-26-DND-110SB1-2CB-06 | COUPLER/SECTIONALISING CB - DARNDALE 110-DARNDALE 110-110SB1-2CB | 5 | 5 | 5 | Proposed | 13/04/2026 | 17/04/2026
TO-26-DND-T123-01 | TSO CUSTOMER TRANSFORMER - DARNDALE 110-DARNDALE 20-T123 | 5 | 5 | 5 | Proposed | 13/04/2026 | 17/04/2026
TO-26-LSA-T131-02 | GENERATOR TRANSFORMER - LISLEA 110-LISLEA 33-T131 | 4 | 4 | 4 | Scheduled | 13/04/2026 | 16/04/2026
TO-26-RRU-T122-01 | GENERATOR TRANSFORMER - RATRUSSAN 110-RATRUSSAN 20-T122 | 5 | 5 | 5 | Scheduled | 13/04/2026 | 17/04/2026
TO-26-CBT-T2101-01 | TRANSFORMER - CASTLEBAGOT 220-CASTLEBAGOT 110-T2101 | 2 | 2 | 2 | Scheduled | 14/04/2026 | 15/04/2026
TO-26-DDK-MLN-1-02 | 110kV FEEDER - DUNDALK 110-MULLAGHARLIN 110-1 | 2 | 2 | 2 | Scheduled | 14/04/2026 | 15/04/2026
TO-26-GOR-T122-01 | GENERATOR TRANSFORMER - GORMAN 110-GORMAN 20-T122 | 2 | 2 | 2 | Scheduled | 14/04/2026 | 15/04/2026
TO-26-PRN-T4301-03 | TRANSFORMER - PORTAN 400-PORTAN 260-T4301 | 14 | 10 | 10 | Scheduled | 14/04/2026 | 27/04/2026
TO-26-PRN-WOO-1-03 | 400kV FEEDER - PORTAN 400-WOODLAND 400-1 | 14 | 10 | 10 | Scheduled | 14/04/2026 | 27/04/2026
TO-26-400 kV A1 @ WOO-04 | BUSBAR SECTION - WOODLAND 400-WOODLAND 400-400A1 | 18 | 14 | 14 | Scheduled | 14/04/2026 | 01/05/2026
TO-26-400 kV A1 @ WOO-03 | BUSBAR SECTION - WOODLAND 400-WOODLAND 400-400A1 | 5 | 4 | 4 | Proposed | 14/04/2026 | 18/04/2026
TO-26-400 kV B1 @ WOO-03 | BUSBAR SECTION - WOODLAND 400-WOODLAND 400-400B1 | 5 | 4 | 4 | Proposed | 14/04/2026 | 18/04/2026
TO-26-400 kV B1 @ WOO-04 | BUSBAR SECTION - WOODLAND 400-WOODLAND 400-400B1 | 18 | 14 | 14 | Scheduled | 14/04/2026 | 01/05/2026
TO-26-WOO-T4201-02 | TRANSFORMER - WOODLAND 400-WOODLAND 220-T4201 | 18 | 14 | 14 | Scheduled | 14/04/2026 | 01/05/2026
TO-26-AD-RAF-1-03 | 220kV FEEDER - AGHADA 220-RAFFEEN 220-1 | 19 | 14 | 14 | Scheduled | 20/04/2026 | 08/05/2026
TO-26-AA GIS-T102-01 | GENERATOR TRANSFORMER - ARDNACRUSHA GIS 110-ARDNACRUSHA GIS G2-T102 | 11 | 9 | 9 | Scheduled | 20/04/2026 | 30/04/2026
TO-26-AA GIS-T103-02 | GENERATOR TRANSFORMER - ARDNACRUSHA GIS 110-ARDNACRUSHA GIS G3-T103 | 152 | 107 | 107 | Scheduled | 20/04/2026 | 18/09/2026
TO-26-BVK-220SB1-2CB-03 | COUPLER/SECTIONALISING CB - BALLYVOUSKILL 220-BALLYVOUSKILL 220-220SB1-2CB | 3 | 3 | 3 | Scheduled | 20/04/2026 | 22/04/2026
TO-26-CBT-CLU-1-02 | 110kV FEEDER - CASTLEBAGOT 110-CLUTTERLAND 110-1 | 2 | 2 | 2 | Scheduled | 20/04/2026 | 21/04/2026
TO-26-CDK-LWD-1-01 | 110kV FEEDER - CASTLEDOCKRELL 110-LODGEWOOD 110-1 | 5 | 5 | 5 | Scheduled | 20/04/2026 | 24/04/2026
TO-26-CDK-T121-02 | GENERATOR TRANSFORMER - CASTLEDOCKRELL 110-CASTLEDOCKRELL 20-T121 | 5 | 5 | 5 | Reference | 20/04/2026 | 24/04/2026
TO-26-DDK-LOU-1-01 | 110kV FEEDER - DUNDALK 110-LOUTH 110-1 | 115 | 80 |  | Scheduled | 20/04/2026 | 12/08/2026
TO-26-IA-T101-01 | GENERATOR TRANSFORMER - INNISCARRA 110-INNISCARRA G1-T101 | 12 | 10 | 10 | Scheduled | 20/04/2026 | 01/05/2026
TO-26-KRA-RAF-1-06 | 220kV FEEDER - KNOCKRAHA 220-RAFFEEN 220-1 | 12 | 10 | 10 | Scheduled | 20/04/2026 | 01/05/2026
TO-26-LWD-T2102-01 | TRANSFORMER - LODGEWOOD 220-LODGEWOOD 110-T2102 | 5 | 5 | 5 | Scheduled | 20/04/2026 | 24/04/2026
TO-26-110 kV A2 @ LOU-09 | BUSBAR SECTION - LOUTH 110-LOUTH 110-110A2 | 4 | 4 | 4 | Scheduled | 20/04/2026 | 23/04/2026
TO-26-110 kV B2 @ LOU-09 | BUSBAR SECTION - LOUTH 110-LOUTH 110-110B2 | 4 | 4 | 4 | Scheduled | 20/04/2026 | 23/04/2026
TO-26-PRO-TB-1-03 | 220kV FEEDER - PROSPECT 220-TARBERT 220-1 | 12 | 10 |  | Scheduled | 20/04/2026 | 01/05/2026
TO-26-CBT-T2102-02 | TRANSFORMER - CASTLEBAGOT 220-CASTLEBAGOT 110-T2102 | 2 | 2 | 2 | Scheduled | 21/04/2026 | 22/04/2026
TO-26-110 kV A1 @ CDU-02 | BUSBAR SECTION - CORDUFF 110-CORDUFF 110-110A1 | 37 | 26 | 26 | Scheduled | 21/04/2026 | 27/05/2026
TO-26-110 kV B1 @ CDU-02 | BUSBAR SECTION - CORDUFF 110-CORDUFF 110-110B1 | 37 | 26 | 26 | Scheduled | 21/04/2026 | 27/05/2026
TO-26-220 kV A1 @ CDU-05 | BUSBAR SECTION - CORDUFF 220-CORDUFF 220-220A1 | 37 | 26 | 26 | Scheduled | 21/04/2026 | 27/05/2026
TO-26-220 kV B1 @ CDU-02 | BUSBAR SECTION - CORDUFF 220-CORDUFF 220-220B1 | 37 | 26 | 26 | Scheduled | 21/04/2026 | 27/05/2026
TO-26-CDU-T2101-01 | TRANSFORMER - CORDUFF 220-CORDUFF 110-T2101 | 37 | 26 | 26 | Scheduled | 21/04/2026 | 27/05/2026
TO-26-KTL-CAP1-01 | CAPACITOR/SVC/REACTOR - KILTEEL 110-KILTEEL 110-CAP1 | 3 | 3 | 3 | Scheduled | 21/04/2026 | 23/04/2026
TO-26-RYB GIS-T106-01 | TSO CUSTOMER TRANSFORMER - RYEBROOK GIS 110-RYEBROOK 10-T106 | 3 | 3 | 3 | Scheduled | 21/04/2026 | 23/04/2026
TO-26-AA GIS-110K3-02 | COUPLER/SECTIONALISING CB - ARDNACRUSHA GIS 110-ARDNACRUSHA GIS 110-110K3 | 2 | 2 | 2 | Scheduled | 22/04/2026 | 23/04/2026
TO-26-GOR-MTH-1-03 | 110kV FEEDER - GORMAN 110-MEATH HILL 110-1 | 15 | 10 | 10 | Scheduled | 22/04/2026 | 06/05/2026
TO-26-TTU-110K1-02 | COUPLER/SECTIONALISING CB - TULLABEG 110-TULLABEG 110-110K1 | 1 | 1 | 1 | Scheduled | 22/04/2026 | 22/04/2026
TO-26-AA GIS-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - ARDNACRUSHA GIS 110-ARDNACRUSHA GIS 110-110SA1-2CB | 2 | 2 | 2 | Scheduled | 23/04/2026 | 24/04/2026
TO-26-PRN-T4301-05 | TRANSFORMER - PORTAN 400-PORTAN 260-T4301 | 1 | 1 | 1 | Scheduled | 23/04/2026 | 23/04/2026
TO-26-SHL-T2016-02 | GENERATOR TRANSFORMER - SHELLYBANKS 220-SHELLYBANKS G6-T2016 | 7 | 5 | 5 | Scheduled | 23/04/2026 | 29/04/2026
TO-26-ATY-110SA1-03 | SECTIONALISING DISCONNECT - ATHY 110-ATHY 110-110SA1 | 15 | 10 | 10 | Scheduled | 24/04/2026 | 08/05/2026
TO-26-ATY-110SA2-03 | SECTIONALISING DISCONNECT - ATHY 110-ATHY 110-110SA2 | 15 | 10 | 10 | Scheduled | 24/04/2026 | 08/05/2026
TO-26-ATY-CLW-1-05 | 110kV FEEDER - ATHY 110-CARLOW 110-1 | 15 | 10 | 10 | Scheduled | 24/04/2026 | 08/05/2026
TO-26-110 kV A2 @ DND-02 | BUSBAR SECTION - DARNDALE 110-DARNDALE 110-110A2 | 5 | 5 | 5 | Scheduled | 27/04/2026 | 01/05/2026
TO-26-110 kV B2 @ DND-02 | BUSBAR SECTION - DARNDALE 110-DARNDALE 110-110B2 | 5 | 5 | 5 | Scheduled | 27/04/2026 | 01/05/2026
TO-26-DND-110K2-04 | COUPLER/SECTIONALISING CB - DARNDALE 110-DARNDALE 110-110K2 | 5 | 5 | 5 | Scheduled | 27/04/2026 | 01/05/2026
TO-26-DND-110SA1-2CB-08 | COUPLER/SECTIONALISING CB - DARNDALE 110-DARNDALE 110-110SA1-2CB | 5 | 5 | 5 | Scheduled | 27/04/2026 | 01/05/2026
TO-26-DND-110SB1-2CB-07 | COUPLER/SECTIONALISING CB - DARNDALE 110-DARNDALE 110-110SB1-2CB | 5 | 5 | 5 | Scheduled | 27/04/2026 | 01/05/2026
TO-26-DND-T122-01 | TSO CUSTOMER TRANSFORMER - DARNDALE 110-DARNDALE 20-T122 | 5 | 5 | 5 | Scheduled | 27/04/2026 | 01/05/2026
TO-26-DER-TSB-1-04 | 110kV FEEDER - DERRYIRON 110-THORNSBERRY 110-1 | 56 | 38 | 38 | Scheduled | 27/04/2026 | 21/06/2026
TO-26-KDN-T131-01 | GENERATOR TRANSFORMER - KNOCKDRIN 110-KNOCKDRIN 33-T131 | 4 | 4 | 4 | Scheduled | 27/04/2026 | 30/04/2026
TO-26-MP GIS-220K1-01 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 220-MONEYPOINT GIS 220-220K1 | 10 | 7 | 7 | Scheduled | 27/04/2026 | 06/05/2026
TO-26-MP GIS-220K2-01 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 220-MONEYPOINT GIS 220-220K2 | 10 | 7 | 7 | Scheduled | 27/04/2026 | 06/05/2026
TO-26-MP GIS-220SA1-2CB-01 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 220-MONEYPOINT GIS 220-220SA1-2CB | 10 | 7 | 7 | Scheduled | 27/04/2026 | 06/05/2026
TO-26-MP GIS-220SB1-2CB-01 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 220-MONEYPOINT GIS 220-220SB1-2CB | 10 | 7 | 7 | Scheduled | 27/04/2026 | 06/05/2026
TO-26-WOH-T122-01 | GENERATOR TRANSFORMER - WOODHOUSE 110-WOODHOUSE 20-T122 | 5 | 5 | 5 | Scheduled | 27/04/2026 | 01/05/2026
TO-26-CDU-RYB GIS-1-02 | 110kV FEEDER - CORDUFF 110-RYEBROOK GIS 110-1 | 1 | 1 | 1 | Scheduled | 28/04/2026 | 28/04/2026
TO-26-KPG-220K4-01 | COUPLER/SECTIONALISING CB - KILPADDOGE 220-KILPADDOGE 220-220K4 | 3 | 3 | 3 | Scheduled | 28/04/2026 | 30/04/2026
TO-26-KPG-220SA2-4CB-01 | COUPLER/SECTIONALISING CB - KILPADDOGE 220-KILPADDOGE 220-220SA2-4CB | 3 | 3 | 3 | Scheduled | 28/04/2026 | 30/04/2026
TO-26-KPG-220SB2-4CB-01 | COUPLER/SECTIONALISING CB - KILPADDOGE 220-KILPADDOGE 220-220SB2-4CB | 3 | 3 | 3 | Scheduled | 28/04/2026 | 30/04/2026
TO-26-220 kV A4 @ INC-03 | BUSBAR SECTION - INCHICORE 220-INCHICORE 220-220A4 | 58 | 40 | 40 | Scheduled | 29/04/2026 | 25/06/2026
TO-26-220 kV A6 @ INC-04 | BUSBAR SECTION - INCHICORE 220-INCHICORE 220-220A6 | 15 | 10 | 10 | Scheduled | 29/04/2026 | 13/05/2026
TO-26-220 kV B4 @ INC-03 | BUSBAR SECTION - INCHICORE 220-INCHICORE 220-220B4 | 58 | 40 | 40 | Scheduled | 29/04/2026 | 25/06/2026
TO-26-220 kV B6 @ INC-04 | BUSBAR SECTION - INCHICORE 220-INCHICORE 220-220B6 | 15 | 10 | 10 | Scheduled | 29/04/2026 | 13/05/2026
TO-26-INC-220K4-6-03 | COUPLER/SECTIONALISING CB - INCHICORE 220-INCHICORE 220-220K4-6 | 58 | 40 | 40 | Scheduled | 29/04/2026 | 25/06/2026
TO-26-INC-T2106-02 | TRANSFORMER - INCHICORE 220-INCHICORE 110-T2106 | 58 | 40 |  | Reference | 29/04/2026 | 25/06/2026
TO-26-LYT-T132-03 | GENERATOR TRANSFORMER - LYSAGHTSTOWN 110-LYSAGHTSTOWN 33-T132 | 1 | 1 | 1 | Scheduled | 29/04/2026 | 29/04/2026
TO-26-SHL-D1/CB1-04 | COUPLER/SECTIONALISING CB - SHELLYBANKS 220-SHELLYBANKS 220-D1/CB1 | 8 | 5 | 5 | Scheduled | 30/04/2026 | 07/05/2026
TO-26-SHL-D1/CB2-04 | COUPLER/SECTIONALISING CB - SHELLYBANKS 220-SHELLYBANKS 220-D1/CB2 | 1 | 1 | 1 | Scheduled | 30/04/2026 | 30/04/2026
TO-26-SHL-D1/CB3-02 | COUPLER/SECTIONALISING CB - SHELLYBANKS 220-SHELLYBANKS 220-D1/CB3 | 1 | 1 | 1 | Scheduled | 30/04/2026 | 30/04/2026
TO-26-SHL-D2/CB1-03 | COUPLER/SECTIONALISING CB - SHELLYBANKS 220-SHELLYBANKS 220-D2/CB1 | 8 | 5 | 5 | Scheduled | 30/04/2026 | 07/05/2026
TO-26-SHL-T2014-03 | GENERATOR TRANSFORMER - SHELLYBANKS 220-SHELLYBANKS G4-T2014 | 9 | 6 | 6 | Scheduled | 30/04/2026 | 08/05/2026
TO-26-SHL-T2016-01 | GENERATOR TRANSFORMER - SHELLYBANKS 220-SHELLYBANKS G6-T2016 | 8 | 5 | 5 | Scheduled | 30/04/2026 | 07/05/2026
TO-26-BLK-T142-01 | DISTRIBUTION TRANSFORMER - BLAKE 110-BLAKE 38-T142 | 3 | 1 | 1 | Reference | 01/05/2026 | 03/05/2026
TO-26-BLK,T-BLK-1-03 | 110kV FEEDER - BLAKE tee-BLAKE 110-1 | 3 | 1 | 1 | Scheduled | 01/05/2026 | 03/05/2026
TO-26-BLK,T-MAY-1-03 | 110kV FEEDER - BLAKE tee-MAYNOOTH 110-1 | 3 | 1 | 1 | Scheduled | 01/05/2026 | 03/05/2026
TO-26-BLK,T-MAY-1-03 | 110kV FEEDER - BLAKE tee-MAYNOOTH 110-1 | Unknown | Unknown | 1 | Planned | May | May
TO-26-BLK,T-NEW-1-04 | 110kV FEEDER - BLAKE tee-NEWBRIDGE 110-1 | 3 | 1 | 1 | Scheduled | 01/05/2026 | 03/05/2026
TO-26-MP GIS-T4002-02 | GENERATOR TRANSFORMER - MONEYPOINT GIS 400-MONEYPOINT GIS G2-T4002 | 89 | 61 | 61 | Scheduled | 01/05/2026 | 28/07/2026
TO-26-CLH-T122-01 | GENERATOR TRANSFORMER - CLAHANE 110-CLAHANE 20-T122 | 4 | 4 | 4 | Scheduled | 05/05/2026 | 08/05/2026
TO-26-DRM-LET-1-01 | 110kV FEEDER - DRUMKEEN 110-LETTERKENNY 110-1 | 17 | 13 | 13 | Scheduled | 05/05/2026 | 21/05/2026
TO-26-220 kV A1 @ MP GIS-01 | BUSBAR SECTION - MONEYPOINT GIS 220-MONEYPOINT GIS 220-220A1 | 14 | 10 | 10 | Scheduled | 05/05/2026 | 18/05/2026
TO-26-220 kV B1 @ MP GIS-01 | BUSBAR SECTION - MONEYPOINT GIS 220-MONEYPOINT GIS 220-220B1 | 14 | 10 | 10 | Scheduled | 05/05/2026 | 18/05/2026
TO-26-MP GIS-220K1-05 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 220-MONEYPOINT GIS 220-220K1 | 14 | 10 | 10 | Scheduled | 05/05/2026 | 18/05/2026
TO-26-MP GIS-220SA1-2CB-03 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 220-MONEYPOINT GIS 220-220SA1-2CB | 14 | 10 | 10 | Scheduled | 05/05/2026 | 18/05/2026
TO-26-MP GIS-220SB1-2CB-02 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 220-MONEYPOINT GIS 220-220SB1-2CB | 14 | 10 | 10 | Scheduled | 05/05/2026 | 18/05/2026
TO-26-400 kV A1 @ MP GIS-02 | BUSBAR SECTION - MONEYPOINT GIS 400-MONEYPOINT GIS 400-400A1 | 14 | 10 | 10 | Scheduled | 05/05/2026 | 18/05/2026
TO-26-400 kV B1 @ MP GIS-02 | BUSBAR SECTION - MONEYPOINT GIS 400-MONEYPOINT GIS 400-400B1 | 14 | 10 | 10 | Scheduled | 05/05/2026 | 18/05/2026
TO-26-MP GIS-400SA1-2CB-03 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 400-MONEYPOINT GIS 400-400SA1-2CB | 14 | 10 | 10 | Scheduled | 05/05/2026 | 18/05/2026
TO-26-MP GIS-400SA1-3CB-06 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 400-MONEYPOINT GIS 400-400SA1-3CB | 14 | 10 | 10 | Scheduled | 05/05/2026 | 18/05/2026
TO-26-MP GIS-400SB1-2CB-03 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 400-MONEYPOINT GIS 400-400SB1-2CB | 14 | 10 | 10 | Scheduled | 05/05/2026 | 18/05/2026
TO-26-MP GIS-400SB1-3CB-06 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 400-MONEYPOINT GIS 400-400SB1-3CB | 14 | 10 | 10 | Scheduled | 05/05/2026 | 18/05/2026
TO-26-RAF-TBG-2-03 | 110kV FEEDER - RAFFEEN 110-TRABEG 110-2 | 25 | 19 |  | Scheduled | 05/05/2026 | 29/05/2026
TO-26-RYB GIS-T109-01 | TSO CUSTOMER TRANSFORMER - RYEBROOK GIS 110-RYEBROOK 10-T109 | 11 | 9 | 9 | Scheduled | 05/05/2026 | 15/05/2026
TO-26-THU-STATCOM-02 | CAPACITOR/SVC/REACTOR - THURLES 110-THURLES 110-STATCOM | 4 | 4 | 4 | Scheduled | 05/05/2026 | 08/05/2026
TO-26-110 kV A1 @ TBG-01 | BUSBAR SECTION - TRABEG 110-TRABEG 110-110A1 | 14 | 10 | 10 | Scheduled | 05/05/2026 | 18/05/2026
TO-26-110 kV B1 @ TBG-01 | BUSBAR SECTION - TRABEG 110-TRABEG 110-110B1 | 14 | 10 | 10 | Scheduled | 05/05/2026 | 18/05/2026
TO-26-AUG-MTN-1-01 | 110kV FEEDER - AUGHINISH 110-MONETEEN 110-1 | 2 | 2 | 2 | Scheduled | 06/05/2026 | 07/05/2026
TO-26-BEG-T101-01 | DISTRIBUTION TRANSFORMER - BALLYBEG 110-BALLYBEG 10-T101 | 2 | 2 | 2 | Reference | 06/05/2026 | 07/05/2026
TO-26-CNO-T131-01 | GENERATOR TRANSFORMER - COOLNANOONAGH 110-COOLNANOONAGH 33-T131 | 2 | 2 | 2 | Scheduled | 06/05/2026 | 07/05/2026
TO-26-110 kV A1 @ SNU-01 | BUSBAR SECTION - SNUGBOROUGH 110-SNUGBOROUGH 110-110A1 | 13 | 9 | 9 | Scheduled | 06/05/2026 | 18/05/2026
TO-26-110 kV A2 @ SNU-01 | BUSBAR SECTION - SNUGBOROUGH 110-SNUGBOROUGH 110-110A2 | 13 | 9 | 9 | Scheduled | 06/05/2026 | 18/05/2026
TO-26-110 kV B1 @ SNU-01 | BUSBAR SECTION - SNUGBOROUGH 110-SNUGBOROUGH 110-110B1 | 13 | 9 | 9 | Scheduled | 06/05/2026 | 18/05/2026
TO-26-110 kV B2 @ SNU-01 | BUSBAR SECTION - SNUGBOROUGH 110-SNUGBOROUGH 110-110B2 | 13 | 9 | 9 | Scheduled | 06/05/2026 | 18/05/2026
TO-26-SNU-110K1-01 | COUPLER/SECTIONALISING CB - SNUGBOROUGH 110-SNUGBOROUGH 110-110K1 | 13 | 9 | 9 | Scheduled | 06/05/2026 | 18/05/2026
TO-26-SNU-110K2-01 | COUPLER/SECTIONALISING CB - SNUGBOROUGH 110-SNUGBOROUGH 110-110K2 | 13 | 9 | 9 | Scheduled | 06/05/2026 | 18/05/2026
TO-26-SNU-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - SNUGBOROUGH 110-SNUGBOROUGH 110-110SA1-2CB | 13 | 9 | 9 | Scheduled | 06/05/2026 | 18/05/2026
TO-26-SNU-110SB1-2CB-01 | COUPLER/SECTIONALISING CB - SNUGBOROUGH 110-SNUGBOROUGH 110-110SB1-2CB | 13 | 9 | 9 | Scheduled | 06/05/2026 | 18/05/2026
TO-26-400 kV A1 @ WOO-05 | BUSBAR SECTION - WOODLAND 400-WOODLAND 400-400A1 | 15 | 11 | 11 | Scheduled | 06/05/2026 | 20/05/2026
TO-26-400 kV A2 @ WOO-02 | BUSBAR SECTION - WOODLAND 400-WOODLAND 400-400A2 | 15 | 11 | 11 | Scheduled | 06/05/2026 | 20/05/2026
TO-26-400 kV B1 @ WOO-05 | BUSBAR SECTION - WOODLAND 400-WOODLAND 400-400B1 | 15 | 11 | 11 | Scheduled | 06/05/2026 | 20/05/2026
TO-26-WOO-400K1-2-02 | COUPLER/SECTIONALISING CB - WOODLAND 400-WOODLAND 400-400K1-2 | 15 | 11 | 11 | Scheduled | 06/05/2026 | 20/05/2026
TO-26-KHL-T131-01 | GENERATOR TRANSFORMER - KILL HILL 110-KILL HILL 33-T131 | 2 | 2 |  | Scheduled | 07/05/2026 | 08/05/2026
TO-26-LOU-MTH-1-03 | 110kV FEEDER - LOUTH 110-MEATH HILL 110-1 | 21 | 15 | 15 | Scheduled | 07/05/2026 | 27/05/2026
TO-26-MP GIS-T4201-01 | TRANSFORMER - MONEYPOINT GIS 400-MONEYPOINT GIS 220-T4201 | 14 | 10 | 10 | Scheduled | 07/05/2026 | 20/05/2026
TO-26-GI GIS-T2004-03 | GENERATOR TRANSFORMER - GREAT ISLAND GIS 220-GREAT ISLAND GIS G4-T2004 | 14 | 10 | 10 | Scheduled | 08/05/2026 | 21/05/2026
TO-26-PHT-131-01 | GENERATOR TRANSFORMER - PHILIPSTOWN 110-PHILIPSTOWN 33-T131 | 1 | 1 | 1 | Scheduled | 08/05/2026 | 08/05/2026
TO-26-SHL-D1/CB2-05 | COUPLER/SECTIONALISING CB - SHELLYBANKS 220-SHELLYBANKS 220-D1/CB2 | 1 | 1 | 1 | Scheduled | 08/05/2026 | 08/05/2026
TO-26-SHL-D1/CB3-03 | COUPLER/SECTIONALISING CB - SHELLYBANKS 220-SHELLYBANKS 220-D1/CB3 | 1 | 1 | 1 | Scheduled | 08/05/2026 | 08/05/2026
TO-26-110 kV A1 @ CUL-03 | BUSBAR SECTION - CULLENAGH 110-CULLENAGH 110-110A1 | 2 | 0 | 0 | Scheduled | 09/05/2026 | 10/05/2026
TO-26-CUL-WAT-1-01 | 110kV FEEDER - CULLENAGH 110-WATERFORD 110-1 | 2 | 0 | 0 | Scheduled | 09/05/2026 | 10/05/2026
TO-26-AA GIS-T104-01 | GENERATOR TRANSFORMER - ARDNACRUSHA GIS 110-ARDNACRUSHA GIS G4-T104 | 5 | 5 | 5 | Scheduled | 11/05/2026 | 15/05/2026
TO-26-ATY-110SA1-08 | SECTIONALISING DISCONNECT - ATHY 110-ATHY 110-110SA1 | 5 | 5 | 5 | Scheduled | 11/05/2026 | 15/05/2026
TO-26-ATY-110SA2-08 | SECTIONALISING DISCONNECT - ATHY 110-ATHY 110-110SA2 | 5 | 5 | 5 | Scheduled | 11/05/2026 | 15/05/2026
TO-26-ATY-PLS-1-01 | 110kV FEEDER - ATHY 110-PORTLAOISE 110-1 | 156 | 110 | 110 | Scheduled | 11/05/2026 | 13/10/2026
TO-26-ATY-T102-05 | DISTRIBUTION TRANSFORMER - ATHY 110-ATHY 10-T102 | 5 | 5 | 5 | Reference | 11/05/2026 | 15/05/2026
TO-26-220 kV A1 @ BYH-01 | BUSBAR SECTION - BALLYNAHULLA 220-BALLYNAHULLA 220-220A1 | 8 | 6 | 6 | Scheduled | 11/05/2026 | 18/05/2026
TO-26-220 kV B1 @ BYH-02 | BUSBAR SECTION - BALLYNAHULLA 220-BALLYNAHULLA 220-220B1 | 8 | 6 | 6 | Scheduled | 11/05/2026 | 18/05/2026
TO-26-BYH-220K1-02 | COUPLER/SECTIONALISING CB - BALLYNAHULLA 220-BALLYNAHULLA 220-220K1 | 8 | 6 | 6 | Scheduled | 11/05/2026 | 18/05/2026
TO-26-BYH-220SA1-2CB-04 | COUPLER/SECTIONALISING CB - BALLYNAHULLA 220-BALLYNAHULLA 220-220SA1-2CB | 8 | 6 | 6 | Scheduled | 11/05/2026 | 18/05/2026
TO-26-BYH-220SB1-2CB-04 | COUPLER/SECTIONALISING CB - BALLYNAHULLA 220-BALLYNAHULLA 220-220SB1-2CB | 8 | 6 | 6 | Scheduled | 11/05/2026 | 18/05/2026
TO-26-BYH-KNR-1-01 | 220kV FEEDER - BALLYNAHULLA 220-KNOCKANURE 220-1 | 8 | 6 | 6 | Scheduled | 11/05/2026 | 18/05/2026
TO-26-110 kV A1 @ BLC-03 | BUSBAR SECTION - BELCAMP 110-BELCAMP 110-110A1 | 19 | 15 | 15 | Scheduled | 11/05/2026 | 29/05/2026
TO-26-110 kV A3 @ BLC-03 | BUSBAR SECTION - BELCAMP 110-BELCAMP 110-110A3 | 19 | 15 | 15 | Scheduled | 11/05/2026 | 29/05/2026
TO-26-110 kV B1 @ BLC-03 | BUSBAR SECTION - BELCAMP 110-BELCAMP 110-110B1 | 19 | 15 | 15 | Scheduled | 11/05/2026 | 29/05/2026
TO-26-110 kV B3 @ BLC-03 | BUSBAR SECTION - BELCAMP 110-BELCAMP 110-110B3 | 19 | 15 | 15 | Scheduled | 11/05/2026 | 29/05/2026
TO-26-BLC-110K1-03 | COUPLER/SECTIONALISING CB - BELCAMP 110-BELCAMP 110-110K1 | 19 | 15 | 15 | Scheduled | 11/05/2026 | 29/05/2026
TO-26-BLC-110K3-03 | COUPLER/SECTIONALISING CB - BELCAMP 110-BELCAMP 110-110K3 | 19 | 15 | 15 | Scheduled | 11/05/2026 | 29/05/2026
TO-26-BLC-110SA1-3CB-06 | COUPLER/SECTIONALISING CB - BELCAMP 110-BELCAMP 110-110SA1-3CB | 19 | 15 | 15 | Scheduled | 11/05/2026 | 29/05/2026
TO-26-BLC-110SB1-3CB-04 | COUPLER/SECTIONALISING CB - BELCAMP 110-BELCAMP 110-110SB1-3CB | 19 | 15 | 15 | Scheduled | 11/05/2026 | 29/05/2026
TO-26-CLW-KLS-1-03 | 110kV FEEDER - CARLOW 110-KELLIS 110-1 | 71 | 50 | 50 | Scheduled | 11/05/2026 | 20/07/2026
TO-26-COR-PST-03 | TRANSFORMER - CORRACLASSY 110-ENNISKILLEN 110-PST | 23 | 16 | 16 | Scheduled | 11/05/2026 | 02/06/2026
TO-26-220 kV A1 @ CUL-02 | BUSBAR SECTION - CULLENAGH 220-CULLENAGH 220-220A1 | 19 | 15 | 15 | Scheduled | 11/05/2026 | 29/05/2026
TO-26-220 kV B1 @ CUL-02 | BUSBAR SECTION - CULLENAGH 220-CULLENAGH 220-220B1 | 19 | 15 | 15 | Scheduled | 11/05/2026 | 29/05/2026
TO-26-CUL-GI GIS-1-01 | 220kV FEEDER - CULLENAGH 220-GREAT ISLAND GIS 220-1 | 19 | 15 | 15 | Scheduled | 11/05/2026 | 29/05/2026
TO-26-CUN-T121-01 | GENERATOR TRANSFORMER - CUNGHILL 110-CUNGHILL 20-T121 | 4 | 4 | 4 | Scheduled | 11/05/2026 | 14/05/2026
TO-26-KUD-T103-02 | TSO CUSTOMER TRANSFORMER - KILMAHUD 110-KILMAHUD 10-T103 | 5 | 5 | 5 | Scheduled | 11/05/2026 | 15/05/2026
TO-26-220 kV A2 @ KNR-01 | BUSBAR SECTION - KNOCKANURE 220-KNOCKANURE 220-220A2 | 8 | 6 | 6 | Scheduled | 11/05/2026 | 18/05/2026
TO-26-220 kV B2 @ KNR-01 | BUSBAR SECTION - KNOCKANURE 220-KNOCKANURE 220-220B2 | 8 | 6 | 6 | Scheduled | 11/05/2026 | 18/05/2026
TO-26-KNR-220K2-03 | COUPLER/SECTIONALISING CB - KNOCKANURE 220-KNOCKANURE 220-220K2 | 8 | 6 | 6 | Scheduled | 11/05/2026 | 18/05/2026
TO-26-KNR-220SA1-2CB-02 | COUPLER/SECTIONALISING CB - KNOCKANURE 220-KNOCKANURE 220-220SA1-2CB | 8 | 6 | 6 | Scheduled | 11/05/2026 | 18/05/2026
TO-26-KNR-220SB1-2CB-02 | COUPLER/SECTIONALISING CB - KNOCKANURE 220-KNOCKANURE 220-220SB1-2CB | 8 | 6 | 6 | Scheduled | 11/05/2026 | 18/05/2026
TO-26-MLC-T121-01 | GENERATOR TRANSFORMER - MOUNTLUCAS 110-MOUNTLUCAS 20-T121 | 2 | 2 | 2 | Scheduled | 11/05/2026 | 12/05/2026
TO-26-110 kV A2 @ RAF-01 | BUSBAR SECTION - RAFFEEN 110-RAFFEEN 110-110A2 | 115 | 81 | 81 | Scheduled | 11/05/2026 | 02/09/2026
TO-26-110 kV B2 @ RAF-01 | BUSBAR SECTION - RAFFEEN 110-RAFFEEN 110-110B2 | 115 | 81 | 81 | Scheduled | 11/05/2026 | 02/09/2026
TO-26-SH-T2101-01 | TRANSFORMER - SHANNONBRIDGE 220-SHANNONBRIDGE 110-T2101 | 12 | 10 | 10 | Scheduled | 11/05/2026 | 22/05/2026
TO-26-SHL-D2/CB2-02 | COUPLER/SECTIONALISING CB - SHELLYBANKS 220-SHELLYBANKS 220-D2/CB2 | 1 | 1 | 1 | Scheduled | 11/05/2026 | 11/05/2026
TO-26-SHL-D2/CB3-02 | COUPLER/SECTIONALISING CB - SHELLYBANKS 220-SHELLYBANKS 220-D2/CB3 | 1 | 1 | 1 | Scheduled | 11/05/2026 | 11/05/2026
TO-26-SHL-T2015-02 | GENERATOR TRANSFORMER - SHELLYBANKS 220-SHELLYBANKS G5-T2015 | 19 | 15 | 15 | Scheduled | 11/05/2026 | 29/05/2026
TO-26-AUN-CBT-1-02 | 110kV FEEDER - AUNGIERSTOWN 110-CASTLEBAGOT 110-1 | 2 | 2 | 2 | Scheduled | 12/05/2026 | 13/05/2026
TO-26-CDU-CRU-1-01 | 220kV FEEDER - CORDUFF 220-CRUISERATH 220-1 | 4 | 4 | 4 | Scheduled | 12/05/2026 | 15/05/2026
TO-26-220 kV A2 @ GI GIS-01 | BUSBAR SECTION - GREAT ISLAND GIS 220-GREAT ISLAND GIS 220-220A2 | 4 | 4 | 4 | Scheduled | 12/05/2026 | 15/05/2026
TO-26-GI GIS-220K2-03 | COUPLER/SECTIONALISING CB - GREAT ISLAND GIS 220-GREAT ISLAND GIS 220-220K2 | 4 | 4 | 4 | Scheduled | 12/05/2026 | 15/05/2026
TO-26-GI GIS-220SA1-2CB-03 | COUPLER/SECTIONALISING CB - GREAT ISLAND GIS 220-GREAT ISLAND GIS 220-220SA1-2CB | 4 | 4 | 4 | Scheduled | 12/05/2026 | 15/05/2026
TO-26-ARK-T102-01 | DISTRIBUTION TRANSFORMER - ARKLOW 110-ARKLOW 10-T102 | 2 | 2 | 2 | Reference | 13/05/2026 | 14/05/2026
TO-26-SLB-T132-01 | GENERATOR TRANSFORMER - SLIABH BAWN 110-SLIABH BAWN 33-T132 | 2 | 2 | 2 | Scheduled | 13/05/2026 | 14/05/2026
TO-26-DER-T1/T2-02 | GENERATOR TRANSFORMER - DERRYIRON 110-RHODE 110-T1/T2 | 15 | 11 | 11 | Scheduled | 15/05/2026 | 29/05/2026
TO-26-BVK-STATCOM-01 | CAPACITOR/SVC/REACTOR - BALLYVOUSKILL 110-BALLYVOUSKILL 110-STATCOM | 5 | 5 | 5 | Scheduled | 18/05/2026 | 22/05/2026
TO-26-GLE-KCR-1-01 | 110kV FEEDER - GLENLARA 110-KNOCKACUMMER 110-1 | 19 | 14 | 14 | Scheduled | 18/05/2026 | 05/06/2026
TO-26-220 kV A2 @ ISH-01 | BUSBAR SECTION - IRISHTOWN 220-IRISHTOWN 220-220A2 | 5 | 5 | 5 | Scheduled | 18/05/2026 | 22/05/2026
TO-26-220 kV B2 @ ISH-01 | BUSBAR SECTION - IRISHTOWN 220-IRISHTOWN 220-220B2 | 5 | 5 | 5 | Scheduled | 18/05/2026 | 22/05/2026
TO-26-ISH-T2002/3-03 | GENERATOR TRANSFORMER - IRISHTOWN 220-IRISHTOWN G2/3-T2002/3 | 5 | 5 | 5 | Scheduled | 18/05/2026 | 22/05/2026
TO-26-KCR-T121-01 | GENERATOR TRANSFORMER - KNOCKACUMMER 110-KNOCKACUMMER 20-T121 | 19 | 14 | 14 | Scheduled | 18/05/2026 | 05/06/2026
TO-26-AUN-KSG-1-03 | 110kV FEEDER - AUNGIERSTOWN 110-KISHOGE 110-1 | 3 | 3 | 3 | Scheduled | 19/05/2026 | 21/05/2026
TO-26-BIN-T143-01 | DISTRIBUTION TRANSFORMER - BINBANE 110-BINBANE 38-T143 | 2 | 2 | 2 | Reference | 19/05/2026 | 20/05/2026
TO-26-AHA-KLN-2-01 | 110kV FEEDER - AHANE 110-KILLONAN 110-2 | 2 | 2 | 2 | Reference | 20/05/2026 | 21/05/2026
TO-26-AHA-T102-01 | DISTRIBUTION TRANSFORMER - AHANE 110-AHANE 10-T102 | 2 | 2 | 2 | Reference | 20/05/2026 | 21/05/2026
TO-26-AA GIS-T141-01 | DISTRIBUTION TRANSFORMER - ARDNACRUSHA GIS 110-ARDNACRUSHA GIS 38-T141 | 2 | 2 | 2 | Reference | 20/05/2026 | 21/05/2026
TO-26-AUN-T121-02 | TSO CUSTOMER TRANSFORMER - AUNGIERSTOWN 110-AUNGIERSTOWN 20-T121 | 2 | 2 | 2 | Scheduled | 21/05/2026 | 22/05/2026
TO-26-MTH-T141-02 | DISTRIBUTION TRANSFORMER - MEATH HILL 110-MEATH HILL 38-T141 | 7 | 5 | 5 | Reference | 21/05/2026 | 27/05/2026
TO-26-LLA-LET-1-01 | 110kV FEEDER - LENALEA 110-LETTERKENNY 110-1 | 15 | 10 | 10 | Scheduled | 22/05/2026 | 05/06/2026
TO-26-LET-110SA1-3CB-02 | COUPLER/SECTIONALISING CB - LETTERKENNY 110-LETTERKENNY 110-110SA1-3CB | 15 | 10 | 10 | Scheduled | 22/05/2026 | 05/06/2026
TO-26-LET-TLK-1-01 | 110kV FEEDER - LETTERKENNY 110-TRILLICK 110-1 | 15 | 10 | 10 | Reference | 22/05/2026 | 05/06/2026
TO-26-SOR-T122-01 | DISTRIBUTION TRANSFORMER - SORNE HILL 110-SORNE HILL 20-T122 | 15 | 10 | 10 | Reference | 22/05/2026 | 05/06/2026
TO-26-SOR-T124-01 | DISTRIBUTION TRANSFORMER - SORNE HILL 110-SORNE HILL 20-T124 | 15 | 10 | 10 | Reference | 22/05/2026 | 05/06/2026
TO-26-SOR-TLK-1-01 | 110kV FEEDER - SORNE HILL 110-TRILLICK 110-1 | 15 | 10 | 10 | Reference | 22/05/2026 | 05/06/2026
TO-26-TLK-T141-01 | DISTRIBUTION TRANSFORMER - TRILLICK 110-TRILLICK 38-T141 | 15 | 10 | 10 | Reference | 22/05/2026 | 05/06/2026
TO-26-TLK-T142-01 | DISTRIBUTION TRANSFORMER - TRILLICK 110-TRILLICK 38-T142 | 15 | 10 | 10 | Reference | 22/05/2026 | 05/06/2026
TO-26-ARK-BOG-1-04 | 110kV FEEDER - ARKLOW 110-BANOGE 110-1 | 9 | 6 | 6 | Scheduled | 25/05/2026 | 02/06/2026
TO-26-BYH-STATCOM-04 | CAPACITOR/SVC/REACTOR - BALLYNAHULLA 110-BALLYNAHULLA 110-STATCOM | 5 | 5 | 5 | Scheduled | 25/05/2026 | 29/05/2026
TO-26-BOG-110SA1-02 | SECTIONALISING DISCONNECT - BANOGE 110-BANOGE 110-110SA1 | 5 | 5 | 5 | Scheduled | 25/05/2026 | 29/05/2026
TO-26-BOG-110SA2-01 | SECTIONALISING DISCONNECT - BANOGE 110-BANOGE 110-110SA2 | 5 | 5 | 5 | Scheduled | 25/05/2026 | 29/05/2026
TO-26-BOG-T122-01 | DISTRIBUTION TRANSFORMER - BANOGE 110-BANOGE 20-T122 | 5 | 5 | 5 | Reference | 25/05/2026 | 29/05/2026
TO-26-220 kV A1 @ CSH-01 | BUSBAR SECTION - CASHLA 220-CASHLA 220-220A1 | 19 | 14 | 14 | Scheduled | 25/05/2026 | 12/06/2026
TO-26-220 kV A2 @ CSH-02 | BUSBAR SECTION - CASHLA 220-CASHLA 220-220A2 | 19 | 14 | 14 | Scheduled | 25/05/2026 | 12/06/2026
TO-26-220 kV B1 @ CSH-01 | BUSBAR SECTION - CASHLA 220-CASHLA 220-220B1 | 19 | 14 | 14 | Scheduled | 25/05/2026 | 12/06/2026
TO-26-220 kV B2 @ CSH-03 | BUSBAR SECTION - CASHLA 220-CASHLA 220-220B2 | 19 | 14 | 14 | Scheduled | 25/05/2026 | 12/06/2026
TO-26-CSH-220K1-2-01 | COUPLER/SECTIONALISING CB - CASHLA 220-CASHLA 220-220K1-2 | 19 | 14 | 14 | Scheduled | 25/05/2026 | 12/06/2026
TO-26-DER-TEN-1-01 | 110kV FEEDER - DERRYIRON 110-TIMAHOE 110-1 | 22 | 15 | 15 | Scheduled | 25/05/2026 | 15/06/2026
TO-26-220 kV A2 @ KPG-01 | BUSBAR SECTION - KILPADDOGE 220-KILPADDOGE 220-220A2 | 5 | 5 | 5 | Scheduled | 25/05/2026 | 29/05/2026
TO-26-220 kV B2 @ KPG-02 | BUSBAR SECTION - KILPADDOGE 220-KILPADDOGE 220-220B2 | 5 | 5 | 5 | Scheduled | 25/05/2026 | 29/05/2026
TO-26-KPG-220SA1-2CB-01 | COUPLER/SECTIONALISING CB - KILPADDOGE 220-KILPADDOGE 220-220SA1-2CB | 5 | 5 | 5 | Scheduled | 25/05/2026 | 29/05/2026
TO-26-KPG-220SA2-4CB-04 | COUPLER/SECTIONALISING CB - KILPADDOGE 220-KILPADDOGE 220-220SA2-4CB | 5 | 5 | 5 | Scheduled | 25/05/2026 | 29/05/2026
TO-26-KPG-220SB1-2CB-01 | COUPLER/SECTIONALISING CB - KILPADDOGE 220-KILPADDOGE 220-220SB1-2CB | 5 | 5 | 5 | Scheduled | 25/05/2026 | 29/05/2026
TO-26-KPG-220SB2-4CB-04 | COUPLER/SECTIONALISING CB - KILPADDOGE 220-KILPADDOGE 220-220SB2-4CB | 5 | 5 | 5 | Scheduled | 25/05/2026 | 29/05/2026
TO-26-KPG-TB-2-01 | 220kV FEEDER - KILPADDOGE 220-TARBERT 220-2 | 5 | 5 | 5 | Scheduled | 25/05/2026 | 29/05/2026
TO-26-KRA-T2101-01 | TRANSFORMER - KNOCKRAHA 220-KNOCKRAHA 110-T2101 | 4 | 4 | 4 | Scheduled | 25/05/2026 | 28/05/2026
TO-26-MP GIS-T4001-05 | GENERATOR TRANSFORMER - MONEYPOINT GIS 400-MONEYPOINT GIS G1-T4001 | 16 | 11 | 11 | Scheduled | 25/05/2026 | 09/06/2026
TO-26-220 kV A2 @ TB-02 | BUSBAR SECTION - TARBERT 220-TARBERT 220-220A2 | 5 | 5 | 5 | Scheduled | 25/05/2026 | 29/05/2026
TO-26-220 kV B2 @ TB-02 | BUSBAR SECTION - TARBERT 220-TARBERT 220-220B2 | 5 | 5 | 5 | Scheduled | 25/05/2026 | 29/05/2026
TO-26-TRL-CAP2-03 | CAPACITOR/SVC/REACTOR - TRALEE 110-TRALEE 110-CAP2 | 15 | 10 | 10 | Scheduled | 25/05/2026 | 08/06/2026
TO-26-CBT-CKG-2-03 | 110kV FEEDER - CASTLEBAGOT 110-CORKAGH 110-2 | 4 | 4 | 4 | Scheduled | 26/05/2026 | 29/05/2026
TO-26-110 kV A2 @ CDU-03 | BUSBAR SECTION - CORDUFF 110-CORDUFF 110-110A2 | 13 | 8 | 8 | Scheduled | 28/05/2026 | 09/06/2026
TO-26-110 kV A4 @ CDU-04 | BUSBAR SECTION - CORDUFF 110-CORDUFF 110-110A4 | 13 | 8 | 8 | Scheduled | 28/05/2026 | 09/06/2026
TO-26-110 kV B2 @ CDU-03 | BUSBAR SECTION - CORDUFF 110-CORDUFF 110-110B2 | 13 | 8 | 8 | Scheduled | 28/05/2026 | 09/06/2026
TO-26-110 kV B4 @ CDU-03 | BUSBAR SECTION - CORDUFF 110-CORDUFF 110-110B4 | 13 | 8 | 8 | Scheduled | 28/05/2026 | 09/06/2026
TO-26-CDU-110SA2-4CB-03 | COUPLER/SECTIONALISING CB - CORDUFF 110-CORDUFF 110-110SA2-4CB | 13 | 8 | 8 | Scheduled | 28/05/2026 | 09/06/2026
TO-26-CDU-110SB2-4CB-03 | COUPLER/SECTIONALISING CB - CORDUFF 110-CORDUFF 110-110SB2-4CB | 13 | 8 | 8 | Scheduled | 28/05/2026 | 09/06/2026
TO-26-220 kV A2 @ CDU-03 | BUSBAR SECTION - CORDUFF 220-CORDUFF 220-220A2 | 13 | 8 | 8 | Scheduled | 28/05/2026 | 09/06/2026
TO-26-220 kV A4 @ CDU-02 | BUSBAR SECTION - CORDUFF 220-CORDUFF 220-220A4 | 13 | 8 | 8 | Scheduled | 28/05/2026 | 09/06/2026
TO-26-220 kV B2 @ CDU-03 | BUSBAR SECTION - CORDUFF 220-CORDUFF 220-220B2 | 13 | 8 | 8 | Scheduled | 28/05/2026 | 09/06/2026
TO-26-220 kV B4 @ CDU-03 | BUSBAR SECTION - CORDUFF 220-CORDUFF 220-220B4 | 13 | 8 | 8 | Scheduled | 28/05/2026 | 09/06/2026
TO-26-CDU-220SA2-4CB-03 | COUPLER/SECTIONALISING CB - CORDUFF 220-CORDUFF 220-220SA2-4CB | 13 | 8 | 8 | Scheduled | 28/05/2026 | 09/06/2026
TO-26-CDU-220SB2-4CB-03 | COUPLER/SECTIONALISING CB - CORDUFF 220-CORDUFF 220-220SB2-4CB | 13 | 8 | 8 | Scheduled | 28/05/2026 | 09/06/2026
TO-26-CDU-T2102-02 | TRANSFORMER - CORDUFF 220-CORDUFF 110-T2102 | 29 | 20 | 20 | Scheduled | 28/05/2026 | 25/06/2026
TO-26-SHL-D2/CB2-03 | COUPLER/SECTIONALISING CB - SHELLYBANKS 220-SHELLYBANKS 220-D2/CB2 | 1 | 1 | 1 | Scheduled | 29/05/2026 | 29/05/2026
TO-26-SHL-D2/CB3-03 | COUPLER/SECTIONALISING CB - SHELLYBANKS 220-SHELLYBANKS 220-D2/CB3 | 1 | 1 | 1 | Scheduled | 29/05/2026 | 29/05/2026
TO-26-GI-WAT-1-05 | 110kV FEEDER - GREAT ISLAND 110-WATERFORD 110-1 | 1 | 0 | 0 | Scheduled | 30/05/2026 | 30/05/2026
TO-26-GI-WAT-2-03 | 110kV FEEDER - GREAT ISLAND 110-WATERFORD 110-2 | 1 | 0 | 0 | Scheduled | 30/05/2026 | 30/05/2026
TO-26-BYH-CDL-1-01 | 110kV FEEDER - BALLYNAHULLA 110-CORDAL 110-1 | 32 | 24 | 24 | Scheduled | 02/06/2026 | 03/07/2026
TO-26-CBT-CKG-1-03 | 110kV FEEDER - CASTLEBAGOT 110-CORKAGH 110-1 | 4 | 4 | 4 | Scheduled | 02/06/2026 | 05/06/2026
TO-26-CDL-110SA1-01 | SECTIONALISING DISCONNECT - CORDAL 110-CORDAL 110-110SA1 | 32 | 24 | 24 | Scheduled | 02/06/2026 | 03/07/2026
TO-26-CDL-110SA2-01 | SECTIONALISING DISCONNECT - CORDAL 110-CORDAL 110-110SA2 | 32 | 24 | 24 | Scheduled | 02/06/2026 | 03/07/2026
TO-26-CDL-T132-02 | GENERATOR TRANSFORMER - CORDAL 110-CORDAL 33-T132 | 32 | 24 | 24 | Scheduled | 02/06/2026 | 03/07/2026
TO-26-CDL-T141-01 | DISTRIBUTION TRANSFORMER - CORDAL 110-CORDAL 38-T141 | 32 | 24 | 24 | Reference | 02/06/2026 | 03/07/2026
TO-26-110 kV A3 @ CKG-02 | BUSBAR SECTION - CORKAGH 110-CORKAGH 110-110A3 | 4 | 4 | 4 | Scheduled | 02/06/2026 | 05/06/2026
TO-26-110 kV B3 @ CKG-03 | BUSBAR SECTION - CORKAGH 110-CORKAGH 110-110B3 | 4 | 4 | 4 | Scheduled | 02/06/2026 | 05/06/2026
TO-26-CKG-110K3-02 | COUPLER/SECTIONALISING CB - CORKAGH 110-CORKAGH 110-110K3 | 4 | 4 | 4 | Scheduled | 02/06/2026 | 05/06/2026
TO-26-CKG-110SA1-3CB-04 | COUPLER/SECTIONALISING CB - CORKAGH 110-CORKAGH 110-110SA1-3CB | 4 | 4 | 4 | Scheduled | 02/06/2026 | 05/06/2026
TO-26-CKG-110SB1-3CB-04 | COUPLER/SECTIONALISING CB - CORKAGH 110-CORKAGH 110-110SB1-3CB | 4 | 4 | 4 | Scheduled | 02/06/2026 | 05/06/2026
TO-26-CUS-KIR-1-01 | 110kV FEEDER - CUSHALING 110-KILCUMBER 110-1 | 3 | 3 | 3 | Scheduled | 02/06/2026 | 04/06/2026
TO-26-FIN-HN-1-01 | 220kV FEEDER - FINGLAS 220-HUNTSTOWN 220-1 | 23 | 17 | 17 | Scheduled | 02/06/2026 | 24/06/2026
TO-26-FIN-SHL-1-02 | 220kV FEEDER - FINGLAS 220-SHELLYBANKS 220-1 | 71 | 50 |  | Scheduled | 02/06/2026 | 11/08/2026
TO-26-GRI-T141-03 | DISTRIBUTION TRANSFORMER - GRIFFINRATH 110-GRIFFINRATH 38-T141 | 4 | 4 | 4 | Reference | 02/06/2026 | 05/06/2026
TO-26-GRI,T-GRI-1-03 | 110kV FEEDER - GRIFFINRATH tee-GRIFFINRATH 110-1 | 4 | 4 | 4 | Scheduled | 02/06/2026 | 05/06/2026
TO-26-GRI,T-MAY-1-04 | 110kV FEEDER - GRIFFINRATH tee-MAYNOOTH 110-1 | 4 | 4 | 4 | Scheduled | 02/06/2026 | 05/06/2026
TO-26-HN-T2010/11-01 | GENERATOR TRANSFORMER - HUNTSTOWN 220-HUNTSTOWN G10/11-T2010/11 | 23 | 17 | 17 | Scheduled | 02/06/2026 | 24/06/2026
TO-26-KIR-T131-01 | GENERATOR TRANSFORMER - KILCUMBER 110-KILCUMBER 33-T131 | 3 | 3 | 3 | Scheduled | 02/06/2026 | 04/06/2026
TO-26-KLN-KPG-1-02 | 220kV FEEDER - KILLONAN 220-KILPADDOGE 220-1 | 58 | 42 | 42 | Scheduled | 02/06/2026 | 29/07/2026
TO-26-KLN-T2101-03 | TRANSFORMER - KILLONAN 220-KILLONAN 110-T2101 | 4 | 4 | 4 | Scheduled | 02/06/2026 | 05/06/2026
TO-26-LLA-T133-01 | GENERATOR TRANSFORMER - LENALEA 110-LENALEA 33-T133 | 3 | 3 | 3 | Scheduled | 02/06/2026 | 04/06/2026
TO-26-MP GIS-T4202-01 | TRANSFORMER - MONEYPOINT GIS 400-MONEYPOINT GIS 220-T4202 | 11 | 9 |  | Scheduled | 02/06/2026 | 12/06/2026
TO-26-110 kV A1 @ PLS-07 | BUSBAR SECTION - PORTLAOISE 110-PORTLAOISE 110-110A1 | 18 | 14 | 14 | Scheduled | 02/06/2026 | 19/06/2026
TO-26-110 kV A2 @ PLS-01 | BUSBAR SECTION - PORTLAOISE 110-PORTLAOISE 110-110A2 | 18 | 14 | 14 | Scheduled | 02/06/2026 | 19/06/2026
TO-26-110 kV B1 @ PLS-06 | BUSBAR SECTION - PORTLAOISE 110-PORTLAOISE 110-110B1 | 18 | 14 | 14 | Scheduled | 02/06/2026 | 19/06/2026
TO-26-110 kV B2 @ PLS-01 | BUSBAR SECTION - PORTLAOISE 110-PORTLAOISE 110-110B2 | 18 | 14 | 14 | Scheduled | 02/06/2026 | 19/06/2026
TO-26-PLS-110K1-2-03 | COUPLER/SECTIONALISING CB - PORTLAOISE 110-PORTLAOISE 110-110K1-2 | 18 | 14 | 14 | Scheduled | 02/06/2026 | 19/06/2026
TO-26-110 kV A1 @ RAF-04 | BUSBAR SECTION - RAFFEEN 110-RAFFEEN 110-110A1 | 10 | 8 | 8 | Scheduled | 02/06/2026 | 11/06/2026
TO-26-110 kV B1 @ RAF-03 | BUSBAR SECTION - RAFFEEN 110-RAFFEEN 110-110B1 | 10 | 8 | 8 | Scheduled | 02/06/2026 | 11/06/2026
TO-26-220 kV A1 @ RAF-01 | BUSBAR SECTION - RAFFEEN 220-RAFFEEN 220-220A1 | 10 | 8 | 8 | Scheduled | 02/06/2026 | 11/06/2026
TO-26-220 kV B1 @ RAF-01 | BUSBAR SECTION - RAFFEEN 220-RAFFEEN 220-220B1 | 10 | 8 | 8 | Scheduled | 02/06/2026 | 11/06/2026
TO-26-RAF-T2101-01 | TRANSFORMER - RAFFEEN 220-RAFFEEN 110-T2101 | 10 | 8 | 8 | Scheduled | 02/06/2026 | 11/06/2026
TO-26-SHL-D1/CB1-02 | COUPLER/SECTIONALISING CB - SHELLYBANKS 220-SHELLYBANKS 220-D1/CB1 | 4 | 4 | 4 | Scheduled | 02/06/2026 | 05/06/2026
TO-26-SHL-D1/CB2-03 | COUPLER/SECTIONALISING CB - SHELLYBANKS 220-SHELLYBANKS 220-D1/CB2 | 4 | 4 | 4 | Scheduled | 02/06/2026 | 05/06/2026
TO-26-110 kV A1 @ ARK-01 | BUSBAR SECTION - ARKLOW 110-ARKLOW 110-110A1 | 17 | 13 | 13 | Scheduled | 03/06/2026 | 19/06/2026
TO-26-110 kV B1 @ ARK-01 | BUSBAR SECTION - ARKLOW 110-ARKLOW 110-110B1 | 17 | 13 | 13 | Scheduled | 03/06/2026 | 19/06/2026
TO-26-220 kV A1 @ ARK-01 | BUSBAR SECTION - ARKLOW 220-ARKLOW 220-220A1 | 17 | 13 | 13 | Scheduled | 03/06/2026 | 19/06/2026
TO-26-220 kV B1 @ ARK-01 | BUSBAR SECTION - ARKLOW 220-ARKLOW 220-220B1 | 17 | 13 | 13 | Scheduled | 03/06/2026 | 19/06/2026
TO-26-ARK-T2101-03 | TRANSFORMER - ARKLOW 220-ARKLOW 110-T2101 | 17 | 13 | 13 | Scheduled | 03/06/2026 | 19/06/2026
TO-26-CKM GIS-220K4-01 | COUPLER/SECTIONALISING CB - CARRICKMINES GIS 220-CARRICKMINES GIS 220-220K4 | 2 | 2 | 2 | Scheduled | 03/06/2026 | 04/06/2026
TO-26-KYT-T237-02 | TSO CUSTOMER TRANSFORMER - KELLYSTOWN 220-KELLYSTOWN 34.5-T237 | 1 | 1 | 1 | Scheduled | 03/06/2026 | 03/06/2026
TO-26-MR-T106-01 | DISTRIBUTION TRANSFORMER - MARINA 110-MARINA 10-T106 | 2 | 2 | 2 | Reference | 03/06/2026 | 04/06/2026
TO-26-KYT-T233-03 | TSO CUSTOMER TRANSFORMER - KELLYSTOWN 220-KELLYSTOWN 34.5-T233 | 26 | 18 | 18 | Scheduled | 05/06/2026 | 30/06/2026
TO-26-220 kV A1 @ AD-01 | BUSBAR SECTION - AGHADA 220-AGHADA 220-220A1 | 1 | 1 | 1 | Proposed | 08/06/2026 | 08/06/2026
TO-26-220 kV A2 @ AD-01 | BUSBAR SECTION - AGHADA 220-AGHADA 220-220A2 | 1 | 1 | 1 | Proposed | 08/06/2026 | 08/06/2026
TO-26-AD-220K1-03 | COUPLER/SECTIONALISING CB - AGHADA 220-AGHADA 220-220K1 | 1 | 1 | 1 | Proposed | 08/06/2026 | 08/06/2026
TO-26-AD-SA1-2CB-02 | COUPLER/SECTIONALISING CB - AGHADA 220-AGHADA 220-220SA1-2CB | 1 | 1 | 1 | Proposed | 08/06/2026 | 08/06/2026
TO-26-AD-T2011/12-02 | GENERATOR TRANSFORMER - AGHADA 220-AGHADA G11/12-T2011/12 | 1 | 1 | 1 | Proposed | 08/06/2026 | 08/06/2026
TO-26-AA GIS-110SB1-3CB-01 | COUPLER/SECTIONALISING CB - ARDNACRUSHA GIS 110-ARDNACRUSHA GIS 110-110SB1-3CB | 1 | 1 | 1 | Scheduled | 08/06/2026 | 08/06/2026
TO-26-AUG-CFM-1-02 | 110kV FEEDER - AUGHINISH 110-CASTLEFARM 110-1 | 5 | 5 | 5 | Scheduled | 08/06/2026 | 12/06/2026
TO-26-220 kV A4 @ CSH-02 | BUSBAR SECTION - CASHLA 220-CASHLA 220-220A4 | 5 | 5 | 5 | Proposed | 08/06/2026 | 12/06/2026
TO-26-CSH-T2104-03 | TRANSFORMER - CASHLA 220-CASHLA 110-T2104 | 5 | 5 | 5 | Proposed | 08/06/2026 | 12/06/2026
TO-26-CFM-T101-02 | TSO CUSTOMER TRANSFORMER - CASTLEFARM 110-CASTLEFARM 10-T101 | 5 | 5 | 5 | Reference | 08/06/2026 | 12/06/2026
TO-26-CF-CLO-2-02 | 110kV FEEDER - CATHALEENS FALL 110-CLOGHER 110-2 | 19 | 15 | 15 | Scheduled | 08/06/2026 | 26/06/2026
TO-26-CF-T104-01 | GENERATOR TRANSFORMER - CATHALEENS FALL 110-CATHALEENS FALL G4-T104 | 12 | 10 | 10 | Scheduled | 08/06/2026 | 19/06/2026
TO-26-110 kV A2 @ CLO-01 | BUSBAR SECTION - CLOGHER 110-CLOGHER 110-110A2 | 8 | 6 | 6 | Scheduled | 08/06/2026 | 15/06/2026
TO-26-110 kV B2 @ CLO-01 | BUSBAR SECTION - CLOGHER 110-CLOGHER 110-110B2 | 8 | 6 | 6 | Scheduled | 08/06/2026 | 15/06/2026
TO-26-CDU-CRU-2-02 | 220kV FEEDER - CORDUFF 220-CRUISERATH 220-2 | 5 | 5 | 5 | Proposed | 08/06/2026 | 12/06/2026
TO-26-KTL-T131-02 | GENERATOR TRANSFORMER - KILTEEL 110-KILTEEL 33-T131 | 2 | 2 | 2 | Scheduled | 08/06/2026 | 09/06/2026
TO-26-KRA-220SA1-2CB-05 | COUPLER/SECTIONALISING CB - KNOCKRAHA 220-KNOCKRAHA 220-220SA1-2CB | 12 | 10 | 10 | Proposed | 08/06/2026 | 19/06/2026
TO-26-KRA-220SB1-2CB-05 | COUPLER/SECTIONALISING CB - KNOCKRAHA 220-KNOCKRAHA 220-220SB1-2CB | 12 | 10 | 10 | Proposed | 08/06/2026 | 19/06/2026
TO-26-KRA-WOH-1-08 | 110kV FEEDER - KNOCKRAHA 110-WOODHOUSE 110-1 | 12 | 10 | 10 | Proposed | 08/06/2026 | 19/06/2026
TO-26-KRA-WOH-1-02 | 110kV FEEDER - KNOCKRAHA 110-WOODHOUSE 110-1 | 12 | 10 | 10 | Scheduled | 08/06/2026 | 19/06/2026
TO-26-KNY-SAL-1-01 | 110kV FEEDER - KNOCKRANNY 110-SALTHILL 110-1 | 12 | 10 | 10 | Proposed | 08/06/2026 | 19/06/2026
TO-26-PB-R2002-03 | CAPACITOR/SVC/REACTOR - POOLBEG 220-POOLBEG 220-R2002 | 5 | 5 | 5 | Scheduled | 08/06/2026 | 12/06/2026
TO-26-ANR-DOO-1-02 | 110kV FEEDER - ANNER 110-DOON 110-1 | 1 | 1 | 1 | Proposed | 09/06/2026 | 09/06/2026
TO-26-ANR-T101-07 | TSO CUSTOMER TRANSFORMER - ANNER 110-ANNER 10-T101 | 1 | 1 | 1 | Reference (Proposed) | 09/06/2026 | 09/06/2026
TO-26-ANR-T103-06 | TSO CUSTOMER TRANSFORMER - ANNER 110-ANNER 10-T103 | 1 | 1 | 1 | Reference (Proposed) | 09/06/2026 | 09/06/2026
TO-26-AA GIS-110SA1-3CB-02 | COUPLER/SECTIONALISING CB - ARDNACRUSHA GIS 110-ARDNACRUSHA GIS 110-110SA1-3CB | 2 | 2 | 2 | Proposed | 09/06/2026 | 10/06/2026
TO-26-ARK-T142-01 | DISTRIBUTION TRANSFORMER - ARKLOW 110-ARKLOW 38-T142 | 2 | 2 | 2 | Reference (Proposed) | 09/06/2026 | 10/06/2026
TO-26-BAL-T122-03 | DISTRIBUTION TRANSFORMER - BALTRASNA 110-BALTRASNA 20-T122 | 2 | 2 | 2 | Reference (Proposed) | 09/06/2026 | 10/06/2026
TO-26-CD-T103-03 | GENERATOR TRANSFORMER - CARRIGADROHID 110-CARRIGADROHID G3-T103 | 11 | 9 | 9 | Proposed | 09/06/2026 | 19/06/2026
TO-26-CHA-KLN-1-02 | 110kV FEEDER - CHARLEVILLE 110-KILLONAN 110-1 | 7 | 5 | 5 | Proposed | 09/06/2026 | 15/06/2026
TO-26-FIN-T2104-01 | TRANSFORMER - FINGLAS 220-FINGLAS 110-T2104 | 113 | 80 | 80 | Proposed | 09/06/2026 | 29/09/2026
TO-26-GAL GIS-110K2-01 | COUPLER/SECTIONALISING CB - GALWAY GIS 110-GALWAY GIS 110-110K2 | 2 | 2 | 2 | Scheduled | 09/06/2026 | 10/06/2026
TO-26-GAL GIS-110K3-01 | COUPLER/SECTIONALISING CB - GALWAY GIS 110-GALWAY GIS 110-110K3 | 2 | 2 | 2 | Scheduled | 09/06/2026 | 10/06/2026
TO-26-GAL GIS-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - GALWAY GIS 110-GALWAY GIS 110-110SA1-2CB | 2 | 2 | 2 | Scheduled | 09/06/2026 | 10/06/2026
TO-26-GAL GIS-110SA1-3CB-01 | COUPLER/SECTIONALISING CB - GALWAY GIS 110-GALWAY GIS 110-110SA1-3CB | 2 | 2 | 2 | Scheduled | 09/06/2026 | 10/06/2026
TO-26-GAL GIS-110SB1-2CB-01 | COUPLER/SECTIONALISING CB - GALWAY GIS 110-GALWAY GIS 110-110SB1-2CB | 2 | 2 | 2 | Scheduled | 09/06/2026 | 10/06/2026
TO-26-GAL GIS-110SB1-3CB-01 | COUPLER/SECTIONALISING CB - GALWAY GIS 110-GALWAY GIS 110-110SB1-3CB | 2 | 2 | 2 | Scheduled | 09/06/2026 | 10/06/2026
TO-26-GRI-MAY-1-01 | 110kV FEEDER - GRIFFINRATH 110-MAYNOOTH 110-1 | 2 | 2 | 2 | Reference (Proposed) | 09/06/2026 | 10/06/2026
TO-26-GRI-T142-01 | DISTRIBUTION TRANSFORMER - GRIFFINRATH 110-GRIFFINRATH 38-T142 | 2 | 2 | 2 | Reference (Proposed) | 09/06/2026 | 10/06/2026
TO-26-LLA-110K1-07 | COUPLER/SECTIONALISING CB - LENALEA 110-LENALEA 110-110K1 | 2 | 2 | 2 | Scheduled | 09/06/2026 | 10/06/2026
TO-26-KLS-220K1-2-02 | COUPLER/SECTIONALISING CB - KELLIS 220-KELLIS 220-220K1-2 | 1 | 1 | 1 | Proposed | 10/06/2026 | 10/06/2026
TO-26-110 kV A1 @ TBG-02 | BUSBAR SECTION - TRABEG 110-TRABEG 110-110A1 | 10 | 8 | 8 | Proposed | 10/06/2026 | 19/06/2026
TO-26-110 kV A2 @ TBG-03 | BUSBAR SECTION - TRABEG 110-TRABEG 110-110A2 | 10 | 8 | 8 | Proposed | 10/06/2026 | 19/06/2026
TO-26-110 kV B1 @ TBG-02 | BUSBAR SECTION - TRABEG 110-TRABEG 110-110B1 | 10 | 8 | 8 | Proposed | 10/06/2026 | 19/06/2026
TO-26-110 kV B2 @ TBG-03 | BUSBAR SECTION - TRABEG 110-TRABEG 110-110B2 | 10 | 8 | 8 | Proposed | 10/06/2026 | 19/06/2026
TO-26-TBG-110K1-2-01 | COUPLER/SECTIONALISING CB - TRABEG 110-TRABEG 110-110K1-2 | 10 | 8 | 8 | Proposed | 10/06/2026 | 19/06/2026
TO-26-110 kV A1 @ AA GIS-01 | BUSBAR SECTION - ARDNACRUSHA GIS 110-ARDNACRUSHA GIS 110-110A1 | 9 | 7 | 7 | Proposed | 11/06/2026 | 19/06/2026
TO-26-110 kV B1 @ AA GIS-01 | BUSBAR SECTION - ARDNACRUSHA GIS 110-ARDNACRUSHA GIS 110-110B1 | 9 | 7 | 7 | Proposed | 11/06/2026 | 19/06/2026
TO-26-AA GIS-110SA1-2CB-02 | COUPLER/SECTIONALISING CB - ARDNACRUSHA GIS 110-ARDNACRUSHA GIS 110-110SA1-2CB | 9 | 7 | 7 | Proposed | 11/06/2026 | 19/06/2026
TO-26-AA GIS-110SA1-3CB-01 | COUPLER/SECTIONALISING CB - ARDNACRUSHA GIS 110-ARDNACRUSHA GIS 110-110SA1-3CB | 9 | 7 | 7 | Proposed | 11/06/2026 | 19/06/2026
TO-26-AA GIS-110SB1-2CB-02 | COUPLER/SECTIONALISING CB - ARDNACRUSHA GIS 110-ARDNACRUSHA GIS 110-110SB1-2CB | 9 | 7 | 7 | Proposed | 11/06/2026 | 19/06/2026
TO-26-AA GIS-110SB1-3CB-03 | COUPLER/SECTIONALISING CB - ARDNACRUSHA GIS 110-ARDNACRUSHA GIS 110-110SB1-3CB | 9 | 7 | 7 | Proposed | 11/06/2026 | 19/06/2026
TO-26-AA GIS-T103-01 | GENERATOR TRANSFORMER - ARDNACRUSHA GIS 110-ARDNACRUSHA GIS G3-T103 | 9 | 7 | 7 | Proposed | 11/06/2026 | 19/06/2026
TO-26-PHT-131-02 | GENERATOR TRANSFORMER - PHILIPSTOWN 110-PHILIPSTOWN 33-T131 | 1 | 1 | 1 | Scheduled | 11/06/2026 | 11/06/2026
TO-26-220 kV A1 @ FIN-06 | BUSBAR SECTION - FINGLAS 220-FINGLAS 220-220A1 | 13 | 9 | 9 | Scheduled | 12/06/2026 | 24/06/2026
TO-26-220 kV B1 @ FIN-06 | BUSBAR SECTION - FINGLAS 220-FINGLAS 220-220B1 | 13 | 9 | 9 | Scheduled | 12/06/2026 | 24/06/2026
TO-26-FIN-220K1-05 | COUPLER/SECTIONALISING CB - FINGLAS 220-FINGLAS 220-220K1 | 13 | 9 | 9 | Scheduled | 12/06/2026 | 24/06/2026
TO-26-FIN-220SA1-2CB-15 | COUPLER/SECTIONALISING CB - FINGLAS 220-FINGLAS 220-220SA1-2CB | 13 | 9 | 9 | Scheduled | 12/06/2026 | 24/06/2026
TO-26-FIN-220SB1-2CB-12 | COUPLER/SECTIONALISING CB - FINGLAS 220-FINGLAS 220-220SB1-2CB | 13 | 9 | 9 | Scheduled | 12/06/2026 | 24/06/2026
TO-26-220 kV A1 @ ISH-01 | BUSBAR SECTION - IRISHTOWN 220-IRISHTOWN 220-220A1 | 8 | 6 | 6 | Proposed | 12/06/2026 | 19/06/2026
TO-26-220 kV B1 @ ISH-01 | BUSBAR SECTION - IRISHTOWN 220-IRISHTOWN 220-220B1 | 8 | 6 | 6 | Proposed | 12/06/2026 | 19/06/2026
TO-26-ISH-T2001-02 | GENERATOR TRANSFORMER - IRISHTOWN 220-IRISHTOWN G1-T2001 | 8 | 6 | 6 | Proposed | 12/06/2026 | 19/06/2026
TO-26-ARK-110K1-2-03 | COUPLER/SECTIONALISING CB - ARKLOW 110-ARKLOW 110-110K1-2 | 5 | 5 | 5 | Proposed | 15/06/2026 | 19/06/2026
TO-26-ATE-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - ATHEA 110-ATHEA 110-110SA1-2CB | 5 | 5 | 5 | Proposed | 15/06/2026 | 19/06/2026
TO-26-ATE-DRO-1-01 | 110kV FEEDER - ATHEA 110-DROMADA 110-1 | 5 | 5 | 5 | Proposed | 15/06/2026 | 19/06/2026
TO-26-ATE-KNR-1-01 | 110kV FEEDER - ATHEA 110-KNOCKANURE 110-1 | 5 | 5 | 5 | Proposed | 15/06/2026 | 19/06/2026
TO-26-ATE-T121-02 | GENERATOR TRANSFORMER - ATHEA 110-ATHEA 20-T121 | 5 | 5 | 5 | Scheduled | 15/06/2026 | 19/06/2026
TO-26-ATE-TOB-1-01 | 110kV FEEDER - ATHEA 110-TOBERTOREEN 110-1 | 5 | 5 | 5 | Proposed | 15/06/2026 | 19/06/2026
TO-26-ATH-T142-08 | DISTRIBUTION TRANSFORMER - ATHLONE 110-ATHLONE 38-T142 | 2 | 2 | 2 | Reference (Proposed) | 15/06/2026 | 16/06/2026
TO-26-BVK-T2102-02 | TRANSFORMER - BALLYVOUSKILL 220-BALLYVOUSKILL 110-T2102 | 5 | 5 | 5 | Proposed | 15/06/2026 | 19/06/2026
TO-26-BAN-CAP1-01 | CAPACITOR/SVC/REACTOR - BANDON 110-BANDON 110-CAP1 | 5 | 5 | 5 | Proposed | 15/06/2026 | 19/06/2026
TO-26-DYN-T121-01 | GENERATOR TRANSFORMER - DERRYBRIEN 110-DERRYBRIEN 20-T121 | 5 | 5 | 5 | Reference | 15/06/2026 | 19/06/2026
TO-26-DRO-T121-01 | GENERATOR TRANSFORMER - DROMADA 110-DROMADA 20-T121 | 5 | 5 | 5 | Proposed | 15/06/2026 | 19/06/2026
TO-26-DJG-KPG-1-01 | 110kV FEEDER - DROMBEG 110-KILPADDOGE 110-1 | 5 | 5 | 5 | Proposed | 15/06/2026 | 19/06/2026
TO-26-220 kV A2 @ FIN-08 | BUSBAR SECTION - FINGLAS 220-FINGLAS 220-220A2 | 12 | 10 | 10 | Scheduled | 15/06/2026 | 26/06/2026
TO-26-220 kV B2 @ FIN-06 | BUSBAR SECTION - FINGLAS 220-FINGLAS 220-220B2 | 12 | 10 | 10 | Scheduled | 15/06/2026 | 26/06/2026
TO-26-FIN-220K2-11 | COUPLER/SECTIONALISING CB - FINGLAS 220-FINGLAS 220-220K2 | 12 | 10 | 10 | Proposed | 15/06/2026 | 26/06/2026
TO-26-FIN-220SA1-2CB-16 | COUPLER/SECTIONALISING CB - FINGLAS 220-FINGLAS 220-220SA1-2CB | 12 | 10 | 10 | Proposed | 15/06/2026 | 26/06/2026
TO-26-FIN-220SB1-2CB-13 | COUPLER/SECTIONALISING CB - FINGLAS 220-FINGLAS 220-220SB1-2CB | 12 | 10 | 10 | Proposed | 15/06/2026 | 26/06/2026
TO-26-FIN GIS-SVN-1-03 | 110kV FEEDER - FINGLAS GIS 110-STEPHENSTOWN 110-1 | 40 | 30 | 30 | Reference | 15/06/2026 | 24/07/2026
TO-26-110 kV A1 @ GLN-01 | BUSBAR SECTION - GALLANSTOWN 110-GALLANSTOWN 110-110A1 | 5 | 5 | 5 | Scheduled | 15/06/2026 | 19/06/2026
TO-26-110 kV B1 @ GLN-01 | BUSBAR SECTION - GALLANSTOWN 110-GALLANSTOWN 110-110B1 | 5 | 5 | 5 | Scheduled | 15/06/2026 | 19/06/2026
TO-26-GLN-110K1-02 | COUPLER/SECTIONALISING CB - GALLANSTOWN 110-GALLANSTOWN 110-110K1 | 5 | 5 | 5 | Scheduled | 15/06/2026 | 19/06/2026
TO-26-GLN-PLA-1-05 | 110kV FEEDER - GALLANSTOWN 110-PLATIN 110-1 | 5 | 5 | 5 | Scheduled | 15/06/2026 | 19/06/2026
TO-26-GAR-PLA-1-04 | 110kV FEEDER - GARBALLAGH 110-PLATIN 110-1 | 5 | 5 | 5 | Proposed | 15/06/2026 | 19/06/2026
TO-26-MRY-T131-01 | GENERATOR TRANSFORMER - MULREAVY 110-MULREAVY 33-T131 | 2 | 2 | 2 | Proposed | 15/06/2026 | 16/06/2026
TO-26-PLA-110SA1-05 | SECTIONALISING DISCONNECT - PLATIN 110-PLATIN 110-110SA1 | 5 | 5 | 5 | Proposed | 15/06/2026 | 19/06/2026
TO-26-PLA-110SA2-05 | SECTIONALISING DISCONNECT - PLATIN 110-PLATIN 110-110SA2 | 5 | 5 | 5 | Proposed | 15/06/2026 | 19/06/2026
TO-26-PLA-T105-02 | TSO CUSTOMER TRANSFORMER - PLATIN 110-PLATIN 10-T105 | 5 | 5 | 5 | Proposed | 15/06/2026 | 19/06/2026
TO-26-SLI-CAP1-01 | CAPACITOR/SVC/REACTOR - SLIGO 110-SLIGO 110-CAP1 | 5 | 5 | 5 | Proposed | 15/06/2026 | 19/06/2026
TO-26-TOB-T132-02 | GENERATOR TRANSFORMER - TOBERTOREEN 110-TOBERTOREEN 33-T132 | 5 | 5 | 5 | Proposed | 15/06/2026 | 19/06/2026
TO-26-TOB-T132-01 | GENERATOR TRANSFORMER - TOBERTOREEN 110-TOBERTOREEN 33-T132 | 1 | 1 | 1 | Proposed | 15/06/2026 | 15/06/2026
TO-26-CKM GIS-220SA1-2CB-01 | COUPLER/SECTIONALISING CB - CARRICKMINES GIS 220-CARRICKMINES GIS 220-220SA1-2CB | 3 | 3 | 3 | Scheduled | 16/06/2026 | 18/06/2026
TO-26-CKM GIS-220SA1-3CB-01 | COUPLER/SECTIONALISING CB - CARRICKMINES GIS 220-CARRICKMINES GIS 220-220SA1-3CB | 3 | 3 | 3 | Scheduled | 16/06/2026 | 18/06/2026
TO-26-CKM GIS-220SA2-4CB-01 | COUPLER/SECTIONALISING CB - CARRICKMINES GIS 220-CARRICKMINES GIS 220-220SA2-4CB | 3 | 3 | 3 | Scheduled | 16/06/2026 | 18/06/2026
TO-26-220 kV A2 @ CSH-01 | BUSBAR SECTION - CASHLA 220-CASHLA 220-220A2 | 11 | 9 | 9 | Proposed | 16/06/2026 | 26/06/2026
TO-26-220 kV A4 @ CSH-01 | BUSBAR SECTION - CASHLA 220-CASHLA 220-220A4 | 11 | 9 | 9 | Proposed | 16/06/2026 | 26/06/2026
TO-26-220 kV B2 @ CSH-02 | BUSBAR SECTION - CASHLA 220-CASHLA 220-220B2 | 11 | 9 | 9 | Proposed | 16/06/2026 | 26/06/2026
TO-26-220 kV B4 @ CSH-02 | BUSBAR SECTION - CASHLA 220-CASHLA 220-220B4 | 11 | 9 | 9 | Proposed | 16/06/2026 | 26/06/2026
TO-26-CSH-220K2-4-01 | COUPLER/SECTIONALISING CB - CASHLA 220-CASHLA 220-220K2-4 | 11 | 9 | 9 | Proposed | 16/06/2026 | 26/06/2026
TO-26-CBA-110SA1-01 | SECTIONALISING DISCONNECT - CLOGHBOOLA 110-CLOGHBOOLA 110-110SA1 | 17 | 13 | 13 | Proposed | 16/06/2026 | 02/07/2026
TO-26-CBA-110SA2-01 | SECTIONALISING DISCONNECT - CLOGHBOOLA 110-CLOGHBOOLA 110-110SA2 | 17 | 13 | 13 | Proposed | 16/06/2026 | 02/07/2026
TO-26-CBA-T122-01 | DISTRIBUTION TRANSFORMER - CLOGHBOOLA 110-CLOGHBOOLA 20-T122 | 17 | 13 | 13 | Reference (Proposed) | 16/06/2026 | 02/07/2026
TO-26-CBA-T131-01 | GENERATOR TRANSFORMER - CLOGHBOOLA 110-CLOGHBOOLA 33-T131 | 17 | 13 | 13 | Proposed | 16/06/2026 | 02/07/2026
TO-26-CBA-TRI-1-01 | 110kV FEEDER - CLOGHBOOLA 110-TRIEN 110-1 | 17 | 13 | 13 | Proposed | 16/06/2026 | 02/07/2026
TO-26-CRU-T223-01 | TSO CUSTOMER TRANSFORMER - CRUISERATH 220-CRUISERATH 20-T223 | 2 | 2 | 2 | Scheduled | 16/06/2026 | 17/06/2026
TO-26-DLT-CAP1-01 | CAPACITOR/SVC/REACTOR - DALTON 110-DALTON 110-CAP1 | 2 | 2 | 2 | Scheduled | 16/06/2026 | 17/06/2026
TO-26-DMY-T141-01 | DISTRIBUTION TRANSFORMER - DUNMANWAY 110-DUNMANWAY 38-T141 | 2 | 2 | 2 | Reference | 16/06/2026 | 17/06/2026
TO-26-KDN-T131-02 | GENERATOR TRANSFORMER - KNOCKDRIN 110-KNOCKDRIN 33-T131 | 1 | 1 | 1 | Scheduled | 16/06/2026 | 16/06/2026
TO-26-LYT-110K2-01 | COUPLER/SECTIONALISING CB - LYSAGHTSTOWN 110-LYSAGHTSTOWN 110-110K2 | 1 | 1 | 1 | Scheduled | 16/06/2026 | 16/06/2026
TO-26-TB-T102-01 | GENERATOR TRANSFORMER - TARBERT 110-TARBERT G2-T102 | 2 | 2 | 2 | Proposed | 16/06/2026 | 17/06/2026
TO-26-BNK-CBT-1-03 | 110kV FEEDER - BARNAKYLE 110-CASTLEBAGOT 110-1 | 7 | 5 | 5 | Proposed | 17/06/2026 | 23/06/2026
TO-26-110 kV A1 @ CBT-02 | BUSBAR SECTION - CASTLEBAGOT 110-CASTLEBAGOT 110-110A1 | 7 | 5 | 5 | Proposed | 17/06/2026 | 23/06/2026
TO-26-110 kV B1 @ CBT-02 | BUSBAR SECTION - CASTLEBAGOT 110-CASTLEBAGOT 110-110B1 | 7 | 5 | 5 | Proposed | 17/06/2026 | 23/06/2026
TO-26-CBT-110K1-04 | COUPLER/SECTIONALISING CB - CASTLEBAGOT 110-CASTLEBAGOT 110-110K1 | 7 | 5 | 5 | Proposed | 17/06/2026 | 23/06/2026
TO-26-CBT-110SA1-2CB-02 | COUPLER/SECTIONALISING CB - CASTLEBAGOT 110-CASTLEBAGOT 110-110SA1-2CB | 7 | 5 | 5 | Proposed | 17/06/2026 | 23/06/2026
TO-26-CBT-110SB1-2CB-02 | COUPLER/SECTIONALISING CB - CASTLEBAGOT 110-CASTLEBAGOT 110-110SB1-2CB | 7 | 5 | 5 | Proposed | 17/06/2026 | 23/06/2026
TO-26-STN-T131-01 | GENERATOR TRANSFORMER - STONESTOWN 110-STONESTOWN 33-T131 | 1 | 1 | 1 | Proposed | 17/06/2026 | 17/06/2026
TO-26-AD-GGO-1-01 | 220kV FEEDER - AGHADA 220-GLANAGOW 220-1 | 12 | 10 |  | Proposed | 22/06/2026 | 03/07/2026
TO-26-AD-GGO-1-02 | 220kV FEEDER - AGHADA 220-GLANAGOW 220-1 | 2 | 2 | 2 | Scheduled | 22/06/2026 | 23/06/2026
TO-26-AA GIS-CAP1-02 | CAPACITOR/SVC/REACTOR - ARDNACRUSHA GIS 110-ARDNACRUSHA GIS 110-CAP1 | 10 | 8 | 8 | Proposed | 22/06/2026 | 01/07/2026
TO-26-BAR-T141-04 | DISTRIBUTION TRANSFORMER - BARRYMORE 110-BARRYMORE 38-T141 | 9 | 7 | 7 | Reference (Proposed) | 22/06/2026 | 30/06/2026
TO-26-BAR,T-BAR-1-04 | 110kV FEEDER - BARRYMORE tee-BARRYMORE 110-1 | 9 | 7 | 7 | Proposed | 22/06/2026 | 30/06/2026
TO-26-BAR,T-CAH-1-05 | 110kV FEEDER - BARRYMORE tee-CAHIR 110-1 | 9 | 7 | 7 | Proposed | 22/06/2026 | 30/06/2026
TO-26-BAR,T-KRA-1-05 | 110kV FEEDER - BARRYMORE tee-KNOCKRAHA 110-1 | 9 | 7 | 7 | Proposed | 22/06/2026 | 30/06/2026
TO-26-110 kV A3 @ CDU-01 | BUSBAR SECTION - CORDUFF 110-CORDUFF 110-110A3 | 9 | 7 | 7 | Proposed | 22/06/2026 | 30/06/2026
TO-26-110 kV B3 @ CDU-01 | BUSBAR SECTION - CORDUFF 110-CORDUFF 110-110B3 | 9 | 7 | 7 | Proposed | 22/06/2026 | 30/06/2026
TO-26-CDU-SNU-1-01 | 110kV FEEDER - CORDUFF 110-SNUGBOROUGH 110-1 | 9 | 7 | 7 | Proposed | 22/06/2026 | 30/06/2026
TO-26-FLA-T2102-02 | TRANSFORMER - FLAGFORD 220-FLAGFORD 110-T2102 | 5 | 5 | 5 | Proposed | 22/06/2026 | 26/06/2026
TO-26-GI GIS-LON-1-02 | 220kV FEEDER - GREAT ISLAND GIS 220-LOUGHTOWN 220-1 | 24 | 18 | 18 | Proposed | 22/06/2026 | 15/07/2026
TO-26-220 kV A1 @ KLN-01 | BUSBAR SECTION - KILLONAN 220-KILLONAN 220-220A1 | 26 | 20 | 20 | Proposed | 22/06/2026 | 17/07/2026
TO-26-220 kV A2 @ KLN-02 | BUSBAR SECTION - KILLONAN 220-KILLONAN 220-220A2 | 26 | 20 | 20 | Proposed | 22/06/2026 | 17/07/2026
TO-26-KLN-220K1-2-01 | COUPLER/SECTIONALISING CB - KILLONAN 220-KILLONAN 220-220K1-2 | 26 | 20 | 20 | Proposed | 22/06/2026 | 17/07/2026
TO-26-KPG-T122-01 | DISTRIBUTION TRANSFORMER - KILPADDOGE 110-KILPADDOGE 20-T122 | 5 | 5 | 5 | Reference | 22/06/2026 | 26/06/2026
TO-26-110 kV B2 @ MAY-01 | BUSBAR SECTION - MAYNOOTH 110-MAYNOOTH 110-110B2 | 12 | 10 | 10 | Proposed | 22/06/2026 | 03/07/2026
TO-26-220 kV A1 @ MAY-02 | BUSBAR SECTION - MAYNOOTH 220-MAYNOOTH 220-220A1 | 12 | 10 | 10 | Proposed | 22/06/2026 | 03/07/2026
TO-26-220 kV B1 @ MAY-02 | BUSBAR SECTION - MAYNOOTH 220-MAYNOOTH 220-220B1 | 12 | 10 | 10 | Proposed | 22/06/2026 | 03/07/2026
TO-26-MAY-T2102-01 | TRANSFORMER - MAYNOOTH 220-MAYNOOTH 110-T2102 | 12 | 10 | 10 | Proposed | 22/06/2026 | 03/07/2026
TO-26-110 kV A2 @ SNU-02 | BUSBAR SECTION - SNUGBOROUGH 110-SNUGBOROUGH 110-110A2 | 9 | 7 | 7 | Proposed | 22/06/2026 | 30/06/2026
TO-26-110 kV B2 @ SNU-02 | BUSBAR SECTION - SNUGBOROUGH 110-SNUGBOROUGH 110-110B2 | 9 | 7 | 7 | Proposed | 22/06/2026 | 30/06/2026
TO-26-SNU-110K2-06 | COUPLER/SECTIONALISING CB - SNUGBOROUGH 110-SNUGBOROUGH 110-110K2 | 9 | 7 | 7 | Proposed | 22/06/2026 | 30/06/2026
TO-26-SNU-110SA1-2CB-05 | COUPLER/SECTIONALISING CB - SNUGBOROUGH 110-SNUGBOROUGH 110-110SA1-2CB | 9 | 7 | 7 | Proposed | 22/06/2026 | 30/06/2026
TO-26-SNU-110SB1-2CB-02 | COUPLER/SECTIONALISING CB - SNUGBOROUGH 110-SNUGBOROUGH 110-110SB1-2CB | 9 | 7 | 7 | Proposed | 22/06/2026 | 30/06/2026
TO-26-AA GIS-110K2-01 | COUPLER/SECTIONALISING CB - ARDNACRUSHA GIS 110-ARDNACRUSHA GIS 110-110K2 | 2 | 2 | 2 | Proposed | 23/06/2026 | 24/06/2026
TO-26-110 kV A2 @ ARK-01 | BUSBAR SECTION - ARKLOW 110-ARKLOW 110-110A2 | 18 | 14 | 14 | Scheduled | 23/06/2026 | 10/07/2026
TO-26-110 kV B2 @ ARK-01 | BUSBAR SECTION - ARKLOW 110-ARKLOW 110-110B2 | 18 | 14 | 14 | Scheduled | 23/06/2026 | 10/07/2026
TO-26-220 kV A2 @ ARK-02 | BUSBAR SECTION - ARKLOW 220-ARKLOW 220-220A2 | 18 | 14 | 14 | Scheduled | 23/06/2026 | 10/07/2026
TO-26-220 kV B2 @ ARK-02 | BUSBAR SECTION - ARKLOW 220-ARKLOW 220-220B2 | 18 | 14 | 14 | Scheduled | 23/06/2026 | 10/07/2026
TO-26-ARK-T2102-01 | TRANSFORMER - ARKLOW 220-ARKLOW 110-T2102 | 18 | 14 | 14 | Scheduled | 23/06/2026 | 10/07/2026
TO-26-CKM GIS-220SB1-2CB-01 | COUPLER/SECTIONALISING CB - CARRICKMINES GIS 220-CARRICKMINES GIS 220-220SB1-2CB | 3 | 3 | 3 | Scheduled | 23/06/2026 | 25/06/2026
TO-26-CKM GIS-220SB1-3CB-01 | COUPLER/SECTIONALISING CB - CARRICKMINES GIS 220-CARRICKMINES GIS 220-220SB1-3CB | 3 | 3 | 3 | Scheduled | 23/06/2026 | 25/06/2026
TO-26-CKM GIS-220SB2-4CB-01 | COUPLER/SECTIONALISING CB - CARRICKMINES GIS 220-CARRICKMINES GIS 220-220SB2-4CB | 3 | 3 | 3 | Scheduled | 23/06/2026 | 25/06/2026
TO-26-CDU-T2104-02 | TRANSFORMER - CORDUFF 220-CORDUFF 110-T2104 | 2 | 2 | 2 | Scheduled | 23/06/2026 | 24/06/2026
TO-26-FIN GIS-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110SA1-2CB | 10 | 8 | 8 | Proposed | 23/06/2026 | 02/07/2026
TO-26-LOU-RRU-1-05 | 110kV FEEDER - LOUTH 110-RATRUSSAN 110-1 | 3 | 3 | 3 | Proposed | 23/06/2026 | 25/06/2026
TO-26-CDL-T132-01 | GENERATOR TRANSFORMER - CORDAL 110-CORDAL 33-T132 | 1 | 1 | 1 | Proposed | 26/06/2026 | 26/06/2026
TO-26-AGP-T141-01 | DISTRIBUTION TRANSFORMER - ARDNAGAPPARY 110-ARDNAGAPPARY 38-T141 | 11 | 9 | 9 | Reference (Proposed) | 29/06/2026 | 09/07/2026
TO-26-AGP-TIV-1-01 | 110kV FEEDER - ARDNAGAPPARY 110-TIEVEBRACK 110-1 | 11 | 9 | 9 | Reference (Proposed) | 29/06/2026 | 09/07/2026
TO-26-BVK-COT-1-01 | 110kV FEEDER - BALLYVOUSKILL 110-COOMATAGGART 110-1 | 12 | 10 |  | Proposed | 29/06/2026 | 10/07/2026
TO-26-BAL-110SA1-04 | SECTIONALISING DISCONNECT - BALTRASNA 110-BALTRASNA 110-110SA1 | 4 | 4 | 4 | Proposed | 29/06/2026 | 02/07/2026
TO-26-BAL-110SA2-05 | SECTIONALISING DISCONNECT - BALTRASNA 110-BALTRASNA 110-110SA2 | 4 | 4 | 4 | Proposed | 29/06/2026 | 02/07/2026
TO-26-BAL-DEN-1-01 | 110kV FEEDER - BALTRASNA 110-DEENES 110-1 | 4 | 4 | 4 | Proposed | 29/06/2026 | 02/07/2026
TO-26-BAL-T121-02 | DISTRIBUTION TRANSFORMER - BALTRASNA 110-BALTRASNA 20-T121 | 4 | 4 | 4 | Reference (Proposed) | 29/06/2026 | 02/07/2026
TO-26-BIN-TIV-1-01 | 110kV FEEDER - BINBANE 110-TIEVEBRACK 110-1 | 11 | 9 | 9 | Proposed | 29/06/2026 | 09/07/2026
TO-26-BOL-110SA1-01 | SECTIONALISING DISCONNECT - BOOLTIAGH 110-BOOLTIAGH 110-110SA1 | 9 | 7 | 7 | Proposed | 29/06/2026 | 07/07/2026
TO-26-BOL-110SA1-3CB-01 | COUPLER/SECTIONALISING CB - BOOLTIAGH 110-BOOLTIAGH 110-110SA1-3CB | 9 | 7 | 7 | Proposed | 29/06/2026 | 07/07/2026
TO-26-BOL-T121-01 | GENERATOR TRANSFORMER - BOOLTIAGH 110-BOOLTIAGH 20-T121 | 9 | 7 | 7 | Proposed | 29/06/2026 | 07/07/2026
TO-26-CGG-DMY-1-01 | 110kV FEEDER - CARRIGDANGAN 110-DUNMANWAY 110-1 | 12 | 10 | 10 | Proposed | 29/06/2026 | 10/07/2026
TO-26-CGG-T131-01 | GENERATOR TRANSFORMER - CARRIGDANGAN 110-CARRIGDANGAN 33-T131 | 12 | 10 | 10 | Proposed | 29/06/2026 | 10/07/2026
TO-26-CBT-220K2-01 | COUPLER/SECTIONALISING CB - CASTLEBAGOT 220-CASTLEBAGOT 220-220K2 | 4 | 4 | 4 | Proposed | 29/06/2026 | 02/07/2026
TO-26-COT-110SA1-01 | SECTIONALISING DISCONNECT - COOMATAGGART 110-COOMATAGGART 110-110SA1 | 12 | 10 | 10 | Proposed | 29/06/2026 | 10/07/2026
TO-26-COT-110SA2-01 | SECTIONALISING DISCONNECT - COOMATAGGART 110-COOMATAGGART 110-110SA2 | 12 | 10 | 10 | Proposed | 29/06/2026 | 10/07/2026
TO-26-COT-FILTER1-01 | CAPACITOR/SVC/REACTOR - COOMATAGGART 110-COOMATAGGART 110-FILTER1 | 12 | 10 | 10 | Proposed | 29/06/2026 | 10/07/2026
TO-26-COT-T132-01 | GENERATOR TRANSFORMER - COOMATAGGART 110-COOMATAGGART 33-T132 | 5 | 5 | 5 | Proposed | 29/06/2026 | 03/07/2026
TO-26-COT-T132-02 | GENERATOR TRANSFORMER - COOMATAGGART 110-COOMATAGGART 33-T132 | 12 | 10 | 10 | Proposed | 29/06/2026 | 10/07/2026
TO-26-COT-T141-01 | DISTRIBUTION TRANSFORMER - COOMATAGGART 110-COOMATAGGART 38-T141 | 12 | 10 | 10 | Reference (Proposed) | 29/06/2026 | 10/07/2026
TO-26-DSN-MAY-1-01 | 220kV FEEDER - DUNSTOWN 220-MAYNOOTH 220-1 | 12 | 10 | 10 | Proposed | 29/06/2026 | 10/07/2026
TO-26-220 kV A1 @ INC-01 | BUSBAR SECTION - INCHICORE 220-INCHICORE 220-220A1 | 9 | 7 | 7 | Proposed | 29/06/2026 | 07/07/2026
TO-26-220 kV B1 @ INC-02 | BUSBAR SECTION - INCHICORE 220-INCHICORE 220-220B1 | 9 | 7 | 7 | Proposed | 29/06/2026 | 07/07/2026
TO-26-INC-PB-1-07 | 220kV FEEDER - INCHICORE 220-POOLBEG 220-1 | 33 | 25 | 25 | Proposed | 29/06/2026 | 31/07/2026
TO-26-KYT-T233-01 | TSO CUSTOMER TRANSFORMER - KELLYSTOWN 220-KELLYSTOWN 34.5-T233 | 2 | 2 | 2 | Proposed | 29/06/2026 | 30/06/2026
TO-26-110 kV A1 @ KBY-06 | BUSBAR SECTION - KILBARRY 110-KILBARRY 110-110A1 | 26 | 20 | 20 | Proposed | 29/06/2026 | 24/07/2026
TO-26-110 kV A2 @ KBY-01 | BUSBAR SECTION - KILBARRY 110-KILBARRY 110-110A2 | 26 | 20 | 20 | Proposed | 29/06/2026 | 24/07/2026
TO-26-110 kV B1 @ KBY-05 | BUSBAR SECTION - KILBARRY 110-KILBARRY 110-110B1 | 26 | 20 | 20 | Proposed | 29/06/2026 | 24/07/2026
TO-26-110 kV B2 @ KBY-01 | BUSBAR SECTION - KILBARRY 110-KILBARRY 110-110B2 | 26 | 20 | 20 | Proposed | 29/06/2026 | 24/07/2026
TO-26-KBY-110K1-2-01 | COUPLER/SECTIONALISING CB - KILBARRY 110-KILBARRY 110-110K1-2 | 26 | 20 | 20 | Proposed | 29/06/2026 | 24/07/2026
TO-26-KPG-MP GIS-1-02 | 220kV FEEDER - KILPADDOGE 220-MONEYPOINT GIS 220-1 | 12 | 10 | 10 | Proposed | 29/06/2026 | 10/07/2026
TO-26-LOU-T2102-07 | TRANSFORMER - LOUTH 220-LOUTH 110-T2102 | 10 | 8 | 8 | Proposed | 29/06/2026 | 08/07/2026
TO-26-220 kV A1 @ PB-02 | BUSBAR SECTION - POOLBEG 220-POOLBEG 220-220A1 | 9 | 7 | 7 | Proposed | 29/06/2026 | 07/07/2026
TO-26-220 kV B1 @ PB-03 | BUSBAR SECTION - POOLBEG 220-POOLBEG 220-220B1 | 9 | 7 | 7 | Proposed | 29/06/2026 | 07/07/2026
TO-26-110 kV A2 @ RAF-03 | BUSBAR SECTION - RAFFEEN 110-RAFFEEN 110-110A2 | 12 | 10 | 10 | Proposed | 29/06/2026 | 10/07/2026
TO-26-110 kV B2 @ RAF-05 | BUSBAR SECTION - RAFFEEN 110-RAFFEEN 110-110B2 | 12 | 10 | 10 | Proposed | 29/06/2026 | 10/07/2026
TO-26-RAF-CAP2-02 | CAPACITOR/SVC/REACTOR - RAFFEEN 110-RAFFEEN 110-CAP2 | 12 | 10 | 10 | Proposed | 29/06/2026 | 10/07/2026
TO-26-SK-T104-04 | GENERATOR TRANSFORMER - SEALROCK 110-SEALROCK G4-T104 | 5 | 5 | 5 | Proposed | 29/06/2026 | 03/07/2026
TO-26-TIV-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - TIEVEBRACK 110-TIEVEBRACK 110-110SA1-2CB | 11 | 9 | 9 | Proposed | 29/06/2026 | 09/07/2026
TO-26-TBK-T141-01 | DISTRIBUTION TRANSFORMER - TULLABRACK 110-TULLABRACK 38-T141 | 9 | 7 | 7 | Reference (Proposed) | 29/06/2026 | 07/07/2026
TO-26-TBK,T-BOL-1-01 | 110kV FEEDER - TULLABRACK tee-BOOLTIAGH 110-1 | 9 | 7 | 7 | Proposed | 29/06/2026 | 07/07/2026
TO-26-TBK,T-MP GIS-1-01 | 110kV FEEDER - TULLABRACK tee-MONEYPOINT GIS 110-1 | 9 | 7 | 7 | Proposed | 29/06/2026 | 07/07/2026
TO-26-TBK,T-TBK-1-01 | 110kV FEEDER - TULLABRACK tee-TULLABRACK 110-1 | 9 | 7 | 7 | Proposed | 29/06/2026 | 07/07/2026
TO-26-GWE-CAP1-01 | CAPACITOR/SVC/REACTOR - GORTAWEE 110-GORTAWEE 110-CAP1 | 10 | 8 | 8 | Proposed | 30/06/2026 | 09/07/2026
TO-26-AUG-SK-4-02 | 110kV FEEDER - AUGHINISH 110-SEALROCK 110-4 | 3 | 3 | 3 | Proposed | 01/07/2026 | 03/07/2026
TO-26-GAL GIS-KNY-1-01 | 110kV FEEDER - GALWAY GIS 110-KNOCKRANNY 110-1 | 2 | 2 | 2 | Proposed | 01/07/2026 | 02/07/2026
TO-26-KHL-THU-1-02 | 110kV FEEDER - KILL HILL 110-THURLES 110-1 | 2 | 2 | 2 | Proposed | 01/07/2026 | 02/07/2026
TO-26-SK-T104-02 | GENERATOR TRANSFORMER - SEALROCK 110-SEALROCK G4-T104 | 3 | 3 | 3 | Proposed | 01/07/2026 | 03/07/2026
TO-26-BK-110SA1-02 | SECTIONALISING DISCONNECT - BELLACORICK 110-BELLACORICK 110-110SA1 | 5 | 5 | 5 | Proposed | 06/07/2026 | 10/07/2026
TO-26-COS-FLA-1-01 | 110kV FEEDER - CARRICK ON SHANNON 110-FLAGFORD 110-1 | 5 | 5 | 5 | Proposed | 06/07/2026 | 10/07/2026
TO-26-110 kV A4 @ CBT-03 | BUSBAR SECTION - CASTLEBAGOT 110-CASTLEBAGOT 110-110A4 | 12 | 10 | 10 | Proposed | 06/07/2026 | 17/07/2026
TO-26-110 kV B4 @ CBT-03 | BUSBAR SECTION - CASTLEBAGOT 110-CASTLEBAGOT 110-110B4 | 12 | 10 | 10 | Proposed | 06/07/2026 | 17/07/2026
TO-26-CBT-110K4-04 | COUPLER/SECTIONALISING CB - CASTLEBAGOT 110-CASTLEBAGOT 110-110K4 | 12 | 10 | 10 | Proposed | 06/07/2026 | 17/07/2026
TO-26-CBT-110SA2-4CB-03 | COUPLER/SECTIONALISING CB - CASTLEBAGOT 110-CASTLEBAGOT 110-110SA2-4CB | 12 | 10 | 10 | Proposed | 06/07/2026 | 17/07/2026
TO-26-CBT-110SB2-4CB-04 | COUPLER/SECTIONALISING CB - CASTLEBAGOT 110-CASTLEBAGOT 110-110SB2-4CB | 12 | 10 | 10 | Proposed | 06/07/2026 | 17/07/2026
TO-26-220 kV A2 @ CBT-01 | BUSBAR SECTION - CASTLEBAGOT 220-CASTLEBAGOT 220-220A2 | 12 | 10 | 10 | Proposed | 06/07/2026 | 17/07/2026
TO-26-220 kV B2 @ CBT-01 | BUSBAR SECTION - CASTLEBAGOT 220-CASTLEBAGOT 220-220B2 | 12 | 10 | 10 | Proposed | 06/07/2026 | 17/07/2026
TO-26-CBT-220K2-02 | COUPLER/SECTIONALISING CB - CASTLEBAGOT 220-CASTLEBAGOT 220-220K2 | 12 | 10 | 10 | Proposed | 06/07/2026 | 17/07/2026
TO-26-CBT-220SA1-2CB-02 | COUPLER/SECTIONALISING CB - CASTLEBAGOT 220-CASTLEBAGOT 220-220SA1-2CB | 12 | 10 | 10 | Proposed | 06/07/2026 | 17/07/2026
TO-26-CBT-220SB1-2CB-02 | COUPLER/SECTIONALISING CB - CASTLEBAGOT 220-CASTLEBAGOT 220-220SB1-2CB | 12 | 10 | 10 | Proposed | 06/07/2026 | 17/07/2026
TO-26-CBT-T2104-01 | TRANSFORMER - CASTLEBAGOT 220-CASTLEBAGOT 110-T2104 | 12 | 10 | 10 | Proposed | 06/07/2026 | 17/07/2026
TO-26-CF-CL-1-03 | 110kV FEEDER - CATHALEENS FALL 110-CLIFF 110-1 | 12 | 10 | 10 | Proposed | 06/07/2026 | 17/07/2026
TO-26-CLH-TRL-1-02 | 110kV FEEDER - CLAHANE 110-TRALEE 110-1 | 12 | 10 | 10 | Proposed | 06/07/2026 | 17/07/2026
TO-26-CL-T101-02 | GENERATOR TRANSFORMER - CLIFF 110-CLIFF G1-T101 | 12 | 10 | 10 | Proposed | 06/07/2026 | 17/07/2026
TO-26-CL-T102-03 | GENERATOR TRANSFORMER - CLIFF 110-CLIFF G2-T102 | 12 | 10 | 10 | Proposed | 06/07/2026 | 17/07/2026
TO-26-CFN-SH-1-01 | 220kV FEEDER - CLONIFFEEN 220-SHANNONBRIDGE 220-1 | 5 | 5 | 5 | Proposed | 06/07/2026 | 10/07/2026
TO-26-CFN-T232-01 | GENERATOR TRANSFORMER - CLONIFFEEN 220-CLONIFFEEN 33-T232 | 5 | 5 | 5 | Proposed | 06/07/2026 | 10/07/2026
TO-26-CUS-T101-01 | GENERATOR TRANSFORMER - CUSHALING 110-CUSHALING G1-T101 | 1 | 1 | 1 | Proposed | 06/07/2026 | 06/07/2026
TO-26-DRU-CAP2-01 | CAPACITOR/SVC/REACTOR - DRUMLINE 110-DRUMLINE 110-CAP2 | 10 | 8 | 8 | Proposed | 06/07/2026 | 15/07/2026
TO-26-FIN GIS-110SB2-4CB-03 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110SB2-4CB | 10 | 8 | 8 | Proposed | 06/07/2026 | 15/07/2026
TO-26-110 kV A2 @ FLA-01 | BUSBAR SECTION - FLAGFORD 110-FLAGFORD 110-110A2 | 5 | 5 | 5 | Proposed | 06/07/2026 | 10/07/2026
TO-26-110 kV B2 @ FLA-01 | BUSBAR SECTION - FLAGFORD 110-FLAGFORD 110-110B2 | 5 | 5 | 5 | Proposed | 06/07/2026 | 10/07/2026
TO-26-IKE-T141-01 | DISTRIBUTION TRANSFORMER - IKERRIN 110-IKERRIN 38-T141 | 5 | 5 | 5 | Reference (Proposed) | 06/07/2026 | 10/07/2026
TO-26-IKE,T-IKE-1-01 | 110kV FEEDER - IKERRIN tee-IKERRIN 110-1 | 5 | 5 | 5 | Proposed | 06/07/2026 | 10/07/2026
TO-26-IKE,T-TMY1-01 | 110kV FEEDER - IKERRIN tee-TIMONEY 110-1 | 5 | 5 | 5 | Proposed | 06/07/2026 | 10/07/2026
TO-26-220 kV A2/A4 @ INC-01 | BUSBAR SECTION - INCHICORE 220-INCHICORE 220-220A2-A4 | 12 | 10 | 10 | Proposed | 06/07/2026 | 17/07/2026
TO-26-220 kV B2/B4 @ INC-01 | BUSBAR SECTION - INCHICORE 220-INCHICORE 220-220B2-B4 | 12 | 10 | 10 | Proposed | 06/07/2026 | 17/07/2026
TO-26-INC-220K2-4-01 | COUPLER/SECTIONALISING CB - INCHICORE 220-INCHICORE 220-220K2-4 | 12 | 10 | 10 | Proposed | 06/07/2026 | 17/07/2026
TO-26-KLN-LIM-1-02 | 110kV FEEDER - KILLONAN 110-LIMERICK 110-1 | 12 | 10 | 10 | Proposed | 06/07/2026 | 17/07/2026
TO-26-KNR-T2102-01 | TRANSFORMER - KNOCKANURE 220-KNOCKANURE 110-T2102 | 11 | 9 | 9 | Proposed | 06/07/2026 | 16/07/2026
TO-26-KRA-220SA2-4CB-05 | COUPLER/SECTIONALISING CB - KNOCKRAHA 220-KNOCKRAHA 220-220SA2-4CB | 5 | 5 | 5 | Proposed | 06/07/2026 | 10/07/2026
TO-26-KRA-T2102-01 | TRANSFORMER - KNOCKRAHA 220-KNOCKRAHA 110-T2102 | Unknown | Unknown | 7 | Planned | July | July
TO-26-LIS-CAP1-04 | CAPACITOR/SVC/REACTOR - LISDRUM 110-LISDRUM 110-CAP1 | 11 | 9 | 9 | Proposed | 06/07/2026 | 16/07/2026
TO-26-NW-T2004/5-01 | GENERATOR TRANSFORMER - NORTH WALL 220-NORTH WALL G4/5-T2004/5 | 2 | 2 |  | Proposed | 06/07/2026 | 07/07/2026
TO-26-REM-110SA1-01 | SECTIONALISING DISCONNECT - REAMORE 110-REAMORE 110-110SA1 | 19 | 15 | 15 | Proposed | 06/07/2026 | 24/07/2026
TO-26-REM-110SA2-01 | SECTIONALISING DISCONNECT - REAMORE 110-REAMORE 110-110SA2 | 19 | 15 | 15 | Proposed | 06/07/2026 | 24/07/2026
TO-26-REM-T141-01 | DISTRIBUTION TRANSFORMER - REAMORE 110-REAMORE 38-T141 | 19 | 15 | 15 | Reference (Proposed) | 06/07/2026 | 24/07/2026
TO-26-REM-T142-01 | DISTRIBUTION TRANSFORMER - REAMORE 110-REAMORE 38-T142 | 19 | 15 | 15 | Reference (Proposed) | 06/07/2026 | 24/07/2026
TO-26-REM-TRL-1-01 | 110kV FEEDER - REAMORE 110-TRALEE 110-1 | 19 | 15 |  | Proposed | 06/07/2026 | 24/07/2026
TO-26-220 kV A2 @ SH-02 | BUSBAR SECTION - SHANNONBRIDGE 220-SHANNONBRIDGE 220-220A2 | 5 | 5 | 5 | Proposed | 06/07/2026 | 10/07/2026
TO-26-220 kV B2 @ SH-02 | BUSBAR SECTION - SHANNONBRIDGE 220-SHANNONBRIDGE 220-220B2 | 5 | 5 | 5 | Proposed | 06/07/2026 | 10/07/2026
TO-26-DGY-FIN GIS-1-01 | 110kV FEEDER - DUNSOGHLY 110-FINGLAS GIS 110-1 | 3 | 3 | 3 | Proposed | 07/07/2026 | 09/07/2026
TO-26-DGY-T101-01 | GENERATOR TRANSFORMER - DUNSOGHLY 110-DUNSOGHLY 11-T101 | 3 | 3 | 3 | Proposed | 07/07/2026 | 09/07/2026
TO-26-ENN-SLC-1-02 | 110kV FEEDER - ENNIS 110-SLIEVECALLAN 110-1 | 2 | 2 | 2 | Proposed | 07/07/2026 | 08/07/2026
TO-26-MUL-CAP2-02 | CAPACITOR/SVC/REACTOR - MULLINGAR 110-MULLINGAR 110-CAP2 | 3 | 3 | 3 | Proposed | 07/07/2026 | 09/07/2026
TO-26-RYB GIS-T103-01 | TSO CUSTOMER TRANSFORMER - RYEBROOK GIS 110-RYEBROOK 10-T103 | 3 | 3 | 3 | Proposed | 07/07/2026 | 09/07/2026
TO-26-SLC-110SA2-02 | SECTIONALISING DISCONNECT - SLIEVECALLAN 110-SLIEVECALLAN 110-110SA2 | 2 | 2 | 2 | Proposed | 07/07/2026 | 08/07/2026
TO-26-SLC-T121-02 | GENERATOR TRANSFORMER - SLIEVECALLAN 110-SLIEVECALLAN 20-T121 | 2 | 2 | 2 | Proposed | 07/07/2026 | 08/07/2026
TO-26-SLC-T122-02 | GENERATOR TRANSFORMER - SLIEVECALLAN 110-SLIEVECALLAN 20-T122 | 2 | 2 | 2 | Proposed | 07/07/2026 | 08/07/2026
TO-26-SLC-T122-03 | GENERATOR TRANSFORMER - SLIEVECALLAN 110-SLIEVECALLAN 20-T122 | 2 | 2 | 2 | Proposed | 07/07/2026 | 08/07/2026
TO-26-IA-T101-02 | GENERATOR TRANSFORMER - INNISCARRA 110-INNISCARRA G1-T101 | 1 | 1 | 1 | Proposed | 08/07/2026 | 08/07/2026
TO-26-KYT-T237-03 | TSO CUSTOMER TRANSFORMER - KELLYSTOWN 220-KELLYSTOWN 34.5-T237 | 34 | 23 | 23 | Proposed | 08/07/2026 | 10/08/2026
TO-26-KRA-LYT-1-02 | 110kV FEEDER - KNOCKRAHA 110-LYSAGHTSTOWN 110-1 | 50 | 35 | 35 | Proposed | 08/07/2026 | 26/08/2026
TO-26-SLC-110SA1-02 | SECTIONALISING DISCONNECT - SLIEVECALLAN 110-SLIEVECALLAN 110-110SA1 | 2 | 2 | 2 | Proposed | 08/07/2026 | 09/07/2026
TO-26-BDN-MRK3-03 | TSO CUSTOMER TRANSFORMER - BALLYDINE 110-BALLYDINE 10-MRK3 | 9 | 7 | 7 | Proposed | 09/07/2026 | 17/07/2026
TO-26-BDN-110SA2-01 | SECTIONALISING DISCONNECT - BALLYDINE 110-BALLYDINE 110-110SA2 | 4 | 4 | 4 | Proposed | 13/07/2026 | 16/07/2026
TO-26-BDN-DOO-1-05 | 110kV FEEDER - BALLYDINE 110-DOON 110-1 | 4 | 4 | 4 | Proposed | 13/07/2026 | 16/07/2026
TO-26-BDN-MRK3-01 | TSO CUSTOMER TRANSFORMER - BALLYDINE 110-BALLYDINE 10-MRK3 | 4 | 4 | 4 | Proposed | 13/07/2026 | 16/07/2026
TO-26-CAH-CAP1/3-01 | CAPACITOR/SVC/REACTOR - CAHIR 110-CAHIR 110-CAP1/3 | 5 | 5 | 5 | Proposed | 13/07/2026 | 17/07/2026
TO-26-KPG-TB-1-03 | 220kV FEEDER - KILPADDOGE 220-TARBERT 220-1 | 9 | 7 | 7 | Proposed | 13/07/2026 | 21/07/2026
TO-26-KRA-220SB2-4CB-05 | COUPLER/SECTIONALISING CB - KNOCKRAHA 220-KNOCKRAHA 220-220SB2-4CB | 5 | 5 | 5 | Proposed | 13/07/2026 | 17/07/2026
TO-26-KNY-UGL-1-01 | 110kV FEEDER - KNOCKRANNY 110-UGGOOL 110-1 | 4 | 4 | 4 | Proposed | 13/07/2026 | 16/07/2026
TO-26-UGL-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - UGGOOL 110-UGGOOL 110-110SA1-2CB | 4 | 4 |  | Proposed | 13/07/2026 | 16/07/2026
TO-26-UGL-T131-01 | GENERATOR TRANSFORMER - UGGOOL 110-UGGOOL 33-T131 | 4 | 4 | 4 | Proposed | 13/07/2026 | 16/07/2026
TO-26-UGL-T131-02 | GENERATOR TRANSFORMER - UGGOOL 110-UGGOOL 33-T131 | 4 | 4 | 4 | Proposed | 13/07/2026 | 16/07/2026
TO-26-UGL-T132-02 | GENERATOR TRANSFORMER - UGGOOL 110-UGGOOL 33-T132 | 4 | 4 | 4 | Proposed | 13/07/2026 | 16/07/2026
TO-26-UGL-T132-01 | GENERATOR TRANSFORMER - UGGOOL 110-UGGOOL 33-T132 | 4 | 4 | 4 | Proposed | 13/07/2026 | 16/07/2026
TO-26-UGL-T134-01 | GENERATOR TRANSFORMER - UGGOOL 110-UGGOOL 33-T134 | 4 | 4 | 4 | Proposed | 13/07/2026 | 16/07/2026
TO-26-UGL-T134-02 | GENERATOR TRANSFORMER - UGGOOL 110-UGGOOL 33-T134 | 4 | 4 | 4 | Proposed | 13/07/2026 | 16/07/2026
TO-26-BYH-T2101-01 | TRANSFORMER - BALLYNAHULLA 220-BALLYNAHULLA 110-T2101 | 1 | 1 | 1 | Proposed | 14/07/2026 | 14/07/2026
TO-26-CF-CAP2-01 | CAPACITOR/SVC/REACTOR - CATHALEENS FALL 110-CATHALEENS FALL 110-CAP2 | 11 | 9 | 9 | Proposed | 14/07/2026 | 24/07/2026
TO-26-CLU-110K1-02 | COUPLER/SECTIONALISING CB - CLUTTERLAND 110-CLUTTERLAND 110-110K1 | 1 | 1 | 1 | Proposed | 14/07/2026 | 14/07/2026
TO-26-CLU-110K2-01 | COUPLER/SECTIONALISING CB - CLUTTERLAND 110-CLUTTERLAND 110-110K2 | 1 | 1 | 1 | Proposed | 14/07/2026 | 14/07/2026
TO-26-CLU-110SA1-2CB-02 | COUPLER/SECTIONALISING CB - CLUTTERLAND 110-CLUTTERLAND 110-110SA1-2CB | 1 | 1 | 1 | Proposed | 14/07/2026 | 14/07/2026
TO-26-DMY-CAP2-01 | CAPACITOR/SVC/REACTOR - DUNMANWAY 110-DUNMANWAY 110-CAP2 | 3 | 3 | 3 | Proposed | 14/07/2026 | 16/07/2026
TO-26-MUL-CAP1-01 | CAPACITOR/SVC/REACTOR - MULLINGAR 110-MULLINGAR 110-CAP1 | 11 | 9 | 9 | Proposed | 14/07/2026 | 24/07/2026
TO-26-CF-110K1-2-02 | COUPLER/SECTIONALISING CB - CATHALEENS FALL 110-CATHALEENS FALL 110-110K1-2 | 21 | 14 | 14 | Proposed | 15/07/2026 | 04/08/2026
TO-26-DMY-T142-01 | DISTRIBUTION TRANSFORMER - DUNMANWAY 110-DUNMANWAY 38-T142 | 2 | 2 | 2 | Reference (Proposed) | 15/07/2026 | 16/07/2026
TO-26-LIB-T101-01 | DISTRIBUTION TRANSFORMER - LIBERTY STREET 110-LIBERTY STREET 10-T101 | 2 | 2 | 2 | Reference (Proposed) | 15/07/2026 | 16/07/2026
TO-26-DRY-110SA1-02 | SECTIONALISING DISCONNECT - DRYBRIDGE 110-DRYBRIDGE 110-110SA1 | 8 | 6 | 6 | Proposed | 16/07/2026 | 23/07/2026
TO-26-DRY-LOU-1-02 | 110kV FEEDER - DRYBRIDGE 110-LOUTH 110-1 | 22 | 15 | 15 | Proposed | 16/07/2026 | 06/08/2026
TO-26-DRY-OBE-1-01 | 110kV FEEDER - DRYBRIDGE 110-OLDBRIDGE 110-1 | 8 | 6 | 6 | Proposed | 16/07/2026 | 23/07/2026
TO-26-DRY-OBE-1-03 | 110kV FEEDER - DRYBRIDGE 110-OLDBRIDGE 110-1 | 8 | 6 | 6 | Proposed | 16/07/2026 | 23/07/2026
TO-26-MLN-T123-02 | TSO CUSTOMER TRANSFORMER - MULLAGHARLIN 110-MULLAGHARLIN 20-T123 | 2 | 2 | 2 | Proposed | 16/07/2026 | 17/07/2026
TO-26-CLN-110SA2-04 | SECTIONALISING DISCONNECT - CLOON 110-CLOON 110-110SA2 | 7 | 5 | 5 | Proposed | 17/07/2026 | 23/07/2026
TO-26-CLN-LA-1-06 | 110kV FEEDER - CLOON 110-LANESBORO 110-1 | 7 | 5 | 5 | Proposed | 17/07/2026 | 23/07/2026
TO-26-CLN-T142-02 | DISTRIBUTION TRANSFORMER - CLOON 110-CLOON 38-T142 | 7 | 5 | 5 | Reference | 17/07/2026 | 23/07/2026
TO-26-LA-T104-04 | GENERATOR TRANSFORMER - LANESBORO 110-LANESBORO G4-T104 | 7 | 5 | 5 | Proposed | 17/07/2026 | 23/07/2026
TO-26-AA GIS-LIM-1-01 | 110kV FEEDER - ARDNACRUSHA GIS 110-LIMERICK 110-1 | 12 | 10 | 10 | Proposed | 20/07/2026 | 31/07/2026
TO-26-110 kV A2 @ ARV-01 | BUSBAR SECTION - ARVA 110-ARVA 110-110A2 | 12 | 10 | 10 | Proposed | 20/07/2026 | 31/07/2026
TO-26-110 kV B2 @ ARV-01 | BUSBAR SECTION - ARVA 110-ARVA 110-110B2 | 12 | 10 | 10 | Proposed | 20/07/2026 | 31/07/2026
TO-26-ARV-COS-1-07 | 110kV FEEDER - ARVA 110-CARRICK ON SHANNON 110-1 | 12 | 10 | 10 | Proposed | 20/07/2026 | 31/07/2026
TO-26-BOT-MLC-1-01 | 110kV FEEDER - BOGTOWN 110-MOUNTLUCAS 110-1 | 9 | 7 | 7 | Proposed | 20/07/2026 | 28/07/2026
TO-26-BOT-T131-01 | GENERATOR TRANSFORMER - BOGTOWN 110-BOGTOWN 33-T131 | 1 | 1 | 1 | Proposed | 20/07/2026 | 20/07/2026
TO-26-BOT-T131-02 | GENERATOR TRANSFORMER - BOGTOWN 110-BOGTOWN 33-T131 | 9 | 7 | 7 | Proposed | 20/07/2026 | 28/07/2026
TO-26-CAH-CAP2/4-01 | CAPACITOR/SVC/REACTOR - CAHIR 110-CAHIR 110-CAP2/4 | 5 | 5 | 5 | Proposed | 20/07/2026 | 24/07/2026
TO-26-110 kV B1 @ CSH-05 | BUSBAR SECTION - CASHLA 110-CASHLA 110-110B1 | 8 | 6 | 6 | Proposed | 20/07/2026 | 27/07/2026
TO-26-110 kV B2 @ CSH-03 | BUSBAR SECTION - CASHLA 110-CASHLA 110-110B2 | 8 | 6 | 6 | Proposed | 20/07/2026 | 27/07/2026
TO-26-CSH-110K1-2-03 | COUPLER/SECTIONALISING CB - CASHLA 110-CASHLA 110-110K1-2 | 8 | 6 | 6 | Proposed | 20/07/2026 | 27/07/2026
TO-26-CSH-GAL GIS-1-01 | 110kV FEEDER - CASHLA 110-GALWAY GIS 110-1 | 2 | 2 | 2 | Proposed | 20/07/2026 | 21/07/2026
TO-26-110 kV A2 @ CLG-02 | BUSBAR SECTION - CLOGHRAN 110-CLOGHRAN 110-110A2 | 5 | 5 | 5 | Proposed | 20/07/2026 | 24/07/2026
TO-26-110 kV B2 @ CLG-02 | BUSBAR SECTION - CLOGHRAN 110-CLOGHRAN 110-110B2 | 5 | 5 | 5 | Proposed | 20/07/2026 | 24/07/2026
TO-26-CLG-110K2-01 | COUPLER/SECTIONALISING CB - CLOGHRAN 110-CLOGHRAN 110-110K2 | 5 | 5 | 5 | Proposed | 20/07/2026 | 24/07/2026
TO-26-CLG-110SA1-2CB-03 | COUPLER/SECTIONALISING CB - CLOGHRAN 110-CLOGHRAN 110-110SA1-2CB | 5 | 5 | 5 | Proposed | 20/07/2026 | 24/07/2026
TO-26-CLG-110SB1-2CB-03 | COUPLER/SECTIONALISING CB - CLOGHRAN 110-CLOGHRAN 110-110SB1-2CB | 5 | 5 | 5 | Proposed | 20/07/2026 | 24/07/2026
TO-26-COL-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - COLLEGE PARK 110-COLLEGE PARK 110-110SA1-2CB | 12 | 10 | 10 | Proposed | 20/07/2026 | 31/07/2026
TO-26-COL-FIN GIS-1-01 | 110kV FEEDER - COLLEGE PARK 110-FINGLAS GIS 110-1 | 12 | 10 | 10 | Proposed | 20/07/2026 | 31/07/2026
TO-26-COL-T102-01 | DISTRIBUTION TRANSFORMER - COLLEGE PARK 110-COLLEGE PARK 10-T102 | 12 | 10 | 10 | Reference (Proposed) | 20/07/2026 | 31/07/2026
TO-26-CRA-110SA1-01 | SECTIONALISING DISCONNECT - CRANE 110-CRANE 110-110SA1 | 12 | 10 | 10 | Proposed | 20/07/2026 | 31/07/2026
TO-26-CRA-110SA2-05 | SECTIONALISING DISCONNECT - CRANE 110-CRANE 110-110SA2 | 12 | 10 | 10 | Proposed | 20/07/2026 | 31/07/2026
TO-26-CRA-T141-05 | DISTRIBUTION TRANSFORMER - CRANE 110-CRANE 38-T141 | 12 | 10 | 10 | Reference (Proposed) | 20/07/2026 | 31/07/2026
TO-26-CRA-TTU-1-01 | 110kV FEEDER - CRANE 110-TULLABEG 110-1 | 12 | 10 | 10 | Proposed | 20/07/2026 | 31/07/2026
TO-26-110 kV A2 @ DEY-02 | BUSBAR SECTION - DERRYCARNEY 110-DERRYCARNEY 110-110A2 | 5 | 5 | 5 | Proposed | 20/07/2026 | 24/07/2026
TO-26-110 kV B2 @ DEY-02 | BUSBAR SECTION - DERRYCARNEY 110-DERRYCARNEY 110-110B2 | 5 | 5 | 5 | Proposed | 20/07/2026 | 24/07/2026
TO-26-DEY-110K2-03 | COUPLER/SECTIONALISING CB - DERRYCARNEY 110-DERRYCARNEY 110-110K2 | 5 | 5 | 5 | Proposed | 20/07/2026 | 24/07/2026
TO-26-DEY-T132-01 | GENERATOR TRANSFORMER - DERRYCARNEY 110-DERRYCARNEY 33-T132 | 5 | 5 | 5 | Proposed | 20/07/2026 | 24/07/2026
TO-26-DSN-400K1-2-04 | COUPLER/SECTIONALISING CB - DUNSTOWN 400-DUNSTOWN 400-400K1-2 | 1 | 1 | 1 | Proposed | 20/07/2026 | 20/07/2026
TO-26-DSN-MP GIS-1-02 | 400kV FEEDER - DUNSTOWN 400-MONEYPOINT GIS 400-1 | 40 | 29 | 29 | Proposed | 20/07/2026 | 28/08/2026
TO-26-110 kV A5 @ FIN GIS-01 | BUSBAR SECTION - FINGLAS GIS 110-FINGLAS GIS 110-110A5 | 12 | 10 | 10 | Proposed | 20/07/2026 | 31/07/2026
TO-26-110 kV B5 @ FIN GIS-01 | BUSBAR SECTION - FINGLAS GIS 110-FINGLAS GIS 110-110B5 | 12 | 10 | 10 | Proposed | 20/07/2026 | 31/07/2026
TO-26-FIN GIS-110K5-02 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110K5 | 12 | 10 | 10 | Proposed | 20/07/2026 | 31/07/2026
TO-26-FIN GIS-110SA3-5CB-02 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110SA3-5CB | 12 | 10 | 10 | Proposed | 20/07/2026 | 31/07/2026
TO-26-FIN GIS-110SB3-5CB-02 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110SB3-5CB | 12 | 10 | 10 | Proposed | 20/07/2026 | 31/07/2026
TO-26-FIN GIS-MCE-1-01 | 110kV FEEDER - FINGLAS GIS 110-MACETOWN 110-1 | 12 | 10 | 10 | Proposed | 20/07/2026 | 31/07/2026
TO-26-KYT-MAY-1-01 | 220kV FEEDER - KELLYSTOWN 220-MAYNOOTH 220-1 | 5 | 5 | 5 | Proposed | 20/07/2026 | 24/07/2026
TO-26-KLH-KNY-1-01 | 110kV FEEDER - KNOCKALOUGH 110-KNOCKRANNY 110-1 | 5 | 5 | 5 | Proposed | 20/07/2026 | 24/07/2026
TO-26-KLH-T121-01 | GENERATOR TRANSFORMER - KNOCKALOUGH 110-KNOCKALOUGH 20-T121 | 5 | 5 | 5 | Proposed | 20/07/2026 | 24/07/2026
TO-26-220 kV A4 @ KRA-08 | BUSBAR SECTION - KNOCKRAHA 220-KNOCKRAHA 220-220A4 | 5 | 5 | 5 | Proposed | 20/07/2026 | 24/07/2026
TO-26-220 kV B4 @ KRA-10 | BUSBAR SECTION - KNOCKRAHA 220-KNOCKRAHA 220-220B4 | 5 | 5 | 5 | Proposed | 20/07/2026 | 24/07/2026
TO-26-KRA-220K4-04 | COUPLER/SECTIONALISING CB - KNOCKRAHA 220-KNOCKRAHA 220-220K4 | 5 | 5 | 5 | Proposed | 20/07/2026 | 24/07/2026
TO-26-KRA-220SA2-4CB-09 | COUPLER/SECTIONALISING CB - KNOCKRAHA 220-KNOCKRAHA 220-220SA2-4CB | 5 | 5 | 5 | Proposed | 20/07/2026 | 24/07/2026
TO-26-KRA-220SB2-4CB-09 | COUPLER/SECTIONALISING CB - KNOCKRAHA 220-KNOCKRAHA 220-220SB2-4CB | 5 | 5 | 5 | Proposed | 20/07/2026 | 24/07/2026
TO-26-220 kV A1 @ LOU-01 | BUSBAR SECTION - LOUTH 220-LOUTH 220-220A1 | 12 | 10 | 10 | Proposed | 20/07/2026 | 31/07/2026
TO-26-220 kV B1 @ LOU-01 | BUSBAR SECTION - LOUTH 220-LOUTH 220-220B1 | 12 | 10 | 10 | Proposed | 20/07/2026 | 31/07/2026
TO-26-LOU-AT2-02 | TRANSFORMER - LOUTH 220-LOUTH 275-AT2 | 12 | 10 | 10 | Proposed | 20/07/2026 | 31/07/2026
TO-26-LOU-TAN-2-03 | 275kV FEEDER - LOUTH 275-TANDRAGEE 275-2 | 12 | 10 | 10 | Proposed | 20/07/2026 | 31/07/2026
TO-26-BDN-MRK1-04 | TSO CUSTOMER TRANSFORMER - BALLYDINE 110-BALLYDINE 10-MRK1 | 17 | 12 | 12 | Proposed | 21/07/2026 | 06/08/2026
TO-26-KBY-MR-1-01 | 110kV FEEDER - KILBARRY 110-MARINA 110-1 | 4 | 4 | 4 | Proposed | 21/07/2026 | 24/07/2026
TO-26-LA-RIC-2-08 | 110kV FEEDER - LANESBORO 110-RICHMOND 110-2 | 2 | 2 | 2 | Reference (Proposed) | 21/07/2026 | 22/07/2026
TO-26-LA-SLB-1-07 | 110kV FEEDER - LANESBORO 110-SLIABH BAWN 110-1 | 11 | 9 | 9 | Proposed | 21/07/2026 | 31/07/2026
TO-26-BOL-ENN-1-01 | 110kV FEEDER - BOOLTIAGH 110-ENNIS 110-1 | 10 | 8 | 8 | Proposed | 22/07/2026 | 31/07/2026
TO-26-CAH-KHL-1-01 | 110kV FEEDER - CAHIR 110-KILL HILL 110-1 | 2 | 2 | 2 | Proposed | 22/07/2026 | 23/07/2026
TO-26-KLH-T121-02 | GENERATOR TRANSFORMER - KNOCKALOUGH 110-KNOCKALOUGH 20-T121 | 2 | 2 | 2 | Proposed | 22/07/2026 | 23/07/2026
TO-26-THU-CAP1-01 | CAPACITOR/SVC/REACTOR - THURLES 110-THURLES 110-CAP1 | 3 | 3 | 3 | Proposed | 22/07/2026 | 24/07/2026
TO-26-110 kV A1 @ RAF-03 | BUSBAR SECTION - RAFFEEN 110-RAFFEEN 110-110A1 | 16 | 11 | 11 | Proposed | 23/07/2026 | 07/08/2026
TO-26-110 kV B1 @ RAF-02 | BUSBAR SECTION - RAFFEEN 110-RAFFEEN 110-110B1 | 16 | 11 | 11 | Proposed | 23/07/2026 | 07/08/2026
TO-26-RAF-TBG-1-04 | 110kV FEEDER - RAFFEEN 110-TRABEG 110-1 | 16 | 11 | 11 | Proposed | 23/07/2026 | 07/08/2026
TO-26-110 kV A2 @ TBG-02 | BUSBAR SECTION - TRABEG 110-TRABEG 110-110A2 | 16 | 11 | 11 | Proposed | 23/07/2026 | 07/08/2026
TO-26-110 kV B2 @ TBG-02 | BUSBAR SECTION - TRABEG 110-TRABEG 110-110B2 | 16 | 11 | 11 | Proposed | 23/07/2026 | 07/08/2026
TO-26-BDN-110SA1-01 | SECTIONALISING DISCONNECT - BALLYDINE 110-BALLYDINE 110-110SA1 | 4 | 4 | 4 | Proposed | 27/07/2026 | 30/07/2026
TO-26-BDN-CUL-1-06 | 110kV FEEDER - BALLYDINE 110-CULLENAGH 110-1 | 4 | 4 | 4 | Proposed | 27/07/2026 | 30/07/2026
TO-26-CLW-KLS-2-05 | 110kV FEEDER - CARLOW 110-KELLIS 110-2 | 5 | 5 | 5 | Proposed | 27/07/2026 | 31/07/2026
TO-26-CD-KBY-1-03 | 110kV FEEDER - CARRIGADROHID 110-KILBARRY 110-1 | 12 | 9 | 9 | Proposed | 27/07/2026 | 07/08/2026
TO-26-CHA-110SA1-2CB-02 | COUPLER/SECTIONALISING CB - CHARLEVILLE 110-CHARLEVILLE 110-110SA1-2CB | 10 | 7 | 7 | Proposed | 27/07/2026 | 05/08/2026
TO-26-CLA-DMY-1-01 | 110kV FEEDER - CLASHAVOON 110-DUNMANWAY 110-1 | 5 | 5 | 5 | Proposed | 27/07/2026 | 31/07/2026
TO-26-220 kV A2 @ DSN-05 | BUSBAR SECTION - DUNSTOWN 220-DUNSTOWN 220-220A2 | 19 | 14 | 14 | Proposed | 27/07/2026 | 14/08/2026
TO-26-220 kV B2 @ DSN-04 | BUSBAR SECTION - DUNSTOWN 220-DUNSTOWN 220-220B2 | 19 | 14 | 14 | Proposed | 27/07/2026 | 14/08/2026
TO-26-400 kV A2 @ DSN-04 | BUSBAR SECTION - DUNSTOWN 400-DUNSTOWN 400-400A2 | 19 | 14 | 14 | Proposed | 27/07/2026 | 14/08/2026
TO-26-400 kV B2 @ DSN-06 | BUSBAR SECTION - DUNSTOWN 400-DUNSTOWN 400-400B2 | 19 | 14 | 14 | Proposed | 27/07/2026 | 14/08/2026
TO-26-DSN-T4202-02 | TRANSFORMER - DUNSTOWN 400-DUNSTOWN 220-T4202 | 19 | 14 | 14 | Proposed | 27/07/2026 | 14/08/2026
TO-26-KBY-KRA-2-02 | 110kV FEEDER - KILBARRY 110-KNOCKRAHA 110-2 | 75 | 54 | 54 | Proposed | 27/07/2026 | 09/10/2026
TO-26-KBY-KRA-2-03 | 110kV FEEDER - KILBARRY 110-KNOCKRAHA 110-2 | 22 | 15 | 15 | Proposed | 27/07/2026 | 17/08/2026
TO-26-LIS-CAP2-05 | CAPACITOR/SVC/REACTOR - LISDRUM 110-LISDRUM 110-CAP2 | 5 | 5 | 5 | Proposed | 27/07/2026 | 31/07/2026
TO-26-MP GIS-T4002-01 | GENERATOR TRANSFORMER - MONEYPOINT GIS 400-MONEYPOINT GIS G2-T4002 | 2 | 2 | 2 | Proposed | 27/07/2026 | 28/07/2026
TO-26-WOO-T4201-03 | TRANSFORMER - WOODLAND 400-WOODLAND 220-T4201 | 5 | 5 | 5 | Proposed | 27/07/2026 | 31/07/2026
TO-26-110 kV A3 @ BOL-01 | BUSBAR SECTION - BOOLTIAGH 110-BOOLTIAGH 110-110A3 | 4 | 4 | 4 | Proposed | 28/07/2026 | 31/07/2026
TO-26-BOL-110SA1-3CB-02 | COUPLER/SECTIONALISING CB - BOOLTIAGH 110-BOOLTIAGH 110-110SA1-3CB | 4 | 4 | 4 | Proposed | 28/07/2026 | 31/07/2026
TO-26-BOL-T141-01 | DISTRIBUTION TRANSFORMER - BOOLTIAGH 110-BOOLTIAGH 38-T141 | 4 | 4 | 4 | Reference (Proposed) | 28/07/2026 | 31/07/2026
TO-26-BOL-T143-01 | DISTRIBUTION TRANSFORMER - BOOLTIAGH 110-BOOLTIAGH 38-T143 | 4 | 4 | 4 | Reference (Proposed) | 28/07/2026 | 31/07/2026
TO-26-CSH-GAL GIS-2-02 | 110kV FEEDER - CASHLA 110-GALWAY GIS 110-2 | 2 | 2 | 2 | Proposed | 28/07/2026 | 29/07/2026
TO-26-CLG-T121-01 | TSO CUSTOMER TRANSFORMER - CLOGHRAN 110-CLOGHRAN 20-T121 | 3 | 3 | 3 | Proposed | 28/07/2026 | 30/07/2026
TO-26-CLU-KUD-1-02 | 110kV FEEDER - CLUTTERLAND 110-KILMAHUD 110-1 | 3 | 3 | 3 | Proposed | 28/07/2026 | 30/07/2026
TO-26-DJG-TRL-1-01 | 110kV FEEDER - DROMBEG 110-TRALEE 110-1 | 3 | 3 | 3 | Proposed | 28/07/2026 | 30/07/2026
TO-26-KKY-T141-01 | DISTRIBUTION TRANSFORMER - KILKENNY 110-KILKENNY 38-T141 | 2 | 2 | 2 | Reference (Proposed) | 28/07/2026 | 29/07/2026
TO-26-OUG-T141-01 | DISTRIBUTION TRANSFORMER - OUGHTRAGH 110-OUGHTRAGH 38-T141 | 3 | 3 | 3 | Reference (Proposed) | 28/07/2026 | 30/07/2026
TO-26-OUG,T-KER-1-02 | 110kV FEEDER - OUGHTRAGH tee-KNOCKEARAGH 110-1 | 3 | 3 | 3 | Proposed | 28/07/2026 | 30/07/2026
TO-26-OUG,T-OUG-1-02 | 110kV FEEDER - OUGHTRAGH tee-OUGHTRAGH 110-1 | 3 | 3 | 3 | Proposed | 28/07/2026 | 30/07/2026
TO-26-OUG,T-TRL-1-01 | 110kV FEEDER - OUGHTRAGH tee-TRALEE 110-1 | 3 | 3 | 3 | Proposed | 28/07/2026 | 30/07/2026
TO-26-TRL-110SA1-2CB-02 | COUPLER/SECTIONALISING CB - TRALEE 110-TRALEE 110-110SA1-2CB | 3 | 3 | 3 | Proposed | 28/07/2026 | 30/07/2026
TO-26-TRL-T142-01 | DISTRIBUTION TRANSFORMER - TRALEE 110-TRALEE 38-T142 | 3 | 3 | 3 | Reference (Proposed) | 28/07/2026 | 30/07/2026
TO-26-KKY-CAP2-02 | CAPACITOR/SVC/REACTOR - KILKENNY 110-KILKENNY 110-CAP2 | 2 | 2 | 2 | Proposed | 29/07/2026 | 30/07/2026
TO-26-LET-PST-01 | TRANSFORMER - LETTERKENNY 110-STRABANE 110-PST | 10 | 7 | 7 | Proposed | 29/07/2026 | 07/08/2026
TO-26-CSH-SAL-1-01 | 110kV FEEDER - CASHLA 110-SALTHILL 110-1 | 23 | 16 | 16 | Proposed | 30/07/2026 | 21/08/2026
TO-26-CLN-T141-04 | DISTRIBUTION TRANSFORMER - CLOON 110-CLOON 38-T141 | 2 | 2 | 2 | Reference (Proposed) | 30/07/2026 | 31/07/2026
TO-26-KLS-KKY-1-04 | 110kV FEEDER - KELLIS 110-KILKENNY 110-1 | 12 | 9 | 9 | Proposed | 03/08/2026 | 14/08/2026
TO-26-AA GIS-T101-01 | GENERATOR TRANSFORMER - ARDNACRUSHA GIS 110-ARDNACRUSHA GIS G1-T101 | Unknown | Unknown | 7 | Planned | August | August
TO-26-ARK-BEG-1-01 | 110kV FEEDER - ARKLOW 110-BALLYBEG 110-1 | Unknown | Unknown | 4 | Planned | August | August
TO-26-ATH-110SA1-2CB-06 | COUPLER/SECTIONALISING CB - ATHLONE 110-ATHLONE 110-110SA1-2CB | Unknown | Unknown | 10 | Planned | August | August
TO-26-ATH-SH-1-09 | 110kV FEEDER - ATHLONE 110-SHANNONBRIDGE 110-1 | Unknown | Unknown | 15 | Planned | August | August
TO-26-CBT-KUD-1-02 | 110kV FEEDER - CASTLEBAGOT 110-KILMAHUD 110-1 | Unknown | Unknown | 3 | Planned | August | August
TO-26-CF-CLO-1-01 | 110kV FEEDER - CATHALEENS FALL 110-CLOGHER 110-1 | 3 | 3 | 3 | Proposed | 04/08/2026 | 06/08/2026
TO-26-CLH-TRI-1-01 | 110kV FEEDER - CLAHANE 110-TRIEN 110-1 | Unknown | Unknown | 2 | Planned | August | August
TO-26-CLE-220K1-01 | COUPLER/SECTIONALISING CB - CLONEE 220-CLONEE 220-220K1 | Unknown | Unknown | 14 | Planned | August | August
TO-26-CLE-220SA1-2CB-01 | COUPLER/SECTIONALISING CB - CLONEE 220-CLONEE 220-220SA1-2CB | Unknown | Unknown | 14 | Planned | August | August
TO-26-CLE-220SB1-2CB-01 | COUPLER/SECTIONALISING CB - CLONEE 220-CLONEE 220-220SB1-2CB | Unknown | Unknown | 14 | Planned | August | August
TO-26-CKN-GRO-1-01 | 110kV FEEDER - CLONKEEN 110-GARROW 110-1 | Unknown | Unknown | 24 | Planned | August | September
TO-26-COL-110SA1-2CB-02 | COUPLER/SECTIONALISING CB - COLLEGE PARK 110-COLLEGE PARK 110-110SA1-2CB | 18 | 14 | 14 | Proposed | 04/08/2026 | 21/08/2026
TO-26-COL-110SA1-3CB-01 | COUPLER/SECTIONALISING CB - COLLEGE PARK 110-COLLEGE PARK 110-110SA1-3CB | 18 | 14 | 14 | Proposed | 04/08/2026 | 21/08/2026
TO-26-COL-CDU-1-01 | 110kV FEEDER - COLLEGE PARK 110-CORDUFF 110-1 | 18 | 14 | 14 | Proposed | 04/08/2026 | 21/08/2026
TO-26-COL-T101-01 | DISTRIBUTION TRANSFORMER - COLLEGE PARK 110-COLLEGE PARK 10-T101 | 18 | 14 | 14 | Reference (Proposed) | 04/08/2026 | 21/08/2026
TO-26-COL-T103-01 | DISTRIBUTION TRANSFORMER - COLLEGE PARK 110-COLLEGE PARK 10-T103 | 18 | 14 | 14 | Reference (Proposed) | 04/08/2026 | 21/08/2026
TO-26-110 kV A1 @ CDU-01 | BUSBAR SECTION - CORDUFF 110-CORDUFF 110-110A1 | 18 | 14 | 14 | Proposed | 04/08/2026 | 21/08/2026
TO-26-110 kV B1 @ CDU-01 | BUSBAR SECTION - CORDUFF 110-CORDUFF 110-110B1 | 18 | 14 | 14 | Proposed | 04/08/2026 | 21/08/2026
TO-26-CDU-HN-1-01 | 220kV FEEDER - CORDUFF 220-HUNTSTOWN 220-1 | Unknown | Unknown | 10 | Planned | August | August
TO-26-CKG-110K2-02 | COUPLER/SECTIONALISING CB - CORKAGH 110-CORKAGH 110-110K2 | Unknown | Unknown | 3 | Planned | August | August
TO-26-CKG-110SA1-2CB-05 | COUPLER/SECTIONALISING CB - CORKAGH 110-CORKAGH 110-110SA1-2CB | Unknown | Unknown | 3 | Planned | August | August
TO-26-CKG-110SB1-2CB-05 | COUPLER/SECTIONALISING CB - CORKAGH 110-CORKAGH 110-110SB1-2CB | Unknown | Unknown | 3 | Planned | August | August
TO-26-GRO-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - GARROW 110-GARROW 110-110SA1-2CB | Unknown | Unknown | 1 | Planned | August | August
TO-26-GRO-T122-01 | GENERATOR TRANSFORMER - GARROW 110-GARROW 20-T122 | Unknown | Unknown | 4 | Planned | August | August
TO-26-HN-T2002-01 | GENERATOR TRANSFORMER - HUNTSTOWN 220-HUNTSTOWN G2-T2002 | Unknown | Unknown |  | Planned | August | August
TO-26-INC-220K1-2-01 | COUPLER/SECTIONALISING CB - INCHICORE 220-INCHICORE 220-220K1-2 | 18 | 14 | 14 | Proposed | 04/08/2026 | 21/08/2026
TO-26-LOU-AT3-02 | TRANSFORMER - LOUTH 220-LOUTH 275-AT3 | Unknown | Unknown | 9 | Planned | August | August
TO-26-AA GIS-T102-03 | GENERATOR TRANSFORMER - ARDNACRUSHA GIS 110-ARDNACRUSHA GIS G2-T102 | 1 | 1 | 1 | Proposed | 05/08/2026 | 05/08/2026
TO-26-AUG-KPG-1-02 | 110kV FEEDER - AUGHINISH 110-KILPADDOGE 110-1 | Unknown | Unknown |  | Planned | August | November
TO-26-CLG-T123-01 | TSO CUSTOMER TRANSFORMER - CLOGHRAN 110-CLOGHRAN 20-T123 | Unknown | Unknown | 3 | Planned | August | August
TO-26-110 kV A1 @ SRA-02 | BUSBAR SECTION - SRANANAGH 110-SRANANAGH 110-110A1 | 10 | 8 | 8 | Proposed | 05/08/2026 | 14/08/2026
TO-26-110 kV A2 @ SRA-01 | BUSBAR SECTION - SRANANAGH 110-SRANANAGH 110-110A2 | 10 | 8 | 8 | Proposed | 05/08/2026 | 14/08/2026
TO-26-110 kV B1 @ SRA-02 | BUSBAR SECTION - SRANANAGH 110-SRANANAGH 110-110B1 | 10 | 8 | 8 | Proposed | 05/08/2026 | 14/08/2026
TO-26-110 kV B2 @ SRA-01 | BUSBAR SECTION - SRANANAGH 110-SRANANAGH 110-110B2 | 10 | 8 | 8 | Proposed | 05/08/2026 | 14/08/2026
TO-26-SRA-110K1-2-03 | COUPLER/SECTIONALISING CB - SRANANAGH 110-SRANANAGH 110-110K1-2 | 10 | 8 | 8 | Proposed | 05/08/2026 | 14/08/2026
TO-26-CDK-T121-01 | GENERATOR TRANSFORMER - CASTLEDOCKRELL 110-CASTLEDOCKRELL 20-T121 | Unknown | Unknown | 22 | Reference (Planned) | August | September
TO-26-AGL-SH-1-02 | 110kV FEEDER - AGANNYGAL 110-SHANNONBRIDGE 110-1 | 19 | 15 | 15 | Proposed | 10/08/2026 | 28/08/2026
TO-26-AUG-SK-3-01 | 110kV FEEDER - AUGHINISH 110-SEALROCK 110-3 | 5 | 5 | 5 | Proposed | 10/08/2026 | 14/08/2026
TO-26-BGH-110SA1-01 | SECTIONALISING DISCONNECT - BOGGERAGH 110-BOGGERAGH 110-110SA1 | Unknown | Unknown | 10 | Planned | August | August
TO-26-BGH-110SA2-01 | SECTIONALISING DISCONNECT - BOGGERAGH 110-BOGGERAGH 110-110SA2 | Unknown | Unknown | 10 | Planned | August | August
TO-26-BGH-CLA-1-01 | 110kV FEEDER - BOGGERAGH 110-CLASHAVOON 110-1 | Unknown | Unknown |  | Planned | August | August
TO-26-BGH-T121-01 | GENERATOR TRANSFORMER - BOGGERAGH 110-BOGGERAGH 20-T121 | Unknown | Unknown | 10 | Planned | August | August
TO-26-BGH-T121-02 | GENERATOR TRANSFORMER - BOGGERAGH 110-BOGGERAGH 20-T121 | Unknown | Unknown | 2 | Planned | August | August
TO-26-BGH-T132-01 | GENERATOR TRANSFORMER - BOGGERAGH 110-BOGGERAGH 33-T132 | Unknown | Unknown | 10 | Planned | August | August
TO-26-BGH-T142-01 | DISTRIBUTION TRANSFORMER - BOGGERAGH 110-BOGGERAGH 38-T142 | Unknown | Unknown | 10 | Reference (Planned) | August | August
TO-26-CLG-T122-01 | TSO CUSTOMER TRANSFORMER - CLOGHRAN 110-CLOGHRAN 20-T122 | Unknown | Unknown | 2 | Planned | August | August
TO-26-CDY-110SA1-01 | SECTIONALISING DISCONNECT - CORDERRY 110-CORDERRY 110-110SA1 | Unknown | Unknown | 5 | Planned | August | August
TO-26-CDY-110SA2-01 | SECTIONALISING DISCONNECT - CORDERRY 110-CORDERRY 110-110SA2 | Unknown | Unknown | 5 | Planned | August | August
TO-26-CDY-GRV-1-01 | 110kV FEEDER - CORDERRY 110-GARVAGH 110-1 | Unknown | Unknown | 10 | Planned | August | August
TO-26-CDY-T122-01 | DISTRIBUTION TRANSFORMER - CORDERRY 110-CORDERRY 20-T122 | Unknown | Unknown | 5 | Reference (Planned) | August | August
TO-26-CRA-WEX-1-06 | 110kV FEEDER - CRANE 110-WEXFORD 110-1 | 19 | 15 | 15 | Proposed | 10/08/2026 | 28/08/2026
TO-26-FLA-GIL-1-03 | 110kV FEEDER - FLAGFORD 110-GILRA 110-1 | 5 | 5 | 5 | Proposed | 10/08/2026 | 14/08/2026
TO-26-GRV-110K1-01 | COUPLER/SECTIONALISING CB - GARVAGH 110-GARVAGH 110-110K1 | Unknown | Unknown | 2 | Planned | August | August
TO-26-GRV-T121-01 | GENERATOR TRANSFORMER - GARVAGH 110-GARVAGH 20-T121 | Unknown | Unknown | 8 | Planned | August | August
TO-26-GRV-T141-01 | DISTRIBUTION TRANSFORMER - GARVAGH 110-GARVAGH 20-T141 | Unknown | Unknown | 8 | Reference (Planned) | August | August
TO-26-GIL-T121-01 | TSO CUSTOMER TRANSFORMER - GILRA 110-GILRA 20-T121 | 5 | 5 | 5 | Reference (Proposed) | 10/08/2026 | 14/08/2026
TO-26-MR-110K1-2-02 | COUPLER/SECTIONALISING CB - MARINA 110-MARINA 110-110K1-2 | Unknown | Unknown | 10 | Planned | August | August
TO-26-MP GIS-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 110-MONEYPOINT GIS 110-110SA1-2CB | Unknown | Unknown | 5 | Planned | August | August
TO-26-MP GIS-400SA1-2CB-01 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 400-MONEYPOINT GIS 400-400SA1-2CB | Unknown | Unknown | 5 | Planned | August | August
TO-26-MP GIS-ST101-01 | GENERATOR TRANSFORMER - MONEYPOINT GIS 110-MONEYPOINT GIS 10-ST101 | Unknown | Unknown | 5 | Planned | August | August
TO-26-MP GIS-T121-01 | GENERATOR TRANSFORMER - MONEYPOINT GIS 110-MONEYPOINT GIS 20-T121 | Unknown | Unknown | 5 | Planned | August | August
TO-26-MP GIS-T121-02 | GENERATOR TRANSFORMER - MONEYPOINT GIS 110-MONEYPOINT GIS 20-T121 | Unknown | Unknown | 5 | Planned | August | August
TO-26-SK-T103-01 | GENERATOR TRANSFORMER - SEALROCK 110-SEALROCK G3-T103 | 5 | 5 | 5 | Proposed | 10/08/2026 | 14/08/2026
TO-26-SK-T103-02 | GENERATOR TRANSFORMER - SEALROCK 110-SEALROCK G3-T103 | 5 | 5 | 5 | Proposed | 10/08/2026 | 14/08/2026
TO-26-BYH-GLE-1-01 | 110kV FEEDER - BALLYNAHULLA 110-GLENLARA 110-1 | Unknown | Unknown | 2 | Planned | August | August
TO-26-CKG-T121-01 | TSO CUSTOMER TRANSFORMER - CORKAGH 110-CORKAGH 20-T121 | Unknown | Unknown | 3 | Planned | August | August
TO-26-KIN-T101-02 | TSO CUSTOMER TRANSFORMER - KINNEGAD 110-KINNEGAD 10-T101 | 2 | 2 | 2 | Proposed | 11/08/2026 | 12/08/2026
TO-26-KIN-T101-03 | TSO CUSTOMER TRANSFORMER - KINNEGAD 110-KINNEGAD 10-T101 | Unknown | Unknown | 2 | Planned | August | August
TO-26-KIN-T102-05 | TSO CUSTOMER TRANSFORMER - KINNEGAD 110-KINNEGAD 10-T102 | Unknown | Unknown | 2 | Planned | August | August
TO-26-BLC-FIN-1-03 | 220kV FEEDER - BELCAMP 220-FINGLAS 220-1 | Unknown | Unknown |  | Planned | August | September
TO-26-BLC-T2103-02 | TRANSFORMER - BELCAMP 220-BELCAMP 110-T2103 | Unknown | Unknown | 80 | Planned | August | December
TO-26-BGH-T132-02 | GENERATOR TRANSFORMER - BOGGERAGH 110-BOGGERAGH 33-T132 | Unknown | Unknown | 1 | Planned | August | August
TO-26-CBT-KSG-1-02 | 110kV FEEDER - CASTLEBAGOT 110-KISHOGE 110-1 | Unknown | Unknown | 1 | Planned | August | August
TO-26-MLN-T124-01 | TSO CUSTOMER TRANSFORMER - MULLAGHARLIN 110-MULLAGHARLIN 20-T124 | 2 | 1 | 1 | Proposed | 14/08/2026 | 15/08/2026
TO-26-CD-MAC-1-03 | 110kV FEEDER - CARRIGADROHID 110-MACROOM 110-1 | Unknown | Unknown | 5 | Planned | August | August
TO-26-CDU-MCE-1-01 | 110kV FEEDER - CORDUFF 110-MACETOWN 110-1 | Unknown | Unknown | 10 | Planned | August | August
TO-26-GGO-220K1-2-02 | COUPLER/SECTIONALISING CB - GLANAGOW 220-GLANAGOW 220-220K1-2 | Unknown | Unknown | 8 | Planned | August | August
TO-26-GOL-T101-02 | GENERATOR TRANSFORMER - GOLAGH 110-GOLAGH 10-T101 | Unknown | Unknown | 15 | Planned | August | September
TO-26-GOL,T-CLO-1-02 | 110kV FEEDER - GOLAGH tee-CLOGHER 110-1 | Unknown | Unknown | 15 | Planned | August | September
TO-26-GOL,T-GOL-1-01 | 110kV FEEDER - GOLAGH tee-GOLAGH 110-1 | Unknown | Unknown | 15 | Planned | August | September
TO-26-GOL,T-LET-1-01 | 110kV FEEDER - GOLAGH tee-LETTERKENNY 110-1 | Unknown | Unknown | 15 | Planned | August | September
TO-26-220 kV A1 @ KRA-04 | BUSBAR SECTION - KNOCKRAHA 220-KNOCKRAHA 220-220A1 | 12 | 10 | 10 | Proposed | 17/08/2026 | 28/08/2026
TO-26-220 kV B1 @ KRA-04 | BUSBAR SECTION - KNOCKRAHA 220-KNOCKRAHA 220-220B1 | 12 | 10 | 10 | Proposed | 17/08/2026 | 28/08/2026
TO-26-KRA-220K1-03 | COUPLER/SECTIONALISING CB - KNOCKRAHA 220-KNOCKRAHA 220-220K1 | 12 | 10 | 10 | Proposed | 17/08/2026 | 28/08/2026
TO-26-KRA-220SA1-2CB-07 | COUPLER/SECTIONALISING CB - KNOCKRAHA 220-KNOCKRAHA 220-220SA1-2CB | 12 | 10 | 10 | Proposed | 17/08/2026 | 28/08/2026
TO-26-KRA-220SB1-2CB-07 | COUPLER/SECTIONALISING CB - KNOCKRAHA 220-KNOCKRAHA 220-220SB1-2CB | 12 | 10 | 10 | Proposed | 17/08/2026 | 28/08/2026
TO-26-MCE-110SA1-01 | SECTIONALISING DISCONNECT - MACETOWN 110-MACETOWN 110-110SA1 | Unknown | Unknown | 5 | Planned | August | August
TO-26-MCE-T101-01 | DISTRIBUTION TRANSFORMER - MACETOWN 110-MACETOWN 10-T101 | Unknown | Unknown | 5 | Reference (Planned) | August | August
TO-26-MCE-T121-02 | TSO CUSTOMER TRANSFORMER - MACETOWN 110-MACETOWN 20-T121 | Unknown | Unknown | 7 | Planned | August | August
TO-26-MP GIS-400SA1-3CB-01 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 400-MONEYPOINT GIS 400-400SA1-3CB | Unknown | Unknown | 2 | Planned | August | August
TO-26-SHL-D2/CB1-01 | COUPLER/SECTIONALISING CB - SHELLYBANKS 220-SHELLYBANKS 220-D2/CB1 | Unknown | Unknown | 5 | Planned | August | August
TO-26-TB-T2102-01 | TRANSFORMER - TARBERT 220-TARBERT 110-T2102 | Unknown | Unknown | 10 | Planned | August | August
TO-26-CKG-T122-01 | TSO CUSTOMER TRANSFORMER - CORKAGH 110-CORKAGH 20-T122 | Unknown | Unknown | 2 | Planned | August | August
TO-26-TRI-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - TRIEN 110-TRIEN 110-110SA1-2CB | Unknown | Unknown | 2 | Planned | August | August
TO-26-BK-SKY-1-01 | 110kV FEEDER - BELLACORICK 110-SRAHNAKILLY 110-1 | 5 | 5 | 5 | Proposed | 24/08/2026 | 28/08/2026
TO-26-CSH-CAP1-02 | CAPACITOR/SVC/REACTOR - CASHLA 110-CASHLA 110-CAP1 | 10 | 8 | 8 | Proposed | 24/08/2026 | 02/09/2026
TO-26-CSH-T2101-02 | TRANSFORMER - CASHLA 220-CASHLA 110-T2101 | Unknown | Unknown | 7 | Planned | August | September
TO-26-IKE,T-THU-1-02 | 110kV FEEDER - IKERRIN tee-THURLES 110-1 | 5 | 5 | 5 | Proposed | 24/08/2026 | 28/08/2026
TO-26-KYT-T237-01 | TSO CUSTOMER TRANSFORMER - KELLYSTOWN 220-KELLYSTOWN 34.5-T237 | Unknown | Unknown | 2 | Planned | August | August
TO-26-LSN-THU-1-03 | 110kV FEEDER - LISHEEN 110-THURLES 110-1 | 26 | 20 | 20 | Proposed | 24/08/2026 | 18/09/2026
TO-26-MP GIS-400SA2-4CB-01 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 400-MONEYPOINT GIS 400-400SA2-4CB | Unknown | Unknown | 5 | Planned | August | August
TO-26-SHL-D2/CB3-01 | COUPLER/SECTIONALISING CB - SHELLYBANKS 220-SHELLYBANKS 220-D2/CB3 | Unknown | Unknown | 5 | Planned | August | August
TO-26-SKY-110SA1-01 | SECTIONALISING DISCONNECT - SRAHNAKILLY 110-SRAHNAKILLY 110-110SA1 | 5 | 5 | 5 | Proposed | 24/08/2026 | 28/08/2026
TO-26-SKY-110SA2-01 | SECTIONALISING DISCONNECT - SRAHNAKILLY 110-SRAHNAKILLY 110-110SA2 | 5 | 5 | 5 | Proposed | 24/08/2026 | 28/08/2026
TO-26-SKY-T131-01 | GENERATOR TRANSFORMER - SRAHNAKILLY 110-SRAHNAKILLY 33-T131 | 5 | 5 | 5 | Proposed | 24/08/2026 | 28/08/2026
TO-26-SKY-T131-02 | GENERATOR TRANSFORMER - SRAHNAKILLY 110-SRAHNAKILLY 33-T131 | 5 | 5 | 5 | Proposed | 24/08/2026 | 28/08/2026
TO-26-SKY-T132-01 | GENERATOR TRANSFORMER - SRAHNAKILLY 110-SRAHNAKILLY 33-T132 | 8 | 6 | 6 | Proposed | 24/08/2026 | 31/08/2026
TO-26-SKY-T132-02 | GENERATOR TRANSFORMER - SRAHNAKILLY 110-SRAHNAKILLY 33-T132 | 5 | 5 | 5 | Proposed | 24/08/2026 | 28/08/2026
TO-26-THU-110SA1-2CB-02 | COUPLER/SECTIONALISING CB - THURLES 110-THURLES 110-110SA1-2CB | 5 | 5 | 5 | Proposed | 24/08/2026 | 28/08/2026
TO-26-THU-STATCOM-03 | CAPACITOR/SVC/REACTOR - THURLES 110-THURLES 110-STATCOM | 5 | 5 | 5 | Proposed | 24/08/2026 | 28/08/2026
TO-26-THU-T142-06 | DISTRIBUTION TRANSFORMER - THURLES 110-THURLES 38-T142 | 5 | 5 | 5 | Reference (Proposed) | 24/08/2026 | 28/08/2026
TO-26-ATH-CAP3-06 | CAPACITOR/SVC/REACTOR - ATHLONE 110-ATHLONE 110-CAP3 | 21 | 15 | 15 | Proposed | 25/08/2026 | 14/09/2026
TO-26-ATH-LA-1-04 | 110kV FEEDER - ATHLONE 110-LANESBORO 110-1 | Unknown | Unknown | 15 | Planned | August | September
TO-26-CKG-T123-01 | TSO CUSTOMER TRANSFORMER - CORKAGH 110-CORKAGH 20-T123 | Unknown | Unknown | 2 | Planned | August | August
TO-26-LOU-MLN-1-02 | 110kV FEEDER - LOUTH 110-MULLAGHARLIN 110-1 | Unknown | Unknown | 4 | Planned | August | August
TO-26-MLN-110SA1-2CB-02 | COUPLER/SECTIONALISING CB - MULLAGHARLIN 110-MULLAGHARLIN 110-110SA1-2CB | Unknown | Unknown | 4 | Planned | August | August
TO-26-MLN-T122-01 | DISTRIBUTION TRANSFORMER - MULLAGHARLIN 110-MULLAGHARLIN 20-T122 | Unknown | Unknown | 4 | Reference (Planned) | August | August
TO-26-MLN-T124-02 | TSO CUSTOMER TRANSFORMER - MULLAGHARLIN 110-MULLAGHARLIN 20-T124 | Unknown | Unknown | 4 | Planned | August | August
TO-26-TRI-T143-01 | DISTRIBUTION TRANSFORMER - TRIEN 110-TRIEN 38-T143 | Unknown | Unknown | 2 | Reference (Planned) | August | August
TO-26-KTL-T142-01 | DISTRIBUTION TRANSFORMER - KILTEEL 110-KILTEEL 38-T142 | Unknown | Unknown | 2 | Reference (Planned) | August | August
TO-26-DOO-CAP1-04 | CAPACITOR/SVC/REACTOR - DOON 110-DOON 110-CAP1 | Unknown | Unknown | 20 | Planned | August | September
TO-26-AD-KRA-1-03 | 220kV FEEDER - AGHADA 220-KNOCKRAHA 220-1 | Unknown | Unknown | 15 | Planned | August | September
TO-26-AD-KRA-2-03 | 220kV FEEDER - AGHADA 220-KNOCKRAHA 220-2 | Unknown | Unknown | 15 | Planned | August | September
TO-26-CLG-T124-01 | TSO CUSTOMER TRANSFORMER - CLOGHRAN 110-CLOGHRAN 20-T124 | Unknown | Unknown | 5 | Planned | August | September
TO-26-CLG-T124-02 | TSO CUSTOMER TRANSFORMER - CLOGHRAN 110-CLOGHRAN 20-T124 | Unknown | Unknown | 5 | Planned | August | September
TO-26-CDU-110K1-2-01 | COUPLER/SECTIONALISING CB - CORDUFF 110-CORDUFF 110-110K1-2 | Unknown | Unknown | 10 | Planned | August | September
TO-26-GGO-T2001-01 | GENERATOR TRANSFORMER - GLANAGOW 220-GLANAGOW G1-T2001 | Unknown | Unknown |  | Planned | August | September
TO-26-ISH-220K1-2-01 | COUPLER/SECTIONALISING CB - IRISHTOWN 220-IRISHTOWN 220-220K1-2 | Unknown | Unknown | 10 | Planned | August | September
TO-26-MCE-T124-01 | TSO CUSTOMER TRANSFORMER - MACETOWN 110-MACETOWN 20-T124 | Unknown | Unknown | 7 | Planned | August | September
TO-26-MAY-RYB GIS-1-02 | 110kV FEEDER - MAYNOOTH 110-RYEBROOK GIS 110-1 | Unknown | Unknown | 45 | Planned | August | November
TO-26-MP GIS-400SB1-2CB-01 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 400-MONEYPOINT GIS 400-400SB1-2CB | Unknown | Unknown | 5 | Planned | August | September
TO-26-MP GIS-OST-1-01 | 400kV FEEDER - MONEYPOINT GIS 400-OLDSTREET 400-1 | Unknown | Unknown | 15 | Planned | August | September
TO-26-OST-400SA2-01 | SECTIONALISING DISCONNECT - OLDSTREET 400-OLDSTREET 400-400SA2 | Unknown | Unknown | 8 | Planned | August | September
TO-26-OST-T4202-02 | TRANSFORMER - OLDSTREET 400-OLDSTREET 220-T4202 | Unknown | Unknown | 10 | Planned | August | September
TO-26-OST-WOO-1-02 | 400kV FEEDER - OLDSTREET 400-WOODLAND 400-1 | Unknown | Unknown | 15 | Planned | August | September
TO-26-RNW-T121-03 | TSO CUSTOMER TRANSFORMER - RINAWADE 110-RINAWADE 20-T121 | Unknown | Unknown | 1 | Planned | August | August
TO-26-TY-220SA2-01 | SECTIONALISING DISCONNECT - TYNAGH 220-TYNAGH 220-220SA2 | Unknown | Unknown | 3 | Planned | August | September
TO-26-WHI-CKB-T102-01 | TSO CUSTOMER TRANSFORMER - WHITEGATE 110-WHITEGATE 10-CKB-T102 | Unknown | Unknown | 5 | Planned | August | September
TO-26-WOO-220K1-2-02 | COUPLER/SECTIONALISING CB - WOODLAND 220-WOODLAND 220-220K1-2 | 45 | 33 | 33 | Proposed | 31/08/2026 | 14/10/2026
TO-26-WOO-T4202-03 | TRANSFORMER - WOODLAND 400-WOODLAND 220-T4202 | Unknown | Unknown | 15 | Planned | August | September
TO-26-220 kV B1/B2 @ AD-01 | BUSBAR SECTION - AGHADA 220-AGHADA 220-220B1-B2 | Unknown | Unknown | 2 | Planned | September | September
TO-26-AD-SB1-2CB-02 | COUPLER/SECTIONALISING CB - AGHADA 220-AGHADA 220-220SB1-2CB | Unknown | Unknown | 2 | Planned | September | September
TO-26-BRT-T222-01 | TSO CUSTOMER TRANSFORMER - BRACETOWN 220-BRACETOWN 20-T222 | Unknown | Unknown | 23 | Planned | September | October
TO-26-LA-RIC-1-01 | 110kV FEEDER - LANESBORO 110-RICHMOND 110-1 | Unknown | Unknown | 2 | Reference (Planned) | September | September
TO-26-LOU-AT1-02 | TRANSFORMER - LOUTH 220-LOUTH 275-AT1 | Unknown | Unknown | 9 | Planned | September | September
TO-26-LOU-TAN-1-01 | 275kV FEEDER - LOUTH 275-TANDRAGEE 275-1 | Unknown | Unknown | 9 | Planned | September | September
TO-26-CSH-CAP2-02 | CAPACITOR/SVC/REACTOR - CASHLA 110-CASHLA 110-CAP2 | Unknown | Unknown | 3 | Planned | September | September
TO-26-CSH-T2102-02 | TRANSFORMER - CASHLA 220-CASHLA 110-T2102 | Unknown | Unknown | 18 | Planned | September | September
TO-26-AD-T2011/12-01 | GENERATOR TRANSFORMER - AGHADA 220-AGHADA G11/12-T2011/12 | Unknown | Unknown |  | Planned | September | September
TO-26-LA-T141-01 | DISTRIBUTION TRANSFORMER - LANESBORO 110-LANESBORO 38-T141 | 2 | 2 | 2 | Reference (Proposed) | 03/09/2026 | 04/09/2026
TO-26-WOO-T4202-04 | TRANSFORMER - WOODLAND 400-WOODLAND 220-T4202 | 2 | 2 | 2 | Proposed | 03/09/2026 | 04/09/2026
TO-26-AUG-CFM-2-03 | 110kV FEEDER - AUGHINISH 110-CASTLEFARM 110-2 | Unknown | Unknown | 5 | Planned | September | September
TO-26-BRT-T222-02 | TSO CUSTOMER TRANSFORMER - BRACETOWN 220-BRACETOWN 20-T222 | Unknown | Unknown | 6 | Planned | September | September
TO-26-CBR-CLN-1-08 | 110kV FEEDER - CASTLEBAR 110-CLOON 110-1 | Unknown | Unknown | 5 | Planned | September | September
TO-26-CFM-T102-02 | TSO CUSTOMER TRANSFORMER - CASTLEFARM 110-CASTLEFARM 10-T102 | Unknown | Unknown | 5 | Reference (Planned) | September | September
TO-26-CF-SRA-1-04 | 110kV FEEDER - CATHALEENS FALL 110-SRANANAGH 110-1 | Unknown | Unknown | 10 | Planned | September | September
TO-26-CLG-T126-01 | TSO CUSTOMER TRANSFORMER - CLOGHRAN 110-CLOGHRAN 20-T126 | Unknown | Unknown | 5 | Planned | September | September
TO-26-CLG-T126-02 | TSO CUSTOMER TRANSFORMER - CLOGHRAN 110-CLOGHRAN 20-T126 | Unknown | Unknown | 10 | Planned | September | September
TO-26-DND-110K1-03 | COUPLER/SECTIONALISING CB - DARNDALE 110-DARNDALE 110-110K1 | Unknown | Unknown | 5 | Planned | September | September
TO-26-MP GIS-400SB1-3CB-01 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 400-MONEYPOINT GIS 400-400SB1-3CB | 5 | 5 | 5 | Proposed | 07/09/2026 | 11/09/2026
TO-26-PB-T2007/8-02 | GENERATOR TRANSFORMER - POOLBEG 220-POOLBEG G7/8-T2007/8 | Unknown | Unknown | 2 | Planned | September | September
TO-26-WHI-CKB-T101-02 | TSO CUSTOMER TRANSFORMER - WHITEGATE 110-WHITEGATE 10-CKB-T101 | Unknown | Unknown | 5 | Planned | September | September
TO-26-BVK-GRO-1-01 | 110kV FEEDER - BALLYVOUSKILL 110-GARROW 110-1 | Unknown | Unknown | 3 | Planned | September | September
TO-26-CLO-110K1-2-01 | COUPLER/SECTIONALISING CB - CLOGHER 110-CLOGHER 110-110K1-2 | Unknown | Unknown | 2 | Planned | September | September
TO-26-DND-110SB1-2CB-01 | COUPLER/SECTIONALISING CB - DARNDALE 110-DARNDALE 110-110SB1-2CB | Unknown | Unknown | 2 | Planned | September | September
TO-26-SLB-110K2-01 | COUPLER/SECTIONALISING CB - SLIABH BAWN 110-SLIABH BAWN 110-110K2 | Unknown | Unknown | 2 | Planned | September | September
TO-26-BDA-T101-01 | TSO CUSTOMER TRANSFORMER - BARODA 110-BARODA 10-T101 | Unknown | Unknown | 5 | Planned | September | September
TO-26-110 kV B4 @ FIN GIS-02 | BUSBAR SECTION - FINGLAS GIS 110-FINGLAS GIS 110-110B4 | 3 | 3 | 3 | Proposed | 09/09/2026 | 11/09/2026
TO-26-FIN GIS-110SB2-4CB-01 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110SB2-4CB | 3 | 3 | 3 | Proposed | 09/09/2026 | 11/09/2026
TO-26-FIN GIS-110SB4-6CB-01 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110SB4-6CB | 3 | 3 | 3 | Proposed | 09/09/2026 | 11/09/2026
TO-26-ENN-T102-02 | DISTRIBUTION TRANSFORMER - ENNIS 110-ENNIS 10-T102 | Unknown | Unknown | 2 | Reference (Planned) | September | September
TO-26-BRT-CLE-2-01 | 220kV FEEDER - BRACETOWN 220-CLONEE 220-2 | Unknown | Unknown | 10 | Planned | September | September
TO-26-CBT-MAY-1-02 | 220kV FEEDER - CASTLEBAGOT 220-MAYNOOTH 220-1 | Unknown | Unknown | 10 | Planned | September | September
TO-26-CUS-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - CUSHALING 110-CUSHALING 110-110SA1-2CB | Unknown | Unknown | 24 | Planned | September | September
TO-26-CUS-T103/5-01 | GENERATOR TRANSFORMER - CUSHALING 110-CUSHALING G3/5-T103/5 | Unknown | Unknown | 5 | Planned | September | September
TO-26-220 kV A2 @ FIN-02 | BUSBAR SECTION - FINGLAS 220-FINGLAS 220-220A2 | 5 | 5 | 5 | Proposed | 14/09/2026 | 18/09/2026
TO-26-220 kV B2 @ FIN-01 | BUSBAR SECTION - FINGLAS 220-FINGLAS 220-220B2 | 5 | 5 | 5 | Proposed | 14/09/2026 | 18/09/2026
TO-26-FIN-220K2-02 | COUPLER/SECTIONALISING CB - FINGLAS 220-FINGLAS 220-220K2 | 5 | 5 | 5 | Proposed | 14/09/2026 | 18/09/2026
TO-26-FIN-220SA1-2CB-02 | COUPLER/SECTIONALISING CB - FINGLAS 220-FINGLAS 220-220SA1-2CB | 5 | 5 | 5 | Proposed | 14/09/2026 | 18/09/2026
TO-26-FIN-220SB1-2CB-01 | COUPLER/SECTIONALISING CB - FINGLAS 220-FINGLAS 220-220SB1-2CB | 5 | 5 | 5 | Proposed | 14/09/2026 | 18/09/2026
TO-26-110 kV A4 @ FIN GIS-01 | BUSBAR SECTION - FINGLAS GIS 110-FINGLAS GIS 110-110A4 | 5 | 5 | 5 | Proposed | 14/09/2026 | 18/09/2026
TO-26-110 kV B4 @ FIN GIS-01 | BUSBAR SECTION - FINGLAS GIS 110-FINGLAS GIS 110-110B4 | 5 | 5 | 5 | Proposed | 14/09/2026 | 18/09/2026
TO-26-FIN GIS-110SA2-4CB-01 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110SA2-4CB | 5 | 5 | 5 | Proposed | 14/09/2026 | 18/09/2026
TO-26-FIN GIS-110SA4-6CB-01 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110SA4-6CB | 5 | 5 | 5 | Proposed | 14/09/2026 | 18/09/2026
TO-26-FIN GIS-110SB2-4CB-02 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110SB2-4CB | 5 | 5 | 5 | Proposed | 14/09/2026 | 18/09/2026
TO-26-FIN GIS-110SB4-6CB-02 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110SB4-6CB | 5 | 5 | 5 | Proposed | 14/09/2026 | 18/09/2026
TO-26-KUD-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - KILMAHUD 110-KILMAHUD 110-110SA1-2CB | Unknown | Unknown | 2 | Planned | September | September
TO-26-LET-T142-01 | DISTRIBUTION TRANSFORMER - LETTERKENNY 110-LETTERKENNY 38-T142 | Unknown | Unknown | 10 | Reference (Planned) | September | September
TO-26-MAY-110K1-2-01 | COUPLER/SECTIONALISING CB - MAYNOOTH 110-MAYNOOTH 110-110K1-2 | Unknown | Unknown | 10 | Planned | September | September
TO-26-400 kV B1 @ MP GIS-01 | BUSBAR SECTION - MONEYPOINT GIS 400-MONEYPOINT GIS 400-400B1 | Unknown | Unknown | 8 | Planned | September | September
TO-26-MP GIS-400SB2-4CB-01 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 400-MONEYPOINT GIS 400-400SB2-4CB | Unknown | Unknown | 5 | Planned | September | September
TO-26-CRU-T224-02 | TSO CUSTOMER TRANSFORMER - CRUISERATH 220-CRUISERATH 20-T224 | Unknown | Unknown | 2 | Planned | September | September
TO-26-KUD-T102-01 | TSO CUSTOMER TRANSFORMER - KILMAHUD 110-KILMAHUD 10-T102 | Unknown | Unknown | 3 | Planned | September | September
TO-26-CBR-CLN-1-09 | 110kV FEEDER - CASTLEBAR 110-CLOON 110-1 | Unknown | Unknown | 7 | Planned | September | September
TO-26-CLN-110SA1-05 | SECTIONALISING DISCONNECT - CLOON 110-CLOON 110-110SA1 | Unknown | Unknown | 7 | Planned | September | September
TO-26-DND-T124-01 | TSO CUSTOMER TRANSFORMER - DARNDALE 110-DARNDALE 20-T124 | Unknown | Unknown | 5 | Planned | September | September
TO-26-DND-T124-02 | TSO CUSTOMER TRANSFORMER - DARNDALE 110-DARNDALE 20-T124 | Unknown | Unknown | 5 | Planned | September | September
TO-26-FIN GIS-110SB3-5CB-01 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110SB3-5CB | Unknown | Unknown | 8 | Planned | September | September
TO-26-KUD-T101-01 | TSO CUSTOMER TRANSFORMER - KILMAHUD 110-KILMAHUD 10-T101 | Unknown | Unknown | 3 | Planned | September | September
TO-26-OBE-110K1-01 | COUPLER/SECTIONALISING CB - OLDBRIDGE 110-OLDBRIDGE 110-110K1 | Unknown | Unknown | 4 | Planned | September | September
TO-26-OBE-110K2-01 | COUPLER/SECTIONALISING CB - OLDBRIDGE 110-OLDBRIDGE 110-110K2 | Unknown | Unknown | 4 | Planned | September | September
TO-26-OBE-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - OLDBRIDGE 110-OLDBRIDGE 110-110SA1-2CB | Unknown | Unknown | 4 | Planned | September | September
TO-26-OBE-110SB1-2CB-01 | COUPLER/SECTIONALISING CB - OLDBRIDGE 110-OLDBRIDGE 110-110SB1-2CB | Unknown | Unknown | 4 | Planned | September | September
TO-26-SH-110K1-2-02 | COUPLER/SECTIONALISING CB - SHANNONBRIDGE 110-SHANNONBRIDGE 110-110K1-2 | Unknown | Unknown | 8 | Planned | September | September
TO-26-TY-220SA1-01 | SECTIONALISING DISCONNECT - TYNAGH 220-TYNAGH 220-220SA1 | Unknown | Unknown | 1 | Planned | September | September
TO-26-CRO-KBY-1-02 | 110kV FEEDER - COOLROE 110-KILBARRY 110-1 | Unknown | Unknown | 3 | Planned | September | September
TO-26-110 kV A1 @ PLS-01 | BUSBAR SECTION - PORTLAOISE 110-PORTLAOISE 110-110A1 | 2 | 2 | 2 | Scheduled | 24/09/2026 | 25/09/2026
TO-26-110 kV B1 @ PLS-01 | BUSBAR SECTION - PORTLAOISE 110-PORTLAOISE 110-110B1 | 2 | 2 | 2 | Scheduled | 24/09/2026 | 25/09/2026
TO-26-ATY-110SA1-02 | SECTIONALISING DISCONNECT - ATHY 110-ATHY 110-110SA1 | 2 | 2 | 2 | Scheduled | 28/09/2026 | 29/09/2026
TO-26-ATY-110SA2-02 | SECTIONALISING DISCONNECT - ATHY 110-ATHY 110-110SA2 | 2 | 2 | 2 | Scheduled | 28/09/2026 | 29/09/2026
TO-26-ATY-T102-02 | DISTRIBUTION TRANSFORMER - ATHY 110-ATHY 10-T102 | 2 | 2 | 2 | Reference | 28/09/2026 | 29/09/2026
TO-26-BVK-110K2-03 | COUPLER/SECTIONALISING CB - BALLYVOUSKILL 110-BALLYVOUSKILL 110-110K2 | Unknown | Unknown | 2 | Planned | September | September
TO-26-BRT-CLE-4-01 | 220kV FEEDER - BRACETOWN 220-CLONEE 220-4 | Unknown | Unknown | 5 | Planned | September | October
TO-26-CBT-MAY-2-01 | 220kV FEEDER - CASTLEBAGOT 220-MAYNOOTH 220-2 | Unknown | Unknown |  | Planned | September | October
TO-26-CDU-FIN-2-02 | 220kV FEEDER - CORDUFF 220-FINGLAS 220-2 | 2 | 2 | 2 | Proposed | 28/09/2026 | 29/09/2026
TO-26-COR-GWE-1-02 | 110kV FEEDER - CORRACLASSY 110-GORTAWEE 110-1 | Unknown | Unknown | 10 | Planned | September | October
TO-26-220 kV A2 @ FIN-03 | BUSBAR SECTION - FINGLAS 220-FINGLAS 220-220A2 | 2 | 2 | 2 | Proposed | 28/09/2026 | 29/09/2026
TO-26-FIN-220K2-03 | COUPLER/SECTIONALISING CB - FINGLAS 220-FINGLAS 220-220K2 | 2 | 2 | 2 | Proposed | 28/09/2026 | 29/09/2026
TO-26-FIN-220SA1-2CB-03 | COUPLER/SECTIONALISING CB - FINGLAS 220-FINGLAS 220-220SA1-2CB | 2 | 2 | 2 | Proposed | 28/09/2026 | 29/09/2026
TO-26-FIN GIS-110K1-01 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110K1 | Unknown | Unknown | 7 | Planned | September | October
TO-26-MAY-110K3-4-01 | COUPLER/SECTIONALISING CB - MAYNOOTH 110-MAYNOOTH 110-110K3-4 | Unknown | Unknown | 10 | Planned | September | October
TO-26-PB-R2002-04 | CAPACITOR/SVC/REACTOR - POOLBEG 220-POOLBEG 220-R2002 | Unknown | Unknown |  | Planned | September | October
TO-26-MAY-T2101-02 | TRANSFORMER - MAYNOOTH 220-MAYNOOTH 110-T2101 | Unknown | Unknown | 9 | Planned | September | October
TO-26-WOO-T4202-05 | TRANSFORMER - WOODLAND 400-WOODLAND 220-T4202 | 2 | 2 | 2 | Proposed | 30/09/2026 | 01/10/2026
TO-26-GAR-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - GARBALLAGH 110-GARBALLAGH 110-110SA1-2CB | Unknown | Unknown | 1 | Planned | October | October
TO-26-GAR-110SB1-2CB-01 | COUPLER/SECTIONALISING CB - GARBALLAGH 110-GARBALLAGH 110-110SB1-2CB | Unknown | Unknown | 1 | Planned | October | October
TO-26-ARI-T121-01 | DISTRIBUTION TRANSFORMER - ARIGNA 110-ARIGNA 20-T121 | Unknown | Unknown | 5 | Reference (Planned) | October | October
TO-26-ARI,T-ARI-1-02 | 110kV FEEDER - ARIGNA tee-ARIGNA 110-1 | Unknown | Unknown | 5 | Planned | October | October
TO-26-ARI,T-COS-1-03 | 110kV FEEDER - ARIGNA tee-CARRICK ON SHANNON 110-1 | Unknown | Unknown | 5 | Planned | October | October
TO-26-ARI,T-CDY-1-02 | 110kV FEEDER - ARIGNA tee-CORDERRY 110-1 | Unknown | Unknown | 5 | Planned | October | October
TO-26-FIN-220SA1-2CB-12 | COUPLER/SECTIONALISING CB - FINGLAS 220-FINGLAS 220-220SA1-2CB | Unknown | Unknown | 5 | Planned | October | October
TO-26-FIN GIS-110SB4-6CB-03 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110SB4-6CB | Unknown | Unknown | 8 | Planned | October | October
TO-26-KLN-SH-1-03 | 220kV FEEDER - KILLONAN 220-SHANNONBRIDGE 220-1 | Unknown | Unknown | 52 | Planned | October | December
TO-26-PB-220K2-3-02 | COUPLER/SECTIONALISING CB - POOLBEG 220-POOLBEG 220-220K2-3 | Unknown | Unknown | 10 | Planned | October | October
TO-26-PB-220SA1-2-03 | SECTIONALISING DISCONNECT - POOLBEG 220-POOLBEG 220-220SA1-2 | Unknown | Unknown | 10 | Planned | October | October
TO-26-PB-220SB1-2-04 | SECTIONALISING DISCONNECT - POOLBEG 220-POOLBEG 220-220SB1-2 | Unknown | Unknown | 5 | Planned | October | October
TO-26-WOO-T4204-06 | TRANSFORMER - WOODLAND 400-WOODLAND 220-T4204 | Unknown | Unknown | 15 | Planned | October | October
TO-26-FIN GIS-110K2-01 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110K2 | Unknown | Unknown | 3 | Planned | October | October
TO-26-110 kV B1 @ PLS-03 | BUSBAR SECTION - PORTLAOISE 110-PORTLAOISE 110-110B1 | 2 | 2 | 2 | Scheduled | 06/10/2026 | 07/10/2026
TO-26-NEW-PLS-1-03 | 110kV FEEDER - NEWBRIDGE 110-PORTLAOISE 110-1 | 7 | 5 | 5 | Scheduled | 07/10/2026 | 13/10/2026
TO-26-GAR-GOR-1-03 | 110kV FEEDER - GARBALLAGH 110-GORMAN 110-1 | 23 | 16 | 16 | Proposed | 08/10/2026 | 30/10/2026
TO-26-LOU-CAP1-03 | CAPACITOR/SVC/REACTOR - LOUTH 110-LOUTH 110-CAP1 | Unknown | Unknown | 5 | Planned | October | October
TO-26-110 kV A1 @ PLS-03 | BUSBAR SECTION - PORTLAOISE 110-PORTLAOISE 110-110A1 | 6 | 4 | 4 | Scheduled | 08/10/2026 | 13/10/2026
TO-26-AD-HWL-1-01 | 220kV FEEDER - AGHADA 220-HADWELL 220-1 | Unknown | Unknown | 2 | Planned | October | October
TO-26-COS-FLA-2-01 | 110kV FEEDER - CARRICK ON SHANNON 110-FLAGFORD 110-2 | Unknown | Unknown | 10 | Planned | October | October
TO-26-CLE-T221-01 | TSO CUSTOMER TRANSFORMER - CLONEE 220-CLONEE 20-T221 | Unknown | Unknown | 6 | Planned | October | October
TO-26-CUS-NEW-1-03 | 110kV FEEDER - CUSHALING 110-NEWBRIDGE 110-1 | Unknown | Unknown |  | Planned | October | October
TO-26-DEY-110K2-01 | COUPLER/SECTIONALISING CB - DERRYCARNEY 110-DERRYCARNEY 110-110K2 | Unknown | Unknown | 5 | Planned | October | October
TO-26-FIN-220SB1-2CB-05 | COUPLER/SECTIONALISING CB - FINGLAS 220-FINGLAS 220-220SB1-2CB | Unknown | Unknown | 10 | Planned | October | October
TO-26-FIN GIS-110K5-01 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110K5 | Unknown | Unknown | 8 | Planned | October | October
TO-26-MAY-220K1-2-02 | COUPLER/SECTIONALISING CB - MAYNOOTH 220-MAYNOOTH 220-220K1-2 | Unknown | Unknown | 3 | Planned | October | October
TO-26-MAY-T2103-01 | TRANSFORMER - MAYNOOTH 220-MAYNOOTH 110-T2103 | Unknown | Unknown | 19 | Planned | October | November
TO-26-NEW-110SA2-03 | SECTIONALISING DISCONNECT - NEWBRIDGE 110-NEWBRIDGE 110-110SA2 | Unknown | Unknown | 10 | Planned | October | October
TO-26-RAF-T2102-01 | TRANSFORMER - RAFFEEN 220-RAFFEEN 110-T2102 | Unknown | Unknown | 7 | Planned | October | October
TO-26-KPG-T2101-01 | TRANSFORMER - KILPADDOGE 220-KILPADDOGE 110-T2101 | Unknown | Unknown | 4 | Planned | October | October
TO-26-BNK-CBT-2-05 | 110kV FEEDER - BARNAKYLE 110-CASTLEBAGOT 110-2 | Unknown | Unknown | 2 | Planned | October | October
TO-26-PB-TF4-01 | TRANSFORMER - POOLBEG 220-POOLBEG 110-TF4 | Unknown | Unknown | 2 | Reference (Planned) | October | October
TO-26-LLA-TIV-1-02 | 110kV FEEDER - LENALEA 110-TIEVEBRACK 110-1 | Unknown | Unknown | 10 | Planned | October | October
TO-26-BRT-220K2-01 | COUPLER/SECTIONALISING CB - BRACETOWN 220-BRACETOWN 220-220K2 | Unknown | Unknown | 5 | Planned | October | October
TO-26-CKM-PB-1-04 | 220kV FEEDER - CARRICKMINES 220-POOLBEG 220-1 | Unknown | Unknown |  | Planned | October | November
TO-26-CKM-PST2201-04 | TRANSFORMER - CARRICKMINES 220-CARRICKMINES 220-PST2201 | Unknown | Unknown | 24 | Planned | October | November
TO-26-CSH-TY-1-01 | 220kV FEEDER - CASHLA 220-TYNAGH 220-1 | Unknown | Unknown | 5 | Planned | October | October
TO-26-KPG-MP GIS-2-01 | 220kV FEEDER - KILPADDOGE 220-MONEYPOINT GIS 220-2 | Unknown | Unknown | 9 | Planned | October | October
TO-26-LOU-T2101-03 | TRANSFORMER - LOUTH 220-LOUTH 110-T2101 | Unknown | Unknown | 14 | Planned | October | November
TO-26-PB-R223-4-01 | CAPACITOR/SVC/REACTOR - POOLBEG 220-POOLBEG 220-R223-4 | Unknown | Unknown | 6 | Planned | October | October
TO-26-CKM-CKM GIS-1-01 | 220kV FEEDER - CARRICKMINES 220-CARRICKMINES GIS 220-1 | 3 | 2 | 2 | Proposed | 26/10/2026 | 28/10/2026
TO-26-CKM-PB-1-06 | 220kV FEEDER - CARRICKMINES 220-POOLBEG 220-1 | 3 | 2 | 2 | Proposed | 26/10/2026 | 28/10/2026
TO-26-CKM-PST2201-05 | TRANSFORMER - CARRICKMINES 220-CARRICKMINES 220-PST2201 | 3 | 2 | 2 | Proposed | 26/10/2026 | 28/10/2026
TO-26-KRA-110K1-2-02 | COUPLER/SECTIONALISING CB - KNOCKRAHA 110-KNOCKRAHA 110-110K1-2 | Unknown | Unknown | 19 | Planned | October | November
TO-26-CVW-COW-1-01 | 110kV FEEDER - CASTLEVIEW 110-COW CROSS 110-1 | Unknown | Unknown | 14 | Planned | October | November
TO-26-DAL-T141-01 | DISTRIBUTION TRANSFORMER - DALLOW 110-DALLOW 38-T141 | Unknown | Unknown | 14 | Reference (Planned) | October | November
TO-26-DAL,T-DAL-1-01 | 110kV FEEDER - DALLOW tee-DALLOW 110-1 | Unknown | Unknown | 14 | Planned | October | November
TO-26-DAL,T-SH-1-01 | 110kV FEEDER - DALLOW tee-SHANNONBRIDGE 110-1 | Unknown | Unknown | 14 | Planned | October | November
TO-26-DAL,T-STN-1-01 | 110kV FEEDER - DALLOW tee-STONESTOWN 110-1 | Unknown | Unknown | 14 | Planned | October | November
TO-26-FIN GIS-110SA1-3CB-01 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110SA1-3CB | Unknown | Unknown | 8 | Planned | October | November
TO-26-PB-220K3-4-01 | COUPLER/SECTIONALISING CB - POOLBEG 220-POOLBEG 220-220K3-4 | Unknown | Unknown | 4 | Planned | October | October
TO-26-SNU-T104-01 | TSO CUSTOMER TRANSFORMER - SNUGBOROUGH 110-SNUGBOROUGH 10-T104 | Unknown | Unknown | 7 | Planned | October | November
TO-26-BRT-T224-01 | TSO CUSTOMER TRANSFORMER - BRACETOWN 220-BRACETOWN 20-T224 | Unknown | Unknown | 6 | Planned | November | November
TO-26-CF-COR-1-02 | 110kV FEEDER - CATHALEENS FALL 110-CORRACLASSY 110-1 | Unknown | Unknown | 10 | Planned | November | November
TO-26-GI-KKY-1-03 | 110kV FEEDER - GREAT ISLAND 110-KILKENNY 110-1 | 17 | 13 | 13 | Proposed | 04/11/2026 | 20/11/2026
TO-26-AUG-110SA1-2CB-02 | COUPLER/SECTIONALISING CB - AUGHINISH 110-AUGHINISH 110-110SA1-2CB | Unknown | Unknown | 2 | Planned | November | November
TO-26-AUG-CFM-2-02 | 110kV FEEDER - AUGHINISH 110-CASTLEFARM 110-2 | Unknown | Unknown | 2 | Planned | November | November
TO-26-AD-WHI-1-03 | 110kV FEEDER - AGHADA 110-WHITEGATE 110-1 | Unknown | Unknown | 5 | Planned | November | November
TO-26-CLA-T2102-01 | TRANSFORMER - CLASHAVOON 220-CLASHAVOON 110-T2102 | Unknown | Unknown | 10 | Planned | November | November
TO-26-CDU-WOO-1-03 | 220kV FEEDER - CORDUFF 220-WOODLAND 220-1 | 12 | 10 | 10 | Proposed | 09/11/2026 | 20/11/2026
TO-26-COW-WHI-1-01 | 110kV FEEDER - COW CROSS 110-WHITEGATE 110-1 | Unknown | Unknown | 15 | Planned | November | November
TO-26-FIN GIS-110SA2-4CB-02 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110SA2-4CB | Unknown | Unknown | 8 | Planned | November | November
TO-26-KLN-SNG-1-03 | 110kV FEEDER - KILLONAN 110-SINGLAND 110-1 | Unknown | Unknown | 10 | Planned | November | November
TO-26-LOU-110K1-2-03 | COUPLER/SECTIONALISING CB - LOUTH 110-LOUTH 110-110K1-2 | Unknown | Unknown | 8 | Planned | November | November
TO-26-LOU-T2103-03 | TRANSFORMER - LOUTH 220-LOUTH 110-T2103 | Unknown | Unknown | 5 | Planned | November | November
TO-26-MAY-T2104-01 | TRANSFORMER - MAYNOOTH 220-MAYNOOTH 110-T2104 | Unknown | Unknown | 15 | Planned | November | November
TO-26-SNU-T131-01 | TSO CUSTOMER TRANSFORMER - SNUGBOROUGH 110-SNUGBOROUGH 33-T131 | Unknown | Unknown | 4 | Planned | November | November
TO-26-BLU-MUL-1-02 | 110kV FEEDER - BLUNDELSTOWN 110-MULLINGAR 110-1 | Unknown | Unknown |  | Planned | November | December
TO-26-CSH-PRO-1-01 | 220kV FEEDER - CASHLA 220-PROSPECT 220-1 | Unknown | Unknown | 25 | Planned | November | December
TO-26-CVW-COW-1-03 | 110kV FEEDER - CASTLEVIEW 110-COW CROSS 110-1 | Unknown | Unknown | 5 | Planned | November | November
TO-26-COW-110SA2-01 | SECTIONALISING DISCONNECT - COW CROSS 110-COW CROSS 110-110SA2 | Unknown | Unknown | 5 | Planned | November | November
TO-26-DGN-WOH-1-01 | 110kV FEEDER - DUNGARVAN 110-WOODHOUSE 110-1 | Unknown | Unknown | 20 | Planned | November | December
TO-26-FLA-SRA-1-03 | 220kV FEEDER - FLAGFORD 220-SRANANAGH 220-1 | Unknown | Unknown | 10 | Planned | November | November
TO-26-LOU-T2104-06 | TRANSFORMER - LOUTH 220-LOUTH 110-T2104 | Unknown | Unknown | 10 | Planned | November | November
TO-26-MUL-110SA1-2CB-02 | COUPLER/SECTIONALISING CB - MULLINGAR 110-MULLINGAR 110-110SA1-2CB | Unknown | Unknown | 5 | Planned | November | November
TO-26-SNU-T133-01 | TSO CUSTOMER TRANSFORMER - SNUGBOROUGH 110-SNUGBOROUGH 33-T133 | Unknown | Unknown | 4 | Planned | November | November
TO-26-SRA-220SA1-04 | SECTIONALISING DISCONNECT - SRANANAGH 220-SRANANAGH 220-220SA1 | Unknown | Unknown | 5 | Planned | November | November
TO-26-SRA-220SA2-04 | SECTIONALISING DISCONNECT - SRANANAGH 220-SRANANAGH 220-220SA2 | Unknown | Unknown | 6 | Planned | November | November
TO-26-SRA-T2102-04 | TRANSFORMER - SRANANAGH 220-SRANANAGH 110-T2102 | Unknown | Unknown | 10 | Planned | November | November
TO-26-CKM GIS-DSN-1-02 | 220kV FEEDER - CARRICKMINES GIS 220-DUNSTOWN 220-1 | Unknown | Unknown |  | Planned | November | November
TO-26-DSN-MAY-2-03 | 220kV FEEDER - DUNSTOWN 220-MAYNOOTH 220-2 | Unknown | Unknown | 5 | Planned | November | November
TO-26-ARV-NAV-1-01 | 110kV FEEDER - ARVA 110-NAVAN 110-1 | Unknown | Unknown | 9 | Planned | November | December
TO-26-FIN GIS-110SA3-5CB-01 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110SA3-5CB | Unknown | Unknown |  | Planned | November | December
TO-26-GOR-NAV-3-01 | 110kV FEEDER - GORMAN 110-NAVAN 110-3 | Unknown | Unknown | 10 | Planned | November | December
TO-26-KBY-MAL-1-02 | 110kV FEEDER - KILBARRY 110-MALLOW 110-1 | Unknown | Unknown | 7 | Planned | November | December
TO-26-TH-220K1-2-01 | COUPLER/SECTIONALISING CB - TURLOUGH HILL 220-TURLOUGH HILL 220-220K1-2 | Unknown | Unknown | 10 | Planned | November | December
TO-26-WEX-110SA1-2CB-02 | COUPLER/SECTIONALISING CB - WEXFORD 110-WEXFORD 110-110SA1-2CB | Unknown | Unknown | 5 | Planned | November | November
TO-26-WEX-CAP2-02 | CAPACITOR/SVC/REACTOR - WEXFORD 110-WEXFORD 110-CAP2 | Unknown | Unknown | 5 | Planned | November | November
TO-26-WEX-CAP4-02 | CAPACITOR/SVC/REACTOR - WEXFORD 110-WEXFORD 110-CAP4 | Unknown | Unknown | 5 | Planned | November | November
TO-26-FLA-LOU-1-02 | 220kV FEEDER - FLAGFORD 220-LOUTH 220-1 | Unknown | Unknown | 3 | Planned | November | November
TO-26-ARK-LWD-1-01 | 220kV FEEDER - ARKLOW 220-LODGEWOOD 220-1 | Unknown | Unknown | 10 | Planned | November | December
TO-26-ARV-GWE-1-03 | 110kV FEEDER - ARVA 110-GORTAWEE 110-1 | Unknown | Unknown | 10 | Planned | November | December
TO-26-LIM-MTN-1-02 | 110kV FEEDER - LIMERICK 110-MONETEEN 110-1 | Unknown | Unknown | 5 | Planned | November | December
TO-26-CSH-ENN-1-01 | 110kV FEEDER - CASHLA 110-ENNIS 110-1 | Unknown | Unknown | 3 | Planned | December | December
TO-26-KLN-110K1-2-01 | COUPLER/SECTIONALISING CB - KILLONAN 110-KILLONAN 110-110K1-2 | Unknown | Unknown | 2 | Planned | December | December
TO-26-BLU-T131-02 | GENERATOR TRANSFORMER - BLUNDELSTOWN 110-BLUNDELSTOWN 33-T131 | Unknown | Unknown | 2 | Planned | December | December
TO-26-BLU-T131-01 | GENERATOR TRANSFORMER - BLUNDELSTOWN 110-BLUNDELSTOWN 33-T131 | Unknown | Unknown | 2 | Planned | December | December
TO-26-FIN GIS-110SA4-6CB-02 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110SA4-6CB | Unknown | Unknown | 8 | Planned | December | December
TO-26-PB-R2002-05 | CAPACITOR/SVC/REACTOR - POOLBEG 220-POOLBEG 220-R2002 | Unknown | Unknown |  | Planned | December | December
TO-26-RRU-SKL-1-01 | 110kV FEEDER - RATRUSSAN 110-SHANKILL 110-1 | Unknown | Unknown | 8 | Planned | December | December
TO-26-SLI-SRA-2-01 | 110kV FEEDER - SLIGO 110-SRANANAGH 110-2 | Unknown | Unknown | 6 | Planned | December | December
TO-26-BGT-110K1-01 | COUPLER/SECTIONALISING CB - BALLYRAGGET 110-BALLYRAGGET 110-110K1 | Unknown | Unknown | 1 | Planned | December | December
TO-26-110kV A1 @ BGT-01 | BUSBAR SECTION - BALLYRAGGET 110-BALLYRAGGET 110-110A1 | Unknown | Unknown | 1 | Planned | December | December
TO-26-BGT-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - BALLYRAGGET 110-BALLYRAGGET 110-110SA1-2CB | Unknown | Unknown | 1 | Planned | December | December
TO-26-DEY-PLS-1-01 | 110kV FEEDER - DERRYCARNEY 110-PORTLAOISE 110-1 | 11 | 9 | 9 | Proposed | 08/12/2026 | 18/12/2026
TO-26-ARK-SHE-2-02 | 110kV FEEDER - ARKLOW 110-SHELTON ABBEY 110-2 | Unknown | Unknown | 5 | Planned | December | December
TO-26-SHE-T102-01 | TSO CUSTOMER TRANSFORMER - SHELTON ABBEY 110-SHELTON ABBEY 10-T102 | Unknown | Unknown | 5 | Planned | December | December
TO-26-RTN-T131-01 | GENERATOR TRANSFORMER - RATTIN 110-RATTIN 33-T131 | Unknown | Unknown | 1 | Planned | December | December

## GEN_AreaSouthWest
Outage ID | Feeder ID | Calendar Day Duration | Working Day Duration | Work Days | Outage Status | Start | Finish
TO-26-CHA-MAL-1-02 | 110kV FEEDER - CHARLEVILLE 110-MALLOW 110-1 | 5 | 5 | 5 | Scheduled | 05/01/2026 | 09/01/2026
TO-26-PRO-TB-1-02 | 220kV FEEDER - PROSPECT 220-TARBERT 220-1 | 9 | 7 |  | Scheduled | 12/01/2026 | 20/01/2026
TO-26-220 kV A2 @ TB-01 | BUSBAR SECTION - TARBERT 220-TARBERT 220-220A2 | 9 | 7 | 7 | Scheduled | 12/01/2026 | 20/01/2026
TO-26-220 kV B2 @ TB-01 | BUSBAR SECTION - TARBERT 220-TARBERT 220-220B2 | 9 | 7 | 7 | Scheduled | 12/01/2026 | 20/01/2026
TO-26-CAH-TIP-1-01 | 110kV FEEDER - CAHIR 110-TIPPERARY 110-1 | 1 | 1 | 1 | Scheduled | 14/01/2026 | 14/01/2026
TO-26-TIP-110SA1-01 | SECTIONALISING DISCONNECT - TIPPERARY 110-TIPPERARY 110-110SA1 | 1 | 1 | 1 | Scheduled | 14/01/2026 | 14/01/2026
TO-26-TIP-110SA2-01 | SECTIONALISING DISCONNECT - TIPPERARY 110-TIPPERARY 110-110SA2 | 1 | 1 | 1 | Scheduled | 14/01/2026 | 14/01/2026
TO-26-AGL-ENN-1-03 | 110kV FEEDER - AGANNYGAL 110-ENNIS 110-1 | 12 | 10 |  | Scheduled | 19/01/2026 | 30/01/2026
TO-26-KPG-TRL-1-01 | 110kV FEEDER - KILPADDOGE 110-TRALEE 110-1 | 3 | 3 |  | Scheduled | 21/01/2026 | 23/01/2026
TO-26-DSN-MP GIS-1-03 | 400kV FEEDER - DUNSTOWN 400-MONEYPOINT GIS 400-1 | 59 | 42 |  | Scheduled | 03/02/2026 | 02/04/2026
TO-26-LSN-110SA1-2-02 | SECTIONALISING DISCONNECT - LISHEEN 110-LISHEEN 110-110SA1-2 | 5 | 5 | 5 | Scheduled | 09/02/2026 | 13/02/2026
TO-26-LSN-110SA2-4-02 | SECTIONALISING DISCONNECT - LISHEEN 110-LISHEEN 110-110SA2-4 | 5 | 5 | 5 | Scheduled | 09/02/2026 | 13/02/2026
TO-26-LSN-T122-02 | GENERATOR TRANSFORMER - LISHEEN 110-LISHEEN 20-T122 | 5 | 5 | 5 | Scheduled | 09/02/2026 | 13/02/2026
TO-26-LSN-T131-01 | GENERATOR TRANSFORMER - LISHEEN 110-LISHEEN 33-T131 | 9 | 7 | 7 | Scheduled | 09/02/2026 | 17/02/2026
TO-26-LSN-T142-01 | DISTRIBUTION TRANSFORMER - LISHEEN 110-LISHEEN 38-T142 | 5 | 5 | 5 | Reference | 09/02/2026 | 13/02/2026
TO-26-LSN-THU-1-02 | 110kV FEEDER - LISHEEN 110-THURLES 110-1 | 5 | 5 | 5 | Scheduled | 09/02/2026 | 13/02/2026
TO-26-CBA-T131-02 | GENERATOR TRANSFORMER - CLOGHBOOLA 110-CLOGHBOOLA 33-T131 | 3 | 3 | 3 | Scheduled | 10/02/2026 | 12/02/2026
TO-26-DJG-KPG-1-03 | 110kV FEEDER - DROMBEG 110-KILPADDOGE 110-1 | 1 | 1 | 1 | Scheduled | 11/02/2026 | 11/02/2026
TO-26-BYH-STATCOM-03 | CAPACITOR/SVC/REACTOR - BALLYNAHULLA 110-BALLYNAHULLA 110-STATCOM | 1 | 1 | 1 | Scheduled | 18/02/2026 | 18/02/2026
TO-26-CTN-TIP-1-01 | 110kV FEEDER - CAUTEEN 110-TIPPERARY 110-1 | 8 | 6 | 6 | Scheduled | 23/02/2026 | 02/03/2026
TO-26-110 kV A1 @ BVK-02 | BUSBAR SECTION - BALLYVOUSKILL 110-BALLYVOUSKILL 110-110A1 | 19 | 14 | 14 | Scheduled | 02/03/2026 | 20/03/2026
TO-26-110 kV B1 @ BVK-01 | BUSBAR SECTION - BALLYVOUSKILL 110-BALLYVOUSKILL 110-110B1 | 19 | 14 | 14 | Scheduled | 02/03/2026 | 20/03/2026
TO-26-BVK-110K1-01 | COUPLER/SECTIONALISING CB - BALLYVOUSKILL 110-BALLYVOUSKILL 110-110K1 | 19 | 14 | 14 | Scheduled | 02/03/2026 | 20/03/2026
TO-26-BVK-110SA1-2CB-06 | COUPLER/SECTIONALISING CB - BALLYVOUSKILL 110-BALLYVOUSKILL 110-110SA1-2CB | 19 | 14 | 14 | Scheduled | 02/03/2026 | 20/03/2026
TO-26-BVK-110SB1-2CB-04 | COUPLER/SECTIONALISING CB - BALLYVOUSKILL 110-BALLYVOUSKILL 110-110SB1-2CB | 19 | 14 | 14 | Scheduled | 02/03/2026 | 20/03/2026
TO-26-220 kV A1 @ BVK-01 | BUSBAR SECTION - BALLYVOUSKILL 220-BALLYVOUSKILL 220-220A1 | 19 | 14 | 14 | Scheduled | 02/03/2026 | 20/03/2026
TO-26-220 kV B1 @ BVK-01 | BUSBAR SECTION - BALLYVOUSKILL 220-BALLYVOUSKILL 220-220B1 | 19 | 14 | 14 | Scheduled | 02/03/2026 | 20/03/2026
TO-26-BVK-220K1-01 | COUPLER/SECTIONALISING CB - BALLYVOUSKILL 220-BALLYVOUSKILL 220-220K1 | 19 | 14 | 14 | Scheduled | 02/03/2026 | 20/03/2026
TO-26-BVK-220SA1-2CB-05 | COUPLER/SECTIONALISING CB - BALLYVOUSKILL 220-BALLYVOUSKILL 220-220SA1-2CB | 19 | 14 | 14 | Scheduled | 02/03/2026 | 20/03/2026
TO-26-BVK-220SB1-2CB-05 | COUPLER/SECTIONALISING CB - BALLYVOUSKILL 220-BALLYVOUSKILL 220-220SB1-2CB | 19 | 14 | 14 | Scheduled | 02/03/2026 | 20/03/2026
TO-26-BVK-T2101-02 | TRANSFORMER - BALLYVOUSKILL 220-BALLYVOUSKILL 110-T2101 | 19 | 14 | 14 | Scheduled | 02/03/2026 | 20/03/2026
TO-26-KLN-T2103-01 | TRANSFORMER - KILLONAN 220-KILLONAN 110-T2103 | 12 | 10 | 10 | Scheduled | 02/03/2026 | 13/03/2026
TO-26-AA GIS-DRU-1-03 | 110kV FEEDER - ARDNACRUSHA GIS 110-DRUMLINE 110-1 | 4 | 4 |  | Scheduled | 03/03/2026 | 06/03/2026
TO-26-AUG-CFM-1-01 | 110kV FEEDER - AUGHINISH 110-CASTLEFARM 110-1 | 3 | 3 |  | Scheduled | 03/03/2026 | 05/03/2026
TO-26-CFM-T101-01 | TSO CUSTOMER TRANSFORMER - CASTLEFARM 110-CASTLEFARM 10-T101 | 3 | 3 | 3 | Reference | 03/03/2026 | 05/03/2026
TO-26-KPG-KNR-1-01 | 220kV FEEDER - KILPADDOGE 220-KNOCKANURE 220-1 | 1 | 1 | 1 | Scheduled | 04/03/2026 | 04/03/2026
TO-26-KPG-KNR-2-01 | 220kV FEEDER - KILPADDOGE 220-KNOCKANURE 220-2 | 5 | 5 | 5 | Scheduled | 09/03/2026 | 13/03/2026
TO-26-TB-110K1-2-01 | COUPLER/SECTIONALISING CB - TARBERT 110-TARBERT 110-110K1-2 | 2 | 2 | 2 | Scheduled | 10/03/2026 | 11/03/2026
TO-26-110 kV B2 @ KPG-02 | BUSBAR SECTION - KILPADDOGE 110-KILPADDOGE 110-110B2 | 12 | 9 | 9 | Scheduled | 16/03/2026 | 27/03/2026
TO-26-110 kV B4 @ KPG-01 | BUSBAR SECTION - KILPADDOGE 110-KILPADDOGE 110-110B4 | 12 | 9 |  | Scheduled | 16/03/2026 | 27/03/2026
TO-26-KPG-110K4-02 | COUPLER/SECTIONALISING CB - KILPADDOGE 110-KILPADDOGE 110-110K4 | 12 | 9 | 9 | Scheduled | 16/03/2026 | 27/03/2026
TO-26-LIM-RAT-1-01 | 110kV FEEDER - LIMERICK 110-RATHKEALE 110-1 | 5 | 4 |  | Scheduled | 16/03/2026 | 20/03/2026
TO-26-110 kV A2 @ RAT-01 | BUSBAR SECTION - RATHKEALE 110-RATHKEALE 110-110A2 | 4 | 3 | 3 | Scheduled | 16/03/2026 | 19/03/2026
TO-26-RAT-110SA1-02 | SECTIONALISING DISCONNECT - RATHKEALE 110-RATHKEALE 110-110SA1 | 4 | 3 | 3 | Scheduled | 16/03/2026 | 19/03/2026
TO-26-RAT-110SA2-01 | SECTIONALISING DISCONNECT - RATHKEALE 110-RATHKEALE 110-110SA2 | 4 | 3 | 3 | Scheduled | 16/03/2026 | 19/03/2026
TO-26-RAT-T142-01 | DISTRIBUTION TRANSFORMER - RATHKEALE 110-RATHKEALE 38-T142 | 4 | 3 | 3 | Reference | 16/03/2026 | 19/03/2026
TO-26-BVK-CLA-1-02 | 220kV FEEDER - BALLYVOUSKILL 220-CLASHAVOON 220-1 | 1 | 1 | 1 | Scheduled | 20/03/2026 | 20/03/2026
TO-26-DJG-KPG-1-05 | 110kV FEEDER - DROMBEG 110-KILPADDOGE 110-1 | 5 | 5 | 5 | Scheduled | 23/03/2026 | 27/03/2026
TO-26-KPG-RAT-1-02 | 110kV FEEDER - KILPADDOGE 110-RATHKEALE 110-1 | 12 | 9 |  | Scheduled | 23/03/2026 | 03/04/2026
TO-26-400 kV A3 @ MP GIS-01 | BUSBAR SECTION - MONEYPOINT GIS 400-MONEYPOINT GIS 400-400A3 | 11 | 9 | 9 | Scheduled | 23/03/2026 | 02/04/2026
TO-26-400 kV B3 @ MP GIS-01 | BUSBAR SECTION - MONEYPOINT GIS 400-MONEYPOINT GIS 400-400B3 | 11 | 9 | 9 | Scheduled | 23/03/2026 | 02/04/2026
TO-26-MP GIS-400K3-04 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 400-MONEYPOINT GIS 400-400K3 | 11 | 9 | 9 | Scheduled | 23/03/2026 | 02/04/2026
TO-26-MP GIS-400SA1-3CB-05 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 400-MONEYPOINT GIS 400-400SA1-3CB | 11 | 9 | 9 | Scheduled | 23/03/2026 | 02/04/2026
TO-26-MP GIS-400SB1-3CB-05 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 400-MONEYPOINT GIS 400-400SB1-3CB | 11 | 9 | 9 | Scheduled | 23/03/2026 | 02/04/2026
TO-26-MP GIS-T4003-01 | GENERATOR TRANSFORMER - MONEYPOINT GIS 400-MONEYPOINT GIS G3-T4003 | 11 | 9 | 9 | Scheduled | 23/03/2026 | 02/04/2026
TO-26-RAT-110SA1-01 | SECTIONALISING DISCONNECT - RATHKEALE 110-RATHKEALE 110-110SA1 | 5 | 5 | 5 | Scheduled | 23/03/2026 | 27/03/2026
TO-26-RAT-110SA2-02 | SECTIONALISING DISCONNECT - RATHKEALE 110-RATHKEALE 110-110SA2 | 5 | 5 | 5 | Scheduled | 23/03/2026 | 27/03/2026
TO-26-RAT-T141-01 | DISTRIBUTION TRANSFORMER - RATHKEALE 110-RATHKEALE 38-T141 | 5 | 5 | 5 | Reference | 23/03/2026 | 27/03/2026
TO-26-110 kV A1 @ KNR-01 | BUSBAR SECTION - KNOCKANURE 110-KNOCKANURE 110-110A1 | 18 | 12 | 12 | Scheduled | 24/03/2026 | 10/04/2026
TO-26-110 kV B1 @ KNR-01 | BUSBAR SECTION - KNOCKANURE 110-KNOCKANURE 110-110B1 | 18 | 12 | 12 | Scheduled | 24/03/2026 | 10/04/2026
TO-26-KNR-110K1-01 | COUPLER/SECTIONALISING CB - KNOCKANURE 110-KNOCKANURE 110-110K1 | 18 | 12 | 12 | Scheduled | 24/03/2026 | 10/04/2026
TO-26-KNR-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - KNOCKANURE 110-KNOCKANURE 110-110SA1-2CB | 18 | 12 | 12 | Scheduled | 24/03/2026 | 10/04/2026
TO-26-KNR-110SB1-2CB-01 | COUPLER/SECTIONALISING CB - KNOCKANURE 110-KNOCKANURE 110-110SB1-2CB | 18 | 12 | 12 | Scheduled | 24/03/2026 | 10/04/2026
TO-26-220 kV A1 @ KNR-01 | BUSBAR SECTION - KNOCKANURE 220-KNOCKANURE 220-220A1 | 18 | 12 | 12 | Scheduled | 24/03/2026 | 10/04/2026
TO-26-220 kV B1 @ KNR-01 | BUSBAR SECTION - KNOCKANURE 220-KNOCKANURE 220-220B1 | 18 | 12 | 12 | Scheduled | 24/03/2026 | 10/04/2026
TO-26-KNR-220K1-01 | COUPLER/SECTIONALISING CB - KNOCKANURE 220-KNOCKANURE 220-220K1 | 18 | 12 | 12 | Scheduled | 24/03/2026 | 10/04/2026
TO-26-KNR-220SA1-2CB-01 | COUPLER/SECTIONALISING CB - KNOCKANURE 220-KNOCKANURE 220-220SA1-2CB | 18 | 12 | 12 | Scheduled | 24/03/2026 | 10/04/2026
TO-26-KNR-220SB1-2CB-01 | COUPLER/SECTIONALISING CB - KNOCKANURE 220-KNOCKANURE 220-220SB1-2CB | 18 | 12 | 12 | Scheduled | 24/03/2026 | 10/04/2026
TO-26-KNR-T2101-01 | TRANSFORMER - KNOCKANURE 220-KNOCKANURE 110-T2101 | 18 | 12 | 12 | Scheduled | 24/03/2026 | 10/04/2026
TO-26-CLA-CKN-1-01 | 110kV FEEDER - CLASHAVOON 110-CLONKEEN 110-1 | 2 | 2 | 2 | Scheduled | 25/03/2026 | 26/03/2026
TO-26-220 kV B1 @ BYH-01 | BUSBAR SECTION - BALLYNAHULLA 220-BALLYNAHULLA 220-220B1 | 4 | 4 | 4 | Scheduled | 30/03/2026 | 02/04/2026
TO-26-220 kV B2 @ BYH-01 | BUSBAR SECTION - BALLYNAHULLA 220-BALLYNAHULLA 220-220B2 | 4 | 4 | 4 | Scheduled | 30/03/2026 | 02/04/2026
TO-26-BYH-220K1-01 | COUPLER/SECTIONALISING CB - BALLYNAHULLA 220-BALLYNAHULLA 220-220K1 | 4 | 4 | 4 | Scheduled | 30/03/2026 | 02/04/2026
TO-26-BYH-220K2-01 | COUPLER/SECTIONALISING CB - BALLYNAHULLA 220-BALLYNAHULLA 220-220K2 | 4 | 4 | 4 | Scheduled | 30/03/2026 | 02/04/2026
TO-26-BYH-220SA1-2CB-01 | COUPLER/SECTIONALISING CB - BALLYNAHULLA 220-BALLYNAHULLA 220-220SA1-2CB | 4 | 4 | 4 | Scheduled | 30/03/2026 | 02/04/2026
TO-26-BYH-220SB1-2CB-01 | COUPLER/SECTIONALISING CB - BALLYNAHULLA 220-BALLYNAHULLA 220-220SB1-2CB | 4 | 4 | 4 | Scheduled | 30/03/2026 | 02/04/2026
TO-26-CHA-MAL-1-01 | 110kV FEEDER - CHARLEVILLE 110-MALLOW 110-1 | 30 | 20 | 20 | Scheduled | 30/03/2026 | 28/04/2026
TO-26-CKN-KER-1-02 | 110kV FEEDER - CLONKEEN 110-KNOCKEARAGH 110-1 | 3 | 3 | 3 | Scheduled | 31/03/2026 | 02/04/2026
TO-26-KPG-T2102-02 | TRANSFORMER - KILPADDOGE 220-KILPADDOGE 110-T2102 | 1 | 1 | 1 | Scheduled | 31/03/2026 | 31/03/2026
TO-26-220 kV B2 @ KPG-01 | BUSBAR SECTION - KILPADDOGE 220-KILPADDOGE 220-220B2 | 1 | 1 | 1 | Scheduled | 01/04/2026 | 01/04/2026
TO-26-AA GIS-ENN-1-03 | 110kV FEEDER - ARDNACRUSHA GIS 110-ENNIS 110-1 | 11 | 9 | 9 | Scheduled | 07/04/2026 | 17/04/2026
TO-26-BVK-110SA1-2CB-03 | COUPLER/SECTIONALISING CB - BALLYVOUSKILL 110-BALLYVOUSKILL 110-110SA1-2CB | 2 | 2 | 2 | Scheduled | 07/04/2026 | 08/04/2026
TO-26-BVK-110SB1-2CB-03 | COUPLER/SECTIONALISING CB - BALLYVOUSKILL 110-BALLYVOUSKILL 110-110SB1-2CB | 2 | 2 | 2 | Scheduled | 07/04/2026 | 08/04/2026
TO-26-220 kV A1 @ BVK-02 | BUSBAR SECTION - BALLYVOUSKILL 220-BALLYVOUSKILL 220-220A1 | 4 | 4 | 4 | Scheduled | 07/04/2026 | 10/04/2026
TO-26-BVK-220K1-02 | COUPLER/SECTIONALISING CB - BALLYVOUSKILL 220-BALLYVOUSKILL 220-220K1 | 4 | 4 | 4 | Scheduled | 07/04/2026 | 10/04/2026
TO-26-BVK-T2101-03 | TRANSFORMER - BALLYVOUSKILL 220-BALLYVOUSKILL 110-T2101 | 4 | 4 | 4 | Scheduled | 07/04/2026 | 10/04/2026
TO-26-KPG-KNR-1-110-01 | 110kV FEEDER - KILPADDOGE 110-KNOCKANURE 110-1-110 | 11 | 9 | 9 | Scheduled | 07/04/2026 | 17/04/2026
TO-26-KLN-KRA-1-06 | 220kV FEEDER - KILLONAN 220-KNOCKRAHA 220-1 | 10 | 8 | 8 | Scheduled | 08/04/2026 | 17/04/2026
TO-26-AA GIS-T102-01 | GENERATOR TRANSFORMER - ARDNACRUSHA GIS 110-ARDNACRUSHA GIS G2-T102 | 11 | 9 | 9 | Scheduled | 20/04/2026 | 30/04/2026
TO-26-AA GIS-T103-02 | GENERATOR TRANSFORMER - ARDNACRUSHA GIS 110-ARDNACRUSHA GIS G3-T103 | 152 | 107 | 107 | Scheduled | 20/04/2026 | 18/09/2026
TO-26-BVK-220SB1-2CB-03 | COUPLER/SECTIONALISING CB - BALLYVOUSKILL 220-BALLYVOUSKILL 220-220SB1-2CB | 3 | 3 | 3 | Scheduled | 20/04/2026 | 22/04/2026
TO-26-PRO-TB-1-03 | 220kV FEEDER - PROSPECT 220-TARBERT 220-1 | 12 | 10 |  | Scheduled | 20/04/2026 | 01/05/2026
TO-26-AA GIS-110K3-02 | COUPLER/SECTIONALISING CB - ARDNACRUSHA GIS 110-ARDNACRUSHA GIS 110-110K3 | 2 | 2 | 2 | Scheduled | 22/04/2026 | 23/04/2026
TO-26-AA GIS-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - ARDNACRUSHA GIS 110-ARDNACRUSHA GIS 110-110SA1-2CB | 2 | 2 | 2 | Scheduled | 23/04/2026 | 24/04/2026
TO-26-MP GIS-220K1-01 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 220-MONEYPOINT GIS 220-220K1 | 10 | 7 | 7 | Scheduled | 27/04/2026 | 06/05/2026
TO-26-MP GIS-220K2-01 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 220-MONEYPOINT GIS 220-220K2 | 10 | 7 | 7 | Scheduled | 27/04/2026 | 06/05/2026
TO-26-MP GIS-220SA1-2CB-01 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 220-MONEYPOINT GIS 220-220SA1-2CB | 10 | 7 | 7 | Scheduled | 27/04/2026 | 06/05/2026
TO-26-MP GIS-220SB1-2CB-01 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 220-MONEYPOINT GIS 220-220SB1-2CB | 10 | 7 | 7 | Scheduled | 27/04/2026 | 06/05/2026
TO-26-KPG-220K4-01 | COUPLER/SECTIONALISING CB - KILPADDOGE 220-KILPADDOGE 220-220K4 | 3 | 3 | 3 | Scheduled | 28/04/2026 | 30/04/2026
TO-26-KPG-220SA2-4CB-01 | COUPLER/SECTIONALISING CB - KILPADDOGE 220-KILPADDOGE 220-220SA2-4CB | 3 | 3 | 3 | Scheduled | 28/04/2026 | 30/04/2026
TO-26-KPG-220SB2-4CB-01 | COUPLER/SECTIONALISING CB - KILPADDOGE 220-KILPADDOGE 220-220SB2-4CB | 3 | 3 | 3 | Scheduled | 28/04/2026 | 30/04/2026
TO-26-MP GIS-T4002-02 | GENERATOR TRANSFORMER - MONEYPOINT GIS 400-MONEYPOINT GIS G2-T4002 | 89 | 61 | 61 | Scheduled | 01/05/2026 | 28/07/2026
TO-26-CLH-T122-01 | GENERATOR TRANSFORMER - CLAHANE 110-CLAHANE 20-T122 | 4 | 4 | 4 | Scheduled | 05/05/2026 | 08/05/2026
TO-26-220 kV A1 @ MP GIS-01 | BUSBAR SECTION - MONEYPOINT GIS 220-MONEYPOINT GIS 220-220A1 | 14 | 10 | 10 | Scheduled | 05/05/2026 | 18/05/2026
TO-26-220 kV B1 @ MP GIS-01 | BUSBAR SECTION - MONEYPOINT GIS 220-MONEYPOINT GIS 220-220B1 | 14 | 10 | 10 | Scheduled | 05/05/2026 | 18/05/2026
TO-26-MP GIS-220K1-05 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 220-MONEYPOINT GIS 220-220K1 | 14 | 10 | 10 | Scheduled | 05/05/2026 | 18/05/2026
TO-26-MP GIS-220SA1-2CB-03 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 220-MONEYPOINT GIS 220-220SA1-2CB | 14 | 10 | 10 | Scheduled | 05/05/2026 | 18/05/2026
TO-26-MP GIS-220SB1-2CB-02 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 220-MONEYPOINT GIS 220-220SB1-2CB | 14 | 10 | 10 | Scheduled | 05/05/2026 | 18/05/2026
TO-26-400 kV A1 @ MP GIS-02 | BUSBAR SECTION - MONEYPOINT GIS 400-MONEYPOINT GIS 400-400A1 | 14 | 10 | 10 | Scheduled | 05/05/2026 | 18/05/2026
TO-26-400 kV B1 @ MP GIS-02 | BUSBAR SECTION - MONEYPOINT GIS 400-MONEYPOINT GIS 400-400B1 | 14 | 10 | 10 | Scheduled | 05/05/2026 | 18/05/2026
TO-26-MP GIS-400SA1-2CB-03 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 400-MONEYPOINT GIS 400-400SA1-2CB | 14 | 10 | 10 | Scheduled | 05/05/2026 | 18/05/2026
TO-26-MP GIS-400SA1-3CB-06 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 400-MONEYPOINT GIS 400-400SA1-3CB | 14 | 10 | 10 | Scheduled | 05/05/2026 | 18/05/2026
TO-26-MP GIS-400SB1-2CB-03 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 400-MONEYPOINT GIS 400-400SB1-2CB | 14 | 10 | 10 | Scheduled | 05/05/2026 | 18/05/2026
TO-26-MP GIS-400SB1-3CB-06 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 400-MONEYPOINT GIS 400-400SB1-3CB | 14 | 10 | 10 | Scheduled | 05/05/2026 | 18/05/2026
TO-26-THU-STATCOM-02 | CAPACITOR/SVC/REACTOR - THURLES 110-THURLES 110-STATCOM | 4 | 4 | 4 | Scheduled | 05/05/2026 | 08/05/2026
TO-26-AUG-MTN-1-01 | 110kV FEEDER - AUGHINISH 110-MONETEEN 110-1 | 2 | 2 | 2 | Scheduled | 06/05/2026 | 07/05/2026
TO-26-CNO-T131-01 | GENERATOR TRANSFORMER - COOLNANOONAGH 110-COOLNANOONAGH 33-T131 | 2 | 2 | 2 | Scheduled | 06/05/2026 | 07/05/2026
TO-26-KHL-T131-01 | GENERATOR TRANSFORMER - KILL HILL 110-KILL HILL 33-T131 | 2 | 2 |  | Scheduled | 07/05/2026 | 08/05/2026
TO-26-MP GIS-T4201-01 | TRANSFORMER - MONEYPOINT GIS 400-MONEYPOINT GIS 220-T4201 | 14 | 10 | 10 | Scheduled | 07/05/2026 | 20/05/2026
TO-26-AA GIS-T104-01 | GENERATOR TRANSFORMER - ARDNACRUSHA GIS 110-ARDNACRUSHA GIS G4-T104 | 5 | 5 | 5 | Scheduled | 11/05/2026 | 15/05/2026
TO-26-220 kV A1 @ BYH-01 | BUSBAR SECTION - BALLYNAHULLA 220-BALLYNAHULLA 220-220A1 | 8 | 6 | 6 | Scheduled | 11/05/2026 | 18/05/2026
TO-26-220 kV B1 @ BYH-02 | BUSBAR SECTION - BALLYNAHULLA 220-BALLYNAHULLA 220-220B1 | 8 | 6 | 6 | Scheduled | 11/05/2026 | 18/05/2026
TO-26-BYH-220K1-02 | COUPLER/SECTIONALISING CB - BALLYNAHULLA 220-BALLYNAHULLA 220-220K1 | 8 | 6 | 6 | Scheduled | 11/05/2026 | 18/05/2026
TO-26-BYH-220SA1-2CB-04 | COUPLER/SECTIONALISING CB - BALLYNAHULLA 220-BALLYNAHULLA 220-220SA1-2CB | 8 | 6 | 6 | Scheduled | 11/05/2026 | 18/05/2026
TO-26-BYH-220SB1-2CB-04 | COUPLER/SECTIONALISING CB - BALLYNAHULLA 220-BALLYNAHULLA 220-220SB1-2CB | 8 | 6 | 6 | Scheduled | 11/05/2026 | 18/05/2026
TO-26-BYH-KNR-1-01 | 220kV FEEDER - BALLYNAHULLA 220-KNOCKANURE 220-1 | 8 | 6 | 6 | Scheduled | 11/05/2026 | 18/05/2026
TO-26-220 kV A2 @ KNR-01 | BUSBAR SECTION - KNOCKANURE 220-KNOCKANURE 220-220A2 | 8 | 6 | 6 | Scheduled | 11/05/2026 | 18/05/2026
TO-26-220 kV B2 @ KNR-01 | BUSBAR SECTION - KNOCKANURE 220-KNOCKANURE 220-220B2 | 8 | 6 | 6 | Scheduled | 11/05/2026 | 18/05/2026
TO-26-KNR-220K2-03 | COUPLER/SECTIONALISING CB - KNOCKANURE 220-KNOCKANURE 220-220K2 | 8 | 6 | 6 | Scheduled | 11/05/2026 | 18/05/2026
TO-26-KNR-220SA1-2CB-02 | COUPLER/SECTIONALISING CB - KNOCKANURE 220-KNOCKANURE 220-220SA1-2CB | 8 | 6 | 6 | Scheduled | 11/05/2026 | 18/05/2026
TO-26-KNR-220SB1-2CB-02 | COUPLER/SECTIONALISING CB - KNOCKANURE 220-KNOCKANURE 220-220SB1-2CB | 8 | 6 | 6 | Scheduled | 11/05/2026 | 18/05/2026
TO-26-BVK-STATCOM-01 | CAPACITOR/SVC/REACTOR - BALLYVOUSKILL 110-BALLYVOUSKILL 110-STATCOM | 5 | 5 | 5 | Scheduled | 18/05/2026 | 22/05/2026
TO-26-GLE-KCR-1-01 | 110kV FEEDER - GLENLARA 110-KNOCKACUMMER 110-1 | 19 | 14 | 14 | Scheduled | 18/05/2026 | 05/06/2026
TO-26-KCR-T121-01 | GENERATOR TRANSFORMER - KNOCKACUMMER 110-KNOCKACUMMER 20-T121 | 19 | 14 | 14 | Scheduled | 18/05/2026 | 05/06/2026
TO-26-AHA-KLN-2-01 | 110kV FEEDER - AHANE 110-KILLONAN 110-2 | 2 | 2 | 2 | Reference | 20/05/2026 | 21/05/2026
TO-26-AHA-T102-01 | DISTRIBUTION TRANSFORMER - AHANE 110-AHANE 10-T102 | 2 | 2 | 2 | Reference | 20/05/2026 | 21/05/2026
TO-26-AA GIS-T141-01 | DISTRIBUTION TRANSFORMER - ARDNACRUSHA GIS 110-ARDNACRUSHA GIS 38-T141 | 2 | 2 | 2 | Reference | 20/05/2026 | 21/05/2026
TO-26-BYH-STATCOM-04 | CAPACITOR/SVC/REACTOR - BALLYNAHULLA 110-BALLYNAHULLA 110-STATCOM | 5 | 5 | 5 | Scheduled | 25/05/2026 | 29/05/2026
TO-26-220 kV A2 @ KPG-01 | BUSBAR SECTION - KILPADDOGE 220-KILPADDOGE 220-220A2 | 5 | 5 | 5 | Scheduled | 25/05/2026 | 29/05/2026
TO-26-220 kV B2 @ KPG-02 | BUSBAR SECTION - KILPADDOGE 220-KILPADDOGE 220-220B2 | 5 | 5 | 5 | Scheduled | 25/05/2026 | 29/05/2026
TO-26-KPG-220SA1-2CB-01 | COUPLER/SECTIONALISING CB - KILPADDOGE 220-KILPADDOGE 220-220SA1-2CB | 5 | 5 | 5 | Scheduled | 25/05/2026 | 29/05/2026
TO-26-KPG-220SA2-4CB-04 | COUPLER/SECTIONALISING CB - KILPADDOGE 220-KILPADDOGE 220-220SA2-4CB | 5 | 5 | 5 | Scheduled | 25/05/2026 | 29/05/2026
TO-26-KPG-220SB1-2CB-01 | COUPLER/SECTIONALISING CB - KILPADDOGE 220-KILPADDOGE 220-220SB1-2CB | 5 | 5 | 5 | Scheduled | 25/05/2026 | 29/05/2026
TO-26-KPG-220SB2-4CB-04 | COUPLER/SECTIONALISING CB - KILPADDOGE 220-KILPADDOGE 220-220SB2-4CB | 5 | 5 | 5 | Scheduled | 25/05/2026 | 29/05/2026
TO-26-KPG-TB-2-01 | 220kV FEEDER - KILPADDOGE 220-TARBERT 220-2 | 5 | 5 | 5 | Scheduled | 25/05/2026 | 29/05/2026
TO-26-MP GIS-T4001-05 | GENERATOR TRANSFORMER - MONEYPOINT GIS 400-MONEYPOINT GIS G1-T4001 | 16 | 11 | 11 | Scheduled | 25/05/2026 | 09/06/2026
TO-26-220 kV A2 @ TB-02 | BUSBAR SECTION - TARBERT 220-TARBERT 220-220A2 | 5 | 5 | 5 | Scheduled | 25/05/2026 | 29/05/2026
TO-26-220 kV B2 @ TB-02 | BUSBAR SECTION - TARBERT 220-TARBERT 220-220B2 | 5 | 5 | 5 | Scheduled | 25/05/2026 | 29/05/2026
TO-26-TRL-CAP2-03 | CAPACITOR/SVC/REACTOR - TRALEE 110-TRALEE 110-CAP2 | 15 | 10 | 10 | Scheduled | 25/05/2026 | 08/06/2026
TO-26-BYH-CDL-1-01 | 110kV FEEDER - BALLYNAHULLA 110-CORDAL 110-1 | 32 | 24 | 24 | Scheduled | 02/06/2026 | 03/07/2026
TO-26-CDL-110SA1-01 | SECTIONALISING DISCONNECT - CORDAL 110-CORDAL 110-110SA1 | 32 | 24 | 24 | Scheduled | 02/06/2026 | 03/07/2026
TO-26-CDL-110SA2-01 | SECTIONALISING DISCONNECT - CORDAL 110-CORDAL 110-110SA2 | 32 | 24 | 24 | Scheduled | 02/06/2026 | 03/07/2026
TO-26-CDL-T132-02 | GENERATOR TRANSFORMER - CORDAL 110-CORDAL 33-T132 | 32 | 24 | 24 | Scheduled | 02/06/2026 | 03/07/2026
TO-26-CDL-T141-01 | DISTRIBUTION TRANSFORMER - CORDAL 110-CORDAL 38-T141 | 32 | 24 | 24 | Reference | 02/06/2026 | 03/07/2026
TO-26-KLN-KPG-1-02 | 220kV FEEDER - KILLONAN 220-KILPADDOGE 220-1 | 58 | 42 | 42 | Scheduled | 02/06/2026 | 29/07/2026
TO-26-KLN-T2101-03 | TRANSFORMER - KILLONAN 220-KILLONAN 110-T2101 | 4 | 4 | 4 | Scheduled | 02/06/2026 | 05/06/2026
TO-26-MP GIS-T4202-01 | TRANSFORMER - MONEYPOINT GIS 400-MONEYPOINT GIS 220-T4202 | 11 | 9 |  | Scheduled | 02/06/2026 | 12/06/2026
TO-26-AA GIS-110SB1-3CB-01 | COUPLER/SECTIONALISING CB - ARDNACRUSHA GIS 110-ARDNACRUSHA GIS 110-110SB1-3CB | 1 | 1 | 1 | Proposed | 08/06/2026 | 08/06/2026
TO-26-AUG-CFM-1-02 | 110kV FEEDER - AUGHINISH 110-CASTLEFARM 110-1 | 5 | 5 | 5 | Scheduled | 08/06/2026 | 12/06/2026
TO-26-CFM-T101-02 | TSO CUSTOMER TRANSFORMER - CASTLEFARM 110-CASTLEFARM 10-T101 | 5 | 5 | 5 | Reference | 08/06/2026 | 12/06/2026
TO-26-AA GIS-110SA1-3CB-02 | COUPLER/SECTIONALISING CB - ARDNACRUSHA GIS 110-ARDNACRUSHA GIS 110-110SA1-3CB | 2 | 2 | 2 | Proposed | 09/06/2026 | 10/06/2026
TO-26-CHA-KLN-1-02 | 110kV FEEDER - CHARLEVILLE 110-KILLONAN 110-1 | 7 | 5 | 5 | Proposed | 09/06/2026 | 15/06/2026
TO-26-110 kV A1 @ AA GIS-01 | BUSBAR SECTION - ARDNACRUSHA GIS 110-ARDNACRUSHA GIS 110-110A1 | 9 | 7 | 7 | Proposed | 11/06/2026 | 19/06/2026
TO-26-110 kV B1 @ AA GIS-01 | BUSBAR SECTION - ARDNACRUSHA GIS 110-ARDNACRUSHA GIS 110-110B1 | 9 | 7 | 7 | Proposed | 11/06/2026 | 19/06/2026
TO-26-AA GIS-110SA1-2CB-02 | COUPLER/SECTIONALISING CB - ARDNACRUSHA GIS 110-ARDNACRUSHA GIS 110-110SA1-2CB | 9 | 7 | 7 | Proposed | 11/06/2026 | 19/06/2026
TO-26-AA GIS-110SA1-3CB-01 | COUPLER/SECTIONALISING CB - ARDNACRUSHA GIS 110-ARDNACRUSHA GIS 110-110SA1-3CB | 9 | 7 | 7 | Proposed | 11/06/2026 | 19/06/2026
TO-26-AA GIS-110SB1-2CB-02 | COUPLER/SECTIONALISING CB - ARDNACRUSHA GIS 110-ARDNACRUSHA GIS 110-110SB1-2CB | 9 | 7 | 7 | Proposed | 11/06/2026 | 19/06/2026
TO-26-AA GIS-110SB1-3CB-03 | COUPLER/SECTIONALISING CB - ARDNACRUSHA GIS 110-ARDNACRUSHA GIS 110-110SB1-3CB | 9 | 7 | 7 | Proposed | 11/06/2026 | 19/06/2026
TO-26-AA GIS-T103-01 | GENERATOR TRANSFORMER - ARDNACRUSHA GIS 110-ARDNACRUSHA GIS G3-T103 | 9 | 7 | 7 | Proposed | 11/06/2026 | 19/06/2026
TO-26-ATE-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - ATHEA 110-ATHEA 110-110SA1-2CB | 5 | 5 | 5 | Proposed | 15/06/2026 | 19/06/2026
TO-26-ATE-DRO-1-01 | 110kV FEEDER - ATHEA 110-DROMADA 110-1 | 5 | 5 | 5 | Proposed | 15/06/2026 | 19/06/2026
TO-26-ATE-KNR-1-01 | 110kV FEEDER - ATHEA 110-KNOCKANURE 110-1 | 5 | 5 | 5 | Proposed | 15/06/2026 | 19/06/2026
TO-26-ATE-T121-02 | GENERATOR TRANSFORMER - ATHEA 110-ATHEA 20-T121 | 5 | 5 | 5 | Scheduled | 15/06/2026 | 19/06/2026
TO-26-ATE-TOB-1-01 | 110kV FEEDER - ATHEA 110-TOBERTOREEN 110-1 | 5 | 5 | 5 | Proposed | 15/06/2026 | 19/06/2026
TO-26-BVK-T2102-02 | TRANSFORMER - BALLYVOUSKILL 220-BALLYVOUSKILL 110-T2102 | 5 | 5 | 5 | Proposed | 15/06/2026 | 19/06/2026
TO-26-DRO-T121-01 | GENERATOR TRANSFORMER - DROMADA 110-DROMADA 20-T121 | 5 | 5 | 5 | Proposed | 15/06/2026 | 19/06/2026
TO-26-DJG-KPG-1-01 | 110kV FEEDER - DROMBEG 110-KILPADDOGE 110-1 | 5 | 5 | 5 | Proposed | 15/06/2026 | 19/06/2026
TO-26-TOB-T132-01 | GENERATOR TRANSFORMER - TOBERTOREEN 110-TOBERTOREEN 33-T132 | 1 | 1 | 1 | Proposed | 15/06/2026 | 15/06/2026
TO-26-TOB-T132-02 | GENERATOR TRANSFORMER - TOBERTOREEN 110-TOBERTOREEN 33-T132 | 5 | 5 | 5 | Proposed | 15/06/2026 | 19/06/2026
TO-26-CBA-110SA1-01 | SECTIONALISING DISCONNECT - CLOGHBOOLA 110-CLOGHBOOLA 110-110SA1 | 17 | 13 | 13 | Proposed | 16/06/2026 | 02/07/2026
TO-26-CBA-110SA2-01 | SECTIONALISING DISCONNECT - CLOGHBOOLA 110-CLOGHBOOLA 110-110SA2 | 17 | 13 | 13 | Proposed | 16/06/2026 | 02/07/2026
TO-26-CBA-T122-01 | DISTRIBUTION TRANSFORMER - CLOGHBOOLA 110-CLOGHBOOLA 20-T122 | 17 | 13 | 13 | Reference (Proposed) | 16/06/2026 | 02/07/2026
TO-26-CBA-T131-01 | GENERATOR TRANSFORMER - CLOGHBOOLA 110-CLOGHBOOLA 33-T131 | 17 | 13 | 13 | Proposed | 16/06/2026 | 02/07/2026
TO-26-CBA-TRI-1-01 | 110kV FEEDER - CLOGHBOOLA 110-TRIEN 110-1 | 17 | 13 | 13 | Proposed | 16/06/2026 | 02/07/2026
TO-26-TB-T102-01 | GENERATOR TRANSFORMER - TARBERT 110-TARBERT G2-T102 | 2 | 2 | 2 | Proposed | 16/06/2026 | 17/06/2026
TO-26-AA GIS-CAP1-02 | CAPACITOR/SVC/REACTOR - ARDNACRUSHA GIS 110-ARDNACRUSHA GIS 110-CAP1 | 10 | 8 | 8 | Proposed | 22/06/2026 | 01/07/2026
TO-26-220 kV A1 @ KLN-01 | BUSBAR SECTION - KILLONAN 220-KILLONAN 220-220A1 | 26 | 20 | 20 | Proposed | 22/06/2026 | 17/07/2026
TO-26-220 kV A2 @ KLN-02 | BUSBAR SECTION - KILLONAN 220-KILLONAN 220-220A2 | 26 | 20 | 20 | Proposed | 22/06/2026 | 17/07/2026
TO-26-KLN-220K1-2-01 | COUPLER/SECTIONALISING CB - KILLONAN 220-KILLONAN 220-220K1-2 | 26 | 20 | 20 | Proposed | 22/06/2026 | 17/07/2026
TO-26-KPG-T122-01 | DISTRIBUTION TRANSFORMER - KILPADDOGE 110-KILPADDOGE 20-T122 | 5 | 5 | 5 | Reference | 22/06/2026 | 26/06/2026
TO-26-AA GIS-110K2-01 | COUPLER/SECTIONALISING CB - ARDNACRUSHA GIS 110-ARDNACRUSHA GIS 110-110K2 | 2 | 2 | 2 | Proposed | 23/06/2026 | 24/06/2026
TO-26-CDL-T132-01 | GENERATOR TRANSFORMER - CORDAL 110-CORDAL 33-T132 | 1 | 1 | 1 | Proposed | 26/06/2026 | 26/06/2026
TO-26-BVK-COT-1-01 | 110kV FEEDER - BALLYVOUSKILL 110-COOMATAGGART 110-1 | 12 | 10 |  | Proposed | 29/06/2026 | 10/07/2026
TO-26-BOL-110SA1-01 | SECTIONALISING DISCONNECT - BOOLTIAGH 110-BOOLTIAGH 110-110SA1 | 9 | 7 | 7 | Proposed | 29/06/2026 | 07/07/2026
TO-26-BOL-110SA1-3CB-01 | COUPLER/SECTIONALISING CB - BOOLTIAGH 110-BOOLTIAGH 110-110SA1-3CB | 9 | 7 | 7 | Proposed | 29/06/2026 | 07/07/2026
TO-26-BOL-T121-01 | GENERATOR TRANSFORMER - BOOLTIAGH 110-BOOLTIAGH 20-T121 | 9 | 7 | 7 | Proposed | 29/06/2026 | 07/07/2026
TO-26-COT-110SA1-01 | SECTIONALISING DISCONNECT - COOMATAGGART 110-COOMATAGGART 110-110SA1 | 12 | 10 | 10 | Proposed | 29/06/2026 | 10/07/2026
TO-26-COT-110SA2-01 | SECTIONALISING DISCONNECT - COOMATAGGART 110-COOMATAGGART 110-110SA2 | 12 | 10 | 10 | Proposed | 29/06/2026 | 10/07/2026
TO-26-COT-FILTER1-01 | CAPACITOR/SVC/REACTOR - COOMATAGGART 110-COOMATAGGART 110-FILTER1 | 12 | 10 | 10 | Proposed | 29/06/2026 | 10/07/2026
TO-26-COT-T132-01 | GENERATOR TRANSFORMER - COOMATAGGART 110-COOMATAGGART 33-T132 | 5 | 5 | 5 | Proposed | 29/06/2026 | 03/07/2026
TO-26-COT-T132-02 | GENERATOR TRANSFORMER - COOMATAGGART 110-COOMATAGGART 33-T132 | 12 | 10 | 10 | Proposed | 29/06/2026 | 10/07/2026
TO-26-COT-T141-01 | DISTRIBUTION TRANSFORMER - COOMATAGGART 110-COOMATAGGART 38-T141 | 12 | 10 | 10 | Reference (Proposed) | 29/06/2026 | 10/07/2026
TO-26-KPG-MP GIS-1-02 | 220kV FEEDER - KILPADDOGE 220-MONEYPOINT GIS 220-1 | 12 | 10 | 10 | Proposed | 29/06/2026 | 10/07/2026
TO-26-SK-T104-04 | GENERATOR TRANSFORMER - SEALROCK 110-SEALROCK G4-T104 | 5 | 5 | 5 | Proposed | 29/06/2026 | 03/07/2026
TO-26-TBK-T141-01 | DISTRIBUTION TRANSFORMER - TULLABRACK 110-TULLABRACK 38-T141 | 9 | 7 | 7 | Reference (Proposed) | 29/06/2026 | 07/07/2026
TO-26-TBK,T-BOL-1-01 | 110kV FEEDER - TULLABRACK tee-BOOLTIAGH 110-1 | 9 | 7 | 7 | Proposed | 29/06/2026 | 07/07/2026
TO-26-TBK,T-MP GIS-1-01 | 110kV FEEDER - TULLABRACK tee-MONEYPOINT GIS 110-1 | 9 | 7 | 7 | Proposed | 29/06/2026 | 07/07/2026
TO-26-TBK,T-TBK-1-01 | 110kV FEEDER - TULLABRACK tee-TULLABRACK 110-1 | 9 | 7 | 7 | Proposed | 29/06/2026 | 07/07/2026
TO-26-AUG-SK-4-02 | 110kV FEEDER - AUGHINISH 110-SEALROCK 110-4 | 3 | 3 | 3 | Proposed | 01/07/2026 | 03/07/2026
TO-26-KHL-THU-1-02 | 110kV FEEDER - KILL HILL 110-THURLES 110-1 | 2 | 2 | 2 | Proposed | 01/07/2026 | 02/07/2026
TO-26-SK-T104-02 | GENERATOR TRANSFORMER - SEALROCK 110-SEALROCK G4-T104 | 3 | 3 | 3 | Proposed | 01/07/2026 | 03/07/2026
TO-26-CLH-TRL-1-02 | 110kV FEEDER - CLAHANE 110-TRALEE 110-1 | 12 | 10 | 10 | Proposed | 06/07/2026 | 17/07/2026
TO-26-DRU-CAP2-01 | CAPACITOR/SVC/REACTOR - DRUMLINE 110-DRUMLINE 110-CAP2 | 10 | 8 | 8 | Proposed | 06/07/2026 | 15/07/2026
TO-26-IKE-T141-01 | DISTRIBUTION TRANSFORMER - IKERRIN 110-IKERRIN 38-T141 | 5 | 5 | 5 | Reference (Proposed) | 06/07/2026 | 10/07/2026
TO-26-IKE,T-IKE-1-01 | 110kV FEEDER - IKERRIN tee-IKERRIN 110-1 | 5 | 5 | 5 | Proposed | 06/07/2026 | 10/07/2026
TO-26-IKE,T-TMY1-01 | 110kV FEEDER - IKERRIN tee-TIMONEY 110-1 | 5 | 5 | 5 | Proposed | 06/07/2026 | 10/07/2026
TO-26-KLN-LIM-1-02 | 110kV FEEDER - KILLONAN 110-LIMERICK 110-1 | 12 | 10 | 10 | Proposed | 06/07/2026 | 17/07/2026
TO-26-KNR-T2102-01 | TRANSFORMER - KNOCKANURE 220-KNOCKANURE 110-T2102 | 11 | 9 | 9 | Proposed | 06/07/2026 | 16/07/2026
TO-26-REM-110SA1-01 | SECTIONALISING DISCONNECT - REAMORE 110-REAMORE 110-110SA1 | 19 | 15 | 15 | Proposed | 06/07/2026 | 24/07/2026
TO-26-REM-110SA2-01 | SECTIONALISING DISCONNECT - REAMORE 110-REAMORE 110-110SA2 | 19 | 15 | 15 | Proposed | 06/07/2026 | 24/07/2026
TO-26-REM-T141-01 | DISTRIBUTION TRANSFORMER - REAMORE 110-REAMORE 38-T141 | 19 | 15 | 15 | Reference (Proposed) | 06/07/2026 | 24/07/2026
TO-26-REM-T142-01 | DISTRIBUTION TRANSFORMER - REAMORE 110-REAMORE 38-T142 | 19 | 15 | 15 | Reference (Proposed) | 06/07/2026 | 24/07/2026
TO-26-REM-TRL-1-01 | 110kV FEEDER - REAMORE 110-TRALEE 110-1 | 19 | 15 |  | Proposed | 06/07/2026 | 24/07/2026
TO-26-ENN-SLC-1-02 | 110kV FEEDER - ENNIS 110-SLIEVECALLAN 110-1 | 2 | 2 | 2 | Proposed | 07/07/2026 | 08/07/2026
TO-26-SLC-110SA2-02 | SECTIONALISING DISCONNECT - SLIEVECALLAN 110-SLIEVECALLAN 110-110SA2 | 2 | 2 | 2 | Proposed | 07/07/2026 | 08/07/2026
TO-26-SLC-T121-02 | GENERATOR TRANSFORMER - SLIEVECALLAN 110-SLIEVECALLAN 20-T121 | 2 | 2 | 2 | Proposed | 07/07/2026 | 08/07/2026
TO-26-SLC-T122-02 | GENERATOR TRANSFORMER - SLIEVECALLAN 110-SLIEVECALLAN 20-T122 | 2 | 2 | 2 | Proposed | 07/07/2026 | 08/07/2026
TO-26-SLC-T122-03 | GENERATOR TRANSFORMER - SLIEVECALLAN 110-SLIEVECALLAN 20-T122 | 2 | 2 | 2 | Proposed | 07/07/2026 | 08/07/2026
TO-26-SLC-110SA1-02 | SECTIONALISING DISCONNECT - SLIEVECALLAN 110-SLIEVECALLAN 110-110SA1 | 2 | 2 | 2 | Proposed | 08/07/2026 | 09/07/2026
TO-26-KPG-TB-1-03 | 220kV FEEDER - KILPADDOGE 220-TARBERT 220-1 | 9 | 7 | 7 | Proposed | 13/07/2026 | 21/07/2026
TO-26-BYH-T2101-01 | TRANSFORMER - BALLYNAHULLA 220-BALLYNAHULLA 110-T2101 | 1 | 1 | 1 | Proposed | 14/07/2026 | 14/07/2026
TO-26-AA GIS-LIM-1-01 | 110kV FEEDER - ARDNACRUSHA GIS 110-LIMERICK 110-1 | 12 | 10 | 10 | Proposed | 20/07/2026 | 31/07/2026
TO-26-DSN-MP GIS-1-02 | 400kV FEEDER - DUNSTOWN 400-MONEYPOINT GIS 400-1 | 40 | 29 | 29 | Proposed | 20/07/2026 | 28/08/2026
TO-26-BOL-ENN-1-01 | 110kV FEEDER - BOOLTIAGH 110-ENNIS 110-1 | 10 | 8 | 8 | Proposed | 22/07/2026 | 31/07/2026
TO-26-CAH-KHL-1-01 | 110kV FEEDER - CAHIR 110-KILL HILL 110-1 | 2 | 2 | 2 | Proposed | 22/07/2026 | 23/07/2026
TO-26-THU-CAP1-01 | CAPACITOR/SVC/REACTOR - THURLES 110-THURLES 110-CAP1 | 3 | 3 | 3 | Proposed | 22/07/2026 | 24/07/2026
TO-26-CHA-110SA1-2CB-02 | COUPLER/SECTIONALISING CB - CHARLEVILLE 110-CHARLEVILLE 110-110SA1-2CB | 10 | 7 | 7 | Proposed | 27/07/2026 | 05/08/2026
TO-26-MP GIS-T4002-01 | GENERATOR TRANSFORMER - MONEYPOINT GIS 400-MONEYPOINT GIS G2-T4002 | 2 | 2 | 2 | Proposed | 27/07/2026 | 28/07/2026
TO-26-110 kV A3 @ BOL-01 | BUSBAR SECTION - BOOLTIAGH 110-BOOLTIAGH 110-110A3 | 4 | 4 | 4 | Proposed | 28/07/2026 | 31/07/2026
TO-26-BOL-110SA1-3CB-02 | COUPLER/SECTIONALISING CB - BOOLTIAGH 110-BOOLTIAGH 110-110SA1-3CB | 4 | 4 | 4 | Proposed | 28/07/2026 | 31/07/2026
TO-26-BOL-T141-01 | DISTRIBUTION TRANSFORMER - BOOLTIAGH 110-BOOLTIAGH 38-T141 | 4 | 4 | 4 | Reference (Proposed) | 28/07/2026 | 31/07/2026
TO-26-BOL-T143-01 | DISTRIBUTION TRANSFORMER - BOOLTIAGH 110-BOOLTIAGH 38-T143 | 4 | 4 | 4 | Reference (Proposed) | 28/07/2026 | 31/07/2026
TO-26-DJG-TRL-1-01 | 110kV FEEDER - DROMBEG 110-TRALEE 110-1 | 3 | 3 | 3 | Proposed | 28/07/2026 | 30/07/2026
TO-26-OUG-T141-01 | DISTRIBUTION TRANSFORMER - OUGHTRAGH 110-OUGHTRAGH 38-T141 | 3 | 3 | 3 | Reference (Proposed) | 28/07/2026 | 30/07/2026
TO-26-OUG,T-KER-1-02 | 110kV FEEDER - OUGHTRAGH tee-KNOCKEARAGH 110-1 | 3 | 3 | 3 | Proposed | 28/07/2026 | 30/07/2026
TO-26-OUG,T-OUG-1-02 | 110kV FEEDER - OUGHTRAGH tee-OUGHTRAGH 110-1 | 3 | 3 | 3 | Proposed | 28/07/2026 | 30/07/2026
TO-26-OUG,T-TRL-1-01 | 110kV FEEDER - OUGHTRAGH tee-TRALEE 110-1 | 3 | 3 | 3 | Proposed | 28/07/2026 | 30/07/2026
TO-26-TRL-110SA1-2CB-02 | COUPLER/SECTIONALISING CB - TRALEE 110-TRALEE 110-110SA1-2CB | 3 | 3 | 3 | Proposed | 28/07/2026 | 30/07/2026
TO-26-TRL-T142-01 | DISTRIBUTION TRANSFORMER - TRALEE 110-TRALEE 38-T142 | 3 | 3 | 3 | Reference (Proposed) | 28/07/2026 | 30/07/2026
TO-26-AA GIS-T101-01 | GENERATOR TRANSFORMER - ARDNACRUSHA GIS 110-ARDNACRUSHA GIS G1-T101 | Unknown | Unknown | 7 | Planned | August | August
TO-26-CLH-TRI-1-01 | 110kV FEEDER - CLAHANE 110-TRIEN 110-1 | Unknown | Unknown | 2 | Planned | August | August
TO-26-CKN-GRO-1-01 | 110kV FEEDER - CLONKEEN 110-GARROW 110-1 | Unknown | Unknown | 24 | Planned | August | September
TO-26-GRO-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - GARROW 110-GARROW 110-110SA1-2CB | Unknown | Unknown | 1 | Planned | August | August
TO-26-GRO-T122-01 | GENERATOR TRANSFORMER - GARROW 110-GARROW 20-T122 | Unknown | Unknown | 4 | Planned | August | August
TO-26-AA GIS-T102-03 | GENERATOR TRANSFORMER - ARDNACRUSHA GIS 110-ARDNACRUSHA GIS G2-T102 | 1 | 1 | 1 | Proposed | 05/08/2026 | 05/08/2026
TO-26-AUG-KPG-1-02 | 110kV FEEDER - AUGHINISH 110-KILPADDOGE 110-1 | Unknown | Unknown |  | Planned | August | November
TO-26-AUG-SK-3-01 | 110kV FEEDER - AUGHINISH 110-SEALROCK 110-3 | 5 | 5 | 5 | Proposed | 10/08/2026 | 14/08/2026
TO-26-MP GIS-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 110-MONEYPOINT GIS 110-110SA1-2CB | Unknown | Unknown | 5 | Planned | August | August
TO-26-MP GIS-400SA1-2CB-01 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 400-MONEYPOINT GIS 400-400SA1-2CB | Unknown | Unknown | 5 | Planned | August | August
TO-26-MP GIS-ST101-01 | GENERATOR TRANSFORMER - MONEYPOINT GIS 110-MONEYPOINT GIS 10-ST101 | Unknown | Unknown | 5 | Planned | August | August
TO-26-MP GIS-T121-01 | GENERATOR TRANSFORMER - MONEYPOINT GIS 110-MONEYPOINT GIS 20-T121 | Unknown | Unknown | 5 | Planned | August | August
TO-26-MP GIS-T121-02 | GENERATOR TRANSFORMER - MONEYPOINT GIS 110-MONEYPOINT GIS 20-T121 | Unknown | Unknown | 5 | Planned | August | August
TO-26-SK-T103-01 | GENERATOR TRANSFORMER - SEALROCK 110-SEALROCK G3-T103 | 5 | 5 | 5 | Proposed | 10/08/2026 | 14/08/2026
TO-26-SK-T103-02 | GENERATOR TRANSFORMER - SEALROCK 110-SEALROCK G3-T103 | 5 | 5 | 5 | Proposed | 10/08/2026 | 14/08/2026
TO-26-BYH-GLE-1-01 | 110kV FEEDER - BALLYNAHULLA 110-GLENLARA 110-1 | Unknown | Unknown | 2 | Planned | August | August
TO-26-MP GIS-400SA1-3CB-01 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 400-MONEYPOINT GIS 400-400SA1-3CB | Unknown | Unknown | 2 | Planned | August | August
TO-26-TB-T2102-01 | TRANSFORMER - TARBERT 220-TARBERT 110-T2102 | Unknown | Unknown | 10 | Planned | August | August
TO-26-TRI-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - TRIEN 110-TRIEN 110-110SA1-2CB | Unknown | Unknown | 2 | Planned | August | August
TO-26-IKE,T-THU-1-02 | 110kV FEEDER - IKERRIN tee-THURLES 110-1 | 5 | 5 | 5 | Proposed | 24/08/2026 | 28/08/2026
TO-26-LSN-THU-1-03 | 110kV FEEDER - LISHEEN 110-THURLES 110-1 | 26 | 20 | 20 | Proposed | 24/08/2026 | 18/09/2026
TO-26-MP GIS-400SA2-4CB-01 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 400-MONEYPOINT GIS 400-400SA2-4CB | Unknown | Unknown | 5 | Planned | August | August
TO-26-THU-110SA1-2CB-02 | COUPLER/SECTIONALISING CB - THURLES 110-THURLES 110-110SA1-2CB | 5 | 5 | 5 | Proposed | 24/08/2026 | 28/08/2026
TO-26-THU-STATCOM-03 | CAPACITOR/SVC/REACTOR - THURLES 110-THURLES 110-STATCOM | 5 | 5 | 5 | Proposed | 24/08/2026 | 28/08/2026
TO-26-THU-T142-06 | DISTRIBUTION TRANSFORMER - THURLES 110-THURLES 38-T142 | 5 | 5 | 5 | Reference (Proposed) | 24/08/2026 | 28/08/2026
TO-26-TRI-T143-01 | DISTRIBUTION TRANSFORMER - TRIEN 110-TRIEN 38-T143 | Unknown | Unknown | 2 | Reference (Planned) | August | August
TO-26-MP GIS-400SB1-2CB-01 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 400-MONEYPOINT GIS 400-400SB1-2CB | Unknown | Unknown | 5 | Planned | August | September
TO-26-MP GIS-OST-1-01 | 400kV FEEDER - MONEYPOINT GIS 400-OLDSTREET 400-1 | Unknown | Unknown | 15 | Planned | August | September
TO-26-OST-400SA2-01 | SECTIONALISING DISCONNECT - OLDSTREET 400-OLDSTREET 400-400SA2 | Unknown | Unknown | 8 | Planned | August | September
TO-26-OST-T4202-02 | TRANSFORMER - OLDSTREET 400-OLDSTREET 220-T4202 | Unknown | Unknown | 10 | Planned | August | September
TO-26-OST-WOO-1-02 | 400kV FEEDER - OLDSTREET 400-WOODLAND 400-1 | Unknown | Unknown | 15 | Planned | August | September
TO-26-AUG-CFM-2-03 | 110kV FEEDER - AUGHINISH 110-CASTLEFARM 110-2 | Unknown | Unknown | 5 | Planned | September | September
TO-26-CFM-T102-02 | TSO CUSTOMER TRANSFORMER - CASTLEFARM 110-CASTLEFARM 10-T102 | Unknown | Unknown | 5 | Reference (Planned) | September | September
TO-26-MP GIS-400SB1-3CB-01 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 400-MONEYPOINT GIS 400-400SB1-3CB | 5 | 5 | 5 | Proposed | 07/09/2026 | 11/09/2026
TO-26-BVK-GRO-1-01 | 110kV FEEDER - BALLYVOUSKILL 110-GARROW 110-1 | Unknown | Unknown | 3 | Planned | September | September
TO-26-ENN-T102-02 | DISTRIBUTION TRANSFORMER - ENNIS 110-ENNIS 10-T102 | Unknown | Unknown | 2 | Reference (Planned) | September | September
TO-26-400 kV B1 @ MP GIS-01 | BUSBAR SECTION - MONEYPOINT GIS 400-MONEYPOINT GIS 400-400B1 | Unknown | Unknown | 8 | Planned | September | September
TO-26-MP GIS-400SB2-4CB-01 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 400-MONEYPOINT GIS 400-400SB2-4CB | Unknown | Unknown | 5 | Planned | September | September
TO-26-BVK-110K2-03 | COUPLER/SECTIONALISING CB - BALLYVOUSKILL 110-BALLYVOUSKILL 110-110K2 | Unknown | Unknown | 2 | Planned | September | September
TO-26-KLN-SH-1-03 | 220kV FEEDER - KILLONAN 220-SHANNONBRIDGE 220-1 | Unknown | Unknown | 52 | Planned | October | December
TO-26-KPG-T2101-01 | TRANSFORMER - KILPADDOGE 220-KILPADDOGE 110-T2101 | Unknown | Unknown | 4 | Planned | October | October
TO-26-KPG-MP GIS-2-01 | 220kV FEEDER - KILPADDOGE 220-MONEYPOINT GIS 220-2 | Unknown | Unknown | 9 | Planned | October | October
TO-26-DAL-T141-01 | DISTRIBUTION TRANSFORMER - DALLOW 110-DALLOW 38-T141 | Unknown | Unknown | 14 | Reference (Planned) | October | November
TO-26-DAL,T-DAL-1-01 | 110kV FEEDER - DALLOW tee-DALLOW 110-1 | Unknown | Unknown | 14 | Planned | October | November
TO-26-DAL,T-SH-1-01 | 110kV FEEDER - DALLOW tee-SHANNONBRIDGE 110-1 | Unknown | Unknown | 14 | Planned | October | November
TO-26-AUG-110SA1-2CB-02 | COUPLER/SECTIONALISING CB - AUGHINISH 110-AUGHINISH 110-110SA1-2CB | Unknown | Unknown | 2 | Planned | November | November
TO-26-AUG-CFM-2-02 | 110kV FEEDER - AUGHINISH 110-CASTLEFARM 110-2 | Unknown | Unknown | 2 | Planned | November | November
TO-26-KLN-SNG-1-03 | 110kV FEEDER - KILLONAN 110-SINGLAND 110-1 | Unknown | Unknown | 10 | Planned | November | November
TO-26-CSH-PRO-1-01 | 220kV FEEDER - CASHLA 220-PROSPECT 220-1 | Unknown | Unknown | 25 | Planned | November | December
TO-26-LIM-MTN-1-02 | 110kV FEEDER - LIMERICK 110-MONETEEN 110-1 | Unknown | Unknown | 5 | Planned | November | December
TO-26-CSH-ENN-1-01 | 110kV FEEDER - CASHLA 110-ENNIS 110-1 | Unknown | Unknown | 3 | Planned | December | December
TO-26-KLN-110K1-2-01 | COUPLER/SECTIONALISING CB - KILLONAN 110-KILLONAN 110-110K1-2 | Unknown | Unknown | 2 | Planned | December | December

## GEN_SouthEast
Outage ID | Feeder ID | Calendar Day Duration | Working Day Duration | Work Days | Outage Status | Start | Finish
TO-26-BUT-CUL-1-01 | 110kV FEEDER - BUTLERSTOWN 110-CULLENAGH 110-1 | 2 | 2 | 2 | Scheduled | 06/01/2026 | 07/01/2026
TO-26-TTU-131-01 | GENERATOR TRANSFORMER - TULLABEG 110-TULLABEG 33-T131 | 9 | 7 |  | Scheduled | 12/01/2026 | 20/01/2026
TO-26-CAH-TIP-1-01 | 110kV FEEDER - CAHIR 110-TIPPERARY 110-1 | 1 | 1 | 1 | Scheduled | 14/01/2026 | 14/01/2026
TO-26-DGN-RTH-1-01 | 110kV FEEDER - DUNGARVAN 110-RATHNASKILLOGE 110-1 | 1 | 1 |  | Scheduled | 14/01/2026 | 14/01/2026
TO-26-BAR,T-CAH-1-03 | 110kV FEEDER - BARRYMORE tee-CAHIR 110-1 | 4 | 4 | 4 | Scheduled | 19/01/2026 | 22/01/2026
TO-26-NEW-PLS-1-01 | 110kV FEEDER - NEWBRIDGE 110-PORTLAOISE 110-1 | 128 | 87 | 87 | Scheduled | 20/01/2026 | 27/05/2026
TO-26-110 kV A1 @ GI-02 | BUSBAR SECTION - GREAT ISLAND 110-GREAT ISLAND 110-110A1 | 5 | 5 | 5 | Scheduled | 26/01/2026 | 30/01/2026
TO-26-110 kV A2 @ GI-03 | BUSBAR SECTION - GREAT ISLAND 110-GREAT ISLAND 110-110A2 | 5 | 5 | 5 | Scheduled | 26/01/2026 | 30/01/2026
TO-26-110 kV B1 @ GI-02 | BUSBAR SECTION - GREAT ISLAND 110-GREAT ISLAND 110-110B1 | 5 | 5 | 5 | Scheduled | 26/01/2026 | 30/01/2026
TO-26-110 kV B2 @ GI-03 | BUSBAR SECTION - GREAT ISLAND 110-GREAT ISLAND 110-110B2 | 5 | 5 | 5 | Scheduled | 26/01/2026 | 30/01/2026
TO-26-GI-110K1-2-01 | COUPLER/SECTIONALISING CB - GREAT ISLAND 110-GREAT ISLAND 110-110K1-2 | 5 | 5 |  | Scheduled | 26/01/2026 | 30/01/2026
TO-26-STR-T141-02 | DISTRIBUTION TRANSFORMER - STRATFORD 110-STRATFORD 38-T141 | 5 | 5 | 5 | Reference | 26/01/2026 | 30/01/2026
TO-26-STR,T-CLW-1-02 | 110kV FEEDER - STRATFORD tee-CARLOW 110-1 | 5 | 5 |  | Scheduled | 26/01/2026 | 30/01/2026
TO-26-STR,T-PA-1-02 | 110kV FEEDER - STRATFORD tee-POLLAPHUCA 110-1 | 5 | 5 | 5 | Scheduled | 26/01/2026 | 30/01/2026
TO-26-STR,T-STR-1-02 | 110kV FEEDER - STRATFORD tee-STRATFORD 110-1 | 5 | 5 | 5 | Scheduled | 26/01/2026 | 30/01/2026
TO-26-KRA-WOH-1-05 | 110kV FEEDER - KNOCKRAHA 110-WOODHOUSE 110-1 | 9 | 7 | 7 | Scheduled | 12/02/2026 | 20/02/2026
TO-26-ROP-T131-01 | GENERATOR TRANSFORMER - ROSSPILE 110-ROSSPILE 33-T131 | 2 | 2 | 2 | Scheduled | 19/02/2026 | 20/02/2026
TO-26-220 kV A2 @ ARK-01 | BUSBAR SECTION - ARKLOW 220-ARKLOW 220-220A2 | 16 | 12 | 12 | Scheduled | 23/02/2026 | 10/03/2026
TO-26-220 kV B2 @ ARK-01 | BUSBAR SECTION - ARKLOW 220-ARKLOW 220-220B2 | 16 | 12 | 12 | Scheduled | 23/02/2026 | 10/03/2026
TO-26-ARK-CKM GIS-1-01 | 220kV FEEDER - ARKLOW 220-CARRICKMINES GIS 220-1 | 16 | 12 | 12 | Scheduled | 23/02/2026 | 10/03/2026
TO-26-BEG-CKM GIS-1-01 | 110kV FEEDER - BALLYBEG 110-CARRICKMINES GIS 110-1 | 16 | 12 | 12 | Scheduled | 23/02/2026 | 10/03/2026
TO-26-CUL-RTH-1-01 | 110kV FEEDER - CULLENAGH 110-RATHNASKILLOGE 110-1 | 9 | 7 | 7 | Scheduled | 23/02/2026 | 03/03/2026
TO-26-KLS-110K1-2-01 | COUPLER/SECTIONALISING CB - KELLIS 110-KELLIS 110-110K1-2 | 52 | 35 | 35 | Scheduled | 23/02/2026 | 15/04/2026
TO-26-RTH-T133-01 | GENERATOR TRANSFORMER - RATHNASKILLOGE 110-RATHNASKILLOGE 33-T133 | 1 | 1 | 1 | Scheduled | 05/03/2026 | 05/03/2026
TO-26-110 kV A1 @ CUL-02 | BUSBAR SECTION - CULLENAGH 110-CULLENAGH 110-110A1 | 5 | 5 | 5 | Scheduled | 09/03/2026 | 13/03/2026
TO-26-110 kV A2 @ CUL-01 | BUSBAR SECTION - CULLENAGH 110-CULLENAGH 110-110A2 | 5 | 5 | 5 | Scheduled | 09/03/2026 | 13/03/2026
TO-26-110 kV B1 @ CUL-02 | BUSBAR SECTION - CULLENAGH 110-CULLENAGH 110-110B1 | 5 | 5 | 5 | Scheduled | 09/03/2026 | 13/03/2026
TO-26-110 kV B2 @ CUL-01 | BUSBAR SECTION - CULLENAGH 110-CULLENAGH 110-110B2 | 5 | 5 | 5 | Scheduled | 09/03/2026 | 13/03/2026
TO-26-CUL-110K1-2-01 | COUPLER/SECTIONALISING CB - CULLENAGH 110-CULLENAGH 110-110K1-2 | 5 | 5 | 5 | Scheduled | 09/03/2026 | 13/03/2026
TO-26-BDN-CUL-1-05 | 110kV FEEDER - BALLYDINE 110-CULLENAGH 110-1 | 6 | 4 | 4 | Scheduled | 16/03/2026 | 21/03/2026
TO-26-KRA-WOH-1-07 | 110kV FEEDER - KNOCKRAHA 110-WOODHOUSE 110-1 | 5 | 5 | 5 | Scheduled | 23/03/2026 | 27/03/2026
TO-26-BDN-DOO-1-02 | 110kV FEEDER - BALLYDINE 110-DOON 110-1 | 4 | 4 | 4 | Scheduled | 30/03/2026 | 02/04/2026
TO-26-CAH-DOO-1-01 | 110kV FEEDER - CAHIR 110-DOON 110-1 | 58 | 40 | 40 | Scheduled | 07/04/2026 | 03/06/2026
TO-26-CDK-LWD-1-01 | 110kV FEEDER - CASTLEDOCKRELL 110-LODGEWOOD 110-1 | 5 | 5 | 5 | Scheduled | 20/04/2026 | 24/04/2026
TO-26-CDK-T121-02 | GENERATOR TRANSFORMER - CASTLEDOCKRELL 110-CASTLEDOCKRELL 20-T121 | 5 | 5 | 5 | Reference | 20/04/2026 | 24/04/2026
TO-26-LWD-T2102-01 | TRANSFORMER - LODGEWOOD 220-LODGEWOOD 110-T2102 | 5 | 5 | 5 | Scheduled | 20/04/2026 | 24/04/2026
TO-26-TTU-110K1-02 | COUPLER/SECTIONALISING CB - TULLABEG 110-TULLABEG 110-110K1 | 1 | 1 | 1 | Scheduled | 22/04/2026 | 22/04/2026
TO-26-ATY-110SA1-03 | SECTIONALISING DISCONNECT - ATHY 110-ATHY 110-110SA1 | 15 | 10 | 10 | Scheduled | 24/04/2026 | 08/05/2026
TO-26-ATY-110SA2-03 | SECTIONALISING DISCONNECT - ATHY 110-ATHY 110-110SA2 | 15 | 10 | 10 | Scheduled | 24/04/2026 | 08/05/2026
TO-26-ATY-CLW-1-05 | 110kV FEEDER - ATHY 110-CARLOW 110-1 | 15 | 10 | 10 | Scheduled | 24/04/2026 | 08/05/2026
TO-26-WOH-T122-01 | GENERATOR TRANSFORMER - WOODHOUSE 110-WOODHOUSE 20-T122 | 5 | 5 | 5 | Scheduled | 27/04/2026 | 01/05/2026
TO-26-BLK-T142-01 | DISTRIBUTION TRANSFORMER - BLAKE 110-BLAKE 38-T142 | 3 | 1 | 1 | Reference | 01/05/2026 | 03/05/2026
TO-26-BLK,T-BLK-1-03 | 110kV FEEDER - BLAKE tee-BLAKE 110-1 | 3 | 1 | 1 | Scheduled | 01/05/2026 | 03/05/2026
TO-26-BLK,T-NEW-1-04 | 110kV FEEDER - BLAKE tee-NEWBRIDGE 110-1 | 3 | 1 | 1 | Scheduled | 01/05/2026 | 03/05/2026
TO-26-BEG-T101-01 | DISTRIBUTION TRANSFORMER - BALLYBEG 110-BALLYBEG 10-T101 | 2 | 2 | 2 | Reference | 06/05/2026 | 07/05/2026
TO-26-GI GIS-T2004-03 | GENERATOR TRANSFORMER - GREAT ISLAND GIS 220-GREAT ISLAND GIS G4-T2004 | 14 | 10 | 10 | Scheduled | 08/05/2026 | 21/05/2026
TO-26-PHT-131-01 | GENERATOR TRANSFORMER - PHILIPSTOWN 110-PHILIPSTOWN 33-T131 | 1 | 1 | 1 | Scheduled | 08/05/2026 | 08/05/2026
TO-26-110 kV A1 @ CUL-03 | BUSBAR SECTION - CULLENAGH 110-CULLENAGH 110-110A1 | 2 | 0 | 0 | Scheduled | 09/05/2026 | 10/05/2026
TO-26-CUL-WAT-1-01 | 110kV FEEDER - CULLENAGH 110-WATERFORD 110-1 | 2 | 0 | 0 | Scheduled | 09/05/2026 | 10/05/2026
TO-26-ATY-110SA1-08 | SECTIONALISING DISCONNECT - ATHY 110-ATHY 110-110SA1 | 5 | 5 | 5 | Scheduled | 11/05/2026 | 15/05/2026
TO-26-ATY-110SA2-08 | SECTIONALISING DISCONNECT - ATHY 110-ATHY 110-110SA2 | 5 | 5 | 5 | Scheduled | 11/05/2026 | 15/05/2026
TO-26-ATY-PLS-1-01 | 110kV FEEDER - ATHY 110-PORTLAOISE 110-1 | 156 | 110 | 110 | Scheduled | 11/05/2026 | 13/10/2026
TO-26-ATY-T102-05 | DISTRIBUTION TRANSFORMER - ATHY 110-ATHY 10-T102 | 5 | 5 | 5 | Reference | 11/05/2026 | 15/05/2026
TO-26-CLW-KLS-1-03 | 110kV FEEDER - CARLOW 110-KELLIS 110-1 | 71 | 50 | 50 | Scheduled | 11/05/2026 | 20/07/2026
TO-26-220 kV A1 @ CUL-02 | BUSBAR SECTION - CULLENAGH 220-CULLENAGH 220-220A1 | 19 | 15 | 15 | Scheduled | 11/05/2026 | 29/05/2026
TO-26-220 kV B1 @ CUL-02 | BUSBAR SECTION - CULLENAGH 220-CULLENAGH 220-220B1 | 19 | 15 | 15 | Scheduled | 11/05/2026 | 29/05/2026
TO-26-CUL-GI GIS-1-01 | 220kV FEEDER - CULLENAGH 220-GREAT ISLAND GIS 220-1 | 19 | 15 | 15 | Scheduled | 11/05/2026 | 29/05/2026
TO-26-220 kV A2 @ GI GIS-01 | BUSBAR SECTION - GREAT ISLAND GIS 220-GREAT ISLAND GIS 220-220A2 | 4 | 4 | 4 | Scheduled | 12/05/2026 | 15/05/2026
TO-26-GI GIS-220K2-03 | COUPLER/SECTIONALISING CB - GREAT ISLAND GIS 220-GREAT ISLAND GIS 220-220K2 | 4 | 4 | 4 | Scheduled | 12/05/2026 | 15/05/2026
TO-26-GI GIS-220SA1-2CB-03 | COUPLER/SECTIONALISING CB - GREAT ISLAND GIS 220-GREAT ISLAND GIS 220-220SA1-2CB | 4 | 4 | 4 | Scheduled | 12/05/2026 | 15/05/2026
TO-26-ARK-T102-01 | DISTRIBUTION TRANSFORMER - ARKLOW 110-ARKLOW 10-T102 | 2 | 2 | 2 | Reference | 13/05/2026 | 14/05/2026
TO-26-ARK-BOG-1-04 | 110kV FEEDER - ARKLOW 110-BANOGE 110-1 | 9 | 6 | 6 | Scheduled | 25/05/2026 | 02/06/2026
TO-26-BOG-110SA1-02 | SECTIONALISING DISCONNECT - BANOGE 110-BANOGE 110-110SA1 | 5 | 5 | 5 | Scheduled | 25/05/2026 | 29/05/2026
TO-26-BOG-110SA2-01 | SECTIONALISING DISCONNECT - BANOGE 110-BANOGE 110-110SA2 | 5 | 5 | 5 | Scheduled | 25/05/2026 | 29/05/2026
TO-26-BOG-T122-01 | DISTRIBUTION TRANSFORMER - BANOGE 110-BANOGE 20-T122 | 5 | 5 | 5 | Reference | 25/05/2026 | 29/05/2026
TO-26-GI-WAT-1-05 | 110kV FEEDER - GREAT ISLAND 110-WATERFORD 110-1 | 1 | 0 | 0 | Scheduled | 30/05/2026 | 30/05/2026
TO-26-GI-WAT-2-03 | 110kV FEEDER - GREAT ISLAND 110-WATERFORD 110-2 | 1 | 0 | 0 | Scheduled | 30/05/2026 | 30/05/2026
TO-26-CUS-KIR-1-01 | 110kV FEEDER - CUSHALING 110-KILCUMBER 110-1 | 3 | 3 | 3 | Scheduled | 02/06/2026 | 04/06/2026
TO-26-KIR-T131-01 | GENERATOR TRANSFORMER - KILCUMBER 110-KILCUMBER 33-T131 | 3 | 3 | 3 | Scheduled | 02/06/2026 | 04/06/2026
TO-26-110 kV A1 @ PLS-07 | BUSBAR SECTION - PORTLAOISE 110-PORTLAOISE 110-110A1 | 18 | 14 | 14 | Scheduled | 02/06/2026 | 19/06/2026
TO-26-110 kV A2 @ PLS-01 | BUSBAR SECTION - PORTLAOISE 110-PORTLAOISE 110-110A2 | 18 | 14 | 14 | Scheduled | 02/06/2026 | 19/06/2026
TO-26-110 kV B1 @ PLS-06 | BUSBAR SECTION - PORTLAOISE 110-PORTLAOISE 110-110B1 | 18 | 14 | 14 | Scheduled | 02/06/2026 | 19/06/2026
TO-26-110 kV B2 @ PLS-01 | BUSBAR SECTION - PORTLAOISE 110-PORTLAOISE 110-110B2 | 18 | 14 | 14 | Scheduled | 02/06/2026 | 19/06/2026
TO-26-PLS-110K1-2-03 | COUPLER/SECTIONALISING CB - PORTLAOISE 110-PORTLAOISE 110-110K1-2 | 18 | 14 | 14 | Scheduled | 02/06/2026 | 19/06/2026
TO-26-110 kV A1 @ ARK-01 | BUSBAR SECTION - ARKLOW 110-ARKLOW 110-110A1 | 17 | 13 | 13 | Scheduled | 03/06/2026 | 19/06/2026
TO-26-110 kV B1 @ ARK-01 | BUSBAR SECTION - ARKLOW 110-ARKLOW 110-110B1 | 17 | 13 | 13 | Scheduled | 03/06/2026 | 19/06/2026
TO-26-220 kV A1 @ ARK-01 | BUSBAR SECTION - ARKLOW 220-ARKLOW 220-220A1 | 17 | 13 | 13 | Scheduled | 03/06/2026 | 19/06/2026
TO-26-220 kV B1 @ ARK-01 | BUSBAR SECTION - ARKLOW 220-ARKLOW 220-220B1 | 17 | 13 | 13 | Scheduled | 03/06/2026 | 19/06/2026
TO-26-ARK-T2101-03 | TRANSFORMER - ARKLOW 220-ARKLOW 110-T2101 | 17 | 13 | 13 | Scheduled | 03/06/2026 | 19/06/2026
TO-26-KRA-WOH-1-02 | 110kV FEEDER - KNOCKRAHA 110-WOODHOUSE 110-1 | 12 | 10 | 10 | Scheduled | 08/06/2026 | 19/06/2026
TO-26-KRA-WOH-1-08 | 110kV FEEDER - KNOCKRAHA 110-WOODHOUSE 110-1 | 12 | 10 | 10 | Proposed | 08/06/2026 | 19/06/2026
TO-26-ANR-DOO-1-02 | 110kV FEEDER - ANNER 110-DOON 110-1 | 1 | 1 | 1 | Proposed | 09/06/2026 | 09/06/2026
TO-26-ANR-T101-07 | TSO CUSTOMER TRANSFORMER - ANNER 110-ANNER 10-T101 | 1 | 1 | 1 | Reference (Proposed) | 09/06/2026 | 09/06/2026
TO-26-ANR-T103-06 | TSO CUSTOMER TRANSFORMER - ANNER 110-ANNER 10-T103 | 1 | 1 | 1 | Reference (Proposed) | 09/06/2026 | 09/06/2026
TO-26-ARK-T142-01 | DISTRIBUTION TRANSFORMER - ARKLOW 110-ARKLOW 38-T142 | 2 | 2 | 2 | Reference (Proposed) | 09/06/2026 | 10/06/2026
TO-26-KLS-220K1-2-02 | COUPLER/SECTIONALISING CB - KELLIS 220-KELLIS 220-220K1-2 | 1 | 1 | 1 | Proposed | 10/06/2026 | 10/06/2026
TO-26-PHT-131-02 | GENERATOR TRANSFORMER - PHILIPSTOWN 110-PHILIPSTOWN 33-T131 | 1 | 1 | 1 | Scheduled | 11/06/2026 | 11/06/2026
TO-26-ARK-110K1-2-03 | COUPLER/SECTIONALISING CB - ARKLOW 110-ARKLOW 110-110K1-2 | 5 | 5 | 5 | Proposed | 15/06/2026 | 19/06/2026
TO-26-STN-T131-01 | GENERATOR TRANSFORMER - STONESTOWN 110-STONESTOWN 33-T131 | 1 | 1 | 1 | Proposed | 17/06/2026 | 17/06/2026
TO-26-BAR,T-CAH-1-05 | 110kV FEEDER - BARRYMORE tee-CAHIR 110-1 | 9 | 7 | 7 | Proposed | 22/06/2026 | 30/06/2026
TO-26-GI GIS-LON-1-02 | 220kV FEEDER - GREAT ISLAND GIS 220-LOUGHTOWN 220-1 | 24 | 18 | 18 | Proposed | 22/06/2026 | 15/07/2026
TO-26-110 kV A2 @ ARK-01 | BUSBAR SECTION - ARKLOW 110-ARKLOW 110-110A2 | 18 | 14 | 14 | Scheduled | 23/06/2026 | 10/07/2026
TO-26-110 kV B2 @ ARK-01 | BUSBAR SECTION - ARKLOW 110-ARKLOW 110-110B2 | 18 | 14 | 14 | Scheduled | 23/06/2026 | 10/07/2026
TO-26-220 kV A2 @ ARK-02 | BUSBAR SECTION - ARKLOW 220-ARKLOW 220-220A2 | 18 | 14 | 14 | Scheduled | 23/06/2026 | 10/07/2026
TO-26-220 kV B2 @ ARK-02 | BUSBAR SECTION - ARKLOW 220-ARKLOW 220-220B2 | 18 | 14 | 14 | Scheduled | 23/06/2026 | 10/07/2026
TO-26-ARK-T2102-01 | TRANSFORMER - ARKLOW 220-ARKLOW 110-T2102 | 18 | 14 | 14 | Scheduled | 23/06/2026 | 10/07/2026
TO-26-CUS-T101-01 | GENERATOR TRANSFORMER - CUSHALING 110-CUSHALING G1-T101 | 1 | 1 | 1 | Proposed | 06/07/2026 | 06/07/2026
TO-26-BDN-MRK3-03 | TSO CUSTOMER TRANSFORMER - BALLYDINE 110-BALLYDINE 10-MRK3 | 9 | 7 | 7 | Proposed | 09/07/2026 | 17/07/2026
TO-26-BDN-110SA2-01 | SECTIONALISING DISCONNECT - BALLYDINE 110-BALLYDINE 110-110SA2 | 4 | 4 | 4 | Proposed | 13/07/2026 | 16/07/2026
TO-26-BDN-DOO-1-05 | 110kV FEEDER - BALLYDINE 110-DOON 110-1 | 4 | 4 | 4 | Proposed | 13/07/2026 | 16/07/2026
TO-26-BDN-MRK3-01 | TSO CUSTOMER TRANSFORMER - BALLYDINE 110-BALLYDINE 10-MRK3 | 4 | 4 | 4 | Proposed | 13/07/2026 | 16/07/2026
TO-26-CAH-CAP1/3-01 | CAPACITOR/SVC/REACTOR - CAHIR 110-CAHIR 110-CAP1/3 | 5 | 5 | 5 | Proposed | 13/07/2026 | 17/07/2026
TO-26-BOT-MLC-1-01 | 110kV FEEDER - BOGTOWN 110-MOUNTLUCAS 110-1 | 9 | 7 | 7 | Proposed | 20/07/2026 | 28/07/2026
TO-26-BOT-T131-01 | GENERATOR TRANSFORMER - BOGTOWN 110-BOGTOWN 33-T131 | 1 | 1 | 1 | Proposed | 20/07/2026 | 20/07/2026
TO-26-BOT-T131-02 | GENERATOR TRANSFORMER - BOGTOWN 110-BOGTOWN 33-T131 | 9 | 7 | 7 | Proposed | 20/07/2026 | 28/07/2026
TO-26-CAH-CAP2/4-01 | CAPACITOR/SVC/REACTOR - CAHIR 110-CAHIR 110-CAP2/4 | 5 | 5 | 5 | Proposed | 20/07/2026 | 24/07/2026
TO-26-CRA-110SA1-01 | SECTIONALISING DISCONNECT - CRANE 110-CRANE 110-110SA1 | 12 | 10 | 10 | Proposed | 20/07/2026 | 31/07/2026
TO-26-CRA-110SA2-05 | SECTIONALISING DISCONNECT - CRANE 110-CRANE 110-110SA2 | 12 | 10 | 10 | Proposed | 20/07/2026 | 31/07/2026
TO-26-CRA-T141-05 | DISTRIBUTION TRANSFORMER - CRANE 110-CRANE 38-T141 | 12 | 10 | 10 | Reference (Proposed) | 20/07/2026 | 31/07/2026
TO-26-CRA-TTU-1-01 | 110kV FEEDER - CRANE 110-TULLABEG 110-1 | 12 | 10 | 10 | Proposed | 20/07/2026 | 31/07/2026
TO-26-110 kV A2 @ DEY-02 | BUSBAR SECTION - DERRYCARNEY 110-DERRYCARNEY 110-110A2 | 5 | 5 | 5 | Proposed | 20/07/2026 | 24/07/2026
TO-26-110 kV B2 @ DEY-02 | BUSBAR SECTION - DERRYCARNEY 110-DERRYCARNEY 110-110B2 | 5 | 5 | 5 | Proposed | 20/07/2026 | 24/07/2026
TO-26-DEY-110K2-03 | COUPLER/SECTIONALISING CB - DERRYCARNEY 110-DERRYCARNEY 110-110K2 | 5 | 5 | 5 | Proposed | 20/07/2026 | 24/07/2026
TO-26-BDN-MRK1-04 | TSO CUSTOMER TRANSFORMER - BALLYDINE 110-BALLYDINE 10-MRK1 | 17 | 12 | 12 | Proposed | 21/07/2026 | 06/08/2026
TO-26-CAH-KHL-1-01 | 110kV FEEDER - CAHIR 110-KILL HILL 110-1 | 2 | 2 | 2 | Proposed | 22/07/2026 | 23/07/2026
TO-26-BDN-110SA1-01 | SECTIONALISING DISCONNECT - BALLYDINE 110-BALLYDINE 110-110SA1 | 4 | 4 | 4 | Proposed | 27/07/2026 | 30/07/2026
TO-26-BDN-CUL-1-06 | 110kV FEEDER - BALLYDINE 110-CULLENAGH 110-1 | 4 | 4 | 4 | Proposed | 27/07/2026 | 30/07/2026
TO-26-CLW-KLS-2-05 | 110kV FEEDER - CARLOW 110-KELLIS 110-2 | 5 | 5 | 5 | Proposed | 27/07/2026 | 31/07/2026
TO-26-KKY-T141-01 | DISTRIBUTION TRANSFORMER - KILKENNY 110-KILKENNY 38-T141 | 2 | 2 | 2 | Reference (Proposed) | 28/07/2026 | 29/07/2026
TO-26-KKY-CAP2-02 | CAPACITOR/SVC/REACTOR - KILKENNY 110-KILKENNY 110-CAP2 | 2 | 2 | 2 | Proposed | 29/07/2026 | 30/07/2026
TO-26-KLS-KKY-1-04 | 110kV FEEDER - KELLIS 110-KILKENNY 110-1 | 12 | 9 | 9 | Proposed | 03/08/2026 | 14/08/2026
TO-26-ARK-BEG-1-01 | 110kV FEEDER - ARKLOW 110-BALLYBEG 110-1 | Unknown | Unknown | 4 | Planned | August | August
TO-26-CDK-T121-01 | GENERATOR TRANSFORMER - CASTLEDOCKRELL 110-CASTLEDOCKRELL 20-T121 | Unknown | Unknown | 22 | Reference (Planned) | August | September
TO-26-CRA-WEX-1-06 | 110kV FEEDER - CRANE 110-WEXFORD 110-1 | 19 | 15 | 15 | Proposed | 10/08/2026 | 28/08/2026
TO-26-DOO-CAP1-04 | CAPACITOR/SVC/REACTOR - DOON 110-DOON 110-CAP1 | Unknown | Unknown | 20 | Planned | August | September
TO-26-BDA-T101-01 | TSO CUSTOMER TRANSFORMER - BARODA 110-BARODA 10-T101 | Unknown | Unknown | 5 | Planned | September | September
TO-26-CUS-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - CUSHALING 110-CUSHALING 110-110SA1-2CB | Unknown | Unknown | 24 | Planned | September | September
TO-26-CUS-T103/5-01 | GENERATOR TRANSFORMER - CUSHALING 110-CUSHALING G3/5-T103/5 | Unknown | Unknown | 5 | Planned | September | September
TO-26-110 kV A1 @ PLS-01 | BUSBAR SECTION - PORTLAOISE 110-PORTLAOISE 110-110A1 | 2 | 2 | 2 | Scheduled | 24/09/2026 | 25/09/2026
TO-26-110 kV B1 @ PLS-01 | BUSBAR SECTION - PORTLAOISE 110-PORTLAOISE 110-110B1 | 2 | 2 | 2 | Scheduled | 24/09/2026 | 25/09/2026
TO-26-ATY-110SA1-02 | SECTIONALISING DISCONNECT - ATHY 110-ATHY 110-110SA1 | 2 | 2 | 2 | Scheduled | 28/09/2026 | 29/09/2026
TO-26-ATY-110SA2-02 | SECTIONALISING DISCONNECT - ATHY 110-ATHY 110-110SA2 | 2 | 2 | 2 | Scheduled | 28/09/2026 | 29/09/2026
TO-26-ATY-T102-02 | DISTRIBUTION TRANSFORMER - ATHY 110-ATHY 10-T102 | 2 | 2 | 2 | Reference | 28/09/2026 | 29/09/2026
TO-26-110 kV B1 @ PLS-03 | BUSBAR SECTION - PORTLAOISE 110-PORTLAOISE 110-110B1 | 2 | 2 | 2 | Scheduled | 06/10/2026 | 07/10/2026
TO-26-NEW-PLS-1-03 | 110kV FEEDER - NEWBRIDGE 110-PORTLAOISE 110-1 | 7 | 5 | 5 | Scheduled | 07/10/2026 | 13/10/2026
TO-26-110 kV A1 @ PLS-03 | BUSBAR SECTION - PORTLAOISE 110-PORTLAOISE 110-110A1 | 6 | 4 | 4 | Scheduled | 08/10/2026 | 13/10/2026
TO-26-CUS-NEW-1-03 | 110kV FEEDER - CUSHALING 110-NEWBRIDGE 110-1 | Unknown | Unknown |  | Planned | October | October
TO-26-DEY-110K2-01 | COUPLER/SECTIONALISING CB - DERRYCARNEY 110-DERRYCARNEY 110-110K2 | Unknown | Unknown | 5 | Planned | October | October
TO-26-NEW-110SA2-03 | SECTIONALISING DISCONNECT - NEWBRIDGE 110-NEWBRIDGE 110-110SA2 | Unknown | Unknown | 10 | Planned | October | October
TO-26-DAL,T-DAL-1-01 | 110kV FEEDER - DALLOW tee-DALLOW 110-1 | Unknown | Unknown | 14 | Planned | October | November
TO-26-DAL,T-SH-1-01 | 110kV FEEDER - DALLOW tee-SHANNONBRIDGE 110-1 | Unknown | Unknown | 14 | Planned | October | November
TO-26-DAL,T-STN-1-01 | 110kV FEEDER - DALLOW tee-STONESTOWN 110-1 | Unknown | Unknown | 14 | Planned | October | November
TO-26-GI-KKY-1-03 | 110kV FEEDER - GREAT ISLAND 110-KILKENNY 110-1 | 17 | 13 | 13 | Proposed | 04/11/2026 | 20/11/2026
TO-26-DGN-WOH-1-01 | 110kV FEEDER - DUNGARVAN 110-WOODHOUSE 110-1 | Unknown | Unknown | 20 | Planned | November | December
TO-26-WEX-110SA1-2CB-02 | COUPLER/SECTIONALISING CB - WEXFORD 110-WEXFORD 110-110SA1-2CB | Unknown | Unknown | 5 | Planned | November | November
TO-26-WEX-CAP2-02 | CAPACITOR/SVC/REACTOR - WEXFORD 110-WEXFORD 110-CAP2 | Unknown | Unknown | 5 | Planned | November | November
TO-26-WEX-CAP4-02 | CAPACITOR/SVC/REACTOR - WEXFORD 110-WEXFORD 110-CAP4 | Unknown | Unknown | 5 | Planned | November | November
TO-26-ARK-LWD-1-01 | 220kV FEEDER - ARKLOW 220-LODGEWOOD 220-1 | Unknown | Unknown | 10 | Planned | November | December
TO-26-BGT-110K1-01 | COUPLER/SECTIONALISING CB - BALLYRAGGET 110-BALLYRAGGET 110-110K1 | Unknown | Unknown | 1 | Planned | December | December
TO-26-110kV A1 @ BGT-01 | BUSBAR SECTION - BALLYRAGGET 110-BALLYRAGGET 110-110A1 | Unknown | Unknown | 1 | Planned | December | December
TO-26-BGT-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - BALLYRAGGET 110-BALLYRAGGET 110-110SA1-2CB | Unknown | Unknown | 1 | Planned | December | December
TO-26-DEY-PLS-1-01 | 110kV FEEDER - DERRYCARNEY 110-PORTLAOISE 110-1 | 11 | 9 | 9 | Proposed | 08/12/2026 | 18/12/2026
TO-26-ARK-SHE-2-02 | 110kV FEEDER - ARKLOW 110-SHELTON ABBEY 110-2 | Unknown | Unknown | 5 | Planned | December | December
TO-26-SHE-T102-01 | TSO CUSTOMER TRANSFORMER - SHELTON ABBEY 110-SHELTON ABBEY 10-T102 | Unknown | Unknown | 5 | Planned | December | December

## GEN_NorthWest
Outage ID | Feeder ID | Calendar Day Duration | Working Day Duration | Work Days | Outage Status | Start | Finish
TO-26-CBR-SVC-02 | CAPACITOR/SVC/REACTOR - CASTLEBAR 110-CASTLEBAR 110-SVC | 368 | 253 | 253 | Scheduled | 29/12/2025 | 31/12/2026
TO-26-LET-PST-04 | TRANSFORMER - LETTERKENNY 110-STRABANE 110-PST | 64 | 44 | 44 | Scheduled | 19/01/2026 | 23/03/2026
TO-26-LET-SVC-01 | CAPACITOR/SVC/REACTOR - LETTERKENNY 110-LETTERKENNY 110-SVC | 13 | 10 | 10 | Scheduled | 19/01/2026 | 31/01/2026
TO-26-CLO-CRD-1-01 | 110kV FEEDER - CLOGHER 110-CROAGHONAGH 110-1 | 2 | 2 | 2 | Scheduled | 02/03/2026 | 03/03/2026
TO-26-CRD-T131-01 | GENERATOR TRANSFORMER - CROAGHONAGH 110-CROAGHONAGH 33-T131 | 2 | 2 | 2 | Scheduled | 02/03/2026 | 03/03/2026
TO-26-CLO-DRM-1-01 | 110kV FEEDER - CLOGHER 110-DRUMKEEN 110-1 | 3 | 3 | 3 | Scheduled | 31/03/2026 | 02/04/2026
TO-26-GOL-T101-01 | GENERATOR TRANSFORMER - GOLAGH 110-GOLAGH 10-T101 | 3 | 3 | 3 | Scheduled | 31/03/2026 | 02/04/2026
TO-26-GOL,T-CLO-1-01 | 110kV FEEDER - GOLAGH tee-CLOGHER 110-1 | 3 | 3 | 3 | Scheduled | 31/03/2026 | 02/04/2026
TO-26-GOL,T-GOL-1-03 | 110kV FEEDER - GOLAGH tee-GOLAGH 110-1 | 3 | 3 | 3 | Scheduled | 31/03/2026 | 02/04/2026
TO-26-GOL,T-LET-1-03 | 110kV FEEDER - GOLAGH tee-LETTERKENNY 110-1 | 3 | 3 | 3 | Scheduled | 31/03/2026 | 02/04/2026
TO-26-FLA-110K1-2-01 | COUPLER/SECTIONALISING CB - FLAGFORD 110-FLAGFORD 110-110K1-2 | 1 | 1 | 1 | Scheduled | 01/04/2026 | 01/04/2026
TO-26-TAW-T1/T2-01 | GENERATOR TRANSFORMER - TAWNAGHMORE 110-TAWNAGHMORE 10-T1/T2 | 163 | 114 | 114 | Scheduled | 07/04/2026 | 16/09/2026
TO-26-TAW-T3-02 | GENERATOR TRANSFORMER - TAWNAGHMORE 110-TAWNAGHMORE 10-T3 | 163 | 114 | 114 | Scheduled | 07/04/2026 | 16/09/2026
TO-26-FLA-LOU-1-06 | 220kV FEEDER - FLAGFORD 220-LOUTH 220-1 | 51 | 36 | 36 | Scheduled | 09/04/2026 | 29/05/2026
TO-26-DRM-LET-1-01 | 110kV FEEDER - DRUMKEEN 110-LETTERKENNY 110-1 | 17 | 13 | 13 | Scheduled | 05/05/2026 | 21/05/2026
TO-26-CUN-T121-01 | GENERATOR TRANSFORMER - CUNGHILL 110-CUNGHILL 20-T121 | 4 | 4 | 4 | Scheduled | 11/05/2026 | 14/05/2026
TO-26-BIN-T143-01 | DISTRIBUTION TRANSFORMER - BINBANE 110-BINBANE 38-T143 | 2 | 2 | 2 | Reference | 19/05/2026 | 20/05/2026
TO-26-LLA-LET-1-01 | 110kV FEEDER - LENALEA 110-LETTERKENNY 110-1 | 15 | 10 | 10 | Scheduled | 22/05/2026 | 05/06/2026
TO-26-LET-110SA1-3CB-02 | COUPLER/SECTIONALISING CB - LETTERKENNY 110-LETTERKENNY 110-110SA1-3CB | 15 | 10 | 10 | Scheduled | 22/05/2026 | 05/06/2026
TO-26-LET-TLK-1-01 | 110kV FEEDER - LETTERKENNY 110-TRILLICK 110-1 | 15 | 10 | 10 | Reference | 22/05/2026 | 05/06/2026
TO-26-SOR-T122-01 | DISTRIBUTION TRANSFORMER - SORNE HILL 110-SORNE HILL 20-T122 | 15 | 10 | 10 | Reference | 22/05/2026 | 05/06/2026
TO-26-SOR-T124-01 | DISTRIBUTION TRANSFORMER - SORNE HILL 110-SORNE HILL 20-T124 | 15 | 10 | 10 | Reference | 22/05/2026 | 05/06/2026
TO-26-SOR-TLK-1-01 | 110kV FEEDER - SORNE HILL 110-TRILLICK 110-1 | 15 | 10 | 10 | Reference | 22/05/2026 | 05/06/2026
TO-26-TLK-T141-01 | DISTRIBUTION TRANSFORMER - TRILLICK 110-TRILLICK 38-T141 | 15 | 10 | 10 | Reference | 22/05/2026 | 05/06/2026
TO-26-TLK-T142-01 | DISTRIBUTION TRANSFORMER - TRILLICK 110-TRILLICK 38-T142 | 15 | 10 | 10 | Reference | 22/05/2026 | 05/06/2026
TO-26-220 kV A1 @ CSH-01 | BUSBAR SECTION - CASHLA 220-CASHLA 220-220A1 | 19 | 14 | 14 | Scheduled | 25/05/2026 | 12/06/2026
TO-26-220 kV A2 @ CSH-02 | BUSBAR SECTION - CASHLA 220-CASHLA 220-220A2 | 19 | 14 | 14 | Scheduled | 25/05/2026 | 12/06/2026
TO-26-220 kV B1 @ CSH-01 | BUSBAR SECTION - CASHLA 220-CASHLA 220-220B1 | 19 | 14 | 14 | Scheduled | 25/05/2026 | 12/06/2026
TO-26-220 kV B2 @ CSH-03 | BUSBAR SECTION - CASHLA 220-CASHLA 220-220B2 | 19 | 14 | 14 | Scheduled | 25/05/2026 | 12/06/2026
TO-26-CSH-220K1-2-01 | COUPLER/SECTIONALISING CB - CASHLA 220-CASHLA 220-220K1-2 | 19 | 14 | 14 | Scheduled | 25/05/2026 | 12/06/2026
TO-26-LLA-T133-01 | GENERATOR TRANSFORMER - LENALEA 110-LENALEA 33-T133 | 3 | 3 | 3 | Scheduled | 02/06/2026 | 04/06/2026
TO-26-220 kV A4 @ CSH-02 | BUSBAR SECTION - CASHLA 220-CASHLA 220-220A4 | 5 | 5 | 5 | Proposed | 08/06/2026 | 12/06/2026
TO-26-CSH-T2104-03 | TRANSFORMER - CASHLA 220-CASHLA 110-T2104 | 5 | 5 | 5 | Proposed | 08/06/2026 | 12/06/2026
TO-26-CF-CLO-2-02 | 110kV FEEDER - CATHALEENS FALL 110-CLOGHER 110-2 | 19 | 15 | 15 | Scheduled | 08/06/2026 | 26/06/2026
TO-26-CF-T104-01 | GENERATOR TRANSFORMER - CATHALEENS FALL 110-CATHALEENS FALL G4-T104 | 12 | 10 | 10 | Scheduled | 08/06/2026 | 19/06/2026
TO-26-110 kV A2 @ CLO-01 | BUSBAR SECTION - CLOGHER 110-CLOGHER 110-110A2 | 8 | 6 | 6 | Scheduled | 08/06/2026 | 15/06/2026
TO-26-110 kV B2 @ CLO-01 | BUSBAR SECTION - CLOGHER 110-CLOGHER 110-110B2 | 8 | 6 | 6 | Scheduled | 08/06/2026 | 15/06/2026
TO-26-KNY-SAL-1-01 | 110kV FEEDER - KNOCKRANNY 110-SALTHILL 110-1 | 12 | 10 | 10 | Proposed | 08/06/2026 | 19/06/2026
TO-26-GAL GIS-110K2-01 | COUPLER/SECTIONALISING CB - GALWAY GIS 110-GALWAY GIS 110-110K2 | 2 | 2 | 2 | Scheduled | 09/06/2026 | 10/06/2026
TO-26-GAL GIS-110K3-01 | COUPLER/SECTIONALISING CB - GALWAY GIS 110-GALWAY GIS 110-110K3 | 2 | 2 | 2 | Scheduled | 09/06/2026 | 10/06/2026
TO-26-GAL GIS-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - GALWAY GIS 110-GALWAY GIS 110-110SA1-2CB | 2 | 2 | 2 | Scheduled | 09/06/2026 | 10/06/2026
TO-26-GAL GIS-110SA1-3CB-01 | COUPLER/SECTIONALISING CB - GALWAY GIS 110-GALWAY GIS 110-110SA1-3CB | 2 | 2 | 2 | Scheduled | 09/06/2026 | 10/06/2026
TO-26-GAL GIS-110SB1-2CB-01 | COUPLER/SECTIONALISING CB - GALWAY GIS 110-GALWAY GIS 110-110SB1-2CB | 2 | 2 | 2 | Scheduled | 09/06/2026 | 10/06/2026
TO-26-GAL GIS-110SB1-3CB-01 | COUPLER/SECTIONALISING CB - GALWAY GIS 110-GALWAY GIS 110-110SB1-3CB | 2 | 2 | 2 | Scheduled | 09/06/2026 | 10/06/2026
TO-26-LLA-110K1-07 | COUPLER/SECTIONALISING CB - LENALEA 110-LENALEA 110-110K1 | 2 | 2 | 2 | Scheduled | 09/06/2026 | 10/06/2026
TO-26-DYN-T121-01 | GENERATOR TRANSFORMER - DERRYBRIEN 110-DERRYBRIEN 20-T121 | 5 | 5 | 5 | Reference | 15/06/2026 | 19/06/2026
TO-26-MRY-T131-01 | GENERATOR TRANSFORMER - MULREAVY 110-MULREAVY 33-T131 | 2 | 2 | 2 | Proposed | 15/06/2026 | 16/06/2026
TO-26-SLI-CAP1-01 | CAPACITOR/SVC/REACTOR - SLIGO 110-SLIGO 110-CAP1 | 5 | 5 | 5 | Proposed | 15/06/2026 | 19/06/2026
TO-26-220 kV A2 @ CSH-01 | BUSBAR SECTION - CASHLA 220-CASHLA 220-220A2 | 11 | 9 | 9 | Proposed | 16/06/2026 | 26/06/2026
TO-26-220 kV A4 @ CSH-01 | BUSBAR SECTION - CASHLA 220-CASHLA 220-220A4 | 11 | 9 | 9 | Proposed | 16/06/2026 | 26/06/2026
TO-26-220 kV B2 @ CSH-02 | BUSBAR SECTION - CASHLA 220-CASHLA 220-220B2 | 11 | 9 | 9 | Proposed | 16/06/2026 | 26/06/2026
TO-26-220 kV B4 @ CSH-02 | BUSBAR SECTION - CASHLA 220-CASHLA 220-220B4 | 11 | 9 | 9 | Proposed | 16/06/2026 | 26/06/2026
TO-26-CSH-220K2-4-01 | COUPLER/SECTIONALISING CB - CASHLA 220-CASHLA 220-220K2-4 | 11 | 9 | 9 | Proposed | 16/06/2026 | 26/06/2026
TO-26-DLT-CAP1-01 | CAPACITOR/SVC/REACTOR - DALTON 110-DALTON 110-CAP1 | 2 | 2 | 2 | Scheduled | 16/06/2026 | 17/06/2026
TO-26-FLA-T2102-02 | TRANSFORMER - FLAGFORD 220-FLAGFORD 110-T2102 | 5 | 5 | 5 | Proposed | 22/06/2026 | 26/06/2026
TO-26-AGP-T141-01 | DISTRIBUTION TRANSFORMER - ARDNAGAPPARY 110-ARDNAGAPPARY 38-T141 | 11 | 9 | 9 | Reference (Proposed) | 29/06/2026 | 09/07/2026
TO-26-AGP-TIV-1-01 | 110kV FEEDER - ARDNAGAPPARY 110-TIEVEBRACK 110-1 | 11 | 9 | 9 | Reference (Proposed) | 29/06/2026 | 09/07/2026
TO-26-BIN-TIV-1-01 | 110kV FEEDER - BINBANE 110-TIEVEBRACK 110-1 | 11 | 9 | 9 | Proposed | 29/06/2026 | 09/07/2026
TO-26-TIV-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - TIEVEBRACK 110-TIEVEBRACK 110-110SA1-2CB | 11 | 9 | 9 | Proposed | 29/06/2026 | 09/07/2026
TO-26-GAL GIS-KNY-1-01 | 110kV FEEDER - GALWAY GIS 110-KNOCKRANNY 110-1 | 2 | 2 | 2 | Proposed | 01/07/2026 | 02/07/2026
TO-26-BK-110SA1-02 | SECTIONALISING DISCONNECT - BELLACORICK 110-BELLACORICK 110-110SA1 | 5 | 5 | 5 | Proposed | 06/07/2026 | 10/07/2026
TO-26-COS-FLA-1-01 | 110kV FEEDER - CARRICK ON SHANNON 110-FLAGFORD 110-1 | 5 | 5 | 5 | Proposed | 06/07/2026 | 10/07/2026
TO-26-CF-CL-1-03 | 110kV FEEDER - CATHALEENS FALL 110-CLIFF 110-1 | 12 | 10 | 10 | Proposed | 06/07/2026 | 17/07/2026
TO-26-CL-T101-02 | GENERATOR TRANSFORMER - CLIFF 110-CLIFF G1-T101 | 12 | 10 | 10 | Proposed | 06/07/2026 | 17/07/2026
TO-26-CL-T102-03 | GENERATOR TRANSFORMER - CLIFF 110-CLIFF G2-T102 | 12 | 10 | 10 | Proposed | 06/07/2026 | 17/07/2026
TO-26-110 kV A2 @ FLA-01 | BUSBAR SECTION - FLAGFORD 110-FLAGFORD 110-110A2 | 5 | 5 | 5 | Proposed | 06/07/2026 | 10/07/2026
TO-26-110 kV B2 @ FLA-01 | BUSBAR SECTION - FLAGFORD 110-FLAGFORD 110-110B2 | 5 | 5 | 5 | Proposed | 06/07/2026 | 10/07/2026
TO-26-KNY-UGL-1-01 | 110kV FEEDER - KNOCKRANNY 110-UGGOOL 110-1 | 4 | 4 | 4 | Proposed | 13/07/2026 | 16/07/2026
TO-26-UGL-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - UGGOOL 110-UGGOOL 110-110SA1-2CB | 4 | 4 |  | Proposed | 13/07/2026 | 16/07/2026
TO-26-UGL-T131-02 | GENERATOR TRANSFORMER - UGGOOL 110-UGGOOL 33-T131 | 4 | 4 | 4 | Proposed | 13/07/2026 | 16/07/2026
TO-26-UGL-T131-01 | GENERATOR TRANSFORMER - UGGOOL 110-UGGOOL 33-T131 | 4 | 4 | 4 | Proposed | 13/07/2026 | 16/07/2026
TO-26-UGL-T132-01 | GENERATOR TRANSFORMER - UGGOOL 110-UGGOOL 33-T132 | 4 | 4 | 4 | Proposed | 13/07/2026 | 16/07/2026
TO-26-UGL-T132-02 | GENERATOR TRANSFORMER - UGGOOL 110-UGGOOL 33-T132 | 4 | 4 | 4 | Proposed | 13/07/2026 | 16/07/2026
TO-26-UGL-T134-01 | GENERATOR TRANSFORMER - UGGOOL 110-UGGOOL 33-T134 | 4 | 4 | 4 | Proposed | 13/07/2026 | 16/07/2026
TO-26-UGL-T134-02 | GENERATOR TRANSFORMER - UGGOOL 110-UGGOOL 33-T134 | 4 | 4 | 4 | Proposed | 13/07/2026 | 16/07/2026
TO-26-CF-CAP2-01 | CAPACITOR/SVC/REACTOR - CATHALEENS FALL 110-CATHALEENS FALL 110-CAP2 | 11 | 9 | 9 | Proposed | 14/07/2026 | 24/07/2026
TO-26-CF-110K1-2-02 | COUPLER/SECTIONALISING CB - CATHALEENS FALL 110-CATHALEENS FALL 110-110K1-2 | 21 | 14 | 14 | Proposed | 15/07/2026 | 04/08/2026
TO-26-CLN-110SA2-04 | SECTIONALISING DISCONNECT - CLOON 110-CLOON 110-110SA2 | 7 | 5 | 5 | Proposed | 17/07/2026 | 23/07/2026
TO-26-CLN-LA-1-06 | 110kV FEEDER - CLOON 110-LANESBORO 110-1 | 7 | 5 | 5 | Proposed | 17/07/2026 | 23/07/2026
TO-26-CLN-T142-02 | DISTRIBUTION TRANSFORMER - CLOON 110-CLOON 38-T142 | 7 | 5 | 5 | Reference | 17/07/2026 | 23/07/2026
TO-26-ARV-COS-1-07 | 110kV FEEDER - ARVA 110-CARRICK ON SHANNON 110-1 | 12 | 10 | 10 | Proposed | 20/07/2026 | 31/07/2026
TO-26-110 kV B1 @ CSH-05 | BUSBAR SECTION - CASHLA 110-CASHLA 110-110B1 | 8 | 6 | 6 | Proposed | 20/07/2026 | 27/07/2026
TO-26-110 kV B2 @ CSH-03 | BUSBAR SECTION - CASHLA 110-CASHLA 110-110B2 | 8 | 6 | 6 | Proposed | 20/07/2026 | 27/07/2026
TO-26-CSH-110K1-2-03 | COUPLER/SECTIONALISING CB - CASHLA 110-CASHLA 110-110K1-2 | 8 | 6 | 6 | Proposed | 20/07/2026 | 27/07/2026
TO-26-CSH-GAL GIS-1-01 | 110kV FEEDER - CASHLA 110-GALWAY GIS 110-1 | 2 | 2 | 2 | Proposed | 20/07/2026 | 21/07/2026
TO-26-KLH-KNY-1-01 | 110kV FEEDER - KNOCKALOUGH 110-KNOCKRANNY 110-1 | 5 | 5 | 5 | Proposed | 20/07/2026 | 24/07/2026
TO-26-KLH-T121-01 | GENERATOR TRANSFORMER - KNOCKALOUGH 110-KNOCKALOUGH 20-T121 | 5 | 5 | 5 | Proposed | 20/07/2026 | 24/07/2026
TO-26-KLH-T121-02 | GENERATOR TRANSFORMER - KNOCKALOUGH 110-KNOCKALOUGH 20-T121 | 2 | 2 | 2 | Proposed | 22/07/2026 | 23/07/2026
TO-26-CSH-GAL GIS-2-02 | 110kV FEEDER - CASHLA 110-GALWAY GIS 110-2 | 2 | 2 | 2 | Proposed | 28/07/2026 | 29/07/2026
TO-26-LET-PST-01 | TRANSFORMER - LETTERKENNY 110-STRABANE 110-PST | 10 | 7 | 7 | Proposed | 29/07/2026 | 07/08/2026
TO-26-CSH-SAL-1-01 | 110kV FEEDER - CASHLA 110-SALTHILL 110-1 | 23 | 16 | 16 | Proposed | 30/07/2026 | 21/08/2026
TO-26-CLN-T141-04 | DISTRIBUTION TRANSFORMER - CLOON 110-CLOON 38-T141 | 2 | 2 | 2 | Reference (Proposed) | 30/07/2026 | 31/07/2026
TO-26-CF-CLO-1-01 | 110kV FEEDER - CATHALEENS FALL 110-CLOGHER 110-1 | 3 | 3 | 3 | Proposed | 04/08/2026 | 06/08/2026
TO-26-110 kV A1 @ SRA-02 | BUSBAR SECTION - SRANANAGH 110-SRANANAGH 110-110A1 | 10 | 8 | 8 | Proposed | 05/08/2026 | 14/08/2026
TO-26-110 kV A2 @ SRA-01 | BUSBAR SECTION - SRANANAGH 110-SRANANAGH 110-110A2 | 10 | 8 | 8 | Proposed | 05/08/2026 | 14/08/2026
TO-26-110 kV B1 @ SRA-02 | BUSBAR SECTION - SRANANAGH 110-SRANANAGH 110-110B1 | 10 | 8 | 8 | Proposed | 05/08/2026 | 14/08/2026
TO-26-110 kV B2 @ SRA-01 | BUSBAR SECTION - SRANANAGH 110-SRANANAGH 110-110B2 | 10 | 8 | 8 | Proposed | 05/08/2026 | 14/08/2026
TO-26-SRA-110K1-2-03 | COUPLER/SECTIONALISING CB - SRANANAGH 110-SRANANAGH 110-110K1-2 | 10 | 8 | 8 | Proposed | 05/08/2026 | 14/08/2026
TO-26-CDY-110SA1-01 | SECTIONALISING DISCONNECT - CORDERRY 110-CORDERRY 110-110SA1 | Unknown | Unknown | 5 | Planned | August | August
TO-26-CDY-110SA2-01 | SECTIONALISING DISCONNECT - CORDERRY 110-CORDERRY 110-110SA2 | Unknown | Unknown | 5 | Planned | August | August
TO-26-CDY-GRV-1-01 | 110kV FEEDER - CORDERRY 110-GARVAGH 110-1 | Unknown | Unknown | 10 | Planned | August | August
TO-26-CDY-T122-01 | DISTRIBUTION TRANSFORMER - CORDERRY 110-CORDERRY 20-T122 | Unknown | Unknown | 5 | Reference (Planned) | August | August
TO-26-FLA-GIL-1-03 | 110kV FEEDER - FLAGFORD 110-GILRA 110-1 | 5 | 5 | 5 | Proposed | 10/08/2026 | 14/08/2026
TO-26-GRV-110K1-01 | COUPLER/SECTIONALISING CB - GARVAGH 110-GARVAGH 110-110K1 | Unknown | Unknown | 2 | Planned | August | August
TO-26-GRV-T121-01 | GENERATOR TRANSFORMER - GARVAGH 110-GARVAGH 20-T121 | Unknown | Unknown | 8 | Planned | August | August
TO-26-GRV-T141-01 | DISTRIBUTION TRANSFORMER - GARVAGH 110-GARVAGH 20-T141 | Unknown | Unknown | 8 | Reference (Planned) | August | August
TO-26-GIL-T121-01 | TSO CUSTOMER TRANSFORMER - GILRA 110-GILRA 20-T121 | 5 | 5 | 5 | Reference (Proposed) | 10/08/2026 | 14/08/2026
TO-26-GOL-T101-02 | GENERATOR TRANSFORMER - GOLAGH 110-GOLAGH 10-T101 | Unknown | Unknown | 15 | Planned | August | September
TO-26-GOL,T-CLO-1-02 | 110kV FEEDER - GOLAGH tee-CLOGHER 110-1 | Unknown | Unknown | 15 | Planned | August | September
TO-26-GOL,T-GOL-1-01 | 110kV FEEDER - GOLAGH tee-GOLAGH 110-1 | Unknown | Unknown | 15 | Planned | August | September
TO-26-GOL,T-LET-1-01 | 110kV FEEDER - GOLAGH tee-LETTERKENNY 110-1 | Unknown | Unknown | 15 | Planned | August | September
TO-26-BK-SKY-1-01 | 110kV FEEDER - BELLACORICK 110-SRAHNAKILLY 110-1 | 5 | 5 | 5 | Proposed | 24/08/2026 | 28/08/2026
TO-26-CSH-CAP1-02 | CAPACITOR/SVC/REACTOR - CASHLA 110-CASHLA 110-CAP1 | 10 | 8 | 8 | Proposed | 24/08/2026 | 02/09/2026
TO-26-CSH-T2101-02 | TRANSFORMER - CASHLA 220-CASHLA 110-T2101 | Unknown | Unknown | 7 | Planned | August | September
TO-26-SKY-110SA1-01 | SECTIONALISING DISCONNECT - SRAHNAKILLY 110-SRAHNAKILLY 110-110SA1 | 5 | 5 | 5 | Proposed | 24/08/2026 | 28/08/2026
TO-26-SKY-110SA2-01 | SECTIONALISING DISCONNECT - SRAHNAKILLY 110-SRAHNAKILLY 110-110SA2 | 5 | 5 | 5 | Proposed | 24/08/2026 | 28/08/2026
TO-26-SKY-T131-01 | GENERATOR TRANSFORMER - SRAHNAKILLY 110-SRAHNAKILLY 33-T131 | 5 | 5 | 5 | Proposed | 24/08/2026 | 28/08/2026
TO-26-SKY-T131-02 | GENERATOR TRANSFORMER - SRAHNAKILLY 110-SRAHNAKILLY 33-T131 | 5 | 5 | 5 | Proposed | 24/08/2026 | 28/08/2026
TO-26-SKY-T132-01 | GENERATOR TRANSFORMER - SRAHNAKILLY 110-SRAHNAKILLY 33-T132 | 8 | 6 | 6 | Proposed | 24/08/2026 | 31/08/2026
TO-26-SKY-T132-02 | GENERATOR TRANSFORMER - SRAHNAKILLY 110-SRAHNAKILLY 33-T132 | 5 | 5 | 5 | Proposed | 24/08/2026 | 28/08/2026
TO-26-CSH-CAP2-02 | CAPACITOR/SVC/REACTOR - CASHLA 110-CASHLA 110-CAP2 | Unknown | Unknown | 3 | Planned | September | September
TO-26-CSH-T2102-02 | TRANSFORMER - CASHLA 220-CASHLA 110-T2102 | Unknown | Unknown | 18 | Planned | September | September
TO-26-CBR-CLN-1-08 | 110kV FEEDER - CASTLEBAR 110-CLOON 110-1 | Unknown | Unknown | 5 | Planned | September | September
TO-26-CF-SRA-1-04 | 110kV FEEDER - CATHALEENS FALL 110-SRANANAGH 110-1 | Unknown | Unknown | 10 | Planned | September | September
TO-26-CLO-110K1-2-01 | COUPLER/SECTIONALISING CB - CLOGHER 110-CLOGHER 110-110K1-2 | Unknown | Unknown | 2 | Planned | September | September
TO-26-LET-T142-01 | DISTRIBUTION TRANSFORMER - LETTERKENNY 110-LETTERKENNY 38-T142 | Unknown | Unknown | 10 | Reference (Planned) | September | September
TO-26-CBR-CLN-1-09 | 110kV FEEDER - CASTLEBAR 110-CLOON 110-1 | Unknown | Unknown | 7 | Planned | September | September
TO-26-CLN-110SA1-05 | SECTIONALISING DISCONNECT - CLOON 110-CLOON 110-110SA1 | Unknown | Unknown | 7 | Planned | September | September
TO-26-ARI-T121-01 | DISTRIBUTION TRANSFORMER - ARIGNA 110-ARIGNA 20-T121 | Unknown | Unknown | 5 | Reference (Planned) | October | October
TO-26-ARI,T-ARI-1-02 | 110kV FEEDER - ARIGNA tee-ARIGNA 110-1 | Unknown | Unknown | 5 | Planned | October | October
TO-26-ARI,T-COS-1-03 | 110kV FEEDER - ARIGNA tee-CARRICK ON SHANNON 110-1 | Unknown | Unknown | 5 | Planned | October | October
TO-26-ARI,T-CDY-1-02 | 110kV FEEDER - ARIGNA tee-CORDERRY 110-1 | Unknown | Unknown | 5 | Planned | October | October
TO-26-COS-FLA-2-01 | 110kV FEEDER - CARRICK ON SHANNON 110-FLAGFORD 110-2 | Unknown | Unknown | 10 | Planned | October | October
TO-26-LLA-TIV-1-02 | 110kV FEEDER - LENALEA 110-TIEVEBRACK 110-1 | Unknown | Unknown | 10 | Planned | October | October
TO-26-CSH-TY-1-01 | 220kV FEEDER - CASHLA 220-TYNAGH 220-1 | Unknown | Unknown | 5 | Planned | October | October
TO-26-CF-COR-1-02 | 110kV FEEDER - CATHALEENS FALL 110-CORRACLASSY 110-1 | Unknown | Unknown | 10 | Planned | November | November
TO-26-CSH-PRO-1-01 | 220kV FEEDER - CASHLA 220-PROSPECT 220-1 | Unknown | Unknown | 25 | Planned | November | December
TO-26-FLA-SRA-1-03 | 220kV FEEDER - FLAGFORD 220-SRANANAGH 220-1 | Unknown | Unknown | 10 | Planned | November | November
TO-26-SRA-220SA1-04 | SECTIONALISING DISCONNECT - SRANANAGH 220-SRANANAGH 220-220SA1 | Unknown | Unknown | 5 | Planned | November | November
TO-26-SRA-220SA2-04 | SECTIONALISING DISCONNECT - SRANANAGH 220-SRANANAGH 220-220SA2 | Unknown | Unknown | 6 | Planned | November | November
TO-26-SRA-T2102-04 | TRANSFORMER - SRANANAGH 220-SRANANAGH 110-T2102 | Unknown | Unknown | 10 | Planned | November | November
TO-26-FLA-LOU-1-02 | 220kV FEEDER - FLAGFORD 220-LOUTH 220-1 | Unknown | Unknown | 3 | Planned | November | November
TO-26-CSH-ENN-1-01 | 110kV FEEDER - CASHLA 110-ENNIS 110-1 | Unknown | Unknown | 3 | Planned | December | December
TO-26-SLI-SRA-2-01 | 110kV FEEDER - SLIGO 110-SRANANAGH 110-2 | Unknown | Unknown | 6 | Planned | December | December

## GEN_NorthEast
Outage ID | Feeder ID | Calendar Day Duration | Working Day Duration | Work Days | Outage Status | Start | Finish
TO-26-GWE-T102-01 | TSO CUSTOMER TRANSFORMER - GORTAWEE 110-GORTAWEE 10-T102 | 5 | 5 |  | Scheduled | 05/01/2026 | 09/01/2026
TO-26-DRY-OBE-1-02 | 110kV FEEDER - DRYBRIDGE 110-OLDBRIDGE 110-1 | 5 | 5 | 5 | Scheduled | 12/01/2026 | 16/01/2026
TO-26-LIS-LSA-1-04 | 110kV FEEDER - LISDRUM 110-LISLEA 110-1 | 10 | 8 |  | Scheduled | 12/01/2026 | 21/01/2026
TO-26-AGL-ENN-1-03 | 110kV FEEDER - AGANNYGAL 110-ENNIS 110-1 | 12 | 10 |  | Scheduled | 19/01/2026 | 30/01/2026
TO-26-SH-T2102-02 | TRANSFORMER - SHANNONBRIDGE 220-SHANNONBRIDGE 110-T2102 | 103 | 71 | 71 | Scheduled | 19/01/2026 | 01/05/2026
TO-26-ARV-SKL-2-01 | 110kV FEEDER - ARVA 110-SHANKILL 110-2 | 3 | 3 |  | Scheduled | 26/01/2026 | 28/01/2026
TO-26-BLU-MUL-1-03 | 110kV FEEDER - BLUNDELSTOWN 110-MULLINGAR 110-1 | 3 | 3 |  | Scheduled | 03/02/2026 | 05/02/2026
TO-26-MUL-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - MULLINGAR 110-MULLINGAR 110-110SA1-2CB | 2 | 2 | 2 | Scheduled | 03/02/2026 | 04/02/2026
TO-26-MUL-T102-01 | DISTRIBUTION TRANSFORMER - MULLINGAR 110-MULLINGAR 10-T102 | 2 | 2 | 2 | Reference | 03/02/2026 | 04/02/2026
TO-26-MUL-T142-01 | DISTRIBUTION TRANSFORMER - MULLINGAR 110-MULLINGAR 38-T142 | 2 | 2 | 2 | Reference | 03/02/2026 | 04/02/2026
TO-26-ARV-SKL-1-02 | 110kV FEEDER - ARVA 110-SHANKILL 110-1 | 3 | 3 | 3 | Scheduled | 04/02/2026 | 06/02/2026
TO-26-OBE-PLA-1-01 | 110kV FEEDER - OLDBRIDGE 110-PLATIN 110-1 | 5 | 5 | 5 | Scheduled | 09/02/2026 | 13/02/2026
TO-26-PLA-110SA1-01 | SECTIONALISING DISCONNECT - PLATIN 110-PLATIN 110-110SA1 | 5 | 5 | 5 | Scheduled | 09/02/2026 | 13/02/2026
TO-26-PLA-110SA2-01 | SECTIONALISING DISCONNECT - PLATIN 110-PLATIN 110-110SA2 | 5 | 5 | 5 | Scheduled | 09/02/2026 | 13/02/2026
TO-26-PLA-T101/2/3/4-01 | TSO CUSTOMER TRANSFORMER - PLATIN 110-PLATIN 10-T101/2/3/4 | 5 | 5 | 5 | Scheduled | 09/02/2026 | 13/02/2026
TO-26-GLN-PLA-1-01 | 110kV FEEDER - GALLANSTOWN 110-PLATIN 110-1 | 19 | 15 |  | Scheduled | 16/02/2026 | 06/03/2026
TO-26-GAR-PLA-1-02 | 110kV FEEDER - GARBALLAGH 110-PLATIN 110-1 | 71 | 48 | 48 | Scheduled | 16/02/2026 | 27/04/2026
TO-26-PLA-T105-01 | TSO CUSTOMER TRANSFORMER - PLATIN 110-PLATIN 10-T105 | 19 | 15 |  | Scheduled | 16/02/2026 | 06/03/2026
TO-26-DDK-110SA1-01 | SECTIONALISING DISCONNECT - DUNDALK 110-DUNDALK 110-110SA1 | 6 | 5 |  | Scheduled | 23/02/2026 | 28/02/2026
TO-26-DDK-110SA2-01 | SECTIONALISING DISCONNECT - DUNDALK 110-DUNDALK 110-110SA2 | 6 | 5 | 5 | Scheduled | 23/02/2026 | 28/02/2026
TO-26-DDK-MLN-1-01 | 110kV FEEDER - DUNDALK 110-MULLAGHARLIN 110-1 | 6 | 5 | 5 | Scheduled | 23/02/2026 | 28/02/2026
TO-26-DDK-T141-01 | DISTRIBUTION TRANSFORMER - DUNDALK 110-DUNDALK 38-T141 | 6 | 5 | 5 | Reference | 23/02/2026 | 28/02/2026
TO-26-110 kV A1 @ GOR-05 | BUSBAR SECTION - GORMAN 110-GORMAN 110-110A1 | 40 | 28 | 28 | Scheduled | 23/02/2026 | 03/04/2026
TO-26-110 kV A2 @ GOR-01 | BUSBAR SECTION - GORMAN 110-GORMAN 110-110A2 | 40 | 28 | 28 | Scheduled | 23/02/2026 | 03/04/2026
TO-26-GAR-110K1-01 | COUPLER/SECTIONALISING CB - GARBALLAGH 110-GARBALLAGH 110-110K1 | 1 | 1 | 1 | Scheduled | 03/03/2026 | 03/03/2026
TO-26-DEN-DRY-1-03 | 110kV FEEDER - DEENES 110-DRYBRIDGE 110-1 | 38 | 25 | 25 | Scheduled | 09/03/2026 | 15/04/2026
TO-26-LSA-110K1-02 | COUPLER/SECTIONALISING CB - LISLEA 110-LISLEA 110-110K1 | 1 | 1 | 1 | Scheduled | 09/03/2026 | 09/03/2026
TO-26-TEN-T132-01 | GENERATOR TRANSFORMER - TIMAHOE 110-TIMAHOE 33-T132 | 2 | 2 | 2 | Scheduled | 09/03/2026 | 10/03/2026
TO-26-GOR-NAV-1-02 | 110kV FEEDER - GORMAN 110-NAVAN 110-1 | 1 | 1 | 1 | Scheduled | 10/03/2026 | 10/03/2026
TO-26-LIS-LOU-1-06 | 110kV FEEDER - LISDRUM 110-LOUTH 110-1 | 3 | 3 | 3 | Scheduled | 11/03/2026 | 13/03/2026
TO-26-ATH-110SA1-2CB-08 | COUPLER/SECTIONALISING CB - ATHLONE 110-ATHLONE 110-110SA1-2CB | 1 | 0 | 0 | Scheduled | 14/03/2026 | 14/03/2026
TO-26-ATH-CAP3-08 | CAPACITOR/SVC/REACTOR - ATHLONE 110-ATHLONE 110-CAP3 | 1 | 0 | 0 | Scheduled | 14/03/2026 | 14/03/2026
TO-26-ATH-LA-1-08 | 110kV FEEDER - ATHLONE 110-LANESBORO 110-1 | 1 | 0 | 0 | Scheduled | 14/03/2026 | 14/03/2026
TO-26-ATH-T141-04 | DISTRIBUTION TRANSFORMER - ATHLONE 110-ATHLONE 38-T141 | 1 | 0 | 0 | Reference | 14/03/2026 | 14/03/2026
TO-26-SH-220K1-2-02 | COUPLER/SECTIONALISING CB - SHANNONBRIDGE 220-SHANNONBRIDGE 220-220K1-2 | 24 | 15 | 15 | Scheduled | 16/03/2026 | 08/04/2026
TO-26-GOR-NAV-2-02 | 110kV FEEDER - GORMAN 110-NAVAN 110-2 | 5 | 5 | 5 | Scheduled | 23/03/2026 | 27/03/2026
TO-26-OBE-T123-01 | TSO CUSTOMER TRANSFORMER - OLDBRIDGE 110-OLDBRIDGE 20-T123 | 5 | 5 | 5 | Scheduled | 23/03/2026 | 27/03/2026
TO-26-LSA-SKL-1-02 | 110kV FEEDER - LISLEA 110-SHANKILL 110-1 | 3 | 3 | 3 | Scheduled | 30/03/2026 | 01/04/2026
TO-26-OBE-T121-01 | TSO CUSTOMER TRANSFORMER - OLDBRIDGE 110-OLDBRIDGE 20-T121 | 5 | 4 | 4 | Scheduled | 30/03/2026 | 03/04/2026
TO-26-DEN-T132-02 | GENERATOR TRANSFORMER - DEENES 110-DEENES 33-T132 | 1 | 1 | 1 | Scheduled | 02/04/2026 | 02/04/2026
TO-26-ARV-GWE-1-04 | 110kV FEEDER - ARVA 110-GORTAWEE 110-1 | 2 | 2 | 2 | Scheduled | 07/04/2026 | 08/04/2026
TO-26-FLA-LOU-1-06 | 220kV FEEDER - FLAGFORD 220-LOUTH 220-1 | 51 | 36 | 36 | Scheduled | 09/04/2026 | 29/05/2026
TO-26-220 kV A2 @ LOU-06 | BUSBAR SECTION - LOUTH 220-LOUTH 220-220A2 | 9 | 7 | 7 | Scheduled | 09/04/2026 | 17/04/2026
TO-26-220 kV B2 @ LOU-06 | BUSBAR SECTION - LOUTH 220-LOUTH 220-220B2 | 9 | 7 | 7 | Scheduled | 09/04/2026 | 17/04/2026
TO-26-LSA-T131-02 | GENERATOR TRANSFORMER - LISLEA 110-LISLEA 33-T131 | 4 | 4 | 4 | Scheduled | 13/04/2026 | 16/04/2026
TO-26-RRU-T122-01 | GENERATOR TRANSFORMER - RATRUSSAN 110-RATRUSSAN 20-T122 | 5 | 5 | 5 | Scheduled | 13/04/2026 | 17/04/2026
TO-26-DDK-MLN-1-02 | 110kV FEEDER - DUNDALK 110-MULLAGHARLIN 110-1 | 2 | 2 | 2 | Scheduled | 14/04/2026 | 15/04/2026
TO-26-GOR-T122-01 | GENERATOR TRANSFORMER - GORMAN 110-GORMAN 20-T122 | 2 | 2 | 2 | Scheduled | 14/04/2026 | 15/04/2026
TO-26-DDK-LOU-1-01 | 110kV FEEDER - DUNDALK 110-LOUTH 110-1 | 115 | 80 |  | Scheduled | 20/04/2026 | 12/08/2026
TO-26-110 kV A2 @ LOU-09 | BUSBAR SECTION - LOUTH 110-LOUTH 110-110A2 | 4 | 4 | 4 | Scheduled | 20/04/2026 | 23/04/2026
TO-26-110 kV B2 @ LOU-09 | BUSBAR SECTION - LOUTH 110-LOUTH 110-110B2 | 4 | 4 | 4 | Scheduled | 20/04/2026 | 23/04/2026
TO-26-GOR-MTH-1-03 | 110kV FEEDER - GORMAN 110-MEATH HILL 110-1 | 15 | 10 | 10 | Scheduled | 22/04/2026 | 06/05/2026
TO-26-DER-TSB-1-04 | 110kV FEEDER - DERRYIRON 110-THORNSBERRY 110-1 | 56 | 38 | 38 | Scheduled | 27/04/2026 | 21/06/2026
TO-26-KDN-T131-01 | GENERATOR TRANSFORMER - KNOCKDRIN 110-KNOCKDRIN 33-T131 | 4 | 4 | 4 | Scheduled | 27/04/2026 | 30/04/2026
TO-26-LOU-MTH-1-03 | 110kV FEEDER - LOUTH 110-MEATH HILL 110-1 | 21 | 15 | 15 | Scheduled | 07/05/2026 | 27/05/2026
TO-26-COR-PST-03 | TRANSFORMER - CORRACLASSY 110-ENNISKILLEN 110-PST | 23 | 16 | 16 | Scheduled | 11/05/2026 | 02/06/2026
TO-26-MLC-T121-01 | GENERATOR TRANSFORMER - MOUNTLUCAS 110-MOUNTLUCAS 20-T121 | 2 | 2 | 2 | Scheduled | 11/05/2026 | 12/05/2026
TO-26-SH-T2101-01 | TRANSFORMER - SHANNONBRIDGE 220-SHANNONBRIDGE 110-T2101 | 12 | 10 | 10 | Scheduled | 11/05/2026 | 22/05/2026
TO-26-SLB-T132-01 | GENERATOR TRANSFORMER - SLIABH BAWN 110-SLIABH BAWN 33-T132 | 2 | 2 | 2 | Scheduled | 13/05/2026 | 14/05/2026
TO-26-DER-T1/T2-02 | GENERATOR TRANSFORMER - DERRYIRON 110-RHODE 110-T1/T2 | 15 | 11 | 11 | Scheduled | 15/05/2026 | 29/05/2026
TO-26-MTH-T141-02 | DISTRIBUTION TRANSFORMER - MEATH HILL 110-MEATH HILL 38-T141 | 7 | 5 | 5 | Reference | 21/05/2026 | 27/05/2026
TO-26-DER-TEN-1-01 | 110kV FEEDER - DERRYIRON 110-TIMAHOE 110-1 | 22 | 15 | 15 | Scheduled | 25/05/2026 | 15/06/2026
TO-26-ATH-T142-08 | DISTRIBUTION TRANSFORMER - ATHLONE 110-ATHLONE 38-T142 | 2 | 2 | 2 | Reference (Proposed) | 15/06/2026 | 16/06/2026
TO-26-GLN-PLA-1-05 | 110kV FEEDER - GALLANSTOWN 110-PLATIN 110-1 | 5 | 5 | 5 | Scheduled | 15/06/2026 | 19/06/2026
TO-26-GAR-PLA-1-04 | 110kV FEEDER - GARBALLAGH 110-PLATIN 110-1 | 5 | 5 | 5 | Proposed | 15/06/2026 | 19/06/2026
TO-26-PLA-110SA1-05 | SECTIONALISING DISCONNECT - PLATIN 110-PLATIN 110-110SA1 | 5 | 5 | 5 | Proposed | 15/06/2026 | 19/06/2026
TO-26-PLA-110SA2-05 | SECTIONALISING DISCONNECT - PLATIN 110-PLATIN 110-110SA2 | 5 | 5 | 5 | Proposed | 15/06/2026 | 19/06/2026
TO-26-PLA-T105-02 | TSO CUSTOMER TRANSFORMER - PLATIN 110-PLATIN 10-T105 | 5 | 5 | 5 | Proposed | 15/06/2026 | 19/06/2026
TO-26-KDN-T131-02 | GENERATOR TRANSFORMER - KNOCKDRIN 110-KNOCKDRIN 33-T131 | 1 | 1 | 1 | Scheduled | 16/06/2026 | 16/06/2026
TO-26-LOU-RRU-1-05 | 110kV FEEDER - LOUTH 110-RATRUSSAN 110-1 | 3 | 3 | 3 | Proposed | 23/06/2026 | 25/06/2026
TO-26-BAL-DEN-1-01 | 110kV FEEDER - BALTRASNA 110-DEENES 110-1 | 4 | 4 | 4 | Proposed | 29/06/2026 | 02/07/2026
TO-26-LOU-T2102-07 | TRANSFORMER - LOUTH 220-LOUTH 110-T2102 | 10 | 8 | 8 | Proposed | 29/06/2026 | 08/07/2026
TO-26-GWE-CAP1-01 | CAPACITOR/SVC/REACTOR - GORTAWEE 110-GORTAWEE 110-CAP1 | 10 | 8 | 8 | Proposed | 30/06/2026 | 09/07/2026
TO-26-CFN-SH-1-01 | 220kV FEEDER - CLONIFFEEN 220-SHANNONBRIDGE 220-1 | 5 | 5 | 5 | Proposed | 06/07/2026 | 10/07/2026
TO-26-CFN-T232-01 | GENERATOR TRANSFORMER - CLONIFFEEN 220-CLONIFFEEN 33-T232 | 5 | 5 | 5 | Proposed | 06/07/2026 | 10/07/2026
TO-26-LIS-CAP1-04 | CAPACITOR/SVC/REACTOR - LISDRUM 110-LISDRUM 110-CAP1 | 11 | 9 | 9 | Proposed | 06/07/2026 | 16/07/2026
TO-26-220 kV A2 @ SH-02 | BUSBAR SECTION - SHANNONBRIDGE 220-SHANNONBRIDGE 220-220A2 | 5 | 5 | 5 | Proposed | 06/07/2026 | 10/07/2026
TO-26-220 kV B2 @ SH-02 | BUSBAR SECTION - SHANNONBRIDGE 220-SHANNONBRIDGE 220-220B2 | 5 | 5 | 5 | Proposed | 06/07/2026 | 10/07/2026
TO-26-MUL-CAP2-02 | CAPACITOR/SVC/REACTOR - MULLINGAR 110-MULLINGAR 110-CAP2 | 3 | 3 | 3 | Proposed | 07/07/2026 | 09/07/2026
TO-26-MUL-CAP1-01 | CAPACITOR/SVC/REACTOR - MULLINGAR 110-MULLINGAR 110-CAP1 | 11 | 9 | 9 | Proposed | 14/07/2026 | 24/07/2026
TO-26-DRY-110SA1-02 | SECTIONALISING DISCONNECT - DRYBRIDGE 110-DRYBRIDGE 110-110SA1 | 8 | 6 | 6 | Proposed | 16/07/2026 | 23/07/2026
TO-26-DRY-LOU-1-02 | 110kV FEEDER - DRYBRIDGE 110-LOUTH 110-1 | 22 | 15 | 15 | Proposed | 16/07/2026 | 06/08/2026
TO-26-DRY-OBE-1-01 | 110kV FEEDER - DRYBRIDGE 110-OLDBRIDGE 110-1 | 8 | 6 | 6 | Proposed | 16/07/2026 | 23/07/2026
TO-26-DRY-OBE-1-03 | 110kV FEEDER - DRYBRIDGE 110-OLDBRIDGE 110-1 | 8 | 6 | 6 | Proposed | 16/07/2026 | 23/07/2026
TO-26-MLN-T123-02 | TSO CUSTOMER TRANSFORMER - MULLAGHARLIN 110-MULLAGHARLIN 20-T123 | 2 | 2 | 2 | Proposed | 16/07/2026 | 17/07/2026
TO-26-CLN-LA-1-06 | 110kV FEEDER - CLOON 110-LANESBORO 110-1 | 7 | 5 | 5 | Proposed | 17/07/2026 | 23/07/2026
TO-26-LA-T104-04 | GENERATOR TRANSFORMER - LANESBORO 110-LANESBORO G4-T104 | 7 | 5 | 5 | Proposed | 17/07/2026 | 23/07/2026
TO-26-110 kV A2 @ ARV-01 | BUSBAR SECTION - ARVA 110-ARVA 110-110A2 | 12 | 10 | 10 | Proposed | 20/07/2026 | 31/07/2026
TO-26-110 kV B2 @ ARV-01 | BUSBAR SECTION - ARVA 110-ARVA 110-110B2 | 12 | 10 | 10 | Proposed | 20/07/2026 | 31/07/2026
TO-26-ARV-COS-1-07 | 110kV FEEDER - ARVA 110-CARRICK ON SHANNON 110-1 | 12 | 10 | 10 | Proposed | 20/07/2026 | 31/07/2026
TO-26-DEY-T132-01 | GENERATOR TRANSFORMER - DERRYCARNEY 110-DERRYCARNEY 33-T132 | 5 | 5 | 5 | Proposed | 20/07/2026 | 24/07/2026
TO-26-220 kV A1 @ LOU-01 | BUSBAR SECTION - LOUTH 220-LOUTH 220-220A1 | 12 | 10 | 10 | Proposed | 20/07/2026 | 31/07/2026
TO-26-220 kV B1 @ LOU-01 | BUSBAR SECTION - LOUTH 220-LOUTH 220-220B1 | 12 | 10 | 10 | Proposed | 20/07/2026 | 31/07/2026
TO-26-LOU-AT2-02 | TRANSFORMER - LOUTH 220-LOUTH 275-AT2 | 12 | 10 | 10 | Proposed | 20/07/2026 | 31/07/2026
TO-26-LOU-TAN-2-03 | 275kV FEEDER - LOUTH 275-TANDRAGEE 275-2 | 12 | 10 | 10 | Proposed | 20/07/2026 | 31/07/2026
TO-26-LA-RIC-2-08 | 110kV FEEDER - LANESBORO 110-RICHMOND 110-2 | 2 | 2 | 2 | Reference (Proposed) | 21/07/2026 | 22/07/2026
TO-26-LA-SLB-1-07 | 110kV FEEDER - LANESBORO 110-SLIABH BAWN 110-1 | 11 | 9 | 9 | Proposed | 21/07/2026 | 31/07/2026
TO-26-LIS-CAP2-05 | CAPACITOR/SVC/REACTOR - LISDRUM 110-LISDRUM 110-CAP2 | 5 | 5 | 5 | Proposed | 27/07/2026 | 31/07/2026
TO-26-ATH-110SA1-2CB-06 | COUPLER/SECTIONALISING CB - ATHLONE 110-ATHLONE 110-110SA1-2CB | Unknown | Unknown | 10 | Planned | August | August
TO-26-ATH-SH-1-09 | 110kV FEEDER - ATHLONE 110-SHANNONBRIDGE 110-1 | Unknown | Unknown | 15 | Planned | August | August
TO-26-LOU-AT3-02 | TRANSFORMER - LOUTH 220-LOUTH 275-AT3 | Unknown | Unknown | 9 | Planned | August | August
TO-26-AGL-SH-1-02 | 110kV FEEDER - AGANNYGAL 110-SHANNONBRIDGE 110-1 | 19 | 15 | 15 | Proposed | 10/08/2026 | 28/08/2026
TO-26-KIN-T101-02 | TSO CUSTOMER TRANSFORMER - KINNEGAD 110-KINNEGAD 10-T101 | 2 | 2 | 2 | Proposed | 11/08/2026 | 12/08/2026
TO-26-KIN-T101-03 | TSO CUSTOMER TRANSFORMER - KINNEGAD 110-KINNEGAD 10-T101 | Unknown | Unknown | 2 | Planned | August | August
TO-26-KIN-T102-05 | TSO CUSTOMER TRANSFORMER - KINNEGAD 110-KINNEGAD 10-T102 | Unknown | Unknown | 2 | Planned | August | August
TO-26-MLN-T124-01 | TSO CUSTOMER TRANSFORMER - MULLAGHARLIN 110-MULLAGHARLIN 20-T124 | 2 | 1 | 1 | Proposed | 14/08/2026 | 15/08/2026
TO-26-ATH-CAP3-06 | CAPACITOR/SVC/REACTOR - ATHLONE 110-ATHLONE 110-CAP3 | 21 | 15 | 15 | Proposed | 25/08/2026 | 14/09/2026
TO-26-ATH-LA-1-04 | 110kV FEEDER - ATHLONE 110-LANESBORO 110-1 | Unknown | Unknown | 15 | Planned | August | September
TO-26-LOU-MLN-1-02 | 110kV FEEDER - LOUTH 110-MULLAGHARLIN 110-1 | Unknown | Unknown | 4 | Planned | August | August
TO-26-MLN-110SA1-2CB-02 | COUPLER/SECTIONALISING CB - MULLAGHARLIN 110-MULLAGHARLIN 110-110SA1-2CB | Unknown | Unknown | 4 | Planned | August | August
TO-26-MLN-T122-01 | DISTRIBUTION TRANSFORMER - MULLAGHARLIN 110-MULLAGHARLIN 20-T122 | Unknown | Unknown | 4 | Reference (Planned) | August | August
TO-26-MLN-T124-02 | TSO CUSTOMER TRANSFORMER - MULLAGHARLIN 110-MULLAGHARLIN 20-T124 | Unknown | Unknown | 4 | Planned | August | August
TO-26-MP GIS-OST-1-01 | 400kV FEEDER - MONEYPOINT GIS 400-OLDSTREET 400-1 | Unknown | Unknown | 15 | Planned | August | September
TO-26-OST-WOO-1-02 | 400kV FEEDER - OLDSTREET 400-WOODLAND 400-1 | Unknown | Unknown | 15 | Planned | August | September
TO-26-TY-220SA2-01 | SECTIONALISING DISCONNECT - TYNAGH 220-TYNAGH 220-220SA2 | Unknown | Unknown | 3 | Planned | August | September
TO-26-LA-RIC-1-01 | 110kV FEEDER - LANESBORO 110-RICHMOND 110-1 | Unknown | Unknown | 2 | Reference (Planned) | September | September
TO-26-LOU-AT1-02 | TRANSFORMER - LOUTH 220-LOUTH 275-AT1 | Unknown | Unknown | 9 | Planned | September | September
TO-26-LOU-TAN-1-01 | 275kV FEEDER - LOUTH 275-TANDRAGEE 275-1 | Unknown | Unknown | 9 | Planned | September | September
TO-26-LA-T141-01 | DISTRIBUTION TRANSFORMER - LANESBORO 110-LANESBORO 38-T141 | 2 | 2 | 2 | Reference (Proposed) | 03/09/2026 | 04/09/2026
TO-26-SLB-110K2-01 | COUPLER/SECTIONALISING CB - SLIABH BAWN 110-SLIABH BAWN 110-110K2 | Unknown | Unknown | 2 | Planned | September | September
TO-26-OBE-110K1-01 | COUPLER/SECTIONALISING CB - OLDBRIDGE 110-OLDBRIDGE 110-110K1 | Unknown | Unknown | 4 | Planned | September | September
TO-26-OBE-110K2-01 | COUPLER/SECTIONALISING CB - OLDBRIDGE 110-OLDBRIDGE 110-110K2 | Unknown | Unknown | 4 | Planned | September | September
TO-26-OBE-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - OLDBRIDGE 110-OLDBRIDGE 110-110SA1-2CB | Unknown | Unknown | 4 | Planned | September | September
TO-26-OBE-110SB1-2CB-01 | COUPLER/SECTIONALISING CB - OLDBRIDGE 110-OLDBRIDGE 110-110SB1-2CB | Unknown | Unknown | 4 | Planned | September | September
TO-26-SH-110K1-2-02 | COUPLER/SECTIONALISING CB - SHANNONBRIDGE 110-SHANNONBRIDGE 110-110K1-2 | Unknown | Unknown | 8 | Planned | September | September
TO-26-TY-220SA1-01 | SECTIONALISING DISCONNECT - TYNAGH 220-TYNAGH 220-220SA1 | Unknown | Unknown | 1 | Planned | September | September
TO-26-COR-GWE-1-02 | 110kV FEEDER - CORRACLASSY 110-GORTAWEE 110-1 | Unknown | Unknown | 10 | Planned | September | October
TO-26-GAR-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - GARBALLAGH 110-GARBALLAGH 110-110SA1-2CB | Unknown | Unknown | 1 | Planned | October | October
TO-26-GAR-110SB1-2CB-01 | COUPLER/SECTIONALISING CB - GARBALLAGH 110-GARBALLAGH 110-110SB1-2CB | Unknown | Unknown | 1 | Planned | October | October
TO-26-KLN-SH-1-03 | 220kV FEEDER - KILLONAN 220-SHANNONBRIDGE 220-1 | Unknown | Unknown | 52 | Planned | October | December
TO-26-GAR-GOR-1-03 | 110kV FEEDER - GARBALLAGH 110-GORMAN 110-1 | 23 | 16 | 16 | Proposed | 08/10/2026 | 30/10/2026
TO-26-LOU-CAP1-03 | CAPACITOR/SVC/REACTOR - LOUTH 110-LOUTH 110-CAP1 | Unknown | Unknown | 5 | Planned | October | October
TO-26-CSH-TY-1-01 | 220kV FEEDER - CASHLA 220-TYNAGH 220-1 | Unknown | Unknown | 5 | Planned | October | October
TO-26-LOU-T2101-03 | TRANSFORMER - LOUTH 220-LOUTH 110-T2101 | Unknown | Unknown | 14 | Planned | October | November
TO-26-DAL,T-DAL-1-01 | 110kV FEEDER - DALLOW tee-DALLOW 110-1 | Unknown | Unknown | 14 | Planned | October | November
TO-26-DAL,T-SH-1-01 | 110kV FEEDER - DALLOW tee-SHANNONBRIDGE 110-1 | Unknown | Unknown | 14 | Planned | October | November
TO-26-CF-COR-1-02 | 110kV FEEDER - CATHALEENS FALL 110-CORRACLASSY 110-1 | Unknown | Unknown | 10 | Planned | November | November
TO-26-LOU-110K1-2-03 | COUPLER/SECTIONALISING CB - LOUTH 110-LOUTH 110-110K1-2 | Unknown | Unknown | 8 | Planned | November | November
TO-26-LOU-T2103-03 | TRANSFORMER - LOUTH 220-LOUTH 110-T2103 | Unknown | Unknown | 5 | Planned | November | November
TO-26-BLU-MUL-1-02 | 110kV FEEDER - BLUNDELSTOWN 110-MULLINGAR 110-1 | Unknown | Unknown |  | Planned | November | December
TO-26-LOU-T2104-06 | TRANSFORMER - LOUTH 220-LOUTH 110-T2104 | Unknown | Unknown | 10 | Planned | November | November
TO-26-MUL-110SA1-2CB-02 | COUPLER/SECTIONALISING CB - MULLINGAR 110-MULLINGAR 110-110SA1-2CB | Unknown | Unknown | 5 | Planned | November | November
TO-26-ARV-NAV-1-01 | 110kV FEEDER - ARVA 110-NAVAN 110-1 | Unknown | Unknown | 9 | Planned | November | December
TO-26-GOR-NAV-3-01 | 110kV FEEDER - GORMAN 110-NAVAN 110-3 | Unknown | Unknown | 10 | Planned | November | December
TO-26-FLA-LOU-1-02 | 220kV FEEDER - FLAGFORD 220-LOUTH 220-1 | Unknown | Unknown | 3 | Planned | November | November
TO-26-ARV-GWE-1-03 | 110kV FEEDER - ARVA 110-GORTAWEE 110-1 | Unknown | Unknown | 10 | Planned | November | December
TO-26-RRU-SKL-1-01 | 110kV FEEDER - RATRUSSAN 110-SHANKILL 110-1 | Unknown | Unknown | 8 | Planned | December | December
TO-26-RTN-T131-01 | GENERATOR TRANSFORMER - RATTIN 110-RATTIN 33-T131 | Unknown | Unknown | 1 | Planned | December | December

## GEN_Dublin
Outage ID | Feeder ID | Calendar Day Duration | Working Day Duration | Work Days | Outage Status | Start | Finish
TO-26-110 kV A4 @ CBT-01 | BUSBAR SECTION - CASTLEBAGOT 110-CASTLEBAGOT 110-110A4 | 5 | 5 | 5 | Scheduled | 05/01/2026 | 09/01/2026
TO-26-110 kV B4 @ CBT-01 | BUSBAR SECTION - CASTLEBAGOT 110-CASTLEBAGOT 110-110B4 | 5 | 5 | 5 | Scheduled | 05/01/2026 | 09/01/2026
TO-26-CBT-110K4-01 | COUPLER/SECTIONALISING CB - CASTLEBAGOT 110-CASTLEBAGOT 110-110K4 | 5 | 5 |  | Scheduled | 05/01/2026 | 09/01/2026
TO-26-CBT-110SA2-4CB-01 | COUPLER/SECTIONALISING CB - CASTLEBAGOT 110-CASTLEBAGOT 110-110SA2-4CB | 5 | 5 | 5 | Scheduled | 05/01/2026 | 09/01/2026
TO-26-CBT-110SB2-4CB-01 | COUPLER/SECTIONALISING CB - CASTLEBAGOT 110-CASTLEBAGOT 110-110SB2-4CB | 5 | 5 | 5 | Scheduled | 05/01/2026 | 09/01/2026
TO-26-220 kV A2 @ FIN-05 | BUSBAR SECTION - FINGLAS 220-FINGLAS 220-220A2 | 5 | 5 | 5 | Scheduled | 05/01/2026 | 09/01/2026
TO-26-220 kV B2 @ FIN-03 | BUSBAR SECTION - FINGLAS 220-FINGLAS 220-220B2 | 5 | 5 | 5 | Scheduled | 05/01/2026 | 09/01/2026
TO-26-FIN-220K2-05 | COUPLER/SECTIONALISING CB - FINGLAS 220-FINGLAS 220-220K2 | 5 | 5 | 5 | Scheduled | 05/01/2026 | 09/01/2026
TO-26-FIN-220SA1-2CB-06 | COUPLER/SECTIONALISING CB - FINGLAS 220-FINGLAS 220-220SA1-2CB | 5 | 5 | 5 | Scheduled | 05/01/2026 | 09/01/2026
TO-26-FIN-220SB1-2CB-04 | COUPLER/SECTIONALISING CB - FINGLAS 220-FINGLAS 220-220SB1-2CB | 5 | 5 | 5 | Scheduled | 05/01/2026 | 09/01/2026
TO-26-GLN-110K1-01 | COUPLER/SECTIONALISING CB - GALLANSTOWN 110-GALLANSTOWN 110-110K1 | 1 | 1 | 1 | Scheduled | 06/01/2026 | 06/01/2026
TO-26-AUN-110K1-01 | COUPLER/SECTIONALISING CB - AUNGIERSTOWN 110-AUNGIERSTOWN 110-110K1 | 3 | 3 | 3 | Scheduled | 07/01/2026 | 09/01/2026
TO-26-AUN-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - AUNGIERSTOWN 110-AUNGIERSTOWN 110-110SA1-2CB | 3 | 3 | 3 | Scheduled | 07/01/2026 | 09/01/2026
TO-26-AUN-110SB1-2CB-01 | COUPLER/SECTIONALISING CB - AUNGIERSTOWN 110-AUNGIERSTOWN 110-110SB1-2CB | 3 | 3 | 3 | Scheduled | 07/01/2026 | 09/01/2026
TO-26-110 kV B2 @ CBT-01 | BUSBAR SECTION - CASTLEBAGOT 110-CASTLEBAGOT 110-110B2 | 5 | 5 | 5 | Scheduled | 12/01/2026 | 16/01/2026
TO-26-110 kV B4 @ CBT-02 | BUSBAR SECTION - CASTLEBAGOT 110-CASTLEBAGOT 110-110B4 | 5 | 5 | 5 | Scheduled | 12/01/2026 | 16/01/2026
TO-26-CBT-110K4-02 | COUPLER/SECTIONALISING CB - CASTLEBAGOT 110-CASTLEBAGOT 110-110K4 | 5 | 5 | 5 | Scheduled | 12/01/2026 | 16/01/2026
TO-26-CBT-110SB2-4CB-02 | COUPLER/SECTIONALISING CB - CASTLEBAGOT 110-CASTLEBAGOT 110-110SB2-4CB | 5 | 5 | 5 | Scheduled | 12/01/2026 | 16/01/2026
TO-26-BLU-CDU-1-02 | 110kV FEEDER - BLUNDELSTOWN 110-CORDUFF 110-1 | 5 | 5 |  | Scheduled | 19/01/2026 | 23/01/2026
TO-26-110 kV A2 @ CBT-01 | BUSBAR SECTION - CASTLEBAGOT 110-CASTLEBAGOT 110-110A2 | 5 | 5 | 5 | Scheduled | 19/01/2026 | 23/01/2026
TO-26-110 kV A4 @ CBT-02 | BUSBAR SECTION - CASTLEBAGOT 110-CASTLEBAGOT 110-110A4 | 5 | 5 | 5 | Scheduled | 19/01/2026 | 23/01/2026
TO-26-CBT-110K4-03 | COUPLER/SECTIONALISING CB - CASTLEBAGOT 110-CASTLEBAGOT 110-110K4 | 5 | 5 | 5 | Scheduled | 19/01/2026 | 23/01/2026
TO-26-CBT-110SA2-4CB-02 | COUPLER/SECTIONALISING CB - CASTLEBAGOT 110-CASTLEBAGOT 110-110SA2-4CB | 5 | 5 | 5 | Scheduled | 19/01/2026 | 23/01/2026
TO-26-220 kV A1 @ FIN-02 | BUSBAR SECTION - FINGLAS 220-FINGLAS 220-220A1 | 4 | 4 | 4 | Scheduled | 19/01/2026 | 22/01/2026
TO-26-220 kV B1 @ FIN-02 | BUSBAR SECTION - FINGLAS 220-FINGLAS 220-220B1 | 4 | 4 | 4 | Scheduled | 19/01/2026 | 22/01/2026
TO-26-FIN-220K1-02 | COUPLER/SECTIONALISING CB - FINGLAS 220-FINGLAS 220-220K1 | 4 | 4 | 4 | Scheduled | 19/01/2026 | 22/01/2026
TO-26-FIN-220SA1-2CB-07 | COUPLER/SECTIONALISING CB - FINGLAS 220-FINGLAS 220-220SA1-2CB | 4 | 4 | 4 | Scheduled | 19/01/2026 | 22/01/2026
TO-26-FIN-220SB1-2CB-06 | COUPLER/SECTIONALISING CB - FINGLAS 220-FINGLAS 220-220SB1-2CB | 4 | 4 | 4 | Scheduled | 19/01/2026 | 22/01/2026
TO-26-CRU-220K1-01 | COUPLER/SECTIONALISING CB - CRUISERATH 220-CRUISERATH 220-220K1 | 1 | 1 | 1 | Scheduled | 20/01/2026 | 20/01/2026
TO-26-CRU-220K2-01 | COUPLER/SECTIONALISING CB - CRUISERATH 220-CRUISERATH 220-220K2 | 1 | 1 | 1 | Scheduled | 21/01/2026 | 21/01/2026
TO-26-CRU-SA1-2CB-01 | COUPLER/SECTIONALISING CB - CRUISERATH 220-CRUISERATH 220-220SA1-2CB | 1 | 1 | 1 | Scheduled | 22/01/2026 | 22/01/2026
TO-26-CDU-FIN-2-03 | 220kV FEEDER - CORDUFF 220-FINGLAS 220-2 | 22 | 15 | 15 | Scheduled | 23/01/2026 | 13/02/2026
TO-26-CRU-SB1-2CB-01 | COUPLER/SECTIONALISING CB - CRUISERATH 220-CRUISERATH 220-220SB1-2CB | 1 | 1 | 1 | Scheduled | 23/01/2026 | 23/01/2026
TO-26-110 kV B1 @ CBT-01 | BUSBAR SECTION - CASTLEBAGOT 110-CASTLEBAGOT 110-110B1 | 5 | 5 | 5 | Scheduled | 26/01/2026 | 30/01/2026
TO-26-110 kV B2 @ CBT-02 | BUSBAR SECTION - CASTLEBAGOT 110-CASTLEBAGOT 110-110B2 | 5 | 5 | 5 | Scheduled | 26/01/2026 | 30/01/2026
TO-26-CBT-110K1-02 | COUPLER/SECTIONALISING CB - CASTLEBAGOT 110-CASTLEBAGOT 110-110K1 | 5 | 5 | 5 | Scheduled | 26/01/2026 | 30/01/2026
TO-26-CBT-110SB1-2CB-01 | COUPLER/SECTIONALISING CB - CASTLEBAGOT 110-CASTLEBAGOT 110-110SB1-2CB | 5 | 5 |  | Scheduled | 26/01/2026 | 30/01/2026
TO-26-PA-110SA1-02 | SECTIONALISING DISCONNECT - POLLAPHUCA 110-POLLAPHUCA 110-110SA1 | 5 | 5 | 5 | Scheduled | 26/01/2026 | 30/01/2026
TO-26-PA-110SA2-02 | SECTIONALISING DISCONNECT - POLLAPHUCA 110-POLLAPHUCA 110-110SA2 | 5 | 5 | 5 | Scheduled | 26/01/2026 | 30/01/2026
TO-26-PA-T101-02 | GENERATOR TRANSFORMER - POLLAPHUCA 110-POLLAPHUCA G1-T101 | 5 | 5 | 5 | Scheduled | 26/01/2026 | 30/01/2026
TO-26-PB-R2002-01 | CAPACITOR/SVC/REACTOR - POOLBEG 220-POOLBEG 220-R2002 | 5 | 5 |  | Scheduled | 26/01/2026 | 30/01/2026
TO-26-STR,T-PA-1-02 | 110kV FEEDER - STRATFORD tee-POLLAPHUCA 110-1 | 5 | 5 | 5 | Scheduled | 26/01/2026 | 30/01/2026
TO-26-CDU-110K1-3-01 | COUPLER/SECTIONALISING CB - CORDUFF 110-CORDUFF 110-110K1-3 | 2 | 2 |  | Scheduled | 28/01/2026 | 29/01/2026
TO-26-BAL-CDU-1-03 | 110kV FEEDER - BALTRASNA 110-CORDUFF 110-1 | 8 | 6 | 6 | Scheduled | 03/02/2026 | 10/02/2026
TO-26-BLU-MUL-1-03 | 110kV FEEDER - BLUNDELSTOWN 110-MULLINGAR 110-1 | 3 | 3 |  | Scheduled | 03/02/2026 | 05/02/2026
TO-26-110 kV A2 @ CDU-01 | BUSBAR SECTION - CORDUFF 110-CORDUFF 110-110A2 | 8 | 6 | 6 | Scheduled | 03/02/2026 | 10/02/2026
TO-26-110 kV A4 @ CDU-02 | BUSBAR SECTION - CORDUFF 110-CORDUFF 110-110A4 | 8 | 6 | 6 | Scheduled | 03/02/2026 | 10/02/2026
TO-26-110 kV B2 @ CDU-01 | BUSBAR SECTION - CORDUFF 110-CORDUFF 110-110B2 | 8 | 6 | 6 | Scheduled | 03/02/2026 | 10/02/2026
TO-26-110 kV B4 @ CDU-01 | BUSBAR SECTION - CORDUFF 110-CORDUFF 110-110B4 | 8 | 6 | 6 | Scheduled | 03/02/2026 | 10/02/2026
TO-26-CDU-110SA2-4CB-01 | COUPLER/SECTIONALISING CB - CORDUFF 110-CORDUFF 110-110SA2-4CB | 8 | 6 | 6 | Scheduled | 03/02/2026 | 10/02/2026
TO-26-CDU-110SB2-4CB-01 | COUPLER/SECTIONALISING CB - CORDUFF 110-CORDUFF 110-110SB2-4CB | 8 | 6 | 6 | Scheduled | 03/02/2026 | 10/02/2026
TO-26-DSN-MP GIS-1-03 | 400kV FEEDER - DUNSTOWN 400-MONEYPOINT GIS 400-1 | 59 | 42 |  | Scheduled | 03/02/2026 | 02/04/2026
TO-26-220 kV A2 @ INC-01 | BUSBAR SECTION - INCHICORE 220-INCHICORE 220-220A2 | 32 | 24 | 24 | Scheduled | 03/02/2026 | 06/03/2026
TO-26-220 kV B2 @ INC-01 | BUSBAR SECTION - INCHICORE 220-INCHICORE 220-220B2 | 32 | 24 | 24 | Scheduled | 03/02/2026 | 06/03/2026
TO-26-INC-PB-2-02 | 220kV FEEDER - INCHICORE 220-POOLBEG 220-2 | 32 | 24 | 24 | Scheduled | 03/02/2026 | 06/03/2026
TO-26-220 kV A3 @ PB-01 | BUSBAR SECTION - POOLBEG 220-POOLBEG 220-220A3 | 32 | 24 | 24 | Scheduled | 03/02/2026 | 06/03/2026
TO-26-220 kV B3 @ PB-01 | BUSBAR SECTION - POOLBEG 220-POOLBEG 220-220B3 | 32 | 24 | 24 | Scheduled | 03/02/2026 | 06/03/2026
TO-26-110 kV A2 @ CLG-01 | BUSBAR SECTION - CLOGHRAN 110-CLOGHRAN 110-110A2 | 12 | 10 | 10 | Scheduled | 16/02/2026 | 27/02/2026
TO-26-110 kV B2 @ CLG-01 | BUSBAR SECTION - CLOGHRAN 110-CLOGHRAN 110-110B2 | 12 | 10 | 10 | Scheduled | 16/02/2026 | 27/02/2026
TO-26-CLG-110K2-05 | COUPLER/SECTIONALISING CB - CLOGHRAN 110-CLOGHRAN 110-110K2 | 12 | 10 | 10 | Scheduled | 16/02/2026 | 27/02/2026
TO-26-CLG-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - CLOGHRAN 110-CLOGHRAN 110-110SA1-2CB | 12 | 10 | 10 | Scheduled | 16/02/2026 | 27/02/2026
TO-26-CLG-110SB1-2CB-01 | COUPLER/SECTIONALISING CB - CLOGHRAN 110-CLOGHRAN 110-110SB1-2CB | 12 | 10 | 10 | Scheduled | 16/02/2026 | 27/02/2026
TO-26-CLG-CDU-1-01 | 110kV FEEDER - CLOGHRAN 110-CORDUFF 110-1 | 12 | 10 | 10 | Scheduled | 16/02/2026 | 27/02/2026
TO-26-CDU-FIN-1-01 | 220kV FEEDER - CORDUFF 220-FINGLAS 220-1 | 19 | 15 | 15 | Scheduled | 16/02/2026 | 06/03/2026
TO-26-DSN-T4201-01 | TRANSFORMER - DUNSTOWN 400-DUNSTOWN 220-T4201 | 5 | 5 | 5 | Scheduled | 16/02/2026 | 20/02/2026
TO-26-GLN-PLA-1-01 | 110kV FEEDER - GALLANSTOWN 110-PLATIN 110-1 | 19 | 15 |  | Scheduled | 16/02/2026 | 06/03/2026
TO-26-ARK-CKM GIS-1-01 | 220kV FEEDER - ARKLOW 220-CARRICKMINES GIS 220-1 | 16 | 12 | 12 | Scheduled | 23/02/2026 | 10/03/2026
TO-26-BEG-CKM GIS-1-01 | 110kV FEEDER - BALLYBEG 110-CARRICKMINES GIS 110-1 | 16 | 12 | 12 | Scheduled | 23/02/2026 | 10/03/2026
TO-26-220 kV A3 @ CKM GIS-01 | BUSBAR SECTION - CARRICKMINES GIS 220-CARRICKMINES GIS 220-220A3 | 16 | 12 | 12 | Scheduled | 23/02/2026 | 10/03/2026
TO-26-220 kV B3 @ CKM GIS-01 | BUSBAR SECTION - CARRICKMINES GIS 220-CARRICKMINES GIS 220-220B3 | 16 | 12 | 12 | Scheduled | 23/02/2026 | 10/03/2026
TO-26-CKM GIS-220K3-02 | COUPLER/SECTIONALISING CB - CARRICKMINES GIS 220-CARRICKMINES GIS 220-220K3 | 16 | 12 | 12 | Scheduled | 23/02/2026 | 10/03/2026
TO-26-CKM GIS-220SA1-3CB-05 | COUPLER/SECTIONALISING CB - CARRICKMINES GIS 220-CARRICKMINES GIS 220-220SA1-3CB | 16 | 12 | 12 | Scheduled | 23/02/2026 | 10/03/2026
TO-26-CKM GIS-220SB1-3CB-03 | COUPLER/SECTIONALISING CB - CARRICKMINES GIS 220-CARRICKMINES GIS 220-220SB1-3CB | 16 | 12 | 12 | Scheduled | 23/02/2026 | 10/03/2026
TO-26-BAG 110 - CLG 110 - 1-02 | 110kV FEEDER - BARNAGEERAGH 110-CLOGHRAN 110-1 | 12 | 10 | 10 | Scheduled | 02/03/2026 | 13/03/2026
TO-26-BAG-T101-01 | TSO CUSTOMER TRANSFORMER - BARNAGEERAGH 110-BARNAGEERAGH 11-T101 | 5 | 5 | 5 | Scheduled | 02/03/2026 | 06/03/2026
TO-26-110 kV A1 @ CLG-01 | BUSBAR SECTION - CLOGHRAN 110-CLOGHRAN 110-110A1 | 12 | 10 | 10 | Scheduled | 02/03/2026 | 13/03/2026
TO-26-110 kV B1 @ CLG-01 | BUSBAR SECTION - CLOGHRAN 110-CLOGHRAN 110-110B1 | 12 | 10 | 10 | Scheduled | 02/03/2026 | 13/03/2026
TO-26-CLG-110K1-04 | COUPLER/SECTIONALISING CB - CLOGHRAN 110-CLOGHRAN 110-110K1 | 12 | 10 | 10 | Scheduled | 02/03/2026 | 13/03/2026
TO-26-CLG-110SA1-2CB-02 | COUPLER/SECTIONALISING CB - CLOGHRAN 110-CLOGHRAN 110-110SA1-2CB | 12 | 10 | 10 | Scheduled | 02/03/2026 | 13/03/2026
TO-26-CLG-110SB1-2CB-02 | COUPLER/SECTIONALISING CB - CLOGHRAN 110-CLOGHRAN 110-110SB1-2CB | 12 | 10 | 10 | Scheduled | 02/03/2026 | 13/03/2026
TO-26-220 kV A1 @ MAY-01 | BUSBAR SECTION - MAYNOOTH 220-MAYNOOTH 220-220A1 | 12 | 10 | 10 | Scheduled | 02/03/2026 | 13/03/2026
TO-26-220 kV B1 @ MAY-01 | BUSBAR SECTION - MAYNOOTH 220-MAYNOOTH 220-220B1 | 12 | 10 | 10 | Scheduled | 02/03/2026 | 13/03/2026
TO-26-MAY-TH-1-01 | 220kV FEEDER - MAYNOOTH 220-TURLOUGH HILL 220-1 | 12 | 10 | 10 | Scheduled | 02/03/2026 | 13/03/2026
TO-26-220 kV A2 @ TH-01 | BUSBAR SECTION - TURLOUGH HILL 220-TURLOUGH HILL 220-220A2 | 12 | 10 | 10 | Scheduled | 02/03/2026 | 13/03/2026
TO-26-220 kV B2 @ TH-01 | BUSBAR SECTION - TURLOUGH HILL 220-TURLOUGH HILL 220-220B2 | 12 | 10 | 10 | Scheduled | 02/03/2026 | 13/03/2026
TO-26-CKG-T121-02 | TSO CUSTOMER TRANSFORMER - CORKAGH 110-CORKAGH 20-T121 | 7 | 5 | 5 | Scheduled | 08/03/2026 | 14/03/2026
TO-26-TH-T2001/2-02 | GENERATOR TRANSFORMER - TURLOUGH HILL 220-TURLOUGH HILL G1-T2001/2 | 4 | 3 | 3 | Scheduled | 08/03/2026 | 11/03/2026
TO-26-TH-T2003/4-03 | GENERATOR TRANSFORMER - TURLOUGH HILL 220-TURLOUGH HILL G1-T2003/4 | 1 | 0 | 0 | Scheduled | 08/03/2026 | 08/03/2026
TO-26-BAG-T103-01 | TSO CUSTOMER TRANSFORMER - BARNAGEERAGH 110-BARNAGEERAGH 11-T103 | 5 | 5 | 5 | Scheduled | 09/03/2026 | 13/03/2026
TO-26-CBT-INC-2-05 | 220kV FEEDER - CASTLEBAGOT 220-INCHICORE 220-2 | 51 | 34 | 34 | Scheduled | 09/03/2026 | 28/04/2026
TO-26-CLE-WOO-1-02 | 220kV FEEDER - CLONEE 220-WOODLAND 220-1 | 81 | 55 | 55 | Scheduled | 09/03/2026 | 28/05/2026
TO-26-220 kV A6 @ INC-03 | BUSBAR SECTION - INCHICORE 220-INCHICORE 220-220A6 | 51 | 34 | 34 | Scheduled | 09/03/2026 | 28/04/2026
TO-26-220 kV B6 @ INC-03 | BUSBAR SECTION - INCHICORE 220-INCHICORE 220-220B6 | 51 | 34 | 34 | Scheduled | 09/03/2026 | 28/04/2026
TO-26-BLC-DND-1-02 | 110kV FEEDER - BELCAMP 110-DARNDALE 110-1 | 3 | 3 |  | Scheduled | 10/03/2026 | 12/03/2026
TO-26-DSN-T4202-07 | TRANSFORMER - DUNSTOWN 400-DUNSTOWN 220-T4202 | 1 | 1 | 1 | Scheduled | 10/03/2026 | 10/03/2026
TO-26-400 kV B2 @ DSN-05 | BUSBAR SECTION - DUNSTOWN 400-DUNSTOWN 400-400B2 | 1 | 1 | 1 | Scheduled | 11/03/2026 | 11/03/2026
TO-26-TH-T2003/4-02 | GENERATOR TRANSFORMER - TURLOUGH HILL 220-TURLOUGH HILL G1-T2003/4 | 2 | 2 | 2 | Scheduled | 12/03/2026 | 13/03/2026
TO-26-220 kV A2 @ CLE-01 | BUSBAR SECTION - CLONEE 220-CLONEE 220-220A2 | 15 | 10 | 10 | Scheduled | 16/03/2026 | 30/03/2026
TO-26-220 kV B2 @ CLE-01 | BUSBAR SECTION - CLONEE 220-CLONEE 220-220B2 | 15 | 10 | 10 | Scheduled | 16/03/2026 | 30/03/2026
TO-26-CLE-220K2-02 | COUPLER/SECTIONALISING CB - CLONEE 220-CLONEE 220-220K2 | 15 | 10 | 10 | Scheduled | 16/03/2026 | 30/03/2026
TO-26-CLE-220SA1-2CB-02 | COUPLER/SECTIONALISING CB - CLONEE 220-CLONEE 220-220SA1-2CB | 15 | 10 | 10 | Scheduled | 16/03/2026 | 30/03/2026
TO-26-CLE-220SB1-2CB-02 | COUPLER/SECTIONALISING CB - CLONEE 220-CLONEE 220-220SB1-2CB | 15 | 10 | 10 | Scheduled | 16/03/2026 | 30/03/2026
TO-26-220 kV A1 @ CDU-04 | BUSBAR SECTION - CORDUFF 220-CORDUFF 220-220A1 | 4 | 3 | 3 | Scheduled | 16/03/2026 | 19/03/2026
TO-26-220 kV A3 @ CDU-02 | BUSBAR SECTION - CORDUFF 220-CORDUFF 220-220A3 | 4 | 3 | 3 | Scheduled | 16/03/2026 | 19/03/2026
TO-26-CDU-220K1-3-01 | COUPLER/SECTIONALISING CB - CORDUFF 220-CORDUFF 220-220K1-3 | 4 | 3 | 3 | Scheduled | 16/03/2026 | 19/03/2026
TO-26-CKM GIS-220K3-03 | COUPLER/SECTIONALISING CB - CARRICKMINES GIS 220-CARRICKMINES GIS 220-220K3 | 2 | 2 | 2 | Scheduled | 18/03/2026 | 19/03/2026
TO-26-RYB GIS-T105-01 | TSO CUSTOMER TRANSFORMER - RYEBROOK GIS 110-RYEBROOK 10-T105 | 2 | 2 | 2 | Scheduled | 18/03/2026 | 19/03/2026
TO-26-220 kV A1 @ CDU-01 | BUSBAR SECTION - CORDUFF 220-CORDUFF 220-220A1 | 12 | 9 | 9 | Scheduled | 23/03/2026 | 03/04/2026
TO-26-220 kV A2 @ CDU-02 | BUSBAR SECTION - CORDUFF 220-CORDUFF 220-220A2 | 12 | 9 | 9 | Scheduled | 23/03/2026 | 03/04/2026
TO-26-220 kV B1 @ CDU-01 | BUSBAR SECTION - CORDUFF 220-CORDUFF 220-220B1 | 12 | 9 | 9 | Scheduled | 23/03/2026 | 03/04/2026
TO-26-220 kV B2 @ CDU-02 | BUSBAR SECTION - CORDUFF 220-CORDUFF 220-220B2 | 12 | 9 | 9 | Scheduled | 23/03/2026 | 03/04/2026
TO-26-CDU-220K1-2-01 | COUPLER/SECTIONALISING CB - CORDUFF 220-CORDUFF 220-220K1-2 | 12 | 9 | 9 | Scheduled | 23/03/2026 | 03/04/2026
TO-26-CDU-220SA2-4CB-02 | COUPLER/SECTIONALISING CB - CORDUFF 220-CORDUFF 220-220SA2-4CB | 12 | 9 | 9 | Scheduled | 23/03/2026 | 03/04/2026
TO-26-CDU-220SB2-4CB-02 | COUPLER/SECTIONALISING CB - CORDUFF 220-CORDUFF 220-220SB2-4CB | 12 | 9 | 9 | Scheduled | 23/03/2026 | 03/04/2026
TO-26-DSN-TH-1-02 | 220kV FEEDER - DUNSTOWN 220-TURLOUGH HILL 220-1 | 5 | 5 | 5 | Scheduled | 23/03/2026 | 27/03/2026
TO-26-GLN-T133-01 | GENERATOR TRANSFORMER - GALLANSTOWN 110-GALLANSTOWN 33-T133 | 2 | 2 | 2 | Scheduled | 23/03/2026 | 24/03/2026
TO-26-GRI-T141-02 | DISTRIBUTION TRANSFORMER - GRIFFINRATH 110-GRIFFINRATH 38-T141 | 12 | 9 | 9 | Reference | 23/03/2026 | 03/04/2026
TO-26-GRI,T-GRI-1-02 | 110kV FEEDER - GRIFFINRATH tee-GRIFFINRATH 110-1 | 12 | 9 | 9 | Scheduled | 23/03/2026 | 03/04/2026
TO-26-GRI,T-MAY-1-03 | 110kV FEEDER - GRIFFINRATH tee-MAYNOOTH 110-1 | 12 | 9 | 9 | Scheduled | 23/03/2026 | 03/04/2026
TO-26-BLC-DND-3-01 | 110kV FEEDER - BELCAMP 110-DARNDALE 110-3 | 3 | 3 | 3 | Scheduled | 24/03/2026 | 26/03/2026
TO-26-CLU-T124-01 | TSO CUSTOMER TRANSFORMER - CLUTTERLAND 110-CLUTTERLAND 20-T124 | 2 | 2 | 2 | Scheduled | 24/03/2026 | 25/03/2026
TO-26-RYB GIS-T104-01 | TSO CUSTOMER TRANSFORMER - RYEBROOK GIS 110-RYEBROOK 10-T104 | 3 | 3 | 3 | Scheduled | 24/03/2026 | 26/03/2026
TO-26-CKG-T123-02 | TSO CUSTOMER TRANSFORMER - CORKAGH 110-CORKAGH 20-T123 | 8 | 5 | 5 | Scheduled | 27/03/2026 | 03/04/2026
TO-26-FIN GIS-T2101-01 | TRANSFORMER - FINGLAS 220-FINGLAS GIS 110-T2101 | 2 | 2 | 2 | Scheduled | 31/03/2026 | 01/04/2026
TO-26-RYB GIS-T107-01 | TSO CUSTOMER TRANSFORMER - RYEBROOK GIS 110-RYEBROOK 10-T107 | 2 | 2 | 2 | Scheduled | 01/04/2026 | 02/04/2026
TO-26-220 kV A2 @ FIN-07 | BUSBAR SECTION - FINGLAS 220-FINGLAS 220-220A2 | 18 | 14 | 14 | Scheduled | 07/04/2026 | 24/04/2026
TO-26-220 kV B2 @ FIN-05 | BUSBAR SECTION - FINGLAS 220-FINGLAS 220-220B2 | 18 | 14 | 14 | Scheduled | 07/04/2026 | 24/04/2026
TO-26-FIN-220K2-10 | COUPLER/SECTIONALISING CB - FINGLAS 220-FINGLAS 220-220K2 | 18 | 14 | 14 | Scheduled | 07/04/2026 | 24/04/2026
TO-26-FIN-220SA1-2CB-13 | COUPLER/SECTIONALISING CB - FINGLAS 220-FINGLAS 220-220SA1-2CB | 18 | 14 | 14 | Scheduled | 07/04/2026 | 24/04/2026
TO-26-FIN-220SB1-2CB-10 | COUPLER/SECTIONALISING CB - FINGLAS 220-FINGLAS 220-220SB1-2CB | 18 | 14 | 14 | Scheduled | 07/04/2026 | 24/04/2026
TO-26-110 kV A3 @ FIN GIS-01 | BUSBAR SECTION - FINGLAS GIS 110-FINGLAS GIS 110-110A3 | 18 | 14 | 14 | Scheduled | 07/04/2026 | 24/04/2026
TO-26-110 kV B3 @ FIN GIS-01 | BUSBAR SECTION - FINGLAS GIS 110-FINGLAS GIS 110-110B3 | 18 | 14 | 14 | Scheduled | 07/04/2026 | 24/04/2026
TO-26-FIN GIS-110SA1-3CB-02 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110SA1-3CB | 18 | 14 | 14 | Scheduled | 07/04/2026 | 24/04/2026
TO-26-FIN GIS-110SA3-5CB-03 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110SA3-5CB | 18 | 14 | 14 | Scheduled | 07/04/2026 | 24/04/2026
TO-26-FIN GIS-110SB1-3CB-01 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110SB1-3CB | 18 | 14 | 14 | Scheduled | 07/04/2026 | 24/04/2026
TO-26-FIN GIS-110SB3-5CB-03 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110SB3-5CB | 18 | 14 | 14 | Scheduled | 07/04/2026 | 24/04/2026
TO-26-FIN GIS-T2106-01 | TRANSFORMER - FINGLAS 220-FINGLAS GIS 110-T2106 | 18 | 14 | 14 | Scheduled | 07/04/2026 | 24/04/2026
TO-26-RYB GIS-T108-01 | TSO CUSTOMER TRANSFORMER - RYEBROOK GIS 110-RYEBROOK 10-T108 | 11 | 9 | 9 | Scheduled | 07/04/2026 | 17/04/2026
TO-26-DND-T121-03 | TSO CUSTOMER TRANSFORMER - DARNDALE 110-DARNDALE 20-T121 | 2 | 2 | 2 | Scheduled | 08/04/2026 | 09/04/2026
TO-26-CLE-T224-01 | TSO CUSTOMER TRANSFORMER - CLONEE 220-CLONEE 20-T224 | 47 | 34 |  | Scheduled | 13/04/2026 | 29/05/2026
TO-26-CLE-T224-02 | TSO CUSTOMER TRANSFORMER - CLONEE 220-CLONEE 20-T224 | 5 | 5 | 5 | Scheduled | 13/04/2026 | 17/04/2026
TO-26-110 kV A1 @ DND-02 | BUSBAR SECTION - DARNDALE 110-DARNDALE 110-110A1 | 5 | 5 | 5 | Proposed | 13/04/2026 | 17/04/2026
TO-26-110 kV B1 @ DND-01 | BUSBAR SECTION - DARNDALE 110-DARNDALE 110-110B1 | 5 | 5 | 5 | Proposed | 13/04/2026 | 17/04/2026
TO-26-DND-110K1-06 | COUPLER/SECTIONALISING CB - DARNDALE 110-DARNDALE 110-110K1 | 5 | 5 | 5 | Proposed | 13/04/2026 | 17/04/2026
TO-26-DND-110SA1-2CB-07 | COUPLER/SECTIONALISING CB - DARNDALE 110-DARNDALE 110-110SA1-2CB | 5 | 5 | 5 | Proposed | 13/04/2026 | 17/04/2026
TO-26-DND-110SB1-2CB-06 | COUPLER/SECTIONALISING CB - DARNDALE 110-DARNDALE 110-110SB1-2CB | 5 | 5 | 5 | Proposed | 13/04/2026 | 17/04/2026
TO-26-DND-T123-01 | TSO CUSTOMER TRANSFORMER - DARNDALE 110-DARNDALE 20-T123 | 5 | 5 | 5 | Proposed | 13/04/2026 | 17/04/2026
TO-26-CBT-T2101-01 | TRANSFORMER - CASTLEBAGOT 220-CASTLEBAGOT 110-T2101 | 2 | 2 | 2 | Scheduled | 14/04/2026 | 15/04/2026
TO-26-PRN-T4301-03 | TRANSFORMER - PORTAN 400-PORTAN 260-T4301 | 14 | 10 | 10 | Scheduled | 14/04/2026 | 27/04/2026
TO-26-PRN-WOO-1-03 | 400kV FEEDER - PORTAN 400-WOODLAND 400-1 | 14 | 10 | 10 | Scheduled | 14/04/2026 | 27/04/2026
TO-26-400 kV A1 @ WOO-03 | BUSBAR SECTION - WOODLAND 400-WOODLAND 400-400A1 | 5 | 4 | 4 | Proposed | 14/04/2026 | 18/04/2026
TO-26-400 kV A1 @ WOO-04 | BUSBAR SECTION - WOODLAND 400-WOODLAND 400-400A1 | 18 | 14 | 14 | Scheduled | 14/04/2026 | 01/05/2026
TO-26-400 kV B1 @ WOO-03 | BUSBAR SECTION - WOODLAND 400-WOODLAND 400-400B1 | 5 | 4 | 4 | Proposed | 14/04/2026 | 18/04/2026
TO-26-400 kV B1 @ WOO-04 | BUSBAR SECTION - WOODLAND 400-WOODLAND 400-400B1 | 18 | 14 | 14 | Scheduled | 14/04/2026 | 01/05/2026
TO-26-WOO-T4201-02 | TRANSFORMER - WOODLAND 400-WOODLAND 220-T4201 | 18 | 14 | 14 | Scheduled | 14/04/2026 | 01/05/2026
TO-26-CBT-CLU-1-02 | 110kV FEEDER - CASTLEBAGOT 110-CLUTTERLAND 110-1 | 2 | 2 | 2 | Scheduled | 20/04/2026 | 21/04/2026
TO-26-CBT-T2102-02 | TRANSFORMER - CASTLEBAGOT 220-CASTLEBAGOT 110-T2102 | 2 | 2 | 2 | Scheduled | 21/04/2026 | 22/04/2026
TO-26-110 kV A1 @ CDU-02 | BUSBAR SECTION - CORDUFF 110-CORDUFF 110-110A1 | 37 | 26 | 26 | Scheduled | 21/04/2026 | 27/05/2026
TO-26-110 kV B1 @ CDU-02 | BUSBAR SECTION - CORDUFF 110-CORDUFF 110-110B1 | 37 | 26 | 26 | Scheduled | 21/04/2026 | 27/05/2026
TO-26-220 kV A1 @ CDU-05 | BUSBAR SECTION - CORDUFF 220-CORDUFF 220-220A1 | 37 | 26 | 26 | Scheduled | 21/04/2026 | 27/05/2026
TO-26-220 kV B1 @ CDU-02 | BUSBAR SECTION - CORDUFF 220-CORDUFF 220-220B1 | 37 | 26 | 26 | Scheduled | 21/04/2026 | 27/05/2026
TO-26-CDU-T2101-01 | TRANSFORMER - CORDUFF 220-CORDUFF 110-T2101 | 37 | 26 | 26 | Scheduled | 21/04/2026 | 27/05/2026
TO-26-KTL-CAP1-01 | CAPACITOR/SVC/REACTOR - KILTEEL 110-KILTEEL 110-CAP1 | 3 | 3 | 3 | Scheduled | 21/04/2026 | 23/04/2026
TO-26-RYB GIS-T106-01 | TSO CUSTOMER TRANSFORMER - RYEBROOK GIS 110-RYEBROOK 10-T106 | 3 | 3 | 3 | Scheduled | 21/04/2026 | 23/04/2026
TO-26-PRN-T4301-05 | TRANSFORMER - PORTAN 400-PORTAN 260-T4301 | 1 | 1 | 1 | Scheduled | 23/04/2026 | 23/04/2026
TO-26-SHL-T2016-02 | GENERATOR TRANSFORMER - SHELLYBANKS 220-SHELLYBANKS G6-T2016 | 7 | 5 | 5 | Scheduled | 23/04/2026 | 29/04/2026
TO-26-110 kV A2 @ DND-02 | BUSBAR SECTION - DARNDALE 110-DARNDALE 110-110A2 | 5 | 5 | 5 | Scheduled | 27/04/2026 | 01/05/2026
TO-26-110 kV B2 @ DND-02 | BUSBAR SECTION - DARNDALE 110-DARNDALE 110-110B2 | 5 | 5 | 5 | Scheduled | 27/04/2026 | 01/05/2026
TO-26-DND-110K2-04 | COUPLER/SECTIONALISING CB - DARNDALE 110-DARNDALE 110-110K2 | 5 | 5 | 5 | Scheduled | 27/04/2026 | 01/05/2026
TO-26-DND-110SA1-2CB-08 | COUPLER/SECTIONALISING CB - DARNDALE 110-DARNDALE 110-110SA1-2CB | 5 | 5 | 5 | Scheduled | 27/04/2026 | 01/05/2026
TO-26-DND-110SB1-2CB-07 | COUPLER/SECTIONALISING CB - DARNDALE 110-DARNDALE 110-110SB1-2CB | 5 | 5 | 5 | Scheduled | 27/04/2026 | 01/05/2026
TO-26-DND-T122-01 | TSO CUSTOMER TRANSFORMER - DARNDALE 110-DARNDALE 20-T122 | 5 | 5 | 5 | Scheduled | 27/04/2026 | 01/05/2026
TO-26-CDU-RYB GIS-1-02 | 110kV FEEDER - CORDUFF 110-RYEBROOK GIS 110-1 | 1 | 1 | 1 | Scheduled | 28/04/2026 | 28/04/2026
TO-26-220 kV A4 @ INC-03 | BUSBAR SECTION - INCHICORE 220-INCHICORE 220-220A4 | 58 | 40 | 40 | Scheduled | 29/04/2026 | 25/06/2026
TO-26-220 kV A6 @ INC-04 | BUSBAR SECTION - INCHICORE 220-INCHICORE 220-220A6 | 15 | 10 | 10 | Scheduled | 29/04/2026 | 13/05/2026
TO-26-220 kV B4 @ INC-03 | BUSBAR SECTION - INCHICORE 220-INCHICORE 220-220B4 | 58 | 40 | 40 | Scheduled | 29/04/2026 | 25/06/2026
TO-26-220 kV B6 @ INC-04 | BUSBAR SECTION - INCHICORE 220-INCHICORE 220-220B6 | 15 | 10 | 10 | Scheduled | 29/04/2026 | 13/05/2026
TO-26-INC-220K4-6-03 | COUPLER/SECTIONALISING CB - INCHICORE 220-INCHICORE 220-220K4-6 | 58 | 40 | 40 | Scheduled | 29/04/2026 | 25/06/2026
TO-26-INC-T2106-02 | TRANSFORMER - INCHICORE 220-INCHICORE 110-T2106 | 58 | 40 |  | Reference | 29/04/2026 | 25/06/2026
TO-26-SHL-D1/CB1-04 | COUPLER/SECTIONALISING CB - SHELLYBANKS 220-SHELLYBANKS 220-D1/CB1 | 8 | 5 | 5 | Scheduled | 30/04/2026 | 07/05/2026
TO-26-SHL-D1/CB2-04 | COUPLER/SECTIONALISING CB - SHELLYBANKS 220-SHELLYBANKS 220-D1/CB2 | 1 | 1 | 1 | Scheduled | 30/04/2026 | 30/04/2026
TO-26-SHL-D1/CB3-02 | COUPLER/SECTIONALISING CB - SHELLYBANKS 220-SHELLYBANKS 220-D1/CB3 | 1 | 1 | 1 | Scheduled | 30/04/2026 | 30/04/2026
TO-26-SHL-D2/CB1-03 | COUPLER/SECTIONALISING CB - SHELLYBANKS 220-SHELLYBANKS 220-D2/CB1 | 8 | 5 | 5 | Scheduled | 30/04/2026 | 07/05/2026
TO-26-SHL-T2014-03 | GENERATOR TRANSFORMER - SHELLYBANKS 220-SHELLYBANKS G4-T2014 | 9 | 6 | 6 | Scheduled | 30/04/2026 | 08/05/2026
TO-26-SHL-T2016-01 | GENERATOR TRANSFORMER - SHELLYBANKS 220-SHELLYBANKS G6-T2016 | 8 | 5 | 5 | Scheduled | 30/04/2026 | 07/05/2026
TO-26-BLK,T-MAY-1-03 | 110kV FEEDER - BLAKE tee-MAYNOOTH 110-1 | 3 | 1 | 1 | Scheduled | 01/05/2026 | 03/05/2026
TO-26-BLK,T-MAY-1-03 | 110kV FEEDER - BLAKE tee-MAYNOOTH 110-1 | Unknown | Unknown | 1 | Planned | May | May
TO-26-RYB GIS-T109-01 | TSO CUSTOMER TRANSFORMER - RYEBROOK GIS 110-RYEBROOK 10-T109 | 11 | 9 | 9 | Scheduled | 05/05/2026 | 15/05/2026
TO-26-110 kV A1 @ SNU-01 | BUSBAR SECTION - SNUGBOROUGH 110-SNUGBOROUGH 110-110A1 | 13 | 9 | 9 | Scheduled | 06/05/2026 | 18/05/2026
TO-26-110 kV A2 @ SNU-01 | BUSBAR SECTION - SNUGBOROUGH 110-SNUGBOROUGH 110-110A2 | 13 | 9 | 9 | Scheduled | 06/05/2026 | 18/05/2026
TO-26-110 kV B1 @ SNU-01 | BUSBAR SECTION - SNUGBOROUGH 110-SNUGBOROUGH 110-110B1 | 13 | 9 | 9 | Scheduled | 06/05/2026 | 18/05/2026
TO-26-110 kV B2 @ SNU-01 | BUSBAR SECTION - SNUGBOROUGH 110-SNUGBOROUGH 110-110B2 | 13 | 9 | 9 | Scheduled | 06/05/2026 | 18/05/2026
TO-26-SNU-110K1-01 | COUPLER/SECTIONALISING CB - SNUGBOROUGH 110-SNUGBOROUGH 110-110K1 | 13 | 9 | 9 | Scheduled | 06/05/2026 | 18/05/2026
TO-26-SNU-110K2-01 | COUPLER/SECTIONALISING CB - SNUGBOROUGH 110-SNUGBOROUGH 110-110K2 | 13 | 9 | 9 | Scheduled | 06/05/2026 | 18/05/2026
TO-26-SNU-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - SNUGBOROUGH 110-SNUGBOROUGH 110-110SA1-2CB | 13 | 9 | 9 | Scheduled | 06/05/2026 | 18/05/2026
TO-26-SNU-110SB1-2CB-01 | COUPLER/SECTIONALISING CB - SNUGBOROUGH 110-SNUGBOROUGH 110-110SB1-2CB | 13 | 9 | 9 | Scheduled | 06/05/2026 | 18/05/2026
TO-26-400 kV A1 @ WOO-05 | BUSBAR SECTION - WOODLAND 400-WOODLAND 400-400A1 | 15 | 11 | 11 | Scheduled | 06/05/2026 | 20/05/2026
TO-26-400 kV A2 @ WOO-02 | BUSBAR SECTION - WOODLAND 400-WOODLAND 400-400A2 | 15 | 11 | 11 | Scheduled | 06/05/2026 | 20/05/2026
TO-26-400 kV B1 @ WOO-05 | BUSBAR SECTION - WOODLAND 400-WOODLAND 400-400B1 | 15 | 11 | 11 | Scheduled | 06/05/2026 | 20/05/2026
TO-26-WOO-400K1-2-02 | COUPLER/SECTIONALISING CB - WOODLAND 400-WOODLAND 400-400K1-2 | 15 | 11 | 11 | Scheduled | 06/05/2026 | 20/05/2026
TO-26-SHL-D1/CB2-05 | COUPLER/SECTIONALISING CB - SHELLYBANKS 220-SHELLYBANKS 220-D1/CB2 | 1 | 1 | 1 | Scheduled | 08/05/2026 | 08/05/2026
TO-26-SHL-D1/CB3-03 | COUPLER/SECTIONALISING CB - SHELLYBANKS 220-SHELLYBANKS 220-D1/CB3 | 1 | 1 | 1 | Scheduled | 08/05/2026 | 08/05/2026
TO-26-110 kV A1 @ BLC-03 | BUSBAR SECTION - BELCAMP 110-BELCAMP 110-110A1 | 19 | 15 | 15 | Scheduled | 11/05/2026 | 29/05/2026
TO-26-110 kV A3 @ BLC-03 | BUSBAR SECTION - BELCAMP 110-BELCAMP 110-110A3 | 19 | 15 | 15 | Scheduled | 11/05/2026 | 29/05/2026
TO-26-110 kV B1 @ BLC-03 | BUSBAR SECTION - BELCAMP 110-BELCAMP 110-110B1 | 19 | 15 | 15 | Scheduled | 11/05/2026 | 29/05/2026
TO-26-110 kV B3 @ BLC-03 | BUSBAR SECTION - BELCAMP 110-BELCAMP 110-110B3 | 19 | 15 | 15 | Scheduled | 11/05/2026 | 29/05/2026
TO-26-BLC-110K1-03 | COUPLER/SECTIONALISING CB - BELCAMP 110-BELCAMP 110-110K1 | 19 | 15 | 15 | Scheduled | 11/05/2026 | 29/05/2026
TO-26-BLC-110K3-03 | COUPLER/SECTIONALISING CB - BELCAMP 110-BELCAMP 110-110K3 | 19 | 15 | 15 | Scheduled | 11/05/2026 | 29/05/2026
TO-26-BLC-110SA1-3CB-06 | COUPLER/SECTIONALISING CB - BELCAMP 110-BELCAMP 110-110SA1-3CB | 19 | 15 | 15 | Scheduled | 11/05/2026 | 29/05/2026
TO-26-BLC-110SB1-3CB-04 | COUPLER/SECTIONALISING CB - BELCAMP 110-BELCAMP 110-110SB1-3CB | 19 | 15 | 15 | Scheduled | 11/05/2026 | 29/05/2026
TO-26-KUD-T103-02 | TSO CUSTOMER TRANSFORMER - KILMAHUD 110-KILMAHUD 10-T103 | 5 | 5 | 5 | Scheduled | 11/05/2026 | 15/05/2026
TO-26-SHL-D2/CB2-02 | COUPLER/SECTIONALISING CB - SHELLYBANKS 220-SHELLYBANKS 220-D2/CB2 | 1 | 1 | 1 | Scheduled | 11/05/2026 | 11/05/2026
TO-26-SHL-D2/CB3-02 | COUPLER/SECTIONALISING CB - SHELLYBANKS 220-SHELLYBANKS 220-D2/CB3 | 1 | 1 | 1 | Scheduled | 11/05/2026 | 11/05/2026
TO-26-SHL-T2015-02 | GENERATOR TRANSFORMER - SHELLYBANKS 220-SHELLYBANKS G5-T2015 | 19 | 15 | 15 | Scheduled | 11/05/2026 | 29/05/2026
TO-26-AUN-CBT-1-02 | 110kV FEEDER - AUNGIERSTOWN 110-CASTLEBAGOT 110-1 | 2 | 2 | 2 | Scheduled | 12/05/2026 | 13/05/2026
TO-26-CDU-CRU-1-01 | 220kV FEEDER - CORDUFF 220-CRUISERATH 220-1 | 4 | 4 | 4 | Scheduled | 12/05/2026 | 15/05/2026
TO-26-220 kV A2 @ ISH-01 | BUSBAR SECTION - IRISHTOWN 220-IRISHTOWN 220-220A2 | 5 | 5 | 5 | Scheduled | 18/05/2026 | 22/05/2026
TO-26-220 kV B2 @ ISH-01 | BUSBAR SECTION - IRISHTOWN 220-IRISHTOWN 220-220B2 | 5 | 5 | 5 | Scheduled | 18/05/2026 | 22/05/2026
TO-26-ISH-T2002/3-03 | GENERATOR TRANSFORMER - IRISHTOWN 220-IRISHTOWN G2/3-T2002/3 | 5 | 5 | 5 | Scheduled | 18/05/2026 | 22/05/2026
TO-26-AUN-KSG-1-03 | 110kV FEEDER - AUNGIERSTOWN 110-KISHOGE 110-1 | 3 | 3 | 3 | Scheduled | 19/05/2026 | 21/05/2026
TO-26-AUN-T121-02 | TSO CUSTOMER TRANSFORMER - AUNGIERSTOWN 110-AUNGIERSTOWN 20-T121 | 2 | 2 | 2 | Scheduled | 21/05/2026 | 22/05/2026
TO-26-CBT-CKG-2-03 | 110kV FEEDER - CASTLEBAGOT 110-CORKAGH 110-2 | 4 | 4 | 4 | Scheduled | 26/05/2026 | 29/05/2026
TO-26-110 kV A2 @ CDU-03 | BUSBAR SECTION - CORDUFF 110-CORDUFF 110-110A2 | 13 | 8 | 8 | Scheduled | 28/05/2026 | 09/06/2026
TO-26-110 kV A4 @ CDU-04 | BUSBAR SECTION - CORDUFF 110-CORDUFF 110-110A4 | 13 | 8 | 8 | Scheduled | 28/05/2026 | 09/06/2026
TO-26-110 kV B2 @ CDU-03 | BUSBAR SECTION - CORDUFF 110-CORDUFF 110-110B2 | 13 | 8 | 8 | Scheduled | 28/05/2026 | 09/06/2026
TO-26-110 kV B4 @ CDU-03 | BUSBAR SECTION - CORDUFF 110-CORDUFF 110-110B4 | 13 | 8 | 8 | Scheduled | 28/05/2026 | 09/06/2026
TO-26-CDU-110SA2-4CB-03 | COUPLER/SECTIONALISING CB - CORDUFF 110-CORDUFF 110-110SA2-4CB | 13 | 8 | 8 | Scheduled | 28/05/2026 | 09/06/2026
TO-26-CDU-110SB2-4CB-03 | COUPLER/SECTIONALISING CB - CORDUFF 110-CORDUFF 110-110SB2-4CB | 13 | 8 | 8 | Scheduled | 28/05/2026 | 09/06/2026
TO-26-220 kV A2 @ CDU-03 | BUSBAR SECTION - CORDUFF 220-CORDUFF 220-220A2 | 13 | 8 | 8 | Scheduled | 28/05/2026 | 09/06/2026
TO-26-220 kV A4 @ CDU-02 | BUSBAR SECTION - CORDUFF 220-CORDUFF 220-220A4 | 13 | 8 | 8 | Scheduled | 28/05/2026 | 09/06/2026
TO-26-220 kV B2 @ CDU-03 | BUSBAR SECTION - CORDUFF 220-CORDUFF 220-220B2 | 13 | 8 | 8 | Scheduled | 28/05/2026 | 09/06/2026
TO-26-220 kV B4 @ CDU-03 | BUSBAR SECTION - CORDUFF 220-CORDUFF 220-220B4 | 13 | 8 | 8 | Scheduled | 28/05/2026 | 09/06/2026
TO-26-CDU-220SA2-4CB-03 | COUPLER/SECTIONALISING CB - CORDUFF 220-CORDUFF 220-220SA2-4CB | 13 | 8 | 8 | Scheduled | 28/05/2026 | 09/06/2026
TO-26-CDU-220SB2-4CB-03 | COUPLER/SECTIONALISING CB - CORDUFF 220-CORDUFF 220-220SB2-4CB | 13 | 8 | 8 | Scheduled | 28/05/2026 | 09/06/2026
TO-26-CDU-T2102-02 | TRANSFORMER - CORDUFF 220-CORDUFF 110-T2102 | 29 | 20 | 20 | Scheduled | 28/05/2026 | 25/06/2026
TO-26-SHL-D2/CB2-03 | COUPLER/SECTIONALISING CB - SHELLYBANKS 220-SHELLYBANKS 220-D2/CB2 | 1 | 1 | 1 | Scheduled | 29/05/2026 | 29/05/2026
TO-26-SHL-D2/CB3-03 | COUPLER/SECTIONALISING CB - SHELLYBANKS 220-SHELLYBANKS 220-D2/CB3 | 1 | 1 | 1 | Scheduled | 29/05/2026 | 29/05/2026
TO-26-CBT-CKG-1-03 | 110kV FEEDER - CASTLEBAGOT 110-CORKAGH 110-1 | 4 | 4 | 4 | Scheduled | 02/06/2026 | 05/06/2026
TO-26-110 kV A3 @ CKG-02 | BUSBAR SECTION - CORKAGH 110-CORKAGH 110-110A3 | 4 | 4 | 4 | Scheduled | 02/06/2026 | 05/06/2026
TO-26-110 kV B3 @ CKG-03 | BUSBAR SECTION - CORKAGH 110-CORKAGH 110-110B3 | 4 | 4 | 4 | Scheduled | 02/06/2026 | 05/06/2026
TO-26-CKG-110K3-02 | COUPLER/SECTIONALISING CB - CORKAGH 110-CORKAGH 110-110K3 | 4 | 4 | 4 | Scheduled | 02/06/2026 | 05/06/2026
TO-26-CKG-110SA1-3CB-04 | COUPLER/SECTIONALISING CB - CORKAGH 110-CORKAGH 110-110SA1-3CB | 4 | 4 | 4 | Scheduled | 02/06/2026 | 05/06/2026
TO-26-CKG-110SB1-3CB-04 | COUPLER/SECTIONALISING CB - CORKAGH 110-CORKAGH 110-110SB1-3CB | 4 | 4 | 4 | Scheduled | 02/06/2026 | 05/06/2026
TO-26-FIN-HN-1-01 | 220kV FEEDER - FINGLAS 220-HUNTSTOWN 220-1 | 23 | 17 | 17 | Scheduled | 02/06/2026 | 24/06/2026
TO-26-FIN-SHL-1-02 | 220kV FEEDER - FINGLAS 220-SHELLYBANKS 220-1 | 71 | 50 |  | Scheduled | 02/06/2026 | 11/08/2026
TO-26-GRI-T141-03 | DISTRIBUTION TRANSFORMER - GRIFFINRATH 110-GRIFFINRATH 38-T141 | 4 | 4 | 4 | Reference | 02/06/2026 | 05/06/2026
TO-26-GRI,T-GRI-1-03 | 110kV FEEDER - GRIFFINRATH tee-GRIFFINRATH 110-1 | 4 | 4 | 4 | Scheduled | 02/06/2026 | 05/06/2026
TO-26-GRI,T-MAY-1-04 | 110kV FEEDER - GRIFFINRATH tee-MAYNOOTH 110-1 | 4 | 4 | 4 | Scheduled | 02/06/2026 | 05/06/2026
TO-26-HN-T2010/11-01 | GENERATOR TRANSFORMER - HUNTSTOWN 220-HUNTSTOWN G10/11-T2010/11 | 23 | 17 | 17 | Scheduled | 02/06/2026 | 24/06/2026
TO-26-SHL-D1/CB1-02 | COUPLER/SECTIONALISING CB - SHELLYBANKS 220-SHELLYBANKS 220-D1/CB1 | 4 | 4 | 4 | Scheduled | 02/06/2026 | 05/06/2026
TO-26-SHL-D1/CB2-03 | COUPLER/SECTIONALISING CB - SHELLYBANKS 220-SHELLYBANKS 220-D1/CB2 | 4 | 4 | 4 | Scheduled | 02/06/2026 | 05/06/2026
TO-26-CKM GIS-220K4-01 | COUPLER/SECTIONALISING CB - CARRICKMINES GIS 220-CARRICKMINES GIS 220-220K4 | 2 | 2 | 2 | Scheduled | 03/06/2026 | 04/06/2026
TO-26-KYT-T237-02 | TSO CUSTOMER TRANSFORMER - KELLYSTOWN 220-KELLYSTOWN 34.5-T237 | 1 | 1 | 1 | Scheduled | 03/06/2026 | 03/06/2026
TO-26-KYT-T233-03 | TSO CUSTOMER TRANSFORMER - KELLYSTOWN 220-KELLYSTOWN 34.5-T233 | 26 | 18 | 18 | Scheduled | 05/06/2026 | 30/06/2026
TO-26-CDU-CRU-2-02 | 220kV FEEDER - CORDUFF 220-CRUISERATH 220-2 | 5 | 5 | 5 | Proposed | 08/06/2026 | 12/06/2026
TO-26-KTL-T131-02 | GENERATOR TRANSFORMER - KILTEEL 110-KILTEEL 33-T131 | 2 | 2 | 2 | Scheduled | 08/06/2026 | 09/06/2026
TO-26-PB-R2002-03 | CAPACITOR/SVC/REACTOR - POOLBEG 220-POOLBEG 220-R2002 | 5 | 5 | 5 | Scheduled | 08/06/2026 | 12/06/2026
TO-26-BAL-T122-03 | DISTRIBUTION TRANSFORMER - BALTRASNA 110-BALTRASNA 20-T122 | 2 | 2 | 2 | Reference (Proposed) | 09/06/2026 | 10/06/2026
TO-26-FIN-T2104-01 | TRANSFORMER - FINGLAS 220-FINGLAS 110-T2104 | 113 | 80 | 80 | Proposed | 09/06/2026 | 29/09/2026
TO-26-GRI-T142-01 | DISTRIBUTION TRANSFORMER - GRIFFINRATH 110-GRIFFINRATH 38-T142 | 2 | 2 | 2 | Reference (Proposed) | 09/06/2026 | 10/06/2026
TO-26-220 kV A1 @ FIN-06 | BUSBAR SECTION - FINGLAS 220-FINGLAS 220-220A1 | 13 | 9 | 9 | Scheduled | 12/06/2026 | 24/06/2026
TO-26-220 kV B1 @ FIN-06 | BUSBAR SECTION - FINGLAS 220-FINGLAS 220-220B1 | 13 | 9 | 9 | Scheduled | 12/06/2026 | 24/06/2026
TO-26-FIN-220K1-05 | COUPLER/SECTIONALISING CB - FINGLAS 220-FINGLAS 220-220K1 | 13 | 9 | 9 | Scheduled | 12/06/2026 | 24/06/2026
TO-26-FIN-220SA1-2CB-15 | COUPLER/SECTIONALISING CB - FINGLAS 220-FINGLAS 220-220SA1-2CB | 13 | 9 | 9 | Scheduled | 12/06/2026 | 24/06/2026
TO-26-FIN-220SB1-2CB-12 | COUPLER/SECTIONALISING CB - FINGLAS 220-FINGLAS 220-220SB1-2CB | 13 | 9 | 9 | Scheduled | 12/06/2026 | 24/06/2026
TO-26-220 kV A1 @ ISH-01 | BUSBAR SECTION - IRISHTOWN 220-IRISHTOWN 220-220A1 | 8 | 6 | 6 | Proposed | 12/06/2026 | 19/06/2026
TO-26-220 kV B1 @ ISH-01 | BUSBAR SECTION - IRISHTOWN 220-IRISHTOWN 220-220B1 | 8 | 6 | 6 | Proposed | 12/06/2026 | 19/06/2026
TO-26-ISH-T2001-02 | GENERATOR TRANSFORMER - IRISHTOWN 220-IRISHTOWN G1-T2001 | 8 | 6 | 6 | Proposed | 12/06/2026 | 19/06/2026
TO-26-220 kV A2 @ FIN-08 | BUSBAR SECTION - FINGLAS 220-FINGLAS 220-220A2 | 12 | 10 | 10 | Scheduled | 15/06/2026 | 26/06/2026
TO-26-220 kV B2 @ FIN-06 | BUSBAR SECTION - FINGLAS 220-FINGLAS 220-220B2 | 12 | 10 | 10 | Scheduled | 15/06/2026 | 26/06/2026
TO-26-FIN-220K2-11 | COUPLER/SECTIONALISING CB - FINGLAS 220-FINGLAS 220-220K2 | 12 | 10 | 10 | Proposed | 15/06/2026 | 26/06/2026
TO-26-FIN-220SA1-2CB-16 | COUPLER/SECTIONALISING CB - FINGLAS 220-FINGLAS 220-220SA1-2CB | 12 | 10 | 10 | Proposed | 15/06/2026 | 26/06/2026
TO-26-FIN-220SB1-2CB-13 | COUPLER/SECTIONALISING CB - FINGLAS 220-FINGLAS 220-220SB1-2CB | 12 | 10 | 10 | Proposed | 15/06/2026 | 26/06/2026
TO-26-FIN GIS-SVN-1-03 | 110kV FEEDER - FINGLAS GIS 110-STEPHENSTOWN 110-1 | 40 | 30 | 30 | Reference | 15/06/2026 | 24/07/2026
TO-26-110 kV A1 @ GLN-01 | BUSBAR SECTION - GALLANSTOWN 110-GALLANSTOWN 110-110A1 | 5 | 5 | 5 | Scheduled | 15/06/2026 | 19/06/2026
TO-26-110 kV B1 @ GLN-01 | BUSBAR SECTION - GALLANSTOWN 110-GALLANSTOWN 110-110B1 | 5 | 5 | 5 | Scheduled | 15/06/2026 | 19/06/2026
TO-26-GLN-110K1-02 | COUPLER/SECTIONALISING CB - GALLANSTOWN 110-GALLANSTOWN 110-110K1 | 5 | 5 | 5 | Scheduled | 15/06/2026 | 19/06/2026
TO-26-GLN-PLA-1-05 | 110kV FEEDER - GALLANSTOWN 110-PLATIN 110-1 | 5 | 5 | 5 | Scheduled | 15/06/2026 | 19/06/2026
TO-26-CKM GIS-220SA1-2CB-01 | COUPLER/SECTIONALISING CB - CARRICKMINES GIS 220-CARRICKMINES GIS 220-220SA1-2CB | 3 | 3 | 3 | Scheduled | 16/06/2026 | 18/06/2026
TO-26-CKM GIS-220SA1-3CB-01 | COUPLER/SECTIONALISING CB - CARRICKMINES GIS 220-CARRICKMINES GIS 220-220SA1-3CB | 3 | 3 | 3 | Scheduled | 16/06/2026 | 18/06/2026
TO-26-CKM GIS-220SA2-4CB-01 | COUPLER/SECTIONALISING CB - CARRICKMINES GIS 220-CARRICKMINES GIS 220-220SA2-4CB | 3 | 3 | 3 | Scheduled | 16/06/2026 | 18/06/2026
TO-26-CRU-T223-01 | TSO CUSTOMER TRANSFORMER - CRUISERATH 220-CRUISERATH 20-T223 | 2 | 2 | 2 | Scheduled | 16/06/2026 | 17/06/2026
TO-26-BNK-CBT-1-03 | 110kV FEEDER - BARNAKYLE 110-CASTLEBAGOT 110-1 | 7 | 5 | 5 | Proposed | 17/06/2026 | 23/06/2026
TO-26-110 kV A1 @ CBT-02 | BUSBAR SECTION - CASTLEBAGOT 110-CASTLEBAGOT 110-110A1 | 7 | 5 | 5 | Proposed | 17/06/2026 | 23/06/2026
TO-26-110 kV B1 @ CBT-02 | BUSBAR SECTION - CASTLEBAGOT 110-CASTLEBAGOT 110-110B1 | 7 | 5 | 5 | Proposed | 17/06/2026 | 23/06/2026
TO-26-CBT-110K1-04 | COUPLER/SECTIONALISING CB - CASTLEBAGOT 110-CASTLEBAGOT 110-110K1 | 7 | 5 | 5 | Proposed | 17/06/2026 | 23/06/2026
TO-26-CBT-110SA1-2CB-02 | COUPLER/SECTIONALISING CB - CASTLEBAGOT 110-CASTLEBAGOT 110-110SA1-2CB | 7 | 5 | 5 | Proposed | 17/06/2026 | 23/06/2026
TO-26-CBT-110SB1-2CB-02 | COUPLER/SECTIONALISING CB - CASTLEBAGOT 110-CASTLEBAGOT 110-110SB1-2CB | 7 | 5 | 5 | Proposed | 17/06/2026 | 23/06/2026
TO-26-110 kV A3 @ CDU-01 | BUSBAR SECTION - CORDUFF 110-CORDUFF 110-110A3 | 9 | 7 | 7 | Proposed | 22/06/2026 | 30/06/2026
TO-26-110 kV B3 @ CDU-01 | BUSBAR SECTION - CORDUFF 110-CORDUFF 110-110B3 | 9 | 7 | 7 | Proposed | 22/06/2026 | 30/06/2026
TO-26-CDU-SNU-1-01 | 110kV FEEDER - CORDUFF 110-SNUGBOROUGH 110-1 | 9 | 7 | 7 | Proposed | 22/06/2026 | 30/06/2026
TO-26-110 kV B2 @ MAY-01 | BUSBAR SECTION - MAYNOOTH 110-MAYNOOTH 110-110B2 | 12 | 10 | 10 | Proposed | 22/06/2026 | 03/07/2026
TO-26-220 kV A1 @ MAY-02 | BUSBAR SECTION - MAYNOOTH 220-MAYNOOTH 220-220A1 | 12 | 10 | 10 | Proposed | 22/06/2026 | 03/07/2026
TO-26-220 kV B1 @ MAY-02 | BUSBAR SECTION - MAYNOOTH 220-MAYNOOTH 220-220B1 | 12 | 10 | 10 | Proposed | 22/06/2026 | 03/07/2026
TO-26-MAY-T2102-01 | TRANSFORMER - MAYNOOTH 220-MAYNOOTH 110-T2102 | 12 | 10 | 10 | Proposed | 22/06/2026 | 03/07/2026
TO-26-110 kV A2 @ SNU-02 | BUSBAR SECTION - SNUGBOROUGH 110-SNUGBOROUGH 110-110A2 | 9 | 7 | 7 | Proposed | 22/06/2026 | 30/06/2026
TO-26-110 kV B2 @ SNU-02 | BUSBAR SECTION - SNUGBOROUGH 110-SNUGBOROUGH 110-110B2 | 9 | 7 | 7 | Proposed | 22/06/2026 | 30/06/2026
TO-26-SNU-110K2-06 | COUPLER/SECTIONALISING CB - SNUGBOROUGH 110-SNUGBOROUGH 110-110K2 | 9 | 7 | 7 | Proposed | 22/06/2026 | 30/06/2026
TO-26-SNU-110SA1-2CB-05 | COUPLER/SECTIONALISING CB - SNUGBOROUGH 110-SNUGBOROUGH 110-110SA1-2CB | 9 | 7 | 7 | Proposed | 22/06/2026 | 30/06/2026
TO-26-SNU-110SB1-2CB-02 | COUPLER/SECTIONALISING CB - SNUGBOROUGH 110-SNUGBOROUGH 110-110SB1-2CB | 9 | 7 | 7 | Proposed | 22/06/2026 | 30/06/2026
TO-26-CKM GIS-220SB1-2CB-01 | COUPLER/SECTIONALISING CB - CARRICKMINES GIS 220-CARRICKMINES GIS 220-220SB1-2CB | 3 | 3 | 3 | Scheduled | 23/06/2026 | 25/06/2026
TO-26-CKM GIS-220SB1-3CB-01 | COUPLER/SECTIONALISING CB - CARRICKMINES GIS 220-CARRICKMINES GIS 220-220SB1-3CB | 3 | 3 | 3 | Scheduled | 23/06/2026 | 25/06/2026
TO-26-CKM GIS-220SB2-4CB-01 | COUPLER/SECTIONALISING CB - CARRICKMINES GIS 220-CARRICKMINES GIS 220-220SB2-4CB | 3 | 3 | 3 | Scheduled | 23/06/2026 | 25/06/2026
TO-26-CDU-T2104-02 | TRANSFORMER - CORDUFF 220-CORDUFF 110-T2104 | 2 | 2 | 2 | Scheduled | 23/06/2026 | 24/06/2026
TO-26-FIN GIS-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110SA1-2CB | 10 | 8 | 8 | Proposed | 23/06/2026 | 02/07/2026
TO-26-BAL-110SA1-04 | SECTIONALISING DISCONNECT - BALTRASNA 110-BALTRASNA 110-110SA1 | 4 | 4 | 4 | Proposed | 29/06/2026 | 02/07/2026
TO-26-BAL-110SA2-05 | SECTIONALISING DISCONNECT - BALTRASNA 110-BALTRASNA 110-110SA2 | 4 | 4 | 4 | Proposed | 29/06/2026 | 02/07/2026
TO-26-BAL-DEN-1-01 | 110kV FEEDER - BALTRASNA 110-DEENES 110-1 | 4 | 4 | 4 | Proposed | 29/06/2026 | 02/07/2026
TO-26-BAL-T121-02 | DISTRIBUTION TRANSFORMER - BALTRASNA 110-BALTRASNA 20-T121 | 4 | 4 | 4 | Reference (Proposed) | 29/06/2026 | 02/07/2026
TO-26-CBT-220K2-01 | COUPLER/SECTIONALISING CB - CASTLEBAGOT 220-CASTLEBAGOT 220-220K2 | 4 | 4 | 4 | Proposed | 29/06/2026 | 02/07/2026
TO-26-DSN-MAY-1-01 | 220kV FEEDER - DUNSTOWN 220-MAYNOOTH 220-1 | 12 | 10 | 10 | Proposed | 29/06/2026 | 10/07/2026
TO-26-220 kV A1 @ INC-01 | BUSBAR SECTION - INCHICORE 220-INCHICORE 220-220A1 | 9 | 7 | 7 | Proposed | 29/06/2026 | 07/07/2026
TO-26-220 kV B1 @ INC-02 | BUSBAR SECTION - INCHICORE 220-INCHICORE 220-220B1 | 9 | 7 | 7 | Proposed | 29/06/2026 | 07/07/2026
TO-26-INC-PB-1-07 | 220kV FEEDER - INCHICORE 220-POOLBEG 220-1 | 33 | 25 | 25 | Proposed | 29/06/2026 | 31/07/2026
TO-26-KYT-T233-01 | TSO CUSTOMER TRANSFORMER - KELLYSTOWN 220-KELLYSTOWN 34.5-T233 | 2 | 2 | 2 | Proposed | 29/06/2026 | 30/06/2026
TO-26-220 kV A1 @ PB-02 | BUSBAR SECTION - POOLBEG 220-POOLBEG 220-220A1 | 9 | 7 | 7 | Proposed | 29/06/2026 | 07/07/2026
TO-26-220 kV B1 @ PB-03 | BUSBAR SECTION - POOLBEG 220-POOLBEG 220-220B1 | 9 | 7 | 7 | Proposed | 29/06/2026 | 07/07/2026
TO-26-110 kV A4 @ CBT-03 | BUSBAR SECTION - CASTLEBAGOT 110-CASTLEBAGOT 110-110A4 | 12 | 10 | 10 | Proposed | 06/07/2026 | 17/07/2026
TO-26-110 kV B4 @ CBT-03 | BUSBAR SECTION - CASTLEBAGOT 110-CASTLEBAGOT 110-110B4 | 12 | 10 | 10 | Proposed | 06/07/2026 | 17/07/2026
TO-26-CBT-110K4-04 | COUPLER/SECTIONALISING CB - CASTLEBAGOT 110-CASTLEBAGOT 110-110K4 | 12 | 10 | 10 | Proposed | 06/07/2026 | 17/07/2026
TO-26-CBT-110SA2-4CB-03 | COUPLER/SECTIONALISING CB - CASTLEBAGOT 110-CASTLEBAGOT 110-110SA2-4CB | 12 | 10 | 10 | Proposed | 06/07/2026 | 17/07/2026
TO-26-CBT-110SB2-4CB-04 | COUPLER/SECTIONALISING CB - CASTLEBAGOT 110-CASTLEBAGOT 110-110SB2-4CB | 12 | 10 | 10 | Proposed | 06/07/2026 | 17/07/2026
TO-26-220 kV A2 @ CBT-01 | BUSBAR SECTION - CASTLEBAGOT 220-CASTLEBAGOT 220-220A2 | 12 | 10 | 10 | Proposed | 06/07/2026 | 17/07/2026
TO-26-220 kV B2 @ CBT-01 | BUSBAR SECTION - CASTLEBAGOT 220-CASTLEBAGOT 220-220B2 | 12 | 10 | 10 | Proposed | 06/07/2026 | 17/07/2026
TO-26-CBT-220K2-02 | COUPLER/SECTIONALISING CB - CASTLEBAGOT 220-CASTLEBAGOT 220-220K2 | 12 | 10 | 10 | Proposed | 06/07/2026 | 17/07/2026
TO-26-CBT-220SA1-2CB-02 | COUPLER/SECTIONALISING CB - CASTLEBAGOT 220-CASTLEBAGOT 220-220SA1-2CB | 12 | 10 | 10 | Proposed | 06/07/2026 | 17/07/2026
TO-26-CBT-220SB1-2CB-02 | COUPLER/SECTIONALISING CB - CASTLEBAGOT 220-CASTLEBAGOT 220-220SB1-2CB | 12 | 10 | 10 | Proposed | 06/07/2026 | 17/07/2026
TO-26-CBT-T2104-01 | TRANSFORMER - CASTLEBAGOT 220-CASTLEBAGOT 110-T2104 | 12 | 10 | 10 | Proposed | 06/07/2026 | 17/07/2026
TO-26-FIN GIS-110SB2-4CB-03 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110SB2-4CB | 10 | 8 | 8 | Proposed | 06/07/2026 | 15/07/2026
TO-26-220 kV A2/A4 @ INC-01 | BUSBAR SECTION - INCHICORE 220-INCHICORE 220-220A2-A4 | 12 | 10 | 10 | Proposed | 06/07/2026 | 17/07/2026
TO-26-220 kV B2/B4 @ INC-01 | BUSBAR SECTION - INCHICORE 220-INCHICORE 220-220B2-B4 | 12 | 10 | 10 | Proposed | 06/07/2026 | 17/07/2026
TO-26-INC-220K2-4-01 | COUPLER/SECTIONALISING CB - INCHICORE 220-INCHICORE 220-220K2-4 | 12 | 10 | 10 | Proposed | 06/07/2026 | 17/07/2026
TO-26-NW-T2004/5-01 | GENERATOR TRANSFORMER - NORTH WALL 220-NORTH WALL G4/5-T2004/5 | 2 | 2 |  | Proposed | 06/07/2026 | 07/07/2026
TO-26-DGY-FIN GIS-1-01 | 110kV FEEDER - DUNSOGHLY 110-FINGLAS GIS 110-1 | 3 | 3 | 3 | Proposed | 07/07/2026 | 09/07/2026
TO-26-DGY-T101-01 | GENERATOR TRANSFORMER - DUNSOGHLY 110-DUNSOGHLY 11-T101 | 3 | 3 | 3 | Proposed | 07/07/2026 | 09/07/2026
TO-26-RYB GIS-T103-01 | TSO CUSTOMER TRANSFORMER - RYEBROOK GIS 110-RYEBROOK 10-T103 | 3 | 3 | 3 | Proposed | 07/07/2026 | 09/07/2026
TO-26-KYT-T237-03 | TSO CUSTOMER TRANSFORMER - KELLYSTOWN 220-KELLYSTOWN 34.5-T237 | 34 | 23 | 23 | Proposed | 08/07/2026 | 10/08/2026
TO-26-CLU-110K1-02 | COUPLER/SECTIONALISING CB - CLUTTERLAND 110-CLUTTERLAND 110-110K1 | 1 | 1 | 1 | Proposed | 14/07/2026 | 14/07/2026
TO-26-CLU-110K2-01 | COUPLER/SECTIONALISING CB - CLUTTERLAND 110-CLUTTERLAND 110-110K2 | 1 | 1 | 1 | Proposed | 14/07/2026 | 14/07/2026
TO-26-CLU-110SA1-2CB-02 | COUPLER/SECTIONALISING CB - CLUTTERLAND 110-CLUTTERLAND 110-110SA1-2CB | 1 | 1 | 1 | Proposed | 14/07/2026 | 14/07/2026
TO-26-110 kV A2 @ CLG-02 | BUSBAR SECTION - CLOGHRAN 110-CLOGHRAN 110-110A2 | 5 | 5 | 5 | Proposed | 20/07/2026 | 24/07/2026
TO-26-110 kV B2 @ CLG-02 | BUSBAR SECTION - CLOGHRAN 110-CLOGHRAN 110-110B2 | 5 | 5 | 5 | Proposed | 20/07/2026 | 24/07/2026
TO-26-CLG-110K2-01 | COUPLER/SECTIONALISING CB - CLOGHRAN 110-CLOGHRAN 110-110K2 | 5 | 5 | 5 | Proposed | 20/07/2026 | 24/07/2026
TO-26-CLG-110SA1-2CB-03 | COUPLER/SECTIONALISING CB - CLOGHRAN 110-CLOGHRAN 110-110SA1-2CB | 5 | 5 | 5 | Proposed | 20/07/2026 | 24/07/2026
TO-26-CLG-110SB1-2CB-03 | COUPLER/SECTIONALISING CB - CLOGHRAN 110-CLOGHRAN 110-110SB1-2CB | 5 | 5 | 5 | Proposed | 20/07/2026 | 24/07/2026
TO-26-COL-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - COLLEGE PARK 110-COLLEGE PARK 110-110SA1-2CB | 12 | 10 | 10 | Proposed | 20/07/2026 | 31/07/2026
TO-26-COL-FIN GIS-1-01 | 110kV FEEDER - COLLEGE PARK 110-FINGLAS GIS 110-1 | 12 | 10 | 10 | Proposed | 20/07/2026 | 31/07/2026
TO-26-COL-T102-01 | DISTRIBUTION TRANSFORMER - COLLEGE PARK 110-COLLEGE PARK 10-T102 | 12 | 10 | 10 | Reference (Proposed) | 20/07/2026 | 31/07/2026
TO-26-DSN-400K1-2-04 | COUPLER/SECTIONALISING CB - DUNSTOWN 400-DUNSTOWN 400-400K1-2 | 1 | 1 | 1 | Proposed | 20/07/2026 | 20/07/2026
TO-26-DSN-MP GIS-1-02 | 400kV FEEDER - DUNSTOWN 400-MONEYPOINT GIS 400-1 | 40 | 29 | 29 | Proposed | 20/07/2026 | 28/08/2026
TO-26-110 kV A5 @ FIN GIS-01 | BUSBAR SECTION - FINGLAS GIS 110-FINGLAS GIS 110-110A5 | 12 | 10 | 10 | Proposed | 20/07/2026 | 31/07/2026
TO-26-110 kV B5 @ FIN GIS-01 | BUSBAR SECTION - FINGLAS GIS 110-FINGLAS GIS 110-110B5 | 12 | 10 | 10 | Proposed | 20/07/2026 | 31/07/2026
TO-26-FIN GIS-110K5-02 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110K5 | 12 | 10 | 10 | Proposed | 20/07/2026 | 31/07/2026
TO-26-FIN GIS-110SA3-5CB-02 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110SA3-5CB | 12 | 10 | 10 | Proposed | 20/07/2026 | 31/07/2026
TO-26-FIN GIS-110SB3-5CB-02 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110SB3-5CB | 12 | 10 | 10 | Proposed | 20/07/2026 | 31/07/2026
TO-26-FIN GIS-MCE-1-01 | 110kV FEEDER - FINGLAS GIS 110-MACETOWN 110-1 | 12 | 10 | 10 | Proposed | 20/07/2026 | 31/07/2026
TO-26-KYT-MAY-1-01 | 220kV FEEDER - KELLYSTOWN 220-MAYNOOTH 220-1 | 5 | 5 | 5 | Proposed | 20/07/2026 | 24/07/2026
TO-26-220 kV A2 @ DSN-05 | BUSBAR SECTION - DUNSTOWN 220-DUNSTOWN 220-220A2 | 19 | 14 | 14 | Proposed | 27/07/2026 | 14/08/2026
TO-26-220 kV B2 @ DSN-04 | BUSBAR SECTION - DUNSTOWN 220-DUNSTOWN 220-220B2 | 19 | 14 | 14 | Proposed | 27/07/2026 | 14/08/2026
TO-26-400 kV A2 @ DSN-04 | BUSBAR SECTION - DUNSTOWN 400-DUNSTOWN 400-400A2 | 19 | 14 | 14 | Proposed | 27/07/2026 | 14/08/2026
TO-26-400 kV B2 @ DSN-06 | BUSBAR SECTION - DUNSTOWN 400-DUNSTOWN 400-400B2 | 19 | 14 | 14 | Proposed | 27/07/2026 | 14/08/2026
TO-26-DSN-T4202-02 | TRANSFORMER - DUNSTOWN 400-DUNSTOWN 220-T4202 | 19 | 14 | 14 | Proposed | 27/07/2026 | 14/08/2026
TO-26-WOO-T4201-03 | TRANSFORMER - WOODLAND 400-WOODLAND 220-T4201 | 5 | 5 | 5 | Proposed | 27/07/2026 | 31/07/2026
TO-26-CLG-T121-01 | TSO CUSTOMER TRANSFORMER - CLOGHRAN 110-CLOGHRAN 20-T121 | 3 | 3 | 3 | Proposed | 28/07/2026 | 30/07/2026
TO-26-CLU-KUD-1-02 | 110kV FEEDER - CLUTTERLAND 110-KILMAHUD 110-1 | 3 | 3 | 3 | Proposed | 28/07/2026 | 30/07/2026
TO-26-CBT-KUD-1-02 | 110kV FEEDER - CASTLEBAGOT 110-KILMAHUD 110-1 | Unknown | Unknown | 3 | Planned | August | August
TO-26-CLE-220K1-01 | COUPLER/SECTIONALISING CB - CLONEE 220-CLONEE 220-220K1 | Unknown | Unknown | 14 | Planned | August | August
TO-26-CLE-220SA1-2CB-01 | COUPLER/SECTIONALISING CB - CLONEE 220-CLONEE 220-220SA1-2CB | Unknown | Unknown | 14 | Planned | August | August
TO-26-CLE-220SB1-2CB-01 | COUPLER/SECTIONALISING CB - CLONEE 220-CLONEE 220-220SB1-2CB | Unknown | Unknown | 14 | Planned | August | August
TO-26-COL-110SA1-2CB-02 | COUPLER/SECTIONALISING CB - COLLEGE PARK 110-COLLEGE PARK 110-110SA1-2CB | 18 | 14 | 14 | Proposed | 04/08/2026 | 21/08/2026
TO-26-COL-110SA1-3CB-01 | COUPLER/SECTIONALISING CB - COLLEGE PARK 110-COLLEGE PARK 110-110SA1-3CB | 18 | 14 | 14 | Proposed | 04/08/2026 | 21/08/2026
TO-26-COL-CDU-1-01 | 110kV FEEDER - COLLEGE PARK 110-CORDUFF 110-1 | 18 | 14 | 14 | Proposed | 04/08/2026 | 21/08/2026
TO-26-COL-T101-01 | DISTRIBUTION TRANSFORMER - COLLEGE PARK 110-COLLEGE PARK 10-T101 | 18 | 14 | 14 | Reference (Proposed) | 04/08/2026 | 21/08/2026
TO-26-COL-T103-01 | DISTRIBUTION TRANSFORMER - COLLEGE PARK 110-COLLEGE PARK 10-T103 | 18 | 14 | 14 | Reference (Proposed) | 04/08/2026 | 21/08/2026
TO-26-110 kV A1 @ CDU-01 | BUSBAR SECTION - CORDUFF 110-CORDUFF 110-110A1 | 18 | 14 | 14 | Proposed | 04/08/2026 | 21/08/2026
TO-26-110 kV B1 @ CDU-01 | BUSBAR SECTION - CORDUFF 110-CORDUFF 110-110B1 | 18 | 14 | 14 | Proposed | 04/08/2026 | 21/08/2026
TO-26-CDU-HN-1-01 | 220kV FEEDER - CORDUFF 220-HUNTSTOWN 220-1 | Unknown | Unknown | 10 | Planned | August | August
TO-26-CKG-110K2-02 | COUPLER/SECTIONALISING CB - CORKAGH 110-CORKAGH 110-110K2 | Unknown | Unknown | 3 | Planned | August | August
TO-26-CKG-110SA1-2CB-05 | COUPLER/SECTIONALISING CB - CORKAGH 110-CORKAGH 110-110SA1-2CB | Unknown | Unknown | 3 | Planned | August | August
TO-26-CKG-110SB1-2CB-05 | COUPLER/SECTIONALISING CB - CORKAGH 110-CORKAGH 110-110SB1-2CB | Unknown | Unknown | 3 | Planned | August | August
TO-26-HN-T2002-01 | GENERATOR TRANSFORMER - HUNTSTOWN 220-HUNTSTOWN G2-T2002 | Unknown | Unknown |  | Planned | August | August
TO-26-INC-220K1-2-01 | COUPLER/SECTIONALISING CB - INCHICORE 220-INCHICORE 220-220K1-2 | 18 | 14 | 14 | Proposed | 04/08/2026 | 21/08/2026
TO-26-CLG-T123-01 | TSO CUSTOMER TRANSFORMER - CLOGHRAN 110-CLOGHRAN 20-T123 | Unknown | Unknown | 3 | Planned | August | August
TO-26-CLG-T122-01 | TSO CUSTOMER TRANSFORMER - CLOGHRAN 110-CLOGHRAN 20-T122 | Unknown | Unknown | 2 | Planned | August | August
TO-26-CKG-T121-01 | TSO CUSTOMER TRANSFORMER - CORKAGH 110-CORKAGH 20-T121 | Unknown | Unknown | 3 | Planned | August | August
TO-26-BLC-FIN-1-03 | 220kV FEEDER - BELCAMP 220-FINGLAS 220-1 | Unknown | Unknown |  | Planned | August | September
TO-26-BLC-T2103-02 | TRANSFORMER - BELCAMP 220-BELCAMP 110-T2103 | Unknown | Unknown | 80 | Planned | August | December
TO-26-CBT-KSG-1-02 | 110kV FEEDER - CASTLEBAGOT 110-KISHOGE 110-1 | Unknown | Unknown | 1 | Planned | August | August
TO-26-CDU-MCE-1-01 | 110kV FEEDER - CORDUFF 110-MACETOWN 110-1 | Unknown | Unknown | 10 | Planned | August | August
TO-26-MCE-110SA1-01 | SECTIONALISING DISCONNECT - MACETOWN 110-MACETOWN 110-110SA1 | Unknown | Unknown | 5 | Planned | August | August
TO-26-MCE-T101-01 | DISTRIBUTION TRANSFORMER - MACETOWN 110-MACETOWN 10-T101 | Unknown | Unknown | 5 | Reference (Planned) | August | August
TO-26-MCE-T121-02 | TSO CUSTOMER TRANSFORMER - MACETOWN 110-MACETOWN 20-T121 | Unknown | Unknown | 7 | Planned | August | August
TO-26-SHL-D2/CB1-01 | COUPLER/SECTIONALISING CB - SHELLYBANKS 220-SHELLYBANKS 220-D2/CB1 | Unknown | Unknown | 5 | Planned | August | August
TO-26-CKG-T122-01 | TSO CUSTOMER TRANSFORMER - CORKAGH 110-CORKAGH 20-T122 | Unknown | Unknown | 2 | Planned | August | August
TO-26-KYT-T237-01 | TSO CUSTOMER TRANSFORMER - KELLYSTOWN 220-KELLYSTOWN 34.5-T237 | Unknown | Unknown | 2 | Planned | August | August
TO-26-SHL-D2/CB3-01 | COUPLER/SECTIONALISING CB - SHELLYBANKS 220-SHELLYBANKS 220-D2/CB3 | Unknown | Unknown | 5 | Planned | August | August
TO-26-CKG-T123-01 | TSO CUSTOMER TRANSFORMER - CORKAGH 110-CORKAGH 20-T123 | Unknown | Unknown | 2 | Planned | August | August
TO-26-KTL-T142-01 | DISTRIBUTION TRANSFORMER - KILTEEL 110-KILTEEL 38-T142 | Unknown | Unknown | 2 | Reference (Planned) | August | August
TO-26-CLG-T124-01 | TSO CUSTOMER TRANSFORMER - CLOGHRAN 110-CLOGHRAN 20-T124 | Unknown | Unknown | 5 | Planned | August | September
TO-26-CLG-T124-02 | TSO CUSTOMER TRANSFORMER - CLOGHRAN 110-CLOGHRAN 20-T124 | Unknown | Unknown | 5 | Planned | August | September
TO-26-CDU-110K1-2-01 | COUPLER/SECTIONALISING CB - CORDUFF 110-CORDUFF 110-110K1-2 | Unknown | Unknown | 10 | Planned | August | September
TO-26-ISH-220K1-2-01 | COUPLER/SECTIONALISING CB - IRISHTOWN 220-IRISHTOWN 220-220K1-2 | Unknown | Unknown | 10 | Planned | August | September
TO-26-MCE-T124-01 | TSO CUSTOMER TRANSFORMER - MACETOWN 110-MACETOWN 20-T124 | Unknown | Unknown | 7 | Planned | August | September
TO-26-MAY-RYB GIS-1-02 | 110kV FEEDER - MAYNOOTH 110-RYEBROOK GIS 110-1 | Unknown | Unknown | 45 | Planned | August | November
TO-26-OST-WOO-1-02 | 400kV FEEDER - OLDSTREET 400-WOODLAND 400-1 | Unknown | Unknown | 15 | Planned | August | September
TO-26-RNW-T121-03 | TSO CUSTOMER TRANSFORMER - RINAWADE 110-RINAWADE 20-T121 | Unknown | Unknown | 1 | Planned | August | August
TO-26-WOO-220K1-2-02 | COUPLER/SECTIONALISING CB - WOODLAND 220-WOODLAND 220-220K1-2 | 45 | 33 | 33 | Proposed | 31/08/2026 | 14/10/2026
TO-26-WOO-T4202-03 | TRANSFORMER - WOODLAND 400-WOODLAND 220-T4202 | Unknown | Unknown | 15 | Planned | August | September
TO-26-BRT-T222-01 | TSO CUSTOMER TRANSFORMER - BRACETOWN 220-BRACETOWN 20-T222 | Unknown | Unknown | 23 | Planned | September | October
TO-26-WOO-T4202-04 | TRANSFORMER - WOODLAND 400-WOODLAND 220-T4202 | 2 | 2 | 2 | Proposed | 03/09/2026 | 04/09/2026
TO-26-BRT-T222-02 | TSO CUSTOMER TRANSFORMER - BRACETOWN 220-BRACETOWN 20-T222 | Unknown | Unknown | 6 | Planned | September | September
TO-26-CLG-T126-02 | TSO CUSTOMER TRANSFORMER - CLOGHRAN 110-CLOGHRAN 20-T126 | Unknown | Unknown | 10 | Planned | September | September
TO-26-CLG-T126-01 | TSO CUSTOMER TRANSFORMER - CLOGHRAN 110-CLOGHRAN 20-T126 | Unknown | Unknown | 5 | Planned | September | September
TO-26-DND-110K1-03 | COUPLER/SECTIONALISING CB - DARNDALE 110-DARNDALE 110-110K1 | Unknown | Unknown | 5 | Planned | September | September
TO-26-PB-T2007/8-02 | GENERATOR TRANSFORMER - POOLBEG 220-POOLBEG G7/8-T2007/8 | Unknown | Unknown | 2 | Planned | September | September
TO-26-DND-110SB1-2CB-01 | COUPLER/SECTIONALISING CB - DARNDALE 110-DARNDALE 110-110SB1-2CB | Unknown | Unknown | 2 | Planned | September | September
TO-26-110 kV B4 @ FIN GIS-02 | BUSBAR SECTION - FINGLAS GIS 110-FINGLAS GIS 110-110B4 | 3 | 3 | 3 | Proposed | 09/09/2026 | 11/09/2026
TO-26-FIN GIS-110SB2-4CB-01 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110SB2-4CB | 3 | 3 | 3 | Proposed | 09/09/2026 | 11/09/2026
TO-26-FIN GIS-110SB4-6CB-01 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110SB4-6CB | 3 | 3 | 3 | Proposed | 09/09/2026 | 11/09/2026
TO-26-BRT-CLE-2-01 | 220kV FEEDER - BRACETOWN 220-CLONEE 220-2 | Unknown | Unknown | 10 | Planned | September | September
TO-26-CBT-MAY-1-02 | 220kV FEEDER - CASTLEBAGOT 220-MAYNOOTH 220-1 | Unknown | Unknown | 10 | Planned | September | September
TO-26-220 kV A2 @ FIN-02 | BUSBAR SECTION - FINGLAS 220-FINGLAS 220-220A2 | 5 | 5 | 5 | Proposed | 14/09/2026 | 18/09/2026
TO-26-220 kV B2 @ FIN-01 | BUSBAR SECTION - FINGLAS 220-FINGLAS 220-220B2 | 5 | 5 | 5 | Proposed | 14/09/2026 | 18/09/2026
TO-26-FIN-220K2-02 | COUPLER/SECTIONALISING CB - FINGLAS 220-FINGLAS 220-220K2 | 5 | 5 | 5 | Proposed | 14/09/2026 | 18/09/2026
TO-26-FIN-220SA1-2CB-02 | COUPLER/SECTIONALISING CB - FINGLAS 220-FINGLAS 220-220SA1-2CB | 5 | 5 | 5 | Proposed | 14/09/2026 | 18/09/2026
TO-26-FIN-220SB1-2CB-01 | COUPLER/SECTIONALISING CB - FINGLAS 220-FINGLAS 220-220SB1-2CB | 5 | 5 | 5 | Proposed | 14/09/2026 | 18/09/2026
TO-26-110 kV A4 @ FIN GIS-01 | BUSBAR SECTION - FINGLAS GIS 110-FINGLAS GIS 110-110A4 | 5 | 5 | 5 | Proposed | 14/09/2026 | 18/09/2026
TO-26-110 kV B4 @ FIN GIS-01 | BUSBAR SECTION - FINGLAS GIS 110-FINGLAS GIS 110-110B4 | 5 | 5 | 5 | Proposed | 14/09/2026 | 18/09/2026
TO-26-FIN GIS-110SA2-4CB-01 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110SA2-4CB | 5 | 5 | 5 | Proposed | 14/09/2026 | 18/09/2026
TO-26-FIN GIS-110SA4-6CB-01 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110SA4-6CB | 5 | 5 | 5 | Proposed | 14/09/2026 | 18/09/2026
TO-26-FIN GIS-110SB2-4CB-02 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110SB2-4CB | 5 | 5 | 5 | Proposed | 14/09/2026 | 18/09/2026
TO-26-FIN GIS-110SB4-6CB-02 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110SB4-6CB | 5 | 5 | 5 | Proposed | 14/09/2026 | 18/09/2026
TO-26-KUD-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - KILMAHUD 110-KILMAHUD 110-110SA1-2CB | Unknown | Unknown | 2 | Planned | September | September
TO-26-MAY-110K1-2-01 | COUPLER/SECTIONALISING CB - MAYNOOTH 110-MAYNOOTH 110-110K1-2 | Unknown | Unknown | 10 | Planned | September | September
TO-26-CRU-T224-02 | TSO CUSTOMER TRANSFORMER - CRUISERATH 220-CRUISERATH 20-T224 | Unknown | Unknown | 2 | Planned | September | September
TO-26-KUD-T102-01 | TSO CUSTOMER TRANSFORMER - KILMAHUD 110-KILMAHUD 10-T102 | Unknown | Unknown | 3 | Planned | September | September
TO-26-DND-T124-01 | TSO CUSTOMER TRANSFORMER - DARNDALE 110-DARNDALE 20-T124 | Unknown | Unknown | 5 | Planned | September | September
TO-26-DND-T124-02 | TSO CUSTOMER TRANSFORMER - DARNDALE 110-DARNDALE 20-T124 | Unknown | Unknown | 5 | Planned | September | September
TO-26-FIN GIS-110SB3-5CB-01 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110SB3-5CB | Unknown | Unknown | 8 | Planned | September | September
TO-26-KUD-T101-01 | TSO CUSTOMER TRANSFORMER - KILMAHUD 110-KILMAHUD 10-T101 | Unknown | Unknown | 3 | Planned | September | September
TO-26-BRT-CLE-4-01 | 220kV FEEDER - BRACETOWN 220-CLONEE 220-4 | Unknown | Unknown | 5 | Planned | September | October
TO-26-CBT-MAY-2-01 | 220kV FEEDER - CASTLEBAGOT 220-MAYNOOTH 220-2 | Unknown | Unknown |  | Planned | September | October
TO-26-CDU-FIN-2-02 | 220kV FEEDER - CORDUFF 220-FINGLAS 220-2 | 2 | 2 | 2 | Proposed | 28/09/2026 | 29/09/2026
TO-26-220 kV A2 @ FIN-03 | BUSBAR SECTION - FINGLAS 220-FINGLAS 220-220A2 | 2 | 2 | 2 | Proposed | 28/09/2026 | 29/09/2026
TO-26-FIN-220K2-03 | COUPLER/SECTIONALISING CB - FINGLAS 220-FINGLAS 220-220K2 | 2 | 2 | 2 | Proposed | 28/09/2026 | 29/09/2026
TO-26-FIN-220SA1-2CB-03 | COUPLER/SECTIONALISING CB - FINGLAS 220-FINGLAS 220-220SA1-2CB | 2 | 2 | 2 | Proposed | 28/09/2026 | 29/09/2026
TO-26-FIN GIS-110K1-01 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110K1 | Unknown | Unknown | 7 | Planned | September | October
TO-26-MAY-110K3-4-01 | COUPLER/SECTIONALISING CB - MAYNOOTH 110-MAYNOOTH 110-110K3-4 | Unknown | Unknown | 10 | Planned | September | October
TO-26-PB-R2002-04 | CAPACITOR/SVC/REACTOR - POOLBEG 220-POOLBEG 220-R2002 | Unknown | Unknown |  | Planned | September | October
TO-26-MAY-T2101-02 | TRANSFORMER - MAYNOOTH 220-MAYNOOTH 110-T2101 | Unknown | Unknown | 9 | Planned | September | October
TO-26-WOO-T4202-05 | TRANSFORMER - WOODLAND 400-WOODLAND 220-T4202 | 2 | 2 | 2 | Proposed | 30/09/2026 | 01/10/2026
TO-26-FIN-220SA1-2CB-12 | COUPLER/SECTIONALISING CB - FINGLAS 220-FINGLAS 220-220SA1-2CB | Unknown | Unknown | 5 | Planned | October | October
TO-26-FIN GIS-110SB4-6CB-03 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110SB4-6CB | Unknown | Unknown | 8 | Planned | October | October
TO-26-PB-220K2-3-02 | COUPLER/SECTIONALISING CB - POOLBEG 220-POOLBEG 220-220K2-3 | Unknown | Unknown | 10 | Planned | October | October
TO-26-PB-220SA1-2-03 | SECTIONALISING DISCONNECT - POOLBEG 220-POOLBEG 220-220SA1-2 | Unknown | Unknown | 10 | Planned | October | October
TO-26-PB-220SB1-2-04 | SECTIONALISING DISCONNECT - POOLBEG 220-POOLBEG 220-220SB1-2 | Unknown | Unknown | 5 | Planned | October | October
TO-26-WOO-T4204-06 | TRANSFORMER - WOODLAND 400-WOODLAND 220-T4204 | Unknown | Unknown | 15 | Planned | October | October
TO-26-FIN GIS-110K2-01 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110K2 | Unknown | Unknown | 3 | Planned | October | October
TO-26-CLE-T221-01 | TSO CUSTOMER TRANSFORMER - CLONEE 220-CLONEE 20-T221 | Unknown | Unknown | 6 | Planned | October | October
TO-26-FIN-220SB1-2CB-05 | COUPLER/SECTIONALISING CB - FINGLAS 220-FINGLAS 220-220SB1-2CB | Unknown | Unknown | 10 | Planned | October | October
TO-26-FIN GIS-110K5-01 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110K5 | Unknown | Unknown | 8 | Planned | October | October
TO-26-MAY-220K1-2-02 | COUPLER/SECTIONALISING CB - MAYNOOTH 220-MAYNOOTH 220-220K1-2 | Unknown | Unknown | 3 | Planned | October | October
TO-26-MAY-T2103-01 | TRANSFORMER - MAYNOOTH 220-MAYNOOTH 110-T2103 | Unknown | Unknown | 19 | Planned | October | November
TO-26-BNK-CBT-2-05 | 110kV FEEDER - BARNAKYLE 110-CASTLEBAGOT 110-2 | Unknown | Unknown | 2 | Planned | October | October
TO-26-PB-TF4-01 | TRANSFORMER - POOLBEG 220-POOLBEG 110-TF4 | Unknown | Unknown | 2 | Reference (Planned) | October | October
TO-26-BRT-220K2-01 | COUPLER/SECTIONALISING CB - BRACETOWN 220-BRACETOWN 220-220K2 | Unknown | Unknown | 5 | Planned | October | October
TO-26-CKM-PB-1-04 | 220kV FEEDER - CARRICKMINES 220-POOLBEG 220-1 | Unknown | Unknown |  | Planned | October | November
TO-26-CKM-PST2201-04 | TRANSFORMER - CARRICKMINES 220-CARRICKMINES 220-PST2201 | Unknown | Unknown | 24 | Planned | October | November
TO-26-PB-R223-4-01 | CAPACITOR/SVC/REACTOR - POOLBEG 220-POOLBEG 220-R223-4 | Unknown | Unknown | 6 | Planned | October | October
TO-26-CKM-CKM GIS-1-01 | 220kV FEEDER - CARRICKMINES 220-CARRICKMINES GIS 220-1 | 3 | 2 | 2 | Proposed | 26/10/2026 | 28/10/2026
TO-26-CKM-PB-1-06 | 220kV FEEDER - CARRICKMINES 220-POOLBEG 220-1 | 3 | 2 | 2 | Proposed | 26/10/2026 | 28/10/2026
TO-26-CKM-PST2201-05 | TRANSFORMER - CARRICKMINES 220-CARRICKMINES 220-PST2201 | 3 | 2 | 2 | Proposed | 26/10/2026 | 28/10/2026
TO-26-FIN GIS-110SA1-3CB-01 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110SA1-3CB | Unknown | Unknown | 8 | Planned | October | November
TO-26-PB-220K3-4-01 | COUPLER/SECTIONALISING CB - POOLBEG 220-POOLBEG 220-220K3-4 | Unknown | Unknown | 4 | Planned | October | October
TO-26-SNU-T104-01 | TSO CUSTOMER TRANSFORMER - SNUGBOROUGH 110-SNUGBOROUGH 10-T104 | Unknown | Unknown | 7 | Planned | October | November
TO-26-BRT-T224-01 | TSO CUSTOMER TRANSFORMER - BRACETOWN 220-BRACETOWN 20-T224 | Unknown | Unknown | 6 | Planned | November | November
TO-26-CDU-WOO-1-03 | 220kV FEEDER - CORDUFF 220-WOODLAND 220-1 | 12 | 10 | 10 | Proposed | 09/11/2026 | 20/11/2026
TO-26-FIN GIS-110SA2-4CB-02 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110SA2-4CB | Unknown | Unknown | 8 | Planned | November | November
TO-26-MAY-T2104-01 | TRANSFORMER - MAYNOOTH 220-MAYNOOTH 110-T2104 | Unknown | Unknown | 15 | Planned | November | November
TO-26-SNU-T131-01 | TSO CUSTOMER TRANSFORMER - SNUGBOROUGH 110-SNUGBOROUGH 33-T131 | Unknown | Unknown | 4 | Planned | November | November
TO-26-BLU-MUL-1-02 | 110kV FEEDER - BLUNDELSTOWN 110-MULLINGAR 110-1 | Unknown | Unknown |  | Planned | November | December
TO-26-SNU-T133-01 | TSO CUSTOMER TRANSFORMER - SNUGBOROUGH 110-SNUGBOROUGH 33-T133 | Unknown | Unknown | 4 | Planned | November | November
TO-26-CKM GIS-DSN-1-02 | 220kV FEEDER - CARRICKMINES GIS 220-DUNSTOWN 220-1 | Unknown | Unknown |  | Planned | November | November
TO-26-DSN-MAY-2-03 | 220kV FEEDER - DUNSTOWN 220-MAYNOOTH 220-2 | Unknown | Unknown | 5 | Planned | November | November
TO-26-FIN GIS-110SA3-5CB-01 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110SA3-5CB | Unknown | Unknown |  | Planned | November | December
TO-26-TH-220K1-2-01 | COUPLER/SECTIONALISING CB - TURLOUGH HILL 220-TURLOUGH HILL 220-220K1-2 | Unknown | Unknown | 10 | Planned | November | December
TO-26-BLU-T131-01 | GENERATOR TRANSFORMER - BLUNDELSTOWN 110-BLUNDELSTOWN 33-T131 | Unknown | Unknown | 2 | Planned | December | December
TO-26-BLU-T131-02 | GENERATOR TRANSFORMER - BLUNDELSTOWN 110-BLUNDELSTOWN 33-T131 | Unknown | Unknown | 2 | Planned | December | December
TO-26-FIN GIS-110SA4-6CB-02 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110SA4-6CB | Unknown | Unknown | 8 | Planned | December | December
TO-26-PB-R2002-05 | CAPACITOR/SVC/REACTOR - POOLBEG 220-POOLBEG 220-R2002 | Unknown | Unknown |  | Planned | December | December

## GEN_Cork
Outage ID | Feeder ID | Calendar Day Duration | Working Day Duration | Work Days | Outage Status | Start | Finish
TO-26-CHA-MAL-1-02 | 110kV FEEDER - CHARLEVILLE 110-MALLOW 110-1 | 5 | 5 | 5 | Scheduled | 05/01/2026 | 09/01/2026
TO-26-AD-T2014-01 | GENERATOR TRANSFORMER - AGHADA 220-AGHADA G14-T2014 | 49 | 34 | 34 | Scheduled | 11/01/2026 | 28/02/2026
TO-26-BAR-T141-03 | DISTRIBUTION TRANSFORMER - BARRYMORE 110-BARRYMORE 38-T141 | 4 | 4 | 4 | Reference | 19/01/2026 | 22/01/2026
TO-26-BAR,T-BAR-1-03 | 110kV FEEDER - BARRYMORE tee-BARRYMORE 110-1 | 4 | 4 | 4 | Scheduled | 19/01/2026 | 22/01/2026
TO-26-BAR,T-CAH-1-03 | 110kV FEEDER - BARRYMORE tee-CAHIR 110-1 | 4 | 4 | 4 | Scheduled | 19/01/2026 | 22/01/2026
TO-26-BAR,T-KRA-1-03 | 110kV FEEDER - BARRYMORE tee-KNOCKRAHA 110-1 | 4 | 4 | 4 | Scheduled | 19/01/2026 | 22/01/2026
TO-26-LYT-T132-01 | GENERATOR TRANSFORMER - LYSAGHTSTOWN 110-LYSAGHTSTOWN 33-T132 | 2 | 2 | 2 | Scheduled | 19/01/2026 | 20/01/2026
TO-26-110 kV A2 @ MR-01 | BUSBAR SECTION - MARINA 110-MARINA 110-110A2 | 11 | 9 | 9 | Scheduled | 19/01/2026 | 29/01/2026
TO-26-110 kV B2 @ MR-01 | BUSBAR SECTION - MARINA 110-MARINA 110-110B2 | 11 | 9 | 9 | Scheduled | 19/01/2026 | 29/01/2026
TO-26-MR-TBG-2-02 | 110kV FEEDER - MARINA 110-TRABEG 110-2 | 11 | 9 |  | Scheduled | 19/01/2026 | 29/01/2026
TO-26-110 kV A2 @ TBG-01 | BUSBAR SECTION - TRABEG 110-TRABEG 110-110A2 | 11 | 9 | 9 | Scheduled | 19/01/2026 | 29/01/2026
TO-26-110 kV B2 @ TBG-01 | BUSBAR SECTION - TRABEG 110-TRABEG 110-110B2 | 11 | 9 | 9 | Scheduled | 19/01/2026 | 29/01/2026
TO-26-MID-WHI-1-01 | 110kV FEEDER - MIDLETON 110-WHITEGATE 110-1 | 96 | 66 | 66 | Scheduled | 26/01/2026 | 01/05/2026
TO-26-DMY-MAC-1-04 | 110kV FEEDER - DUNMANWAY 110-MACROOM 110-1 | 28 | 20 | 20 | Scheduled | 03/02/2026 | 02/03/2026
TO-26-110 kV A2 @ KRA-03 | BUSBAR SECTION - KNOCKRAHA 110-KNOCKRAHA 110-110A2 | 9 | 7 | 7 | Scheduled | 12/02/2026 | 20/02/2026
TO-26-110 kV B2 @ KRA-03 | BUSBAR SECTION - KNOCKRAHA 110-KNOCKRAHA 110-110B2 | 9 | 7 | 7 | Scheduled | 12/02/2026 | 20/02/2026
TO-26-KRA-WOH-1-05 | 110kV FEEDER - KNOCKRAHA 110-WOODHOUSE 110-1 | 9 | 7 | 7 | Scheduled | 12/02/2026 | 20/02/2026
TO-26-RAF-110K1-2-02 | COUPLER/SECTIONALISING CB - RAFFEEN 110-RAFFEEN 110-110K1-2 | 3 | 3 | 3 | Scheduled | 16/02/2026 | 18/02/2026
TO-26-KBY-KRA-1-01 | 110kV FEEDER - KILBARRY 110-KNOCKRAHA 110-1 | 5 | 5 | 5 | Scheduled | 23/02/2026 | 27/02/2026
TO-26-220 kV A2 @ KRA-03 | BUSBAR SECTION - KNOCKRAHA 220-KNOCKRAHA 220-220A2 | 5 | 5 | 5 | Scheduled | 23/02/2026 | 27/02/2026
TO-26-220 kV B2 @ KRA-03 | BUSBAR SECTION - KNOCKRAHA 220-KNOCKRAHA 220-220B2 | 5 | 5 | 5 | Scheduled | 23/02/2026 | 27/02/2026
TO-26-MID-WHI-1-02 | 110kV FEEDER - MIDLETON 110-WHITEGATE 110-1 | 9 | 7 | 7 | Scheduled | 18/03/2026 | 26/03/2026
TO-26-WHI-110SA1-01 | SECTIONALISING DISCONNECT - WHITEGATE 110-WHITEGATE 110-110SA1 | 9 | 7 | 7 | Scheduled | 18/03/2026 | 26/03/2026
TO-26-WHI-110SA2-01 | SECTIONALISING DISCONNECT - WHITEGATE 110-WHITEGATE 110-110SA2 | 9 | 7 | 7 | Scheduled | 18/03/2026 | 26/03/2026
TO-26-WHI-CKB-T101-01 | TSO CUSTOMER TRANSFORMER - WHITEGATE 110-WHITEGATE 10-CKB-T101 | 9 | 7 | 7 | Scheduled | 18/03/2026 | 26/03/2026
TO-26-KRA-WOH-1-07 | 110kV FEEDER - KNOCKRAHA 110-WOODHOUSE 110-1 | 5 | 5 | 5 | Scheduled | 23/03/2026 | 27/03/2026
TO-26-CLA-CKN-1-01 | 110kV FEEDER - CLASHAVOON 110-CLONKEEN 110-1 | 2 | 2 | 2 | Scheduled | 25/03/2026 | 26/03/2026
TO-26-LYT-T132-02 | GENERATOR TRANSFORMER - LYSAGHTSTOWN 110-LYSAGHTSTOWN 33-T132 | 1 | 1 | 1 | Scheduled | 25/03/2026 | 25/03/2026
TO-26-BAN-RAF-1-02 | 110kV FEEDER - BANDON 110-RAFFEEN 110-1 | 119 | 81 |  | Scheduled | 26/03/2026 | 22/07/2026
TO-26-CHA-MAL-1-01 | 110kV FEEDER - CHARLEVILLE 110-MALLOW 110-1 | 30 | 20 | 20 | Scheduled | 30/03/2026 | 28/04/2026
TO-26-CLA-MAC-1-02 | 110kV FEEDER - CLASHAVOON 110-MACROOM 110-1 | 38 | 25 | 25 | Scheduled | 30/03/2026 | 06/05/2026
TO-26-AD-220K1-01 | COUPLER/SECTIONALISING CB - AGHADA 220-AGHADA 220-220K1 | 1 | 1 | 1 | Scheduled | 31/03/2026 | 31/03/2026
TO-26-AD-SA1-2CB-01 | COUPLER/SECTIONALISING CB - AGHADA 220-AGHADA 220-220SA1-2CB | 2 | 2 | 2 | Scheduled | 01/04/2026 | 02/04/2026
TO-26-KLN-KRA-1-06 | 220kV FEEDER - KILLONAN 220-KNOCKRAHA 220-1 | 10 | 8 | 8 | Scheduled | 08/04/2026 | 17/04/2026
TO-26-220 kV A1 @ KRA-03 | BUSBAR SECTION - KNOCKRAHA 220-KNOCKRAHA 220-220A1 | 10 | 8 | 8 | Scheduled | 08/04/2026 | 17/04/2026
TO-26-220 kV B1 @ KRA-03 | BUSBAR SECTION - KNOCKRAHA 220-KNOCKRAHA 220-220B1 | 10 | 8 | 8 | Scheduled | 08/04/2026 | 17/04/2026
TO-26-KRA-220K1-06 | COUPLER/SECTIONALISING CB - KNOCKRAHA 220-KNOCKRAHA 220-220K1 | 10 | 8 | 8 | Scheduled | 08/04/2026 | 17/04/2026
TO-26-KRA-220SA1-2CB-06 | COUPLER/SECTIONALISING CB - KNOCKRAHA 220-KNOCKRAHA 220-220SA1-2CB | 10 | 8 | 8 | Scheduled | 08/04/2026 | 17/04/2026
TO-26-KRA-220SB1-2CB-06 | COUPLER/SECTIONALISING CB - KNOCKRAHA 220-KNOCKRAHA 220-220SB1-2CB | 10 | 8 | 8 | Scheduled | 08/04/2026 | 17/04/2026
TO-26-AD-LPT-1-01 | 220kV FEEDER - AGHADA 220-LONG POINT 220-1 | 27 | 18 | 18 | Scheduled | 10/04/2026 | 06/05/2026
TO-26-LPT-T2002-01 | GENERATOR TRANSFORMER - LONG POINT 220-LONG POINT G1-T2002 | 27 | 18 | 18 | Scheduled | 10/04/2026 | 06/05/2026
TO-26-AD-RAF-1-03 | 220kV FEEDER - AGHADA 220-RAFFEEN 220-1 | 19 | 14 | 14 | Scheduled | 20/04/2026 | 08/05/2026
TO-26-IA-T101-01 | GENERATOR TRANSFORMER - INNISCARRA 110-INNISCARRA G1-T101 | 12 | 10 | 10 | Scheduled | 20/04/2026 | 01/05/2026
TO-26-KRA-RAF-1-06 | 220kV FEEDER - KNOCKRAHA 220-RAFFEEN 220-1 | 12 | 10 | 10 | Scheduled | 20/04/2026 | 01/05/2026
TO-26-LYT-T132-03 | GENERATOR TRANSFORMER - LYSAGHTSTOWN 110-LYSAGHTSTOWN 33-T132 | 1 | 1 | 1 | Scheduled | 29/04/2026 | 29/04/2026
TO-26-RAF-TBG-2-03 | 110kV FEEDER - RAFFEEN 110-TRABEG 110-2 | 25 | 19 |  | Scheduled | 05/05/2026 | 29/05/2026
TO-26-110 kV A1 @ TBG-01 | BUSBAR SECTION - TRABEG 110-TRABEG 110-110A1 | 14 | 10 | 10 | Scheduled | 05/05/2026 | 18/05/2026
TO-26-110 kV B1 @ TBG-01 | BUSBAR SECTION - TRABEG 110-TRABEG 110-110B1 | 14 | 10 | 10 | Scheduled | 05/05/2026 | 18/05/2026
TO-26-110 kV A2 @ RAF-01 | BUSBAR SECTION - RAFFEEN 110-RAFFEEN 110-110A2 | 115 | 81 | 81 | Scheduled | 11/05/2026 | 02/09/2026
TO-26-110 kV B2 @ RAF-01 | BUSBAR SECTION - RAFFEEN 110-RAFFEEN 110-110B2 | 115 | 81 | 81 | Scheduled | 11/05/2026 | 02/09/2026
TO-26-KRA-T2101-01 | TRANSFORMER - KNOCKRAHA 220-KNOCKRAHA 110-T2101 | 4 | 4 | 4 | Scheduled | 25/05/2026 | 28/05/2026
TO-26-110 kV A1 @ RAF-04 | BUSBAR SECTION - RAFFEEN 110-RAFFEEN 110-110A1 | 10 | 8 | 8 | Scheduled | 02/06/2026 | 11/06/2026
TO-26-110 kV B1 @ RAF-03 | BUSBAR SECTION - RAFFEEN 110-RAFFEEN 110-110B1 | 10 | 8 | 8 | Scheduled | 02/06/2026 | 11/06/2026
TO-26-220 kV A1 @ RAF-01 | BUSBAR SECTION - RAFFEEN 220-RAFFEEN 220-220A1 | 10 | 8 | 8 | Scheduled | 02/06/2026 | 11/06/2026
TO-26-220 kV B1 @ RAF-01 | BUSBAR SECTION - RAFFEEN 220-RAFFEEN 220-220B1 | 10 | 8 | 8 | Scheduled | 02/06/2026 | 11/06/2026
TO-26-RAF-T2101-01 | TRANSFORMER - RAFFEEN 220-RAFFEEN 110-T2101 | 10 | 8 | 8 | Scheduled | 02/06/2026 | 11/06/2026
TO-26-MR-T106-01 | DISTRIBUTION TRANSFORMER - MARINA 110-MARINA 10-T106 | 2 | 2 | 2 | Reference | 03/06/2026 | 04/06/2026
TO-26-220 kV A1 @ AD-01 | BUSBAR SECTION - AGHADA 220-AGHADA 220-220A1 | 1 | 1 | 1 | Proposed | 08/06/2026 | 08/06/2026
TO-26-220 kV A2 @ AD-01 | BUSBAR SECTION - AGHADA 220-AGHADA 220-220A2 | 1 | 1 | 1 | Proposed | 08/06/2026 | 08/06/2026
TO-26-AD-220K1-03 | COUPLER/SECTIONALISING CB - AGHADA 220-AGHADA 220-220K1 | 1 | 1 | 1 | Proposed | 08/06/2026 | 08/06/2026
TO-26-AD-SA1-2CB-02 | COUPLER/SECTIONALISING CB - AGHADA 220-AGHADA 220-220SA1-2CB | 1 | 1 | 1 | Proposed | 08/06/2026 | 08/06/2026
TO-26-AD-T2011/12-02 | GENERATOR TRANSFORMER - AGHADA 220-AGHADA G11/12-T2011/12 | 1 | 1 | 1 | Proposed | 08/06/2026 | 08/06/2026
TO-26-KRA-220SA1-2CB-05 | COUPLER/SECTIONALISING CB - KNOCKRAHA 220-KNOCKRAHA 220-220SA1-2CB | 12 | 10 | 10 | Proposed | 08/06/2026 | 19/06/2026
TO-26-KRA-220SB1-2CB-05 | COUPLER/SECTIONALISING CB - KNOCKRAHA 220-KNOCKRAHA 220-220SB1-2CB | 12 | 10 | 10 | Proposed | 08/06/2026 | 19/06/2026
TO-26-KRA-WOH-1-08 | 110kV FEEDER - KNOCKRAHA 110-WOODHOUSE 110-1 | 12 | 10 | 10 | Proposed | 08/06/2026 | 19/06/2026
TO-26-KRA-WOH-1-02 | 110kV FEEDER - KNOCKRAHA 110-WOODHOUSE 110-1 | 12 | 10 | 10 | Scheduled | 08/06/2026 | 19/06/2026
TO-26-CD-T103-03 | GENERATOR TRANSFORMER - CARRIGADROHID 110-CARRIGADROHID G3-T103 | 11 | 9 | 9 | Proposed | 09/06/2026 | 19/06/2026
TO-26-110 kV A1 @ TBG-02 | BUSBAR SECTION - TRABEG 110-TRABEG 110-110A1 | 10 | 8 | 8 | Proposed | 10/06/2026 | 19/06/2026
TO-26-110 kV A2 @ TBG-03 | BUSBAR SECTION - TRABEG 110-TRABEG 110-110A2 | 10 | 8 | 8 | Proposed | 10/06/2026 | 19/06/2026
TO-26-110 kV B1 @ TBG-02 | BUSBAR SECTION - TRABEG 110-TRABEG 110-110B1 | 10 | 8 | 8 | Proposed | 10/06/2026 | 19/06/2026
TO-26-110 kV B2 @ TBG-03 | BUSBAR SECTION - TRABEG 110-TRABEG 110-110B2 | 10 | 8 | 8 | Proposed | 10/06/2026 | 19/06/2026
TO-26-TBG-110K1-2-01 | COUPLER/SECTIONALISING CB - TRABEG 110-TRABEG 110-110K1-2 | 10 | 8 | 8 | Proposed | 10/06/2026 | 19/06/2026
TO-26-BAN-CAP1-01 | CAPACITOR/SVC/REACTOR - BANDON 110-BANDON 110-CAP1 | 5 | 5 | 5 | Proposed | 15/06/2026 | 19/06/2026
TO-26-DMY-T141-01 | DISTRIBUTION TRANSFORMER - DUNMANWAY 110-DUNMANWAY 38-T141 | 2 | 2 | 2 | Reference | 16/06/2026 | 17/06/2026
TO-26-LYT-110K2-01 | COUPLER/SECTIONALISING CB - LYSAGHTSTOWN 110-LYSAGHTSTOWN 110-110K2 | 1 | 1 | 1 | Scheduled | 16/06/2026 | 16/06/2026
TO-26-AD-GGO-1-01 | 220kV FEEDER - AGHADA 220-GLANAGOW 220-1 | 12 | 10 |  | Proposed | 22/06/2026 | 03/07/2026
TO-26-AD-GGO-1-02 | 220kV FEEDER - AGHADA 220-GLANAGOW 220-1 | 2 | 2 | 2 | Scheduled | 22/06/2026 | 23/06/2026
TO-26-BAR-T141-04 | DISTRIBUTION TRANSFORMER - BARRYMORE 110-BARRYMORE 38-T141 | 9 | 7 | 7 | Reference (Proposed) | 22/06/2026 | 30/06/2026
TO-26-BAR,T-BAR-1-04 | 110kV FEEDER - BARRYMORE tee-BARRYMORE 110-1 | 9 | 7 | 7 | Proposed | 22/06/2026 | 30/06/2026
TO-26-BAR,T-CAH-1-05 | 110kV FEEDER - BARRYMORE tee-CAHIR 110-1 | 9 | 7 | 7 | Proposed | 22/06/2026 | 30/06/2026
TO-26-BAR,T-KRA-1-05 | 110kV FEEDER - BARRYMORE tee-KNOCKRAHA 110-1 | 9 | 7 | 7 | Proposed | 22/06/2026 | 30/06/2026
TO-26-CGG-DMY-1-01 | 110kV FEEDER - CARRIGDANGAN 110-DUNMANWAY 110-1 | 12 | 10 | 10 | Proposed | 29/06/2026 | 10/07/2026
TO-26-CGG-T131-01 | GENERATOR TRANSFORMER - CARRIGDANGAN 110-CARRIGDANGAN 33-T131 | 12 | 10 | 10 | Proposed | 29/06/2026 | 10/07/2026
TO-26-110 kV A1 @ KBY-06 | BUSBAR SECTION - KILBARRY 110-KILBARRY 110-110A1 | 26 | 20 | 20 | Proposed | 29/06/2026 | 24/07/2026
TO-26-110 kV A2 @ KBY-01 | BUSBAR SECTION - KILBARRY 110-KILBARRY 110-110A2 | 26 | 20 | 20 | Proposed | 29/06/2026 | 24/07/2026
TO-26-110 kV B1 @ KBY-05 | BUSBAR SECTION - KILBARRY 110-KILBARRY 110-110B1 | 26 | 20 | 20 | Proposed | 29/06/2026 | 24/07/2026
TO-26-110 kV B2 @ KBY-01 | BUSBAR SECTION - KILBARRY 110-KILBARRY 110-110B2 | 26 | 20 | 20 | Proposed | 29/06/2026 | 24/07/2026
TO-26-KBY-110K1-2-01 | COUPLER/SECTIONALISING CB - KILBARRY 110-KILBARRY 110-110K1-2 | 26 | 20 | 20 | Proposed | 29/06/2026 | 24/07/2026
TO-26-110 kV A2 @ RAF-03 | BUSBAR SECTION - RAFFEEN 110-RAFFEEN 110-110A2 | 12 | 10 | 10 | Proposed | 29/06/2026 | 10/07/2026
TO-26-110 kV B2 @ RAF-05 | BUSBAR SECTION - RAFFEEN 110-RAFFEEN 110-110B2 | 12 | 10 | 10 | Proposed | 29/06/2026 | 10/07/2026
TO-26-RAF-CAP2-02 | CAPACITOR/SVC/REACTOR - RAFFEEN 110-RAFFEEN 110-CAP2 | 12 | 10 | 10 | Proposed | 29/06/2026 | 10/07/2026
TO-26-KRA-220SA2-4CB-05 | COUPLER/SECTIONALISING CB - KNOCKRAHA 220-KNOCKRAHA 220-220SA2-4CB | 5 | 5 | 5 | Proposed | 06/07/2026 | 10/07/2026
TO-26-KRA-T2102-01 | TRANSFORMER - KNOCKRAHA 220-KNOCKRAHA 110-T2102 | Unknown | Unknown | 7 | Planned | July | July
TO-26-IA-T101-02 | GENERATOR TRANSFORMER - INNISCARRA 110-INNISCARRA G1-T101 | 1 | 1 | 1 | Proposed | 08/07/2026 | 08/07/2026
TO-26-KRA-LYT-1-02 | 110kV FEEDER - KNOCKRAHA 110-LYSAGHTSTOWN 110-1 | 50 | 35 | 35 | Proposed | 08/07/2026 | 26/08/2026
TO-26-KRA-220SB2-4CB-05 | COUPLER/SECTIONALISING CB - KNOCKRAHA 220-KNOCKRAHA 220-220SB2-4CB | 5 | 5 | 5 | Proposed | 13/07/2026 | 17/07/2026
TO-26-DMY-CAP2-01 | CAPACITOR/SVC/REACTOR - DUNMANWAY 110-DUNMANWAY 110-CAP2 | 3 | 3 | 3 | Proposed | 14/07/2026 | 16/07/2026
TO-26-DMY-T142-01 | DISTRIBUTION TRANSFORMER - DUNMANWAY 110-DUNMANWAY 38-T142 | 2 | 2 | 2 | Reference (Proposed) | 15/07/2026 | 16/07/2026
TO-26-LIB-T101-01 | DISTRIBUTION TRANSFORMER - LIBERTY STREET 110-LIBERTY STREET 10-T101 | 2 | 2 | 2 | Reference (Proposed) | 15/07/2026 | 16/07/2026
TO-26-220 kV A4 @ KRA-08 | BUSBAR SECTION - KNOCKRAHA 220-KNOCKRAHA 220-220A4 | 5 | 5 | 5 | Proposed | 20/07/2026 | 24/07/2026
TO-26-220 kV B4 @ KRA-10 | BUSBAR SECTION - KNOCKRAHA 220-KNOCKRAHA 220-220B4 | 5 | 5 | 5 | Proposed | 20/07/2026 | 24/07/2026
TO-26-KRA-220K4-04 | COUPLER/SECTIONALISING CB - KNOCKRAHA 220-KNOCKRAHA 220-220K4 | 5 | 5 | 5 | Proposed | 20/07/2026 | 24/07/2026
TO-26-KRA-220SA2-4CB-09 | COUPLER/SECTIONALISING CB - KNOCKRAHA 220-KNOCKRAHA 220-220SA2-4CB | 5 | 5 | 5 | Proposed | 20/07/2026 | 24/07/2026
TO-26-KRA-220SB2-4CB-09 | COUPLER/SECTIONALISING CB - KNOCKRAHA 220-KNOCKRAHA 220-220SB2-4CB | 5 | 5 | 5 | Proposed | 20/07/2026 | 24/07/2026
TO-26-KBY-MR-1-01 | 110kV FEEDER - KILBARRY 110-MARINA 110-1 | 4 | 4 | 4 | Proposed | 21/07/2026 | 24/07/2026
TO-26-110 kV A1 @ RAF-03 | BUSBAR SECTION - RAFFEEN 110-RAFFEEN 110-110A1 | 16 | 11 | 11 | Proposed | 23/07/2026 | 07/08/2026
TO-26-110 kV B1 @ RAF-02 | BUSBAR SECTION - RAFFEEN 110-RAFFEEN 110-110B1 | 16 | 11 | 11 | Proposed | 23/07/2026 | 07/08/2026
TO-26-RAF-TBG-1-04 | 110kV FEEDER - RAFFEEN 110-TRABEG 110-1 | 16 | 11 | 11 | Proposed | 23/07/2026 | 07/08/2026
TO-26-110 kV A2 @ TBG-02 | BUSBAR SECTION - TRABEG 110-TRABEG 110-110A2 | 16 | 11 | 11 | Proposed | 23/07/2026 | 07/08/2026
TO-26-110 kV B2 @ TBG-02 | BUSBAR SECTION - TRABEG 110-TRABEG 110-110B2 | 16 | 11 | 11 | Proposed | 23/07/2026 | 07/08/2026
TO-26-CD-KBY-1-03 | 110kV FEEDER - CARRIGADROHID 110-KILBARRY 110-1 | 12 | 9 | 9 | Proposed | 27/07/2026 | 07/08/2026
TO-26-CLA-DMY-1-01 | 110kV FEEDER - CLASHAVOON 110-DUNMANWAY 110-1 | 5 | 5 | 5 | Proposed | 27/07/2026 | 31/07/2026
TO-26-KBY-KRA-2-02 | 110kV FEEDER - KILBARRY 110-KNOCKRAHA 110-2 | 75 | 54 | 54 | Proposed | 27/07/2026 | 09/10/2026
TO-26-KBY-KRA-2-03 | 110kV FEEDER - KILBARRY 110-KNOCKRAHA 110-2 | 22 | 15 | 15 | Proposed | 27/07/2026 | 17/08/2026
TO-26-BGH-110SA1-01 | SECTIONALISING DISCONNECT - BOGGERAGH 110-BOGGERAGH 110-110SA1 | Unknown | Unknown | 10 | Planned | August | August
TO-26-BGH-110SA2-01 | SECTIONALISING DISCONNECT - BOGGERAGH 110-BOGGERAGH 110-110SA2 | Unknown | Unknown | 10 | Planned | August | August
TO-26-BGH-CLA-1-01 | 110kV FEEDER - BOGGERAGH 110-CLASHAVOON 110-1 | Unknown | Unknown |  | Planned | August | August
TO-26-BGH-T121-01 | GENERATOR TRANSFORMER - BOGGERAGH 110-BOGGERAGH 20-T121 | Unknown | Unknown | 10 | Planned | August | August
TO-26-BGH-T121-02 | GENERATOR TRANSFORMER - BOGGERAGH 110-BOGGERAGH 20-T121 | Unknown | Unknown | 2 | Planned | August | August
TO-26-BGH-T132-01 | GENERATOR TRANSFORMER - BOGGERAGH 110-BOGGERAGH 33-T132 | Unknown | Unknown | 10 | Planned | August | August
TO-26-BGH-T142-01 | DISTRIBUTION TRANSFORMER - BOGGERAGH 110-BOGGERAGH 38-T142 | Unknown | Unknown | 10 | Reference (Planned) | August | August
TO-26-MR-110K1-2-02 | COUPLER/SECTIONALISING CB - MARINA 110-MARINA 110-110K1-2 | Unknown | Unknown | 10 | Planned | August | August
TO-26-BGH-T132-02 | GENERATOR TRANSFORMER - BOGGERAGH 110-BOGGERAGH 33-T132 | Unknown | Unknown | 1 | Planned | August | August
TO-26-CD-MAC-1-03 | 110kV FEEDER - CARRIGADROHID 110-MACROOM 110-1 | Unknown | Unknown | 5 | Planned | August | August
TO-26-GGO-220K1-2-02 | COUPLER/SECTIONALISING CB - GLANAGOW 220-GLANAGOW 220-220K1-2 | Unknown | Unknown | 8 | Planned | August | August
TO-26-220 kV A1 @ KRA-04 | BUSBAR SECTION - KNOCKRAHA 220-KNOCKRAHA 220-220A1 | 12 | 10 | 10 | Proposed | 17/08/2026 | 28/08/2026
TO-26-220 kV B1 @ KRA-04 | BUSBAR SECTION - KNOCKRAHA 220-KNOCKRAHA 220-220B1 | 12 | 10 | 10 | Proposed | 17/08/2026 | 28/08/2026
TO-26-KRA-220K1-03 | COUPLER/SECTIONALISING CB - KNOCKRAHA 220-KNOCKRAHA 220-220K1 | 12 | 10 | 10 | Proposed | 17/08/2026 | 28/08/2026
TO-26-KRA-220SA1-2CB-07 | COUPLER/SECTIONALISING CB - KNOCKRAHA 220-KNOCKRAHA 220-220SA1-2CB | 12 | 10 | 10 | Proposed | 17/08/2026 | 28/08/2026
TO-26-KRA-220SB1-2CB-07 | COUPLER/SECTIONALISING CB - KNOCKRAHA 220-KNOCKRAHA 220-220SB1-2CB | 12 | 10 | 10 | Proposed | 17/08/2026 | 28/08/2026
TO-26-AD-KRA-1-03 | 220kV FEEDER - AGHADA 220-KNOCKRAHA 220-1 | Unknown | Unknown | 15 | Planned | August | September
TO-26-AD-KRA-2-03 | 220kV FEEDER - AGHADA 220-KNOCKRAHA 220-2 | Unknown | Unknown | 15 | Planned | August | September
TO-26-GGO-T2001-01 | GENERATOR TRANSFORMER - GLANAGOW 220-GLANAGOW G1-T2001 | Unknown | Unknown |  | Planned | August | September
TO-26-WHI-CKB-T102-01 | TSO CUSTOMER TRANSFORMER - WHITEGATE 110-WHITEGATE 10-CKB-T102 | Unknown | Unknown | 5 | Planned | August | September
TO-26-220 kV B1/B2 @ AD-01 | BUSBAR SECTION - AGHADA 220-AGHADA 220-220B1-B2 | Unknown | Unknown | 2 | Planned | September | September
TO-26-AD-SB1-2CB-02 | COUPLER/SECTIONALISING CB - AGHADA 220-AGHADA 220-220SB1-2CB | Unknown | Unknown | 2 | Planned | September | September
TO-26-AD-T2011/12-01 | GENERATOR TRANSFORMER - AGHADA 220-AGHADA G11/12-T2011/12 | Unknown | Unknown |  | Planned | September | September
TO-26-WHI-CKB-T101-02 | TSO CUSTOMER TRANSFORMER - WHITEGATE 110-WHITEGATE 10-CKB-T101 | Unknown | Unknown | 5 | Planned | September | September
TO-26-CRO-KBY-1-02 | 110kV FEEDER - COOLROE 110-KILBARRY 110-1 | Unknown | Unknown | 3 | Planned | September | September
TO-26-AD-HWL-1-01 | 220kV FEEDER - AGHADA 220-HADWELL 220-1 | Unknown | Unknown | 2 | Planned | October | October
TO-26-RAF-T2102-01 | TRANSFORMER - RAFFEEN 220-RAFFEEN 110-T2102 | Unknown | Unknown | 7 | Planned | October | October
TO-26-KRA-110K1-2-02 | COUPLER/SECTIONALISING CB - KNOCKRAHA 110-KNOCKRAHA 110-110K1-2 | Unknown | Unknown | 19 | Planned | October | November
TO-26-CVW-COW-1-01 | 110kV FEEDER - CASTLEVIEW 110-COW CROSS 110-1 | Unknown | Unknown | 14 | Planned | October | November
TO-26-AD-WHI-1-03 | 110kV FEEDER - AGHADA 110-WHITEGATE 110-1 | Unknown | Unknown | 5 | Planned | November | November
TO-26-CLA-T2102-01 | TRANSFORMER - CLASHAVOON 220-CLASHAVOON 110-T2102 | Unknown | Unknown | 10 | Planned | November | November
TO-26-COW-WHI-1-01 | 110kV FEEDER - COW CROSS 110-WHITEGATE 110-1 | Unknown | Unknown | 15 | Planned | November | November
TO-26-CVW-COW-1-03 | 110kV FEEDER - CASTLEVIEW 110-COW CROSS 110-1 | Unknown | Unknown | 5 | Planned | November | November
TO-26-COW-110SA2-01 | SECTIONALISING DISCONNECT - COW CROSS 110-COW CROSS 110-110SA2 | Unknown | Unknown | 5 | Planned | November | November
TO-26-KBY-MAL-1-02 | 110kV FEEDER - KILBARRY 110-MALLOW 110-1 | Unknown | Unknown | 7 | Planned | November | December