## Sheet1
General |  |  |  | Communicated Ex-Ante |  |  |  |  | Actual Works |  |  |  | Indicative Window |  |  | Indicative Duration |  |  | Scheduled Days |  |  | Designated Days |  |  | Works Description Communicated Ex-Ante |  |  | Generator Dates |  |  | Scheduled Works Not Completed |  |  | No | TAO | Yes
OACA | Unit | Work Item Description | Work ID | Included in Ex-Ante Report? | TOP ID | Outage Window | Outage Duration | Reason for Works Addition | Actual Start Date | Actual End Date | Works completed? | Reason for not completing, if applicable | Change? | Reason for Change | Driver | Change to Indicative Duration communicated Ex-Ante? | Reason for Change to Duration Communicated Ex-Ante, if applicable | Driver of Change to Duration Communicated Ex-Ante(e.g. TSO, TAO, Gen) | Change to Scheduled Dates communicated M-1? | Reason for Change to Scheduled Dates communicated M-1, if applicable | Driver of Change to Scheduled Dates communicated M-1 (e.g. TSO, TAO, Gen) | Change to Designated Days communicated M-1? | Reason for Change to Designated Days communicated M-1, if applicable | Driver of Change to Designated Days communicated M-1 (e.g. TSO, TAO, Gen) | Change to Works Description Communicated Ex-Ante | Reason for Change to Works Description communicated Ex-Ante, if applicable | Driver of Change to Works Description communicated Ex-Ante | Change to Generator Outage Dates | Reason for Change to Generator Dates | Driver of Change to Generator Outage Dates | Works Completed | Reason for Works Not Being Completed | Driver of Reason for Works Not Being Completed | Completed in Previous Outage Season | GENERATOR | No
[34 empty] | Yes | No Change
Aghada T2011/12 | AT11/12 | As a consequence of hotspot repairs to (Lwr 1 Span 28/29) Lower phase midspan joint on Aghada - Knockraha 1 | 901098961 | No | N/A | N/A | N/A | TAO requested repairs in season | 2020-07-19 | 2020-07-24 | Yes | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Yes | Work completed early by TAO | TAO | Yes | Work completed early by TAO | TAO | Yes | TAO requested repairs in season | TAO | No | N/A | N/A | Yes | N/A | N/A | N/A | N/A
Aghada T2011/12 | AT11/12 | As a consequence of hotspot repairs to (Lwr 2 Span 28/29) lower phase midspan joint on Aghada - Knockraha 1 | 901098964 | No | N/A | N/A | N/A | TAO requested repairs in season | 2020-07-19 | 2020-07-24 | Yes | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Yes | Work completed a day early by TAO | TAO | Yes | Work completed early by TAO | TAO | Yes | TAO requested repairs in season | TAO | No | N/A | N/A | Yes | N/A | N/A |  | COVID
Aghada T2011/12 | AT11/12 | As a consequence of hotspot repairs to (C1 Span 61/62) centre midspan joint on Aghada - Knockraha 2 | 901098965 | No | N/A | N/A | N/A | TAO requested repairs in season | 2020-07-19 | 2020-07-24 | Yes | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Yes | Work completed a day early by TAO | TAO | No | Work completed early by TAO | TAO | Yes | TAO requested repairs in season | TAO | No | N/A | N/A | Yes | N/A | N/A |  | TSO
Aghada T2011/12 | AT11/12 | As a consequence of hotspot repairs to (Upr 1 Span 61 / 62) upper midspan joint on Aghada - Knockraha 2 | 901098966 | No | N/A | N/A | N/A | TAO requested repairs in season | 2020-07-19 | 2020-07-24 | Yes | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Yes | Work completed a day early by TAO | TAO | No | Work completed early by TAO | TAO | Yes | TAO requested repairs in season | TAO | No | N/A | N/A | Yes | N/A | N/A
Aghada T2011/12 | AT11/12 | As a consequence of hotspot repairs to (C2 Span 28/29) centre midspan on Aghada - Knockraha 2 | 901098967 | No | N/A | N/A | N/A | TAO requested repairs in season | 2020-07-19 | 2020-07-24 | Yes | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Yes | Work completed a day early by TAO | TAO | No | Work completed early by TAO | TAO | Yes | TAO requested repairs in season | TAO | No | N/A | N/A | Yes | N/A | N/A
Aghada T2011/12 | AT11/12 | As a consequence of hotspot repairs to (C2 Span 61/62) centre midspan joint on Aghada Knockraha 2 | 901098971 | No | N/A | N/A | N/A | TAO requested repairs in season | 2020-07-19 | 2020-07-24 | Yes | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Yes | Work completed a day early by TAO | TAO | No | Work completed early by TAO | TAO | Yes | TAO requested repairs in season | TAO | No | N/A | N/A | Yes | N/A | N/A
Ardnacrusha T101 | AA1 | 110KV MO Cubicle Operational Test | 901050256 | Yes | TO-20-AA GIS-T101-01 | July | 1 day | N/A | 2020-06-15 | 2020-06-19 | Yes | N/A | Yes | Generator requested change to Committed Outage Programme as a result of COVID-19 restrictions | COVID | No | N/A | N/A | Yes | Generator requested change to Committed Outage Programme as a result of COVID-19 restrictions | COVID | Yes | Generator requested change to Committed Outage Programme as a result of COVID-19 restrictions | COVID | No | N/A | N/A | Yes | Generator requested change to Committed Outage Programme as a result of COVID-19 restrictions | COVID | Yes | N/A | N/A
Ardnacrusha T103 | AA3 | 110kV GIS Cubicle Operational Test | 901129531 | Yes | TO-20-AA GIS-T103-01 | July | 1 day | N/A | 2020-04-20 | 2020-04-24 | Yes | N/A | Yes | Generator requested change to Committed Outage Programme as a result of COVID-19 restrictions | COVID | No | N/A | N/A | No | N/A | N/A | No | N/A | N/A | No | N/A | N/A | Yes | Generator requested change to Committed Outage Programme as a result of COVID-19 restrictions | COVID | Yes | N/A | N/A
Aghada - Longpoint | AD2 | P3 Protection maintenance of 7SA612, GRL100 | Protection | Yes | TO-20-AD-LPT-1-01 | July | 2 days | N/A | N/A | N/A | Completed in Previous Outage Season | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Yes | Application of extra designated days after TAO advised of further transmission maintenance to overlapping work on double circuit outage of Aghada - Knockraha | TAO | Completed in Previous Outage Season | Completed in Previous Outage Season | TAO | N/A | N/A | N/A | N/A | N/A | N/A
Aghada - Longpoint | AD2 | Cable Insp. 400 & 220kV Feeder XLPE | 901129020 | Yes | TO-20-AD-LPT-1-01 | July | 2 days | N/A | 2020-07-19 | 2020-07-24 | Yes | N/A | No | N/A | N/A | No | N/A | N/A | No | N/A | N/A | Yes | Application of extra designated days after TAO advised of further transmission maintenance to overlapping work on double circuit outage of Aghada - Knockraha | TAO | No | N/A | N/A | No | N/A | N/A | Yes | N/A | N/A
Aghada T2011/12 | Aghada AT11 & AT12 | 220kV SF6 Cubicle Ordinary Service | 901130028 | Yes | TO-20-AD-T2011/12-02 | February | 5 days | N/A | 2020-02-24 | 2020-06-03 | Yes | N/A | No | N/A | N/A | No | N/A | N/A | No | N/A | N/A | No | N/A | N/A | No | N/A | N/A | No | N/A | N/A | Yes | N/A | N/A
Aghada T2011/12 | Aghada AT11 & AT12 | 220kV Cubicle Condition Assessment | 901129234 | Yes | TO-20-AD-T2011/12-02 | February | 5 days | N/A | 2020-02-24 | 2020-06-03 | Yes | N/A | No | N/A | N/A | No | N/A | N/A | No | N/A | N/A | No | N/A | N/A | No | N/A | N/A | No | N/A | N/A | Yes | N/A | N/A
Aghada T2011/12 | Aghada AT11 & AT12 | Annual Insp. 400 & 220 Station OF Cable | 901129053 | Yes | TO-20-AD-T2011/12-02 | February | 5 days | N/A | 2020-02-24 | 2020-06-03 | Yes | N/A | No | N/A | N/A | No | N/A | N/A | No | N/A | N/A | No | N/A | N/A | No | N/A | N/A | No | N/A | N/A | Yes | N/A | N/A
Aghada T2011/12 | Aghada AT11 & AT12 | HV Pressure Vessel Inspection | 901160149 | Yes | TO-20-AD-T2011/12-02 | February | 5 days | N/A | 2020-02-24 | 2020-06-03 | Yes | N/A | No | N/A | N/A | No | N/A | N/A | No | N/A | N/A | No | N/A | N/A | No | N/A | N/A | No | N/A | N/A | Yes | N/A | N/A
Aghada T2014 | Aghada AT14 | P3 Protection maintenance of 7SA612, 7UT92 | Protection | Yes | TO-20-AD-T2014-02 | July | 2 days | N/A | N/A | N/A | No | Work deferred by TSO as non-priority | Yes | TSO requested change to due to system reasons | TSO | No | N/A | N/A | No | N/A | N/A | No | N/A | N/A | No | N/A | N/A | Yes | TSO requested change to due to system reasons | TSO | No | Work deferred by TSO as non-priority | TSO
Aghada T2014 | Aghada AT14 | Annual Insp. 400 & 220 Station OF Cable | 901129052 | Yes | TO-20-AD-T2014-02 | July | 2 days | N/A | 2020-08-06 | 2020-08-07 | Yes | N/A | Yes | TSO requested change to due to system reasons | TSO | Yes | TSO requested change to due to system reasons | TSO | Yes | TSO requested change to due to system reasons | TSO | Yes | TSO requested change to due to system reasons | TSO | No | N/A | N/A | Yes | TSO requested change to due to system reasons | TSO | Yes | N/A | N/A
Aghada T2014 | Aghada AT14 | Oil sampling of cable boxes on T2102 | 900908020 | No | TO-20-AD-T2014-02 | N/A | N/A | Added to overlap with maintenance works in Aghada T2014 and generator outage to ensure unit was not offloaded a second time later in season | 2020-08-06 | 2020-08-07 | Yes | N/A | N/A | N/A | N/A | N/A | N/A | N/A | No | N/A | N/A | No | N/A | N/A | Yes | Added to overlap with maintenance works in Aghada T2014 and generator outage to ensure unit was not offloaded a second time later in season | TAO | No | N/A | N/A | Yes | N/A | N/A
Agannygal - Derrybrien | Derrybrien DY1 | 110kV SF6 Cubicle Operational Test | 901129953 | Yes | TO-20-AGL-DYN-1-02 | June | 5 days | N/A | 2020-09-07 | 2020-09-11 | Yes | N/A | Yes | Original outage deferred due to COVID 19 restrictions | COVID | No | N/A | N/A | Yes | TAO completed works earlier than anticipated | TAO | No | N/A | N/A | No | N/A | N/A | No | N/A | N/A | Yes | N/A | N/A
Agannygal - Derrybrien | Derrybrien DY1 | CB - Siemens 3AP mod required to prevent spring charging lockout with loss of AC. | 900713712 | Yes | TO-20-AGL-DYN-1-02 | June | 5 days | N/A | 2020-09-07 | 2020-09-11 | Yes | N/A | Yes | Original outage deferred due to COVID 19 restrictions | COVID | No | N/A | N/A | Yes | TAO completed works earlier than anticipated | TAO | No | N/A | N/A | No | N/A | N/A | No | N/A | N/A | Yes | N/A | N/A
Athea - Dromada | Dromada DR1 | 110kV SF6 Cubicle Operational Test | 901043693 | Yes | TO-20-ATE-DRO-1-01 | August | 2 days | N/A | 2020-08-24 | 2020-08-28 | Yes | N/A | No | N/A | N/A | No | N/A | N/A | Yes | Changed due to generator request | GENERATOR | Yes | Changed due to generator request | GENERATOR | No | N/A | N/A | Yes | Changed due to generator request | GENERATOR | Yes | N/A | N/A
Athea - Dromada | Dromada DR1 | Cable Insp. 110kV XLPE | 901129101 | Yes | TO-20-ATE-DRO-1-01 | August | 2 days | N/A | 2020-08-24 | 2020-08-28 | Yes | N/A | No | N/A | N/A | No | N/A | N/A | Yes | Changed due to generator request | GENERATOR | Yes | Changed due to generator request | GENERATOR | No | N/A | N/A | Yes | Changed due to generator request | GENERATOR | Yes | N/A | N/A
Athea - Knockanure | Athea AH1 | 110kV SF6 Cubicle Ordinary Service | 901042193 | Yes | TO-20-ATE-KNR-1-01 | August | 4 days | N/A | N/A | N/A | No | Work item was deferred to 2021 following generator request | Yes | Work item was deferred to 2021 following generator request | GENERATOR | No | N/A | N/A | Yes | Work item was deferred to 2021 following generator request | GENERATOR | Yes | Work item was deferred to 2021 following generator request | GENERATOR | No | N/A | N/A | No | N/A | N/A | No | Work item was deferred to 2021 following generator request | GENERATOR
Athea - Knockanure | Athea AH1 | Cable Insp. 110kV XLPE (Knockanure) | 901129103 | Yes | TO-20-ATE-KNR-1-01 | August | 4 days | N/A | N/A | N/A | No | Work item was deferred to 2021 following generator request | Yes | Work item was deferred to 2021 following generator request | GENERATOR | No | N/A | N/A | Yes | Work item was deferred to 2021 following generator request | GENERATOR | Yes | Work item was deferred to 2021 following generator request | GENERATOR | No | N/A | N/A | No | N/A | N/A | No | Work item was deferred to 2021 following generator request | GENERATOR
Athea - Knockanure | Athea AH1 | Cable Insp. 110kV XLPE (Athea) | 901129104 | Yes | TO-20-ATE-KNR-1-01 | August | 4 days | N/A | N/A | N/A | No | Work item was deferred to 2021 following generator request | Yes | Work item was deferred to 2021 following generator request | GENERATOR | No | N/A | N/A | Yes | Work item was deferred to 2021 following generator request | GENERATOR | Yes | Work item was deferred to 2021 following generator request | GENERATOR | No | N/A | N/A | No | N/A | N/A | No | Work item was deferred to 2021 following generator request | GENERATOR
Athea - Knockanure | Athea AH1 | 110kV SF6 Cubicle Operational Test | 901043731 | Yes | TO-20-ATE-KNR-1-01 | August | 4 days | N/A | N/A | N/A | No | Work item was deferred to 2021 following generator request | Yes | Work item was deferred to 2021 following generator request | GENERATOR | No | N/A | N/A | Yes | Work item was deferred to 2021 following generator request | GENERATOR | Yes | Work item was deferred to 2021 following generator request | GENERATOR | No | N/A | N/A | No | N/A | N/A | No | Work item was deferred to 2021 following generator request | GENERATOR
Athea 121 | Athea AH1 | Cable Insp. 110kV XLPE | 901129087 | Yes | TO-20-ATE-T121-01 | August | 2 days | N/A | 2020-08-24 | 2020-08-25 | Yes | N/A | No | N/A | N/A | No | N/A | N/A | Yes | Changed due to generator request | GENERATOR | Yes | Changed due to generator request | GENERATOR | No | N/A | N/A | Yes | Changed due to generator request | GENERATOR | Yes | N/A | N/A
Athea 121 | Athea AH1 | 110kV SF6 Cubicle Operational Test | 901043038 | Yes | TO-20-ATE-T121-01 | August | 2 days | N/A | 2020-08-24 | 2020-08-25 | Yes | N/A | No | N/A | N/A | No | N/A | N/A | Yes | Changed due to generator request | GENERATOR | Yes | Changed due to generator request | GENERATOR | No | N/A | N/A | Yes | Changed due to generator request | GENERATOR | Yes | N/A | N/A
Aughinish - Sealrock 3 | SK3 | Cable Insp. 110kV XLPE | 901129109 | Yes | TO-20-AUG-SK-3-01 | September | 3 days | N/A | 2020-07-20 | 2020-07-24 | Yes | N/A | Yes | Generator requested change to Committed Outage Programme as a result of COVID-19 restrictions | COVID | Yes | Work scope duration increased to 5 days at TAO request | TAO | No | N/A | N/A | No | N/A | N/A | No | N/A | N/A | Yes | Generator requested change to Committed Outage Programme as a result of COVID-19 restrictions | COVID | Yes | N/A | N/A
Aughinish - Sealrock 3 | SK3 | 110kV SF6 Cubicle Operational Test | 901129644 | Yes | TO-20-AUG-SK-3-01 | September | 3 days | N/A | 2020-07-20 | 2020-07-24 | Yes | N/A | Yes | Generator requested change to Committed Outage Programme as a result of COVID-19 restrictions | COVID | Yes | Work scope duration increased to 5 days at TAO request | TAO | No | N/A | N/A | No | N/A | N/A | No | N/A | N/A | Yes | Generator requested change to Committed Outage Programme as a result of COVID-19 restrictions | COVID | Yes | N/A | N/A
Boggeragh 110SA2 | Boggeragh BG2, Esk ES1 & Carraigcannon CD1 | 110kV Sect / Dist Operational Test | 901130115 | Yes | TO-20-BGH-110SA2-02 | May | 1 day | N/A | 2020-07-29 | 2020-07-31 | Yes | N/A | Yes | Original outage deferred due to COVID 19 restrictions | COVID | No | N/A | N/A | Yes | Original outage deferred due to COVID 19 restrictions | COVID | Yes | Original outage deferred due to COVID 19 restrictions | COVID | No | N/A | N/A | No | N/A | N/A | Yes | N/A | N/A
Boggeragh - Clashavoon | Boggeragh BG1, Boggeragh BG2, Esk ES1 & Carraigcannon CD1 | Cable Insp. 110kV XLPE | 901129114 | Yes | TO-20-BGH-CLA-1-02 | May | 3 days | N/A | 2020-07-29 | 2020-07-31 | Yes | N/A | Yes | Original outage deferred due to COVID 19 restrictions | COVID | No | N/A | N/A | Yes | Original outage deferred due to COVID 19 restrictions | COVID | Yes | Original outage deferred due to COVID 19 restrictions | COVID | No | N/A | N/A | No | N/A | N/A | Yes | N/A | N/A
Boggeragh - Clashavoon | Boggeragh BG1, Boggeragh BG2, Esk ES1 & Carraigcannon CD1 | O1- Hotspot Boggeragh CT T Phase. | 900989872 | Yes | TO-20-BGH-CLA-1-02 | May | 3 days | N/A | 2020-07-29 | 2020-07-31 | Yes | N/A | Yes | Original outage deferred due to COVID 19 restrictions | COVID | No | N/A | N/A | Yes | Original outage deferred due to COVID 19 restrictions | COVID | Yes | Original outage deferred due to COVID 19 restrictions | COVID | No | N/A | N/A | No | N/A | N/A | Yes | N/A | N/A
Boggeragh - Clashavoon | Boggeragh BG1, Boggeragh BG2, Esk ES1 & Carraigcannon CD1 | O1-Main ON sign in c.b. chassis is very | 900973236 | Yes | TO-20-BGH-CLA-1-02 | May | 3 days | N/A | 2020-07-29 | 2020-07-31 | Yes | N/A | Yes | Original outage deferred due to COVID 19 restrictions | COVID | No | N/A | N/A | Yes | Original outage deferred due to COVID 19 restrictions | COVID | Yes | Original outage deferred due to COVID 19 restrictions | COVID | No | N/A | N/A | No | N/A | N/A | Yes | N/A | N/A
Boggeragh T121 | Boggeragh BG1 | 110 kV Cubicle Op Test | 901157678 | No | TO-20-BGH-T121-02 | N/A | N/A | Added to outage following request from TAO to include | 2020-07-29 | 2020-07-31 | Yes | N/A | N/A | N/A | N/A | N/A | N/A | N/A | No | N/A | N/A | No | N/A | N/A | Yes | Added to outage following request from TAO to include | TAO | No | N/A | N/A | Yes | N/A | N/A
Bellacorick - Srahnakilly | Oweninny OY1 | Investigate failure to remotely operate Breaker - Bellacorrick-Srahnakilly | 901137803 | No | TO-20-BK-SKY-1-03 | N/A | N/A | TAO requested inclusion of works in season. Scheduled to overlap with opt test | 2020-07-14 | 2020-07-15 | Yes | N/A | N/A | N/A | N/A | N/A | N/A | N/A | No | N/A | N/A | No | N/A | N/A | Yes | TAO requested inclusion of works in season. Scheduled to overlap with opt test | TAO | No | N/A | N/A | Yes | N/A | N/A
Bellacorick - Srahnakilly | Oweninny OY1 | 110kV Operational Test - Bellacorick Srahnakilly both ends | 901129688 | No | TO-20-BK-SKY-1-03 | N/A | N/A | Scheduled in season by the TSO as item was incorrectly not included in Ex Ante report. TAO requested works to overlap with parallel low voltage works ensuring windfarm was only offloaded once | 2020-07-14 | 2020-07-15 | Yes | N/A | N/A | N/A | N/A | N/A | N/A | N/A | No | N/A | N/A | No | N/A | N/A | Yes | Scheduled in season by the TSO as item was incorrectly not included in Ex Ante report. TAO requested works to overlap with parallel low voltage works ensuring windfarm was only offloaded once | TSO | No | N/A | N/A | Yes | N/A | N/A
Booltiagh T121 | Booltiagh 1 & 2 WF | 110kV SF6 Cubicle Ordinary Service | 901129964 | Yes | TO-20-BOL-T121-01 | July | 4 days | N/A | 2020-07-20 | 2020-07-23 | Yes | N/A | No | N/A | N/A | No | N/A | N/A | No | N/A | N/A | No | N/A | N/A | No | N/A | N/A | No | N/A | N/A | Yes | N/A | N/A
Ballyvouskil - Coomataggart | Cleanrath YT1, Grousemount GD1 | Cable Insp. 110kV XLPE | 901132973 | No | TO-20-BVK-COT-1-01 | N/A | N/A | Scheduled in season by the TSO as requirement for inspection post EI in 2019 was incorrectly not included in Ex-Ante report. Work to be split between 2020 and 2021 due to length of cable. | 2020-09-28 | 2020-10-02 | Yes | N/A | N/A | N/A | N/A | N/A | N/A | N/A | No | N/A | N/A | No | N/A | N/A | Yes | Scheduled in season by the TSO as requirement for inspection post EI in 2019 was not included in Ex-Ante report. Work to be split between 2020 and 2021 due to length of cable. | TSO | No | N/A | N/A | Yes | N/A | N/A
Ballywater - Crane | Ballywater WF | P2 Protection maintenance of 7SA513 | Protection | Yes | TO-20-BWR-CRA-1-01 | August | 1 day | N/A | 2020-06-02 | 2020-06-02 | Yes | N/A | Yes | Changed due to generator request | GENERATOR | No | N/A | N/A | No | N/A | N/A | No | N/A | N/A | No | N/A | N/A | No | N/A | N/A | Yes | N/A | N/A
Ballywater - Crane | Ballywater WF | 110kV SF6 Cubicle Operational Test | 901129684 | Yes | TO-20-BWR-CRA-1-01 | August | 1 day | N/A | 2020-06-02 | 2020-06-02 | Yes | N/A | Yes | Changed due to generator request | GENERATOR | No | N/A | N/A | No | N/A | N/A | No | N/A | N/A | No | N/A | N/A | No | N/A | N/A | Yes | N/A | N/A
Ballynahulla - Cordal | Cordal 1 DL1, Cordal 2 DL2, Scartaglen 1 ST1, Scartaglen 2 ST2, Coollegrean OG1 | Insp. 110kV Feeder XLPE Cable | 901006625 | Yes | TO-20-BYH-CDL-1-01 | May | 2 days | N/A | 2020-08-11 | 2020-08-13 | Yes | N/A | Yes | Rescheduled as TAO crews were unable to travel due to COVID restrictions during initial indicative window | COVID | No | N/A | N/A | Yes | Rescheduled as TAO crews were unable to travel due to COVID restrictions during initial indicative window | COVID | Yes | Rescheduled as TAO crews were unable to travel due to COVID restrictions during initial indicative window | COVID | No | N/A | N/A | No | N/A | N/A | Yes | N/A | N/A
Ballynahulla - Cordal | Cordal 1 DL1, Cordal 2 DL2, Scartaglen 1 ST1, Scartaglen 2 ST2, Coollegrean OG1 | 110kV SF6 Cubicle Operational Test | 901129678 | Yes | TO-20-BYH-CDL-1-01 | May | 2 days | N/A | 2020-08-11 | 2020-08-13 | Yes | N/A | Yes | Rescheduled as TAO crews were unable to travel due to COVID restrictions during initial indicative window | COVID | No | N/A | N/A | Yes | Rescheduled as crews were unable to travel due to COVID restrictions during initial window | COVID | Yes | Rescheduled as TAO crews were unable to travel due to COVID restrictions during initial indicative window | COVID | No | N/A | N/A | No | N/A | N/A | Yes | N/A | N/A
Cloghboola SA1 | Cloghboola CL1 | 110kV SF6 Cubicle Operational Test | 900938714 | Yes | TO-20-CBA-110SA1-01 | April | 1 day | N/A | 2020-06-22 | 2020-06-23 | Yes | N/A | Yes | Original outage deferred due to COVID 19 restrictions | COVID | No | N/A | N/A | Yes | Original outage deferred due to COVID 19 restrictions | COVID | Yes | Original outage deferred due to COVID 19 restrictions | COVID | No | N/A | N/A | No | N/A | N/A | Yes | N/A | N/A
Cloghboola SA2 | Cloghaneleskirt 1 KI1, Glanaruddery 1 DA1, Glanaruddery 2 DA2, Glantaunyalkeen GC1 | 110kV SF6 Cubicle Operational Test | 900938714 | Yes | TO-20-CBA-110SA2-01 | April | 1 day | N/A | 2020-06-22 | 2020-06-23 | Yes | N/A | Yes | Original outage deferred due to COVID 19 restrictions | COVID | No | N/A | N/A | Yes | Original outage deferred due to COVID 19 restrictions | COVID | Yes | Original outage deferred due to COVID 19 restrictions | COVID | No | N/A | N/A | No | N/A | N/A | Yes | N/A | N/A
Cloghboola T131 | Cloghboola CL1 | 110kV SF6 Cubicle Operational Test | 901068541 | Yes | TO-20-CBA-T131-01 | April | 1 day | N/A | 2020-06-22 | 2020-06-23 | Yes | N/A | Yes | Original outage deferred due to COVID 19 restrictions | COVID | No | N/A | N/A | Yes | Original outage deferred due to COVID 19 restrictions | COVID | Yes | Original outage deferred due to COVID 19 restrictions | COVID | No | N/A | N/A | No | N/A | N/A | Yes | N/A | N/A
Cloghboola - Trien | Cloghboola CL1, Cloghaneleskirt 1 KI1, Glanaruddery 1 DA1, Glanaruddery 2 DA2, Glantaunyalkeen GC1 | Cable Insp. 110kV XLPE | 901129163 | Yes | TO-20-CBA-TRI-1-01 | April | 2 days | N/A | 2020-06-22 | 2020-06-23 | Yes | N/A | Yes | Original outage deferred due to COVID 19 restrictions | COVID | No | N/A | N/A | Yes | Original outage deferred due to COVID 19 restrictions | COVID | Yes | Original outage deferred due to COVID 19 restrictions | COVID | No | N/A | N/A | No | N/A | N/A | Yes | N/A | N/A
Cloghboola - Trien | Cloghboola CL1, Cloghaneleskirt 1 KI1, Glanaruddery 1 DA1, Glanaruddery 2 DA2, Glantaunyalkeen GC1 | 110kV SF6 Cubicle Operational Test | 901043718 | Yes | TO-20-CBA-TRI-1-01 | April | 2 days | N/A | 2020-06-22 | 2020-06-23 | Yes | N/A | Yes | Original outage deferred due to COVID 19 restrictions | COVID | No | N/A | N/A | Yes | Original outage deferred due to COVID 19 restrictions | COVID | Yes | Original outage deferred due to COVID 19 restrictions | COVID | No | N/A | N/A | No | N/A | N/A | Yes | N/A | N/A
Cloghboola - Trien | Cloghboola CL1, Cloghaneleskirt 1 KI1, Glanaruddery 1 DA1, Glanaruddery 2 DA2, Glantaunyalkeen GC1 | 110kV SF6 Cubicle Operational Test | 901050357 | Yes | TO-20-CBA-TRI-1-01 | April | 2 days | N/A | 2020-06-22 | 2020-06-23 | Yes | N/A | Yes | Original outage deferred due to COVID 19 restrictions | COVID | No | N/A | N/A | Yes | Original outage deferred due to COVID 19 restrictions | COVID | Yes | Original outage deferred due to COVID 19 restrictions | COVID | No | N/A | N/A | No | N/A | N/A | Yes | N/A | N/A
Castledockrell - Lodgewood | Castledockrell WF | P2 Protection maintenance of 7SA612 | Protection | Yes | TO-20-CDK-LWD-1-01 | July | 5 days | N/A | 2020-07-20 | 2020-07-24 | Yes | N/A | No | N/A | N/A | No | N/A | N/A | No | N/A | N/A | No | N/A | N/A | No | N/A | N/A | No | N/A | N/A | Yes | N/A | N/A
Castledockrell - Lodgewood | Castledockrell WF | 110kV SF6 Cubicle Ordinary Service | 901129863 | Yes | TO-20-CDK-LWD-1-01 | July | 5 days | N/A | 2020-07-20 | 2020-07-24 | Yes | N/A | No | N/A | N/A | No | N/A | N/A | No | N/A | N/A | No | N/A | N/A | No | N/A | N/A | No | N/A | N/A | Yes | N/A | N/A
Castledockrell - Lodgewood | Castledockrell WF | 110kV Cubicle Condition Assessment | 901129181 | Yes | TO-20-CDK-LWD-1-01 | July | 5 days | N/A | 2020-07-20 | 2020-07-24 | Yes | N/A | No | N/A | N/A | No | N/A | N/A | No | N/A | N/A | No | N/A | N/A | No | N/A | N/A | No | N/A | N/A | Yes | N/A | N/A
Cordal SA1 | Scartaglen 1 ST1, Scartaglen 2 ST2 & Coollegrean OG1 | 110kV Sect / Dist Operational Test | 901130105 | Yes | TO-20-CDL-110SA1-01 | May | 1 day | N/A | 2020-08-11 | 2020-08-13 | Yes | N/A | Yes | Rescheduled as TAO crews were unable to travel due to COVID restrictions during initial indicative window | COVID | No | N/A | N/A | Yes | Rescheduled as TAO crews were unable to travel due to COVID restrictions during initial indicative window | COVID | Yes | Rescheduled as TAO crews were unable to travel due to COVID restrictions during initial indicative window | COVID | No | N/A | N/A | No | N/A | N/A | Yes | N/A | N/A
Cordal SA2 | Scartaglen 1 ST1, Scartaglen 2 ST2 & Coollegrean OG1 | 110kV Sect / Dist Operational Test | 901146308 | Yes | TO-20-CDL-110SA2-01 | May | 1 day | N/A | 2020-08-11 | 2020-08-13 | Yes | N/A | Yes | Rescheduled as TAO crews were unable to travel due to COVID restrictions during initial indicative window | COVID | No | N/A | N/A | Yes | Rescheduled as TAO crews were unable to travel due to COVID restrictions during initial indicative window | COVID | Yes | Rescheduled as TAO crews were unable to travel due to COVID restrictions during initial indicative window | COVID | No | N/A | N/A | No | N/A | N/A | Yes | N/A | N/A
Cordal T132 | Cordal 1 DL1 & Cordal 2 DL2 | 110kV SF6 Cubicle Operational Test | 901118391 | Yes | TO-20-CDL-T132-01 | May | 3 days | N/A | 2020-08-13 | 2020-08-14 | Yes | N/A | Yes | Rescheduled as TAO crews were unable to travel due to COVID restrictions during initial indicative window | COVID | Yes | Changed as per generator request | GENERATOR | Yes | Rescheduled as TAO crews were unable to travel due to COVID restrictions during initial indicative window | COVID | Yes | Rescheduled as TAO crews were unable to travel due to COVID restrictions during initial indicative window | COVID | No | N/A | N/A | Yes | Changed as per generator request | GENERATOR | Yes | N/A | N/A
Cordal T132 | Cordal 1 DL1 & Cordal 2 DL2 | Repair replace bonding leads (damaged) | 901074069 | Yes | TO-20-CDL-T132-01 | May | 3 days | N/A | 2020-08-13 | 2020-08-14 | Yes | N/A | Yes | Rescheduled as TAO crews were unable to travel due to COVID restrictions during initial indicative window | COVID | Yes | Changed as per generator request | GENERATOR | Yes | Rescheduled as TAO crews were unable to travel due to COVID restrictions during initial indicative window | COVID | Yes | Rescheduled as TAO crews were unable to travel due to COVID restrictions during initial indicative window | COVID | No | N/A | N/A | Yes | Changed as per generator request | GENERATOR | Yes | N/A | N/A
Cordal T141 | Scartaglen 1 ST1, Scartaglen 2 ST2 & Coollegrean OG1 | 110kV SF6 Cubicle Operational Test | 901118392 | No | TO-20-CDL-T141-01 | N/A | N/A | Added to work scope at the request of TAO | 2020-08-11 | 2020-08-13 | Yes | N/A | N/A | N/A | N/A | N/A | N/A | N/A | No | N/A | N/A | No | N/A | N/A | Yes | Added to work scope at the request of TAO | TAO | No | N/A | N/A | Yes | N/A | N/A
Carrigadrohid T103 | LE3 | 110KV SF6 Cubicle Operational Test | 901129579 | Yes | TO-20-CD-T103-01 | July | 1 day | N/A | 2020-06-16 | 2020-06-26 | Yes | N/A | Yes | TSO realigned maintenance works so they overlapped with generator outage in the Committed Outage Programme | TSO | No | N/A | N/A | No | N/A | N/A | No | N/A | N/A | No | N/A | N/A | No | N/A | N/A | Yes | N/A | N/A
Corduff - Huntstown | Huntstown HN2 | Cable Insp. 220kV Feeder XLPE |  | Yes | TO-20-CDU-HN-1-01 | November | 5 days | N/A | N/A | N/A | No | Generator requested change to Committed Outage Programme as a result of COVID-19 restrictions | Yes | Generator requested change to Committed Outage Programme as a result of COVID-19 restrictions | COVID | No | N/A | N/A | Yes | Generator requested change to Committed Outage Programme as a result of COVID-19 restrictions | COVID | Yes | Generator requested change to Committed Outage Programme as a result of COVID-19 restrictions | COVID | No | N/A | N/A | Yes | Generator requested change to Committed Outage Programme as a result of COVID-19 restrictions | COVID | No | Generator requested change to Committed Outage Programme as a result of COVID-19 restrictions | COVID
Corderry - Garvagh | Garvagh 1 & 2 WF & Derrysallagh WF | 110kV SF6 Cubicle Operational Test | 901129706 | Yes | TO-20-CDY-GRV-1-01 | July | 3 days | N/A | 2020-07-13 | 2020-07-15 | Yes | N/A | No | N/A | N/A | No | N/A | TAO | No | N/A | N/A | No | N/A | N/A | No | N/A | N/A | No | N/A | N/A | Yes | N/A | N/A
Corderry - Garvagh | Garvagh 1 & 2 WF & Derrysallagh WF | Leak detection on CB & repair if required | 901129384 | Yes | TO-20-CDY-GRV-1-01 | July | 3 days | N/A | 2020-07-13 | 2020-07-15 | Yes | N/A | No | N/A | N/A | No | N/A | TAO | No | N/A | N/A | No | N/A | N/A | No | N/A | N/A | No | N/A | N/A | Yes | N/A | N/A
Corderry - Garvagh | Garvagh 1 & 2 WF & Derrysallagh WF | Cable Insp. 110kV XLPE | 901129145 | Yes | TO-20-CDY-GRV-1-01 | July | 3 days | N/A | 2020-07-13 | 2020-07-15 | Yes | N/A | No | N/A | N/A | No | N/A | TAO | No | N/A | N/A | No | N/A | N/A | No | N/A | N/A | No | N/A | N/A | Yes | N/A | N/A
Cathaleens Fall - Cliff | Erne ER1 & ER2 | P3 Protection maintenance of 7SA511 | Protection | Yes | TO-20-CF-CL-1-01 | August | 1 day | N/A | N/A | N/A | No | TAO resourcing | Yes | TAO resourcing | TAO | No | N/A | N/A | Yes | TAO resourcing | TAO | Yes | TAO resourcing | TAO | No | N/A | N/A | No | N/A | N/A | No | TAO resourcing | TAO
Cathaleens Fall T103 | ER3 | 110KV SF6 Cubicle Ordinary Service | 901129790 | Yes | TO-20-CF-T103-01 | June | 4 days | N/A | 2020-06-29 | 2020-07-03 | Yes | N/A | No | N/A | N/A | Yes | Changed due to generator request | GENERATOR | Yes | Changed due to generator request | GENERATOR | No | N/A | N/A | No | N/A | N/A | Yes | Changed due to generator request | GENERATOR | Yes | N/A | N/A
COOMAGEARLAHY 110SA1 | Coomagearlahy 3 WF | O2.Sectionaliser not working from Mimic. | 900801826 | Yes | TO-20-CGL-110SA1-01 | June | 2 days | N/A | 2020-07-13 | 2020-07-15 | Yes | N/A | Yes | Changed as per generator request | GENERATOR | No | N/A | N/A | No | N/A | N/A | No | N/A | N/A | No | N/A | N/A | No | N/A | N/A | Yes | N/A | N/A
Glanlee - Coomagearlahy | Glanlee WF | CB operations counter not working. Repl | 900973584 | Yes | TO-20-CGL-GAE-1-01 | June | 3 days | N/A | 2020-07-13 | 2020-07-15 | Yes | N/A | Yes | Changed as per generator request | GENERATOR | No | N/A | N/A | No | N/A | N/A | No | N/A | N/A | No | N/A | N/A | No | N/A | N/A | Yes | N/A | N/A
Glanlee - Coomagearlahy | Glanlee WF | 110kV SF6 Cubicle Operational Test | 901129700 | Yes | TO-20-CGL-GAE-1-01 | June | 3 days | N/A | 2020-07-13 | 2020-07-15 | Yes | N/A | Yes | Changed as per generator request | GENERATOR | No | N/A | N/A | No | N/A | N/A | No | N/A | N/A | No | N/A | N/A | No | N/A | N/A | Yes | N/A | N/A
Coomagearlahy T121 | Coomagearlahy 3 WF | 110kV SF6 Cubicle Operational Test | 901129701 | Yes | TO-20-CGL-T121-01 | June | 1 day | N/A | 2020-07-13 | 2020-07-16 | Yes | N/A | Yes | Changed as per generator request | GENERATOR | Yes | Generator requested additional time to complete works | GENERATOR | Yes | Generator requested additional time to complete works | GENERATOR | No | N/A | N/A | No | N/A | N/A | Yes | Generator requested additional time to complete works | GENERATOR | Yes | N/A | N/A
Coomagearlahy T122 | Coomagearlahy 1 & 2 WF | 110kV SF6 Cubicle Operational Test | 901129699 | Yes | TO-20-CGL-T122-01 | June | 1 day | N/A | 2020-07-13 | 2020-07-15 | Yes | N/A | Yes | Changed as per generator request | GENERATOR | No | N/A | N/A | No | N/A | N/A | No | N/A | N/A | No | N/A | N/A | No | N/A | N/A | Yes | N/A | N/A
Clonkeen - Coomagearlahy | Coomagearlahy 3 WF | 110kV SF6 Cubicle Operational Test | 901129658 | Yes | TO-20-CKN-CGL-1-01 | June | 3 days | N/A | 2020-07-13 | 2020-07-15 | Yes | N/A | Yes | Changed as per generator request | GENERATOR | No | N/A | N/A | No | N/A | N/A | No | N/A | N/A | No | N/A | N/A | No | N/A | N/A | Yes | N/A | N/A
Clonkeen - Coomagearlahy | Coomagearlahy 3 WF | 110kV SF6 Cubicle Operational Test | 901129698 | Yes | TO-20-CKN-CGL-1-01 | June | 3 days | N/A | 2020-07-13 | 2020-07-15 | Yes | N/A | Yes | Changed as per generator request | GENERATOR | No | N/A | N/A | No | N/A | N/A | No | N/A | N/A | No | N/A | N/A | No | N/A | N/A | Yes | N/A | N/A
Clogher - Mulreavy | Mulreavy MB1, Mulreavy MB2 | Cable Insp. 110kV XLPE | 901129091 | Yes | TO-20-CLO-MRY-1-01 | July | 2 days | N/A | N/A | N/A | No | Generator requested a postponement of works to late in 2020 following communication of July outage - Generator had already arranged their annual works in advance of transmission works being confirmed. After review, it was decided by TSO to reschedule outage to 2021. | Yes | Generator requested a postponement of works to late in 2020 following communication of July outage - Generator had already arranged their annual works in advance of transmission works being confirmed. After review, it was decided by TSO to reschedule outage to 2021. | GENERATOR | No | N/A | N/A | Yes | Generator requested a postponement of works to late in 2020 following communication of July outage - Generator had already arranged their annual works in advance of transmission works being confirmed. After review, it was decided by TSO to reschedule outage to 2021. | GENERATOR | Yes | Generator requested a postponement of works to late in 2020 following communication of proposed July outage - Generator had already arranged their annual works in advance of transmission works being confirmed. After review, it was decided by TSO to reschedule outage to 2021. | GENERATOR | No | N/A | N/A | No | N/A | N/A | No | Generator requested a postponement of works to late in 2020 following communication of July outage - Generator had already arranged their annual works in advance of transmission works being confirmed. After review, it was decided by TSO to reschedule outage to 2021. | GENERATOR
Cliff T101 | ER1 | 110KV SF6 Cubicle Operational Test | 901129648 | Yes | TO-20-CL-T101-01 | August | 1 day | N/A | 2020-06-08 | 2020-06-21 | Yes | N/A | Yes | Rescheduled by TSO to align with generator outage in Committed Outage Programme | TSO | No | N/A | N/A | No | N/A | N/A | No | N/A | N/A | No | N/A | N/A | No | N/A | N/A | Yes | N/A | N/A
Cliff T102 | Erne ER2 | P2 Protection maintenance of 7SJ511 | Protection | Yes | TO-20-CL-T102-01 | August | 1 day | N/A | 2020-08-25 | 2020-08-28 | Yes | N/A | No |  | No Change | Yes | TAO required extra time to resource and complete protection maintenance | TAO | Yes | TAO required extra time to resource and complete protection maintenance | TAO | Yes | TAO required extra time to resource and complete protection maintenance | TAO | No | N/A | N/A | No | N/A | N/A | Yes | N/A | N/A
Cliff T102 | Erne ER2 | 110KV SF6 Cubicle Operational Test | 901129649 | Yes | TO-20-CL-T102-01 | August | 1 day | N/A | 2020-08-25 | 2020-08-28 | Yes | N/A | No |  | No Change | Yes | TAO required extra time to resource and complete protection maintenance | TAO | Yes | TAO required extra time to resource and complete protection maintenance | TAO | Yes | TAO required extra time to resource and complete protection maintenance | TAO | No | N/A | N/A | No | N/A | N/A | Yes | N/A | N/A
Coolnanoonagh - Kilpaddoge | Kelwin WF | Annual Insp. 110kV Feeder XLPE Cable | 901076134 | Yes | TO-20-CNO-KPG-1-01 | May | 2 days | N/A | N/A | N/A | Completed in Previous Outage Season | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed in Previous Outage Season | Completed in Previous Outage Season | TAO | N/A | N/A | N/A | N/A | N/A | N/A
Cunghill T121 | Kingsmountain KG2 | P1 Protection maintenance of 7SA513 | Protection | Yes | TO-20-CUN-T121-01 | June | 2 days | N/A | 2020-06-16 | 2020-06-17 | Yes | N/A | No | N/A | N/A | No | N/A | N/A | No | N/A | N/A | No | N/A | N/A | No | N/A | N/A | No | N/A | N/A | Yes | N/A | N/A
Cunghill T121 | Kingsmountain KG2 | 110kV SF6 Cubicle Operational Test | 901151354 | No | TO-20-CUN-T121-01 | N/A | N/A | Added by TAO in advance of works starting | 2020-06-16 | 2020-06-17 | Yes | N/A | N/A | N/A | N/A | N/A | N/A | N/A | No | N/A | N/A | No | N/A | N/A | Yes | Added by TAO in advance of works starting | TAO | No | N/A | N/A | Yes | N/A | N/A
Cunghill T121 | Kingsmountain KG2 | 7SV512 CBF relay - has been found to be faulty and needs to be replaced | Protection | No | TO-20-CUN-T121-01 | N/A | N/A | Relay was found to be faulty by TAO crew so was replaced during outage | 2020-06-16 | 2020-06-17 | Yes | N/A | N/A | N/A | N/A | N/A | N/A | N/A | No | N/A | N/A | No | N/A | N/A | Yes | Relay was found to be faulty by TAO crew so was replaced during outage | TAO | No | N/A | N/A | Yes | N/A | N/A
Cushaling - Mountlucas | Mountlucas WF | 110kV SF6 Cubicle Operational Test- Cushaling | 901130485 | Yes | TO-20-CUS-MLC-1-01 | June | 2 days | N/A | 2020-06-09 | 2020-06-10 | Yes | N/A | No | N/A | N/A | No | N/A | N/A | No | N/A | N/A | No | N/A | N/A | No | N/A | N/A | No | N/A | N/A | Yes | N/A | N/A
Cushaling - Mountlucas | Mountlucas WF | 110kV SF6 Cubicle Operational Test - Mountlucas | 901129680 | Yes | TO-20-CUS-MLC-1-01 | June | 2 days | N/A | 2020-06-09 | 2020-06-10 | Yes | N/A | No | N/A | N/A | No | N/A | N/A | No | N/A | N/A | No | N/A | N/A | No | N/A | N/A | No | N/A | N/A | Yes | N/A | N/A
Cushaling T101 | Edenderry ED1 | 110kV SF6 Cubicle Operational Test |  | Yes | TO-20-CUS-T101-01 | April | 1 day | N/A | 2020-07-07 | 2020-07-07 | Yes | N/A | Yes | Generator requested change to Committed Outage Programme as a result of COVID-19 restrictions | COVID | No | N/A | N/A | Yes | Generator requested change to Committed Outage Programme as a result of COVID-19 restrictions | COVID | Yes | Generator requested change to Committed Outage Programme as a result of COVID-19 restrictions | COVID | No | N/A | N/A | Yes | Generator requested change to Committed Outage Programme as a result of COVID-19 restrictions | COVID | Yes | N/A | N/A
Cushaling T103/T105 | Edenderry ED3/ED5 | 110kV SF6 Cubicle Operational Test | 901129669 | Yes | TO-20-CUS-T103/5-01 | April | 1 day | N/A | 2020-11-19 | 2020-11-19 | Yes | N/A | Yes | Generator requested change to Committed Outage Programme as a result of COVID-19 restrictions | COVID | No | N/A | N/A | No | N/A | N/A | No | N/A | N/A | No | N/A | N/A | Yes | Generator requested change to Committed Outage Programme as a result of COVID-19 restrictions | COVID | Yes | N/A | N/A
Derryiron Rhode T1/T2 | Rhode RP1 & RP2 | P2 Protection maintenance of 7SA513 |  | Yes | TO-20-DER-T1/T2-02 | June | 1 day | N/A | N/A | N/A | No | No Generator outage in Committed Outage Programme so rather than offload generator works were deferred to 2021 | Yes | No Generator outage in Committed Outage Programme so rather than offload generator works were deferred to 2021 | TSO | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | No | No Generator outage in Committed Outage Programme so rather than offload generator works were deferred to 2021 | TSO
Derryiron Rhode T1/T2 | Rhode RP1 & RP2 | 110KV SF6 Cubicle Operational Test |  | Yes | TO-20-DER-T1/T2-02 | June | 1 day | N/A | N/A | N/A | No | No Generator outage in Committed Outage Programme so rather than offload generator works were deferred to 2021 | Yes | No Generator outage in Committed Outage Programme so rather than offload generator works were deferred to 2021 | TSO | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | No | No Generator outage in Committed Outage Programme so rather than offload generator works were deferred to 2021 | TSO
Drumkeen - Meentycat | Meentycat MCT | P1 Protection maintenance of 7SA513 | Protection | Yes | TO-20-DRM-MEE-1-01 | October | 5 days | N/A | 2020-09-14 | 2020-09-18 | Yes | N/A | Yes | Changed as per generator request | GENERATOR | No | N/A | N/A | Yes | TAO resourcing | TAO | Yes | TAO resourcing | TAO | No | N/A | N/A | Yes | TAO resourcing | TAO | Yes | N/A | N/A
Drumkeen - Meentycat | Meentycat MCT | 110kV SF6 Cubicle Ordinary Service - Drumkeen Stn | 901129892 | Yes | TO-20-DRM-MEE-1-01 | October | 5 days | N/A | 2020-09-14 | 2020-09-18 | Yes | N/A | Yes | Changed as per generator request | GENERATOR | No | N/A | N/A | Yes | TAO resourcing | TAO | Yes | TAO resourcing | TAO | No | N/A | N/A | Yes | TAO resourcing | TAO | Yes | N/A | N/A
Drumkeen - Meentycat | Meentycat MCT | 110kV SF6 Cubicle Ordinary Service - Meentycat Stn | 901129894 | Yes | TO-20-DRM-MEE-1-01 | October | 5 days | N/A | 2020-09-14 | 2020-09-18 | Yes | N/A | Yes | Changed as per generator request | GENERATOR | No | N/A | N/A | Yes | TAO resourcing | TAO | Yes | TAO resourcing | TAO | No | N/A | N/A | Yes | TAO resourcing | TAO | Yes | N/A | N/A
Dromada T121 | Dromada DR1 | 110KV CUBICLE CONDITION ASSESSMENT | 901038511 | Yes | TO-20-DRO-T121-01 | August | 5 days | N/A | 2020-08-24 | 2020-08-28 | Yes | N/A | No | N/A | N/A | No | N/A | N/A | Yes | Changed due to generator request | GENERATOR | Yes | Changed due to generator request | GENERATOR | No | N/A | N/A | No | N/A | N/A | Yes | N/A | N/A
Dromada T121 | Dromada DR1 | 110kV SF6 Cubicle Ordinary Service | 901042263 | Yes | TO-20-DRO-T121-01 | August | 5 days | N/A | N/A | N/A | Completed in Previous Outage Season | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed in Previous Outage Season | Completed in Previous Outage Season | TAO | N/A | N/A | N/A | N/A | N/A | N/A
Ennis - Slievecallan | Knockalassa WF & Boolinrudda WF | Hot spot repair: S Phase Ennis 110kv Cubicle. S Phase cable end bushing connection | 901134796 | No | TO-20-ENN-SLC-1-01 | N/A | N/A | Works added by TAO in season | 2020-07-13 | 2020-07-17 | Yes | N/A | N/A | N/A | N/A | N/A | N/A | N/A | No | N/A | N/A | No | N/A | N/A | Yes | Works added by TAO in season | TAO | No | N/A | N/A | Yes | N/A | N/A
Ennis - Slievecallan | Knockalassa WF & Boolinrudda WF | R & S Phases Ennis 110kV cubicle. R & S Phase DL/DE | 901134797 | No | TO-20-ENN-SLC-1-01 | N/A | N/A | Works added by TAO in season | 2020-07-13 | 2020-07-17 | Yes | N/A | N/A | N/A | N/A | N/A | N/A | N/A | No | N/A | N/A | No | N/A | N/A | Yes | Works added by TAO in season | TAO | No | N/A | N/A | Yes | N/A | N/A
Ennis - Slievecallan | Knockalassa WF & Boolinrudda WF | Hot spot repair: S Phase SlieveCallan 110kv Cubicle, S phase Cable End Bushing Connection | 901134782 | No | TO-20-ENN-SLC-1-02 | N/A | N/A | Works added by TAO in season | 2020-07-13 | 2020-07-17 | Yes | N/A | N/A | N/A | N/A | N/A | N/A | N/A | No | N/A | N/A | No | N/A | N/A | Yes | Works added by TAO in season | TAO | No | N/A | N/A | Yes | N/A | N/A
Finglas - Huntstown | Huntstown HNC | Replace CB counter/ complete CA on VT's & SA's | 901076401 | Yes | TO-20-FIN-HN-1-02 | August | 3 days | N/A | 2020-09-22 | 2020-11-21 | Yes | N/A | Yes | Generator requested change to Committed Outage Programme as a result of COVID-19 restrictions | COVID | No | N/A | N/A | No | N/A | N/A | No | N/A | No Change | No | N/A | N/A | Yes | Generator requested change to Committed Outage Programme as a result of COVID-19 restrictions | COVID | Yes | N/A | N/A
Finglas - Huntstown | Huntstown HNC | T Phase Hotspot on T phase DL/DE disconnect | 901128554 | No | TO-20-FIN-HN-1-02 | N/A | N/A | Hotspot identified by TAO in advance of outage | 2020-09-22 | 2020-11-21 | Yes | N/A | N/A | N/A | N/A | N/A | N/A | N/A | No | N/A | N/A | No | N/A | N/A | Yes | Hotspot identified by TAO in advance of outage | TAO | Yes | Generator requested change to Committed Outage Programme as a result of COVID-19 restrictions | COVID | Yes | N/A | N/A
Glanlee T121 | Glanlee WF | 110kV SF6 Cubicle Operational Test | 901129611 | Yes | TO-20-GAE-T121-01 | June | 1 day | N/A | 2020-07-13 | 2020-07-15 | Yes | N/A | Yes | Changed as per generator request | GENERATOR | No | N/A | N/A | No | N/A | N/A | No | N/A | N/A | No | N/A | N/A | No | N/A | N/A | Yes | N/A | N/A
Glanlee T121 | Glanlee WF | AC and DC Supplies: | 900973585 | Yes | TO-20-GAE-T121-01 | June | 1 day | N/A | 2020-07-13 | 2020-07-15 | Yes | N/A | Yes | Changed as per generator request | GENERATOR | No | N/A | N/A | No | N/A | N/A | No | N/A | N/A | No | N/A | N/A | No | N/A | N/A | Yes | N/A | N/A
Glanagow T2001 | Whitegate WG1 | Cable Insp. 400 & 220kV Feeder XLPE |  | Yes | TO-20-GGO-T2001-02 | August | 2 days | N/A | 2020-08-26 | 2020-08-26 | Yes | N/A | No | N/A | N/A | Yes | TAO completed work quicker than anticipated | TAO | Yes | Generator requested change to Committed Outage Programme | GENERATOR | Yes | Generator requested change to Committed Outage Programme | GENERATOR | No | N/A | N/A | Yes | Generator requested change to Committed Outage Programme | GENERATOR | Yes | N/A | N/A
Glanagow T2001 | Whitegate WG1 | O1- T2001 Protection Maintenance | 900951244 | Yes | TO-20-GGO-T2001-02 | August | 2 days | N/A | 2020-08-26 | 2020-08-26 | Yes | N/A | No | N/A | N/A | Yes | TAO completed work quicker than anticipated | TAO | Yes | Generator requested change to Committed Outage Programme | GENERATOR | Yes | Generator requested change to Committed Outage Programme | GENERATOR | No | N/A | N/A | Yes | Generator requested change to Committed Outage Programme | GENERATOR | Yes | N/A | N/A
Great Island GIS T2004 | Great Island GI4 | P3 Protection maintenance of 7SA612 | Protection | Yes | TO-20-GI GIS-T2004-01 | October | 1 days | N/A | N/A | N/A | No | Work not done due to TAO resourcing constraints | Yes | Work not done due to TAO resourcing constraints | TAO | No | N/A | N/A | Yes | Work not done due to TAO resourcing constraints | TAO | Yes | Work not done due to TAO resourcing constraints | TAO | No | N/A | N/A | Yes | Generator requested change to Committed Outage Programme | GENERATOR | No | Work not done due to TAO resourcing constraints | TAO
Glenlara - Knockacummer | Knockacummer KC1 | Cable Insp. 110kV XLPE | 901129175 | Yes | TO-20-GLE-KCR-1-01 | August | 5 days | N/A | N/A | N/A | No | Work was deferred by TAO due to incoming Storm Ellen | Yes | Work was deferred by TAO due to incoming Storm Ellen | TAO | No | N/A | N/A | Yes | Work was deferred by TAO due to incoming Storm Ellen | TAO | Yes | Work was deferred by TAO due to incoming Storm Ellen | TAO | No | N/A | N/A | No | N/A | N/A | No | Work was deferred by TAO due to incoming Storm Ellen | TAO
Glenlara - Knockacummer | Knockacummer KC1 | 110kV SF6 Cubicle Operational Test | 901129705 (KCR) | Yes | TO-20-GLE-KCR-1-01 | August | 5 days | N/A | N/A | N/A | No | Work was deferred by TAO due to incoming Storm Ellen | Yes | Work was deferred by TAO due to incoming Storm Ellen | TAO | No | N/A | N/A | Yes | Work was deferred by TAO due to incoming Storm Ellen | TAO | Yes | Work was deferred by TAO due to incoming Storm Ellen | TAO | No | N/A | N/A | No | N/A | N/A | No | Work was deferred by TAO due to incoming Storm Ellen | TAO
Glenlara - Knockacummer | Knockacummer KC1 | 110kV SF6 Cubicle Operational Test | 901095021 (GLE) | Yes | TO-20-GLE-KCR-1-01 | August | 5 days | N/A | N/A | N/A | No | Work was deferred by TAO due to incoming Storm Ellen | Yes | Work was deferred by TAO due to incoming Storm Ellen | TAO | No | N/A | N/A | Yes | Work was deferred by TAO due to incoming Storm Ellen | TAO | Yes | Work was deferred by TAO due to incoming Storm Ellen | TAO | No | N/A | N/A | No | N/A | N/A | No | Work was deferred by TAO due to incoming Storm Ellen | TAO
Garrow SA1 | Coomacheo CZ1 | 110kV Sect / Dist Operational Test on SA1 | 901130110 | No | TO-20-GRO-110-SA1-2-CB-01 | N/A | N/A | Works added by TAO in days leading up to outage | 2020-06-23 | 2020-06-25 | Yes | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Yes | IPP requested extension of outage to complete their own works | GENERATOR | No | N/A | N/A | Yes | Works added by TAO in days leading up to outage | TAO | Yes | IPP requested extension of outage to complete their own works | GENERATOR | Yes | N/A | N/A
Garrow SA2 | Coomacheo CZ1 | 110kV Sect / Dist Operational Test on SA2 | 901130111 | No | TO-20-GRO-110-SA1-2-CB-01 | N/A | N/A | Works added by TAO in days leading up to outage | 2020-06-23 | 2020-06-25 | Yes | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Yes | IPP requested extension of outage to complete their own works | GENERATOR | No | N/A | N/A | Yes | Works added by TAO in days leading up to outage | TAO | Yes | IPP requested extension of outage to complete their own works | GENERATOR | Yes | N/A | N/A
Garrow SA1/SA2 | Coomacheo CZ1 | 110kV SF6 Cubicle Operational Test on Sect CB | 901129711 | No | TO-20-GRO-110-SA1-2-CB-01 | N/A | N/A | Works added by TAO in days leading up to outage | 2020-06-23 | 2020-06-25 | Yes | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Yes | IPP requested extension of outage to complete their own works | GENERATOR | No | N/A | N/A | Yes | Works added by TAO in days leading up to outage | TAO | Yes | IPP requested extension of outage to complete their own works | GENERATOR | Yes | N/A | N/A
Garrow T122 | Coomacheo CZ1 | 110kV SF6 Cubicle Operational Test | 901129713 | Yes | TO-20-GRO-T122-01 | June | 1 day | N/A | 2020-06-23 | 2020-06-25 | Yes | N/A | No | N/A | No Change | Yes | TSO requested extra day for system reasons | TSO | Yes | IPP requested extension of outage to complete their own works | GENERATOR | Yes | TSO requested extra day for system reasons | TSO | No | N/A | N/A | Yes | IPP requested extension of outage to complete their own works | GENERATOR | Yes | N/A | N/A
Garvagh T121 | Garvagh 1 & 2 WF | 110kV SF6 Cubicle Ordinary Service | 901129861 EI in 2018 not required in 2020 - PWI 07Jul2020 | Yes | TO-20-GRV-T121-01 | July | 5 days | N/A | N/A | N/A | No | EI took place in 2018 so TAO requested cancellation of Ordinary Service as not due until 2022. Work reduced from 5 days to 3 days as a result | No | N/A | N/A | Yes | Change to work scope allowed TAO to complete work quicker than anticipated | TAO | Yes | Change to work scope allowed TAO to complete work quicker than anticipated | TAO | Yes | Change to work scope allowed TAO to complete work quicker than anticipated | TAO | No | N/A | N/A | No | N/A | N/A | No | EI took place in 2018 so TAO requested cancellation of Ordinary Service as not due until 2022. Work reduced from 5 days to 3 days as a result | TAO
Garvagh T121 | Garvagh 1 & 2 WF | 110KV CUBICLE CONDITION ASSESSMENT | 901129190 | Yes | TO-20-GRV-T121-01 | July | 5 days | N/A | N/A | N/A | No | TAO requested postponement of work as Condition Assessment not due on cubicle in 2020. Work reduced from 5 days to 3 days as a result. | No | N/A | N/A | Yes | Change to work scope allowed TAO to complete work quicker than anticipated | TAO | Yes | Change to work scope allowed TAO to complete work quicker than anticipated | TAO | Yes | Change to work scope allowed TAO to complete work quicker than anticipated | TAO | No | N/A | N/A | No | N/A | N/A | No | TAO requested postponement of work as Condition Assessment not due on cubicle in 2020. Work reduced from 5 days to 3 days as a result. | TAO
Garvagh T121 | Garvagh 1 & 2 WF | 110kV SF6 Cubicle Operational Test |  | No | TO-20-GRV-T121-01 | N/A | N/A | TAO requested to carry out an Opt Test instead of an Ordinary Service as Ordinary service not due in 2020 | 2020-07-13 | 2020-07-15 | Yes | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Yes | Change to work scope allowed TAO to complete work quicker than anticipated | TAO | Yes | Change to work scope allowed TAO to complete work quicker than anticipated | TAO | Yes | TAO requested to carry out an Opt Test instead of an Ordinary Service as Ordinary service not due in 2020 | TAO | No | N/A | N/A | Yes | N/A | N/A
Garvagh T121 | Garvagh 1 & 2 WF | Bird Nest Removal 2018HP-1[Am11]Bird Nests | 900985802 | No | TO-20-GRV-T121-01 | N/A | N/A | TAO requested addition of work item in days leading up to outage | 2020-07-13 | 2020-07-15 | Yes | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Yes | Change to work scope allowed TAO to complete work quicker than anticipated | TAO | Yes | Change to work scope allowed TAO to complete work quicker than anticipated | TAO | Yes | TAO requested addition of work item in days leading up to outage | TAO | No | N/A | N/A | Yes | N/A | N/A
Huntstown T2002 | Huntstown HN2 | 220kV SF6 Cubicle Ordinary Service | 901042455 | Yes | TO-20-HN-T2002-01 | July | 5 days | N/A | N/A | N/A | No | Due to difficulties in scheduling a full 5 days to accommodate ordinary service it was decided by TSO to defer this part of outage to 2021. Duration reduced to 2 days as a consequence | Yes | Due to difficulties in scheduling a full 5 days to accommodate ordinary service it was decided by TSO to defer this part of outage to 2021. Duration reduced to 2 days as a consequence | TSO | Yes | Due to difficulties in scheduling a full 5 days to accommodate ordinary service it was decided by TSO to defer this part of outage to 2021. Duration reduced to 2 days as a consequence | TSO | No | N/A | N/A | No | N/A | N/A | No | N/A | N/A | Yes | Generator requested change to Committed Outage Programme as a result of COVID-19 restrictions | COVID | No | Due to difficulties in scheduling a full 5 days to accommodate ordinary service it was decided by TSO to defer this part of outage to 2021. Duration reduced to 2 days as a consequence | TSO
Huntstown T2002 | Huntstown HN2 | Cable Insp. 400 & 220kV Feeder XLPE | 901129030 | Yes | TO-20-HN-T2002-01 | July | 5 days | N/A | 2020-09-02 | 2020-09-03 | Yes | N/A | Yes | Outage was postponed at short notice twice by TSO in July and August due to system conditions | TSO | Yes | Due to difficulties in scheduling a full 5 days to accommodate ordinary service it was decided by TSO to defer this part of outage to 2021. Duration reduced to 2 days as a consequence | TSO | Yes | Outage was postponed at short notice twice by TSO over July and August due to system conditions | TSO | Yes | Outage was postponed at short notice twice by TSO over July and August due to system conditions | TSO | No | N/A | N/A | Yes | Generator requested change to Committed Outage Programme as a result of COVID-19 restrictions | COVID | Yes | N/A | N/A
Huntstown T2010/11 | Huntstown HNC | Cable Insp. 400 & 220kV Feeder XLPE | 901005718 | Yes | TO-20-HN-T2010/11-02 | August | 2 days | N/A | N/A | N/A | Completed in Previous Outage Season | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed in Previous Outage Season | Completed in Previous Outage Season | TAO | N/A | N/A | N/A | N/A | N/A | N/A
Huntstown T2010/11 | Huntstown HNC | 220kV SF6 Cubicle Operational Test | 901129554 | Yes | TO-20-HN-T2010/11-02 | August | 2 days | N/A | 2020-09-21 | 2020-11-21 | Yes | N/A | Yes | Generator requested change to Committed Outage Programme as a result of COVID-19 restrictions | COVID | No | N/A | N/A | No | N/A | N/A | No | N/A | N/A | No | N/A | N/A | Yes | Generator requested change to Committed Outage Programme as a result of COVID-19 restrictions | COVID | Yes | N/A | N/A
Inniscarra T101 | LE1 | 110KV SF6 Cubicle Operational Test | 901129723 | Yes | TO-20-IA-T101-01 | April | 1 day | N/A | 2020-05-15 | 2020-05-20 | Yes | N/A | Yes | Generator requested change to Committed Outage Programme as a result of COVID-19 restrictions | COVID | No | N/A | N/A | No | N/A | N/A | No | N/A | N/A | No | N/A | N/A | Yes | Generator requested change to Committed Outage Programme as a result of COVID-19 restrictions | COVID | Yes | N/A | N/A
Inniscarra T101 | LE2 | 110KV SF6 Cubicle Operational Test | 901129723 | Yes | TO-20-IA-T101-01 | April | 1 day | N/A | 2020-05-15 | 2020-05-20 | Yes | N/A | Yes | Generator requested change to Committed Outage Programme as a result of COVID-19 restrictions | COVID | No | N/A | N/A | No | N/A | N/A | No | N/A | N/A | No | N/A | N/A | Yes | Generator requested change to Committed Outage Programme as a result of COVID-19 restrictions | COVID | Yes | N/A | N/A
Ikerrin - Thurles | Monaincha Bog WF | P3 Protection maintenance of 7SA612, GRZ100 | Protection | Yes | TO-20-IKE,T-THU-1-01 | August | 2 days | N/A | N/A | N/A | No | Works deferred by TSO as a result of network proximity to capital project at Dallow Tee | Yes | Works deferred by TSO as a result of network proximity to capital project at Dallow Tee | TSO | No | N/A | N/A | Yes | Works deferred by TSO as a result of network proximity to capital project at Dallow Tee | TSO | Yes | Works deferred by TSO as a result of network proximity to capital project at Dallow Tee | TSO | No | N/A | N/A | No | N/A | N/A | No | Works deferred by TSO as a result of network proximity to capital project at Dallow Tee | TSO
Ikerrin - Thurles | Monaincha Bog WF | 110kV MO Cubicle Operational Test |  | Yes | TO-20-IKE,T-THU-1-01 | August | 2 days | N/A | N/A | N/A | No | Works deferred by TSO as a result of network proximity to capital project at Dallow Tee | Yes | Works deferred by TSO as a result of network proximity to capital project at Dallow Tee | TSO | No | N/A | N/A | Yes | Works deferred by TSO as a result of network proximity to capital project at Dallow Tee | TSO | Yes | Works deferred by TSO as a result of network proximity to capital project at Dallow Tee | TSO | No | N/A | N/A | No | N/A | N/A | No | Works deferred by TSO as a result of network proximity to capital project at Dallow Tee | TSO
Irishtown T2001 | Dublin Bay DB1 | 110kV GIS Cubicle Ordinary Service |  | Yes | TO-20-ISH-T2001-01 | September | 5 days | N/A | N/A | N/A | No | Generator requested change to Committed Outage Programme as a result of COVID-19 restrictions. Works deferred to 2021 to overlap with rescheduled generator outage | Yes | Generator requested change to Committed Outage Programme as a result of COVID-19 restrictions. Works deferred to 2021 to overlap with rescheduled generator outage | COVID | No | N/A | N/A | No | N/A | N/A | No | N/A | N/A | No | N/A | N/A | Yes | Generator requested change to Committed Outage Programme as a result of COVID-19 restrictions. Works deferred to 2021 to overlap with rescheduled generator outage | COVID | No | Generator requested change to Committed Outage Programme as a result of COVID-19 restrictions. Works deferred to 2021 to overlap with rescheduled generator outage | COVID
Irishtown T2001 | Dublin Bay DB1 | 220kV Cubicle Condition Assessment |  | Yes | TO-20-ISH-T2001-01 | September | 5 days | N/A | N/A | N/A | No | Generator requested change to Committed Outage Programme as a result of COVID-19 restrictions. Works deferred to 2021 to overlap with rescheduled generator outage | Yes | Generator requested change to Committed Outage Programme as a result of COVID-19 restrictions. Works deferred to 2021 to overlap with rescheduled generator outage | COVID | No | N/A | N/A | No | N/A | N/A | No | N/A | N/A | No | N/A | N/A | Yes | Generator requested change to Committed Outage Programme as a result of COVID-19 restrictions. Works deferred to 2021 to overlap with rescheduled generator outage | COVID | No | Generator requested change to Committed Outage Programme as a result of COVID-19 restrictions. Works deferred to 2021 to overlap with rescheduled generator outage | COVID
Irishtown T2001 | Dublin Bay DB1 | Cable Insp. 400 & 220kV Feeder XLPE |  | Yes | TO-20-ISH-T2001-01 | September | 5 days | N/A | N/A | N/A | No | Generator requested change to Committed Outage Programme as a result of COVID-19 restrictions. Works deferred to 2021 to overlap with rescheduled generator outage | Yes | Generator requested change to Committed Outage Programme as a result of COVID-19 restrictions. Works deferred to 2021 to overlap with rescheduled generator outage | COVID | No | N/A | N/A | No | N/A | N/A | No | N/A | N/A | No | N/A | N/A | Yes | Generator requested change to Committed Outage Programme as a result of COVID-19 restrictions. Works deferred to 2021 to overlap with rescheduled generator outage | COVID | No | Generator requested change to Committed Outage Programme as a result of COVID-19 restrictions. Works deferred to 2021 to overlap with rescheduled generator outage | COVID
Kill Hill T131 | Kill Hill KH1 | 110kV SF6 Cubicle Ordinary Service | 901129925 | Yes | TO-20-KHL-T131-01 | September | 4 days | N/A | 2020-09-01 | 2020-09-04 | Yes | N/A | No | N/A | N/A | No | N/A | N/A | No | N/A | N/A | No | N/A | N/A | No | N/A | N/A | No | N/A | N/A | Yes | N/A | N/A
Knockranny - Uggool | Uggool UG1 & Seecon SO1 | 110kV GIS Cubicle Operational Test | 901129520 | Yes | TO-20-KNY-UGL-1-01 | April | 2 days | N/A | 2020-09-08 | 2020-09-08 | Yes | N/A | Yes | Original outage deferred due to COVID 19 restrictions | COVID | Yes | TAO completed works quicker than anticipated | TAO | Yes | TAO requested change: Circuit op test completed as stand alone item on 8th September | TAO | No | N/A | N/A | No | N/A | N/A | Yes | Changed as per generator request | GENERATOR | Yes | N/A | N/A
Lanesboro T104 | Lough Ree LR4 | Cable Insp. 110kV XLPE | 901129120 | Yes | TO-20-LA-T104-01 | August | 2 days | N/A | N/A | N/A | Completed in Previous Outage Season | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed in Previous Outage Season | Completed in Previous Outage Season | TAO | N/A | N/A | N/A | N/A | N/A | N/A
Longpoint T2002 | AD2 | Cable Insp. 400 & 220kV Feeder XLPE | 901129012 | Yes | TO-20-LPT-T2002-01 | July | 2 days | N/A | 2020-07-19 | 2020-07-24 | Yes | N/A | No | N/A | N/A | Yes | Work completed a day early by TAO | TAO | Yes | Work completed a day early by TAO | TAO | Yes | Application of extra designated days after TAO advised of further transmission maintenance | TAO | No | N/A | N/A | No | N/A | N/A | Yes | N/A | N/A
Longpoint T2002 | AD2 | 2200kV SF6 Cubicle Operational Test | 901129732 | Yes | TO-20-LPT-T2002-01 | July | 2 days | N/A | 2020-07-19 | 2020-07-24 | Yes | N/A | No | N/A | N/A | Yes | Work completed a day early by TAO | TAO | Yes | Work completed a day early by TAO | TAO | Yes | Application of extra designated days after TAO advised of further transmission maintenance | TAO | No | N/A | N/A | No | N/A | N/A | Yes | N/A | N/A
Lisheen T122 | Lisheen 1 & 2 WF | 110kV SF6 Cubicle Operational Test | 901129653 | Yes | TO-20-LSN-T122-01 | October | 1 day | N/A | 2020-07-06 | 2020-07-07 | Yes | N/A | Yes | Generator requested change | GENERATOR | No | N/A | N/A | No | N/A | N/A | No | N/A | N/A | No | N/A | N/A | No | N/A | N/A | Yes | N/A | N/A
Meentycat T121 | Meentycat WF | 110kV SF6 Cubicle Ordinary Service |  | Yes | TO-20-MEE-T121-01 | October | 5 days | N/A | 2020-09-14 | 2020-09-18 | Yes | N/A | Yes | Changed as per generator request | GENERATOR | No | N/A | N/A | Yes | TAO advised they did not have adequate resources to complete works in August. Outage rescheduled for September following agreement with generator | TAO | Yes | TAO advised they did not have adequate resources to complete works in August. Outage rescheduled for September following agreement with generator | TAO | No | N/A | N/A | Yes | TAO advised they did not have adequate resources to complete works in August. Outage rescheduled for September following agreement with generator | TAO | Yes | N/A | N/A
Mountlucas T121 | Mountlucas WF | 110kV SF6 Cubicle Operational Test | 901129681 | Yes | TO-20-MLC-T121-01 | June | 1 day | N/A | 2020-06-09 | 2020-06-10 | Yes | N/A | No | N/A | N/A | No | N/A | No Change | No | N/A | N/A | No | N/A | N/A | No | N/A | N/A | No | N/A | N/A | Yes | N/A | N/A
Mountlucas T121 | Mountlucas WF | P3 Protection maintenance of 7SA612 | Protection | Yes | TO-20-MLC-T121-01 | June | 1 day | N/A | N/A | N/A | Completed in Previous Outage Season | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed in Previous Outage Season | Completed in Previous Outage Season | TAO | N/A | N/A | N/A | N/A | N/A | N/A
Moneypoint GIS T121 | Moneypoint WF | 110KV GIS Cubicle Operational Test | 901129527 | Yes | TO-20-MP GIS-T121-01 | July | 1 day | N/A | 2020-07-24 | 2020-07-24 | Yes | N/A | No | N/A | N/A | No | N/A | N/A | No | N/A | N/A | No | N/A | N/A | No | N/A | N/A | No | N/A | N/A | Yes | N/A | N/A
Moneypoint GIS T4003 | Moneypoint MP3 | Aux Relay - replace contactors |  | Yes | TO-20-MP GIS-T4003-01 | August | 6 days | N/A | 2020-06-10 | 2020-06-17 | Yes | N/A | Yes | TSO requested work was completed while unit was on FO | TSO | No | N/A | N/A | Yes | TSO requested work was completed while unit was on FO | TSO | Yes | TSO requested work was completed while unit was on FO | TSO | No | N/A | N/A | No | N/A | N/A | Yes | N/A | N/A
Moneypoint T4001 | Moneypoint MP1 | 400kV GIS Cubicle Operational Test | 901005716 | Yes | TO-20-MP-T4001-01 | May | 3 days | N/A | N/A | N/A | Completed in Previous Outage Season | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed in Previous Outage Season | Completed in Previous Outage Season | TAO | N/A | N/A | N/A | N/A | N/A | N/A
Moneypoint T4001 | Moneypoint MP1 | Insp. 400 & 220 Station XLPE Cable | 901005716 | Yes | TO-20-MP-T4001-01 | May | 3 days | N/A | 2020-11-20 | 2020-12-02 | Yes | N/A | Yes | Generator requested change to Committed Outage Programme as a result of COVID-19 restrictions | COVID | No | N/A | N/A | No | N/A | N/A | No | N/A | N/A | No | N/A | N/A | Yes | Generator requested change to Committed Outage Programme as a result of COVID-19 restrictions | COVID | Yes | N/A | N/A
Moneypoint T4001 | Moneypoint MP1 | HV Pressure Vessel Inspection | 901114160 | Yes | TO-20-MP-T4001-01 | May | 3 days | N/A | N/A | N/A | Completed in Previous Outage Season | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed in Previous Outage Season | Completed in Previous Outage Season | TAO | N/A | N/A | N/A | N/A | N/A | N/A
Mulreavy T131 | Mulreavy MB1, Mulreavy MB2 | 110kV SF6 Cubicle Ordinary Service |  | Yes | TO-20-MRY-T131-01 | July | 2 days | N/A | N/A | N/A | No | Generator requested a postponement of works to late in 2020 following communication of proposed July outage. After review, it was decided by the TSO to reschedule outage for 2021. | Yes | Generator requested a postponement of works to late in 2020 following communication of proposed July outage. After review, it was decided by the TSO to reschedule outage for 2021. | GENERATOR | No | N/A | N/A | Yes | Generator requested a postponement of works to late in 2020 following communication of proposed July outage. After review, it was decided by the TSO to reschedule outage for 2021. | GENERATOR | Yes | Generator requested a postponement of works to late in 2020 following communication of proposed July outage. After review, it was decided by the TSO to reschedule outage for 2021. | GENERATOR | No | N/A | N/A | Yes | Generator requested change | GENERATOR | No | Generator requested a postponement of works to late in 2020 following communication of proposed July outage. After review, it was decided by the TSO to reschedule outage for 2021. | GENERATOR
Reamore - Tralee | Knocknagoum KM1, Muignaminnane MU1 | Cable Insp. 110kV XLPE | 901129161 | Yes | TO-20-REM-TRL-1-02 | August | 2 days | N/A | 2020-11-03 | 2020-11-04 | Yes | N/A | Yes | TAO requested change to align with distribution network outage in November | TAO | No | N/A | N/A | No | N/A | N/A | No | N/A | N/A | No | N/A | N/A | No | N/A | N/A | Yes | N/A | N/A
Reamore - Tralee | Knocknagoum KM1, Muignaminnane MU1 | 110kV SF6 Cubicle Operational Test in Reamore | 901129631 | Yes | TO-20-REM-TRL-1-02 | August | 2 days | N/A | 2020-11-03 | 2020-11-04 | Yes | N/A | Yes | TAO requested change to align with distribution network outage in November | TAO | No | N/A | N/A | No | N/A | N/A | No | N/A | N/A | No | N/A | N/A | No | N/A | N/A | Yes | N/A | N/A
Reamore - Tralee | Knocknagoum KM1, Muignaminnane MU1 | 110kV SF6 Cubicle Operational Test in Tralee | 901129585 | Yes | TO-20-REM-TRL-1-02 | August | 2 days | N/A | 2020-11-03 | 2020-11-04 | Yes | N/A | Yes | TAO requested change to align with distribution network outage in November | TAO | No | N/A | N/A | No | N/A | N/A | No | N/A | N/A | No | N/A | N/A | No | N/A | N/A | Yes | N/A | N/A
Ratrussan T121 | Bindoo BD1 WF | 110kV SF6 Cubicle Operational Test | 901039107 | Yes | TO-20-RRU-T121-01 | April | 2 days | N/A | N/A | N/A | No | Works were deferred due to COVID-19 restrictions as they were not priority P1. Subsequently deferred works to next outage season | Yes | Works were deferred due to COVID-19 restrictions as they were not priority P1. Subsequently deferred works to next outage season | COVID | No | N/A | N/A | Yes | Works were deferred due to COVID-19 restrictions as they were not priority P1. Subsequently deferred works to next outage season | COVID | Yes | Works were deferred due to COVID-19 restrictions as they were not priority P1. Subsequently deferred works to next outage season | COVID | No | N/A | N/A | No | N/A | N/A | No | Works were deferred due to COVID-19 restrictions as they were not priority P1. Subsequently deferred works to next outage season | COVID
Ratrussan T122 | Mountain Lodge WF | P3 Protection maintenance of 7SA612 | Protection | Yes | TO-20-RRU-T122-01 | May | 3 days | N/A | N/A | N/A | No | Works were not P1 priority so were postponed due to ongoing COVID restrictions | Yes | Works were not P1 priority so were postponed due to ongoing COVID restrictions | COVID | No | N/A | N/A | No | N/A | N/A | No | N/A | N/A | No | N/A | N/A | Yes | Changed due to generator request | GENERATOR | No | Works were not P1 priority so were postponed due to ongoing COVID restrictions | COVID
Ratrussan T122 | Mountain Lodge WF | Re-Test - Condition Assessment of the Cubicle | 900990024 | Yes | TO-20-RRU-T122-01 | May | 3 days | N/A | 2020-05-18 | 2020-05-21 | Yes | N/A | No | N/A | N/A | Yes | Changed due to generator request | GENERATOR | Yes | Changed due to generator request | GENERATOR | No | N/A | N/A | No | N/A | N/A | Yes | Changed due to generator request | GENERATOR | Yes | N/A | N/A
Ratrussan T122 | Mountain Lodge WF | 110kV SF6 Cubicle Operational Test | 901129708 | Yes | TO-20-RRU-T122-01 | May | 3 days | N/A | 2020-05-18 | 2020-05-21 | Yes | N/A | No | N/A | N/A | Yes | Changed due to generator request | GENERATOR | Yes | Changed due to generator request | GENERATOR | No | N/A | N/A | No | N/A | N/A | Yes | Changed due to generator request | GENERATOR | Yes | N/A | N/A
Shellybanks T2014 | PBA | 220kV Sect / Dist Ordinary Service | 901130163 | Yes | TO-20-SHL-T2014-01 | June | 4 days | N/A | 2020-08-17 | 2020-08-20 | Yes | N/A | Yes | Generator requested change to Committed Outage Programme as a result of COVID-19 restrictions | COVID | No | N/A | N/A | No | N/A | N/A | No | N/A | N/A | No | N/A | N/A | Yes | Generator requested change to Committed Outage Programme as a result of COVID-19 restrictions | COVID | Yes | N/A | N/A
Shellybanks T2014 | PBA | Annual Insp. 400 & 220 Statn. XLPE Cable | 901114888 | Yes | TO-20-SHL-T2014-01 | June | 4 days | N/A | 2020-08-17 | 2020-08-20 | Yes | N/A | Yes | Generator requested change to Committed Outage Programme as a result of COVID-19 restrictions | COVID | No | N/A | N/A | No | N/A | N/A | No | N/A | N/A | No | N/A | N/A | Yes | Generator requested change to Committed Outage Programme as a result of COVID-19 restrictions | COVID | Yes | N/A | N/A
Sealrock T103 | SK3 | SF6 leak repair on Sealrock T103 110 kV CB, followed by EI. | 901137683 | No | TO-20-SHL-T2015-01 |  |  | Work item added by TAO in days leading up to outage | 2020-07-20 | 2020-07-24 | Yes | N/A | N/A | N/A | N/A | N/A | N/A | N/A | No | N/A | N/A | No | N/A | N/A | Yes | Work item added by TAO in days leading up to outage | TAO | Yes | Generator requested change to Committed Outage Programme as a result of COVID-19 restrictions | COVID | Yes | N/A | N/A
Shellybanks T2015 | Poolbeg PB15 | Cable Insp. 400 & 220kV Feeder XLPE | 901005629 | Yes | TO-20-SHL-T2015-01 | June | 9 days | N/A | N/A | N/A | No | Work item was deprioritised due to increased duration required by TAO to comply with COVID restrictions. | Yes | Work item was deprioritised due to increased duration required by TAO to comply with COVID restrictions. | COVID | No | N/A | N/A | No | N/A | N/A | No | N/A | N/A | No | N/A | N/A | Yes | Generator requested change to Committed Outage Programme | Generator | No | Work item was deprioritised due to increased duration required by TAO to comply with COVID restrictions. | TAO
Shellybanks T2015 | Poolbeg PB15 | 220kV Sect / Dist Ordinary Service | 901130137 | Yes | TO-20-SHL-T2015-01 | June | 9 days | N/A | N/A | N/A | No | Work item was deprioritised due to increased duration required by TAO to comply with COVID restrictions. | Yes | Work item was deprioritised due to increased duration required by TAO to comply with COVID restrictions. | COVID | No | N/A | N/A | No | N/A | N/A | No | N/A | N/A | No | N/A | N/A | Yes | Generator requested change to Committed Outage Programme | Generator | No | Work item was deprioritised due to increased duration required by TAO to comply with COVID restrictions. | TAO
Shellybanks T2016 | Poolbeg PB16 | Cable Insp. 400 & 220kV Feeder XLPE | 901129027 | Yes | TO-20-SHL-T2016-01 | June/July | 4 days | N/A | N/A | N/A | No | Generator requested change to Committed Outage Programme as a result of COVID-19 restrictions. To comply with COVID-19 restrictions the TAO required 15 working days to complete all works including Ordinary Service and Cable Inspection which would have offloaded generation. Work was deferred from 2020 outage season | Yes | Generator requested change to Committed Outage Programme as a result of COVID-19 restrictions | COVID | No | N/A | N/A | No | N/A | N/A | No | N/A | N/A | No | N/A | N/A | Yes | Generator requested change to Committed Outage Programme as a result of COVID-19 restrictions | COVID | No | Generator requested change to Committed Outage Programme as a result of COVID-19 restrictions. To comply with COVID-19 restrictions the TAO required 15 working days to complete all works including Ordinary Service and Cable Inspection which would have offloaded generation. Work was deferred from 2020 outage season | COVID
Shellybanks T2016 | Poolbeg PB16 | 220kV Sect / Dist Ordinary Service | 901130138 | Yes | TO-20-SHL-T2016-01 | June/July | 4 days | N/A | N/A | N/A | No | Generator requested change to Committed Outage Programme as a result of COVID-19 restrictions. To comply with COVID-19 restrictions the TAO required 15 working days to complete all works including Ordinary Service and Cable Inspection which would have offloaded generation. Work was deferred from 2020 outage season | Yes | Generator requested change to Committed Outage Programme as a result of COVID-19 restrictions | COVID | No | N/A | N/A | No | N/A | N/A | No | N/A | N/A | No | N/A | N/A | Yes | Generator requested change to Committed Outage Programme as a result of COVID-19 restrictions | COVID | No | Generator requested change to Committed Outage Programme as a result of COVID-19 restrictions. To comply with COVID-19 restrictions the TAO required 15 working days to complete all works including Ordinary Service and Cable Inspection which would have offloaded generation. Work was deferred from 2020 outage season | COVID
Shellybanks T2016 | Poolbeg PB16 | Repair SF6 leak on T2016 DL |  | No | TO-20-SHL-T2016-01 |  |  | Corrective maintenance item identified in season by the TAO. Work was overlapped with a short term maintenance outage of generator in June 2020 | 2021-06-01 | 2021-06-04 | Yes | N/A | N/A | N/A | N/A | N/A | N/A | N/A | No | N/A | N/A | No | N/A | N/A | Yes | Corrective maintenance item identified in season by the TAO. Work was overlapped with a short term maintenance outage of generator in June 2020 | TAO | Yes | Generator requested change to Committed Outage Programme as a result of COVID-19 restrictions | COVID | Yes | N/A | N/A
Shannonbridge T104 | West Offaly WO4 | Cable Insp. 110kV XLPE | 901129123 | Yes | TO-20-SH-T104-01 | May | 2 days | N/A | 2020-08-31 | 2020-09-02 | Yes | N/A | Yes | Generator requested change to Committed Outage Programme as a result of COVID-19 restrictions | COVID | Yes | TAO began outage early as 3 days were required instead of 2 | TAO | Yes | TAO began outage early as 3 days were required instead of 2 | TAO | Yes | TAO began outage early as 3 days were required instead of 2 | TAO | No | N/A | N/A | Yes | Generator requested change to Committed Outage Programme as a result of COVID-19 restrictions | COVID | Yes | N/A | N/A
Sealrock T103 | SK3 | Cable Insp. 110kV XLPE | 901129121 | Yes | TO-20-SK-T103-01 | September | 3 days | N/A | 2020-07-20 | 2020-07-24 | Yes | N/A | Yes | Generator requested change to Committed Outage Programme as a result of COVID-19 restrictions | COVID | Yes | Work scope duration increased to 5 days at TAO request | TAO | No | N/A | N/A | No | N/A | N/A | No | N/A | N/A | Yes | Generator requested change to Committed Outage Programme as a result of COVID-19 restrictions | COVID | Yes | N/A | N/A
Srahnakilly T131 | Oweninny OY1 | 110kv Operational Test - T131 Cubicle | 901211739 | No | TO-20-SKY-T131-01 |  |  | TAO requested works to overlap with parallel low voltage works ensuring windfarm was only offloaded once | 2020-07-14 | 2020-07-15 | Yes | N/A | N/A | N/A | N/A | N/A | N/A | N/A | No | N/A | N/A | No | N/A | N/A | Yes | TAO requested works to overlap with parallel low voltage works ensuring windfarm was only offloaded once | TAO | No | N/A | N/A | Yes | N/A | N/A
Stratford tee Carlow | Liffey LI1, LI2, LI4 | 2019HP-1[110]Replace Pole only -Rot | 901086426 | Yes | TO-20-STR,T-CLW-1-01 | August/September | 21 days | N/A | 2020-08-24 | 2020-09-21 | Yes | N/A | No | N/A | N/A | No | N/A | N/A | Yes | TAO completed work earlier than expected | TAO | Yes | TAO completed work earlier than expected | TAO | No | N/A | N/A | Yes | Generator requested change to Committed Outage Programme | GENERATOR | Yes | N/A | N/A
Stratford tee Carlow | Liffey LI1, LI2, LI4 | 2016CP-1[109]Off Plumb Pole & insulators | 900864816 | Yes | TO-20-STR,T-CLW-1-01 | August/September | 21 days | N/A | 2020-08-24 | 2020-09-21 | Yes | N/A | No | N/A | N/A | No | N/A | N/A | Yes | TAO completed work earlier than expected | TAO | Yes | TAO completed work earlier than expected | TAO | No | N/A | N/A | Yes | Generator requested change to Committed Outage Programme | GENERATOR | Yes | N/A | N/A
Stratford tee Carlow | Liffey LI1, LI2, LI4 | 2016CP-1[109]Replace Pole Bolt -Bent | 900864817 | Yes | TO-20-STR,T-CLW-1-01 | August/September | 21 days | N/A | 2020-08-24 | 2020-09-21 | Yes | N/A | No | N/A | N/A | No | N/A | N/A | Yes | TAO completed work earlier than expected | TAO | Yes | TAO completed work earlier than expected | TAO | No | N/A | N/A | Yes | Generator requested change to Committed Outage Programme | GENERATOR | Yes | N/A | N/A
Stratford tee Carlow | Liffey LI1, LI2, LI4 | 2016CP-1[109]Vibration Dampers Replace | 900864818 | Yes | TO-20-STR,T-CLW-1-01 | August/September | 21 days | N/A | 2020-08-24 | 2020-09-21 | Yes | N/A | No | N/A | N/A | No | N/A | N/A | Yes | TAO completed work earlier than expected | TAO | Yes | TAO completed work earlier than expected | TAO | No | N/A | N/A | Yes | Generator requested change to Committed Outage Programme | GENERATOR | Yes | N/A | N/A
Stratford tee Carlow | Liffey LI1, LI2, LI4 | 2016CP-1[109]H-ware Susp Clamps corroded | 900864820 | Yes | TO-20-STR,T-CLW-1-01 | August/September | 21 days | N/A | 2020-08-24 | 2020-09-21 | Yes | N/A | No | N/A | N/A | No | N/A | N/A | Yes | TAO completed work earlier than expected | TAO | Yes | TAO completed work earlier than expected | TAO | No | N/A | N/A | Yes | Generator requested change to Committed Outage Programme | GENERATOR | Yes | N/A | N/A
Stratford tee Carlow | Liffey LI1, LI2, LI4 | 2016CP-1[109]Crossarm Replacement | 900864821 | Yes | TO-20-STR,T-CLW-1-01 | August/September | 21 days | N/A | 2020-08-24 | 2020-09-21 | Yes | N/A | No | N/A | N/A | No | N/A | N/A | Yes | TAO completed work earlier than expected | TAO | Yes | TAO completed work earlier than expected | TAO | No | N/A | N/A | Yes | Generator requested change to Committed Outage Programme | GENERATOR | Yes | N/A | N/A
Stratford tee Carlow | Liffey LI1, LI2, LI4 | 2016CP-1[110]Replace Pole only -Rotten | 900864822 | Yes | TO-20-STR,T-CLW-1-01 | August/September | 21 days | N/A | 2020-08-24 | 2020-09-21 | Yes | N/A | No | N/A | N/A | No | N/A | N/A | Yes | TAO completed work earlier than expected | TAO | Yes | TAO completed work earlier than expected | TAO | No | N/A | N/A | Yes | Generator requested change to Committed Outage Programme | GENERATOR | Yes | N/A | N/A
Stratford tee Carlow | Liffey LI1, LI2, LI4 | 2018HP-1[90]ACGfit ACG | 900984379 | Yes | TO-20-STR,T-CLW-1-01 | August/September | 21 days | N/A | 2020-08-24 | 2020-09-21 | Yes | N/A | No | N/A | N/A | No | N/A | N/A | Yes | TAO completed work earlier than expected | TAO | Yes | TAO completed work earlier than expected | TAO | No | N/A | N/A | Yes | Generator requested change to Committed Outage Programme | GENERATOR | Yes | N/A | N/A
Stratford tee Carlow | Liffey LI1, LI2, LI4 | 2018HP-1[94]Check Structure-top rot - Ch | 900989809 | Yes | TO-20-STR,T-CLW-1-01 | August/September | 21 days | N/A | 2020-08-24 | 2020-09-21 | Yes | N/A | No | N/A | N/A | No | N/A | N/A | Yes | TAO completed work earlier than expected | TAO | Yes | TAO completed work earlier than expected | TAO | No | N/A | N/A | Yes | Generator requested change to Committed Outage Programme | GENERATOR | Yes | N/A | N/A
Stratford tee Carlow | Liffey LI1, LI2, LI4 | 2019HP-1[124]Check Structure -Check Rot | 901086400 | Yes | TO-20-STR,T-CLW-1-01 | August/September | 21 days | N/A | 2020-08-24 | 2020-09-21 | Yes | N/A | No | N/A | N/A | No | N/A | N/A | Yes | TAO completed work earlier than expected | TAO | Yes | TAO completed work earlier than expected | TAO | No | N/A | N/A | Yes | Generator requested change to Committed Outage Programme | GENERATOR | Yes | N/A | N/A
Stratford tee Carlow | Liffey LI1, LI2, LI4 | 110kV SF6 Cubicle Operational Test | 901129608 (CLW) | Yes | TO-20-STR,T-CLW-1-01 | August/September | 21 days | N/A | 2020-08-24 | 2020-09-21 | Yes | N/A | No | N/A | N/A | No | N/A | N/A | Yes | TAO completed work earlier than expected | TAO | Yes | TAO completed work earlier than expected | TAO | No | N/A | N/A | Yes | Generator requested change to Committed Outage Programme | GENERATOR | Yes | N/A | N/A
Stratford tee Pollaphuca | Liffey LI1, LI2, LI4 | 2017HP-1[14]Crossarm Replacement Replace | 900898188 | Yes | TO-20-STR,T-PA-1-01 | August/September | 21 days | N/A | 2020-08-24 | 2020-09-21 | Yes | N/A | No | N/A | N/A | No | N/A | N/A | Yes | TAO completed work earlier than expected | TAO | Yes | TAO completed work earlier than expected | TAO | No | N/A | N/A | Yes | Generator requested change to Committed Outage Programme | GENERATOR | Yes | N/A | N/A
Stratford tee Pollaphuca | Liffey LI1, LI2, LI4 | 2019HP-1[13]Off Plumb -plumb poles | 901085001 | Yes | TO-20-STR,T-PA-1-01 | August/September | 21 days | N/A | N/A | N/A | No | Work item is a duplicate of another work item 900864747 | No | N/A | N/A | No | N/A | N/A | Yes | TAO completed work earlier than expected | TAO | Yes | TAO completed work earlier than expected | TAO | No | N/A | N/A | Yes | Generator requested change to Committed Outage Programme | GENERATOR | No | Work item is a duplicate of another work item 900864747 | TAO
Stratford tee Pollaphuca | Liffey LI1, LI2, LI4 | 2016CP-1[13]Off Plumb Poles | 900864747 | Yes | TO-20-STR,T-PA-1-01 | August/September | 21 days | N/A | 2020-08-24 | 2020-09-21 | Yes | N/A | No | N/A | N/A | No | N/A | N/A | Yes | TAO completed work earlier than expected | TAO | Yes | TAO completed work earlier than expected | TAO | No | N/A | N/A | Yes | Generator requested change to Committed Outage Programme | GENERATOR | Yes | N/A | N/A
Stratford tee Pollaphuca | Liffey LI1, LI2, LI4 | 1[33]Replace Rotten Pole | 900973774 | Yes | TO-20-STR,T-PA-1-01 | August/September | 21 days | N/A | N/A | N/A | Completed in Previous Outage Season | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed in Previous Outage Season | Completed in Previous Outage Season | TAO | N/A | N/A | N/A | N/A | N/A | N/A
Stratford tee Pollaphuca | Liffey LI1, LI2, LI4 | 1[53]Install ACG on mast no. 53 | 900975368 | Yes | TO-20-STR,T-PA-1-01 | August/September | 21 days | N/A | 2020-08-24 | 2020-09-21 | Yes | N/A | No | N/A | N/A | No | N/A | N/A | Yes | TAO completed work earlier than expected | TAO | Yes | TAO completed work earlier than expected | TAO | No | N/A | N/A | Yes | Generator requested change to Committed Outage Programme | GENERATOR | Yes | N/A | N/A
Stratford tee Pollaphuca | Liffey LI1, LI2, LI4 | 2018HP-1[15]Off Plumb-Poles | 900989394 | Yes | TO-20-STR,T-PA-1-01 | August/September | 21 days | N/A | 2020-08-24 | 2020-09-21 | Yes | N/A | No | N/A | N/A | No | N/A | N/A | Yes | TAO completed work earlier than expected | TAO | Yes | TAO completed work earlier than expected | TAO | No | N/A | N/A | Yes | Generator requested change to Committed Outage Programme | GENERATOR | Yes | N/A | N/A
Stratford tee Pollaphuca | Liffey LI1, LI2, LI4 | 110kV MO Cubicle Ordinary Service | 901129824 (PA) | Yes | TO-20-STR,T-PA-1-01 | August/September | 21 days | N/A | 2020-08-24 | 2020-09-21 | Yes | N/A | No | N/A | N/A | No | N/A | N/A | Yes | TAO completed work earlier than expected | TAO | Yes | TAO completed work earlier than expected | TAO | No | N/A | N/A | Yes | Generator requested change to Committed Outage Programme | GENERATOR | Yes | N/A | N/A
Stratford tee Pollaphuca | Liffey LI1, LI2, LI4 | 110KV CUBICLE CONDITION ASSESSMENT | 901129197 (PA) | Yes | TO-20-STR,T-PA-1-01 | August/September | 21 days | N/A | 2020-08-24 | 2020-09-21 | Yes | N/A | No | N/A | N/A | No | N/A | N/A | Yes | TAO completed work earlier than expected | TAO | Yes | TAO completed work earlier than expected | TAO | No | N/A | N/A | Yes | Generator requested change to Committed Outage Programme | GENERATOR | Yes | N/A | N/A
Tawnaghmore T1/T2 | Tawnaghmore TP1 | Cable Insp. 110kV XLPE | 901129131 | Yes | TO-20-TAW-T1/T2-01 | August | 3 days | N/A | 2020-08-10 | 2020-08-12 | Yes | N/A | No | N/A | N/A | No | N/A | N/A | No | N/A | N/A | No | N/A | N/A | No | N/A | N/A | Yes | Generator requested change to Committed Outage Programme | GENERATOR | Yes | N/A | N/A
Tawnaghmore T1/T2 | Tawnaghmore TP1 | 110kV SF6 Cubicle Operational Test | 901043726 | Yes | TO-20-TAW-T1/T2-01 | August | 3 days | N/A | 2020-08-10 | 2020-08-12 | Yes | N/A | No | N/A | N/A | No | N/A | N/A | No | N/A | N/A | No | N/A | N/A | No | N/A | N/A | Yes | Generator requested change to Committed Outage Programme | GENERATOR | Yes | N/A | N/A
Tawnaghmore T3 | Tawnaghmore TP3 | 110kV SF6 Cubicle Operational Test | 901043728 | Yes | TO-20-TAW-T3-01 | August | 1 day | N/A | N/A | N/A | Completed in Previous Outage Season | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed in Previous Outage Season | Completed in Previous Outage Season | TAO | No | N/A | N/A | N/A | N/A | N/A
Tarbert T101 | Tarbert TB1 | P2 Protection maintenance of 7SA513 | Protection | Yes | TO-20-TB-T101-01 | April | 2 days | N/A | N/A | N/A | No | Works were deferred due to COVID-19 restrictions as they were not priority P1. Subsequently deferred works to next outage season | Yes | Works were deferred due to COVID-19 restrictions as they were not priority P1. Subsequently deferred works to next outage season | COVID | No | N/A | N/A | Yes | Works were deferred due to COVID-19 restrictions as they were not priority P1. Subsequently deferred works to next outage season | COVID | Yes | Works were deferred due to COVID-19 restrictions as they were not priority P1. Subsequently deferred works to next outage season | COVID | No | N/A | N/A | No | N/A | N/A | No | Works were deferred due to COVID-19 restrictions as they were not priority P1. Subsequently deferred works to next outage season | COVID
Tarbert T101 | Tarbert TB1 | Annual Insp. 110kV Station OF Cable |  | Yes | TO-20-TB-T101-01 | April | 2 days | N/A | N/A | N/A | No | Works were deferred due to COVID-19 restrictions as they were not priority P1. Subsequently deferred works to next outage season | Yes | Works were deferred due to COVID-19 restrictions as they were not priority P1. Subsequently deferred works to next outage season | COVID | No | N/A | N/A | Yes | Works were deferred due to COVID-19 restrictions as they were not priority P1. Subsequently deferred works to next outage season | COVID | Yes | Works were deferred due to COVID-19 restrictions as they were not priority P1. Subsequently deferred works to next outage season | COVID | No | N/A | N/A | No | N/A | N/A | No | Works were deferred due to COVID-19 restrictions as they were not priority P1. Subsequently deferred works to next outage season | COVID
Tarbert T102 | Tarbert TB2 | P2 Protection maintenance of 7SA513 | Protection | Yes | TO-20-TB-T102-01 | April | 2 days | N/A | N/A | N/A | No | Works were deferred due to COVID-19 restrictions as they were not priority P1. Subsequently deferred works to next outage season | Yes | Works were deferred due to COVID-19 restrictions as they were not priority P1. Subsequently deferred works to next outage season | COVID | No | N/A | N/A | Yes | Works were deferred due to COVID-19 restrictions as they were not priority P1. Subsequently deferred works to next outage season | COVID | Yes | Works were deferred due to COVID-19 restrictions as they were not priority P1. Subsequently deferred works to next outage season | COVID | No | N/A | N/A | No | N/A | N/A | No | Works were deferred due to COVID-19 restrictions as they were not priority P1. Subsequently deferred works to next outage season | COVID
Tarbert T102 | Tarbert TB2 | Annual Insp. 110kV Station OF Cable |  | Yes | TO-20-TB-T102-01 | April | 2 days | N/A | N/A | N/A | No | Works were deferred due to COVID-19 restrictions as they were not priority P1. Subsequently deferred works to next outage season | Yes | Works were deferred due to COVID-19 restrictions as they were not priority P1. Subsequently deferred works to next outage season | COVID | No | N/A | N/A | Yes | Works were deferred due to COVID-19 restrictions as they were not priority P1. Subsequently deferred works to next outage season | COVID | Yes | Works were deferred due to COVID-19 restrictions as they were not priority P1. Subsequently deferred works to next outage season | COVID | No | N/A | N/A | No | N/A | N/A | No | Works were deferred due to COVID-19 restrictions as they were not priority P1. Subsequently deferred works to next outage season | COVID
Tarbert T2003 | TB3 | 220kV MO Cubicle Operational Test | 901129535 | Yes | TO-20-TB-T2003-01 | July | 2 days | N/A | 2020-06-29 | 2020-07-03 | Yes | N/A | Yes | Maintenance overlapped with simultaneous Capital Works | TAO | No | N/A | N/A | No | N/A | N/A | No | N/A | N/A | No | N/A | N/A | No | N/A | N/A | Yes | N/A | N/A
Tarbert T2004 | Tarbert TB4 | P2 Protection maintenance of R1Z23b, S Type Overcurrent | Protection | Yes | TO-20-TB-T2004-01 | June | 2 days | N/A | 2020-08-04 | 2020-08-21 | Yes | N/A | Yes | Changed as per generator request | GENERATOR | No | N/A | N/A | No | N/A | N/A | No | N/A | N/A | No | N/A | N/A | Yes | Generator requested change to Committed Outage Programme | GENERATOR | Yes | N/A | N/A
Turlough Hill T2001/2002 | TH1/TH2 | Annual Insp. 400 & 220 Station OF Cable | 901005766 | Yes | TO-20-TH-T2001/2-01 | June | 2 days | N/A | 2020-07-13 | 2020-07-14 | Yes | N/A | Yes | Generator requested change to Committed Outage Programme as a result of COVID-19 restrictions | COVID | No | N/A | N/A | No | N/A | N/A | No | N/A | N/A | No | N/A | N/A | Yes | Generator requested change to Committed Outage Programme as a result of COVID-19 restrictions | COVID | Yes | N/A | N/A
Turlough Hill T2003/2004 | TH3/TH4 | 110kV MO Cubicle Ordinary Service | 901129829 | Yes | TO-20-TH-T2003/4-01 | June | 6 days | N/A | N/A | N/A | No | Work item deferred until 2021 as TAO requested increased duration to complete in order to comply with social distancing requirements | Yes | Work item postponed until 2021 as TAO requested increased duration to complete in order to comply with social distancing requirements | TAO | No | N/A | N/A | No | N/A | N/A | No | N/A | N/A | No | N/A | N/A | No | N/A | N/A | No | Work item deferred until 2021 as TAO requested increased duration to complete in order to comply with social distancing requirements | TAO
Turlough Hill T2003/2004 | TH3/TH4 | Annual Insp. 400 & 220 Station OF Cable | 901005768 | Yes | TO-20-TH-T2003/4-01 | June | 6 days | N/A | 2020-06-29 | 2020-06-30 | Yes | N/A | No | N/A | No Change | No | N/A | N/A | No | N/A | N/A | No | N/A | N/A | No | N/A | N/A | No | N/A | N/A | Yes | N/A | N/A
Turlough Hill T2003/2004 | TH3/TH4 | Low Oil / Leak- 220kv vt oil level low | 901083957 | Yes | TO-20-TH-T2003/4-01 | June | 6 days | N/A | N/A | N/A | Completed in Previous Outage Season | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | No | N/A | N/A | Completed in Previous Outage Season | Completed in Previous Outage Season | TAO | No | N/A | N/A | N/A | N/A | N/A
Turlough Hill T2003/2004 | TH3/TH4 | 220kV MO Cubicle Operational Test | 901038977 | No | TO-20-TH-T2003/4-01 | N/A | N/A | Work item added by TAO in days leading up to outage | 2020-06-29 | 2020-06-30 | Yes | N/A | N/A | N/A | N/A | N/A | N/A | N/A | No | N/A | N/A | No | N/A | N/A | Yes | Work item added by TAO in days leading up to outage | TAO | No | N/A | N/A | Yes | N/A | N/A
Tynagh T2001/2 | TYC | 220kV SF6 Cubicle Operational Test | 901129555 | Yes | TO-20-TY-T2001/2-01 | March | 2 days | N/A | 2020-03-30 | 2020-04-01 | Yes | N/A | No | N/A | N/A | Yes | Changed due to generator request | GENERATOR | Yes | Changed due to generator request | GENERATOR | Yes | Changed due to generator request | GENERATOR | No | N/A | N/A | Yes | Changed due to generator request | GENERATOR | Yes | N/A | N/A
Tynagh T2001/2 | TYC | 2 Hot spot detected on T 2001/2 220kV R and S Phase DE Disconnects | 900990025 | Yes | TO-20-TY-T2001/2-01 | March | 2 days | N/A | 2020-03-30 | 2020-04-01 | Yes | N/A | No | N/A | N/A | Yes | Changed due to generator request | GENERATOR | Yes | Changed due to generator request | GENERATOR | Yes | Changed due to generator request | GENERATOR | No | N/A | N/A | Yes | Changed due to generator request | GENERATOR | Yes | N/A | N/A
Uggool T131 | Uggool UG1 | 110kV SF6 Cubicle Operational Test | 901129677 | Yes | TO-20-UGL-T131-01 | April | 2 days | N/A | 2020-09-07 | 2020-09-08 | Yes | N/A | Yes | Original outage deferred due to COVID 19 restrictions | COVID | No | N/A | N/A | No | N/A | N/A | No | N/A | N/A | No | N/A | N/A | Yes | Changed as per generator request | GENERATOR | Yes | N/A | N/A
Uggool T132 | Seecon SO1 | 110kV SF6 Cubicle Operational Test | 901129676 | Yes | TO-20-UGL-T132-01 | April | 1 day | N/A | 2020-09-07 | 2020-09-08 | Yes | N/A | Yes | Original outage deferred due to COVID 19 restrictions | COVID | No | N/A | N/A | No | N/A | N/A | No | N/A | N/A | No | N/A | N/A | Yes | Changed as per generator request | GENERATOR | Yes | N/A | N/A
Uggool T134 | Seecon SO1 | 110kV SF6 Cubicle Operational Test | 901129516 | Yes | TO-20-UGL-T134-01 | April | 1 day | N/A | 2020-09-07 | 2020-09-08 | Yes | N/A | Yes | Original outage deferred due to COVID 19 restrictions | COVID | No | N/A | N/A | No | N/A | N/A | No | N/A | N/A | No | N/A | N/A | Yes | Changed as per generator request | GENERATOR | Yes | N/A | N/A
Woodhouse T122 | Woodhouse WS1 | 110kV SF6 Cubicle Operational Test | 901129682 | Yes | TO-20-WOH-T122-01 | June | 1 day | N/A | 2020-06-22 | 2020-06-26 | Yes | N/A | No | N/A | N/A | Yes | To facilitate generator repair works. | GENERATOR | Yes | To facilitate generator repair works. | GENERATOR | No | N/A | N/A | No | N/A | N/A | Yes | To facilitate generator repair works. | GENERATOR | Yes | N/A | N/A
Ratrussan T122 | Montainlodge ML1 | Protection Maintenance testing on T122 in Ratrussan 110 kV station | Protection | No | TO-2O-RRU-T122-02 |  |  | TAO requested inclusion of works | 2020-09-29 | 2020-10-01 | Yes | N/A | N/A | N/A | N/A | N/A | N/A | N/A | No | N/A | N/A | No | N/A | N/A | Yes | TAO requested inclusion of works | TAO | No | N/A | N/A | Yes | N/A | N/A