## Ex-Post OACA Report 2021
General |  |  |  | Communicated Ex-Ante | [6 empty] | Actual Works |  |  |  | Indicative Window |  |  | Indicative Duration |  |  | Scheduled Days |  |  | Designated Days |  |  | Works Description Communicated Ex-Ante |  |  | Generator Dates |  |  | Scheduled Works Not Completed
OACA | Unit | Work Item Description | Work ID | Included in Ex-Ante Report? | TOP ID | Outage Window | Start Date if Appicable | End Date if Applicable | Outage Duration | Reason for Works Addition | Actual Start Date | Actual End Date | Works completed? | Reason for not completing, if applicable | Change to Window? | Reason for Change to Window, if applicable | Driver of Change to Window (e.g. TSO, TAO, Gen) | Change to Indicative Duration communicated Ex-Ante? | Reason for Change to Duration Communicated Ex-Ante, if applicable | Driver of Change to Duration Communicated Ex-Ante(e.g. TSO, TAO, Gen) | Change to Scheduled Dates communicated M-1? | Reason for Change to Scheduled Dates communicated M-1, if applicable | Driver of Change to Scheduled Dates communicated M-1 (e.g. TSO, TAO, Gen) | Change to Designated Days communicated M-1? | Reason for Change to Designated Days communicated M-1, if applicable | Driver of Change to Designated Days communicated M-1 (e.g. TSO, TAO, Gen) | Change to Works Description Communicated Ex-Ante | Reason for Change to Works Description communicated Ex-Ante, if applicable | Driver of Change to Works Description communicated Ex-Ante | Change to Generator Outage Dates | Reason for Change to Generator Dates | Driver of Change to Generator Outage Dates | Works Completed | Reason for Works Not Being Completed | Driver of Reason for Works Not Being Completed
AGHADA LONG POINT | AD2 | VT oil sampling | 901212888 | Yes | TO-21-AD-LPT-1-01 | May | - | - | 1 | N/A | 17-MAY-21 12:01:00 | 19-MAY-21 16:56:00 | No | Works Unscheduled - Samples taking on other VTs | No | N/A | No Change | Yes | Work scope duration increased at TAO request | TAO | Yes | TAO completed works earlier than anticipated | TAO | Yes | TAO completed works earlier than anticipated | TAO | No | N/A | No Change | No | N/A | No Change | No | Works Unscheduled - Samples taking on other VTs | TAO
AGHADA LONG POINT | AD2 | VT oil sampling | 901212889 | Yes | TO-21-AD-LPT-1-01 | May | - | - | 1 | N/A | 17-MAY-21 12:01:00 | 19-MAY-21 16:56:00 | No | Works Unscheduled - Samples taking on other VTs | No | N/A | No Change | Yes | Work scope duration increased at TAO request | TAO | Yes | TAO completed works earlier than anticipated | TAO | Yes | TAO completed works earlier than anticipated | TAO | No | N/A | No Change | No | N/A | No Change | No | Works Unscheduled - Samples taking on other VTs | TAO
AGHADA LONG POINT | AD2 | VT oil sampling | 901212890 | Yes | TO-21-AD-LPT-1-01 | May | - | - | 1 | N/A | 17-MAY-21 12:01:00 | 19-MAY-21 16:56:00 | No | Works Unscheduled - Samples taking on other VTs | No | N/A | No Change | Yes | Work scope duration increased at TAO request | TAO | Yes | TAO completed works earlier than anticipated | TAO | Yes | TAO completed works earlier than anticipated | TAO | No | N/A | No Change | No | N/A | No Change | No | Works Unscheduled - Samples taking on other VTs | TAO
AGHADA LONG POINT | AD2 | VT oil sampling | 901212895 | Yes | TO-21-AD-LPT-1-01 | May | - | - | 1 | N/A | 17-MAY-21 12:01:00 | 19-MAY-21 16:56:00 | Yes | N/A | No | N/A | No Change | Yes | Work scope duration increased at TAO request | TAO | Yes | TAO completed works earlier than anticipated | TAO | Yes | TAO completed works earlier than anticipated | TAO | No | N/A | No Change | No | N/A | No Change | Yes | N/A | No Change
AGHADA LONG POINT | AD2 | VT oil sampling | 901212897 | Yes | TO-21-AD-LPT-1-01 | May | - | - | 1 | N/A | 17-MAY-21 12:01:00 | 19-MAY-21 16:56:00 | Yes | N/A | No | N/A | No Change | Yes | Work scope duration increased at TAO request | TAO | Yes | TAO completed works earlier than anticipated | TAO | Yes | TAO completed works earlier than anticipated | TAO | No | N/A | No Change | No | N/A | No Change | Yes | N/A | No Change
AGHADA LONG POINT | AD2 | VT oil sampling | 901212898 | Yes | TO-21-AD-LPT-1-01 | May | - | - | 1 | N/A | 17-MAY-21 12:01:00 | 19-MAY-21 16:56:00 | Yes | N/A | No | N/A | No Change | Yes | Work scope duration increased at TAO request | TAO | Yes | TAO completed works earlier than anticipated | TAO | Yes | TAO completed works earlier than anticipated | TAO | No | N/A | No Change | No | N/A | No Change | Yes | N/A | No Change
AGHADA LONG POINT | AD2 | 220kV SF6 Cubicle Operational Test | 901212567 | Yes | TO-21-AD-LPT-1-01 | May | - | - | 1 | N/A | 17-MAY-21 12:01:00 | 19-MAY-21 16:56:00 | Yes | N/A | No | N/A | No Change | Yes | Work scope duration increased at TAO request | TAO | Yes | TAO completed works earlier than anticipated | TAO | Yes | TAO completed works earlier than anticipated | TAO | No | N/A | No Change | No | N/A | No Change | Yes | N/A | No Change
AGHADA LONG POINT | AD2 | VT oil sampling | 901212893 | Yes | TO-21-AD-LPT-1-01 | May | - | - | 1 | N/A | 17-MAY-21 12:01:00 | 19-MAY-21 16:56:00 | Yes | N/A | No | N/A | No Change | Yes | Work scope duration increased at TAO request | TAO | Yes | TAO completed works earlier than anticipated | TAO | Yes | TAO completed works earlier than anticipated | TAO | No | N/A | No Change | No | N/A | No Change | Yes | N/A | No Change
AGHADA LONG POINT | AD2 | VT oil sampling | 901212894 | Yes | TO-21-AD-LPT-1-01 | May | - | - | 1 | N/A | 17-MAY-21 12:01:00 | 19-MAY-21 16:56:00 | Yes | N/A | No | N/A | No Change | Yes | Work scope duration increased at TAO request | TAO | Yes | TAO completed works earlier than anticipated | TAO | Yes | TAO completed works earlier than anticipated | TAO | No | N/A | No Change | No | N/A | No Change | Yes | N/A | No Change
AGHADA LONG POINT | AD2 | VT oil sampling | 901212896 | Yes | TO-21-AD-LPT-1-01 | May | - | - | 1 | N/A | 17-MAY-21 12:01:00 | 19-MAY-21 16:56:00 | Yes | N/A | No | N/A | No Change | Yes | Work scope duration increased at TAO request | TAO | Yes | TAO completed works earlier than anticipated | TAO | Yes | TAO completed works earlier than anticipated | TAO | No | N/A | No Change | No | N/A | No Change | Yes | N/A | No Change
AGHADA T2011/12 | AT11/AT12 | HV Pressure Vessel Inspection | 901114127 | Yes | TO-21-AD-T2011/12-01 | August | - | - | 1 | N/A | 13-AUG-21 10:14:00 | 28-AUG-21 15:38:00 | Yes | N/A | No | N/A | No Change | Yes | Changed as per generator request | GEN | Yes | Rescheduled to align with generator works | GEN | Yes | Rescheduled to align with generator works | GEN | No | N/A | No Change | Yes | Generator requested change to Committed Outage Programme | GEN | Yes | N/A | No Change
AGHADA T2011/12 | AT11/AT12 | Annual Insp. 400 & 220 Station OF Cable | 901181291 | Yes | TO-21-AD-T2011/12-01 | August | - | - | 1 | N/A | 13-AUG-21 10:14:00 | 28-AUG-21 15:38:00 | Yes | N/A | No | N/A | No Change | Yes | Changed as per generator request | GEN | Yes | Rescheduled to align with generator works | GEN | Yes | Rescheduled to align with generator works | GEN | No | N/A | No Change | Yes | Generator requested change to Committed Outage Programme | GEN | Yes | N/A | No Change
AGHADA T2011/12 | AT11/AT12 | 220kV SF6 Cubicle Operational Test | 901212578 | Yes | TO-21-AD-T2011/12-01 | August | - | - | 1 | N/A | 13-AUG-21 10:14:00 | 28-AUG-21 15:38:00 | Yes | N/A | No | N/A | No Change | Yes | Changed as per generator request | GEN | Yes | Rescheduled to align with generator works | GEN | Yes | Rescheduled to align with generator works | GEN | No | N/A | No Change | Yes | Generator requested change to Committed Outage Programme | GEN | Yes | N/A | No Change
AGHADA T2014 | AT14 | Annual Insp. 400 & 220 Station OF Cable | 901181292 | Yes | TO-21-AD-T2014-01 | March | 2021-03-08 | 2021-03-09 | 2 | N/A | 10-MAR-21 10:07:00 | 12-MAR-21 19:05:00 | No | Works cancelled due to TAO resourcing | No | N/A | No Change | Yes | Work scope duration increased at TAO request | TAO | Yes | TSO requested change due to system constraints | TSO | Yes | TSO requested change due to system constraints | TSO | No | N/A | No Change | Yes | TSO requested change due to system constraints | TSO | No | Works cancelled due to TAO resourcing | TAO
AGHADA T2014 | AT14 | 220kV SF6 Cubicle Operational Test | 901212579 | Yes | TO-21-AD-T2014-01 | March | 2021-03-08 | 2021-03-09 | 2 | N/A | 10-MAR-21 10:07:00 | 12-MAR-21 19:05:00 | Yes | N/A | No | N/A | No Change | Yes | Work scope duration increased at TAO request | TAO | Yes | TSO requested change due to system constraints | TSO | Yes | TSO requested change due to system constraints | TSO | No | N/A | No Change | Yes | TSO requested change due to system constraints | TSO | Yes | N/A | No Change
AGHADA T2014 | AT14 | Clean CSE stand-off insulators in Aghada | 901167032 | Yes | TO-21-AD-T2014-01 | March | 2021-03-08 | 2021-03-09 | 2 | N/A | 10-MAR-21 10:07:00 | 12-MAR-21 19:05:00 | Yes | N/A | No | N/A | No Change | Yes | Work scope duration increased at TAO request | TAO | Yes | TSO requested change due to system constraints | TSO | Yes | TSO requested change due to system constraints | TSO | No | N/A | No Change | Yes | TSO requested change due to system constraints | TSO | Yes | N/A | No Change
AGHADA T2014 | AT14 | P3 Protection maintenance of 7SA612, R1Z23b, | Protection | Yes | TO-21-AD-T2014-01 | March | 2021-03-10 | 2021-03-11 | 2 | N/A | 10-MAR-21 10:07:00 | 12-MAR-21 19:05:00 | Yes | N/A | No | N/A | No Change | Yes | Work scope duration increased at TAO request | TAO | Yes | TSO requested change due to system constraints | TSO | Yes | TSO requested change due to system constraints | TSO | No | N/A | No Change | Yes | TSO requested change due to system constraints | TSO | Yes | N/A | No Change
ARDNACRUSHA GIS T101 | AA1 | Cable Insp. 110kV XLPE | 901212143 | Yes | TO-21-AA GIS-T101-02 | July | - | - | 4 | N/A | 12-JUL-21 09:25:00 | 16-JUL-21 11:02:00 | Yes | N/A | No | N/A | No Change | Yes | Outage duration changed to facilitate Capex works | TAO | No | N/A | No Change | No | N/A | No Change | No | N/A | No Change | No | N/A | No Change | Yes | N/A | No Change
ARDNACRUSHA GIS T101 | AA1 | 110KV GIS Cubicle Operational Test | 901212238 | Yes | TO-21-AA GIS-T101-02 | July | - | - | 4 | N/A | 12-JUL-21 09:25:00 | 16-JUL-21 11:02:00 | Yes | N/A | No | N/A | No Change | Yes | Outage duration changed to facilitate Capex works | TAO | No | N/A | No Change | No | N/A | No Change | No | N/A | No Change | No | N/A | No Change | Yes | N/A | No Change
ARDNACRUSHA GIS T102 | AA2 | Cable Insp. 110kV XLPE | 901212144 | Yes | TO-21-AA GIS-T102-02 | June | - | - | 4 | N/A | 11-JUN-21 10:01:00 | 16-JUN-21 10:09:00 | Completed in Previous Outage Season | N/A | No | N/A | No Change | Yes | Changed as per generator request | GEN | Yes | Rescheduled as per generator request | GEN | Yes | Rescheduled as per generator request | GEN | Completed in Previous Outage Season | Completed in Previous Outage Season | TAO | Yes | Generator requested change to Committed Outage Programme | GEN | N/A | N/A | N/A
ARDNACRUSHA GIS T103 | AA3 | 110KV GIS Cubicle Operational Test | 901212239 | Yes | TO-21-AA GIS-T103-02 | August | - | - | 4 | N/A | 13-AUG-21 21:22:00 | 23-SEP-21 17:49:00 | No | Unscheduled due to TAO resources | Yes | Rescheduled to align with generator outage | GEN | Yes | Changed as per generator request | GEN | Yes | Rescheduled as per generator request | GEN | Yes | Rescheduled as per generator request | GEN | No | N/A | No Change | No | N/A | No Change | No | Unscheduled due to TAO resources | TAO
ARDNACRUSHA GIS T103 | AA3 | Cable Insp. 110kV XLPE | 901212145 | Yes | TO-21-AA GIS-T103-02 | August | - | - | 4 | N/A | 13-AUG-21 21:22:00 | 23-SEP-21 17:49:00 | Yes | N/A | Yes | Rescheduled to align with generator outage | GEN | Yes | Changed as per generator request | GEN | Yes | Rescheduled as per generator request | GEN | Yes | Rescheduled as per generator request | GEN | No | N/A | No Change | No | N/A | No Change | Yes | N/A | No Change
ARDNACRUSHA GIS T104 | AA4 | Cable Insp. 110kV XLPE | 901212146 | Yes | TO-21-AA GIS-T104-01 | April | 2021-04-06 | 2021-04-19 | 14 | N/A | 10-MAR-21 09:07:00 | 12-AUG-21 14:06:00 | Yes | N/A | Yes | Rescheduled as per generator request | GEN | Yes | Changed as per generator request | GEN | Yes | Rescheduled as per generator request | GEN | Yes | Rescheduled as per generator request | GEN | No | N/A | No Change | Yes | Generator requested change to Committed Outage Programme | GEN | Yes | N/A | No Change
ARDNACRUSHA GIS T104 | AA4 | 110KV GIS Cubicle Operational Test | 901212240 | Yes | TO-21-AA GIS-T104-01 | April | 2021-04-06 | 2021-04-19 | 14 | N/A | 10-MAR-21 09:07:00 | 12-AUG-21 14:06:00 | Yes | N/A | Yes | Rescheduled as per generator request | GEN | Yes | Changed as per generator request | GEN | Yes | Rescheduled as per generator request | GEN | Yes | Rescheduled as per generator request | GEN | No | N/A | No Change | Yes | Generator requested change to Committed Outage Programme | GEN | Yes | N/A | No Change
ATHEA 110SA1-2CB | Athea AH1, Beenanaspuck & Tobertoreen XT1, Dromada DR1 | 110kV SF6 Cubicle Operational Test - ATE | 901129582 | Yes | TO-21-ATE-110SA1-2CB | July | - | - | 4 | N/A | 28-JUN-21 08:32:00 | 02-JUL-21 14:30:00 | Yes | N/A | Yes | Dates reschedued to align with Capex works CP0726 | TSO | Yes | Work scope duration increased at TAO request | TAO | No | N/A | No Change | No | N/A | No Change | No | N/A | No Change | No | N/A | No Change | Yes | N/A | No Change
ATHEA 110SA1-2CB | Athea AH1, Beenanaspuck & Tobertoreen XT1, Dromada DR1 | 110kV Sect / Dist Operational Test - SA2 | 901130093 | Yes | TO-21-ATE-110SA1-2CB | July | - | - | 4 | N/A | 28-JUN-21 08:32:00 | 02-JUL-21 14:30:00 | Yes | N/A | Yes | Dates reschedued to align with Capex works CP0726 | TSO | Yes | Work scope duration increased at TAO request | TAO | No | N/A | No Change | No | N/A | No Change | No | N/A | No Change | No | N/A | No Change | Yes | N/A | No Change
ATHEA 110SA1-2CB | Athea AH1, Beenanaspuck & Tobertoreen XT1, Dromada DR1 | 110kV Sect / Dist Operational Test - SA1 | 901130094 | Yes | TO-21-ATE-110SA1-2CB | July | - | - | 4 | N/A | 28-JUN-21 08:32:00 | 02-JUL-21 14:30:00 | Yes | N/A | Yes | Dates reschedued to align with Capex works CP0726 | TSO | Yes | Work scope duration increased at TAO request | TAO | No | N/A | No Change | No | N/A | No Change | No | N/A | No Change | No | N/A | No Change | Yes | N/A | No Change
ATHEA DROMADA | Athea AH1, Beenanaspuck & Tobertoreen XT1, Dromada DR1 | P2 Protection maintenance of 7SA612, GRL100 - Athea | Protection | Yes | TO-21-ATE-DRO-1-01 | July | - | - | 5 | N/A | 28-JUN-21 08:32:00 | 02-JUL-21 14:30:00 | No | Unscheduled due to TAO resources | Yes | Dates reschedued to align with Capex works CP0726 | TSO | No | N/A | No Change | No | N/A | No Change | No | N/A | No Change | No | N/A | No Change | No | N/A | No Change | No | Unscheduled due to TAO resources | TAO
ATHEA DROMADA | Athea AH1, Beenanaspuck & Tobertoreen XT1, Dromada DR1 | P2 Protection maintenance of 7SA612, GRL100 - Dromada | Protection | Yes | TO-21-ATE-DRO-1-01 | July | - | - | 5 | N/A | 28-JUN-21 08:32:00 | 02-JUL-21 14:30:00 | Yes | N/A | Yes | Dates reschedued to align with Capex works CP0726 | TSO | No | N/A | No Change | No | N/A | No Change | No | N/A | No Change | No | N/A | No Change | No | N/A | No Change | Yes | N/A | No Change
ATHEA DROMADA | Athea AH1, Beenanaspuck & Tobertoreen XT1, Dromada DR1 | Clean CSE stand-off insulators in Dromada | 901167020 | Yes | TO-21-ATE-DRO-1-01 | July | - | - | 5 | N/A | 28-JUN-21 08:32:00 | 02-JUL-21 14:30:00 | Yes | N/A | Yes | Dates reschedued to align with Capex works CP0726 | TSO | No | N/A | No Change | No | N/A | No Change | No | N/A | No Change | No | N/A | No Change | No | N/A | No Change | Yes | N/A | No Change
ATHEA DROMADA | Athea AH1, Beenanaspuck & Tobertoreen XT1, Dromada DR1 | 110kV SF6 Cubicle Operational Test - ATE | 901212429 | Yes | TO-21-ATE-DRO-1-01 | July | - | - | 5 | N/A | 28-JUN-21 08:32:00 | 02-JUL-21 14:30:00 | Yes | N/A | Yes | Dates reschedued to align with Capex works CP0726 | TSO | No | N/A | No Change | No | N/A | No Change | No | N/A | No Change | No | N/A | No Change | No | N/A | No Change | Yes | N/A | No Change
ATHEA KNOCKANURE | Athea AH1, Beenanaspuck & Tobertoreen XT1, Dromada DR1 | 110kV SF6 Cubicle Ordinary Service - ATE | 901042193 | Yes | TO-21-ATE-KNR-1-01 | July | - | - | 5 | N/A | 28-JUN-21 08:32:00 | 02-JUL-21 14:30:00 | Yes | N/A | Yes | Dates reschedued to align with Capex works CP0726 | TSO | No | N/A | No Change | No | N/A | No Change | No | N/A | No Change | No | N/A | No Change | No | N/A | No Change | Yes | N/A | No Change
ATHEA KNOCKANURE | Athea AH1, Beenanaspuck & Tobertoreen XT1, Dromada DR1 | Cable Insp. 110kV XLPE - ATE | 901129104 | Yes | TO-21-ATE-KNR-1-01 | July | - | - | 5 | N/A | 28-JUN-21 08:32:00 | 02-JUL-21 14:30:00 | Yes | N/A | Yes | Dates reschedued to align with Capex works CP0726 | TSO | No | N/A | No Change | No | N/A | No Change | No | N/A | No Change | No | N/A | No Change | No | N/A | No Change | Yes | N/A | No Change
ATHEA KNOCKANURE | Athea AH1, Beenanaspuck & Tobertoreen XT1, Dromada DR1 | P2 Protection maintenance of 7SA612, GRL100 - Knockanure | Protection | Yes | TO-21-ATE-KNR-1-01 | July | - | - | 5 | N/A | 28-JUN-21 08:32:00 | 02-JUL-21 14:30:00 | Yes | N/A | Yes | Dates reschedued to align with Capex works CP0726 | TSO | No | N/A | No Change | No | N/A | No Change | No | N/A | No Change | No | N/A | No Change | No | N/A | No Change | Yes | N/A | No Change
ATHEA KNOCKANURE | Athea AH1, Beenanaspuck & Tobertoreen XT1, Dromada DR1 | Cable Insp. 110kV XLPE - KCR | 901129103 | Yes | TO-21-ATE-KNR-1-01 | July | - | - | 5 | N/A | 28-JUN-21 08:32:00 | 02-JUL-21 14:30:00 | Yes | N/A | Yes | Dates reschedued to align with Capex works CP0726 | TSO | No | N/A | No Change | No | N/A | No Change | No | N/A | No Change | No | N/A | No Change | No | N/A | No Change | Yes | N/A | No Change
ATHEA KNOCKANURE | Athea AH1, Beenanaspuck & Tobertoreen XT1, Dromada DR1 | 110kV SF6 Cubicle Operational Test - KCR | 901043731 | Yes | TO-21-ATE-KNR-1-01 | July | - | - | 5 | N/A | 28-JUN-21 08:32:00 | 02-JUL-21 14:30:00 | Yes | N/A | Yes | Dates reschedued to align with Capex works CP0726 | TSO | No | N/A | No Change | No | N/A | No Change | No | N/A | No Change | No | N/A | No Change | No | N/A | No Change | Yes | N/A | No Change
ATHEA T121 | Athea AH1 | Clean CSE stand-off insulators at transf | 901167024 | Yes | TO-21-ATE-T121-01 | July | - | - | 5 | N/A | 28-JUN-21 08:32:00 | 02-JUL-21 14:30:00 | Yes | N/A | Yes | Dates reschedued to align with Capex works CP0726 | TSO | No | N/A | No Change | No | N/A | No Change | No | N/A | No Change | No | N/A | No Change | No | N/A | No Change | Yes | N/A | No Change
ATHEA T121 | Athea AH1 | 110kV SF6 Cubicle Operational Test - ATE | 901212519 | Yes | TO-21-ATE-T121-01 | July | - | - | 5 | N/A | 28-JUN-21 08:32:00 | 02-JUL-21 14:30:00 | Yes | N/A | Yes | Dates reschedued to align with Capex works CP0726 | TSO | No | N/A | No Change | No | N/A | No Change | No | N/A | No Change | No | N/A | No Change | No | N/A | No Change | Yes | N/A | No Change
AUGHINISH SEALROCK 3 | SK3 | Replace bonding leads - corrosion on LB | 901166995 | Yes | TO-21-AUG-SK-3-01 | June | - | - | 6 | TAO requested repairs in season | 24-JUN-21 16:01:00 | 28-JUN-21 16:30:00 | Yes | N/A | No | N/A | No Change | Yes | Changed as per generator request | GEN | Yes | Generator requested works be completed at later half of their outage | GEN | Yes | Generator requested works be completed at later half of their outage | GEN | Yes | TAO requested repairs in season | TAO | Yes | Generator requested change to Committed Outage Programme | GEN | Yes | N/A | No Change
AUGHINISH SEALROCK 3 | SK3 | 6 months - Sealrock 3 110 kV Cubicle R & S Phases Overhead busbar adjacent the cubicle Corrective maintenance action required within 6 months HOTSPOT DUE: 27Jul2021 | 901212049 | No | TO-21-AUG-SK-3-01 | - | - | - | - | TAO requested repairs in season | 24-JUN-21 16:01:00 | 28-JUN-21 16:30:00 | Yes | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Yes | Generator requested works be completed at later half of their outage | GEN | Yes | Generator requested works be completed at later half of their outage | GEN | Yes | TAO requested repairs in season | TAO | Yes | Generator requested change to Committed Outage Programme | GEN | Yes | N/A | No Change
AUGHINISH SEALROCK 3 | SK3 | Replace bonding leads - corrosion on LB | 901166481 | Yes | TO-21-AUG-SK-3-01 | June | - | - | 6 | N/A | 24-JUN-21 16:01:00 | 28-JUN-21 16:30:00 | Yes | N/A | No | N/A | No Change | Yes | Changed as per generator request | GEN | Yes | Generator requested works be completed at later half of their outage | GEN | Yes | Generator requested works be completed at later half of their outage | GEN | No | N/A | No Change | Yes | Generator requested change to Committed Outage Programme | GEN | Yes | N/A | No Change
AUGHINISH SEALROCK 3 | SK3 | Low Gas / Leak: EMP AMS: Overhaul T103/A | 901148360 | Yes | TO-21-AUG-SK-3-01 | June | - | - | 6 | N/A | 24-JUN-21 16:01:00 | 28-JUN-21 16:30:00 | Yes | N/A | No | N/A | No Change | Yes | Changed as per generator request | GEN | Yes | Generator requested works be completed at later half of their outage | GEN | Yes | Generator requested works be completed at later half of their outage | GEN | No | N/A | No Change | Yes | Generator requested change to Committed Outage Programme | GEN | Yes | N/A | No Change
AUGHINISH SEALROCK 3 | SK3 | 110kV SF6 Cubicle Operational Test | 901129644 | Yes | TO-21-AUG-SK-3-01 | June | - | - | 6 | N/A | 24-JUN-21 16:01:00 | 28-JUN-21 16:30:00 | Yes | N/A | No | N/A | No Change | Yes | Changed as per generator request | GEN | Yes | Generator requested works be completed at later half of their outage | GEN | Yes | Generator requested works be completed at later half of their outage | GEN | No | N/A | No Change | Yes | Generator requested change to Committed Outage Programme | GEN | Yes | N/A | No Change
AUGHINISH SEALROCK 3 | SK3 | Replace bonding leads - corrosion on LB | 901166995 | No | TO-21-AUG-SK-3-01 | - | - | - | - | N/A | 24-JUN-21 16:01:00 | 28-JUN-21 16:30:00 | Yes | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Yes | Generator requested works be completed at later half of their outage | GEN | Yes | Generator requested works be completed at later half of their outage | GEN | No | N/A | No Change | Yes | Generator requested change to Committed Outage Programme | GEN | Yes | N/A | No Change
AUGHINISH SEALROCK 4 | SK4 | Replace bonding leads in Aughinish stati | 901166997 | Yes | TO-21-AUG-SK-4-01 | June | - | - | 5 | TAO requested repairs in season | 05-JUL-21 09:43:00 | 09-JUL-21 13:33:00 | Yes | N/A | Yes | Rescheduled to align with generator outage | TSO | No | N/A | No Change | No | N/A | No Change | No | N/A | No Change | Yes | TAO requested repairs in season | TAO | No | N/A | No Change | Yes | N/A | No Change
AUGHINISH SEALROCK 4 | SK4 | 110kV SF6 Cubicle Operational Test | 901129645 | Yes | TO-21-AUG-SK-4-01 | June | - | - | 5 | TAO requested repairs in season | 05-JUL-21 09:43:00 | 09-JUL-21 13:33:00 | Yes | N/A | Yes | Rescheduled to align with generator outage | TSO | No | N/A | No Change | No | N/A | No Change | No | N/A | No Change | Yes | TAO requested repairs in season | TAO | No | N/A | No Change | Yes | N/A | No Change
AUGHINISH SEALROCK 4 | SK4 | 3 monthsSealrock 4 110 kV Cubicle T Phase Cable sheath lug connection T Phase Corrective maintenance action required within 3 months HOTSPOT DUE:27Apr2021 | 901212079 | No | TO-21-AUG-SK-4-01 | - | - | - | - | N/A | 05-JUL-21 09:43:00 | 09-JUL-21 13:33:00 | Yes | N/A | N/A | N/A | N/A | N/A | N/A | N/A | No | N/A | No Change | No | N/A | No Change | No | N/A | No Change | No | N/A | No Change | Yes | N/A | No Change
AUGHINISH SEALROCK 4 | SK4 | 6 months - Sealrock 4 110 kV Cubicle T Phase T Phase DL connection, SA/Line side A corrective maintenance action will be necessary during the next planned maintenance. HOTSPOT DUE:27Jul2021 | 901212082 | No | TO-21-AUG-SK-4-01 | - | - | - | - | N/A | 05-JUL-21 09:43:00 | 09-JUL-21 13:33:00 | Yes | N/A | N/A | N/A | N/A | N/A | N/A | N/A | No | N/A | No Change | No | N/A | No Change | No | N/A | No Change | No | N/A | No Change | Yes | N/A | No Change
BALLYVOUSKILL COOMATAGGART | Grousemount GD1, Cleanrath YT1 | Cable Insp. 110kV XLPE | 901211501 | No | TO-21-BVK-COT-1-01 | - | - | - | - | TAO requested repairs in season | 05-JUL-21 09:02:00 | 09-JUL-21 14:34:00 | Yes | N/A | N/A | N/A | N/A | N/A | N/A | N/A | No | N/A | No Change | No | N/A | No Change | Yes | TAO requested repairs in season | TAO | No | N/A | No Change | Yes | N/A | No Change
BALLYVOUSKILL COOMATAGGART | Grousemount GD1, Cleanrath YT1 | 3 months - Ballyvouskill 110 kV cubicle. S phase S phase 110 kV VT connection, DL side. A corrective maintenance action will be required within 3 months. | 901212718 | No | TO-21-BVK-COT-1-02 | - | - | - | - | TAO requested repairs in season | 10-MAR-21 09:40:00 | 11-MAR-21 17:30:00 | Yes | N/A | N/A | N/A | N/A | N/A | N/A | N/A | No | N/A | No Change | No | N/A | No Change | Yes | TAO requested repairs in season | TAO | No | N/A | No Change | Yes | N/A | No Change
BALLYVOUSKILL COOMATAGGART | Grousemount GD1, Cleanrath YT1 | 3 months - Ballyvouskill 110 kV cubicle, S & T phases R, S & T phases 110 kV CT connections. A corrective maintenance action will be required in 3 months. | 901212719 | No | TO-21-BVK-COT-1-02 | - | - | - | - | Scheduled in season by the TSO as requirement for inspection post EI. | 10-MAR-21 09:40:00 | 11-MAR-21 17:30:00 | Yes | N/A | N/A | N/A | N/A | N/A | N/A | N/A | No | N/A | No Change | No | N/A | No Change | Yes | Scheduled in season by the TSO as requirement for inspection post EI. | TSO | No | N/A | No Change | Yes | N/A | No Change
BALLYWATER CRANE | Ballywater BW1 | Hotspot 1, R-phase CT/VT (repair by 4th Dec 2020) | 901211989 | Yes | TO-21-BWR-CRA-1-02 | June | - | - | 4 | N/A | 2021-07-08 17:36 | 2021-07-09 13:41 | Yes | N/A | Yes | Dates reschedued to align with Capex works CP0972 | TSO | Yes | TAO completed works earlier than anticipated | TAO | Yes | Reschedued to align with Capex works | TSO | Yes | Reschedued to align with Capex works | TSO | No | N/A | No Change | No | N/A | No Change | Yes | N/A | No Change
BALLYWATER CRANE | Ballywater BW1 | 6 Months - Hotspot 2, T and S phases DA (repair by 4th May 2021). HOTSPOT DUE:02AUG2021. | 901168066 | Yes | TO-21-BWR-CRA-1-02 | June | - | - | 4 | N/A | 2021-07-08 17:36 | 2021-07-09 13:41 | Yes | N/A | Yes | Dates reschedued to align with Capex works CP0972 | TSO | Yes | TAO completed works earlier than anticipated | TAO | Yes | Reschedued to align with Capex works | TSO | Yes | Reschedued to align with Capex works | TSO | No | N/A | No Change | No | N/A | No Change | Yes | N/A | No Change
BALLYWATER CRANE | Ballywater BW1 | 110kV SF6 Cubicle Operational Test | 901212432 | Yes | TO-21-BWR-CRA-1-02 | June | - | - | 4 | N/A | 2021-07-08 17:36 | 2021-07-09 13:41 | Yes | N/A | Yes | Dates reschedued to align with Capex works CP0972 | TSO | Yes | TAO completed works earlier than anticipated | TAO | Yes | Reschedued to align with Capex works | TSO | Yes | Reschedued to align with Capex works | TSO | No | N/A | No Change | No | N/A | No Change | Yes | N/A | No Change
BALLYWATER CRANE | Ballywater BW1 | Bulb Blown in Mech Box | 901211140 | No | TO-21-BWR-CRA-1-02 | - | - | - | - | TAO requested repairs in season | 2021-07-08 17:36 | 2021-07-09 13:41 | Yes | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Yes | Reschedued to align with Capex works | TSO | Yes | Reschedued to align with Capex works | TSO | Yes | TAO requested repairs in season | TAO | No | N/A | No Change | Yes | N/A | No Change
BELLACORICK SRAHNAKILLY | Oweninny OY1 | 110kV SF6 Cubicle Operational Test - Srahnakilly | 901212438 | Yes | TO-21-BK-SKY-1-01 | June | - | - | 5 | N/A | 06-JUL-21 11:46:00 | 14-JUL-21 12:20:00 | Yes | N/A | Yes | Rescheduled to align with generator outage | GEN | Yes | Outage increased to facilitate generator works | GEN | Yes | Outage began late as per generator request | GEN | Yes | Outage began late as per generator request | GEN | No | N/A | No Change | Yes | Generator requested change | GEN | Yes | N/A | No Change
BELLACORICK SRAHNAKILLY | Oweninny OY1 | 110kV SF6 Cubicle Operational Test - Bellacorrick | 901212439 | Yes | TO-21-BK-SKY-1-01 | June | - | - | 5 | N/A | 06-JUL-21 11:46:00 | 14-JUL-21 12:20:00 | Yes | N/A | Yes | Rescheduled to align with generator outage | GEN | Yes | Outage increased to facilitate generator works | GEN | Yes | Outage began late as per generator request | GEN | Yes | Outage began late as per generator request | GEN | No | N/A | No Change | Yes | Generator requested change | GEN | Yes | N/A | No Change
BELLACORICK SRAHNAKILLY | Oweninny OY1 | Cable Insp. 110kV XLPE | 901171474 | Yes | TO-21-BK-SKY-1-01 | June | - | - | 5 | N/A | 14-SEP-21 08:49:00 | 16-SEP-21 15:12:00 | Yes | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Yes | Outage began late as per generator request | GEN | Yes | Outage began late as per generator request | GEN | No | N/A | No Change | No | N/A | No Change | Yes | N/A | No Change
BELLACORICK SRAHNAKILLY | Oweninny OY1 | 2021PM_Investigation & repair of S-Phase | 901238134 | No | TO-21-BK-SKY-1-02 | - | - | - | - | TAO requested inclusion of works in season. Scheduled to overlap with cable inspection. | 14-SEP-21 08:49:00 | 16-SEP-21 15:12:00 | Yes | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Yes | Outage began late as per generator request | GEN | Yes | Outage began late as per generator request | GEN | Yes | TAO requested inclusion of works in season. Scheduled to overlap with cable inspection. | TAO | No | N/A | No Change | Yes | N/A | No Change
BOGGERAGH CLASHAVOON | Boggeragh BG1 ,BG2, Esk ES1 | 2020HP-1[30]Check (General) E/W Clamps | 901171140 | Yes | TO-21-BGH-CLA-1-01 | March | 2021-03-01 | 2021-03-05 | 5 | N/A | 02-MAR-21 17:56:00 | 05-MAR-21 23:09:00 | Yes | N/A | No | N/A | No Change | Yes | Work scope duration increased at TAO request | TAO | Yes | Outage began late as per generator request | GEN | Yes | Outage began late as per generator request | GEN | No | N/A | No Change | No | N/A | No Change | Yes | N/A | No Change
BOGGERAGH CLASHAVOON | Boggeragh BG1 ,BG2, Esk ES1 | 2020HP-1[10]Earths-Replace At Pole Top | 901171254 | Yes | TO-21-BGH-CLA-1-01 | March | 2021-03-01 | 2021-03-05 | 5 | N/A | 02-MAR-21 17:56:00 | 05-MAR-21 23:09:00 | Yes | N/A | No | N/A | No Change | Yes | Work scope duration increased at TAO request | TAO | Yes | Outage began late as per generator request | GEN | Yes | Outage began late as per generator request | GEN | No | N/A | No Change | No | N/A | No Change | Yes | N/A | No Change
BOGGERAGH CLASHAVOON | Boggeragh BG1 ,BG2, Esk ES1 | 2020HP-1[13]Earths-Replace At Pole Top | 901171255 | Yes | TO-21-BGH-CLA-1-01 | March | 2021-03-01 | 2021-03-05 | 5 | N/A | 02-MAR-21 17:56:00 | 05-MAR-21 23:09:00 | Yes | N/A | No | N/A | No Change | Yes | Work scope duration increased at TAO request | TAO | Yes | Outage began late as per generator request | GEN | Yes | Outage began late as per generator request | GEN | No | N/A | No Change | No | N/A | No Change | Yes | N/A | No Change
BOGGERAGH CLASHAVOON | Boggeragh BG1 ,BG2, Esk ES1 | 2020HP-1[45]Earths-Replace At Pole Top | 901171256 | Yes | TO-21-BGH-CLA-1-01 | March | 2021-03-01 | 2021-03-05 | 5 | N/A | 02-MAR-21 17:56:00 | 05-MAR-21 23:09:00 | Yes | N/A | No | N/A | No Change | Yes | Work scope duration increased at TAO request | TAO | Yes | Outage began late as per generator request | GEN | Yes | Outage began late as per generator request | GEN | No | N/A | No Change | No | N/A | No Change | Yes | N/A | No Change
BOGGERAGH CLASHAVOON | Boggeragh BG1 ,BG2, Esk ES1 | 2020HP-1[60]Earths-Replace At Pole Top | 901171257 | Yes | TO-21-BGH-CLA-1-01 | March | 2021-03-01 | 2021-03-05 | 5 | N/A | 02-MAR-21 17:56:00 | 05-MAR-21 23:09:00 | Yes | N/A | No | N/A | No Change | Yes | Work scope duration increased at TAO request | TAO | Yes | Outage began late as per generator request | GEN | Yes | Outage began late as per generator request | GEN | No | N/A | No Change | No | N/A | No Change | Yes | N/A | No Change
BOGGERAGH CLASHAVOON | Boggeragh BG1 ,BG2, Esk ES1 | 2020HP-1[77]Earths-Replace At Pole Top | 901171258 | Yes | TO-21-BGH-CLA-1-01 | March | 2021-03-01 | 2021-03-05 | 5 | N/A | 02-MAR-21 17:56:00 | 05-MAR-21 23:09:00 | Yes | N/A | No | N/A | No Change | Yes | Work scope duration increased at TAO request | TAO | Yes | Outage began late as per generator request | GEN | Yes | Outage began late as per generator request | GEN | No | N/A | No Change | No | N/A | No Change | Yes | N/A | No Change
BOGGERAGH CLASHAVOON | Boggeragh BG1 ,BG2, Esk ES1 | 110kV SF6 Cubicle Operational Test - Clashavoon | 901212440 | Yes | TO-21-BGH-CLA-1-01 | March | 2021-03-01 | 2021-03-05 | 5 | N/A | 02-MAR-21 17:56:00 | 05-MAR-21 23:09:00 | Yes | N/A | No | N/A | No Change | Yes | Work scope duration increased at TAO request | TAO | Yes | Outage began late as per generator request | GEN | Yes | Outage began late as per generator request | GEN | No | N/A | No Change | No | N/A | No Change | Yes | N/A | No Change
BOGGERAGH T121 | Boggeragh BG1 | 110kV SF6 Cubicle Operational Test | 901212520 | Yes | TO-21-BGH-T121-01 | March | 2021-03-01 | 2021-03-05 | 5 | N/A | 02-MAR-21 17:56:00 | 05-MAR-21 23:09:00 | Yes | N/A | No | N/A | No Change | Yes | Work scope duration increased at TAO request | TAO | Yes | Outage began late as per generator request | GEN | Yes | Outage began late as per generator request | GEN | No | N/A | No Change | No | N/A | No Change | Yes | N/A | No Change
BOGGERAGH T132 | Boggeragh BG2 | 110kV SF6 Cubicle Operational Test | 901212521 | Yes | TO-21-BGH-T132-01 | March | 2021-03-01 | 2021-03-05 | 5 | N/A | 02-MAR-21 17:56:00 | 05-MAR-21 23:09:00 | Yes | N/A | No | N/A | No Change | Yes | Work scope duration increased at TAO request | TAO | Yes | Outage began late as per generator request | GEN | Yes | Outage began late as per generator request | GEN | No | N/A | No Change | No | N/A | No Change | Yes | N/A | No Change
CARRIGADROHID T103 | LE3 | 110kV SF6 Cubicle Operational Test | 901212522 | Yes | TO-21-CD-T103-01 | April | 2021-04-28 | 2021-04-29 | 1 | N/A | 15-MAR-21 11:16:00 | 29-MAR-21 17:45:00 | Yes | N/A | Yes | Dates reschedued to align with Capex works | TSO | Yes | Outage moved to facilitate Capex works | TSO | Yes | Work scope duration increased at TAO request | TAO | No | N/A | No Change | No | N/A | No Change | No | N/A | No Change | Yes | N/A | No Change
CATHALEENS FALL CLIFF | ER1/ER2 | P3 Protection maintenance of 7SA511 | Protection | Yes | TO-21-CF-CL-1-01 | April | 2021-04-15 | 2021-04-16 | 2 | N/A | 12-APR-21 11:46:00 | 19-APR-21 18:03:00 | Yes | N/A | No | N/A | No Change | Yes | Work scope duration increased at TAO request | TAO | Yes | Work scope duration increased at TAO request | TAO | No | N/A | No Change | No | N/A | No Change | No | N/A | No Change | Yes | N/A | No Change
CATHALEENS FALL CLIFF | ER1/ER2 | 110kV SF6 Cubicle Operational Test | 901212444 | Yes | TO-21-CF-CL-1-01 | April | 2021-04-15 | 2021-04-16 | 2 | N/A | 12-APR-21 11:46:00 | 19-APR-21 18:03:00 | Yes | N/A | No | N/A | No Change | Yes | Work scope duration increased at TAO request | TAO | Yes | Work scope duration increased at TAO request | TAO | No | N/A | No Change | No | N/A | No Change | No | N/A | No Change | Yes | N/A | No Change
CATHALEENS FALL T103 | ER3 | 110kV SF6 Cubicle Operational Test | 901212523 | Yes | TO-21-CF-T103-01 | June | - | - | 1 | N/A | 14-JUN-21 16:14:00 | 02-JUL-21 18:29:00 | Yes | N/A | No | N/A | No Change | Yes | Changed as per generator request | GEN | Yes | Rescheduled as per generator request | GEN | Yes | Rescheduled as per generator request | GEN | No | N/A | No Change | No | N/A | No Change | Yes | N/A | No Change
CATHALEENS FALL T104 | ER4 | HOT SPOT CATHALEENS FALL T104 T PHASE CT HOT SPOT | 901206431 | Yes | TO-21-CF-T104-01 | September | - | - | 2 | N/A | 2021-09-06 09:12 | 2021-09-10 17:31 | No | Work item was deferred following generator request | No | N/A | No Change | Yes | Changed as per generator request | GEN | Yes | Rescheduled as per generator request | GEN | Yes | Rescheduled as per generator request | GEN | No | N/A | No Change | Yes | Generator requested change to Committed Outage Programme | GEN | No | Work item was deferred to 2022 following generator request | GEN
CATHALEENS FALL T104 | ER4 | 110kV SF6 Cubicle Operational Test | 901212524 | Yes | TO-21-CF-T104-01 | September | - | - | 2 | N/A | 2021-09-06 09:12 | 2021-09-10 17:31 | Yes | N/A | No | N/A | No Change | Yes | Changed as per generator request | GEN | Yes | Rescheduled as per generator request | GEN | Yes | Rescheduled as per generator request | GEN | No | N/A | No Change | Yes | Generator requested change to Committed Outage Programme | GEN | Yes | N/A | No Change
CLIFF T101 | ER1 | 110KV SF6 Cubicle Ordinary Service | 901212651 | Yes | TO-21-CL-T101-01 | April | 2021-04-13 | 2021-04-20 | 8 | N/A | 12-APR-21 11:47:00 | 26-APR-21 15:40:00 | Yes | N/A | No | N/A | No Change | Yes | Changed as per generator request | GEN | Yes | Rescheduled as per generator request | GEN | No | N/A | No Change | No | N/A | No Change | Yes | Generator requested change to Committed Outage Programme | GEN | Yes | N/A | No Change
CLIFF T101 | ER1 | 110KV CUBICLE CONDITION ASSESSMENT | 901212212 | Yes | TO-21-CL-T101-01 | April | 2021-04-13 | 2021-04-20 | 8 | N/A | 12-APR-21 11:47:00 | 26-APR-21 15:40:00 | Yes | N/A | No | N/A | No Change | Yes | Changed as per generator request | GEN | Yes | Rescheduled as per generator request | GEN | No | N/A | No Change | No | N/A | No Change | Yes | Generator requested change to Committed Outage Programme | GEN | Yes | N/A | No Change
CLIFF T102 | ER2 | 110KV SF6 Cubicle Ordinary Service | 901212652 | Yes | TO-21-CL-T102-01 | May | - | - | 6 | N/A | N/A | N/A | No | Unscheduled due to TAO resources | No | N/A | TAO | N/A | N/A | N/A | Yes | Unscheduled due to TAO resources | TAO | N/A | N/A | N/A | No | N/A | No Change | No | N/A | No Change | No | Unscheduled due to TAO resources | TAO
CLIFF T102 | ER2 | 110KV CUBICLE CONDITION ASSESSMENT | 901212213 | Yes | TO-21-CL-T102-01 | May | - | - | 6 | N/A | N/A | N/A | No | Unscheduled due to TAO resources | No | N/A | TAO | N/A | N/A | N/A | Yes | Unscheduled due to TAO resources | TAO | N/A | N/A | N/A | No | N/A | No Change | No | N/A | No Change | No | Unscheduled due to TAO resources | TAO
CLOGHBOOLA TRIEN | Cloghboola CL1, Cloghaneleskirt KI1, Glantaunyalkeen GC1, Glanaruddery DA1, DA2 | P2 Protection maintenance of 7SA612, GRL100 - CBA | Protection | Yes | TO-21-CBA-TRI-1-01 | June | - | - | 3 | N/A | 15-JUN-21 14:17:00 | 18-JUN-21 16:05:00 | No | Work not done due to TAO resourcing constraints | No | N/A | No Change | Yes | TAO completed works earlier than anticipated | TAO | No | N/A | No Change | No | N/A | No Change | No | N/A | No Change | No | N/A | No Change | No | Work not done due to TAO resourcing constraints | TAO
CLOGHBOOLA TRIEN | Cloghboola CL1, Cloghaneleskirt KI1, Glantaunyalkeen GC1, Glanaruddery DA1, DA2 | P2 Protection maintenance of 7SA612, GRL100 _ TRI | Protection | Yes | TO-21-CBA-TRI-1-01 | June | - | - | 3 | N/A | 15-JUN-21 14:17:00 | 18-JUN-21 16:05:00 | No | Work not done due to TAO resourcing constraints | No | N/A | No Change | Yes | TAO completed works earlier than anticipated | TAO | No | N/A | No Change | No | N/A | No Change | No | N/A | No Change | No | N/A | No Change | No | Work not done due to TAO resourcing constraints | TAO
CLOGHBOOLA TRIEN | Cloghboola CL1, Cloghaneleskirt KI1, Glantaunyalkeen GC1, Glanaruddery DA1, DA2 | 110kV SF6 Cubicle Operational Test - Cloghboola | 901212449 | Yes | TO-21-CBA-TRI-1-01 | June | - | - | 3 | N/A | 15-JUN-21 14:17:00 | 18-JUN-21 16:05:00 | Yes | N/A | No | N/A | No Change | Yes | TAO completed works earlier than anticipated | TAO | No | N/A | No Change | No | N/A | No Change | No | N/A | No Change | No | N/A | No Change | Yes | N/A | No Change
CLOGHBOOLA TRIEN | Cloghboola CL1, Cloghaneleskirt KI1, Glantaunyalkeen GC1, Glanaruddery DA1, DA2 | 110kV SF6 Cubicle Operational Test - Trien | 901212450 | Yes | TO-21-CBA-TRI-1-01 | June | - | - | 3 | N/A | 15-JUN-21 14:17:00 | 18-JUN-21 16:05:00 | Yes | N/A | No | N/A | No Change | Yes | TAO completed works earlier than anticipated | TAO | No | N/A | No Change | No | N/A | No Change | No | N/A | No Change | No | N/A | No Change | Yes | N/A | No Change
CLOGHBOOLA TRIEN | Cloghboola CL1, Cloghaneleskirt KI1, Glantaunyalkeen GC1, Glanaruddery DA1, DA2 | Clean CSE stand-off insulators in Cloghb | 901155245 | Yes | TO-21-CBA-TRI-1-01 | June | - | - | 3 | N/A | 15-JUN-21 14:17:00 | 18-JUN-21 16:05:00 | Yes | N/A | No | N/A | No Change | Yes | TAO completed works earlier than anticipated | TAO | No | N/A | No Change | No | N/A | No Change | No | N/A | No Change | No | N/A | No Change | Yes | N/A | No Change
CLOGHBOOLA TRIEN | Cloghboola CL1, Cloghaneleskirt KI1, Glantaunyalkeen GC1, Glanaruddery DA1, DA2 | Water ingress into link box at JB12 - ra | 901155246 | Yes | TO-21-CBA-TRI-1-01 | June | - | - | 3 | N/A | 15-JUN-21 14:17:00 | 18-JUN-21 16:05:00 | Yes | N/A | No | N/A | No Change | Yes | TAO completed works earlier than anticipated | TAO | No | N/A | No Change | No | N/A | No Change | No | N/A | No Change | No | N/A | No Change | Yes | N/A | No Change
CLOGHER MULREAVY | Mulreavy MB1, MB2 | S Phase Hotspot on CT connection Corrective maintenance action is required within 6. 6 months HOTSPOT DUE: 07Jul2021 | 901210782 | No | TO-21-CLO-MRY-1-01 | - | - | - | - | Corrective maintenance item identified in season by the TAO. | 09-AUG-21 07:42:00 | 12-AUG-21 17:01:00 | No | Work not done due to TAO resourcing constraints | N/A | N/A | N/A | N/A | N/A | N/A | Yes | Rescheduled to align with generator works | GEN | Yes | TAO completed works earlier than anticipated | TAO | Yes | Corrective maintenance item identified in season by the TAO | TAO | Yes | Generator requested change | GEN | No | Work not done due to TAO resourcing constraints | TAO
CLOGHER MULREAVY | Mulreavy MB1, MB2 | Cable Insp. 110kV XLPE | 901129091 | Yes | TO-21-CLO-MRY-1-01 | May | - | - | 2 | N/A | 09-AUG-21 07:42:00 | 12-AUG-21 17:01:00 | No | Works cancelled due to TAO resourcing | Yes | Rescheduled to align with generator outage | GEN | Yes | Outage increased to facilitate generator works | GEN | Yes | Rescheduled to align with generator works | GEN | Yes | TAO completed works earlier than anticipated | TAO | No | N/A | No Change | Yes | Generator requested change | GEN | No | Works cancelled due to TAO resourcing | TAO
CLOGHER MULREAVY | Mulreavy MB1, MB2 | P2 Protection maintenance of 7SA612, GRL100, 7SJ804 - CLO | Protection | Yes | TO-21-CLO-MRY-1-01 | May | - | - | 2 | N/A | 09-AUG-21 07:42:00 | 12-AUG-21 17:01:00 | No | Works cancelled due to TAO resourcing | Yes | Rescheduled to align with generator outage | GEN | Yes | Outage increased to facilitate generator works | GEN | Yes | Rescheduled to align with generator works | GEN | Yes | TAO completed works earlier than anticipated | TAO | No | N/A | No Change | Yes | Generator requested change | GEN | No | Works cancelled due to TAO resourcing | TAO
CLOGHER MULREAVY | Mulreavy MB1, MB2 | P2 Protection maintenance of 7SA612, GRL100 - MRY | Protection | Yes | TO-21-CLO-MRY-1-01 | May | - | - | 2 | N/A | 09-AUG-21 07:42:00 | 12-AUG-21 17:01:00 | Yes | N/A | Yes | Rescheduled to align with generator outage | GEN | Yes | Outage increased to facilitate generator works | GEN | Yes | Rescheduled to align with generator works | GEN | Yes | TAO completed works earlier than anticipated | TAO | No | N/A | No Change | Yes | Generator requested change | GEN | Yes | N/A | No Change
CLONKEEN COOMAGEARLAHY | Coomagearlahy CG1/CG2/CG3 | 3 months - Coomagearlahy 110 kV cubicle R, S & T phases. Coomagearlahy 110 kV cubicle. R,S & T phase DL connections A corrective maintenance action will be required within 3 months. HOTSPOT DUE: 13MAY2021 | 901212694 | No | TO-21-CKN-CGL-1-01 | - | - | - | - | TAO requested repairs in season | 12-JUL-21 08:39:00 | 26-JUL-21 16:33:00 | Yes | N/A | N/A | N/A | N/A | N/A | N/A | N/A | No | N/A | No Change | No | N/A | No Change | Yes | TAO requested repairs in season | TAO | No | N/A | No Change | Yes | N/A | No Change
COOMAGEARLAHY 110SA1 | Coomagearlahy CG1/CG2 | O2.Sectionaliser not working from Mimic. | 900801826 | Yes | TO-21-CGL-110SA1-01 | July | - | - | 2 | N/A | 12-JUL-21 08:39:00 | 26-JUL-21 16:33:00 | Yes | N/A | No | N/A | No Change | Yes | TAO requested extra time to complete additional works | TAO | No | N/A | No Change | No | N/A | No Change | No | N/A | No Change | No | N/A | No Change | Yes | N/A | No Change
COOMAGEARLAHY T121 | Coomagearlahy CG3 | 110kV SF6 Cubicle Operational Test | 901212526 | Yes | TO-21-CGL-T121-01 | July | - | - | 1 | N/A | 12-JUL-21 08:39:00 | 26-JUL-21 16:33:00 | Yes | N/A | No | N/A | No Change | Yes | TAO requested extra time to complete additional works | TAO | No | N/A | No Change | No | N/A | No Change | No | N/A | No Change | No | N/A | No Change | Yes | N/A | No Change
COOMAGEARLAHY T122 | Coomagearlahy CG1/CG2 | 110kV SF6 Cubicle Operational Test | 901212527 | Yes | TO-21-CGL-T122-01 | July | - | - | 2 | N/A | 12-JUL-21 08:39:00 | 26-JUL-21 16:33:00 | Yes | N/A | No | N/A | No Change | Yes | TAO requested extra time to complete additional works | TAO | No | N/A | No Change | No | N/A | No Change | No | N/A | No Change | No | N/A | No Change | Yes | N/A | No Change
COOMATAGGART T132 | Grousemount GD1 | 110kV SF6 Cubicle Operational Test | 901217455 | Yes | TO-21-COT-T132-01 | May | - | - | 5 | N/A | 05-JUL-21 09:02:00 | 09-JUL-21 14:34:00 | Yes | N/A | Yes | Rescheduled to align with generator outage | GEN | No | N/A | No Change | Yes | Outage unscheduled for voltage security reasons | TSO | N/A | N/A | N/A | No | N/A | No Change | Yes | TSO requested change due to system constraints | TSO | Yes | N/A | No Change
CORDAL T132 | Cordal DL1, DL2 | 110kV SF6 Cubicle Operational Test | 901212528 | Yes | TO-21-CDL-T132-01 | July | - | - | 1 | N/A | 30-JUN-21 08:25:00 | 30-JUN-21 16:08:00 | Yes | N/A | Yes | Rescheduled to align with generator outage | GEN | No | N/A | No Change | No | N/A | No Change | No | N/A | No Change | No | N/A | No Change | No | N/A | No Change | Yes | N/A | No Change
CORDERRY GARVAGH | Garvagh GH1/GH2, Derrysallagh DS1 | P3 Protection maintenance of 7SA612, GRL100 | Protection | Yes | TO-21-CDY-GRV-1-01 | July | - | - | 7 | N/A | 07-JUL-21 12:35:00 | 15-JUL-21 14:50:00 | Yes | N/A | No | N/A | No Change | No | N/A | No Change | No | N/A | No Change | No | N/A | No Change | No | N/A | No Change | No | N/A | No Change | Yes | N/A | No Change
CORDERRY GARVAGH | Garvagh GH1/GH2, Derrysallagh DS1 | 110kV SF6 Cubicle Ordinary Service | 901212208 | Yes | TO-21-CDY-GRV-1-01 | July | - | - | 7 | N/A | 07-JUL-21 12:35:00 | 15-JUL-21 14:50:00 | Yes | N/A | No | N/A | No Change | No | N/A | No Change | No | N/A | No Change | No | N/A | No Change | No | N/A | No Change | No | N/A | No Change | Yes | N/A | No Change
CORDERRY GARVAGH | Garvagh GH1/GH2, Derrysallagh DS1 | 110KV CUBICLE CONDITION ASSESSMENT | 901212667 | Yes | TO-21-CDY-GRV-1-01 | July | - | - | 7 | N/A | 07-JUL-21 12:35:00 | 15-JUL-21 14:50:00 | Yes | N/A | No | N/A | No Change | No | N/A | No Change | No | N/A | No Change | No | N/A | No Change | No | N/A | No Change | No | N/A | No Change | Yes | N/A | No Change
CORDUFF HUNTSTOWN | Huntstown HN2 | Cable Insp. 220kV Feeder XLPE | 901229212 | Yes | TO-21-CDU-HN-1-01 | March | 2021-03-02 | 2021-03-08 | 7 | N/A | 31-MAR-21 07:30:00 | 17-OCT-21 11:10:00 | Yes | N/A | No | N/A | No Change | No | N/A | No Change | Yes | Huntstown HN2 on forced outage | GEN | Yes | Huntstown HN2 on forced outage | GEN | No | N/A | No Change | Yes | Huntstown HN2 on forced outage | GEN | Yes | N/A | No Change
CUSHALING T101 | ED1 | 110KV SF6 Cubicle Operational Test | 901129668 | Yes | TO-21-CUS-T101-01 | June | - | - | 1 | N/A | 27-JUL-21 19:36:00 | 27-JUL-21 18:27:00 | No | Work not done due to TAO resourcing constraints | Yes | Rescheduled to align with generator outage | GEN | No | N/A | No Change | No | N/A | No Change | No | N/A | No Change | No | N/A | No Change | No | N/A | No Change | No | Work not done due to TAO resourcing constraints | TAO
DERRYIRON RHODE T1/T2 | RP1/RP2 | 110KV SF6 Cubicle Operational Test | 901129636 | Yes | TO-21-DER-T1/T2-01 | June | - | - | 3 | N/A | 01-JUN-21 11:34:00 | 18-JUN-21 14:23:00 | Yes | N/A | No | N/A | No Change | Yes | Changed as per generator request | GEN | Yes | Rescheduled as per generator request | GEN | Yes | Rescheduled as per generator request | GEN | No | N/A | No Change | Yes | Generator requested change | GEN | Yes | N/A | No Change
DERRYIRON RHODE T1/T2 | RP1/RP2 | P1 Protection maintenance of 7SA513 | Protection | Yes | TO-21-DER-T1/T2-01 | May | - | - | 2 | N/A | 01-JUN-21 11:34:00 | 18-JUN-21 14:23:00 | No | Generator had been returned to service before protection maintenance could be scheduled. | Yes | TSO realigned maintenance works so they overlapped with generator outage in the Committed Outage Programme | TSO | Yes | Changed as per generator request | GEN | Yes | Rescheduled as per generator request | GEN | Yes | Rescheduled as per generator request | GEN | No | N/A | No Change | Yes | Generator requested change | GEN | No | Generator had been returned to service before protection maintenance could be scheduled. | TSO
ENNIS SLIEVECALLAN | Knockalassa KD1, Boolinrudda RD1 | Cable Insp. 110kV XLPE | Asset not transferred to ESBN | Yes | TO-21-ENN-SLC-1-01 | July | - | - | 3 | N/A | 17-AUG-21 08:50:00 | 20-AUG-21 13:21:00 | No | Asset not transferred to ESBN | Yes | Rescheduled to align with generator outage | Gen | Yes | Changed as per generator request | GEN | No | N/A | No Change | No | N/A | No Change | No | N/A | No Change | No | N/A | No Change | No | Asset not transferred to ESBN | GEN
FINGLAS HUNTSTOWN | Huntstown HNC | Replace CB counter/ complete CA on VT's & SA's | 901130262 | Yes | TO-21-FIN-HN-1-02 | July | - | - | 2 | N/A | N/A | N/A | No | Unscheduled - Gen outage cancelled due to forced outage of Huntstown HN2 | Yes | Unscheduled - Gen outage cancelled due to forced outage of Huntstown HN2 | GEN | No | N/A | No Change | Yes | Unscheduled - Gen outage cancelled due to forced outage of Huntstown HN2 | GEN | No | N/A | No Change | No | N/A | No Change | Yes | Unscheduled - Gen outage cancelled due to forced outage of Huntstown HN2 | GEN | No | Unscheduled - Gen outage cancelled due to forced outage of Huntstown HN2 | GEN
FINGLAS HUNTSTOWN | Huntstown HNC | 220kV SF6 Cubicle Operational Test | 901212486 | Yes | TO-21-FIN-HN-1-02 | July | - | - | 2 | N/A | N/A | N/A | No | Unscheduled - Gen outage cancelled due to forced outage of Huntstown HN2 | Yes | Unscheduled - Gen outage cancelled due to forced outage of Huntstown HN2 | GEN | No | N/A | No Change | Yes | Unscheduled - Gen outage cancelled due to forced outage of Huntstown HN2 | GEN | No | N/A | No Change | No | N/A | No Change | Yes | Unscheduled - Gen outage cancelled due to forced outage of Huntstown HN2 | GEN | No | Unscheduled - Gen outage cancelled due to forced outage of Huntstown HN2 | GEN
FINGLAS HUNTSTOWN | Huntstown HNC | T Phase Hotspot on T phase DL/DE disconnect DUE : 17-Jul-20 | 901128554 | Yes | TO-21-FIN-HN-1-02 | July | - | - | 2 | N/A | N/A | N/A | No | Unscheduled - Gen outage cancelled due to forced outage of Huntstown HN2 | Yes | Unscheduled - Gen outage cancelled due to forced outage of Huntstown HN2 | GEN | No | N/A | No Change | Yes | Unscheduled - Gen outage cancelled due to forced outage of Huntstown HN2 | GEN | No | N/A | No Change | No | N/A | No Change | Yes | Unscheduled - Gen outage cancelled due to forced outage of Huntstown HN2 | GEN | No | Unscheduled - Gen outage cancelled due to forced outage of Huntstown HN2 | GEN
GARROW T122 | Coomacheo CZ1 | 110kV SF6 Cubicle Operational Test | 901212530 | Yes | TO-21-GRO-T122-01 | July | - | - | 1 | N/A | 08-JUL-21 08:34:00 | 08-JUL-21 14:57:00 | Yes | N/A | No | N/A | No Change | No | N/A | No Change | No | N/A | No Change | No | N/A | No Change | No | N/A | No Change | No | N/A | No Change | Yes | N/A | No Change
GARVAGH T121 | Garvagh GH1/GH2 | Cable Insp. 110kV XLPE | 901212138 | Yes | TO-21-GRV-T121-01 | July | - | - | 7 | N/A | 07-JUL-21 12:35:00 | 15-JUL-21 14:50:00 | Yes | N/A | No | N/A | No Change | No | N/A | No Change | No | N/A | No Change | No | N/A | No Change | No | N/A | No Change | No | N/A | No Change | Yes | N/A | No Change
GARVAGH T121 | Garvagh GH1/GH2 | 110kV SF6 Cubicle Operational Test | 901212531 | Yes | TO-21-GRV-T121-01 | July | - | - | 7 | N/A | 07-JUL-21 12:35:00 | 15-JUL-21 14:50:00 | Yes | N/A | No | N/A | No Change | No | N/A | No Change | No | N/A | No Change | No | N/A | No Change | No | N/A | No Change | No | N/A | No Change | Yes | N/A | No Change
GLANAGOW T2001 | Bord Gais WG1 | 220kV SF6 Cubicle Operational Test | 901212580 | Yes | TO-21-GGO-T2001-01 | April | 2021-04-08 | 2021-04-09 | 1 | N/A | 06-MAY-21 11:09:00 | 03-JUN-21 11:00:00 | Yes | N/A | Yes | Rescheduled as per generator request | GEN | Yes | Changed as per generator request | GEN | Yes | Whitegate WG1 on forced outage | GEN | Yes | Whitegate WG1 on forced outage | GEN | No | N/A | No Change | No | N/A | No Change | Yes | N/A | No Change
GLANLEE T121 | Glanlee GL1 | 110kV SF6 Cubicle Operational Test | 901212532 | Yes | TO-21-GAE-T121-01 | July | - | - | 2 | N/A | 12-JUL-21 08:39:00 | 26-JUL-21 16:33:00 | Yes | N/A | No | N/A | No Change | Yes | TAO requested extra time to complete additional works | TAO | No | N/A | No Change | No | N/A | No Change | No | N/A | No Change | No | N/A | No Change | Yes | N/A | No Change
GLENLARA KNOCKACUMMER | Knockacummer KCR | Repair Link Box @JB7 due to Water Ingres | 900895976 | Yes | TO-21-GLE-KCR-1-01 | July | - | - | 5 | Corrective maintenance item identified in season by the TAO. | 17-AUG-21 08:31:00 | 20-AUG-21 14:20:00 | Yes | N/A | Yes | Dates reschedued to align with Capex works | TSO | N/A | N/A | N/A | Yes | Rescheduled as per TAO request | TAO | Yes | Rescheduled as per TAO request | TAO | Yes | Corrective maintenance item identified in season by the TAO | TAO | No | N/A | No Change | Yes | N/A | No Change
GLENLARA KNOCKACUMMER | Knockacummer KCR | Cable Insp. 110kV XLPE | 901129175 | Yes | TO-21-GLE-KCR-1-01 | July | - | - | 5 | N/A | 17-AUG-21 08:31:00 | 20-AUG-21 14:20:00 | Yes | N/A | Yes | Dates reschedued to align with Capex works | TSO | Yes | TAO completed works earlier than anticipated | TAO | Yes | Outage began late as per generator request | GEN | Yes | Outage began late as per generator request | GEN | No | N/A | No Change | No | N/A | No Change | Yes | N/A | No Change
GLENLARA KNOCKACUMMER | Knockacummer KCR | 110kV SF6 Cubicle Operational Test - GLE | 901095021 | Yes | TO-21-GLE-KCR-1-01 | July | - | - | 5 | N/A | 17-AUG-21 08:31:00 | 20-AUG-21 14:20:00 | Yes | N/A | Yes | Dates reschedued to align with Capex works | TSO | Yes | TAO completed works earlier than anticipated | TAO | Yes | Outage began late as per generator request | GEN | Yes | Outage began late as per generator request | GEN | No | N/A | No Change | No | N/A | No Change | Yes | N/A | No Change
GLENLARA KNOCKACUMMER | Knockacummer KCR | Repair SF6 leak on KCR 110 kV CB in GLE station | 901212856 | No | TO-21-GLE-KCR-1-02 | - | - | - | - | N/A | 26-APR-21 08:11:00 | 27-APR-21 14:42:00 | Yes | N/A | N/A | N/A | N/A | Yes | TAO completed works earlier than anticipated | TAO | Yes | Outage began late as per generator request | GEN | Yes | Outage began late as per generator request | GEN | No | N/A | No Change | No | N/A | No Change | Yes | N/A | No Change
Great Island GIS T2004 | GI4 | 220kV GIS Cubicle Operational Test | 901212273 | Yes | TO-21-GI GIS-T2004-01 | October | - | - | 1 | N/A | N/A | N/A | No | Unscheduled - Gen outage moved for system security | Yes | Rescheduled as per generator request | GEN | No | N/A | No Change | Yes | Unscheduled - Gen outage moved for system security | TSO | N/A | N/A | N/A | No | N/A | No Change | Yes | TSO requested change due to system constraints | TSO | No | Unscheduled - Gen outage moved for system security | TSO
Great Island GIS T2004 | GI4 | P1 Protection maintenance of 7SA612 | Protection | Yes | TO-21-GI GIS-T2004-01 | October | - | - | 2 | N/A | N/A | N/A | No | Unscheduled - Gen outage moved for system security | Yes | Rescheduled as per generator request | GEN | No | N/A | No Change | Yes | Unscheduled - Gen outage moved for system security | TSO | N/A | N/A | N/A | No | N/A | No Change | Yes | TSO requested change due to system constraints | TSO | No | Unscheduled - Gen outage moved for system security | TSO
Huntstown T2002 | Huntstown HN2 | 220kV cubicle operational test | 901042455 | Yes | TO-21-HN-T2002-01 | March | 2021-03-02 | 2021-03-15 | 14 | N/A | 30-JAN-21 09:00:00 | 16-OCT-21 11:37:00 | No | Work not done due to TAO resourcing constraints | No | N/A | No Change | No | N/A | No Change | Yes | Huntstown HN2 on forced outage | GEN | Yes | Huntstown HN2 on forced outage | GEN | No | N/A | No Change | Yes | Huntstown HN2 on forced outage | GEN | No | Work not done due to TAO resourcing constraints | TAO
Huntstown T2002 | Huntstown HN2 | Cable Insp. 400 & 220kV Feeder XLPE | 901129030 | Yes | TO-21-HN-T2002-01 | March | 2021-03-02 | 2021-03-15 | 14 | N/A | 30-JAN-21 09:00:00 | 16-OCT-21 11:37:00 | No | Work not done due to TAO resourcing constraints | No | N/A | No Change | No | N/A | No Change | Yes | Huntstown HN2 on forced outage | GEN | Yes | Huntstown HN2 on forced outage | GEN | No | N/A | No Change | Yes | Huntstown HN2 on forced outage | GEN | No | Work not done due to TAO resourcing constraints | TAO
Huntstown T2002 | Huntstown HN2 | 220kV SF6 Cubicle Ordinary Service | 901182889 | Yes | TO-21-HN-T2002-01 | March | 2021-03-02 | 2021-03-15 | 14 | N/A | 30-JAN-21 09:00:00 | 16-OCT-21 11:37:00 | Yes | N/A | No | N/A | No Change | No | N/A | No Change | Yes | Huntstown HN2 on forced outage | GEN | Yes | Huntstown HN2 on forced outage | GEN | No | N/A | No Change | Yes | Huntstown HN2 on forced outage | GEN | Yes | N/A | No Change
HUNTSTOWN T2010/11 | Huntstown HNC | Cable Insp. 400 & 220kV Feeder XLPE | 901005718 | Yes | TO-21-HN-T2010/11-02 | July | - | - | 2 | N/A | N/A | N/A | No | Unscheduled - Gen outage cancelled due to forced outage of Huntstown HN2 | Yes | Unscheduled - Gen outage cancelled due to forced outage of Huntstown HN2 | GEN | No | N/A | No Change | Yes | Unscheduled - Gen outage cancelled due to forced outage of Huntstown HN2 | GEN | N/A | N/A | N/A | No | N/A | No Change | Yes | Unscheduled - Gen outage cancelled due to forced outage of Huntstown HN2 | GEN | No | Unscheduled - Gen outage cancelled due to forced outage of Huntstown HN2 | GEN
IKERRIN tee IKERRIN | Monaincha Bog MH1 | 2017HP-3[415]Check Structure 3 poles, | 900898166 | No | TO-21-IKE,T-IKE-1-02 | - | - | - | - | Preventative maintenance item identified in season by the TAO. | 27-JUL-21 08:58:00 | 27-JUL-21 18:13:00 | Yes | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Yes | Reschedued to align with Capex works | TAO | Yes | Reschedued to align with Capex works | TAO | Yes | Preventative maintenance item identified in season by the TAO. | TAO | No | N/A | No Change | Yes | N/A | No Change
IKERRIN tee IKERRIN | Monaincha Bog MH1 | 2020HP-3[415]Check Structure Insul & HW | 901172501 | No | TO-21-IKE,T-IKE-1-02 | - | - | - | - | Preventative maintenance item identified in season by the TAO. | 27-JUL-21 08:58:00 | 27-JUL-21 18:13:00 | Yes | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Yes | Reschedued to align with Capex works | TAO | Yes | Reschedued to align with Capex works | TAO | Yes | Preventative maintenance item identified in season by the TAO. | TAO | No | N/A | No Change | Yes | N/A | No Change
IKERRIN tee SHANNONBRIDGE | Monaincha Bog MH1 | 2018HP-1[277]Bird Nests remove | 900989547 | Yes | TO-21-IKE,T-SH-1-01 | August | - | - | 7 | N/A | 15-SEP-21 11:36:00 | 17-SEP-21 14:58:00 | No | Unscheduled due to TAO resources | Yes | Dates reschedued to align with Capex works CP1096 | TSO | Yes | Change to work scope allowed TAO to complete work quicker than anticipated | TAO | Yes | Reschedued to align with Capex works CP1096 | TAO | Yes | Reschedued to align with Capex works CP1096 | TAO | No | N/A | No Change | No | N/A | No Change | No | Unscheduled due to TAO resources | TAO
IKERRIN tee SHANNONBRIDGE | Monaincha Bog MH1 | 2014HP-1[191]Off Plumb; LOCATED AT THE BACK OF A 40 ACRE FIELD. NEED TO ENGAGE WITH ESB TO INFORM LAND OWNER ON GAINING ACCESS | 900651092 | Yes | TO-21-IKE,T-SH-1-01 | August | - | - | 7 | N/A | 15-SEP-21 11:36:00 | 17-SEP-21 14:58:00 | No | Unscheduled - Works do not require an outage | Yes | Dates reschedued to align with Capex works CP1096 | TSO | Yes | Change to work scope allowed TAO to complete work quicker than anticipated | TAO | Yes | Reschedued to align with Capex works CP1096 | TAO | Yes | Reschedued to align with Capex works CP1096 | TAO | No | N/A | No Change | No | N/A | No Change | No | Unscheduled - Works do not require an outage | TAO
IKERRIN tee SHANNONBRIDGE | Monaincha Bog MH1 | 2020HP-1[191]Off Plumb (Straighten) | 901171426 | Yes | TO-21-IKE,T-SH-1-01 | August | - | - | 7 | N/A | 15-SEP-21 11:36:00 | 17-SEP-21 14:58:00 | No | Unscheduled - Works do not require an outage | Yes | Dates reschedued to align with Capex works CP1096 | TSO | Yes | Change to work scope allowed TAO to complete work quicker than anticipated | TAO | Yes | Reschedued to align with Capex works CP1096 | TAO | Yes | Reschedued to align with Capex works CP1096 | TAO | No | N/A | No Change | No | N/A | No Change | No | Unscheduled - Works do not require an outage | TAO
IKERRIN tee SHANNONBRIDGE | Monaincha Bog MH1 | 2020HP-1[24]Check Structure Top Rot | 901172525 | Yes | TO-21-IKE,T-SH-1-01 | August | - | - | 7 | N/A | 15-SEP-21 11:36:00 | 17-SEP-21 14:58:00 | No | Unscheduled - Works do not require an outage | Yes | Dates reschedued to align with Capex works CP1096 | TSO | Yes | Change to work scope allowed TAO to complete work quicker than anticipated | TAO | Yes | Reschedued to align with Capex works CP1096 | TAO | Yes | Reschedued to align with Capex works CP1096 | TAO | No | N/A | No Change | No | N/A | No Change | No | Unscheduled - Works do not require an outage | TAO
IKERRIN tee SHANNONBRIDGE | Monaincha Bog MH1 | 2020HP-1[38]Check Structure Top Rot | 901172526 | Yes | TO-21-IKE,T-SH-1-01 | August | - | - | 7 | N/A | 15-SEP-21 11:36:00 | 17-SEP-21 14:58:00 | No | Unscheduled - Works do not require an outage | Yes | Dates reschedued to align with Capex works CP1096 | TSO | Yes | Change to work scope allowed TAO to complete work quicker than anticipated | TAO | Yes | Reschedued to align with Capex works CP1096 | TAO | Yes | Reschedued to align with Capex works CP1096 | TAO | No | N/A | No Change | No | N/A | No Change | No | Unscheduled - Works do not require an outage | TAO
IKERRIN tee SHANNONBRIDGE | Monaincha Bog MH1 | 2020HP-1[219]Check Structure Top Rot | 901172529 | Yes | TO-21-IKE,T-SH-1-01 | August | - | - | 7 | N/A | 15-SEP-21 11:36:00 | 17-SEP-21 14:58:00 | No | Unscheduled - Works do not require an outage | Yes | Dates reschedued to align with Capex works CP1096 | TSO | Yes | Change to work scope allowed TAO to complete work quicker than anticipated | TAO | Yes | Reschedued to align with Capex works CP1096 | TAO | Yes | Reschedued to align with Capex works CP1096 | TAO | No | N/A | No Change | No | N/A | No Change | No | Unscheduled - Works do not require an outage | TAO
IKERRIN tee SHANNONBRIDGE | Monaincha Bog MH1 | 110kV SF6 Cubicle Ordinary Service | 901212852 | Yes | TO-21-IKE,T-SH-1-01 | August | - | - | 7 | N/A | 15-SEP-21 11:36:00 | 17-SEP-21 14:58:00 | No | Work not done due to TAO resourcing constraints | Yes | Dates reschedued to align with Capex works CP1096 | TSO | Yes | Change to work scope allowed TAO to complete work quicker than anticipated | TAO | Yes | Reschedued to align with Capex works CP1096 | TAO | Yes | Reschedued to align with Capex works CP1096 | TAO | No | N/A | No Change | No | N/A | No Change | No | Work not done due to TAO resourcing constraints | TAO
IKERRIN tee SHANNONBRIDGE | Monaincha Bog MH1 | 110KV CUBICLE CONDITION ASSESSMENT | 901212210 | Yes | TO-21-IKE,T-SH-1-01 | August | - | - | 7 | N/A | 15-SEP-21 11:36:00 | 17-SEP-21 14:58:00 | No | Work not done due to TAO resourcing constraints | Yes | Dates reschedued to align with Capex works CP1096 | TSO | Yes | Change to work scope allowed TAO to complete work quicker than anticipated | TAO | Yes | Reschedued to align with Capex works CP1096 | TAO | Yes | Reschedued to align with Capex works CP1096 | TAO | No | N/A | No Change | No | N/A | No Change | No | Work not done due to TAO resourcing constraints | TAO
IKERRIN tee SHANNONBRIDGE | Monaincha Bog MH1 | 2020HP-1[67]Check Structure Top Rot | 901172527 | Yes | TO-21-IKE,T-SH-1-01 | August | - | - | 7 | N/A | 15-SEP-21 11:36:00 | 17-SEP-21 14:58:00 | No | Unscheduled - Works do not require an outage | Yes | Dates reschedued to align with Capex works CP1096 | TSO | Yes | Change to work scope allowed TAO to complete work quicker than anticipated | TAO | Yes | Reschedued to align with Capex works CP1096 | TAO | Yes | Reschedued to align with Capex works CP1096 | TAO | No | N/A | No Change | No | N/A | No Change | No | Unscheduled - Works do not require an outage | TAO
IKERRIN tee SHANNONBRIDGE | Monaincha Bog MH1 | 2020HP-1[180]Check Structure Top Rot | 901172528 | Yes | TO-21-IKE,T-SH-1-01 | August | - | - | 7 | N/A | 15-SEP-21 11:36:00 | 17-SEP-21 14:58:00 | Yes | N/A | Yes | Dates reschedued to align with Capex works CP1096 | TSO | Yes | Change to work scope allowed TAO to complete work quicker than anticipated | TAO | Yes | Reschedued to align with Capex works CP1096 | TAO | Yes | Reschedued to align with Capex works CP1096 | TAO | No | N/A | No Change | No | N/A | No Change | Yes | N/A | No Change
IKERRIN tee THURLES | Monaincha Bog MH1 | 2019LP-1[291]Off Plumb - Pole | 901126159 | Yes | TO-21-IKE,T-THU-1-01 | August | - | - | 2 | N/A | 15-SEP-21 11:36:00 | 17-SEP-21 14:58:00 | No | Work not done due to TAO resourcing constraints | Yes | Dates reschedued to align with Capex works CP1096 | TSO | Yes | Work scope duration increased at TAO request | TAO | Yes | Reschedued to align with Capex works CP1096 | TAO | Yes | Reschedued to align with Capex works CP1096 | TAO | No | N/A | No Change | No | N/A | No Change | No | Work not done due to TAO resourcing constraints | TAO
IKERRIN tee THURLES | Monaincha Bog MH1 | 110kV MO Cubicle Operational Test | 901129466 | Yes | TO-21-IKE,T-THU-1-01 | August | - | - | 2 | N/A | 15-SEP-21 11:36:00 | 17-SEP-21 14:58:00 | Yes | N/A | Yes | Dates reschedued to align with Capex works CP1096 | TSO | Yes | Work scope duration increased at TAO request | TAO | Yes | Reschedued to align with Capex works CP1096 | TAO | Yes | Reschedued to align with Capex works CP1096 | TAO | No | N/A | No Change | No | N/A | No Change | Yes | N/A | No Change
INNISCARRA T101 | LE1/LE2 | 110KV SF6 Cubicle Operational Test | 901212533 | Yes | TO-21-IA-T101-01 | June | - | - | 1 | N/A | N/A | N/A | No | Unscheduled due to TAO resources | Yes | Unscheduled due to TAO resources | TAO | N/A | N/A | N/A | Yes | Unscheduled due to TAO resources | TAO | N/A | N/A | N/A | No | N/A | No Change | No | N/A | No Change | No | Unscheduled due to TAO resources | TAO
IRISHTOWN T2001 | DB1 | P2 Protection maintenance of 7SA513, | Protection | Yes | TO-21-ISH-T2001-01 | April | 2021-04-27 | 2021-05-06 | 10 | N/A | 27-APR-21 07:00:00 | 02-JUL-21 11:12:00 | Yes | N/A | No | N/A | No Change | Yes | Outage increased to facilitate generator works | GEN | Yes | Generators outage force extended | GEN | Yes | Rescheduled as per generator request | GEN | No | N/A | No Change | Yes | Generator requested change to Committed Outage Programme | GEN | Yes | N/A | No Change
IRISHTOWN T2001 | DB1 | Cable Insp. 400 & 220kV Feeder XLPE | 901129031 | Yes | TO-21-ISH-T2001-01 | April | 2021-04-27 | 2021-05-06 | 10 | N/A | 27-APR-21 07:00:00 | 02-JUL-21 11:12:00 | Yes | N/A | No | N/A | No Change | Yes | Outage increased to facilitate generator works | GEN | Yes | Generators outage force extended | GEN | Yes | Rescheduled as per generator request | GEN | No | N/A | No Change | Yes | Generator requested change to Committed Outage Programme | GEN | Yes | N/A | No Change
IRISHTOWN T2001 | DB1 | 220kV Cubicle Condition Assessment | 901129251 | Yes | TO-21-ISH-T2001-01 | April | 2021-04-27 | 2021-05-06 | 10 | N/A | 27-APR-21 07:00:00 | 02-JUL-21 11:12:00 | Yes | N/A | No | N/A | No Change | Yes | Outage increased to facilitate generator works | GEN | Yes | Generators outage force extended | GEN | Yes | Rescheduled as per generator request | GEN | No | N/A | No Change | Yes | Generator requested change to Committed Outage Programme | GEN | Yes | N/A | No Change
IRISHTOWN T2001 | DB1 | 110kV GIS Cubicle Ordinary Service | 901129784 | Yes | TO-21-ISH-T2001-01 | April | 2021-04-27 | 2021-05-06 | 10 | N/A | 27-APR-21 07:00:00 | 02-JUL-21 11:12:00 | Yes | N/A | No | N/A | No Change | Yes | Outage increased to facilitate generator works | GEN | Yes | Generators outage force extended | GEN | Yes | Rescheduled as per generator request | GEN | No | N/A | No Change | Yes | Generator requested change to Committed Outage Programme | GEN | Yes | N/A | No Change
KILL HILL T131 | Kill Hill KH1 | 110kV SF6 Cubicle Ordinary Service | 901129925 | Yes | TO-21-KHL-T131-01 | May | - | - | 4 | N/A | 31-MAY-21 08:43:00 | 03-JUN-21 12:04:00 | Yes | N/A | No | N/A | No Change | No | N/A | No Change | No | N/A | No Change | No | N/A | No Change | No | N/A | No Change | No | N/A | No Change | Yes | N/A | No Change
KNOCKALOUGH KNOCKRANNY | Knockalough KU1 | 110kV SF6 Cubicle Operational Test - Knockalough Stn |  | Yes | TO-21-KLH-KNY-1-01 | August | - | - | 2 | N/A | 10-AUG-21 10:38:00 | 11-AUG-21 14:34:00 | No | Asset not transferred to ESBN | No | N/A | No Change | No | N/A | No Change | Yes | Rescheduled as per generator request | GEN | Yes | Rescheduled as per generator request | GEN | No | N/A | No Change | No | N/A | No Change | No | Asset not transferred to ESBN | GEN
KNOCKALOUGH KNOCKRANNY | Knockalough KU1 | Cable Insp. 110kV XLPE | Asset not transferred to ESBN | Yes | TO-21-KLH-KNY-1-01 | August | - | - | 2 | N/A | 10-AUG-21 10:38:00 | 11-AUG-21 14:34:00 | No | Asset not transferred to ESBN | No | N/A | No Change | No | N/A | No Change | Yes | Rescheduled as per generator request | GEN | Yes | Rescheduled as per generator request | GEN | No | N/A | No Change | No | N/A | No Change | No | Asset not transferred to ESBN | GEN
KNOCKALOUGH KNOCKRANNY | Knockalough KU1 | 110kV SF6 Cubicle Operational Test - Knockranny Stn | Asset not transferred to ESBN | Yes | TO-21-KLH-KNY-1-01 | August | - | - | 2 | N/A | 10-AUG-21 10:38:00 | 11-AUG-21 14:34:00 | No | Asset not transferred to ESBN | No | N/A | No Change | No | N/A | No Change | Yes | Rescheduled as per generator request | GEN | Yes | Rescheduled as per generator request | GEN | No | N/A | No Change | No | N/A | No Change | No | Asset not transferred to ESBN | GEN
KNOCKRANNY UGGOOL | Uggool UG1, Seecon SO1 | 110kV GIS Cubicle Operational Test - Uggool Sectionaliser | 901212471 | Yes | TO-21-KNY-UGL-1-01 | July | - | - | 3 | N/A | 05-JUL-21 11:55:00 | 07-JUL-21 17:36:00 | Yes | N/A | No | N/A | No Change | No | N/A | No Change | No | N/A | No Change | No | N/A | No Change | No | N/A | No Change | No | N/A | No Change | Yes | N/A | No Change
KNOCKRANNY UGGOOL | Uggool UG1, Seecon SO1 | P2 Protection maintenance of 7SA612, GRL100 702D - KNY | Protection | Yes | TO-21-KNY-UGL-1-01 | July | - | - | 3 | N/A | 05-JUL-21 11:55:00 | 07-JUL-21 17:36:00 | Yes | N/A | No | N/A | No Change | No | N/A | No Change | No | N/A | No Change | No | N/A | No Change | No | N/A | No Change | No | N/A | No Change | Yes | N/A | No Change
KNOCKRANNY UGGOOL | Uggool UG1, Seecon SO1 | P2 Protection maintenance of 7SA612, GRL100 702D - UGL | Protection | Yes | TO-21-KNY-UGL-1-01 | July | - | - | 3 | N/A | 05-JUL-21 11:55:00 | 07-JUL-21 17:36:00 | Yes | N/A | No | N/A | No Change | No | N/A | No Change | No | N/A | No Change | No | N/A | No Change | No | N/A | No Change | No | N/A | No Change | Yes | N/A | No Change
LISHEEN T122 | Lisheen LS1/LS2 | 110kV SF6 Cubicle Operational Test | 901212534 | Yes | TO-21-LSN-T122-01 | June | - | - | 10 | N/A | 28-JUN-21 08:12:00 | 09-JUL-21 11:49:00 | Completed in Previous Outage Season | N/A | No | N/A | No Change | No | N/A | No Change | No | N/A | No Change | No | N/A | No Change | Completed in Previous Outage Season | Completed in Previous Outage Season | TAO | No | N/A | No Change | N/A | N/A | N/A
LISHEEN T122 | Lisheen LS1/LS2 | P1 Protection maintenance of 7SA612 | Protection | Yes | TO-21-LSN-T122-01 | June | - | - | 10 | N/A | 28-JUN-21 08:12:00 | 09-JUL-21 11:49:00 | Yes | N/A | No | N/A | No Change | No | N/A | No Change | No | N/A | No Change | No | N/A | No Change | No | N/A | No Change | No | N/A | No Change | Yes | N/A | No Change
LISHEEN THURLES | Lisheen LS1, LS2, Bruckana BU1 | 2018HP-1[25]Bird Nestsremove asap | 900988512 | Yes | TO-21-LSN-THU-1-02 | June | - | - | 10 | N/A | 28-JUN-21 08:12:00 | 09-JUL-21 11:49:00 | Yes | N/A | No | N/A | No Change | No | N/A | No Change | No | N/A | No Change | No | N/A | No Change | No | N/A | No Change | No | N/A | No Change | Yes | N/A | No Change
LISHEEN THURLES | Lisheen LS1, LS2, Bruckana BU1 | 1[AM3]: Replacement of polymeric auxilia | 901155772 | Yes | TO-21-LSN-THU-1-02 | June | - | - | 10 | N/A | 28-JUN-21 08:12:00 | 09-JUL-21 11:49:00 | Yes | N/A | No | N/A | No Change | No | N/A | No Change | No | N/A | No Change | No | N/A | No Change | No | N/A | No Change | No | N/A | No Change | Yes | N/A | No Change
LISHEEN THURLES | Lisheen LS1, LS2, Bruckana BU1 | 1[AM5]: Replacement of polymeric auxilia | 901155778 | Yes | TO-21-LSN-THU-1-02 | June | - | - | 10 | N/A | 28-JUN-21 08:12:00 | 09-JUL-21 11:49:00 | Yes | N/A | No | N/A | No Change | No | N/A | No Change | No | N/A | No Change | No | N/A | No Change | No | N/A | No Change | No | N/A | No Change | Yes | N/A | No Change
LISHEEN THURLES | Lisheen LS1, LS2, Bruckana BU1 | 1[AM20]: Replacement of polymeric auxili | 901155782 | Yes | TO-21-LSN-THU-1-02 | June | - | - | 10 | N/A | 28-JUN-21 08:12:00 | 09-JUL-21 11:49:00 | Yes | N/A | No | N/A | No Change | No | N/A | No Change | No | N/A | No Change | No | N/A | No Change | No | N/A | No Change | No | N/A | No Change | Yes | N/A | No Change
LISHEEN THURLES | Lisheen LS1, LS2, Bruckana BU1 | 1[AM25]: Replacement of polymeric auxili | 901155783 | Yes | TO-21-LSN-THU-1-02 | June | - | - | 10 | N/A | 28-JUN-21 08:12:00 | 09-JUL-21 11:49:00 | Yes | N/A | No | N/A | No Change | No | N/A | No Change | No | N/A | No Change | No | N/A | No Change | No | N/A | No Change | No | N/A | No Change | Yes | N/A | No Change
LISHEEN THURLES | Lisheen LS1, LS2, Bruckana BU1 | 1[AM38]: Replacement of polymeric auxili | 901155785 | Yes | TO-21-LSN-THU-1-02 | June | - | - | 10 | N/A | 28-JUN-21 08:12:00 | 09-JUL-21 11:49:00 | Yes | N/A | No | N/A | No Change | No | N/A | No Change | No | N/A | No Change | No | N/A | No Change | No | N/A | No Change | No | N/A | No Change | Yes | N/A | No Change
LISHEEN THURLES | Lisheen LS1, LS2, Bruckana BU1 | 1[AM47]: Replacement of polymeric auxili | 901155786 | Yes | TO-21-LSN-THU-1-02 | June | - | - | 10 | N/A | 28-JUN-21 08:12:00 | 09-JUL-21 11:49:00 | Yes | N/A | No | N/A | No Change | No | N/A | No Change | No | N/A | No Change | No | N/A | No Change | No | N/A | No Change | No | N/A | No Change | Yes | N/A | No Change
LISHEEN THURLES | Lisheen LS1, LS2, Bruckana BU1 | 2020LP-1[49]Earths-Repl -Bonding strap | 901169040 | Yes | TO-21-LSN-THU-1-02 | June | - | - | 10 | N/A | 28-JUN-21 08:12:00 | 09-JUL-21 11:49:00 | Yes | N/A | No | N/A | No Change | No | N/A | No Change | No | N/A | No Change | No | N/A | No Change | No | N/A | No Change | No | N/A | No Change | Yes | N/A | No Change
LISHEEN THURLES | Lisheen LS1, LS2, Bruckana BU1 | 2020LP-1[54]Earths-Repl -Wire brokenL/P | 901169041 | Yes | TO-21-LSN-THU-1-02 | June | - | - | 10 | N/A | 28-JUN-21 08:12:00 | 09-JUL-21 11:49:00 | Yes | N/A | No | N/A | No Change | No | N/A | No Change | No | N/A | No Change | No | N/A | No Change | No | N/A | No Change | No | N/A | No Change | Yes | N/A | No Change
LISHEEN THURLES | Lisheen LS1, LS2, Bruckana BU1 | 2020LP-1[47]Bird Nests -Remove | 901169044 | Yes | TO-21-LSN-THU-1-02 | June | - | - | 10 | N/A | 28-JUN-21 08:12:00 | 09-JUL-21 11:49:00 | Yes | N/A | No | N/A | No Change | No | N/A | No Change | No | N/A | No Change | No | N/A | No Change | No | N/A | No Change | No | N/A | No Change | Yes | N/A | No Change
LISHEEN THURLES | Lisheen LS1, LS2, Bruckana BU1 | 2020LP-1[1]Bird Nests -Remove | 901169045 | Yes | TO-21-LSN-THU-1-02 | June | - | - | 10 | N/A | 28-JUN-21 08:12:00 | 09-JUL-21 11:49:00 | Yes | N/A | No | N/A | No Change | No | N/A | No Change | No | N/A | No Change | No | N/A | No Change | No | N/A | No Change | No | N/A | No Change | Yes | N/A | No Change
LISHEEN THURLES | Lisheen LS1, LS2, Bruckana BU1 | 2020LP-1[11]Repl. Pole -Botton Rot | 901169994 | Yes | TO-21-LSN-THU-1-02 | June | - | - | 10 | N/A | 28-JUN-21 08:12:00 | 09-JUL-21 11:49:00 | Yes | N/A | No | N/A | No Change | No | N/A | No Change | No | N/A | No Change | No | N/A | No Change | No | N/A | No Change | No | N/A | No Change | Yes | N/A | No Change
LISHEEN THURLES | Lisheen LS1, LS2, Bruckana BU1 | 2020HP-1[54]Earths-Replace Earth strapRP | 901171273 | Yes | TO-21-LSN-THU-1-02 | June | - | - | 10 | N/A | 28-JUN-21 08:12:00 | 09-JUL-21 11:49:00 | Yes | N/A | No | N/A | No Change | No | N/A | No Change | No | N/A | No Change | No | N/A | No Change | No | N/A | No Change | No | N/A | No Change | Yes | N/A | No Change
LISHEEN THURLES | Lisheen LS1, LS2, Bruckana BU1 | 2020HP-1[49]Earths-Replace Earth strapRP | 901171274 | Yes | TO-21-LSN-THU-1-02 | June | - | - | 10 | N/A | 28-JUN-21 08:12:00 | 09-JUL-21 11:49:00 | Yes | N/A | No | N/A | No Change | No | N/A | No Change | No | N/A | No Change | No | N/A | No Change | No | N/A | No Change | No | N/A | No Change | Yes | N/A | No Change
LISHEEN THURLES | Lisheen LS1, LS2, Bruckana BU1 | 2020HP-1[14]Off Plumb Straighten Poleset | 901171410 | Yes | TO-21-LSN-THU-1-02 | June | - | - | 10 | N/A | 28-JUN-21 08:12:00 | 09-JUL-21 11:49:00 | Yes | N/A | No | N/A | No Change | No | N/A | No Change | No | N/A | No Change | No | N/A | No Change | No | N/A | No Change | No | N/A | No Change | Yes | N/A | No Change
LISHEEN THURLES | Lisheen LS1, LS2, Bruckana BU1 | P3 Protection maintenance of 7SA612 | Protection | Yes | TO-21-LSN-THU-1-02 | June | - | - | 10 | N/A | 28-JUN-21 08:12:00 | 09-JUL-21 11:49:00 | Yes | N/A | No | N/A | No Change | No | N/A | No Change | No | N/A | No Change | No | N/A | No Change | No | N/A | No Change | No | N/A | No Change | Yes | N/A | No Change
LODGEWOOD 110SA1 | Castledockrell CK1 | 110kV Sect / Dist Operational Test on SA1 | 901130095 | No | TO-21-LWD-110SA1-01 | - | - | - | - | N/A | 2021-09-29 08:34 | 2021-09-29 17:12 | Yes | N/A | N/A | N/A | N/A | N/A | N/A | N/A | No | N/A | No Change | No | N/A | No Change | Yes | TAO requested repairs in season | TAO | No | N/A | No Change | Yes | N/A | No Change
LODGEWOOD 110SA2 | Castledockrell CK1 | 110kV Sect / Dist Operational Test on SA2 | 901130096 | No | TO-21-LWD-110SA2-01 | - | - | - | - | N/A | 2021-09-29 08:34 | 2021-09-29 17:12 | Yes | N/A | N/A | N/A | N/A | N/A | N/A | N/A | No | N/A | No Change | No | N/A | No Change | Yes | TAO requested repairs in season | TAO | No | N/A | No Change | Yes | N/A | No Change
LONG POINT T2002 | AD2 | 220kV SF6 Cubicle Operational Test | 901212581 | Yes | TO-21-LPT-T2002-01 | May | - | - | 1 | N/A | 17-MAY-21 12:01:00 | 19-MAY-21 16:56:00 | Yes | N/A | No | N/A | No Change | Yes | Work scope duration increased at TAO request | TAO | Yes | TAO completed works earlier than anticipated | TAO | Yes | TAO completed works earlier than anticipated | TAO | No | N/A | No Change | No | N/A | No Change | Yes | N/A | No Change
MONEYPOINT GIS T121 | Moneypoint MP9 | 110KV GIS Cubicle Operational Test | 901212242 | Yes | TO-21-MP GIS-T121-01 | July | - | - | 2 | N/A | 26-JUL-21 11:53:00 | 27-JUL-21 17:21:00 | Yes | N/A | No | N/A | No Change | No | N/A | No Change | No | N/A | No Change | No | N/A | No Change | No | N/A | No Change | No | N/A | No Change | Yes | N/A | No Change
MONEYPOINT GIS T4002 | MP2 | 400kV GIS Cubicle Operational Test | 901212422 | Yes | TO-21-MP GIS-T4002-01 | July | - | - | 3 | N/A | 24-JUL-21 06:38:00 | 30-JUL-21 21:50:00 | Yes | N/A | No | N/A | No Change | Yes | Outage increased to facilitate generator works | GEN | Yes | Rescheduled as per generator request | GEN | Yes | Rescheduled as per generator request | GEN | No | N/A | No Change | Yes | Generator requested change to Committed Outage Programme | GEN | Yes | N/A | No Change
MONEYPOINT GIS T4002 | MP2 | Cable Insp. 400 & 220kV Feeder XLPE | 901181267 | No | TO-21-MP GIS-T4002-01 | - | - | - | - | Scheduled in season by the TSO as requirement for inspection post EI. | 24-JUL-21 06:38:00 | 30-JUL-21 21:50:00 | Yes | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Yes | Rescheduled as per generator request | GEN | Yes | Rescheduled as per generator request | GEN | Yes | Scheduled in season by the TSO as requirement for inspection post EI. | TSO | Yes | Generator requested change to Committed Outage Programme | GEN | Yes | N/A | No Change
MONEYPOINT GIS T4003 | MP3 | Cable Insp. 400 & 220kV Feeder XLPE | 901217395 | Yes | TO-21-MP GIS-T4003-01 | August | - | - | 3 | N/A | 13-JUL-21 19:05:00 | 14-JUL-21 19:31:00 | No | Work item was deferred following generator request | Yes | Rescheduled to align with generator outage | GEN | Yes | TAO completed works earlier than anticipated | TAO | Yes | Rescheduled as per generator request | GEN | Yes | Rescheduled as per generator request | GEN | No | N/A | No Change | Yes | Generator requested change to Committed Outage Programme | GEN | No | Work item was deferred following generator request | GEN
MONEYPOINT T4001 | MP1 | 400kV GIS Cubicle Operational Test | 901129532 | Yes | TO-21-MP-T4001-01 | July | - | - | 3 | N/A | 24-SEP-21 12:17:00 | 08-OCT-21 17:00:00 | Yes | N/A | Yes | Rescheduled as per generator request | GEN | Yes | Outage increased to facilitate generator works | GEN | Yes | Rescheduled as per generator request | GEN | Yes | Rescheduled as per generator request | GEN | No | N/A | No Change | Yes | Generator requested change to Committed Outage Programme | GEN | Yes | N/A | No Change
MOUNTLUCAS T121 | Mountlucas MO1 | 110kV SF6 Cubicle Operational Test | 901212535 | Yes | TO-21-MLC-T121-01 | August | - | - | 1 | N/A | 2021-08-13 08:00 | 2021-08-13 17:00 | Yes | N/A | No | N/A | No Change | No | N/A | No Change | No | N/A | No Change | No | N/A | No Change | No | N/A | No Change | No | N/A | No Change | Yes | N/A | No Change
MULREAVY T131 | Mulreavy MB1, MB2 | 110kV SF6 Cubicle Ordinary Service | 901129929 | Yes | TO-21-MRY-T131-01 | May | - | - | 4 | N/A | 09-AUG-21 07:42:00 | 12-AUG-21 17:01:00 | No | Work not done due to TAO resourcing constraints | Yes | Rescheduled to align with generator outage | GEN | Yes | Outage increased to facilitate generator works | GEN | Yes | TAO completed works earlier than anticipated | GEN | Yes | TAO completed works earlier than anticipated | TAO | No | N/A | No Change | No | N/A | No Change | No | Work not done due to TAO resourcing constraints | TAO
POLLAPHUCA 110SA1 | LI1, LI2, LI4 | 110kV Sect / Dist Ordinary Service | 901212625 | Yes | TO-21-PA-110SA1-01 | April | 2021-04-12 | 2021-04-30 | 19 | N/A | 14-APR-21 07:00:00 | 16-APR-21 10:00:00 | Yes | N/A | No | N/A | No Change | Yes | Outage increased to facilitate generator works | GEN | Yes | Outage increased to facilitate generator works | GEN | No | N/A | No Change | No | N/A | No Change | No | N/A | No Change | Yes | N/A | No Change
POLLAPHUCA 110SA2 | LI1, LI2, LI4 | 110kV Sect / Dist Ordinary Service | 901212776 | Yes | TO-21-PA-110SA2-01 | April | 2021-04-12 | 2021-04-30 | 19 | N/A | 14-APR-21 07:00:00 | 16-APR-21 10:00:00 | Yes | N/A | No | N/A | No Change | Yes | Outage increased to facilitate generator works | GEN | Yes | Outage increased to facilitate generator works | GEN | No | N/A | No Change | No | N/A | No Change | No | N/A | No Change | Yes | N/A | No Change
POLLAPHUCA T101 | LI1, LI2, LI4 | P1 Protection maintenance of 7SA511 | Protection | Yes | TO-21-PA-T101-01 | April | 2021-04-12 | 2021-04-30 | 19 | N/A | 14-APR-21 07:00:00 | 16-APR-21 10:00:00 | No | Works cancelled due to TAO resourcing | No | N/A | No Change | Yes | Outage increased to facilitate generator works | GEN | Yes | Outage increased to facilitate generator works | GEN | No | N/A | No Change | No | N/A | No Change | No | N/A | No Change | No | Works cancelled due to TAO resourcing | TAO
RATRUSSAN T121 | Bindoo BD1 | 110kV SF6 Cubicle Operational Test | 901212536 | Yes | TO-21-RRU-T121-01 | May | - | - | 3 | N/A | 03-JUN-21 08:31:00 | 03-JUN-21 18:31:00 | Yes | N/A | No | N/A | No Change | Yes | TAO completed works earlier than anticipated | TAO | Yes | Rescheduled as per generator request | GEN | Yes | Rescheduled as per generator request | GEN | No | N/A | No Change | No | N/A | No Change | Yes | N/A | No Change
RATRUSSAN T122 | Mountain Lodge ML1 | 110kV SF6 Cubicle Operational Test | 901212537 | Yes | TO-21-RRU-T122-01 | April | 2021-04-21 | 2021-04-27 | 7 | N/A | 21-APR-21 07:49:00 | 27-APR-21 15:48:00 | Yes | N/A | No | N/A | No Change | Yes | TAO completed works earlier than anticipated | TAO | No | N/A | No Change | No | N/A | No Change | No | N/A | No Change | No | N/A | No Change | Yes | N/A | No Change
RATRUSSAN T122 | Mountain Lodge ML1 | EMP AMS: Retest of VTs: Condition assess | 901154420 | Yes | TO-21-RRU-T122-01 | April | 2021-04-21 | 2021-04-27 | 7 | N/A | 21-APR-21 07:49:00 | 27-APR-21 15:48:00 | Yes | N/A | No | N/A | No Change | Yes | TAO completed works earlier than anticipated | TAO | No | N/A | No Change | No | N/A | No Change | No | N/A | No Change | No | N/A | No Change | Yes | N/A | No Change
SEALROCK T103 | SK3 | 6 months - Sealrock T103 R,S & T phase R, S & T Phase 110 kV DA A corrective maintenance action will be required within 6 months HOTSPOT DUE: 27JUL2021 | 901213244 | No | TO-21-SK-T103-01 | - | - | - | - | TAO requested repairs in season | 24-JUN-21 16:01:00 | 28-JUN-21 16:30:00 | Yes | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Yes | Generator requested works be completed at later half of their outage | GEN | Yes | Generator requested works be completed at later half of their outage | GEN | Yes | TAO requested repairs in season | TAO | Yes | Generator requested change to Committed Outage Programme | GEN | Yes | N/A | No Change
SEALROCK T104 | SK4 | Replace bonding leads due to damage in S | 901166998 | No | TO-21-SK-T104-01 | - | - | - | - | TAO requested repairs in season | 05-JUL-21 09:43:00 | 09-JUL-21 13:33:00 | Yes | N/A | N/A | N/A | N/A | N/A | N/A | N/A | No | N/A | No Change | No | N/A | No Change | Yes | TAO requested repairs in season | TAO | No | N/A | No Change | Yes | N/A | No Change
SEALROCK T104 | SK4 | 110KV SF6 Cubicle Ordinary Service | 901212214 | Yes | TO-21-SK-T104-01 | May | - | - | 5 | TAO requested repairs in season | 05-JUL-21 09:43:00 | 09-JUL-21 13:33:00 | Yes | N/A | Yes | Rescheduled to align with generator outage | TSO | No | N/A | No Change | No | N/A | No Change | No | N/A | No Change | Yes | TAO requested repairs in season | TAO | No | N/A | No Change | Yes | N/A | No Change
SEALROCK T104 | SK4 | 110KV CUBICLE CONDITION ASSESSMENT | 901212648 | Yes | TO-21-SK-T104-01 | May | - | - | 5 | TAO requested repairs in season | 05-JUL-21 09:43:00 | 09-JUL-21 13:33:00 | Yes | N/A | Yes | Rescheduled to align with generator outage | TSO | No | N/A | No Change | No | N/A | No Change | No | N/A | No Change | Yes | TAO requested repairs in season | TAO | No | N/A | No Change | Yes | N/A | No Change
SEALROCK T104 | SK4 | 110KV SF6 Cubicle Operational Test | 901129638 | Yes | TO-21-SK-T104-01 | May | - | - | 5 | TAO requested repairs in season | 05-JUL-21 09:43:00 | 09-JUL-21 13:33:00 | Yes | N/A | Yes | Rescheduled to align with generator outage | TSO | No | N/A | No Change | No | N/A | No Change | No | N/A | No Change | Yes | TAO requested repairs in season | TAO | No | N/A | No Change | Yes | N/A | No Change
SEALROCK T104 | SK4 | 6 months - Aughinish 4 S Phase S Phase 110 kV DL blade connection. A corrective maintenance action will be required within 6 months | 901213138 | No | TO-21-SK-T104-01 | - | - | - | - | N/A | 05-JUL-21 09:43:00 | 09-JUL-21 13:33:00 | Yes | N/A | N/A | N/A | N/A | N/A | N/A | N/A | No | N/A | No Change | No | N/A | No Change | No | N/A | No Change | No | N/A | No Change | Yes | N/A | No Change
SEALROCK T104 | SK4 | 3 months - Sealrock T104 R, S & T phase. Sealrock T104 DA, R,S & T phase A corrective maintenance action will be required within 3 months HOTSPOT DUE: 27Apr2021 | 901213139 | No | TO-21-SK-T104-01 | - | - | - | - | N/A | 05-JUL-21 09:43:00 | 09-JUL-21 13:33:00 | Yes | N/A | N/A | N/A | N/A | N/A | N/A | N/A | No | N/A | No Change | No | N/A | No Change | No | N/A | No Change | No | N/A | No Change | Yes | N/A | No Change
SEALROCK T104 | SK4 | Immediate - Aughinish 4 T Phase T Phase 110 kV cable sheath earth bolted connection Immediate corrective action required. | 901166996 | No | TO-21-SK-T104-01 | - | - | - | - | N/A | 05-JUL-21 09:43:00 | 09-JUL-21 13:33:00 | Yes | N/A | N/A | N/A | N/A | N/A | N/A | N/A | No | N/A | No Change | No | N/A | No Change | No | N/A | No Change | No | N/A | No Change | Yes | N/A | No Change
SHELLYBANKS T2014 | PB4 | 220kV Sect / Dist Operational Test | 901042991 | Yes | TO-21-SHL-T2014-02 | Unscheduled | - | - | - | N/A | 31-AUG-21 15:14:00 | 10-SEP-21 09:36:00 | Yes | N/A | No | N/A | No Change | N/A | N/A | N/A | Yes | Rescheduled as per generator request | GEN | Yes | Rescheduled as per generator request | GEN | No | N/A | No Change | Yes | Generator requested change to Committed Outage Programme | GEN | Yes | N/A | No Change
SHELLYBANKS T2014 | PB4 | Annual Insp. 400 & 220 Statn. XLPE Cable | 901005628 | Yes | TO-21-SHL-T2014-02 | Unscheduled | - | - | - | N/A | 31-AUG-21 15:14:00 | 10-SEP-21 09:36:00 | Yes | N/A | No | N/A | No Change | N/A | N/A | N/A | Yes | Rescheduled as per generator request | GEN | Yes | Rescheduled as per generator request | GEN | No | N/A | No Change | Yes | Generator requested change to Committed Outage Programme | GEN | Yes | N/A | No Change
SHELLYBANKS T2014 | PB4 | 220kV Sect / Dist Ordinary Service | 901130163 | Yes | TO-21-SHL-T2014-02 | Unscheduled | - | - | - | N/A | 31-AUG-21 15:14:00 | 10-SEP-21 09:36:00 | Yes | N/A | No | N/A | No Change | N/A | N/A | N/A | Yes | Rescheduled as per generator request | GEN | Yes | Rescheduled as per generator request | GEN | No | N/A | No Change | Yes | Generator requested change to Committed Outage Programme | GEN | Yes | N/A | No Change
SHELLYBANKS T2015 | PB5 | 220kV Sect / Dist Ordinary Service | 901130137 | Yes | TO-21-SHL-T2015-01 | October | - | - | 4 | N/A | 05-OCT-21 08:29:00 | 22-NOV-21 14:00:00 | Yes | N/A | No | N/A | No Change | No | N/A | No Change | Yes | Rescheduled to align with generator outage | TSO | Yes | Rescheduled to align with generator outage | GEN | No | N/A | No Change | Yes | Generator requested change to Committed Outage Programme | GEN | Yes | N/A | No Change
SHELLYBANKS T2015 | PB5 | 220kV Sect / Dist Operational Test | 901212414 | Yes | TO-21-SHL-T2015-01 | October | - | - | 4 | N/A | 05-OCT-21 08:29:00 | 22-NOV-21 14:00:00 | Yes | N/A | No | N/A | No Change | No | N/A | No Change | Yes | Rescheduled to align with generator outage | TSO | Yes | Rescheduled to align with generator outage | GEN | No | N/A | No Change | Yes | Generator requested change to Committed Outage Programme | GEN | Yes | N/A | No Change
SHELLYBANKS T2015 | PB5 | Cable Insp. 400 & 220kV Feeder XLPE | 901005629 | Yes | TO-21-SHL-T2015-01 | October | - | - | 4 | N/A | 05-OCT-21 08:29:00 | 22-NOV-21 14:00:00 | Yes | N/A | No | N/A | No Change | No | N/A | No Change | Yes | Rescheduled to align with generator outage | TSO | Yes | Rescheduled to align with generator outage | GEN | No | N/A | No Change | Yes | Generator requested change to Committed Outage Programme | GEN | Yes | N/A | No Change
SHELLYBANKS T2016 | PB6 | 220kV Sect / Dist Operational Test | 901042993 | Yes | TO-21-SHL-T2016-01 | September | - | - | 3 | N/A | 27-SEP-21 19:59:00 | 08-OCT-21 12:19:00 | Yes | N/A | Yes | Rescheduled to align with generator outage | TSO | No | N/A | No Change | Yes | Rescheduled to align with generator outage | TSO | Yes | Rescheduled to align with generator outage | GEN | No | N/A | No Change | Yes | Generator requested change to Committed Outage Programme | GEN | Yes | N/A | No Change
SHELLYBANKS T2016 | PB6 | 220kV Sect / Dist Ordinary Service | 901130138 | Yes | TO-21-SHL-T2016-01 | September | - | - | 3 | N/A | 27-SEP-21 19:59:00 | 08-OCT-21 12:19:00 | Yes | N/A | Yes | Rescheduled to align with generator outage | TSO | No | N/A | No Change | Yes | Rescheduled to align with generator outage | TSO | Yes | Rescheduled to align with generator outage | GEN | No | N/A | No Change | Yes | Generator requested change to Committed Outage Programme | GEN | Yes | N/A | No Change
SHELLYBANKS T2016 | PB6 | P2 Protection maintenance of 7SA513, | Protection | Yes | TO-21-SHL-T2016-03 | September | - | - | 3 | N/A | 27-SEP-21 19:59:00 | 08-OCT-21 12:19:00 | Yes | N/A | Yes | Rescheduled to align with generator outage | TSO | No | N/A | No Change | Yes | Rescheduled to align with generator outage | TSO | Yes | Rescheduled to align with generator outage | GEN | No | N/A | No Change | Yes | Generator requested change to Committed Outage Programme | GEN | Yes | N/A | No Change
SHELLYBANKS T2016 | PB6 | Cable Insp. 400 & 220kV Feeder XLPE | 901005630 | Yes | TO-21-SHL-T2016-01 | September | - | - | 3 | N/A | 27-SEP-21 19:59:00 | 08-OCT-21 12:19:00 | No | Unscheduled due to TAO resources | Yes | Rescheduled to align with generator outage | TSO | No | N/A | No Change | Yes | Rescheduled to align with generator outage | TSO | Yes | Rescheduled to align with generator outage | GEN | No | N/A | No Change | Yes | Generator requested change to Committed Outage Programme | TSO | No | Unscheduled due to TAO resources | TAO
SLIABH BAWN T132 | Sliabh Bawn SB1 | 110kV SF6 Cubicle Operational Test | 901212539 | Yes | TO-21-SLB-T132-01 | August | - | - | 1 | N/A | 07-APR-21 11:34:00 | 07-APR-21 17:55:00 | Yes | N/A | Yes | Rescheduled to align with generator outage | GEN | No | N/A | No Change | No | N/A | No Change | No | N/A | No Change | No | N/A | No Change | No | N/A | No Change | Yes | N/A | No Change
SLIEVECALLAN T121 | Knockalassa KD1 | 110kV MO Cubicle Operational Test | 901212922 | No | TO-21-SLC-T121-01 | - | - | - | - | TAO requested to carry out an Opt Test in season. Works aligned with cable inspection. | 17-AUG-21 08:50:00 | 20-AUG-21 13:21:00 | Yes | N/A | N/A | N/A | N/A | N/A | N/A | N/A | No | N/A | No Change | No | N/A | No Change | Yes | TAO requested to carry out an Opt Test in season. Works aligned with cable inspection. | TAO | No | N/A | No Change | Yes | N/A | No Change
SLIEVECALLAN T122 | Boolinrudda RD1 | 110kV MO Cubicle Operational Test | 901212921 | No | TO-21-SLC-T122-01 | - | - | - | - | TAO requested to carry out an Opt Test in season. Works aligned with cable inspection. | 17-AUG-21 08:50:00 | 20-AUG-21 13:21:00 | Yes | N/A | N/A | N/A | N/A | N/A | N/A | N/A | No | N/A | No Change | No | N/A | No Change | Yes | TAO requested to carry out an Opt Test in season. Works aligned with cable inspection. | TAO | No | N/A | No Change | Yes | N/A | No Change
SRAHNAKILLY T131 | Oweninny OY1 | 110kV SF6 Cubicle Operational Test | 901212540 | Yes | TO-21-SKY-T131-01 | June | - | - | 5 | N/A | 06-JUL-21 11:46:00 | 14-JUL-21 12:20:00 | Yes | N/A | Yes | Rescheduled to align with generator outage | GEN | Yes | Outage increased to facilitate generator works | GEN | Yes | Outage began late as per generator request | GEN | Yes | Outage began late as per generator request | GEN | No | N/A | No Change | Yes | Generator requested change | GEN | Yes | N/A | No Change
STRATFORD tee CARLOW | LI1, LI2, LI4 | P2 Protection maintenance of 7SA511 | Protection | Yes | TO-21-STR,T-CLW-1-01 | April | 2021-04-12 | 2021-04-30 | 19 | N/A | 14-APR-21 07:00:00 | 16-APR-21 10:00:00 | No | Works cancelled due to TAO resourcing | No | N/A | No Change | Yes | Work scope duration reduced at TAO request | GEN | Yes | Work scope duration reduced at TAO request | TAO | Yes | TAO completed works earlier than anticipated | TAO | No | N/A | No Change | No | N/A | No Change | No | Works cancelled due to TAO resourcing | TAO
STRATFORD tee CARLOW | LI1, LI2, LI4 | 110kV SF6 Cubicle Operational Test | 901129608 | Yes | TO-21-STR,T-CLW-1-01 | April | 2021-04-12 | 2021-04-30 | 19 | N/A | 14-APR-21 07:00:00 | 16-APR-21 10:00:00 | No | Works cancelled due to TAO resourcing | No | N/A | No Change | Yes | Work scope duration reduced at TAO request | GEN | Yes | Work scope duration reduced at TAO request | TAO | Yes | TAO completed works earlier than anticipated | TAO | No | N/A | No Change | No | N/A | No Change | No | Works cancelled due to TAO resourcing | TAO
STRATFORD tee CARLOW | LI1, LI2, LI4 | 2020LP-1[112]Off Plumb -Pole | 901169116 | Yes | TO-21-STR,T-CLW-1-01 | April | 2021-04-12 | 2021-04-30 | 19 | N/A | 14-APR-21 07:00:00 | 16-APR-21 10:00:00 | No | Works cancelled due to TAO resourcing | No | N/A | No Change | Yes | Work scope duration reduced at TAO request | GEN | Yes | Work scope duration reduced at TAO request | TAO | Yes | TAO completed works earlier than anticipated | TAO | No | N/A | No Change | No | N/A | No Change | No | Works cancelled due to TAO resourcing | TAO
STRATFORD tee CARLOW | LI1, LI2, LI4 | 2020LP-1[153]Off Plumb -Pole | 901169117 | Yes | TO-21-STR,T-CLW-1-01 | April | 2021-04-12 | 2021-04-30 | 19 | N/A | 14-APR-21 07:00:00 | 16-APR-21 10:00:00 | No | Works cancelled due to TAO resourcing | No | N/A | No Change | Yes | Work scope duration reduced at TAO request | GEN | Yes | Work scope duration reduced at TAO request | TAO | Yes | TAO completed works earlier than anticipated | TAO | No | N/A | No Change | No | N/A | No Change | No | Works cancelled due to TAO resourcing | TAO
STRATFORD tee CARLOW | LI1, LI2, LI4 | 2020LP-1[48]Off Plumb -Pole | 901169118 | Yes | TO-21-STR,T-CLW-1-01 | April | 2021-04-12 | 2021-04-30 | 19 | N/A | 14-APR-21 07:00:00 | 16-APR-21 10:00:00 | No | Works cancelled due to TAO resourcing | No | N/A | No Change | Yes | Work scope duration reduced at TAO request | GEN | Yes | Work scope duration reduced at TAO request | TAO | Yes | TAO completed works earlier than anticipated | TAO | No | N/A | No Change | No | N/A | No Change | No | Works cancelled due to TAO resourcing | TAO
STRATFORD tee CARLOW | LI1, LI2, LI4 | 2020LP-1[142]Repl. Pole -Botton rot | 901170002 | Yes | TO-21-STR,T-CLW-1-01 | April | 2021-04-12 | 2021-04-30 | 19 | N/A | 14-APR-21 07:00:00 | 16-APR-21 10:00:00 | No | Works cancelled due to TAO resourcing | No | N/A | No Change | Yes | Work scope duration reduced at TAO request | GEN | Yes | Work scope duration reduced at TAO request | TAO | Yes | TAO completed works earlier than anticipated | TAO | No | N/A | No Change | No | N/A | No Change | No | Works cancelled due to TAO resourcing | TAO
STRATFORD tee CARLOW | LI1, LI2, LI4 | 2020LP-1[144]Repl. Pole -Botton rot | 901170003 | Yes | TO-21-STR,T-CLW-1-01 | April | 2021-04-12 | 2021-04-30 | 19 | N/A | 14-APR-21 07:00:00 | 16-APR-21 10:00:00 | No | Works cancelled due to TAO resourcing | No | N/A | No Change | Yes | Work scope duration reduced at TAO request | GEN | Yes | Work scope duration reduced at TAO request | TAO | Yes | TAO completed works earlier than anticipated | TAO | No | N/A | No Change | No | N/A | No Change | No | Works cancelled due to TAO resourcing | TAO
STRATFORD tee CARLOW | LI1, LI2, LI4 | 2020LP-1[44]Repl. Pole -Botton rot | 901170004 | Yes | TO-21-STR,T-CLW-1-01 | April | 2021-04-12 | 2021-04-30 | 19 | N/A | 14-APR-21 07:00:00 | 16-APR-21 10:00:00 | No | Works cancelled due to TAO resourcing | No | N/A | No Change | Yes | Work scope duration reduced at TAO request | GEN | Yes | Work scope duration reduced at TAO request | TAO | Yes | TAO completed works earlier than anticipated | TAO | No | N/A | No Change | No | N/A | No Change | No | Works cancelled due to TAO resourcing | TAO
STRATFORD tee CARLOW | LI1, LI2, LI4 | 2020LP-1[60]Repl. Pole -Botton rot | 901170005 | Yes | TO-21-STR,T-CLW-1-01 | April | 2021-04-12 | 2021-04-30 | 19 | N/A | 14-APR-21 07:00:00 | 16-APR-21 10:00:00 | No | Works cancelled due to TAO resourcing | No | N/A | No Change | Yes | Work scope duration reduced at TAO request | GEN | Yes | Work scope duration reduced at TAO request | TAO | Yes | TAO completed works earlier than anticipated | TAO | No | N/A | No Change | No | N/A | No Change | No | Works cancelled due to TAO resourcing | TAO
STRATFORD tee CARLOW | LI1, LI2, LI4 | 2020HP-1[182]Off Plumb Straighten | 901171343 | Yes | TO-21-STR,T-CLW-1-01 | April | 2021-04-12 | 2021-04-30 | 19 | N/A | 14-APR-21 07:00:00 | 16-APR-21 10:00:00 | No | Works cancelled - No need for pole sag rectify | No | N/A | No Change | Yes | Work scope duration reduced at TAO request | GEN | Yes | Work scope duration reduced at TAO request | TAO | Yes | TAO completed works earlier than anticipated | TAO | No | N/A | No Change | No | N/A | No Change | No | Cancelled - No need for pole sag rectify | TAO
STRATFORD tee CARLOW | LI1, LI2, LI4 | 2020SAG-CHECK-1[59]Repl. Pole Sag issue | 901206243 | Yes | TO-21-STR,T-CLW-1-01 | April | 2021-04-12 | 2021-04-30 | 19 | N/A | 14-APR-21 07:00:00 | 16-APR-21 10:00:00 | No | Works cancelled - No need for pole sag rectify | No | N/A | No Change | Yes | Work scope duration reduced at TAO request | GEN | Yes | Work scope duration reduced at TAO request | TAO | Yes | TAO completed works earlier than anticipated | TAO | No | N/A | No Change | No | N/A | No Change | No | Cancelled - No need for pole sag rectify | TAO
STRATFORD tee CARLOW | LI1, LI2, LI4 | 2020SAG-CHECK-1[160]Repl. Pole Sag issue | 901206244 | Yes | TO-21-STR,T-CLW-1-01 | April | 2021-04-12 | 2021-04-30 | 19 | N/A | 14-APR-21 07:00:00 | 16-APR-21 10:00:00 | No | Works cancelled due to TAO resourcing | No | N/A | No Change | Yes | Work scope duration reduced at TAO request | GEN | Yes | Work scope duration reduced at TAO request | TAO | Yes | TAO completed works earlier than anticipated | TAO | No | N/A | No Change | No | N/A | No Change | No | Works cancelled due to TAO resourcing | TAO
STRATFORD tee POLLAPHUCA | LI1, LI2, LI4 | 2017HP-6[g/1]Insul & HW replace check | 900898185 | Yes | TO-21-STR,T-PA-1-01 | April | 2021-04-12 | 2021-04-30 | 19 | N/A | 14-APR-21 07:00:00 | 16-APR-21 10:00:00 | No | Work item was deferred following TAO request for a full station outage to complete works | No | N/A | No Change | Yes | Work scope duration reduced at TAO request | GEN | Yes | Work scope duration reduced at TAO request | TAO | Yes | TAO completed works earlier than anticipated | TAO | No | N/A | No Change | No | N/A | No Change | No | Work item was deferred following TAO request for a full station outage to complete works | TAO
STRATFORD tee POLLAPHUCA | LI1, LI2, LI4 | 2019HP-1[13]Off Plumb -plumb poles | 900864747 | Yes | TO-21-STR,T-PA-1-01 | April | 2021-04-12 | 2021-04-30 | 19 | N/A | 14-APR-21 07:00:00 | 16-APR-21 10:00:00 | No | Works cancelled due to TAO resourcing | No | N/A | No Change | Yes | Work scope duration reduced at TAO request | GEN | Yes | Work scope duration reduced at TAO request | TAO | Yes | TAO completed works earlier than anticipated | TAO | No | N/A | No Change | No | N/A | No Change | No | Works cancelled due to TAO resourcing | TAO
STRATFORD tee POLLAPHUCA | LI1, LI2, LI4 | P3 Protection maintenance of 7SA511 | Protection | Yes | TO-21-STR,T-PA-1-01 | April | 2021-04-12 | 2021-04-30 | 19 | N/A | 14-APR-21 07:00:00 | 16-APR-21 10:00:00 | Yes | N/A | No | N/A | No Change | Yes | Work scope duration reduced at TAO request | GEN | Yes | Work scope duration reduced at TAO request | TAO | Yes | TAO completed works earlier than anticipated | TAO | No | N/A | No Change | No | N/A | No Change | Yes | N/A | No Change
TARBERT T101 | TB1 | Annual Insp. 110kV Station OF Cable | 901129017 | Yes | TO-21-TB-T101-01 | May | - | - | 2 | N/A | 15-MAY-21 07:00:00 | 19-MAY-21 13:15:00 | Completed in Previous Outage Season | N/A | No | N/A | No Change | Yes | Outage duration changed to facilitate Capex works | TAO | Yes | Generators outage started a day late due to plant fault | GEN | Yes | Generators outage started a day late due to plant fault | GEN | Completed in Previous Outage Season | Completed in Previous Outage Season | TAO | Yes | Generator requested change to Committed Outage Programme | GEN | N/A | N/A | N/A
TARBERT T101 | TB1 | 110KV SF6 Cubicle Operational Test | 901212259 | Yes | TO-21-TB-T101-01 | May | - | - | 2 | N/A | 15-MAY-21 07:00:00 | 19-MAY-21 13:15:00 | Yes | N/A | No | N/A | No Change | Yes | Outage duration changed to facilitate Capex works | TAO | Yes | Generators outage started a day late due to plant fault | GEN | Yes | Generators outage started a day late due to plant fault | GEN | No | N/A | No Change | Yes | Generator requested change to Committed Outage Programme | GEN | Yes | N/A | No Change
TARBERT T102 | TB2 | Annual Insp. 110kV Station OF Cable | 901129018 | Yes | TO-21-TB-T102-01 | May | - | - | 2 | N/A | 19-MAY-21 12:00:00 | 26-MAY-21 16:25:00 | Completed in Previous Outage Season | N/A | No | N/A | No Change | Yes | Outage increased to facilitate generator works | GEN | Yes | Outage increased to facilitate generator works | GEN | Yes | Outage increased to facilitate generator works | GEN | Completed in Previous Outage Season | Completed in Previous Outage Season | TAO | Yes | Generator requested change to Committed Outage Programme | GEN | N/A | N/A | N/A
TARBERT T102 | TB2 | 110KV SF6 Cubicle Operational Test | 901212542 | Yes | TO-21-TB-T102-01 | May | - | - | 2 | N/A | 19-MAY-21 12:00:00 | 26-MAY-21 16:25:00 | Yes | N/A | No | N/A | No Change | Yes | Outage increased to facilitate generator works | GEN | Yes | Outage increased to facilitate generator works | GEN | Yes | Outage increased to facilitate generator works | GEN | No | N/A | No Change | Yes | Generator requested change to Committed Outage Programme | GEN | Yes | N/A | No Change
TARBERT T2003 | TB3 | 6 months - T2003 220 kV cubicle. S Phase S Phase DA Pantograph knuckle joints. A corrective maintenance action will be necessary during the next planned maintenance | 901212946 | No | TO-21-TB-T2003-03 | - | - | - | - | TAO requested repairs in season | 09-AUG-21 20:59:00 | 11-AUG-21 15:45:00 | Yes | N/A | N/A | N/A | N/A | N/A | N/A | N/A | No | N/A | No Change | No | N/A | No Change | Yes | TAO requested repairs in season | TAO | No | N/A | No Change | Yes | N/A | No Change
TARBERT T2003 | TB3 | 6 months - T2003 220 kV cubicle. T Phase DA Pantograph knuckle joints. A corrective maintenance action will be necessary during the next planned maintenance | 901212947 | No | TO-21-TB-T2003-03 | - | - | - | - | TAO requested repairs in season | 09-AUG-21 20:59:00 | 11-AUG-21 15:45:00 | Yes | N/A | N/A | N/A | N/A | N/A | N/A | N/A | No | N/A | No Change | No | N/A | No Change | Yes | TAO requested repairs in season | TAO | No | N/A | No Change | Yes | N/A | No Change
TARBERT T2003 | TB3 | P3 Protection maintenance of R1Z23b, S TYPE, RT22b | Protection | Yes | TO-21-TB-T2003-03 | May | - | - | 2 | N/A | 09-AUG-21 20:59:00 | 11-AUG-21 15:45:00 | Yes | N/A | Yes | Rescheduled to align with generator outage | TSO | Yes | Work scope duration increased at TAO request | TAO | No | N/A | No Change | No | N/A | No Change | No | N/A | No Change | No | N/A | No Change | Yes | N/A | No Change
TARBERT T2004 | TB4 | Investigate & Repair Hotspot Next Planned Opportunity HotSpot | 901212948 | No | TO-21-TB-T2004-04 | - | - | - | - | Hotspot identified by TAO in advance of outage. Aligned with generator outage | 2021-11-19 17:01 | 2021-11-22 17:42 | Yes | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Yes | Rescheduled as per TAO request | TAO | Yes | Rescheduled as per TAO request | TAO | Yes | Hotspot identified by TAO in advance of outage. Aligned with generator outage | TAO | Yes | Generator requested change to Committed Outage Programme | TAO | Yes | N/A | No Change
TARBERT T2004 | TB4 | Investigate & Repair Hotspot Next Planned Maintenance | 901212949 | No | TO-21-TB-T2004-04 | - | - | - | - | Hotspot identified by TAO in advance of outage. Aligned with generator outage | 2021-11-19 17:01 | 2021-11-22 17:42 | Yes | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Yes | Rescheduled as per TAO request | TAO | Yes | Rescheduled as per TAO request | TAO | Yes | Hotspot identified by TAO in advance of outage. Aligned with generator outage | TAO | Yes | Generator requested change to Committed Outage Programme | TAO | Yes | N/A | No Change
TAWNAGHMORE T1/T2 | TP1 | 110kV SF6 Cubicle Operational Test | 901212543 | Yes | TO-21-TAW-T1/T2-01 | April | 2021-04-13 | 2021-04-13 | 1 | N/A | 12-APR-21 13:02:00 | 04-MAY-21 13:00:00 | Yes | N/A | No | N/A | No Change | No | N/A | No Change | Yes | Rescheduled as per generator request | GEN | No | N/A | No Change | No | N/A | No Change | Yes | Generator requested change | GEN | Yes | N/A | No Change
TAWNAGHMORE T3 | TP3 | 110kV SF6 Cubicle Operational Test | 901212544 | Yes | TO-21-TAW-T3-01 | April | 2021-04-13 | 2021-04-13 | 1 | N/A | 12-APR-21 13:02:00 | 04-MAY-21 13:00:00 | Yes | N/A | No | N/A | No Change | No | N/A | No Change | Yes | Rescheduled as per generator request | GEN | No | N/A | No Change | No | N/A | No Change | Yes | Generator requested change | GEN | Yes | N/A | No Change
TURLOUGH HILL T2001/2 | TH1/2 | Annual Insp. 400 & 220 Station OF Cable | 901212197 | Yes | TO-21-TH-T2001/2-01 | October | - | - | 2 | N/A | - | - | No | Unscheduled due to TAO resources | N/A | N/A | N/A | N/A | N/A | N/A | Yes | Unscheduled due to TAO resources | TAO | N/A | N/A | N/A | No | N/A | No Change | No | N/A | No Change | No | Unscheduled due to TAO resources | TAO
TURLOUGH HILL T2001/2 | TH1/2 | 220kV MO Cubicle Operational Test | 901212400 | Yes | TO-21-TH-T2001/2-01 | October | - | - | 2 | N/A | - | - | No | Unscheduled due to TAO resources | N/A | N/A | N/A | N/A | N/A | N/A | Yes | Unscheduled due to TAO resources | TAO | N/A | N/A | N/A | No | N/A | No Change | No | N/A | No Change | No | Unscheduled due to TAO resources | TAO
TURLOUGH HILL T2003/4 | TH3/4 | Annual Insp. 400 & 220 Station OF Cable | 901005768 | Yes | TO-21-TH-T2003/4-01 | March | 2021-03-22 | 2021-03-23 | 2 | N/A | 21-MAR-21 23:30:00 | 25-MAR-21 11:48:00 | No | Unscheduled due to TAO resources | Yes | Rescheduled to align with generator outage | GEN | Yes | Outage increased to facilitate generator works | GEN | Yes | Rescheduled as per generator request | GEN | Yes | Rescheduled as per TAO request | TAO | No | N/A | No Change | No | N/A | No Change | No | Unscheduled due to TAO resources | TAO
TURLOUGH HILL T2003/4 | TH3/4 | 110kV MO Cubicle Ordinary Service | 901129829 | Yes | TO-21-TH-T2003/4-02 | Unscheduled | - | - | 10 | N/A | - | - | Yes | N/A | N/A | N/A | N/A | N/A | N/A | N/A | - | N/A | - | N/A | N/A | N/A | N/A | N/A | N/A | No | N/A | No Change | Yes | N/A | No Change
TYNAGH T2001/2 | TYC | O1-Replace T2001/2 220kv Contacts on DL | 901135020 | Yes | TO-21-TY-T2001/2-01 | April | 2021-04-12 | 2021-04-20 | 9 | N/A | 14-APR-21 18:53:00 | 30-APR-21 17:14:00 | No | Unscheduled due to TAO resources | No | N/A | No Change | Yes | Work scope duration increased at TAO request | TAO | Yes | Rescheduled as per generator request | GEN | Yes | Rescheduled as per TAO request | TAO | No | N/A | No Change | No | N/A | No Change | No | Unscheduled due to TAO resources | TAO
TYNAGH T2001/2 | TYC | 220kV SF6 Cubicle Ordinary Service | 901227721 | Yes | TO-21-TY-T2001/2-01 | April | 2021-04-12 | 2021-04-20 | 9 | N/A | 14-APR-21 18:53:00 | 30-APR-21 17:14:00 | Yes | N/A | No | N/A | No Change | Yes | Work scope duration increased at TAO request | TAO | Yes | Rescheduled as per generator request | GEN | Yes | Rescheduled as per TAO request | TAO | No | N/A | No Change | No | N/A | No Change | Yes | N/A | No Change
TYNAGH T2001/2 | TYC | 220kV Cubicle Condition Assessment | 901212227 | Yes | TO-21-TY-T2001/2-01 | April | 2021-04-12 | 2021-04-20 | 9 | N/A | 14-APR-21 18:53:00 | 30-APR-21 17:14:00 | Yes | N/A | No | N/A | No Change | Yes | Work scope duration increased at TAO request | TAO | Yes | Rescheduled as per generator request | GEN | Yes | Rescheduled as per TAO request | TAO | No | N/A | No Change | No | N/A | No Change | Yes | N/A | No Change
UGGOOL 110SA1-2CB | Seecon SO1 | P2 Protection maintenance of 7SJ611 | Protection | Yes | TO-21-UGL-110SA1-2CB | July | - | - | 3 | N/A | 05-JUL-21 11:55:00 | 07-JUL-21 17:36:00 | Yes | N/A | No | N/A | No Change | No | N/A | No Change | No | N/A | No Change | No | N/A | No Change | No | N/A | No Change | No | N/A | No Change | Yes | N/A | No Change
UGGOOL 110SA1-2CB | Seecon SO1 | 110kV GIS Cubicle Operational Test | 901212188 | Yes | TO-21-UGL-110SA1-2CB | July | - | - | 3 | N/A | 05-JUL-21 11:55:00 | 07-JUL-21 17:36:00 | Yes | N/A | No | N/A | No Change | No | N/A | No Change | No | N/A | No Change | No | N/A | No Change | No | N/A | No Change | No | N/A | No Change | Yes | N/A | No Change
UGGOOL T131 | Uggool UG1 | Annual Insp. 110kV Feeder XLPE Cable | Asset not transferred to ESBN | Yes | TO-21-UGL-T131-01 | July | - | - | 3 | N/A | 05-JUL-21 11:55:00 | 07-JUL-21 17:36:00 | No | Asset not transferred to ESBN | No | N/A | No Change | No | N/A | No Change | No | N/A | No Change | No | N/A | No Change | No | N/A | No Change | No | N/A | No Change | No | Asset not transferred to ESBN | GEN
UGGOOL T131 | Uggool UG1 | 110 kV SF6 Cubicle Operational Test - T131 | 901212545 | Yes | TO-21-UGL-T131-01 | July | - | - | 3 | N/A | 05-JUL-21 11:55:00 | 07-JUL-21 17:36:00 | No | Asset not transferred to ESBN | No | N/A | No Change | No | N/A | No Change | No | N/A | No Change | No | N/A | No Change | No | N/A | No Change | No | N/A | No Change | No | Asset not transferred to ESBN | GEN
UGGOOL T132 | Seecon SO1 | Annual Insp. 110kV Feeder XLPE Cable | Asset not transferred to ESBN | Yes | TO-21-UGL-T132-01 | July | - | - | 3 | N/A | 05-JUL-21 11:55:00 | 07-JUL-21 17:36:00 | No | Asset not transferred to ESBN | No | N/A | No Change | No | N/A | No Change | No | N/A | No Change | No | N/A | No Change | No | N/A | No Change | No | N/A | No Change | No | Asset not transferred to ESBN | GEN
UGGOOL T132 | Seecon SO1 | 110 kV SF6 Cubicle Operational Test - T132 | 901212546 | Yes | TO-21-UGL-T132-01 | July | - | - | 3 | N/A | 05-JUL-21 11:55:00 | 07-JUL-21 17:36:00 | No | Asset not transferred to ESBN | No | N/A | No Change | No | N/A | No Change | No | N/A | No Change | No | N/A | No Change | No | N/A | No Change | No | N/A | No Change | No | Asset not transferred to ESBN | GEN
UGGOOL T134 | Seecon SO1 | Annual Insp. 110kV Feeder XLPE Cable | Asset not transferred to ESBN | Yes | TO-21-UGL-T134-01 | July | - | - | 3 | N/A | 05-JUL-21 11:55:00 | 07-JUL-21 17:36:00 | No | Asset not transferred to ESBN | No | N/A | No Change | No | N/A | No Change | No | N/A | No Change | No | N/A | No Change | No | N/A | No Change | No | N/A | No Change | No | Asset not transferred to ESBN | GEN
UGGOOL T134 | Seecon SO1 | 110 kV SF6 Cubicle Operational Test - T134 | 901212547 | Yes | TO-21-UGL-T134-01 | July | - | - | 3 | N/A | 05-JUL-21 11:55:00 | 07-JUL-21 17:36:00 | No | Asset not transferred to ESBN | No | N/A | No Change | No | N/A | No Change | No | N/A | No Change | No | N/A | No Change | No | N/A | No Change | No | N/A | No Change | No | Asset not transferred to ESBN | GEN
WOODHOUSE T122 | Woodhouse WS1 | 110kV SF6 Cubicle Operational Test | 901212548 | Yes | TO-21-WOH-T122-01 | May | - | - | 2 | N/A | 05-MAY-21 10:43:00 | 06-MAY-21 18:43:00 | Yes | N/A | No | N/A | No Change | No | N/A | No Change | No | N/A | No Change | No | N/A | No Change | No | N/A | No Change | No | N/A | No Change | Yes | N/A | No Change