## OACA Outage Tracker
General |  | Communicated in Ex-Ante Report | [5 empty] | Communicated M-1 | [7 empty] | Actual Outage |  | 1. Indicative Window (Actual - Ex-Ante) |  |  | 2. Indicative Duration (Actual - Ex-Ante) |  |  | 3. Scheduled Days |  |  | Actual Designated Days |  |  |  |  | 4. Designated Days
[8 empty] | Scheduled Dates |  |  | Designated Days
OACA | Unit(s) | Included in Ex-Ante Report? | TOP ID in the Ex-Ante Report | Outage Window | Start Date if Applicable | End Date if Applicable | Outage Duration | Date of Communication | Scheduled Start | Scheduled End | Day 1 | Day 2 | Day 3 | Day4 | Day 5 | Actual Start Date | Actual End Date | Change to Window? | Reason for Change to Window, if applicable | Driver of Change to Window (e.g. TSO, TAO, GEN) | Change to Duration? | Reason for Change to Duration, if applicable | Driver of Change to Duration (e.g. TSO, TAO, GEN) | Change to Scheduled Dates communicated M-1? | Reason for Change to Scheduled Dates communicated M-1, if applicable | Driver of Change to Scheduled Dates communicated M-1 (e.g. TSO, TAO, GEN) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Change to Designated Days communicated M-1? | Reason for change to Designated Days communicated M-1, if applicable | Driver of Change to Designated Days (e.g. TSO, TAO, GEN)
AGHADA LONG POINT | AD2 | Yes | TO-24-AD-LPT-1-02 | Mar | 2024-03-04 | 2024-03-08 | 5 | 2024-03-06 | 2024-02-26 | 2024-04-12 | 2024-02-26 | N/A | N/A | N/A | N/A | 2024-02-26 | 2024-06-11 | Yes | Aligned to long term generator forced outage | Generator | Yes | Aligned to long term generator forced outage | Generator | Yes | To align with customer request | Generator | 2024-02-26 | N/A | N/A | N/A | N/A | No | N/A | No Change
AGHADA ST101 | AD3 | Yes | TO-24-AD-ST101-01 | Apr | 2024-04-22 | 2024-04-26 | 5 | 2024-04-04 | 2024-04-22 | 2024-04-26 | 2024-04-22 | 2024-04-23 | 2024-04-24 | 2024-04-25 | 2024-04-26 | 2024-04-22 | 2024-05-10 | No | N/A | No Change | Yes | Increased duration due to request by TAO | TAO | Yes | Increase in maintenance required and TAO request | TAO | 2024-04-22 | 2024-04-23 | 2024-04-24 | 2024-04-25 | 2024-04-26 | No | N/A | No Change
AGHADA T2011/12 | AT11/AT12 | Yes | TO-24-AD-T2011/12-02 | Sep | - | - | 5 | 2024-08-19 | 2024-08-21 | 2024-08-28 | 2024-08-21 | 2024-08-22 | 2024-08-23 | 2024-08-24 | 2024-08-25 | 2024-08-21 | 2024-08-28 | Yes | To align maintenance with capital works | TSO | Yes | To align maintenance with capital works | TSO | No | N/A | No Change | 2024-08-21 | 2024-08-22 | 2024-08-23 | 2024-08-24 | 2024-08-25 | No | N/A | No Change
AGHADA T2014 | AT14 | Yes | TO-24-AD-T2014-02 | Sep | - | - | 5 | 2024-08-19 | 2024-08-21 | 2024-08-28 | 2024-08-21 | 2024-08-22 | 2024-08-23 | 2024-08-24 | 2024-08-25 | 2024-08-21 | 2024-08-28 | Yes | To align maintenance with capital works | TSO | Yes | To align maintenance with capital works | TSO | No | N/A | No Change | 2024-08-21 | 2024-08-22 | 2024-08-23 | 2024-08-24 | 2024-08-25 | No | N/A | No Change
MONEYPOINT GIS T121 | MP9 | Yes | TO-24-MP GIS-T121-02 | Aug | - | - | 10 | 2024-08-22 | 2024-09-02 | 2024-09-06 | 2024-09-02 | 2024-09-03 | N/A | N/A | N/A | 2024-09-02 | 2024-09-06 | Yes | Aligned with generator outage change in dates | Generator | Yes | Change in maintenance requirements | Generator | No | N/A | No Change | 2024-09-02 | 2024-09-03 | N/A | N/A | N/A | No | N/A | No Change
CARRIGDANGAN DUNMANWAY | XA1 | Yes | TO-24-CGG-DMY-1-01 | Mar | 2024-03-19 | 2024-03-25 | 7 | 2024-03-08 | 2024-03-19 | 2024-03-25 | 2024-04-19 | N/A | N/A | N/A | N/A | 2024-03-19 | 2024-03-26 | No | N/A | No Change | Yes | To align with customer request | Generator | Yes | Operator unavailable | TAO | 2024-03-19 | N/A | N/A | N/A | N/A | No | N/A | No Change
ARDNACRUSHA GIS T103 | AA3 | Yes | TO-24-AA GIS-T103-01 | Sep | - | - | 4 |  | 2024-09-09 | 2024-09-13 | 2024-09-09 | 2024-09-10 | 2024-09-11 | 2024-09-12 | 2024-09-13 | 2024-09-09 | 2024-09-12 | No | N/A | No Change | No | N/A | No Change | No | N/A | No Change | 2024-09-09 | 2024-09-10 | 2024-09-11 | 2024-09-12 | N/A | No | N/A | No Change
BELLACORICK SRAHNAKILLY | OY1, OY2 | Yes | TO-24-BK-SKY-1-02 | Apr | 2024-04-08 | 2024-04-26 | 19 | 2024-03-21 | 2024-04-08 | 2024-04-26 | 2024-04-08 | 2024-04-09 | 2024-04-10 | 2024-04-11 | 2024-04-12 | 2024-04-08 | 2024-05-24 | No | N/A | No Change | Yes | Due to cable fault | Generator | Yes | Due to cable fault | Generator | 2024-04-08 | 2024-04-09 | 2024-04-10 | 2024-04-11 | 2024-04-12 | No | N/A | No Change
ATHEA DROMADA | DR1 | Yes | TO-24-ATE-DRO-1-01 | Jun | - | - | 5 | 2024-06-06 | 2024-06-17 | 2024-06-26 | 2024-06-17 | 2024-06-18 | 2024-06-19 | 2024-06-20 | 2024-06-21 | 2024-06-17 | 2024-06-26 | No | N/A | No Change | Yes | Increased duration due to request by TAO | TAO | No | N/A | No Change | 2024-06-17 | 2024-06-18 | 2024-06-19 | 2024-06-20 | 2024-06-21 | No | N/A | No Change
ATHEA KNOCKANURE | AH1, XT1, XT2, DR1 | Yes | TO-24-ATE-KNR-1-01 | Jun | - | - | 5 | 2024-06-06 | 2024-06-17 | 2024-06-26 | 2024-06-17 | 2024-06-18 | 2024-06-19 | 2024-06-20 | 2024-06-21 | 2024-06-17 | 2024-06-26 | No | N/A | No Change | Yes | Increased duration due to request by TAO | TAO | No | N/A | No Change | 2024-06-17 | 2024-06-18 | 2024-06-19 | 2024-06-20 | 2024-06-21 | No | N/A | No Change
ATHEA T121 | AH1 | Yes | TO-24-ATE-T121-01 | Jun | - | - | 5 | 2024-06-06 | 2024-06-17 | 2024-06-26 | 2024-06-17 | 2024-06-18 | 2024-06-19 | 2024-06-20 | 2024-06-21 | 2024-06-17 | 2024-06-26 | No | N/A | No Change | Yes | Increased duration due to request by TAO | TAO | No | N/A | No Change | 2024-06-17 | 2024-06-18 | 2024-06-19 | 2024-06-20 | 2024-06-21 | No | N/A | No Change
ATHEA TOBERTOREEN | XT1, XT2 | Yes | TO-24-ATE-TOB-1-02 | Jun | - | - | 5 | 2024-06-06 | 2024-06-17 | 2024-06-26 | 2024-06-17 | 2024-06-18 | 2024-06-19 | 2024-06-20 | 2024-06-21 | 2024-06-17 | 2024-06-26 | No | N/A | No Change | Yes | Increased duration due to request by TAO | TAO | No | N/A | No Change | 2024-06-17 | 2024-06-18 | 2024-06-19 | 2024-06-20 | 2024-06-21 | No | N/A | No Change
SRAHNAKILLY 110SA1 | OY2 | Yes | TO-24-SKY-110SA1-02 | Apr | 2024-04-08 | 2024-04-26 | 19 | 2024-03-07 | 2024-04-08 | 2024-04-26 | 2024-04-08 | 2024-04-09 | 2024-04-10 | 2024-04-11 | 2024-04-12 | 2024-04-08 | 2024-05-24 | No | N/A | No Change | Yes | Due to cable fault | Generator | Yes | Due to cable fault | Generator | 2024-04-08 | 2024-04-09 | 2024-04-10 | 2024-04-11 | 2024-04-12 | No | N/A | No Change
SRAHNAKILLY 110SA2 | OY2 | Yes | TO-24-SKY-110SA2-02 | Apr | 2024-04-08 | 2024-04-26 | 19 | 2024-03-21 | 2024-04-08 | 2024-04-26 | 2024-04-08 | 2024-04-09 | 2024-04-10 | 2024-04-11 | 2024-04-12 | 2024-04-08 | 2024-05-24 | No | N/A | No Change | Yes | Due to cable fault | Generator | Yes | Due to cable fault | Generator | 2024-04-08 | 2024-04-09 | 2024-04-10 | 2024-04-11 | 2024-04-12 | No | N/A | No Change
BALLYNAHULLA CORDAL | DL1/DL2 | Yes | TO-24-BYH-CDL-1-01 | May | - | - | 4 | 2024-04-04 | 2024-05-27 | 2024-05-30 | 2024-05-27 | 2024-05-28 | 2024-05-29 | 2024-05-30 | N/A | 2024-05-27 | 2024-05-30 | No | N/A | No Change | No | N/A | No Change | No | N/A | No Change | 2024-05-27 | 2024-05-28 | 2024-05-29 | 2024-05-30 | N/A | No | N/A | No Change
BALLYVOUSKILL COOMATAGGART | GD1 | Yes | TO-24-BVK-COT-1-01 | Jul | - | - | 5 | 2024-06-13 | 2024-07-01 | 2024-07-09 | 2024-07-01 | 2024-07-02 | 2024-07-03 | 2024-07-04 | 2024-07-05 | 2024-07-01 | 2024-07-09 | No | N/A | No Change | Yes | TAO request increase to complete all works | TAO | No | N/A | No Change | 2024-07-01 | 2024-07-02 | 2024-07-03 | 2024-07-04 | 2024-07-05 | No | N/A | No Change
BALLYWATER CRANE | BW1 | Yes | TO-24-BWR-CRA-1-02 | - | - | - | 2 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BARRYMORE tee CAHIR | BF1 | Yes | TO-24-BAR,T-CAH-1-01 | Jul-Aug | - | - | 10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BARRYMORE tee KNOCKRAHA | BF1 | Yes | TO-24-BAR,T-KRA-1-01 | Jul-Aug | - | - | 10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SRAHNAKILLY T131 | OY1 | Yes | TO-24-SKY-T131-03 | Apr | 2024-04-08 | 2024-04-26 | 19 | 2024-03-21 | 2024-04-08 | 2024-04-26 | 2024-04-08 | 2024-04-09 | 2024-04-10 | 2024-04-11 | 2024-04-12 | 2024-04-08 | 2024-05-24 | No | N/A | No Change | Yes | Due to cable fault | Generator | Yes | Due to cable fault | Generator | 2024-04-08 | 2024-04-09 | 2024-04-10 | 2024-04-11 | 2024-04-12 | No | N/A | No Change
BOGGERAGH 110SA1 | BG2 | Yes | TO-24-BGH-110SA1-01 | Aug | - | - | 7 | 2024-06-25 | 2024-08-19 | 2024-08-30 | 2024-08-19 | 2024-08-20 | 2024-08-21 | 2024-08-22 | 2024-08-23 | 2024-08-19 | 2024-08-30 | No | N/A | No Change | Yes | Increased duration due to request by TAO | TAO | No | N/A | No Change | 2024-08-19 | 2024-08-20 | 2024-08-21 | 2024-08-22 | 2024-08-23 | No | N/A | No Change
BOGGERAGH CLASHAVOON | BG1, BG2 | Yes | TO-24-BGH-CLA-1-01 | Aug | - | - | 7 | 2024-06-25 | 2024-08-19 | 2024-08-30 | 2024-08-19 | 2024-08-20 | 2024-08-21 | 2024-08-22 | 2024-08-23 | 2024-08-19 | 2024-08-30 | No | N/A | No Change | Yes | Increased duration due to request by TAO | TAO | No | N/A | No Change | 2024-08-19 | 2024-08-20 | 2024-08-21 | 2024-08-22 | 2024-08-27 | No | To align with updated customer outage dates | Generator
BOGGERAGH T121 | BG1 | Yes | TO-24-BGH-T121-01 | Aug | - | - | 7 | 2024-06-25 | 2024-08-19 | 2024-08-30 | 2024-08-19 | 2024-08-20 | 2024-08-21 | 2024-08-22 | 2024-08-23 | 2024-08-19 | 2024-08-30 | No | N/A | No Change | Yes | Increased duration due to request by TAO | TAO | No | N/A | No Change | 2024-08-19 | 2024-08-20 | 2024-08-21 | 2024-08-22 | 2024-08-27 | Yes | To align with updated customer outage dates | Generator
BOGGERAGH T132 | BG2 | Yes | TO-24-BGH-T132-01 | Aug | - | - | 7 | 2024-06-25 | 2024-08-19 | 2024-08-30 | 2024-08-19 | 2024-08-20 | 2024-08-21 | 2024-08-22 | 2024-08-23 | 2024-08-19 | 2024-08-30 | No | N/A | No Change | Yes | Increased duration due to request by TAO | TAO | No | N/A | No Change | 2024-08-19 | 2024-08-20 | 2024-08-21 | 2024-08-22 | 2024-08-23 | No | N/A | No Change
BOOLTIAGH T121 | BT1, BT2 | Yes | TO-24-BOL-T121-01 | Aug | - | - | 12 | 2024-08-08 | 2024-08-19 | 2024-08-30 | 2024-08-19 | 2024-08-20 | 2024-08-21 | 2024-08-22 | 2024-08-23 | 2024-08-19 | 2024-08-30 | No | N/A | No Change | No | N/A | No Change | No | N/A | No Change | 2024-08-19 | 2024-08-20 | 2024-08-21 | 2024-08-28 | 2024-08-29 | Yes | To align with updated customer outage dates | Generator
CARRIGADROHID T103 | LE3 | Yes | TO-24-CD-T103-02 | Unscheduled | - | - | 2 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
LONG POINT T2002 | AD2 | Yes | TO-24-LPT-T2002-02 | Feb-Apr | 2024-02-26 | 2024-04-12 | 47 | 2024-02-20 | 2024-02-26 | 2024-04-12 | 2024-02-26 | N/A | N/A | N/A | N/A | 2024-02-26 | 2024-06-11 | Yes | Due to generator forced outage | Generator | YES | Due to generator forced outage | Generator | Yes | To align with generator outage | Generator | 2024-02-26 | N/A | N/A | N/A | N/A | No | N/A | No Change
AUGHINISH SEALROCK 4 | SK4 | Yes | TO-24-AUG-SK-4-01 | Jul-Sep | - | - | 44 | 2024-06-25 | 2024-07-08 | 2024-09-02 | 2024-07-08 | 2024-07-09 | 2024-07-10 | 2024-07-11 | 2024-07-12 | 2024-07-08 | 2024-09-11 | No | N/A | No Change | Yes | Generator request | Generator | No | N/A | No Change | 2024-07-08 | 2024-07-09 | 2024-07-10 | 2024-07-11 | 2024-07-12 | No | N/A | No Change
CATHALEENS FALL T103 | ER3 | Yes | TO-24-CF-T103-01 | Jun | - | - | 7 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CATHALEENS FALL T104 | ER4 | Yes | TO-24-CF-T104-01 | Sep | - | - | 7 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CLAHANE T122 | CJ1, CJ2 | Yes | TO-24-CLH-T122-01 | May | - | - | 5 | 2024-04-04 | 2024-05-13 | 2024-05-17 | 2024-05-13 | 2024-05-14 | 2024-05-15 | 2024-05-16 | 2024-05-17 | 2024-05-13 | 2024-05-17 | No | N/A | No Change | No | N/A | No Change | No | N/A | No Change | 2024-05-13 | 2024-05-14 | 2024-05-15 | 2024-05-16 | 2024-05-17 | No | N/A | No Change
CUSHALING T101 | ED1 | Yes | TO-24-CUS-T101-01 | Aug | - | - | 1 | 2024-06-25 | 2024-08-06 | 2024-08-22 | 2024-08-06 | 2024-08-07 | 2024-08-08 | 2024-08-09 | 2024-08-12 | 2024-08-08 | 2024-08-22 | No | N/A | No Change | Yes | Generator required transformer outage for long duration facilitate works | Generator | Yes | Operator unavailable | TAO | 2024-08-08 | 2024-08-09 | 2024-08-12 | 2024-08-13 | 2024-08-14 | Yes | Due to TAO resourcing | TAO
DERRYCARNEY T134 | NC1 | Yes | TO-24-DEY-T134-02 | Jun | - | - | 2 | 2024-03-07 | 2024-03-20 | 2024-03-21 | 2024-03-20 | 2024-03-21 | N/A | N/A | N/A | 2024-03-21 | 2024-03-21 | Yes | Aligned with generator outage change in dates | Generator | Yes | IPP change in operator availability | Generator | Yes | IPP change in operator availability | Generator | 2024-03-21 | N/A | N/A | N/A | N/A | Yes | Decrease in duration due to IPP operator availability | Generator
CLOGHBOOLA T131 | CL1 | Yes | TO-24-CBA-T131-01 | Jul | - | - | 5 | 2024-07-11 | 2024-07-29 | 2024-08-02 | 2024-07-29 | 2024-07-30 | 2024-07-31 | N/A | N/A | 2024-07-29 | 2024-08-02 | No | N/A | No Change | No | N/A | No Change | No | N/A | No Change | 2024-07-29 | 2024-07-30 | 2024-07-31 | N/A | N/A | No | N/A | No Change
CLOGHBOOLA TRIEN | CL1 | Yes | TO-24-CBA-TRI-1-01 | Jul | - | - | 5 | 2024-07-11 | 2024-07-29 | 2024-08-02 | 2024-07-29 | 2024-07-30 | 2024-07-31 | N/A | N/A | 2024-07-29 | 2024-08-02 | No | N/A | No Change | No | N/A | No Change | No | N/A | No Change | 2024-07-29 | 2024-07-30 | 2024-07-31 | N/A | N/A | No | N/A | No Change
CLOGHER MULREAVY | MB1, MB2 | Yes | TO-24-CLO-MRY-1-01 | Apr | 2024-04-22 | 2024-04-29 | 8 | 2024-04-04 | 2024-04-22 | 2024-04-29 | 2024-04-22 | 2024-04-23 | 2024-04-24 | 2024-04-25 | 2024-04-26 | 2024-04-22 | 2024-04-29 | No | N/A | No Change | No | N/A | No Change | No | N/A | No Change | 2024-04-22 | 2024-04-23 | 2024-04-24 | 2024-04-25 | 2024-04-26 | No | N/A | No Change
GORMAN T122 | GF1 | Yes | TO-24-GOR-T122-01 | Apr | 2024-04-30 | 2024-04-30 | 1 | 2024-04-04 | 2024-04-30 | 2024-04-30 | 2024-04-30 | N/A | N/A | N/A | N/A | N/A | N/A | Yes | Outage did not proceed due to change in dates by customer | Generator | No | N/A | Generator | Yes | Outage Cancelled | Generator | N/A | N/A | N/A | N/A | N/A | YES | Outage Cancelled | Generator
CLONKEEN COOMAGEARLAHY | CG1, CG2, CG3 | Yes | TO-24-CKN-CGL-1-02 | Apr | 2024-04-08 | 2024-04-26 | 19 | 2024-06-25 | 2024-07-08 | 2024-06-26 | 2024-07-08 | 2024-07-15 | 2024-07-16 | 2024-07-17 | 2024-07-18 | 2024-07-08 | 2024-07-26 | Yes | To align with capex works | TSO | Yes | Increased duration due to request by TAO | TAO | No | N/A | No Change | 2024-07-08 | 2024-07-09 | 2024-07-10 | 2024-07-11 | 2024-07-12 | Yes | To align with updated customer outage dates | Generator
COOLNANOONAGH KILPADDOGE | KZ4, KZ1, KZ3 | Yes | TO-24-CNO-KPG-1-02 | Unscheduled | - | - | 2 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
COOLNANOONAGH KILPADDOGE | KZ4, KZ1, KZ3 | Yes | TO-24-CNO-KPG-1-01 | Jun | - | - | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
COOMAGEARLAHY GLANLEE | GL1 | Yes | TO-24-CGL-GAE-1-02 |  |  |  | 19 | 2024-06-25 | 2024-07-08 | 2024-07-26 | 2024-07-08 | 2024-07-09 | 2024-07-10 | 2024-07-11 | 2024-07-12 | 2024-07-08 | 2024-07-26 | Yes | To align with capex works | TSO | No | N/A | No Change | No | N/A | No Change | 2024-07-08 | 2024-07-09 | 2024-07-10 | 2024-07-11 | 2024-07-12 | No | N/A | No Change
COOMAGEARLAHY T121 | CG3 | Yes | TO-24-CGL-T121-02 | Apr | 2024-04-08 | 2024-04-26 | 19 | 2024-06-25 | 2024-07-08 | 2024-06-26 | 2024-07-08 | 2024-07-16 | 2024-07-17 | 2024-07-18 | 2024-07-19 | 2024-07-08 | 2024-07-26 | Yes | To align with capex works | TSO | No | N/A | No Change | No | N/A | No Change | 2024-07-08 | 2024-07-09 | 2024-07-10 | 2024-07-11 | 2024-07-12 | Yes | To align with updated customer outage dates | Generator
COOMATAGGART 110SA1 | YT1 | Yes | TO-24-COT-110SA1-02 | Jul | - | - | 5 | 2024-06-13 | 2024-07-01 | 2024-07-09 | 2024-07-01 | 2024-07-02 | 2024-07-03 | 2024-07-04 | 2024-07-05 | 2024-07-01 | 2024-07-09 | No | N/A | No Change | Yes | Increased duration due to request by TAO | TAO | No | N/A | No Change | 2024-07-01 | 2024-07-02 | 2024-07-03 | 2024-07-04 | 2024-07-05 | No | N/A | No Change
COOMATAGGART 110SA2 | GD1, YT1 | Yes | TO-24-COT-110SA2-02 | Jul | - | - | 5 | 2024-06-13 | 2024-07-01 | 2024-07-09 | 2024-07-01 | 2024-07-02 | 2024-07-03 | 2024-07-04 | 2024-07-05 | 2024-07-01 | 2024-07-09 | No | N/A | No Change | Yes | Increased duration due to request by TAO | TAO | No | N/A | No Change | 2024-07-01 | 2024-07-02 | 2024-07-03 | 2024-07-04 | 2024-07-05 | No | N/A | No Change
COOMATAGGART T132 | GD1 | Yes | TO-24-COT-T132-01 | Jul | - | - | 5 | 2024-06-13 | 2024-07-01 | 2024-07-09 | 2024-07-01 | 2024-07-02 | 2024-07-03 | 2024-07-04 | 2024-07-05 | 2024-07-01 | 2024-07-09 | No | N/A | No Change | Yes | Increased duration due to request by TAO | TAO | No | N/A | No Change | 2024-07-01 | 2024-07-02 | 2024-07-03 | 2024-07-04 | 2024-07-05 | No | N/A | No Change
CORDAL T132 | DL1/DL2 | Yes | TO-24-CDL-T132-01 | May | - | - | 4 | 2024-04-04 | 2024-05-27 | 2024-05-30 | 2024-05-27 | 2024-05-28 | 2024-05-29 | 2024-05-30 | N/A | 2024-05-27 | 2024-05-30 | No | N/A | No Change | No | N/A | No Change | No | N/A | No Change | 2024-05-27 | 2024-05-28 | 2024-05-29 | 2024-05-30 | N/A | No | N/A | No Change
CORDERRY GARVAGH | GH1, GH2 | Yes | TO-24-CDY-GRV-1-02 | Unscheduled | - | - | 2 | 2024-06-20 | 2024-07-15 | 2024-07-23 | 2024-07-15 | 2024-07-16 | 2024-07-17 | 2024-07-18 | 2024-07-19 | 2024-07-15 | 2024-07-16 | No | N/A | No Change | No | N/A | No Change | No | N/A | No Change | 2024-07-15 | 2024-07-16 | N/A | N/A | N/A | No | N/A | No Change
CATHALEENS FALL CLIFF | ER1, ER2 | Yes | TO-24-CF-CL-1-02 | Apr | 2024-04-10 | 2024-04-11 | 2 | 2024-03-14 | 2024-04-10 | 2024-04-11 | 2024-04-10 | N/A | N/A | N/A | N/A | N/A | N/A | Yes | Outage did not proceed due to forced outage of generator | Generator | N/A | Outage did not proceed due to forced outage of generator | Generator | N/A | N/A | No Change | N/A | N/A | N/A | N/A | N/A | YES | Outage did not proceed due to forced outage of generator | Generator
CUNGHILL T121 | KGM, KG2 | Yes | TO-24-CUN-T121-01 | Jun | - | - | 5 | 2024-05-30 | 2024-06-17 | 2024-06-21 | 2024-06-17 | 2024-06-18 | 2024-06-19 | 2024-06-20 | 2024-06-21 | 2024-06-17 | 2024-06-21 | No | N/A | No Change | No | N/A | No Change | No | N/A | No Change | 2024-06-17 | 2024-06-18 | 2024-06-19 | 2024-06-20 | 2024-06-21 | No | N/A | No Change
CUSHALING KILCUMBER | OE1 | Yes | TO-24-CUS-KIR-1-01 | Jul | - | - | 2 | 2024-06-25 | 2024-06-24 | 2024-07-17 | 2024-06-24 | N/A | N/A | N/A | N/A | 2024-06-24 | 2024-07-17 | No | N/A | No Change | Yes | To align with capex works | TSO | No | N/A | No Change | 2024-06-24 | N/A | N/A | N/A | N/A | No | N/A | No Change
ROSSPILE T131 | R01 | Yes | TO-24-ROP-T131-01 | Nov | - | - | 2 | 2024-11-28 | 2024-12-09 | 2024-12-09 | 2024-12-09 | N/A | N/A | N/A | N/A | 2024-12-09 | 2024-12-09 | Yes | Aligned with generator outage change in dates | Generator | Yes | To align with generator outage | Generator | No | N/A | No Change | 2024-12-09 | N/A | N/A | N/A | N/A | No | N/A | No Change
CUSHALING T103/5 | ED3, ED5 | Yes | TO-24-CUS-T103/5-01 | Jul-Aug | - | - | 10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
DERRYCARNEY T132 | LU1, LU2 | Yes | TO-24-DEY-T132-01 | Jul | - | - | 2 | 2024-06-12 | 2024-07-22 | 2024-07-23 | 2024-07-22 | N/A | N/A | N/A | N/A | 2024-07-22 | 2024-07-23 | No | N/A | No Change | No | N/A | No Change | No | N/A | No Change | 2024-07-22 | 2024-07-23 | N/A | N/A | N/A | No | N/A | No Change
SEALROCK T103 | SK3 | Yes | TO-24-SK-T103-01 | Jun | - | - | 10 | 2024-06-10 | 2024-06-10 | 2024-06-14 | 2024-06-10 | 2024-06-11 | 2024-06-12 | 2024-06-13 | 2024-06-14 | 2024-06-10 | 2024-06-14 | No | N/A | No Change | Yes | To align with generator outage | Generator | No | N/A | No Change | 2024-06-10 | 2024-06-11 | 2024-06-12 | 2024-06-13 | 2024-06-14 | No | N/A | No Change
DERRYIRON RHODE T1/T2 | RP1, RP2 | Yes | TO-24-DER-T1/T2-04 | Mar-Apr | 2024-03-18 | 2024-04-10 | 24 | 2024-03-06 | 2024-03-19 | 2024-04-10 | 2024-03-20 | 2024-03-21 | 2024-03-22 | 2024-03-25 | 2024-03-26 | 2024-03-19 | 2024-04-16 | No | N/A | No Change | Yes | Increased duration due to request by TAO | TAO | No | N/A | No Change | 2024-03-20 | 2024-03-21 | 2024-03-22 | 2024-03-25 | 2024-03-26 | No | N/A | No Change
DRUMKEEN MEENTYCAT | MCT | Yes | TO-24-DRM-MEE-1-01 | Unscheduled | - | - | - | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ENNIS SLIEVECALLAN | KD1, RD1 | Yes | TO-24-ENN-SLC-1-02 | Jul | - | - | 3 | 2024-06-06 | 2024-07-03 | 2024-07-05 | 2024-07-03 | 2024-07-04 | 2024-07-05 | N/A | N/A | 2024-07-03 | 2024-07-05 | No | N/A | No Change | No | N/A | No Change | No | N/A | No Change | 2024-07-03 | 2024-07-04 | 2024-07-05 | N/A | N/A | No | N/A | No Change
FINGLAS HUNTSTOWN | HNC | Yes | TO-24-FIN-HN-1-01 | Apr-May | 2024-04-27 | 2024-05-08 | 12 | 2024-04-29 | 2024-04-27 | 2024-05-08 | 2024-04-29 | 2024-04-30 | 2024-05-01 | 2024-05-02 | 2024-05-03 | 2024-04-27 | 2024-05-08 | No | N/A | No Change | No | N/A | No Change | No | N/A | No Change | 2024-04-29 | 2024-04-30 | 2024-05-01 | 2024-05-02 | 2024-05-03 | No | N/A | No Change
GALLANSTOWN T133 | IA1 | Yes | TO-24-GLN-T133-03 | Feb-Mar | 2024-02-12 | 2024-03-06 | 24 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
GARROW 110SA1-2CB | CZ1 | Yes | TO-24-GRO-110SA1-2CB-01 | Jul | - | - | 5 | 2024-06-12 | 2024-07-15 | 2024-07-19 | 2024-07-15 | 2024-07-16 | 2024-07-17 | 2024-07-18 | 2024-07-19 | 2024-07-15 | 2024-07-19 | No | N/A | No Change | No | N/A | No Change | No | N/A | No Change | 2024-07-15 | 2024-07-16 | 2024-07-17 | 2024-07-18 | 2024-07-19 | No | N/A | No Change
GARROW T122 | CZ1 | Yes | TO-24-GRO-T122-01 | Jul | - | - | 5 | 2024-06-12 | 2024-07-15 | 2024-07-19 | 2024-07-15 | 2024-07-16 | 2024-07-17 | 2024-07-18 | 2024-07-19 | 2024-07-15 | 2024-07-19 | No | N/A | No Change | No | N/A | No Change | No | N/A | No Change | 2024-07-15 | 2024-07-16 | 2024-07-17 | 2024-07-18 | 2024-07-19 | No | N/A | No Change
GARVAGH T121 | GH1, GH2 | Yes | TO-24-GRV-T121-01 | Jul | - | - | 9 | 2024-06-20 | 2024-07-15 | 2024-07-23 | 2024-07-15 | 2024-07-16 | 2024-07-17 | 2024-07-18 | 2024-07-19 | 2024-07-15 | 2024-07-23 | No | N/A | No Change | No | N/A | No Change | No | N/A | No Change | 2024-07-15 | 2024-07-16 | 2024-07-17 | 2024-07-18 | 2024-07-19 | No | N/A | No Change
SEALROCK T104 | SK4 | Yes | TO-24-SK-T104-01 | Jul-Sep | - | - | 44 | 2024-06-25 | 2024-07-08 | 2024-09-02 | 2024-07-08 | 2024-07-09 | 2024-07-10 | 2024-07-11 | 2024-07-12 | 2024-07-08 | 2024-09-11 | No | N/A | No Change | Yes | To align with generator outage | Generator | Yes | To align with generator outage | Generator | 2024-07-08 | 2024-07-09 | 2024-07-10 | 2024-07-11 | 2024-07-12 | No | N/A | No Change
GLENLARA KNOCKACUMMER | KC1 | Yes | TO-24-GLE-KCR-1-01 | Jun | - | - | 4 | 2024-05-14 | 2024-06-04 | 2024-06-06 | 2024-06-04 | 2024-06-05 | 2024-06-06 | 2024-06-07 | N/A | 2024-06-05 | 2024-06-07 | No | N/A | No Change | No | N/A | No Change | Yes | Reduced maintenance duration required | TAO | 2024-06-05 | 2024-06-06 | 2024-06-07 | N/A | N/A | Yes | Reduced maintenance duration required | TAO
SLIABH BAWN T132 | SB1 | Yes | TO-24-SLB-T132-02 | Unscheduled | - | - | 2 | 2024-05-15 | 2024-06-12 | 2024-06-14 | 2024-06-12 | 2024-06-13 | N/A | N/A | N/A | 2024-06-12 | 2024-06-14 | Yes | Aligned with generator outage change in dates | Generator | Yes | To align with customer request | Generator | No | N/A | No Change | 2024-06-12 | 2024-06-13 | N/A | N/A | N/A | No | N/A | No Change
MONEYPOINT GIS T4003 | MP3 | Yes | TO-24-MP GIS-T4003-02 | Sep | - | - | 2 |  | 2024-09-05 | 2024-11-14 | 2024-09-05 | N/A | N/A | N/A | N/A | 2024-09-05 | 2024-12-04 | No | N/A | No Change | Yes | To align with customer request | Generator | Yes | To align with generator outage | Generator | 2024-09-05 | N/A | N/A | N/A | N/A | No | N/A | No Change
UGGOOL T131 | UG1 | Yes | TO-24-UGL-T131-01 | Jul | - | - | 2 | 2024-08-08 | 2024-08-19 | 2024-08-23 | 2024-08-19 | 2024-08-20 | 2024-08-21 | 2024-08-22 | 2024-08-23 | 2024-08-19 | 2024-08-23 | Yes | Aligned with generator outage change in dates | Generator | Yes | To align with customer request | Generator | No | N/A | No Change | 2024-08-19 | 2024-08-20 | 2024-08-21 | 2024-08-22 | 2024-08-23 | No | N/A | No Change
UGGOOL T132 | UG1 | Yes | TO-24-UGL-T132-02 | Jul | - | - | 2 | 2024-08-08 | 2024-08-19 | 2024-08-23 | 2024-08-19 | 2024-08-20 | 2024-08-21 | 2024-08-22 | 2024-08-23 | 2024-08-19 | 2024-08-23 | Yes | Aligned with generator outage change in dates | Generator | Yes | To align with customer request | Generator | No | N/A | No Change | 2024-08-19 | 2024-08-20 | 2024-08-21 | 2024-08-22 | 2024-08-23 | No | N/A | No Change
IKERRIN tee SHANNONBRIDGE |  | Yes | TO-24-IKE,T-SH-1-05 | Sep | - | - | 7 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
IKERRIN tee THURLES |  | Yes | TO-24-IKE,T-THU-1-05 | Sep | - | - | 7 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
UGGOOL T134 | UG1 | Yes | TO-24-UGL-T134-01 | Jul | - | - | 2 | 2024-08-08 | 2024-08-19 | 2024-08-23 | 2024-08-19 | 2024-08-20 | 2024-08-21 | 2024-08-22 | 2024-08-23 | 2024-08-19 | 2024-08-23 | Yes | Aligned with generator outage change in dates | Generator | Yes | To align with customer request | Generator | No | N/A | No Change | 2024-08-19 | 2024-08-20 | 2024-08-21 | 2024-08-22 | 2024-08-23 | No | N/A | No Change
WOODHOUSE T122 | WS1 | Yes | TO-24-WOH-T122-01 | May | - | - | 4 | 2024-04-25 | 2024-05-09 | 2024-05-10 | 2024-05-09 | N/A | N/A | N/A | N/A | 2024-05-08 | 2024-05-10 | No | N/A | No Change | Yes | To align with customer request | Generator | Yes | To align with customer request | Generator | 2024-05-09 | N/A | N/A | N/A | N/A | No | N/A | No Change
KILCUMBER T131 | OE1 | Yes | TO-24-KIR-T131-01 | Jul | - | - | 2 | 2024-06-25 | 2024-06-24 | 2024-07-17 | 2024-06-24 | N/A | N/A | N/A | N/A | 2024-06-24 | 2024-07-12 | Yes | To align with capex works | TSO | Yes | Overall outage duration increase due to capex, maintenance duration remained at 1 day | TSO | Yes | Reduced maintenance duration required | TAO | 2024-06-24 | N/A | N/A | N/A | N/A | No | N/A | No Change
KILL HILL T131 | KH1 | Yes | TO-24-KHL-T131-01 | Jul | - | - | 1 | 2024-06-12 | 2024-07-16 | 2024-07-16 | 2024-07-16 | N/A | N/A | N/A | N/A | 2024-07-16 | 2024-07-16 | No | N/A | No Change | No | N/A | No Change | No | N/A | No Change | 2024-07-16 | N/A | N/A | N/A | N/A | No | N/A | No Change
KILTEEL T131 | PN1 | Yes | TO-24-KTL-T131-01 | May | - | - | 1 | 2024-04-04 | 2024-05-07 | 2024-05-07 | 2024-05-07 | N/A | N/A | N/A | N/A | 2024-05-07 | 2024-05-07 | No | N/A | No Change | No | N/A | No Change | No | N/A | No Change | 2024-05-07 | N/A | N/A | N/A | N/A | No | N/A | No Change
KNOCKALOUGH KNOCKRANNY | KU1 | Yes | TO-24-KLH-KNY-1-01 | Jul | - | - | 3 | 2024-06-12 | 2024-07-02 | 2024-07-04 | 2024-07-02 | 2024-07-03 | 2024-07-04 | N/A | N/A | N/A | N/A | Yes | Due to TAO resourcing outage did not proceed | TAO | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KNOCKRANNY UGGOOL | SO1, UG1 | Yes | TO-24-KNY-UGL-1-01 | Jul | - | - | 2 | 2024-06-12 | 2024-07-02 | 2024-07-04 | 2024-07-02 | 2024-07-03 | 2024-07-04 | N/A | N/A | N/A | N/A | Yes | Due to TAO resourcing outage did not proceed | TAO | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
LISDRUM T131 | LF1 | Yes | TO-24-LIS-T131-01 | May | - | - | 1 | 2024-04-04 | 2024-05-08 | 2024-05-08 | 2024-05-08 | N/A | N/A | N/A | N/A | N/A | N/A | Yes | Outage did not proceed due to TAO resources unavailable | TAO | Yes | Outage did not proceed due to TAO resources unavailable | TAO | Yes | Outage did not proceed due to TAO resources unavailable | TAO | N/A | N/A | N/A | N/A | N/A | Yes | Due to TAO resourcing | TAO
LISHEEN T122 | LS1, LS2 | Yes | TO-24-LSN-T122-03 | Aug | - | - | 11 | 2024-07-18 | 2024-08-06 | 2024-08-16 | 2024-08-06 | 2024-08-07 | 2024-08-08 | 2024-08-12 | 2024-08-13 | 2024-08-06 | 2024-08-16 | No | N/A | No Change | No | N/A | No Change | No | N/A | No Change | 2024-08-06 | 2024-08-07 | 2024-08-08 | 2024-08-12 | 2024-08-13 | No | N/A | No Change
LISHEEN THURLES | LS1, LS2, LS3 | Yes | TO-24-LSN-THU-1-03 | Aug | - | - | 11 | 2024-07-18 | 2024-08-06 | 2024-08-16 | 2024-08-06 | 2024-08-07 | 2024-08-08 | 2024-08-12 | 2024-08-13 | 2024-08-06 | 2024-08-16 | No | N/A | No Change | No | N/A | No Change | No | N/A | No Change | 2024-08-06 | 2024-08-07 | 2024-08-08 | 2024-08-12 | 2024-08-13 | No | N/A | No Change
TAWNAGHMORE T1/T2 | TP1 | Yes | TO-24-TAW-T1/T2-01 | Jul | - | - | 3 | 2024-07-04 | 2024-07-08 | 2024-07-19 | 2024-07-08 | 2024-07-09 | 2024-07-10 | N/A | N/A | 2024-07-08 | 2024-07-19 | No | N/A | No Change | Yes | To align with generator switch in/out dates | Generator | No | N/A | No Change | 2024-07-08 | 2024-07-09 | 2024-07-10 | N/A | N/A | No | N/A | No Change
ARDNACRUSHA GIS T101 | AA1 | Yes | TO-24-AA GIS-T101-02 | Apr | 2024-04-15 | 2024-04-18 | 4 | 2024-05-13 | 2024-05-01 | 2024-09-13 | 2024-05-01 | 2024-05-02 | 2024-05-03 | 2024-05-04 | N/A | 2024-05-01 | 2024-11-06 | Yes | Aligned with generator outage change in dates | Generator | Yes | To align with generator outage | Generator | Yes | To align with generator outage | Generator | 2024-05-01 | 2024-05-02 | 2024-05-03 | 2024-05-04 | N/A | No | N/A | No Change
ARDNACRUSHA GIS T102 | AA2 | Yes | TO-24-AA GIS-T102-01 | Jun | - | - | 3 | 2024-05-20 | 2024-06-10 | 2024-05-19 | 2024-06-12 | 2024-06-13 | 2024-06-14 | N/A | N/A | 2024-06-10 | 2024-06-13 | No | N/A | No Change | Yes | To align with generator outage | Generator | Yes | To align with generator outage | Generator | 2024-06-12 | 2024-06-13 | N/A | N/A | N/A | Yes | Reduced maintenance duration required | TAO
MONEYPOINT GIS T4002 | MP2 | Yes | TO-24-MP GIS-T4002-02 | May | - | - | 5 | 2024-05-23 | 2024-05-27 | 2024-05-31 | 2024-05-27 | 2024-05-28 | 2024-05-29 | 2024-05-30 | 2024-05-31 | 2024-05-28 | 2024-05-31 | No | N/A | No Change | No | N/A | No Change | No | N/A | No Change | 2024-05-27 | 2024-05-28 | 2024-05-29 | 2024-05-30 | 2024-05-31 | No | N/A | No Change
ARDNACRUSHA GIS T104 | AA4 | Yes | TO-24-AA GIS-T104-01 | May | - | - | 3 | 2024-05-22 | 2024-05-09 | 2024-05-22 | 2024-05-09 | 2024-05-10 | 2024-05-13 | N/A | N/A | 2024-05-09 | 2024-05-22 | No | N/A | No Change | Yes | To align with generator outage | Generator | No | N/A | No Change | 2024-05-09 | 2024-05-10 | 2024-05-13 | N/A | N/A | No | N/A | No Change
MOUNTLUCAS T121 | M01 | Yes | TO-24-MLC-T121-02 | Unscheduled | - | - | 2 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MOUNTLUCAS T121 | M01 | Yes | TO-24-MLC-T121-01 | May | - | - | 2 |  | 2024-05-29 | 2024-05-29 | 2024-05-29 | N/A | N/A | N/A | N/A | 2024-05-29 | 2024-05-29 | No | N/A | No Change | Yes | Change in maintenance requirements | TAO | No | N/A | No Change | 2024-05-29 | N/A | N/A | N/A | N/A | No | N/A | No Change
POLLAPHUCA T101 | LI1, LI2, LI4 | Yes | TO-24-PA-T101-04 | May-Jun | - | - | 19 | 2024-05-30 | 2024-06-04 | 2024-06-11 | 2024-06-04 | 2024-06-05 | 2024-06-06 | 2024-06-07 | 2024-06-10 | 2024-06-04 | 2024-06-14 | No | N/A | No Change | Yes | Change in maintenance requirements | TAO | Yes | To align with generator outage | Generator | 2024-06-04 | 2024-06-05 | 2024-06-06 | 2024-06-07 | 2024-06-10 | No | N/A | No Change
RATRUSSAN T121 | BD1 | Yes | TO-24-RRU-T121-05 | Apr-May | 2024-04-24 | 2024-05-22 | 29 | 2024-04-11 | 2024-04-24 | 2024-05-22 | 2024-04-24 | 2024-04-25 | 2024-04-26 | 2024-04-29 | 2024-04-30 | 2024-04-24 | 2024-05-30 | No | N/A | No Change | Yes | Increased duration due to request by TAO | TAO | Yes | To align with generator outage | TAO | 2024-04-24 | 2024-04-25 | 2024-04-26 | 2024-04-29 | 2024-04-30 | No | N/A | No Change
RATRUSSAN T122 | ML1 | Yes | TO-24-RRU-T122-05 | Apr-May | 2024-04-24 | 2024-05-22 | 29 | 2024-04-11 | 2024-04-24 | 2024-05-22 | 2024-04-24 | 2024-05-17 | 2024-05-20 | 2024-05-21 | 2024-05-22 | 2024-04-24 | 2024-05-30 | No | N/A | No Change | Yes | Increased duration due to request by TAO | TAO | Yes | To align with generator outage | TAO | 2024-04-24 | 2024-05-17 | 2024-05-20 | 2024-05-21 | 2024-05-22 | No | N/A | No Change
REAMORE TRALEE | KM1 | Yes | TO-24-REM-TRL-1-01 | Aug | - | - | 8 | 2024-08-01 | 2024-08-07 | 2024-08-28 | 2024-08-07 | 2024-08-08 | 2024-08-09 | 2024-08-12 | 2024-08-13 | 2024-08-07 | 2024-08-29 | No | N/A | No Change | Yes | Increased duration due to request by TAO | TAO | Yes | To align with generator outage | Generator | 2024-08-07 | 2024-08-08 | 2024-08-09 | 2024-08-12 | 2024-08-13 | No | N/A | No Change
AUGHINISH SEALROCK 3 | SK3 | Yes | TO-24-AUG-SK-3-01 | Jun | - | - | 10 | 2024-06-10 | 2024-06-10 | 2024-06-14 | 2024-06-10 | 2024-06-11 | 2024-06-12 | 2024-06-13 | 2024-06-14 | 2024-06-10 | 2024-06-14 | No | N/A | No Change | Yes | To align with generator outage | Generator | No | N/A | No Change | 2024-06-10 | 2024-06-11 | 2024-06-12 | 2024-06-13 | 2024-06-14 | No | N/A | No Change
SHELLYBANKS T2015 | PB15 | Yes | TO-24-SHL-T2015-01 | Sep | - | - | 5 | 2024-08-08 | 2024-09-01 | 2024-09-27 | 2024-09-23 | 2024-09-24 | 2024-09-25 | 2024-09-26 | 2024-09-27 | 2024-09-01 | 2024-09-27 | No | N/A | No Change | Yes | To align with generator outage | Generator | No | N/A | No Change | 2024-09-23 | 2024-09-24 | 2024-09-25 | 2024-09-26 | 2024-09-27 | No | N/A | No Change
SHELLYBANKS T2016 | PB16 | Yes | TO-24-SHL-T2016-01 | Oct | - | - | 5 | 2024-09-06 | 2024-09-10 | 2024-10-18 | 2024-10-14 | 2024-10-15 | 2024-10-16 | 2024-10-17 | 2024-10-18 | 2024-10-02 | 2024-10-31 | No | N/A | No Change | Yes | To align with generator outage | Generator | Yes | To align with generator outage | Generator | 2024-10-23 | 2024-10-24 | 2024-10-25 | N/A | N/A | Yes | To align with updated customer outage dates | Generator
SHELLYBANKS T2014 | PB14 | Yes | TO-24-SHL-T2014-01 | Unscheduled | - | - | - | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CLIFF T101 | ER1 | Yes | TO-24-CL-T101-03 | Unscheduled |  |  | 2 | 2024-03-21 | 2024-04-08 | 2024-04-12 | 2024-04-10 | 2024-04-11 | N/A | N/A | N/A | 2024-04-08 | 2024-04-12 | Yes | Aligned with generator outage change in dates | Generator | Yes | To align with generator switch in/out dates | Generator | No | N/A | No Change | 2024-04-10 | 2024-04-11 | N/A | N/A | N/A | No | N/A | No Change
CLIFF T102 | ER2 | Yes | TO-24-CL-T102-03 | May | - | - | 5 | 2024-05-02 | 2024-05-13 | 2024-05-23 | 2024-05-13 | 2024-05-14 | 2024-05-15 | 2024-05-16 | 2024-05-17 | 2024-05-13 | 2024-05-23 | No | N/A | No Change | Yes | To align with generator switch in/out dates | Generator | No | N/A | No Change | 2024-05-13 | 2024-05-14 | 2024-05-15 | 2024-05-16 | 2024-05-17 | No | N/A | No Change
CLONIFFEEN SHANNONBRIDGE | SI1, SI2 | Yes | TO-24-CFN-SH-1-01 | Jul | - | - | 1 | 2024-06-12 | 2024-07-08 | 2024-07-09 | 2024-07-08 | N/A | N/A | N/A | N/A | 2024-07-08 | 2024-07-09 | No | N/A | No Change | Yes | To align with generator switch in/out dates | Generator | No | N/A | No Change | 2024-07-08 | N/A | N/A | N/A | N/A | No | N/A | No Change
SLIEVECALLAN T121 | KD1 | Yes | TO-24-SLC-T121-02 | Jul | - | - | 3 | 2024-06-06 | 2024-07-03 | 2024-07-05 | 2024-07-03 | 2024-07-04 | 2024-07-05 | N/A | N/A | 2024-07-03 | 2024-07-05 | No | N/A | No Change | No | N/A | No Change | No | N/A | No Change | 2024-07-03 | 2024-07-04 | 2024-07-05 | N/A | N/A | No | N/A | No Change
SLIEVECALLAN T122 | RD1 | Yes | TO-24-SLC-T122-02 | Jul | - | - | 3 | 2024-06-06 | 2024-07-03 | 2024-07-05 | 2024-07-03 | 2024-07-04 | 2024-07-05 | N/A | N/A | 2024-07-03 | 2024-07-05 | No | N/A | No Change | No | N/A | No Change | No | N/A | No Change | 2024-07-03 | 2024-07-04 | 2024-07-05 | N/A | N/A | No | N/A | No Change
CORDUFF HUNTSTOWN | HN2 | Yes | TO-24-CDU-HN-1-01 | Oct | - | - | 5 | 2024-10-17 | 2024-10-05 | 2024-10-23 | 2024-10-07 | 2024-10-08 | 2024-10-09 | 2024-10-10 | 2024-10-11 | 2024-10-05 | 2024-10-23 | No | N/A | No Change | Yes | To align with generator switch in/out dates | Generator | No | N/A | No Change | 2024-10-07 | 2024-10-08 | 2024-10-09 | 2024-10-10 | 2024-10-11 | No | N/A | No Change
GLANAGOW T2001 | WG1 | Yes | TO-24-GGO-T2001-01 | Sep | - | - | 2 | 2024-08-02 | 2024-09-02 | 2024-09-17 | 2024-09-09 | 2024-09-10 | N/A | N/A | N/A | 2024-09-09 | 2024-09-17 | No | N/A | No Change | Yes | To align with generator switch in/out dates | Generator | No | N/A | No Change | 2024-09-09 | 2024-09-10 | N/A | N/A | N/A | No | N/A | No Change
GREAT ISLAND GIS T2004 | GI4 | Yes | TO-24-GI GIS-T2004-02 | May | - | - | 9 | 2024-05-15 | 2024-05-21 | 2024-05-31 | 2024-05-21 | N/A | N/A | N/A | N/A | 2024-05-21 | 2024-05-31 | No | N/A | No Change | Yes | To align with generator switch in/out dates | Generator | No | N/A | No Change | 2024-05-21 | N/A | N/A | N/A | N/A | No | N/A | No Change
STRATFORD tee CARLOW | LI1, LI2, LI4 | Yes | TO-24-STR,T-CLW-1-04 | May-Jun | - | - | 19 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
STRATFORD tee POLLAPHUCA | LI1, LI2, LI4 | Yes | TO-24-STR,T-PA-1-04 | May-Jun | - | - | 19 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
HUNTSTOWN T2002 | HN2 | Yes | TO-24-HN-T2002-01 | Oct | - | - | 5 | 2024-10-17 | 2024-10-05 | 2024-10-23 | 2024-10-07 | 2024-10-08 | 2024-10-09 | 2024-10-10 | 2024-10-11 | 2024-10-05 | 2024-10-23 | No | N/A | No Change | Yes | To align with generator switch in/out dates | Generator | No | N/A | No Change | 2024-10-07 | 2024-10-08 | 2024-10-09 | 2024-10-10 | 2024-10-11 | No | N/A | No Change
HUNTSTOWN T2010/11 | HNC | Yes | TO-24-HN-T2010/11-02 | May | - | - | 2 | 2024-04-29 | 2024-04-27 | 2024-05-08 | 2024-04-29 | 2024-04-30 | 2024-05-01 | 2024-05-02 | 2024-05-03 | 2024-04-27 | 2024-05-08 | No | N/A | No Change | Yes | To align with generator switch in/out dates | Generator | No | N/A | No Change | 2024-04-29 | 2024-04-30 | 2024-05-01 | 2024-05-02 | 2024-05-03 | No | N/A | No Change
TULLABRACK tee BOOLTIAGH | BT1, BT2 | Yes | TO-24-TBK,T-BOL-1-01 | Aug | - | - | 12 | 2024-08-08 | 2024-08-19 | 2024-08-30 | 2024-08-19 | 2024-08-20 | 2024-08-21 | 2024-08-22 | 2024-08-23 | 2024-08-19 | 2024-08-30 | No | N/A | No Change | No | N/A | No Change | No | N/A | No Change | 2024-08-19 | 2024-08-20 | 2024-08-21 | 2024-08-28 | 2024-08-29 | Yes | To align with updated customer outage dates | Generator
TULLABRACK tee MONEYPOINT GIS | BT1, BT2 | Yes | TO-24-TBK,T-MP GIS-1-01 | Aug | - | - | 12 | 2024-08-08 | 2024-08-19 | 2024-08-30 | 2024-08-19 | 2024-08-20 | 2024-08-21 | 2024-08-22 | 2024-08-23 | 2024-08-19 | 2024-08-30 | No | N/A | No Change | No | N/A | No Change | No | N/A | No Change | 2024-08-19 | 2024-08-20 | 2024-08-21 | 2024-08-28 | 2024-08-29 | Yes | To align with updated customer outage dates | Generator
TURLOUGH HILL T2001/2 | TH1, TH2 | Yes | TO-24-TH-T2001/2-02 | Mar | 2024-03-10 | 2024-03-13 | 4 | 2024-02-06 | 2024-03-10 | 2024-03-13 | 2024-03-11 | 2024-03-12 | N/A | N/A | N/A | 2024-03-10 | 2024-03-13 | No | N/A | No Change | No | N/A | No Change | No | N/A | No Change | 2024-03-11 | 2024-03-12 | N/A | N/A | N/A | No | N/A | No Change
TURLOUGH HILL T2003/4 | TH3, TH4 | Yes | TO-24-TH-T2003/4-02 | Mar | 2024-03-03 | 2024-03-06 | 4 | 2024-02-06 | 2024-03-03 | 2024-03-06 | 2024-03-03 | 2024-03-04 | 2024-03-05 | 2024-03-06 | N/A | 2024-03-03 | 2024-03-06 | No | N/A | No Change | No | N/A | No Change | No | N/A | No Change | 2024-03-03 | 2024-03-04 | 2024-03-05 | 2024-03-06 | N/A | No | N/A | No Change
INNISCARRA T101 | LE1, LE2 | Yes | TO-24-IA-T101-02 | May | - | - | 1 | 2024-05-03 | 2024-05-14 | 2024-05-23 | 2024-05-14 | N/A | N/A | N/A | N/A | 2024-05-14 | 2024-05-23 | No | N/A | No Change | Yes | To align with generator switch in/out dates | Generator | No | N/A | No Change | 2024-05-14 | N/A | N/A | N/A | N/A | No | N/A | No Change
UGGOOL 110SA1-2CB | SO1 | Yes | TO-24-UGL-110SA1-2CB-01 | Jul | - | - | 2 | 2024-08-08 | 2024-08-19 | 2024-08-20 | 2024-08-19 | 2024-08-20 | 2024-08-21 | 2024-08-22 | 2024-08-23 | N/A | N/A | Yes | Outage did not proceed due to TAO resources unavailable | TAO | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Yes | Due to TAO resourcing | TAO
IRISHTOWN T2001 | DB1 | Yes | TO-24-ISH-T2001-01 | Aug | - | - | 1 | 2024-08-01 | 2024-08-11 | 2024-08-30 | 2024-08-11 | N/A | N/A | N/A | N/A | 2024-08-11 | 2024-08-29 | No | N/A | No Change | Yes | To align with generator switch in/out dates | Generator | Yes | To align with generator outage | Generator | 2024-08-11 | N/A | N/A | N/A | N/A | No | N/A | No Change
MONEYPOINT GIS T4001 | MP1 | Yes | TO-24-MP GIS-T4001-01 | May | - | - | 7 | 2024-05-21 | 2024-05-20 | 2024-05-31 | 2024-05-20 | 2024-05-21 | 2024-05-22 | 2024-05-23 | 2024-05-24 | 2024-05-21 | 2024-05-31 | No | N/A | No Change | Yes | To align with generator switch in/out dates | Generator | No | N/A | No Change | 2024-05-20 | 2024-05-21 | 2024-05-22 | 2024-05-23 | 2024-05-24 | No | N/A | No Change
TAWNAGHMORE T3 | TP3 | Yes | TO-24-TAW-T3-01 | Jul | - | - | 1 | 2024-07-04 | 2024-07-08 | 2024-07-19 | 2024-07-08 | 2024-07-09 | 2024-07-10 | N/A | N/A | 2024-07-08 | 2024-07-19 | No | N/A | No Change | Yes | To align with generator switch in/out dates | Generator | No | N/A | No Change | 2024-07-08 | 2024-07-09 | 2024-07-10 | N/A | N/A | No | N/A | No Change
TYNAGH T2001/2 | TYC | Yes | TO-24-TY-T2001/2-02 | Jun | - | - | 1 |  | 2024-06-23 | 2024-06-29 | 2024-06-23 | N/A | N/A | N/A | N/A | 2024-06-23 | 2024-06-29 | No | N/A | No Change | Yes | To align with generator switch in/out dates | Generator | No | N/A | No Change | 2024-06-23 | N/A | N/A | N/A | N/A | No | N/A | No Change
CLOGHBOOLA TRIEN | CL1 | No | N/A | N/A | N/A | N/A | N/A | 2024-02-01 | 2024-02-13 | 2024-02-14 | 2024-02-13 | 2024-02-14 | N/A | N/A | N/A | 2024-03-20 | 2024-03-21 | N/A | N/A | N/A | N/A | N/A | N/A | Yes | Operator unavailable | TAO | 2024-03-20 | 2024-03-21 | N/A | N/A | N/A | Yes | Due to TAO resourcing | TAO

## OACA Work Item Tracker
|  |  |  | Communicated in Ex-Ante Report |  | 7. Works not completed - To be provided by ESBN in Completions Report |  |  | 5. Works Description Communicated Ex-Ante
General
OACA | Unit(s) | Work Item Description | Work ID | Included in Ex-Ante Report? | TOP ID in the Ex-Ante Report | Works completed? | Reason for not completing, if applicable | Responsible | Change to Works Description Communicated Ex-Ante | Reason for Works Exclusion/Addition | Driver of Change to Works Description communicated Ex-Ante
AGHADA LONG POINT | AD2 | P3 Protection maintenance of 7SA612,GRL100 |  | Yes | TO-24-AD-LPT-1-02 | Yes | N/A | No Change | No | N/A | No Change
AGHADA LONG POINT | AD2 | 220kV SF6 Cubicle Operational Test | 901396997 | Yes | TO-24-AD-LPT-1-02 | Yes | N/A | No Change | No | N/A | No Change
AGHADA LONG POINT | AD2 | Cable Insp. 400 & 220kV Feeder XLPE | 901413560 | Yes | TO-24-AD-LPT-1-02 | Yes | N/A | No Change | No | N/A | No Change
AGHADA LONG POINT | AD2 | P3 Protection maintenance of 7SA612,GRL100 |  | Yes | TO-24-AD-LPT-1-02 | Yes | N/A | No Change | No | N/A | No Change
AGHADA LONG POINT | AD2 | Repeat Oil Sampling | 901240106 | Yes | TO-24-AD-LPT-1-02 | Yes | N/A | No Change | No | N/A | No Change
AGHADA LONG POINT | AD2 | O1-DE Earth Straps Birdcaging. | 901433727 | Yes | TO-24-AD-LPT-1-02 | Yes | N/A | No Change | No | N/A | No Change
AGHADA ST101 | AD3 | 110kV SF6 Cubicle Ordinary Service (excludes busbar disconnects) | 901396366 | Yes | TO-24-AD-ST101-01 | Yes | N/A | No Change | No | N/A | No Change
AGHADA ST101 | AD3 | O1-MO for Ordinary Service ST101 Cubicle | 901348642 | Yes | TO-24-AD-ST101-01 | Yes | N/A | No Change | No | N/A | No Change
AGHADA ST101 | AD3 | 110KV Cubicle Condition Assessment (excludes busbar disconnects) | 901396292 | Yes | TO-24-AD-ST101-01 | Yes | N/A | No Change | No | N/A | No Change
AGHADA T2011/12 | AT11/AT12 | P3 Protection maintenance of BOC (M1),RET630,7SA612,RET670,RET630 |  | Yes | TO-24-AD-T2011/12-02 | N/A | N/A | N/A | Yes | Not due in 2024 | TSO
AGHADA T2011/12 | AT11/AT12 | 220kV SF6 Cubicle Ordinary Service | ESBN TO CONFIRM | Yes | TO-24-AD-T2011/12-02 | No | TAO resourcing | TAO | No | N/A | No Change
AGHADA T2011/12 | AT11/AT12 | Annual Insp. 400 & 220 Station OF Cable | ESBN TO CONFIRM | Yes | TO-24-AD-T2011/12-02 | Yes | N/A | No Change | No | N/A | No Change
AGHADA T2011/12 | AT11/AT12 | 2021PM_Monitor oil pressure levels withi | 901247447 | Yes | TO-24-AD-T2011/12-02 | No | TAO resourcing | TAO | No | N/A | No Change
AGHADA T2011/12 | AT11/AT12 | 2022PM_Replacement of corroded earthing | 901302176 | Yes | TO-24-AD-T2011/12-02 | No | Conflicts with higher priority work | TSO | No | N/A | No Change
AGHADA T2011/12 | AT11/AT12 | 2022PM_Replacement of corroded bolts on | 901302177 | Yes | TO-24-AD-T2011/12-02 | No | Conflicts with higher priority work | TSO | No | N/A | No Change
AGHADA T2011/12 | AT11/AT12 | 2022PM_Replace Low Pressure & Differenti | 901302178 | Yes | TO-24-AD-T2011/12-02 | No | TAO resourcing | TAO | No | N/A | No Change
AGHADA T2014 | AT14 | 2021PM_Replace S-Phase differential rela | 901246243 | Yes | TO-24-AD-T2014-02 | No | Not scheduled to avoid constraining generator during tight margins | TSO | No | N/A | No Change
AGHADA T2014 | AT14 | Annual Insp. 400 & 220 Station OF Cable | ESBN TO CONFIRM | Yes | TO-24-AD-T2014-02 | Yes | N/A | No Change | No | N/A | No Change
AGHADA T2014 | AT14 | 220kV SF6 Cubicle Operational Test | ESBN TO CONFIRM | Yes | TO-24-AD-T2014-02 | Yes | N/A | No Change | No | N/A | No Change
AGHADA T2014 | AT14 | P3 Protection maintenance of BOC (M1),RET630,7SA612,RET650,RATUA |  | Yes | TO-24-AD-T2014-02 | No | Conflicts with higher priority work | TSO | No | N/A | No Change
AGHADA T2014 | AT14 | O1-Corrosion on CB Mech Box. | 901344954 | Yes | TO-24-AD-T2014-02 | Yes | N/A | No Change | No | N/A | No Change
ARDNACRUSHA GIS T101 | AA1 | P2 Protection maintenance of 7SA612,BOC(M1),7UT513 |  | Yes | TO-24-AA GIS-T101-02 | N/A | N/A | N/A | Yes | Not due in 2024 | TSO
ARDNACRUSHA GIS T101 | AA1 | Cable Insp. 110kV XLPE | ESBN TO CONFIRM | Yes | TO-24-AA GIS-T101-02 | Yes | N/A | No Change | No | N/A | No Change
ARDNACRUSHA GIS T102 | AA2 | P3 Protection maintenance of 7SA612,7UT513 |  | Yes | TO-24-AA GIS-T102-01 | N/A | N/A | N/A | Yes | Not due in 2024 | TSO
ARDNACRUSHA GIS T102 | AA2 | Cable Insp. 110kV XLPE | ESBN TO CONFIRM | Yes | TO-24-AA GIS-T102-01 | Yes | N/A | No Change | No | N/A | No Change
ARDNACRUSHA GIS T103 | AA3 | 110KV GIS Cubicle Operational Test | ESBN TO CONFIRM | Yes | TO-24-AA GIS-T103-01 | No | TAO resourcing | TAO | No | N/A | No Change
ARDNACRUSHA GIS T103 | AA3 | Cable Insp. 110kV XLPE | ESBN TO CONFIRM | Yes | TO-24-AA GIS-T103-01 | Yes | N/A | No Change | No | N/A | No Change
ARDNACRUSHA GIS T103 | AA3 | P3 Protection maintenance of 7SA612,7UT513 |  | Yes | TO-24-AA GIS-T103-01 | N/A | N/A | N/A | Yes | Not due in 2024 | TSO
ARDNACRUSHA GIS T104 | AA4 | Cable Insp. 110kV XLPE | ESBN TO CONFIRM | Yes | TO-24-AA GIS-T104-01 | Yes | N/A | No Change | No | N/A | No Change
ARDNACRUSHA GIS T104 | AA4 | P2 Protection maintenance of 7SA612,BOC(M1),7UT513 |  | Yes | TO-24-AA GIS-T104-01 | N/A | N/A | N/A | Yes | Not due in 2024 | TSO
ATHEA DROMADA | DR1 | 110kV SF6 Cubicle Operational Test | ESBN TO CONFIRM | Yes | TO-24-ATE-DRO-1-01 | Yes | N/A | No Change | No | N/A | No Change
ATHEA KNOCKANURE | AH1, XT1, XT2, DR1 | Cable Insp. 110kV XLPE | ESBN TO CONFIRM | Yes | TO-24-ATE-KNR-1-01 | Yes | N/A | No Change | No | N/A | No Change
ATHEA KNOCKANURE | AH1, XT1, XT2, DR1 | 2022HP-1[31]Bird Nests | 901370202 | Yes | TO-24-ATE-KNR-1-01 | Yes | N/A | No Change | No | N/A | No Change
ATHEA KNOCKANURE | AH1, XT1, XT2, DR1 | 2023CM_Install bridging SVL's at GIS ter | 901423890 | Yes | TO-24-ATE-KNR-1-01 | No | TAO resourcing | TAO | No | N/A | No Change
ATHEA KNOCKANURE | AH1, XT1, XT2, DR1 | 110kV SF6 Cubicle Operational Test | ESBN TO CONFIRM | Yes | TO-24-ATE-KNR-1-01 | Yes | N/A | No Change | No | N/A | No Change
ATHEA KNOCKANURE | AH1, XT1, XT2, DR1 | Cable Insp. 110kV XLPE | ESBN TO CONFIRM | Yes | TO-24-ATE-KNR-1-01 | Yes | N/A | No Change | No | N/A | No Change
ATHEA KNOCKANURE | AH1, XT1, XT2, DR1 | 2023HP-1[29]Check Structure (Top Rot)-S2 | 901503231 | Yes | TO-24-ATE-KNR-1-01 | Yes | N/A | No Change | No | N/A | No Change
ATHEA KNOCKANURE | AH1, XT1, XT2, DR1 | 2023HP-1[34]Check Structure (Top Rot)-S2 | 901503232 | Yes | TO-24-ATE-KNR-1-01 | Yes | N/A | No Change | No | N/A | No Change
ATHEA KNOCKANURE | AH1, XT1, XT2, DR1 | 2023HP-1[21]Check Structure (Top Rot)-S2 | 901503229 | Yes | TO-24-ATE-KNR-1-01 | Yes | N/A | No Change | No | N/A | No Change
ATHEA KNOCKANURE | AH1, XT1, XT2, DR1 | 2023HP-1[26]Check Structure (Top Rot)-S2 | 901503230 | Yes | TO-24-ATE-KNR-1-01 | Yes | N/A | No Change | No | N/A | No Change
ATHEA KNOCKANURE | AH1, XT1, XT2, DR1 | 2023HP-1[35]Check Structure (Top Rot)-S2 | 901503233 | Yes | TO-24-ATE-KNR-1-01 | Yes | N/A | No Change | No | N/A | No Change
ATHEA T121 | AH1 | 110kV SF6 Cubicle Ordinary Service (excludes busbar disconnects) | 901396378 | Yes | TO-24-ATE-T121-01 | Yes | N/A | No Change | No | N/A | No Change
ATHEA T121 | AH1 | 110KV Cubicle Condition Assessment (excludes busbar disconnects) | 901396303 | Yes | TO-24-ATE-T121-01 | Yes | N/A | No Change | No | N/A | No Change
ATHEA T121 | AH1 | 2023PM_Install BL Shrinks-OD 2 Days | 901452092 | Yes | TO-24-ATE-T121-01 | No | TAO resourcing | TAO | No | N/A | No Change
ATHEA TOBERTOREEN | XT1, XT2 | 110kV SF6 Cubicle Ordinary Service | ESBN TO CONFIRM | Yes | TO-24-ATE-TOB-1-02 | N/A | N/A | N/A | Yes | Not due in 2024 | TAO
ATHEA TOBERTOREEN | XT1, XT2 | 110kV SF6 Cubicle Operational Test | ESBN TO CONFIRM | Yes | TO-24-ATE-TOB-1-03 | Yes | N/A | No Change | No | N/A | No Change
ATHEA TOBERTOREEN | XT1, XT2 | Cable Insp. 110kV XLPE | ESBN TO CONFIRM | Yes | TO-24-ATE-TOB-1-02 | Yes | N/A | No Change | No | N/A | No Change
AUGHINISH SEALROCK 3 | SK3 | P3 Protection maintenance of 7SA513,REL551 |  | Yes | TO-24-AUG-SK-3-01 | Yes | N/A | No Change | No | N/A | No Change
AUGHINISH SEALROCK 3 | SK3 | P3 Protection maintenance of 7SA511,REL551 |  | Yes | TO-24-AUG-SK-3-01 | Yes | N/A | No Change | No | N/A | No Change
AUGHINISH SEALROCK 3 | SK3 | CB spring charge AC supply mod required | 901445480 | Yes | TO-24-AUG-SK-3-01 | No | Not scheduled at request of generator | GEN | No | N/A | No Change
AUGHINISH SEALROCK 3 | SK3 | Cable Insp. 110kV XLPE | ESBN TO CONFIRM | Yes | TO-24-AUG-SK-3-01 | Yes | N/A | No Change | No | N/A | No Change
AUGHINISH SEALROCK 3 | SK3 | SF6 densimeter isolation plunger required | 901445482 | Yes | TO-24-AUG-SK-3-01 | No | Not scheduled at request of generator | GEN | No | N/A | No Change
AUGHINISH SEALROCK 3 | SK3 | Replace CB HV flange bolts | 901445481 | Yes | TO-24-AUG-SK-3-01 | No | Not scheduled at request of generator | GEN | No | N/A | No Change
AUGHINISH SEALROCK 4 | SK4 | Cable Insp. 110kV XLPE | ESBN TO CONFIRM | Yes | TO-24-AUG-SK-4-01 | Yes | N/A | No Change | No | N/A | No Change
AUGHINISH SEALROCK 4 | SK4 | 110kV SF6 Cubicle Operational Test | ESBN TO CONFIRM | Yes | TO-24-AUG-SK-4-01 | No | TAO resourcing | TAO | No | N/A | No Change
BALLYNAHULLA CORDAL | DL1/DL2 | 110kV SF6 Cubicle Operational Test | ESBN TO CONFIRM | Yes | TO-24-BYH-CDL-1-01 | Yes | N/A | No Change | No | N/A | No Change
BALLYNAHULLA CORDAL | DL1/DL2 | Cable Insp. 400 & 220kV Feeder XLPE | 901535585 | Yes | TO-24-BYH-CDL-1-01 | Yes | N/A | No Change | No | N/A | No Change
BALLYVOUSKILL COOMATAGGART | GD1 | 2023PM_Water ingress in CB link box @ JB33 - raise or relocate. | 901468879 | Yes | TO-24-BVK-COT-1-01 | No | TAO resourcing | TAO | No | N/A | No Change
BALLYVOUSKILL COOMATAGGART | GD1 | Cable Insp. 110kV XLPE (MID SECTION 1/3) | ESBN TO CONFIRM | Yes | TO-24-BVK-COT-1-01 | Yes | N/A | No Change | No | N/A | No Change
BALLYVOUSKILL COOMATAGGART | GD1 | 2023PM_Replace all SVL's in JB33 link box - water logged and poor readings. | 901468941 | Yes | TO-24-BVK-COT-1-01 | No | TAO resourcing | TAO | No | N/A | No Change
BALLYVOUSKILL COOMATAGGART | GD1 | P3 Protection maintenance of 7SA612,GRL100 702D |  | Yes | TO-24-BVK-COT-1-01 | Yes | N/A | No Change | No | N/A | No Change
BALLYVOUSKILL COOMATAGGART | GD1 | 110kV SF6 Cubicle Operational Test | ESBN TO CONFIRM | Yes | TO-24-BVK-COT-1-01 | Yes | N/A | No Change | No | N/A | No Change
BALLYVOUSKILL COOMATAGGART | GD1 | 110kV SF6 Cubicle Ordinary Service (excludes busbar disconnects) | ESBN TO CONFIRM | Yes | TO-24-BVK-COT-1-01 | Yes | N/A | No Change | No | N/A | No Change
BALLYVOUSKILL COOMATAGGART | GD1 | P3 Protection maintenance of 7SA612,GRL100 702D |  | Yes | TO-24-BVK-COT-1-01 | Yes | N/A | No Change | No | N/A | No Change
BALLYVOUSKILL COOMATAGGART | GD1 | P1 Hotspot on Ballyvouskill DA S phase required immediately | 901520009 | Yes | TO-24-BVK-COT-1-01 | Yes | N/A | No Change | No | N/A | No Change
BALLYVOUSKILL COOMATAGGART | GD1 | P3 Hotspot on Ballyvouskill DL R phase required within the next 12 months | 901520010 | Yes | TO-24-BVK-COT-1-01 | Yes | N/A | No Change | No | N/A | No Change
BALLYVOUSKILL COOMATAGGART | GD1 | P2 Hotspot on Ballyvouskill DA T phase required within the next 3 months | 901534443 | Yes | TO-24-BVK-COT-1-01 | Yes | N/A | No Change | No | N/A | No Change
BALLYWATER CRANE | BW1 | P3 Protection maintenance of 7SD610,7SA513 |  | Yes | TO-24-BWR-CRA-1-02 | N/A | N/A | N/A | Yes | Not due in 2024 | TSO
BARRYMORE tee CAHIR | BF1 | 2022HP-1[120]Off Plumb (Re-plumb poles) | 901368960 | Yes | TO-24-BAR,T-CAH-1-01 | No | Outage scheduled for winter 2024/25 off-season | TSO | No | N/A | No Change
BARRYMORE tee CAHIR | BF1 | HOTSPOT - 2023IR[AT 181]L/Ph Repl. Deadend. Response: 1 Month. Due: 12-Feb-2024 | 901519329 | Yes | TO-24-BAR,T-CAH-1-01 | No | Outage scheduled for winter 2024/25 off-season | TSO | No | N/A | No Change
BARRYMORE tee CAHIR | BF1 | HOTSPOT - 2023IR[53-54]C/Ph Repl Midspan Immediate. Response: Immediately. Due: Immediately | 901519320 | Yes | TO-24-BAR,T-CAH-1-01 | No | Outage scheduled for winter 2024/25 off-season | TSO | No | N/A | No Change
BARRYMORE tee CAHIR | BF1 | HOTSPOT - 2023IR[62-63]L/Ph Repl. Midspan. Response: 6 Months. Due: 12-Jul-2024 | 901519321 | Yes | TO-24-BAR,T-CAH-1-01 | No | Outage scheduled for winter 2024/25 off-season | TSO | No | N/A | No Change
BARRYMORE tee CAHIR | BF1 | HOTSPOT - 2023IR[63-64]C/Ph Repl. Midspan. Response: 3 Months. Due: 12-Apr-2024 | 901519325 | Yes | TO-24-BAR,T-CAH-1-01 | No | Outage scheduled for winter 2024/25 off-season | TSO | No | N/A | No Change
BARRYMORE tee CAHIR | BF1 | HOTSPOT - 2023IR[63-64]R/Ph Repl. Midspan. Response: 3 Months. Due: 12-Apr-2024 | 901519324 | Yes | TO-24-BAR,T-CAH-1-01 | No | Outage scheduled for winter 2024/25 off-season | TSO | No | N/A | No Change
BARRYMORE tee CAHIR | BF1 | HOTSPOT - 2023IR[AT 22]C/Ph Repl. Deadend 1 Months. Response: 1 Month. Due: 12-Feb-2024 | 901519317 | Yes | TO-24-BAR,T-CAH-1-01 | No | Outage scheduled for winter 2024/25 off-season | TSO | No | N/A | No Change
BARRYMORE tee CAHIR | BF1 | HOTSPOT - 2023IR[AT 22]C/Ph Repl. Deadend 3 Months. Response: 3 Months. Due: 12-Apr-2024 | 901519316 | Yes | TO-24-BAR,T-CAH-1-01 | No | Outage scheduled for winter 2024/25 off-season | TSO | No | N/A | No Change
BARRYMORE tee CAHIR | BF1 | O-Ring Replacement to prevent SF6 leaks | ESBN TO CONFIRM | Yes | TO-24-BAR,T-CAH-1-01 | No | Outage scheduled for winter 2024/25 off-season | TSO | No | N/A | No Change
BARRYMORE tee CAHIR | BF1 | HOTSPOT - 2023IR[AT 63]R/Ph Repl. Deadend. Response: 3 Months. Due: 12-Apr-2024 | 901519322 | Yes | TO-24-BAR,T-CAH-1-01 | No | Outage scheduled for winter 2024/25 off-season | TSO | No | N/A | No Change
BARRYMORE tee CAHIR | BF1 | 2022HP-1[121]Off Plumb (Re-plumb poles) | 901368961 | Yes | TO-24-BAR,T-CAH-1-01 | No | Outage scheduled for winter 2024/25 off-season | TSO | No | N/A | No Change
BARRYMORE tee CAHIR | BF1 | HOTSPOT - 2023IR[70-71]C/Ph Repl. Midspan. Response: 1 Month. Due: 12-Feb-2024 | 901519326 | Yes | TO-24-BAR,T-CAH-1-01 | No | Outage scheduled for winter 2024/25 off-season | TSO | No | N/A | No Change
BARRYMORE tee CAHIR | BF1 | HOTSPOT - 2023IR[AT 63]L/Ph Repl. Deadend. Response: 1 Month. Due: 12-Feb-2024 | 901519323 | Yes | TO-24-BAR,T-CAH-1-01 | No | Outage scheduled for winter 2024/25 off-season | TSO | No | N/A | No Change
BARRYMORE tee CAHIR | BF1 | HOTSPOT - 2023IR[AT 22]C/Ph Repl. Jumper 1 Months. Response: 1 Month. Due: 12-Feb-2024 | 901519318 | Yes | TO-24-BAR,T-CAH-1-01 | No | Outage scheduled for winter 2024/25 off-season | TSO | No | N/A | No Change
BARRYMORE tee CAHIR | BF1 | Insulator off Plumb. Pole No. 227 | 901385039 | Yes | TO-24-BAR,T-CAH-1-01 | No | Outage scheduled for winter 2024/25 off-season | TSO | No | N/A | No Change
BARRYMORE tee CAHIR | BF1 | HOTSPOT - 2023IR[181-182]C/Ph Repl Midspan. Response: 3 Months. Due: 12-Apr-2024 | 901519328 | Yes | TO-24-BAR,T-CAH-1-01 | No | Outage scheduled for winter 2024/25 off-season | TSO | No | N/A | No Change
BARRYMORE tee CAHIR | BF1 | HOTSPOT - 2023IR[130-131]C/Ph Repl Midspan. Response: 1 Month. Due: 12-Feb-2024 | 901519327 | Yes | TO-24-BAR,T-CAH-1-01 | No | Outage scheduled for winter 2024/25 off-season | TSO | No | N/A | No Change
BARRYMORE tee CAHIR | BF1 | HOTSPOT - 2023IR[23-24]L/Ph Repl Midspan Immediate. Response: Immediately. Due: Immediately | 901519319 | Yes | TO-24-BAR,T-CAH-1-01 | No | Outage scheduled for winter 2024/25 off-season | TSO | No | N/A | No Change
BARRYMORE tee CAHIR | BF1 | 2023HP-1[205]Insulator 1xBroken disc R/P | 901500688 | Yes | TO-24-BAR,T-CAH-1-01 | No | Outage scheduled for winter 2024/25 off-season | TSO | No | N/A | No Change
BARRYMORE tee CAHIR | BF1 | 2023HP-1[107]off Plumb | 901500689 | Yes | TO-24-BAR,T-CAH-1-01 | No | Outage scheduled for winter 2024/25 off-season | TSO | No | N/A | No Change
BARRYMORE tee CAHIR | BF1 | BAR-CAH-KRA-1: Protection relay works in Knockraha and Cahir only | CP1116 | Yes | TO-24-BAR,T-CAH-1-02 | No | Outage scheduled for winter 2024/25 off-season | TSO | No | N/A | No Change
BARRYMORE tee CAHIR | BF1 | P3 Protection maintenance of 7SA511,REL521 |  | Yes | TO-24-BAR,T-CAH-1-01 | No | Outage scheduled for winter 2024/25 off-season | TSO | No | N/A | No Change
BARRYMORE tee CAHIR | BF1 | 2020HP-1[22-23]Air Craft Sphere Bird Div | 901170978 | Yes | TO-24-BAR,T-CAH-1-01 | No | Outage scheduled for winter 2024/25 off-season | TSO | No | N/A | No Change
BARRYMORE tee CAHIR | BF1 | 110kV SF6 Cubicle Ordinary Service | 901300801 | Yes | TO-24-BAR,T-CAH-1-01 | No | Outage scheduled for winter 2024/25 off-season | TSO | No | N/A | No Change
BARRYMORE tee KNOCKRAHA | BF1 | 2023IR[AT 287]R/Ph Repl. Deadend Immediat | 901519331` | Yes | TO-24-BAR,T-KRA-1-01 | No | Outage scheduled for winter 2024/25 off-season | TSO | No | N/A | No Change
BARRYMORE tee KNOCKRAHA | BF1 | Replace Pole No. 248. Top Right Pole Rot | 901397306 | Yes | TO-24-BAR,T-KRA-1-01 | No | Outage scheduled for winter 2024/25 off-season | TSO | No | N/A | No Change
BARRYMORE tee KNOCKRAHA | BF1 | HOTSPOT - 2023IR[286-287]L1/Ph Resistance Midspan. Response: Next Planned Maintenance. Due: Next Planned Maintenance | 901519333 | Yes | TO-24-BAR,T-KRA-1-01 | No | Outage scheduled for winter 2024/25 off-season | TSO | No | N/A | No Change
BARRYMORE tee KNOCKRAHA | BF1 | 2023IR[AT 287]R/Ph Repl. Deadend 3 Months | 901519330 | Yes | TO-24-BAR,T-KRA-1-01 | No | Outage scheduled for winter 2024/25 off-season | TSO | No | N/A | No Change
BARRYMORE tee KNOCKRAHA | BF1 | HOTSPOT - 2023IR[286-287]R/Ph Rep Midspan. Response: Immediately. Due: Immediately | 901519332 | Yes | TO-24-BAR,T-KRA-1-01 | No | Outage scheduled for winter 2024/25 off-season | TSO | No | N/A | No Change
BARRYMORE tee KNOCKRAHA | BF1 | HOTSPOT - 2023IR[AT 278]L/Ph Repl Deadend . Response: Immediately. Due: Immediately | 901519331 | Yes | TO-24-BAR,T-KRA-1-01 | No | Outage scheduled for winter 2024/25 off-season | TSO | No | N/A | No Change
BARRYMORE tee KNOCKRAHA | BF1 | 2023HP-1[341]Check Structure (Top Rot)S2 | 901503248 | Yes | TO-24-BAR,T-KRA-1-01 | No | Outage scheduled for winter 2024/25 off-season | TSO | No | N/A | No Change
BARRYMORE tee KNOCKRAHA | BF1 | BAR-CAH-KRA-1: Protection relay works in Knockraha and Cahir only | CP1116 | Yes | TO-24-BAR,T-KRA-1-02 | No | Outage scheduled for winter 2024/25 off-season | TSO | No | N/A | No Change
BARRYMORE tee KNOCKRAHA | BF1 | P3 Protection maintenance of 7SA511,REL521 |  | Yes | TO-24-BAR,T-KRA-1-01 | No | Outage scheduled for winter 2024/25 off-season | TSO | No | N/A | No Change
BARRYMORE tee KNOCKRAHA | BF1 | 110KV CUBICLE CONDITION ASSESSMENT | 901396433 | Yes | TO-24-BAR,T-KRA-1-01 | No | Outage scheduled for winter 2024/25 off-season | TSO | No | N/A | No Change
BARRYMORE tee KNOCKRAHA | BF1 | 2021HP-1[332]Off Plumb | 901253795 | Yes | TO-24-BAR,T-KRA-1-01 | No | Outage scheduled for winter 2024/25 off-season | TSO | No | N/A | No Change
BARRYMORE tee KNOCKRAHA | BF1 | Replace Pole No. 296. Rotten | 901298990 | Yes | TO-24-BAR,T-KRA-1-01 | No | Outage scheduled for winter 2024/25 off-season | TSO | No | N/A | No Change
BARRYMORE tee KNOCKRAHA | BF1 | 110kV SF6 Cubicle Ordinary Service | 901396820 | Yes | TO-24-BAR,T-KRA-1-01 | No | Outage scheduled for winter 2024/25 off-season | TSO | No | N/A | No Change
BARRYMORE tee KNOCKRAHA | BF1 | Replace Pole Set 227- Pole Rot | 901298981 | Yes | TO-24-BAR,T-KRA-1-01 | No | Outage scheduled for winter 2024/25 off-season | TSO | No | N/A | No Change
BARRYMORE tee KNOCKRAHA | BF1 | HAZ CNF 40M (278-279) Tim Cut | 901217145 | Yes | TO-24-BAR,T-KRA-1-01 | No | Outage scheduled for winter 2024/25 off-season | TSO | No | N/A | No Change
BARRYMORE tee KNOCKRAHA | BF1 | Replace Pole Set 236. -Rotten | 901298983 | Yes | TO-24-BAR,T-KRA-1-01 | No | Outage scheduled for winter 2024/25 off-season | TSO | No | N/A | No Change
BELLACORICK SRAHNAKILLY | OY1, OY2 | Cable Insp. 110kV XLPE | ESBN TO CONFIRM | Yes | TO-24-BK-SKY-1-02 | N/A | N/A | N/A | Yes | Asset not yet transferred to TAO | Other
BELLACORICK SRAHNAKILLY | OY1, OY2 | 2021PM_Investigation & repair of S-Phase | 901238134 | Yes | TO-24-BK-SKY-1-03 | Yes | N/A | No Change | No | N/A | No Change
BELLACORICK SRAHNAKILLY | OY1, OY2 | 110kV SF6 Cubicle Ordinary Service (excludes busbar disconnects) | ESBN TO CONFIRM | Yes | TO-24-BK-SKY-1-04 | N/A | N/A | N/A | Yes | Asset not yet transferred to TAO | Other
BELLACORICK SRAHNAKILLY | OY1, OY2 | O-Ring Replacement to prevent SF6 leaks | ESBN TO CONFIRM | Yes | TO-24-BK-SKY-1-05 | N/A | N/A | N/A | Yes | Asset not yet transferred to TAO | Other
BELLACORICK SRAHNAKILLY | OY1, OY2 | 110kV SF6 Cubicle Ordinary Service (excludes busbar disconnects) | ESBN TO CONFIRM | Yes | TO-24-BK-SKY-1-06 | N/A | N/A | N/A | Yes | Asset not yet transferred to TAO | Other
BOGGERAGH 110SA1 | BG2 | 110kV Sect / Dist Ordinary Service (including busbar disconnects of all bays that are connected to the busbar section that is on outage) | ESBN TO CONFIRM | Yes | TO-24-BGH-110SA1-01 | Yes | N/A | No Change | No | N/A | No Change
BOGGERAGH CLASHAVOON | BG1, BG2 | Cable Insp. 110kV XLPE | ESBN TO CONFIRM | Yes | TO-24-BGH-CLA-1-01 | Yes | N/A | No Change | No | N/A | No Change
BOGGERAGH CLASHAVOON | BG1, BG2 | 110kV SF6 Cubicle Ordinary Service | ESBN TO CONFIRM | Yes | TO-24-BGH-CLA-1-01 | No | TAO resourcing | TAO | No | N/A | No Change
BOGGERAGH CLASHAVOON | BG1, BG2 | O1- H3 CB light defect | 901474431 | Yes | TO-24-BGH-CLA-1-01 | Yes | N/A | No Change | No | N/A | No Change
BOGGERAGH CLASHAVOON | BG1, BG2 | O-Ring Replacement to prevent SF6 leaks | ESBN TO CONFIRM | Yes | TO-24-BGH-CLA-1-01 | No | TAO resourcing | TAO | No | N/A | No Change
BOGGERAGH CLASHAVOON | BG1, BG2 | 110kV SF6 Cubicle Ordinary Service | ESBN TO CONFIRM | Yes | TO-24-BGH-CLA-1-01 | No | TAO resourcing | TAO | No | N/A | No Change
BOGGERAGH CLASHAVOON | BG1, BG2 | 2023HP-1[77]Earths-Replace (Pole Top) | 901501298 | Yes | TO-24-BGH-CLA-1-01 | Yes | N/A | No Change | No | N/A | No Change
BOGGERAGH CLASHAVOON | BG1, BG2 | 2023HP-1[7]Earths-Replace (Pole Top) | 901501297 | Yes | TO-24-BGH-CLA-1-01 | Yes | N/A | No Change | No | N/A | No Change
BOGGERAGH CLASHAVOON | BG1, BG2 | O1-Surge Counter Screen not working S Ph | 901412245 | Yes | TO-24-BGH-CLA-1-01 | Yes | N/A | No Change | No | N/A | No Change
BOGGERAGH T121 | BG1, BG2 | 110kV SF6 Cubicle Ordinary Service (excludes busbar disconnects) | ESBN TO CONFIRM | Yes | TO-24-BGH-T121-01 | No | TAO resourcing | TAO | No | N/A | No Change
BOGGERAGH T132 | BG2 | 110kV SF6 Cubicle Operational Test | ESBN TO CONFIRM | Yes | TO-24-BGH-T132-01 | Yes | N/A | No Change | No | N/A | No Change
BOOLTIAGH T121 | BT1, BT2 | 110kV SF6 Cubicle Operational Test | ESBN TO CONFIRM | Yes | TO-24-BOL-T121-01 | Yes | N/A | No Change | No | N/A | No Change
CARRIGADROHID T103 | LE3 | P3 Protection maintenance of 7SA612,RET521,7SV512 |  | Yes | TO-24-CD-T103-02 | No | P2 and P3 protection maintenance is opportunistic only | Other | No | N/A | No Change
CARRIGDANGAN DUNMANWAY | XA1 | 110kV GIS Cubicle Operational Test | ESBN TO CONFIRM | Yes | TO-24-CGG-DMY-1-01 | Yes | N/A | No Change | No | N/A | No Change
CARRIGDANGAN DUNMANWAY | XA1 | 110kV SF6 Cubicle Operational Test | ESBN TO CONFIRM | Yes | TO-24-CGG-DMY-1-01 | Yes | N/A | No Change | No | N/A | No Change
CARRIGDANGAN DUNMANWAY | XA1 | Cable Insp. 110kV XLPE | 901535620 | Yes | TO-24-CGG-DMY-1-01 | N/A | N/A | N/A | Yes | Asset not yet transferred to TAO | Other
CATHALEENS FALL CLIFF | ER1, ER2 | P1 Protection maintenance of 7SA511 |  | Yes | TO-24-CF-CL-1-02 | Yes | N/A | No Change | No | N/A | No Change
CATHALEENS FALL CLIFF | ER1, ER2 | H5 CB densimeter replacement. | 901335734 | Yes | TO-24-CF-CL-1-02 | No | Conflicts with generator forced outage | GEN | No | N/A | No Change
CATHALEENS FALL CLIFF | ER1, ER2 | 110kV SF6 Cubicle Operational Test | 901396673 | Yes | TO-24-CF-CL-1-02 | No | Conflicts with generator forced outage | GEN | No | N/A | No Change
CATHALEENS FALL T103 | T103 | P3 Protection maintenance of BOC (M1),7SA612,7UT513 |  | Yes | TO-24-CF-T103-01 | N/A | N/A | N/A | Yes | Not due in 2024 | TSO
CATHALEENS FALL T103 | T103 | 110KV SF6 Cubicle Ordinary Service | ESBN TO CONFIRM | Yes | TO-24-CF-T103-01 | No | TAO resourcing | TAO | No | N/A | No Change
CATHALEENS FALL T103 | T103 | 110kV CUBICLE CONDITION ASSESSMENT | ESBN TO CONFIRM | Yes | TO-24-CF-T103-01 | No | TAO resourcing | TAO | No | N/A | No Change
CATHALEENS FALL T104 | T104 | P3 Protection maintenance of 7SA612,7UT513 |  | Yes | TO-24-CF-T104-01 | No | Conflicts with higher priority work | TSO | No | N/A | No Change
CATHALEENS FALL T104 | T104 | 110KV SF6 Cubicle Ordinary Service | 901396849 | Yes | TO-24-CF-T104-01 | No | Conflicts with higher priority work | TSO | No | N/A | No Change
CATHALEENS FALL T104 | T104 | 110KV CUBICLE CONDITION ASSESSMENT | 901396488 | Yes | TO-24-CF-T104-01 | No | Conflicts with higher priority work | TSO | No | N/A | No Change
CATHALEENS FALL T104 | T104 | T104 SF6 CB Operational Test C Falls | 901332346 | Yes | TO-24-CF-T104-01 | No | Conflicts with higher priority work | TSO | No | N/A | No Change
CLAHANE T122 | CJ1, CJ2 | 110kV SF6 Cubicle Ordinary Service (excludes busbar disconnects) | ESBN TO CONFIRM | Yes | TO-24-CLH-T122-01 | N/A | N/A | N/A | Yes | Not due in 2024 | TAO
CLIFF T101 | ER1 | P3 Protection maintenance of 7SJ511,7UT513 |  | Yes | TO-24-CL-T101-03 | Yes | N/A | No Change | No | N/A | No Change
CLIFF T101 | ER1 | Repair corrosion issue on CTs | 901230085 | Yes | TO-24-CL-T101-02 | No | TAO resourcing | TAO | No | N/A | No Change
CLIFF T102 | ER2 | P1 Protection maintenance of 7SJ511,7UT513 |  | Yes | TO-24-CL-T102-03 | N/A | N/A | N/A | Yes | Not due in 2024 | TAO
CLIFF T102 | ER2 | Visually Inspect CT's bellow pipework | 901314311 | Yes | TO-24-CL-T102-03 | No | TAO resourcing | TAO | No | N/A | No Change
CLIFF T102 | ER2 | Replace SF6 Pressure gauge | 901314313 | Yes | TO-24-CL-T102-03 | No | TAO resourcing | TAO | No | N/A | No Change
CLIFF T102 | ER2 | Measure SF6 gasquality for level of SO2 | 901314314 | Yes | TO-24-CL-T102-03 | Yes | N/A | No Change | No | N/A | No Change
CLIFF T102 | ER2 | 110KV SF6 Cubicle Operational Test | 901432253 | Yes | TO-24-CL-T102-03 | No | TAO resourcing | TAO | No | N/A | No Change
CLOGHBOOLA T131 | CL1 | P3 Protection maintenance of 7SA611,7SJ804 |  | Yes | TO-24-CBA-T131-01 | N/A | N/A | N/A | Yes | Not due in 2024 | TSO
CLOGHBOOLA TRIEN | CL1 | 2023PM_Testing after correctives (LB cha | 901423790 | Yes | TO-24-CBA-TRI-1-01 | No | TAO resourcing | TAO | No | N/A | No Change
CLOGHBOOLA TRIEN | CL1 | 2023PMWater ingress into link box at JB08 | 901423791 | Yes | TO-24-CBA-TRI-1-01 | No | TAO resourcing | TAO | No | N/A | No Change
CLOGHBOOLA TRIEN | CL1 | 2023PMWater ingress into link box at JB10 | 901423792 | Yes | TO-24-CBA-TRI-1-01 | No | TAO resourcing | TAO | No | N/A | No Change
CLOGHBOOLA TRIEN | CL1 | Clean CSE stand-off insulators in Cloghb | 901155245 | Yes | TO-24-CBA-TRI-1-01 | No | TAO resourcing | TAO | No | N/A | No Change
CLOGHBOOLA TRIEN | CL1 | Water ingress into link box at JB12 - ra | 901155246 | Yes | TO-24-CBA-TRI-1-01 | No | TAO resourcing | TAO | No | N/A | No Change
CLOGHBOOLA TRIEN | CL1 | 110kV SF6 Cubicle Operational Test | ESBN TO CONFIRM | Yes | TO-24-CBA-TRI-1-01 | Yes | N/A | No Change | No | N/A | No Change
CLOGHBOOLA TRIEN | CL1 | 110kV SF6 Cubicle Operational Test | ESBN TO CONFIRM | Yes | TO-24-CBA-TRI-1-01 | Yes | N/A | No Change | No | N/A | No Change
CLOGHER MULREAVY | MB1, MB2 | Cable Insp. 110kV XLPE | 901129091 | Yes | TO-24-CLO-MRY-1-01 | Yes | N/A | No Change | No | N/A | No Change
CLOGHER MULREAVY | MB1, MB2 | 110kV GIS Cubicle Ordinary Service | 901300588 | Yes | TO-24-CLO-MRY-1-01 | No | TAO resourcing | TAO | No | N/A | No Change
CLOGHER MULREAVY | MB1, MB2 | P2 Protection maintenance of 7SA612,GRL100 |  | Yes | TO-24-CLO-MRY-1-01 | Yes | N/A | No Change | No | N/A | No Change
CLOGHER MULREAVY | MB1, MB2 | P2 Protection maintenance of 7SA612,GRL100 |  | Yes | TO-24-CLO-MRY-1-01 | Yes | N/A | No Change | No | N/A | No Change
CLONIFFEEN SHANNONBRIDGE | SI1, SI2 | 220kV SF6 Cubicle Operational Test | 901397035 | Yes | TO-24-CFN-SH-1-01 | Yes | N/A | No Change | No | N/A | No Change
CLONKEEN COOMAGEARLAHY | CG1, CG2, CG3 | 2023LP-1[40] Treat Jumper Bolts | 901495141 | Yes | TO-24-CKN-CGL-1-02 | Yes | N/A | No Change | No | N/A | No Change
CLONKEEN COOMAGEARLAHY | CG1, CG2, CG3 | 2023LP-1[44] Treat Jumper Bolts | 901495142 | Yes | TO-24-CKN-CGL-1-02 | Yes | N/A | No Change | No | N/A | No Change
CLONKEEN COOMAGEARLAHY | CG1, CG2, CG3 | 2023LP-1[45] Treat Jumper Bolts | 901495143 | Yes | TO-24-CKN-CGL-1-02 | Yes | N/A | No Change | No | N/A | No Change
CLONKEEN COOMAGEARLAHY | CG1, CG2, CG3 | 2023LP-1[14]Vibration Dampers Replace | 901495144 | Yes | TO-24-CKN-CGL-1-02 | Yes | N/A | No Change | No | N/A | No Change
CLONKEEN COOMAGEARLAHY | CG1, CG2, CG3 | 2023LP-1[24]Vibration Dampers Replace | 901495145 | Yes | TO-24-CKN-CGL-1-02 | Yes | N/A | No Change | No | N/A | No Change
CLONKEEN COOMAGEARLAHY | CG1, CG2, CG3 | 2023LP-1[25]Vibration Dampers Replace | 901495146 | Yes | TO-24-CKN-CGL-1-02 | Yes | N/A | No Change | No | N/A | No Change
CLONKEEN COOMAGEARLAHY | CG1, CG2, CG3 | 2023LP-1[28]Vibration Dampers Replace | 901495147 | Yes | TO-24-CKN-CGL-1-02 | Yes | N/A | No Change | No | N/A | No Change
CLONKEEN COOMAGEARLAHY | CG1, CG2, CG3 | 2023LP-1[29]Vibration Dampers Replace | 901495148 | Yes | TO-24-CKN-CGL-1-02 | Yes | N/A | No Change | No | N/A | No Change
CLONKEEN COOMAGEARLAHY | CG1, CG2, CG3 | 2023LP-1[41]Vibration Dampers Replace | 901495149 | Yes | TO-24-CKN-CGL-1-02 | Yes | N/A | No Change | No | N/A | No Change
CLONKEEN COOMAGEARLAHY | CG1, CG2, CG3 | 2023LP-1[28]Check - Ubolts (S2) | 901495157 | Yes | TO-24-CKN-CGL-1-02 | Yes | N/A | No Change | No | N/A | No Change
CLONKEEN COOMAGEARLAHY | CG1, CG2, CG3 | 2023LP-1[29]Check -Ubolts (S2) | 901495158 | Yes | TO-24-CKN-CGL-1-02 | Yes | N/A | No Change | No | N/A | No Change
CLONKEEN COOMAGEARLAHY | CG1, CG2, CG3 | Cable Insp. 110kV XLPE | ESBN TO CONFIRM | Yes | TO-24-CKN-CGL-1-02 | No | TAO resourcing | TAO | No | N/A | No Change
CLONKEEN COOMAGEARLAHY | CG1, CG2, CG3 | 110kV SF6 Cubicle Operational Test | ESBN TO CONFIRM | Yes | TO-24-CKN-CGL-1-02 | Yes | N/A | No Change | No | N/A | No Change
CLONKEEN COOMAGEARLAHY | CG1, CG2, CG3 | P3 Protection maintenance of 7SA612,GRL100 |  | Yes | TO-24-CKN-CGL-1-02 | Yes | N/A | No Change | No | N/A | No Change
CLONKEEN COOMAGEARLAHY | CG1, CG2, CG3 | 110kV SF6 Cubicle Operational Test | ESBN TO CONFIRM | Yes | TO-24-CKN-CGL-1-02 | Yes | N/A | No Change | No | N/A | No Change
COOLNANOONAGH KILPADDOGE | KZ4, KZ1, KZ3 | P3 Protection maintenance of 7SA611,BOC,RET670,GRB100,7SJ804 |  | Yes | TO-24-CNO-KPG-1-02 | No | P2 and P3 protection maintenance is opportunistic only | Other | No | N/A | No Change
COOLNANOONAGH KILPADDOGE | KZ4, KZ1, KZ3 | 110kV SF6 Cubicle Operational Test |  | Yes | TO-24-CNO-KPG-1-01 | N/A | N/A | N/A | Yes | Not due in 2024 | TAO
COOMAGEARLAHY GLANLEE | GL1 | 110kV SF6 Cubicle Ordinary Service (excludes busbar disconnects) | 901396332 | Yes | TO-24-CGL-GAE-1-02 | Yes | N/A | No Change | No | N/A | No Change
COOMAGEARLAHY GLANLEE | GL1 | P3 Protection maintenance of 7SA612,GRL100 |  | Yes | TO-24-CGL-GAE-1-02 | N/A | N/A | N/A | Yes | Not due in 2024 | TSO
COOMAGEARLAHY GLANLEE | GL1 | Cable Insp. 110kV XLPE | ESBN TO CONFIRM | Yes | TO-24-CGL-GAE-1-02 | Yes | N/A | No Change | No | N/A | No Change
COOMAGEARLAHY T121 | CG3 | Carry out loss of AC supply mod | 901323272 | Yes | TO-24-CGL-T121-02 | No | TAO resourcing | TAO | No | N/A | No Change
COOMAGEARLAHY T121 | CG3 | P3 Protection maintenance of 7SA612,7VK611 |  | Yes | TO-24-CGL-T121-02 | N/A | N/A | N/A | Yes | Not due in 2024 | TSO
COOMATAGGART 110SA1 | YT1 | 110kV Sect / Dist Ordinary Service (including busbar disconnects of all bays that are connected to the busbar section that is on outage) | ESBN TO CONFIRM | Yes | TO-24-COT-110SA1-02 | N/A | N/A | N/A | Yes | Not due in 2024 | TAO
COOMATAGGART 110SA2 | GD1, YT1 | 110kV Sect / Dist Ordinary Service (including busbar disconnects of all bays that are connected to the busbar section that is on outage) | ESBN TO CONFIRM | Yes | TO-24-COT-110SA2-02 | N/A | N/A | N/A | Yes | Not due in 2024 | TAO
COOMATAGGART T132 | GD1 | 110kV SF6 Cubicle Ordinary Service (excludes busbar disconnects) | ESBN TO CONFIRM | Yes | TO-24-COT-T132-01 | N/A | N/A | N/A | Yes | Not due in 2024 | TAO
COOMATAGGART T132 | GD1 | P3 Hotspot on T132 DT disconnect R phase required within 12 months | 901520011 | Yes | TO-24-COT-T132-01 | Yes | N/A | No Change | No | N/A | No Change
COOMATAGGART T132 | GD1 | P3 Hotspot on T132 DA disconnect T phase required during next planned maintenance | 901520012 | Yes | TO-24-COT-T132-01 | Yes | N/A | No Change | No | N/A | No Change
CORDAL T132 | DL1/DL2 | 2023PM_Install shrinks to top of bonding leads-water ingress. | 901469066 | Yes | TO-24-CDL-T132-01 | Yes | N/A | No Change | No | N/A | No Change
CORDERRY GARVAGH | GH1, GH2 | 2023PM_Inst.LCIM bonding cbl ties;OD1Day | 901452521 | Yes | TO-24-CDY-GRV-1-01 | No | TAO resourcing | TAO | No | N/A | No Change
CORDERRY GARVAGH | GH1, GH2 | 110kV SF6 Cubicle Operational Test | ESBN TO CONFIRM | Yes | TO-24-CDY-GRV-1-01 | Yes | N/A | No Change | No | N/A | No Change
CORDERRY GARVAGH | GH1, GH2 | 110kV GIS Cubicle Operational Test | ESBN TO CONFIRM | Yes | TO-24-CDY-GRV-1-01 | No | TAO resourcing | TAO | No | N/A | No Change
CORDUFF HUNTSTOWN | HN2 | Cable Insp. 220kV Feeder XLPE | ESBN TO CONFIRM | Yes | TO-24-CDU-HN-1-01 | No | TAO resourcing | TAO | No | N/A | No Change
CORDUFF HUNTSTOWN | HN2 | 220kV SF6 Cubicle Operational Test | ESBN TO CONFIRM | Yes | TO-24-CDU-HN-1-01 | Yes | N/A | No Change | No | N/A | No Change
CUNGHILL T121 | KGM, KG2 | 110kV SF6 Cubicle Ordinary Service (excludes busbar disconnects) | ESBN TO CONFIRM | Yes | TO-24-CUN-T121-01 | Yes | N/A | No Change | No | N/A | No Change
CUNGHILL T121 | KGM, KG2 | O-Ring Replacement to prevent SF6 leaks | ESBN TO CONFIRM | Yes | TO-24-CUN-T121-01 | Yes | N/A | No Change | No | N/A | No Change
CUNGHILL T121 | KGM, KG2 | 110KV Cubicle Condition Assessment (excludes busbar disconnects) | ESBN TO CONFIRM | Yes | TO-24-CUN-T121-01 | Yes | N/A | No Change | No | N/A | No Change
CUSHALING KILCUMBER | OE1 | Cable Insp. 110kV XLPE | ESBN TO CONFIRM | Yes | TO-24-CUS-KIR-1-01 | N/A | N/A | N/A | Yes | Asset not yet transferred to TAO | Other
CUSHALING T101 | ED1 | 110kV SF6 Cubicle Operational Test | ESBN TO CONFIRM | Yes | TO-24-CUS-T101-01 | No | TAO resourcing | TAO | No | N/A | No Change
CUSHALING T103/5 | ED3, ED5 | O-Ring Replacement to prevent SF6 leaks | ESBN TO CONFIRM | Yes | TO-24-CUS-T103/5-01 | No | Generator outage insufficient duration to align works | TSO | No | N/A | No Change
CUSHALING T103/5 | ED3, ED5 | 110kV SF6 Cubicle Ordinary Service (excludes busbar disconnects) | ESBN TO CONFIRM | Yes | TO-24-CUS-T103/5-01 | No | No generator outage to align works | TSO | No | N/A | No Change
CUSHALING T103/5 | ED3, ED5 | P1 Protection maintenance of 7SA612,SEL551 |  | Yes | TO-24-CUS-T103/5-01 | No | No generator outage to align works | TSO | No | N/A | No Change
DERRYCARNEY T132 | LU1, LU2 | 110kV AIS Cubicle Operational Test | ESBN TO CONFIRM | Yes | TO-24-DEY-T132-01 | No | TAO resourcing | TAO | No | N/A | No Change
DERRYCARNEY T134 | NC1 | Cable Insp. 110kV XLPE | 901535601 | Yes | TO-24-DEY-T134-02 | Yes | N/A | No Change | No | N/A | No Change
DERRYCARNEY T134 | NC1 | 110kV AIS Cubicle Operational Test | ESBN TO CONFIRM | Yes | TO-24-DEY-T134-03 | Yes | N/A | No Change | No | N/A | No Change
DERRYIRON RHODE T1/T2 | RP1, RP2 | 60m[1-2]TimCut 110kV(Rural) | 901332399 | Yes | TO-24-DER-T1/T2-04 | No | TAO resourcing | TAO | No | N/A | No Change
DERRYIRON RHODE T1/T2 | RP1, RP2 | 110kV SF6 Cubicle Ordinary Service (excludes busbar disconnects) | ESBN TO CONFIRM | Yes | TO-24-DER-T1/T2-04 | Yes | N/A | No Change | No | N/A | No Change
DERRYIRON RHODE T1/T2 | RP1, RP2 | O-Ring Replacement to prevent SF6 leaks | ESBN TO CONFIRM | Yes | TO-24-DER-T1/T2-04 | Yes | N/A | No Change | No | N/A | No Change
DERRYIRON RHODE T1/T2 | RP1, RP2 | 110KV Cubicle Condition Assessment (excludes busbar disconnects) | ESBN TO CONFIRM | Yes | TO-24-DER-T1/T2-04 | N/A | N/A | N/A | Yes | Not due in 2024 | TAO
DERRYIRON RHODE T1/T2 | RP1, RP2 | 110KV SF6 Cubicle Operational Test | 901396752 | Yes | TO-24-DER-T1/T2-04 | Yes | N/A | No Change | No | N/A | No Change
DRUMKEEN MEENTYCAT | MCT | P3 Protection maintenance of 7SA513 |  | Yes | TO-24-DRM-MEE-1-01 | No | P2 and P3 protection maintenance is opportunistic only | Other | No | N/A | No Change
ENNIS SLIEVECALLAN | KD1, RD1 | Cable Insp. 110kV XLPE | 901212142 | Yes | TO-24-ENN-SLC-1-02 | Yes | N/A | No Change | No | N/A | No Change
ENNIS SLIEVECALLAN | KD1, RD1 | 110kV SF6 Cubicle Operational Test | ESBN TO CONFIRM | Yes | TO-24-ENN-SLC-1-02 | No | TAO resourcing | TAO | No | N/A | No Change
ENNIS SLIEVECALLAN | KD1, RD1 | P3 Protection maintenance of 7SA612,GRL100 702D |  | Yes | TO-24-ENN-SLC-1-02 | Yes | N/A | No Change | No | N/A | No Change
ENNIS SLIEVECALLAN | KD1, RD1 | 110kV SF6 Cubicle Operational Test | ESBN TO CONFIRM | Yes | TO-24-ENN-SLC-1-02 | Yes | N/A | No Change | No | N/A | No Change
FINGLAS HUNTSTOWN | HNC | 220kV SF6 Cubicle Ordinary Service | 901300960 | Yes | TO-24-FIN-HN-1-01 | No | TAO resourcing | TAO | No | N/A | No Change
FINGLAS HUNTSTOWN | HNC | CHECK TORQUE OF MECHANISM DRIVE RODS | 901301504 | Yes | TO-24-FIN-HN-1-01 | Yes | N/A | No Change | No | N/A | No Change
GALLANSTOWN T133 | IA01 | 110kV SF6 Cubicle Operational Test | ESBN TO CONFIRM | Yes | TO-24-GLN-T133-03 | N/A | N/A | N/A | Yes | Asset not yet transferred to TAO | Other
GARROW 110SA1-2CB | CZ1 | 110KV Cubicle Condition Assessment (excludes busbar disconnects) | 901396295 | Yes | TO-24-GRO-110SA1-2CB-01 | Yes | N/A | No Change | No | N/A | No Change
GARROW 110SA1-2CB | CZ1 | 110kV SF6 Cubicle Ordinary Service (excludes busbar disconnects) | 901396370 | Yes | TO-24-GRO-110SA1-2CB-01 | Yes | N/A | No Change | No | N/A | No Change
GARROW 110SA1-2CB | CZ1 | 110kV Sect / Dist Ordinary Service (including busbar disconnects of all bays that are connected to the busbar section that is on outage) | 901396211 | Yes | TO-24-GRO-110SA1-2CB-01 | Yes | N/A | No Change | No | N/A | No Change
GARROW 110SA1-2CB | CZ1 | 110kV Sect / Dist Ordinary Service (including busbar disconnects of all bays that are connected to the busbar section that is on outage) | 901396212 | Yes | TO-24-GRO-110SA1-2CB-01 | Yes | N/A | No Change | No | N/A | No Change
GARROW 110SA1-2CB | CZ1 | O-Ring Replacement to prevent SF6 leaks | ESBN TO CONFIRM | Yes | TO-24-GRO-110SA1-2CB-01 | No | TAO resourcing | TAO | No | N/A | No Change
GARROW 110SA1-2CB | CZ1 | O-Ring Replacement to prevent SF6 leaks | ESBN TO CONFIRM | Yes | TO-24-GRO-110SA1-2CB-01 | Yes | N/A | No Change | No | N/A | No Change
GARROW T122 | CZ1 | O-Ring Replacement to prevent SF6 leaks | ESBN TO CONFIRM | Yes | TO-24-GRO-T122-01 | No | TAO resourcing | TAO | No | N/A | No Change
GARROW T122 | CZ1 | 110kV SF6 Cubicle Ordinary Service (excludes busbar disconnects) | ESBN TO CONFIRM | Yes | TO-24-GRO-T122-01 | Yes | N/A | No Change | No | N/A | No Change
GARROW T122 | CZ1 | Cable Insp. 110kV XLPE | ESBN TO CONFIRM | Yes | TO-24-GRO-T122-01 | Yes | N/A | No Change | No | N/A | No Change
GARROW T122 | CZ1 | 110kV SF6 Cubicle Operational Test | 901396741 | Yes | TO-24-GRO-T122-01 | Yes | N/A | No Change | No | N/A | No Change
GARVAGH T121 | GH1, GH2 | P3 Protection maintenance of BOC (M1),7SA611,RET670,GRB100,7SJ804 |  | Yes | TO-24-GRV-T121-01 | Yes | N/A | No Change | No | N/A | No Change
GARVAGH T121 | GH1, GH2 | 110kV SF6 Cubicle Ordinary Service | 901396852 | Yes | TO-24-GRV-T121-01 | Yes | N/A | No Change | No | N/A | No Change
GARVAGH T121 | GH1, GH2 | 110KV CUBICLE CONDITION ASSESSMENT | 901396493 | Yes | TO-24-GRV-T121-01 | Yes | N/A | No Change | No | N/A | No Change
GARVAGH T121 | GH1, GH2 | Cable Insp. 110kV XLPE | ESBN TO CONFIRM | Yes | TO-24-GRV-T121-01 | Yes | N/A | No Change | No | N/A | No Change
GLANAGOW T2001 | WG1 | Cable Insp. 400 & 220kV Feeder XLPE | ESBN TO CONFIRM | Yes | TO-24-GGO-T2001-01 | Yes | N/A | No Change | No | N/A | No Change
GLENLARA KNOCKACUMMER | KC1 | Cable Insp. 110kV XLPE | ESBN TO CONFIRM | Yes | TO-24-GLE-KCR-1-01 | Yes | N/A | No Change | No | N/A | No Change
GLENLARA KNOCKACUMMER | KC1 | P3 Protection maintenance of 7SA612,GRL100 |  | Yes | TO-24-GLE-KCR-1-01 | Yes | N/A | No Change | No | N/A | No Change
GLENLARA KNOCKACUMMER | KC1 | P3 Protection maintenance of 7SA612, GRL100 |  | Yes | TO-24-GLE-KCR-1-01 | Yes | N/A | No Change | No | N/A | No Change
GORMAN T122 | GF1 | 110KV SF6 Cubicle Operational Test | 901432254 | Yes | TO-24-GOR-T122-01 | No | TAO resourcing | TAO | No | N/A | No Change
GREAT ISLAND GIS T2004 | GI4 | P3 Protection maintenance of 7SA612 |  | Yes | TO-24-GI GIS-T2004-02 | N/A | N/A | N/A | Yes | Not due in 2024 | TSO
GREAT ISLAND GIS T2004 | GI4 | 220kV GIS Cubicle Operational Test | ESBN TO CONFIRM | Yes | TO-24-GI GIS-T2004-02 | Yes | N/A | No Change | No | N/A | No Change
HUNTSTOWN T2002 | HN2 | Hotspot on R Phase DL/DE disconnect DUE: IMMEDIATE 3 month wait time on parts 12/04/2023 | 901385523 | Yes | TO-24-HN-T2002-01 | Yes | N/A | No Change | No | N/A | No Change
HUNTSTOWN T2002 | HN2 | RE-test CB | 901450455 | Yes | TO-24-HN-T2002-01 | Yes | N/A | No Change | No | N/A | No Change
HUNTSTOWN T2002 | HN2 | Cable Insp. 400 & 220kV Feeder XLPE | 901299975 | Yes | TO-24-HN-T2002-01 | No | TAO resourcing | TAO | No | N/A | No Change
HUNTSTOWN T2002 | HN2 | 220kV SF6 Cubicle Operational Test | ESBN TO CONFIRM | Yes | TO-24-HN-T2002-01 | Yes | N/A | No Change | No | N/A | No Change
HUNTSTOWN T2010/11 | HNC | Hotspot- DL/DE disconnect R phase Due- Immediate | 901348865 | Yes | TO-24-HN-T2010/11-02 | Yes | N/A | No Change | No | N/A | No Change
HUNTSTOWN T2010/11 | HNC | 220kV SF6 Cubicle Operational Test | ESBN TO CONFIRM | Yes | TO-24-HN-T2010/11-02 | No | TAO resourcing | TAO | No | N/A | No Change
IKERRIN tee SHANNONBRIDGE |  | Poleset replacement @38 | 901311071 | Yes | TO-24-IKE,T-SH-1-05 | No | DSO could not facilitate outage | Other | No | N/A | No Change
IKERRIN tee SHANNONBRIDGE |  | 1[219]Replace Pole Rot Confirmed (Drone) | 901324409 | Yes | TO-24-IKE,T-SH-1-05 | No | DSO could not facilitate outage | Other | No | N/A | No Change
IKERRIN tee SHANNONBRIDGE |  | 1[137]Replace Pole Rot Confirmed (Drone) | 901324406 | Yes | TO-24-IKE,T-SH-1-05 | No | DSO could not facilitate outage | Other | No | N/A | No Change
IKERRIN tee SHANNONBRIDGE |  | 2022HP-24[261-285]Danger Notices Replace | 901370781 | Yes | TO-24-IKE,T-SH-1-05 | No | DSO could not facilitate outage | Other | No | N/A | No Change
IKERRIN tee SHANNONBRIDGE |  | 2023HP-1[236]Bird Nests (Remove) | 901504230 | Yes | TO-24-IKE,T-SH-1-05 | No | DSO could not facilitate outage | Other | No | N/A | No Change
IKERRIN tee SHANNONBRIDGE |  | 2023HP-1[126]Check Structure (Top Rot)S2 | 901504231 | Yes | TO-24-IKE,T-SH-1-05 | No | DSO could not facilitate outage | Other | No | N/A | No Change
IKERRIN tee SHANNONBRIDGE |  | 2023HP-1[137]Check Structure (Top Rot)S2 | 901504232 | Yes | TO-24-IKE,T-SH-1-05 | No | DSO could not facilitate outage | Other | No | N/A | No Change
IKERRIN tee SHANNONBRIDGE |  | 2023HP-1[199]Check Structure (Top Rot)S2 | 901504233 | Yes | TO-24-IKE,T-SH-1-05 | No | DSO could not facilitate outage | Other | No | N/A | No Change
IKERRIN tee SHANNONBRIDGE |  | 2023HP-1[241]Check Structure (Top Rot)S2 | 901504235 | Yes | TO-24-IKE,T-SH-1-05 | No | DSO could not facilitate outage | Other | No | N/A | No Change
IKERRIN tee SHANNONBRIDGE |  | 2023HP-1[253]Check Structure (Top Rot)S2 | 901504236 | Yes | TO-24-IKE,T-SH-1-05 | No | DSO could not facilitate outage | Other | No | N/A | No Change
IKERRIN tee SHANNONBRIDGE |  | 2023HP-1[27]Check Structure (Top Rot)-S2 | 901504237 | Yes | TO-24-IKE,T-SH-1-05 | No | DSO could not facilitate outage | Other | No | N/A | No Change
IKERRIN tee SHANNONBRIDGE |  | 2023HP-1[37]Check Structure (Top Rot)-S2 | 901504238 | Yes | TO-24-IKE,T-SH-1-05 | No | DSO could not facilitate outage | Other | No | N/A | No Change
IKERRIN tee SHANNONBRIDGE |  | 2023HP-1[38]Check Structure (Top Rot)-S2 | 901504239 | Yes | TO-24-IKE,T-SH-1-05 | No | DSO could not facilitate outage | Other | No | N/A | No Change
IKERRIN tee SHANNONBRIDGE |  | 2023HP-1[57]Check Structure (Top Rot)-S2 | 901504240 | Yes | TO-24-IKE,T-SH-1-05 | No | DSO could not facilitate outage | Other | No | N/A | No Change
IKERRIN tee SHANNONBRIDGE |  | 2023HP-1[9]Check Structure (Top Rot)-S2 | 901504241 | Yes | TO-24-IKE,T-SH-1-05 | No | DSO could not facilitate outage | Other | No | N/A | No Change
IKERRIN tee SHANNONBRIDGE |  | 2023HP-1[17-18]Conflicts Shed underline | 901504242 | Yes | TO-24-IKE,T-SH-1-05 | No | DSO could not facilitate outage | Other | No | N/A | No Change
IKERRIN tee SHANNONBRIDGE |  | 2023HP-1[117]Stays-Replace (Bog Stays) | 901504246 | Yes | TO-24-IKE,T-SH-1-05 | No | DSO could not facilitate outage | Other | No | N/A | No Change
IKERRIN tee SHANNONBRIDGE |  | 2023HP-1[282]Check Structure (Top Rot)S2 | 901504252 | Yes | TO-24-IKE,T-SH-1-05 | No | DSO could not facilitate outage | Other | No | N/A | No Change
IKERRIN tee SHANNONBRIDGE |  | Replace bellows on T-phase CTVT | 901365415 | Yes | TO-24-IKE,T-SH-1-05 | No | DSO could not facilitate outage | Other | No | N/A | No Change
IKERRIN tee SHANNONBRIDGE |  | Replace surge counter on R-phase SA | 901365416 | Yes | TO-24-IKE,T-SH-1-05 | No | DSO could not facilitate outage | Other | No | N/A | No Change
IKERRIN tee SHANNONBRIDGE |  | Replace surge counter on T-phase SA | 901365417 | Yes | TO-24-IKE,T-SH-1-05 | No | DSO could not facilitate outage | Other | No | N/A | No Change
IKERRIN tee THURLES |  | Take Conductor Samples of 1962 430 ACSR. Take 3 samples at different spans along its route. | 901432133 | Yes | TO-24-IKE,T-THU-1-05 | No | MO cancelled | TAO | No | N/A | No Change
IKERRIN tee THURLES |  | 2019LP-1[291]Off Plumb - Pole | 901126159 | Yes | TO-24-IKE,T-THU-1-05 | No | DSO could not facilitate outage | Other | No | N/A | No Change
IKERRIN tee THURLES |  | 110kV MO Cubicle Operational Test | ESBN TO CONFIRM | Yes | TO-24-IKE,T-THU-1-05 | No | DSO could not facilitate outage | Other | No | N/A | No Change
INNISCARRA T101 | LE1, LE2 | 110KV SF6 Cubicle Operational Test | ESBN TO CONFIRM | Yes | TO-24-IA-T101-02 | Yes | N/A | No Change | No | N/A | No Change
IRISHTOWN T2001 | DB1 | Cable Insp. 400 & 220kV Feeder XLPE | 901280821 | Yes | TO-24-ISH-T2001-01 | No | TAO resourcing | TAO | No | N/A | No Change
IRISHTOWN T2001 | DB1 | 220kV GIS Cubicle Operational Test | 901300310 | Yes | TO-24-ISH-T2001-01 | Yes | N/A | No Change | No | N/A | No Change
KILCUMBER T131 | OE1 | 110kV SF6 Cubicle Operational Test | ESBN TO CONFIRM | Yes | TO-24-KIR-T131-01 | N/A | N/A | N/A | Yes | Not due in 2024 | TAO
KILL HILL T131 | KH1 | 110kV SF6 Cubicle Operational Test | ESBN TO CONFIRM | Yes | TO-24-KHL-T131-01 | No | TAO resourcing | TAO | No | N/A | No Change
KILTEEL T131 | PN1 | 110kV SF6 Cubicle Operational Test | 901397142 | Yes | TO-24-KTL-T131-01 | No | TAO resourcing | TAO | No | N/A | No Change
KNOCKALOUGH KNOCKRANNY | KU1 | Master Sub Remote Switch | 901343446 | Yes | TO-24-KLH-KNY-1-01 | No | TAO resourcing | TAO | No | N/A | No Change
KNOCKALOUGH KNOCKRANNY | KU1 | Surge Arrestor Counter Covers | 901343450 | Yes | TO-24-KLH-KNY-1-01 | No | TAO resourcing | TAO | No | N/A | No Change
KNOCKALOUGH KNOCKRANNY | KU1 | V.T Secondary fuse holders | 901343451 | Yes | TO-24-KLH-KNY-1-01 | No | TAO resourcing | TAO | No | N/A | No Change
KNOCKALOUGH KNOCKRANNY | KU1 | 110kV SF6 Cubicle Operational Test | 901396808 | Yes | TO-24-KLH-KNY-1-01 | No | TAO resourcing | TAO | No | N/A | No Change
KNOCKALOUGH KNOCKRANNY | KU1 | P3 Protection maintenance of 7SA612,GRL100 702D |  | Yes | TO-24-KLH-KNY-1-01 | No | P2 and P3 protection maintenance is opportunistic only | Other | No | N/A | No Change
KNOCKALOUGH KNOCKRANNY | KU1 | 110kV SF6 Cubicle Operational Test | 901396809 | Yes | TO-24-KLH-KNY-1-01 | No | TAO resourcing | TAO | No | N/A | No Change
KNOCKRANNY UGGOOL | SO1, UG1 | Cable Insp. 110kV XLPE | ESBN TO CONFIRM | Yes | TO-24-KNY-UGL-1-01 | No | TAO resourcing | TAO | No | N/A | No Change
KNOCKRANNY UGGOOL | SO1, UG1 | 110kV GIS Cubicle Operational Test | ESBN TO CONFIRM | Yes | TO-24-KNY-UGL-1-01 | No | TAO resourcing | TAO | No | N/A | No Change
KNOCKRANNY UGGOOL | SO1, UG1 | 110kV GIS Cubicle Operational Test | ESBN TO CONFIRM | Yes | TO-24-KNY-UGL-1-01 | No | TAO resourcing | TAO | No | N/A | No Change
LISDRUM T131 | LF1 | 110KV SF6 Cubicle Operational Test | 901348591 | Yes | TO-24-LIS-T131-01 | No | TAO resourcing | TAO | No | N/A | No Change
LISHEEN 110SA2-4 |  | 110kV Sect / Dist Ordinary Service (including busbar disconnects of all bays that are connected to the busbar section that is on outage) | ESBN TO CONFIRM | Yes | TO-24-LSN-110SA2-4-03 | Yes | N/A | No Change | No | N/A | No Change
LISHEEN 110SA2-4 |  | 110kV Sect / Dist Ordinary Service (including busbar disconnects of all bays that are connected to the busbar section that is on outage) | ESBN TO CONFIRM | Yes | TO-24-LSN-110SA2-4-03 | Yes | N/A | No Change | No | N/A | No Change
LISHEEN T122 | LS1, LS2 | 110kV SF6 Cubicle Ordinary Service (excludes busbar disconnects) | ESBN TO CONFIRM | Yes | TO-24-LSN-T122-03 | No | TAO resourcing | TAO | No | N/A | No Change
LISHEEN THURLES | LS1, LS2, LS3 | 110kV SF6 Cubicle Ordinary Service (excludes busbar disconnects) | ESBN TO CONFIRM | Yes | TO-24-LSN-THU-1-03 | Yes | N/A | No Change | No | N/A | No Change
LISHEEN THURLES | LS1, LS2, LS3 | 110kV MO Cubicle Ordinary Service (excludes busbar disconnects) | ESBN TO CONFIRM | Yes | TO-24-LSN-THU-1-03 | Yes | N/A | No Change | No | N/A | No Change
LISHEEN THURLES | LS1, LS2, LS3 | 110KV Cubicle Condition Assessment (excludes busbar disconnects) | ESBN TO CONFIRM | Yes | TO-24-LSN-THU-1-03 | Yes | N/A | No Change | No | N/A | No Change
LONG POINT T2002 | AD2 | 220kV SF6 Cubicle Operational Test | 901397021 | Yes | TO-24-LPT-T2002-02 | No | TAO resourcing | TAO | No | N/A | No Change
MONEYPOINT GIS T121 | MP9 | 110KV GIS Cubicle Operational Test | ESBN TO CONFIRM | Yes | TO-24-MP GIS-T121-02 | N/A | N/A | N/A | Yes | Not due in 2024 | TAO
MONEYPOINT GIS T121 | MP9 | 2023PM_Retest follow corr. Work; OD1 Day | 901452318 | Yes | TO-24-MP GIS-T121-02 | Yes | N/A | No Change | No | N/A | No Change
MONEYPOINT GIS T121 | MP9 | 2023PM_Clean cable SO Ins @ T121; OD1Day | 901452500 | Yes | TO-24-MP GIS-T121-02 | Yes | N/A | No Change | No | N/A | No Change
MONEYPOINT GIS T4001 | MP1 | 400KV CUBICLE CONDITION ASSESSMENT | ESBN TO CONFIRM | Yes | TO-24-MP GIS-T4001-01 | Yes | N/A | No Change | No | N/A | No Change
MONEYPOINT GIS T4001 | MP1 | 400kV GIS Cubicle Ordinary Service | ESBN TO CONFIRM | Yes | TO-24-MP GIS-T4001-01 | Yes | N/A | No Change | No | N/A | No Change
MONEYPOINT GIS T4002 | MP2 | 400kV GIS Cubicle Ordinary Service | ESBN TO CONFIRM | Yes | TO-24-MP GIS-T4002-02 | Yes | N/A | No Change | No | N/A | No Change
MONEYPOINT GIS T4002 | MP2 | Cable Insp. 400 & 220kV Feeder XLPE | ESBN TO CONFIRM | Yes | TO-24-MP GIS-T4002-02 | N/A | N/A | N/A | Yes | Not due in 2024 | TAO
MONEYPOINT GIS T4003 | MP3 | Cable Insp. 400 & 220kV Feeder XLPE | ESBN TO CONFIRM | Yes | TO-24-MP GIS-T4003-02 | Yes | N/A | No Change | No | N/A | No Change
MOUNTLUCAS T121 | M01 | P3 Protection maintenance of BOC (M1),7SA612,SPS (M1) |  | Yes | TO-24-MLC-T121-02 | No | P2 and P3 protection maintenance is opportunistic only | Other | No | N/A | No Change
MOUNTLUCAS T121 | M01 | P1 Protection maintenance of 7SA612,BOC(M1),SPS(M1) |  | Yes | TO-24-MLC-T121-01 | No | P2 and P3 protection maintenance is opportunistic only | Other | No | N/A | No Change
MOUNTLUCAS T121 | M01 | 110kV SF6 Cubicle Operational Test | ESBN TO CONFIRM | Yes | TO-24-MLC-T121-01 | No | TAO resourcing | TAO | No | N/A | No Change
POLLAPHUCA T101 | LI1, LI2, LI4 | P2 Protection maintenance of 7SA511,7UT513,7SV512 |  | Yes | TO-24-PA-T101-04 | N/A | N/A | N/A | Yes | Not due in 2024 | TSO
POLLAPHUCA T101 | LI1, LI2, LI4 | 110kV MO Cubicle Ordinary Service | ESBN TO CONFIRM | Yes | TO-24-PA-T101-04 | No | TAO resourcing | TAO | No | N/A | No Change
RATRUSSAN T121 | BD1 | 110kV SF6 Cubicle Ordinary Service | 901300859 | Yes | TO-24-RRU-T121-05 | Yes | N/A | No Change | No | N/A | No Change
RATRUSSAN T121 | BD1 | O-Ring Replacement to prevent SF6 leaks | ESBN TO CONFIRM | Yes | TO-24-RRU-T121-05 | No | TAO resourcing | TAO | No | N/A | No Change
RATRUSSAN T122 | ML1 | 110kV SF6 Cubicle Ordinary Service | 901396364 | Yes | TO-24-RRU-T122-05 | Yes | N/A | No Change | No | N/A | No Change
RATRUSSAN T122 | ML1 | O-Ring Replacement to prevent SF6 leaks | ESBN TO CONFIRM | Yes | TO-24-RRU-T122-05 | No | TAO resourcing | TAO | No | N/A | No Change
REAMORE TRALEE | KM1 | 2023PM_Raise JB15 cham lid 100mm OD:3Day | 901452070 | Yes | TO-24-REM-TRL-1-01 | No | TAO resourcing | TAO | No | N/A | No Change
REAMORE TRALEE | KM1 | 2023PM_Mntr Leak Current JB1-2 OD:3 Day | 901452081 | Yes | TO-24-REM-TRL-1-01 | No | TAO resourcing | TAO | No | N/A | No Change
REAMORE TRALEE | KM1 | 2023PM_Mntr Leak Current JB2-3 OD:3 Day | 901452082 | Yes | TO-24-REM-TRL-1-01 | No | TAO resourcing | TAO | No | N/A | No Change
REAMORE TRALEE | KM1 | 2023PM_Mntr Leak Current JB3-6_OD 3 Days | 901452087 | Yes | TO-24-REM-TRL-1-01 | No | TAO resourcing | TAO | No | N/A | No Change
REAMORE TRALEE | KM1 | 2023PM_Mntr Leak Current JB6-9_OD 3 Days | 901452088 | Yes | TO-24-REM-TRL-1-01 | No | TAO resourcing | TAO | No | N/A | No Change
REAMORE TRALEE | KM1 | 2023PM_Mntr Leak Current JB9-12_OD 3 Day | 901452089 | Yes | TO-24-REM-TRL-1-01 | No | TAO resourcing | TAO | No | N/A | No Change
REAMORE TRALEE | KM1 | 2023PM_Mntr Leak Current JB12-15_OD 3Day | 901452090 | Yes | TO-24-REM-TRL-1-01 | No | TAO resourcing | TAO | No | N/A | No Change
REAMORE TRALEE | KM1 | 2023PM_Repl.JB18 LB-bad connect.-OD3days | 901452091 | Yes | TO-24-REM-TRL-1-01 | No | TAO resourcing | TAO | No | N/A | No Change
REAMORE TRALEE | KM1 | 2023PM_Replace JB01 LB bolts x6-OD 1 Day | 901452076 | Yes | TO-24-REM-TRL-1-01 | No | TAO resourcing | TAO | No | N/A | No Change
REAMORE TRALEE | KM1 | 2023PM_Install all LB # labels-OD 1 Day | 901452080 | Yes | TO-24-REM-TRL-1-01 | No | TAO resourcing | TAO | No | N/A | No Change
REAMORE TRALEE | KM1 | CB overhaul required. Pole radial seals. | 901445458 | Yes | TO-24-REM-TRL-1-01 | No | TAO resourcing | TAO | No | N/A | No Change
REAMORE TRALEE | KM1 | Comms fail alarm - replace relay. Replac | 901451461 | Yes | TO-24-REM-TRL-1-01 | Yes | N/A | No Change | No | N/A | No Change
REAMORE TRALEE | KM1 | P3 Protection maintenance of 7SA612,GRL100 |  | Yes | TO-24-REM-TRL-1-01 | Yes | N/A | No Change | No | N/A | No Change
REAMORE TRALEE | KM1 | Comms fail alarm on diff relay | 901450768 | Yes | TO-24-REM-TRL-1-01 | Yes | N/A | No Change | No | N/A | No Change
ROSSPILE T131 | R01 | Cable Insp. 110kV XLPE | ESBN TO CONFIRM | Yes | TO-24-ROP-T131-01 | N/A | N/A | N/A | Yes | Not due in 2024 | TAO
ROSSPILE T131 | R01 | 110kV SF6 Cubicle Operational Test | ESBN TO CONFIRM | Yes | TO-24-ROP-T131-01 | No | TAO resourcing | TAO | No | N/A | No Change
SEALROCK T104 | SK4 | 110KV SF6 Cubicle Operational Test | ESBN TO CONFIRM | Yes | TO-24-SK-T104-01 | No | TAO resourcing | TAO | No | N/A | No Change
SHELLYBANKS T2014 | PB14 | 220kV Sect / Dist Ordinary Service | ESBN TO CONFIRM | Yes | TO-24-SHL-T2014-01 | No | No generator outage to align works | TSO | No | N/A | No Change
SHELLYBANKS T2014 | PB14 | Cable Insp. 400 & 220kV Feeder XLPE | ESBN TO CONFIRM | Yes | TO-24-SHL-T2014-01 | No | No generator outage to align works | TSO | No | N/A | No Change
SHELLYBANKS T2014 | PB14 | P1 Protection maintenance of 7SA513 |  | Yes | TO-24-SHL-T2014-01 | No | No generator outage to align works | TSO | No | N/A | No Change
SHELLYBANKS T2014 | PB14 | 220kV Sect / Dist Operational Test | 901396980 | Yes | TO-24-SHL-T2014-01 | No | No generator outage to align works | TSO | No | N/A | No Change
SHELLYBANKS T2015 | PB15 | 220kV Sect / Dist Ordinary Service | 901130137 | Yes | TO-24-SHL-T2015-01 | No | TAO resourcing | TAO | No | N/A | No Change
SHELLYBANKS T2015 | PB15 | P2 Protection maintenance of 7SA513 |  | Yes | TO-24-SHL-T2015-01 | Yes | N/A | No Change | No | N/A | No Change
SHELLYBANKS T2015 | PB15 | Cable Insp. 400 & 220kV Feeder XLPE | 901281053 | Yes | TO-24-SHL-T2015-01 | No | TAO resourcing | TAO | No | N/A | No Change
SHELLYBANKS T2016 | PB16 | 220kV Sect / Dist Operational Test | 901042993 | Yes | TO-24-SHL-T2016-01 | No | TAO resourcing | TAO | No | N/A | No Change
SLIABH BAWN T132 | SB1 | P2 Protection maintenance of BOC (M1),7SA612 |  | Yes | TO-24-SLB-T132-02 | Yes | N/A | No Change | No | N/A | No Change
SLIEVECALLAN T121 | KD1 | P3 Protection maintenance of BOC (M1),7SA611,RET615,7SJ804 |  | Yes | TO-24-SLC-T121-02 | N/A | N/A | N/A | Yes | Not due in 2024 | TSO
SLIEVECALLAN T122 | RD1 | P3 Protection maintenance of BOC (M1),7SA611,RET615,7SJ804 |  | Yes | TO-24-SLC-T122-02 | N/A | N/A | N/A | Yes | Not due in 2024 | TSO
SRAHNAKILLY 110SA1 | OY2 | 110kV Sect / Dist Ordinary Service (including busbar disconnects of all bays that are connected to the busbar section that is on outage) | ESBN TO CONFIRM | Yes | TO-24-SKY-110SA1-02 | No | TAO resourcing | TAO | No | N/A | No Change
SRAHNAKILLY 110SA2 | OY2 | 110kV Sect / Dist Ordinary Service (including busbar disconnects of all bays that are connected to the busbar section that is on outage) | ESBN TO CONFIRM | Yes | TO-24-SKY-110SA2-02 | No | TAO resourcing | TAO | No | N/A | No Change
SRAHNAKILLY 110SA2 | OY2 | 110kV Sect / Dist Ordinary Service (including busbar disconnects of all bays that are connected to the busbar section that is on outage) | 901310005 | Yes | TO-24-SKY-110SA2-02 | Yes | N/A | No Change | No | N/A | No Change
SRAHNAKILLY T131 | OY1 | 110kV SF6 Cubicle Ordinary Service | ESBN TO CONFIRM | Yes | TO-24-SKY-T131-03 | No | TAO resourcing | TAO | No | N/A | No Change
SRAHNAKILLY T131 | OY1 | P3 Protection maintenance of BOC (M1),7SA611,RET630,7SJ804 |  | Yes | TO-24-SKY-T131-03 | Yes | N/A | No Change | No | N/A | No Change
STRATFORD tee CARLOW | LI1, LI2, LI4 | 110kV SF6 Cubicle Operational Test | ESBN TO CONFIRM | Yes | TO-24-STR,T-CLW-1-04 | No | TAO resourcing | TAO | No | N/A | No Change
STRATFORD tee CARLOW | LI1, LI2, LI4 | 1[169-170]Conductor Samp R or L Phase | 901472696 | Yes | TO-24-STR,T-CLW-1-04 | No | TAO resourcing | TAO | No | N/A | No Change
STRATFORD tee CARLOW | LI1, LI2, LI4 | 1[90-91]Conductor Sampling R or L Phase | 901472697 | Yes | TO-24-STR,T-CLW-1-04 | No | TAO resourcing | TAO | No | N/A | No Change
STRATFORD tee CARLOW | LI1, LI2, LI4 | 1[127-128]Conductor Sampling R or L Phas | 901472699 | Yes | TO-24-STR,T-CLW-1-04 | No | TAO resourcing | TAO | No | N/A | No Change
STRATFORD tee CARLOW | LI1, LI2, LI4 | 1[153-154]Conductor Sampling R or L Phas | 901472780 | Yes | TO-24-STR,T-CLW-1-04 | No | TAO resourcing | TAO | No | N/A | No Change
STRATFORD tee CARLOW | LI1, LI2, LI4 | 1[71-72]Conductor Sampling R or L Phase | 901472781 | Yes | TO-24-STR,T-CLW-1-04 | No | TAO resourcing | TAO | No | N/A | No Change
STRATFORD tee CARLOW | LI1, LI2, LI4 | 1[5-6]Conductor Sampling R or L Phase | 901472782 | Yes | TO-24-STR,T-CLW-1-04 | No | TAO resourcing | TAO | No | N/A | No Change
STRATFORD tee CARLOW | LI1, LI2, LI4 | 2023HP-1[94]Check Structure (Top Rot)S2 | 901500728 | Yes | TO-24-STR,T-CLW-1-04 | No | TAO resourcing | TAO | No | N/A | No Change
STRATFORD tee CARLOW | LI1, LI2, LI4 | 2023HP-1[160]Off Plumb (Poles) | 901500732 | Yes | TO-24-STR,T-CLW-1-04 | Yes | N/A | No Change | Yes | Duplicate work item, work previously completed | TSO
STRATFORD tee POLLAPHUCA | LI1, LI2, LI4 | 2019HP-1[13]Off Plumb -plumb poles | 901085001 | Yes | TO-24-STR,T-PA-1-04 | Yes | N/A | No Change | Yes | Duplicate work item, work previously completed | TSO
STRATFORD tee POLLAPHUCA | LI1, LI2, LI4 | 2023LP-1[14]Crossarm Treat/Replace | 901454006 | Yes | TO-24-STR,T-PA-1-04 | No | TAO resourcing | TAO | No | N/A | No Change
STRATFORD tee POLLAPHUCA | LI1, LI2, LI4 | 2023LP-1[11]Insulator (Re-Plumb) | 901454007 | Yes | TO-24-STR,T-PA-1-04 | No | TAO resourcing | TAO | No | N/A | No Change
STRATFORD tee POLLAPHUCA | LI1, LI2, LI4 | 2023LP-1[17]Insulator (Re-Plumb) | 901454008 | Yes | TO-24-STR,T-PA-1-04 | No | TAO resourcing | TAO | No | N/A | No Change
STRATFORD tee POLLAPHUCA | LI1, LI2, LI4 | 2023LP-1[28]Insulator (Re-Plumb) | 901454009 | Yes | TO-24-STR,T-PA-1-04 | No | TAO resourcing | TAO | No | N/A | No Change
STRATFORD tee POLLAPHUCA | LI1, LI2, LI4 | 2023LP-1[34]Insulator (Re-Plumb) | 901454010 | Yes | TO-24-STR,T-PA-1-04 | No | TAO resourcing | TAO | No | N/A | No Change
STRATFORD tee POLLAPHUCA | LI1, LI2, LI4 | 2023LP-1[37]Insulator (Re-Plumb) | 901454011 | Yes | TO-24-STR,T-PA-1-04 | No | TAO resourcing | TAO | No | N/A | No Change
STRATFORD tee POLLAPHUCA | LI1, LI2, LI4 | 2023LP-1[41]Insulator (Re-Plumb) | 901454012 | Yes | TO-24-STR,T-PA-1-04 | No | TAO resourcing | TAO | No | N/A | No Change
STRATFORD tee POLLAPHUCA | LI1, LI2, LI4 | 2023LP-1[43]Insulator (Re-Plumb) | 901454013 | Yes | TO-24-STR,T-PA-1-04 | No | TAO resourcing | TAO | No | N/A | No Change
STRATFORD tee POLLAPHUCA | LI1, LI2, LI4 | 2023LP-1[49]Insulator (Re-Plumb) | 901454014 | Yes | TO-24-STR,T-PA-1-04 | No | TAO resourcing | TAO | No | N/A | No Change
STRATFORD tee POLLAPHUCA | LI1, LI2, LI4 | 2023LP-1[51]Insulator (Re-Plumb) | 901454015 | Yes | TO-24-STR,T-PA-1-04 | No | TAO resourcing | TAO | No | N/A | No Change
STRATFORD tee POLLAPHUCA | LI1, LI2, LI4 | 2023LP-1[57]Insulator (Re-Plumb) | 901454016 | Yes | TO-24-STR,T-PA-1-04 | No | TAO resourcing | TAO | No | N/A | No Change
STRATFORD tee POLLAPHUCA | LI1, LI2, LI4 | 2023LP-1[59]Insulator (Re-Plumb) | 901454017 | Yes | TO-24-STR,T-PA-1-04 | No | TAO resourcing | TAO | No | N/A | No Change
STRATFORD tee POLLAPHUCA | LI1, LI2, LI4 | 2023LP-1[61]Insulator (Re-Plumb) | 901454018 | Yes | TO-24-STR,T-PA-1-04 | No | TAO resourcing | TAO | No | N/A | No Change
STRATFORD tee POLLAPHUCA | LI1, LI2, LI4 | 2023LP-1[64]Insulator (Re-Plumb) | 901454019 | Yes | TO-24-STR,T-PA-1-04 | No | TAO resourcing | TAO | No | N/A | No Change
STRATFORD tee POLLAPHUCA | LI1, LI2, LI4 | 2023HP-1[49]Repl./Retire pole butts | 901504153 | Yes | TO-24-STR,T-PA-1-04 | No | TAO resourcing | TAO | No | N/A | No Change
STRATFORD tee POLLAPHUCA | LI1, LI2, LI4 | P1 Protection maintenance of 7SA511 |  | Yes | TO-24-STR,T-PA-1-04 | No | TAO resourcing | TAO | No | N/A | No Change
STRATFORD tee POLLAPHUCA | LI1, LI2, LI4 | 110kV MO Cubicle Operational Test | 901300349 | Yes | TO-24-STR,T-PA-1-04 | Yes | N/A | No Change | Yes | Duplicate work item, work previously completed | TSO
TAWNAGHMORE T1/T2 | TP1 | P1 Protection maintenance of 7SA611,BOC(M1) |  | Yes | TO-24-TAW-T1/T2-01 | Yes | N/A | No Change | No | N/A | No Change
TAWNAGHMORE T1/T2 | TP1 | 2023PM_Clean CSE SO Ins in Stn_OD 1Day | 901465088 | Yes | TO-24-TAW-T1/T2-01 | Yes | N/A | No Change | No | N/A | No Change
TAWNAGHMORE T1/T2 | TP1 | 2023PM_Repl S-Ph SVL @ Trafo End OD 1Day | 901465090 | Yes | TO-24-TAW-T1/T2-01 | Yes | N/A | No Change | No | N/A | No Change
TAWNAGHMORE T1/T2 | TP1 | 2023PM_Clean CSE SO Ins @ Trafo_OD 1 Day | 901465089 | Yes | TO-24-TAW-T1/T2-01 | Yes | N/A | No Change | No | N/A | No Change
TAWNAGHMORE T1/T2 | TP1 | 110kV SF6 Cubicle Operational Test | ESBN TO CONFIRM | Yes | TO-24-TAW-T1/T2-01 | Yes | N/A | No Change | No | N/A | No Change
TAWNAGHMORE T3 | TP3 | 110kV SF6 Cubicle Operational Test | ESBN TO CONFIRM | Yes | TO-24-TAW-T3-01 | Yes | N/A | No Change | No | N/A | No Change
TULLABRACK tee BOOLTIAGH |  | P1 Protection maintenance of 7SA612,GRZ100 |  | Yes | TO-24-TBK,T-BOL-1-01 | Yes | N/A | No Change | No | N/A | No Change
TULLABRACK tee BOOLTIAGH |  | 110kV SF6 Cubicle Operational Test | 901396731 | Yes | TO-24-TBK,T-BOL-1-01 | Yes | N/A | No Change | No | N/A | No Change
TULLABRACK tee BOOLTIAGH |  | Booltiagh Moneypoint Tullabrack Pro Main | 901469811 | Yes | TO-24-TBK,T-BOL-1-01 | Yes | N/A | No Change | No | N/A | No Change
TULLABRACK tee BOOLTIAGH |  | 2023HP-1[75]Check Structure (Top Rot)-S2 | 901500640 | Yes | TO-24-TBK,T-BOL-1-01 | Yes | N/A | No Change | No | N/A | No Change
TULLABRACK tee BOOLTIAGH |  | 2023HP-1[79]Check Structure (Top Rot)-S2 | 901500641 | Yes | TO-24-TBK,T-BOL-1-01 | Yes | N/A | No Change | No | N/A | No Change
TULLABRACK tee MONEYPOINT GIS |  | 2020LP-1[99]Off Plumb (4 Heads off) | 901168382 | Yes | TO-24-TBK,T-MP GIS-1-01 | Yes | N/A | No Change | No | N/A | No Change
TULLABRACK tee MONEYPOINT GIS |  | 2022HP-1[125]Off Plumb Plumb IMP Poleset | 901370581 | Yes | TO-24-TBK,T-MP GIS-1-01 | Yes | N/A | No Change | No | N/A | No Change
TULLABRACK tee MONEYPOINT GIS | TK1 | Annual Insp. 110kV Feeder XLPE Cable | ESBN TO CONFIRM | Yes | TO-24-TBK,T-MP GIS-1-01 | Yes | N/A | No Change | No | N/A | No Change
TULLABRACK tee MONEYPOINT GIS |  | 110kV GIS Cubicle Operational Test | ESBN TO CONFIRM | Yes | TO-24-TBK,T-MP GIS-1-01 | Yes | N/A | No Change | No | N/A | No Change
TULLABRACK tee MONEYPOINT GIS |  | P3 Protection maintenance of 7SA612, GRZ100 |  | Yes | TO-24-TBK,T-MP GIS-1-01 | Yes | N/A | No Change | No | N/A | No Change
TULLABRACK tee MONEYPOINT GIS |  | 2023HP-1[118]Check Structure (Top Rot)S2 | 901503849 | Yes | TO-24-TBK,T-MP GIS-1-01 | Yes | N/A | No Change | No | N/A | No Change
TURLOUGH HILL T2001/2 | TH1, TH2 | Annual Insp. 400 & 220 Station OF Cable | 901432315 | Yes | TO-24-TH-T2001/2-02 | Yes | N/A | No Change | No | N/A | No Change
TURLOUGH HILL T2003/4 | TH3, TH4 | P2 Protection maintenance of S,R1Z23b,RT22b |  | Yes | TO-24-TH-T2003/4-02 | Yes | N/A | No Change | No | N/A | No Change
TURLOUGH HILL T2003/4 | TH3, TH4 | Annual Insp. 400 & 220 Station OF Cable | 901432318 | Yes | TO-24-TH-T2003/4-02 | No | TAO resourcing | TAO | No | N/A | No Change
TYNAGH T2001/2 | TYC | 220kV SF6 Cubicle Operational Test | ESBN TO CONFIRM | Yes | TO-24-TY-T2001/2-02 | No | TAO resourcing | TAO | No | N/A | No Change
UGGOOL 110SA1-2CB | SO1 | 110kV GIS Cubicle Operational Test | ESBN TO CONFIRM | Yes | TO-24-UGL-110SA1-2CB-01 | No | TAO resourcing | TAO | No | N/A | No Change
UGGOOL T131 | UG1 | Cable Insp. 110kV XLPE | 901212057 | Yes | TO-24-UGL-T131-01 | Yes | N/A | No Change | No | N/A | No Change
UGGOOL T132 | UG1 | Cable Insp. 110kV XLPE | 901212058 | Yes | TO-24-UGL-T132-02 | Yes | N/A | No Change | No | N/A | No Change
UGGOOL T134 | UG1 | Cable Insp. 110kV XLPE | 901212059 | Yes | TO-24-UGL-T134-01 | Yes | N/A | No Change | No | N/A | No Change
WOODHOUSE T122 | WS1 | 110kV SF6 Cubicle Operational Test | ESBN TO CONFIRM | Yes | TO-24-WOH-T122-01 | Yes | N/A | No Change | No | N/A | No Change
CLOGHBOOLA TRIEN | CL1 | SF6 Leak Check | 901537928 | No | TO-24-CBA-TRI-1-01 | Yes | N/A | No Change | Yes | Works identified within year | TAO
CLOGHBOOLA TRIEN | CL1 | SF6 Leak Repair | 901537927 | No | TO-24-CBA-TRI-1-01 | Yes | N/A | No Change | Yes | Works identified within year | TAO
SEALROCK T103 | SK3 | Cable Insp. 110kV XLPE | 901542918 | No | TO-24-SK-T103-01 | Yes | N/A | No Change | Yes | Works identified within year | TAO
SEALROCK T103 | SK3 | 110KV SF6 Cubicle Operational Test | 901542475 | No | TO-24-SK-T103-01 | Yes | N/A | No Change | Yes | Works identified within year | TAO
SRAHNAKILLY 110SA2 | OY2 | 110kV Sect / Dist Ordinary Service (including busbar disconnects of all bays that are connected to the busbar section that is on outage) | 901542655 | No | TO-24-SKY-110SA2-01 | Yes | N/A | No Change | Yes | Works identified within year | TAO

## Charts 2 (hidden)
THESE NEED TO BE FIXED
Total Work Items | 127
Works Description Communicated Ex-Ante |  | Scheduled Works Not Completed | What is this?
TSO | #REF! | TSO | #REF!
TAO | #REF! | TAO | #REF!
GEN | #REF! | GEN | #REF!
No Change | #REF! | No Change | #REF!
Other | #REF! | Other | #REF!
N/A | #REF! | N/A | #REF!