## OACA Outage Tracker
General |  | Communicated in Ex-Ante Report | [5 empty] | Communicated M-1 | [7 empty] | Actual Outage |  | 1. Indicative Window (Actual - Ex-Ante) |  |  | 2. Indicative Duration (Actual - Ex-Ante) |  |  | 3. Scheduled Days |  |  | Actual Designated Days |  |  |  |  | 4. Designated Days
[9 empty] | Scheduled Dates |  | Designated Days
OACA | Unit(s) | Included in Ex-Ante Report? | TOP ID in the Ex-Ante Report | Outage Window | Start Date if Applicable | End Date if Applicable | Outage Duration (Workings) | Date of Communication | Scheduled Start | Scheduled End | Day 1 | Day 2 | Day 3 | Day4 | Day 5 | Actual Start Date | Actual End Date | Change to Window? | Reason for Change to Window, if applicable | Driver of Change to Window (e.g. TSO, TAO, Generator) | Change to Duration? | Reason for Change to Duration, if applicable | Driver of Change to Duration (e.g. TSO, TAO, Generator) | Change to Scheduled Dates communicated M-1? | Reason for Change to Scheduled Dates communicated M-1, if applicable | Driver of Change to Scheduled Dates communicated M-1 (e.g. TSO, TAO, GEN) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Change to Designateds communicated M-1? | Reason for change to Designateds communicated M-1, if applicable | Driver of Change to Designateds (e.g. TSO, TAO, GEN)
BALLYWATER CRANE | BW1 | Yes | TO-23-BWR-CRA-1-01 | Unscheduled | - | - | - | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BARRYMORE tee CAHIR | BF1 | Yes | TO-23-BAR,T-CAH-1-02 | Unscheduled | - | - | - | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BARRYMORE tee KNOCKRAHA | BF1 | Yes | TO-23-BAR,T-KRA-1-01 | Unscheduled | - | - | - | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
DRUMKEEN MEENTYCAT | MCT | Yes | TO-23-DRM-MEE-1-01 | Unscheduled | - | - | - | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
GLENLARA KNOCKACUMMER | KC1 | Yes | TO-23-GLE-KCR-1-01 | Unscheduled | - | - | - | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
IKERRIN tee SHANNONBRIDGE | MH1 | Yes | TO-23-IKE,T-SH-1-03 | Unscheduled | - | - | - | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
IKERRIN tee THURLES | MH1 | Yes | TO-23-IKE,T-THU-1-07 | Unscheduled | - | - | - | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MOUNTLUCAS T121 | MO1 | Yes | TO-23-MLC-T121-02 | Unscheduled | - | - | - | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
RATRUSSAN T121 | BD1 | Yes | TO-23-RRU-T121-02 | Unscheduled | - | - | - | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
RATRUSSAN T122 | ML1 | Yes | TO-23-RRU-T122-03 | Unscheduled | - | - | - | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SHELLYBANKS T2014 | PB14 | Yes | TO-23-SHL-T2014-02 | Unscheduled | - | - | 2 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SLIABH BAWN T132 | SB1 | Yes | TO-23-SLB-T132-02 | Unscheduled | - | - | - | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
TULLABRACK tee BOOLTIAGH | MMR1/TBK1/TK1 | Yes | TO-23-TBK,T-BOL-1-01 | Unscheduled | - | - | - | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
TULLABRACK tee MONEYPOINT GIS | MMR1/TBK1/TK1 | Yes | TO-23-TBK,T-MP GIS-1-01 | Unscheduled | - | - | - | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
TURLOUGH HILL T2003/4 | TH3/TH4 | Yes | TO-23-TH-T2003/4-01 | Unscheduled | - | - | - | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
REAMORE 110SA1 | KM1 | Yes | TO-23-REM-110SA1-02 | Unscheduled | - | - | - | 2023-05-19 | 2023-05-29 | 2023-06-02 | N/A | N/A | N/A | N/A | N/A | 2023-05-29 | 2023-06-02 | N/A | N/A | N/A | N/A | N/A | N/A | No | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
REAMORE 110SA2 | KM1 | Yes | TO-23-REM-110SA2-02 | Unscheduled | - | - | - | 2023-05-19 | 2023-05-29 | 2023-06-02 | N/A | N/A | N/A | N/A | N/A | 2023-05-29 | 2023-06-02 | N/A | N/A | N/A | N/A | N/A | N/A | No | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
REAMORE TRALEE | MU1/KM1 | Yes | TO-23-REM-TRL-1-02 | Unscheduled | - | - | - | 2023-05-19 | 2023-05-29 | 2023-06-02 | N/A | N/A | N/A | N/A | N/A | 2023-05-29 | 2023-06-02 | N/A | N/A | N/A | N/A | N/A | N/A | No | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CUSHALING KILCUMBER | OE1 | No | N/A | N/A | N/A | N/A | N/A | 2023-08-04 | 2023-08-15 | 2023-08-18 | 2023-08-15 | 2023-08-16 | 2023-08-17 | 2023-08-18 |  | 2023-08-15 | 2023-08-18 | N/A | N/A | N/A | N/A | N/A | N/A | No | N/A | N/A | 2023-08-15 | 2023-08-16 | 2023-08-17 | 2023-08-18 |  | No | N/A | N/A
KILCUMBER T131 | OE1 | No | N/A | N/A | N/A | N/A | N/A | 2023-08-04 | 2023-08-15 | 2023-08-18 | 2023-08-15 | 2023-08-16 | 2023-08-17 | 2023-08-18 |  | 2023-08-15 | 2023-08-18 | N/A | N/A | N/A | N/A | N/A | N/A | No | N/A | N/A | 2023-08-15 | 2023-08-16 | 2023-08-17 | 2023-08-18 |  | No | N/A | N/A
LODGEWOOD CASTLEDOCKRELL | CK1 | No | N/A | N/A | N/A | N/A | N/A | 2023-04-24 | 2023-04-26 | 2023-04-28 | 2023-04-26 | 2023-04-27 | 2023-04-28 |  |  | 2023-04-24 | 2023-04-28 | N/A | N/A | N/A | N/A | N/A | N/A | No | N/A | N/A | 2023-04-26 | 2023-04-27 | 2023-04-28 |  |  | No | N/A | N/A
TAWNAGHMORE T3 | TP3 | Yes | TO-23-TAW-T3-01 | Unscheduled | - | - | 2 | 2023-08-24 | 2023-09-01 | 2023-09-08 | 2023-09-01 | 2023-09-04 |  |  |  | 2023-09-01 | 2023-09-08 | N/A | N/A | N/A | Yes | Customer request | Generator | No | N/A | N/A | 2023-09-01 | 2023-09-04 |  |  |  | No | N/A | N/A
CLAHANE T122 | CL1/CL2 | No | N/A | N/A | N/A | N/A | N/A | 2023-04-05 | 2023-05-16 | 2023-05-17 | 2023-05-16 | 2023-05-17 |  |  |  | 2023-05-15 | 2023-05-18 | N/A | N/A | N/A | N/A | N/A | N/A | Yes | SF6 Leak found so outage extended for repairs | Other | 2023-05-15 | 2023-05-16 | 2023-05-17 | 2023-05-18 |  | Yes | SF6 Leak found so outage extended for repairs | Other
KILTEEL T131 | PN1 | Yes | TO-23-KTL-T131-02 | Unscheduled | - | - | - | 2023-08-30 | 2023-10-06 | 2023-10-06 | 2023-10-06 |  |  |  |  | 2023-10-06 | 2023-10-06 | N/A | N/A | N/A | N/A | N/A | N/A | Yes | TAO requested to cancel outage | TAO | [5 empty] | Yes | TAO requested to cancel outage | TAO
ATHEA 110SA1-2CB | XT1/XT2 | Yes | TO-23-ATE-110SA1-2CB-01 | Jun | - | - | 5 | 2023-05-19 | 2023-06-12 | 2023-06-16 | 2023-06-12 | 2023-06-13 | 2023-06-14 | 2023-06-15 | 2023-06-16 | 2023-06-12 | 2023-06-16 | No | N/A | N/A | N/A | N/A | N/A | No | N/A | N/A | 2023-06-12 | 2023-06-13 | 2023-06-14 | 2023-06-15 | 2023-06-16 | No | N/A | N/A
ATHEA DROMADA | DR1 | Yes | TO-23-ATE-DRO-1-01 | Jun | - | - | 5 | 2023-05-19 | 2023-06-12 | 2023-06-16 | 2023-06-12 | 2023-06-13 | 2023-06-14 | 2023-06-15 | 2023-06-16 | 2023-06-12 | 2023-06-16 | No | N/A | N/A | N/A | N/A | N/A | No | N/A | N/A | 2023-06-12 | 2023-06-13 | 2023-06-14 | 2023-06-15 | 2023-06-16 | No | N/A | N/A
ATHEA KNOCKANURE | AH1/DR1/XT1/XT2 | Yes | TO-23-ATE-KNR-1-01 | Jun | - | - | 5 | 2023-05-19 | 2023-06-12 | 2023-06-16 | 2023-06-12 | 2023-06-13 | 2023-06-14 | 2023-06-15 | 2023-06-16 | 2023-06-12 | 2023-06-16 | No | N/A | N/A | N/A | N/A | N/A | No | N/A | N/A | 2023-06-12 | 2023-06-13 | 2023-06-14 | 2023-06-15 | 2023-06-16 | No | N/A | N/A
ATHEA T121 | AH1 | Yes | TO-23-ATE-T121-01 | Jun | - | - | 5 | 2023-05-19 | 2023-06-12 | 2023-06-16 | 2023-06-12 | 2023-06-13 | 2023-06-14 | 2023-06-15 | 2023-06-16 | 2023-06-12 | 2023-06-16 | No | N/A | N/A | N/A | N/A | N/A | No | N/A | N/A | 2023-06-12 | 2023-06-13 | 2023-06-14 | 2023-06-15 | 2023-06-16 | No | N/A | N/A
ATHEA TOBERTOREEN | XT1/XT2 | Yes | TO-23-ATE-TOB-1-01 | Jun | - | - | 5 | 2023-05-19 | 2023-06-12 | 2023-06-16 | 2023-06-12 | 2023-06-13 | 2023-06-14 | 2023-06-15 | 2023-06-16 | 2023-06-12 | 2023-06-16 | No | N/A | N/A | No | N/A | N/A | No | N/A | N/A | 2023-06-12 | 2023-06-13 | 2023-06-14 | 2023-06-15 | 2023-06-16 | No | N/A | N/A
BOOLTIAGH T121 | BT1/BT2 | Yes | TO-23-BOL-T121-01 | Jun | - | - | 1 | 2023-05-30 | 2023-06-14 | 2023-06-14 | 2023-06-14 |  |  |  |  | 2023-06-14 | 2023-06-14 | No | N/A | N/A | No | N/A | N/A | No | N/A | N/A | 2023-06-14 |  |  |  |  | No | N/A | N/A
CLOGHBOOLA TRIEN | CL1, KI1, DA1, DS2, GC1 | Yes | TO-23-CBA-TRI-1-01 | Mar | 2023-03-13 | 2023-03-16 | 4 | 2023-03-08 | 2023-03-13 | 2023-03-16 | 2023-03-13 | 2023-03-14 | 2023-03-15 | 2023-03-16 |  | 2023-03-13 | 2023-03-16 | No | N/A | N/A | No | N/A | N/A | No | N/A | N/A | 2023-03-13 | 2023-03-14 | 2023-03-15 | 2023-03-16 |  | No | N/A | N/A
CORDUFF HUNTSTOWN | HN2 | Yes | TO-23-CDU-HN-1-01 | May-Jun | 2023-05-26 | 2023-06-10 | 16 | 2023-04-28 | 2023-05-26 | 2023-06-10 | 2023-05-26 | 2023-05-27 | 2023-05-28 | 2023-05-29 | 2023-05-30 | 2023-05-26 | 2023-06-10 | No | N/A | N/A | No | N/A | N/A | No | N/A | N/A | 2023-05-26 | 2023-05-27 | 2023-05-28 | 2023-05-29 | 2023-05-30 | No | N/A | N/A
CUSHALING T103/5 | ED3/ED5 | Yes | TO-23-CUS-T103/5-01 | Oct | - | - | 1 | 2023-08-30 | 2023-10-06 | 2023-10-06 | 2023-10-06 |  |  |  |  | 2023-10-06 | 2023-10-06 | No | N/A | N/A | No | N/A | N/A | No | N/A | N/A | 2023-10-06 |  |  |  |  | No | N/A | N/A
GORMAN T122 | GF1 | Yes | TO-23-GOR-T122-01 | May | 2023-05-10 | 2023-05-11 | 2 | 2023-04-06 | 2023-05-10 | 2023-05-11 | 2023-05-10 | 2023-05-11 |  |  |  | 2023-05-10 | 2023-05-11 | No | N/A | N/A | No | N/A | N/A | No | N/A | N/A | 2023-05-10 | 2023-05-11 |  |  |  | No | N/A | N/A
HUNTSTOWN T2002 | HN2 | Yes | TO-23-HN-T2002-01 | May-Jun | 2023-05-26 | 2023-06-10 | 16 | 2023-04-28 | 2023-05-26 | 2023-06-10 | 2023-05-26 | 2023-05-27 | 2023-05-28 | 2023-05-29 | 2023-05-30 | 2023-05-26 | 2023-06-10 | No | N/A | N/A | No | N/A | N/A | No | N/A | N/A | 2023-05-26 | 2023-05-27 | 2023-05-28 | 2023-05-29 | 2023-05-30 | No | N/A | N/A
MONEYPOINT GIS T121 | MP9 | Yes | TO-23-MP GIS-T121-01 | Jul | - | - | 5 | 2023-05-31 | 2023-07-17 | 2023-07-21 | 2023-07-17 | 2023-07-18 | 2023-07-19 | 2023-07-20 | 2023-07-21 | 2023-07-17 | 2023-07-21 | No | N/A | N/A | No | N/A | N/A | No | N/A | N/A | 2023-07-17 | 2023-07-18 | 2023-07-19 | 2023-07-20 | 2023-07-21 | No | N/A | N/A
MONEYPOINT GIS T4001 | MP1 | Yes | TO-23-MP GIS-T4001-01 | May | - | - | 2 | 2023-04-06 | 2023-05-22 | 2023-05-23 | 2023-05-22 | 2023-05-23 |  |  |  | 2023-05-22 | 2023-05-23 | No | N/A | N/A | No | N/A | N/A | No | N/A | N/A | 2023-05-22 | 2023-05-23 |  |  |  | No | N/A | N/A
MONEYPOINT GIS T4001 | MP1 | Yes | TO-23-MP GIS-T4001-02 | May | - | - | 1 | 2023-04-06 | 2023-05-22 | 2023-05-23 | 2023-05-22 | 2023-05-23 |  |  |  | 2023-05-22 | 2023-05-23 | No | N/A | N/A | No | N/A | N/A | No | N/A | N/A | 2023-05-22 | 2023-05-23 |  |  |  | No | N/A | N/A
MOUNTLUCAS T121 | MO1 | Yes | TO-23-MLC-T121-01 | May | - | - | 1 | 2023-04-05 | 2023-05-24 | 2023-05-24 | 2023-05-24 |  |  |  |  | 2023-05-24 | 2023-05-24 | No | N/A | N/A | No | N/A | N/A | No | N/A | N/A | 2023-05-24 |  |  |  |  | No | N/A | N/A
REAMORE TRALEE | MU1/KM1 | Yes | TO-23-REM-TRL-1-01 | Mar | 2023-03-20 | 2023-03-24 | 5 | 2023-03-08 | 2023-03-20 | 2023-03-24 | 2023-03-20 | 2023-03-21 | 2023-03-22 | 2023-03-23 | 2023-03-24 | 2023-03-20 | 2023-03-24 | No | N/A | N/A | No | N/A | N/A | No | N/A | N/A | 2023-03-20 | 2023-03-21 | 2023-03-22 | 2023-03-23 | 2023-03-24 | No | N/A | N/A
SEALROCK T104 | SK4 | Yes | TO-23-SK-T104-01 | Mar-Apr | 2023-03-20 | 2023-04-14 | 26 | 2023-03-20 | 2023-03-20 | 2023-04-14 | 2023-03-20 | 2023-03-21 | 2023-03-22 | 2023-03-23 | 2023-03-24 | 2023-03-20 | 2023-04-14 | No | N/A | N/A | No | N/A | N/A | No | N/A | N/A | 2023-03-20 | 2023-03-21 | 2023-03-22 | 2023-03-23 | 2023-03-24 | No | N/A | N/A
SHELLYBANKS T2014 | PB14 | Yes | TO-23-SHL-T2014-01 | Sep | - | - | 1 | 2023-07-26 | 2023-09-06 | 2023-09-06 | 2023-09-06 |  |  |  |  | 2023-09-06 | 2023-09-06 | No | N/A | N/A | No | N/A | N/A | No | N/A | N/A | 2023-09-06 |  |  |  |  | No | N/A | N/A
SLIABH BAWN T132 | SB1 | Yes | TO-23-SLB-T132-01 | Jul | - | - | 2 | 2023-05-30 | 2023-07-04 | 2023-07-05 | 2023-07-04 |  |  |  |  | 2023-07-04 | 2023-07-05 | No | N/A | N/A | No | N/A | N/A | No | N/A | N/A | 2023-07-04 |  |  |  |  | No | N/A | N/A
TYNAGH T2001/2 | TYC | Yes | TO-23-TY-T2001/2-01 | Sep | - | - | 3 | 2023-07-25 | 2023-09-11 | 2023-09-13 | 2023-09-11 | 2023-09-12 | 2023-09-13 |  |  | 2023-09-11 | 2023-09-13 | No | N/A | N/A | No | N/A | N/A | No | N/A | N/A | 2023-09-11 | 2023-09-12 | 2023-09-13 |  |  | No | N/A | N/A
CLIFF T101 | ER1 | Yes | TO-23-CL-T101-01 | Sep | - | - | 2 | 2023-08-17 | 2023-09-04 | 2023-09-08 | 2023-09-04 | 2023-09-05 |  |  |  | 2023-09-04 | 2023-09-08 | No | N/A | N/A | Yes | Customer request | Generator | No | N/A | N/A | 2023-09-04 | 2023-09-05 |  |  |  | No | N/A | N/A
FINGLAS HUNTSTOWN | HNC | Yes | TO-23-FIN-HN-1-01 | Mar-Apr | 2023-03-24 | 2023-04-09 | 17 | 2023-03-21 | 2023-03-25 | 2023-03-07 | 2023-03-25 | 2023-03-26 | 2023-03-27 | 2023-03-28 | 2023-03-29 | 2023-03-24 | 2023-04-06 | No | N/A | N/A | Yes | Customer request | Generator | No | N/A | N/A | 2023-03-25 | 2023-03-26 | 2023-03-27 | 2023-03-28 | 2023-03-29 | No | N/A | N/A
HUNTSTOWN T2010/11 | HNC | Yes | TO-23-HN-T2010/11-01 | Mar-Apr | 2023-03-24 | 2023-04-09 | 17 | 2023-03-21 | 2023-03-25 | 2023-03-07 | 2023-03-25 | 2023-03-26 | 2023-03-27 | 2023-03-28 | 2023-03-29 | 2023-03-24 | 2023-04-06 | No | N/A | N/A | Yes | Customer request | Generator | No | N/A | N/A | 2023-03-25 | 2023-03-26 | 2023-03-27 | 2023-03-28 | 2023-03-29 | No | N/A | N/A
KILL HILL T131 | KH1 | Yes | TO-23-KHL-T131-01 | Jun | - | - | 1 | 2023-05-19 | 2023-06-27 | 2023-06-29 | 2023-06-27 |  |  |  |  | 2023-06-27 | 2023-06-29 | No | N/A | N/A | Yes | Customer request | Generator | No | N/A | N/A | 2023-06-27 |  |  |  |  | No | N/A | N/A
SEALROCK T103 | SK3 | Yes | TO-23-SK-T103-01 | Jun-Jul | - | - | 14 | 2023-06-16 | 2023-06-19 | 2023-07-10 | 2023-06-19 | 2023-06-20 | 2023-06-21 | 2023-06-22 | 2023-06-23 | 2023-06-19 | 2023-07-10 | No | N/A | N/A | Yes | Aligned with generator outage | Generator | No | N/A | N/A | 2023-06-19 | 2023-06-20 | 2023-06-21 | 2023-06-22 | 2023-06-23 | No | N/A | N/A
CLONKEEN COOMAGEARLAHY | CG1/CG2/CG3/GL1 | Yes | TO-23-CKN-CGL-1-01 | Aug | - | - | 7 | 2023-08-04 | 2023-08-21 | 2023-08-31 | 2023-08-21 | 2023-08-22 | 2023-08-23 | 2023-08-24 | 2023-08-25 | 2023-08-21 | 2023-08-31 | No | N/A | N/A | Yes | Extension requested by TAO | TAO | No | N/A | N/A | 2023-08-21 | 2023-08-22 | 2023-08-23 | 2023-08-24 | 2023-08-25 | No | N/A | N/A
COOMAGEARLAHY GLANLEE | GL1 | Yes | TO-23-CGL-GAE-1-01 | Aug | - | - | 7 | 2023-08-04 | 2023-08-21 | 2023-08-31 | 2023-08-21 | 2023-08-22 | 2023-08-23 | 2023-08-24 | 2023-08-25 | 2023-08-21 | 2023-08-31 | No | N/A | N/A | Yes | Extension requested by TAO | TAO | No | N/A | N/A | 2023-08-21 | 2023-08-22 | 2023-08-23 | 2023-08-24 | 2023-08-25 | No | N/A | N/A
COOMAGEARLAHY T121 | CG3 | Yes | TO-23-CGL-T121-01 | Aug | - | - | 7 | 2023-08-04 | 2023-08-21 | 2023-08-31 | 2023-08-21 | 2023-08-22 | 2023-08-23 | 2023-08-24 | 2023-08-25 | 2023-08-21 | 2023-08-31 | No | N/A | N/A | Yes | Extension requested by TAO | TAO | No | N/A | N/A | 2023-08-21 | 2023-08-22 | 2023-08-23 | 2023-08-24 | 2023-08-25 | No | N/A | N/A
BALLYVOUSKILL COOMATAGGART | GD1, YT1 | Yes | TO-23-BVK-COT-1-02 | Aug | - | - | 5 | 2023-07-14 | 2023-08-08 | 2023-08-18 | 2023-08-08 | 2023-08-09 | 2023-08-10 | 2023-08-11 | 2023-08-12 | 2023-08-08 | 2023-08-18 | No | N/A | N/A | Yes | Duration driven by CAPEX works | TSO | No | N/A | N/A | 2023-08-08 | 2023-08-09 | 2023-08-10 | 2023-08-11 | 2023-08-12 | No | N/A | N/A
CLONIFFEEN SHANNONBRIDGE | SI1/SI2 | Yes | TO-23-CFN-SH-1-02 | May | 2023-05-02 | 2023-05-02 | 1 | 2023-04-20 | 2023-05-02 | 2023-05-29 | 2023-05-02 |  |  |  |  | 2023-05-02 | 2023-05-29 | No | N/A | N/A | Yes | Duration driven by CAPEX works | TSO | No | N/A | N/A | 2023-05-02 |  |  |  |  | No | N/A | N/A
COOMATAGGART 110SA1 | YT1 | Yes | TO-23-COT-110SA1-02 | Aug | - | - | 5 | 2023-07-14 | 2023-08-08 | 2023-08-18 | 2023-08-08 | 2023-08-09 | 2023-08-10 | 2023-08-11 | 2023-08-12 | 2023-08-08 | 2023-08-18 | No | N/A | N/A | Yes | Duration driven by CAPEX works | TSO | No | N/A | N/A | 2023-08-08 | 2023-08-09 | 2023-08-10 | 2023-08-11 | 2023-08-12 | No | N/A | N/A
COOMATAGGART 110SA2 | YT1 | Yes | TO-23-COT-110SA2-02 | Aug | - | - | 5 | 2023-07-14 | 2023-08-08 | 2023-08-18 | 2023-08-08 | 2023-08-09 | 2023-08-10 | 2023-08-11 | 2023-08-12 | 2023-08-08 | 2023-08-18 | No | N/A | N/A | Yes | Duration driven by CAPEX works | TSO | No | N/A | N/A | 2023-08-08 | 2023-08-09 | 2023-08-10 | 2023-08-11 | 2023-08-12 | No | N/A | N/A
TURLOUGH HILL T2001/2 | TH1/TH2 | Yes | TO-23-TH-T2001/2-01 | May | - | - | 3 | 2023-04-20 | 2023-05-03 | 2023-05-12 | 2023-05-03 | 2023-05-04 | 2023-05-05 |  |  | 2023-05-03 | 2023-05-18 | No | N/A | N/A | Yes | Customer request | Generator | Yes | Customer request | Generator | 2023-05-03 | 2023-05-04 | 2023-05-05 |  |  | No | N/A | N/A
CLOGHER MULREAVY | MB1/MB2 | Yes | TO-23-CLO-MRY-1-01 | Aug | - | - | 8 | 2023-08-04 | 2023-08-21 | 2023-08-25 | 2023-08-21 | 2023-08-22 | 2023-08-23 | 2023-08-24 |  | 2023-08-21 | 2023-08-24 | No | N/A | N/A | Yes | Assets not transferred so not all works could be completed | Other | Yes | Duration was driven by customer works which finished a day earlier | Generator | 2023-08-21 | 2023-08-22 | 2023-08-23 | 2023-08-24 |  | No | N/A | N/A
MULREAVY T131 | MB1/MB2 | Yes | TO-23-MRY-T131-01 | Aug | - | - | 8 | 2023-08-04 | 2023-08-21 | 2023-08-25 | 2023-08-21 | 2023-08-22 | 2023-08-23 | 2023-08-24 |  | 2023-08-21 | 2023-08-24 | No | N/A | N/A | Yes | Assets not transferred so not all works could be completed | Other | Yes | Duration was driven by customer works which finished a day earlier | Generator | 2023-08-21 | 2023-08-22 | 2023-08-23 | 2023-08-24 |  | No | N/A | N/A
BELLACORICK SRAHNAKILLY | OY1 | Yes | TO-23-BK-SKY-1-02 | Jun-Jul | - | - | 15 | 2023-05-23 | 2023-06-19 | 2023-07-07 | 2023-06-19 |  |  |  |  | 2023-06-19 | 2023-07-14 | No | N/A | N/A | Yes | Overlapping CAPEX works extended | TAO | Yes | Overlapping CAPEX works extended | TAO | 2023-06-19 |  |  |  |  | No | N/A | N/A
SRAHNAKILLY T131 | OY1 | Yes | TO-23-SKY-T131-02 | Jun-Jul | - | - | 15 | 2023-05-23 | 2023-06-19 | 2023-07-07 | 2023-06-19 |  |  |  |  | 2023-06-19 | 2023-07-14 | No | N/A | N/A | Yes | Overlapping CAPEX works extended | TAO | Yes | Overlapping CAPEX works extended | TAO | 2023-06-19 |  |  |  |  | No | N/A | N/A
GLANLEE T121 | GL1 | Yes | TO-23-GAE-T121-01 | Aug | - | - | 7 | 2023-08-04 | 2023-08-21 | 2023-08-29 | 2023-08-21 | 2023-08-22 | 2023-08-23 | 2023-08-24 | 2023-08-25 | 2023-08-21 | 2023-08-31 | No | N/A | N/A | Yes | Extension requested by TAO | TAO | Yes | To align with circuit outage that feeds station | TSO | 2023-08-21 | 2023-08-22 | 2023-08-23 | 2023-08-24 | 2023-08-25 | No | N/A | N/A
COOLNANOONAGH KILPADDOGE | KZ1/KZ3/KZ4 | Yes | TO-23-CNO-KPG-1-01 | Jul | - | - | 4 | 2023-06-22 | 2023-07-03 | 2023-07-06 | 2023-07-03 | 2023-07-04 | 2023-07-05 |  |  | 2023-07-03 | 2023-07-03 | No | N/A | N/A | Yes | Customer request | Generator | Yes | Customer request | Generator | 2023-07-03 |  |  |  |  | Yes | Customer request | Generator
KNOCKALOUGH KNOCKRANNY | KU1 | Yes | TO-23-KLH-KNY-1-01 | Jul | - | - | 3 | 2023-05-30 | 2023-07-26 | 2023-07-28 | 2023-07-26 | 2023-07-27 | 2023-07-28 |  |  | 2023-07-26 | 2023-07-26 | No | N/A | N/A | Yes | Customer request | Generator | Yes | Customer request | Generator | 2023-07-26 |  |  |  |  | Yes | Customer request | Generator
WOODHOUSE T122 | WS1 | Yes | TO-23-WOH-T122-01 | May | - | - | 8 | 2023-04-05 | 2023-05-06 | 2023-05-17 | 2023-05-06 | 2023-05-07 | 2023-05-08 | 2023-05-09 | 2023-05-10 | 2023-05-08 | 2023-05-22 | No | N/A | N/A | Yes | Customer request | Generator | Yes | Customer request | Generator | 2023-05-08 |  |  |  |  | Yes | Customer request | Generator
CORDERRY GARVAGH | GH1/GH2, DS1 | Yes | TO-23-CDY-GRV-1-01 | Jul | - | - | 6 | 2023-07-06 | 2023-07-17 | 2023-07-21 | 2023-07-17 | 2023-07-18 | 2023-07-19 | 2023-07-20 | 2023-07-21 | 2023-07-17 | 2023-07-20 | No | N/A | N/A | Yes | Customer request | Generator | Yes | Outage finished a day earlier | TAO | 2023-07-17 | 2023-07-18 | 2023-07-19 | 2023-07-20 |  | Yes | Outage finished a day earlier | TAO
GARVAGH T121 | GH1/GH2 | Yes | TO-23-GRV-T121-01 | Jul | - | - | 6 | 2023-07-06 | 2023-07-17 | 2023-07-21 | 2023-07-17 | 2023-07-18 | 2023-07-19 | 2023-07-20 | 2023-07-21 | 2023-07-17 | 2023-07-20 | No | N/A | N/A | Yes | Customer request | Generator | Yes | Outage finished a day earlier | TAO | 2023-07-17 | 2023-07-18 | 2023-07-19 | 2023-07-20 |  | Yes | Outage finished a day earlier | TAO
BALLYNAHULLA CORDAL | DL1/DL2/OG1/ST1/ST2 | Yes | TO-23-BYH-CDL-1-01 | Jun | - | - | 4 | 2023-06-09 | 2023-06-19 | 2023-06-23 | 2023-06-19 | 2023-06-20 | 2023-06-21 | 2023-06-22 | 2023-06-23 | 2023-06-20 | 2023-06-22 | No | N/A | N/A | Yes | TAO requested an increase to 5 days but outage completed in 3 days | TAO | Yes | TAO started a day late and completed outage in 3 days | TAO | 2023-06-20 | 2023-06-21 | 2023-06-22 |  |  | Yes | TAO started a day late and completed outage in 3 days | TAO
CLOGHBOOLA T131 | CL1 | Yes | TO-23-CBA-T131-01 | Mar | 2023-03-13 | 2023-03-22 | 10 | 2023-03-06 | 2023-03-13 | 2023-03-22 | 2023-03-13 | 2023-03-14 | 2023-03-15 | 2023-03-16 | 2023-03-17 | 2023-03-13 | 2023-03-16 | No | N/A | N/A | Yes | Some works had been completed in a previous outage | TAO | Yes | Some works had been completed in a previous outage | TAO | 2023-03-13 | 2023-03-14 | 2023-03-15 | 2023-03-16 |  | Yes | Some works had been completed in a previous outage | TAO
CORDAL T132 | DL1/DL2 | Yes | TO-23-CDL-T132-01 | Jun | - | - | 4 | 2023-06-09 | 2023-06-19 | 2023-06-23 | 2023-06-19 | 2023-06-20 | 2023-06-21 | 2023-06-22 | 2023-06-23 | 2023-06-19 | 2023-06-23 | No | N/A | N/A | Yes | TAO requested an increase to 5 days but outage completed in 3 days | TAO | Yes | TAO started a day late and completed outage in 3 days | TAO | 2023-06-20 | 2023-06-21 | 2023-06-22 |  |  | Yes | TAO started a day late and completed outage in 3 days | TAO
AGHADA LONG POINT | AD2 | Yes | TO-23-AD-LPT-1-01 | Oct | - | - | 2 |  | 2023-10-10 | 2023-10-16 | N/A | N/A | N/A | N/A | N/A | 2023-10-10 | 2023-10-16 | No | N/A | N/A | Yes | Additional maintenance items and to align with updated generator outage | Generator | No | N/A | N/A | 2023-10-10 | 2023-10-11 | N/A | N/A | N/A | Yes | No communication of designated days sent | TSO
LONG POINT T2002 | AD2 | Yes | TO-23-LPT-T2002-01 | Oct | - | - | 2 |  | 2023-10-10 | 2023-10-16 | N/A | N/A | N/A | N/A | N/A | 2023-10-10 | 2023-10-16 | No | N/A | N/A | Yes | Additional maintenance items and to align with updated generator outage | Generator | No | N/A | N/A | 2023-10-10 | 2023-10-11 | N/A | N/A | N/A | Yes | No communication of designated days sent | TSO
ARDNACRUSHA GIS T102 | AA2 | Yes | TO-23-AA GIS-T102-01 | Jun | - | - | 2 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | Yes | Works completed as part of customer requested outage | TAO | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
AGHADA ST101 | AD3 | Yes | TO-23-AD-ST101-01 | May | - | - | 7 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | Yes | Outage was aligned to generator outage. Generator cancelled outage and decision made not to proceed as low priority | Generator | Yes | Outage was aligned to generator outage. Generator cancelled outage and decision made not to proceed as low priority | Generator | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ARDNACRUSHA GIS T104 | AA4 | Yes | TO-23-AA GIS-T104-01 | May | - | - | 2 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | Yes | Aligned to long-term generator outage | Generator | Yes | Aligned to long-term generator outage | Generator | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ARDNACRUSHA GIS T104 | AA4 | Yes | TO-23-AA GIS-T104-02 | Unscheduled | - | - | 2 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | Yes | Aligned to long-term generator outage | Generator | Yes | Aligned to long-term generator outage | Generator | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SHELLYBANKS T2015 | PB15 | Yes | TO-23-SHL-T2015-01 | Oct | - | - | 5 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | Yes | Customer cancelled outage | Generator | Yes | Customer cancelled outage | Generator | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
GARBALLAGH T131 | NB1 | Yes | TO-23-GAR-T131-01 | Nov | - | - | 3 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | Yes | Outage not scheduled | TSO | Yes | Customer request to defer to 2024 | Generator | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CATHALEENS FALL CLIFF | ER1/ER2 | Yes | TO-23-CF-CL-1-01 | Sep | - | - | 3 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | Yes | Outage did not proceed as works low priority and generator outage that it was aligned with did not proceed | TSO | Yes | Outage cancelled as generator outage cancelled. Low priority works | Generator | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
DERRYCARNEY T132 | LU1/LU2 | Yes | TO-23-DEY-T132-01 | May | 2023-05-16 | 2023-05-17 | 2 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | Yes | Works not required | TSO | Yes | Works not required | TSO | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
GARROW 110SA1-2CB | CZ1 | Yes | TO-23-GRO-110SA1-2CB-01 | Aug | - | - | 4 | 2023-07-25 | 2023-09-04 | 2023-09-07 | 2023-09-04 | 2023-09-05 | 2023-09-06 | 2023-09-07 |  | 2023-09-04 | 2023-09-07 | Yes | TAO resourcing | TAO | No | N/A | N/A | No | N/A | N/A | 2023-09-04 | 2023-09-05 | 2023-09-06 | 2023-09-07 |  | No | N/A | N/A
GARROW T122 | CZ1 | Yes | TO-23-GRO-T122-01 | Aug | - | - | 4 | 2023-07-25 | 2023-09-04 | 2023-09-07 | 2023-09-04 | 2023-09-05 | 2023-09-06 | 2023-09-07 |  | 2023-09-04 | 2023-09-07 | Yes | TAO resourcing | TAO | No | N/A | N/A | No | N/A | N/A | 2023-09-04 | 2023-09-05 | 2023-09-06 | 2023-09-07 |  | No | N/A | N/A
CUSHALING T101 | ED1 | Yes | TO-23-CUS-T101-01 | Jul | - | - | 9 | 2023-07-14 | 2023-08-10 | 2023-08-18 | 2023-08-10 | 2023-08-11 | 2023-08-12 | 2023-08-13 | 2023-08-14 | 2023-08-10 | 2023-08-18 | Yes | To align with maintenance on Cushaling A2 | TSO | No | N/A | N/A | No | N/A | N/A | 2023-08-10 | 2023-08-11 | 2023-08-12 | 2023-08-13 | 2023-08-14 | No | N/A | N/A
ENNIS SLIEVECALLAN | KD1/RD1 | Yes | TO-23-ENN-SLC-1-01 | Jul | - | - | 10 | 2023-05-25 | 2023-06-12 | 2023-06-16 | 2023-06-12 | 2023-06-13 | 2023-06-14 | 2023-06-15 | 2023-06-16 | 2023-06-12 | 2023-06-16 | Yes | To align with planned outage of generator | TSO | No | N/A | N/A | No | N/A | N/A | 2023-06-12 | 2023-06-13 | 2023-06-14 | 2023-06-15 | 2023-06-16 | No | N/A | N/A
ARDNACRUSHA GIS T101 | AA1 | Yes | TO-23-AA GIS-T101-01 | May | - | - | 1 | 2023-08-17 | 2023-09-04 | 2023-09-08 | 2023-09-04 |  |  |  |  | 2023-09-04 | 2023-09-08 | Yes | Customer request | Generator | Yes | Customer request | Generator | No | N/A | N/A | 2023-09-04 |  |  |  |  | No | N/A | N/A
AUGHINISH SEALROCK 3 | SK3 | Yes | TO-23-AUG-SK-3-01 | Jun | - | - | 5 | 2023-06-16 | 2023-06-19 | 2023-07-10 | 2023-06-19 | 2023-06-20 | 2023-06-21 | 2023-06-22 | 2023-06-23 | 2023-06-19 | 2023-07-10 | Yes | Aligned with generator outage | Generator | Yes | Aligned with generator outage | Generator | No | N/A | N/A | 2023-06-19 | 2023-06-20 | 2023-06-21 | 2023-06-22 | 2023-06-23 | No | N/A | N/A
AUGHINISH SEALROCK 4 | SK4 | Yes | TO-23-AUG-SK-4-01 | Mar | 2023-03-20 | 2023-03-29 | 10 | 2023-03-20 | 2023-03-20 | 2023-04-14 | 2023-03-20 | 2023-03-21 | 2023-03-22 | 2023-03-23 | 2023-03-24 | 2023-03-20 | 2023-04-14 | Yes | Aligned with generator outage | Generator | Yes | Aligned with generator outage | Generator | No | N/A | N/A | 2023-03-20 | 2023-03-21 | 2023-03-22 | 2023-03-23 | 2023-03-24 | No | N/A | N/A
CATHALEENS FALL T103 | ER3 | Yes | TO-23-CF-T103-01 | Sep | - | - | 2 | 2023-05-19 | 2023-06-26 | 2023-06-30 | 2023-06-26 |  |  |  |  | 2023-06-26 | 2023-06-30 | Yes | Customer request | Generator | Yes | Customer request | Generator | No | N/A | N/A | 2023-06-26 |  |  |  |  | No | N/A | N/A
TAWNAGHMORE T1/T2 | TP1 | Yes | TO-23-TAW-T1/T2-01 | Sep | - | - | 4 | 2023-08-24 | 2023-08-25 | 2023-09-01 | 2023-08-25 | 2023-08-28 | 2023-08-29 | 2023-08-30 | 2023-08-31 | 2023-08-25 | 2023-09-01 | Yes | Outage moved for security of supply reasons | TSO | Yes | Customer request | Generator | No | N/A | N/A | 2023-08-25 | 2023-08-28 | 2023-08-29 | 2023-08-30 | 2023-08-31 | No | N/A | N/A
LISHEEN T122 | LS1/LS2 | Yes | TO-23-LSN-T122-06 | Oct | - | - | 1 | 2023-07-25 | 2023-08-29 | 2023-09-07 | 2023-08-29 | 2023-08-30 | 2023-08-31 | 2023-09-01 | 2023-09-02 | 2023-08-29 | 2023-09-07 | Yes | Aligned with CAPEX works | TSO | Yes | Extra maintenance added | TAO | No | N/A | N/A | 2023-08-29 | 2023-08-30 | 2023-08-31 | 2023-09-01 | 2023-09-02 | No | N/A | N/A
LISHEEN THURLES | LS1/LS2/BU1 | Yes | TO-23-LSN-T122-06 | Oct | - | - | 1 | 2023-08-18 | 2023-08-29 | 2023-09-07 | 2023-08-29 | 2023-08-30 | 2023-09-04 | 2023-09-05 | 2023-09-06 | 2023-08-29 | 2023-09-07 | Yes | Aligned with CAPEX works | TSO | Yes | Extra maintenance added | TAO | No | N/A | N/A | 2023-08-29 | 2023-08-30 | 2023-09-04 | 2023-09-05 | 2023-09-06 | No | N/A | N/A
COOMATAGGART T132 | GD1 | No | TO-23-COT-T132-03 | Unscheduled | - | - | - | 2023-07-14 | 2023-08-08 | 2023-08-18 | 2023-08-08 | 2023-08-09 | 2023-08-10 | 2023-08-11 | 2023-08-12 | 2023-08-08 | 2023-08-18 | Yes | Not in Ex-Ante Report | TSO | Yes | Not in Ex-Ante Report | TSO | No | N/A | N/A | 2023-08-08 | 2023-08-09 | 2023-08-10 | 2023-08-11 | 2023-08-12 | No | N/A | N/A
ARDNACRUSHA GIS T103 | AA3 | Yes | TO-23-AA GIS-T103-01 | Sep | - | - | 5 | 2023-06-12 | 2023-06-06 | 2023-06-23 | 2023-06-06 | 2023-06-07 | 2023-06-08 | 2023-06-09 | 2023-06-10 | 2023-06-06 | 2023-07-31 | Yes | Rescheduled to realign with generator outage change | Generator | Yes | Aligned with generator outage | Generator | Yes | Aligned with generator outage | Generator | 2023-06-06 | 2023-06-07 | 2023-06-08 | 2023-06-09 | 2023-06-10 | No | N/A | N/A
MONEYPOINT GIS T4002 | MP2 | Yes | TO-23-MP GIS-T4002-01 | May | - | - | 1 | 2023-04-06 | 2023-05-08 | 2023-05-08 | 2023-05-08 |  |  |  |  | 2023-05-08 | 2023-06-14 | Yes | Customer request | Generator | Yes | Customer request | Generator | Yes | Customer request | Generator | 2023-05-08 |  |  |  |  | No | N/A | N/A
GLANAGOW T2001 | WG1 | Yes | TO-23-GGO-T2001-01 | Sep | - | - | 5 | 2023-08-04 | 2023-08-18 | 2023-09-03 | 2023-08-18 | 2023-08-19 | 2023-08-20 | 2023-08-21 | 2023-08-22 | 2023-08-18 | 2023-09-08 | Yes | To accommodate OEM resourcing | Other | Yes | To accommodate OEM resourcing | Other | Yes | OEM delays | Other | 2023-08-18 | 2023-08-19 | 2023-08-20 | 2023-08-21 | 2023-08-22 | No | N/A | N/A
UGGOOL T131 | UG1 | Yes | TO-23-UGL-T131-01 | Jul-Aug | - | - | 5 | 2023-06-14 | 2023-07-17 | 2023-07-21 | 2023-07-17 | 2023-07-18 | 2023-07-19 | 2023-07-20 | 2023-07-21 | 2023-07-17 | 2023-07-20 | Yes | Customer request | Generator | No | N/A | N/A | Yes | Customer request | Generator | 2023-07-17 | 2023-07-18 | 2023-07-19 | 2023-07-20 | 2023-07-21 | Yes | Customer request | Generator
AGHADA T2011/12 | AT11/AT12 | Yes | TO-23-AD-T2011/12-01 | May-Jun | - | - | 3 | 2023-07-06 | 2023-07-17 | 2023-07-20 | 2023-07-17 | 2023-07-18 | 2023-07-19 | 2023-07-20 |  | 2023-07-17 | 2023-07-18 | Yes | Rescheduled to realign with generator outage change | Generator | Yes | Customer request | Generator | Yes | Customer request | Generator | 2023-07-17 | 2023-07-18 |  |  |  | Yes | Customer request | Generator
LISDRUM T131 | LF1 | Yes | TO-23-LIS-T131-01 | Mar | 2023-03-22 | 2023-03-24 | 3 | 2023-07-25 | 2023-09-25 | 2023-09-26 | 2023-09-25 |  |  |  |  | 2023-07-13 | 2023-12-31 | Yes | Customer request | Generator | Yes | Customer plant on forced outage | Generator | Yes | Customer plant on forced outage | Generator | N/A | N/A | N/A | N/A | N/A | Yes | Customer plant on forced outage | Generator
MONEYPOINT GIS T4003 | MP3 | Yes | TO-23-MP GIS-T4003-01 | Aug | - | - | 2 | N/A | 2023-08-09 | 2023-08-10 | N/A | N/A | N/A | N/A | N/A | 2023-09-25 | 2023-10-03 | Yes | Customer request | Generator | Yes | Customer request | Generator | Yes | Customer request | Generator | 2023-09-25 | 2023-09-26 |  |  |  | Yes | Customer request | Generator
POLLAPHUCA T101 | LI1/LI2/LI4 | Yes | TO-23-PA-T101-01 | Jun | - | - | 14 | 2023-05-19 | 2023-06-07 | 2023-06-23 | 2023-06-07 | 2023-06-08 | 2023-06-09 | 2023-06-10 | 2023-06-11 | 2023-06-08 | 2023-07-26 | Yes | Customer request | Generator | Yes | Customer request | Generator | Yes | Customer request | Generator | 2023-06-08 | 2023-06-09 | 2023-06-10 | 2023-06-11 | 2023-06-12 | Yes | Customer request | Generator
UGGOOL 110SA1-2CB | SO1 | Yes | TO-23-UGL-110SA1-2CB-01 | Jul-Aug | - | - | 5 | 2023-06-14 | 2023-07-10 | 2023-07-17 | 2023-07-10 | 2023-07-11 | 2023-07-12 | 2023-07-13 | 2023-07-14 | 2023-07-11 | 2023-07-17 | Yes | Customer request | Generator | YES | Customer request | Generator | Yes | Customer request | Generator | 2023-07-11 | 2023-07-12 | 2023-07-13 | 2023-07-14 | 2023-07-15 | Yes | Customer request | Generator
UGGOOL T132 | SO1 | Yes | TO-23-UGL-T132-01 | Jul-Aug | - | - | 5 | 2023-06-14 | 2023-07-10 | 2023-07-17 | 2023-07-10 | 2023-07-11 | 2023-07-12 | 2023-07-13 | 2023-07-14 | 2023-07-11 | 2023-07-17 | Yes | Customer request | Generator | YES | Customer request | Generator | Yes | Customer request | Generator | 2023-07-11 | 2023-07-12 | 2023-07-13 | 2023-07-14 | 2023-07-15 | Yes | Customer request | Generator
UGGOOL T134 | SO1 | Yes | TO-23-UGL-T134-01 | Jul-Aug | - | - | 5 | 2023-06-14 | 2023-07-10 | 2023-07-17 | 2023-07-10 | 2023-07-11 | 2023-07-12 | 2023-07-13 | 2023-07-14 | 2023-07-11 | 2023-07-17 | Yes | Customer request | Generator | YES | Customer request | Generator | Yes | Customer request | Generator | 2023-07-11 | 2023-07-12 | 2023-07-13 | 2023-07-14 | 2023-07-15 | Yes | Customer request | Generator
AGHADA T2014 | AT14 | Yes | TO-23-AD-T2014-01 | May | - | - | 6 | 2023-07-06 | 2023-07-24 | 2023-07-28 | 2023-07-24 | 2023-07-25 | 2023-07-26 | 2023-07-27 | 2023-07-28 | 2023-07-25 | 2023-07-28 | Yes | Aligned with generator outage change | Generator | Yes | Aligned with generator outage | Generator | Yes | Outage started a day late | Other | 2023-07-25 | 2023-07-26 | 2023-07-27 | 2023-07-28 |  | Yes | Outage started a day late | Other
BOGGERAGH CLASHAVOON | BG1/BG2 | Yes | TO-23-BGH-CLA-1-01 | May | - | - | 3 | 2023-04-05 | 2023-05-08 | 2023-05-12 | 2023-05-08 | 2023-05-09 | 2023-05-10 | 2023-05-11 | 2023-05-12 |  |  | Yes | Works completed during earlier forced outage | TSO | Yes | Works completed during earlier forced outage | Other | Yes | Works completed during earlier forced outage | Other | N/A | N/A | N/A | N/A | N/A | Yes | Works completed during earlier forced outage | Other
BOGGERAGH T121 | BG1 | Yes | TO-23-BGH-T121-01 | May | - | - | 3 | 2023-04-05 | 2023-05-08 | 2023-05-12 | 2023-05-08 | 2023-05-09 | 2023-05-10 | 2023-05-11 | 2023-05-12 |  |  | Yes | Works completed during earlier forced outage | TSO | Yes | Works completed during earlier forced outage | Other | Yes | Works completed during earlier forced outage | Other | N/A | N/A | N/A | N/A | N/A | Yes | Works completed during earlier forced outage | Other
BOGGERAGH T132 | BG2 | Yes | TO-23-BGH-T132-01 | May | - | - | 3 | 2023-04-05 | 2023-05-08 | 2023-05-12 | 2023-05-08 | 2023-05-09 | 2023-05-10 | 2023-05-11 | 2023-05-12 |  |  | Yes | Works completed during earlier forced outage | TSO | Yes | Works completed during earlier forced outage | Other | Yes | Works completed during earlier forced outage | Other | N/A | N/A | N/A | N/A | N/A | Yes | Works completed during earlier forced outage | Other
CARRIGDANGAN DUNMANWAY | XA1 | Yes | TO-23-CGG-DMY-1-01 | Jun | - | - | 4 | 2023-05-19 | 2023-06-19 | 2023-06-22 | 2023-06-19 | 2023-06-20 | 2023-06-21 | 2023-06-22 |  |  |  | Yes | Works completed during earlier forced outage | TSO | Yes | Works completed during earlier forced outage | Other | Yes | Works completed during earlier forced outage | Other | N/A | N/A | N/A | N/A | N/A | Yes | Works completed during earlier forced outage | Other
CATHALEENS FALL T104 | ER4 | Yes | TO-23-CF-T104-01 | Jun | - | - | 4 | 2023-04-25 | 2023-05-08 | 2023-05-17 | 2023-05-08 | 2023-05-09 | 2023-05-10 | 2023-05-11 | 2023-05-12 | 2023-05-08 | 2023-05-18 | Yes | Customer request | Generator | Yes | Customer request | Generator | Yes | Extended by a day by generator | Generator | [5 empty] | Yes | TAO unable to resource works | TAO
STRATFORD tee CARLOW | LI1/LI2/LI4 | Yes | TO-23-STR,T-CLW-1-01 | Jun | - | - | 14 | 2023-05-19 | 2023-06-07 | 2023-06-23 | 2023-06-07 | 2023-06-08 | 2023-06-09 | 2023-06-10 | 2023-06-11 | 2023-06-08 | 2023-06-27 | Yes | Customer request | Generator | Yes | Customer request | Generator | Yes | Customer request | Generator | 2023-06-08 | 2023-06-09 | 2023-06-10 | 2023-06-11 | 2023-06-12 | Yes | Outage delayed by a day due to special procedure for switching Stratford tee | TAO
KNOCKRANNY UGGOOL | SO1/UG1 | Yes | TO-23-KNY-UGL-1-01 | Jul-Aug | - | - | 5 | 2023-06-14 | 2023-07-10 | 2023-07-14 | 2023-07-10 | 2023-07-11 | 2023-07-12 | 2023-07-13 | 2023-07-14 |  |  | Yes | Works completed in previous year | TAO | Yes | Works completed in previous year | TAO | Yes | Works completed in previous year | TAO | [5 empty] | Yes | Works completed in previous year | TAO
DERRYIRON RHODE T1/T2 | RP1/RP2 | Yes | TO-23-DER-T1/T2-01 | Jul | - | - | 3 | 2023-06-30 | 2023-07-24 | 2023-08-04 | 2023-07-24 |  |  |  |  | 2023-07-25 | 2023-08-04 | Yes | Customer request | Generator | Yes | Customer request | Generator | Yes | Outage delayed by a day for security of supply reasons | TSO | 2023-07-25 |  |  |  |  | Yes | Outage delayed by a day for security of supply reasons | TSO

## OACA Work Item Tracker
General |  |  |  | Communicated in Ex-Ante Report |  | 7. Works not completed - To be provided by ESBN in Completions Report |  |  | 5. Works Description Communicated Ex-Ante
OACA | Unit(s) | Work Item Description | Work ID | Included in Ex-Ante Report? | TOP ID in the Ex-Ante Report | Works completed? | Reason for not completing, if applicable | Responsible | Change to Works Description Communicated Ex-Ante | Reason for Works Exclusion/Addition | Driver of Change to Works Description communicated Ex-Ante
CLOGHER MULREAVY | MB1/MB2 | 110kV GIS Cubicle Ordinary Service | 901300588 | Yes | TO-23-CLO-MRY-1-01 | N/A | N/A | N/A | Yes | Asset not yet transferred to TAO | Other
KNOCKALOUGH KNOCKRANNY | KU1 | Cable Insp. 110kV XLPE | ESBN TO CONFIRM | Yes | TO-23-KLH-KNY-1-01 | N/A | N/A | N/A | Yes | Asset not yet transferred to TAO | Other
UGGOOL 110SA1-2CB | SO1 | 110kV GIS Cubicle Operational Test | TBC | Yes | TO-23-UGL-110SA1-2CB-01 | N/A | N/A | N/A | Yes | Asset not yet transferred to TAO | Other
UGGOOL T131 | UG1 | Cable Insp. 110kV XLPE | 901212057 | Yes | TO-23-UGL-T131-01 | N/A | N/A | N/A | Yes | Asset not yet transferred to TAO | Other
UGGOOL T132 | SO1 | Cable Insp. 110kV XLPE | 901212058 | Yes | TO-23-UGL-T132-01 | N/A | N/A | N/A | Yes | Asset not yet transferred to TAO | Other
UGGOOL T134 | SO1 | Cable Insp. 110kV XLPE | 901212059 | Yes | TO-23-UGL-T134-01 | N/A | N/A | N/A | Yes | Asset not yet transferred to TAO | Other
CLOGHER MULREAVY | MB1/MB2 | Cable Insp. 110kV XLPE | 901129091 | Yes | TO-23-CLO-MRY-1-01 | N/A | N/A | N/A | Yes | Asset not yet transferred to TAO | Other
ENNIS SLIEVECALLAN | KD1/RD1 | Cable Insp. 110kV XLPE | 901212142 | Yes | TO-23-ENN-SLC-1-01 | N/A | N/A | N/A | Yes | Asset not yet transferred to TAO | Other
IKERRIN tee THURLES | MH1 | 2019LP-1[291]Off Plumb - Pole | 901126159 | Yes | TO-23-IKE,T-THU-1-07 | N/A | N/A | N/A | Yes | Not required | TAO
IKERRIN tee THURLES | MH1 | 2022HP-1[292]Off Plumb | 901370788 | Yes | TO-23-IKE,T-THU-1-07 | N/A | N/A | N/A | Yes | Not required | TAO
AUGHINISH SEALROCK 3 | SK3 | Cable Insp. 110kV XLPE | ESBN TO CONFIRM | Yes | TO-23-AUG-SK-3-01 | N/A | N/A | N/A | Yes | Not due in 2023 | TAO
AUGHINISH SEALROCK 4 | SK4 | Cable Insp. 110kV XLPE | ESBN TO CONFIRM | Yes | TO-23-AUG-SK-4-01 | N/A | N/A | N/A | Yes | Not due in 2023 | TAO
SEALROCK T103 | SK3 | Cable Insp. 110kV XLPE | ESBN TO CONFIRM | Yes | TO-23-SK-T103-01 | N/A | N/A | N/A | Yes | Not due in 2023 | TAO
ARDNACRUSHA GIS T103 | AA3 | Cable Insp. 110kV XLPE | 901212145 | Yes | TO-23-AA GIS-T103-02 | N/A | N/A | N/A | Yes | Completed in previous year | TAO
ARDNACRUSHA GIS T104 | AA4 | Cable Insp. 110kV XLPE | 901212146 | Yes | TO-23-AA GIS-T104-01 | N/A | N/A | N/A | Yes | Completed in previous year | TAO
HUNTSTOWN T2010/11 | HNC | Hotspoty on R phase DL/DE disconnect DUE IMMEDIATE | 901346940 | Yes | TO-23-HN-T2010/11-01 | N/A | N/A | N/A | Yes | Not Required | TAO
DERRYCARNEY T132 | LU1/LU2 | Cable Insp. 110kV XLPE | ESBN TO CONFIRM | Yes | TO-23-DEY-T132-01 | N/A | N/A | N/A | Yes | Not required. No cable asset associated with T132 | TSO
GLANLEE T121 | GL1 | 110KV CUBICLE CONDITION ASSESSMENT | 901396483 | Yes | TO-23-GAE-T121-01 | N/A | N/A | N/A | Yes | Not due in 2023 | TSO
COOLNANOONAGH KILPADDOGE | KZ1/KZ3/KZ4 | Inspect Densimeters on GIS Switchgear | 901396810 | Yes | TO-23-CNO-KPG-1-01 | N/A | N/A | N/A | Yes | Not required | TSO
COOMAGEARLAHY GLANLEE | GL1 | 110KV Cubicle Condition Assessment (excludes busbar disconnects) | 901396274 | Yes | TO-23-CGL-GAE-1-01 | N/A | N/A | N/A | Yes | Not due in 2023 | TSO
ENNIS SLIEVECALLAN | KD1/RD1 | 110KV Cubicle Condition Assessment (excludes busbar disconnects) | ESBN TO CONFIRM | Yes | TO-23-ENN-SLC-1-01 | N/A | N/A | N/A | Yes | Not due in 2023 | TSO
ENNIS SLIEVECALLAN | KD1/RD1 | 110KV Cubicle Condition Assessment (excludes busbar disconnects) | 901396308 | Yes | TO-23-ENN-SLC-1-01 | N/A | N/A | N/A | Yes | Not due in 2023 | TSO
GLANAGOW T2001 | WG1 | Cable Insp. 400 & 220kV Feeder XLPE | ESBN TO CONFIRM | Yes | TO-23-GGO-T2001-01 | N/A | N/A | N/A | Yes | Not due in 2023 | TSO
MONEYPOINT GIS T121 | MP9 | 110KV GIS Cubicle Operational Test | TBC | Yes | TO-23-GGO-T2001-01 | N/A | N/A | N/A | Yes | Not due in 2023 | TSO
SEALROCK T104 | SK4 | Cable Insp. 110kV XLPE | ESBN TO CONFIRM | Yes | TO-23-SK-T104-01 | N/A | N/A | N/A | Yes | Not due in 2023 | TSO
SEALROCK T103 | SK3 | 110KV SF6 Cubicle Operational Test | TBC | Yes | TO-23-SK-T103-01 | N/A | N/A | N/A | Yes | Not required as Ordinary Service completed | TSO
GARBALLAGH T131 | NB1 | Cable Insp. 110kV XLPE | ESBN TO CONFIRM | Yes | TO-23-GAR-T131-01 | No | Customer request to defer to 2024 | Generator | No | N/A | N/A
AGHADA ST101 | AD3 | O1-MO for Ordinary Service ST101 Cubicle | 901348642 | Yes | TO-23-AD-ST101-01 | No | Customer cancelled their outage. Low priority works | Generator | No | N/A | N/A
AGHADA ST101 | AD3 | 110kV SF6 Cubicle Ordinary Service (excludes busbar disconnects) | 901396366 | Yes | TO-23-AD-ST101-01 | No | Customer cancelled their outage. Low priority works | Generator | No | N/A | N/A
AGHADA ST101 | AD3 | 110KV Cubicle Condition Assessment (excludes busbar disconnects) | 901396292 | Yes | TO-23-AD-ST101-01 | No | Customer cancelled their outage. Low priority works | Generator | No | N/A | N/A
GARVAGH T121 | GH1/GH2 | 110kV SF6 Cubicle Ordinary Service | 901396852 | Yes | TO-23-GRV-T121-01 | No | Cancelled at request of customer | Generator | No | N/A | N/A
GARVAGH T121 | GH1/GH2 | 110KV CUBICLE CONDITION ASSESSMENT | 901396493 | Yes | TO-23-GRV-T121-01 | No | Cancelled at request of customer | Generator | No | N/A | N/A
LISDRUM T131 | LF1 | 110KV SF6 Cubicle Operational Test | 901348591 | Yes | TO-23-LIS-T131-01 | No | Generator on long-term forced outage | Generator | No | N/A | N/A
SHELLYBANKS T2015 | PB15 | 220kV Sect / Dist Ordinary Service | 901130137 | Yes | TO-23-SHL-T2015-01 | No | Customer requested change to planned ouatge | Generator | No | N/A | N/A
SHELLYBANKS T2015 | PB15 | Cable Insp. 400 & 220kV Feeder XLPE | 901005629 | Yes | TO-23-SHL-T2015-01 | No | Customer requested change to planned ouatge | Generator | No | N/A | N/A
AGHADA T2011/12 | AT11/AT12 | P3 Protection maintenance of 7SA612, RET670 |  | Yes | TO-23-AD-T2011/12-01 | No | P2 and P3 protection maintenance is opportunistic only | Other | No | N/A | N/A
AGHADA T2014 | AT14 | P3 Protection maintenance of 7SA612, RET650 |  | Yes | TO-23-AD-T2014-01 | No | P2 and P3 protection maintenance is opportunistic only | Other | No | N/A | N/A
COOLNANOONAGH KILPADDOGE | KZ1/KZ3/KZ4 | P3 Protection maintenance of 7SA611, RET670 |  | Yes | TO-23-CNO-KPG-1-01 | No | P2 and P3 protection maintenance is opportunistic only | Other | No | N/A | N/A
ENNIS SLIEVECALLAN | KD1/RD1 | P3 Protection maintenance of 7SA612, GRL100 |  | Yes | TO-23-ENN-SLC-1-01 | No | P2 and P3 protection maintenance is opportunistic only | Other | No | N/A | N/A
KNOCKALOUGH KNOCKRANNY | KU1 | P3 Protection maintenance of 7SA612, GRL100 |  | Yes | TO-23-KLH-KNY-1-01 | No | P2 and P3 protection maintenance is opportunistic only | Other | No | N/A | N/A
POLLAPHUCA T101 | LI1/LI2/LI4 | P2 Protection maintenance of 7SA511, 7UT513 |  | Yes | TO-23-PA-T101-01 | No | P2 and P3 protection maintenance is opportunistic only | Other | No | N/A | N/A
TAWNAGHMORE T1/T2 | TP1 | P2 Protection maintenance of 7SA612, BOC(M1) |  | Yes | TO-23-TAW-T1/T2-01 | No | P2 and P3 protection maintenance is opportunistic only | Other | No | N/A | N/A
TAWNAGHMORE T3 | TP3 | P2 Protection maintenance of 7SA612, BOC(M1) |  | Yes | TO-23-TAW-T3-01 | No | P2 and P3 protection maintenance is opportunistic only | Other | No | N/A | N/A
TYNAGH T2001/2 | TYC | P3 Protection maintenance of 7SA513 |  | Yes | TO-23-TY-T2001/2-01 | No | P2 and P3 protection maintenance is opportunistic only | Other | No | N/A | N/A
CATHALEENS FALL T104 | ER4 | P3 Protection maintenance of 7SA612, 7UT513 |  | Yes | TO-23-CF-T104-01 | No | P2 and P3 protection maintenance only to be scheduled if existing outage in excess of two days | Other | No | N/A | N/A
TULLABRACK tee BOOLTIAGH | MMR1/TBK1/TK1 | P2 Protection maintenance of 7SA612, GRZ100 |  | Yes | TO-23-TBK,T-BOL-1-01 | No | P2 and P3 protection maintenance only to be scheduled if existing outage in excess of two days | Other | No | N/A | N/A
ARDNACRUSHA GIS T104 | AA4 | P3 Protection maintenance of 7SA612, BOC(M1), 7UT513 |  | Yes | TO-23-AA GIS-T104-02 | No | P2 and P3 protection maintenance only to be scheduled if existing outage in excess of two days | Other | No | N/A | N/A
BALLYWATER CRANE | BW1 | P3 Protection maintenance of 7SA513, 7SD610 |  | Yes | TO-23-BWR-CRA-1-01 | No | P2 and P3 protection maintenance only to be scheduled if existing outage in excess of two days | Other | No | N/A | N/A
BARRYMORE tee CAHIR | BF1 | P3 Protection maintenance of 7SA511, REL521 |  | Yes | TO-23-BAR,T-CAH-1-02 | No | P2 and P3 protection maintenance only to be scheduled if existing outage in excess of two days | Other | No | N/A | N/A
BARRYMORE tee KNOCKRAHA | BF1 | P3 Protection maintenance of 7SA511, REL521 |  | Yes | TO-23-BAR,T-KRA-1-01 | No | P2 and P3 protection maintenance only to be scheduled if existing outage in excess of two days | Other | No | N/A | N/A
CATHALEENS FALL CLIFF | ER1/ER2 | P2 Protection maintenance of 7SA511 |  | Yes | TO-23-CF-CL-1-01 | No | P2 and P3 protection maintenance only to be scheduled if existing outage in excess of two days | Other | No | N/A | N/A
DRUMKEEN MEENTYCAT | MCT | P3 Protection maintenance of 7SA513 |  | Yes | TO-23-DRM-MEE-1-01 | No | P2 and P3 protection maintenance only to be scheduled if existing outage in excess of two days | Other | No | N/A | N/A
GLENLARA KNOCKACUMMER | KC1 | P3 Protection maintenance of 7SA612, GRl100 |  | Yes | TO-23-GLE-KCR-1-01 | No | P2 and P3 protection maintenance only to be scheduled if existing outage in excess of two days | Other | No | N/A | N/A
GLENLARA KNOCKACUMMER | KC1 | P3 Protection maintenance of 7SA612, GRL100 |  | Yes | TO-23-GLE-KCR-1-01 | No | P2 and P3 protection maintenance only to be scheduled if existing outage in excess of two days | Other | No | N/A | N/A
MOUNTLUCAS T121 | MO1 | P2 Protection maintenance of 7SA612 |  | Yes | TO-23-MLC-T121-02 | No | P2 and P3 protection maintenance only to be scheduled if existing outage in excess of two days | Other | No | N/A | N/A
SHELLYBANKS T2014 | PB14 | P3 Protection maintenance of 7SA513 |  | Yes | TO-23-SHL-T2014-02 | No | P2 and P3 protection maintenance only to be scheduled if existing outage in excess of two days | Other | No | N/A | N/A
SLIABH BAWN T132 | SB1 | P2 Protection maintenance of 7SA612 |  | Yes | TO-23-SLB-T132-02 | No | P2 and P3 protection maintenance only to be scheduled if existing outage in excess of two days | Other | No | N/A | N/A
TURLOUGH HILL T2003/4 | TH3/TH4 | P3 Protection maintenance of S relay, RT22b |  | Yes | TO-23-TH-T2003/4-01 | No | P2 and P3 protection maintenance only to be scheduled if existing outage in excess of two days | Other | No | N/A | N/A
IKERRIN tee THURLES | MH1 | 110kV MO Cubicle Operational Test | 901396580 | Yes | TO-23-IKE,T-THU-1-07 | No | TAO Resourcing | TAO | No | N/A | N/A
ATHEA T121 | AH1 | 110kV SF6 Cubicle Ordinary Service (excludes busbar disconnects) | 901396378 | Yes | TO-23-ATE-T121-01 | No | TAO Resourcing | TAO | No | N/A | N/A
ATHEA T121 | AH1 | 110KV Cubicle Condition Assessment (excludes busbar disconnects) | 901396303 | Yes | TO-23-ATE-T121-01 | No | TAO Resourcing | TAO | No | N/A | N/A
BALLYNAHULLA CORDAL | DL1/DL2 | Cable Insp. 400 & 220kV Feeder XLPE | 901413566 | Yes | TO-23-BYH-CDL-1-01 | No | TAO Resourcing | TAO | No | N/A | N/A
HUNTSTOWN T2002 | HN2 | Cable Insp. 400 & 220kV Feeder XLPE | 901280931 | Yes | TO-23-HN-T2002-01 | No | TAO Resourcing | TAO | No | N/A | N/A
SRAHNAKILLY T131 | OY1 | 110kV SF6 Cubicle Operational Test | 901300388 | Yes | TO-23-SKY-T131-02 | No | TAO Resourcing | TAO | No | N/A | N/A
BELLACORICK SRAHNAKILLY | OY1/OY2 | 110kV SF6 Cubicle Operational Test | 901300389 | Yes | TO-23-BK-SKY-1-02 | No | TAO Resourcing | TAO | No | N/A | N/A
CATHALEENS FALL T104 | ER4 | 110KV SF6 Cubicle Ordinary Service | 901396849 | Yes | TO-23-CF-T104-01 | No | TAO Resourcing | TAO | No | N/A | N/A
CATHALEENS FALL T104 | ER4 | 110KV CUBICLE CONDITION ASSESSMENT | 901396488 | Yes | TO-23-CF-T104-01 | No | TAO Resourcing | TAO | No | N/A | N/A
CATHALEENS FALL T104 | ER4 | T104 sf6 cb operational test cfalls | 901332346 | Yes | TO-23-CF-T104-01 | No | TAO Resourcing | TAO | No | N/A | N/A
MONEYPOINT GIS T4003 | MP3 | 400kV GIS Cubicle Operational Test | 901397058 | Yes | TO-23-MP GIS-T4003-01 | No | TAO Resourcing | TAO | No | N/A | N/A
AGHADA LONG POINT | AD2 | 220kV SF6 Cubicle Operational Test | 901396997 | Yes | TO-23-AD-LPT-1-01 | No | TAO Resourcing | TAO | No | N/A | N/A
AGHADA LONG POINT | AD2 | Cable Insp. 400 & 220kV Feeder XLPE | ESBN TO CONFIRM | Yes | TO-23-AD-LPT-1-01 | No | TAO Resourcing | TAO | No | N/A | N/A
AGHADA T2011/12 | AT11/AT12 | 2021PM_Monitor oil pressure levels withi | 901247447 | Yes | TO-23-AD-T2011/12-03 | No | TAO Resourcing | TAO | No | N/A | N/A
AGHADA T2011/12 | AT11/AT12 | 2022PM_Replacement of corroded earthing | 901302176 | Yes | TO-23-AD-T2011/12-04 | No | TAO Resourcing | TAO | No | N/A | N/A
AGHADA T2014 | AT14 | Clean CSE stand-off insulators in Aghada | 901167032 | Yes | TO-23-AD-T2014-05 | No | TAO Resourcing | TAO | No | N/A | N/A
AGHADA T2014 | AT14 | O1-Corrosion on CB Mech Box. | 901344954 | Yes | TO-23-AD-T2014-06 | No | TAO Resourcing | TAO | No | N/A | N/A
CATHALEENS FALL T103 | ER3 | 110KV SF6 Cubicle Operational Test | 901396750 | Yes | TO-23-CF-T103-01 | No | TAO Resourcing | TAO | No | N/A | N/A
CLIFF T101 | ER1 | Repair corrosion issue on CTs | 901230085 | Yes | TO-23-CL-T101-01 | No | TAO Resourcing | TAO | No | N/A | N/A
CLONIFFEEN SHANNONBRIDGE | SI1/SI2 | 220kV SF6 Cubicle Operational Test | 901397035 | Yes | TO-23-CFN-SH-1-02 | No | TAO Resourcing | TAO | No | N/A | N/A
COOLNANOONAGH KILPADDOGE | KZ1/KZ3/KZ4 | 110kV SF6 Cubicle Operational Test | 901396810 | Yes | TO-23-CNO-KPG-1-01 | No | TAO Resourcing | TAO | No | N/A | N/A
COOMAGEARLAHY GLANLEE | GL1 | 110kV SF6 Cubicle Ordinary Service (excludes busbar disconnects) | 901396332 | Yes | TO-23-CGL-GAE-1-01 | No | TAO Resourcing | TAO | No | N/A | N/A
COOMAGEARLAHY T121 | CG3 | Carry out loss of AC supply mod | 901323272 | Yes | TO-23-CGL-T121-01 | No | TAO Resourcing | TAO | No | N/A | N/A
CUSHALING T103/5 | ED3/ED5 | 110kV SF6 Cubicle Operational Test | 901396751 | Yes | TO-23-CUS-T103/5-01 | No | TAO Resourcing | TAO | No | N/A | N/A
DERRYIRON RHODE T1/T2 | RP1/RP2 | 60m[1-2]TimCut 110kV(Rural) | 901332399 | Yes | TO-23-DER-T1/T2-01 | No | TAO Resourcing | TAO | No | N/A | N/A
DERRYIRON RHODE T1/T2 | RP1/RP2 | 110KV SF6 Cubicle Operational Test | 901396752 | Yes | TO-23-DER-T1/T2-01 | No | TAO Resourcing | TAO | No | N/A | N/A
FINGLAS HUNTSTOWN | HNC | 220kV SF6 Cubicle Operational Test | 901397005 | Yes | TO-23-FIN-HN-1-01 | No | TAO Resourcing | TAO | No | N/A | N/A
GARROW 110SA1-2CB | CZ1 | 110kV SF6 Cubicle Ordinary Service (excludes busbar disconnects) | 901396370 | Yes | TO-23-GRO-110SA1-2CB-01 | No | TAO Resourcing | TAO | No | N/A | N/A
GARROW 110SA1-2CB | CZ1 | 110KV Cubicle Condition Assessment (excludes busbar disconnects) | 901396295 | Yes | TO-23-GRO-110SA1-2CB-01 | No | TAO Resourcing | TAO | No | N/A | N/A
GARROW 110SA1-2CB | CZ1 | 110kV Sect / Dist Ordinary Service (including busbar disconnects of all bays that are connected to the busbar section that is on outage) | 901396211 | Yes | TO-23-GRO-110SA1-2CB-01 | No | TAO Resourcing | TAO | No | N/A | N/A
GARROW T122 | CZ1 | 110kV SF6 Cubicle Operational Test | 901396741 | Yes | TO-23-GRO-T122-01 | No | TAO Resourcing | TAO | No | N/A | N/A
HUNTSTOWN T2010/11 | HNC | Hotspot- DL/DE disconnect R phase Due- Immediate | 901348865 | Yes | TO-23-HN-T2010/11-01 | No | TAO Resourcing | TAO | No | N/A | N/A
KILTEEL T131 | PN1 | 110kV SF6 Cubicle Operational Test | 901397142 | Yes | TO-23-KTL-T131-02 | No | TAO Resourcing | TAO | No | N/A | N/A
KNOCKALOUGH KNOCKRANNY | KU1 | Master Sub Remote Switch | 901343446 | Yes | TO-23-KLH-KNY-1-01 | No | TAO Resourcing | TAO | No | N/A | N/A
KNOCKALOUGH KNOCKRANNY | KU1 | Surge Arrestor Counter Covers | 901343450 | Yes | TO-23-KLH-KNY-1-01 | No | TAO Resourcing | TAO | No | N/A | N/A
KNOCKALOUGH KNOCKRANNY | KU1 | V.T Secondary fuse holders | 901343451 | Yes | TO-23-KLH-KNY-1-01 | No | TAO Resourcing | TAO | No | N/A | N/A
KNOCKALOUGH KNOCKRANNY | KU1 | 110kV SF6 Cubicle Operational Test | 901396808 | Yes | TO-23-KLH-KNY-1-01 | No | TAO Resourcing | TAO | No | N/A | N/A
KNOCKALOUGH KNOCKRANNY | KU1 | 110kV SF6 Cubicle Operational Test | 901396809 | Yes | TO-23-KLH-KNY-1-01 | No | TAO Resourcing | TAO | No | N/A | N/A
LONG POINT T2002 | AD2 | Cable Insp. 400 & 220kV Feeder XLPE | ESBN TO CONFIRM | Yes | TO-23-LPT-T2002-01 | No | TAO Resourcing | TAO | No | N/A | N/A
LONG POINT T2002 | AD2 | 220kV SF6 Cubicle Operational Test | 901397021 | Yes | TO-23-LPT-T2002-01 | No | TAO Resourcing | TAO | No | N/A | N/A
POLLAPHUCA T101 | LI1/LI2/LI4 | 110kV MO Cubicle Operational Test | 901396591 | Yes | TO-23-PA-T101-01 | No | TAO Resourcing | TAO | No | N/A | N/A
SHELLYBANKS T2014 | PB14 | 220kV Sect / Dist Operational Test | 901396980 | Yes | TO-23-SHL-T2014-01 | No | TAO Resourcing | TAO | No | N/A | N/A
TARBERT T2003 | TB3 | Retest R-phase 220 kV CT in 2023 | 901346097 | Yes | TO-23-TB-T2003-02 | No | TAO Resourcing | TAO | No | N/A | N/A
TULLABRACK tee MONEYPOINT GIS | MMR1/TBK1/TK1 | 2020LP-1[99]Off Plumb (4 Heads off) | 901168382 | Yes | TO-23-TBK,T-MP GIS-1-01 | No | TAO Resourcing | TAO | No | N/A | N/A
TULLABRACK tee MONEYPOINT GIS | MMR1/TBK1/TK1 | 2022HP-1[125]Off Plumb Plumb IMP Poleset | 901370581 | Yes | TO-23-TBK,T-MP GIS-1-01 | No | TAO Resourcing | TAO | No | N/A | N/A
TURLOUGH HILL T2001/2 | TH1/TH2 | Annual Insp. 400 & 220 Station OF Cable | 901432315 | Yes | TO-23-TH-T2001/2-01 | No | TAO Resourcing | TAO | No | N/A | N/A
GARROW 110SA1-2CB | CZ1 | 110kV Sect / Dist Ordinary Service (including busbar disconnects of all bays that are connected to the busbar section that is on outage) | 901396212 | Yes | TO-23-GRO-110SA1-2CB-01 | No | Deferred to 2024 to avoid high dispatch down of renewables due to concurrent outages in region | TSO | No | N/A | N/A
ATHEA KNOCKANURE | AH1/DR1/XT1/XT2 | 2022HP-1[31]Bird Nests | 901370202 | Yes | TO-23-ATE-KNR-1-01 | No | Bird nests can only be removed in the period from September to February inclusive. Chose to accommodate customer preference of mid-summer as low priority work item | TSO | No | N/A | N/A
TULLABRACK tee BOOLTIAGH | MMR1/TBK1/TK1 | 110kV SF6 Cubicle Operational Test | 901396731 | Yes | TO-23-TBK,T-BOL-1-01 | No | Low priority. Cancelled due to issue with TSO system | TSO | No | N/A | N/A
BARRYMORE tee CAHIR | BF1 | 2020HP-1[22-23]Air Craft Sphere Bird Div | 901170978 | Yes | TO-23-BAR,T-CAH-1-02 | No | Conflicts with higher priority work | TSO | No | N/A | N/A
BARRYMORE tee CAHIR | BF1 | 2022HP-1[120]Off Plumb (Re-plumb poles) | 901368960 | Yes | TO-23-BAR,T-CAH-1-02 | No | Conflicts with higher priority work | TSO | No | N/A | N/A
BARRYMORE tee CAHIR | BF1 | 2022HP-1[121]Off Plumb (Re-plumb poles) | 901368961 | Yes | TO-23-BAR,T-CAH-1-02 | No | Conflicts with higher priority work | TSO | No | N/A | N/A
BARRYMORE tee CAHIR | BF1 | 110kV SF6 Cubicle Ordinary Service (excludes busbar disconnects) | 901300801 | Yes | TO-23-BAR,T-CAH-1-02 | No | Conflicts with higher priority work | TSO | No | N/A | N/A
BARRYMORE tee KNOCKRAHA | BF1 | Replace Pole Set 227- Pole Rot | 901298981 | Yes | TO-23-BAR,T-KRA-1-01 | No | Conflicts with higher priority work | TSO | No | N/A | N/A
BARRYMORE tee KNOCKRAHA | BF1 | Replace Pole Set 236. -Rotten | 901298983 | Yes | TO-23-BAR,T-KRA-1-01 | No | Conflicts with higher priority work | TSO | No | N/A | N/A
BARRYMORE tee KNOCKRAHA | BF1 | Replace Pole No. 296. Rotten | 901298990 | Yes | TO-23-BAR,T-KRA-1-01 | No | Conflicts with higher priority work | TSO | No | N/A | N/A
BARRYMORE tee KNOCKRAHA | BF1 | HAZ CNF 40M (278-279) Tim Cut | 901217145 | Yes | TO-23-BAR,T-KRA-1-01 | No | Conflicts with higher priority work | TSO | No | N/A | N/A
BARRYMORE tee KNOCKRAHA | BF1 | 2021HP-1[332]Off Plumb | 901253795 | Yes | TO-23-BAR,T-KRA-1-01 | No | Conflicts with higher priority work | TSO | No | N/A | N/A
BARRYMORE tee KNOCKRAHA | BF1 | 110kV SF6 Cubicle Ordinary Service | 901396820 | Yes | TO-23-BAR,T-KRA-1-01 | No | Conflicts with higher priority work | TSO | No | N/A | N/A
BARRYMORE tee KNOCKRAHA | BF1 | 110KV CUBICLE CONDITION ASSESSMENT | 901396433 | Yes | TO-23-BAR,T-KRA-1-01 | No | Conflicts with higher priority work | TSO | No | N/A | N/A
BARRYMORE tee KNOCKRAHA | BF1 | 110kV SF6 Cubicle Operational Test | TBC | Yes | TO-23-BAR,T-KRA-1-01 | No | Conflicts with higher priority work | TSO | No | N/A | N/A
CATHALEENS FALL CLIFF | ER1/ER2 | H5 CB densimeter replacement. | 901335734 | Yes | TO-23-CF-CL-1-01 | No | Outage cancelled as generator outage cancelled. Low priority works | TSO | No | N/A | N/A
CATHALEENS FALL CLIFF | ER1/ER2 | 110kV SF6 Cubicle Operational Test | 901396673 | Yes | TO-23-CF-CL-1-01 | No | Outage cancelled as generator outage cancelled. Low priority works | TSO | No | N/A | N/A
IKERRIN tee SHANNONBRIDGE | MH1 | 2022HP-24[261-285]Danger Notices Replace | 901370781 | Yes | TO-23-IKE,T-SH-1-03 | No | Low priority. Conflicts with higher priority work | TSO | No | N/A | N/A
IKERRIN tee SHANNONBRIDGE | MH1 | Replace bellows on T-phase CTVT | 901365415 | Yes | TO-23-IKE,T-SH-1-03 | No | Low priority. Conflicts with higher priority work | TSO | No | N/A | N/A
IKERRIN tee SHANNONBRIDGE | MH1 | Replace surge counter on R-phase SA | 901365416 | Yes | TO-23-IKE,T-SH-1-03 | No | Low priority. Conflicts with higher priority work | TSO | No | N/A | N/A
IKERRIN tee SHANNONBRIDGE | MH1 | Replace surge counter on T-phase SA | 901365417 | Yes | TO-23-IKE,T-SH-1-03 | No | Low priority. Conflicts with higher priority work | TSO | No | N/A | N/A
RATRUSSAN T121 | BD1 | 110kV SF6 Cubicle Ordinary Service (excludes busbar disconnects) | 901300859 | Yes | TO-23-RRU-T121-02 | No | Full station outage required in Ratrussan due to issue with CTs. Low priority | TSO | No | N/A | N/A
RATRUSSAN T122 | ML1 | 110kV SF6 Cubicle Ordinary Service (excludes busbar disconnects) | 901396364 | Yes | TO-23-RRU-T122-03 | No | Full station outage required in Ratrussan due to issue with CTs. Low priority | TSO | No | N/A | N/A
CLOGHER MULREAVY | MB1/MB2 | P2 Protection maintenance of 7SA612, GRL100 |  | Yes | TO-23-CLO-MRY-1-01 | No | P2 and P3 protection maintenance only to be scheduled if existing outage in excess of two days | Other | No | N/A | N/A
CLOGHER MULREAVY | MB1/MB2 | P2 Protection maintenance of 7SA612, GRL100, 7SJ804 |  | Yes | TO-23-CLO-MRY-1-01 | No | P2 and P3 protection maintenance only to be scheduled if existing outage in excess of two days | Other | No | N/A | N/A
LISHEEN THURLES | LS1/LS2/LS3/BU1 | HOTSPOT. 2023IR[5]:4-5-Left/PH-Jump. 6 Months. Due: 24/08/2023 | 901406215 | No | TO-23-LSN-THU-1-07 | Yes | N/A | No Change | Yes | Works identified within year | TAO
LISHEEN THURLES | LS1/LS2/LS3/BU1 | HOTSPOT. 2023IR[R1]:22-23-Right/PH-Midspan. Next planned outage | 901406244 | No | TO-23-LSN-THU-1-07 | Yes | N/A | No Change | Yes | Works identified within year | TAO
LISHEEN THURLES | LS1/LS2/LS3/BU1 | HOTSPOT. 2023IR[C1]:22-23-Cen/PH-Midspan. Next planned outage | 901406245 | No | TO-23-LSN-THU-1-07 | Yes | N/A | No Change | Yes | Works identified within year | TAO
LISHEEN THURLES | LS1/LS2/LS3/BU1 | HOTSPOT. 2023IR[L1]:37-38-Left/PH-Midspan. 6 Months. Due: 12/08/2023. | 901406246 | No | TO-23-LSN-THU-1-07 | Yes | N/A | No Change | Yes | Works identified within year | TAO
LISHEEN THURLES | LS1/LS2/LS3/BU1 | HOTSPOT. 2023IR[38]:38-39-Right/PH-Deadend. Next planned outage. | 901406247 | No | TO-23-LSN-THU-1-07 | Yes | N/A | No Change | Yes | Works identified within year | TAO
LISHEEN THURLES | LS1/LS2/LS3/BU1 | HOTSPOT. 2023IR[38]:38-39-Left/PH-Deadend. Next planned outage. | 901406248 | No | TO-23-LSN-THU-1-07 | Yes | N/A | No Change | Yes | Works identified within year | TAO
LISHEEN THURLES | LS1/LS2/LS3/BU1 | HOTSPOT. 2023IR[L1]:39-40-Left/PH-Midspan. Next planned outage | 901406249 | No | TO-23-LSN-THU-1-07 | Yes | N/A | No Change | Yes | Works identified within year | TAO
LISHEEN THURLES | LS1/LS2/LS3/BU1 | HOTSPOT. 2023IR[C1]:39-40-Cen/PH-Midspan. 6 Months. Due: 12/08/2023. | 901406250 | No | TO-23-LSN-THU-1-07 | Yes | N/A | No Change | Yes | Works identified within year | TAO
LISHEEN THURLES | LS1/LS2/LS3/BU1 | HOTSPOT. 2023IR[R1]:39-40-Right/PH-Midspan. Next planned outage | 901406251 | No | TO-23-LSN-THU-1-07 | Yes | N/A | No Change | Yes | Works identified within year | TAO
LISHEEN THURLES | LS1/LS2/LS3/BU1 | HOTSPOT. 2023IR[47]:46-47-Right/PH-Deadend. Next planned outage | 901406252 | No | TO-23-LSN-THU-1-07 | Yes | N/A | No Change | Yes | Works identified within year | TAO
CLAHANE T122 | CL1/CL2 | SF6 Leak Investigation | 901414560 | No | TO-23-CLH-T122-01 | YES | N/A | No change | Yes | Works identified within year | TAO
CLAHANE T122 | CL1/CL2 | SF6 Leak Repair | 901414561 | No | TO-23-CLH-T122-01 | YES | N/A | No change | Yes | Works identified within year | TAO
CLAHANE T122 | CL1/CL2 | SF6 Leak Check | 901414563 | No | TO-23-CLH-T122-01 | YES | N/A | No change | Yes | Works identified within year | TAO
LODGEWOOD CASTLEDOCKRELL | CK1 | SF6 Repair |  | No | N/A | YES | N/A | No Change | Yes | Works identified within year | TAO
LISHEEN THURLES | LS1/LS2/LS3/BU1 | 110kV SF6 Cubicle Operational Test | 901396723 | No | TO-23-LSN-THU-1-07 | Yes | N/A | No Change | Yes | Works identified within year | TSO
LISHEEN THURLES | LS1/LS2/LS3/BU1 | 110kV MO Cubicle Operational Test | 901396582 | No | TO-23-LSN-THU-1-07 | Yes | N/A | No Change | Yes | Works identified within year | TSO
CORDERRY GARVAGH | GH1/GH2 | 110kV GIS Cubicle Ordinary Service | 901310087 | No | TO-23-CDY-GRV-1-01 | Yes | N/A | No Change | Yes | Works identified within year | TSO
LISHEEN THURLES | LS1/LS2/LS3/BU1 | 110kV SF6 Cubicle Operational Test | 901396723 | Yes | TO-23-LSN-THU-1-06 | Yes | N/A | N/A | No | N/A | N/A
LISHEEN THURLES | LS1/LS2/LS3/BU1 | 110kV MO Cubicle Operational Test | 901396582 | Yes | TO-23-LSN-THU-1-06 | Yes | N/A | N/A | No | N/A | N/A
REAMORE 110SA1 | KM1 | 110kV Sect / Dist Ordinary Service (including busbar disconnects of all bays that are connected to the busbar section that is on outage) | 901396237 | Yes | TO-23-REM-110SA1-02 | Yes | N/A | N/A | No | N/A | N/A
REAMORE 110SA2 | KM1 | 110kV Sect / Dist Ordinary Service (including busbar disconnects of all bays that are connected to the busbar section that is on outage) | 901396238 | Yes | TO-23-REM-110SA2-02 | Yes | N/A | N/A | No | N/A | N/A
REAMORE TRALEE | MU1/KM1 | Cable Insp. 110kV XLPE | 901435208 | Yes | TO-23-REM-TRL-1-02 | Yes | N/A | N/A | No | N/A | N/A
REAMORE TRALEE | MU1/KM1 | 110kV SF6 Cubicle Ordinary Service (excludes busbar disconnects) | 901396374 | Yes | TO-23-REM-TRL-1-02 | Yes | N/A | N/A | No | N/A | N/A
REAMORE TRALEE | MU1/KM1 | 110KV Cubicle Condition Assessment (excludes busbar disconnects) | 901396299 | Yes | TO-23-REM-TRL-1-02 | Yes | N/A | N/A | No | N/A | N/A
REAMORE TRALEE | MU1/KM1 | HOTSPOT. P2 hotspot R-phase cable screen lug. 6 Months. Due: 12/07/2023 | 901365461 | Yes | TO-23-REM-TRL-1-02 | Yes | N/A | N/A | No | N/A | N/A
REAMORE TRALEE | MU1/KM1 | 110kV SF6 Cubicle Ordinary Service (excludes busbar disconnects) | 901396375 | Yes | TO-23-REM-TRL-1-01 | Yes | N/A | N/A | No | N/A | N/A
REAMORE TRALEE | MU1/KM1 | 110KV Cubicle Condition Assessment (excludes busbar disconnects) | 901396300 | Yes | TO-23-REM-TRL-1-01 | Yes | N/A | N/A | No | N/A | N/A
AGANNYGAL DERRYBRIEN | DY1 | 110kV SF6 Cubicle Operational Test | 901396616 | Yes | TO-23-AGL-DYN-1-01 | Yes | N/A | N/A | No | N/A | N/A
AGHADA ST101 | AD3 | O1-SF6 Leak Repair | 901365567 | Yes | TO-23-AD-ST101-01 | Yes | N/A | N/A | No | N/A | N/A
AGHADA ST101 | AD3 | O1- SF6 Leak Investigation | 901365566 | Yes | TO-23-AD-ST101-01 | Yes | N/A | N/A | No | N/A | N/A
AGHADA ST101 | AD3 | O1- ST101 Gas Regeneration | 901365576 | Yes | TO-23-AD-ST101-01 | Yes | N/A | N/A | No | N/A | N/A
AGHADA T2011/12 | AT11/AT12 | Annual Insp. 400 & 220 Station OF Cable | 901299757 | Yes | TO-23-AD-T2011/12-02 | Yes | N/A | N/A | No | N/A | N/A
AGHADA T2011/12 | AT11/AT12 | 220kV SF6 Cubicle Operational Test | 901397019 | Yes | TO-23-AD-T2011/12-05 | Yes | N/A | N/A | No | N/A | N/A
AGHADA T2011/12 | AT11/AT12 | HV Pressure Vessel Inspection | 901406874 | Yes | TO-23-AD-T2011/12-06 | Yes | N/A | N/A | No | N/A | N/A
AGHADA T2014 | AT14 | 220kV SF6 Cubicle Ordinary Service | 901301022 | Yes | TO-23-AD-T2014-02 | Yes | N/A | N/A | No | N/A | N/A
AGHADA T2014 | AT14 | 220KV CUBICLE CONDITION ASSESSMENT | 901300004 | Yes | TO-23-AD-T2014-03 | Yes | N/A | N/A | No | N/A | N/A
AGHADA T2014 | AT14 | Annual Insp. 400 & 220 Station OF Cable | 901299758 | Yes | TO-23-AD-T2014-04 | Yes | N/A | N/A | No | N/A | N/A
AGHADA T2014 | AT14 | 2022PM_Investigate discharge at top of T | 901347004 | Yes | TO-23-AD-T2014-07 | Yes | N/A | N/A | No | N/A | N/A
ARDNACRUSHA GIS T101 | AA1 | 110KV GIS Cubicle Operational Test | 901396513 | Yes | TO-23-AA GIS-T101-01 | Yes | N/A | N/A | No | N/A | N/A
ARDNACRUSHA GIS T102 | AA2 | 110KV GIS Cubicle Operational Test | 901396514 | Yes | TO-23-AA GIS-T102-01 | Yes | N/A | N/A | No | N/A | N/A
ARDNACRUSHA GIS T103 | AA3 | 110KV GIS Cubicle Ordinary Service | 901396553 | Yes | TO-23-AA GIS-T103-01 | Yes | N/A | N/A | No | N/A | N/A
ARDNACRUSHA GIS T104 | AA4 | 110KV GIS Cubicle Operational Test | 901396515 | Yes | TO-23-AA GIS-T104-01 | Yes | N/A | N/A | No | N/A | N/A
ATHEA 110SA1-2CB | XT1/XT2 | 110kV SF6 Cubicle Ordinary Service | 901396856 | Yes | TO-23-ATE-110SA1-2CB-01 | Yes | N/A | N/A | No | N/A | N/A
ATHEA 110SA1-2CB | XT1/XT2 | 110KV CUBICLE CONDITION ASSESSMENT | 901396498 | Yes | TO-23-ATE-110SA1-2CB-01 | Yes | N/A | N/A | No | N/A | N/A
ATHEA 110SA1-2CB | XT1/XT2 | 110kV Sect / Dist Ordinary Service (including busbar disconnects of all bays that are connected to the busbar section that is on outage) | 901396218 | Yes | TO-23-ATE-110SA1-2CB-01 | Yes | N/A | N/A | No | N/A | N/A
ATHEA 110SA1-2CB | XT1/XT2 | 110kV Sect / Dist Ordinary Service (including busbar disconnects of all bays that are connected to the busbar section that is on outage) | 901396219 | Yes | TO-23-ATE-110SA1-2CB-01 | Yes | N/A | N/A | No | N/A | N/A
ATHEA DROMADA | DR1 | 110kV SF6 Cubicle Ordinary Service (excludes busbar disconnects) | 901396373 | Yes | TO-23-ATE-DRO-1-01 | Yes | N/A | N/A | No | N/A | N/A
ATHEA DROMADA | DR1 | 110KV Cubicle Condition Assessment (excludes busbar disconnects) | 901396297 | Yes | TO-23-ATE-DRO-1-01 | Yes | N/A | N/A | No | N/A | N/A
ATHEA DROMADA | DR1 | Cable Insp. 110kV XLPE | 901413563 | Yes | TO-23-ATE-DRO-1-01 | Yes | N/A | N/A | No | N/A | N/A
ATHEA KNOCKANURE | AH1/DR1/XT1/XT2 | 110kV SF6 Cubicle Operational Test | 901396698 | Yes | TO-23-ATE-KNR-1-01 | Yes | N/A | N/A | No | N/A | N/A
ATHEA T121 | AH1 | Cable Insp. 110kV XLPE | 901413562 | Yes | TO-23-ATE-T121-01 | Yes | N/A | N/A | No | N/A | N/A
ATHEA TOBERTOREEN | XT1/XT2 | 110kV SF6 Cubicle Operational Test | 901396805 | Yes | TO-23-ATE-TOB-1-01 | Yes | N/A | N/A | No | N/A | N/A
AUGHINISH SEALROCK 3 | SK3 | 110KV Cubicle Condition Assessment (excludes busbar disconnects) | 901299992 | Yes | TO-23-AUG-SK-3-01 | Yes | N/A | N/A | No | N/A | N/A
AUGHINISH SEALROCK 3 | SK3 | 110kV SF6 Cubicle Operational Test | 901396653 | Yes | TO-23-AUG-SK-3-01 | Yes | N/A | N/A | No | N/A | N/A
AUGHINISH SEALROCK 4 | SK4 | 110kV Cubicle Ordinary Service | 901426941 | Yes | TO-23-AUG-SK-4-01 | Yes | N/A | N/A | No | N/A | N/A
AUGHINISH SEALROCK 4 | SK4 | 110KV Cubicle Condition Assessment (excludes busbar disconnects) | 901299993 | Yes | TO-23-AUG-SK-4-01 | Yes | N/A | N/A | No | N/A | N/A
BALLYNAHULLA CORDAL | DL1/DL2 | 110kV GIS Cubicle Operational Test | 901396543 | Yes | TO-23-BYH-CDL-1-01 | Yes | N/A | N/A | No | N/A | N/A
BALLYNAHULLA CORDAL | DL1/DL2 | 110kV SF6 Cubicle Operational Test | 901396802 | Yes | TO-23-BYH-CDL-1-01 | Yes | N/A | N/A | No | N/A | N/A
BALLYVOUSKILL COOMATAGGART | GD1 | Cable Insp. 110kV XLPE (BALLYVOUSKILL SECTION 1/3) | 901434673 | Yes | TO-23-BVK-COT-1-02 | Yes | N/A | N/A | No | N/A | N/A
BALLYVOUSKILL COOMATAGGART | GD1 | 110kV SF6 Cubicle Operational Test | 901396804 | Yes | TO-23-BVK-COT-1-02 | Yes | N/A | N/A | No | N/A | N/A
BARRYMORE tee CAHIR | BF1 | 2022HP-1[47]Off Plumb (Re-plumb poles) | 901368992 | Yes | TO-23-BAR,T-CAH-1-02 | Yes | N/A | N/A | No | N/A | N/A
BELLACORICK SRAHNAKILLY | OY1/OY2 | 110kV SF6 Cubicle Operational Test | 901300390 | Yes | TO-23-BK-SKY-1-02 | Yes | N/A | N/A | No | N/A | N/A
BOGGERAGH CLASHAVOON | BG1/BG2 | Clashavoon CB lock out alarm. | 901346284 | Yes | TO-23-BGH-CLA-1-01 | Yes | N/A | N/A | No | N/A | N/A
BOGGERAGH CLASHAVOON | BG1/BG2 | 110kV SF6 Cubicle Operational Test | 901396663 | Yes | TO-23-BGH-CLA-1-01 | Yes | N/A | N/A | No | N/A | N/A
BOGGERAGH CLASHAVOON | BG1/BG2 | 110kV SF6 Cubicle Operational Test | 901396662 | Yes | TO-23-BGH-CLA-1-01 | Yes | N/A | N/A | No | N/A | N/A
BOGGERAGH T121 | BG1 | 110kV SF6 Cubicle Operational Test | 901396801 | Yes | TO-23-BGH-T121-01 | Yes | N/A | N/A | No | N/A | N/A
BOGGERAGH T132 | BG2 | 110kV SF6 Cubicle Operational Test | 901396776 | Yes | TO-23-BGH-T132-01 | Yes | N/A | N/A | No | N/A | N/A
BOOLTIAGH T121 | BT1/BT2 | 110kV SF6 Cubicle Operational Test | 901396739 | Yes | TO-23-BOL-T121-01 | Yes | N/A | N/A | No | N/A | N/A
CARRIGDANGAN DUNMANWAY | XA1 | Cable Insp. 110kV XLPE | 901310478 | Yes | TO-23-CGG-DMY-1-01 | Yes | N/A | N/A | No | N/A | N/A
CARRIGDANGAN DUNMANWAY | XA1 | 110kV GIS Cubicle Operational Test | 901315720 | Yes | TO-23-CGG-DMY-1-01 | Yes | N/A | N/A | No | N/A | N/A
CARRIGDANGAN DUNMANWAY | XA1 | 110kV MO Cubicle Operational Test | 901314338 | Yes | TO-23-CGG-DMY-1-01 | Yes | N/A | N/A | No | N/A | N/A
CLOGHBOOLA T131 | CL1 | 110kV SF6 Cubicle Ordinary Service (excludes busbar disconnects) | 901396397 | Yes | TO-23-CBA-T131-01 | Yes | N/A | N/A | No | N/A | N/A
CLOGHBOOLA T131 | CL1 | 110KV Cubicle Condition Assessment (excludes busbar disconnects) | 901396309 | Yes | TO-23-CBA-T131-01 | Yes | N/A | N/A | No | N/A | N/A
CLOGHBOOLA TRIEN | CL1 | Cable Insp. 110kV XLPE | 901413541 | Yes | TO-23-CBA-TRI-1-01 | Yes | N/A | N/A | No | N/A | N/A
CLOGHBOOLA TRIEN | CL1 | HOTSPOT. P3 hotspot on R-phase VT connection. 12 months. Due 12/01/2024 | 901365462 | Yes | TO-23-CBA-TRI-1-01 | Yes | N/A | N/A | No | N/A | N/A
CLOGHBOOLA TRIEN | CL1 | 110kV SF6 Cubicle Operational Test | 901396775 | Yes | TO-23-CBA-TRI-1-01 | Yes | N/A | N/A | No | N/A | N/A
CLOGHBOOLA TRIEN | CL1 | 110kV SF6 Cubicle Ordinary Service (excludes busbar disconnects) | 901396391 | Yes | TO-23-CBA-TRI-1-01 | Yes | N/A | N/A | No | N/A | N/A
CLOGHBOOLA TRIEN | CL1 | HOTSPOT. P2 hotspot on DL disconnect T-phase. 6 Months. Due: 12/07/2023 | 901381261 | Yes | TO-23-CBA-TRI-1-01 | Yes | N/A | N/A | No | N/A | N/A
CLOGHBOOLA TRIEN | CL1 | HOTSPOT. P2 hotspot on DL disconnect S-phase. 6 Months. Due: 12/07/2023 | 901381262 | Yes | TO-23-CBA-TRI-1-01 | Yes | N/A | N/A | No | N/A | N/A
CLOGHBOOLA TRIEN | CL1 | HOTSPOT. P2 hotspot on DL disconnect R-phase. 6 Months. Due: 12/07/2023 | 901381263 | Yes | TO-23-CBA-TRI-1-01 | Yes | N/A | N/A | No | N/A | N/A
CLONKEEN COOMAGEARLAHY | CG1/CG2/CG3/GL1 | 110kV SF6 Cubicle Ordinary Service (excludes busbar disconnects) | 901396330 | Yes | TO-23-CKN-CGL-1-01 | Yes | N/A | N/A | No | N/A | N/A
CLONKEEN COOMAGEARLAHY | CG1/CG2/CG3/GL1 | 110KV Cubicle Condition Assessment (excludes busbar disconnects) | 901396271 | Yes | TO-23-CKN-CGL-1-01 | Yes | N/A | N/A | No | N/A | N/A
CLONKEEN COOMAGEARLAHY | CG1/CG2/CG3/GL1 | 110kV SF6 Cubicle Operational Test | 901396680 | Yes | TO-23-CKN-CGL-1-01 | Yes | N/A | N/A | No | N/A | N/A
COOMAGEARLAHY GLANLEE | GL1 | HOTSPOT. P2 hotspot S-ph middle BB support. 6 Months. Due: 12/07/2023 | 901381264 | Yes | TO-23-CGL-GAE-1-01 | Yes | N/A | N/A | No | N/A | N/A
COOMATAGGART 110SA1 | YT1 | 110kV Sect / Dist Operational Test | 901396606 | Yes | TO-23-COT-110SA1-02 | Yes | N/A | N/A | No | N/A | N/A
COOMATAGGART 110SA2 | YT1 | 110kV Sect / Dist Operational Test | 901396607 | Yes | TO-23-COT-110SA2-02 | Yes | N/A | N/A | No | N/A | N/A
COOMATAGGART 110SA2 | YT1 | 110kV SF6 Cubicle Operational Test | 901396807 | Yes | TO-23-COT-T132-03 | Yes | N/A | N/A | No | N/A | N/A
CORDAL T132 | DL1/DL2 | Cable Insp. 110kV XLPE | 901413577 | Yes | TO-23-CDL-T132-01 | Yes | N/A | N/A | No | N/A | N/A
CORDERRY GARVAGH | GH1/GH2 | Cable Insp. 110kV XLPE | 901413578 | Yes | TO-23-CDY-GRV-1-01 | Yes | N/A | N/A | No | N/A | N/A
CORDERRY GARVAGH | GH1/GH2 | 110kV SF6 Cubicle Operational Test | 901396687 | Yes | TO-23-CDY-GRV-1-01 | Yes | N/A | N/A | No | N/A | N/A
CORDERRY GARVAGH | GH1/GH2 | Cable Insp. 110kV XLPE | 901413579 | Yes | TO-23-CDY-GRV-1-01 | Yes | N/A | N/A | No | N/A | N/A
CORDUFF HUNTSTOWN | HN2 | 220kV SF6 Cubicle Ordinary Service | 901300956 | Yes | TO-23-CDU-HN-1-01 | Yes | N/A | N/A | No | N/A | N/A
CUSHALING T101 | ED1 | 110kV SF6 Cubicle Ordinary Service (excludes busbar disconnects) | 901300865 | Yes | TO-23-CUS-T101-01 | Yes | N/A | N/A | No | N/A | N/A
CUSHALING T101 | ED1 | Investigate PI on the DA for it may show as indeterminate/suspect position | 901317061 | Yes | TO-23-CUS-T101-01 | Yes | N/A | N/A | No | N/A | N/A
ENNIS SLIEVECALLAN | KD1/RD1 | 110kV SF6 Cubicle Ordinary Service (excludes busbar disconnects) | 901396395 | Yes | TO-23-ENN-SLC-1-01 | Yes | N/A | N/A | No | N/A | N/A
ENNIS SLIEVECALLAN | KD1/RD1 | 110kV SF6 Cubicle Ordinary Service (excludes busbar disconnects) | 901396394 | Yes | TO-23-ENN-SLC-1-01 | Yes | N/A | N/A | No | N/A | N/A
GLANAGOW T2001 | WG1 | 220kV GIS Cubicle Ordinary Service | 901300716 | Yes | TO-23-GGO-T2001-01 | Yes | N/A | N/A | No | N/A | N/A
GLANAGOW T2001 | WG1 | 220KV CUBICLE CONDITION ASSESSMENT | 901396895 | Yes | TO-23-GGO-T2001-01 | Yes | N/A | N/A | No | N/A | N/A
GLANLEE T121 | GL1 | 110kV SF6 Cubicle Ordinary Service | 901396847 | Yes | TO-23-GAE-T121-01 | Yes | N/A | N/A | No | N/A | N/A
GLANLEE T121 | GL1 | HOTSPOT. P2 hotspot S-phase DT disconnect. 6 Months. Due: 12/07/2023 | 901381265 | Yes | TO-23-GAE-T121-01 | Yes | N/A | N/A | No | N/A | N/A
GLANLEE T121 | GL1 | HOTSPOT. P2 hotspot T-phase DT disconnect. 6 Months. Due: 12/07/2023 | 901381266 | Yes | TO-23-GAE-T121-01 | Yes | N/A | N/A | No | N/A | N/A
GLANLEE T121 | GL1 | HOTSPOT. P2 hotspot T-ph disconnect. 6 Months. Due: 12/07/2023 | 901381267 | Yes | TO-23-GAE-T121-01 | Yes | N/A | N/A | No | N/A | N/A
GLANLEE T121 | GL1 | HOTSPOT. P2 hotspot on T-phase busbar support. 3 months. Due: 12/04/2023 | 901384671 | Yes | TO-23-GAE-T121-01 | Yes | N/A | N/A | No | N/A | N/A
GLANLEE T121 | GL1 | HOTSPOT. P2 hotspot on S-phase busbar support. 6 Months. Due: 12/07/2023 | 901384672 | Yes | TO-23-GAE-T121-01 | Yes | N/A | N/A | No | N/A | N/A
GOLAGH tee LETTERKENNY | GO2/GOL1 | Replace Poleset 41 | 901332693 | Yes | TO-23-GOL,T-LET-1-01 | Yes | N/A | N/A | No | N/A | N/A
GOLAGH tee LETTERKENNY | GO2/GOL1 | Replace poleset 83 | 901332694 | Yes | TO-23-GOL,T-LET-1-01 | Yes | N/A | N/A | No | N/A | N/A
GOLAGH tee LETTERKENNY | GO2/GOL1 | 2022HP-1[88]Earths-Replace Broken EW | 901370303 | Yes | TO-23-GOL,T-LET-1-01 | Yes | N/A | N/A | No | N/A | N/A
GOLAGH tee LETTERKENNY | GO2/GOL1 | Clogher/Gola Couter R | 901321003 | Yes | TO-23-GOL,T-LET-1-01 | Yes | N/A | N/A | No | N/A | N/A
GOLAGH tee LETTERKENNY | GO2/GOL1 | H8 Clogher/GolaghtT Pole of Breaker | 901335816 | Yes | TO-23-GOL,T-LET-1-01 | Yes | N/A | N/A | No | N/A | N/A
GORMAN T122 | GF1 | Cable Insp. 110kV XLPE | 901307674 | Yes | TO-23-GOR-T122-01 | Yes | N/A | N/A | No | N/A | N/A
HUNTSTOWN T2002 | HN2 | HOTSPOT - 2022 IR[93/94]:Right Phase R1. Replace mid span joint. 1 month DUE: 30Jul2022 | 901302179 | Yes | TO-23-HN-T2002-01 | Yes | N/A | N/A | No | N/A | N/A
HUNTSTOWN T2002 | HN2 | Hotspot on T phase VT connect 6 Months DUE: 17May2023 | 901346857 | Yes | TO-23-HN-T2002-01 | Yes | N/A | N/A | No | N/A | N/A
HUNTSTOWN T2002 | HN2 | Hotspot on T Phase DL/DE disconnect DUE: IMMEDIATE | 901346859 | Yes | TO-23-HN-T2002-01 | Yes | N/A | N/A | No | N/A | N/A
HUNTSTOWN T2002 | HN2 | 220kV SF6 Cubicle Ordinary Service | 901129991 | Yes | TO-23-HN-T2002-01 | Yes | N/A | N/A | No | N/A | N/A
HUNTSTOWN T2002 | HN2 | 220KV CUBICLE CONDITION ASSESSMENT | 901300093 | Yes | TO-23-HN-T2002-01 | Yes | N/A | N/A | No | N/A | N/A
HUNTSTOWN T2002 | HN2 | Hotspot DL/DE disconnect R phase Due- IMMEDIATE 3 month wait time on parts 12/04/2023 | 901346859 | Yes | TO-23-HN-T2002-01 | Yes | N/A | N/A | No | N/A | N/A
HUNTSTOWN T2010/11 | HNC | 220kV SF6 Cubicle Operational Test | 901397020 | Yes | TO-23-HN-T2010/11-01 | Yes | N/A | N/A | No | N/A | N/A
IKERRIN tee SHANNONBRIDGE | MH1 | 2022HP-50[101-150]Danger Notices Replace | 901370757 | Yes | TO-23-IKE,T-SH-1-03 | Yes | N/A | N/A | No | N/A | N/A
IKERRIN tee SHANNONBRIDGE | MH1 | 2022HP-50[1-50]Danger Notices Replace | 901370759 | Yes | TO-23-IKE,T-SH-1-03 | Yes | N/A | N/A | No | N/A | N/A
IKERRIN tee SHANNONBRIDGE | MH1 | 2022HP-50[151-200]Danger Notices Replace | 901370760 | Yes | TO-23-IKE,T-SH-1-03 | Yes | N/A | N/A | No | N/A | N/A
IKERRIN tee SHANNONBRIDGE | MH1 | 2022HP-50[201-250]Danger Notices Replace | 901370764 | Yes | TO-23-IKE,T-SH-1-03 | Yes | N/A | N/A | No | N/A | N/A
IKERRIN tee SHANNONBRIDGE | MH1 | 2022HP-10[251-260]Danger Notices Replace | 901370773 | Yes | TO-23-IKE,T-SH-1-03 | Yes | N/A | N/A | No | N/A | N/A
IKERRIN tee SHANNONBRIDGE | MH1 | 2022HP-50[51-100]Danger Notices Replace | 901370775 | Yes | TO-23-IKE,T-SH-1-03 | Yes | N/A | N/A | No | N/A | N/A
IKERRIN tee THURLES | MH1 | 2022HP-50[286-336]Danger Notices Replace | 901370787 | Yes | TO-23-IKE,T-THU-1-07 | Yes | N/A | N/A | No | N/A | N/A
IKERRIN tee THURLES | MH1 | 2022HP-50[337-386]Danger Notices Replace | 901370791 | Yes | TO-23-IKE,T-THU-1-07 | Yes | N/A | N/A | No | N/A | N/A
IKERRIN tee THURLES | MH1 | 2022HP-28[387-414]Danger Notices Replace | 901370796 | Yes | TO-23-IKE,T-THU-1-07 | Yes | N/A | N/A | No | N/A | N/A
KILL HILL T131 | KH1 | 110kV SF6 Cubicle Operational Test | 901300479 | Yes | TO-23-KHL-T131-01 | Yes | N/A | N/A | No | N/A | N/A
KNOCKRANNY UGGOOL | SO1/UG1 | 110kV GIS Cubicle Ordinary Service | 901300589 | Yes | TO-23-KNY-UGL-1-01 | Yes | N/A | N/A | No | N/A | N/A
KNOCKRANNY UGGOOL | SO1/UG1 | 110kV GIS Cubicle Ordinary Service (excludes busbar disconnects) | 901300594 | Yes | TO-23-KNY-UGL-1-01 | Yes | N/A | N/A | No | N/A | N/A
LISHEEN T122 | LS1/LS2 | 110kV SF6 Cubicle Operational Test | 901396761 | Yes | TO-23-LSN-T122-06 | Yes | N/A | N/A | No | N/A | N/A
MONEYPOINT GIS T121 | MP9 | Cable Insp. 110kV XLPE | 901280722 | Yes | TO-23-MP GIS-T121-01 | Yes | N/A | N/A | No | N/A | N/A
MONEYPOINT GIS T4001 | MP1 | 400kV GIS Cubicle Operational Test | 901397056 | Yes | TO-23-MP GIS-T4001-02 | Yes | N/A | N/A | No | N/A | N/A
MONEYPOINT GIS T4002 | MP2 | 400kV GIS Cubicle Operational Test | 901397061 | Yes | TO-23-MP GIS-T4002-01 | Yes | N/A | N/A | No | N/A | N/A
MOUNTLUCAS T121 | MO1 | 110kV SF6 Cubicle Operational Test | 901396770 | Yes | TO-23-MLC-T121-01 | Yes | N/A | N/A | No | N/A | N/A
MULREAVY T131 | MB1/MB2 | 110kV SF6 Cubicle Ordinary Service | 901129929 | Yes | TO-23-MRY-T131-01 | Yes | N/A | N/A | No | N/A | N/A
SEALROCK T103 | SK3 | 110KV CUBICLE CONDITION ASSESSMENT | 901300072 | Yes | TO-23-SK-T103-01 | Yes | N/A | N/A | No | N/A | N/A
SEALROCK T104 | SK4 | 110KV SF6 Cubicle Operational Test | 901396753 | Yes | TO-23-SK-T104-01 | Yes | N/A | N/A | No | N/A | N/A
SLIABH BAWN T132 | SB1 | 110kV SF6 Cubicle Operational Test | 901396782 | Yes | TO-23-SLB-T132-01 | Yes | N/A | N/A | No | N/A | N/A
STRATFORD tee CARLOW | LI1/LI2/LI4 | 2020LP-1[48]Off Plumb -Pole | 901169118 | Yes | TO-23-STR,T-CLW-1-01 | Yes | N/A | N/A | No | N/A | N/A
STRATFORD tee CARLOW | LI1/LI2/LI4 | 2020LP-1[142]Repl. Pole -Botton rot | 901170002 | Yes | TO-23-STR,T-CLW-1-01 | Yes | N/A | N/A | No | N/A | N/A
STRATFORD tee CARLOW | LI1/LI2/LI4 | 2020LP-1[144]Repl. Pole -Botton rot | 901170003 | Yes | TO-23-STR,T-CLW-1-01 | Yes | N/A | N/A | No | N/A | N/A
STRATFORD tee CARLOW | LI1/LI2/LI4 | 2020LP-1[44]Repl. Pole -Botton rot | 901170004 | Yes | TO-23-STR,T-CLW-1-01 | Yes | N/A | N/A | No | N/A | N/A
STRATFORD tee CARLOW | LI1/LI2/LI4 | 2020LP-1[60]Repl. Pole -Botton rot | 901170005 | Yes | TO-23-STR,T-CLW-1-01 | Yes | N/A | N/A | No | N/A | N/A
STRATFORD tee CARLOW | LI1/LI2/LI4 | 2020SAG-CHECK-1[160]Repl. Pole Sag issue | 901206244 | Yes | TO-23-STR,T-CLW-1-01 | Yes | N/A | N/A | No | N/A | N/A
STRATFORD tee CARLOW | LI1/LI2/LI4 | 2020LP-1[153]Off Plumb -Pole | 901169117 | Yes | TO-23-STR,T-CLW-1-01 | Yes | N/A | N/A | No | N/A | N/A
STRATFORD tee CARLOW | LI1/LI2/LI4 | 2020HP-1[182]Off Plumb Straighten | 901171343 | Yes | TO-23-STR,T-CLW-1-01 | Yes | N/A | N/A | No | N/A | N/A
STRATFORD tee CARLOW | LI1/LI2/LI4 | 2022IR[166/167]:Right Phase R1. Replace. HotSport - DUE: 19May2022 | 901310511 | Yes | TO-23-STR,T-CLW-1-01 | Yes | N/A | N/A | No | N/A | N/A
STRATFORD tee CARLOW | LI1/LI2/LI4 | 110kV SF6 Cubicle Ordinary Service (excludes busbar disconnects) | 901396350 | Yes | TO-23-STR,T-CLW-1-01 | Yes | N/A | N/A | No | N/A | N/A
TARBERT T2003 | TB3 | HOTSPOT - Hotspot on the S phase DB pantograph knuckle joint - Corrective maintenance action will be required within 12 months. DUE: 01Dec2022 | 901274136 | Yes | TO-23-TB-T2003-02 | Yes | N/A | N/A | No | N/A | N/A
TAWNAGHMORE T1/T2 | TP1 | Cable Insp. 110kV XLPE | 901413628 | Yes | TO-23-TAW-T1/T2-01 | Yes | N/A | N/A | No | N/A | N/A
TAWNAGHMORE T1/T2 | TP1 | 110kV SF6 Cubicle Operational Test | 901396786 | Yes | TO-23-TAW-T1/T2-01 | Yes | N/A | N/A | No | N/A | N/A
TURLOUGH HILL T2001/2 | TH1/TH2 | 220kV MO Cubicle Operational Test | 901396962 | Yes | TO-23-TH-T2001/2-01 | Yes | N/A | N/A | No | N/A | N/A
TYNAGH T2001/2 | TYC | O1-Replace T2001/2 220kv Contacts on DL | 901135020 | Yes | TO-23-TY-T2001/2-01 | Yes | N/A | N/A | No | N/A | N/A
TYNAGH T2001/2 | TYC | 220kV SF6 Cubicle Operational Test | 901300520 | Yes | TO-23-TY-T2001/2-01 | Yes | N/A | N/A | No | N/A | N/A
UGGOOL T131 | UG1 | 110kV SF6 Cubicle Ordinary Service (excludes busbar disconnects) | 901300906 | Yes | TO-23-UGL-T131-01 | Yes | N/A | N/A | No | N/A | N/A
UGGOOL T132 | SO1 | 110kV SF6 Cubicle Ordinary Service (excludes busbar disconnects) | 901300915 | Yes | TO-23-UGL-T132-01 | Yes | N/A | N/A | No | N/A | N/A
UGGOOL T134 | SO1 | 110kV SF6 Cubicle Ordinary Service (excludes busbar disconnects) | 901300914 | Yes | TO-23-UGL-T134-01 | Yes | N/A | N/A | No | N/A | N/A
WOODHOUSE T122 | WS1 | 110kV SF6 Cubicle Operational Test | 901396615 | Yes | TO-23-WOH-T122-01 | Yes | N/A | N/A | No | N/A | N/A
ATHEA T121 | AH1 | P2 Protection maintenance of 7SA612, 7SG1431 |  | Yes | TO-23-ATE-T121-01 | Yes | N/A | N/A | No | N/A | N/A
AUGHINISH SEALROCK 4 | SK4 | P3 Protection maintenance of 7SA513, REL521 |  | Yes | TO-23-AUG-SK-4-01 | Yes | N/A | N/A | No | N/A | N/A
AUGHINISH SEALROCK 4 | SK4 | P3 Protection maintenance of 7SA511, REL551 |  | Yes | TO-23-AUG-SK-4-01 | Yes | N/A | N/A | No | N/A | N/A
CUSHALING T101 | ED1 | P3 Protection maintenance of 7SA513, RET521 |  | Yes | TO-23-CUS-T101-01 | Yes | N/A | N/A | No | N/A | N/A
GLANAGOW T2001 | WG1 | P3 Protection maintenance of 7SA612 |  | Yes | TO-23-GGO-T2001-01 | Yes | N/A | N/A | No | N/A | N/A
HUNTSTOWN T2002 | HN2 | P2 Protection maintenance of 7SA612, GRL100 |  | Yes | TO-23-HN-T2002-01 | Yes | N/A | N/A | No | N/A | N/A
MONEYPOINT GIS T4001 | MP1 | P1 Protection maintenance of 7SA612, BOC(M1), 7UT633, 7SW21 |  | Yes | TO-23-MP GIS-T4001-01 | Yes | N/A | N/A | No | N/A | N/A
MONEYPOINT GIS T4003 | MP3 | P1 Protection maintenance of 7SA612, BOC(M1), 7UT633, 7SW21 |  | Yes | TO-23-MP GIS-T4003-01 | Yes | N/A | N/A | No | N/A | N/A
STRATFORD tee CARLOW | LI1/LI2/LI4 | P2 Protection maintenance of 7SA511 |  | Yes | TO-23-STR,T-CLW-1-01 | Yes | N/A | N/A | No | N/A | N/A
Note on D148: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Not in ESBN returned list