## Questions July 22nd Workshop
Question Text | Answer | Topic
In relation to FASS, is a consultation on firm-access requirement for participating in the DASSA on the project agenda? | A consultation on firm access for system services is planned for post go-live of the DASSA. | FASS
Is there any consideration of a common shared platform with participants for secondary trading ..or how this will work especially with required collateral etc | An automated secondary trading platform will be implemented for DASSA go-live, which will enable participants to buy and sell DASSA Orders. The TSOs continue to investigate the options for the settlement of secondary trades between buyers and sellers, i.e. the payment of the Secondary Trading Clearing Price per traded MW volume. An update will be provided to industry through appropriate channels in due course. | FASS
What is required for schedule to trend upwards? | The RAG status of the FASS schedule will trend upwards subject to the closure of open consultations, approval of design recommendations by the SEMC, and progression through the design phases with IT vendors. | FASS
Will RAD end up like the FAM? | The TSOs conducted a Joint Options Assessment exercise with the RAs to develop an alternative DASSA top-up mechanism after the SEMC decided not to approve the FAM (SEM-24-066), and having noted broad industry feedback in favour of a top-up mechanism. Having developed the mechanism in tandem with RAs, the hope is that it will be approved by the SEMC. | FASS
Will the 'gap' paper require another consultation because this will extend the duration of the 'gap'. | The SEMC decision on the 'gap' (SEM-25-031) was made with the knowledge of the revised DASSA delivery date of May 2027. | FASS
Will a secondary capacity platform be delivered for go-live? | An automated secondary trading platform will be implemented for DASSA go-live, which will enable participants to buy and sell DASSA Orders. The TSOs continue to investigate the options for the settlement of secondary trades between buyers and sellers, i.e. the payment of the Secondary Trading Clearing Price per traded MW volume. An update will be provided to industry through appropriate channels in due course. | FASS
Which is the coordination level to be expected between FPM Programme and SEMC Multi-Year Markets plan? | EirGrid and SONI are working with the RAs on the Multi Year Plan. We will be able to provide more feedback once these engagements commence and the FPM programmes will be part of these discussions. | General
AOB - There are multiple timelines/programmes being revised. Once finalised, a Master FPM programme would be very beneficial for MPs out to 2028/29. Thank you. | Acknowledged - We will look to include something like this to the Future Power Markets newsletter which is regularly published. | General
AOB - Will the in person workshops be a consistent option moving forward? Thank you. | Yes, in-person workshops will be an option moving forward but this may depend on the agenda. | General
Can LDES SONI update be included in FPM Newsletter? | Update will be provided going forward. | General
In relation to LDES, please could you include information on SONI project for Northen Ireland in FPM newsletters? | Acknowledged - We will take this under consideration and add a section on NI Flexibility Needs assessment and LDES. | LDES
Scheduling of markets and LDES won't be over the same time horizons, LDES requires a greater look-ahead. Has there been more development on this front and will it be included in this programme? | This will be included in a future market reform project. | LDES
Will LDES procurement be a tender or an auction? | Tender for procurement. | LDES
What options are in place around revenue models/contract instructors? | Contract arrangements will be addressed in the 2nd consultation paper. There will be an operational consideration first and then payment arrangement considerations will come after. | LDES
How long will it take for the payment arrangements consultation to come out after the September paper? | The timeline for this will be provided with the first paper. | LDES
SDP - Any idea of the time frame for September ESPS PIT? How long will it be open for? | Exact timings for the September PIT phase will be confirmed alongside further detail on the SDP_02 and SDP_04 delivery plans. However, we are planning to commence SDP_02 PIT mid-September with access to the environment to be available for 2 weeks. This reflects the majority of participants confirming they had completed the recommended testing as part of the initial PIT phase. | SDP
SDP - In terms of that NPDR unit identification - is it known yet what is needed from the Market Participants side in this process? I.E director sign off etc | This is under discussion internally and will be confirmed alongside the communication of the NPDR units identified. The SDP Programme notes previous participant feedback for the participant engagement process to be made as simple as possible. | SDP
SDP - Last official timeline for SDP_01 saw a two step go live - first week of September for NCC, 3rd week for MPs. Will we see the same approach in 2026 Q1? | As per the SDP status update at the Future Power Markets Industry Workshop, the programme is assessing the delivery schedule of SDP-01 (NPDR) initiative. Further detail will be provided following the completion of this assessment. | SDP
SDP - Tranche 2 SDP_03 & SDP_05 - Is there any update here or are these changes ready to go once Tranche 2 timeline is confirmed? | As per the SDP status update at the Future Power Markets Industry Workshop, the programme is assessing the delivery schedule of the T2 initiatives. Further detail will be provided following the completion of this assessment. | SDP
In relation to ESPS, will a new operational document be published? Will there be much change from the document published in December? | Yes, it will be more concise and address open questions from industry. | SDP
Concerns about no changes to timelines for T2/SDP01 since last update - When are the exact dates for T1 delivery? | Planning exercise is underway and dates will be circulated in due course. | SDP
Concern over SEM-24-044 impact on curtailment and effect on industry - Where does industry get to interact with mods committee on this mod which greatly impacts them? | Question to be put to RAs - This mod will only effect energy balancing. | SDP
Will more than 1 unit be allowed in next round of ESPS PIT testing? | As per the initial SDP_02 PIT phase, participants will be able register 1 unit for the second PIT window. Participants who wish to register an additional unit to the PIT environment should contact the SDP Programme at schedulinganddispatch@eirgrid.com or schedulinganddispatch@soni.ltd.uk | SDP
Does SDP02 have a dependency on SDP04 since their delivery timelines are linked? | No dependency on SDP04, the initiatives can be delivered independent of each other. | SDP