|  |  |  |  |  |
| --- | --- | --- | --- | --- |
|  |  |  |  |  |
| **Transmission Reinforcement** | **Assumed Completion Date** | **Scheduled Completion Date** | **Actual Completion Date** | **Revised Scheduled Competion Date (Sep 2012)** |
|  | **(Month/Year)** | **(Month/Year)** | **(Month/Year)** | **(Month/Year)** |
| *\* notes change to scheduled completion date since last update*  |  |  |  |  |
| Construction of Tarbert - Tralee No. 2 110kV line | **2011** | **2011** | **Nov-11** | **n/a** |
| Corderry 110kV station busbar uprate | 30/09/2012 | 30/09/2012 |  | 30/09/2012 |
| Srananagh 220kV project | 31/12/2012 | 31/12/2012 |  | 31/12/2012 |
| Construction of Arva - Shankill No. 2 110kV line | 31/12/2012 | 31/12/2012 |  | 31/12/2012 |
| Cullenagh - Waterford 110kV line uprate | 31/12/2012 | 31/12/2012 |  | 31/12/2012 |
| Crane 110kV station busbar uprate | 31/12/2012 | 31/12/2012 |  | 31/12/2012 |
| Cathaleen's Fall - Srananagh No.1 110kV line uprate | 31/12/2012 | 31/12/2012 |  | 31/12/2012 |
| Cathaleen's Fall - Golagh T 110kV line uprate | 31/12/2012 | 31/12/2012 |  | 31/12/2012 |
| Butlerstown 110kV station busbar uprate | 2013 | 2013 |  | 2013 |
| Cathaleen's Fall - 110kV station busbar uprate | 2013 | 2013 |  | 2014\* |
| Cathaleen's Fall - Srananagh No. 2 110kV line uprate | 2013 | 2014\* |  | 2014 |
| Clashavoon - Knockraha 220kV line uprate | 2013 | 2013 |  | 2013 |
| Construction of Binbane - Letterkenny 110kV line | 2013 | 2013 |  | 2013 |
| Cullenagh - Great Island 220kV line uprate | 2013 | 2013 |  | 2013 |
| Ennis 110kV station busbar uprate | 2013 | 2013 |  | 2013 |
| Carrick-on-Shannon 110kV station busbar uprate | 2014 | 2014 |  | 2014 |
| Cathaleen's Fall - Clogher 110kV line uprate | 2014 | 2014 |  | 2014 |
| Clashavoon - Tarbert 220kV line uprate | 2014 | 2014 |  | 2015\* |
| Construction of Kilpaddoge - Moneypoint 220kV cable | 2014 | 2014 |  | 2015\* |
| Construction of Kilpaddoge 220/110kV station | 2014 | 2014 |  | 2015\* |
| Construction of North Kerry 220/110kV station | 2014 | 2014 |  | 2015\* |
| Drumkeen 110kV station sectionaliser | 2014 | 2014 |  | 2014 |
| Loop in of Cathaleen's Fall - Drumkeen 110kV line into the new Clogher 110kV station | 2014 | 2014 |  | 2014 |
| Moneypoint 220/110kV Station Project\*\*  | 2014 | 2014 |  | 2015\* |
| Sligo 110kV station busbar uprate | 2014 | 2014 |  | 2014 |
| Ardnacrusha 110kV station refurbishment/replacement | 2015 | 2015 |  | 2015 |
| Clashavoon 220kV station busbar coupler uprate | 2015 | 2015 |  | 2015 |
| Clogher - Drumkeen 110kV line uprate | 2015 | 2015 |  | 2015 |
| Moneypoint 400/220kV Station Project | 2015 | 2015 |  | 2016\* |
| Sligo Srananagh No. 1 110kV line uprate | 2015 | 2015 |  | 2015 |
| Sligo Srananagh No. 2 110kV line uprate | 2015 | 2015 |  | 2015 |
| Letterkenny 110kV station busbar uprate | 2016 | 2016 |  | 2016 |
| ***New ATR updates - Sep 2012***  |  |  |  |  |
| Marina – Trabeg I 110kV line uprate | n/a | n/a |  | 2013 |
| Marina – Trabeg II 110kV line uprate | n/a | n/a |  | 2013 |
| Butlerstown – Cullenagh 110kV line uprate | n/a | n/a |  | 2013 |
| Charleville – Mallow 110kV line uprate | n/a | n/a |  | 2013 |
| Cullenagh – Dungarvan 110kV line uprate | n/a | n/a |  | 2013 |
| Rafeen – Trabeg I 110kV line uprate | n/a | n/a |  | 2014 |
|  |  |  |  |  |
|  |  |  |  |  |
| \*\*Moneypoint 220/110kV Station Project was formerly called Moneypoint 220/110kV 250MVA transformer. The project descriptor for this ATR was changed to better reflect the totality of the project and no project elements are being changed.  |  |  |  |  |
|  |  |  |  |  |