## Wks 26 - 27
Report covers outages commencing/returning/spanning the period: 23/06/2025 - 06/07/2025
Outages commencing/returning in Week 26
OUTAGE ID | PLANT |  | Week 26 | [6 empty] | Week 27
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7
TO-25-SHL-D1/CB1-03 | SHELLYBANKS D1/CB1
TO-25-SHL-D2/CB1-02 | SHELLYBANKS D2/CB1
TO-25-110 kV A1 @ SH-03 | SHANNONBRIDGE 110 kV A1
TO-25-110 kV B1 @ SH-03 | SHANNONBRIDGE 110 kV B1
TO-25-SH-110K1-2-02 | SHANNONBRIDGE 110K1-2
TO-25-ATE-110SA1-2CB-01 | ATHEA 110SA1-2CB | bar: Week 26 Fr 27
TO-25-ATE-DRO-1-01 | ATHEA DROMADA | bar: Week 26 Fr 27
TO-25-ATE-KNR-1-01 | ATHEA KNOCKANURE | bar: Week 26 Fr 27
TO-25-ATE-T121-01 | ATHEA T121 | bar: Week 26 Fr 27
TO-25-ATE-TOB-1-01 | ATHEA TOBERTOREEN | bar: Week 26 Fr 27
TO-25-DRO-T121-01 | DROMADA T121 | bar: Week 26 Fr 27
TO-25-KLN-SH-1-01 | KILLONAN SHANNONBRIDGE | bar: Week 26 Fr 27
TO-25-110 kV A1 @ KNR-01 | KNOCKANURE 110 kV A1 | bar: Week 26 Fr 27
TO-25-110 kV B1 @ KNR-01 | KNOCKANURE 110 kV B1 | bar: Week 26 Fr 27
TO-25-KNR-110K1-01 | KNOCKANURE 110K1 | bar: Week 26 Fr 27
TO-25-KNR-110SA1-2CB-01 | KNOCKANURE 110SA1-2CB | bar: Week 26 Fr 27
TO-25-KNR-110SB1-2CB-01 | KNOCKANURE 110SB1-2CB | bar: Week 26 Fr 27
TO-25-MP GIS-T121-01 | MONEYPOINT GIS T121 | bar: Week 26 Fr 27
TO-25-SHL-T2016-03 | SHELLYBANKS T2016 | bar: Week 26 Fr 27
TO-25-TOB-T132-01 | TOBERTOREEN T132 | bar: Week 26 Fr 27
TO-25-110 kV A1 @ CSH-09 | CASHLA 110 kV A1 | bar: Week 26 Fr 27 to Week 27 Mo 30
TO-25-CSH-110K1-2-03 | CASHLA 110K1-2 | bar: Week 26 Fr 27 to Week 27 Mo 30
TO-25-CD-KBY-1-02 | CARRIGADROHID KILBARRY | bar: Week 26 Fr 27 to Week 27 Fr 4
TO-25-CD-MAC-1-03 | CARRIGADROHID MACROOM | bar: Week 26 Fr 27 to Week 27 Fr 4
TO-25-CD-T103-01 | CARRIGADROHID T103 | bar: Week 26 Fr 27 to Week 27 Fr 4
TO-25-CSH-DLT-1-02 | CASHLA DALTON | bar: Week 26 Fr 27 to Week 27 Fr 4
TO-25-110 kV A1 @ CF-02 | CATHALEENS FALL 110 kV A1 | bar: Week 26 Fr 27 to Week 27 Fr 4
TO-25-110 kV B1 @ CF-01 | CATHALEENS FALL 110 kV B1 | bar: Week 26 Fr 27 to Week 27 Fr 4
TO-25-CF-CLO-1-02 | CATHALEENS FALL CLOGHER 1 | bar: Week 26 Fr 27 to Week 27 Fr 4
TO-25-CF-T103-01 | CATHALEENS FALL T103 | bar: Week 26 Fr 27 to Week 27 Fr 4
TO-25-110 kV A1 @ CLO-01 | CLOGHER 110 kV A1 | bar: Week 26 Fr 27 to Week 27 Fr 4
TO-25-110 kV B1 @ CLO-01 | CLOGHER 110 kV B1 | bar: Week 26 Fr 27 to Week 27 Fr 4
TO-25-110 kV A1 @ KBY-01 | KILBARRY 110 kV A1 | bar: Week 26 Fr 27 to Week 27 Fr 4
TO-25-110 kV B1 @ KBY-01 | KILBARRY 110 kV B1 | bar: Week 26 Fr 27 to Week 27 Fr 4
TO-25-220 kV A1 @ LOU-02 | LOUTH 220 kV A1 | bar: Week 26 Fr 27 to Week 27 Mo 7
TO-25-220 kV A2 @ LOU-03 | LOUTH 220 kV A2 | bar: Week 26 Fr 27 to Week 27 Mo 7
TO-25-220 kV B1 @ LOU-02 | LOUTH 220 kV B1 | bar: Week 26 Fr 27 to Week 27 Mo 7
TO-25-220 kV B2 @ LOU-02 | LOUTH 220 kV B2 | bar: Week 26 Fr 27 to Week 27 Mo 7
TO-25-110 kV A2 @ KBY-01 | KILBARRY 110 kV A2 | bar: Su 22
TO-25-110 kV B2 @ KBY-01 | KILBARRY 110 kV B2 | bar: Su 22
TO-25-KBY-MAL-1-01 | KILBARRY MALLOW | bar: Su 22
TO-25-SH-T2101-03 | SHANNONBRIDGE T2101 | bar: Su 22
TO-25-KIR-T131-04 | KILCUMBER T131
TO-25-IKE-T141-02 | IKERRIN T141 | bar: Week 26 Fr 27 to Week 27 Mo 7
TO-25-IKE,T-IKE-1-02 | IKERRIN tee IKERRIN | bar: Week 26 Fr 27 to Week 27 Mo 7
TO-25-IKE,T-SH-1-02 | IKERRIN tee SHANNONBRIDGE | bar: Week 26 Fr 27 to Week 27 Mo 7
TO-25-IKE,T-THU-1-02 | IKERRIN tee THURLES | bar: Week 26 Fr 27 to Week 27 Mo 7
TO-25-IKE,T-THU-1-05 | bar: Su 22
TO-25-110 kV A1/A2/A3 @ FIN-01 | FINGLAS 110 kV A1/A2/A3 | bar: Su 22
TO-25-220 kV A2 @ FIN-08 | FINGLAS 220 kV A2 | bar: Su 22
TO-25-220 kV B2 @ FIN-05 | FINGLAS 220 kV B2 | bar: Su 22
TO-25-FIN-220K2-10 | FINGLAS 220K2 | bar: Su 22
TO-25-FIN-220SA1-2CB-14 | FINGLAS 220SA1-2CB | bar: Su 22
TO-25-FIN-220SB1-2CB-11 | FINGLAS 220SB1-2CB | bar: Su 22
TO-25-FIN-FIN GIS-2-03 | FINGLAS FINGLAS GIS 2 | bar: Su 22
TO-25-FIN-T2104-03 | FINGLAS T2104 | bar: Su 22
TO-25-SHL-D1/CB1-04 | SHELLYBANKS D1/CB1 | bar: Week 26 Fr 27
TO-25-SHL-D2/CB1-03 | SHELLYBANKS D2/CB1 | bar: Week 26 Fr 27
TO-25-220 kV A2 @ FIN-09 | FINGLAS 220 kV A2 | bar: Week 26 Fr 27 to Week 27 Mo 7
TO-25-220 kV B2 @ FIN-04 | FINGLAS 220 kV B2 | bar: Week 26 Fr 27 to Week 27 Mo 7
TO-25-FIN-220K2-11 | FINGLAS 220K2 | bar: Week 26 Fr 27 to Week 27 Mo 7
Report covers outages commencing/returning/spanning the period: 23/06/2025 - 06/07/2025
Outages commencing/returning in Week 26
OUTAGE ID | PLANT | Week 26 Mo 23: Week 26; Week 27 Mo 30: Week 27
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7
TO-25-FIN-220SA1-2CB-15 | FINGLAS 220SA1-2CB | bar: Week 26 Fr 27 to Week 27 Mo 30; Week 27 We 2 to Week 27 Mo 7
TO-25-FIN-220SB1-2CB-12 | FINGLAS 220SB1-2CB | bar: Week 26 Fr 27 to Week 27 Mo 30; Week 27 We 2 to Week 27 Mo 7
TO-25-110 kV A3 @ FIN GIS-02 | FINGLAS GIS 110 kV A3 | bar: Week 26 Fr 27 to Week 27 Mo 30; Week 27 We 2 to Week 27 Mo 7
TO-25-110 kV B3 @ FIN GIS-01 | FINGLAS GIS 110 kV B3 | bar: Week 26 Fr 27 to Week 27 Mo 30; Week 27 We 2 to Week 27 Mo 7
TO-25-FIN GIS-110SA1-3CB-02 | FINGLAS GIS 110SA1-3CB | bar: Week 26 Fr 27 to Week 27 Mo 30; Week 27 We 2 to Week 27 Mo 7
TO-25-FIN GIS-110SA3-5CB-04 | FINGLAS GIS 110SA3-5CB | bar: Week 26 Fr 27 to Week 27 Mo 30; Week 27 We 2 to Week 27 Mo 7
TO-25-FIN GIS-110SB1-3CB-02 | FINGLAS GIS 110SB1-3CB | bar: Week 26 Fr 27 to Week 27 Mo 30; Week 27 We 2 to Week 27 Mo 7
TO-25-FIN GIS-110SB3-5CB-03 | FINGLAS GIS 110SB3-5CB | bar: Week 26 Fr 27 to Week 27 Mo 30; Week 27 We 2 to Week 27 Mo 7
TO-25-FIN GIS-T2106-02 | FINGLAS GIS T2106 | bar: Week 26 Fr 27 to Week 27 Mo 30; Week 27 We 2 to Week 27 Mo 7
TO-25-GAL GIS-SAL-1-02 | GALWAY GIS SALTHILL | bar: Su 22 to Week 26 Fr 27
TO-25-NAV-T142-01 | NAVAN T142 | bar: Su 22 to Week 26 Fr 27
TO-25-RYB GIS-T107-01 | RYEBROOK GIS T107 | bar: Su 22 to Week 26 Fr 27
TO-25-SAL-110SA1-2CB-02 | SALTHILL 110SA1-2CB | bar: Su 22 to Week 26 Fr 27
TO-25-SAL-T101-01 | SALTHILL T101 | bar: Su 22 to Week 26 Fr 27
TO-25-SAL-T141-01 | SALTHILL T141 | bar: Su 22 to Week 26 Fr 27
TO-25-TAW-T1/T2-01 | TAWNAGHMORE T1/T2 | bar: Su 22 to Week 26 Fr 27
TO-25-TAW-T3-01 | TAWNAGHMORE T3 | bar: Su 22 to Week 26 Fr 27
TO-25-SHL-D2/CB2-02 | SHELLYBANKS D2/CB2 | bar: Su 22 to Week 26 Sa 28
TO-25-SHL-D2/CB3-02 | SHELLYBANKS D2/CB3 | bar: Su 22 to Week 26 Sa 28
TO-25-SHL-T2015-01 | SHELLYBANKS T2015 | bar: Su 22 to Week 26 Sa 28
Outages commencing/returning in Week 27
OUTAGE ID | PLANT | Week 26 Mo 23: Week 26; Week 27 Mo 30: Week 27
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7
TO-25-KLN-SH-1-05 | KILLONAN SHANNONBRIDGE | bar: Week 27 Mo 30 to Week 27 Tu 1
TO-25-220 kV A1 @ SH-01 | SHANNONBRIDGE 220 kV A1 | bar: Week 27 Mo 30 to Week 27 Tu 1
TO-25-220 kV A2 @ SH-03 | SHANNONBRIDGE 220 kV A2 | bar: Week 27 Mo 30 to Week 27 Tu 1
TO-25-220 kV B1 @ SH-01 | SHANNONBRIDGE 220 kV B1 | bar: Week 27 Mo 30 to Week 27 Tu 1
TO-25-220 kV B2 @ SH-03 | SHANNONBRIDGE 220 kV B2 | bar: Week 27 Mo 30 to Week 27 Tu 1
TO-25-CLU-T121-01 | CLUTTERLAND T121 | bar: Week 27 Mo 30 to Week 27 Fr 4
TO-25-FLA-T2101-01 | FLAGFORD T2101 | bar: Week 27 Mo 30 to Week 27 Fr 4
TO-25-GRO-T122-01 | GARROW T122 | bar: Week 27 Mo 30 to Week 27 Fr 4
TO-25-RRU-T122-01 | RATRUSSAN T122 | bar: Week 27 Mo 30 to Week 27 Fr 4
TO-25-110 kV A2 @ BVK-01 | BALLYVOUSKILL 110 kV A2 | bar: Week 27 Mo 30 to Week 27 Mo 7
TO-25-110 kV B2 @ BVK-01 | BALLYVOUSKILL 110 kV B2 | bar: Week 27 Mo 30 to Week 27 Mo 7
TO-25-BVK-110K2-02 | BALLYVOUSKILL 110K2 | bar: Week 27 Mo 30 to Week 27 Mo 7
TO-25-BVK-110SA1-2CB-01 | BALLYVOUSKILL 110SA1-2CB | bar: Week 27 Mo 30 to Week 27 Mo 7
TO-25-BVK-110SB1-2CB-01 | BALLYVOUSKILL 110SB1-2CB | bar: Week 27 Mo 30 to Week 27 Mo 7
TO-25-BVK-COT-1-01 | BALLYVOUSKILL COOMATAGGART | bar: Week 27 Mo 30 to Week 27 Mo 7
TO-25-COT-110SA1-01 | COOMATAGGART 110SA1 | bar: Week 27 Mo 30 to Week 27 Mo 7
TO-25-COT-110SA2-01 | COOMATAGGART 110SA2 | bar: Week 27 Mo 30 to Week 27 Mo 7
TO-25-COT-FILTER1-01 | COOMATAGGART FILTER1 | bar: Week 27 Mo 30 to Week 27 Mo 7
TO-25-COT-T132-01 | COOMATAGGART T132 | bar: Week 27 Mo 30 to Week 27 Mo 7
TO-25-COT-T141-01 | COOMATAGGART T141 | bar: Week 27 Mo 30 to Week 27 Mo 7
TO-25-LOU-MTH-1-01 | LOUTH MEATH HILL | bar: Week 27 Mo 30 to Week 27 Mo 7
TO-25-MTH-110SA1-01 | MEATH HILL 110SA1 | bar: Week 27 Mo 30 to Week 27 Mo 7
TO-25-MTH-110SA2-02 | MEATH HILL 110SA2 | bar: Week 27 Mo 30 to Week 27 Mo 7
TO-25-MTH-T141-01 | MEATH HILL T141 | bar: Week 27 Mo 30 to Week 27 Mo 7
TO-25-SH-T102/4-01 | SHANNONBRIDGE T102/4 | bar: Week 27 Mo 30 to Week 27 Mo 7
TO-25-110 kV A1 @ CSH-01 | CASHLA 110 kV A1 | bar: Week 27 Tu 1 to Week 27 Fr 4
TO-25-110 kV B1 @ CSH-07 | CASHLA 110 kV B1 | bar: Week 27 Tu 1 to Week 27 Fr 4
TO-25-220 kV A1 @ CBT-02 | CASTLEBAGOT 220 kV A1 | bar: Week 27 Tu 1 to Week 27 Mo 7
TO-25-220 kV B1 @ CBT-03 | CASTLEBAGOT 220 kV B1 | bar: Week 27 Tu 1 to Week 27 Mo 7
TO-25-CBT-220K1-05 | CASTLEBAGOT 220K1 | bar: Week 27 Tu 1 to Week 27 Mo 7
TO-25-CBT-220SA1-2CB-03 | CASTLEBAGOT 220SA1-2CB | bar: Week 27 Tu 1 to Week 27 Mo 7
TO-25-CBT-220SB1-2CB-03 | CASTLEBAGOT 220SB1-2CB | bar: Week 27 Tu 1 to Week 27 Mo 7
TO-25-CF-SRA-2-01 | CATHALEENS FALL SRANANAGH 2 | bar: Su 22 to Week 27 Tu 1
TO-25-CRA-LWD-1-07 | CRANE LODGEWOOD | bar: Su 22 to Week 27 Tu 1
TO-25-220 kV B2 @ MAY-01 | MAYNOOTH 220 kV B2 | bar: Week 27 We 2 to Week 27 Mo 7
TO-25-MAY-SH-1-03 | MAYNOOTH SHANNONBRIDGE | bar: Week 27 We 2 to Week 27 Mo 7
Report covers outages commencing/returning/spanning the period: 23/06/2025 - 06/07/2025
Outages commencing/returning in Week 27
OUTAGE ID | PLANT | Week 26 Mo 23: Week 26; Week 27 Mo 30: Week 27
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7
TO-25-220 kV A1 @ SH-05 | SHANNONBRIDGE 220 kV A1 | bar: Week 27 We 2 to Week 27 Mo 7
TO-25-220 kV B1 @ SH-05 | SHANNONBRIDGE 220 kV B1 | bar: Week 27 We 2 to Week 27 Mo 7
TO-25-CD-MAC-1-01 | CARRIGADROHID MACROOM | bar: Su 22 to Week 27 Fr 4
Outages spanning Weeks 26-27
OUTAGE ID | PLANT | Week 26 Mo 23: Week 26; Week 27 Mo 30: Week 27
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7
TO-25-AA GIS-T102-02 | ARDNACRUSHA GIS T102
TO-25-ATH-M/CAP1-06 | ATHLONE M/CAP1
TO-25-BIN-T141-01 | BINBANE T141
TO-25-BUT-KTN-1-04 | BUTLERSTOWN KILLOTERAN
TO-25-CAH-110K1-2-01 | CAHIR 110K1-2
TO-25-CSH-CAP2-01 | CASHLA CAP2
TO-25-CBR-SVC-01 | CASTLEBAR SVC
TO-25-CRA-WEX-1-02 | CRANE WEXFORD
TO-25-CUS-PLS-1-04 | CUSHALING PORTLAOISE
TO-25-CUS-PLS-1-01
TO-25-DND-T121-01 | DARNDALE T121
TO-25-FIN-110K1-2-02 | FINGLAS 110K1-2
TO-25-FIN-110K2-3-04 | FINGLAS 110K2-3
TO-25-GAL-GAL GIS-1-01 | GALWAY GALWAY GIS 1
TO-25-GAL-T103-01 | GALWAY T103
TO-25-GGO-220K1-2-01 | GLANAGOW 220K1-2
TO-25-GI GIS-220SA1-2CB-02 | GREAT ISLAND GIS 220SA1-2CB
TO-25-GI-T141-01 | GREAT ISLAND T141
TO-25-INC-220K1-2-01 | INCHICORE 220K1-2
TO-25-KYT-T232-02 | KELLYSTOWN T232
TO-25-KBY-MR-1-03 | KILBARRY MARINA 1
TO-25-KBY-MR-2-03 | KILBARRY MARINA 2
TO-25-KTN-110SA1-02 | KILLOTERAN 110SA1
TO-25-KTN-110SA2-02 | KILLOTERAN 110SA2
TO-25-KTN-T101-01 | KILLOTERAN T101
TO-25-KPG-TRL-2-02 | KILPADDOGE TRALEE 2
TO-25-LET-PST-01 | LETTERKENNY STRABANE PST
TO-25-LOU-CAP1-02 | LOUTH CAP1
TO-25-MP GIS-T4001-03 | MONEYPOINT GIS T4001
TO-25-MUL-CAP2-01 | MULLINGAR CAP2
TO-25-NW-PB-1-03 | NORTH WALL POOLBEG
TO-25-OBE-PLA-1-02 | OLDBRIDGE PLATIN
TO-25-PB-R2001-01 | POOLBEG R2001
TO-25-TB-T2003-01 | TARBERT T2003
TO-25-TB-T2004-01 | TARBERT T2004