## Wks 49 - 50
Report covers outages commencing/returning/spanning the period: 04/12/2023 - 17/12/2023
Outages commencing/returning in Week 49
OUTAGE ID | PLANT |  | Week 49 | [6 empty] | Week 50
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18
TO-23-ROP-T131-02 | ROSSPILE T131 | bar: Week 49 Mo 4
TO-23-BNK-T121-01 | BARNAKYLE T121 | bar: Week 49 Mo 4 to Week 49 Tu 5
TO-23-ARV-SKL-2-04 | ARVA SHANKILL 2 | bar: Week 49 Mo 4 to Week 49 We 6
TO-23-RRU-SKL-1-04 | RATRUSSAN SHANKILL | bar: Week 49 Mo 4 to Week 49 We 6
TO-23-SKL-110SA1-04 | SHANKILL 110SA1 | bar: Week 49 Mo 4 to Week 49 We 6
TO-23-SKL-110SA2-03 | SHANKILL 110SA2 | bar: Week 49 Mo 4 to Week 49 We 6
TO-23-SKL-T141-03 | SHANKILL T141 | bar: Week 49 Mo 4 to Week 49 We 6
TO-23-AUG-KPG-1-03 | AUGHINISH KILPADDOGE | bar: Week 49 Mo 4 to Week 49 Fr 8
TO-23-CSH-SAL-1-02 | CASHLA SALTHILL | bar: Week 49 Mo 4 to Week 49 Fr 8
TO-23-220 kV A2 @ CLE-03 | CLONEE 220 kV A2 | bar: Week 49 Mo 4 to Week 49 Fr 8
TO-23-220 kV B2 @ CLE-02 | CLONEE 220 kV B2 | bar: Week 49 Mo 4 to Week 49 Fr 8
TO-23-CLE-220K2-02 | CLONEE 220K2 | bar: Week 49 Mo 4 to Week 49 Fr 8
TO-23-CUS-MLC-1-02 | CUSHALING MOUNTLUCAS | bar: Week 49 Mo 4 to Week 49 Fr 8
TO-23-110 kV A1 @ GI-01 | GREAT ISLAND 110 kV A1 | bar: Week 49 Mo 4 to Week 49 Fr 8
TO-23-110 kV A2 @ GI-01 | GREAT ISLAND 110 kV A2 | bar: Week 49 Mo 4 to Week 49 Fr 8
TO-23-110 kV B1 @ GI-01 | GREAT ISLAND 110 kV B1 | bar: Week 49 Mo 4 to Week 49 Fr 8
TO-23-110 kV B2 @ GI-01 | GREAT ISLAND 110 kV B2 | bar: Week 49 Mo 4 to Week 49 Fr 8
TO-23-GI-110K1-2-01 | GREAT ISLAND 110K1-2 | bar: Week 49 Mo 4 to Week 49 Fr 8
TO-23-220 kV A1 @ FLA-01 | FLAGFORD 220 kV A1 | bar: Week 49 Mo 4 to Week 50 Tu 12
TO-23-220 kV A2 @ FLA-01 | FLAGFORD 220 kV A2 | bar: Week 49 Mo 4 to Week 50 Tu 12
TO-23-220 kV B1 @ FLA-01 | FLAGFORD 220 kV B1 | bar: Week 49 Mo 4 to Week 50 Tu 12
TO-23-220 kV B2 @ FLA-01 | FLAGFORD 220 kV B2 | bar: Week 49 Mo 4 to Week 50 Tu 12
TO-23-FLA-220K1-2-01 | FLAGFORD 220K1-2 | bar: Week 49 Mo 4 to Week 50 Tu 12
TO-23-110 kV A1 @ LOU-05 | LOUTH 110 kV A1 | bar: Week 49 Mo 4 to Week 50 We 13
TO-23-110 kV A2 @ LOU-02 | LOUTH 110 kV A2 | bar: Week 49 Mo 4 to Week 50 We 13
TO-23-110 kV B1 @ LOU-05 | LOUTH 110 kV B1 | bar: Week 49 Mo 4 to Week 50 We 13
TO-23-110 kV B2 @ LOU-03 | LOUTH 110 kV B2 | bar: Week 49 Mo 4 to Week 50 We 13
TO-23-LOU-110K1-2-05 | LOUTH 110K1-2 | bar: Week 49 Mo 4 to Week 50 We 13
TO-23-BYH-T132-02 | BALLYNAHULLA T132 | bar: Su 3 to Week 49 Mo 4
TO-23-110 kV A2 @ KBY-05 | KILBARRY 110 kV A2 | bar: Su 3 to Week 49 Mo 4
TO-23-110 kV B2 @ KBY-06 | KILBARRY 110 kV B2 | bar: Su 3 to Week 49 Mo 4
TO-23-KBY-KRA-2-01 | KILBARRY KNOCKRAHA 2 | bar: Su 3 to Week 49 Mo 4
TO-23-110 kV A2 @ KRA-03 | KNOCKRAHA 110 kV A2 | bar: Su 3 to Week 49 Mo 4
TO-23-110 kV B2 @ KRA-05 | KNOCKRAHA 110 kV B2 | bar: Su 3 to Week 49 Mo 4
TO-23-CKN-GRO-1-02 | CLONKEEN GARROW | bar: Week 49 Tu 5
TO-23-CD-KBY-1-01 | CARRIGADROHID KILBARRY | bar: Week 49 Tu 5 to Week 49 Fr 8
TO-23-CDU-220SB2-4-03 | CORDUFF 220SB2-4 | bar: Week 49 Th 7
TO-23-LIS-110SA1-07 | LISDRUM 110SA1 | bar: Week 49 Th 7 to Week 49 Fr 8
TO-23-LIS-110SA2-07 | LISDRUM 110SA2 | bar: Week 49 Th 7 to Week 49 Fr 8
TO-23-LIS-CAP2-06 | LISDRUM CAP2 | bar: Week 49 Th 7 to Week 49 Fr 8
TO-23-LIS-LSA-1-01 | LISDRUM LISLEA | bar: Week 49 Th 7 to Week 49 Fr 8
TO-23-LIS-T142-05 | LISDRUM T142 | bar: Week 49 Th 7 to Week 49 Fr 8
TO-23-ARV-110K1-2-03 | ARVA 110K1-2 | bar: Week 49 Th 7 to Week 50 Th 14
TO-23-MAY-SH-1-01 | MAYNOOTH SHANNONBRIDGE | bar: Su 3 to Week 49 Th 7
TO-23-110 kV A1 @ SH-05 | SHANNONBRIDGE 110 kV A1 | bar: Su 3 to Week 49 Th 7
TO-23-110 kV A2 @ SH-03 | SHANNONBRIDGE 110 kV A2 | bar: Su 3 to Week 49 Th 7
TO-23-110 kV B1 @ SH-02 | SHANNONBRIDGE 110 kV B1 | bar: Su 3 to Week 49 Th 7
TO-23-110 kV B2 @ SH-02 | SHANNONBRIDGE 110 kV B2 | bar: Su 3 to Week 49 Th 7
TO-23-CDU-110SA2-4-04 | CORDUFF 110SA2-4 | bar: Week 49 Fr 8
TO-23-AGL-SH-1-02 | AGANNYGAL SHANNONBRIDGE | bar: Week 49 Fr 8 to Week 49 Sa 9
TO-23-110 kV A2 @ SH-02 | SHANNONBRIDGE 110 kV A2 | bar: Week 49 Fr 8 to Week 49 Sa 9
TO-23-110 kV B2 @ SH-01 | SHANNONBRIDGE 110 kV B2 | bar: Week 49 Fr 8 to Week 49 Sa 9
TO-23-220 kV B1 @ CKM GIS-04 | CARRICKMINES GIS 220 kV B1 | bar: Su 3 to Week 49 Fr 8
TO-23-220 kV B3 @ CKM GIS-03 | CARRICKMINES GIS 220 kV B3 | bar: Su 3 to Week 49 Fr 8
TO-23-CKM GIS-220SB1-3CB-01 | CARRICKMINES GIS 220SB1-3CB | bar: Su 3 to Week 49 Fr 8
TO-23-110 kV A1 @ SH-07 | SHANNONBRIDGE 110 kV A1 | bar: Week 49 Su 10 to Week 50 Fr 15
TO-23-110 kV B1 @ SH-10 | SHANNONBRIDGE 110 kV B1 | bar: Week 49 Su 10 to Week 50 Fr 15
Report covers outages commencing/returning/spanning the period: 04/12/2023 - 17/12/2023
Outages commencing/returning in Week 50
OUTAGE ID | PLANT | Week 49 Mo 4: Week 49; Week 50 Mo 11: Week 50
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18
TO-23-KNR-R2002-01 | KNOCKANURE R2002 | bar: Week 50 Mo 11
TO-23-COW-OLD-2-03 | COW CROSS OLDCOURT 2 | bar: Week 50 Mo 11 to Week 50 Tu 12
TO-23-OLD-T102-03 | OLDCOURT T102 | bar: Week 50 Mo 11 to Week 50 Tu 12
TO-23-SK-T104-03 | SEALROCK T104 | bar: Week 50 Mo 11 to Week 50 Tu 12
TO-23-220 kV B2 @ CKM GIS-05 | CARRICKMINES GIS 220 kV B2 | bar: Week 50 Mo 11 to Week 50 Fr 15
TO-23-220 kV B4 @ CKM GIS-03 | CARRICKMINES GIS 220 kV B4 | bar: Week 50 Mo 11 to Week 50 Fr 15
TO-23-CKM GIS-220SB2-4CB-02 | CARRICKMINES GIS 220SB2-4CB | bar: Week 50 Mo 11 to Week 50 Fr 15
TO-23-110 kV A1 @ CSH-05 | CASHLA 110 kV A1 | bar: Week 50 Mo 11 to Week 50 Fr 15
TO-23-110 kV B1 @ CSH-05 | CASHLA 110 kV B1 | bar: Week 50 Mo 11 to Week 50 Fr 15
TO-23-CSH-CLN-1-02 | CASHLA CLOON | bar: Week 50 Mo 11 to Week 50 Fr 15
TO-23-GLN-PLA-1-01 | GALLANSTOWN PLATIN | bar: Week 50 Mo 11 to Week 50 Fr 15
TO-23-110 kV A1 @ KBY-03 | KILBARRY 110 kV A1 | bar: Week 50 Mo 11 to Week 50 Fr 15
TO-23-110 kV A2 @ KBY-06 | KILBARRY 110 kV A2 | bar: Week 50 Mo 11 to Week 50 Fr 15
TO-23-110 kV B1 @ KBY-03 | KILBARRY 110 kV B1 | bar: Week 50 Mo 11 to Week 50 Fr 15
TO-23-110 kV B2 @ KBY-07 | KILBARRY 110 kV B2 | bar: Week 50 Mo 11 to Week 50 Fr 15
TO-23-KBY-110K1-2-02 | KILBARRY 110K1-2 | bar: Week 50 Mo 11 to Week 50 Fr 15
TO-23-BOG-CRA-1-01 | BANOGE CRANE | bar: Su 3 to Week 50 Mo 11
TO-23-ISH-SHL-1-06 | IRISHTOWN SHELLYBANKS | bar: Week 50 Tu 12 to Week 50 We 13
TO-23-220 kV A2 @ ISH-01 | IRISHTOWN 220 kV A2 | bar: Su 3 to Week 50 We 13
TO-23-220 kV B2 @ ISH-01 | IRISHTOWN 220 kV B2 | bar: Su 3 to Week 50 We 13
TO-23-110 kV B2 @ KRA-01 | KNOCKRAHA 110 kV B2 | bar: Week 50 Su 17 to Week 50 Mo 18
TO-23-KRA-WOH-1-04 | KNOCKRAHA WOODHOUSE | bar: Week 50 Su 17 to Week 50 Mo 18
Outages spanning Weeks 49-50
OUTAGE ID | PLANT | Week 49 Mo 4: Week 49; Week 50 Mo 11: Week 50
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18
TO-23-CSH-CAP2-04 | CASHLA CAP2
TO-23-CLG-110K1-01 | CLOGHRAN 110K1
TO-23-220 kV A2 @ FIN-02 | FINGLAS 220 kV A2
TO-23-FIN-T2104-02 | FINGLAS T2104
TO-23-GAL-110K2-3-02 | GALWAY 110K2-3
TO-23-GGO-220K1-2-02 | GLANAGOW 220K1-2
TO-23-INC-220K1-2-01 | INCHICORE 220K1-2
TO-23-KLS-220K1-2-04 | KELLIS 220K1-2
TO-23-KPG-TB-1-02 | KILPADDOGE TARBERT 1
TO-23-KRA-220K1-2-03 | KNOCKRAHA 220K1-2
TO-23-KRA-MID-1-01 | KNOCKRAHA MIDLETON
TO-23-LET-M/CAP1-01 | LETTERKENNY M/CAP1
TO-23-LIS-SKL-1-06 | LISDRUM SHANKILL
TO-23-LIS-T131-05 | LISDRUM T131
TO-23-MUL-CAP1-02 | MULLINGAR CAP1
TO-23-PB-R2002-02 | POOLBEG R2002
TO-23-PRO-TB-1-04 | PROSPECT TARBERT
TO-23-220 kV A2 @ SH-02 | SHANNONBRIDGE 220 kV A2
TO-23-220 kV B2 @ SH-02 | SHANNONBRIDGE 220 kV B2
TO-23-SOM,T-SH-1-06 | SOMERSET tee SHANNONBRIDGE
TO-23-TB-T101-02 | TARBERT T101
TO-23-TB-T2003-03 | TARBERT T2003
TO-23-TB-T2004-02 | TARBERT T2004
TO-23-TB-T2101-02 | TARBERT T2101
TO-23-THU-CAP2-01 | THURLES CAP2
TO-23-TRL-CAP2-02 | TRALEE CAP2