## Wks 11 - 12
Report covers outages commencing/returning/spanning the period: 14/03/2022 - 27/03/2022
Outages commencing/returning in Week 11
OUTAGE ID | PLANT |  | Week 11 | [6 empty] | Week 12
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28
TO-22-PRN-T4301-02 | PORTAN T4301 | bar: Week 11 Mo 14
TO-22-PRN-WOO-1-02 | PORTAN WOODLAND | bar: Week 11 Mo 14
TO-22-400 kV B1 @ WOO-03 | WOODLAND 400 kV B1 | bar: Week 11 Mo 14
TO-22-CDU-SNU-1-01 | CORDUFF SNUGBOROUGH | bar: Week 11 Mo 14 to Week 11 Tu 15
TO-22-KRA-MID-1-01 | KNOCKRAHA MIDLETON | bar: Week 11 Mo 14 to Week 11 We 16
TO-22-CRA-WEX-1-01 | CRANE WEXFORD | bar: Week 11 Mo 14 to Week 12 Tu 22
TO-22-WOO-T4201-01 | WOODLAND T4201
TO-22-BUT-KTN-1-01 | BUTLERSTOWN KILLOTERAN | bar: Week 11 Tu 15
TO-22-400 kV A1 @ WOO-01 | WOODLAND 400 kV A1 | bar: Week 11 Tu 15 to Week 12 We 23
TO-22-400 kV B1 @ WOO-01 | WOODLAND 400 kV B1 | bar: Week 11 Tu 15 to Week 12 We 23
TO-22-PRN-T4301-01 | PORTAN T4301 | bar: Week 11 Tu 15 to Week 12 Mo 28
TO-22-PRN-WOO-1-01 | PORTAN WOODLAND | bar: Week 11 Tu 15 to Week 12 Mo 28
TO-22-110 kV A1/A2 @ PLS-01 | PORTLAOISE 110 kV A1/A2 | bar: Week 11 We 16
TO-22-110 kV B1/B2 @ PLS-01 | PORTLAOISE 110 kV B1/B2 | bar: Week 11 We 16
TO-22-PLA-T101/2/3/4-04 | PLATIN T101/2/3/4 | bar: Su 13 to Week 11 We 16
Outages commencing/returning in Week 12
OUTAGE ID | PLANT | Week 11 Mo 14: Week 11; Week 12 Mo 21: Week 12
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28
TO-22-LOU-MLN-1-01 | LOUTH MULLAGHARLIN | bar: Week 12 Mo 21
TO-22-AA GIS-110K3-01 | ARDNACRUSHA GIS 110K3 | bar: Week 12 Mo 21 to Week 12 Fr 25
TO-22-BYH-110K1-01 | BALLYNAHULLA 110K1 | bar: Week 12 Mo 21 to Week 12 Fr 25
TO-22-110 kV A2 @ CDU-01 | CORDUFF 110 kV A2 | bar: Week 12 Mo 21 to Week 12 Fr 25
TO-22-110 kV B2 @ CDU-01 | CORDUFF 110 kV B2 | bar: Week 12 Mo 21 to Week 12 Fr 25
TO-22-110 kV A1 @ FIN GIS-02 | FINGLAS GIS 110 kV A1 | bar: Week 12 Mo 21 to Week 12 Fr 25
TO-22-110 kV B1 @ FIN GIS-02 | FINGLAS GIS 110 kV B1 | bar: Week 12 Mo 21 to Week 12 Fr 25
TO-22-FIN GIS-110K1-01 | FINGLAS GIS 110K1 | bar: Week 12 Mo 21 to Week 12 Fr 25
TO-22-KNR-TRI-1-01 | KNOCKANURE TRIEN 1 | bar: Week 12 Mo 21 to Week 12 Fr 25
TO-22-RAF-TBG-1-02 | RAFFEEN TRABEG 1 | bar: Week 12 Mo 21 to Week 12 Fr 25
TO-22-110 kV B1 @ TBG-01 | TRABEG 110 kV B1 | bar: Week 12 Mo 21 to Week 12 Fr 25
TO-22-110 kV B2 @ TBG-01 | TRABEG 110 kV B2 | bar: Week 12 Mo 21 to Week 12 Fr 25
TO-22-220 kV A3 @ CKM GIS-03 | CARRICKMINES GIS 220 kV A3 | bar: Week 12 Mo 21 to Week 12 Mo 28
TO-22-220 kV B3 @ CKM GIS-03 | CARRICKMINES GIS 220 kV B3 | bar: Week 12 Mo 21 to Week 12 Mo 28
TO-22-CKM GIS-220K3-01 | CARRICKMINES GIS 220K3 | bar: Week 12 Mo 21 to Week 12 Mo 28
TO-22-CDU-T2102-01 | CORDUFF T2102 | bar: Week 12 Mo 21 to Week 12 Mo 28
TO-22-DMY-MAC-1-01 | DUNMANWAY MACROOM | bar: Week 12 Mo 21 to Week 12 Mo 28
TO-22-RYB GIS-T133-02 | RYEBROOK GIS T133 | bar: Week 12 Mo 21 to Week 12 Mo 28
TO-22-220 kV A1 @ TB-02 | TARBERT 220 kV A1 | bar: Week 12 Mo 21 to Week 12 Mo 28
TO-22-220 kV B1 @ TB-02 | TARBERT 220 kV B1 | bar: Week 12 Mo 21 to Week 12 Mo 28
TO-22-110 kV A2 @ CAH-01 | CAHIR 110 kV A2 | bar: Week 12 Tu 22 to Week 12 Th 24
TO-22-CAH-110K1-2-02 | CAHIR 110K1-2 | bar: Week 12 Tu 22 to Week 12 Th 24
TO-22-DDK-LOU-1-01 | DUNDALK LOUTH | bar: Week 12 Tu 22 to Week 12 Fr 25
TO-22-CF-CLO-1-03 | CATHALEENS FALL CLOGHER 1 | bar: Week 12 Tu 22 to Week 12 Su 27
TO-22-GGO-RAF-1-02 | GLANAGOW RAFFEEN | bar: Week 12 Tu 22 to Week 12 Mo 28
TO-22-BYH-KNR-1-01 | BALLYNAHULLA KNOCKANURE | bar: Su 13 to Week 12 Tu 22
TO-22-110 kV A1/A2/A4 @ KNR-01 | KNOCKANURE 110 kV A1/A2/A4 | bar: Week 12 We 23
TO-22-110 kV B1/B2/B4 @ KNR-01 | KNOCKANURE 110 kV B1/B2/B4 | bar: Week 12 We 23
TO-22-220 kV A1/A2 @ KNR-01 | KNOCKANURE 220 kV A1/A2 | bar: Week 12 We 23
TO-22-220 kV B1/B2 @ KNR-01 | KNOCKANURE 220 kV B1/B2 | bar: Week 12 We 23
TO-22-400 kV A1 @ WOO-02 | WOODLAND 400 kV A1 | bar: Week 12 Th 24 to Week 12 Mo 28
TO-22-400 kV A2 @ WOO-01 | WOODLAND 400 kV A2 | bar: Week 12 Th 24 to Week 12 Mo 28
TO-22-400 kV B1 @ WOO-02 | WOODLAND 400 kV B1 | bar: Week 12 Th 24 to Week 12 Mo 28
TO-22-400 kV B2 @ WOO-01 | WOODLAND 400 kV B2 | bar: Week 12 Th 24 to Week 12 Mo 28
TO-22-WOO-400K1-2-02 | WOODLAND 400K1-2 | bar: Week 12 Th 24 to Week 12 Mo 28
Report covers outages commencing/returning/spanning the period: 14/03/2022 - 27/03/2022
Outages spanning Weeks 11-12
OUTAGE ID | PLANT | Week 11 Mo 14: Week 11; Week 12 Mo 21: Week 12
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28
TO-22-AD-GGO-1-01 | AGHADA GLANAGOW
TO-22-ARK-220K1-2-01 | ARKLOW 220K1-2
TO-22-BIN-T142-01 | BINBANE T142
TO-22-110 kV A1 @ CAH-01 | CAHIR 110 kV A1
TO-22-CSH-PRO-1-01 | CASHLA PROSPECT
TO-22-CLG-T122-01 | CLOGHRAN T122
TO-22-CDU-PLA-1-01 | CORDUFF PLATIN
TO-22-110 kV B2 @ DEY-02 | DERRYCARNEY 110 kV B2
TO-22-DEY-110K2-01 | DERRYCARNEY 110K2
TO-22-DRU-CAP2-02 | DRUMLINE CAP2
TO-22-220 kV A1/A2 @ FIN-01 | FINGLAS 220 kV A1/A2
TO-22-FIN-220K1-06 | FINGLAS 220K1
TO-22-FIN-220K2-01 | FINGLAS 220K2
TO-22-FIN-MCD-1-01 | FINGLAS McDERMOTT
TO-22-FLA-SLB-1-01 | FLAGFORD SLIABH BAWN
TO-22-GGO-220K1-2-02 | GLANAGOW 220K1-2
TO-22-INC-220K1-2-03 | INCHICORE 220K1-2
TO-22-KLN-T2101-01 | KILLONAN T2101
TO-22-LET-M/CAP1-01 | LETTERKENNY M/CAP1
TO-22-LIS-LOU-1-03 | LISDRUM LOUTH
TO-22-LIS-LOU-1-01
TO-22-MAY-WOO-1-12 | MAYNOOTH WOODLAND
TO-22-MAY-WOO-1-02
TO-22-MUL-CAP2-03 | MULLINGAR CAP2
TO-22-NAV-M/CAP1-01 | NAVAN M/CAP1
TO-22-PB-R2002-01 | POOLBEG R2002
TO-22-SOM-T142-01 | SOMERSET T142
TO-22-110 kV A1 @ TB-01 | TARBERT 110 kV A1
TO-22-110 kV B1 @ TB-01 | TARBERT 110 kV B1
TO-22-220 kV A1 @ TB-04 | TARBERT 220 kV A1
TO-22-220 kV B1 @ TB-04 | TARBERT 220 kV B1
TO-22-TB-T101-02 | TARBERT T101
TO-22-TB-T102-02 | TARBERT T102
TO-22-TB-T2004-03 | TARBERT T2004
TO-22-TB-T2101-03 | TARBERT T2101