## Wks 13 - 14
Report covers outages commencing/returning/spanning the period: 28/03/2022 - 10/04/2022
Outages commencing/returning in Week 13
OUTAGE ID | PLANT |  | Week 13 | [6 empty] | Week 14
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11
TO-22-GOL-T101-02 | GOLAGH T101 | bar: Week 13 Mo 28 to Week 13 Tu 29
TO-22-GOL,T-CLO-1-02 | GOLAGH tee CLOGHER | bar: Week 13 Mo 28 to Week 13 Tu 29
TO-22-GOL,T-GOL-1-01 | GOLAGH tee GOLAGH | bar: Week 13 Mo 28 to Week 13 Tu 29
TO-22-GOL,T-LET-1-01 | GOLAGH tee LETTERKENNY | bar: Week 13 Mo 28 to Week 13 Tu 29
TO-22-KPG-RAT-1-01 | KILPADDOGE RATHKEALE | bar: Week 13 Mo 28 to Week 13 Th 31
TO-22-CKM GIS-220K3-02 | CARRICKMINES GIS 220K3 | bar: Week 13 Mo 28 to Week 13 Fr 1
TO-22-220 kV A2 @ CLE-04 | CLONEE 220 kV A2 | bar: Week 13 Mo 28 to Week 13 Fr 1
TO-22-220 kV B2 @ CLE-03 | CLONEE 220 kV B2 | bar: Week 13 Mo 28 to Week 13 Fr 1
TO-22-220 kV A2 @ CDU-04 | CORDUFF 220 kV A2 | bar: Week 13 Mo 28 to Week 13 Fr 1
TO-22-220 kV B2 @ CDU-05 | CORDUFF 220 kV B2 | bar: Week 13 Mo 28 to Week 13 Fr 1
TO-22-220 kV A1 @ KLN-01 | KILLONAN 220 kV A1 | bar: Week 13 Mo 28 to Week 13 Fr 1
TO-22-220 kV A2 @ KLN-01 | KILLONAN 220 kV A2 | bar: Week 13 Mo 28 to Week 13 Fr 1
TO-22-220 kV B1 @ KLN-01 | KILLONAN 220 kV B1 | bar: Week 13 Mo 28 to Week 13 Fr 1
TO-22-220 kV B2 @ KLN-01 | KILLONAN 220 kV B2 | bar: Week 13 Mo 28 to Week 13 Fr 1
TO-22-KLN-220K1-2-01 | KILLONAN 220K1-2 | bar: Week 13 Mo 28 to Week 13 Fr 1
TO-22-KPG-TRL-2-01 | KILPADDOGE TRALEE 2 | bar: Week 13 Mo 28 to Week 13 Fr 1
TO-22-CLE-WOO-1-06 | CLONEE WOODLAND | bar: Week 13 Mo 28 to Week 14 Mo 4
TO-22-MAY-WOO-1-01 | MAYNOOTH WOODLAND | bar: Week 13 Mo 28 to Week 14 Mo 4
TO-22-ARK-220K1-2-02 | ARKLOW 220K1-2
TO-22-ARK-CKM GIS-1-01 | ARKLOW CARRICKMINES GIS
TO-22-ARK-LWD-1-02 | ARKLOW LODGEWOOD
TO-22-ARK-LWD-1-01
TO-22-ARK-T2101-01 | ARKLOW T2101
TO-22-ARK-T2102-01 | ARKLOW T2102
TO-22-DDK-MLN-1-01 | DUNDALK MULLAGHARLIN
TO-22-110 kV A2 @ LOU-02 | LOUTH 110 kV A2
TO-22-110 kV B2 @ LOU-01 | LOUTH 110 kV B2
TO-22-MR-TBG-1-02 | MARINA TRABEG 1 | bar: Week 13 Tu 29 to Week 13 We 30
TO-22-DRY-GOR-1-02 | DRYBRIDGE GORMAN | bar: Week 13 Tu 29 to Week 13 Th 31
TO-22-GOR-MTH-1-03 | GORMAN MEATH HILL | bar: Week 13 Tu 29 to Week 13 Th 31
TO-22-110 kV A1 @ CAH-01 | CAHIR 110 kV A1 | bar: Su 27 to Week 13 Tu 29
TO-22-110 kV A1 @ GRV-01 | GARVAGH 110 kV A1 | bar: Week 13 We 30
TO-22-110 kV B1 @ GRV-01 | GARVAGH 110 kV B1 | bar: Week 13 We 30
TO-22-WOO-T4201-05 | WOODLAND T4201 | bar: Week 13 We 30 to Week 14 Mo 11
TO-22-CSH-PRO-1-01 | CASHLA PROSPECT | bar: Su 27 to Week 13 We 30
TO-22-PRN-T4301-01 | PORTAN T4301 | bar: Su 27 to Week 13 We 30
TO-22-PRN-WOO-1-01 | PORTAN WOODLAND | bar: Su 27 to Week 13 We 30
TO-22-220 kV A3 @ CKM GIS-03 | CARRICKMINES GIS 220 kV A3 | bar: Su 27 to Week 13 Fr 1
TO-22-220 kV B3 @ CKM GIS-03 | CARRICKMINES GIS 220 kV B3 | bar: Su 27 to Week 13 Fr 1
TO-22-CKM GIS-220K3-01 | CARRICKMINES GIS 220K3 | bar: Su 27 to Week 13 Fr 1
TO-22-CDU-T2102-01 | CORDUFF T2102 | bar: Su 27 to Week 13 Fr 1
TO-22-DMY-MAC-1-01 | DUNMANWAY MACROOM | bar: Su 27 to Week 13 Fr 1
TO-22-220 kV A1 @ TB-02 | TARBERT 220 kV A1 | bar: Su 27 to Week 13 Fr 1
TO-22-220 kV B1 @ TB-02 | TARBERT 220 kV B1 | bar: Su 27 to Week 13 Fr 1
Outages commencing/returning in Week 14
OUTAGE ID | PLANT | Week 13 Mo 28: Week 13; Week 14 Mo 4: Week 14
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11
TO-22-CDU-220K1-2-01 | CORDUFF 220K1-2 | bar: Week 14 Mo 4 to Week 14 We 6
TO-22-CDU-220K1-3-02 | CORDUFF 220K1-3 | bar: Week 14 Mo 4 to Week 14 We 6
TO-22-CDU-220SA2-4-03 | CORDUFF 220SA2-4 | bar: Week 14 Mo 4 to Week 14 We 6
TO-22-CDU-220SB2-4-02 | CORDUFF 220SB2-4 | bar: Week 14 Mo 4 to Week 14 We 6
TO-22-AGL-SH-1-01 | AGANNYGAL SHANNONBRIDGE | bar: Week 14 Mo 4 to Week 14 Th 7
TO-22-220 kV A1 @ CBT-01 | CASTLEBAGOT 220 kV A1 | bar: Week 14 Mo 4 to Week 14 Fr 8
TO-22-220 kV A2 @ CBT-01 | CASTLEBAGOT 220 kV A2 | bar: Week 14 Mo 4 to Week 14 Fr 8
TO-22-CBT-220SA1-2CB-01 | CASTLEBAGOT 220SA1-2CB | bar: Week 14 Mo 4 to Week 14 Fr 8
TO-22-CF-SRA-1-01 | CATHALEENS FALL SRANANAGH 1 | bar: Week 14 Mo 4 to Week 14 Fr 8
TO-22-CL-T101-03 | CLIFF T101 | bar: Week 14 Mo 4 to Week 14 Fr 8
TO-22-DDK-110SA1-01 | DUNDALK 110SA1 | bar: Week 14 Mo 4 to Week 14 Fr 8
Report covers outages commencing/returning/spanning the period: 28/03/2022 - 10/04/2022
Outages commencing/returning in Week 14
OUTAGE ID | PLANT | Week 13 Mo 28: Week 13; Week 14 Mo 4: Week 14
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11
TO-22-DDK-110SA2-01 | DUNDALK 110SA2 | bar: Week 14 Mo 4 to Week 14 Fr 8
TO-22-DDK-T141-01 | DUNDALK T141 | bar: Week 14 Mo 4 to Week 14 Fr 8
TO-22-DSN-MP GIS-1-03 | DUNSTOWN MONEYPOINT GIS | bar: Week 14 Mo 4 to Week 14 Fr 8
TO-22-110 kV A2 @ FIN GIS-06 | FINGLAS GIS 110 kV A2 | bar: Week 14 Mo 4 to Week 14 Fr 8
TO-22-110 kV A4 @ FIN GIS-01 | FINGLAS GIS 110 kV A4 | bar: Week 14 Mo 4 to Week 14 Fr 8
TO-22-FIN GIS-110SA2-4CB-07 | FINGLAS GIS 110SA2-4CB | bar: Week 14 Mo 4 to Week 14 Fr 8
TO-22-GI-T2101-06 | GREAT ISLAND T2101 | bar: Week 14 Mo 4 to Week 14 Fr 8
TO-22-KPG-TB-1-03 | KILPADDOGE TARBERT 1 | bar: Week 14 Mo 4 to Week 14 Fr 8
TO-22-KPG-TRL-1-01 | KILPADDOGE TRALEE 1 | bar: Week 14 Mo 4 to Week 14 Fr 8
TO-22-SH-T104-01 | SHANNONBRIDGE T104 | bar: Week 14 Mo 4 to Week 14 Fr 8
TO-22-AA GIS-T104-01 | ARDNACRUSHA GIS T104 | bar: Week 14 Mo 4 to Week 14 Mo 11
TO-22-BDA-MON-1-01 | BARODA MONREAD | bar: Week 14 Mo 4 to Week 14 Mo 11
TO-22-220 kV A1 @ CKM GIS-02 | CARRICKMINES GIS 220 kV A1 | bar: Week 14 Mo 4 to Week 14 Mo 11
TO-22-220 kV A2 @ CKM GIS-01 | CARRICKMINES GIS 220 kV A2 | bar: Week 14 Mo 4 to Week 14 Mo 11
TO-22-CKM GIS-220SA1-2CB-01 | CARRICKMINES GIS 220SA1-2CB | bar: Week 14 Mo 4 to Week 14 Mo 11
TO-22-CVW-KRA-1-01 | CASTLEVIEW KNOCKRAHA | bar: Week 14 Mo 4 to Week 14 Mo 11
TO-22-CHA-GLE-1-01 | CHARLEVILLE GLENLARA | bar: Week 14 Mo 4 to Week 14 Mo 11
TO-22-CLA-CKN-1-01 | CLASHAVOON CLONKEEN | bar: Week 14 Mo 4 to Week 14 Mo 11
TO-22-KPG-TRL-1-02 | KILPADDOGE TRALEE 1 | bar: Week 14 Mo 4 to Week 14 Mo 11
TO-22-MON-110SA1-01 | MONREAD 110SA1 | bar: Week 14 Mo 4 to Week 14 Mo 11
TO-22-MON-110SA2-02 | MONREAD 110SA2 | bar: Week 14 Mo 4 to Week 14 Mo 11
TO-22-MON-T101-01 | MONREAD T101 | bar: Week 14 Mo 4 to Week 14 Mo 11
TO-22-110 kV A1 @ TB-01 | TARBERT 110 kV A1 | bar: Su 27 to Week 14 Mo 4
TO-22-110 kV B1 @ TB-01 | TARBERT 110 kV B1 | bar: Su 27 to Week 14 Mo 4
TO-22-220 kV A1 @ TB-04 | TARBERT 220 kV A1 | bar: Su 27 to Week 14 Mo 4
TO-22-220 kV B1 @ TB-04 | TARBERT 220 kV B1 | bar: Su 27 to Week 14 Mo 4
TO-22-TB-T2101-03 | TARBERT T2101 | bar: Su 27 to Week 14 Mo 4
TO-22-AD-220K1-01 | AGHADA 220K1 | bar: Week 14 Tu 5
TO-22-COL-FIN GIS-1-05 | COLLEGE PARK FINGLAS GIS | bar: Week 14 Tu 5
TO-22-KPG-TB-1-01 | KILPADDOGE TARBERT 1 | bar: Week 14 Tu 5 to Week 14 Mo 11
TO-22-220 kV A1 @ TB-01 | TARBERT 220 kV A1 | bar: Week 14 Tu 5 to Week 14 Mo 11
TO-22-220 kV B1 @ TB-01 | TARBERT 220 kV B1 | bar: Week 14 Tu 5 to Week 14 Mo 11
TO-22-KLN-T2101-01 | KILLONAN T2101 | bar: Su 27 to Week 14 Tu 5
TO-22-110 kV A1/A2 @ TBG-01 | TRABEG 110 kV A1/A2 | bar: Week 14 We 6
TO-22-110 kV B1/B2 @ TBG-01 | TRABEG 110 kV B1/B2 | bar: Week 14 We 6
TO-22-TB-110K1-2-01 | TARBERT 110K1-2 | bar: Week 14 We 6 to Week 14 Th 7
TO-22-MP GIS-T4002-01 | MONEYPOINT GIS T4002 | bar: Week 14 We 6 to Week 14 Fr 8
TO-22-BDA-T102-01 | BARODA T102 | bar: Week 14 Th 7 to Week 14 Fr 8
TO-22-MR-T107-01 | MARINA T107 | bar: Week 14 Th 7 to Week 14 Fr 8
TO-22-220 kV A2 @ CDU-02 | CORDUFF 220 kV A2 | bar: Week 14 Th 7 to Week 14 Mo 11
TO-22-220 kV B2 @ CDU-06 | CORDUFF 220 kV B2 | bar: Week 14 Th 7 to Week 14 Mo 11
TO-22-BDA-110SA1-2CB-01 | BARODA 110SA1-2CB | bar: Week 14 Fr 8
TO-22-AD-GGO-1-01 | AGHADA GLANAGOW | bar: Su 27 to Week 14 Fr 8
Outages spanning Weeks 13-14
OUTAGE ID | PLANT | Week 13 Mo 28: Week 13; Week 14 Mo 4: Week 14
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11
TO-22-ARK-220K1-2-01 | ARKLOW 220K1-2
TO-22-BIN-T142-01 | BINBANE T142
TO-22-CLG-T122-01 | CLOGHRAN T122
TO-22-CDU-PLA-1-01 | CORDUFF PLATIN
TO-22-110 kV B2 @ DEY-02 | DERRYCARNEY 110 kV B2
TO-22-DEY-110K2-01 | DERRYCARNEY 110K2
TO-22-DRU-CAP2-02 | DRUMLINE CAP2
TO-22-220 kV A1/A2 @ FIN-01 | FINGLAS 220 kV A1/A2
TO-22-FIN-220K1-06 | FINGLAS 220K1
TO-22-FIN-220K2-01 | FINGLAS 220K2
TO-22-FIN-MCD-1-01 | FINGLAS McDERMOTT
TO-22-FLA-SLB-1-01 | FLAGFORD SLIABH BAWN
TO-22-GGO-220K1-2-02 | GLANAGOW 220K1-2
Report covers outages commencing/returning/spanning the period: 28/03/2022 - 10/04/2022
Outages spanning Weeks 13-14
OUTAGE ID | PLANT | Week 13 Mo 28: Week 13; Week 14 Mo 4: Week 14
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11
TO-22-GGO-RAF-1-02 | GLANAGOW RAFFEEN
TO-22-INC-220K1-2-03 | INCHICORE 220K1-2
TO-22-LET-M/CAP1-01 | LETTERKENNY M/CAP1
TO-22-LIS-LOU-1-01 | LISDRUM LOUTH
TO-22-LIS-LOU-1-03
TO-22-MAY-WOO-1-12 | MAYNOOTH WOODLAND
TO-22-MAY-WOO-1-02
TO-22-MUL-CAP2-03 | MULLINGAR CAP2
TO-22-NAV-M/CAP1-01 | NAVAN M/CAP1
TO-22-PB-R2002-01 | POOLBEG R2002
TO-22-RYB GIS-T133-02 | RYEBROOK GIS T133
TO-22-SOM-T142-01 | SOMERSET T142
TO-22-TB-T101-02 | TARBERT T101
TO-22-TB-T102-02 | TARBERT T102
TO-22-TB-T2004-03 | TARBERT T2004
TO-22-400 kV A1 @ WOO-02 | WOODLAND 400 kV A1
TO-22-400 kV A2 @ WOO-01 | WOODLAND 400 kV A2
TO-22-400 kV B1 @ WOO-02 | WOODLAND 400 kV B1
TO-22-400 kV B2 @ WOO-01 | WOODLAND 400 kV B2
TO-22-WOO-400K1-2-02 | WOODLAND 400K1-2
TO-22-WOO-T4201-01 | WOODLAND T4201