## Wks 21 - 22
Report covers outages commencing/returning/spanning the period: 23/05/2022 - 05/06/2022
Outages commencing/returning in Week 21
OUTAGE ID | PLANT |  | Week 21 | [6 empty] | Week 22
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6
TO-22-SNU-T102-01 | SNUGBOROUGH T102 | bar: Week 21 Mo 23
TO-22-220 kV A1 @ CLE-02 | CLONEE 220 kV A1 | bar: Week 21 Mo 23 to Week 21 Tu 24
TO-22-220 kV B1 @ CLE-01 | CLONEE 220 kV B1 | bar: Week 21 Mo 23 to Week 21 Tu 24
TO-22-CLE-220K1-02 | CLONEE 220K1 | bar: Week 21 Mo 23 to Week 21 Tu 24
TO-22-CLE-220SA1-2CB-02 | CLONEE 220SA1-2CB | bar: Week 21 Mo 23 to Week 21 Tu 24
TO-22-CLE-220SB1-2CB-01 | CLONEE 220SB1-2CB | bar: Week 21 Mo 23 to Week 21 Tu 24
TO-22-CLE-CDU-1-02 | CLONEE CORDUFF | bar: Week 21 Mo 23 to Week 21 Tu 24
TO-22-GOL-T101-03 | GOLAGH T101 | bar: Week 21 Mo 23 to Week 21 Th 26
TO-22-GOL,T-CLO-1-01 | GOLAGH tee CLOGHER | bar: Week 21 Mo 23 to Week 21 Th 26
TO-22-GOL,T-GOL-1-02 | GOLAGH tee GOLAGH | bar: Week 21 Mo 23 to Week 21 Th 26
TO-22-GOL,T-LET-1-02 | GOLAGH tee LETTERKENNY | bar: Week 21 Mo 23 to Week 21 Th 26
TO-22-SNU-T102-02 | SNUGBOROUGH T102 | bar: Week 21 Mo 23 to Week 21 Th 26
TO-22-CAH-KHL-1-01 | CAHIR KILL HILL | bar: Week 21 Mo 23 to Week 21 Fr 27
TO-22-110 kV A1 @ CBA-01 | CLOGHBOOLA 110 kV A1 | bar: Week 21 Mo 23 to Week 21 Fr 27
TO-22-110 kV A2 @ CBA-01 | CLOGHBOOLA 110 kV A2 | bar: Week 21 Mo 23 to Week 21 Fr 27
TO-22-CBA-110SA1-01 | CLOGHBOOLA 110SA1 | bar: Week 21 Mo 23 to Week 21 Fr 27
TO-22-CBA-110SA2-01 | CLOGHBOOLA 110SA2 | bar: Week 21 Mo 23 to Week 21 Fr 27
TO-22-CBA-T122-01 | CLOGHBOOLA T122 | bar: Week 21 Mo 23 to Week 21 Fr 27
TO-22-CBA-T131-01 | CLOGHBOOLA T131 | bar: Week 21 Mo 23 to Week 21 Fr 27
TO-22-CBA-TRI-1-01 | CLOGHBOOLA TRIEN | bar: Week 21 Mo 23 to Week 21 Fr 27
TO-22-220 kV A1 @ DSN-02 | DUNSTOWN 220 kV A1 | bar: Week 21 Mo 23 to Week 21 Fr 27
TO-22-220 kV B1 @ DSN-02 | DUNSTOWN 220 kV B1 | bar: Week 21 Mo 23 to Week 21 Fr 27
TO-22-220 kV A2 @ INC-03 | INCHICORE 220 kV A2 | bar: Week 21 Mo 23 to Week 21 Fr 27
TO-22-220 kV B2 @ INC-03 | INCHICORE 220 kV B2 | bar: Week 21 Mo 23 to Week 21 Fr 27
TO-22-RYB GIS-T108-01 | RYEBROOK GIS T108 | bar: Week 21 Mo 23 to Week 21 Fr 27
TO-22-CD-T103-01 | CARRIGADROHID T103 | bar: Week 21 Mo 23 to Week 22 Fr 3
TO-22-110 kV A1 @ CLG-03 | CLOGHRAN 110 kV A1 | bar: Week 21 Mo 23 to Week 22 Fr 3
TO-22-110 kV B1 @ CLG-05 | CLOGHRAN 110 kV B1 | bar: Week 21 Mo 23 to Week 22 Fr 3
TO-22-CLG-110K1-04 | CLOGHRAN 110K1 | bar: Week 21 Mo 23 to Week 22 Fr 3
TO-22-CLG-110SA1-2CB-04 | CLOGHRAN 110SA1-2CB | bar: Week 21 Mo 23 to Week 22 Fr 3
TO-22-CLG-110SB1-2CB-06 | CLOGHRAN 110SB1-2CB | bar: Week 21 Mo 23 to Week 22 Fr 3
TO-22-DSN-220K1-2-02 | DUNSTOWN 220K1-2 | bar: Week 21 Mo 23 to Week 22 Fr 3
TO-22-INC-PB-2-02 | INCHICORE POOLBEG 2 | bar: Week 21 Mo 23 to Week 22 Fr 3
TO-22-MP GIS-T4201-01 | MONEYPOINT GIS T4201 | bar: Week 21 Mo 23 to Week 22 Fr 3
TO-22-SLB-T132-01 | SLIABH BAWN T132 | bar: Week 21 Tu 24 to Week 21 We 25
TO-22-CHA-110SA1-2CB-02 | CHARLEVILLE 110SA1-2CB | bar: Week 21 Tu 24 to Week 21 Fr 27
TO-22-COL-FIN GIS-1-03 | COLLEGE PARK FINGLAS GIS | bar: Week 21 We 25
TO-22-CNO-T131-02 | COOLNANOONAGH T131 | bar: Week 21 We 25
TO-22-FLA-SRA-1-02 | FLAGFORD SRANANAGH | bar: Su 22 to Week 21 We 25
TO-22-SRA-220SA1-02 | SRANANAGH 220SA1 | bar: Su 22 to Week 21 We 25
TO-22-SRA-220SA2-02 | SRANANAGH 220SA2 | bar: Su 22 to Week 21 We 25
TO-22-SRA-T2102-02 | SRANANAGH T2102 | bar: Su 22 to Week 21 We 25
TO-22-TH-T2001/2-01 | TURLOUGH HILL T2001/2 | bar: Week 21 Th 26 to Week 22 Mo 6
TO-22-AA GIS-T104-01 | ARDNACRUSHA GIS T104 | bar: Su 22 to Week 21 Fr 27
TO-22-BDA-MON-1-02 | BARODA MONREAD | bar: Su 22 to Week 21 Fr 27
TO-22-LIS-LOU-1-01 | LISDRUM LOUTH | bar: Su 22 to Week 21 Fr 27
TO-22-BK-CBR-1-02 | BELLACORICK CASTLEBAR | bar: Week 21 Sa 28 to Week 21 Su 29
TO-22-CBR-110SA1-2CB-02 | CASTLEBAR 110SA1-2CB | bar: Week 21 Sa 28 to Week 21 Su 29
TO-22-DAL-T141-01 | DALLOW T141 | bar: Week 21 Sa 28 to Week 21 Su 29
TO-22-DAL,T-DAL-1-01 | DALLOW tee DALLOW | bar: Week 21 Sa 28 to Week 21 Su 29
TO-22-DAL,T-DEY-1-01 | DALLOW tee DERRYCARNEY | bar: Week 21 Sa 28 to Week 21 Su 29
TO-22-DAL,T-SH-1-01 | DALLOW tee SHANNONBRIDGE | bar: Week 21 Sa 28 to Week 21 Su 29
TO-22-DAL,T-SH-1-02 | bar: Week 21 Sa 28 to Week 22 Mo 6
TO-22-TH-T2003/4-01 | TURLOUGH HILL T2003/4 | bar: Su 22 to Week 21 Sa 28
Outages commencing/returning in Week 22
OUTAGE ID | PLANT | Week 21 Mo 23: Week 21; Week 22 Mo 30: Week 22
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6
TO-22-SNU-T104-01 | SNUGBOROUGH T104 | bar: Week 22 Mo 30
Report covers outages commencing/returning/spanning the period: 23/05/2022 - 05/06/2022
Outages commencing/returning in Week 22
OUTAGE ID | PLANT | Week 21 Mo 23: Week 21; Week 22 Mo 30: Week 22
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6
TO-22-GOR-PLA-1-03 | GORMAN PLATIN | bar: Week 22 Mo 30 to Week 22 Tu 31
TO-22-PLA-110SA1-02 | PLATIN 110SA1 | bar: Week 22 Mo 30 to Week 22 Tu 31
TO-22-PLA-110SA2-02 | PLATIN 110SA2 | bar: Week 22 Mo 30 to Week 22 Tu 31
TO-22-PLA-T105-05 | PLATIN T105 | bar: Week 22 Mo 30 to Week 22 Tu 31
TO-22-110 kV A1 @ CLO-01 | CLOGHER 110 kV A1 | bar: Week 22 Mo 30 to Week 22 We 1
TO-22-110 kV B1 @ CLO-01 | CLOGHER 110 kV B1 | bar: Week 22 Mo 30 to Week 22 We 1
TO-22-SHL-T2016-01 | SHELLYBANKS T2016 | bar: Week 22 Mo 30 to Week 22 We 1
TO-22-KTL-MAY-1-02 | KILTEEL MAYNOOTH | bar: Week 22 Mo 30 to Week 22 Th 2
TO-22-SNU-T104-02 | SNUGBOROUGH T104 | bar: Week 22 Mo 30 to Week 22 Th 2
TO-22-BIN-T141-01 | BINBANE T141 | bar: Week 22 Mo 30 to Week 22 Fr 3
TO-22-220 kV A3 @ PB-01 | POOLBEG 220 kV A3 | bar: Week 22 Mo 30 to Week 22 Fr 3
TO-22-220 kV B3 @ PB-01 | POOLBEG 220 kV B3 | bar: Week 22 Mo 30 to Week 22 Fr 3
TO-22-220 kV A1 @ CDU-04 | CORDUFF 220 kV A1 | bar: Week 22 Mo 30 to Week 22 Mo 6
TO-22-220 kV A3 @ CDU-03 | CORDUFF 220 kV A3 | bar: Week 22 Mo 30 to Week 22 Mo 6
TO-22-220 kV B1 @ CDU-05 | CORDUFF 220 kV B1 | bar: Week 22 Mo 30 to Week 22 Mo 6
TO-22-220 kV B3 @ CDU-03 | CORDUFF 220 kV B3 | bar: Week 22 Mo 30 to Week 22 Mo 6
TO-22-CDU-220K1-3-03 | CORDUFF 220K1-3 | bar: Week 22 Mo 30 to Week 22 Mo 6
TO-22-KLN-SH-1-01 | KILLONAN SHANNONBRIDGE | bar: Week 22 Mo 30 to Week 22 Mo 6
TO-22-MOY-T142-01 | MOY T142 | bar: Week 22 Mo 30 to Week 22 Mo 6
TO-22-CBR-SVC-01 | CASTLEBAR SVC | bar: Su 22 to Week 22 Mo 30
TO-22-BYH-GLE-1-02 | BALLYNAHULLA GLENLARA | bar: Week 22 Tu 31 to Week 22 Fr 3
TO-22-KIN-MUL-1-02 | KINNEGAD MULLINGAR | bar: Week 22 Tu 31 to Week 22 Fr 3
TO-22-LA-MUL-1-01 | LANESBORO MULLINGAR | bar: Week 22 Tu 31 to Week 22 Fr 3
TO-22-MUL-110SA1-2CB-01 | MULLINGAR 110SA1-2CB | bar: Week 22 Tu 31 to Week 22 Fr 3
TO-22-MUL-CAP1-01 | MULLINGAR CAP1 | bar: Week 22 Tu 31 to Week 22 Fr 3
TO-22-MUL-T101-01 | MULLINGAR T101 | bar: Week 22 Tu 31 to Week 22 Fr 3
TO-22-MUL-T141-01 | MULLINGAR T141 | bar: Week 22 Tu 31 to Week 22 Fr 3
TO-22-MP GIS-400K3-02 | MONEYPOINT GIS 400K3 | bar: Week 22 We 1
TO-22-CVW-T101-01 | CASTLEVIEW T101 | bar: Week 22 We 1 to Week 22 Th 2
TO-22-110 kV B3 @ CDU-01 | CORDUFF 110 kV B3 | bar: Week 22 We 1 to Week 22 Th 2
TO-22-CDU-SNU-1-02 | CORDUFF SNUGBOROUGH | bar: Week 22 We 1 to Week 22 Th 2
TO-22-COW-T142-01 | COW CROSS T142 | bar: Week 22 We 1 to Week 22 Th 2
TO-22-110 kV A2 @ LOU-01 | LOUTH 110 kV A2 | bar: Week 22 We 1 to Week 22 Mo 6
TO-22-110 kV B2 @ LOU-02 | LOUTH 110 kV B2 | bar: Week 22 We 1 to Week 22 Mo 6
TO-22-CF-CLO-1-01 | CATHALEENS FALL CLOGHER 1 | bar: Week 22 Th 2 to Week 22 Fr 3
TO-22-110 kV A1 @ CLO-02 | CLOGHER 110 kV A1 | bar: Week 22 Th 2 to Week 22 Fr 3
TO-22-110 kV B1 @ CLO-02 | CLOGHER 110 kV B1 | bar: Week 22 Th 2 to Week 22 Fr 3
TO-22-CDU-PLA-1-01 | CORDUFF PLATIN | bar: Su 22 to Week 22 Th 2
TO-22-KLN-T2101-02 | KILLONAN T2101 | bar: Su 22 to Week 22 Fr 3
Outages spanning Weeks 21-22
OUTAGE ID | PLANT | Week 21 Mo 23: Week 21; Week 22 Mo 30: Week 22
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6
TO-22-BIN-T142-01 | BINBANE T142
TO-22-CSH-220K1-2-01 | CASHLA 220K1-2
TO-22-CBR-CLN-1-01 | CASTLEBAR CLOON
TO-22-CBR-SVC-04 | CASTLEBAR SVC
TO-22-CBR-T141-01 | CASTLEBAR T141
TO-22-CLH-TRI-1-01 | CLAHANE TRIEN
TO-22-CUS-MLC-1-01 | CUSHALING MOUNTLUCAS
TO-22-CUS-MLC-1-02
TO-22-110 kV A2 @ DEY-02 | DERRYCARNEY 110 kV A2
TO-22-110 kV B2 @ DEY-03 | DERRYCARNEY 110 kV B2
TO-22-DEY-110K2-02 | DERRYCARNEY 110K2
TO-22-DRU-CAP2-02 | DRUMLINE CAP2
TO-22-DDK-MLN-1-01 | DUNDALK MULLAGHARLIN
TO-22-220 kV A1/A2 @ FIN-01 | FINGLAS 220 kV A1/A2
TO-22-FIN-220K1-06 | FINGLAS 220K1
TO-22-FIN-220K2-01 | FINGLAS 220K2
TO-22-GGO-220K1-2-02 | GLANAGOW 220K1-2
Report covers outages commencing/returning/spanning the period: 23/05/2022 - 05/06/2022
Outages spanning Weeks 21-22
OUTAGE ID | PLANT | Week 21 Mo 23: Week 21; Week 22 Mo 30: Week 22
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6
TO-22-GGO-RAF-1-02 | GLANAGOW RAFFEEN
TO-22-GOR-220K1-2-01 | GORMAN 220K1-2
TO-22-GI-KKY-1-01 | GREAT ISLAND KILKENNY
TO-22-INC-220K1-2-03 | INCHICORE 220K1-2
TO-22-KPG-TB-1-01 | KILPADDOGE TARBERT 1
TO-22-LET-M/CAP1-01 | LETTERKENNY M/CAP1
TO-22-LIS-LOU-1-03 | LISDRUM LOUTH
TO-22-LOU-AT3-01 | LOUTH AT3
TO-22-MAY-WOO-1-02 | MAYNOOTH WOODLAND
TO-22-MAY-WOO-1-12
TO-22-MUL-CAP2-03 | MULLINGAR CAP2
TO-22-NAV-M/CAP1-01 | NAVAN M/CAP1
TO-22-OST-T4202-03 | OLDSTREET T4202
TO-22-OST-TY-1-03 | OLDSTREET TYNAGH
TO-22-PB-R2002-01 | POOLBEG R2002
TO-22-RYB GIS-T133-02 | RYEBROOK GIS T133
TO-22-220 kV A1 @ TB-01 | TARBERT 220 kV A1
TO-22-220 kV B1 @ TB-01 | TARBERT 220 kV B1
TO-22-TB-T101-02 | TARBERT T101
TO-22-TB-T102-02 | TARBERT T102
TO-22-TB-T2004-03 | TARBERT T2004
TO-22-110 kV A1 @ TRI-01 | TRIEN 110 kV A1
TO-22-TRI-110SA1-2CB-01 | TRIEN 110SA1-2CB
TO-22-TRI-110SA1-3CB-01 | TRIEN 110SA1-3CB
TO-22-TRI-CAP1-01 | TRIEN CAP1
TO-22-TRI-T141-01 | TRIEN T141
TO-22-WOO-T4201-05 | WOODLAND T4201