## Wks 21 - 22
Report covers outages commencing/returning/spanning the period: 22/05/2023 - 04/06/2023
Outages commencing/returning in Week 21
OUTAGE ID | PLANT |  | Week 21 | [6 empty] | Week 22
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5
TO-23-MP GIS-T4001-01 | MONEYPOINT GIS T4001 | bar: Week 21 Mo 22 to Week 21 Tu 23
TO-23-110 kV A1 @ AA GIS-01 | ARDNACRUSHA GIS 110 kV A1 | bar: Week 21 Mo 22 to Week 21 Tu 23; Week 21 Fr 26
TO-23-110 kV B1 @ AA GIS-01 | ARDNACRUSHA GIS 110 kV B1 | bar: Week 21 Mo 22 to Week 21 Tu 23; Week 21 Fr 26
TO-23-AA GIS-110SA1-2CB-01 | ARDNACRUSHA GIS 110SA1-2CB | bar: Week 21 Mo 22 to Week 21 Tu 23; Week 21 Fr 26
TO-23-AA GIS-110SA1-3CB-02 | ARDNACRUSHA GIS 110SA1-3CB | bar: Week 21 Mo 22 to Week 21 Tu 23; Week 21 Fr 26
TO-23-AA GIS-110SB1-2CB-02 | ARDNACRUSHA GIS 110SB1-2CB | bar: Week 21 Mo 22 to Week 21 Tu 23; Week 21 Fr 26
TO-23-AA GIS-110SB1-3CB-02 | ARDNACRUSHA GIS 110SB1-3CB | bar: Week 21 Mo 22 to Week 21 Tu 23; Week 21 Fr 26
TO-23-AA GIS-LIM-1-01 | ARDNACRUSHA GIS LIMERICK | bar: Week 21 Mo 22 to Week 21 Tu 23; Week 21 Fr 26
TO-23-110 kV A1 @ CBT-04 | CASTLEBAGOT 110 kV A1 | bar: Week 21 Mo 22 to Week 21 Tu 23; Week 21 Fr 26
TO-23-110 kV A2 @ CBT-01 | CASTLEBAGOT 110 kV A2 | bar: Week 21 Mo 22 to Week 21 Tu 23; Week 21 Fr 26
TO-23-CBT-110K1-06 | CASTLEBAGOT 110K1 | bar: Week 21 Mo 22 to Week 21 Tu 23; Week 21 Fr 26
TO-23-CBT-110SA1-2CB-01 | CASTLEBAGOT 110SA1-2CB | bar: Week 21 Mo 22 to Week 21 Tu 23; Week 21 Fr 26
TO-23-CBT-110SA2-4CB-07 | CASTLEBAGOT 110SA2-4CB | bar: Week 21 Mo 22 to Week 21 Tu 23; Week 21 Fr 26
TO-23-KLN-T2101-01 | KILLONAN T2101 | bar: Week 21 Mo 22 to Week 21 Tu 23; Week 21 Fr 26
TO-23-KBY-MR-2-01 | KILBARRY MARINA 2 | bar: Week 21 Mo 22 to Week 21 Tu 23; Week 21 Fr 26 to Week 22 Mo 29
TO-23-KPG-TRL-1-03 | KILPADDOGE TRALEE 1 | bar: Week 21 Mo 22 to Week 21 Tu 23; Week 21 Fr 26 to Week 22 Tu 30
TO-23-CLE-CDU-1-01 | CLONEE CORDUFF | bar: Week 21 Mo 22 to Week 21 Tu 23; Week 21 Fr 26 to Week 22 Fr 2
TO-23-220 kV A1 @ CDU-04 | CORDUFF 220 kV A1 | bar: Week 21 Mo 22 to Week 21 Tu 23; Week 21 Fr 26 to Week 22 Fr 2
TO-23-220 kV B1 @ CDU-04 | CORDUFF 220 kV B1 | bar: Week 21 Mo 22 to Week 21 Tu 23; Week 21 Fr 26 to Week 22 Fr 2
TO-23-BEG-CKM GIS-1-01 | BALLYBEG CARRICKMINES GIS | bar: Su 21 to Week 21 Mo 22
TO-23-110 kV A1 @ BVK-01 | BALLYVOUSKILL 110 kV A1 | bar: Week 21 Tu 23
TO-23-110 kV B1 @ BVK-01 | BALLYVOUSKILL 110 kV B1 | bar: Week 21 Tu 23
TO-23-BVK-110K1-01 | BALLYVOUSKILL 110K1 | bar: Week 21 Tu 23
TO-23-BVK-110SA1-2CB-01 | BALLYVOUSKILL 110SA1-2CB | bar: Week 21 Tu 23
TO-23-BVK-110SB1-2CB-01 | BALLYVOUSKILL 110SB1-2CB | bar: Week 21 Tu 23
TO-23-GI-WAT-1-01 | GREAT ISLAND WATERFORD 1 | bar: Week 21 Tu 23; Week 21 Fr 26
TO-23-220 kV A2 @ PB-01 | POOLBEG 220 kV A2 | bar: Su 21 to Week 21 Tu 23
TO-23-220 kV B2 @ PB-01 | POOLBEG 220 kV B2 | bar: Su 21 to Week 21 Tu 23
TO-23-PB-220SA1-2-04 | POOLBEG 220SA1-2 | bar: Su 21 to Week 21 Tu 23
TO-23-PB-220SB1-2-03 | POOLBEG 220SB1-2 | bar: Su 21 to Week 21 Tu 23
TO-23-MLC-T121-01 | MOUNTLUCAS T121
TO-23-DFR-T122-02 | DUNFIRTH T122
TO-23-DFR,T-DFR-1-03 | DUNFIRTH tee DUNFIRTH
TO-23-DFR,T-KIN-1-06 | DUNFIRTH tee KINNEGAD
TO-23-GAL-GAL GIS-1-02 | GALWAY GALWAY GIS 1
TO-23-110 kV A2 @ GAL GIS-02 | GALWAY GIS 110 kV A2
TO-23-110 kV B2 @ GAL GIS-02 | GALWAY GIS 110 kV B2
TO-23-GAL GIS-110K2-03 | GALWAY GIS 110K2
TO-23-GAL GIS-110SA1-2CB-04 | GALWAY GIS 110SA1-2CB
TO-23-GAL GIS-110SB1-2CB-04 | GALWAY GIS 110SB1-2CB
TO-23-CKM-PB-1-04 | CARRICKMINES POOLBEG | bar: Week 21 Fr 26
TO-23-CKM-PST2201-04 | CARRICKMINES PST2201 | bar: Week 21 Fr 26
TO-23-INC-PB-1-02 | INCHICORE POOLBEG 1 | bar: Week 21 Fr 26
TO-23-PB-220K2-3-04 | POOLBEG 220K2-3 | bar: Week 21 Fr 26
TO-23-PB-220SA1-2-02 | POOLBEG 220SA1-2 | bar: Week 21 Fr 26
TO-23-PB-220SB1-2-02 | POOLBEG 220SB1-2 | bar: Week 21 Fr 26
TO-23-PB-R2001-03 | POOLBEG R2001 | bar: Week 21 Fr 26
TO-23-CD-T103-01 | CARRIGADROHID T103 | bar: Su 21 to Week 21 Tu 23
TO-23-110 kV B1 @ CF-01 | CATHALEENS FALL 110 kV B1
TO-23-CF-T103-02 | CATHALEENS FALL T103
TO-23-CSH-GAL-3-02 | CASHLA GALWAY 3 | bar: Su 21 to Week 21 Tu 23
TO-23-DFR,T-RNW-1-06 | DUNFIRTH tee RINAWADE | bar: Su 21 to Week 21 Tu 23
TO-23-HN-T2002-01 | HUNTSTOWN T2002 | bar: Week 21 Fr 26 to Week 22 Mo 5
TO-23-BYH-T2101-01 | BALLYNAHULLA T2101 | bar: Su 21 to Week 21 Tu 23; Week 21 Fr 26
TO-23-WOH-T122-01 | WOODHOUSE T122 | bar: Su 21 to Week 21 Tu 23; Week 21 Fr 26
Outages commencing/returning in Week 22
OUTAGE ID | PLANT | Week 21 Mo 22: Week 21; Week 22 Mo 29: Week 22
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5
Report covers outages commencing/returning/spanning the period: 22/05/2023 - 04/06/2023
Outages commencing/returning in Week 22
OUTAGE ID | PLANT | Week 21 Mo 22: Week 21; Week 22 Mo 29: Week 22
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5
TO-23-KPG-110K3-01 | KILPADDOGE 110K3
TO-23-INC-PB-1-04 | INCHICORE POOLBEG 1
TO-23-220 kV A1 @ PB-02 | POOLBEG 220 kV A1
TO-23-220 kV A2 @ PB-02 | POOLBEG 220 kV A2
TO-23-220 kV B1 @ PB-02 | POOLBEG 220 kV B1
TO-23-220 kV B2 @ PB-02 | POOLBEG 220 kV B2
TO-23-PB-220SA1-2-05 | POOLBEG 220SA1-2
TO-23-PB-220SB1-2-05 | POOLBEG 220SB1-2
TO-23-ARK-CKM GIS-1-01 | ARKLOW CARRICKMINES GIS | bar: Week 22 We 31 to Week 22 Fr 2
TO-23-220 kV A3 @ CKM GIS-01 | CARRICKMINES GIS 220 kV A3 | bar: Week 22 We 31 to Week 22 Fr 2
TO-23-220 kV B3 @ CKM GIS-01 | CARRICKMINES GIS 220 kV B3 | bar: Week 22 We 31 to Week 22 Fr 2
TO-23-CKM GIS-220K3-01 | CARRICKMINES GIS 220K3 | bar: Week 22 We 31 to Week 22 Fr 2
TO-23-CKM GIS-220SA1-3CB-03 | CARRICKMINES GIS 220SA1-3CB | bar: Week 22 We 31 to Week 22 Fr 2
TO-23-CKM GIS-220SB1-3CB-03 | CARRICKMINES GIS 220SB1-3CB | bar: Week 22 We 31 to Week 22 Fr 2
TO-23-110 kV A1/A2 @ CLA-02 | CLASHAVOON 110 kV A1/A2 | bar: Week 22 We 31 to Week 22 Fr 2
TO-23-110 kV B1/B2 @ CLA-02 | CLASHAVOON 110 kV B1/B2 | bar: Week 22 We 31 to Week 22 Fr 2
TO-23-CLA-110K1-2-01 | CLASHAVOON 110K1-2 | bar: Week 22 We 31 to Week 22 Fr 2
TO-23-220 kV A1 @ CDU-02 | CORDUFF 220 kV A1 | bar: Week 22 We 31 to Week 22 Fr 2
TO-23-220 kV B1 @ CDU-02 | CORDUFF 220 kV B1 | bar: Week 22 We 31 to Week 22 Fr 2
TO-23-CDU-HN-1-01 | CORDUFF HUNTSTOWN | bar: Week 22 We 31 to Week 22 Fr 2
TO-23-REM-110SA1-02 | REAMORE 110SA1 | bar: Week 22 We 31 to Week 22 Fr 2
TO-23-REM-110SA2-02 | REAMORE 110SA2 | bar: Week 22 We 31 to Week 22 Fr 2
TO-23-REM-T141-03 | REAMORE T141 | bar: Week 22 We 31 to Week 22 Fr 2
TO-23-REM-T142-02 | REAMORE T142 | bar: Week 22 We 31 to Week 22 Fr 2
TO-23-REM-TRL-1-02 | REAMORE TRALEE | bar: Week 22 We 31 to Week 22 Fr 2
TO-23-110 kV A2 @ CSH-06 | CASHLA 110 kV A2 | bar: Week 22 We 31 to Week 22 Mo 5
TO-23-110 kV B2 @ CSH-07 | CASHLA 110 kV B2 | bar: Week 22 We 31 to Week 22 Mo 5
TO-23-CSH-GAL-2-07 | CASHLA GALWAY 2 | bar: Week 22 We 31 to Week 22 Mo 5
TO-23-CSH-GAL-2-02 | bar: Week 22 Mo 29 to Week 22 Mo 5
TO-23-GAL-110K1-2-01 | GALWAY 110K1-2 | bar: Week 22 Mo 29 to Week 22 Mo 5
TO-23-MCE-T124-02 | MACETOWN T124 | bar: Week 22 We 31 to Week 22 Mo 5
TO-23-CFN-SH-1-01 | CLONIFFEEN SHANNONBRIDGE | bar: Su 21 to Week 21 Su 28
TO-23-CFN-T232-01 | CLONIFFEEN T232 | bar: Su 21 to Week 21 Su 28
TO-23-MP GIS-OST-1-01 | MONEYPOINT GIS OLDSTREET | bar: Su 21 to Week 21 Su 28
TO-23-KPG-110SA2-4CB-02 | KILPADDOGE 110SA2-4CB
TO-23-BNK-CBT-2-01 | BARNAKYLE CASTLEBAGOT 2 | bar: Week 22 We 31
TO-23-KPG-110SB1-2CB-01 | KILPADDOGE 110SB1-2CB | bar: Week 22 We 31
TO-23-PRO-TB-1-02 | PROSPECT TARBERT | bar: Su 21 to Week 21 Su 28; Week 22 We 31
TO-23-KPG-110SB1-3CB-02 | KILPADDOGE 110SB1-3CB | bar: Week 22 Th 1
TO-23-FIN GIS-T144-01 | FINGLAS GIS T144 | bar: Week 22 Th 1 to Week 22 Sa 3
TO-23-KPG-110SB2-4CB-01 | KILPADDOGE 110SB2-4CB | bar: Week 22 Fr 2
TO-23-CDU-RYB GIS-1-02 | CORDUFF RYEBROOK GIS | bar: Su 21 to Week 21 Su 28; Week 22 We 31 to Week 22 Fr 2
Outages spanning Weeks 21-22
OUTAGE ID | PLANT | Week 21 Mo 22: Week 21; Week 22 Mo 29: Week 22
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5
TO-23-220 kV A2 @ AD-01 | AGHADA 220 kV A2
TO-23-220 kV B2 @ AD-01 | AGHADA 220 kV B2
TO-23-AD-SA1-2CB-01 | AGHADA 220SA1-2CB
TO-23-AD-SB1-2CB-01 | AGHADA 220SB1-2CB
TO-23-AD-T2001-03 | AGHADA T2001
TO-23-ARV-GWE-1-03 | ARVA GORTAWEE
TO-23-BDN-T141-01 | BALLYDINE T141
TO-23-CSH-220K2-4-01 | CASHLA 220K2-4
TO-23-CSH-CAP2-04 | CASHLA CAP2
TO-23-CLG-110K1-01 | CLOGHRAN 110K1
TO-23-CDU-GLN-1-03 | CORDUFF GALLANSTOWN
TO-23-CDU-MUL-1-02 | CORDUFF MULLINGAR
TO-23-CUL-DGN-1-01 | CULLENAGH DUNGARVAN
TO-23-DRY-T141-02 | DRYBRIDGE T141
Report covers outages commencing/returning/spanning the period: 22/05/2023 - 04/06/2023
Outages spanning Weeks 21-22
OUTAGE ID | PLANT | Week 21 Mo 22: Week 21; Week 22 Mo 29: Week 22
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5
TO-23-DDK-LOU-1-01 | DUNDALK LOUTH
TO-23-FIN GIS-110K6-01 | FINGLAS GIS 110K6
TO-23-FLA-T2101-02 | FLAGFORD T2101
TO-23-GAL-110K2-3-02 | GALWAY 110K2-3
TO-23-GAL-T142-02 | GALWAY T142
TO-23-GGO-220K1-2-01 | GLANAGOW 220K1-2
TO-23-INC-220K1-2-01 | INCHICORE 220K1-2
TO-23-KLS-220K1-2-04 | KELLIS 220K1-2
TO-23-110 kV B2 @ KBY-03 | KILBARRY 110 kV B2
TO-23-KBY-MR-1-01 | KILBARRY MARINA 1
TO-23-KBY-MR-2-03 | KILBARRY MARINA 2
TO-23-220 kV B1/B2 @ KRA-01 | KNOCKRAHA 220 kV B1/B2
TO-23-KRA-220K1-05 | KNOCKRAHA 220K1
TO-23-KRA-220K1-2-03 | KNOCKRAHA 220K1-2
TO-23-KRA-220SB2-4CB-02 | KNOCKRAHA 220SB2-4CB
TO-23-LET-M/CAP1-01 | LETTERKENNY M/CAP1
TO-23-LET-SVC-01 | LETTERKENNY SVC
TO-23-LET-TIV-1-01 | LETTERKENNY TIEVEBRACK
TO-23-LIS-T141-01 | LISDRUM T141
TO-23-110 kV A2 @ LOU-01 | LOUTH 110 kV A2
TO-23-110 kV B2 @ LOU-01 | LOUTH 110 kV B2
TO-23-220 kV A1/A2 @ LOU-01 | LOUTH 220 kV A1/A2
TO-23-MP GIS-T4202-02 | MONEYPOINT GIS T4202
TO-23-MUL-CAP1-02 | MULLINGAR CAP1
TO-23-MUL-CAP2-01 | MULLINGAR CAP2
TO-23-PB-R2002-02 | POOLBEG R2002
TO-23-PRO-TB-1-04 | PROSPECT TARBERT
TO-23-TB-T101-02 | TARBERT T101
TO-23-TB-T2003-03 | TARBERT T2003
TO-23-TB-T2004-02 | TARBERT T2004
TO-23-TB-T2101-02 | TARBERT T2101
TO-23-THU-CAP2-01 | THURLES CAP2