## Wks 23 - 24
Report covers outages commencing/returning/spanning the period: 05/06/2023 - 18/06/2023
Outages commencing/returning in Week 23
OUTAGE ID | PLANT |  | Week 23 | [6 empty] | Week 24
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19
TO-23-KPG-KNR-1-110-01 | KILPADDOGE KNOCKANURE 110 | bar: Week 23 Tu 6 to Week 23 Th 8
TO-23-CBT-T2104-01 | CASTLEBAGOT T2104 | bar: Week 23 Tu 6 to Week 23 Fr 9
TO-23-CRU-T221-02 | CRUISERATH T221 | bar: Week 23 Tu 6 to Week 23 Fr 9
TO-23-AA GIS-T102-04 | ARDNACRUSHA GIS T102 | bar: Week 23 Tu 6 to Week 24 Mo 19
TO-23-220 kV A4 @ CDU-01 | CORDUFF 220 kV A4 | bar: Week 23 Tu 6 to Week 24 Mo 19
TO-23-220 kV B4 @ CDU-01 | CORDUFF 220 kV B4 | bar: Week 23 Tu 6 to Week 24 Mo 19
TO-23-KLS-KKY-1-02 | KELLIS KILKENNY | bar: Week 23 Tu 6 to Week 24 Mo 19
TO-23-KKY-110SA1-2CB-02 | KILKENNY 110SA1-2CB | bar: Week 23 Tu 6 to Week 24 Mo 19
TO-23-KKY-T141-02 | KILKENNY T141 | bar: Week 23 Tu 6 to Week 24 Mo 19
TO-23-BAN-BRI-2-01 | BANDON BRINNY 2 | bar: Week 23 We 7
TO-23-BRI-T102-01 | BRINNY T102 | bar: Week 23 We 7
TO-23-KPG-RAT-1-01 | KILPADDOGE RATHKEALE | bar: Week 23 We 7
TO-23-110 kV A1 @ CAH-01 | CAHIR 110 kV A1 | bar: Week 23 We 7 to Week 23 Th 8
TO-23-110 kV A2 @ CAH-01 | CAHIR 110 kV A2 | bar: Week 23 We 7 to Week 23 Th 8
TO-23-CAH-110K1-2-03 | CAHIR 110K1-2 | bar: Week 23 We 7 to Week 23 Th 8
TO-23-110 kV A1 @ BVK-01 | BALLYVOUSKILL 110 kV A1 | bar: Week 23 We 7 to Week 23 Fr 9
TO-23-110 kV B1 @ BVK-01 | BALLYVOUSKILL 110 kV B1 | bar: Week 23 We 7 to Week 23 Fr 9
TO-23-BVK-110K1-01 | BALLYVOUSKILL 110K1 | bar: Week 23 We 7 to Week 23 Fr 9
TO-23-BVK-110SA1-2CB-01 | BALLYVOUSKILL 110SA1-2CB | bar: Week 23 We 7 to Week 23 Fr 9
TO-23-BVK-110SB1-2CB-01 | BALLYVOUSKILL 110SB1-2CB | bar: Week 23 We 7 to Week 23 Fr 9
TO-23-220 kV A1 @ WOO-01 | WOODLAND 220 kV A1 | bar: Week 23 We 7 to Week 23 Fr 9
TO-23-110 kV A1 @ PA-01 | POLLAPHUCA 110 kV A1 | bar: Week 23 We 7 to Week 24 Mo 19
TO-23-110 kV A2 @ PA-01 | POLLAPHUCA 110 kV A2 | bar: Week 23 We 7 to Week 24 Mo 19
TO-23-PA-110SA1-01 | POLLAPHUCA 110SA1 | bar: Week 23 We 7 to Week 24 Mo 19
TO-23-PA-110SA2-01 | POLLAPHUCA 110SA2 | bar: Week 23 We 7 to Week 24 Mo 19
TO-23-PA-T101-01 | POLLAPHUCA T101 | bar: Week 23 We 7 to Week 24 Mo 19
TO-23-STR-T141-01 | STRATFORD T141 | bar: Week 23 We 7 to Week 24 Mo 19
TO-23-STR,T-CLW-1-01 | STRATFORD tee CARLOW | bar: Week 23 We 7 to Week 24 Mo 19
TO-23-STR,T-PA-1-04 | STRATFORD tee POLLAPHUCA | bar: Week 23 We 7 to Week 24 Mo 19
TO-23-STR,T-STR-1-01 | STRATFORD tee STRATFORD | bar: Week 23 We 7 to Week 24 Mo 19
TO-23-110 kV A1/A2 @ CLA-02 | CLASHAVOON 110 kV A1/A2 | bar: Su 4 to Week 23 We 7
TO-23-110 kV B1/B2 @ CLA-02 | CLASHAVOON 110 kV B1/B2 | bar: Su 4 to Week 23 We 7
TO-23-CLA-110K1-2-01 | CLASHAVOON 110K1-2 | bar: Su 4 to Week 23 We 7
TO-23-MCE-T124-02 | MACETOWN T124 | bar: Su 4 to Week 23 We 7
TO-23-INC-PB-1-04 | INCHICORE POOLBEG 1 | bar: Week 23 Th 8 to Week 23 Fr 9
TO-23-220 kV A1 @ PB-02 | POOLBEG 220 kV A1 | bar: Week 23 Th 8 to Week 23 Fr 9
TO-23-220 kV A2 @ PB-02 | POOLBEG 220 kV A2 | bar: Week 23 Th 8 to Week 23 Fr 9
TO-23-220 kV B1 @ PB-02 | POOLBEG 220 kV B1 | bar: Week 23 Th 8 to Week 23 Fr 9
TO-23-220 kV B2 @ PB-02 | POOLBEG 220 kV B2 | bar: Week 23 Th 8 to Week 23 Fr 9
TO-23-PB-220SA1-2-05 | POOLBEG 220SA1-2 | bar: Week 23 Th 8 to Week 23 Fr 9
TO-23-PB-220SB1-2-05 | POOLBEG 220SB1-2 | bar: Week 23 Th 8 to Week 23 Fr 9
TO-23-BAN-BRI-1-01 | BANDON BRINNY 1 | bar: Week 23 Th 8 to Week 24 Fr 16
TO-23-BRI-T101-01 | BRINNY T101 | bar: Week 23 Th 8 to Week 24 Fr 16
TO-23-BYH-T2102-02 | BALLYNAHULLA T2102 | bar: Week 23 Fr 9 to Week 24 Mo 19
TO-23-COW-T142-01 | COW CROSS T142 | bar: Week 23 Sa 10 to Week 24 Mo 19
TO-23-220 kV A1 @ CDU-02 | CORDUFF 220 kV A1 | bar: Su 4 to Week 23 Sa 10
TO-23-220 kV B1 @ CDU-02 | CORDUFF 220 kV B1 | bar: Su 4 to Week 23 Sa 10
TO-23-CDU-HN-1-01 | CORDUFF HUNTSTOWN | bar: Su 4 to Week 23 Sa 10
TO-23-HN-T2002-01 | HUNTSTOWN T2002 | bar: Su 4 to Week 23 Sa 10
Outages commencing/returning in Week 24
OUTAGE ID | PLANT | Week 23 Mo 5: Week 23; Week 24 Mo 12: Week 24
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19
TO-23-KYT-T232-01 | KELLYSTOWN T232 | bar: Week 24 Mo 12
TO-23-CRU-T223-02 | CRUISERATH T223 | bar: Week 24 Mo 12; Week 24 Th 15
TO-23-ATE-110SA1-2CB-01 | ATHEA 110SA1-2CB | bar: Week 24 Mo 12; Week 24 Th 15 to Week 24 Fr 16
TO-23-ATE-DRO-1-01 | ATHEA DROMADA | bar: Week 24 Mo 12; Week 24 Th 15 to Week 24 Fr 16
TO-23-ATE-KNR-1-01 | ATHEA KNOCKANURE | bar: Week 24 Mo 12; Week 24 Th 15 to Week 24 Fr 16
TO-23-ATE-T121-01 | ATHEA T121 | bar: Week 24 Mo 12; Week 24 Th 15 to Week 24 Fr 16
Report covers outages commencing/returning/spanning the period: 05/06/2023 - 18/06/2023
Outages commencing/returning in Week 24
OUTAGE ID | PLANT | Week 23 Mo 5: Week 23; Week 24 Mo 12: Week 24
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19
TO-23-ATE-TOB-1-01 | ATHEA TOBERTOREEN
TO-23-CBT-T2102-01 | CASTLEBAGOT T2102
TO-23-DRO-T121-01 | DROMADA T121
TO-23-ENN-110SA1-2CB-01 | ENNIS 110SA1-2CB
TO-23-ENN-SLC-1-01 | ENNIS SLIEVECALLAN
TO-23-ENN-T101-01 | ENNIS T101
TO-23-ENN-T141-01 | ENNIS T141
TO-23-110 kV A1 @ KNY-01 | KNOCKRANNY 110 kV A1
TO-23-110 kV B1 @ KNY-01 | KNOCKRANNY 110 kV B1
TO-23-KNY-110K1-01 | KNOCKRANNY 110K1
TO-23-KNY-110SA1-2CB-03 | KNOCKRANNY 110SA1-2CB
TO-23-KNY-110SB1-2CB-03 | KNOCKRANNY 110SB1-2CB
TO-23-KNY-FILTER1-01 | KNOCKRANNY FILTER1
TO-23-220 kV A2 @ MP GIS-01 | MONEYPOINT GIS 220 kV A2
TO-23-220 kV B2 @ MP GIS-01 | MONEYPOINT GIS 220 kV B2
TO-23-MP GIS-220K2-01 | MONEYPOINT GIS 220K2
TO-23-MP GIS-220SA1-2CB-01 | MONEYPOINT GIS 220SA1-2CB
TO-23-MP GIS-220SB1-2CB-01 | MONEYPOINT GIS 220SB1-2CB
TO-23-400 kV A4 @ MP GIS-02 | MONEYPOINT GIS 400 kV A4
TO-23-400 kV B4 @ MP GIS-01 | MONEYPOINT GIS 400 kV B4
TO-23-MP GIS-400K4-02 | MONEYPOINT GIS 400K4
TO-23-MP GIS-400SA2-4CB-02 | MONEYPOINT GIS 400SA2-4CB
TO-23-MP GIS-400SB2-4CB-01 | MONEYPOINT GIS 400SB2-4CB
TO-23-SLC-110SA1-01 | SLIEVECALLAN 110SA1
TO-23-SLC-110SA2-01 | SLIEVECALLAN 110SA2
TO-23-SLC-T121-01 | SLIEVECALLAN T121
TO-23-SLC-T122-01 | SLIEVECALLAN T122
TO-23-TOB-T132-01 | TOBERTOREEN T132
TO-23-FIN-NW-1-03 | FINGLAS NORTH WALL | bar: Week 24 Sa 17 to Week 24 Mo 19
TO-23-NW-PB-1-03 | NORTH WALL POOLBEG | bar: Week 24 Sa 17 to Week 24 Mo 19
TO-23-NW-T2004/5-01 | NORTH WALL T2004/5 | bar: Week 24 Sa 17 to Week 24 Mo 19
TO-23-110 kV A1 @ CUL-01 | CULLENAGH 110 kV A1 | bar: Su 4 to Week 23 Su 11
TO-23-110 kV B1 @ CUL-01 | CULLENAGH 110 kV B1 | bar: Su 4 to Week 23 Su 11
TO-23-CUL-DGN-1-01 | CULLENAGH DUNGARVAN | bar: Su 4 to Week 23 Su 11
TO-23-ANR-DOO-1-03 | ANNER DOON
TO-23-ANR-T101-02 | ANNER T101
TO-23-ANR-T103-02 | ANNER T103
TO-23-BAG-T103-01 | BARNAGEERAGH T103
TO-23-CSH-220K2-4-01 | CASHLA 220K2-4 | bar: Su 4 to Week 23 Su 11
TO-23-BOL-T121-01 | BOOLTIAGH T121
TO-23-KYT-T233-02 | KELLYSTOWN T233
TO-23-CDU-GLN-1-03 | CORDUFF GALLANSTOWN | bar: Su 4 to Week 23 Su 11
TO-23-110 kV A1 @ FLA-02 | FLAGFORD 110 kV A1
TO-23-110 kV B1 @ FLA-02 | FLAGFORD 110 kV B1
TO-23-CDU-GLN-1-05 | CORDUFF GALLANSTOWN | bar: Week 24 Sa 17 to Week 24 Mo 19
TO-23-OST-WOO-1-02 | OLDSTREET WOODLAND | bar: Week 24 Sa 17 to Week 24 Mo 19
TO-23-220 kV B1 @ TH-03 | TURLOUGH HILL 220 kV B1
TO-23-TH-T2001/2-02 | TURLOUGH HILL T2001/2
Outages spanning Weeks 23-24
OUTAGE ID | PLANT | Week 23 Mo 5: Week 23; Week 24 Mo 12: Week 24
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19
TO-23-220 kV A2 @ AD-01 | AGHADA 220 kV A2
TO-23-220 kV B2 @ AD-01 | AGHADA 220 kV B2
TO-23-AD-SA1-2CB-01 | AGHADA 220SA1-2CB
TO-23-AD-SB1-2CB-01 | AGHADA 220SB1-2CB
TO-23-AD-T2001-03 | AGHADA T2001
TO-23-ARV-GWE-1-03 | ARVA GORTAWEE
TO-23-BDN-T141-01 | BALLYDINE T141
TO-23-CSH-CAP2-04 | CASHLA CAP2
Report covers outages commencing/returning/spanning the period: 05/06/2023 - 18/06/2023
Outages spanning Weeks 23-24
OUTAGE ID | PLANT | Week 23 Mo 5: Week 23; Week 24 Mo 12: Week 24
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19
TO-23-CSH-GAL-2-02 | CASHLA GALWAY 2
TO-23-CLG-110K1-01 | CLOGHRAN 110K1
TO-23-CDU-MUL-1-02 | CORDUFF MULLINGAR
TO-23-DRY-T141-02 | DRYBRIDGE T141
TO-23-DDK-LOU-1-01 | DUNDALK LOUTH
TO-23-220 kV A2 @ FIN-02 | FINGLAS 220 kV A2
TO-23-FIN GIS-110K6-01 | FINGLAS GIS 110K6
TO-23-FIN-T2104-02 | FINGLAS T2104
TO-23-FLA-T2101-02 | FLAGFORD T2101
TO-23-GAL-110K2-3-02 | GALWAY 110K2-3
TO-23-GGO-220K1-2-01 | GLANAGOW 220K1-2
TO-23-INC-220K1-2-01 | INCHICORE 220K1-2
TO-23-KLS-220K1-2-04 | KELLIS 220K1-2
TO-23-110 kV B2 @ KBY-03 | KILBARRY 110 kV B2
TO-23-KBY-MR-1-01 | KILBARRY MARINA 1
TO-23-KBY-MR-2-03 | KILBARRY MARINA 2
TO-23-KPG-TB-1-02 | KILPADDOGE TARBERT 1
TO-23-220 kV B1/B2 @ KRA-01 | KNOCKRAHA 220 kV B1/B2
TO-23-KRA-220K1-05 | KNOCKRAHA 220K1
TO-23-KRA-220K1-2-03 | KNOCKRAHA 220K1-2
TO-23-KRA-220SB2-4CB-02 | KNOCKRAHA 220SB2-4CB
TO-23-LET-M/CAP1-01 | LETTERKENNY M/CAP1
TO-23-LET-SVC-01 | LETTERKENNY SVC
TO-23-LET-TIV-1-01 | LETTERKENNY TIEVEBRACK
TO-23-LIS-T141-01 | LISDRUM T141
TO-23-110 kV A2 @ LOU-01 | LOUTH 110 kV A2
TO-23-110 kV B2 @ LOU-01 | LOUTH 110 kV B2
TO-23-220 kV A1/A2 @ LOU-01 | LOUTH 220 kV A1/A2
TO-23-MP GIS-T4202-02 | MONEYPOINT GIS T4202
TO-23-MUL-CAP1-02 | MULLINGAR CAP1
TO-23-MUL-CAP2-01 | MULLINGAR CAP2
TO-23-PB-R2002-02 | POOLBEG R2002
TO-23-PRO-TB-1-04 | PROSPECT TARBERT
TO-23-TB-220K1-2-01 | TARBERT 220K1-2
TO-23-TB-T101-02 | TARBERT T101
TO-23-TB-T2003-03 | TARBERT T2003
TO-23-TB-T2004-03 | TARBERT T2004
TO-23-TB-T2004-02
TO-23-TB-T2101-02 | TARBERT T2101
TO-23-TB-T2101-03
TO-23-THU-CAP2-01 | THURLES CAP2