## Wks 25 - 26
Report covers outages commencing/returning/spanning the period: 19/06/2023 - 02/07/2023
Outages commencing/returning in Week 25
OUTAGE ID | PLANT |  | Week 25 | [6 empty] | Week 26
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3
TO-23-220 kV B2 @ CSH-01 | CASHLA 220 kV B2 | bar: Week 25 Mo 19
TO-23-CGG-DMY-1-01 | CARRIGDANGAN DUNMANWAY | bar: Week 25 Mo 19
TO-23-CGG-T131-01 | CARRIGDANGAN T131 | bar: Week 25 Mo 19
TO-23-KTL-CAP1-01 | KILTEEL CAP1 | bar: Week 25 Mo 19
TO-23-BYH-CDL-1-01 | BALLYNAHULLA CORDAL | bar: Week 25 Mo 19; Week 25 Fr 23
TO-23-CDL-110SA1-01 | CORDAL 110SA1 | bar: Week 25 Mo 19; Week 25 Fr 23
TO-23-CDL-110SA2-01 | CORDAL 110SA2 | bar: Week 25 Mo 19; Week 25 Fr 23
TO-23-CDL-T132-01 | CORDAL T132 | bar: Week 25 Mo 19; Week 25 Fr 23
TO-23-CDL-T141-01 | CORDAL T141 | bar: Week 25 Mo 19; Week 25 Fr 23
TO-23-LIS-110SA1-05 | LISDRUM 110SA1 | bar: Week 25 Mo 19; Week 25 Fr 23
TO-23-LIS-110SA2-05 | LISDRUM 110SA2 | bar: Week 25 Mo 19; Week 25 Fr 23
TO-23-LIS-CAP1-03 | LISDRUM CAP1 | bar: Week 25 Mo 19; Week 25 Fr 23
TO-23-LIS-LOU-1-02 | LISDRUM LOUTH | bar: Week 25 Mo 19; Week 25 Fr 23
TO-23-LIS-T131-04 | LISDRUM T131 | bar: Week 25 Mo 19; Week 25 Fr 23
TO-23-LIS-T141-04 | LISDRUM T141 | bar: Week 25 Mo 19; Week 25 Fr 23
TO-23-110 kV A2 @ CSH-10 | CASHLA 110 kV A2 | bar: Week 25 Mo 19; Week 25 Fr 23 to Week 26 Mo 26
TO-23-110 kV B2 @ CSH-11 | CASHLA 110 kV B2 | bar: Week 25 Mo 19; Week 25 Fr 23 to Week 26 Mo 26
TO-23-220 kV A2 @ CSH-02 | CASHLA 220 kV A2 | bar: Week 25 Mo 19; Week 25 Fr 23 to Week 26 Fr 30
TO-23-220 kV B2 @ CSH-04 | CASHLA 220 kV B2 | bar: Week 25 Mo 19; Week 25 Fr 23 to Week 26 Fr 30
TO-23-BK-SKY-1-01 | BELLACORICK SRAHNAKILLY | bar: Week 25 Mo 19; Week 25 Fr 23 to Week 26 Mo 3
TO-23-CSH-T2102-01 | CASHLA T2102 | bar: Week 25 Mo 19; Week 25 Fr 23 to Week 26 Mo 3
TO-23-IA-MAC-1-03 | INNISCARRA MACROOM | bar: Week 25 Mo 19; Week 25 Fr 23 to Week 26 Mo 3
TO-23-SKY-110SA1-01 | SRAHNAKILLY 110SA1 | bar: Week 25 Mo 19; Week 25 Fr 23 to Week 26 Mo 3
TO-23-SKY-110SA2-01 | SRAHNAKILLY 110SA2 | bar: Week 25 Mo 19; Week 25 Fr 23 to Week 26 Mo 3
TO-23-SKY-T131-01 | SRAHNAKILLY T131 | bar: Week 25 Mo 19; Week 25 Fr 23 to Week 26 Mo 3
TO-23-SKY-T132-01 | SRAHNAKILLY T132 | bar: Week 25 Mo 19; Week 25 Fr 23 to Week 26 Mo 3
TO-23-CUL-DGN-1-01 | CULLENAGH DUNGARVAN | bar: Su 18 to Week 25 Mo 19
TO-23-BAG-T101-01 | BARNAGEERAGH T101
TO-23-AUG-SK-3-01 | AUGHINISH SEALROCK 3 | bar: Week 25 Fr 23 to Week 26 We 28
TO-23-SK-T103-01 | SEALROCK T103 | bar: Week 25 Fr 23 to Week 26 Mo 3
TO-23-110 kV A2 @ CSH-08 | CASHLA 110 kV A2
TO-23-110 kV B2 @ CSH-09 | CASHLA 110 kV B2
TO-23-220 kV A1 @ INC-02 | INCHICORE 220 kV A1
TO-23-220 kV A2 @ INC-02 | INCHICORE 220 kV A2
TO-23-220 kV B1 @ INC-02 | INCHICORE 220 kV B1
TO-23-220 kV B2 @ INC-02 | INCHICORE 220 kV B2
TO-23-INC-220K1-2-03 | INCHICORE 220K1-2
TO-23-220 kV B1 @ FLA-03 | FLAGFORD 220 kV B1 | bar: Week 25 Fr 23
TO-23-AA GIS-T103-01 | ARDNACRUSHA GIS T103 | bar: Su 18 to Week 25 Mo 19; Week 25 Fr 23
TO-23-BYH-T2102-02 | BALLYNAHULLA T2102 | bar: Su 18 to Week 25 Mo 19; Week 25 Fr 23
TO-23-110 kV A1 @ PA-01 | POLLAPHUCA 110 kV A1 | bar: Su 18 to Week 25 Mo 19; Week 25 Fr 23
TO-23-110 kV A2 @ PA-01 | POLLAPHUCA 110 kV A2 | bar: Su 18 to Week 25 Mo 19; Week 25 Fr 23
TO-23-PA-110SA1-01 | POLLAPHUCA 110SA1 | bar: Su 18 to Week 25 Mo 19; Week 25 Fr 23
TO-23-PA-110SA2-01 | POLLAPHUCA 110SA2 | bar: Su 18 to Week 25 Mo 19; Week 25 Fr 23
TO-23-STR-T141-01 | STRATFORD T141 | bar: Su 18 to Week 25 Mo 19; Week 25 Fr 23
TO-23-STR,T-CLW-1-01 | STRATFORD tee CARLOW | bar: Su 18 to Week 25 Mo 19; Week 25 Fr 23
TO-23-STR,T-PA-1-04 | STRATFORD tee POLLAPHUCA | bar: Su 18 to Week 25 Mo 19; Week 25 Fr 23
TO-23-STR,T-STR-1-01 | STRATFORD tee STRATFORD | bar: Su 18 to Week 25 Mo 19; Week 25 Fr 23
TO-23-220 kV B1 @ FLA-04 | FLAGFORD 220 kV B1 | bar: Week 25 Sa 24
TO-23-FLA-LOU-1-03 | FLAGFORD LOUTH | bar: Week 25 Sa 24
TO-23-LIS-110SA1-01 | LISDRUM 110SA1 | bar: Week 25 Sa 24
TO-23-LIS-110SA2-01 | LISDRUM 110SA2 | bar: Week 25 Sa 24
TO-23-LIS-CAP1-01 | LISDRUM CAP1 | bar: Week 25 Sa 24
TO-23-LIS-LOU-1-03 | LISDRUM LOUTH | bar: Week 25 Sa 24
TO-23-LIS-T131-02 | LISDRUM T131 | bar: Week 25 Sa 24
TO-23-FIN-NW-1-03 | FINGLAS NORTH WALL | bar: Su 18 to Week 25 Mo 19; Week 25 Fr 23 to Week 25 Sa 24
TO-23-FLA-T2101-02 | FLAGFORD T2101 | bar: Su 18 to Week 25 Mo 19; Week 25 Fr 23 to Week 25 Sa 24
TO-23-LIS-T141-01 | LISDRUM T141 | bar: Su 18 to Week 25 Mo 19; Week 25 Fr 23 to Week 25 Sa 24
TO-23-NW-PB-1-03 | NORTH WALL POOLBEG | bar: Su 18 to Week 25 Mo 19; Week 25 Fr 23 to Week 25 Sa 24
TO-23-NW-T2004/5-01 | NORTH WALL T2004/5 | bar: Su 18 to Week 25 Mo 19; Week 25 Fr 23 to Week 25 Sa 24
TO-23-COW-T142-01 | COW CROSS T142 | bar: Su 18 to Week 25 Mo 19; Week 25 Fr 23 to Week 25 Su 25
Report covers outages commencing/returning/spanning the period: 19/06/2023 - 02/07/2023
Outages commencing/returning in Week 26
OUTAGE ID | PLANT | Week 25 Mo 19: Week 25; Week 26 Mo 26: Week 26
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3
TO-23-BYH-110SA1-2CB-03 | BALLYNAHULLA 110SA1-2CB | bar: Week 26 Mo 26
TO-23-BYH-110SB1-2CB-03 | BALLYNAHULLA 110SB1-2CB | bar: Week 26 Mo 26
TO-23-110 kV A2 @ FLA-01 | FLAGFORD 110 kV A2 | bar: Week 26 Mo 26
TO-23-110 kV B2 @ FLA-01 | FLAGFORD 110 kV B2 | bar: Week 26 Mo 26
TO-23-KLN-SNG-1-01 | KILLONAN SINGLAND | bar: Week 26 Mo 26; Week 26 Th 29
TO-23-SNG-110SA1-2CB-01 | SINGLAND 110SA1-2CB | bar: Week 26 Mo 26; Week 26 Th 29
TO-23-SNG-T101-01 | SINGLAND T101 | bar: Week 26 Mo 26; Week 26 Th 29
TO-23-CF-T103-01 | CATHALEENS FALL T103 | bar: Week 26 Mo 26; Week 26 Th 29 to Week 26 Fr 30
TO-23-110 kV A2 @ CUL-01 | CULLENAGH 110 kV A2 | bar: Week 26 Mo 26; Week 26 Th 29 to Week 26 Fr 30
TO-23-110 kV B2 @ CUL-01 | CULLENAGH 110 kV B2 | bar: Week 26 Mo 26; Week 26 Th 29 to Week 26 Fr 30
TO-23-110 kV A1 @ LOU-04 | LOUTH 110 kV A1 | bar: Week 26 Mo 26; Week 26 Th 29 to Week 26 Fr 30
TO-23-110 kV B1 @ LOU-04 | LOUTH 110 kV B1 | bar: Week 26 Mo 26; Week 26 Th 29 to Week 26 Fr 30
TO-23-BDN-CUL-1-01 | BALLYDINE CULLENAGH | bar: Week 26 Mo 26; Week 26 Th 29 to Week 26 Mo 3
TO-23-BDN-MRK1-01 | BALLYDINE MRK1 | bar: Week 26 Mo 26; Week 26 Th 29 to Week 26 Mo 3
TO-23-CL-T102-02 | CLIFF T102 | bar: Week 26 Mo 26; Week 26 Th 29 to Week 26 Mo 3
TO-23-220 kV A1 @ DSN-01 | DUNSTOWN 220 kV A1 | bar: Week 26 Mo 26; Week 26 Th 29 to Week 26 Mo 3
TO-23-220 kV A2 @ DSN-01 | DUNSTOWN 220 kV A2 | bar: Week 26 Mo 26; Week 26 Th 29 to Week 26 Mo 3
TO-23-220 kV B1 @ DSN-01 | DUNSTOWN 220 kV B1 | bar: Week 26 Mo 26; Week 26 Th 29 to Week 26 Mo 3
TO-23-220 kV B2 @ DSN-01 | DUNSTOWN 220 kV B2 | bar: Week 26 Mo 26; Week 26 Th 29 to Week 26 Mo 3
TO-23-DSN-220K1-2-01 | DUNSTOWN 220K1-2 | bar: Week 26 Mo 26; Week 26 Th 29 to Week 26 Mo 3
TO-23-FLA-SLI-1-01 | FLAGFORD SLIGO | bar: Week 26 Mo 26; Week 26 Th 29 to Week 26 Mo 3
TO-23-LOU-T2103-01 | LOUTH T2103 | bar: Week 26 Mo 26; Week 26 Th 29 to Week 26 Mo 3
TO-23-110 kV A2 @ CSH-01 | CASHLA 110 kV A2
TO-23-110 kV B2 @ CSH-02 | CASHLA 110 kV B2
TO-23-KHL-T131-02 | KILL HILL T131 | bar: Week 26 Th 29
TO-23-110 kV A2 @ ARV-02 | ARVA 110 kV A2 | bar: Week 26 Th 29 to Week 26 Fr 30
TO-23-110 kV B2 @ ARV-02 | ARVA 110 kV B2 | bar: Week 26 Th 29 to Week 26 Fr 30
TO-23-CSH-GAL-2-01 | CASHLA GALWAY 2 | bar: Week 26 Th 29 to Week 26 Mo 3
TO-23-BYH-GLE-1-02 | BALLYNAHULLA GLENLARA
TO-23-OST-WOO-1-02 | OLDSTREET WOODLAND | bar: Su 18 to Week 26 Mo 26; Week 26 Th 29 to Week 26 Fr 30
TO-23-ARV-GWE-1-03 | ARVA GORTAWEE | bar: Su 18 to Week 26 Mo 26; Week 26 Th 29 to Week 26 Sa 1
Outages spanning Weeks 25-26
OUTAGE ID | PLANT | Week 25 Mo 19: Week 25; Week 26 Mo 26: Week 26
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3
TO-23-220 kV A2 @ AD-01 | AGHADA 220 kV A2
TO-23-220 kV B2 @ AD-01 | AGHADA 220 kV B2
TO-23-AD-SA1-2CB-01 | AGHADA 220SA1-2CB
TO-23-AD-SB1-2CB-01 | AGHADA 220SB1-2CB
TO-23-AD-T2001-03 | AGHADA T2001
TO-23-BDN-T141-01 | BALLYDINE T141
TO-23-CSH-CAP2-04 | CASHLA CAP2
TO-23-CSH-GAL-2-02 | CASHLA GALWAY 2
TO-23-CLG-110K1-01 | CLOGHRAN 110K1
TO-23-220 kV A4 @ CDU-01 | CORDUFF 220 kV A4
TO-23-220 kV B4 @ CDU-01 | CORDUFF 220 kV B4
TO-23-CDU-GLN-1-05 | CORDUFF GALLANSTOWN
TO-23-CDU-MUL-1-02 | CORDUFF MULLINGAR
TO-23-DRY-T141-02 | DRYBRIDGE T141
TO-23-DDK-LOU-1-01 | DUNDALK LOUTH
TO-23-220 kV A2 @ FIN-02 | FINGLAS 220 kV A2
TO-23-FIN-T2104-02 | FINGLAS T2104
TO-23-GLN-110K1-01 | GALLANSTOWN 110K1
TO-23-GAL-110K2-3-02 | GALWAY 110K2-3
TO-23-GGO-220K1-2-01 | GLANAGOW 220K1-2
TO-23-INC-220K1-2-01 | INCHICORE 220K1-2
TO-23-KLS-220K1-2-04 | KELLIS 220K1-2
TO-23-KLS-KKY-1-02 | KELLIS KILKENNY
TO-23-110 kV B2 @ KBY-03 | KILBARRY 110 kV B2
Report covers outages commencing/returning/spanning the period: 19/06/2023 - 02/07/2023
Outages spanning Weeks 25-26
OUTAGE ID | PLANT | Week 25 Mo 19: Week 25; Week 26 Mo 26: Week 26
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3
TO-23-KBY-MR-1-01 | KILBARRY MARINA 1
TO-23-KBY-MR-2-03 | KILBARRY MARINA 2
TO-23-KKY-110SA1-2CB-02 | KILKENNY 110SA1-2CB
TO-23-KKY-T141-02 | KILKENNY T141
TO-23-KPG-TB-1-02 | KILPADDOGE TARBERT 1
TO-23-220 kV B1/B2 @ KRA-01 | KNOCKRAHA 220 kV B1/B2
TO-23-KRA-220K1-05 | KNOCKRAHA 220K1
TO-23-KRA-220K1-2-03 | KNOCKRAHA 220K1-2
TO-23-KRA-220SB2-4CB-02 | KNOCKRAHA 220SB2-4CB
TO-23-LET-M/CAP1-01 | LETTERKENNY M/CAP1
TO-23-LET-SVC-01 | LETTERKENNY SVC
TO-23-LET-TIV-1-01 | LETTERKENNY TIEVEBRACK
TO-23-110 kV A2 @ LOU-01 | LOUTH 110 kV A2
TO-23-110 kV B2 @ LOU-01 | LOUTH 110 kV B2
TO-23-220 kV A1/A2 @ LOU-01 | LOUTH 220 kV A1/A2
TO-23-MP GIS-T4202-02 | MONEYPOINT GIS T4202
TO-23-MUL-CAP1-02 | MULLINGAR CAP1
TO-23-PA-T101-01 | POLLAPHUCA T101
TO-23-PB-R2002-02 | POOLBEG R2002
TO-23-PRO-TB-1-04 | PROSPECT TARBERT
TO-23-TB-220K1-2-01 | TARBERT 220K1-2
TO-23-TB-T101-02 | TARBERT T101
TO-23-TB-T2003-03 | TARBERT T2003
TO-23-TB-T2004-03 | TARBERT T2004
TO-23-TB-T2004-02
TO-23-TB-T2101-02 | TARBERT T2101
TO-23-TB-T2101-03
TO-23-THU-CAP2-01 | THURLES CAP2