## Wks 27 - 28
Report covers outages commencing/returning/spanning the period: 03/07/2023 - 16/07/2023
Outages commencing/returning in Week 27
OUTAGE ID | PLANT |  | Week 27 | [6 empty] | Week 28
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17
TO-23-CNO-KPG-1-01 | COOLNANOONAGH KILPADDOGE | bar: Week 27 Mo 3 to Week 27 Th 6
TO-23-CNO-T131-01 | COOLNANOONAGH T131 | bar: Week 27 Mo 3 to Week 27 Th 6
TO-23-220 kV A2 @ CDU-01 | CORDUFF 220 kV A2 | bar: Week 27 Mo 3 to Week 27 Fr 7
TO-23-220 kV B2 @ CDU-01 | CORDUFF 220 kV B2 | bar: Week 27 Mo 3 to Week 27 Fr 7
TO-23-CDU-FIN-2-01 | CORDUFF FINGLAS 2 | bar: Week 27 Mo 3 to Week 27 Fr 7
TO-23-DSN-TH-1-01 | DUNSTOWN TURLOUGH HILL | bar: Week 27 Mo 3 to Week 28 Fr 14
TO-23-NEW-PLS-1-01 | NEWBRIDGE PORTLAOISE | bar: Week 27 Mo 3 to Week 28 Fr 14
TO-23-220 kV A1 @ TH-02 | TURLOUGH HILL 220 kV A1 | bar: Week 27 Mo 3 to Week 28 Fr 14
TO-23-220 kV B1 @ TH-02 | TURLOUGH HILL 220 kV B1 | bar: Week 27 Mo 3 to Week 28 Fr 14
TO-23-ARV-NAV-1-01 | ARVA NAVAN
TO-23-BNK-T121-01 | BARNAKYLE T121 | bar: Week 27 Tu 4 to Week 27 We 5
TO-23-SLB-T132-01 | SLIABH BAWN T132 | bar: Week 27 Tu 4 to Week 27 We 5
TO-23-110 kV A2 @ CUL-01 | CULLENAGH 110 kV A2 | bar: Su 2 to Week 27 Th 6
TO-23-110 kV B2 @ CUL-01 | CULLENAGH 110 kV B2 | bar: Su 2 to Week 27 Th 6
TO-23-BDN-110SA1-05 | BALLYDINE 110SA1 | bar: Week 27 Fr 7
TO-23-BDN-110SA2-04 | BALLYDINE 110SA2 | bar: Week 27 Fr 7
TO-23-BDN-T141-01 | BALLYDINE T141 | bar: Su 2 to Week 27 Fr 7
TO-23-BK-SKY-1-01 | BELLACORICK SRAHNAKILLY | bar: Su 2 to Week 27 Fr 7
TO-23-CL-T102-02 | CLIFF T102 | bar: Su 2 to Week 27 Fr 7
TO-23-LOU-T2102-08 | LOUTH T2102 | bar: Su 2 to Week 27 Fr 7
TO-23-SKY-110SA1-01 | SRAHNAKILLY 110SA1 | bar: Su 2 to Week 27 Fr 7
TO-23-SKY-110SA2-01 | SRAHNAKILLY 110SA2 | bar: Su 2 to Week 27 Fr 7
TO-23-SKY-T131-01 | SRAHNAKILLY T131 | bar: Su 2 to Week 27 Fr 7
TO-23-SKY-T132-01 | SRAHNAKILLY T132 | bar: Su 2 to Week 27 Fr 7
Outages commencing/returning in Week 28
OUTAGE ID | PLANT | Week 27 Mo 3: Week 27; Week 28 Mo 10: Week 28
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17
TO-23-DEY-T132-03 | DERRYCARNEY T132 | bar: Week 28 Mo 10 to Week 28 Tu 11
TO-23-AUG-KPG-1-01 | AUGHINISH KILPADDOGE | bar: Week 28 Mo 10 to Week 28 Th 13
TO-23-110 kV A2 @ KPG-04 | KILPADDOGE 110 kV A2 | bar: Week 28 Mo 10 to Week 28 Th 13
TO-23-110 kV B2 @ KPG-02 | KILPADDOGE 110 kV B2 | bar: Week 28 Mo 10 to Week 28 Th 13
TO-23-KPG-110SA1-2CB-04 | KILPADDOGE 110SA1-2CB | bar: Week 28 Mo 10 to Week 28 Th 13
TO-23-KPG-110SA2-4CB-04 | KILPADDOGE 110SA2-4CB | bar: Week 28 Mo 10 to Week 28 Th 13
TO-23-KPG-110SB1-2CB-05 | KILPADDOGE 110SB1-2CB | bar: Week 28 Mo 10 to Week 28 Th 13
TO-23-KPG-110SB2-4CB-04 | KILPADDOGE 110SB2-4CB | bar: Week 28 Mo 10 to Week 28 Th 13
TO-23-BRT-T222-01 | BRACETOWN T222 | bar: Week 28 Mo 10 to Week 28 Fr 14
TO-23-220 kV A1 @ DSN-02 | DUNSTOWN 220 kV A1 | bar: Week 28 Mo 10 to Week 28 Fr 14
TO-23-220 kV B1 @ DSN-02 | DUNSTOWN 220 kV B1 | bar: Week 28 Mo 10 to Week 28 Fr 14
TO-23-NEW-110SA1-01 | NEWBRIDGE 110SA1 | bar: Week 28 Mo 10 to Week 28 Fr 14
TO-23-NEW-110SA2-03 | NEWBRIDGE 110SA2 | bar: Week 28 Mo 10 to Week 28 Fr 14
TO-23-NEW-T141-01 | NEWBRIDGE T141 | bar: Week 28 Mo 10 to Week 28 Fr 14
TO-23-110 kV A2 @ ARK-01 | ARKLOW 110 kV A2 | bar: Week 28 Mo 10 to Week 28 Mo 17
TO-23-110 kV B2 @ ARK-01 | ARKLOW 110 kV B2 | bar: Week 28 Mo 10 to Week 28 Mo 17
TO-23-ARK-BEG-1-01 | ARKLOW BALLYBEG | bar: Week 28 Mo 10 to Week 28 Mo 17
TO-23-CUS-NEW-1-01 | CUSHALING NEWBRIDGE | bar: Week 28 Mo 10 to Week 28 Mo 17
TO-23-KKY-CAP2-01 | KILKENNY CAP2 | bar: Week 28 Mo 10 to Week 28 Mo 17
TO-23-LOU-T2103-01 | LOUTH T2103 | bar: Week 28 Mo 10 to Week 28 Mo 17
TO-23-UGL-T132-01 | UGGOOL T132 | bar: Week 28 Mo 10 to Week 28 Mo 17
TO-23-UGL-T134-01 | UGGOOL T134 | bar: Week 28 Mo 10 to Week 28 Mo 17
TO-23-AUG-SK-3-01 | AUGHINISH SEALROCK 3 | bar: Su 2 to Week 28 Mo 10
TO-23-110 kV A1 @ FLA-05 | FLAGFORD 110 kV A1 | bar: Su 2 to Week 28 Mo 10
TO-23-110 kV B1 @ FLA-05 | FLAGFORD 110 kV B1 | bar: Su 2 to Week 28 Mo 10
TO-23-220 kV A1 @ FLA-03 | FLAGFORD 220 kV A1 | bar: Su 2 to Week 28 Mo 10
TO-23-220 kV B1 @ FLA-05 | FLAGFORD 220 kV B1 | bar: Su 2 to Week 28 Mo 10
TO-23-FLA-T2101-01 | FLAGFORD T2101 | bar: Su 2 to Week 28 Mo 10
TO-23-SK-T103-01 | SEALROCK T103 | bar: Su 2 to Week 28 Mo 10
TO-23-BEG-110SA1-01 | BALLYBEG 110SA1 | bar: Week 28 Tu 11 to Week 28 Th 13
TO-23-BEG-110SA2-01 | BALLYBEG 110SA2 | bar: Week 28 Tu 11 to Week 28 Th 13
Report covers outages commencing/returning/spanning the period: 03/07/2023 - 16/07/2023
Outages commencing/returning in Week 28
OUTAGE ID | PLANT | Week 27 Mo 3: Week 27; Week 28 Mo 10: Week 28
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17
TO-23-BEG-T101-01 | BALLYBEG T101
TO-23-110 kV A1 @ LOU-04 | LOUTH 110 kV A1
TO-23-110 kV B1 @ LOU-04 | LOUTH 110 kV B1
TO-23-UGL-110SA1-2CB-03 | UGGOOL 110SA1-2CB
TO-23-CDU-MUL-1-02 | CORDUFF MULLINGAR
TO-23-ATH-LA-1-01 | ATHLONE LANESBORO
TO-23-TIV-110SA1-2CB-01 | TIEVEBRACK 110SA1-2CB
TO-23-CLA-T2102-02 | CLASHAVOON T2102
TO-23-LET-TIV-1-01 | LETTERKENNY TIEVEBRACK
TO-23-CDU-GLN-1-05 | CORDUFF GALLANSTOWN
Outages spanning Weeks 27-28
OUTAGE ID | PLANT | Week 27 Mo 3: Week 27; Week 28 Mo 10: Week 28
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17
TO-23-220 kV A2 @ AD-01 | AGHADA 220 kV A2
TO-23-220 kV B2 @ AD-01 | AGHADA 220 kV B2
TO-23-AD-SA1-2CB-01 | AGHADA 220SA1-2CB
TO-23-AD-SB1-2CB-01 | AGHADA 220SB1-2CB
TO-23-AD-T2001-03 | AGHADA T2001
TO-23-BDN-CUL-1-01 | BALLYDINE CULLENAGH
TO-23-BDN-MRK1-01 | BALLYDINE MRK1
TO-23-110 kV A2 @ CSH-01 | CASHLA 110 kV A2
TO-23-110 kV B2 @ CSH-02 | CASHLA 110 kV B2
TO-23-CSH-CAP2-04 | CASHLA CAP2
TO-23-CSH-GAL-2-02 | CASHLA GALWAY 2
TO-23-CLG-110K1-01 | CLOGHRAN 110K1
TO-23-220 kV A4 @ CDU-01 | CORDUFF 220 kV A4
TO-23-220 kV B4 @ CDU-01 | CORDUFF 220 kV B4
TO-23-DRY-T141-02 | DRYBRIDGE T141
TO-23-DDK-LOU-1-01 | DUNDALK LOUTH
TO-23-220 kV A2 @ FIN-02 | FINGLAS 220 kV A2
TO-23-FIN-T2104-02 | FINGLAS T2104
TO-23-FLA-SLI-1-01 | FLAGFORD SLIGO
TO-23-GAL-110K2-3-02 | GALWAY 110K2-3
TO-23-GGO-220K1-2-01 | GLANAGOW 220K1-2
TO-23-INC-220K1-2-01 | INCHICORE 220K1-2
TO-23-IA-MAC-1-03 | INNISCARRA MACROOM
TO-23-KLS-220K1-2-04 | KELLIS 220K1-2
TO-23-KLS-KKY-1-02 | KELLIS KILKENNY
TO-23-110 kV B2 @ KBY-03 | KILBARRY 110 kV B2
TO-23-KBY-MR-1-01 | KILBARRY MARINA 1
TO-23-KBY-MR-2-03 | KILBARRY MARINA 2
TO-23-KKY-110SA1-2CB-02 | KILKENNY 110SA1-2CB
TO-23-KKY-T141-02 | KILKENNY T141
TO-23-KPG-TB-1-02 | KILPADDOGE TARBERT 1
TO-23-220 kV B1/B2 @ KRA-01 | KNOCKRAHA 220 kV B1/B2
TO-23-KRA-220K1-05 | KNOCKRAHA 220K1
TO-23-KRA-220K1-2-03 | KNOCKRAHA 220K1-2
TO-23-KRA-220SB2-4CB-02 | KNOCKRAHA 220SB2-4CB
TO-23-LET-M/CAP1-01 | LETTERKENNY M/CAP1
TO-23-LET-SVC-01 | LETTERKENNY SVC
TO-23-LIS-T141-01 | LISDRUM T141
TO-23-110 kV A2 @ LOU-01 | LOUTH 110 kV A2
TO-23-110 kV B2 @ LOU-01 | LOUTH 110 kV B2
TO-23-220 kV A1/A2 @ LOU-01 | LOUTH 220 kV A1/A2
TO-23-MP GIS-T4202-02 | MONEYPOINT GIS T4202
TO-23-MUL-CAP1-02 | MULLINGAR CAP1
TO-23-PA-T101-01 | POLLAPHUCA T101
TO-23-PB-R2002-02 | POOLBEG R2002
TO-23-PRO-TB-1-04 | PROSPECT TARBERT
Report covers outages commencing/returning/spanning the period: 03/07/2023 - 16/07/2023
Outages spanning Weeks 27-28
OUTAGE ID | PLANT | Week 27 Mo 3: Week 27; Week 28 Mo 10: Week 28
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17
TO-23-110 kV A1 @ SH-03 | SHANNONBRIDGE 110 kV A1
TO-23-110 kV A2 @ SH-04 | SHANNONBRIDGE 110 kV A2
TO-23-110 kV B1 @ SH-07 | SHANNONBRIDGE 110 kV B1
TO-23-110 kV B2 @ SH-03 | SHANNONBRIDGE 110 kV B2
TO-23-TB-220K1-2-01 | TARBERT 220K1-2
TO-23-TB-T101-02 | TARBERT T101
TO-23-TB-T2003-03 | TARBERT T2003
TO-23-TB-T2004-02 | TARBERT T2004
TO-23-TB-T2004-03
TO-23-TB-T2101-02 | TARBERT T2101
TO-23-TB-T2101-03
TO-23-THU-CAP2-01 | THURLES CAP2