## Wks 33 - 34
Report covers outages commencing/returning/spanning the period: 14/08/2023 - 27/08/2023
Outages commencing/returning in Week 33
OUTAGE ID | PLANT |  | Week 33 | [6 empty] | Week 34
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28
TO-23-KCR-T121-01 | KNOCKACUMMER T121 | bar: Week 33 Mo 14
TO-23-COW-RAF-1-02 | COW CROSS RAFFEEN | bar: Week 33 Mo 14 to Week 33 Th 17
TO-23-MEE-T121-01 | MEENTYCAT T121 | bar: Week 33 Mo 14 to Week 33 Th 17
TO-23-220 kV A1 @ CSH-03 | CASHLA 220 kV A1 | bar: Week 33 Mo 14 to Week 33 Fr 18
TO-23-220 kV A2 @ CSH-03 | CASHLA 220 kV A2 | bar: Week 33 Mo 14 to Week 33 Fr 18
TO-23-220 kV B1 @ CSH-01 | CASHLA 220 kV B1 | bar: Week 33 Mo 14 to Week 33 Fr 18
TO-23-220 kV B2 @ CSH-03 | CASHLA 220 kV B2 | bar: Week 33 Mo 14 to Week 33 Fr 18
TO-23-CSH-220K1-2-01 | CASHLA 220K1-2 | bar: Week 33 Mo 14 to Week 33 Fr 18
TO-23-INC-MAY-2-06 | INCHICORE MAYNOOTH 2 | bar: Week 33 Mo 14 to Week 34 Sa 26
TO-23-LIS-110SA1-04 | LISDRUM 110SA1
TO-23-LIS-110SA2-04 | LISDRUM 110SA2
TO-23-LIS-CAP2-04 | LISDRUM CAP2
TO-23-LIS-T142-03 | LISDRUM T142
TO-23-ROP-WEX-1-01 | ROSSPILE WEXFORD | bar: Su 13 to Week 33 Mo 14
TO-23-CUS-110SA1-2CB-01 | CUSHALING 110SA1-2CB | bar: Week 33 Tu 15 to Week 33 Fr 18
TO-23-CUS-KIR-1-02 | CUSHALING KILCUMBER | bar: Week 33 Tu 15 to Week 33 Fr 18
TO-23-CUS-MLC-1-04 | CUSHALING MOUNTLUCAS | bar: Week 33 Tu 15 to Week 33 Fr 18
TO-23-KIR-T131-03 | KILCUMBER T131 | bar: Week 33 Tu 15 to Week 33 Fr 18
TO-23-BEG-CKM GIS-1-01 | BALLYBEG CARRICKMINES GIS | bar: Week 33 Tu 15 to Week 34 Tu 22
TO-23-DRY-110SA1-02 | DRYBRIDGE 110SA1 | bar: Week 33 We 16
TO-23-DRY-110SA2-01 | DRYBRIDGE 110SA2 | bar: Week 33 We 16
TO-23-CKN-KER-1-02 | CLONKEEN KNOCKEARAGH | bar: Week 33 We 16 to Week 33 Th 17
TO-23-GAE-T121-03 | GLANLEE T121 | bar: Week 33 We 16 to Week 33 Fr 18
TO-23-DRY-LOU-1-02 | DRYBRIDGE LOUTH | bar: Su 13 to Week 33 We 16
TO-23-DRY-T141-02 | DRYBRIDGE T141 | bar: Su 13 to Week 33 We 16
TO-23-FLA-LOU-1-09 | FLAGFORD LOUTH | bar: Week 33 Fr 18 to Week 33 Su 20
TO-23-GOR-LOU-1-03 | GORMAN LOUTH | bar: Week 33 Fr 18 to Week 33 Su 20
TO-23-LOU-AT1-03 | LOUTH AT1 | bar: Week 33 Fr 18 to Week 33 Su 20
TO-23-LOU-AT3-04 | LOUTH AT3 | bar: Week 33 Fr 18 to Week 33 Su 20
TO-23-LOU-T2102-07 | LOUTH T2102 | bar: Week 33 Fr 18 to Week 33 Su 20
TO-23-LOU-T2104-01 | LOUTH T2104 | bar: Week 33 Fr 18 to Week 33 Su 20
TO-23-LOU-TAN-1-02 | LOUTH TANDRAGEE 1 | bar: Week 33 Fr 18 to Week 33 Su 20
TO-23-AD-KRA-2-04 | AGHADA KNOCKRAHA 2 | bar: Week 33 Fr 18 to Week 34 Th 24
TO-23-110 kV B1 @ SH-02 | SHANNONBRIDGE 110 kV B1 | bar: Week 33 Fr 18 to Week 34 Th 24
TO-23-AD-GGO-1-01 | AGHADA GLANAGOW | bar: Week 33 Fr 18 to Week 34 Mo 28
TO-23-GGO-RAF-1-01 | GLANAGOW RAFFEEN | bar: Week 33 Fr 18 to Week 34 Mo 28
TO-23-GGO-T2001-01 | GLANAGOW T2001 | bar: Week 33 Fr 18 to Week 34 Mo 28
TO-23-BVK-COT-1-01 | BALLYVOUSKILL COOMATAGGART | bar: Su 13 to Week 33 Fr 18
TO-23-COT-110SA1-01 | COOMATAGGART 110SA1 | bar: Su 13 to Week 33 Fr 18
TO-23-COT-110SA2-01 | COOMATAGGART 110SA2 | bar: Su 13 to Week 33 Fr 18
TO-23-COT-FILTER1-02 | COOMATAGGART FILTER1 | bar: Su 13 to Week 33 Fr 18
TO-23-COT-T132-01 | COOMATAGGART T132 | bar: Su 13 to Week 33 Fr 18
TO-23-COT-T141-01 | COOMATAGGART T141 | bar: Su 13 to Week 33 Fr 18
TO-23-CUS-T101-01 | CUSHALING T101 | bar: Su 13 to Week 33 Fr 18
TO-23-110 kV B1 @ SH-01 | SHANNONBRIDGE 110 kV B1 | bar: Su 13 to Week 33 Fr 18
TO-23-DSN-KLS-1-05 | DUNSTOWN KELLIS | bar: Week 33 Sa 19 to Week 33 Su 20
TO-23-KLS-T2101-04 | KELLIS T2101 | bar: Week 33 Sa 19 to Week 33 Su 20
TO-23-PLA-110SA1-03 | PLATIN 110SA1 | bar: Su 13 to Week 33 Sa 19
TO-23-PLA-110SA2-03 | PLATIN 110SA2 | bar: Su 13 to Week 33 Sa 19
TO-23-PLA-T101/2/3/4-03 | PLATIN T101/2/3/4 | bar: Su 13 to Week 33 Sa 19
Outages commencing/returning in Week 34
OUTAGE ID | PLANT | Week 33 Mo 14: Week 33; Week 34 Mo 21: Week 34
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28
TO-23-110 kV A1 @ GAL GIS-02 | GALWAY GIS 110 kV A1 | bar: Week 34 Mo 21
TO-23-110 kV B1 @ GAL GIS-02 | GALWAY GIS 110 kV B1 | bar: Week 34 Mo 21
TO-23-GAL GIS-110SA1-2CB-06 | GALWAY GIS 110SA1-2CB | bar: Week 34 Mo 21
TO-23-GAL GIS-110SA1-3CB-02 | GALWAY GIS 110SA1-3CB | bar: Week 34 Mo 21
Report covers outages commencing/returning/spanning the period: 14/08/2023 - 27/08/2023
Outages commencing/returning in Week 34
OUTAGE ID | PLANT | Week 33 Mo 14: Week 33; Week 34 Mo 21: Week 34
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28
TO-23-GAL GIS-110SB1-2CB-06 | GALWAY GIS 110SB1-2CB | bar: Week 34 Mo 21
TO-23-GAL GIS-110SB1-3CB-02 | GALWAY GIS 110SB1-3CB | bar: Week 34 Mo 21
TO-23-GAL GIS-SAL-1-04 | GALWAY GIS SALTHILL | bar: Week 34 Mo 21
TO-23-MRY-T131-01 | MULREAVY T131 | bar: Week 34 Mo 21; Week 34 We 23 to Week 34 Fr 25
TO-23-BOG-CRA-1-01 | BANOGE CRANE | bar: Week 34 Mo 21; Week 34 We 23 to Week 34 Mo 28
TO-23-CLA-CKN-1-01 | CLASHAVOON CLONKEEN | bar: Week 34 Mo 21; Week 34 We 23 to Week 34 Mo 28
TO-23-CKN-110SA1-2CB-01 | CLONKEEN 110SA1-2CB | bar: Week 34 Mo 21; Week 34 We 23 to Week 34 Mo 28
TO-23-CKN-CGL-1-01 | CLONKEEN COOMAGEARLAHY | bar: Week 34 Mo 21; Week 34 We 23 to Week 34 Mo 28
TO-23-CKN-GRO-1-01 | CLONKEEN GARROW | bar: Week 34 Mo 21; Week 34 We 23 to Week 34 Mo 28
TO-23-CKN-KER-1-01 | CLONKEEN KNOCKEARAGH | bar: Week 34 Mo 21; Week 34 We 23 to Week 34 Mo 28
TO-23-CGL-110SA1-01 | COOMAGEARLAHY 110SA1 | bar: Week 34 Mo 21; Week 34 We 23 to Week 34 Mo 28
TO-23-CGL-110SA2-01 | COOMAGEARLAHY 110SA2 | bar: Week 34 Mo 21; Week 34 We 23 to Week 34 Mo 28
TO-23-CGL-GAE-1-01 | COOMAGEARLAHY GLANLEE | bar: Week 34 Mo 21; Week 34 We 23 to Week 34 Mo 28
TO-23-CGL-T122-01 | COOMAGEARLAHY T122 | bar: Week 34 Mo 21; Week 34 We 23 to Week 34 Mo 28
TO-23-220 kV A2 @ DSN-02 | DUNSTOWN 220 kV A2 | bar: Week 34 Mo 21; Week 34 We 23 to Week 34 Mo 28
TO-23-220 kV B2 @ DSN-02 | DUNSTOWN 220 kV B2 | bar: Week 34 Mo 21; Week 34 We 23 to Week 34 Mo 28
TO-23-400 kV A2 @ DSN-01 | DUNSTOWN 400 kV A2 | bar: Week 34 Mo 21; Week 34 We 23 to Week 34 Mo 28
TO-23-400 kV B2 @ DSN-01 | DUNSTOWN 400 kV B2 | bar: Week 34 Mo 21; Week 34 We 23 to Week 34 Mo 28
TO-23-220 kV A1 @ FLA-01 | FLAGFORD 220 kV A1 | bar: Week 34 Mo 21; Week 34 We 23 to Week 34 Mo 28
TO-23-220 kV A2 @ FLA-01 | FLAGFORD 220 kV A2 | bar: Week 34 Mo 21; Week 34 We 23 to Week 34 Mo 28
TO-23-220 kV B1 @ FLA-01 | FLAGFORD 220 kV B1 | bar: Week 34 Mo 21; Week 34 We 23 to Week 34 Mo 28
TO-23-220 kV B2 @ FLA-01 | FLAGFORD 220 kV B2 | bar: Week 34 Mo 21; Week 34 We 23 to Week 34 Mo 28
TO-23-FLA-220K1-2-01 | FLAGFORD 220K1-2 | bar: Week 34 Mo 21; Week 34 We 23 to Week 34 Mo 28
TO-23-GAE-T121-01 | GLANLEE T121 | bar: Week 34 Mo 21; Week 34 We 23 to Week 34 Mo 28
TO-23-SOM-T142-04 | SOMERSET T142 | bar: Week 34 Mo 21; Week 34 We 23 to Week 34 Mo 28
TO-23-SOM,T-CSH-1-03 | SOMERSET tee CASHLA | bar: Week 34 Mo 21; Week 34 We 23 to Week 34 Mo 28
TO-23-SOM,T-SH-1-05 | SOMERSET tee SHANNONBRIDGE | bar: Week 34 Mo 21; Week 34 We 23 to Week 34 Mo 28
TO-23-SOM,T-SOM-1-04 | SOMERSET tee SOMERSET | bar: Week 34 Mo 21; Week 34 We 23 to Week 34 Mo 28
TO-23-CUS-PLS-1-02 | CUSHALING PORTLAOISE | bar: Su 13 to Week 34 Mo 21
TO-23-110 kV A2 @ PLS-02 | PORTLAOISE 110 kV A2 | bar: Su 13 to Week 34 Mo 21
TO-23-110 kV B2 @ PLS-02 | PORTLAOISE 110 kV B2 | bar: Su 13 to Week 34 Mo 21
TO-23-BDN-110SA1-04 | BALLYDINE 110SA1
TO-23-BDN-110SA2-01 | BALLYDINE 110SA2
TO-23-BDN-T141-03 | BALLYDINE T141
TO-23-GAL GIS-SAL-1-05 | GALWAY GIS SALTHILL
TO-23-AA GIS-ENN-1-01 | ARDNACRUSHA GIS ENNIS | bar: Week 34 We 23
TO-23-ATY-PLS-1-03 | ATHY PORTLAOISE | bar: Week 34 We 23 to Week 34 Th 24
TO-23-MAY-TH-1-01 | MAYNOOTH TURLOUGH HILL | bar: Week 34 We 23 to Week 34 Fr 25
TO-23-BDN-CUL-1-01 | BALLYDINE CULLENAGH | bar: Su 13 to Week 34 Mo 21
TO-23-BDN-MRK1-01 | BALLYDINE MRK1 | bar: Su 13 to Week 34 Mo 21
TO-23-110 kV A2 @ CSH-01 | CASHLA 110 kV A2 | bar: Su 13 to Week 34 Mo 21
TO-23-110 kV B2 @ CSH-02 | CASHLA 110 kV B2 | bar: Su 13 to Week 34 Mo 21
TO-23-CSH-GAL-2-02 | CASHLA GALWAY 2 | bar: Su 13 to Week 34 Mo 21
TO-23-DOO-T142-02 | DOON T142 | bar: Week 34 We 23 to Week 34 Mo 28
TO-23-CLW-KLS-2-06 | CARLOW KELLIS 2 | bar: Week 34 Fr 25
TO-23-LOU-AT2-03 | LOUTH AT2 | bar: Week 34 Fr 25 to Week 34 Su 27
TO-23-LOU-T2101-02 | LOUTH T2101 | bar: Week 34 Fr 25 to Week 34 Su 27
TO-23-LOU-T2103-03 | LOUTH T2103 | bar: Week 34 Fr 25 to Week 34 Su 27
TO-23-LOU-TAN-2-03 | LOUTH TANDRAGEE 2 | bar: Week 34 Fr 25 to Week 34 Su 27
TO-23-LOU-WOO-1-02 | LOUTH WOODLAND | bar: Week 34 Fr 25 to Week 34 Su 27
TO-23-CSH-GAL-1-01 | CASHLA GALWAY 1 | bar: Week 34 Fr 25 to Week 34 Mo 28
TO-23-KPG-F11-1-CUB-01 | F11 SPARE 220 kV IN KILPADDOGE | bar: Week 34 Fr 25 to Week 34 Mo 28
TO-23-220 kV A3 @ KPG-04 | KILPADDOGE 220 kV A3 | bar: Week 34 Fr 25 to Week 34 Mo 28
TO-23-220 kV B3 @ KPG-04 | KILPADDOGE 220 kV B3 | bar: Week 34 Fr 25 to Week 34 Mo 28
TO-23-AD-KRA-2-06 | AGHADA KNOCKRAHA 2 | bar: Week 34 Sa 26
TO-23-DSN-KLS-1-06 | DUNSTOWN KELLIS | bar: Week 34 Sa 26 to Week 34 Su 27
TO-23-KLS-T2101-05 | KELLIS T2101 | bar: Week 34 Sa 26 to Week 34 Su 27
TO-23-220 kV B1/B2 @ KRA-01 | KNOCKRAHA 220 kV B1/B2 | bar: Su 13 to Week 34 Mo 21; Week 34 We 23 to Week 34 Sa 26
TO-23-KRA-220K1-05 | KNOCKRAHA 220K1 | bar: Su 13 to Week 34 Mo 21; Week 34 We 23 to Week 34 Sa 26
TO-23-KRA-220SB2-4CB-02 | KNOCKRAHA 220SB2-4CB | bar: Su 13 to Week 34 Mo 21; Week 34 We 23 to Week 34 Sa 26
TO-23-110 kV A4 @ CDU-03 | CORDUFF 110 kV A4 | bar: Su 13 to Week 34 Mo 21; Week 34 We 23 to Week 34 Su 27
TO-23-110 kV B4 @ CDU-03 | CORDUFF 110 kV B4 | bar: Su 13 to Week 34 Mo 21; Week 34 We 23 to Week 34 Su 27
Report covers outages commencing/returning/spanning the period: 14/08/2023 - 27/08/2023
Outages commencing/returning in Week 34
OUTAGE ID | PLANT | Week 33 Mo 14: Week 33; Week 34 Mo 21: Week 34
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28
TO-23-220 kV A1/A2 @ LOU-03 | LOUTH 220 kV A1/A2
TO-23-220 kV A1/A2 @ LOU-01
TO-23-LOU-220K1-2-03 | LOUTH 220K1-2
Outages spanning Weeks 33-34
OUTAGE ID | PLANT | Week 33 Mo 14: Week 33; Week 34 Mo 21: Week 34
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28
TO-23-220 kV A2 @ AD-01 | AGHADA 220 kV A2
TO-23-220 kV B2 @ AD-01 | AGHADA 220 kV B2
TO-23-AD-SA1-2CB-01 | AGHADA 220SA1-2CB
TO-23-AD-SB1-2CB-01 | AGHADA 220SB1-2CB
TO-23-AD-T2001-03 | AGHADA T2001
TO-23-BIN-CF-1-01 | BINBANE CATHALEENS FALL
TO-23-BUT-T141-02 | BUTLERSTOWN T141
TO-23-CSH-CAP2-04 | CASHLA CAP2
TO-23-CLG-110K1-01 | CLOGHRAN 110K1
TO-23-CDU-MUL-1-02 | CORDUFF MULLINGAR
TO-23-DRY-PLA-1-04 | DRYBRIDGE PLATIN
TO-23-DDK-LOU-1-01 | DUNDALK LOUTH
TO-23-DSN-T4202-01 | DUNSTOWN T4202
TO-23-220 kV A2 @ FIN-02 | FINGLAS 220 kV A2
TO-23-FIN-T2104-02 | FINGLAS T2104
TO-23-FLA-SLI-1-01 | FLAGFORD SLIGO
TO-23-GAL-110K2-3-02 | GALWAY 110K2-3
TO-23-GGO-220K1-2-01 | GLANAGOW 220K1-2
TO-23-INC-220K1-2-01 | INCHICORE 220K1-2
TO-23-IA-MAC-1-03 | INNISCARRA MACROOM
TO-23-KLS-220K1-2-04 | KELLIS 220K1-2
TO-23-KPG-TB-1-02 | KILPADDOGE TARBERT 1
TO-23-KRA-220K1-2-03 | KNOCKRAHA 220K1-2
TO-23-LET-M/CAP1-01 | LETTERKENNY M/CAP1
TO-23-LIS-SKL-1-06 | LISDRUM SHANKILL
TO-23-LIS-T131-05 | LISDRUM T131
TO-23-110 kV A2 @ LOU-01 | LOUTH 110 kV A2
TO-23-110 kV B2 @ LOU-01 | LOUTH 110 kV B2
TO-23-MP GIS-T4202-02 | MONEYPOINT GIS T4202
TO-23-MUL-CAP1-02 | MULLINGAR CAP1
TO-23-PB-R2002-02 | POOLBEG R2002
TO-23-PRO-TB-1-04 | PROSPECT TARBERT
TO-23-TB-220K1-2-01 | TARBERT 220K1-2
TO-23-TB-T101-02 | TARBERT T101
TO-23-TB-T2003-03 | TARBERT T2003
TO-23-TB-T2004-02 | TARBERT T2004
TO-23-TB-T2004-03
TO-23-TB-T2101-02 | TARBERT T2101
TO-23-TB-T2101-03
TO-23-THU-CAP2-01 | THURLES CAP2