## Wks 37 - 38
Report covers outages commencing/returning/spanning the period: 11/09/2023 - 24/09/2023
Outages commencing/returning in Week 37
OUTAGE ID | PLANT |  | Week 37 | [6 empty] | Week 38
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25
TO-23-KUR-NAV-1-01 | KNOCKUMBER NAVAN
TO-23-KUR-T3-01 | KNOCKUMBER T3
TO-23-KUR-T4-01 | KNOCKUMBER T4
TO-23-TY-T2001/2-01 | TYNAGH T2001/2 | bar: Week 37 Tu 12 to Week 37 We 13
TO-23-BDA-T102-01 | BARODA T102 | bar: Week 37 Tu 12 to Week 37 Fr 15
TO-23-110 kV A1 @ CLG-03 | CLOGHRAN 110 kV A1 | bar: Week 37 Tu 12 to Week 37 Fr 15
TO-23-110 kV A2 @ CLG-01 | CLOGHRAN 110 kV A2 | bar: Week 37 Tu 12 to Week 37 Fr 15
TO-23-110 kV B1 @ CLG-03 | CLOGHRAN 110 kV B1 | bar: Week 37 Tu 12 to Week 37 Fr 15
TO-23-110 kV B2 @ CLG-01 | CLOGHRAN 110 kV B2 | bar: Week 37 Tu 12 to Week 37 Fr 15
TO-23-CLG-110K2-02 | CLOGHRAN 110K2 | bar: Week 37 Tu 12 to Week 37 Fr 15
TO-23-CLG-110SA1-2CB-02 | CLOGHRAN 110SA1-2CB | bar: Week 37 Tu 12 to Week 37 Fr 15
TO-23-CLG-110SB1-2CB-02 | CLOGHRAN 110SB1-2CB | bar: Week 37 Tu 12 to Week 37 Fr 15
TO-23-CLG-T126-01 | CLOGHRAN T126 | bar: Week 37 Tu 12 to Week 37 Fr 15
TO-23-DDK-110SA1-02 | DUNDALK 110SA1 | bar: Week 37 Tu 12 to Week 37 Fr 15
TO-23-DDK-110SA2-01 | DUNDALK 110SA2 | bar: Week 37 Tu 12 to Week 37 Fr 15
TO-23-DDK-T142-01 | DUNDALK T142 | bar: Week 37 Tu 12 to Week 37 Fr 15
TO-23-FIN-NW-1-05 | FINGLAS NORTH WALL | bar: Week 37 Tu 12 to Week 37 Fr 15
TO-23-NW-PB-1-05 | NORTH WALL POOLBEG | bar: Week 37 Tu 12 to Week 37 Fr 15
TO-23-NW-T2004/5-02 | NORTH WALL T2004/5 | bar: Week 37 Tu 12 to Week 37 Fr 15
TO-23-WHI-CKB-T101-01 | WHITEGATE CKB-T101 | bar: Week 37 Tu 12 to Week 37 Fr 15
TO-23-CKM GIS-DSN-1-04 | CARRICKMINES GIS DUNSTOWN | bar: Week 37 Tu 12 to Week 37 Sa 16
TO-23-AD-WHI-1-03 | AGHADA WHITEGATE | bar: Week 37 Tu 12 to Week 38 Tu 19
TO-23-220 kV A1 @ DSN-01 | DUNSTOWN 220 kV A1 | bar: Week 37 Tu 12 to Week 38 Fr 22
TO-23-220 kV A2 @ DSN-01 | DUNSTOWN 220 kV A2 | bar: Week 37 Tu 12 to Week 38 Fr 22
TO-23-220 kV B1 @ DSN-01 | DUNSTOWN 220 kV B1 | bar: Week 37 Tu 12 to Week 38 Fr 22
TO-23-220 kV B2 @ DSN-01 | DUNSTOWN 220 kV B2 | bar: Week 37 Tu 12 to Week 38 Fr 22
TO-23-DSN-220K1-2-01 | DUNSTOWN 220K1-2 | bar: Week 37 Tu 12 to Week 38 Fr 22
TO-23-GRI-T141-02 | GRIFFINRATH T141 | bar: Week 37 Tu 12 to Week 38 Fr 22
TO-23-GRI,T-GRI-1-02 | GRIFFINRATH tee GRIFFINRATH | bar: Week 37 Tu 12 to Week 38 Fr 22
TO-23-GRI,T-MAY-1-03 | GRIFFINRATH tee MAYNOOTH | bar: Week 37 Tu 12 to Week 38 Fr 22
TO-23-AA GIS-T102-04 | ARDNACRUSHA GIS T102 | bar: Week 37 Tu 12 to Week 38 Mo 25
TO-23-GRI,T-GCA-1-03 | GRIFFINRATH tee GRANGE CASTLE | bar: Week 37 Tu 12 to Week 38 Mo 25
TO-23-110 kV A2 @ CSH-07 | CASHLA 110 kV A2 | bar: Su 10
TO-23-110 kV B2 @ CSH-08 | CASHLA 110 kV B2 | bar: Su 10
TO-23-SOM-T142-04 | SOMERSET T142 | bar: Su 10
TO-23-SOM,T-CSH-1-03 | SOMERSET tee CASHLA | bar: Su 10
TO-23-SOM,T-SH-1-05 | SOMERSET tee SHANNONBRIDGE | bar: Su 10
TO-23-SOM,T-SOM-1-04 | SOMERSET tee SOMERSET | bar: Su 10
TO-23-BNK-CBT-1-01 | BARNAKYLE CASTLEBAGOT 1 | bar: Week 37 Tu 12 to Week 37 We 13
TO-23-220 kV A1/A2 @ MP GIS-02 | MONEYPOINT GIS 220 kV A1/A2 | bar: Week 37 Tu 12 to Week 37 Th 14
TO-23-MTN-MUN-2-01 | MONETEEN MUNGRET 2 | bar: Week 37 Tu 12 to Week 37 Fr 15
TO-23-MUN-T102-01 | MUNGRET T102 | bar: Week 37 Tu 12 to Week 37 Fr 15
TO-23-KIN-T102-01 | KINNEGAD T102 | bar: Su 10; Week 37 Tu 12
TO-23-CSH-TY-1-03 | CASHLA TYNAGH | bar: Su 10; Week 37 Tu 12 to Week 37 We 13
TO-23-DSN-T4202-01 | DUNSTOWN T4202 | bar: Su 10; Week 37 Tu 12 to Week 37 We 13
TO-23-OST-T4202-01 | OLDSTREET T4202 | bar: Week 37 Th 14 to Week 38 Fr 22
TO-23-OST-TY-1-04 | OLDSTREET TYNAGH | bar: Week 37 Th 14 to Week 38 Fr 22
TO-23-BYH-BVK-1-01 | BALLYNAHULLA BALLYVOUSKILL | bar: Su 10; Week 37 Tu 12 to Week 37 Th 14
TO-23-220 kV A2 @ PB-03 | POOLBEG 220 kV A2 | bar: Su 10; Week 37 Tu 12 to Week 37 Th 14
TO-23-220 kV B2 @ PB-03 | POOLBEG 220 kV B2 | bar: Su 10; Week 37 Tu 12 to Week 37 Th 14
TO-23-PB-220SA1-2-06 | POOLBEG 220SA1-2 | bar: Su 10; Week 37 Tu 12 to Week 37 Th 14
TO-23-PB-220SB1-2-06 | POOLBEG 220SB1-2 | bar: Su 10; Week 37 Tu 12 to Week 37 Th 14
TO-23-INC-PB-1-05 | INCHICORE POOLBEG 1 | bar: Week 37 Fr 15 to Week 37 Sa 16
TO-23-220 kV A1 @ PB-03 | POOLBEG 220 kV A1 | bar: Week 37 Fr 15 to Week 37 Sa 16
TO-23-220 kV A2 @ PB-04 | POOLBEG 220 kV A2 | bar: Week 37 Fr 15 to Week 37 Sa 16
TO-23-220 kV B1 @ PB-03 | POOLBEG 220 kV B1 | bar: Week 37 Fr 15 to Week 37 Sa 16
TO-23-220 kV B2 @ PB-04 | POOLBEG 220 kV B2 | bar: Week 37 Fr 15 to Week 37 Sa 16
TO-23-PB-220SA1-2-07 | POOLBEG 220SA1-2 | bar: Week 37 Fr 15 to Week 37 Sa 16
TO-23-PB-220SB1-2-07 | POOLBEG 220SB1-2 | bar: Week 37 Fr 15 to Week 37 Sa 16
TO-23-KLN-T2103-02 | KILLONAN T2103 | bar: Week 37 Fr 15 to Week 38 Mo 25
TO-23-ARV-NAV-1-05 | ARVA NAVAN | bar: Su 10; Week 37 Tu 12 to Week 37 Fr 15
Report covers outages commencing/returning/spanning the period: 11/09/2023 - 24/09/2023
Outages commencing/returning in Week 37
OUTAGE ID | PLANT | Week 37 Mo 11: Week 37; Week 38 Mo 18: Week 38
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25
TO-23-KHL-THU-1-01 | KILL HILL THURLES | bar: Su 10 to Week 37 Fr 15
TO-23-THU-110SA1-2CB-07 | THURLES 110SA1-2CB | bar: Su 10 to Week 37 Fr 15
TO-23-THU-CAP1-02 | THURLES CAP1 | bar: Su 10 to Week 37 Fr 15
TO-23-THU-T141-01 | THURLES T141 | bar: Su 10 to Week 37 Fr 15
TO-23-FIN-NW-1-04 | FINGLAS NORTH WALL | bar: Week 37 Sa 16 to Week 37 Su 17
TO-23-NW-PB-1-02 | NORTH WALL POOLBEG | bar: Week 37 Sa 16 to Week 37 Su 17
TO-23-NW-T2004/5-03 | NORTH WALL T2004/5 | bar: Week 37 Sa 16 to Week 37 Su 17
TO-23-PB-T2007/8-02 | POOLBEG T2007/8 | bar: Su 10 to Week 37 Sa 16
Outages commencing/returning in Week 38
OUTAGE ID | PLANT | Week 37 Mo 11: Week 37; Week 38 Mo 18: Week 38
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25
TO-23-IKE-T141-03 | IKERRIN T141 | bar: Week 38 Mo 18
TO-23-IKE,T-IKE-1-02 | IKERRIN tee IKERRIN | bar: Week 38 Mo 18
TO-23-IKE,T-SH-1-05 | IKERRIN tee SHANNONBRIDGE | bar: Week 38 Mo 18
TO-23-IKE,T-THU-1-10 | IKERRIN tee THURLES | bar: Week 38 Mo 18
TO-23-RRU-110SA1-03 | RATRUSSAN 110SA1 | bar: Week 38 Mo 18
TO-23-RRU-110SA2-03 | RATRUSSAN 110SA2 | bar: Week 38 Mo 18
TO-23-RRU-SKL-1-01 | RATRUSSAN SHANKILL | bar: Week 38 Mo 18
TO-23-RRU-T121-03 | RATRUSSAN T121 | bar: Week 38 Mo 18
TO-23-RRU-T122-04 | RATRUSSAN T122 | bar: Week 38 Mo 18
TO-23-AUG-CFM-2-01 | AUGHINISH CASTLEFARM 2 | bar: Week 38 Mo 18; Week 38 Fr 22
TO-23-CFM-T102-01 | CASTLEFARM T102 | bar: Week 38 Mo 18; Week 38 Fr 22
TO-23-220 kV A1 @ GI GIS-02 | GREAT ISLAND GIS 220 kV A1 | bar: Week 38 Mo 18; Week 38 Fr 22
TO-23-220 kV A2 @ GI GIS-02 | GREAT ISLAND GIS 220 kV A2 | bar: Week 38 Mo 18; Week 38 Fr 22
TO-23-GI GIS-220SA1-2CB-01 | GREAT ISLAND GIS 220SA1-2CB | bar: Week 38 Mo 18; Week 38 Fr 22
TO-23-PLA-110SA1-04 | PLATIN 110SA1 | bar: Week 38 Mo 18; Week 38 Fr 22
TO-23-PLA-110SA2-04 | PLATIN 110SA2 | bar: Week 38 Mo 18; Week 38 Fr 22
TO-23-PLA-T101/2/3/4-04 | PLATIN T101/2/3/4 | bar: Week 38 Mo 18; Week 38 Fr 22
TO-23-WHI-CKB-T102-01 | WHITEGATE CKB-T102 | bar: Week 38 Mo 18; Week 38 Fr 22
TO-23-BDA-MON-1-02 | BARODA MONREAD | bar: Week 38 Mo 18; Week 38 Fr 22 to Week 38 Mo 25
TO-23-CRO-IA-1-02 | COOLROE INNISCARRA | bar: Week 38 Mo 18; Week 38 Fr 22 to Week 38 Mo 25
TO-23-110 kV A1 @ KLS-03 | KELLIS 110 kV A1 | bar: Week 38 Mo 18; Week 38 Fr 22 to Week 38 Mo 25
TO-23-110 kV A2 @ KLS-04 | KELLIS 110 kV A2 | bar: Week 38 Mo 18; Week 38 Fr 22 to Week 38 Mo 25
TO-23-110 kV B1 @ KLS-03 | KELLIS 110 kV B1 | bar: Week 38 Mo 18; Week 38 Fr 22 to Week 38 Mo 25
TO-23-110 kV B2 @ KLS-04 | KELLIS 110 kV B2 | bar: Week 38 Mo 18; Week 38 Fr 22 to Week 38 Mo 25
TO-23-KLS-110K1-2-02 | KELLIS 110K1-2 | bar: Week 38 Mo 18; Week 38 Fr 22 to Week 38 Mo 25
TO-23-SH-T2101-01 | SHANNONBRIDGE T2101 | bar: Week 38 Mo 18; Week 38 Fr 22 to Week 38 Mo 25
TO-23-110 kV A1/A2/A3/A4 @ CDU-02 | CORDUFF 110 kV A1/A2/A3/A4
TO-23-CDU-110K1-2-02 | CORDUFF 110K1-2
TO-23-CDU-110K1-3-01 | CORDUFF 110K1-3
TO-23-CDU-110SA2-4-01 | CORDUFF 110SA2-4
TO-23-CDU-SNU-1-03 | CORDUFF SNUGBOROUGH | bar: Week 38 Fr 22
TO-23-MOY-110SA1-2CB-03 | MOY 110SA1-2CB | bar: Week 38 Fr 22 to Week 38 Mo 25
TO-23-MOY-CAP1-01 | MOY CAP1 | bar: Week 38 Fr 22 to Week 38 Mo 25
TO-23-MOY-T141-01 | MOY T141 | bar: Week 38 Fr 22 to Week 38 Mo 25
TO-23-MOY-TAW-1-03 | MOY TAWNAGHMORE 1 | bar: Week 38 Fr 22 to Week 38 Mo 25
TO-23-110 kV B2 @ FLA-03 | FLAGFORD 110 kV B2
TO-23-FLA-T2102-03 | FLAGFORD T2102
TO-23-CHA-KLN-1-03 | CHARLEVILLE KILLONAN | bar: Week 38 Fr 22
TO-23-LPT-T2002-01 | LONG POINT T2002 | bar: Week 38 Fr 22 to Week 38 Mo 25
TO-23-FLA-SLI-1-01 | FLAGFORD SLIGO | bar: Su 10 to Week 38 Mo 18
TO-23-110 kV B1/B2/B3/B4 @ CDU-02 | CORDUFF 110 kV B1/B2/B3/B4 | bar: Week 38 Fr 22
TO-23-CDU-110K1-2-03 | CORDUFF 110K1-2 | bar: Week 38 Fr 22
TO-23-CDU-110K1-3-02 | CORDUFF 110K1-3 | bar: Week 38 Fr 22
TO-23-CDU-110SB2-4-01 | CORDUFF 110SB2-4 | bar: Week 38 Fr 22
TO-23-BIN-CF-1-01 | BINBANE CATHALEENS FALL | bar: Su 10 to Week 38 Mo 18; Week 38 Fr 22
Report covers outages commencing/returning/spanning the period: 11/09/2023 - 24/09/2023
Outages spanning Weeks 37-38
OUTAGE ID | PLANT | Week 37 Mo 11: Week 37; Week 38 Mo 18: Week 38
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25
TO-23-220 kV A2 @ AD-01 | AGHADA 220 kV A2
TO-23-220 kV B2 @ AD-01 | AGHADA 220 kV B2
TO-23-AD-SA1-2CB-01 | AGHADA 220SA1-2CB
TO-23-AD-SB1-2CB-01 | AGHADA 220SB1-2CB
TO-23-AD-T2001-03 | AGHADA T2001
TO-23-BOG-CRA-1-01 | BANOGE CRANE
TO-23-BUT-CUL-1-02 | BUTLERSTOWN CULLENAGH
TO-23-BUT-T141-02 | BUTLERSTOWN T141
TO-23-CSH-CAP2-04 | CASHLA CAP2
TO-23-CSH-GAL-1-01 | CASHLA GALWAY 1
TO-23-CLG-110K1-01 | CLOGHRAN 110K1
TO-23-CLE-T221-01 | CLONEE T221
TO-23-DOO-T142-02 | DOON T142
TO-23-DRY-PLA-1-04 | DRYBRIDGE PLATIN
TO-23-DDK-LOU-1-01 | DUNDALK LOUTH
TO-23-220 kV A2 @ FIN-02 | FINGLAS 220 kV A2
TO-23-FIN-T2104-02 | FINGLAS T2104
TO-23-GAL-110K2-3-02 | GALWAY 110K2-3
TO-23-GLR-MOY-1-01 | GLENREE MOY
TO-23-INC-220K1-2-01 | INCHICORE 220K1-2
TO-23-KLS-220K1-2-04 | KELLIS 220K1-2
TO-23-KBY-MR-1-06 | KILBARRY MARINA 1
TO-23-KBY-MR-2-02 | KILBARRY MARINA 2
TO-23-KPG-TB-1-02 | KILPADDOGE TARBERT 1
TO-23-220 kV A1/A2 @ KRA-02 | KNOCKRAHA 220 kV A1/A2
TO-23-KRA-220K1-06 | KNOCKRAHA 220K1
TO-23-KRA-220K1-2-03 | KNOCKRAHA 220K1-2
TO-23-KRA-220SA2-4CB-03 | KNOCKRAHA 220SA2-4CB
TO-23-KRA-MID-1-01 | KNOCKRAHA MIDLETON
TO-23-LET-M/CAP1-01 | LETTERKENNY M/CAP1
TO-23-LIS-SKL-1-06 | LISDRUM SHANKILL
TO-23-LIS-T131-05 | LISDRUM T131
TO-23-110 kV A2 @ LOU-01 | LOUTH 110 kV A2
TO-23-110 kV B2 @ LOU-01 | LOUTH 110 kV B2
TO-23-MUL-CAP1-02 | MULLINGAR CAP1
TO-23-NAV-T141-01 | NAVAN T141
TO-23-PB-R2002-02 | POOLBEG R2002
TO-23-PRO-TB-1-04 | PROSPECT TARBERT
TO-23-110 kV A2 @ SH-03 | SHANNONBRIDGE 110 kV A2
TO-23-110 kV B1 @ SH-02 | SHANNONBRIDGE 110 kV B1
TO-23-110 kV B2 @ SH-04 | SHANNONBRIDGE 110 kV B2
TO-23-SLI-CAP1-02 | SLIGO CAP1
TO-23-TB-220K1-2-01 | TARBERT 220K1-2
TO-23-TB-T101-02 | TARBERT T101
TO-23-TB-T2003-03 | TARBERT T2003
TO-23-TB-T2004-02 | TARBERT T2004
TO-23-TB-T2004-03
TO-23-TB-T2101-02 | TARBERT T2101
TO-23-TB-T2101-03
TO-23-THU-CAP2-01 | THURLES CAP2
TO-23-UGL-T132-04 | UGGOOL T132