## Wks 39 - 40
Report covers outages commencing/returning/spanning the period: 25/09/2023 - 08/10/2023
Outages commencing/returning in Week 39
OUTAGE ID | PLANT |  | Week 39 | [6 empty] | Week 40
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9
TO-23-NEW-PLS-1-04 | NEWBRIDGE PORTLAOISE | bar: Week 39 Mo 25
TO-23-110 kV A1 @ BVK-02 | BALLYVOUSKILL 110 kV A1 | bar: Week 39 Mo 25 to Week 39 Tu 26
TO-23-110 kV B1 @ BVK-02 | BALLYVOUSKILL 110 kV B1 | bar: Week 39 Mo 25 to Week 39 Tu 26
TO-23-BVK-110K1-03 | BALLYVOUSKILL 110K1 | bar: Week 39 Mo 25 to Week 39 Tu 26
TO-23-BVK-110SA1-2CB-02 | BALLYVOUSKILL 110SA1-2CB | bar: Week 39 Mo 25 to Week 39 Tu 26
TO-23-BVK-110SB1-2CB-02 | BALLYVOUSKILL 110SB1-2CB | bar: Week 39 Mo 25 to Week 39 Tu 26
TO-23-BVK-GRO-1-01 | BALLYVOUSKILL GARROW | bar: Week 39 Mo 25 to Week 39 Tu 26
TO-23-CKG-T122-01 | CORKAGH T122 | bar: Week 39 Mo 25 to Week 39 Tu 26
TO-23-MP GIS-T4003-01 | MONEYPOINT GIS T4003 | bar: Week 39 Mo 25 to Week 39 Tu 26
TO-23-CAH-KHL-1-01 | CAHIR KILL HILL | bar: Week 39 Mo 25 to Week 39 We 27
TO-23-110 kV A4 @ CDU-05 | CORDUFF 110 kV A4 | bar: Week 39 Mo 25 to Week 40 Fr 6
TO-23-110 kV B4 @ CDU-05 | CORDUFF 110 kV B4 | bar: Week 39 Mo 25 to Week 40 Fr 6
TO-23-LET-PST-01 | LETTERKENNY STRABANE PST
TO-23-CLE-T221-01 | CLONEE T221 | bar: Su 24 to Week 39 Mo 25
TO-23-GLR-MOY-1-01 | GLENREE MOY | bar: Su 24 to Week 39 Mo 25
TO-23-MOY-110SA1-2CB-03 | MOY 110SA1-2CB | bar: Su 24 to Week 39 Mo 25
TO-23-MOY-CAP1-01 | MOY CAP1 | bar: Su 24 to Week 39 Mo 25
TO-23-MOY-T141-01 | MOY T141 | bar: Su 24 to Week 39 Mo 25
TO-23-MOY-TAW-1-03 | MOY TAWNAGHMORE 1 | bar: Su 24 to Week 39 Mo 25
TO-23-KIN-MUL-1-04 | KINNEGAD MULLINGAR | bar: Week 39 Tu 26
TO-23-LA-MUL-1-02 | LANESBORO MULLINGAR | bar: Week 39 Tu 26
TO-23-MUL-110SA1-2CB-02 | MULLINGAR 110SA1-2CB | bar: Week 39 Tu 26
TO-23-MUL-CAP1-03 | MULLINGAR CAP1 | bar: Week 39 Tu 26
TO-23-MUL-T101-01 | MULLINGAR T101 | bar: Week 39 Tu 26
TO-23-MUL-T141-01 | MULLINGAR T141 | bar: Week 39 Tu 26
TO-23-ARV-GWE-1-04 | ARVA GORTAWEE | bar: Week 39 Tu 26 to Week 39 Th 28
TO-23-ATY-CLW-1-04 | ATHY CARLOW | bar: Week 39 Tu 26 to Week 40 Fr 6
TO-23-CLE-WOO-1-04 | CLONEE WOODLAND | bar: Week 39 We 27
TO-23-220 kV A1 @ CLE-02 | CLONEE 220 kV A1 | bar: Week 39 We 27 to Week 39 Th 28
TO-23-220 kV A2 @ CLE-02 | CLONEE 220 kV A2 | bar: Week 39 We 27 to Week 39 Th 28
TO-23-220 kV B1 @ CLE-01 | CLONEE 220 kV B1 | bar: Week 39 We 27 to Week 39 Th 28
TO-23-220 kV B2 @ CLE-01 | CLONEE 220 kV B2 | bar: Week 39 We 27 to Week 39 Th 28
TO-23-CLE-220K1-02 | CLONEE 220K1 | bar: Week 39 We 27 to Week 39 Th 28
TO-23-CLE-220K2-03 | CLONEE 220K2 | bar: Week 39 We 27 to Week 39 Th 28
TO-23-CLE-220SA1-2CB-02 | CLONEE 220SA1-2CB | bar: Week 39 We 27 to Week 39 Th 28
TO-23-CLE-220SB1-2CB-01 | CLONEE 220SB1-2CB | bar: Week 39 We 27 to Week 39 Th 28
TO-23-CKG-T123-01 | CORKAGH T123 | bar: Week 39 We 27 to Week 39 Th 28
TO-23-CAH-TIP-1-01 | CAHIR TIPPERARY | bar: Week 39 Th 28 to Week 39 Fr 29
TO-23-KLS-KKY-1-05 | KELLIS KILKENNY | bar: Week 39 Th 28 to Week 39 Fr 29
TO-23-KKY-110SA1-2CB-03 | KILKENNY 110SA1-2CB | bar: Week 39 Th 28 to Week 39 Fr 29
TO-23-KKY-T141-04 | KILKENNY T141 | bar: Week 39 Th 28 to Week 39 Fr 29
TO-23-UGL-T132-04 | UGGOOL T132 | bar: Su 24 to Week 39 Th 28
TO-23-CKM GIS-T2103-01 | CARRICKMINES GIS T2103 | bar: Week 39 Fr 29 to Week 40 Mo 9
TO-23-AA GIS-T102-04 | ARDNACRUSHA GIS T102 | bar: Su 24 to Week 39 Fr 29
TO-23-DSN-220K1-2-01 | DUNSTOWN 220K1-2 | bar: Su 24 to Week 39 Fr 29
TO-23-110 kV A1 @ KLS-03 | KELLIS 110 kV A1 | bar: Su 24 to Week 39 Fr 29
TO-23-110 kV A2 @ KLS-04 | KELLIS 110 kV A2 | bar: Su 24 to Week 39 Fr 29
TO-23-110 kV B1 @ KLS-03 | KELLIS 110 kV B1 | bar: Su 24 to Week 39 Fr 29
TO-23-110 kV B2 @ KLS-04 | KELLIS 110 kV B2 | bar: Su 24 to Week 39 Fr 29
TO-23-KLS-110K1-2-02 | KELLIS 110K1-2 | bar: Su 24 to Week 39 Fr 29
TO-23-110 kV A1 @ SH-05 | SHANNONBRIDGE 110 kV A1 | bar: Su 24 to Week 39 Fr 29
TO-23-110 kV A2 @ SH-03 | SHANNONBRIDGE 110 kV A2 | bar: Su 24 to Week 39 Fr 29
TO-23-110 kV B1 @ SH-02 | SHANNONBRIDGE 110 kV B1 | bar: Su 24 to Week 39 Fr 29
TO-23-110 kV B2 @ SH-04 | SHANNONBRIDGE 110 kV B2 | bar: Su 24 to Week 39 Fr 29
Outages commencing/returning in Week 40
OUTAGE ID | PLANT | Week 39 Mo 25: Week 39; Week 40 Mo 2: Week 40
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9
TO-23-ATH-T142-03 | ATHLONE T142 | bar: Week 40 Mo 2 to Week 40 Tu 3
Report covers outages commencing/returning/spanning the period: 25/09/2023 - 08/10/2023
Outages commencing/returning in Week 40
OUTAGE ID | PLANT | Week 39 Mo 25: Week 39; Week 40 Mo 2: Week 40
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9
TO-23-MP GIS-110SA1-2CB-02 | MONEYPOINT GIS 110SA1-2CB
TO-23-MP GIS-ST101-03 | MONEYPOINT GIS ST101
TO-23-TBK-T141-01 | TULLABRACK T141
TO-23-TBK,T-BOL-1-01 | TULLABRACK tee BOOLTIAGH
TO-23-TBK,T-MP GIS-1-01 | TULLABRACK tee MONEYPOINT GIS
TO-23-TBK,T-TBK-1-01 | TULLABRACK tee TULLABRACK
TO-23-CLH-TRL-1-02 | CLAHANE TRALEE
TO-23-GI-T2102-01 | GREAT ISLAND T2102
TO-23-MP GIS-T121-03 | MONEYPOINT GIS T121
TO-23-220 kV A1 @ BVK-01 | BALLYVOUSKILL 220 kV A1
TO-23-220 kV B1 @ BVK-01 | BALLYVOUSKILL 220 kV B1
TO-23-BVK-CLA-1-01 | BALLYVOUSKILL CLASHAVOON
TO-23-BK-110SA1-01 | BELLACORICK 110SA1
TO-23-BK-110SA2-01 | BELLACORICK 110SA2
TO-23-BK-MOY-1-03 | BELLACORICK MOY
TO-23-BK-T141-01 | BELLACORICK T141
TO-23-CDU-MCE-1-02 | CORDUFF MACETOWN
TO-23-COL-CDU-1-02 | COLLEGE PARK CORDUFF
TO-23-KNR-T2102-01 | KNOCKANURE T2102
TO-23-CUS-T103/5-01 | CUSHALING T103/5
TO-23-KTL-T131-01 | KILTEEL T131
TO-23-LOU-T2102-04 | LOUTH T2102
TO-23-AD-KRA-1-05 | AGHADA KNOCKRAHA 1
TO-23-KLN-T2103-02 | KILLONAN T2103
TO-23-LOU-T2102-05 | LOUTH T2102
TO-23-DDK-LOU-1-01 | DUNDALK LOUTH
TO-23-110 kV A2 @ LOU-01 | LOUTH 110 kV A2
TO-23-110 kV B2 @ LOU-01 | LOUTH 110 kV B2
Outages spanning Weeks 39-40
OUTAGE ID | PLANT | Week 39 Mo 25: Week 39; Week 40 Mo 2: Week 40
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9
TO-23-220 kV A2 @ AD-01 | AGHADA 220 kV A2
TO-23-220 kV B2 @ AD-01 | AGHADA 220 kV B2
TO-23-AD-SA1-2CB-01 | AGHADA 220SA1-2CB
TO-23-AD-SB1-2CB-01 | AGHADA 220SB1-2CB
TO-23-AD-T2001-03 | AGHADA T2001
TO-23-BOG-CRA-1-01 | BANOGE CRANE
TO-23-BUT-CUL-1-02 | BUTLERSTOWN CULLENAGH
TO-23-BUT-T141-02 | BUTLERSTOWN T141
TO-23-CSH-CAP2-04 | CASHLA CAP2
TO-23-CSH-GAL-1-01 | CASHLA GALWAY 1
TO-23-CLG-110K1-01 | CLOGHRAN 110K1
TO-23-CRO-IA-1-02 | COOLROE INNISCARRA
TO-23-DOO-T142-02 | DOON T142
TO-23-DRY-PLA-1-04 | DRYBRIDGE PLATIN
TO-23-220 kV A2 @ FIN-02 | FINGLAS 220 kV A2
TO-23-FIN-T2104-02 | FINGLAS T2104
TO-23-GAL-110K2-3-02 | GALWAY 110K2-3
TO-23-GRI,T-GCA-1-03 | GRIFFINRATH tee GRANGE CASTLE
TO-23-INC-220K1-2-01 | INCHICORE 220K1-2
TO-23-KLS-220K1-2-04 | KELLIS 220K1-2
TO-23-KBY-MR-1-06 | KILBARRY MARINA 1
TO-23-KBY-MR-2-02 | KILBARRY MARINA 2
TO-23-KPG-TB-1-02 | KILPADDOGE TARBERT 1
TO-23-220 kV A1/A2 @ KRA-02 | KNOCKRAHA 220 kV A1/A2
TO-23-KRA-220K1-06 | KNOCKRAHA 220K1
TO-23-KRA-220K1-2-03 | KNOCKRAHA 220K1-2
TO-23-KRA-220SA2-4CB-03 | KNOCKRAHA 220SA2-4CB
TO-23-KRA-MID-1-01 | KNOCKRAHA MIDLETON
Report covers outages commencing/returning/spanning the period: 25/09/2023 - 08/10/2023
Outages spanning Weeks 39-40
OUTAGE ID | PLANT | Week 39 Mo 25: Week 39; Week 40 Mo 2: Week 40
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9
TO-23-LET-M/CAP1-01 | LETTERKENNY M/CAP1
TO-23-LIS-SKL-1-06 | LISDRUM SHANKILL
TO-23-LIS-T131-05 | LISDRUM T131
TO-23-MUL-CAP1-02 | MULLINGAR CAP1
TO-23-PB-R2002-02 | POOLBEG R2002
TO-23-PRO-TB-1-04 | PROSPECT TARBERT
TO-23-SH-T2101-01 | SHANNONBRIDGE T2101
TO-23-TB-220K1-2-01 | TARBERT 220K1-2
TO-23-TB-T101-02 | TARBERT T101
TO-23-TB-T2003-03 | TARBERT T2003
TO-23-TB-T2004-03 | TARBERT T2004
TO-23-TB-T2004-02
TO-23-TB-T2101-03 | TARBERT T2101
TO-23-TB-T2101-02
TO-23-THU-CAP2-01 | THURLES CAP2