## Wks 41 - 42
Report covers outages commencing/returning/spanning the period: 09/10/2023 - 22/10/2023
Outages commencing/returning in Week 41
OUTAGE ID | PLANT |  | Week 41 | [6 empty] | Week 42
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23
TO-23-BGH-T121-01 | BOGGERAGH T121
TO-23-BAG-T101-01 | BARNAGEERAGH T101
TO-23-GI-T2101-02 | GREAT ISLAND T2101
TO-23-INC-PB-1-05 | INCHICORE POOLBEG 1
TO-23-220 kV A1 @ PB-03 | POOLBEG 220 kV A1
TO-23-220 kV A2 @ PB-04 | POOLBEG 220 kV A2
TO-23-220 kV B1 @ PB-03 | POOLBEG 220 kV B1
TO-23-220 kV B2 @ PB-04 | POOLBEG 220 kV B2
TO-23-PB-220SA1-2-07 | POOLBEG 220SA1-2
TO-23-PB-220SB1-2-07 | POOLBEG 220SB1-2
TO-23-ATY-T101-01 | ATHY T101 | bar: Week 41 We 11 to Week 41 Th 12
TO-23-CBA-TRI-1-03 | CLOGHBOOLA TRIEN | bar: Week 41 We 11 to Week 41 Th 12
TO-23-110 kV A2 @ CSH-11 | CASHLA 110 kV A2 | bar: Week 41 We 11 to Week 41 Fr 13
TO-23-110 kV B2 @ CSH-12 | CASHLA 110 kV B2 | bar: Week 41 We 11 to Week 41 Fr 13
TO-23-CSH-ENN-1-02 | CASHLA ENNIS | bar: Week 41 We 11 to Week 41 Fr 13
TO-23-CBA-110SA1-02 | CLOGHBOOLA 110SA1 | bar: Week 41 We 11 to Week 41 Fr 13
TO-23-CBA-110SA2-02 | CLOGHBOOLA 110SA2 | bar: Week 41 We 11 to Week 41 Fr 13
TO-23-CBA-T122-03 | CLOGHBOOLA T122 | bar: Week 41 We 11 to Week 41 Fr 13
TO-23-CBA-T131-03 | CLOGHBOOLA T131 | bar: Week 41 We 11 to Week 41 Fr 13
TO-23-110 kV A2 @ FLA-04 | FLAGFORD 110 kV A2 | bar: Week 41 We 11 to Week 42 We 18
TO-23-110 kV B2 @ FLA-05 | FLAGFORD 110 kV B2 | bar: Week 41 We 11 to Week 42 We 18
TO-23-220 kV A2 @ FLA-03 | FLAGFORD 220 kV A2 | bar: Week 41 We 11 to Week 42 We 18
TO-23-220 kV B2 @ FLA-02 | FLAGFORD 220 kV B2 | bar: Week 41 We 11 to Week 42 We 18
TO-23-FLA-T2102-01 | FLAGFORD T2102 | bar: Week 41 We 11 to Week 42 We 18
TO-23-110 kV A2 @ CDU-03 | CORDUFF 110 kV A2 | bar: Week 41 We 11 to Week 42 Fr 20
TO-23-110 kV A4 @ CDU-05 | CORDUFF 110 kV A4 | bar: Week 41 We 11 to Week 42 Fr 20
TO-23-110 kV B2 @ CDU-02 | CORDUFF 110 kV B2 | bar: Week 41 We 11 to Week 42 Fr 20
TO-23-110 kV B4 @ CDU-05 | CORDUFF 110 kV B4 | bar: Week 41 We 11 to Week 42 Fr 20
TO-23-110 kV A2 @ KRA-02 | KNOCKRAHA 110 kV A2 | bar: Week 41 We 11 to Week 42 Fr 20
TO-23-110 kV B2 @ KRA-04 | KNOCKRAHA 110 kV B2 | bar: Week 41 We 11 to Week 42 Fr 20
TO-23-220 kV A2 @ LOU-01 | LOUTH 220 kV A2 | bar: Week 41 We 11 to Week 42 Fr 20
TO-23-220 kV B2 @ LOU-01 | LOUTH 220 kV B2 | bar: Week 41 We 11 to Week 42 Fr 20
TO-23-LOU-T2102-01 | LOUTH T2102 | bar: Week 41 We 11 to Week 42 Fr 20
TO-23-110 kV A2 @ KBY-04 | KILBARRY 110 kV A2 | bar: Week 41 We 11 to Week 42 Su 22
TO-23-110 kV B2 @ KBY-05 | KILBARRY 110 kV B2 | bar: Week 41 We 11 to Week 42 Su 22
TO-23-110 kV A1 @ MR-02 | MARINA 110 kV A1 | bar: Week 41 We 11 to Week 42 Su 22
TO-23-110 kV B1 @ MR-02 | MARINA 110 kV B1 | bar: Week 41 We 11 to Week 42 Su 22
TO-23-BLK-T142-03 | BLAKE T142 | bar: Week 41 We 11 to Week 42 Mo 23
TO-23-BLK,T-BLK-1-03 | BLAKE tee BLAKE | bar: Week 41 We 11 to Week 42 Mo 23
TO-23-BLK,T-MAY-1-02 | BLAKE tee MAYNOOTH | bar: Week 41 We 11 to Week 42 Mo 23
TO-23-BLK,T-NEW-1-01 | BLAKE tee NEWBRIDGE | bar: Week 41 We 11 to Week 42 Mo 23
TO-23-KLS-T2101-03 | KELLIS T2101 | bar: Week 41 We 11 to Week 42 Mo 23
TO-23-BRT-220K2-01 | BRACETOWN 220K2
TO-23-ROP-T131-01 | ROSSPILE T131 | bar: Week 41 We 11
TO-23-BYH-110K1-02 | BALLYNAHULLA 110K1 | bar: Week 41 We 11 to Week 41 Th 12
TO-23-AD-LPT-1-01 | AGHADA LONG POINT | bar: Week 41 We 11 to Week 42 Mo 16
TO-23-LPT-T2002-01 | LONG POINT T2002 | bar: Week 41 We 11 to Week 42 Mo 16
TO-23-PB-T2007/8-02 | POOLBEG T2007/8 | bar: Su 8
TO-23-220 kV A1 @ BVK-01 | BALLYVOUSKILL 220 kV A1 | bar: Su 8; Week 41 We 11 to Week 41 Th 12
TO-23-220 kV B1 @ BVK-01 | BALLYVOUSKILL 220 kV B1 | bar: Su 8; Week 41 We 11 to Week 41 Th 12
TO-23-BVK-CLA-1-01 | BALLYVOUSKILL CLASHAVOON | bar: Su 8; Week 41 We 11 to Week 41 Th 12
TO-23-AD-KRA-1-05 | AGHADA KNOCKRAHA 1 | bar: Su 8; Week 41 We 11 to Week 41 Fr 13
TO-23-RAF-TBG-1-03 | RAFFEEN TRABEG 1 | bar: Week 41 Sa 14 to Week 41 Su 15
Outages commencing/returning in Week 42
OUTAGE ID | PLANT | Week 41 Mo 9: Week 41; Week 42 Mo 16: Week 42
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23
TO-23-BAG-T103-01 | BARNAGEERAGH T103 | bar: Week 42 Mo 16 to Week 42 Tu 17
TO-23-CDU-MCE-1-02 | CORDUFF MACETOWN | bar: Week 42 Mo 16 to Week 42 Tu 17
Report covers outages commencing/returning/spanning the period: 09/10/2023 - 22/10/2023
Outages commencing/returning in Week 42
OUTAGE ID | PLANT | Week 41 Mo 9: Week 41; Week 42 Mo 16: Week 42
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23
TO-23-220 kV A1 @ TB-01 | TARBERT 220 kV A1
TO-23-CTN-KLN-1-01 | CAUTEEN KILLONAN
TO-23-CHA-MAL-1-03 | CHARLEVILLE MALLOW
TO-23-KPG-TRL-2-02 | KILPADDOGE TRALEE 2
TO-23-MAY-SH-1-02 | MAYNOOTH SHANNONBRIDGE
TO-23-KYT-T233-01 | KELLYSTOWN T233
TO-23-110 kV A5 @ FIN GIS-02 | FINGLAS GIS 110 kV A5
TO-23-110 kV B5 @ FIN GIS-02 | FINGLAS GIS 110 kV B5
TO-23-FIN GIS-110K5-01 | FINGLAS GIS 110K5
TO-23-FIN GIS-110SA3-5CB-04 | FINGLAS GIS 110SA3-5CB
TO-23-FIN GIS-110SB3-5CB-04 | FINGLAS GIS 110SB3-5CB
TO-23-KPG-TB-1-02 | KILPADDOGE TARBERT 1
TO-23-TB-220K1-2-01 | TARBERT 220K1-2
TO-23-TB-T2004-03 | TARBERT T2004
TO-23-TB-T2101-03 | TARBERT T2101
TO-23-CDU-220K1-3-03 | CORDUFF 220K1-3
TO-23-220 kV A2 @ AD-01 | AGHADA 220 kV A2
TO-23-220 kV B2 @ AD-01 | AGHADA 220 kV B2
TO-23-AD-SA1-2CB-01 | AGHADA 220SA1-2CB
TO-23-AD-SB1-2CB-01 | AGHADA 220SB1-2CB
TO-23-AD-T2001-03 | AGHADA T2001
TO-23-MOY-110SA1-2CB-01 | MOY 110SA1-2CB
TO-23-MOY-CAP2-01 | MOY CAP2
TO-23-MOY-T142-01 | MOY T142
TO-23-MOY-TAW-2-02 | MOY TAWNAGHMORE 2
TO-23-AD-KRA-2-05 | AGHADA KNOCKRAHA 2
TO-23-MP GIS-T2102-01 | MONEYPOINT GIS T2102
Outages spanning Weeks 41-42
OUTAGE ID | PLANT | Week 41 Mo 9: Week 41; Week 42 Mo 16: Week 42
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23
TO-23-BOG-CRA-1-01 | BANOGE CRANE
TO-23-BK-110SA1-01 | BELLACORICK 110SA1
TO-23-BK-110SA2-01 | BELLACORICK 110SA2
TO-23-BK-MOY-1-03 | BELLACORICK MOY
TO-23-BK-T141-01 | BELLACORICK T141
TO-23-BUT-CUL-1-02 | BUTLERSTOWN CULLENAGH
TO-23-BUT-T141-02 | BUTLERSTOWN T141
TO-23-CSH-CAP2-04 | CASHLA CAP2
TO-23-CSH-GAL-1-01 | CASHLA GALWAY 1
TO-23-CLG-110K1-01 | CLOGHRAN 110K1
TO-23-CRO-IA-1-02 | COOLROE INNISCARRA
TO-23-DOO-T142-02 | DOON T142
TO-23-DRY-PLA-1-04 | DRYBRIDGE PLATIN
TO-23-220 kV A2 @ FIN-02 | FINGLAS 220 kV A2
TO-23-FIN-T2104-02 | FINGLAS T2104
TO-23-GAL-110K2-3-02 | GALWAY 110K2-3
TO-23-GAL-GAL GIS-2-03 | GALWAY GALWAY GIS 2
TO-23-GGO-220K1-2-02 | GLANAGOW 220K1-2
TO-23-GRI,T-GCA-1-03 | GRIFFINRATH tee GRANGE CASTLE
TO-23-INC-220K1-2-01 | INCHICORE 220K1-2
TO-23-KLS-220K1-2-04 | KELLIS 220K1-2
TO-23-KBY-MR-1-06 | KILBARRY MARINA 1
TO-23-KBY-MR-2-02 | KILBARRY MARINA 2
TO-23-220 kV A1/A2 @ KRA-02 | KNOCKRAHA 220 kV A1/A2
TO-23-KRA-220K1-06 | KNOCKRAHA 220K1
TO-23-KRA-220K1-2-03 | KNOCKRAHA 220K1-2
TO-23-KRA-220SA2-4CB-03 | KNOCKRAHA 220SA2-4CB
TO-23-KRA-MID-1-01 | KNOCKRAHA MIDLETON
TO-23-LET-M/CAP1-01 | LETTERKENNY M/CAP1
Report covers outages commencing/returning/spanning the period: 09/10/2023 - 22/10/2023
Outages spanning Weeks 41-42
OUTAGE ID | PLANT | Week 41 Mo 9: Week 41; Week 42 Mo 16: Week 42
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23
TO-23-LET-PST-01 | LETTERKENNY STRABANE PST
TO-23-LIS-SKL-1-06 | LISDRUM SHANKILL
TO-23-LIS-T131-05 | LISDRUM T131
TO-23-LOU-RRU-1-05 | LOUTH RATRUSSAN
TO-23-MUL-CAP1-02 | MULLINGAR CAP1
TO-23-PB-R2002-02 | POOLBEG R2002
TO-23-PRO-TB-1-04 | PROSPECT TARBERT
TO-23-SOM,T-SH-1-06 | SOMERSET tee SHANNONBRIDGE
TO-23-TB-T101-02 | TARBERT T101
TO-23-TB-T2003-03 | TARBERT T2003
TO-23-TB-T2004-02 | TARBERT T2004
TO-23-TB-T2101-02 | TARBERT T2101
TO-23-THU-CAP2-01 | THURLES CAP2
TO-23-TRI-CAP1-01 | TRIEN CAP1