## Wks 43 - 44
Report covers outages commencing/returning/spanning the period: 23/10/2023 - 05/11/2023
Outages commencing/returning in Week 43
OUTAGE ID | PLANT |  | Week 43 | [6 empty] | Week 44
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6
TO-23-CAH-DOO-1-04 | CAHIR DOON
TO-23-DOO-110SA1-04 | DOON 110SA1
TO-23-DOO-110SA2-04 | DOON 110SA2
TO-23-110 kV A1 @ LOU-04 | LOUTH 110 kV A1
TO-23-110 kV B1 @ LOU-04 | LOUTH 110 kV B1
TO-23-MP GIS-110SA1-2CB-02 | MONEYPOINT GIS 110SA1-2CB
TO-23-MP GIS-ST101-03 | MONEYPOINT GIS ST101
TO-23-MP GIS-T2102-02 | MONEYPOINT GIS T2102
TO-23-TBK,T-MP GIS-1-03 | TULLABRACK tee MONEYPOINT GIS
TO-23-110 kV A1 @ ARV-02 | ARVA 110 kV A1 | bar: Week 43 Fr 27
TO-23-110 kV B1 @ ARV-01 | ARVA 110 kV B1 | bar: Week 43 Fr 27
TO-23-ARV-SKL-1-02 | ARVA SHANKILL 1 | bar: Week 43 Fr 27
TO-23-CKM GIS-220K4-02 | CARRICKMINES GIS 220K4 | bar: Week 43 Fr 27
TO-23-CKM GIS-220SA2-4CB-05 | CARRICKMINES GIS 220SA2-4CB | bar: Week 43 Fr 27
TO-23-CKM GIS-220SB2-4CB-05 | CARRICKMINES GIS 220SB2-4CB | bar: Week 43 Fr 27
TO-23-CKM GIS-DSN-1-05 | CARRICKMINES GIS DUNSTOWN | bar: Week 43 Fr 27
TO-23-CKM GIS-T2104-01 | CARRICKMINES GIS T2104 | bar: Week 43 Fr 27
TO-23-DRU-CAP2-03 | DRUMLINE CAP2 | bar: Week 43 Fr 27
TO-23-DRY-110SA1-05 | DRYBRIDGE 110SA1 | bar: Week 43 Fr 27
TO-23-DRY-110SA2-05 | DRYBRIDGE 110SA2 | bar: Week 43 Fr 27
TO-23-DRY-LOU-1-06 | DRYBRIDGE LOUTH | bar: Week 43 Fr 27
TO-23-DRY-T141-04 | DRYBRIDGE T141 | bar: Week 43 Fr 27
TO-23-110 kV A2 @ KNY-03 | KNOCKRANNY 110 kV A2 | bar: Week 43 Fr 27
TO-23-110 kV B2 @ KNY-03 | KNOCKRANNY 110 kV B2 | bar: Week 43 Fr 27
TO-23-KNY-SAL-1-01 | KNOCKRANNY SALTHILL | bar: Week 43 Fr 27
TO-23-MCE-T124-02 | MACETOWN T124 | bar: Week 43 Fr 27
TO-23-MP GIS-T121-03 | MONEYPOINT GIS T121 | bar: Week 43 Fr 27
TO-23-PLA-110SA1-05 | PLATIN 110SA1 | bar: Week 43 Fr 27
TO-23-PLA-110SA2-05 | PLATIN 110SA2 | bar: Week 43 Fr 27
TO-23-PLA-T101/2/3/4-05 | PLATIN T101/2/3/4 | bar: Week 43 Fr 27
TO-23-220 kV A1 @ PB-04 | POOLBEG 220 kV A1 | bar: Week 43 Fr 27
TO-23-220 kV A2 @ PB-03 | POOLBEG 220 kV A2 | bar: Week 43 Fr 27
TO-23-220 kV B1 @ PB-04 | POOLBEG 220 kV B1 | bar: Week 43 Fr 27
TO-23-220 kV B2 @ PB-03 | POOLBEG 220 kV B2 | bar: Week 43 Fr 27
TO-23-PB-220SA1-2-06 | POOLBEG 220SA1-2 | bar: Week 43 Fr 27
TO-23-PB-220SB1-2-06 | POOLBEG 220SB1-2 | bar: Week 43 Fr 27
TO-23-KYT-T237-01 | KELLYSTOWN T237 | bar: Week 43 Fr 27 to Week 44 Mo 6
TO-23-220 kV A1 @ LOU-01 | LOUTH 220 kV A1 | bar: Week 43 Fr 27 to Week 44 Mo 6
TO-23-220 kV B1 @ LOU-02 | LOUTH 220 kV B1 | bar: Week 43 Fr 27 to Week 44 Mo 6
TO-23-LOU-T2103-01 | LOUTH T2103 | bar: Week 43 Fr 27 to Week 44 Mo 6
TO-23-BDA-T101-01 | BARODA T101
TO-23-MOY-110SA1-2CB-01 | MOY 110SA1-2CB | bar: Su 22
TO-23-MOY-CAP2-01 | MOY CAP2 | bar: Su 22
TO-23-MOY-T142-01 | MOY T142 | bar: Su 22
TO-23-MOY-TAW-2-02 | MOY TAWNAGHMORE 2 | bar: Su 22
TO-23-AA GIS-SNG-1-03 | ARDNACRUSHA GIS SINGLAND | bar: Week 43 Fr 27
TO-23-220 kV A1 @ AD-01 | AGHADA 220 kV A1 | bar: Su 22
TO-23-220 kV B1 @ AD-01 | AGHADA 220 kV B1 | bar: Su 22
TO-23-AD-KRA-2-01 | AGHADA KNOCKRAHA 2 | bar: Su 22
TO-23-BK-110SA1-01 | BELLACORICK 110SA1 | bar: Su 22; Week 43 Fr 27
TO-23-BK-110SA2-01 | BELLACORICK 110SA2 | bar: Su 22; Week 43 Fr 27
TO-23-BK-MOY-1-03 | BELLACORICK MOY | bar: Su 22; Week 43 Fr 27
TO-23-BK-T141-01 | BELLACORICK T141 | bar: Su 22; Week 43 Fr 27
TO-23-BLK-T142-03 | BLAKE T142 | bar: Su 22; Week 43 Fr 27
TO-23-BLK,T-BLK-1-03 | BLAKE tee BLAKE | bar: Su 22; Week 43 Fr 27
TO-23-BLK,T-MAY-1-02 | BLAKE tee MAYNOOTH | bar: Su 22; Week 43 Fr 27
TO-23-BLK,T-NEW-1-01 | BLAKE tee NEWBRIDGE | bar: Su 22; Week 43 Fr 27
TO-23-DRY-PLA-1-04 | DRYBRIDGE PLATIN | bar: Su 22; Week 43 Fr 27
TO-23-INC-PB-1-05 | INCHICORE POOLBEG 1 | bar: Week 43 Sa 28 to Week 43 Su 29
TO-23-220 kV A1 @ PB-03 | POOLBEG 220 kV A1 | bar: Week 43 Sa 28 to Week 43 Su 29
TO-23-220 kV A2 @ PB-04 | POOLBEG 220 kV A2 | bar: Week 43 Sa 28 to Week 43 Su 29
Report covers outages commencing/returning/spanning the period: 23/10/2023 - 05/11/2023
Outages commencing/returning in Week 43
OUTAGE ID | PLANT | Week 43 Mo 23: Week 43; Week 44 Mo 30: Week 44
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6
TO-23-220 kV B1 @ PB-03 | POOLBEG 220 kV B1 | bar: Week 43 Sa 28 to Week 43 Su 29
TO-23-220 kV B2 @ PB-04 | POOLBEG 220 kV B2 | bar: Week 43 Sa 28 to Week 43 Su 29
TO-23-PB-220SA1-2-07 | POOLBEG 220SA1-2 | bar: Week 43 Sa 28 to Week 43 Su 29
TO-23-PB-220SB1-2-07 | POOLBEG 220SB1-2 | bar: Week 43 Sa 28 to Week 43 Su 29
TO-23-CAH-DOO-1-01 | CAHIR DOON | bar: Week 43 Su 29
TO-23-DOO-110SA1-03 | DOON 110SA1 | bar: Week 43 Su 29
TO-23-DOO-110SA2-03 | DOON 110SA2 | bar: Week 43 Su 29
TO-23-DOO-T142-02 | DOON T142 | bar: Su 22 to Week 43 Su 29
TO-23-PB-T2007/8-02 | POOLBEG T2007/8 | bar: Su 22 to Week 43 Su 29
Outages commencing/returning in Week 44
OUTAGE ID | PLANT | Week 43 Mo 23: Week 43; Week 44 Mo 30: Week 44
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6
TO-23-DRY-110SA1-01 | DRYBRIDGE 110SA1 | bar: Week 44 Mo 30 to Week 44 Fr 3
TO-23-DRY-110SA2-07 | DRYBRIDGE 110SA2 | bar: Week 44 Mo 30 to Week 44 Fr 3
TO-23-DRY-LOU-1-01 | DRYBRIDGE LOUTH | bar: Week 44 Mo 30 to Week 44 Fr 3
TO-23-DRY-OBE-1-01 | DRYBRIDGE OLDBRIDGE | bar: Week 44 Mo 30 to Week 44 Fr 3
TO-23-DRY-T141-01 | DRYBRIDGE T141 | bar: Week 44 Mo 30 to Week 44 Fr 3
TO-23-PB-R2001-02 | POOLBEG R2001 | bar: Week 44 Mo 30 to Week 44 Fr 3
TO-23-ARV-110K1-2-01 | ARVA 110K1-2 | bar: Week 44 Mo 30 to Week 44 Mo 6
TO-23-DFR-T122-03 | DUNFIRTH T122 | bar: Week 44 Tu 31 to Week 44 We 1
TO-23-DND-T124-01 | DARNDALE T124 | bar: Week 44 Tu 31 to Week 44 Fr 3
TO-23-KPG-MP GIS-1-01 | KILPADDOGE MONEYPOINT GIS 1 | bar: Week 44 Tu 31 to Week 44 Fr 3
TO-23-220 kV A1 @ MP GIS-01 | MONEYPOINT GIS 220 kV A1 | bar: Week 44 Tu 31 to Week 44 Fr 3
TO-23-MP GIS-220K1-01 | MONEYPOINT GIS 220K1 | bar: Week 44 Tu 31 to Week 44 Fr 3
TO-23-MP GIS-220SA1-2CB-02 | MONEYPOINT GIS 220SA1-2CB | bar: Week 44 Tu 31 to Week 44 Fr 3
TO-23-BK-CBR-1-01 | BELLACORICK CASTLEBAR | bar: Week 44 Tu 31 to Week 44 Mo 6
TO-23-INC-ISH-1-04 | INCHICORE IRISHTOWN | bar: Week 44 We 1 to Week 44 Mo 6
TO-23-ISH-220K1-2-02 | IRISHTOWN 220K1-2 | bar: Week 44 We 1 to Week 44 Mo 6
TO-23-ISH-SHL-1-04 | IRISHTOWN SHELLYBANKS | bar: Week 44 We 1 to Week 44 Mo 6
TO-23-KLN-KRA-1-03 | KILLONAN KNOCKRAHA | bar: Week 44 Th 2
TO-23-220 kV A1/A2 @ KRA-02 | KNOCKRAHA 220 kV A1/A2 | bar: Su 22 to Week 44 Th 2
TO-23-KRA-220K1-06 | KNOCKRAHA 220K1 | bar: Su 22 to Week 44 Th 2
TO-23-KRA-220SA2-4CB-03 | KNOCKRAHA 220SA2-4CB | bar: Su 22 to Week 44 Th 2
TO-23-BVK-T2101-02 | BALLYVOUSKILL T2101 | bar: Week 44 Fr 3 to Week 44 Mo 6
Outages spanning Weeks 43-44
OUTAGE ID | PLANT | Week 43 Mo 23: Week 43; Week 44 Mo 30: Week 44
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6
TO-23-BOG-CRA-1-01 | BANOGE CRANE
TO-23-BUT-CUL-1-02 | BUTLERSTOWN CULLENAGH
TO-23-BUT-T141-02 | BUTLERSTOWN T141
TO-23-CSH-CAP2-04 | CASHLA CAP2
TO-23-CSH-GAL-1-01 | CASHLA GALWAY 1
TO-23-CLG-110K1-01 | CLOGHRAN 110K1
TO-23-CRO-IA-1-02 | COOLROE INNISCARRA
TO-23-220 kV A2 @ FIN-02 | FINGLAS 220 kV A2
TO-23-FIN-T2104-02 | FINGLAS T2104
TO-23-GAL-110K2-3-02 | GALWAY 110K2-3
TO-23-GAL-GAL GIS-2-03 | GALWAY GALWAY GIS 2
TO-23-GGO-220K1-2-02 | GLANAGOW 220K1-2
TO-23-GOR-110K1-2-02 | GORMAN 110K1-2
TO-23-GRI,T-GCA-1-03 | GRIFFINRATH tee GRANGE CASTLE
TO-23-INC-220K1-2-01 | INCHICORE 220K1-2
TO-23-KLS-220K1-2-04 | KELLIS 220K1-2
TO-23-KLS-T2101-03 | KELLIS T2101
TO-23-KBY-MR-1-06 | KILBARRY MARINA 1
TO-23-KBY-MR-2-02 | KILBARRY MARINA 2
Report covers outages commencing/returning/spanning the period: 23/10/2023 - 05/11/2023
Outages spanning Weeks 43-44
OUTAGE ID | PLANT | Week 43 Mo 23: Week 43; Week 44 Mo 30: Week 44
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6
TO-23-KRA-220K1-2-03 | KNOCKRAHA 220K1-2
TO-23-KRA-MID-1-01 | KNOCKRAHA MIDLETON
TO-23-LET-M/CAP1-01 | LETTERKENNY M/CAP1
TO-23-LET-PST-01 | LETTERKENNY STRABANE PST
TO-23-LIS-SKL-1-06 | LISDRUM SHANKILL
TO-23-LIS-T131-05 | LISDRUM T131
TO-23-MAY-SH-1-01 | MAYNOOTH SHANNONBRIDGE
TO-23-MUL-CAP1-02 | MULLINGAR CAP1
TO-23-PB-R2002-02 | POOLBEG R2002
TO-23-PRO-TB-1-04 | PROSPECT TARBERT
TO-23-SOM,T-SH-1-06 | SOMERSET tee SHANNONBRIDGE
TO-23-TB-T101-02 | TARBERT T101
TO-23-TB-T2003-03 | TARBERT T2003
TO-23-TB-T2004-02 | TARBERT T2004
TO-23-TB-T2101-02 | TARBERT T2101
TO-23-THU-CAP2-01 | THURLES CAP2
TO-23-TRI-CAP1-01 | TRIEN CAP1