## Wks 47 - 48
Report covers outages commencing/returning/spanning the period: 20/11/2023 - 03/12/2023
Outages commencing/returning in Week 47
OUTAGE ID | PLANT |  | Week 47 | [6 empty] | Week 48
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4
TO-23-BIN-TIV-1-02 | BINBANE TIEVEBRACK | bar: Week 47 Mo 20 to Week 47 Tu 21
TO-23-BVK-R2001-01 | BALLYVOUSKILL R2001 | bar: Week 47 Mo 20 to Week 47 We 22
TO-23-BAN-RAF-1-01 | BANDON RAFFEEN | bar: Week 47 Mo 20 to Week 47 We 22
TO-23-KNR-T2101-01 | KNOCKANURE T2101 | bar: Week 47 Mo 20 to Week 47 Th 23
TO-23-LA-SLB-1-01 | LANESBORO SLIABH BAWN | bar: Week 47 Mo 20 to Week 47 Fr 24
TO-23-CHA-MAL-1-01 | CHARLEVILLE MALLOW | bar: Week 47 Mo 20 to Week 48 We 29
TO-23-220 kV A2 @ SH-02 | SHANNONBRIDGE 220 kV A2
TO-23-220 kV B2 @ SH-02 | SHANNONBRIDGE 220 kV B2
TO-23-SNU-110K1-01 | SNUGBOROUGH 110K1 | bar: Week 47 Tu 21
TO-23-SKL-T142-01 | SHANKILL T142 | bar: Week 47 Tu 21 to Week 47 We 22
TO-23-GRI,T-GCA-1-03 | GRIFFINRATH tee GRANGE CASTLE | bar: Su 19 to Week 47 Tu 21
TO-23-KTL-T141-01 | KILTEEL T141 | bar: Week 47 We 22 to Week 47 Th 23
TO-23-KNR-TRI-1-02 | KNOCKANURE TRIEN 1 | bar: Week 47 We 22 to Week 47 Th 23
TO-23-BDA-MON-1-02 | BARODA MONREAD | bar: Su 19 to Week 47 We 22
TO-23-LET-PST-01 | LETTERKENNY STRABANE PST | bar: Su 19 to Week 47 We 22
TO-23-CDY-SRA-1-01 | CORDERRY SRANANAGH | bar: Week 47 Th 23
TO-23-110 kV A2 @ DND-01 | DARNDALE 110 kV A2 | bar: Su 19 to Week 47 Th 23
TO-23-110 kV B2 @ DND-01 | DARNDALE 110 kV B2 | bar: Su 19 to Week 47 Th 23
TO-23-DND-110K2-02 | DARNDALE 110K2 | bar: Su 19 to Week 47 Th 23
TO-23-DND-110SA1-2CB-01 | DARNDALE 110SA1-2CB | bar: Su 19 to Week 47 Th 23
TO-23-DND-110SB1-2CB-02 | DARNDALE 110SB1-2CB | bar: Su 19 to Week 47 Th 23
TO-23-BYH-T132-01 | BALLYNAHULLA T132 | bar: Week 47 Fr 24 to Week 48 Mo 27
TO-23-220 kV B1 @ CKM GIS-03 | CARRICKMINES GIS 220 kV B1 | bar: Su 19 to Week 47 Fr 24
TO-23-220 kV B2 @ CKM GIS-04 | CARRICKMINES GIS 220 kV B2 | bar: Su 19 to Week 47 Fr 24
TO-23-CKM GIS-220SB1-2CB-02 | CARRICKMINES GIS 220SB1-2CB | bar: Su 19 to Week 47 Fr 24
TO-23-KBY-MR-1-06 | KILBARRY MARINA 1 | bar: Su 19 to Week 47 Fr 24
TO-23-KBY-MR-2-02 | KILBARRY MARINA 2 | bar: Su 19 to Week 47 Fr 24
TO-23-220 kV A1 @ LOU-01 | LOUTH 220 kV A1 | bar: Su 19 to Week 47 Fr 24
TO-23-220 kV B1 @ LOU-02 | LOUTH 220 kV B1 | bar: Su 19 to Week 47 Fr 24
TO-23-LOU-T2103-01 | LOUTH T2103 | bar: Su 19 to Week 47 Fr 24
TO-23-GI-WAT-1-04 | GREAT ISLAND WATERFORD 1 | bar: Week 47 Sa 25 to Week 47 Su 26
TO-23-GI-WAT-2-02 | GREAT ISLAND WATERFORD 2 | bar: Week 47 Sa 25 to Week 48 We 29
Outages commencing/returning in Week 48
OUTAGE ID | PLANT | Week 47 Mo 20: Week 47; Week 48 Mo 27: Week 48
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4
TO-23-IA-MAC-1-07 | INNISCARRA MACROOM | bar: Week 48 Mo 27 to Week 48 Tu 28
TO-23-IA-T101-06 | INNISCARRA T101 | bar: Week 48 Mo 27 to Week 48 Tu 28
TO-23-GAR-GOR-1-01 | GARBALLAGH GORMAN | bar: Week 48 Mo 27 to Week 48 We 29
TO-23-110 kV A1 @ PLS-01 | PORTLAOISE 110 kV A1 | bar: Week 48 Mo 27 to Week 48 Th 30
TO-23-110 kV A2 @ PLS-03 | PORTLAOISE 110 kV A2 | bar: Week 48 Mo 27 to Week 48 Th 30
TO-23-110 kV B1 @ PLS-01 | PORTLAOISE 110 kV B1 | bar: Week 48 Mo 27 to Week 48 Th 30
TO-23-110 kV B2 @ PLS-03 | PORTLAOISE 110 kV B2 | bar: Week 48 Mo 27 to Week 48 Th 30
TO-23-PLS-110K1-2-01 | PORTLAOISE 110K1-2 | bar: Week 48 Mo 27 to Week 48 Th 30
TO-23-110 kV A2 @ LOU-04 | LOUTH 110 kV A2 | bar: Week 48 Mo 27 to Week 48 Fr 1
TO-23-110 kV B2 @ LOU-04 | LOUTH 110 kV B2 | bar: Week 48 Mo 27 to Week 48 Fr 1
TO-23-MLC-110SA1-01 | MOUNTLUCAS 110SA1 | bar: Week 48 Mo 27 to Week 48 Fr 1
TO-23-MLC-110SA2-01 | MOUNTLUCAS 110SA2 | bar: Week 48 Mo 27 to Week 48 Fr 1
TO-23-MLC-TSB-1-01 | MOUNTLUCAS THORNSBERRY | bar: Week 48 Mo 27 to Week 48 Fr 1
TO-23-SH-T2102-02 | SHANNONBRIDGE T2102 | bar: Week 48 Mo 27 to Week 48 Fr 1
TO-23-TSB-110SA1-01 | THORNSBERRY 110SA1 | bar: Week 48 Mo 27 to Week 48 Fr 1
TO-23-TSB-110SA2-01 | THORNSBERRY 110SA2 | bar: Week 48 Mo 27 to Week 48 Fr 1
TO-23-TSB-T141-01 | THORNSBERRY T141 | bar: Week 48 Mo 27 to Week 48 Fr 1
TO-23-220 kV B1 @ CKM GIS-04 | CARRICKMINES GIS 220 kV B1 | bar: Week 48 Mo 27 to Week 48 Mo 4
TO-23-220 kV B3 @ CKM GIS-03 | CARRICKMINES GIS 220 kV B3 | bar: Week 48 Mo 27 to Week 48 Mo 4
TO-23-CKM GIS-220SB1-3CB-01 | CARRICKMINES GIS 220SB1-3CB | bar: Week 48 Mo 27 to Week 48 Mo 4
TO-23-110 kV A2 @ KBY-05 | KILBARRY 110 kV A2 | bar: Week 48 Mo 27 to Week 48 Mo 4
TO-23-110 kV B2 @ KBY-06 | KILBARRY 110 kV B2 | bar: Week 48 Mo 27 to Week 48 Mo 4
TO-23-KBY-KRA-2-01 | KILBARRY KNOCKRAHA 2 | bar: Week 48 Mo 27 to Week 48 Mo 4
Report covers outages commencing/returning/spanning the period: 20/11/2023 - 03/12/2023
Outages commencing/returning in Week 48
OUTAGE ID | PLANT | Week 47 Mo 20: Week 47; Week 48 Mo 27: Week 48
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4
TO-23-110 kV A2 @ KRA-03 | KNOCKRAHA 110 kV A2 | bar: Week 48 Mo 27 to Week 48 Mo 4
TO-23-110 kV B2 @ KRA-05 | KNOCKRAHA 110 kV B2 | bar: Week 48 Mo 27 to Week 48 Mo 4
TO-23-KBY-T101-02 | KILBARRY T101 | bar: Week 48 Tu 28 to Week 48 We 29
TO-23-AD-RAF-1-03 | AGHADA RAFFEEN | bar: Week 48 We 29 to Week 48 Th 30
TO-23-INC-ISH-1-04 | INCHICORE IRISHTOWN | bar: Su 19 to Week 48 We 29
TO-23-ISH-220K1-2-02 | IRISHTOWN 220K1-2 | bar: Su 19 to Week 48 We 29
TO-23-ISH-SHL-1-04 | IRISHTOWN SHELLYBANKS | bar: Su 19 to Week 48 We 29
TO-23-BLC-DND-3-02 | BELCAMP DARNDALE 3 | bar: Week 48 Th 30 to Week 48 Fr 1
TO-23-110 kV A2 @ DND-03 | DARNDALE 110 kV A2 | bar: Week 48 Th 30 to Week 48 Fr 1
TO-23-110 kV B2 @ DND-03 | DARNDALE 110 kV B2 | bar: Week 48 Th 30 to Week 48 Fr 1
TO-23-DND-110K2-04 | DARNDALE 110K2 | bar: Week 48 Th 30 to Week 48 Fr 1
TO-23-DND-110SA1-2CB-03 | DARNDALE 110SA1-2CB | bar: Week 48 Th 30 to Week 48 Fr 1
TO-23-DND-110SB1-2CB-04 | DARNDALE 110SB1-2CB | bar: Week 48 Th 30 to Week 48 Fr 1
TO-23-DSN-T4201-02 | DUNSTOWN T4201 | bar: Week 48 Th 30 to Week 48 Fr 1
TO-23-220 kV A2 @ ISH-01 | IRISHTOWN 220 kV A2 | bar: Week 48 Th 30 to Week 48 Mo 4
TO-23-220 kV B2 @ ISH-01 | IRISHTOWN 220 kV B2 | bar: Week 48 Th 30 to Week 48 Mo 4
TO-23-400 kV A1 @ DSN-03 | DUNSTOWN 400 kV A1 | bar: Week 48 Fr 1
TO-23-400 kV B1 @ DSN-03 | DUNSTOWN 400 kV B1 | bar: Week 48 Fr 1
TO-23-BYH-T132-02 | BALLYNAHULLA T132 | bar: Week 48 Fr 1 to Week 48 Mo 4
TO-23-BK-CBR-1-01 | BELLACORICK CASTLEBAR | bar: Su 19 to Week 48 Fr 1
TO-23-CRO-IA-1-02 | COOLROE INNISCARRA | bar: Su 19 to Week 48 Fr 1
Outages spanning Weeks 47-48
OUTAGE ID | PLANT | Week 47 Mo 20: Week 47; Week 48 Mo 27: Week 48
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4
TO-23-ARV-110K1-2-01 | ARVA 110K1-2
TO-23-BOG-CRA-1-01 | BANOGE CRANE
TO-23-CSH-CAP2-04 | CASHLA CAP2
TO-23-CLG-110K1-01 | CLOGHRAN 110K1
TO-23-220 kV A2 @ FIN-02 | FINGLAS 220 kV A2
TO-23-FIN-T2104-02 | FINGLAS T2104
TO-23-GAL-110K2-3-02 | GALWAY 110K2-3
TO-23-GGO-220K1-2-02 | GLANAGOW 220K1-2
TO-23-INC-220K1-2-01 | INCHICORE 220K1-2
TO-23-KLS-220K1-2-04 | KELLIS 220K1-2
TO-23-KPG-TB-1-02 | KILPADDOGE TARBERT 1
TO-23-KRA-220K1-2-03 | KNOCKRAHA 220K1-2
TO-23-KRA-MID-1-01 | KNOCKRAHA MIDLETON
TO-23-LET-M/CAP1-01 | LETTERKENNY M/CAP1
TO-23-LIS-SKL-1-06 | LISDRUM SHANKILL
TO-23-LIS-T131-05 | LISDRUM T131
TO-23-MAY-SH-1-01 | MAYNOOTH SHANNONBRIDGE
TO-23-MUL-CAP1-02 | MULLINGAR CAP1
TO-23-PB-R2002-02 | POOLBEG R2002
TO-23-PRO-TB-1-04 | PROSPECT TARBERT
TO-23-110 kV A1 @ SH-05 | SHANNONBRIDGE 110 kV A1
TO-23-110 kV A2 @ SH-03 | SHANNONBRIDGE 110 kV A2
TO-23-110 kV B1 @ SH-02 | SHANNONBRIDGE 110 kV B1
TO-23-110 kV B2 @ SH-02 | SHANNONBRIDGE 110 kV B2
TO-23-SOM,T-SH-1-06 | SOMERSET tee SHANNONBRIDGE
TO-23-TB-T101-02 | TARBERT T101
TO-23-TB-T2003-03 | TARBERT T2003
TO-23-TB-T2004-02 | TARBERT T2004
TO-23-TB-T2101-02 | TARBERT T2101
TO-23-THU-CAP2-01 | THURLES CAP2
TO-23-TRL-CAP2-02 | TRALEE CAP2