## Wks 7 - 8
Report covers outages commencing/returning/spanning the period: 13/02/2023 - 26/02/2023
Outages commencing/returning in Week 7
OUTAGE ID | PLANT |  | Week 7 | [6 empty] | Week 8
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27
TO-23-220 kV A1 @ CKM GIS-02 | CARRICKMINES GIS 220 kV A1 | bar: Week 7 Mo 13 to Week 7 We 15
TO-23-220 kV A2 @ CKM GIS-02 | CARRICKMINES GIS 220 kV A2 | bar: Week 7 Mo 13 to Week 7 We 15
TO-23-CKM GIS-220SA1-2CB-01 | CARRICKMINES GIS 220SA1-2CB | bar: Week 7 Mo 13 to Week 7 We 15
TO-23-220 kV B1 @ KPG-02 | KILPADDOGE 220 kV B1 | bar: Week 7 Mo 13 to Week 7 We 15
TO-23-220 kV B3 @ KPG-02 | KILPADDOGE 220 kV B3 | bar: Week 7 Mo 13 to Week 7 We 15
TO-23-KPG-220SB1-3CB-01 | KILPADDOGE 220SB1-3CB | bar: Week 7 Mo 13 to Week 7 We 15
TO-23-GOR-MAY-1-02 | GORMAN MAYNOOTH | bar: Week 7 Mo 13 to Week 8 Su 26
TO-23-220 kV A1/A2 @ MP GIS-01 | MONEYPOINT GIS 220 kV A1/A2 | bar: Week 7 Tu 14
TO-23-220 kV B1/B2 @ MP GIS-01 | MONEYPOINT GIS 220 kV B1/B2 | bar: Week 7 Tu 14
TO-23-400 kV A1/A2/A3/A4 @ MP GIS-01 | MONEYPOINT GIS 400 kV A1/A2/A3/A4 | bar: Week 7 Tu 14
TO-23-400 kV B1/B2/B3/B4 @ MP GIS-01 | MONEYPOINT GIS 400 kV B1/B2/B3/B4 | bar: Week 7 Tu 14
TO-23-COT-FILTER1-01 | COOMATAGGART FILTER1 | bar: Week 7 Tu 14 to Week 7 Fr 17
TO-23-PLA-T101/2/3/4-02 | PLATIN T101/2/3/4 | bar: Week 7 We 15 to Week 8 We 22
TO-23-PLA-T105-01 | PLATIN T105 | bar: Su 12 to Week 7 We 15
TO-23-110 kV A1/A2 @ SRA-01 | SRANANAGH 110 kV A1/A2 | bar: Week 7 Th 16
TO-23-110 kV B1/B2 @ SRA-01 | SRANANAGH 110 kV B1/B2 | bar: Week 7 Th 16
TO-23-220 kV B1 @ CKM GIS-02 | CARRICKMINES GIS 220 kV B1 | bar: Week 7 Th 16 to Week 8 Mo 20
TO-23-220 kV B3 @ CKM GIS-02 | CARRICKMINES GIS 220 kV B3 | bar: Week 7 Th 16 to Week 8 Mo 20
TO-23-CKM GIS-220SB1-3CB-01 | CARRICKMINES GIS 220SB1-3CB | bar: Week 7 Th 16 to Week 8 Mo 20
Outages commencing/returning in Week 8
OUTAGE ID | PLANT | Week 7 Mo 13: Week 7; Week 8 Mo 20: Week 8
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27
TO-23-CBT-MAY-1-02 | CASTLEBAGOT MAYNOOTH 1 | bar: Week 8 Mo 20 to Week 8 Tu 21
TO-23-220 kV B2 @ KPG-02 | KILPADDOGE 220 kV B2 | bar: Week 8 Mo 20 to Week 8 We 22
TO-23-220 kV B4 @ KPG-02 | KILPADDOGE 220 kV B4 | bar: Week 8 Mo 20 to Week 8 We 22
TO-23-KPG-220SB2-4CB-01 | KILPADDOGE 220SB2-4CB | bar: Week 8 Mo 20 to Week 8 We 22
TO-23-IKE,T-THU-1-02 | IKERRIN tee THURLES | bar: Week 8 Mo 20 to Week 8 Fr 24
TO-23-LSN-110SA1-2-02 | LISHEEN 110SA1-2 | bar: Week 8 Mo 20 to Week 8 Fr 24
TO-23-LSN-110SA2-4-02 | LISHEEN 110SA2-4 | bar: Week 8 Mo 20 to Week 8 Fr 24
TO-23-LSN-T122-02 | LISHEEN T122 | bar: Week 8 Mo 20 to Week 8 Fr 24
TO-23-LSN-T131-01 | LISHEEN T131 | bar: Week 8 Mo 20 to Week 8 Fr 24
TO-23-LSN-T142-02 | LISHEEN T142 | bar: Week 8 Mo 20 to Week 8 Fr 24
TO-23-LSN-THU-1-02 | LISHEEN THURLES | bar: Week 8 Mo 20 to Week 8 Fr 24
TO-23-THU-110SA1-2CB-01 | THURLES 110SA1-2CB | bar: Week 8 Mo 20 to Week 8 Fr 24
TO-23-THU-T142-02 | THURLES T142 | bar: Week 8 Mo 20 to Week 8 Fr 24
TO-23-110 kV A1/A3 @ BLC-01 | BELCAMP 110 kV A1/A3 | bar: Week 8 Tu 21
TO-23-110 kV B1/B3 @ BLC-01 | BELCAMP 110 kV B1/B3 | bar: Week 8 Tu 21
TO-23-220 kV B2 @ CKM GIS-02 | CARRICKMINES GIS 220 kV B2 | bar: Week 8 Tu 21 to Week 8 Th 23
TO-23-220 kV B4 @ CKM GIS-02 | CARRICKMINES GIS 220 kV B4 | bar: Week 8 Tu 21 to Week 8 Th 23
TO-23-CKM GIS-220SB2-4CB-01 | CARRICKMINES GIS 220SB2-4CB | bar: Week 8 Tu 21 to Week 8 Th 23
TO-23-CKG-T121-01 | CORKAGH T121 | bar: Su 12 to Week 8 We 22
TO-23-220 kV B1 @ AD-02 | AGHADA 220 kV B1 | bar: Week 8 Th 23
TO-23-AD-T2011/12-02 | AGHADA T2011/12 | bar: Week 8 Th 23
TO-23-110 kV A1/A2/A3/A4 @ KPG-01 | KILPADDOGE 110 kV A1/A2/A3/A4 | bar: Week 8 Th 23
TO-23-110 kV B1/B2/B3/B4 @ KPG-01 | KILPADDOGE 110 kV B1/B2/B3/B4 | bar: Week 8 Th 23
TO-23-220 kV A1/A2/A3/A4 @ KPG-01 | KILPADDOGE 220 kV A1/A2/A3/A4 | bar: Week 8 Th 23
TO-23-220 kV B1/B2/B3/B4 @ KPG-01 | KILPADDOGE 220 kV B1/B2/B3/B4 | bar: Week 8 Th 23
Outages spanning Weeks 7-8
OUTAGE ID | PLANT | Week 7 Mo 13: Week 7; Week 8 Mo 20: Week 8
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27
TO-23-CLG-110K1-01 | CLOGHRAN 110K1
TO-23-CUL-220K1-2-02 | CULLENAGH 220K1-2
TO-23-FIN GIS-110K6-01 | FINGLAS GIS 110K6
TO-23-GAL-T142-02 | GALWAY T142
TO-23-GGO-220K1-2-01 | GLANAGOW 220K1-2
Report covers outages commencing/returning/spanning the period: 13/02/2023 - 26/02/2023
Outages spanning Weeks 7-8
OUTAGE ID | PLANT | Week 7 Mo 13: Week 7; Week 8 Mo 20: Week 8
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27
TO-23-GWE-T101-03 | GORTAWEE T101
TO-23-INC-220K1-2-01 | INCHICORE 220K1-2
TO-23-KRA-220K1-03 | KNOCKRAHA 220K1
TO-23-LET-M/CAP1-01 | LETTERKENNY M/CAP1
TO-23-MUL-CAP2-01 | MULLINGAR CAP2
TO-23-PB-R2002-02 | POOLBEG R2002
TO-23-PRO-TB-1-04 | PROSPECT TARBERT
TO-23-SLI-T142-01 | SLIGO T142
TO-23-TB-T101-02 | TARBERT T101
TO-23-TB-T102-02 | TARBERT T102
TO-23-TB-T2004-02 | TARBERT T2004
TO-23-THU-CAP2-01 | THURLES CAP2