## Wks 9 - 10
Report covers outages commencing/returning/spanning the period: 28/02/2022 - 13/03/2022
Outages commencing/returning in Week 9
OUTAGE ID | PLANT |  | Week 9 | [6 empty] | Week 10
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 27 | 28 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
TO-22-CSH-CLN-1-05 | CASHLA CLOON | bar: Week 9 Mo 28
TO-22-SOM,T-CSH-1-01 | SOMERSET tee CASHLA | bar: Week 9 Mo 28
TO-22-SOM,T-SH-1-01 | SOMERSET tee SHANNONBRIDGE | bar: Week 9 Mo 28
TO-22-SOM,T-SOM-1-01 | SOMERSET tee SOMERSET | bar: Week 9 Mo 28
TO-22-110 kV A1 @ FLA-01 | FLAGFORD 110 kV A1 | bar: Week 9 Mo 28 to Week 9 Tu 1
TO-22-110 kV B1 @ FLA-01 | FLAGFORD 110 kV B1 | bar: Week 9 Mo 28 to Week 9 Tu 1
TO-22-GOR-PLA-1-02 | GORMAN PLATIN | bar: Week 9 Mo 28 to Week 9 Tu 1
TO-22-PLA-110SA1-01 | PLATIN 110SA1 | bar: Week 9 Mo 28 to Week 9 Tu 1
TO-22-PLA-110SA2-01 | PLATIN 110SA2 | bar: Week 9 Mo 28 to Week 9 Tu 1
TO-22-110 kV A1 @ BYH-01 | BALLYNAHULLA 110 kV A1 | bar: Week 9 Mo 28 to Week 9 Th 3
TO-22-110 kV B1 @ BYH-01 | BALLYNAHULLA 110 kV B1 | bar: Week 9 Mo 28 to Week 9 Th 3
TO-22-220 kV A1 @ BYH-01 | BALLYNAHULLA 220 kV A1 | bar: Week 9 Mo 28 to Week 9 Th 3
TO-22-220 kV B1 @ BYH-01 | BALLYNAHULLA 220 kV B1 | bar: Week 9 Mo 28 to Week 9 Th 3
TO-22-110 kV A3 @ CDU-02 | CORDUFF 110 kV A3 | bar: Week 9 Mo 28 to Week 9 Th 3
TO-22-110 kV B3 @ CDU-03 | CORDUFF 110 kV B3 | bar: Week 9 Mo 28 to Week 9 Th 3
TO-22-BYH-KNR-1-02 | BALLYNAHULLA KNOCKANURE | bar: Week 9 Mo 28 to Week 9 Fr 4
TO-22-BYH-T2101-01 | BALLYNAHULLA T2101 | bar: Week 9 Mo 28 to Week 9 Fr 4
TO-22-CBR-DLT-1-02 | CASTLEBAR DALTON | bar: Week 9 Mo 28 to Week 9 Fr 4
TO-22-KLN-T2104-01 | KILLONAN T2104 | bar: Week 9 Mo 28 to Week 9 Fr 4
TO-22-MP GIS-PRO-1-01 | MONEYPOINT GIS PROSPECT | bar: Week 9 Mo 28 to Week 9 Fr 4
TO-22-PRO-TB-1-04 | PROSPECT TARBERT | bar: Week 9 Mo 28 to Week 9 Fr 4
TO-22-110 kV A2 @ CSH-03 | CASHLA 110 kV A2 | bar: Week 9 Mo 28 to Week 10 Mo 7
TO-22-CSH-110K1-2-03 | CASHLA 110K1-2 | bar: Week 9 Mo 28 to Week 10 Mo 7
TO-22-SOM-T142-04 | SOMERSET T142 | bar: Week 9 Mo 28 to Week 10 Fr 11
TO-22-SOM,T-CSH-1-05 | SOMERSET tee CASHLA | bar: Week 9 Mo 28 to Week 10 Fr 11
TO-22-SOM,T-SH-1-05 | SOMERSET tee SHANNONBRIDGE | bar: Week 9 Mo 28 to Week 10 Fr 11
TO-22-SOM,T-SOM-1-04 | SOMERSET tee SOMERSET | bar: Week 9 Mo 28 to Week 10 Fr 11
TO-22-BIN-T142-01 | BINBANE T142
TO-22-CSH-PRO-1-01 | CASHLA PROSPECT
TO-22-CDU-PLA-1-01 | CORDUFF PLATIN
TO-22-FLA-SLB-1-01 | FLAGFORD SLIABH BAWN
TO-22-LIS-LOU-1-01 | LISDRUM LOUTH
TO-22-LIS-LOU-1-03
TO-22-SOM-T142-01 | SOMERSET T142
TO-22-MP GIS-400K4-02 | MONEYPOINT GIS 400K4 | bar: Week 9 Tu 1
TO-22-LIS-LOU-1-05 | LISDRUM LOUTH | bar: Week 9 Tu 1 to Week 9 Th 3
TO-22-KTN-WAT-1-01 | KILLOTERAN WATERFORD | bar: Week 9 Tu 1 to Week 9 Fr 4
TO-22-CF-SRA-2-01 | CATHALEENS FALL SRANANAGH 2 | bar: Week 9 Tu 1 to Week 10 Mo 7
TO-22-FIN-HN-1-01 | FINGLAS HUNTSTOWN | bar: Week 9 Tu 1 to Week 10 Mo 7
TO-22-HN-T2010/11-01 | HUNTSTOWN T2010/11 | bar: Week 9 Tu 1 to Week 10 Mo 7
TO-22-MUL-CAP2-03 | MULLINGAR CAP2 | bar: Week 9 Tu 1 to Week 10 Mo 14
TO-22-MCE-T121-01 | MACETOWN T121 | bar: Week 9 We 2
TO-22-110 kV A1/A2 @ SNU-01 | SNUGBOROUGH 110 kV A1/A2 | bar: Week 9 We 2
TO-22-110 kV B1/B2 @ SNU-01 | SNUGBOROUGH 110 kV B1/B2 | bar: Week 9 We 2
TO-22-MAY-RNW-1-04 | MAYNOOTH RINAWADE | bar: Week 9 We 2 to Week 9 Fr 4
TO-22-MAY-RYB GIS-1-02 | MAYNOOTH RYEBROOK GIS | bar: Week 9 We 2 to Week 9 Fr 4
TO-22-PLA-T105-02 | PLATIN T105 | bar: Su 27 to Week 9 We 2
TO-22-PLA-T101/2/3/4-04 | PLATIN T101/2/3/4 | bar: Week 9 Th 3 to Week 10 Mo 14
Outages commencing/returning in Week 10
OUTAGE ID | PLANT | Week 9 Mo 28: Week 9; Week 10 Mo 7: Week 10
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 27 | 28 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
TO-22-MAY-SH-1-01 | MAYNOOTH SHANNONBRIDGE | bar: Week 10 Mo 7 to Week 10 We 9
TO-22-MAY-WOO-1-13 | MAYNOOTH WOODLAND | bar: Week 10 Mo 7 to Week 10 We 9
TO-22-110 kV A2 @ FIN-01 | FINGLAS 110 kV A2 | bar: Week 10 Mo 7 to Week 10 Fr 11
TO-22-FIN-220K1-11 | FINGLAS 220K1 | bar: Week 10 Mo 7 to Week 10 Fr 11
TO-22-KLN-T2101-01 | KILLONAN T2101 | bar: Week 10 Mo 7 to Week 10 Mo 14
TO-22-MAY-WOO-1-02 | MAYNOOTH WOODLAND | bar: Week 10 Mo 7 to Week 10 Mo 14
TO-22-MAY-WOO-1-12 | bar: Week 10 Mo 7 to Week 10 Mo 14
Report covers outages commencing/returning/spanning the period: 28/02/2022 - 13/03/2022
Outages commencing/returning in Week 10
OUTAGE ID | PLANT | Week 9 Mo 28: Week 9; Week 10 Mo 7: Week 10
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 27 | 28 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
TO-22-110 kV A1 @ TB-01 | TARBERT 110 kV A1 | bar: Week 10 Mo 7 to Week 10 Mo 14
TO-22-110 kV B1 @ TB-01 | TARBERT 110 kV B1 | bar: Week 10 Mo 7 to Week 10 Mo 14
TO-22-220 kV A1 @ TB-04 | TARBERT 220 kV A1 | bar: Week 10 Mo 7 to Week 10 Mo 14
TO-22-220 kV B1 @ TB-04 | TARBERT 220 kV B1 | bar: Week 10 Mo 7 to Week 10 Mo 14
TO-22-TB-T2101-03 | TARBERT T2101 | bar: Week 10 Mo 7 to Week 10 Mo 14
TO-22-ARK-BEG-1-01 | ARKLOW BALLYBEG | bar: Week 10 Tu 8 to Week 10 We 9
TO-22-BIN-110SA1-2CB-01 | BINBANE 110SA1-2CB | bar: Week 10 Tu 8 to Week 10 We 9
TO-22-BIN-CF-1-03 | BINBANE CATHALEENS FALL | bar: Week 10 Tu 8 to Week 10 Fr 11
TO-22-110 kV B2 @ CSH-03 | CASHLA 110 kV B2 | bar: Week 10 Tu 8 to Week 10 Fr 11
TO-22-220 kV A1/A2 @ MP GIS-01 | MONEYPOINT GIS 220 kV A1/A2 | bar: Week 10 We 9
TO-22-220 kV B1/B2 @ MP GIS-01 | MONEYPOINT GIS 220 kV B1/B2 | bar: Week 10 We 9
TO-22-400 kV A1/A2/A3/A4 @ MP GIS-01 | MONEYPOINT GIS 400 kV A1/A2/A3/A4 | bar: Week 10 We 9
TO-22-400 kV B1/B2/B3/B4 @ MP GIS-01 | MONEYPOINT GIS 400 kV B1/B2/B3/B4 | bar: Week 10 We 9
TO-22-KLN-T2102-01 | KILLONAN T2102 | bar: Su 27 to Week 10 Fr 11
Outages spanning Weeks 9-10
OUTAGE ID | PLANT | Week 9 Mo 28: Week 9; Week 10 Mo 7: Week 10
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 27 | 28 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
TO-22-AD-GGO-1-01 | AGHADA GLANAGOW
TO-22-ARK-220K1-2-01 | ARKLOW 220K1-2
TO-22-BYH-KNR-1-01 | BALLYNAHULLA KNOCKANURE
TO-22-110 kV A1 @ CAH-01 | CAHIR 110 kV A1
TO-22-CLG-T122-01 | CLOGHRAN T122
TO-22-110 kV B2 @ DEY-02 | DERRYCARNEY 110 kV B2
TO-22-DEY-110K2-01 | DERRYCARNEY 110K2
TO-22-DRU-CAP2-02 | DRUMLINE CAP2
TO-22-220 kV A1/A2 @ FIN-01 | FINGLAS 220 kV A1/A2
TO-22-FIN-220K1-06 | FINGLAS 220K1
TO-22-FIN-220K2-01 | FINGLAS 220K2
TO-22-FIN-MCD-1-01 | FINGLAS McDERMOTT
TO-22-GGO-220K1-2-02 | GLANAGOW 220K1-2
TO-22-INC-220K1-2-03 | INCHICORE 220K1-2
TO-22-LET-M/CAP1-01 | LETTERKENNY M/CAP1
TO-22-NAV-M/CAP1-01 | NAVAN M/CAP1
TO-22-PB-R2002-01 | POOLBEG R2002
TO-22-TB-T101-02 | TARBERT T101
TO-22-TB-T102-02 | TARBERT T102
TO-22-TB-T2004-03 | TARBERT T2004