## Wks 9 - 10
Report covers outages commencing/returning/spanning the period: 27/02/2023 - 12/03/2023
Outages commencing/returning in Week 9
OUTAGE ID | PLANT |  | Week 9 | [6 empty] | Week 10
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 26 | 27 | 28 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13
TO-23-COS-110SA1-2CB-01 | CARRICK ON SHANNON 110SA1-2CB
TO-23-COS-FLA-1-01 | CARRICK ON SHANNON FLAGFORD 1
TO-23-COS-T141-01 | CARRICK ON SHANNON T141
TO-23-GI-KKY-1-01 | GREAT ISLAND KILKENNY
TO-23-KKY-T141-03 | KILKENNY T141
TO-23-ARK-BOG-1-01 | ARKLOW BANOGE
TO-23-CVW-110SA1-01 | CASTLEVIEW 110SA1
TO-23-CVW-110SA2-01 | CASTLEVIEW 110SA2
TO-23-CVW-COW-1-02 | CASTLEVIEW COW CROSS
TO-23-CVW-T101-01 | CASTLEVIEW T101
TO-23-110 kV A2 @ ARV-01 | ARVA 110 kV A2
TO-23-110 kV B2 @ ARV-01 | ARVA 110 kV B2
TO-23-110 kV A2 @ GOR-01 | GORMAN 110 kV A2
TO-23-110 kV B2 @ GOR-01 | GORMAN 110 kV B2
TO-23-110 kV A2 @ SNU-04 | SNUGBOROUGH 110 kV A2
TO-23-110 kV B2 @ SNU-04 | SNUGBOROUGH 110 kV B2
TO-23-ARV-COS-1-01 | ARVA CARRICK ON SHANNON | bar: Week 9 Fr 3
TO-23-BVK-220K1-01 | BALLYVOUSKILL 220K1 | bar: Week 9 Fr 3
TO-23-BUT-KTN-1-03 | BUTLERSTOWN KILLOTERAN | bar: Week 9 Fr 3
TO-23-DER-110SA1-01 | DERRYIRON 110SA1 | bar: Week 9 Fr 3
TO-23-DER-110SA2-01 | DERRYIRON 110SA2 | bar: Week 9 Fr 3
TO-23-DER-KIN-1-01 | DERRYIRON KINNEGAD | bar: Week 9 Fr 3
TO-23-KIN-110SA1-2CB-01 | KINNEGAD 110SA1-2CB | bar: Week 9 Fr 3
TO-23-KIN-MUL-1-01 | KINNEGAD MULLINGAR | bar: Week 9 Fr 3
TO-23-KIN-T101-01 | KINNEGAD T101 | bar: Week 9 Fr 3
TO-23-MCE-110SA1-01 | MACETOWN 110SA1 | bar: Week 9 Fr 3
TO-23-MCE-110SA2-01 | MACETOWN 110SA2 | bar: Week 9 Fr 3
TO-23-MCE-T102-01 | MACETOWN T102 | bar: Week 9 Fr 3
TO-23-MCE-T124-01 | MACETOWN T124 | bar: Week 9 Fr 3
TO-23-DDK-MLN-1-02 | DUNDALK MULLAGHARLIN | bar: Week 9 Fr 3 to Week 10 We 8
TO-23-MCE-SNU-1-01 | MACETOWN SNUGBOROUGH | bar: Week 9 Fr 3 to Week 10 We 8
TO-23-BYH-BVK-1-03 | BALLYNAHULLA BALLYVOUSKILL | bar: Week 9 Fr 3 to Week 10 Fr 10
TO-23-BDA-MON-1-01 | BARODA MONREAD | bar: Week 9 Fr 3 to Week 10 Fr 10
TO-23-110 kV A1 @ LOU-03 | LOUTH 110 kV A1 | bar: Week 9 Fr 3 to Week 10 Fr 10
TO-23-110 kV B1 @ LOU-03 | LOUTH 110 kV B1 | bar: Week 9 Fr 3 to Week 10 Fr 10
TO-23-220 kV A1 @ LOU-02 | LOUTH 220 kV A1 | bar: Week 9 Fr 3 to Week 10 Fr 10
TO-23-220 kV B1 @ LOU-01 | LOUTH 220 kV B1 | bar: Week 9 Fr 3 to Week 10 Fr 10
TO-23-220 kV A2 @ AD-01 | AGHADA 220 kV A2 | bar: Week 9 Fr 3 to Week 10 Mo 13
TO-23-220 kV B2 @ AD-01 | AGHADA 220 kV B2 | bar: Week 9 Fr 3 to Week 10 Mo 13
TO-23-AD-SA1-2CB-01 | AGHADA 220SA1-2CB | bar: Week 9 Fr 3 to Week 10 Mo 13
TO-23-AD-SB1-2CB-01 | AGHADA 220SB1-2CB | bar: Week 9 Fr 3 to Week 10 Mo 13
TO-23-AD-T2001-03 | AGHADA T2001 | bar: Week 9 Fr 3 to Week 10 Mo 13
TO-23-CSH-GAL-3-03 | CASHLA GALWAY 3 | bar: Week 9 Fr 3 to Week 10 Mo 13
TO-23-CTN-TIP-1-01 | CAUTEEN TIPPERARY | bar: Week 9 Fr 3 to Week 10 Mo 13
TO-23-110 kV A4 @ CDU-01 | CORDUFF 110 kV A4 | bar: Week 9 Fr 3 to Week 10 Mo 13
TO-23-110 kV B4 @ CDU-01 | CORDUFF 110 kV B4 | bar: Week 9 Fr 3 to Week 10 Mo 13
TO-23-GAL-110K2-3-02 | GALWAY 110K2-3 | bar: Week 9 Fr 3 to Week 10 Mo 13
TO-23-GOR-MTH-1-01 | GORMAN MEATH HILL | bar: Week 9 Fr 3 to Week 10 Mo 13
TO-23-KRA-220K1-2-03 | KNOCKRAHA 220K1-2 | bar: Week 9 Fr 3 to Week 10 Mo 13
TO-23-LOU-T2101-03 | LOUTH T2101 | bar: Week 9 Fr 3 to Week 10 Mo 13
TO-23-110 kV A1 @ KNY-01 | KNOCKRANNY 110 kV A1 | bar: Week 9 Fr 3
TO-23-110 kV B1 @ KNY-01 | KNOCKRANNY 110 kV B1 | bar: Week 9 Fr 3
TO-23-KNY-110K1-01 | KNOCKRANNY 110K1 | bar: Week 9 Fr 3
TO-23-KNY-110SA1-2CB-04 | KNOCKRANNY 110SA1-2CB | bar: Week 9 Fr 3
TO-23-KNY-110SB1-2CB-04 | KNOCKRANNY 110SB1-2CB | bar: Week 9 Fr 3
TO-23-KNY-FILTER1-01 | KNOCKRANNY FILTER1 | bar: Week 9 Fr 3
TO-23-110 kV A1/A2 @ CAH-01 | CAHIR 110 kV A1/A2
TO-23-110 kV B1/B2 @ CAH-01 | CAHIR 110 kV B1/B2
TO-23-CRO-KBY-1-01 | COOLROE KILBARRY
TO-23-KLS-KKY-1-01 | KELLIS KILKENNY | bar: Week 9 Fr 3 to Week 10 Mo 13
TO-23-KKY-110SA1-2CB-01 | KILKENNY 110SA1-2CB | bar: Week 9 Fr 3 to Week 10 Mo 13
Report covers outages commencing/returning/spanning the period: 27/02/2023 - 12/03/2023
Outages commencing/returning in Week 9
OUTAGE ID | PLANT | Week 9 Mo 27: Week 9; Week 10 Mo 6: Week 10
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 26 | 27 | 28 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13
TO-23-KKY-T141-01 | KILKENNY T141 | bar: Week 9 We 1 to Week 10 Mo 13
TO-23-220 kV A1/A2 @ KRA-01 | KNOCKRAHA 220 kV A1/A2 | bar: Week 9 Fr 3 to Week 10 Mo 13
TO-23-KRA-220K1-04 | KNOCKRAHA 220K1 | bar: Week 9 Fr 3 to Week 10 Mo 13
TO-23-KRA-220SA2-4CB-02 | KNOCKRAHA 220SA2-4CB | bar: Week 9 Fr 3 to Week 10 Mo 13
TO-23-KRA-220K1-03 | KNOCKRAHA 220K1 | bar: Su 26 to Week 9 Fr 3
TO-23-CDU-220K1-2-05 | CORDUFF 220K1-2 | bar: Week 9 Sa 4 to Week 9 Su 5
TO-23-CDU-220SA2-4-03 | CORDUFF 220SA2-4 | bar: Week 9 Sa 4 to Week 9 Su 5
TO-23-CDU-220SB2-4-04 | CORDUFF 220SB2-4 | bar: Week 9 Sa 4 to Week 9 Su 5
TO-23-CDU-FIN-2-05 | CORDUFF FINGLAS 2 | bar: Week 9 Sa 4 to Week 9 Su 5
TO-23-CDU-T2102-02 | CORDUFF T2102 | bar: Week 9 Sa 4 to Week 9 Su 5
TO-23-CDU-WOO-1-07 | CORDUFF WOODLAND | bar: Week 9 Sa 4 to Week 9 Su 5
TO-23-220 kV A2/A4 @ CDU-01 | CORDUFF 220 kV A2/A4 | bar: Week 9 Su 5
TO-23-CRU-CDU-2-01 | CRUISERATH CORDUFF 2 | bar: Su 26 to Week 9 Su 5
Outages commencing/returning in Week 10
OUTAGE ID | PLANT | Week 9 Mo 27: Week 9; Week 10 Mo 6: Week 10
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 26 | 27 | 28 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13
TO-23-BVK-110K2-01 | BALLYVOUSKILL 110K2 | bar: Week 10 Mo 6
TO-23-110 kV A2 @ AA GIS-01 | ARDNACRUSHA GIS 110 kV A2 | bar: Week 10 Mo 6 to Week 10 Th 9
TO-23-110 kV B2 @ AA GIS-01 | ARDNACRUSHA GIS 110 kV B2 | bar: Week 10 Mo 6 to Week 10 Th 9
TO-23-110 kV A1 @ RAF-01 | RAFFEEN 110 kV A1 | bar: Week 10 Mo 6 to Week 10 Th 9
TO-23-110 kV B1 @ RAF-01 | RAFFEEN 110 kV B1 | bar: Week 10 Mo 6 to Week 10 Th 9
TO-23-AA GIS-SNG-1-01 | ARDNACRUSHA GIS SINGLAND | bar: Week 10 Mo 6 to Week 10 Fr 10
TO-23-CBR-DLT-1-01 | CASTLEBAR DALTON | bar: Week 10 Mo 6 to Week 10 Fr 10
TO-23-COW-RAF-1-01 | COW CROSS RAFFEEN | bar: Week 10 Mo 6 to Week 10 Fr 10
TO-23-CRA-LWD-1-01 | CRANE LODGEWOOD | bar: Week 10 Mo 6 to Week 10 Fr 10
TO-23-DND-T123-01 | DARNDALE T123 | bar: Week 10 Mo 6 to Week 10 Fr 10
TO-23-SLI-SRA-2-04 | SLIGO SRANANAGH 2 | bar: Week 10 Mo 6 to Week 10 Fr 10
TO-23-110 kV A2 @ SRA-01 | SRANANAGH 110 kV A2 | bar: Week 10 Mo 6 to Week 10 Fr 10
TO-23-110 kV B2 @ SRA-01 | SRANANAGH 110 kV B2 | bar: Week 10 Mo 6 to Week 10 Fr 10
TO-23-110 kV A2 @ CSH-05 | CASHLA 110 kV A2 | bar: Week 10 Mo 6 to Week 10 Mo 13
TO-23-110 kV B2 @ CSH-06 | CASHLA 110 kV B2 | bar: Week 10 Mo 6 to Week 10 Mo 13
TO-23-220 kV A3 @ PB-01 | POOLBEG 220 kV A3 | bar: Week 10 Mo 6 to Week 10 Mo 13
TO-23-220 kV B3 @ PB-01 | POOLBEG 220 kV B3 | bar: Week 10 Mo 6 to Week 10 Mo 13
TO-23-PB-R223-4-01 | POOLBEG R223-4 | bar: Week 10 Mo 6 to Week 10 Mo 13
TO-23-CAH-CAP1/3-01 | CAHIR CAP1/3 | bar: Week 10 Tu 7
TO-23-220 kV A1 @ CDU-01 | CORDUFF 220 kV A1 | bar: Week 10 We 8
TO-23-220 kV A2 @ CDU-02 | CORDUFF 220 kV A2 | bar: Week 10 We 8
TO-23-220 kV A3 @ CDU-01 | CORDUFF 220 kV A3 | bar: Week 10 We 8
TO-23-220 kV A4 @ CDU-03 | CORDUFF 220 kV A4 | bar: Week 10 We 8
TO-23-220 kV B1 @ CDU-01 | CORDUFF 220 kV B1 | bar: Week 10 We 8
TO-23-220 kV B2 @ CDU-02 | CORDUFF 220 kV B2 | bar: Week 10 We 8
TO-23-220 kV B3 @ CDU-01 | CORDUFF 220 kV B3 | bar: Week 10 We 8
TO-23-220 kV B4 @ CDU-03 | CORDUFF 220 kV B4 | bar: Week 10 We 8
TO-23-CDU-220K1-2-02 | CORDUFF 220K1-2 | bar: Week 10 We 8
TO-23-CDU-220K1-3-02 | CORDUFF 220K1-3 | bar: Week 10 We 8
TO-23-CDU-220SA2-4-01 | CORDUFF 220SA2-4 | bar: Week 10 We 8
TO-23-CDU-220SB2-4-01 | CORDUFF 220SB2-4 | bar: Week 10 We 8
TO-23-110 kV A1/A2 @ KNY-01 | KNOCKRANNY 110 kV A1/A2 | bar: Week 10 We 8
TO-23-110 kV B1/B2 @ KNY-01 | KNOCKRANNY 110 kV B1/B2 | bar: Week 10 We 8
TO-23-GWE-T101-03 | GORTAWEE T101 | bar: Su 26 to Week 10 Fr 10
Outages spanning Weeks 9-10
OUTAGE ID | PLANT | Week 9 Mo 27: Week 9; Week 10 Mo 6: Week 10
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 26 | 27 | 28 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13
TO-23-CLG-110K1-01 | CLOGHRAN 110K1
TO-23-CUL-220K1-2-02 | CULLENAGH 220K1-2
TO-23-FIN GIS-110K6-01 | FINGLAS GIS 110K6
Report covers outages commencing/returning/spanning the period: 27/02/2023 - 12/03/2023
Outages spanning Weeks 9-10
OUTAGE ID | PLANT | Week 9 Mo 27: Week 9; Week 10 Mo 6: Week 10
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 26 | 27 | 28 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13
TO-23-GGO-220K1-2-01 | GLANAGOW 220K1-2
TO-23-INC-220K1-2-01 | INCHICORE 220K1-2
TO-23-LET-M/CAP1-01 | LETTERKENNY M/CAP1
TO-23-MUL-CAP1-02 | MULLINGAR CAP1
TO-23-MUL-CAP2-01 | MULLINGAR CAP2
TO-23-PB-R2002-02 | POOLBEG R2002
TO-23-PRO-TB-1-04 | PROSPECT TARBERT
TO-23-SLI-T142-01 | SLIGO T142
TO-23-TB-T101-02 | TARBERT T101
TO-23-TB-T102-02 | TARBERT T102
TO-23-TB-T2004-02 | TARBERT T2004
TO-23-THU-CAP2-01 | THURLES CAP2