## Wks 35 - 36
Report covers outages commencing/returning/spanning the period: 28/08/2023 - 10/09/2023
Outages commencing/returning in Week 35
OUTAGE ID | PLANT |  | Week 35 | [6 empty] | Week 36
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11
TO-23-110 kV A1/A2/A3/A4 @ CDU-02 | CORDUFF 110 kV A1/A2/A3/A4 | bar: Week 35 Mo 28
TO-23-CDU-110K1-2-02 | CORDUFF 110K1-2 | bar: Week 35 Mo 28
TO-23-CDU-110K1-3-01 | CORDUFF 110K1-3 | bar: Week 35 Mo 28
TO-23-CDU-110SA2-4-01 | CORDUFF 110SA2-4 | bar: Week 35 Mo 28
TO-23-110 kV A2 @ CSH-02 | CASHLA 110 kV A2 | bar: Week 35 Mo 28
TO-23-CSH-T2104-01 | CASHLA T2104 | bar: Week 35 Mo 28
TO-23-CDU-SNU-1-03 | CORDUFF SNUGBOROUGH | bar: Week 35 Mo 28
TO-23-FIN-NW-1-05 | FINGLAS NORTH WALL | bar: Week 35 Mo 28; Week 35 Fr 1
TO-23-NW-PB-1-05 | NORTH WALL POOLBEG | bar: Week 35 Mo 28; Week 35 Fr 1
TO-23-NW-T2004/5-02 | NORTH WALL T2004/5 | bar: Week 35 Mo 28; Week 35 Fr 1
TO-23-110 kV A2 @ KLS-05 | KELLIS 110 kV A2 | bar: Week 35 Mo 28; Week 35 Fr 1 to Week 36 Fr 8
TO-23-110 kV B2 @ KLS-05 | KELLIS 110 kV B2 | bar: Week 35 Mo 28; Week 35 Fr 1 to Week 36 Fr 8
TO-23-KLS-T2102-01 | KELLIS T2102 | bar: Week 35 Mo 28; Week 35 Fr 1 to Week 36 Fr 8
TO-23-CLE-T221-01 | CLONEE T221 | bar: Week 35 Mo 28; Week 35 Fr 1 to Week 36 Mo 11
TO-23-GOR-110K1-2-02 | GORMAN 110K1-2 | bar: Week 35 Mo 28; Week 35 Fr 1 to Week 36 Mo 11
TO-23-GOR-110K1-2-01 | bar: Week 35 Mo 28; Week 35 Fr 1 to Week 36 Mo 11
TO-23-KLS-220K1-2-02 | KELLIS 220K1-2 | bar: Week 35 Mo 28; Week 35 Fr 1 to Week 36 Mo 11
TO-23-NAV-T141-01 | NAVAN T141 | bar: Week 35 Mo 28; Week 35 Fr 1 to Week 36 Mo 11
TO-23-KPG-F11-1-CUB-01 | F11 SPARE 220 kV IN KILPADDOGE | bar: Su 27 to Week 35 Mo 28
TO-23-220 kV A3 @ KPG-04 | KILPADDOGE 220 kV A3 | bar: Su 27 to Week 35 Mo 28
TO-23-220 kV B3 @ KPG-04 | KILPADDOGE 220 kV B3 | bar: Su 27 to Week 35 Mo 28
TO-23-IKE,T-THU-1-07 | IKERRIN tee THURLES
TO-23-CLA-MAC-1-04 | CLASHAVOON MACROOM 1 | bar: Week 35 Fr 1
TO-23-110 kV A2 @ LSN-01 | LISHEEN 110 kV A2 | bar: Week 35 Fr 1 to Week 36 Mo 4
TO-23-110 kV A4 @ LSN-01 | LISHEEN 110 kV A4 | bar: Week 35 Fr 1 to Week 36 Mo 4
TO-23-IKE,T-THU-1-08 | IKERRIN tee THURLES | bar: Week 35 Fr 1 to Week 36 Th 7
TO-23-110 kV A1 @ LSN-01 | LISHEEN 110 kV A1 | bar: Week 35 Fr 1 to Week 36 Th 7
TO-23-LSN-110SA1-2-06 | LISHEEN 110SA1-2 | bar: Week 35 Fr 1 to Week 36 Th 7
TO-23-LSN-110SA2-4-06 | LISHEEN 110SA2-4 | bar: Week 35 Fr 1 to Week 36 Th 7
TO-23-LSN-T122-06 | LISHEEN T122 | bar: Week 35 Fr 1 to Week 36 Th 7
TO-23-LSN-T131-06 | LISHEEN T131 | bar: Week 35 Fr 1 to Week 36 Th 7
TO-23-LSN-T142-06 | LISHEEN T142 | bar: Week 35 Fr 1 to Week 36 Th 7
TO-23-LSN-THU-1-07 | LISHEEN THURLES | bar: Week 35 Fr 1 to Week 36 Th 7
TO-23-THU-110SA1-2CB-06 | THURLES 110SA1-2CB | bar: Week 35 Fr 1 to Week 36 Th 7
TO-23-THU-T142-05 | THURLES T142 | bar: Week 35 Fr 1 to Week 36 Th 7
TO-23-BUT-CUL-1-02 | BUTLERSTOWN CULLENAGH | bar: Week 35 Fr 1 to Week 36 Mo 11
TO-23-220 kV A1 @ FLA-01 | FLAGFORD 220 kV A1 | bar: Su 27 to Week 35 Mo 28
TO-23-220 kV A2 @ FLA-01 | FLAGFORD 220 kV A2 | bar: Su 27 to Week 35 Mo 28
TO-23-220 kV B1 @ FLA-01 | FLAGFORD 220 kV B1 | bar: Su 27 to Week 35 Mo 28
TO-23-220 kV B2 @ FLA-01 | FLAGFORD 220 kV B2 | bar: Su 27 to Week 35 Mo 28
TO-23-FLA-220K1-2-01 | FLAGFORD 220K1-2 | bar: Su 27 to Week 35 Mo 28
TO-23-AD-SA1-2CB-04 | AGHADA 220SA1-2CB
TO-23-110 kV B1/B2/B3/B4 @ CDU-02 | CORDUFF 110 kV B1/B2/B3/B4
TO-23-CDU-110K1-2-03 | CORDUFF 110K1-2
TO-23-CDU-110K1-3-02 | CORDUFF 110K1-3
TO-23-CDU-110SB2-4-01 | CORDUFF 110SB2-4
TO-23-IA-T101-04 | INNISCARRA T101
TO-23-110 kV A2 @ FLA-02 | FLAGFORD 110 kV A2 | bar: Week 35 Fr 1
TO-23-110 kV B2 @ FLA-02 | FLAGFORD 110 kV B2 | bar: Week 35 Fr 1
TO-23-220 kV A1/A2 @ KRA-02 | KNOCKRAHA 220 kV A1/A2 | bar: Week 35 Fr 1 to Week 36 Mo 11
TO-23-KRA-220K1-06 | KNOCKRAHA 220K1 | bar: Week 35 Fr 1 to Week 36 Mo 11
TO-23-KRA-220SA2-4CB-03 | KNOCKRAHA 220SA2-4CB | bar: Week 35 Fr 1 to Week 36 Mo 11
TO-23-220 kV A2 @ AD-01 | AGHADA 220 kV A2 | bar: Su 27 to Week 35 Mo 28
TO-23-220 kV B2 @ AD-01 | AGHADA 220 kV B2 | bar: Su 27 to Week 35 Mo 28
TO-23-AD-SA1-2CB-01 | AGHADA 220SA1-2CB | bar: Su 27 to Week 35 Mo 28
TO-23-AD-SB1-2CB-01 | AGHADA 220SB1-2CB | bar: Su 27 to Week 35 Mo 28
TO-23-CLA-CKN-1-01 | CLASHAVOON CLONKEEN | bar: Su 27 to Week 35 Mo 28
TO-23-CKN-110SA1-2CB-01 | CLONKEEN 110SA1-2CB | bar: Su 27 to Week 35 Mo 28
TO-23-CKN-CGL-1-01 | CLONKEEN COOMAGEARLAHY | bar: Su 27 to Week 35 Mo 28
TO-23-CKN-GRO-1-01 | CLONKEEN GARROW | bar: Su 27 to Week 35 Mo 28
TO-23-CKN-KER-1-01 | CLONKEEN KNOCKEARAGH | bar: Su 27 to Week 35 Mo 28
Report covers outages commencing/returning/spanning the period: 28/08/2023 - 10/09/2023
Outages commencing/returning in Week 35
OUTAGE ID | PLANT | Week 35 Mo 28: Week 35; Week 36 Mo 4: Week 36
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11
TO-23-CGL-110SA1-01 | COOMAGEARLAHY 110SA1 | bar: Su 27 to Week 35 Th 31
TO-23-CGL-110SA2-01 | COOMAGEARLAHY 110SA2 | bar: Su 27 to Week 35 Th 31
TO-23-CGL-GAE-1-01 | COOMAGEARLAHY GLANLEE | bar: Su 27 to Week 35 Th 31
TO-23-CGL-T121-01 | COOMAGEARLAHY T121 | bar: Su 27 to Week 35 Th 31
TO-23-CGL-T122-01 | COOMAGEARLAHY T122 | bar: Su 27 to Week 35 Th 31
TO-23-GAE-T121-01 | GLANLEE T121 | bar: Su 27 to Week 35 Th 31
TO-23-TAW-T3-01 | TAWNAGHMORE T3 | bar: Week 35 Fr 1 to Week 36 Fr 8
TO-23-110 kV A4 @ CDU-05 | CORDUFF 110 kV A4 | bar: Week 35 Fr 1 to Week 36 Mo 11
TO-23-110 kV B4 @ CDU-05 | CORDUFF 110 kV B4 | bar: Week 35 Fr 1 to Week 36 Mo 11
TO-23-TAW-T1/T2-01 | TAWNAGHMORE T1/T2 | bar: Su 27 to Week 35 Fr 1
TO-23-CLA-MAC-1-02 | CLASHAVOON MACROOM 1 | bar: Week 35 Sa 2
TO-23-DMY-MAC-1-02 | DUNMANWAY MACROOM | bar: Week 35 Sa 2
TO-23-MAC-110SA1-2CB-02 | MACROOM 110SA1-2CB | bar: Week 35 Sa 2
TO-23-MAC-T142-02 | MACROOM T142 | bar: Week 35 Sa 2
TO-23-FIN-NW-1-04 | FINGLAS NORTH WALL | bar: Week 35 Sa 2 to Week 35 Su 3
TO-23-NW-PB-1-02 | NORTH WALL POOLBEG | bar: Week 35 Sa 2 to Week 35 Su 3
TO-23-NW-T2004/5-03 | NORTH WALL T2004/5 | bar: Week 35 Sa 2 to Week 35 Su 3
TO-23-IA-MAC-1-03 | INNISCARRA MACROOM | bar: Su 27 to Week 35 Sa 2
Outages commencing/returning in Week 36
OUTAGE ID | PLANT | Week 35 Mo 28: Week 35; Week 36 Mo 4: Week 36
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11
TO-23-CDU-MCE-1-02 | CORDUFF MACETOWN | bar: Week 36 Mo 4
TO-23-GRO-110SA1-2CB-01 | GARROW 110SA1-2CB | bar: Week 36 Mo 4; Week 36 Th 7
TO-23-GRO-T122-01 | GARROW T122 | bar: Week 36 Mo 4; Week 36 Th 7
TO-23-AA GIS-T101-01 | ARDNACRUSHA GIS T101 | bar: Week 36 Mo 4; Week 36 Th 7 to Week 36 Fr 8
TO-23-CL-T101-01 | CLIFF T101 | bar: Week 36 Mo 4; Week 36 Th 7 to Week 36 Fr 8
TO-23-CLG-T124-01 | CLOGHRAN T124 | bar: Week 36 Mo 4; Week 36 Th 7 to Week 36 Fr 8
TO-23-MOY-TAW-2-04 | MOY TAWNAGHMORE 2 | bar: Week 36 Mo 4; Week 36 Th 7 to Week 36 Fr 8
TO-23-TAW-110SA1-2CB-01 | TAWNAGHMORE 110SA1-2CB | bar: Week 36 Mo 4; Week 36 Th 7 to Week 36 Fr 8
TO-23-TAW-T142-01 | TAWNAGHMORE T142 | bar: Week 36 Mo 4; Week 36 Th 7 to Week 36 Fr 8
TO-23-CRO-IA-1-02 | COOLROE INNISCARRA | bar: Week 36 Mo 4; Week 36 Th 7 to Week 36 Mo 11
TO-23-KBY-MR-1-06 | KILBARRY MARINA 1 | bar: Week 36 Mo 4; Week 36 Th 7 to Week 36 Mo 11
TO-23-KBY-MR-2-05 | KILBARRY MARINA 2 | bar: Week 36 Mo 4; Week 36 Th 7 to Week 36 Mo 11
TO-23-KIN-T102-01 | KINNEGAD T102 | bar: Week 36 Mo 4; Week 36 Th 7 to Week 36 Mo 11
TO-23-KRA-MID-1-01 | KNOCKRAHA MIDLETON | bar: Week 36 Mo 4; Week 36 Th 7 to Week 36 Mo 11
TO-23-400 kV A1 @ MP GIS-03 | MONEYPOINT GIS 400 kV A1
TO-23-400 kV A2 @ MP GIS-01 | MONEYPOINT GIS 400 kV A2
TO-23-400 kV A3 @ MP GIS-03 | MONEYPOINT GIS 400 kV A3
TO-23-400 kV A4 @ MP GIS-03 | MONEYPOINT GIS 400 kV A4
TO-23-400 kV A4 @ MP GIS-01
TO-23-400 kV B1 @ MP GIS-03 | MONEYPOINT GIS 400 kV B1
TO-23-400 kV B2 @ MP GIS-01 | MONEYPOINT GIS 400 kV B2
TO-23-400 kV B3 @ MP GIS-02 | MONEYPOINT GIS 400 kV B3
TO-23-400 kV B4 @ MP GIS-02 | MONEYPOINT GIS 400 kV B4
TO-23-MP GIS-400K3-02 | MONEYPOINT GIS 400K3
TO-23-MP GIS-400K4-01 | MONEYPOINT GIS 400K4
TO-23-MP GIS-400SA1-2CB-01 | MONEYPOINT GIS 400SA1-2CB
TO-23-MP GIS-400SA1-3CB-03 | MONEYPOINT GIS 400SA1-3CB
TO-23-MP GIS-400SA2-4CB-01 | MONEYPOINT GIS 400SA2-4CB
TO-23-MP GIS-400SB1-2CB-01 | MONEYPOINT GIS 400SB1-2CB
TO-23-MP GIS-400SB1-3CB-02 | MONEYPOINT GIS 400SB1-3CB
TO-23-MP GIS-400SB2-4CB-02 | MONEYPOINT GIS 400SB2-4CB
TO-23-MP GIS-OST-1-06 | MONEYPOINT GIS OLDSTREET
TO-23-CRA-110SA1-01 | CRANE 110SA1 | bar: Week 36 Th 7
TO-23-CRA-110SA2-02 | CRANE 110SA2 | bar: Week 36 Th 7
TO-23-CRA-T141-01 | CRANE T141 | bar: Week 36 Th 7
TO-23-LOU-T2104-06 | LOUTH T2104 | bar: Week 36 Th 7 to Week 36 Fr 8
TO-23-SHL-T2014-01 | SHELLYBANKS T2014
TO-23-MP GIS-T4202-02 | MONEYPOINT GIS T4202 | bar: Su 27 to Week 36 Mo 4
Report covers outages commencing/returning/spanning the period: 28/08/2023 - 10/09/2023
Outages commencing/returning in Week 36
OUTAGE ID | PLANT | Week 35 Mo 28: Week 35; Week 36 Mo 4: Week 36
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11
TO-23-CGG-T131-02 | CARRIGDANGAN T131
TO-23-110 kV B2 @ FLA-03 | FLAGFORD 110 kV B2
TO-23-FLA-T2102-03 | FLAGFORD T2102
TO-23-CSH-TY-1-03 | CASHLA TYNAGH
TO-23-KHL-THU-1-01 | KILL HILL THURLES
TO-23-THU-110SA1-2CB-07 | THURLES 110SA1-2CB
TO-23-THU-CAP1-02 | THURLES CAP1
TO-23-THU-T141-01 | THURLES T141
TO-23-AD-GGO-1-01 | AGHADA GLANAGOW
TO-23-220 kV A2 @ DSN-02 | DUNSTOWN 220 kV A2
TO-23-220 kV B2 @ DSN-02 | DUNSTOWN 220 kV B2
TO-23-400 kV A2 @ DSN-01 | DUNSTOWN 400 kV A2
TO-23-400 kV B2 @ DSN-01 | DUNSTOWN 400 kV B2
TO-23-DSN-T4202-01 | DUNSTOWN T4202
TO-23-FLA-SLI-1-01 | FLAGFORD SLIGO
TO-23-GGO-RAF-1-01 | GLANAGOW RAFFEEN
TO-23-GGO-T2001-01 | GLANAGOW T2001
TO-23-LIS-110SA1-04 | LISDRUM 110SA1
TO-23-LIS-110SA2-04 | LISDRUM 110SA2
TO-23-LIS-CAP2-04 | LISDRUM CAP2
TO-23-LIS-T142-03 | LISDRUM T142
Outages spanning Weeks 35-36
OUTAGE ID | PLANT | Week 35 Mo 28: Week 35; Week 36 Mo 4: Week 36
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11
TO-23-AD-T2001-03 | AGHADA T2001
TO-23-ARV-NAV-1-05 | ARVA NAVAN
TO-23-BOG-CRA-1-01 | BANOGE CRANE
TO-23-BIN-CF-1-01 | BINBANE CATHALEENS FALL
TO-23-BUT-T141-02 | BUTLERSTOWN T141
TO-23-CSH-CAP2-04 | CASHLA CAP2
TO-23-CSH-GAL-1-01 | CASHLA GALWAY 1
TO-23-CLG-110K1-01 | CLOGHRAN 110K1
TO-23-DOO-T142-02 | DOON T142
TO-23-DRY-PLA-1-04 | DRYBRIDGE PLATIN
TO-23-DDK-LOU-1-01 | DUNDALK LOUTH
TO-23-220 kV A2 @ FIN-02 | FINGLAS 220 kV A2
TO-23-FIN-T2104-02 | FINGLAS T2104
TO-23-GAL-110K2-3-02 | GALWAY 110K2-3
TO-23-GGO-220K1-2-01 | GLANAGOW 220K1-2
TO-23-INC-220K1-2-01 | INCHICORE 220K1-2
TO-23-KLS-220K1-2-04 | KELLIS 220K1-2
TO-23-KPG-TB-1-02 | KILPADDOGE TARBERT 1
TO-23-KRA-220K1-2-03 | KNOCKRAHA 220K1-2
TO-23-LET-M/CAP1-01 | LETTERKENNY M/CAP1
TO-23-LIS-SKL-1-06 | LISDRUM SHANKILL
TO-23-LIS-T131-05 | LISDRUM T131
TO-23-110 kV A2 @ LOU-01 | LOUTH 110 kV A2
TO-23-110 kV B2 @ LOU-01 | LOUTH 110 kV B2
TO-23-MUL-CAP1-02 | MULLINGAR CAP1
TO-23-PB-R2002-02 | POOLBEG R2002
TO-23-PRO-TB-1-04 | PROSPECT TARBERT
TO-23-110 kV A2 @ SH-03 | SHANNONBRIDGE 110 kV A2
TO-23-110 kV B1 @ SH-02 | SHANNONBRIDGE 110 kV B1
TO-23-110 kV B2 @ SH-04 | SHANNONBRIDGE 110 kV B2
TO-23-TB-220K1-2-01 | TARBERT 220K1-2
TO-23-TB-T101-02 | TARBERT T101
TO-23-TB-T2003-03 | TARBERT T2003
TO-23-TB-T2004-03 | TARBERT T2004
TO-23-TB-T2004-02
Report covers outages commencing/returning/spanning the period: 28/08/2023 - 10/09/2023
Outages spanning Weeks 35-36
OUTAGE ID | PLANT | Week 35 Mo 28: Week 35; Week 36 Mo 4: Week 36
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11
TO-23-TB-T2101-02 | TARBERT T2101
TO-23-TB-T2101-03
TO-23-THU-CAP2-01 | THURLES CAP2