## Wks 46 - 47
Report covers outages commencing/returning/spanning the period: 10/11/2025 - 23/11/2025
Outages commencing/returning in Week 46
OUTAGE ID | PLANT |  | Week 46 | [6 empty] | Week 47
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24
TO-25-220 kV A1 @ FIN-02 | FINGLAS 220 kV A1 | bar: Week 46 Mo 10 to Week 46 Tu 11
TO-25-FIN-220K1-01 | FINGLAS 220K1 | bar: Week 46 Mo 10 to Week 46 Tu 11
TO-25-FIN-220SA1-2CB-04 | FINGLAS 220SA1-2CB | bar: Week 46 Mo 10 to Week 46 Tu 11
TO-25-220 kV A1 @ LOU-04 | LOUTH 220 kV A1 | bar: Week 46 Mo 10 to Week 46 Tu 11
TO-25-220 kV A2 @ LOU-10 | LOUTH 220 kV A2 | bar: Week 46 Mo 10 to Week 46 Tu 11
TO-25-220 kV B1 @ LOU-04 | LOUTH 220 kV B1 | bar: Week 46 Mo 10 to Week 46 Tu 11
TO-25-220 kV B2 @ LOU-11 | LOUTH 220 kV B2 | bar: Week 46 Mo 10 to Week 46 Tu 11
TO-25-LOU-220K1-2-02 | LOUTH 220K1-2 | bar: Week 46 Mo 10 to Week 46 Tu 11
TO-25-LOU-T2102-04 | LOUTH T2102 | bar: Week 46 Mo 10 to Week 46 Tu 11
TO-25-IKE-T141-04 | IKERRIN T141 | bar: Week 46 Mo 10 to Week 46 Th 13
TO-25-IKE,T-IKE-1-04 | IKERRIN tee IKERRIN | bar: Week 46 Mo 10 to Week 46 Th 13
TO-25-IKE,T-THU-1-09 | IKERRIN tee THURLES | bar: Week 46 Mo 10 to Week 46 Th 13
TO-25-IKE,T-TMY-1-02 | IKERRIN tee TIMONEY | bar: Week 46 Mo 10 to Week 46 Th 13
TO-25-CLH-TRL-1-02 | CLAHANE TRALEE | bar: Week 46 Mo 10 to Week 46 Fr 14
TO-25-GAL GIS-110K2-01 | GALWAY GIS 110K2 | bar: Week 46 Mo 10 to Week 46 Fr 14
TO-25-GAL GIS-110K3-02 | GALWAY GIS 110K3 | bar: Week 46 Mo 10 to Week 46 Fr 14
TO-25-GAL GIS-110SA1-3CB-02 | GALWAY GIS 110SA1-3CB | bar: Week 46 Mo 10 to Week 46 Fr 14
TO-25-220 kV A1 @ WOO-05 | WOODLAND 220 kV A1 | bar: Week 46 Mo 10 to Week 46 Fr 14
TO-25-220 kV A2 @ WOO-02 | WOODLAND 220 kV A2 | bar: Week 46 Mo 10 to Week 46 Fr 14
TO-25-220 kV B1 @ WOO-03 | WOODLAND 220 kV B1 | bar: Week 46 Mo 10 to Week 46 Fr 14
TO-25-220 kV B2 @ WOO-02 | WOODLAND 220 kV B2 | bar: Week 46 Mo 10 to Week 46 Fr 14
TO-25-WOO-220K1-2-01 | WOODLAND 220K1-2 | bar: Week 46 Mo 10 to Week 46 Fr 14
TO-25-GGO-RAF-1-02 | GLANAGOW RAFFEEN | bar: Week 46 Mo 10 to Week 47 Fr 21
TO-25-220 kV A1 @ RAF-03 | RAFFEEN 220 kV A1 | bar: Week 46 Mo 10 to Week 47 Fr 21
TO-25-220 kV B1 @ RAF-03 | RAFFEEN 220 kV B1 | bar: Week 46 Mo 10 to Week 47 Fr 21
TO-25-110 kV A2 @ CDU-03 | CORDUFF 110 kV A2 | bar: Su 9 to Week 46 Mo 10
TO-25-110 kV A4 @ CDU-04 | CORDUFF 110 kV A4 | bar: Su 9 to Week 46 Mo 10
TO-25-110 kV B2 @ CDU-05 | CORDUFF 110 kV B2 | bar: Su 9 to Week 46 Mo 10
TO-25-110 kV B4 @ CDU-04 | CORDUFF 110 kV B4 | bar: Su 9 to Week 46 Mo 10
TO-25-CDU-110SA2-4CB-02 | CORDUFF 110SA2-4CB | bar: Su 9 to Week 46 Mo 10
TO-25-CDU-110SB2-4CB-03 | CORDUFF 110SB2-4CB | bar: Su 9 to Week 46 Mo 10
TO-25-CDU-MCE-1-01 | CORDUFF MACETOWN | bar: Su 9 to Week 46 Mo 10
TO-25-IKE,T-THU-1-07 | IKERRIN tee THURLES | bar: Su 9 to Week 46 Mo 10
TO-25-KYT-T237-01 | KELLYSTOWN T237 | bar: Week 46 Tu 11
TO-25-CSH-GAL GIS-4-03 | CASHLA GALWAY GIS 4 | bar: Week 46 Tu 11 to Week 46 Th 13
TO-25-FIN-T2103-01 | FINGLAS T2103 | bar: Su 9 to Week 46 Tu 11
TO-25-CAH-CAP1/3-04 | CAHIR CAP1/3 | bar: Week 46 We 12 to Week 46 Th 13
TO-25-CBT-CKG-2-04 | CASTLEBAGOT CORKAGH 2 | bar: Week 46 We 12 to Week 46 Fr 14
TO-25-LOU-RRU-1-03 | LOUTH RATRUSSAN | bar: Su 9 to Week 46 We 12
TO-25-220 kV A1 @ BYH-02 | BALLYNAHULLA 220 kV A1 | bar: Su 9 to Week 46 Th 13
TO-25-220 kV B1 @ BYH-02 | BALLYNAHULLA 220 kV B1 | bar: Su 9 to Week 46 Th 13
TO-25-BYH-220K1-04 | BALLYNAHULLA 220K1 | bar: Su 9 to Week 46 Th 13
TO-25-BYH-220SA1-2CB-02 | BALLYNAHULLA 220SA1-2CB | bar: Su 9 to Week 46 Th 13
TO-25-BYH-220SB1-2CB-02 | BALLYNAHULLA 220SB1-2CB | bar: Su 9 to Week 46 Th 13
TO-25-BYH-KNR-1-01 | BALLYNAHULLA KNOCKANURE | bar: Su 9 to Week 46 Th 13
TO-25-220 kV A2 @ KNR-02 | KNOCKANURE 220 kV A2 | bar: Su 9 to Week 46 Th 13
TO-25-220 kV B2 @ KNR-02 | KNOCKANURE 220 kV B2 | bar: Su 9 to Week 46 Th 13
TO-25-KNR-220K2-03 | KNOCKANURE 220K2 | bar: Su 9 to Week 46 Th 13
TO-25-KNR-220SA1-2CB-03 | KNOCKANURE 220SA1-2CB | bar: Su 9 to Week 46 Th 13
TO-25-KNR-220SB1-2CB-03 | KNOCKANURE 220SB1-2CB | bar: Su 9 to Week 46 Th 13
TO-25-220 kV A4 @ CKM GIS-01 | CARRICKMINES GIS 220 kV A4 | bar: Week 46 Fr 14 to Week 47 Mo 24
TO-25-220 kV B4 @ CKM GIS-01 | CARRICKMINES GIS 220 kV B4 | bar: Week 46 Fr 14 to Week 47 Mo 24
TO-25-CKM GIS-220K4-02 | CARRICKMINES GIS 220K4 | bar: Week 46 Fr 14 to Week 47 Mo 24
TO-25-CKM GIS-220SA2-4CB-03 | CARRICKMINES GIS 220SA2-4CB | bar: Week 46 Fr 14 to Week 47 Mo 24
TO-25-CKM GIS-220SB2-4CB-01 | CARRICKMINES GIS 220SB2-4CB | bar: Week 46 Fr 14 to Week 47 Mo 24
TO-25-CKM GIS-T2104-01 | CARRICKMINES GIS T2104 | bar: Week 46 Fr 14 to Week 47 Mo 24
TO-25-KRA-WOH-1-06 | KNOCKRAHA WOODHOUSE | bar: Su 9 to Week 46 Fr 14
TO-25-ARV-SKL-1-02 | ARVA SHANKILL 1 | bar: Week 46 Sa 15
TO-25-SKL-110SA1-02 | SHANKILL 110SA1 | bar: Week 46 Sa 15
TO-25-SKL-110SA2-02 | SHANKILL 110SA2 | bar: Week 46 Sa 15
TO-25-SKL-T142-01 | SHANKILL T142 | bar: Week 46 Sa 15
Report covers outages commencing/returning/spanning the period: 10/11/2025 - 23/11/2025
Outages commencing/returning in Week 47
OUTAGE ID | PLANT | Week 46 Mo 10: Week 46; Week 47 Mo 17: Week 47
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24
TO-25-CUL-220K1-2-01 | CULLENAGH 220K1-2
TO-25-BLU-T131-03 | BLUNDELSTOWN T131 | bar: Week 47 Tu 18
TO-25-220 kV A2 @ BVK-01 | BALLYVOUSKILL 220 kV A2 | bar: Week 47 Tu 18 to Week 47 Fr 21
TO-25-220 kV B2 @ BVK-01 | BALLYVOUSKILL 220 kV B2 | bar: Week 47 Tu 18 to Week 47 Fr 21
TO-25-BVK-220SA1-2CB-01 | BALLYVOUSKILL 220SA1-2CB | bar: Week 47 Tu 18 to Week 47 Fr 21
TO-25-BVK-220SB1-2CB-01 | BALLYVOUSKILL 220SB1-2CB | bar: Week 47 Tu 18 to Week 47 Fr 21
TO-25-CDU-CRU-2-09 | CORDUFF CRUISERATH 2 | bar: Week 47 Tu 18 to Week 47 Fr 21
TO-25-220 kV B1 @ CRU-01 | CRUISERATH 220 kV B1 | bar: Week 47 Tu 18 to Week 47 Fr 21
TO-25-CRU-220K1-02 | CRUISERATH 220K1 | bar: Week 47 Tu 18 to Week 47 Fr 21
TO-25-CRU-SB1-2CB-04 | CRUISERATH 220SB1-2CB | bar: Week 47 Tu 18 to Week 47 Fr 21
TO-25-CRU-T221-03 | CRUISERATH T221 | bar: Week 47 Tu 18 to Week 47 Fr 21
TO-25-GLN-T133-03 | GALLANSTOWN T133 | bar: Week 47 Tu 18 to Week 47 Fr 21
TO-25-110 kV A1/A2/A3/A4 @ KPG-01 | KILPADDOGE 110 kV A1/A2/A3/A4 | bar: Week 47 Tu 18 to Week 47 Fr 21
TO-25-KPG-110K3-01 | KILPADDOGE 110K3 | bar: Week 47 Tu 18 to Week 47 Fr 21
TO-25-KPG-110K4-02 | KILPADDOGE 110K4 | bar: Week 47 Tu 18 to Week 47 Fr 21
TO-25-KPG-110SA1-2CB-02 | KILPADDOGE 110SA1-2CB | bar: Week 47 Tu 18 to Week 47 Fr 21
TO-25-KPG-110SA1-3CB-01 | KILPADDOGE 110SA1-3CB | bar: Week 47 Tu 18 to Week 47 Fr 21
TO-25-KPG-110SA2-4CB-02 | KILPADDOGE 110SA2-4CB | bar: Week 47 Tu 18 to Week 47 Fr 21
TO-25-220 kV A4 @ CSH-04 | CASHLA 220 kV A4 | bar: Su 9 to Week 46 Su 16
TO-25-220 kV B4 @ CSH-03 | CASHLA 220 kV B4 | bar: Su 9 to Week 46 Su 16
TO-25-110 kV A2 @ RYB GIS-01 | RYEBROOK GIS 110 kV A2 | bar: Su 9 to Week 46 Su 16
TO-25-110 kV B2 @ RYB GIS-01 | RYEBROOK GIS 110 kV B2 | bar: Su 9 to Week 46 Su 16
TO-25-RYB GIS-110SA1-2CB-03 | RYEBROOK GIS 110SA1-2CB | bar: Su 9 to Week 46 Su 16
TO-25-RYB GIS-110SA2-4CB-02 | RYEBROOK GIS 110SA2-4CB | bar: Su 9 to Week 46 Su 16
TO-25-RYB GIS-110SB1-2CB-03 | RYEBROOK GIS 110SB1-2CB | bar: Su 9 to Week 46 Su 16
TO-25-RYB GIS-110SB2-4CB-02 | RYEBROOK GIS 110SB2-4CB | bar: Su 9 to Week 46 Su 16
TO-25-RYB GIS-T104-01 | RYEBROOK GIS T104 | bar: Su 9 to Week 46 Su 16
TO-25-110 kV A2 @ SH-03 | SHANNONBRIDGE 110 kV A2 | bar: Su 9 to Week 46 Su 16
TO-25-110 kV B2 @ SH-03 | SHANNONBRIDGE 110 kV B2 | bar: Su 9 to Week 46 Su 16
TO-25-BOG-110SA1-01 | BANOGE 110SA1 | bar: Week 47 Tu 18 to Week 47 Th 20
TO-25-BOG-TTU-1-02 | BANOGE TULLABEG | bar: Week 47 Tu 18 to Week 47 Th 20
TO-25-110 kV A1 @ SRA-01 | SRANANAGH 110 kV A1 | bar: Week 47 We 19
TO-25-BUT-T142-02 | BUTLERSTOWN T142 | bar: Week 47 We 19 to Week 47 Th 20
TO-25-SLI-110SA1-2CB-03 | SLIGO 110SA1-2CB | bar: Su 9 to Week 46 Su 16; Week 47 Tu 18 to Week 47 We 19
TO-25-SLI-CAP1-02 | SLIGO CAP1 | bar: Su 9 to Week 46 Su 16; Week 47 Tu 18 to Week 47 We 19
TO-25-SLI-SRA-1-02 | SLIGO SRANANAGH 1 | bar: Su 9 to Week 46 Su 16; Week 47 Tu 18 to Week 47 We 19
TO-25-SLI-T141-01 | SLIGO T141 | bar: Su 9 to Week 46 Su 16; Week 47 Tu 18 to Week 47 We 19
TO-25-AD-ST101-01 | AGHADA ST101 | bar: Su 9 to Week 46 Su 16; Week 47 Tu 18 to Week 47 Fr 21
TO-25-AD-T2102-01 | AGHADA T2102 | bar: Su 9 to Week 46 Su 16; Week 47 Tu 18 to Week 47 Fr 21
TO-25-AD-WHI-1-01 | AGHADA WHITEGATE | bar: Su 9 to Week 46 Su 16; Week 47 Tu 18 to Week 47 Fr 21
TO-25-CLA-MAC-1-02 | CLASHAVOON MACROOM 1 | bar: Su 9 to Week 46 Su 16; Week 47 Tu 18 to Week 47 Fr 21
Outages spanning Weeks 46-47
OUTAGE ID | PLANT | Week 46 Mo 10: Week 46; Week 47 Mo 17: Week 47
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24
TO-25-ATH-M/CAP1-06 | ATHLONE M/CAP1
TO-25-CLW-KLS-1-09 | CARLOW KELLIS 1
TO-25-CSH-PRO-1-02 | CASHLA PROSPECT
TO-25-CSH-T2102-04 | CASHLA T2102
TO-25-CBR-CAP2-03 | CASTLEBAR CAP2
TO-25-CBR-SVC-01 | CASTLEBAR SVC
TO-25-220 kV A2 @ CRU-01 | CRUISERATH 220 kV A2
TO-25-220 kV B2 @ CRU-01 | CRUISERATH 220 kV B2
TO-25-CRU-220K2-02 | CRUISERATH 220K2
TO-25-CRU-SA1-2CB-02 | CRUISERATH 220SA1-2CB
TO-25-CRU-SB1-2CB-02 | CRUISERATH 220SB1-2CB
TO-25-CRU-T224-01 | CRUISERATH T224
TO-25-DND-T121-01 | DARNDALE T121
TO-25-110 kV B1/B2/B3 @ FIN-01 | FINGLAS 110 kV B1/B2/B3
Report covers outages commencing/returning/spanning the period: 10/11/2025 - 23/11/2025
Outages spanning Weeks 46-47
OUTAGE ID | PLANT | Week 46 Mo 10: Week 46; Week 47 Mo 17: Week 47
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24
TO-25-FIN-110K1-2-02 | FINGLAS 110K1-2
TO-25-FIN-110K2-3-04 | FINGLAS 110K2-3
TO-25-FIN-FIN GIS-1-02 | FINGLAS FINGLAS GIS 1
TO-25-FIN-SHL-1-03 | FINGLAS SHELLYBANKS
TO-25-GGO-220K1-2-01 | GLANAGOW 220K1-2
TO-25-GI GIS-220SA1-2CB-02 | GREAT ISLAND GIS 220SA1-2CB
TO-25-GI-T141-01 | GREAT ISLAND T141
TO-25-KLN-LIM-1-05 | KILLONAN LIMERICK 1
TO-25-KIN-MUL-1-01 | KINNEGAD MULLINGAR
TO-25-KDN-T131-04 | KNOCKDRIN T131
TO-25-LET-PST-01 | LETTERKENNY STRABANE PST
TO-25-110 kV A2 @ LOU-01 | LOUTH 110 kV A2
TO-25-110 kV B2 @ LOU-01 | LOUTH 110 kV B2
TO-25-LOU-WOO-1-01 | LOUTH WOODLAND
TO-25-220 kV A1 @ MAY-03 | MAYNOOTH 220 kV A1
TO-25-220 kV B1 @ MAY-03 | MAYNOOTH 220 kV B1
TO-25-MAY-SH-1-03 | MAYNOOTH SHANNONBRIDGE
TO-25-MAY-TEN-1-01 | MAYNOOTH TIMAHOE
TO-25-MAY-TH-1-05 | MAYNOOTH TURLOUGH HILL
TO-25-MUL-CAP2-01 | MULLINGAR CAP2
TO-25-NEW-PLS-1-03 | NEWBRIDGE PORTLAOISE
TO-25-PB-R2001-01 | POOLBEG R2001
TO-25-PLS-T142-01 | PORTLAOISE T142
TO-25-SKL-M/CAP2-03 | SHANKILL M/CAP2
TO-25-SHL-D1/CB1-05 | SHELLYBANKS D1/CB1
TO-25-SHL-D1/CB2-03 | SHELLYBANKS D1/CB2
TO-25-TB-T101-03 | TARBERT T101
TO-25-TB-T2003-01 | TARBERT T2003
TO-25-TB-T2004-01 | TARBERT T2004