## Wks 34 - 35
Report covers outages commencing/returning/spanning the period: 18/08/2025 - 31/08/2025
Outages commencing/returning in Week 34
OUTAGE ID | PLANT |  | Week 34 | [6 empty] | Week 35
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1
TO-25-110 kV A1 @ CLG-01 | CLOGHRAN 110 kV A1
TO-25-110 kV B1 @ CLG-01 | CLOGHRAN 110 kV B1
TO-25-CLG-110K1-03 | CLOGHRAN 110K1
TO-25-CLG-110SA1-2CB-01 | CLOGHRAN 110SA1-2CB
TO-25-CLG-110SB1-2CB-01 | CLOGHRAN 110SB1-2CB
TO-25-MCE-110SA1-02 | MACETOWN 110SA1
TO-25-MCE-110SA2-02 | MACETOWN 110SA2
TO-25-MCE-T102-02 | MACETOWN T102
TO-25-MCE-T124-02 | MACETOWN T124
TO-25-AGL-DYN-1-02 | AGANNYGAL DERRYBRIEN
TO-25-DYN-T121-02 | DERRYBRIEN T121
TO-25-110 kV A1 @ BLC-01 | BELCAMP 110 kV A1 | bar: Week 34 Th 21 to Week 34 Fr 22
TO-25-110 kV A3 @ BLC-03 | BELCAMP 110 kV A3 | bar: Week 34 Th 21 to Week 34 Fr 22
TO-25-BLC-110K1-03 | BELCAMP 110K1 | bar: Week 34 Th 21 to Week 34 Fr 22
TO-25-BLC-110K3-03 | BELCAMP 110K3 | bar: Week 34 Th 21 to Week 34 Fr 22
TO-25-BLC-110SA1-3CB-01 | BELCAMP 110SA1-3CB | bar: Week 34 Th 21 to Week 34 Fr 22
TO-25-CNO-KPG-1-01 | COOLNANOONAGH KILPADDOGE | bar: Week 34 Th 21 to Week 34 Fr 22
TO-25-CNO-T131-01 | COOLNANOONAGH T131 | bar: Week 34 Th 21 to Week 34 Fr 22
TO-25-220 kV B1 @ MP GIS-03 | MONEYPOINT GIS 220 kV B1 | bar: Week 34 Th 21 to Week 34 Fr 22
TO-25-220 kV B2 @ MP GIS-02 | MONEYPOINT GIS 220 kV B2 | bar: Week 34 Th 21 to Week 34 Fr 22
TO-25-MP GIS-220K1-04 | MONEYPOINT GIS 220K1 | bar: Week 34 Th 21 to Week 34 Fr 22
TO-25-MP GIS-220K2-03 | MONEYPOINT GIS 220K2 | bar: Week 34 Th 21 to Week 34 Fr 22
TO-25-MP GIS-220SB1-2CB-01 | MONEYPOINT GIS 220SB1-2CB | bar: Week 34 Th 21 to Week 34 Fr 22
TO-25-CVW-KRA-1-01 | CASTLEVIEW KNOCKRAHA | bar: Week 34 Th 21 to Week 35 Fr 29
TO-25-110 kV A2 @ KRA-04 | KNOCKRAHA 110 kV A2 | bar: Week 34 Th 21 to Week 35 Fr 29
TO-25-110 kV B2 @ KRA-04 | KNOCKRAHA 110 kV B2 | bar: Week 34 Th 21 to Week 35 Fr 29
TO-25-CDY-GRV-1-04 | CORDERRY GARVAGH | bar: Week 34 Th 21 to Week 35 Su 31
TO-25-GRV-110K1-04 | GARVAGH 110K1 | bar: Week 34 Th 21 to Week 35 Su 31
TO-25-GRV-T121-04 | GARVAGH T121 | bar: Week 34 Th 21 to Week 35 Su 31
TO-25-GRV-T141-03 | GARVAGH T141 | bar: Week 34 Th 21 to Week 35 Su 31
TO-25-AA GIS-T104-01 | ARDNACRUSHA GIS T104 | bar: Week 34 Th 21 to Week 35 Mo 1
TO-25-110 kV A1 @ CSH-01 | CASHLA 110 kV A1 | bar: Week 34 Th 21 to Week 35 Mo 1
TO-25-110 kV B1 @ CSH-02 | CASHLA 110 kV B1 | bar: Week 34 Th 21 to Week 35 Mo 1
TO-25-DMY-MAC-1-03 | DUNMANWAY MACROOM | bar: Week 34 Th 21 to Week 35 Mo 1
TO-25-220 kV A2 @ DSN-01 | DUNSTOWN 220 kV A2 | bar: Week 34 Th 21 to Week 35 Mo 1
TO-25-LOU-T2103-05 | LOUTH T2103 | bar: Week 34 Th 21 to Week 35 Mo 1
TO-25-DFR-T122-01 | DUNFIRTH T122 | bar: Su 17
TO-25-DFR,T-DFR-1-03 | DUNFIRTH tee DUNFIRTH | bar: Su 17
TO-25-DFR,T-KIN-1-03 | DUNFIRTH tee KINNEGAD | bar: Su 17
TO-25-OBE-PLA-1-02 | OLDBRIDGE PLATIN | bar: Su 17
TO-25-220 kV A1 @ TB-02 | TARBERT 220 kV A1 | bar: Week 34 Th 21 to Week 34 Fr 22
TO-25-220 kV A2 @ TB-05 | TARBERT 220 kV A2 | bar: Week 34 Th 21 to Week 34 Fr 22
TO-25-220 kV B1 @ TB-02 | TARBERT 220 kV B1 | bar: Week 34 Th 21 to Week 34 Fr 22
TO-25-220 kV B2 @ TB-05 | TARBERT 220 kV B2 | bar: Week 34 Th 21 to Week 34 Fr 22
TO-25-TB-220K1-2-01 | TARBERT 220K1-2 | bar: Week 34 Th 21 to Week 34 Fr 22
TO-25-BOL-ENN-1-01 | BOOLTIAGH ENNIS | bar: Week 34 Th 21 to Week 35 Sa 30
TO-25-BIN-T141-01 | BINBANE T141 | bar: Su 17
TO-25-KHL-T131-01 | KILL HILL T131 | bar: Su 17
TO-25-SKY-T131-02 | SRAHNAKILLY T131
TO-25-BYH-T2101-01 | BALLYNAHULLA T2101 | bar: Week 34 Th 21
TO-25-220 kV A1 @ CDU-02 | CORDUFF 220 kV A1 | bar: Week 34 Th 21
TO-25-220 kV A3 @ CDU-03 | CORDUFF 220 kV A3 | bar: Week 34 Th 21
TO-25-CDU-220K1-3-02 | CORDUFF 220K1-3 | bar: Week 34 Th 21
TO-25-110 kV A3 @ AA GIS-02 | ARDNACRUSHA GIS 110 kV A3 | bar: Week 34 Th 21 to Week 35 Tu 26
TO-25-110 kV B3 @ AA GIS-01 | ARDNACRUSHA GIS 110 kV B3 | bar: Week 34 Th 21 to Week 35 Tu 26
TO-25-AA GIS-110K3-01 | ARDNACRUSHA GIS 110K3 | bar: Week 34 Th 21 to Week 35 Tu 26
TO-25-AA GIS-110SA1-3CB-01 | ARDNACRUSHA GIS 110SA1-3CB | bar: Week 34 Th 21 to Week 35 Tu 26
TO-25-AA GIS-110SB1-3CB-01 | ARDNACRUSHA GIS 110SB1-3CB | bar: Week 34 Th 21 to Week 35 Tu 26
TO-25-BDN-MRK3-03 | BALLYDINE MRK3 | bar: Su 17
TO-25-ATH-CAP3-03 | ATHLONE CAP3 | bar: Week 34 Th 21 to Week 35 Tu 26
TO-25-CBA-110SA1-01 | CLOGHBOOLA 110SA1 | bar: Su 17; Week 34 Th 21
Report covers outages commencing/returning/spanning the period: 18/08/2025 - 31/08/2025
Outages commencing/returning in Week 34
OUTAGE ID | PLANT | Week 34 Mo 18: Week 34; Week 35 Mo 25: Week 35
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1
TO-25-CBA-110SA2-01 | CLOGHBOOLA 110SA2 | bar: Su 17 to Week 34 Th 21
TO-25-CBA-T122-01 | CLOGHBOOLA T122 | bar: Su 17 to Week 34 Th 21
TO-25-CBA-T131-01 | CLOGHBOOLA T131 | bar: Su 17 to Week 34 Th 21
TO-25-CBA-TRI-1-01 | CLOGHBOOLA TRIEN | bar: Su 17 to Week 34 Th 21
TO-25-ATY-110SA1-01 | ATHY 110SA1 | bar: Su 17 to Week 34 Fr 22
TO-25-ATY-110SA2-02 | ATHY 110SA2 | bar: Su 17 to Week 34 Fr 22
TO-25-ATY-T102-01 | ATHY T102 | bar: Su 17 to Week 34 Fr 22
TO-25-110 kV A2 @ BYH-01 | BALLYNAHULLA 110 kV A2 | bar: Su 17 to Week 34 Fr 22
TO-25-110 kV B2 @ BYH-01 | BALLYNAHULLA 110 kV B2 | bar: Su 17 to Week 34 Fr 22
TO-25-BYH-110K2-01 | BALLYNAHULLA 110K2 | bar: Su 17 to Week 34 Fr 22
TO-25-BYH-110SA1-2CB-03 | BALLYNAHULLA 110SA1-2CB | bar: Su 17 to Week 34 Fr 22
TO-25-BYH-110SB1-2CB-03 | BALLYNAHULLA 110SB1-2CB | bar: Su 17 to Week 34 Fr 22
TO-25-BYH-CDL-1-01 | BALLYNAHULLA CORDAL | bar: Su 17 to Week 34 Fr 22
TO-25-CRO-IA-1-01 | COOLROE INNISCARRA | bar: Su 17 to Week 34 Fr 22
TO-25-CDL-110SA1-01 | CORDAL 110SA1 | bar: Su 17 to Week 34 Fr 22
TO-25-CDL-110SA2-01 | CORDAL 110SA2 | bar: Su 17 to Week 34 Fr 22
TO-25-CDL-T132-01 | CORDAL T132 | bar: Su 17 to Week 34 Fr 22
TO-25-CDL-T141-01 | CORDAL T141 | bar: Su 17 to Week 34 Fr 22
TO-25-220 kV A2 @ GOR-01 | GORMAN 220 kV A2 | bar: Su 17 to Week 34 Fr 22
TO-25-220 kV B2 @ GOR-02 | GORMAN 220 kV B2 | bar: Su 17 to Week 34 Fr 22
TO-25-GOR-LOU-1-02 | GORMAN LOUTH | bar: Su 17 to Week 34 Fr 22
TO-25-IA-MAC-1-03 | INNISCARRA MACROOM | bar: Su 17 to Week 34 Fr 22
TO-25-IA-T101-02 | INNISCARRA T101 | bar: Su 17 to Week 34 Fr 22
TO-25-LIS-LOU-1-02 | LISDRUM LOUTH | bar: Su 17 to Week 34 Fr 22
TO-25-220 kV A2 @ LOU-09 | LOUTH 220 kV A2 | bar: Su 17 to Week 34 Fr 22
TO-25-220 kV B2 @ LOU-09 | LOUTH 220 kV B2 | bar: Su 17 to Week 34 Fr 22
TO-25-SLI-110SA1-2CB-02 | SLIGO 110SA1-2CB | bar: Su 17 to Week 34 Fr 22
TO-25-SLI-CAP1-01 | SLIGO CAP1 | bar: Su 17 to Week 34 Fr 22
TO-25-SLI-T141-02 | SLIGO T141 | bar: Su 17 to Week 34 Fr 22
Outages commencing/returning in Week 35
OUTAGE ID | PLANT | Week 34 Mo 18: Week 34; Week 35 Mo 25: Week 35
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1
TO-25-CBT-110SA1-2CB-01 | CASTLEBAGOT 110SA1-2CB | bar: Week 35 Mo 25
TO-25-220 kV A2 @ LOU-04 | LOUTH 220 kV A2 | bar: Week 35 Mo 25 to Week 35 Th 28
TO-25-220 kV B2 @ LOU-03 | LOUTH 220 kV B2 | bar: Week 35 Mo 25 to Week 35 Th 28
TO-25-CLH-110SA1-01 | CLAHANE 110SA1 | bar: Week 35 Mo 25 to Week 35 Fr 29
TO-25-CLH-110SA2-02 | CLAHANE 110SA2 | bar: Week 35 Mo 25 to Week 35 Fr 29
TO-25-CLH-TRL-1-01 | CLAHANE TRALEE | bar: Week 35 Mo 25 to Week 35 Fr 29
TO-25-DRU-CAP2-01 | DRUMLINE CAP2 | bar: Week 35 Mo 25 to Week 35 Fr 29
TO-25-LET-CAP2-02 | LETTERKENNY CAP2 | bar: Week 35 Mo 25 to Week 35 Fr 29
TO-25-110 kV A2 @ KNR-01 | KNOCKANURE 110 kV A2 | bar: Week 35 Mo 25 to Week 35 Mo 1
TO-25-110 kV B2 @ KNR-01 | KNOCKANURE 110 kV B2 | bar: Week 35 Mo 25 to Week 35 Mo 1
TO-25-KNR-110SA1-2CB-02 | KNOCKANURE 110SA1-2CB | bar: Week 35 Mo 25 to Week 35 Mo 1
TO-25-KNR-110SA2-4CB-01 | KNOCKANURE 110SA2-4CB | bar: Week 35 Mo 25 to Week 35 Mo 1
TO-25-KNR-110SB1-2CB-02 | KNOCKANURE 110SB1-2CB | bar: Week 35 Mo 25 to Week 35 Mo 1
TO-25-KNR-110SB2-4CB-01 | KNOCKANURE 110SB2-4CB | bar: Week 35 Mo 25 to Week 35 Mo 1
TO-25-220 kV A2 @ KNR-04 | KNOCKANURE 220 kV A2 | bar: Week 35 Mo 25 to Week 35 Mo 1
TO-25-220 kV B2 @ KNR-05 | KNOCKANURE 220 kV B2 | bar: Week 35 Mo 25 to Week 35 Mo 1
TO-25-KNR-220K2-06 | KNOCKANURE 220K2 | bar: Week 35 Mo 25 to Week 35 Mo 1
TO-25-KNR-220SA1-2CB-05 | KNOCKANURE 220SA1-2CB | bar: Week 35 Mo 25 to Week 35 Mo 1
TO-25-KNR-220SB1-2CB-05 | KNOCKANURE 220SB1-2CB | bar: Week 35 Mo 25 to Week 35 Mo 1
TO-25-KNR-T2102-01 | KNOCKANURE T2102 | bar: Week 35 Mo 25 to Week 35 Mo 1
TO-25-TY-T2001/2-04 | TYNAGH T2001/2 | bar: Week 35 Mo 25 to Week 35 Mo 1
TO-25-RYB GIS-110K3-01 | RYEBROOK GIS 110K3 | bar: Week 35 Tu 26 to Week 35 We 27
TO-25-KNY-SAL-1-02 | KNOCKRANNY SALTHILL | bar: Su 17 to Week 35 Tu 26
TO-25-SAL-110SA1-2CB-01 | SALTHILL 110SA1-2CB | bar: Su 17 to Week 35 Tu 26
TO-25-SAL-T102-01 | SALTHILL T102 | bar: Su 17 to Week 35 Tu 26
TO-25-GOR-LOU-1-01 | GORMAN LOUTH | bar: Week 35 We 27 to Week 35 Th 28
TO-25-220 kV A2 @ LOU-05 | LOUTH 220 kV A2 | bar: Week 35 We 27 to Week 35 Th 28
Report covers outages commencing/returning/spanning the period: 18/08/2025 - 31/08/2025
Outages commencing/returning in Week 35
OUTAGE ID | PLANT | Week 34 Mo 18: Week 34; Week 35 Mo 25: Week 35
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1
TO-25-220 kV B2 @ LOU-05 | LOUTH 220 kV B2
TO-25-220 kV B2 @ MAY-01 | MAYNOOTH 220 kV B2
TO-25-KTL-T142-01 | KILTEEL T142
TO-25-RYB GIS-110K4-01 | RYEBROOK GIS 110K4
TO-25-CSH-SAL-1-03 | CASHLA SALTHILL
TO-25-LOU-AT3-02 | LOUTH AT3
TO-25-SH-T101/3-01 | SHANNONBRIDGE T101/3
TO-25-110 kV A4 @ CBT-01 | CASTLEBAGOT 110 kV A4
TO-25-110 kV B4 @ CBT-01 | CASTLEBAGOT 110 kV B4
TO-25-CBT-110K4-02 | CASTLEBAGOT 110K4
TO-25-CBT-110SA2-4CB-02 | CASTLEBAGOT 110SA2-4CB
TO-25-CBT-110SB2-4CB-02 | CASTLEBAGOT 110SB2-4CB
TO-25-220 kV A2 @ CBT-02 | CASTLEBAGOT 220 kV A2
TO-25-220 kV B2 @ CBT-02 | CASTLEBAGOT 220 kV B2
TO-25-CBT-220K2-04 | CASTLEBAGOT 220K2
TO-25-CBT-220SA1-2CB-04 | CASTLEBAGOT 220SA1-2CB
TO-25-CBT-220SB1-2CB-04 | CASTLEBAGOT 220SB1-2CB
TO-25-CBT-T2104-01 | CASTLEBAGOT T2104
TO-25-KPG-TRL-2-02 | KILPADDOGE TRALEE 2
TO-25-PLS-T141-02 | PORTLAOISE T141
TO-25-TSB-110SA1-01 | THORNSBERRY 110SA1
TO-25-TSB-110SA2-01 | THORNSBERRY 110SA2
TO-25-TSB-T142-01 | THORNSBERRY T142
Outages spanning Weeks 34-35
OUTAGE ID | PLANT | Week 34 Mo 18: Week 34; Week 35 Mo 25: Week 35
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1
TO-25-AA GIS-T102-02 | ARDNACRUSHA GIS T102
TO-25-ATH-M/CAP1-06 | ATHLONE M/CAP1
TO-25-ATY-PLS-1-02 | ATHY PORTLAOISE
TO-25-CSH-CAP2-01 | CASHLA CAP2
TO-25-CBR-CAP2-03 | CASTLEBAR CAP2
TO-25-CBR-SVC-01 | CASTLEBAR SVC
TO-25-CF-CLO-1-03 | CATHALEENS FALL CLOGHER 1
TO-25-CF-T104-02 | CATHALEENS FALL T104
TO-25-CLG-FIN GIS-1-01 | CLOGHRAN FINGLAS GIS
TO-25-CRA-WEX-1-02 | CRANE WEXFORD
TO-25-DND-T121-01 | DARNDALE T121
TO-25-DER-KIN-1-03 | DERRYIRON KINNEGAD
TO-25-DER-T1/T2-02 | DERRYIRON RHODE T1/T2
TO-25-DFR,T-RNW-1-02 | DUNFIRTH tee RINAWADE
TO-25-110 kV B1/B2/B3 @ FIN-01 | FINGLAS 110 kV B1/B2/B3
TO-25-FIN-110K1-2-02 | FINGLAS 110K1-2
TO-25-FIN-110K2-3-04 | FINGLAS 110K2-3
TO-25-FIN-FIN GIS-1-02 | FINGLAS FINGLAS GIS 1
TO-25-FIN-T2103-01 | FINGLAS T2103
TO-25-GAL-GAL GIS-1-01 | GALWAY GALWAY GIS 1
TO-25-GGO-220K1-2-01 | GLANAGOW 220K1-2
TO-25-GLR-MOY-1-02 | GLENREE MOY
TO-25-GI GIS-220SA1-2CB-02 | GREAT ISLAND GIS 220SA1-2CB
TO-25-GI-T141-01 | GREAT ISLAND T141
TO-25-IKE,T-SH-1-05 | IKERRIN tee SHANNONBRIDGE
TO-25-INC-220K1-2-01 | INCHICORE 220K1-2
TO-25-KYT-T232-02 | KELLYSTOWN T232
TO-25-KBY-MR-1-03 | KILBARRY MARINA 1
TO-25-KBY-MR-2-03 | KILBARRY MARINA 2
TO-25-KDN-T131-02 | KNOCKDRIN T131
TO-25-KDN-T131-01
TO-25-KDN,T-KDN-1-02 | KNOCKDRIN tee KNOCKDRIN
TO-25-KDN,T-KDN-1-01
Report covers outages commencing/returning/spanning the period: 18/08/2025 - 31/08/2025
Outages spanning Weeks 34-35
OUTAGE ID | PLANT | Week 34 Mo 18: Week 34; Week 35 Mo 25: Week 35
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1
TO-25-KDN,T-TSB-1-03 | KNOCKDRIN tee THORNSBERRY
TO-25-KDN,T-TSB-1-01
TO-25-KDN,T-TEN-1-03 | KNOCKDRIN tee TIMAHOE
TO-25-KDN,T-TEN-1-02
TO-25-LET-PST-01 | LETTERKENNY STRABANE PST
TO-25-LIS-T142-01 | LISDRUM T142
TO-25-110 kV A2 @ LOU-01 | LOUTH 110 kV A2
TO-25-110 kV B2 @ LOU-01 | LOUTH 110 kV B2
TO-25-MCE-SNU-1-02 | MACETOWN SNUGBOROUGH
TO-25-MAY-RYB GIS-1-01 | MAYNOOTH RYEBROOK GIS
TO-25-MAY-SH-1-03 | MAYNOOTH SHANNONBRIDGE
TO-25-MTN-MUN-1-02 | MONETEEN MUNGRET 1
TO-25-MUL-CAP2-01 | MULLINGAR CAP2
TO-25-NW-PB-1-03 | NORTH WALL POOLBEG
TO-25-PB-R2001-01 | POOLBEG R2001
TO-25-SH-T2102-01 | SHANNONBRIDGE T2102
TO-25-SLI-SRA-1-02 | SLIGO SRANANAGH 1
TO-25-TB-T2003-01 | TARBERT T2003
TO-25-TB-T2004-01 | TARBERT T2004