## Wks 38 - 39
Report covers outages commencing/returning/spanning the period: 15/09/2025 - 28/09/2025
Outages commencing/returning in Week 38
OUTAGE ID | PLANT |  | Week 38 | [6 empty] | Week 39
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29
TO-25-220 kV A1/A2 @ LOU-02 | LOUTH 220 kV A1/A2
TO-25-LOU-220K1-2-05 | LOUTH 220K1-2
TO-25-LOU-T2103-06 | LOUTH T2103
TO-25-CRU-T221-02 | CRUISERATH T221
TO-25-OBE-110K1-01 | OLDBRIDGE 110K1
TO-25-OBE-110K2-01 | OLDBRIDGE 110K2
TO-25-OBE-110SA1-2CB-01 | OLDBRIDGE 110SA1-2CB
TO-25-OBE-110SB1-2CB-01 | OLDBRIDGE 110SB1-2CB
TO-25-BLC-DND-3-02 | BELCAMP DARNDALE 3 | bar: Week 38 Th 18 to Week 38 Fr 19
TO-25-CRU-220K1-01 | CRUISERATH 220K1 | bar: Week 38 Th 18 to Week 38 Fr 19
TO-25-CRU-220K2-01 | CRUISERATH 220K2 | bar: Week 38 Th 18 to Week 38 Fr 19
TO-25-CRU-SA1-2CB-01 | CRUISERATH 220SA1-2CB | bar: Week 38 Th 18 to Week 38 Fr 19
TO-25-CRU-SB1-2CB-01 | CRUISERATH 220SB1-2CB | bar: Week 38 Th 18 to Week 38 Fr 19
TO-25-KYT-220K2-01 | KELLYSTOWN 220K2 | bar: Week 38 Th 18 to Week 38 Fr 19
TO-25-KYT-220K3-01 | KELLYSTOWN 220K3 | bar: Week 38 Th 18 to Week 38 Fr 19
TO-25-KYT-220SA1-2CB-01 | KELLYSTOWN 220SA1-2CB | bar: Week 38 Th 18 to Week 38 Fr 19
TO-25-KYT-220SA1-3CB-01 | KELLYSTOWN 220SA1-3CB | bar: Week 38 Th 18 to Week 38 Fr 19
TO-25-KYT-220SB1-2CB-01 | KELLYSTOWN 220SB1-2CB | bar: Week 38 Th 18 to Week 38 Fr 19
TO-25-KYT-220SB1-3CB-01 | KELLYSTOWN 220SB1-3CB | bar: Week 38 Th 18 to Week 38 Fr 19
TO-25-220 kV A2 @ KLN-04 | KILLONAN 220 kV A2 | bar: Week 38 Th 18 to Week 38 Fr 19
TO-25-220 kV B2 @ KLN-04 | KILLONAN 220 kV B2 | bar: Week 38 Th 18 to Week 38 Fr 19
TO-25-110 kV A1 @ PLS-02 | PORTLAOISE 110 kV A1 | bar: Week 38 Th 18 to Week 38 Fr 19
TO-25-110 kV B1 @ PLS-01 | PORTLAOISE 110 kV B1 | bar: Week 38 Th 18 to Week 38 Fr 19
TO-25-RYB GIS-110SA1-2CB-01 | RYEBROOK GIS 110SA1-2CB | bar: Week 38 Th 18 to Week 38 Fr 19
TO-25-RYB GIS-110SA1-3CB-01 | RYEBROOK GIS 110SA1-3CB | bar: Week 38 Th 18 to Week 38 Fr 19
TO-25-RYB GIS-110SA2-4CB-01 | RYEBROOK GIS 110SA2-4CB | bar: Week 38 Th 18 to Week 38 Fr 19
TO-25-SHL-T2015-02 | SHELLYBANKS T2015 | bar: Week 38 Th 18 to Week 38 Fr 19
TO-25-WHI-CKB-T102-01 | WHITEGATE CKB-T102 | bar: Week 38 Th 18 to Week 38 Fr 19
TO-25-CLW-KLS-1-05 | CARLOW KELLIS 1 | bar: Week 38 Th 18 to Week 39 Fr 26
TO-25-110 kV A1 @ KLS-05 | KELLIS 110 kV A1 | bar: Week 38 Th 18 to Week 39 Fr 26
TO-25-110 kV B1 @ KLS-03 | KELLIS 110 kV B1 | bar: Week 38 Th 18 to Week 39 Fr 26
TO-25-KLN-KPG-1-04 | KILLONAN KILPADDOGE | bar: Week 38 Th 18 to Week 39 Fr 26
TO-25-KIN-MUL-1-01 | KINNEGAD MULLINGAR | bar: Week 38 Th 18 to Week 39 Mo 29
TO-25-MAY-TEN-1-01 | MAYNOOTH TIMAHOE | bar: Week 38 Th 18 to Week 39 Mo 29
TO-25-ARK-T102-01 | ARKLOW T102
TO-25-GAL GIS-KNY-1-01 | GALWAY GIS KNOCKRANNY
TO-25-MP GIS-T4202-03 | MONEYPOINT GIS T4202
TO-25-PLA-T105-05 | PLATIN T105 | bar: Week 38 Th 18
TO-25-TRI-CAP1-02 | TRIEN CAP1 | bar: Week 38 Th 18 to Week 38 Fr 19
TO-25-220 kV A1/A2 @ KNR-01 | KNOCKANURE 220 kV A1/A2 | bar: Week 38 Th 18 to Week 39 Tu 23
TO-25-KNR-220K1-01 | KNOCKANURE 220K1 | bar: Week 38 Th 18 to Week 39 Tu 23
TO-25-KNR-220K2-04 | KNOCKANURE 220K2 | bar: Week 38 Th 18 to Week 39 Tu 23
TO-25-KNR-220SA1-2CB-01 | KNOCKANURE 220SA1-2CB | bar: Week 38 Th 18 to Week 39 Tu 23
TO-25-BDA-T102-02 | BARODA T102 | bar: Su 14
TO-25-CF-T104-02 | CATHALEENS FALL T104 | bar: Su 14
TO-25-220 kV B2 @ DSN-01 | DUNSTOWN 220 kV B2 | bar: Su 14
TO-25-KRA-220K1-04 | KNOCKRAHA 220K1 | bar: Su 14
TO-25-KRA-220SA1-2CB-05 | KNOCKRAHA 220SA1-2CB | bar: Su 14
TO-25-KRA-220SB1-2CB-05 | KNOCKRAHA 220SB1-2CB | bar: Su 14
TO-25-TRL-CAP2-03 | TRALEE CAP2 | bar: Week 38 Th 18
TO-25-400 kV A2 @ DSN-01 | DUNSTOWN 400 kV A2 | bar: Week 38 Th 18 to Week 39 Mo 29
TO-25-DSN-T4202-02 | DUNSTOWN T4202 | bar: Week 38 Th 18 to Week 39 Mo 29
TO-25-COW-RAF-1-02 | COW CROSS RAFFEEN | bar: Su 14
TO-25-110 kV A1 @ RAF-04 | RAFFEEN 110 kV A1 | bar: Su 14
TO-25-110 kV B1 @ RAF-04 | RAFFEEN 110 kV B1 | bar: Su 14
TO-25-BWR-CRA-1-02 | BALLYWATER CRANE | bar: Week 38 Th 18 to Week 38 Fr 19
TO-25-BWR-T124-02 | BALLYWATER T124 | bar: Week 38 Th 18 to Week 38 Fr 19
TO-25-CRA-110SA1-02 | CRANE 110SA1 | bar: Week 38 Th 18 to Week 38 Fr 19
TO-25-CRA-110SA2-02 | CRANE 110SA2 | bar: Week 38 Th 18 to Week 38 Fr 19
TO-25-CRA-LWD-1-02 | CRANE LODGEWOOD | bar: Week 38 Th 18 to Week 38 Fr 19
TO-25-CRA-T122-02 | CRANE T122 | bar: Week 38 Th 18 to Week 38 Fr 19
Report covers outages commencing/returning/spanning the period: 15/09/2025 - 28/09/2025
Outages commencing/returning in Week 38
OUTAGE ID | PLANT | Week 38 Mo 15: Week 38; Week 39 Mo 22: Week 39
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29
TO-25-RAF-T2102-03 | RAFFEEN T2102 | bar: Week 38 Th 18 to Week 38 Fr 19
TO-25-220 kV A2 @ LOU-04 | LOUTH 220 kV A2 | bar: Week 38 Th 18 to Week 38 Su 21
TO-25-220 kV B2 @ LOU-03 | LOUTH 220 kV B2 | bar: Week 38 Th 18 to Week 38 Su 21
TO-25-110 kV A1/A2 @ GOR-01 | GORMAN 110 kV A1/A2 | bar: Su 14 to Week 38 Th 18
TO-25-110 kV B1/B2 @ GOR-01 | GORMAN 110 kV B1/B2 | bar: Su 14 to Week 38 Th 18
TO-25-GOR-110K1-2-03 | GORMAN 110K1-2 | bar: Su 14 to Week 38 Th 18
TO-25-AA GIS-T102-02 | ARDNACRUSHA GIS T102 | bar: Su 14 to Week 38 Fr 19
TO-25-AUG-CFM-1-01 | AUGHINISH CASTLEFARM 1 | bar: Su 14 to Week 38 Fr 19
TO-25-110 kV A4 @ CBT-01 | CASTLEBAGOT 110 kV A4 | bar: Su 14 to Week 38 Fr 19
TO-25-110 kV B4 @ CBT-01 | CASTLEBAGOT 110 kV B4 | bar: Su 14 to Week 38 Fr 19
TO-25-CBT-110K4-02 | CASTLEBAGOT 110K4 | bar: Su 14 to Week 38 Fr 19
TO-25-CBT-110SA2-4CB-02 | CASTLEBAGOT 110SA2-4CB | bar: Su 14 to Week 38 Fr 19
TO-25-CBT-110SB2-4CB-02 | CASTLEBAGOT 110SB2-4CB | bar: Su 14 to Week 38 Fr 19
TO-25-220 kV A2 @ CBT-02 | CASTLEBAGOT 220 kV A2 | bar: Su 14 to Week 38 Fr 19
TO-25-220 kV B2 @ CBT-02 | CASTLEBAGOT 220 kV B2 | bar: Su 14 to Week 38 Fr 19
TO-25-CBT-220K2-04 | CASTLEBAGOT 220K2 | bar: Su 14 to Week 38 Fr 19
TO-25-CBT-220SA1-2CB-04 | CASTLEBAGOT 220SA1-2CB | bar: Su 14 to Week 38 Fr 19
TO-25-CBT-220SB1-2CB-04 | CASTLEBAGOT 220SB1-2CB | bar: Su 14 to Week 38 Fr 19
TO-25-CBT-T2104-01 | CASTLEBAGOT T2104 | bar: Su 14 to Week 38 Fr 19
TO-25-CFM-T101-01 | CASTLEFARM T101 | bar: Su 14 to Week 38 Fr 19
TO-25-110 kV A1 @ CF-01 | CATHALEENS FALL 110 kV A1 | bar: Su 14 to Week 38 Fr 19
TO-25-110 kV B1 @ CF-06 | CATHALEENS FALL 110 kV B1 | bar: Su 14 to Week 38 Fr 19
TO-25-CF-COR-1-03 | CATHALEENS FALL CORRACLASSY | bar: Su 14 to Week 38 Fr 19
TO-25-CHA-KLN-1-03 | CHARLEVILLE KILLONAN | bar: Su 14 to Week 38 Fr 19
TO-25-CRA-WEX-1-02 | CRANE WEXFORD | bar: Su 14 to Week 38 Fr 19
TO-25-220 kV A1 @ GOR-03 | GORMAN 220 kV A1 | bar: Su 14 to Week 38 Fr 19
TO-25-220 kV B1 @ GOR-02 | GORMAN 220 kV B1 | bar: Su 14 to Week 38 Fr 19
TO-25-GOR-MAY-1-01 | GORMAN MAYNOOTH | bar: Su 14 to Week 38 Fr 19
TO-25-110 kV A1 @ KLN-02 | KILLONAN 110 kV A1 | bar: Su 14 to Week 38 Fr 19
TO-25-110 kV B1 @ KLN-02 | KILLONAN 110 kV B1 | bar: Su 14 to Week 38 Fr 19
TO-25-GOR-LOU-1-01 | GORMAN LOUTH | bar: Week 38 Sa 20 to Week 38 Su 21
TO-25-LOU-AT3-02 | LOUTH AT3 | bar: Su 14 to Week 38 Su 21
Outages commencing/returning in Week 39
OUTAGE ID | PLANT | Week 38 Mo 15: Week 38; Week 39 Mo 22: Week 39
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29
TO-25-LET-M/CAP1-01 | LETTERKENNY M/CAP1
TO-25-DMY-CAP2-01 | DUNMANWAY CAP2
TO-25-CRU-T222-01 | CRUISERATH T222
TO-25-LIS-CAP2-02 | LISDRUM CAP2
TO-25-RYB GIS-110SB1-2CB-01 | RYEBROOK GIS 110SB1-2CB
TO-25-RYB GIS-110SB1-3CB-01 | RYEBROOK GIS 110SB1-3CB
TO-25-RYB GIS-110SB2-4CB-01 | RYEBROOK GIS 110SB2-4CB
TO-25-WHI-CKB-T101-02 | WHITEGATE CKB-T101
TO-25-AD-KRA-1-04 | AGHADA KNOCKRAHA 1 | bar: Week 39 Sa 27 to Week 39 Mo 29
TO-25-AD-KRA-2-04 | AGHADA KNOCKRAHA 2 | bar: Week 39 Sa 27 to Week 39 Mo 29
TO-25-BNK-T121-02 | BARNAKYLE T121 | bar: Week 39 Sa 27 to Week 39 Mo 29
TO-25-220 kV A4 @ CSH-04 | CASHLA 220 kV A4 | bar: Week 39 Sa 27 to Week 39 Mo 29
TO-25-220 kV B4 @ CSH-03 | CASHLA 220 kV B4 | bar: Week 39 Sa 27 to Week 39 Mo 29
TO-25-CSH-PRO-1-02 | CASHLA PROSPECT | bar: Week 39 Sa 27 to Week 39 Mo 29
TO-25-KLN-LIM-2-03 | KILLONAN LIMERICK 2 | bar: Week 39 Sa 27 to Week 39 Mo 29
TO-25-110 kV A2 @ KRA-06 | KNOCKRAHA 110 kV A2 | bar: Week 39 Sa 27 to Week 39 Mo 29
TO-25-110 kV B2 @ KRA-05 | KNOCKRAHA 110 kV B2 | bar: Week 39 Sa 27 to Week 39 Mo 29
TO-25-220 kV A1 @ KRA-02 | KNOCKRAHA 220 kV A1 | bar: Week 39 Sa 27 to Week 39 Mo 29
TO-25-220 kV A2 @ KRA-01 | KNOCKRAHA 220 kV A2 | bar: Week 39 Sa 27 to Week 39 Mo 29
TO-25-220 kV B1 @ KRA-02 | KNOCKRAHA 220 kV B1 | bar: Week 39 Sa 27 to Week 39 Mo 29
TO-25-220 kV B2 @ KRA-01 | KNOCKRAHA 220 kV B2 | bar: Week 39 Sa 27 to Week 39 Mo 29
TO-25-KRA-220K1-02 | KNOCKRAHA 220K1 | bar: Week 39 Sa 27 to Week 39 Mo 29
TO-25-KRA-220SA1-2CB-03 | KNOCKRAHA 220SA1-2CB | bar: Week 39 Sa 27 to Week 39 Mo 29
TO-25-KRA-220SA1-2CB-02 | bar: Week 39 Sa 27 to Week 39 Mo 29
Report covers outages commencing/returning/spanning the period: 15/09/2025 - 28/09/2025
Outages commencing/returning in Week 39
OUTAGE ID | PLANT | Week 38 Mo 15: Week 38; Week 39 Mo 22: Week 39
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29
TO-25-KRA-220SA2-4CB-01 | KNOCKRAHA 220SA2-4CB
TO-25-KRA-220SB1-2CB-02 | KNOCKRAHA 220SB1-2CB
TO-25-KRA-220SB1-2CB-03
TO-25-KRA-220SB2-4CB-01 | KNOCKRAHA 220SB2-4CB
TO-25-KRA-T2102-02 | KNOCKRAHA T2102
TO-25-KRA-T2102-01
TO-25-LLA-LET-1-01 | LENALEA LETTERKENNY
TO-25-DEN-DRY-1-02 | DEENES DRYBRIDGE
TO-25-LIS-T131-01 | LISDRUM T131
TO-25-CSH-T2102-02 | CASHLA T2102
TO-25-110 kV A2 @ KPG-01 | KILPADDOGE 110 kV A2
TO-25-KPG-110SA1-2CB-01 | KILPADDOGE 110SA1-2CB
TO-25-KPG-110SA2-4CB-01 | KILPADDOGE 110SA2-4CB
TO-25-KPG-T2102-01 | KILPADDOGE T2102
TO-25-CUL-WAT-1-02 | CULLENAGH WATERFORD
TO-25-110 kV B1/B2/B3/B4 @ KPG-01 | KILPADDOGE 110 kV B1/B2/B3/B4
TO-25-220 kV A1 @ LOU-02 | LOUTH 220 kV A1
TO-25-220 kV A2 @ LOU-03 | LOUTH 220 kV A2
TO-25-220 kV B1 @ LOU-02 | LOUTH 220 kV B1
TO-25-220 kV B2 @ LOU-02 | LOUTH 220 kV B2
TO-25-CLE-T221-01 | CLONEE T221
TO-25-KPG-TRL-2-02 | KILPADDOGE TRALEE 2
TO-25-110 kV A2 @ LOU-01 | LOUTH 110 kV A2
TO-25-110 kV B2 @ LOU-01 | LOUTH 110 kV B2
TO-25-PB-R223-4-01 | POOLBEG R223-4
TO-25-PB-SHL-1-01 | POOLBEG SHELLYBANKS
TO-25-SHL-D1/CB3-05 | SHELLYBANKS D1/CB3
TO-25-SHL-D2/CB3-04 | SHELLYBANKS D2/CB3
Outages spanning Weeks 38-39
OUTAGE ID | PLANT | Week 38 Mo 15: Week 38; Week 39 Mo 22: Week 39
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29
TO-25-AA GIS-T104-01 | ARDNACRUSHA GIS T104
TO-25-ATH-M/CAP1-06 | ATHLONE M/CAP1
TO-25-ATY-PLS-1-02 | ATHY PORTLAOISE
TO-25-BAN-RAF-1-06 | BANDON RAFFEEN
TO-25-110 kV A1 @ CSH-01 | CASHLA 110 kV A1
TO-25-110 kV B1 @ CSH-02 | CASHLA 110 kV B1
TO-25-CSH-CAP2-01 | CASHLA CAP2
TO-25-CBR-CAP2-03 | CASTLEBAR CAP2
TO-25-CBR-SVC-01 | CASTLEBAR SVC
TO-25-CF-CLO-1-03 | CATHALEENS FALL CLOGHER 1
TO-25-CRU-T224-01 | CRUISERATH T224
TO-25-DND-T121-01 | DARNDALE T121
TO-25-110 kV B1/B2/B3 @ FIN-01 | FINGLAS 110 kV B1/B2/B3
TO-25-FIN-110K1-2-02 | FINGLAS 110K1-2
TO-25-FIN-110K2-3-04 | FINGLAS 110K2-3
TO-25-FIN-FIN GIS-1-02 | FINGLAS FINGLAS GIS 1
TO-25-FIN-T2103-01 | FINGLAS T2103
TO-25-GGO-220K1-2-01 | GLANAGOW 220K1-2
TO-25-GLR-MOY-1-02 | GLENREE MOY
TO-25-GI GIS-220SA1-2CB-02 | GREAT ISLAND GIS 220SA1-2CB
TO-25-GI-T141-01 | GREAT ISLAND T141
TO-25-IKE-T141-03 | IKERRIN T141
TO-25-IKE,T-IKE-1-03 | IKERRIN tee IKERRIN
TO-25-IKE,T-SH-1-04 | IKERRIN tee SHANNONBRIDGE
TO-25-IKE,T-THU-1-03 | IKERRIN tee THURLES
TO-25-INC-220K1-2-01 | INCHICORE 220K1-2
TO-25-KYT-T232-02 | KELLYSTOWN T232
TO-25-KDN-T131-02 | KNOCKDRIN T131
Report covers outages commencing/returning/spanning the period: 15/09/2025 - 28/09/2025
Outages spanning Weeks 38-39
OUTAGE ID | PLANT | Week 38 Mo 15: Week 38; Week 39 Mo 22: Week 39
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29
TO-25-KDN,T-KDN-1-01 | KNOCKDRIN tee KNOCKDRIN
TO-25-KDN,T-TSB-1-01 | KNOCKDRIN tee THORNSBERRY
TO-25-KDN,T-TEN-1-02 | KNOCKDRIN tee TIMAHOE
TO-25-LET-PST-01 | LETTERKENNY STRABANE PST
TO-25-LIS-T142-01 | LISDRUM T142
TO-25-LOU-RRU-1-03 | LOUTH RATRUSSAN
TO-25-220 kV B2 @ MAY-01 | MAYNOOTH 220 kV B2
TO-25-MAY-SH-1-03 | MAYNOOTH SHANNONBRIDGE
TO-25-MUL-CAP2-01 | MULLINGAR CAP2
TO-25-NW-PB-1-03 | NORTH WALL POOLBEG
TO-25-PB-R2001-01 | POOLBEG R2001
TO-25-PLS-T142-01 | PORTLAOISE T142
TO-25-SLI-SRA-1-02 | SLIGO SRANANAGH 1
TO-25-TB-T2003-01 | TARBERT T2003
TO-25-TB-T2004-01 | TARBERT T2004
TO-25-TY-T2001/2-04 | TYNAGH T2001/2