## Wks 50 - 51
Report covers outages commencing/returning/spanning the period: 08/12/2025 - 21/12/2025
Outages commencing/returning in Week 50
OUTAGE ID | PLANT |  | Week 50 | [6 empty] | Week 51
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22
TO-25-ROP-T131-03 | ROSSPILE T131
TO-25-220 kV B1/B2 @ BVK-02 | BALLYVOUSKILL 220 kV B1/B2 | bar: Week 50 We 10 to Week 50 Fr 12
TO-25-BVK-220K1-05 | BALLYVOUSKILL 220K1 | bar: Week 50 We 10 to Week 50 Fr 12
TO-25-BVK-220K2-04 | BALLYVOUSKILL 220K2 | bar: Week 50 We 10 to Week 50 Fr 12
TO-25-BVK-220SB1-2CB-02 | BALLYVOUSKILL 220SB1-2CB | bar: Week 50 We 10 to Week 50 Fr 12
TO-25-DSN-MAY-1-04 | DUNSTOWN MAYNOOTH 1 | bar: Week 50 We 10 to Week 50 Fr 12
TO-25-LOU-T2104-08 | LOUTH T2104 | bar: Week 50 We 10 to Week 50 Fr 12
TO-25-RYB GIS-T109-02 | RYEBROOK GIS T109 | bar: Week 50 We 10 to Week 50 Fr 12
TO-25-COL-CDU-1-01 | COLLEGE PARK CORDUFF | bar: Week 50 We 10 to Week 51 Tu 16
TO-25-110 kV A1 @ CDU-02 | CORDUFF 110 kV A1 | bar: Week 50 We 10 to Week 51 Tu 16
TO-25-110 kV A3 @ CDU-02 | CORDUFF 110 kV A3 | bar: Week 50 We 10 to Week 51 Tu 16
TO-25-110 kV B1 @ CDU-02 | CORDUFF 110 kV B1 | bar: Week 50 We 10 to Week 51 Tu 16
TO-25-110 kV B3 @ CDU-02 | CORDUFF 110 kV B3 | bar: Week 50 We 10 to Week 51 Tu 16
TO-25-PRO-TB-1-03 | PROSPECT TARBERT | bar: Week 50 We 10 to Week 51 Tu 16
TO-25-DJG-TRL-1-03 | DROMBEG TRALEE | bar: Week 50 We 10 to Week 51 We 17
TO-25-220 kV A2 @ CRU-01 | CRUISERATH 220 kV A2 | bar: Week 50 We 10 to Week 51 Fr 19
TO-25-220 kV B2 @ CRU-01 | CRUISERATH 220 kV B2 | bar: Week 50 We 10 to Week 51 Fr 19
TO-25-CRU-220K2-02 | CRUISERATH 220K2 | bar: Week 50 We 10 to Week 51 Fr 19
TO-25-CRU-SA1-2CB-02 | CRUISERATH 220SA1-2CB | bar: Week 50 We 10 to Week 51 Fr 19
TO-25-CRU-SB1-2CB-02 | CRUISERATH 220SB1-2CB | bar: Week 50 We 10 to Week 51 Fr 19
TO-25-ARK-110K1-2-01 | ARKLOW 110K1-2 | bar: Week 50 We 10
TO-25-CLA-CKN-1-01 | CLASHAVOON CLONKEEN | bar: Week 50 We 10
TO-25-110 kV A3 @ CDU-01 | CORDUFF 110 kV A3 | bar: Su 7
TO-25-110 kV B3 @ CDU-01 | CORDUFF 110 kV B3 | bar: Su 7
TO-25-CDU-SNU-1-01 | CORDUFF SNUGBOROUGH | bar: Su 7
TO-25-110 kV A1 @ GLN-01 | GALLANSTOWN 110 kV A1 | bar: Su 7
TO-25-110 kV B1 @ GLN-01 | GALLANSTOWN 110 kV B1 | bar: Su 7
TO-25-GLN-110K1-03 | GALLANSTOWN 110K1 | bar: Su 7
TO-25-GLN-PLA-1-03 | GALLANSTOWN PLATIN | bar: Su 7
TO-25-110 kV A2 @ SNU-02 | SNUGBOROUGH 110 kV A2 | bar: Su 7
TO-25-110 kV B2 @ SNU-03 | SNUGBOROUGH 110 kV B2 | bar: Su 7
TO-25-SNU-110K2-04 | SNUGBOROUGH 110K2 | bar: Su 7
TO-25-SNU-110SA1-2CB-05 | SNUGBOROUGH 110SA1-2CB | bar: Su 7
TO-25-SNU-110SB1-2CB-05 | SNUGBOROUGH 110SB1-2CB | bar: Su 7
TO-25-MAY-TEN-1-01 | MAYNOOTH TIMAHOE | bar: Su 7; Week 50 We 10
TO-25-DRY-GOR-1-05 | DRYBRIDGE GORMAN | bar: Su 7; Week 50 We 10 to Week 50 Th 11
TO-25-110 kV A2 @ GOR-01 | GORMAN 110 kV A2 | bar: Su 7; Week 50 We 10 to Week 50 Th 11
TO-25-110 kV B2 @ GOR-01 | GORMAN 110 kV B2 | bar: Su 7; Week 50 We 10 to Week 50 Th 11
TO-25-RRU-SKL-1-03 | RATRUSSAN SHANKILL | bar: Week 50 Fr 12
TO-25-220 kV A3 @ CKM GIS-03 | CARRICKMINES GIS 220 kV A3 | bar: Su 7; Week 50 We 10 to Week 50 Fr 12
TO-25-220 kV B3 @ CKM GIS-03 | CARRICKMINES GIS 220 kV B3 | bar: Su 7; Week 50 We 10 to Week 50 Fr 12
TO-25-CKM GIS-220K3-04 | CARRICKMINES GIS 220K3 | bar: Su 7; Week 50 We 10 to Week 50 Fr 12
TO-25-CKM GIS-220SA1-3CB-05 | CARRICKMINES GIS 220SA1-3CB | bar: Su 7; Week 50 We 10 to Week 50 Fr 12
TO-25-CKM GIS-220SB1-3CB-03 | CARRICKMINES GIS 220SB1-3CB | bar: Su 7; Week 50 We 10 to Week 50 Fr 12
TO-25-CKM GIS-R2001-01 | CARRICKMINES GIS R2001 | bar: Su 7; Week 50 We 10 to Week 50 Fr 12
TO-25-FIN-SHL-1-03 | FINGLAS SHELLYBANKS | bar: Su 7; Week 50 We 10 to Week 50 Fr 12
TO-25-220 kV A2 @ WOO-10 | WOODLAND 220 kV A2 | bar: Su 7; Week 50 We 10 to Week 50 Fr 12
TO-25-220 kV B2 @ WOO-08 | WOODLAND 220 kV B2 | bar: Su 7; Week 50 We 10 to Week 50 Fr 12
TO-25-PHT-PLS-1-01 | PHILIPSTOWN PORTLAOISE | bar: Week 50 Sa 13 to Week 50 Su 14
Outages commencing/returning in Week 51
OUTAGE ID | PLANT | Week 50 Mo 8: Week 50; Week 51 Mo 15: Week 51
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22
TO-25-ARV-SKL-2-02 | ARVA SHANKILL 2 | bar: Week 51 Mo 15 to Week 51 We 17
TO-25-220 kV A1 @ BYH-03 | BALLYNAHULLA 220 kV A1 | bar: Week 51 Mo 15 to Week 51 Th 18
TO-25-220 kV B1 @ BYH-03 | BALLYNAHULLA 220 kV B1 | bar: Week 51 Mo 15 to Week 51 Th 18
TO-25-BYH-220K1-01 | BALLYNAHULLA 220K1 | bar: Week 51 Mo 15 to Week 51 Th 18
TO-25-BYH-220SA1-2CB-03 | BALLYNAHULLA 220SA1-2CB | bar: Week 51 Mo 15 to Week 51 Th 18
TO-25-BYH-220SB1-2CB-03 | BALLYNAHULLA 220SB1-2CB | bar: Week 51 Mo 15 to Week 51 Th 18
Report covers outages commencing/returning/spanning the period: 08/12/2025 - 21/12/2025
Outages commencing/returning in Week 51
OUTAGE ID | PLANT | Week 50 Mo 8: Week 50; Week 51 Mo 15: Week 51
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22
TO-25-110 kV A2 @ LOU-01 | LOUTH 110 kV A2 | bar: Su 7 to Week 51 Mo 15
TO-25-110 kV B2 @ LOU-01 | LOUTH 110 kV B2 | bar: Su 7 to Week 51 Mo 15
TO-25-FIN-NW-1-06 | FINGLAS NORTH WALL | bar: Week 51 Tu 16
TO-25-GOR-NAV-1-01 | GORMAN NAVAN 1 | bar: Week 51 Tu 16
TO-25-DSN-MAY-2-01 | DUNSTOWN MAYNOOTH 2 | bar: Week 51 Tu 16 to Week 51 We 17
TO-25-220 kV A2 @ MAY-02 | MAYNOOTH 220 kV A2 | bar: Week 51 Tu 16 to Week 51 We 17
TO-25-DER-KIN-1-02 | DERRYIRON KINNEGAD | bar: Week 51 Tu 16 to Week 51 Th 18
TO-25-KIN-110SA1-2CB-01 | KINNEGAD 110SA1-2CB | bar: Week 51 Tu 16 to Week 51 Th 18
TO-25-KIN-T101-01 | KINNEGAD T101 | bar: Week 51 Tu 16 to Week 51 Th 18
TO-25-WOO-T4202-05 | WOODLAND T4202 | bar: Su 7 to Week 51 Tu 16
TO-25-400 kV A2 @ WOO-03 | WOODLAND 400 kV A2 | bar: Week 51 We 17 to Week 51 Fr 19
TO-25-WOO-T4204-07 | WOODLAND T4204 | bar: Week 51 We 17 to Week 51 Fr 19
TO-25-MAY-SH-1-03 | MAYNOOTH SHANNONBRIDGE | bar: Su 7 to Week 51 We 17
TO-25-NEW-PLS-1-03 | NEWBRIDGE PORTLAOISE | bar: Su 7 to Week 51 We 17
TO-25-220 kV A2 @ CRU-02 | CRUISERATH 220 kV A2 | bar: Week 51 Th 18 to Week 51 Fr 19
TO-25-220 kV B2 @ CRU-02 | CRUISERATH 220 kV B2 | bar: Week 51 Th 18 to Week 51 Fr 19
TO-25-CRU-220K2-03 | CRUISERATH 220K2 | bar: Week 51 Th 18 to Week 51 Fr 19
TO-25-CRU-SA1-2CB-03 | CRUISERATH 220SA1-2CB | bar: Week 51 Th 18 to Week 51 Fr 19
TO-25-CRU-SB1-2CB-03 | CRUISERATH 220SB1-2CB | bar: Week 51 Th 18 to Week 51 Fr 19
TO-25-KIN-MUL-1-01 | KINNEGAD MULLINGAR | bar: Su 7 to Week 51 Th 18
TO-25-CRU-T224-01 | CRUISERATH T224 | bar: Su 7 to Week 51 Fr 19
TO-25-220 kV A2 @ LOU-11 | LOUTH 220 kV A2 | bar: Su 7 to Week 51 Fr 19
Outages spanning Weeks 50-51
OUTAGE ID | PLANT | Week 50 Mo 8: Week 50; Week 51 Mo 15: Week 51
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22
TO-25-ATH-M/CAP1-06 | ATHLONE M/CAP1
TO-25-CSH-T2102-04 | CASHLA T2102
TO-25-CBR-CAP2-03 | CASTLEBAR CAP2
TO-25-CBR-SVC-01 | CASTLEBAR SVC
TO-25-DND-T121-01 | DARNDALE T121
TO-25-110 kV B1/B2/B3 @ FIN-01 | FINGLAS 110 kV B1/B2/B3
TO-25-FIN-110K1-2-02 | FINGLAS 110K1-2
TO-25-FIN-110K2-3-04 | FINGLAS 110K2-3
TO-25-FIN-FIN GIS-1-02 | FINGLAS FINGLAS GIS 1
TO-25-GGO-220K1-2-01 | GLANAGOW 220K1-2
TO-25-GI GIS-220SA1-2CB-02 | GREAT ISLAND GIS 220SA1-2CB
TO-25-GI-T141-01 | GREAT ISLAND T141
TO-25-MUL-CAP2-01 | MULLINGAR CAP2
TO-25-PB-R2001-01 | POOLBEG R2001
TO-25-SKL-M/CAP2-03 | SHANKILL M/CAP2
TO-25-TB-T101-03 | TARBERT T101
TO-25-TB-T2003-01 | TARBERT T2003
TO-25-TB-T2004-01 | TARBERT T2004

## Wk 52
Report covers outages commencing/returning/spanning the period: 22/12/2025 - 28/12/2025
Outages spanning Week 52
OUTAGE ID | PLANT |  | Week 52
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 15
Outages spanning Week 52
OUTAGE ID | PLANT | Week 52 Mo 22: Week 52
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 15
TO-25-ATH-M/CAP1-06 | ATHLONE M/CAP1
TO-25-CSH-T2102-04 | CASHLA T2102
TO-25-CBR-CAP2-03 | CASTLEBAR CAP2
TO-25-CBR-SVC-01 | CASTLEBAR SVC
TO-25-DND-T121-01 | DARNDALE T121
TO-25-110 kV B1/B2/B3 @ FIN-01 | FINGLAS 110 kV B1/B2/B3
TO-25-FIN-110K1-2-02 | FINGLAS 110K1-2
TO-25-FIN-110K2-3-04 | FINGLAS 110K2-3
TO-25-FIN-FIN GIS-1-02 | FINGLAS FINGLAS GIS 1
TO-25-GGO-220K1-2-01 | GLANAGOW 220K1-2
TO-25-GI GIS-220SA1-2CB-02 | GREAT ISLAND GIS 220SA1-2CB
TO-25-GI-T141-01 | GREAT ISLAND T141
TO-25-MUL-CAP2-01 | MULLINGAR CAP2
TO-25-PB-R2001-01 | POOLBEG R2001
TO-25-SKL-M/CAP2-03 | SHANKILL M/CAP2
TO-25-TB-T101-03 | TARBERT T101
TO-25-TB-T2003-01 | TARBERT T2003
TO-25-TB-T2004-01 | TARBERT T2004