## Cover
Transmission Infrastructure
Delivery Report
Q1 2026
Disclamer - The TID has been produced by EirGrid and is undergoing further reivew by ESB Networks in line with established goverance processes.

## 1 - TID Report
Transmission Infrastructure Delivery Update Report
2026-03-31
CP Number | Project Name | County | Portfolio | Project Driver | Voltage (kV) | Stage | Capital Approval | PA Signed | First Significant EI | Final EI | CA Current Year | PA Current Year | FSEI Current Year | FEI Current Year
CP0466 | North South 400 kV Interconnector - RoI | Meath | Priority | System Reinforcement | 400 | Pre PA | 2016-09-21 |  | 2028-12-20 | 2031-10-06 | 2016 |  | 2028 | 2031
CP0585 | Laois Kilkenny (Coolnabacky) 400 kV Station - New Station & Associated Lines & Station Works | Laois | Priority | System Reinforcement | 400 | Post PA | 2008-04-16 | 2016-06-17 |  | 2027-06-30 | 2008 | 2016 |  | 2027
CP0799 | Louth 220 kV Station Refurbishment | Louth | Priority | Asset Refurbishment | 220 | Post PA | 2013-09-25 | 2020-03-12 | 2025-10-10 | 2032-12-31 | 2013 | 2020 | 2025 | 2032
CP0808 | Maynooth 220 kV Station Reconfiguration | Kildare | Priority | System Reinforcement | 220 | Post PA | 2021-03-16 | 2024-12-05 | 2028-12-20 | 2031-12-31 | 2021 | 2024 | 2028 | 2031
CP0816 | North Connacht 110 kV Project | Galway | Priority | System Reinforcement | 110 | Post PA | 2018-09-12 | 2023-12-20 | 2028-12-20 | 2028-12-31 | 2018 | 2023 | 2028 | 2028
CP0866 | Great Island - Kellis 220 kV Line Uprate | Wexford | Priority | System Reinforcement | 220 | Post PA | 2022-11-16 | 2025-12-18 | 2027-11-30 | 2029-12-31 | 2022 | 2025 | 2027 | 2029
CP0966 | Kildare Meath Grid Reinforcement | Kildare | Priority | System Reinforcement | 400 | Post PA | 2021-03-24 | 2025-09-19 | 2029-12-20 | 2029-12-21 | 2021 | 2025 | 2029 | 2029
CP0967 | Moneypoint 400 kV Series Capacitor | Clare | Priority | System Reinforcement | 400 | Pre PA | 2015-08-31 | 2026-09-30 | 2030-12-31 | 2030-12-31 | 2015 | 2026 | 2030 | 2030
CP0968 | Dunstown 400 kV Series Capacitor | Kildare | Priority | System Reinforcement | 400 | Post PA | 2016-06-15 | 2023-12-13 | 2027-08-20 | 2027-12-31 | 2016 | 2023 | 2027 | 2027
CP0969 | Oldstreet-Woodland 400 kV Series Capacitor | Westmeath | Priority | System Reinforcement | 400 | Post PA | 2016-06-15 | 2023-12-13 | 2028-08-20 | 2028-12-31 | 2016 | 2023 | 2028 | 2028
CP0970 | Cross Shannon 400 kV Cable | Kerry | Priority | System Reinforcement | 400 | Post PA | 2016-09-21 | 2021-12-16 | 2028-12-20 | 2028-12-31 | 2016 | 2021 | 2028 | 2028
CP0982 | Flagford Sligo Capacity Needs | Roscommon | Priority | System Reinforcement | 110 | Pre PA | 2025-12-19 | 2029-03-14 | 2030-12-31 | 2032-12-31 | 2025 | 2029 | 2030 | 2032
CP1021 | East Meath - North Dublin Reinforcement | Dublin | Priority | System Reinforcement | 400 | Post PA | 2022-06-07 | 2025-09-19 | 2029-12-20 | 2029-12-20 | 2022 | 2025 | 2029 | 2029
CP1023 | Letterkenny station redevelopment | Donegal | Priority | System Reinforcement | 110 | Pre PA | 2021-06-17 | 2026-12-04 | 2029-11-01 | 2031-12-31 | 2021 | 2026 | 2029 | 2031
CP1100 | Finglas - North Wall Cable Replacement | Dublin | Priority | Asset Refurbishment | 220 | Post PA | 2022-06-28 | 2024-12-19 |  | 2029-12-31 | 2022 | 2024 |  | 2029
CP1146 | Carrickmines - Poolbeg 220 kV Cable Replacement | Dublin | Priority | Asset Refurbishment | 220 | Pre PA | 2021-12-16 | 2028-12-15 | 2030-01-03 | 2031-12-31 | 2021 | 2028 | 2030 | 2031
CP1150 | Inchicore - Poolbeg 2 220 kV Cable Replacement | Dublin | Priority | Asset Refurbishment | 220 | Pre PA | 2021-12-20 | 2027-09-14 | 2031-12-19 | 2031-12-20 | 2021 | 2027 | 2031 | 2031
CP1157 | Inchicore - Poolbeg 1 220 kV Cable Replacement | Dublin | Priority | Asset Refurbishment | 220 | Pre PA | 2021-12-20 | 2027-09-14 | 2031-12-19 | 2031-12-19 | 2021 | 2027 | 2031 | 2031
CP1190 | Poolbeg 220 kV Station | Dublin | Priority | System Reinforcement | 220 | Post PA | 2021-12-16 | 2024-12-06 | 2028-12-20 | 2030-12-31 | 2021 | 2024 | 2028 | 2030
CP1194 | Woodland 400 kV Station Redevelopment | Meath | Priority | System Reinforcement | 400 | Post PA | 2022-03-21 | 2023-12-14 |  | 2032-12-31 | 2022 | 2023 |  | 2032
CP1196 | Arklow - Ballybeg - Carrickmines 110 kV capacity Needs | Wicklow | Priority | System Reinforcement | 220 | Pre PA | 2024-05-16 | 2028-09-12 | 2028-09-07 | 2032-09-19 | 2024 | 2028 | 2028 | 2032
CP1213 | Belcamp 220 kV Busbar Extension | Dublin | Priority | Diversion | 220 | Post PA | 2021-12-15 | 2025-03-28 | 2029-04-20 | 2029-05-28 | 2021 | 2025 | 2029 | 2029
CP1214 | Fingal to East Meath Grid Reinforcement | Meath | Priority | System Reinforcement | 400 | Pre PA | 2024-12-17 | 2028-03-07 | 2031-04-30 | 2031-12-19 | 2024 | 2028 | 2031 | 2031
CP1215 | Knockraha station Celtic IC Non contested works | Cork | Priority | System Reinforcement | 220 | Post PA | 2022-02-23 | 2023-12-06 | 2026-06-22 | 2026-11-26 | 2022 | 2023 | 2026 | 2026
CP1216 | Poolbeg - North Wall 220 kV Cable Replacement | Dublin | Priority | Asset Refurbishment | 220 | Pre PA | 2022-05-31 | 2027-06-04 |  | 2031-06-30 | 2022 | 2027 |  | 2031
CP1226 | Kildare Dublin Grid Reinforcement | Kildare | Priority | System Reinforcement | 220 | Pipeline |  |  | 2033-04-20 | 2034-04-20 |  |  | 2033 | 2034
CP1233 | Donegal - Srananagh Corridor | Donegal | Priority | System Reinforcement | 220 | Pre PA | 2025-12-17 | 2029-12-12 | 2033-12-31 | 2033-12-31 | 2025 | 2029 | 2033 | 2033
CP1235 | Louth - Woodland 220 kV Uprate | Louth | Priority | Asset Refurbishment | 220 | Post PA | 2022-04-28 | 2024-12-18 | 2025-11-06 | 2029-12-03 | 2022 | 2024 | 2025 | 2029
CP1273 | Dublin Central Bulk Supply Point 220kV Substation | Dublin | Priority | System Reinforcement | 220 | Pre PA | 2024-09-25 | 2026-09-29 | 2030-02-01 | 2031-12-01 | 2024 | 2026 | 2030 | 2031
CP0624 | Killonan 220 kV Station Refurbishment - Killonan Station Works | Limerick | Portfolio | Asset Refurbishment | 220 | Post PA | 2011-09-30 | 2019-04-01 | 2026-11-24 | 2028-07-20 | 2011 | 2019 | 2026 | 2028
CP0644 | Bracklone 110 kV Station - DSO | Offaly | Portfolio | DSO | 110 | Post PA | 2020-03-19 | 2022-06-01 |  | 2026-05-27 | 2020 | 2022 |  | 2026
CP0646 | Finglas 110 kV Station Redevelopment | Dublin | Portfolio | Asset Refurbishment | 110 | Post PA | 2009-08-28 | 2012-08-24 | 2026-09-18 | 2026-09-29 | 2009 | 2012 | 2026 | 2026
CP0692 | Inchicore - 220 kV GIS Station Upgrade | Dublin | Portfolio | Asset Refurbishment | 220 | Post PA | 2016-09-21 | 2019-03-20 | 2026-10-22 | 2029-12-20 | 2016 | 2019 | 2026 | 2029
CP0693 | Baroda 110 kV station - 2 x110 kV Trafo Bays DSO | Waterford | Portfolio | DSO | 110 | Post PA | 2019-06-14 | 2020-01-10 |  | 2028-03-24 | 2019 | 2020 |  | 2028
CP0741 | Trabeg 110 kV station - uprate 2 x 110 kV transformer bays and control room extension DSO | Mayo | Portfolio | DSO | 110 | Post PA | 2020-06-03 | 2021-04-29 |  | 2027-02-26 | 2020 | 2021 |  | 2027
CP0749 | Richardstown 220kV Station (Oriel Offshore WF) | Cork | Portfolio | Customer Connection | 110 | Pre PA | 2022-03-25 | 2028-01-25 |  |  | 2022 | 2028
CP0792 | Finglas 220 kV Reconfiguration Project | Dublin | Portfolio | Asset Refurbishment | 220 | Post PA | 2015-04-22 | 2018-03-11 |  | 2027-12-20 | 2015 | 2018 |  | 2027
CP0796 | Knockraha station & installation of additional couplers | Cork | Portfolio | System Reinforcement | 220 | Post PA | 2016-09-21 | 2016-09-30 | 2022-02-02 | 2033-06-30 | 2016 | 2016 | 2022 | 2033
CP0823 | Maynooth - Turlough Hill 220 kV line refurbishment | Kildare | Portfolio | Asset Refurbishment | 220 | Pre PA | 2017-06-30 | 2026-06-04 | 2031-11-10 | 2033-09-02 | 2017 | 2026 | 2031 | 2033
CP0835 | Coolnabacky - Portlaoise 110 kV line uprate | Laois | Portfolio | System Reinforcement | 110 | Post PA | 2018-05-30 | 2025-10-24 | 2026-10-06 | 2026-10-06 | 2018 | 2025 | 2026 | 2026
CP0841 | Arva - Carrick-on-Shannon 110 kV line uprate | Leitrim | Portfolio | System Reinforcement | 110 | Post PA | 2020-05-21 | 2021-12-15 | 2026-07-22 | 2027-11-29 | 2020 | 2021 | 2026 | 2027
CP0867 | Flagford - Louth 220 kV Line Refurbishment | Roscommon | Portfolio | Asset Refurbishment | 220 | Post PA | 2015-04-20 | 2020-04-30 | 2027-05-31 | 2027-11-29 | 2015 | 2020 | 2027 | 2027
CP0868 | Knockraha - Raffeen 220 kV line refurbishment | Cork | Portfolio | Asset Refurbishment | 220 | Post PA | 2015-10-30 | 2019-09-25 |  |  | 2015 | 2019
CP0873 | Dunstown - Moneypoint 400 kV Refurbishment | Kildare | Portfolio | Asset Refurbishment | 400 | Post PA | 2014-06-20 | 2019-12-05 | 2026-09-18 | 2027-11-30 | 2014 | 2019 | 2026 | 2027
CP0901 | Kilbarry - Knockraha 110 kV No 2 Line Refurbishment | Cork | Portfolio | Asset Refurbishment | 110 | Post PA | 2020-05-13 | 2022-10-03 | 2027-11-10 | 2030-09-05 | 2020 | 2022 | 2027 | 2030
CP0907 | Dalton 110 kV Busbar | Westmeath | Portfolio | System Reinforcement | 110 | Post PA | 2021-10-01 | 2023-09-06 | 2025-08-27 | 2029-06-21 | 2021 | 2023 | 2025 | 2029
CP0917 | Prospect Tarbert 220 kV Cable Replacement Project | Galway | Portfolio | Asset Refurbishment | 220 | Pre PA | 2021-06-16 | 2026-12-02 | 2027-07-15 | 2027-09-20 | 2021 | 2026 | 2027 | 2027
CP0919 | Lanesboro 110 kV Station Redevelopment Project | Longford | Portfolio | System Reinforcement | 110 | Post PA | 2017-12-28 | 2020-06-30 | 2027-03-12 | 2029-12-20 | 2017 | 2020 | 2027 | 2029
CP0949 | Kilnap 110 kV GIS Station | Cork | Portfolio | System Reinforcement | 110 | Post PA | 2017-02-14 | 2021-04-14 |  | 2027-03-31 | 2017 | 2021 |  | 2027
CP0973 | Knockraha Short Circuit Rating Mitigation | Cork | Portfolio | System Reinforcement | 220 | Post PA | 2016-11-03 | 2019-06-21 | 2025-10-10 | 2032-12-20 | 2016 | 2019 | 2025 | 2032
CP0983 | Point on Wave Controller for Glanagow 220 kV Station | Cork | Portfolio | System Reinforcement | 220 | Post PA | 2016-08-04 | 2017-05-23 | 2027-03-01 | 2027-03-01 | 2016 | 2017 | 2027 | 2027
CP0984 | Belcamp Shellybanks 220 kV Cable | Dublin | Portfolio | System Reinforcement | 220 | Post PA | 2016-07-01 | 2020-07-15 |  | 2026-11-25 | 2016 | 2020 |  | 2026
CP1000 | Lanesboro - Mullingar 110 kV Thermal Uprate | Westmeath | Portfolio | System Reinforcement | 110 | Post PA | 2021-01-29 | 2024-09-24 | 2027-11-26 | 2029-09-05 | 2021 | 2024 | 2027 | 2029
CP1001 | Corduff - Finglas 1 & 2 220 kV line refurbishment | Dublin | Portfolio | Asset Refurbishment | 220 | Post PA | 2022-11-10 | 2024-03-28 | 2027-10-29 | 2027-10-29 | 2022 | 2024 | 2027 | 2027
CP1002 | Cushaling - Newbridge 110 kV Thermal Uprate | Offaly | Portfolio | Asset Refurbishment | 110 | Post PA | 2023-03-30 | 2025-05-30 | 2029-08-22 | 2029-11-30 | 2023 | 2025 | 2029 | 2029
CP1003 | Cushaling - Portlaoise 110 kV line uprate | Offaly | Portfolio | Asset Refurbishment | 110 | Pre PA | 2023-07-05 | 2026-06-05 | 2026-12-12 | 2030-08-13 | 2023 | 2026 | 2026 | 2030
CP1032 | Cashla 220 kV Station Sprecher & Schuh CB Replacement | Galway | Portfolio | Asset Refurbishment | 220 | Post PA | 2018-06-30 | 2019-07-11 |  |  | 2018 | 2019
CP1048 | Power Flow Control Scheme | Donegal | Portfolio | System Reinforcement | 110 | Pre PA | 2021-02-04 | 2026-09-11 | 2031-07-28 | 2031-08-01 | 2021 | 2026 | 2031 | 2031
CP1060 | Loughteague 110 kV solar farm | Laois | Portfolio | Customer Connection | 110 | Post PA | 2018-09-18 | 2021-11-05 | 2027-10-19 | 2027-12-20 | 2018 | 2021 | 2027 | 2027
CP1064 | Finglas Pantograph Replacement Project | Dublin | Portfolio | Asset Refurbishment | 220 | Post PA | 2019-12-20 | 2020-11-12 |  | 2027-12-20 | 2019 | 2020 |  | 2027
CP1069 | Ballinknockane 110 kV Station (Ballinknockane Solar Farm) | Kerry | Portfolio | Customer Connection | 110 | Post PA | 2019-05-16 | 2020-12-24 | 2026-11-24 | 2026-11-25 | 2019 | 2020 | 2026 | 2026
CP1073 | Croaghaun West 110 kV Station (Oweninny 3 Wind Farm) | Mayo | Portfolio | Customer Connection | 110 | Post PA | 2020-07-02 | 2025-05-11 | 2026-06-19 | 2027-07-30 | 2020 | 2025 | 2026 | 2027
CP1084 | Lisdrumdoagh 110 kV Battery Storage | Monaghan | Portfolio | Customer Connection | 110 | Post PA | 2020-02-06 | 2021-05-26 |  |  | 2020 | 2021
CP1086 | Dunstown T4201 and Woodland T4201 Transformer replacement | Kildare | Portfolio | Asset Refurbishment | 400 | Post PA | 2023-05-01 | 2024-12-17 | 2027-12-06 | 2028-10-30 | 2023 | 2024 | 2027 | 2028
CP1092 | New 400 kV Strategic Spare Transformer | Kildare | Portfolio | System Reinforcement | 400 | Post PA | 2020-01-29 | 2022-12-15 | 2026-11-25 | 2026-11-25 | 2020 | 2022 | 2026 | 2026
CP1096 | Transformer protection upgrade, 6 Stations | Louth | Portfolio | Asset Refurbishment | 220 | Post PA | 2020-02-10 | 2020-10-02 | 2022-07-25 | 2028-05-29 | 2020 | 2020 | 2022 | 2028
CP1109 | Gorman and Connected Stations 220-110 kV Protection Upgrade | Meath | Portfolio | Asset Refurbishment | 220 | Post PA | 2020-05-13 | 2021-06-25 | 2024-03-01 | 2027-12-22 | 2020 | 2021 | 2024 | 2027
CP1111 | Ballydine, Cahir and Connected Stations 110 kV Protection Upgrade | Tipperary | Portfolio | Asset Refurbishment | 110 | Post PA | 2020-05-21 | 2021-07-18 | 2025-07-15 | 2028-03-10 | 2020 | 2021 | 2025 | 2028
CP1112 | Limerick and Connected Stations 110 kV Protection Upgrade | Limerick | Portfolio | Asset Refurbishment | 110 | Post PA | 2020-05-21 | 2023-12-14 | 2027-08-30 | 2030-03-15 | 2020 | 2023 | 2027 | 2030
CP1114 | Platin and Connected Stations 110 kV Protection Upgrade | Meath | Portfolio | Asset Refurbishment | 110 | Post EI | 2020-05-13 | 2021-08-18 | 2024-03-01 | 2026-03-06 | 2020 | 2021 | 2024 | 2026
CP1115 | Drybridge and Connected Stations 110 kV Protection Upgrade | Meath | Portfolio | Asset Refurbishment | 110 | Post PA | 2020-05-13 | 2021-04-16 | 2024-03-01 | 2027-12-31 | 2020 | 2021 | 2024 | 2027
CP1116 | Tipperary, Cahir and Connected Stations 110 kV Protection Upgrade | Tipperary | Portfolio | Asset Refurbishment | 110 | Post PA | 2020-05-13 | 2021-07-14 | 2023-06-30 | 2030-11-20 | 2020 | 2021 | 2023 | 2030
CP1121 | Arklow Lodgewood Line Uprate | Wicklow | Portfolio | Asset Refurbishment | 220 | Pre PA | 2025-02-26 | 2026-12-22 | 2028-09-14 | 2029-09-14 | 2025 | 2026 | 2028 | 2029
CP1122 | Physical Security of Transmission Stations - Dublin Region | Dublin | Portfolio | System Reinforcement | 220 | Post PA | 2020-09-01 | 2023-12-08 |  |  | 2020 | 2023
CP1123 | Physical Security of Transmission Stations - South Region | Wicklow | Portfolio | System Reinforcement | 220 | Post PA | 2021-05-07 | 2023-12-08 |  |  | 2021 | 2023
CP1124 | Physical Security of Transmission Stations - North Region | Leitrim | Portfolio | System Reinforcement | 220 | Post PA | 2021-06-11 | 2023-12-08 |  |  | 2021 | 2023
CP1125 | Physical Security of Transmission Stations - Central Region | Kildare | Portfolio | System Reinforcement | 220 | Post PA | 2021-07-14 | 2023-12-08 |  |  | 2021 | 2023
CP1126 | Mully Graffy 110 kV Station (Mully Graffy Windfarm) | Donegal | Portfolio | Customer Connection | 110 | Pre PA | 2020-08-06 | 2027-11-30 |  |  | 2020 | 2027
CP1128 | Ballynanelagh 110kV Substation (Ballyvatta solar farm) | Cork | Portfolio | Customer Connection | 110 | Pre PA | 2021-11-04 | 2026-11-09 |  |  | 2021 | 2026
CP1137 | Carlow, Kellis 110 kV Protection Upgrade | Carlow | Portfolio | Asset Refurbishment | 110 | Post PA | 2020-10-01 | 2021-09-01 | 2026-10-05 | 2028-11-10 | 2020 | 2021 | 2026 | 2028
CP1139 | Sligo & Srananagh 220 & 110 kV Protection upgrade | Sligo | Portfolio | Asset Refurbishment | 220 | Post PA | 2020-10-01 | 2021-08-17 | 2025-11-10 | 2027-11-30 | 2020 | 2021 | 2025 | 2027
CP1140 | Athy, Carlow and Connected Stations 110 kV Protection Upgrade | Kildare | Portfolio | Asset Refurbishment | 110 | Post PA | 2020-10-01 | 2021-07-16 | 2026-06-02 | 2028-02-22 | 2020 | 2021 | 2026 | 2028
CP1141 | Kellis Station 220 kV & 110 kV Protection Upgrade | Carlow | Portfolio | Asset Refurbishment | 220 | Post PA | 2020-10-01 | 2021-09-01 | 2026-04-16 | 2027-11-10 | 2020 | 2021 | 2026 | 2027
CP1142 | Firlough 110 kV Station (Firlough WF) | Mayo | Portfolio | Customer Connection | 110 | Pre PA | 2021-02-04 |  |  |  | 2021
CP1143 | Derrylahan 110 kV Station (Blackwater Bog Solar) | Offaly | Portfolio | Customer Connection | 110 | Pre PA | 2021-05-06 |  |  |  | 2021
CP1152 | Arva and Connected Stations 110 kV Protection Upgrade | Roscommon | Portfolio | Asset Refurbishment | 110 | Post PA | 2020-11-12 | 2021-09-01 | 2024-03-01 | 2028-06-15 | 2020 | 2021 | 2024 | 2028
CP1159 | Cullenagh and connected stations protection upgrade | Kerry | Portfolio | Asset Refurbishment | 220 | Post PA | 2020-12-04 | 2021-11-04 |  | 2027-11-29 | 2020 | 2021 |  | 2027
CP1161 | Cathaleens Fall and connected stations 110 kV protection upgrade | Cavan | Portfolio | Asset Refurbishment | 110 | Post PA | 2020-12-04 | 2021-12-16 |  | 2028-08-18 | 2020 | 2021 |  | 2028
CP1162 | Irishtown, Shellybanks and connected stations 220 kV protection upgrade | Dublin | Portfolio | Asset Refurbishment | 220 | Post PA | 2021-02-04 | 2021-12-16 |  | 2027-12-31 | 2021 | 2021 |  | 2027
CP1163 | Butlerstown, Killoteran & Waterford 110 kV protection upgrade | Kilkenny | Portfolio | Asset Refurbishment | 110 | Post PA | 2021-02-04 | 2021-11-04 | 2025-05-30 | 2029-05-08 | 2021 | 2021 | 2025 | 2029
CP1164 | West Cork 110 kV protection upgrade | Cork | Portfolio | Asset Refurbishment | 110 | Post PA | 2021-02-04 | 2022-03-07 | 2026-08-21 |  | 2021 | 2022 | 2026
CP1166 | Gorman - Platin 110 kV line uprate | Meath | Portfolio | Customer Connection | 110 | Post PA | 2021-03-18 | 2025-08-25 | 2026-04-15 | 2026-12-18 | 2021 | 2025 | 2026 | 2026
CP1168 | Cashla-Salthill 110 kV Thermal Uprate | Galway | Portfolio | System Reinforcement | 110 | Post PA | 2021-03-18 | 2025-10-17 | 2026-10-15 | 2027-07-16 | 2021 | 2025 | 2026 | 2027
CP1170 | Newbridge - Portlaoise 110 kV Line uprate | Kildare | Portfolio | System Reinforcement | 110 | Post PA | 2021-08-05 | 2025-06-19 | 2025-12-17 | 2027-04-23 | 2021 | 2025 | 2025 | 2027
CP1172 | Crane - Wexford 110 kV Line uprate | Wexford | Portfolio | System Reinforcement | 110 | Post PA | 2021-06-17 | 2023-10-09 | 2025-09-19 | 2026-04-29 | 2021 | 2023 | 2025 | 2026
CP1173 | Glencloosagh Phase 1 - Rotating Stabiliser | Kerry | Portfolio | Customer Connection | 110 | Post PA | 2021-05-06 | 2025-10-24 | 2026-11-19 | 2026-11-19 | 2021 | 2025 | 2026 | 2026
CP1177 | Whitegate 110 kV Station Refurbishment Project | Cork | Portfolio | Asset Refurbishment | 110 | Pre PA | 2025-09-17 | 2029-08-20 | 2031-07-29 | 2034-04-04 | 2025 | 2029 | 2031 | 2034
CP1182 | Transformer Restoration Project | Galway | Portfolio | Asset Refurbishment | 220 | Post PA | 2023-03-31 | 2025-03-05 | 2027-05-21 | 2029-11-30 | 2023 | 2025 | 2027 | 2029
CP1183 | Mooretown 220 kV Station | Galway | Portfolio | Customer Connection | 220 | Post PA | 2022-04-06 | 2025-12-19 | 2028-03-31 | 2028-10-23 | 2022 | 2025 | 2028 | 2028
CP1186 | Agannygal, Ennis and connected stations 110 kV Protection Upgrade | Clare | Portfolio | Asset Refurbishment | 110 | Post PA | 2021-08-05 | 2022-09-08 | 2026-11-30 | 2027-01-04 | 2021 | 2022 | 2026 | 2027
CP1188 | Kilcarbery 110 kV Station (Profile Park Power Co 1 Ltd) | Donegal | Portfolio | Customer Connection | 110 | Post PA | 2021-07-08 | 2023-12-12 | 2026-09-24 | 2026-09-25 | 2021 | 2023 | 2026 | 2026
CP1191 | Cashla-Galway 110 kV cot 1 Line uprate | Galway | Portfolio | System Reinforcement | 110 | Pre PA | 2022-11-21 | 2027-03-30 | 2027-12-30 | 2028-12-30 | 2022 | 2027 | 2027 | 2028
CP1195 | Turlough Hill 220 kV Station Refurbishment | Galway | Portfolio | Asset Refurbishment | 220 | Pre PA | 2023-09-06 | 2027-06-21 | 2028-09-20 | 2030-09-20 | 2023 | 2027 | 2028 | 2030
CP1197 | Dunstown Asset Replacements | Kildare | Portfolio | Asset Refurbishment | 400 | Post PA | 2021-12-31 | 2023-12-19 | 2026-09-18 | 2030-12-03 | 2021 | 2023 | 2026 | 2030
CP1198 | Barnakyle MIC Increase | Limerick | Portfolio | Customer Connection | 110 | Pre PA | 2022-10-27 |  |  |  | 2022
CP1199 | Derryiron - Thornsberry 110 kV Line Uprate | Offaly | Portfolio | System Reinforcement | 110 | Post PA | 2021-11-19 | 2023-12-20 | 2026-07-21 | 2027-10-25 | 2021 | 2023 | 2026 | 2027
CP1209 | Brown Boveri Circuit Breaker Replacements | Cork | Portfolio | Asset Refurbishment | 220 | Post PA | 2022-03-31 | 2023-12-20 | 2027-10-05 | 2028-12-01 | 2022 | 2023 | 2027 | 2028
CP1212 | Bandon Raffeen 110 kV circuit thermal capacity | Cork | Portfolio | System Reinforcement | 110 | Post PA | 2022-01-28 | 2024-09-05 | 2026-07-22 | 2029-07-11 | 2022 | 2024 | 2026 | 2029
CP1219 | Lickny 110 kV Station (Coole Wind Farm) | Westmeath | Portfolio | Customer Connection | 110 | Pre PA | 2022-02-01 |  |  |  | 2022
CP1221 | Mulgeeth 110 kV Station - Drehid Wind Farm | Kildare | Portfolio | Customer Connection | 110 | Pre PA | 2022-02-01 |  |  |  | 2022
CP1222 | Knockraha 220 kV Transformer Replacement | Cork | Portfolio | Asset Refurbishment | 220 | Post PA | 2022-01-19 | 2022-12-15 |  | 2027-12-22 | 2022 | 2022 |  | 2027
CP1223 | Bandon 110 kV Busbar Rating Needs | Cork | Portfolio | System Reinforcement | 110 | Post PA | 2023-05-03 | 2025-04-01 | 2026-11-11 | 2029-07-11 | 2023 | 2025 | 2026 | 2029
CP1224 | Lysaghtstown 110 kV Station | Cork | Portfolio | Customer Connection | 110 | Post PA | 2022-02-03 | 2023-03-02 |  |  | 2022 | 2023
CP1225 | Finglas - Corduff 220 kV Protection Upgrade | Dublin | Portfolio | Asset Refurbishment | 220 | Post PA | 2022-02-03 | 2022-12-13 |  | 2028-12-20 | 2022 | 2022 |  | 2028
CP1227 | Cashla and Connected Stations 220 kV & 110 kV Protection Upgrade | Galway | Portfolio | Asset Refurbishment | 220 | Post PA | 2022-02-02 | 2022-09-21 |  | 2027-11-30 | 2022 | 2022 |  | 2027
CP1228 | Shannonbridge and Connected Stations 220 kV & 110 kV Protection Upgrade | Offaly | Portfolio | Asset Refurbishment | 220 | Post PA | 2022-02-03 | 2022-09-26 | 2025-06-24 | 2027-08-26 | 2022 | 2022 | 2025 | 2027
CP1230 | Darndale 110kV Station Phase 2 (Amazon Web Services) | Dublin | Portfolio | Customer Connection | 110 | Post PA | 2022-06-17 | 2022-12-19 | 2026-09-30 | 2027-12-31 | 2022 | 2022 | 2026 | 2027
CP1237 | Ferry View 110 kV Station (Knockranny Wind Farm) | Galway | Portfolio | Customer Connection | 110 | Pre PA | 2022-07-07 |  |  |  | 2022
CP1238 | Arklow 220 kV Station Redevelopment | Wicklow | Portfolio | Asset Refurbishment | 220 | Pre PA | 2023-04-20 | 2026-09-08 | 2028-06-12 | 2032-06-08 | 2023 | 2026 | 2028 | 2032
CP1240 | Coumaclovane Solar Extension | Kerry | Portfolio | Customer Connection | 110 | Pre PA | 2022-08-31 |  |  |  | 2022
CP1241 | Belcamp BSP Transfer | Dublin | Portfolio | System Reinforcement | 220 | Post PA | 2022-09-01 | 2024-05-31 | 2026-08-06 | 2026-08-31 | 2022 | 2024 | 2026 | 2026
CP1242 | Great Island 220-110 kV transformer upgrades | Wexford | Portfolio | System Reinforcement | 220 | Post PA | 2022-12-07 | 2023-12-20 | 2026-11-03 | 2027-12-31 | 2022 | 2023 | 2026 | 2027
CP1244 | North Arklow Solar Plus Storage | Wicklow | Portfolio | Customer Connection | 110 | Post PA | 2022-10-06 | 2024-02-07 | 2026-06-30 | 2027-12-31 | 2022 | 2024 | 2026 | 2027
CP1245 | Castletreasure 110 kV Station (Ballinrea Solar Park) | Cork | Portfolio | Customer Connection | 110 | Post PA | 2022-09-09 | 2024-12-12 | 2026-10-21 | 2026-10-21 | 2022 | 2024 | 2026 | 2026
CP1246 | Coomnaclohy 110 kV Station (Knocknamork Wind and Solar Park) | Kerry | Portfolio | Customer Connection | 110 | Pre PA | 2022-07-07 | 2026-04-30 |  |  | 2022 | 2026
CP1247 | New Ballyvouskill 220-110 kV Transformer | Cork | Portfolio | System Reinforcement | 220 | Post PA | 2022-05-10 | 2023-08-28 | 2026-10-16 | 2026-12-23 | 2022 | 2023 | 2026 | 2026
CP1249 | Porterstown Battery 60MW Phase 2 | Kildare | Portfolio | Customer Connection | 110 | Post PA | 2022-06-01 | 2023-11-10 | 2027-08-23 | 2028-11-01 | 2022 | 2023 | 2027 | 2028
CP1251 | North Wall Life Extension Project | Dublin | Portfolio | Asset Refurbishment | 220 | Pre PA | 2024-07-03 | 2026-08-20 | 2031-07-12 | 2031-01-24 | 2024 | 2026 | 2031 | 2031
CP1257 | T-3 P485 Kilshane Power Station | Dublin | Portfolio | Customer Connection | 220 | Post PA | 2022-05-05 | 2025-12-12 | 2027-12-01 | 2027-12-01 | 2022 | 2025 | 2027 | 2027
CP1259 | Cuilleen 110kV Station (Greener Ideas) | Dublin | Portfolio | Customer Connection | 220 | Post PA | 2022-05-05 | 2024-03-06 | 2026-04-30 | 2026-09-30 | 2022 | 2024 | 2026 | 2026
CP1260 | Dennistown 110 kV Station (Tracystown Solar) | Roscommon | Portfolio | Customer Connection | 110 | Post PA | 2022-05-30 | 2024-07-16 | 2026-11-23 | 2026-11-23 | 2022 | 2024 | 2026 | 2026
CP1263 | Rappareehill 110 kV Station (Derryadd Wind Farm) | Wexford | Portfolio | Customer Connection | 110 | Pipeline
CP1264 | Rhode ESS (DSO) | Cork | Portfolio | DSO | 110 | Post PA | 2022-06-23 | 2023-09-01 | 2027-08-20 | 2027-12-20 | 2022 | 2023 | 2027 | 2027
CP1265 | Corkagh 110kV Station Phase 2 (Microsoft) | Dublin | Portfolio | Customer Connection | 110 | Post PA | 2022-07-26 | 2023-10-20 | 2025-11-21 | 2026-12-01 | 2022 | 2023 | 2025 | 2026
CP1266 | Ballyragget 1 (Parksgrove) - DSO Parksgrove SF | Kilkenny | Portfolio | DSO |  | Post PA | 2022-02-01 | 2023-03-01 | 2026-06-30 | 2026-09-01 | 2022 | 2023 | 2026 | 2026
CP1267 | Arklow 220kV - DSO Ballymanus WF | Wicklow | Portfolio | DSO | 220 | Post PA | 2022-09-30 | 2023-11-06 | 2026-07-24 | 2027-12-31 | 2022 | 2023 | 2026 | 2027
CP1268 | Dunfirth 110kV - DSO Dysart PV | Kildare | Portfolio | DSO | 110 | Post PA | 2022-09-30 | 2025-01-15 | 2026-07-06 | 2026-10-01 | 2022 | 2025 | 2026 | 2026
CP1275 | Cashla - Galway 110 kV Circuit 2 Uprate | Galway | Portfolio | System Reinforcement | 110 | Pre PA | 2022-11-21 | 2027-03-30 | 2027-12-30 | 2028-12-30 | 2022 | 2027 | 2027 | 2028
CP1276 | Cashla - Galway 110 kV Circuit 3 Uprate | Galway | Portfolio | System Reinforcement | 110 | Pre PA | 2022-11-21 | 2027-03-30 | 2027-12-30 | 2028-12-30 | 2022 | 2027 | 2027 | 2028
CP1280 | Ballyragget Future Proofed Cable | Kilkenny | Portfolio | Customer Connection | 110 | Post PA | 2022-11-22 | 2025-06-25 | 2026-06-30 | 2026-08-26 | 2022 | 2025 | 2026 | 2026
CP1281 | Batter Lane DSO Station | Dublin | Portfolio | DSO | 110 | Post PA | 2023-02-09 | 2024-11-20 | 2026-10-30 | 2026-10-30 | 2023 | 2024 | 2026 | 2026
CP1282 | Clogher-Drumkeen 110 kV Line Alteration | Kerry | Portfolio | Diversion | 110 | Pre PA | 2023-03-31 | 2029-12-14 | 2031-04-02 | 2032-10-19 | 2023 | 2029 | 2031 | 2032
CP1283 | Belcamp cables masterplan | Dublin | Portfolio | Diversion | 110 | Pre PA | 2024-10-02 | 2027-06-17 |  |  | 2024 | 2027
CP1284 | Walterstown 110kV Station DSO | Cork | Portfolio | DSO | 110 | Pre PA | 2024-01-19 | 2027-03-01 | 2029-07-10 | 2029-10-10 | 2024 | 2027 | 2029 | 2029
CP1285 | Barnahely - Raffeen No 2 110 kV Line | Cork | Portfolio | Customer Connection | 110 | Post PA | 2023-08-04 | 2024-04-16 | 2024-11-29 | 2028-11-24 | 2023 | 2024 | 2024 | 2028
CP1291 | Carlow 110 kV Station Busbar Thermal Capacity Need | Carlow | Portfolio | System Reinforcement | 110 | Post PA | 2023-06-07 | 2025-03-05 | 2027-06-11 | 2028-09-29 | 2023 | 2025 | 2027 | 2028
CP1296 | Rinawade 110 kV GIS Station (Liffey Park) | Kildare | Portfolio | Customer Connection | 110 | Post PA | 2023-10-02 | 2024-09-04 | 2026-10-01 | 2026-10-01 | 2023 | 2024 | 2026 | 2026
CP1297 | Glansillagh 220kV Station S | Kerry | Portfolio | Customer Connection | 220 | Pre PA | 2023-06-08 | 2027-09-06 |  |  | 2023 | 2027
CP1300 | Climate Change Adaptation Measures | Roscommon | Portfolio | Asset Refurbishment | 220 | Pre PA | 2023-04-05 | 2027-07-14 |  |  | 2023 | 2027
CP1301 | Dundalk Louth 110 kV Line Uprate | Louth | Portfolio | Asset Refurbishment | 110 | Post PA | 2024-02-07 | 2025-02-28 |  | 2026-08-12 | 2024 | 2025 |  | 2026
CP1302 | Killonan Shannonbridge 220 kV Line Refurbishment | Limerick | Portfolio | Asset Refurbishment | 220 | Pre PA | 2025-10-08 | 2026-04-23 | 2028-03-31 | 2029-03-01 | 2025 | 2026 | 2028 | 2029
CP1310 | Agannygal-Ennis Line Refurbishment | Clare | Portfolio | Asset Refurbishment | 110 | Pre PA | 2024-12-09 | 2026-06-26 | 2027-06-11 | 2028-03-27 | 2024 | 2026 | 2027 | 2028
CP1311 | Athlone - Lanesboro 110 kV line uprate | Westmeath | Portfolio | System Reinforcement | 110 | Post PA | 2023-02-16 | 2025-09-26 | 2027-11-30 | 2030-09-16 | 2023 | 2025 | 2027 | 2030
CP1312 | Athy - Carlow 110 kV circuit 1 | Kildare | Portfolio | System Reinforcement | 110 | Pre PA | 2024-06-05 | 2027-03-22 | 2027-06-22 | 2029-09-06 | 2024 | 2027 | 2027 | 2029
CP1314 | Baroda - Monread 110 kV circuit 1 (DLR) | Kildare | Portfolio | System Reinforcement | 110 | Pre PA | 2024-07-03 | 2029-12-21 | 2032-06-21 | 2033-09-02 | 2024 | 2029 | 2032 | 2033
CP1315 | Baroda - Newbridge 110 kV circuit 1 (DLR) | Kildare | Portfolio | System Reinforcement | 110 | Pre PA | 2024-07-03 | 2029-12-21 | 2031-03-28 | 2031-03-28 | 2024 | 2029 | 2031 | 2031
CP1316 | Replacement of substation Back-Up supply equipment – North-East Region | Roscommon | Portfolio | Asset Refurbishment |  | Pre PA | 2024-02-07 | 2029-07-17 |  |  | 2024 | 2029
CP1318 | Binbane - Clogher - Cathaleens Fall - 110 kV Clogher tie in | Donegal | Portfolio | System Reinforcement | 110 | Pipeline | 2029-02-21 | 2030-12-06 | 2031-09-05 | 2032-09-03 | 2029 | 2030 | 2031 | 2032
CP1319 | Blake Maynooth Newbridge Uprate | Kildare | Portfolio | Asset Refurbishment | 110 | Pre PA | 2025-09-03 | 2026-12-18 | 2027-09-17 | 2028-09-18 | 2025 | 2026 | 2027 | 2028
CP1320 | Barrymore Cahir Knockraha 110kV Line Uprate | Cork | Portfolio | System Reinforcement | 110 | Pre PA | 2022-07-31 | 2027-03-10 | 2027-10-20 | 2029-11-01 | 2022 | 2027 | 2027 | 2029
CP1325 | Blundelstown Mullingar 110 kV Line Uprate | Dublin | Portfolio | Asset Refurbishment | 110 | Pre PA | 2024-12-20 | 2026-12-21 | 2027-09-01 | 2030-05-08 | 2024 | 2026 | 2027 | 2030
CP1327 | Drumkeen - Clogher 110 kV circuit 1 | Mayo | Portfolio | System Reinforcement | 110 | Pipeline | 2029-02-07 | 2030-07-26 | 2031-04-28 | 2032-04-27 | 2029 | 2030 | 2031 | 2032
CP1331 | Rosspile 110kV Station (Rosspile Storage Facility) | Wexford | Portfolio | Customer Connection | 110 | Pre PA | 2025-05-07 |  |  |  | 2025
CP1332 | Reask Solar Farm (ECP 2-2-12) | Meath | Portfolio | Customer Connection | Pipeline | Pipeline
CP1334 | Newbarn 110 kV Station (Fieldstown Solar Farm) | Dublin | Portfolio | Customer Connection | 110 | Post PA | 2023-08-01 | 2025-12-15 | 2027-07-08 | 2027-11-19 | 2023 | 2025 | 2027 | 2027
CP1335 | Garballagh 110kV Station (Garballagh 2 Solar Farm) | Meath | Portfolio | Customer Connection | 110 | Pre PA | 2023-07-20 |  |  |  | 2023
CP1338 | Effernoge 110kV Station (Tomsallagh Solar) | Wexford | Portfolio | Customer Connection | 110 | Pre PA | 2023-11-10 | 2026-04-13 |  |  | 2023 | 2026
CP1341 | Cloon 110 kV_Barnacurragh Solar Park | Galway | Portfolio | Customer Connection | 110 | Pre PA | 2023-04-04 | 2026-10-01 |  |  | 2023 | 2026
CP1342 | Drumcamill 110 kV Station (Monvallet Hybrid Solar and Battery Farm) | Louth | Portfolio | Customer Connection | 110 | Post PA | 2023-10-06 | 2024-09-04 | 2026-07-01 | 2026-06-30 | 2023 | 2024 | 2026 | 2026
CP1344 | Timahoe North Phase 2 Solar Farm (ECP 2-2-23) | Kildare | Portfolio | Customer Connection | Pipeline | Pipeline
CP1345 | Golagh 110kV Station (Barnesmore WF Repower) | Donegal | Portfolio | Customer Connection | 110 | Pre PA | 2024-03-06 |  |  |  | 2024
CP1346 | Meath Hill 110 kV Station (Ardagh South Energy Storage) | Meath | Portfolio | Customer Connection | 110 | Post PA | 2024-03-06 | 2025-09-26 | 2027-08-31 | 2027-10-07 | 2024 | 2025 | 2027 | 2027
CP1347 | Dunbrody 110 kV Station (Kilmannock Battery Storage Facility Phase 2) | Wexford | Portfolio | Customer Connection | 110 | Pre PA | 2023-10-06 | 2026-10-30 |  |  | 2023 | 2026
CP1351 | Ballynadrideen 110 kV Station (Ballyroe Solar) | Cork | Portfolio | Customer Connection | 110 | Post PA | 2023-03-30 | 2024-05-29 | 2026-08-28 | 2026-10-15 | 2023 | 2024 | 2026 | 2026
CP1352 | Gortatleva 110 kV Station (Ballymoneen Solar Park) | Galway | Portfolio | Customer Connection | 110 | Post EI | 2023-04-09 | 2024-09-23 | 2026-03-02 | 2026-03-02 | 2023 | 2024 | 2026 | 2026
CP1353 | Bendinstown 110kV Station (Garreenleen Solar) | Carlow | Portfolio | Customer Connection | 110 | Post PA | 2023-04-20 | 2024-08-07 | 2026-05-05 | 2026-05-05 | 2023 | 2024 | 2026 | 2026
CP1354 | Coolshamroge 110 kV Station (Manusmore Solar Park) | Clare | Portfolio | Customer Connection | 110 | Pre PA | 2023-04-05 | 2026-08-13 |  |  | 2023 | 2026
CP1355 | Corbetstown 110 kV Station (Garr Solar and Storage) | Offaly | Portfolio | Customer Connection | 110 | Pre PA | 2024-03-06 |  |  |  | 2024
CP1356 | Gortawee 110 kV Station (Mucklagh Battery Storage Facility) | Cavan | Portfolio | Customer Connection | 110 | Pre PA | 2024-08-07 |  |  |  | 2024
CP1357 | Philipstown 110 kV Station (Kilcush solar farm) | Offaly | Portfolio | Customer Connection | 110 | Pre PA | 2024-09-04 |  |  |  | 2024
CP1358 | Thornsberry 110 kV Station (Ballycosney 150 MW BESS) | Offaly | Portfolio | Customer Connection | 110 | Pre PA | 2025-02-05 |  |  |  | 2025
CP1360 | Coolcor 110KV (Coolavacoose Solar Farm) | Kildare | Portfolio | Customer Connection | 110 | Pre PA | 2024-11-06 |  |  |  | 2024
CP1361 | Booltaigh 110KV Station (Carncreagh Energy Storage) | Clare | Portfolio | Customer Connection | 110 | Pre PA | 2024-11-06 | 2026-07-09 |  |  | 2024 | 2026
CP1362 | Bishopswood 110 kV Station (Blue Pine Solar) | Offaly | Portfolio | Customer Connection | 110 | Pipeline
CP1363 | Curraghdoo 110 kV Station (Clonymeath Solar Farm) | Meath | Portfolio | Customer Connection | 110 | Pre PA | 2025-07-01 |  |  |  | 2025
CP1364 | Moanalow 110 kV Station (Grangeford Solar PV) | Carlow | Portfolio | Customer Connection | 110 | Pre PA | 2024-11-06 |  |  |  | 2024
CP1365 | Mihanboy 110 kV station (Taduff Solar Park) | Roscommon | Portfolio | Customer Connection | 110 | Pre PA | 2024-11-06 | 2026-05-30 |  |  | 2024 | 2026
CP1366 | Lysaghtstown 110 kV Station (Lysaghtstown Solar Farm Phase 2) | Cork | Portfolio | Customer Connection | 110 | Pre PA | 2024-09-04 |  |  |  | 2024
CP1367 | Midleton 110kV Station (Carrigogna BESS) | Cork | Portfolio | Customer Connection | 110 | Pre PA | 2025-02-05 |  |  |  | 2025
CP1368 | Crosspatrick 110 kV Station (Mullafarry BESS) | Mayo | Portfolio | Customer Connection | 110 | Pre PA | 2025-01-15 |  |  |  | 2025
CP1369 | Colehill 110 kV Station (Ballyteige Solar Park) | Offaly | Portfolio | Customer Connection | 110 | Pipeline
CP1372 | Drombeg 110 kV Station (Drombeg Solar Park Phase 2) | Kerry | Portfolio | Customer Connection | 110 | Pre PA | 2025-03-05 | 2026-04-07 |  |  | 2025 | 2026
CP1374 | Ballyvouskill 110 kV (ABO Wind Ireland) | Cork | Portfolio | Customer Connection | 110 | Pre PA | 2025-07-25 |  |  |  | 2025
CP1375 | Boggeragh 110 kV Station (Carragraigue Solar Extension) | Cork | Portfolio | Customer Connection | 110 | Pre PA | 2024-06-05 |  |  |  | 2024
CP1377 | Rathcoon 110 kV Station (Gorman Solar Farm) | Meath | Portfolio | Customer Connection | 110 | Pre PA | 2024-07-03 |  |  |  | 2024
CP1378 | Cooleeny 110 kV Station (Killoran Solar PV Farm) | Tipperary | Portfolio | Customer Connection | 110 | Pre PA | 2024-08-07 | 2026-11-27 |  |  | 2024 | 2026
CP1379 | Cauteen 110 kV Station (Barnaleen Solar Farm) | Tipperary | Portfolio | Customer Connection | 110 | Pre PA | 2025-04-02 | 2029-09-26 |  |  | 2025 | 2029
CP1380 | Craddanstown 110kV station (Bracklyn WF) | Westmeath | Portfolio | Customer Connection | 110 | Pre PA | 2024-12-04 | 2026-12-01 |  |  | 2024 | 2026
CP1384 | Kilteel - Maynooth 110 kV | Kildare | Portfolio | System Reinforcement | 110 | Pipeline | 2026-09-02 | 2028-06-09 | 2029-01-16 | 2029-01-16 | 2026 | 2028 | 2029 | 2029
CP1389 | Limerick - Rathkeale Line Uprate | Limerick | Portfolio | Asset Refurbishment | 110 | Pre PA | 2024-08-12 | 2029-10-18 | 2033-02-14 | 2035-07-16 | 2024 | 2029 | 2033 | 2035
CP1390 | Maynooth - Rinawade 110V line uprate | Kildare | Portfolio | System Reinforcement | 110 | Post PA | 2023-06-06 | 2024-12-19 |  | 2026-10-30 | 2023 | 2024 |  | 2026
CP1394 | Offshore Phase 1 - Codling Wind Park | Galway | Portfolio | Customer Connection | 220 | Pre PA | 2022-12-15 |  |  |  | 2022
CP1396 | Arklow Bank Wind Park Phase 2 (Offshore) | Wicklow | Portfolio | Customer Connection | 220 | Pre PA | 2022-12-15 |  |  |  | 2022
CP1397 | Bremore 220 kV Station (North Irish Sea Array) | Dublin | Portfolio | Customer Connection | 220 | Pre PA | 2022-12-15 |  |  |  | 2022
CP1398 | Offshore Phase 1 - Dublin Array | Dublin | Portfolio | Customer Connection | 220 | Pre PA | 2022-12-15 |  |  |  | 2022
CP1402 | Platin 110kV Station Refurbishment | Meath | Portfolio | Asset Refurbishment | 110 | Pre PA | 2025-06-04 | 2026-12-22 | 2028-03-23 | 2030-03-24 | 2025 | 2026 | 2028 | 2030
CP1403 | Rinawade – Dunfirth Tee – Kinnegad 110 kV Circuit Thermal Capacity | Kildare | Portfolio | System Reinforcement | 110 | Pre PA | 2023-05-18 | 2026-10-20 | 2027-06-22 | 2028-06-22 | 2023 | 2026 | 2027 | 2028
CP1412 | Knockraha 220 kV Transformer Replacement (T2102) | Cork | Portfolio | Asset Refurbishment | 220 | Post PA | 2023-03-08 | 2024-05-17 |  | 2026-12-01 | 2023 | 2024 |  | 2026
CP1418 | Oaklands 110 kV Station Crag Wicklow | Wicklow | Portfolio | Customer Connection | 110 | Pre PA | 2023-07-24 | 2026-06-17 |  |  | 2023 | 2026
CP1420 | North Wicklow Reinforcement | Wicklow | Portfolio | System Reinforcement | 110 | Pipeline | 2027-03-02 | 2030-06-30 | 2034-09-01 | 2034-12-01 | 2027 | 2030 | 2034 | 2034
CP1421 | Crakenstown 220-110 kV Station | Meath | Portfolio | Customer Connection | 110 | Pre PA | 2025-09-17 |  |  |  | 2025
CP1422 | Cashla - Prospect 220 kV Line Refurbishment | Galway | Portfolio | Asset Refurbishment | 220 | Pre PA | 2025-09-03 | 2028-03-14 | 2031-04-18 | 2032-04-16 | 2025 | 2028 | 2031 | 2032
CP1423 | Cashla - Tynagh 220 kV Line Refurbishment | Galway | Portfolio | Asset Refurbishment | 220 | Pre PA | 2025-06-04 | 2027-01-05 | 2031-04-09 | 2033-05-13 | 2025 | 2027 | 2031 | 2033
CP1424 | Farrnawana 220 kV (SSE Tarbert OCGT) | Kerry | Portfolio | Customer Connection | 220 | Post PA | 2023-08-02 | 2025-10-15 |  | 2027-09-24 | 2023 | 2025 |  | 2027
CP1425 | Southwall 220kV GIS (ESB Poolbeg) (ESB G&T) | Dublin | Portfolio | Customer Connection | 220 | Pre PA | 2023-07-11 |  |  |  | 2023
CP1426 | Derrygreenagh 220 kV, Rathcobican 400 kV SS (Cushaling Power Ltd) | Offaly | Portfolio | Customer Connection | 400 | Pre PA | 2024-07-19 |  |  |  | 2024
CP1427 | Bellewstown 110kV Station – SSE Platin | Meath | Portfolio | Customer Connection | 110 | Pre PA | 2023-08-02 | 2026-06-30 |  |  | 2023 | 2026
CP1428 | Cashla - Dalton 110kV Thermal Capacity Increase | Galway | Portfolio | System Reinforcement | 110 | Pre PA | 2023-12-12 | 2026-03-31 | 2027-03-09 | 2028-11-02 | 2023 | 2026 | 2027 | 2028
CP1429 | Castlebar Dalton 110kV Thermal Capacity Increase | Mayo | Portfolio | System Reinforcement | 110 | Pre PA | 2023-12-12 | 2026-06-02 | 2027-03-02 | 2028-03-02 | 2023 | 2026 | 2027 | 2028
CP1434 | Drumline 110 kV Station Busbar Thermal Uprate | Clare | Portfolio | System Reinforcement | 110 | Pipeline | 2026-05-06 | 2027-12-07 | 2031-09-11 | 2033-12-19 | 2026 | 2027 | 2031 | 2033
CP1435 | Drumline Ennis 110kV circuit DLR and related works | Clare | Portfolio | Asset Refurbishment | 110 | Pre PA | 2024-02-07 | 2028-08-22 | 2031-03-14 | 2031-03-24 | 2024 | 2028 | 2031 | 2031
CP1436 | Ardnacrusha Ennis 110kV circuit DLR and related works | Clare | Portfolio | System Reinforcement | 110 | Pre PA | 2024-03-06 | 2028-08-22 | 2031-02-19 | 2031-08-15 | 2024 | 2028 | 2031 | 2031
CP1442 | Fosterstown 110 kV Station Connection DSO | Mayo | Portfolio | DSO | 110 | Pre PA | 2024-02-07 | 2026-11-25 | 2029-07-10 | 2029-10-31 | 2024 | 2026 | 2029 | 2029
CP1447 | Letterkenny - Golagh Tee 110 kV circuit thermal capacity needs | Donegal | Portfolio | System Reinforcement | 110 | Pipeline | 2029-02-07 | 2030-07-26 | 2031-04-08 | 2032-12-14 | 2029 | 2030 | 2031 | 2032
CP1448 | Carrickmines Phase Shift Transformer (PST) Replacement | Mayo | Portfolio | System Reinforcement |  | Pipeline | 2028-11-20 | 2030-11-22 | 2032-02-23 | 2034-02-22 | 2028 | 2030 | 2032 | 2034
CP1449 | Midleton 110kV Transformer Uprate and Station works DSO | Cork | Portfolio | DSO | 110 | Post PA | 2024-02-07 | 2025-05-22 | 2027-01-29 | 2027-05-31 | 2024 | 2025 | 2027 | 2027
CP1450 | Ardnacrusha Drumline 110kV thermal capacity needs | Clare | Portfolio | System Reinforcement | 110 | Pre PA | 2024-03-06 | 2028-08-22 | 2031-05-16 | 2032-01-10 | 2024 | 2028 | 2031 | 2032
CP1452 | Poolbeg OCGT (ESB G&T) | Dublin | Portfolio | Customer Connection | 220 | Post PA | 2024-03-05 | 2025-03-05 | 2026-09-18 | 2026-10-21 | 2024 | 2025 | 2026 | 2026
CP1453 | Blake 110 kV Station Redevelopment | Kildare | Portfolio | Asset Refurbishment | 110 | Pre PA | 2024-05-30 | 2029-10-05 | 2031-09-12 | 2034-05-22 | 2024 | 2029 | 2031 | 2034
CP1454 | Gorman - Maynooth 220 kV Circuit Capacity Needs | Meath | Portfolio | System Reinforcement | 220 | Pre PA | 2024-05-01 | 2028-05-12 | 2031-06-11 | 2033-09-02 | 2024 | 2028 | 2031 | 2033
CP1456 | Clutterland 110kV Station Phase 2&3 (Amazon Web Services) | Dublin | Portfolio | Customer Connection | 110 | Post PA | 2024-03-06 | 2024-12-04 | 2026-07-01 | 2026-08-21 | 2024 | 2024 | 2026 | 2026
CP1459 | East Kildare 110 kV Station | Kildare | Portfolio | Customer Connection | 110 | Pre PA | 2024-03-25 |  |  |  | 2024
CP1464 | Tullabeg 110 kV Station (Tullabeg Solar Phase 2 | Clare | Portfolio | Customer Connection | 110 | Pre PA | 2024-06-05 | 2026-09-09 |  |  | 2024 | 2026
CP1465 | Lisdrum 110kV Station Busbar Thermal Capacity Need | Monaghan | Portfolio | System Reinforcement | 110 | Post PA | 2024-11-06 | 2025-12-19 | 2026-12-22 | 2031-05-06 | 2024 | 2025 | 2026 | 2031
CP1466 | Meath Hill 110kV Station Busbar Thermal Capacity Need | Meath | Portfolio | System Reinforcement | 110 | Pre PA | 2024-11-06 | 2026-07-10 | 2027-10-08 | 2029-10-10 | 2024 | 2026 | 2027 | 2029
CP1467 | Caherhurly 110 kV Station (Carrownagowan Wind Farm) | Cork | Portfolio | Customer Connection | 110 | Pre PA | 2024-05-01 | 2026-10-14 |  |  | 2024 | 2026
CP1468 | Kilvinoge 110 kV Station (Castlebanny Wind Farm) | Kilkenny | Portfolio | Customer Connection | 110 | Pre PA | 2024-05-01 | 2027-07-08 |  |  | 2024 | 2027
CP1471 | Lisdrum Louth 110 kV DLR project | Monaghan | Portfolio | System Reinforcement | 110 | Pre PA | 2024-07-03 | 2028-04-21 | 2031-03-19 | 2031-10-24 | 2024 | 2028 | 2031 | 2031
CP1473 | Louth - Meath Hill 110 kV DLR | Louth | Portfolio | System Reinforcement | 110 | Pre PA | 2024-07-03 | 2028-02-11 | 2031-02-28 | 2031-11-06 | 2024 | 2028 | 2031 | 2031
CP1475 | East Galway 110 kV Station (DSO Connection) | Galway | Portfolio | DSO | 110 | Pipeline
CP1477 | Maynooth - Shannonbridge 220 kV Circuit Capacity Needs | Kildare | Portfolio | System Reinforcement | 220 | Pipeline | 2026-06-04 | 2028-06-06 | 2029-03-06 | 2030-03-06 | 2026 | 2028 | 2029 | 2030
CP1478 | Donegal TEN-T Road Network Advanced Ducting | Donegal | Portfolio | System Reinforcement | 220 | Pre PA | 2025-01-15 | 2029-11-25 |  |  | 2025 | 2029
CP1479 | Ratrussan - Shankill 110 kV Dynamic Line Rating | Cavan | Portfolio | System Reinforcement | 110 | Pre PA | 2024-12-20 | 2029-12-21 | 2032-12-02 | 2034-07-25 | 2024 | 2029 | 2032 | 2034
CP1484 | Srananagh 220 kV Station (Quarry Lane LCIS) | Sligo | Portfolio | Customer Connection | 220 | Post PA | 2025-04-02 | 2026-01-14 | 2027-08-26 | 2027-08-26 | 2025 | 2026 | 2027 | 2027
CP1485 | Wexford Synchronous Condenser | Wexford | Portfolio | Customer Connection | 110 | Pre PA | 2025-11-03 | 2026-09-28 |  |  | 2025 | 2026
CP1486 | Athlone - Shannonbridge 110 kV Fibre Wrapping | Westmeath | Portfolio | System Reinforcement | 110 | Pre PA | 2026-03-04 | 2027-03-22 |  | 2029-05-15 | 2026 | 2027 |  | 2029
CP1487 | CP1487 Corduff and Connected Stations Protection Upgrade | Dublin | Portfolio | Asset Refurbishment |  | Pre PA | 2026-03-30 | 2029-02-07 | 2031-08-02 | 2034-10-26 | 2026 | 2029 | 2031 | 2034
CP1488 | CP1488 Tralee and Connected Stations Protection Upgrade | Kerry | Portfolio | Asset Refurbishment |  | Pre PA | 2026-03-04 | 2029-02-06 | 2031-08-02 | 2034-10-26 | 2026 | 2029 | 2031 | 2034
CP1490 | Barrymore 110 kV busbar and new 110 38 transformer | Cork | Portfolio | System Reinforcement | 110 | Pre PA | 2024-12-03 | 2027-09-07 | 2029-11-16 | 2030-12-18 | 2024 | 2027 | 2029 | 2030
CP1491 | Barrymore Land Acquisition | Cork | Portfolio | System Reinforcement | 110 | Pre PA | 2024-12-06 | 2028-04-04 |  |  | 2024 | 2028
CP1492 | Donore 110 kV Station (DSO Connection) | Laois | Portfolio | DSO | 110 | Pre PA | 2024-12-04 | 2027-03-25 | 2029-06-15 | 2029-09-17 | 2024 | 2027 | 2029 | 2029
CP1495 | Lodgewood-Great Island line uprate | Wexford | Portfolio | Asset Refurbishment | 220 | Pre PA | 2025-02-26 | 2028-07-03 | 2031-04-22 | 2033-04-06 | 2025 | 2028 | 2031 | 2033
CP1496 | Cashla - Shannonbridge 110 kV | Galway | Portfolio | System Reinforcement | 110 | Pre PA | 2025-09-10 | 2029-11-23 | 2031-05-02 | 2033-01-06 | 2025 | 2029 | 2031 | 2033
CP1498 | Derryiron - Kinnegad 110 kV Fibre Wrapping | Offaly | Portfolio | System Reinforcement | 110 | Pipeline | 2026-12-20 | 2028-04-01 | 2034-09-02 | 2035-09-02 | 2026 | 2028 | 2034 | 2035
CP1499 | Charleville - Glenlara 110 kV Fibre Wrapping | Louth | Portfolio | System Reinforcement | 110 | Pipeline | 2027-12-02 | 2028-05-01 | 2034-09-02 | 2035-09-02 | 2027 | 2028 | 2034 | 2035
CP1500 | Butlerstown 110kV Station (Traffo Uprate) (DSO) | Cork | Portfolio | DSO | 110 | Post PA | 2025-05-08 | 2026-03-02 | 2027-04-02 | 2028-03-01 | 2025 | 2026 | 2027 | 2028
CP1509 | Cathaleen’s Fall Srananagh 110 kV Circuit No 2 DLR | Sligo | Portfolio | System Reinforcement | 110 | Pre PA | 2025-11-14 | 2030-10-28 | 2031-05-30 | 2031-12-22 | 2025 | 2030 | 2031 | 2031
CP1510 | Peamount 110 kV Station (Bulmer RICE) | Dublin | Portfolio | Customer Connection | 110 | Pre PA | 2024-12-04 |  |  |  | 2024
CP1511 | Castleview 110kV Station DSO (Eastmont DC) | Kerry | Portfolio | DSO | 110 | Pre PA | 2025-02-05 | 2028-02-23 | 2031-09-08 | 2032-10-04 | 2025 | 2028 | 2031 | 2032
CP1512 | Cathaleens Fall 110kV DSO (Derrykillew Wind Farm) | Kilkenny | Portfolio | DSO | 110 | Pre PA | 2025-04-22 | 2029-12-18 | 2032-09-06 | 2033-12-22 | 2025 | 2029 | 2032 | 2033
CP1513 | Ricetown 110kV Station (Mill Farm Solar) | Meath | Portfolio | Customer Connection | 110 | Pre PA | 2025-01-15 | 2026-06-30 |  |  | 2025 | 2026
CP1514 | Deenes - Drybridge 110 kV Circuit DLR | Meath | Portfolio | System Reinforcement | 110 | Pre PA | 2025-11-21 | 2030-03-15 | 2031-08-08 | 2032-10-29 | 2025 | 2030 | 2031 | 2032
CP1515 | Kellymount 110 kV Station (White Hill Wind) | Kilkenny | Portfolio | Customer Connection | 110 | Pre PA | 2025-04-02 |  |  |  | 2025
CP1516 | Kilmacogue 110 kV Station (Ballyvalode Solar) | Cork | Portfolio | Customer Connection | 110 | Pre PA | 2025-05-07 |  |  |  | 2025
CP1517 | Kildinan 110 kV Station (Coom Green Energy Park) | Cork | Portfolio | Customer Connection | 110 | Pre PA | 2025-02-05 |  |  |  | 2025
CP1518 | Glenart 220 kV Station (Pollahoney Autoproducer) | Wicklow | Portfolio | Customer Connection | 220 | Pre PA | 2025-03-05 | 2026-09-29 |  |  | 2025 | 2026
CP1519 | Crane - Wexford 110 kV (DLR) | Wexford | Portfolio | System Reinforcement | 110 | Pre PA | 2025-05-07 | 2030-10-28 | 2032-02-16 | 2032-12-13 | 2025 | 2030 | 2032 | 2032
CP1520 | Great Island - Waterford 110 kV (DLR) | Wexford | Portfolio | System Reinforcement | 110 | Pre PA | 2025-05-07 | 2030-07-12 | 2031-02-11 | 2031-02-11 | 2025 | 2030 | 2031 | 2031
CP1521 | Cappaneary 110kV Station(Dernacart Wind Farm) | Kerry | Portfolio | Customer Connection | 110 | Pre PA | 2025-09-30 |  |  |  | 2025
CP1522 | New Lodgewood 220-110 kV Transformer | Wexford | Portfolio | System Reinforcement | 220 | Pre PA | 2025-06-04 | 2030-06-12 | 2031-09-12 | 2033-09-12 | 2025 | 2030 | 2031 | 2033
CP1523 | Binbane 110 kV Station Busbar Thermal Capacity Need | Donegal | Portfolio | System Reinforcement | 110 | Pre PA | 2025-11-17 | 2030-05-10 | 2031-08-26 | 2033-03-14 | 2025 | 2030 | 2031 | 2033
CP1526 | Baltrasna Corduff 110 kV Circuit DLR Project | Dublin | Portfolio | System Reinforcement | 110 | Pre PA | 2025-11-21 | 2028-10-11 | 2031-08-22 | 2033-01-03 | 2025 | 2028 | 2031 | 2033
CP1527 | Buffy 110 kV (Ardderoo WF Phase 2) | Galway | Portfolio | Customer Connection | 110 | Pipeline
CP1528 | Lislaughtin 110k V Station (Dromlivuan Solar Farm) | Kerry | Portfolio | Customer Connection | 110 | Pipeline
CP1529 | Oldbridge Phase 2&3 | Meath | Portfolio | Customer Connection | 110 | Pre PA | 2025-04-22 | 2026-12-18 |  |  | 2025 | 2026
CP1530 | Ballycummin 110kV Station DSO | Sligo | Portfolio | DSO | 110 | Pre PA | 2025-06-05 | 2026-08-03 | 2029-08-10 | 2029-11-10 | 2025 | 2026 | 2029 | 2029
CP1531 | Kilbarry Knockraha 110 kV Circuit 2 Uprate (Kilbarry Mallow) | Cork | Portfolio | System Reinforcement | 110 | Pipeline | 2026-12-21 | 2028-08-10 | 2031-04-08 | 2032-10-22 | 2026 | 2028 | 2031 | 2032
CP1532 | NM20 Cork to Limerick - Advance Ducting | Cork | Portfolio | System Reinforcement | 400 | Pipeline | 2028-05-18 | 2030-06-02 |  |  | 2028 | 2030
CP1533 | Raheenmeel 110 kV Station (Kilcormac Solar) | Laois | Portfolio | Customer Connection | 110 | Pre PA | 2025-06-04 |  |  |  | 2025
CP1534 | Ennis 110 kV Station (Transformer Uprate) (DSO) | Clare | Portfolio | DSO | 110 | Pre PA | 2025-11-14 | 2026-12-01 | 2027-10-29 | 2028-06-01 | 2025 | 2026 | 2027 | 2028
CP1535 | Trien 110 kV Station (Transformer Uprate) (DSO) | Roscommon | Portfolio | DSO | 110 | Pre PA | 2025-11-14 | 2029-08-13 | 2031-04-21 | 2034-06-02 | 2025 | 2029 | 2031 | 2034
CP1536 | Clogher 220kV Station | Donegal | Portfolio | System Reinforcement | 220 | Pre PA | 2026-03-30 | 2029-12-12 | 2034-12-18 | 2035-12-03 | 2026 | 2029 | 2034 | 2035
CP1539 | Mullingar 110 kV Station (Transformer Uprate) (DSO) | Westmeath | Portfolio | DSO | 110 | Pre PA | 2025-10-06 | 2026-12-01 | 2028-03-01 | 2028-06-01 | 2025 | 2026 | 2028 | 2028
CP1540 | CP1540 220 kV Composite pole – Pilot Energised Project | Kilkenny | Portfolio | System Reinforcement | 220 | Pipeline | 2026-07-03 | 2028-09-06 | 2031-05-06 | 2033-06-09 | 2026 | 2028 | 2031 | 2033
CP1541 | Seven Hills Wind Farm | Galway | Portfolio | Customer Connection | 110 | Pre PA | 2025-10-08 |  |  |  | 2025
CP1542 | Cauteen 110kV Station (DSO Gortdrum SF) | Tipperary | Portfolio | DSO | 110 | Pre PA | 2025-12-01 | 2030-02-13 | 2032-09-09 | 2033-09-05 | 2025 | 2030 | 2032 | 2033
CP1543 | Srananagh 220kV Transformer and Bay Extension | Sligo | Portfolio | System Reinforcement | 220 | Pre PA | 2026-02-04 | 2028-03-07 | 2031-07-28 | 2031-12-05 | 2026 | 2028 | 2031 | 2031
CP1544 | Belcamp 110 kV busbar extension and additional transformer capacity | Dublin | Portfolio | System Reinforcement | 110 | Pre PA | 2025-11-28 | 2027-06-09 | 2028-05-18 | 2030-11-14 | 2025 | 2027 | 2028 | 2030
CP1545 | Maynooth Cable Routing Land Acquisition | Kildare | Portfolio | System Reinforcement |  | Pre PA | 2020-11-19 | 2029-10-01 |  |  | 2020 | 2029
CP1546 | Tincurry Solar Farm (Lodgewood Solar Farm Limited) (ECP 2-4-40) | Galway | Portfolio | Customer Connection | 110 | Pre PA | 2025-10-21 |  |  |  | 2025
CP1547 | Newbridge East- 110 kV Cable Uprate | Kildare | Portfolio | Asset Refurbishment | 110 | Pre PA | 2025-11-14 | 2030-04-26 | 2031-05-02 | 2032-08-12 | 2025 | 2030 | 2031 | 2032
CP1548 | Replacement of substation Back-Up supply equipment – Central Region | Roscommon | Portfolio | Asset Refurbishment | 220 | Pre PA | 2025-12-18 | 2029-07-17 |  |  | 2025 | 2029
CP1549 | Replacement of substation Back-Up supply equipment – North-West Region | Roscommon | Portfolio | Asset Refurbishment | 220 | Pre PA | 2025-12-18 | 2029-07-17 |  |  | 2025 | 2029
CP1550 | Replacement of substation Back-Up supply equipment – South Central Region | Roscommon | Portfolio | Asset Refurbishment | 220 | Pre PA | 2025-12-18 | 2029-07-17 |  |  | 2025 | 2029
CP1551 | Replacement of substation Back-Up supply equipment – South-East Region | Roscommon | Portfolio | Asset Refurbishment | 220 | Pipeline | 2028-05-08 | 2029-07-17 |  |  | 2028 | 2029
CP1552 | Replacement of substation Back-Up supply equipment – South-West Region | Roscommon | Portfolio | Asset Refurbishment | 220 | Pre PA | 2025-12-18 | 2029-07-17 |  |  | 2025 | 2029
CP1556 | Arklow Ballybeg Carrickmines Refurbishment | Wicklow | Portfolio | Asset Refurbishment | 220 | Pre PA | 2025-12-03 | 2026-12-18 | 2029-03-15 | 2031-04-02 | 2025 | 2026 | 2029 | 2031
CP1557 | Cow Cross 110kV Station Refurbishment | Limerick | Portfolio | Asset Refurbishment | 110 | Pipeline | 2027-02-25 | 2029-03-06 | 2031-08-30 | 2034-11-23 | 2027 | 2029 | 2031 | 2034
CP1559 | Ballymac Phase 2 (Ballymac Solar DAC) (ECP 2-4-07) | Cork | Portfolio | Customer Connection |  | Pipeline
CP1560 | Kilnap 110kV Station - 2 New DSO Transformer Bays | Cork | Portfolio | DSO | 110 | Post PA | 2025-08-25 | 2026-02-03 | 2027-03-04 | 2027-10-01 | 2025 | 2026 | 2027 | 2027
CP1562 | N3 Virginia Bypass Road Advance Ducting | Cavan | Portfolio | System Reinforcement |  | Pipeline | 2028-09-15 | 2029-12-21 |  |  | 2028 | 2029
CP1563 | N4 Mullingar to Longford Advance Ducting | Westmeath | Portfolio | System Reinforcement |  | Pipeline | 2028-09-15 | 2029-12-21 |  |  | 2028 | 2029
CP1564 | Affane 110kV Station (Modelligo Solar) | Galway | Portfolio | Customer Connection |  | Pre PA | 2026-02-04 |  |  |  | 2026
CP1565 | Kilteel 110 kV Station (Transformer Uprate) (DSO) Project Setup | Limerick | Portfolio | DSO |  | Pre PA | 2025-09-16 | 2030-01-14 | 2032-08-30 | 2033-11-25 | 2025 | 2030 | 2032 | 2033
CP1566 | Propoge 110 kV (Lyrenacarriga Windfarm and BESS) (Curns Energy Ltd) | Cork | Portfolio | Customer Connection |  | Pipeline
CP1567 | Knockdonagh 110kV (Ballyglass Solar Farm) | Galway | Portfolio | Customer Connection | 110 | Pre PA | 2026-01-19 |  |  |  | 2026
CP1568 | Arva-Carrick On Shannon 110 kV Line Alteration | Mayo | Portfolio | Diversion | 110 | Pipeline | 2028-05-19 | 2030-10-11 | 2033-02-08 | 2033-02-08 | 2028 | 2030 | 2033 | 2033
CP1569 | Culmullin 220kV Station (Derryclare WF) | Meath | Portfolio | Customer Connection | 220 | Pre PA | 2026-02-04 |  |  |  | 2026
CP1572 | Cregcarragh 110 kV Station (Ballymoneen Phase 2) | Wicklow | Portfolio | Customer Connection |  | Pipeline
CP1573 | Kilbarry 110kV Station Redevelopment | Cork | Portfolio | Asset Refurbishment | 110 | Pipeline | 2029-07-18 | 2030-08-08 | 2032-03-15 | 2033-03-15 | 2029 | 2030 | 2032 | 2033
CP1574 | Kellis- Kilkenny 110kV Circuit Refurbishment | Carlow | Portfolio | Asset Refurbishment |  | Pipeline | 2027-06-30 | 2028-08-20 | 2031-09-24 | 2033-12-17 | 2027 | 2028 | 2031 | 2033
CP1575 | Rathkeale 110kV Station Redevelopment | Laois | Portfolio | Asset Refurbishment | 110 | Pipeline | 2029-06-07 | 2030-07-08 | 2032-11-04 | 2033-11-04 | 2029 | 2030 | 2032 | 2033
CP1576 | N25 Midleton to Youghal - Advance Ducting | Cork | Portfolio | System Reinforcement |  | Pipeline | 2026-07-20 | 2030-01-18 |  |  | 2026 | 2030
CP1577 | N6 Galway City Ring Road ​​- Advance Ducting | Galway | Portfolio | System Reinforcement |  | Pipeline | 2026-06-30 | 2030-01-18 |  |  | 2026 | 2030
CP1578 | N11-N25 Oilgate to Rosslare Harbour​-Advance Ducting | Galway | Portfolio | System Reinforcement |  | Pipeline | 2029-01-24 | 2030-09-06 |  |  | 2029 | 2030
CP1579 | N4 Active Travel Collooney to Castlebaldwin - Advance Ducting | Galway | Portfolio | System Reinforcement |  | Pipeline | 2026-08-08 | 2029-03-20 |  |  | 2026 | 2029
CP1580 | N24 Waterford to Cahir ​​​ - Advance Ducting | Kilkenny | Portfolio | System Reinforcement |  | Pipeline | 2026-11-20 | 2030-01-18 |  |  | 2026 | 2030
CP1581 | N72 Mallow Relief Road - Advance Ducting | Cork | Portfolio | System Reinforcement |  | Pipeline | 2026-06-19 | 2029-03-20 |  |  | 2026 | 2029
CP1582 | N3 M50 to Clonee - Advance Ducting | Donegal | Portfolio | System Reinforcement |  | Pipeline | 2026-08-07 | 2029-03-20 |  |  | 2026 | 2029
CP1583 | N24 Cahir to Limerick Junction​​ - Advance Ducting Project | Limerick | Portfolio | System Reinforcement |  | Pipeline | 2026-08-07 | 2029-03-20 |  |  | 2026 | 2029
CP1584 | Carlow Southern Relief Road - Advance Ducting | Carlow | Portfolio | System Reinforcement |  | Pipeline | 2026-08-07 | 2030-01-18 |  |  | 2026 | 2030
DSO-02 | Belmayne 110 kV/38 kV/MV | Dublin | Portfolio | DSO | 110 | Pipeline
DSO-03 | New South East Carlow 110/20 kV | Carlow | Portfolio | DSO | 110 | Pipeline
DSO-06 | Bishopstown (Wilton) 110 kV/38 kV/MV | Waterford | Portfolio | DSO | 110 | Pipeline
CP1610 | Marina Phase 1 / Phase 2 | Roscommon | Portfolio | DSO |  | Pre PA | 2026-03-02 | 2026-12-01 | 2028-06-01 | 2028-06-01 | 2026 | 2026 | 2028 | 2028
DSO-12 | Blundlestown 110/38 kV | Meath | Portfolio | DSO | 110 | Pipeline
DSO-13 | New 110 kV/20 kV Killinick/Rosslare/Dennistown | Donegal | Portfolio | DSO | 110 | Pipeline
DSO-15 | 4th transformer in Carrickmines 220kV BSP (Detail ) | Mayo | Portfolio | DSO | 220 | Pipeline
DSO-16 | New 110 kV/MV Station Fermoy | Cork | Portfolio | DSO | 110 | Pipeline
DSO-17 | New North-East Cashel 110 kV/MV station (Kill Hill) | Galway | Portfolio | DSO | 110 | Pipeline
DSO-18 | New Monaghan (Cavan) 110 kV/MV Station | Monaghan | Portfolio | DSO | 110 | Pipeline
CP1609 | Newbridge G2 | Kildare | Portfolio | DSO |  | Pipeline
CP1628 | Dungarvan G2 | Waterford | Portfolio | DSO |  | Pipeline | 2026-09-01 | 2027-01-04 | 2027-12-01 | 2027-12-01 | 2026 | 2027 | 2027 | 2027
DSO-22 | Drybridge G1 | Meath | Portfolio | DSO |  | Pipeline
DSO-23 | Griffinrath G1 | Kildare | Portfolio | DSO |  | Pipeline
DSO-24 | Galway G4 | Galway | Portfolio | DSO |  | Pipeline | 2027-06-01 | 2028-01-03 | 2028-06-01 | 2028-09-01 | 2027 | 2028 | 2028 | 2028
DSO-25 | Drumline G2 | Clare | Portfolio | DSO |  | Pipeline | 2027-04-01 | 2028-01-01 | 2028-06-01 | 2029-07-12 | 2027 | 2028 | 2028 | 2029
CP1614 | New 110 kV/MV Station near Killacloyne | Cork | Portfolio | DSO | 110 | Pipeline | 2026-05-01 | 2026-12-01 | 2030-07-01 | 2030-10-01 | 2026 | 2026 | 2030 | 2030
CP1613 | Newbridge East 110/38 kV | Kildare | Portfolio | DSO | 110 | Pipeline | 2026-05-01 | 2026-12-01 | 2030-08-01 | 2030-11-01 | 2026 | 2026 | 2030 | 2030
CP1627 | Athy G4 | Kildare | Portfolio | DSO |  | Pipeline | 2026-07-01 | 2026-12-01 | 2027-11-01 | 2027-11-01 | 2026 | 2026 | 2027 | 2027
DSO-29 | Charleville G3 | Roscommon | Portfolio | DSO |  | Pipeline | 2026-08-01 | 2026-12-30 | 2027-08-11 | 2029-04-10 | 2026 | 2026 | 2027 | 2029
DSO-30 | Oughtragh G3 | Leitrim | Portfolio | DSO |  | Pipeline | 2026-08-01 | 2026-12-30 |  |  | 2026 | 2026
DSO-32 | New West Portlaoise 110 kV Station | Laois | Portfolio | DSO | 110 | Pipeline
DSO-33 | New East Athlone 110 kV/38 kV/MV | Westmeath | Portfolio | DSO | 110 | Pipeline
CP1634 | New Mayfield/Riverstown 110/MV 2 x 31.5 MVA | Mayo | Portfolio | DSO | 110 | Pipeline
DSO-35 | New 110 kV/MV station at Birdhill | Tipperary | Portfolio | DSO | 110 | Pipeline
DSO-36 | Castleview 110 kV/MV (Little Island) | Cork | Portfolio | DSO | 110 | Pipeline
DSO-37 | New Navan 110/38 kV or 110 kV/MV station | Meath | Portfolio | DSO | 110 | Pipeline
DSO-38 | Rinwade 110/38/MV Station | Kildare | Portfolio | DSO | 110 | Pipeline
DSO-40 | Bandon G2 | Cork | Portfolio | DSO |  | Pipeline | 2026-08-03 | 2026-11-02 | 2028-09-01 | 2028-09-01 | 2026 | 2026 | 2028 | 2028
DSO-43 | Courtlough (M1) 110 kV/38 kV/MV | Dublin | Portfolio | DSO | 110 | Pipeline
DSO-45 | Dalton G3 | Monaghan | Portfolio | DSO |  | Pipeline | 2026-07-01 | 2026-12-01 | 2028-06-01 | 2028-06-01 | 2026 | 2026 | 2028 | 2028
DSO-51 | Bellacorrick uprate to 2x63 MVA | Mayo | Portfolio | DSO |  | Pipeline
DSO-52 | Limerick G1 | Limerick | Portfolio | DSO |  | Pipeline | 2026-08-01 | 2026-12-30 | 2027-09-17 | 2029-05-28 | 2026 | 2026 | 2027 | 2029
CP1626 | Kinnegad G4 | Meath | Portfolio | DSO |  | Pipeline | 2026-05-14 | 2026-09-01 | 2027-12-01 | 2027-12-01 | 2026 | 2026 | 2027 | 2027
DSO-57 | Macetown G4 | Westmeath | Portfolio | DSO |  | Pipeline | 2026-08-01 | 2026-12-30 | 2028-05-31 | 2028-07-31 | 2026 | 2026 | 2028 | 2028
DSO-58 | Blake G3 | Clare | Portfolio | DSO |  | Pipeline | 2027-04-30 | 2028-01-03 | 2028-06-01 | 2028-09-01 | 2027 | 2028 | 2028 | 2028
CP1607 | College Park G4 | Galway | Portfolio | DSO |  | Pipeline | 2026-04-01 | 2026-09-01 |  | 2027-11-01 | 2026 | 2026 |  | 2027
CP1608 | Crane G5 | Wexford | Portfolio | DSO |  | Pipeline | 2026-06-01 | 2026-06-01 |  | 2028-10-01 | 2026 | 2026 |  | 2028
DSO-82 | Barrymore (Farran Solar) | Cork | Portfolio | DSO |  | Pipeline
DSO-83 | Macroom (Berrings Solar) ECP 2.2 | Galway | Portfolio | DSO |  | Pipeline
DSO-97 | Poolbeg (Ringsend) third transformer | Dublin | Portfolio | DSO |  | Pipeline
DSO-98 | Monread | Kildare | Portfolio | DSO |  | Pipeline | 2026-12-01 | 2027-09-01 | 2028-05-31 | 2028-07-31 | 2026 | 2027 | 2028 | 2028
CP1615 | Tipperary DSO | Tipperary | Portfolio | DSO |  | Pre PA | 2026-03-01 | 2026-06-01 | 2026-02-24 | 2027-12-31 | 2026 | 2026 | 2026 | 2027
ECP-2.4-07 | Coolcarrigan Solar P2 | Kildare | Portfolio | Customer Connection |  | Pipeline
ECP-2.4-14 | Culmullin Solar Farm | Meath | Portfolio | Customer Connection |  | Pipeline
ECP-2.4-18 | Fieldstown Extension No.2 | Dublin | Portfolio | Customer Connection |  | Pipeline
CP1589 | Friarstown Solar Farm | Westmeath | Portfolio | Customer Connection |  | Pipeline
ECP-2.4-21 | Ballyroe Solar Extension | Cork | Portfolio | Customer Connection |  | Pipeline
ECP-2.4-23 | Barnaleen Solar Phase 2 | Cork | Portfolio | Customer Connection |  | Pipeline
ECP-2.4-25 | Reask Phase 2 | Limerick | Portfolio | Customer Connection |  | Pipeline
ECP-2.4-29 | Tawnaghmore DC Power | Mayo | Portfolio | Customer Connection |  | Pipeline
ECP-2.4-37 | Tarbert BESS | Kerry | Portfolio | Customer Connection |  | Pipeline
ECP-2.4-38 | Kilmorna Energy Storage Facility | Kerry | Portfolio | Customer Connection |  | Pipeline
CP1632 | Flagford Battery Storage | Roscommon | Portfolio | Customer Connection |  | Pipeline
ECP-2.4-49 | Aghada Power Station | Cork | Portfolio | Customer Connection |  | Pipeline
CP1616 | Tullabeg Phase 3 | Wexford | Portfolio | Customer Connection |  | Pipeline
ECP-2.4-54 | Templemichael Solar Plus Storage Facility | Longford | Portfolio | Customer Connection |  | Pipeline
ECP-2.4-55 | Clondardis Solar | Westmeath | Portfolio | Customer Connection |  | Pipeline
ECP-2.4-57 | Darthogue Solar Farm Ext 2 | Meath | Portfolio | Customer Connection |  | Pipeline
ECP-2.4-61 | Ballysumaghan BESS & SC | Clare | Portfolio | Customer Connection |  | Pipeline
CP0848 | Castlebar-Cloon 110 kV Line Uprate-Refurb | Mayo | Portfolio | System Reinforcement | 110 | Post PA | 2020-09-16 | 2023-12-15 | 2026-09-30 | 2028-11-30 | 2020 | 2023 | 2026 | 2028
CP1004 | Killonan - Limerick No 1 110 kV Uprate | Limerick | Portfolio | Asset Refurbishment | 110 | Post PA | 2024-09-12 | 2025-12-11 |  | 2028-11-30 | 2024 | 2025 |  | 2028
CP1078 | Lanesboro – Sliabh Bawn 110 KV Line Uprate | Longford | Portfolio | System Reinforcement | 110 | Post PA | 2021-02-18 | 2024-03-06 |  | 2030-11-01 | 2021 | 2024 |  | 2030
CP1104 | Pollaphuca Refurbishment Project | Kildare | Portfolio | Asset Refurbishment |  | Post PA | 2023-09-08 | 2025-12-22 |  | 2028-05-29 | 2023 | 2025 |  | 2028
CP1108 | Dunstown Station 400-220 kV Protection Upgrade | Kildare | Portfolio | Asset Refurbishment | 400 | Post PA | 2020-05-18 | 2021-03-19 |  |  | 2020 | 2021
CP1144 | Kinnegad 110 kV station, Derryiron 110 kV bay conductor uprate | Meath | Portfolio | System Reinforcement | 110 | Post PA | 2021-01-22 | 2021-12-09 | 2026-11-26 | 2028-11-30 | 2021 | 2021 | 2026 | 2028
CP1153 | Oldstreet Tynagh & Cashla 400 kV and 220 kV Protection Upgrade | Westmeath | Portfolio | Asset Refurbishment | 400 | Post PA | 2020-11-12 | 2021-08-05 | 2025-10-02 | 2027-11-30 | 2020 | 2021 | 2025 | 2027
CP1156 | Sligo 110 kV Station - Shrananagh 1 & 2 Bay uprates | Sligo | Portfolio | System Reinforcement | 110 | Post PA | 2021-06-18 | 2022-06-02 | 2025-11-10 | 2028-11-30 | 2021 | 2022 | 2025 | 2028
CP1207 | Lisheen - Thurles 110 kV Protection Upgrade | Tipperary | Portfolio | Asset Refurbishment | 110 | Post PA | 2021-11-04 | 2022-10-25 |  | 2028-10-05 | 2021 | 2022 |  | 2028
CP1211 | Bandon Dunmanway 110 kV circuit thermal capacity | Cork | Portfolio | System Reinforcement | 110 | Post PA | 2022-01-21 | 2024-08-07 | 2027-12-04 | 2027-12-04 | 2022 | 2024 | 2027 | 2027
CP1250 | Sprecher and Schuh Circuit Breaker replacement | Mayo | Portfolio | Asset Refurbishment |  | Post PA | 2023-10-09 | 2025-10-28 | 2027-04-01 | 2028-10-18 | 2023 | 2025 | 2027 | 2028
CP1322 | Cathaleens Fall - Coraclassy 110 kV circuit 1 (DLR) | Cavan | Portfolio | System Reinforcement | 110 | Post PA | 2023-04-05 | 2024-09-27 |  |  | 2023 | 2024
CP1470 | Galway - Salthill Thermal Capacity Need | Galway | Portfolio | System Reinforcement |  | Post PA | 2024-12-20 | 2025-12-17 |  | 2029-11-20 | 2024 | 2025 |  | 2029
CP1538 | Prospect Land Acquisition | Galway | Portfolio | Asset Refurbishment |  | Pipeline |  | 2025-04-24 |  |  |  | 2025
CP1555 | Louth Woodland 220kV OHL diversion | Louth | Portfolio | Diversion | 220 | Pre PA | 2025-10-01 | 2026-09-30 | 2026-11-30 | 2027-12-07 | 2025 | 2026 | 2026 | 2027
CP1269 | The Dell Solar Lodgewood 220kV Crory Station | Galway | Portfolio | Customer Connection | 220 | Post PA | 2022-09-01 | 2023-12-06 | 2026-04-02 | 2026-04-02 | 2022 | 2023 | 2026 | 2026
CP0813 | Trien 110 kV Station Works | Kerry | Portfolio | System Reinforcement |  | Post PA | 2019-04-04 | 2021-10-22 |  | 2026-12-31 | 2019 | 2021 |  | 2026
CP1022 | Maynooth - Turlough Hill PLC Replacement | Kildare | Portfolio | Asset Refurbishment |  | Post PA | 2018-06-22 | 2019-12-06 |  | 2026-12-31 | 2018 | 2019 |  | 2026
CP1062 | Drombeg Solar - 110 kV Station | Kerry | Portfolio | Customer Connection | 110 | Post EI | 2019-06-28 | 2020-12-17 | 2025-10-31 | 2026-03-26 | 2019 | 2020 | 2025 | 2026
CP1255 | T-3 P483 Castlelost FlexGen | Galway | Portfolio | Customer Connection |  | Post PA | 2022-05-04 | 2023-08-28 |  | 2026-05-15 | 2022 | 2023 |  | 2026
CP1256 | T-3 P481 Greener Ideas Profile Park | Westmeath | Portfolio | Customer Connection |  | Post PA | 2022-05-05 | 2024-05-17 |  | 2026-06-12 | 2022 | 2024 |  | 2026
CP1359 | Lenalea 110 kV station (Drumnahough Wind Farm) | Donegal | Portfolio | Customer Connection | 110 | Post PA | 2024-09-04 | 2025-05-29 | 2026-11-06 | 2027-03-01 | 2024 | 2025 | 2026 | 2027
CP1430 | Lanesboro 110 kV Station (Ballycore Solar) | Tipperary | Portfolio | Customer Connection | 110 | Post PA | 2023-12-06 | 2024-12-04 | 2026-09-22 | 2026-09-22 | 2023 | 2024 | 2026 | 2026
CP1480 | Cruiserath 220kV Station Phase 3 (Amazon Web Services) | Dublin | Portfolio | Customer Connection | 220 | Post EI | 2024-05-29 | 2025-06-24 | 2025-11-07 | 2026-01-27 | 2024 | 2025 | 2025 | 2026
This shape represents a table slicer. Table slicers are not supported in this version of Excel. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2007 or earlier, the slicer can’t be used.
This shape represents a table slicer. Table slicers are not supported in this version of Excel. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2007 or earlier, the slicer can’t be used.
This shape represents a table slicer. Table slicers are not supported in this version of Excel. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2007 or earlier, the slicer can’t be used.
This shape represents a table slicer. Table slicers are not supported in this version of Excel. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2007 or earlier, the slicer can’t be used.
This shape represents a table slicer. Table slicers are not supported in this version of Excel. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2007 or earlier, the slicer can’t be used.

## 2 - Non-PR6 Projects
Non-PR6 Projects
The Non PR6 Projects tabworksheet provides transparency of transmission projects that are part of the wider transmission programme including projects at an early stage of development with indicative or unconfirmed timelines and projects not currently within the PR6 delivery scope. Any future proposal to progress a Non PR6 project within PR6 will be subject to the relevant regulatory and governance and regulatory processes.
CP Number | Project Name | Project Driver | Voltage (kV) | CA / GW3 | PA Signed | First Significant Energisation | Final Energisation
CP0817 | Flagford - Sliabh Bawn 110 kV circuit uprate | System Reinforcement | 110 | 2021-02-18 | 2022-06-02 |  | 2025-06-20
CP0857 | Paint Towers Nationwide and refurbish Kilbarry Marina double circuit | Asset Refurbishment | 220 | 2014-02-17 | 2014-11-24 |  | 2025-08-15
CP1031 | Flagford 220 kV Station Sprecher & Schuh CB Replacement | Asset Refurbishment | 220 | 2018-06-01 | 2019-10-21 |  | 2024-11-11
CP1055 | Harristown Solar Farm | Customer Connection | 110
CP1149 | Newbridge - Cushaling 110 kV line, Stations bay conductors and lead-in conductor uprate | System Reinforcement | 110 | 2021-01-22 | 2021-11-04
CP1158 | Rattin 110 kV Station (Clonfad Solar) | Customer Connection | 110 | 2021-01-19 | 2022-12-22 | 2025-12-12 | 2025-12-18
CP1167 | Drybride - Oldbridge - Platin 110 kV line uprate | Customer Connection | 110 | 2021-03-18 | 2023-10-27 | 2025-06-05 | 2025-08-18
CP1200 | Carrickmines Area 220 kV Cable Ducting | System Reinforcement | 220 | 2021-09-30 | 2022-12-20
CP1220 | Garrintaggart 110 kV Station - Pinewoods Wind Farm | Customer Connection | 110
CP1232 | Derryiron 110 kV Busbar Uprate | System Reinforcement | 110 | 2022-04-29 | 2023-07-06 |  | 2025-09-12
CP1262 | Shanonagh 110kV Station | Customer Connection | 110
CP1277 | Intel 110kV line diversion | Conflict | 110 | 2022-11-30 | 2024-11-29 | 2025-09-03 | 2025-09-04
CP1286 | Tonroe 110kV Station DSO | Customer Connection | 110 | 2023-07-19 | 2024-12-09
CP1304 | Strategic Spares for OHL, Stations and Cables | Asset Refurbishment | 110 | 2023-03-08 | 2024-12-16
CP1317 | Bellacorrick - Castlebar 110 kV circuit 1 (DLR) | System Reinforcement | 110
CP1321 | Cashla - Dalton 110 kV circuit 1 (DLR) | System Reinforcement | 110 | 2023-03-23 | 2024-06-28
CP1324 | Clashavoon - Knockraha or Cullenagh - Knockraha 220 kV lines (PFC) | System Reinforcement | 220
CP1370 | Connections Projects Placeholder (ECP 2-3-23) | Customer Connection | Pipeline
CP1371 | Connections Projects Placeholder (ECP 2-3-24) | Customer Connection | Pipeline
CP1376 | Pollagh 110kV Station (Shronowen Wind Farm) | Customer Connection | 110 | 2024-07-03
CP1381 | Maynooth - Rinawade 110V line uprate | System Reinforcement | 110
CP1382 | Increased capacity Cullenagh-Waterford | System Reinforcement
CP1383 | Killonan - Knockraha 220 kV line (PFC) | System Reinforcement | 220
CP1387 | Letterkenny - Cathaleen_s or Letterkenny - Clogher 110 kV lines (PFC) | System Reinforcement | 110
CP1388 | Letterkenny - Tievebrack - Binbane 110 kV lines (PFC) | System Reinforcement | 110
CP1391 | Maynooth-Derryiron-Timahoe 110 kV Line Uprate | System Reinforcement | 110 | 2023-04-06 | 2025-12-18
CP1393 | Offshore Phase 1 Project 1 - Skerd Rocks | Customer Connection | 220
CP1395 | Offshore Phase 1 Project 3 - Codling Wind Park 2 | Customer Connection
CP1399 | Offshore Phase 2 Project 1 - Placeholder | Customer Connection
CP1400 | Offshore Phase 2 Project 2 - Placeholder | Customer Connection
CP1404 | Sligo - Srananagh - Corderry 110 kV lines (PFC) | System Reinforcement | 110
CP1497 | Derrycarney - Portlaoise 110 kV Fibre Wrapping | System Reinforcement
DSO-01 | DSO Station 1 | TBC
DSO-04 | DSO Station 4 | TBC
DSO-05 | DSO Station 5 | TBC
DSO-07 | DSO Station 7 | TBC
DSO-08 | DSO Station 8 | TBC
DSO-09 | DSO Station 9 | TBC
DSO-11 | DSO Station 11 | TBC
DSO-14 | DSO Station 14 | TBC
DSO-20 | DSO Station 20 | TBC
DSO-31 | DSO Station 31 | TBC
DSO-39 | DSO Station 39 | TBC
DSO-41 | DSO Station 41 | TBC
DSO-42 | DSO Station 42 | TBC
EAM01 | Station Refurbishments Replacement | TBC
EAM02 | Transformer Replacements x6 | TBC
EAM03 | Replacement of existing SVC’s x2 | TBC
EAM04 | Replacement of Mobile Cap Banks x4 | TBC
EAM07 | Battery / Generator Replacements | TBC
EAM10 | Bay Control Unit Replacements | TBC
EAM11 | Asbestos Surveys Replacement | TBC
EAM12 | Dedicated Transmission Asset Storage Facility Study | TBC
EAM13 | Replacement Ungreased / Core Greased Conductors | TBC
EAM14 | Replacement of 110 kV Cut Poles | TBC
EAM15 | Tower Painting | TBC
EAM17 | FCI Insulator Replacements | TBC
EAM18 | Sediver Insulator Replacements | TBC
EAM19 | Pilot of Cathodic Protection for OHL | TBC
EAM20 | Artificial Intelligence Research for OHL inspections | TBC
EAM21 | Cables OLCM, PD Monitoring & DAS investigation | TBC
EAM22 | Improvements with reporting & data management | TBC
EAM23 | Production of Corrosion Map for Ireland | TBC
EAM24 | Climate Change Adaptation Studies | TBC
EAM25 | Review design and specs for Link Box | TBC
EAM26 | Link Box Replacements x 25 | TBC
ECP 2-3.18 | Connections Projects Placeholder (ECP 2-3-18) | TBC
ECP 2-3.22 | Connections Projects Placeholder (ECP 2-3-22) | TBC
ECP-2.4-01 | Seven Hills Wind Farm | TBC
ECP-2.4-02 | Coom Green Energy Park | TBC
ECP-2.4-03 | Lyrenacarriga Windfarm and BESS | TBC
ECP-2.4-04 | White Hill Wind Farm | TBC
ECP-2.4-05 | Ballylongford Solar | TBC
ECP-2.4-06 | Kilcormac Solar | TBC
ECP-2.4-08 | Ballyvalode Solar | TBC
ECP-2.4-09 | Knockroe Wind Farm | TBC
ECP-2.4-10 | Garreenleen Solar Farm Phase 2 | TBC
ECP-2.4-11 | Modelligo Solar Farm | TBC
ECP-2.4-12 | Tincurry Solar Farm | TBC
ECP-2.4-13 | Rath Solar PV Extension | TBC
ECP-2.4-15 | TULLYNAMOYLE WIND FARM 6 | TBC
ECP-2.4-16 | Tullamore Solar Farm & BESS | TBC
ECP-2.4-17 | Mill Farm Solar | TBC
ECP-2.4-19 | Drummin Solar | TBC
ECP-2.4-22 | Ballyroe Solar | TBC
ECP-2.4-24 | Ballylough Solar Farm | TBC
ECP-2.4-26 | Ballynahina Solar Farm**planning not finalised | TBC
ECP-2.4-27 | Golden Forth Solar Park | TBC
ECP-2.4-28 | Ballymac Phase 2 | TBC
ECP-2.4-30 | CherryOrchard Solar Park | TBC
ECP-2.4-31 | Ballycunneen PV | TBC
ECP-2.4-32 | Main Solar | TBC
ECP-2.4-33 | Mullagharoy Solar Farm | TBC
ECP-2.4-34 | Cloondara Solar Park | TBC
ECP-2.4-35 | Tonroe Battery Storage System | TBC
ECP-2.4-36 | Lissane West Solar Farm | TBC
ECP-2.4-39 | Silloge/Navan Battery Storage Facility | TBC
ECP-2.4-40 | Clare East BESS Facility | TBC
ECP-2.4-41 | RICHMOND BATTERY STORAGE FACILITY | TBC
ECP-2.4-42 | Horsepasture Battery Storage | TBC
ECP-2.4-44 | Ballyglasheen West BESS Facility | TBC
ECP-2.4-45 | Mothel PV and BESS | TBC
ECP-2.4-46 | Ballykenny Solar | TBC
ECP-2.4-47 | Tooraskeheen Solar & Storage | TBC
ECP-2.4-48 | Spion Kop Windfarm Ext. (Ext to DG978) | TBC
ECP-2.4-50 | Ballymoneen Phase 2 | TBC
ECP-2.4-51 | JOHNSTOWN SOLAR PARK | TBC
ECP-2.4-53 | Lismeen Solar Farm | TBC
ECP-2.4-56 | Sandford Energy Solar Farm Ext. | TBC
ECP-2.4-58 | Cronalaght 3 Wind Farm | TBC
ECP-2.4-59 | Mount Cronalaght Windfarm Repowering | TBC
ECP-2.4-60 | Leam Windfarm | TBC
TPSP 22 | Deenes - Drybridge 110 kV (DLR) | TBC
TPSP 24 | Baltrasna - Corduff 110 kV (DLR) | TBC
TPSP 25 | Crane - Wexford 110 kV (DLR) | TBC
TPSP 26 | Great Island - Waterford 1 110 kV (DLR) | TBC
TPSP 27 | Srananagh - Cathaleen's Fall 2 110 kV (DLR) | TBC
TPSPGrp01 | Macetown 110 kV Busbar Uprate | TBC
TPSPGrp02 | Castleview 110 kV Busbar Uprate | TBC
TPSPGrp03 | Cow Cross 110 kV Busbar Uprate | TBC
TPSPGrp04 | Dundalk 110 kV Busbar Uprate | TBC
TPSPGrp05 | Midleton 110 kV Busbar Uprate | TBC
TPSPGrp06 | Mullagharlin 110 kV Busbar Uprate | TBC
TPSPGrp07 | DSO Demand Driven Projects | TBC
TPSPGrp08 | Renewable / Critical Infrastructure / System Reinforcement / System Reinforcement Driven | TBC
TPSPGrp09 | SOPCM Driven Project A | TBC
TPSPGrp10 | SOPCM Driven Project B | TBC
TPSPGrp11 | TES Driven 2026 | TBC
TPSPGrp12 | TES Driven 2028 | TBC
TPSPGrp13 | Dublin 400 kV Project | TBC
TPSPGrp14 | Cork 220/400 kV Project | TBC
TPSPGrp15 | Maynooth - Shannonbridge - Killonan - Knockraha 400 kV Corridor Project | TBC
TPSPGrp16 | Offshore Supporting Infrastructure Project | TBC
TPSPGrp17 | Short Circuit Mitigation Project 2026 | TBC
TPSPGrp18 | Short Circuit Mitigation Project 2028 | TBC
TPSPGrp19 | Farranrory (CP1280 Ballyragget future proofed cable) | TBC
TPSPGrp20 | Toolestown Solar (CP1459 East Kildare) | TBC
TPSPGrp21 | Midlands (CP1453 - Blake) | TBC
TPSPGrp22 | Wexford DSO demand (Tracystown Solar (CP1260)) | TBC
TPSPGrp23 | NISA cable and remote end station | TBC
TPSPGrp24 | Dernacart (link to Bogtown) (ECP2.4) | TBC
TPSPGrp25 | Culmullin - additional bays for future connection options (ECP 2.4) | TBC
TPSPGrp26 | Friarstown (ECP 2.4) | TBC

## Insights Dashboard
Transmission Infrastructure Delivery Dashboard
Project Information - Q1 2026
The charts below provide an overview of the projects to be delivered or developed in PR6
Number Of PR6 Projects
405
PR6 Project Milestones Summary - Q1 2026
The charts below outlines the number of milestone achieved and forecasted in PR6 annually, in line with the current project schedules in this Q1 2026 TID report.
This chart isn’t available in your version of Excel. Editing this shape or saving this workbook into a different file format will permanently break the chart.

## Definitions
Definitions
CP Number | Unique Capital Project (CP) identifier used by EirGrid & ESB Networks.
Project Name | Official EirGrid & ESN Networks name to describe the project.
County | County of Ireland in which the project is located.
Portfolio | Indicaates whether the project is designated as a priority or portfolio project.
Project Driver | Primary driver for which the project is required.
Voltage (kV) | Nominal operating volage of the project's associated infrastructure in kilovolts.
Stage | The project’s current position in the delivery lifecycle.
Capital Approval | EirGrid's formal governace approval for project scope, cost, and timeframe to proceed.
PA Signed | The Project Agreement between EirGrid & ESB Networks has been jointly signed & agreed.
First Significant Energisation | The date the first major part of the project is energised.
Final Energisation | The date the project is fully energised and operational.
Q1-26 Changes | Identifies projects with schedule changes in Q1 2026, against the CRU's FD Baseline
Guidance Note | Please refer to EirGrid's website

## TID Future Development
Future Development
In this section we outline areas for future development of the TID Update throughout PR6
Development | Expected Implementation
Summary of changes between TID quarterly updates. | Q2-26
Comparison of milestones against the PR6 baseline, via a RAG status | Q2-26
Summary of Outputs & Outcomes for PR6 | Q2-26
Outputs & Outcomes per project following a detailed SO review in 2026. | TBC
Third party driven dependencies - A New Colour Coding | TBC

## Pivot data (hidden)
Row Labels | Count of CP Number |  |  | Row Labels | Count of CP Number | Year | CA Actual | PA Actual | FSEI Actual | FEI Actual
Asset Refurbishment | 89 |  |  | Post EI | 4 | 2026 | 38 | 61 | 52 | 40
Customer Connection | 130 |  |  | Post PA | 143 | 2027 | 7 | 23 | 45 | 48
System Reinforcement | 115 |  |  | Pre PA | 156 | 2028 | 6 | 26 | 23 | 44
DSO | 66 |  |  | Pipeline | 102 | 2029 | 6 | 31 | 13 | 30
Diversion | 5 |  |  | Grand Total | 405 | 2030 | 0 | 23 | 6 | 17
Grand Total | 405
Row Labels | Count of CP Number | County | # of projects
Meath | 28 | Meath | 28
Laois | 7 | Laois | 7
Louth | 8 | Louth | 8
Kildare | 40 | Kildare | 40
Galway | 36 | Galway | 36
Wexford | 14 | Wexford | 14
Clare | 14 | Clare | 14
Westmeath | 15 | Westmeath | 15
Kerry | 18 | Kerry | 18
Roscommon | 16 | Roscommon | 16
Dublin | 42 | Dublin | 42
Donegal | 14 | Donegal | 14
Wicklow | 12 | Wicklow | 12
Cork | 52 | Cork | 52
Limerick | 11 | Limerick | 11
Offaly | 13 | Offaly | 13
Waterford | 3 | Waterford | 3
Mayo | 15 | Mayo | 15
Leitrim | 3 | Leitrim | 3
Longford | 3 | Longford | 3
Monaghan | 5 | Monaghan | 5
Tipperary | 9 | Tipperary | 9
Carlow | 8 | Carlow | 8
Sligo | 6 | Sligo | 6
Cavan | 5 | Cavan | 5
Kilkenny | 8 | Kilkenny | 8
Grand Total | 405