## Cover
Transmission Infrastructure
Delivery Report - Q2 2026
Disclamer - The TID has been produced by EirGrid and is undergoing further reivew by ESB Networks in line with established goverance processes.
EirGrid has followed accepted industry practice in the collection and analysis of data available. While all reasonable care has been taken in the preparation of this data, EirGrid is not responsible for any loss that may be attributed to the use of this information. Prior to taking business decisions, any parties are advised to seek separate and independent opinion in relation to the matters covered by this publication and should not rely solely upon data and information contained herein. Information in this document does not amount to a recommendation in respect of any possible investment. This document does not purport to contain all the information that a prospective investor or stakeholder may need.

## 1 - TID Report
Transmission Infrastructure Delivery Update Report
2026-06-30 | [8 empty] | Current Project Schedule Dates as of 30th June 2026 |  |  |  | CRU PR6 Final Determination Baseline Dates (CRU2025260)
CP Number | Project Name | County | Portfolio | Group | In FD? | Project Driver | Voltage (kV) | Stage | Capital Approval (Current Date) | PA Signed (Current Date) | First Significant EI (Current Date) | Final EI (Current Date) | Capital Approval (Baseline) | PA Signed (Baseline) | First Significant EI (Baseline) | Final EI (Baseline) | Q2-26 Updates | CA Current Year | PA Current Year | FSEI Current Year | FEI Current Year | CA RAG | PA RAG | FSEI RAG | FEI RAG
CP0466 | North South 400 kV Interconnector - RoI | Multiple | Priority | Group 1 | TRUE | System Reinforcement | 400 | Pre PA | 2016-09-21 |  | 2028-12-20 | 2031-10-06 | 2016-09-21 | 2026-02-03 | 2028-12-20 | 2031-10-06 | No Updates | 2016 |  | 2028 | 2031 | PRE-PR6 | Not Achieved | Not Achieved | Not Achieved
CP0585 | Laois Kilkenny (Coolnabacky) 400 kV Station - New Station & Associated Lines & Station Works | Multiple | Priority | Group 1 | TRUE | System Reinforcement | 400 | Post PA | 2008-04-16 | 2016-06-17 |  | 2027-09-17 | 2008-04-16 | 2016-06-17 | Completed | 2027-06-30 | Date(s) Updated | 2008 | 2016 |  | 2027 | PRE-PR6 | PRE-PR6 | Not Achieved | Not Achieved
CP0799 | Louth 220 kV Station Refurbishment | Multiple | Priority | Group 1 | TRUE | Asset Refurbishment | 220 | Post PA | 2013-09-25 | 2020-03-12 | 2021-12-31 | 2032-12-31 | 2013-09-25 | 2020-03-12 | 2025-10-10 | 2032-12-31 | Date(s) Updated | 2013 | 2020 | 2021 | 2032 | PRE-PR6 | PRE-PR6 | PRE-PR6 | Not Achieved
CP0808 | Maynooth 220 kV Station Reconfiguration | Kildare | Priority | Group 1 | TRUE | System Reinforcement | 220 | Post PA | 2021-03-16 | 2024-12-05 | 2028-12-20 | 2031-12-31 | 2021-03-16 | 2024-12-05 | 2028-12-20 | 2031-12-31 | No Updates | 2021 | 2024 | 2028 | 2031 | PRE-PR6 | PRE-PR6 | Not Achieved | Not Achieved
CP0816 | North Connacht 110 kV Project | Multiple | Priority | Group 1 | TRUE | System Reinforcement | 110 | Post PA | 2018-09-12 | 2023-12-20 | 2026-07-30 | 2028-12-31 | 2018-09-12 | 2023-12-20 | 2028-12-20 | 2028-12-31 | Date(s) Updated | 2018 | 2023 | 2026 | 2028 | PRE-PR6 | PRE-PR6 | Not Achieved | Not Achieved
CP0866 | Great Island - Kellis 220 kV Line Uprate | Multiple | Priority | Group 1 | TRUE | System Reinforcement | 220 | Post PA | 2022-11-16 | 2025-12-18 | 2027-11-30 | 2029-12-31 | 2022-11-16 | 2025-12-02 | 2027-11-30 | 2029-12-31 | No Updates | 2022 | 2025 | 2027 | 2029 | PRE-PR6 | PRE-PR6 | Not Achieved | Not Achieved
CP0966 | Kildare Meath Grid Reinforcement | Multiple | Priority | Group 1 | TRUE | System Reinforcement | 400 | Post PA | 2021-03-24 | 2025-09-19 | 2029-12-20 | 2029-12-21 | 2021-03-24 | 2025-09-25 | 2029-12-20 | 2029-12-31 | No Updates | 2021 | 2025 | 2029 | 2029 | PRE-PR6 | PRE-PR6 | Not Achieved | Not Achieved
CP0967 | Moneypoint 400 kV Series Capacitor | Multiple | Priority | Group 1 | TRUE | System Reinforcement | 400 | Pre PA | 2015-08-31 | 2026-09-29 | 2030-12-31 | 2030-12-31 | 2015-08-31 | 2026-09-29 | 2030-12-31 | 2030-12-31 | No Updates | 2015 | 2026 | 2030 | 2030 | PRE-PR6 | Not Achieved | Not Achieved | Not Achieved
CP0968 | Dunstown 400 kV Series Capacitor | Multiple | Priority | Group 1 | TRUE | System Reinforcement | 400 | Post PA | 2016-06-15 | 2023-12-13 | 2027-08-20 | 2027-12-31 | 2016-06-15 | 2023-12-13 | 2027-08-20 | 2027-12-31 | No Updates | 2016 | 2023 | 2027 | 2027 | PRE-PR6 | PRE-PR6 | Not Achieved | Not Achieved
CP0969 | Oldstreet-Woodland 400 kV Series Capacitor | Multiple | Priority | Group 1 | TRUE | System Reinforcement | 400 | Post PA | 2016-06-15 | 2023-12-13 | 2028-08-20 | 2028-12-31 | 2016-06-15 | 2023-12-13 | 2028-08-20 | 2028-12-31 | No Updates | 2016 | 2023 | 2028 | 2028 | PRE-PR6 | PRE-PR6 | Not Achieved | Not Achieved
CP0970 | Cross Shannon 400 kV Cable | Multiple | Priority | Group 1 | TRUE | System Reinforcement | 400 | Post PA | 2016-09-21 | 2021-12-16 | 2028-12-20 | 2028-12-31 | 2016-09-21 | 2021-12-16 | 2028-12-20 | 2028-12-31 | No Updates | 2016 | 2021 | 2028 | 2028 | PRE-PR6 | PRE-PR6 | Not Achieved | Not Achieved
CP0982 | Flagford Sligo Capacity Needs | Multiple | Priority | Group 1 | TRUE | System Reinforcement | 110 | Pre PA | 2025-12-19 | 2029-03-14 | 2030-12-31 | 2032-12-31 | 2025-12-19 | 2029-03-14 | 2030-12-31 | 2032-12-31 | No Updates | 2025 | 2029 | 2030 | 2032 | PRE-PR6 | Not Achieved | Not Achieved | Not Achieved
CP1021 | East Meath - North Dublin Reinforcement | Multiple | Priority | Group 1 | TRUE | System Reinforcement | 400 | Post PA | 2022-06-07 | 2025-09-19 | 2029-12-20 | 2029-12-20 | 2022-06-07 | 2025-09-04 | 2029-12-20 | 2029-12-20 | No Updates | 2022 | 2025 | 2029 | 2029 | PRE-PR6 | PRE-PR6 | Not Achieved | Not Achieved
CP1023 | Letterkenny station redevelopment | Donegal | Priority | Group 1 | TRUE | System Reinforcement | 110 | Pre PA | 2021-06-17 | 2026-12-04 | 2029-11-01 | 2031-12-31 | 2021-06-17 | 2025-12-19 | 2029-11-01 | 2031-12-31 | No Updates | 2021 | 2026 | 2029 | 2031 | PRE-PR6 | Not Achieved | Not Achieved | Not Achieved
CP1100 | Finglas - North Wall Cable Replacement | Dublin | Priority | Group 1 | TRUE | System Reinforcement | 220 | Post PA | 2022-06-28 | 2024-12-19 |  | 2029-12-31 | 2022-06-28 | 2024-12-19 |  | 2029-12-31 | No Updates | 2022 | 2024 |  | 2029 | PRE-PR6 | PRE-PR6 | Not Achieved | Not Achieved
CP1146 | Carrickmines - Poolbeg 220 kV Cable Replacement | Dublin | Priority | Group 1 | TRUE | System Reinforcement | 220 | Pre PA | 2021-12-16 | 2028-12-15 | 2030-01-03 | 2031-12-31 | 2021-12-16 | 2028-12-15 |  | 2031-12-31 | No Updates | 2021 | 2028 | 2030 | 2031 | PRE-PR6 | Not Achieved | Not Achieved | Not Achieved
CP1150 | Inchicore - Poolbeg 2 220 kV Cable Replacement | Dublin | Priority | Group 1 | TRUE | System Reinforcement | 220 | Pre PA | 2021-12-20 | 2027-09-14 | 2031-12-19 | 2031-12-20 | 2021-12-20 | 2027-09-14 | 2031-12-31 | 2031-12-31 | No Updates | 2021 | 2027 | 2031 | 2031 | PRE-PR6 | Not Achieved | Not Achieved | Not Achieved
CP1157 | Inchicore - Poolbeg 1 220 kV Cable Replacement | Dublin | Priority | Group 1 | TRUE | System Reinforcement | 220 | Pre PA | 2021-12-20 | 2027-09-14 | 2031-12-19 | 2031-12-19 | 2021-12-20 | 2027-09-14 | 2031-12-31 | 2031-12-31 | No Updates | 2021 | 2027 | 2031 | 2031 | PRE-PR6 | Not Achieved | Not Achieved | Not Achieved
CP1190 | Poolbeg 220 kV Station | Dublin | Priority | Group 1 | TRUE | System Reinforcement | 220 | Post PA | 2021-12-16 | 2024-12-06 | 2028-12-20 | 2030-12-31 | 2021-12-16 | 2024-12-06 | 2028-12-20 | 2030-12-31 | No Updates | 2021 | 2024 | 2028 | 2030 | PRE-PR6 | PRE-PR6 | Not Achieved | Not Achieved
CP1194 | Woodland 400 kV Station Redevelopment | Meath | Priority | Group 1 | TRUE | System Reinforcement | 400 | Post PA | 2022-03-21 | 2023-12-14 | 2025-04-18 | 2032-12-31 | 2022-03-21 | 2023-12-14 | Completed | 2032-12-31 | Date(s) Updated | 2022 | 2023 | 2025 | 2032 | PRE-PR6 | PRE-PR6 | PRE-PR6 | Not Achieved
CP1196 | Arklow - Ballybeg - Carrickmines 110 kV capacity Needs | Multiple | Priority | Group 1 | TRUE | System Reinforcement | 220 | Pre PA | 2024-05-16 | 2028-09-12 | 2028-09-07 | 2032-09-19 | 2024-05-16 | 2028-06-09 | 2029-09-01 | 2032-09-19 | No Updates | 2024 | 2028 | 2028 | 2032 | PRE-PR6 | Not Achieved | Not Achieved | Not Achieved
CP1213 | Belcamp 220 kV Busbar Extension | Dublin | Priority | Group 1 | TRUE | System Reinforcement | 220 | Post PA | 2021-12-15 | 2025-03-28 | 2029-04-20 | 2029-05-28 | 2021-12-15 | 2025-03-28 | 2029-04-20 | 2029-05-28 | No Updates | 2021 | 2025 | 2029 | 2029 | PRE-PR6 | PRE-PR6 | Not Achieved | Not Achieved
CP1214 | Fingal to East Meath Grid Reinforcement | Multiple | Priority | Group 1 | TRUE | System Reinforcement | 400 | Pre PA | 2024-12-17 | 2028-03-07 | 2031-04-30 | 2031-12-19 | 2024-12-17 | 2028-03-07 | 2031-04-30 | 2031-12-20 | No Updates | 2024 | 2028 | 2031 | 2031 | PRE-PR6 | Not Achieved | Not Achieved | Not Achieved
CP1215 | Knockraha station Celtic IC Non contested works | Cork | Priority | Group 1 | TRUE | System Reinforcement | 220 | Post PA | 2022-02-23 | 2023-12-06 |  | 2026-11-26 | 2022-02-23 | 2023-12-06 | 2026-06-20 | 2026-11-26 | Date(s) Updated | 2022 | 2023 |  | 2026 | PRE-PR6 | PRE-PR6 | Not Achieved | Not Achieved
CP1216 | Poolbeg - North Wall 220 kV Cable Replacement | Dublin | Priority | Group 1 | TRUE | System Reinforcement | 220 | Pre PA | 2022-05-31 | 2027-06-04 |  | 2031-06-30 | 2022-05-31 | 2027-06-04 |  | 2031-06-30 | No Updates | 2022 | 2027 |  | 2031 | PRE-PR6 | Not Achieved | Not Achieved | Not Achieved
CP1226 | Kildare Dublin Grid Reinforcement | Multiple | Priority | Group 1 | TRUE | System Reinforcement | 220 | Pre PA | 2026-05-20 | 2029-08-27 | 2033-04-20 | 2034-04-20 | 2026-03-19 | 2029-05-29 | 2033-04-20 | 2034-04-20 | Date(s) Updated | 2026 | 2029 | 2033 | 2034 | Green | Not Achieved | Not Achieved | Not Achieved
CP1233 | Donegal - Srananagh Corridor | Multiple | Priority | Group 1 | TRUE | System Reinforcement | 220 | Pre PA | 2025-12-17 | 2029-12-12 | 2033-12-31 | 2033-12-31 | 2026-03-30 | 2029-12-12 | 2033-12-31 | 2033-12-31 | No Updates | 2025 | 2029 | 2033 | 2033 | PRE-PR6 | Not Achieved | Not Achieved | Not Achieved
CP1235 | Louth - Woodland 220 kV Uprate | Multiple | Priority | Group 1 | TRUE | System Reinforcement | 220 | Post PA | 2022-04-28 | 2024-12-18 | 2025-11-06 | 2029-12-03 | 2022-04-28 | 2024-12-18 | 2025-10-10 | 2029-12-03 | No Updates | 2022 | 2024 | 2025 | 2029 | PRE-PR6 | PRE-PR6 | PRE-PR6 | Not Achieved
CP1273 | Dublin Central Bulk Supply Point 220kV Substation | Dublin | Priority | Group 1 | TRUE | System Reinforcement | 220 | Pre PA | 2024-09-25 | 2026-09-29 | 2030-02-01 | 2031-12-01 | 2024-09-25 | 2026-09-29 | 2030-02-01 | 2031-12-01 | No Updates | 2024 | 2026 | 2030 | 2031 | PRE-PR6 | Not Achieved | Not Achieved | Not Achieved
CP0624 | Killonan 220 kV Station Refurbishment - Killonan Station Works | Multiple | Portfolio | Group 3 | TRUE | Asset Refurbishment | 220 | Post PA | 2011-09-30 | 2019-04-01 | 2026-11-24 | 2028-07-20 | 2011-09-30 | 2019-04-01 | 2026-11-24 | 2028-07-20 | No Updates | 2011 | 2019 | 2026 | 2028 | PRE-PR6 | PRE-PR6 | Not Achieved | Not Achieved
CP0644 | Bracklone 110 kV Station - DSO | Multiple | Portfolio | Group 3 | TRUE | DSO | 110 | Post EI | 2020-03-19 | 2022-06-01 |  | 2026-05-27 | 2020-03-19 | 2022-06-01 |  | 2027-03-04 | No Updates | 2020 | 2022 |  | 2026 | PRE-PR6 | PRE-PR6 | Not Achieved | Green
CP0646 | Finglas 110 kV Station Redevelopment | Dublin | Portfolio | Group 3 | TRUE | Asset Refurbishment | 110 | Post PA | 2009-08-28 | 2012-08-24 | 2026-09-18 | 2026-09-29 | 2009-08-28 | 2012-08-24 | 2026-09-18 | 2026-09-29 | No Updates | 2009 | 2012 | 2026 | 2026 | PRE-PR6 | PRE-PR6 | Not Achieved | Not Achieved
CP0692 | Inchicore - 220 kV GIS Station Upgrade | Multiple | Portfolio | Group 3 | TRUE | Asset Refurbishment | 220 | Post PA | 2016-09-21 | 2019-03-20 | 2026-10-22 | 2029-12-20 | 2016-09-21 | 2019-03-20 | 2026-10-22 | 2029-12-20 | No Updates | 2016 | 2019 | 2026 | 2029 | PRE-PR6 | PRE-PR6 | Not Achieved | Not Achieved
CP0693 | Baroda 110 kV station - 2 x110 kV Trafo Bays DSO | Kildare | Portfolio | Group 3 | TRUE | DSO | 110 | Post PA | 2019-06-14 | 2020-01-10 |  | 2028-03-24 | 2019-06-14 | 2020-01-10 |  | 2028-03-24 | No Updates | 2019 | 2020 |  | 2028 | PRE-PR6 | PRE-PR6 | Not Achieved | Not Achieved
CP0741 | Trabeg 110 kV station - uprate 2 x 110 kV transformer bays and control room extension DSO | Cork | Portfolio | Group 3 | TRUE | DSO | 110 | Post PA | 2020-06-03 | 2021-04-29 |  | 2027-02-26 | 2020-06-03 | 2021-04-29 |  | 2027-02-28 | No Updates | 2020 | 2021 |  | 2027 | PRE-PR6 | PRE-PR6 | Not Achieved | Not Achieved
CP0749 | Richardstown 220kV Station (Oriel Offshore WF) | Multiple | Portfolio | Group 5 | TRUE | Customer Connection | 220 | Pre PA | 2022-03-25 | 2026-12-21 |  |  | 2020-03-31 | 2024-12-20 |  | 2027-12-20 | Date(s) Updated | 2022 | 2026 |  |  | PRE-PR6 | Not Achieved | Not Achieved | Not Achieved
CP0792 | Finglas 220 kV Reconfiguration Project | Dublin | Portfolio | Group 3 | TRUE | Asset Refurbishment | 220 | Post PA | 2015-04-22 | 2018-03-11 |  | 2027-12-20 | 2015-04-22 | 2018-03-11 |  | 2027-12-20 | No Updates | 2015 | 2018 |  | 2027 | PRE-PR6 | PRE-PR6 | Not Achieved | Not Achieved
CP0796 | Knockraha station & installation of additional couplers | Cork | Portfolio | Group 3 | TRUE | System Reinforcement | 220 | Post PA | 2016-09-21 | 2016-09-30 | 2022-02-02 | 2033-06-30 | 2016-09-21 | 2016-09-30 | 2022-02-01 | 2033-06-30 | No Updates | 2016 | 2016 | 2022 | 2033 | PRE-PR6 | PRE-PR6 | PRE-PR6 | Not Achieved
CP0823 | Maynooth - Turlough Hill 220 kV line refurbishment | Multiple | Portfolio | Group 5 | TRUE | Asset Refurbishment | 220 | Pre PA | 2017-06-30 | 2026-11-12 | 2031-11-10 | 2033-09-02 | 2017-06-30 | 2025-09-04 |  | 2026-10-30 | Date(s) Updated | 2017 | 2026 | 2031 | 2033 | PRE-PR6 | Not Achieved | Not Achieved | Not Achieved
CP0835 | Coolnabacky - Portlaoise 110 kV line uprate | Laois | Portfolio | Group 3 | TRUE | System Reinforcement | 110 | Post PA | 2018-05-30 | 2025-10-24 | 2026-10-13 | 2026-10-13 | 2018-05-30 | 2025-11-14 | 2026-10-06 | 2026-10-09 | No Updates | 2018 | 2025 | 2026 | 2026 | PRE-PR6 | PRE-PR6 | Not Achieved | Not Achieved
CP0841 | Arva - Carrick-on-Shannon 110 kV line uprate | Multiple | Portfolio | Group 3 | TRUE | System Reinforcement | 110 | Post PA | 2020-05-21 | 2021-12-15 | 2027-11-29 | 2027-11-29 | 2020-05-21 | 2021-12-15 | 2026-05-29 | 2027-11-29 | Date(s) Updated | 2020 | 2021 | 2027 | 2027 | PRE-PR6 | PRE-PR6 | Not Achieved | Not Achieved
CP0867 | Flagford - Louth 220 kV Line Refurbishment | Multiple | Portfolio | Group 3 | TRUE | Asset Refurbishment | 220 | Post PA | 2015-04-20 | 2020-04-30 | 2026-05-29 | 2027-11-29 | 2015-04-20 | 2020-04-30 | 2027-05-31 | 2027-11-29 | Date(s) Updated | 2015 | 2020 | 2026 | 2027 | PRE-PR6 | PRE-PR6 | Green | Not Achieved
CP0868 | Knockraha - Raffeen 220 kV line refurbishment | Cork | Portfolio | Group 3 | TRUE | Asset Refurbishment | 220 | Post PA | 2015-10-30 | 2019-09-25 | 2021-02-27 | 2027-04-20 | 2015-10-30 | 2019-09-25 |  | 2026-10-02 | Date(s) Updated | 2015 | 2019 | 2021 | 2027 | PRE-PR6 | PRE-PR6 | PRE-PR6 | Not Achieved
CP0873 | Dunstown - Moneypoint 400 kV Refurbishment | Multiple | Portfolio | Group 3 | TRUE | Asset Refurbishment | 400 | Post PA | 2014-06-20 | 2019-12-05 | 2026-04-02 | 2027-11-30 | 2014-06-20 | 2019-12-05 | 2026-09-18 | 2027-11-30 | Date(s) Updated | 2014 | 2019 | 2026 | 2027 | PRE-PR6 | PRE-PR6 | Green | Not Achieved
CP0901 | Kilbarry - Knockraha 110 kV No 2 Line Refurbishment | Cork | Portfolio | Group 3 | TRUE | System Reinforcement | 110 | Post PA | 2020-05-13 | 2022-10-03 | 2026-10-09 | 2030-09-05 | 2020-05-13 | 2022-10-03 | 2027-11-10 | 2030-09-05 | Date(s) Updated | 2020 | 2022 | 2026 | 2030 | PRE-PR6 | PRE-PR6 | Not Achieved | Not Achieved
CP0907 | Dalton 110 kV Busbar | Mayo | Portfolio | Group 3 | TRUE | System Reinforcement | 110 | Post PA | 2021-10-01 | 2023-09-06 | 2025-08-27 | 2029-06-21 | 2021-10-01 | 2023-09-06 | 2025-08-27 | 2029-06-21 | No Updates | 2021 | 2023 | 2025 | 2029 | PRE-PR6 | PRE-PR6 | PRE-PR6 | Not Achieved
CP0917 | Prospect Tarbert 220 kV Cable Replacement Project | Multiple | Portfolio | Group 3 | TRUE | Asset Refurbishment | 220 | Pre PA | 2021-06-16 | 2026-12-02 | 2027-07-15 | 2027-09-20 | 2021-06-16 | 2025-12-18 | 2027-07-15 | 2027-09-18 | No Updates | 2021 | 2026 | 2027 | 2027 | PRE-PR6 | Not Achieved | Not Achieved | Not Achieved
CP0919 | Lanesboro 110 kV Station Redevelopment Project | Longford | Portfolio | Group 3 | TRUE | System Reinforcement | 110 | Post PA | 2017-12-28 | 2020-06-30 | 2028-05-01 | 2029-12-20 | 2017-12-28 | 2020-06-30 | 2027-03-12 | 2029-12-20 | Date(s) Updated | 2017 | 2020 | 2028 | 2029 | PRE-PR6 | PRE-PR6 | Not Achieved | Not Achieved
CP0949 | Kilnap 110 kV GIS Station | Cork | Portfolio | Group 3 | TRUE | System Reinforcement | 110 | Post PA | 2017-02-14 | 2021-04-14 |  | 2027-03-31 | 2017-02-14 | 2021-04-14 |  | 2026-11-19 | No Updates | 2017 | 2021 |  | 2027 | PRE-PR6 | PRE-PR6 | Not Achieved | Not Achieved
CP0973 | Knockraha Short Circuit Rating Mitigation | Cork | Portfolio | Group 3 | TRUE | System Reinforcement | 220 | Post PA | 2016-11-03 | 2019-06-21 | 2025-10-10 | 2032-12-20 | 2016-11-03 | 2019-06-21 | 2025-10-10 | 2032-12-20 | No Updates | 2016 | 2019 | 2025 | 2032 | PRE-PR6 | PRE-PR6 | PRE-PR6 | Not Achieved
CP0983 | Point on Wave Controller for Glanagow 220 kV Station | Cork | Portfolio | Group 3 | TRUE | System Reinforcement | 220 | Post PA | 2016-08-04 | 2017-05-23 | 2027-03-01 | 2027-03-01 | 2016-08-04 | 2017-05-23 | 2027-03-01 | 2027-03-01 | No Updates | 2016 | 2017 | 2027 | 2027 | PRE-PR6 | PRE-PR6 | Not Achieved | Not Achieved
CP0984 | Belcamp Shellybanks 220 kV Cable | Dublin | Portfolio | Group 3 | TRUE | System Reinforcement | 220 | Post PA | 2016-07-01 | 2020-07-15 |  | 2026-12-02 | 2016-07-01 | 2020-07-15 |  | 2026-11-25 | No Updates | 2016 | 2020 |  | 2026 | PRE-PR6 | PRE-PR6 | Not Achieved | Not Achieved
CP1000 | Lanesboro - Mullingar 110 kV Thermal Uprate | Multiple | Portfolio | Group 3 | TRUE | System Reinforcement | 110 | Post PA | 2021-01-29 | 2024-09-24 | 2027-11-26 | 2029-09-05 | 2021-01-29 | 2024-09-24 | 2027-11-26 | 2029-09-05 | No Updates | 2021 | 2024 | 2027 | 2029 | PRE-PR6 | PRE-PR6 | Not Achieved | Not Achieved
CP1001 | Corduff - Finglas 1 & 2 220 kV line refurbishment | Dublin | Portfolio | Group 3 | TRUE | Asset Refurbishment | 220 | Post PA | 2022-11-10 | 2024-03-28 | 2027-10-29 | 2027-10-29 | 2022-11-10 | 2024-03-28 | 2027-10-30 | 2027-10-30 | No Updates | 2022 | 2024 | 2027 | 2027 | PRE-PR6 | PRE-PR6 | Not Achieved | Not Achieved
CP1002 | Cushaling - Newbridge 110 kV Thermal Uprate | Multiple | Portfolio | Group 2 | TRUE | System Reinforcement | 110 | Post PA | 2023-03-30 | 2025-05-30 | 2029-08-22 | 2029-11-30 | 2023-03-30 | 2025-05-30 | 2029-08-22 | 2029-11-30 | No Updates | 2023 | 2025 | 2029 | 2029 | PRE-PR6 | PRE-PR6 | Not Achieved | Not Achieved
CP1003 | Cushaling - Portlaoise 110 kV line uprate | Multiple | Portfolio | Group 3 | TRUE | Asset Refurbishment | 110 | Post PA | 2023-07-05 | 2026-06-04 | 2027-05-24 | 2030-08-13 | 2023-07-05 | 2026-03-12 | 2026-12-12 | 2030-08-13 | Date(s) Updated | 2023 | 2026 | 2027 | 2030 | PRE-PR6 | Green | Not Achieved | Not Achieved
CP1032 | Cashla 220 kV Station Sprecher & Schuh CB Replacement | Galway | Portfolio | Group 3 | TRUE | Asset Refurbishment | 220 | Post PA | 2018-06-30 | 2019-07-11 | 2026-07-16 | 2026-11-16 | 2018-06-30 | 2019-07-11 |  | 2026-11-30 | Date(s) Updated | 2018 | 2019 | 2026 | 2026 | PRE-PR6 | PRE-PR6 | Not Achieved | Not Achieved
CP1048 | Power Flow Control Scheme | Donegal | Portfolio | Group 3 | TRUE | System Reinforcement | 110 | Pre PA | 2021-02-04 | 2026-09-11 | 2031-07-28 | 2031-08-01 | 2021-03-31 | 2025-06-30 |  | 2027-12-20 | No Updates | 2021 | 2026 | 2031 | 2031 | PRE-PR6 | Not Achieved | Not Achieved | Not Achieved
CP1060 | Loughteague 110 kV solar farm | Laois | Portfolio | Group 3 | TRUE | Customer Connection | 110 | Post PA | 2018-09-18 | 2021-11-05 | 2027-10-19 | 2027-12-20 | 2020-06-03 | 2021-11-05 | 2027-10-19 | 2027-12-31 | No Updates | 2018 | 2021 | 2027 | 2027 | PRE-PR6 | PRE-PR6 | Not Achieved | Not Achieved
CP1064 | Finglas Pantograph Replacement Project | Dublin | Portfolio | Group 3 | TRUE | Asset Refurbishment | 220 | Post PA | 2019-12-20 | 2020-11-12 |  | 2027-12-20 | 2019-12-20 | 2020-11-12 |  | 2027-12-20 | No Updates | 2019 | 2020 |  | 2027 | PRE-PR6 | PRE-PR6 | Not Achieved | Not Achieved
CP1069 | Ballinknockane 110 kV Station (Ballinknockane Solar Farm) | Multiple | Portfolio | Group 3 | TRUE | Customer Connection | 110 | Post PA | 2019-05-16 | 2020-12-24 | 2026-11-24 | 2026-11-25 | 2019-05-16 | 2020-12-24 | 2026-11-04 | 2026-11-20 | No Updates | 2019 | 2020 | 2026 | 2026 | PRE-PR6 | PRE-PR6 | Not Achieved | Not Achieved
CP1073 | Croaghaun West 110 kV Station (Oweninny 3 Wind Farm) | Mayo | Portfolio | Group 3 | TRUE | Customer Connection | 110 | Post PA | 2020-07-02 | 2025-05-11 | 2027-07-30 | 2027-07-30 | 2020-07-02 | 2025-07-15 | 2026-06-19 | 2027-07-30 | Date(s) Updated | 2020 | 2025 | 2027 | 2027 | PRE-PR6 | PRE-PR6 | Not Achieved | Not Achieved
CP1084 | Lisdrumdoagh 110 kV Battery Storage | Monaghan | Portfolio | Group 3 | TRUE | Customer Connection | 110 | Post PA | 2020-02-06 | 2021-05-26 | 2021-12-19 | 2027-06-18 | 2020-02-06 | 2021-05-26 |  | 2026-11-19 | Date(s) Updated | 2020 | 2021 | 2021 | 2027 | PRE-PR6 | PRE-PR6 | PRE-PR6 | Not Achieved
CP1086 | Dunstown T4201 and Woodland T4201 Transformer replacement | Multiple | Portfolio | Group 3 | TRUE | Asset Refurbishment | 400 | Post PA | 2023-05-01 | 2024-12-17 | 2027-08-15 | 2028-10-30 | 2023-05-01 | 2024-12-17 | 2027-12-06 | 2028-10-30 | Date(s) Updated | 2023 | 2024 | 2027 | 2028 | PRE-PR6 | PRE-PR6 | Not Achieved | Not Achieved
CP1092 | New 400 kV Strategic Spare Transformer | Kildare | Portfolio | Group 3 | TRUE | Asset Refurbishment | 400 | Post PA | 2020-01-29 | 2022-12-15 | 2026-11-25 | 2026-11-25 | 2020-01-29 | 2022-12-15 | 2026-11-25 | 2027-12-20 | No Updates | 2020 | 2022 | 2026 | 2026 | PRE-PR6 | PRE-PR6 | Not Achieved | Not Achieved
CP1096 | Transformer protection upgrade, 6 Stations | Multiple | Portfolio | Group 3 | TRUE | Asset Refurbishment | 220 | Post PA | 2020-02-10 | 2020-10-02 | 2022-07-25 | 2028-05-29 | 2020-02-10 | 2020-10-02 | 2022-07-23 | 2028-05-29 | No Updates | 2020 | 2020 | 2022 | 2028 | PRE-PR6 | PRE-PR6 | PRE-PR6 | Not Achieved
CP1109 | Gorman and Connected Stations 220-110 kV Protection Upgrade | Meath | Portfolio | Group 3 | TRUE | Asset Refurbishment | 220 | Post PA | 2020-05-13 | 2021-06-25 | 2024-03-01 | 2027-12-22 | 2020-05-13 | 2021-06-25 | 2024-03-01 | 2026-10-07 | No Updates | 2020 | 2021 | 2024 | 2027 | PRE-PR6 | PRE-PR6 | PRE-PR6 | Not Achieved
CP1111 | Ballydine, Cahir and Connected Stations 110 kV Protection Upgrade | Tipperary | Portfolio | Group 3 | TRUE | Asset Refurbishment | 110 | Post PA | 2020-05-21 | 2021-07-18 | 2025-07-15 | 2028-03-10 | 2020-05-21 | 2021-07-18 | 2025-07-15 | 2028-03-10 | No Updates | 2020 | 2021 | 2025 | 2028 | PRE-PR6 | PRE-PR6 | PRE-PR6 | Not Achieved
CP1112 | Limerick and Connected Stations 110 kV Protection Upgrade | Limerick | Portfolio | Group 3 | TRUE | Asset Refurbishment | 110 | Post PA | 2020-05-21 | 2023-12-14 | 2027-08-30 | 2030-03-15 | 2020-05-21 | 2023-12-14 | 2027-08-30 | 2030-03-15 | No Updates | 2020 | 2023 | 2027 | 2030 | PRE-PR6 | PRE-PR6 | Not Achieved | Not Achieved
CP1114 | Platin and Connected Stations 110 kV Protection Upgrade | Meath | Portfolio | Group 3 | TRUE | Asset Refurbishment | 110 | Post EI | 2020-05-13 | 2021-08-18 | 2024-03-01 | 2026-03-06 | 2020-05-13 | 2021-08-18 | 2024-03-01 | 2027-04-30 | No Updates | 2020 | 2021 | 2024 | 2026 | PRE-PR6 | PRE-PR6 | PRE-PR6 | Green
CP1115 | Drybridge and Connected Stations 110 kV Protection Upgrade | Multiple | Portfolio | Group 3 | TRUE | Asset Refurbishment | 110 | Post PA | 2020-05-13 | 2021-04-16 | 2024-03-01 | 2027-12-31 | 2020-05-13 | 2021-04-16 | 2024-03-01 | 2026-12-06 | No Updates | 2020 | 2021 | 2024 | 2027 | PRE-PR6 | PRE-PR6 | PRE-PR6 | Not Achieved
CP1116 | Tipperary, Cahir and Connected Stations 110 kV Protection Upgrade | Multiple | Portfolio | Group 3 | TRUE | Asset Refurbishment | 110 | Post PA | 2020-05-13 | 2021-07-14 | 2023-06-30 | 2030-11-20 | 2020-05-13 | 2021-07-14 | 2023-06-30 | 2027-12-31 | No Updates | 2020 | 2021 | 2023 | 2030 | PRE-PR6 | PRE-PR6 | PRE-PR6 | Not Achieved
CP1121 | Arklow Lodgewood Line Uprate | Multiple | Portfolio | Group 3 | TRUE | System Reinforcement | 220 | Pre PA | 2025-02-26 | 2026-12-22 | 2028-09-14 | 2029-09-14 | 2025-02-26 | 2027-12-14 | 2028-09-14 | 2029-09-14 | No Updates | 2025 | 2026 | 2028 | 2029 | PRE-PR6 | Not Achieved | Not Achieved | Not Achieved
CP1122 | Physical Security of Transmission Stations - Dublin Region | Multiple | Portfolio | Group 3 | TRUE | Asset Refurbishment | - | Post PA | 2020-09-01 | 2023-12-08 |  |  | 2020-09-01 | 2023-12-08 |  | 2028-12-20 | No Updates | 2020 | 2023 |  |  | PRE-PR6 | PRE-PR6 | Not Achieved | Not Achieved
CP1123 | Physical Security of Transmission Stations - South Region | Multiple | Portfolio | Group 3 | TRUE | Asset Refurbishment | - | Post PA | 2021-05-07 | 2023-12-08 |  |  | 2021-05-07 | 2023-12-08 |  | 2028-12-20 | No Updates | 2021 | 2023 |  |  | PRE-PR6 | PRE-PR6 | Not Achieved | Not Achieved
CP1124 | Physical Security of Transmission Stations - North Region | Multiple | Portfolio | Group 3 | TRUE | Asset Refurbishment | - | Post PA | 2021-06-11 | 2023-12-08 |  |  | 2021-06-11 | 2023-12-08 |  | 2028-12-20 | No Updates | 2021 | 2023 |  |  | PRE-PR6 | PRE-PR6 | Not Achieved | Not Achieved
CP1125 | Physical Security of Transmission Stations - Central Region | Multiple | Portfolio | Group 3 | TRUE | Asset Refurbishment | - | Post PA | 2021-07-14 | 2023-12-08 |  |  | 2021-07-14 | 2023-12-08 |  | 2028-12-20 | No Updates | 2021 | 2023 |  |  | PRE-PR6 | PRE-PR6 | Not Achieved | Not Achieved
CP1126 | Mully Graffy 110 kV Station (Mully Graffy Windfarm) | Donegal | Portfolio | Group 3 | TRUE | Customer Connection | 110 | Pre PA | 2020-08-06 | 2027-11-30 |  |  | 2020-09-30 | 2025-06-30 |  | 2026-12-20 | No Updates | 2020 | 2027 |  |  | PRE-PR6 | Not Achieved | Not Achieved | Not Achieved
CP1128 | Ballynanelagh 110kV Substation (Ballyvatta solar farm) | Cork | Portfolio | Group 3 | TRUE | Customer Connection | 110 | Pre PA | 2021-11-04 |  |  |  | 2021-11-04 | 2026-11-10 | 2027-06-11 | 2027-08-13 | Date(s) Updated | 2021 |  |  |  | PRE-PR6 | Not Achieved | Not Achieved | Not Achieved
CP1137 | Carlow, Kellis 110 kV Protection Upgrade | Carlow | Portfolio | Group 3 | TRUE | Asset Refurbishment | 110 | Post PA | 2020-10-01 | 2021-09-01 | 2026-10-05 | 2028-11-10 | 2020-10-01 | 2021-09-01 | 2026-10-05 | 2028-11-10 | No Updates | 2020 | 2021 | 2026 | 2028 | PRE-PR6 | PRE-PR6 | Not Achieved | Not Achieved
CP1139 | Sligo & Srananagh 220 & 110 kV Protection upgrade | Sligo | Portfolio | Group 3 | TRUE | Asset Refurbishment | 220 | Post PA | 2020-10-01 | 2021-08-17 | 2025-11-10 | 2027-11-30 | 2020-10-01 | 2021-08-17 | 2025-11-10 | 2027-11-30 | No Updates | 2020 | 2021 | 2025 | 2027 | PRE-PR6 | PRE-PR6 | PRE-PR6 | Not Achieved
CP1140 | Athy, Carlow and Connected Stations 110 kV Protection Upgrade | Multiple | Portfolio | Group 3 | TRUE | Asset Refurbishment | 110 | Post PA | 2020-10-01 | 2021-07-16 | 2026-06-02 | 2028-02-22 | 2020-10-01 | 2021-07-16 | 2026-06-01 | 2028-02-22 | No Updates | 2020 | 2021 | 2026 | 2028 | PRE-PR6 | PRE-PR6 | Green | Not Achieved
CP1141 | Kellis Station 220 kV & 110 kV Protection Upgrade | Carlow | Portfolio | Group 3 | TRUE | Asset Refurbishment | 220 | Post PA | 2020-10-01 | 2021-09-01 | 2026-04-16 | 2027-11-10 | 2020-10-01 | 2021-09-01 | 2026-04-16 | 2027-11-10 | No Updates | 2020 | 2021 | 2026 | 2027 | PRE-PR6 | PRE-PR6 | Green | Not Achieved
CP1142 | Firlough 110 kV Station (Firlough WF) | Mayo | Portfolio | Group 3 | TRUE | Customer Connection | 110 | Pre PA | 2021-02-04 |  |  |  | 2021-02-04 | 2026-04-30 | 2027-06-30 | 2030-08-16 | No Updates | 2021 |  |  |  | PRE-PR6 | Not Achieved | Not Achieved | Not Achieved
CP1143 | Derrylahan 110 kV Station (Blackwater Bog Solar) | Offaly | Portfolio | Group 3 | TRUE | Customer Connection | 110 | Pre PA | 2021-05-06 |  |  |  | 2021-05-06 | 2028-11-17 | 2029-09-25 | 2029-09-25 | No Updates | 2021 |  |  |  | PRE-PR6 | Not Achieved | Not Achieved | Not Achieved
CP1152 | Arva and Connected Stations 110 kV Protection Upgrade | Multiple | Portfolio | Group 3 | TRUE | Asset Refurbishment | 110 | Post PA | 2020-11-12 | 2021-09-01 | 2024-03-01 | 2028-06-15 | 2020-11-12 | 2021-09-01 | 2024-03-01 | 2028-06-15 | No Updates | 2020 | 2021 | 2024 | 2028 | PRE-PR6 | PRE-PR6 | PRE-PR6 | Not Achieved
CP1159 | Cullenagh and connected stations protection upgrade | Multiple | Portfolio | Group 3 | TRUE | Asset Refurbishment | 220 | Post PA | 2020-12-04 | 2021-11-04 | 2022-09-01 | 2027-11-29 | 2020-12-04 | 2021-11-04 |  | 2027-11-29 | Date(s) Updated | 2020 | 2021 | 2022 | 2027 | PRE-PR6 | PRE-PR6 | PRE-PR6 | Not Achieved
CP1161 | Cathaleens Fall and connected stations 110 kV protection upgrade | Multiple | Portfolio | Group 3 | TRUE | Asset Refurbishment | 110 | Post PA | 2020-12-04 | 2021-12-16 | 2026-07-14 | 2028-08-18 | 2020-12-04 | 2021-12-16 |  | 2028-08-18 | Date(s) Updated | 2020 | 2021 | 2026 | 2028 | PRE-PR6 | PRE-PR6 | Not Achieved | Not Achieved
CP1162 | Irishtown, Shellybanks and connected stations 220 kV protection upgrade | Dublin | Portfolio | Group 3 | TRUE | Asset Refurbishment | 220 | Post PA | 2021-02-04 | 2021-12-16 | 2025-11-01 | 2028-12-31 | 2021-02-04 | 2021-12-16 |  | 2026-11-30 | Date(s) Updated | 2021 | 2021 | 2025 | 2028 | PRE-PR6 | PRE-PR6 | PRE-PR6 | Not Achieved
CP1163 | Butlerstown, Killoteran & Waterford 110 kV protection upgrade | Waterford | Portfolio | Group 3 | TRUE | Asset Refurbishment | 110 | Post PA | 2021-02-04 | 2021-11-04 | 2025-05-30 | 2029-05-08 | 2021-02-04 | 2021-11-04 | 2025-05-30 | 2028-05-08 | No Updates | 2021 | 2021 | 2025 | 2029 | PRE-PR6 | PRE-PR6 | PRE-PR6 | Not Achieved
CP1164 | West Cork 110 kV protection upgrade | Cork | Portfolio | Group 3 | TRUE | Asset Refurbishment | 110 | Post PA | 2021-02-04 | 2022-03-07 | 2026-08-21 | 2027-11-30 | 2021-02-04 | 2022-03-07 | 2026-08-21 | 2026-11-30 | Date(s) Updated | 2021 | 2022 | 2026 | 2027 | PRE-PR6 | PRE-PR6 | Not Achieved | Not Achieved
CP1166 | Gorman - Platin 110 kV line uprate | Meath | Portfolio | Group 3 | TRUE | Customer Connection | 110 | Post PA | 2021-03-18 | 2025-08-25 | 2026-04-15 | 2026-12-18 | 2021-03-18 | 2025-08-25 | 2026-12-18 | 2026-12-18 | No Updates | 2021 | 2025 | 2026 | 2026 | PRE-PR6 | PRE-PR6 | Green | Not Achieved
CP1168 | Cashla-Salthill 110 kV Thermal Uprate | Multiple | Portfolio | Group 3 | TRUE | System Reinforcement | 110 | Post PA | 2021-03-18 | 2025-10-17 | 2027-10-15 | 2027-07-16 | 2021-03-18 | 2025-10-17 | 2026-10-15 | 2027-07-17 | Date(s) Updated | 2021 | 2025 | 2027 | 2027 | PRE-PR6 | PRE-PR6 | Not Achieved | Not Achieved
CP1170 | Newbridge - Portlaoise 110 kV Line uprate | Multiple | Portfolio | Group 3 | TRUE | System Reinforcement | 110 | Post EI | 2021-08-05 | 2025-06-19 | 2025-12-17 | 2026-05-27 | 2021-08-05 | 2025-06-19 | 2025-12-17 | 2027-04-23 | Date(s) Updated | 2021 | 2025 | 2025 | 2026 | PRE-PR6 | PRE-PR6 | PRE-PR6 | Green
CP1172 | Crane - Wexford 110 kV Line uprate | Wexford | Portfolio | Group 3 | TRUE | System Reinforcement | 110 | Post PA | 2021-06-17 | 2023-10-09 | 2025-09-19 | 2026-08-28 | 2021-06-17 | 2023-10-09 | 2025-09-19 | 2026-04-29 | Date(s) Updated | 2021 | 2023 | 2025 | 2026 | PRE-PR6 | PRE-PR6 | PRE-PR6 | Not Achieved
CP1173 | Glencloosagh Phase 1 - Rotating Stabiliser | Kerry | Portfolio | Group 3 | TRUE | Customer Connection | 220 | Post PA | 2021-05-06 | 2025-10-24 | 2026-11-19 | 2026-11-19 | 2021-05-06 | 2025-10-10 |  | 2026-11-19 | No Updates | 2021 | 2025 | 2026 | 2026 | PRE-PR6 | PRE-PR6 | Not Achieved | Not Achieved
CP1177 | Whitegate 110 kV Station Refurbishment Project | Cork | Portfolio | Group 3 | TRUE | Asset Refurbishment | 110 | Pre PA | 2025-09-17 | 2029-08-20 | 2031-07-29 | 2034-04-04 | 2024-09-30 | 2025-09-01 |  | 2028-12-01 | No Updates | 2025 | 2029 | 2031 | 2034 | PRE-PR6 | Not Achieved | Not Achieved | Not Achieved
CP1182 | Transformer Restoration Project | Multiple | Portfolio | Group 3 | TRUE | Asset Refurbishment | 220 | Post PA | 2023-03-31 | 2025-03-05 | 2027-05-21 | 2029-11-30 | 2023-03-31 | 2025-03-05 | 2027-05-21 | 2029-11-30 | No Updates | 2023 | 2025 | 2027 | 2029 | PRE-PR6 | PRE-PR6 | Not Achieved | Not Achieved
CP1183 | Mooretown 220 kV Station | Dublin | Portfolio | Group 3 | TRUE | Customer Connection | 220 | Post PA | 2022-04-06 | 2025-12-19 | 2028-08-11 | 2028-12-19 | 2022-04-06 | 2025-12-22 | 2028-03-31 | 2028-10-22 | Date(s) Updated | 2022 | 2025 | 2028 | 2028 | PRE-PR6 | PRE-PR6 | Not Achieved | Not Achieved
CP1186 | Agannygal, Ennis and connected stations 110 kV Protection Upgrade | Multiple | Portfolio | Group 3 | TRUE | Asset Refurbishment | 110 | Post PA | 2021-08-05 | 2022-09-08 | 2026-11-30 | 2027-01-04 | 2021-08-05 | 2022-09-08 | 2026-11-30 | 2027-01-01 | No Updates | 2021 | 2022 | 2026 | 2027 | PRE-PR6 | PRE-PR6 | Not Achieved | Not Achieved
CP1188 | Kilcarbery 110 kV Station (Profile Park Power Co 1 Ltd) | Dublin | Portfolio | Group 3 | TRUE | Customer Connection | 110 | Post PA | 2021-07-08 | 2023-12-12 | 2026-09-24 | 2026-09-25 | 2021-07-08 | 2024-12-03 | 2026-09-24 | 2026-09-25 | No Updates | 2021 | 2023 | 2026 | 2026 | PRE-PR6 | PRE-PR6 | Not Achieved | Not Achieved
CP1191 | Cashla-Galway 110 kV cot 1 Line uprate | Galway | Portfolio | Group 2 | TRUE | System Reinforcement | 110 | Pre PA | 2022-11-21 | 2027-09-14 | 2027-12-30 | 2028-12-30 | 2022-11-21 | 2027-03-30 | 2027-12-30 | 2028-12-30 | Date(s) Updated | 2022 | 2027 | 2027 | 2028 | PRE-PR6 | Not Achieved | Not Achieved | Not Achieved
CP1195 | Turlough Hill 220 kV Station Refurbishment | Wicklow | Portfolio | Group 3 | TRUE | Asset Refurbishment | 220 | Pre PA | 2023-09-06 | 2027-06-21 | 2028-09-20 | 2030-09-20 | 2023-09-06 | 2027-06-20 | 2028-09-20 | 2030-09-20 | No Updates | 2023 | 2027 | 2028 | 2030 | PRE-PR6 | Not Achieved | Not Achieved | Not Achieved
CP1197 | Dunstown Asset Replacements | Multiple | Portfolio | Group 3 | TRUE | Asset Refurbishment | 400 | Post PA | 2021-12-31 | 2023-12-19 | 2026-09-18 | 2030-12-03 | 2021-12-31 | 2023-12-19 | 2026-09-18 | 2030-12-03 | No Updates | 2021 | 2023 | 2026 | 2030 | PRE-PR6 | PRE-PR6 | Not Achieved | Not Achieved
CP1198 | Barnakyle MIC Increase | Dublin | Portfolio | Group 3 | TRUE | Customer Connection | 110 | Pre PA | 2022-10-27 |  |  |  | 2022-10-27 | 2026-12-30 | 2027-08-12 | 2027-12-17 | No Updates | 2022 |  |  |  | PRE-PR6 | Not Achieved | Not Achieved | Not Achieved
CP1199 | Derryiron - Thornsberry 110 kV Line Uprate | Offaly | Portfolio | Group 3 | TRUE | System Reinforcement | 110 | Post PA | 2021-11-19 | 2023-12-20 | 2026-08-24 | 2027-10-25 | 2021-11-19 | 2023-12-20 | 2026-07-21 | 2027-10-25 | Date(s) Updated | 2021 | 2023 | 2026 | 2027 | PRE-PR6 | PRE-PR6 | Not Achieved | Not Achieved
CP1209 | Brown Boveri Circuit Breaker Replacements | Multiple | Portfolio | Group 3 | TRUE | Asset Refurbishment | 220 | Post PA | 2022-03-31 | 2023-12-20 | 2027-10-05 | 2028-12-01 | 2022-03-31 | 2023-12-20 | 2027-10-05 | 2028-12-01 | No Updates | 2022 | 2023 | 2027 | 2028 | PRE-PR6 | PRE-PR6 | Not Achieved | Not Achieved
CP1212 | Bandon Raffeen 110 kV circuit thermal capacity | Cork | Portfolio | Group 3 | TRUE | System Reinforcement | 110 | Post PA | 2022-01-28 | 2024-09-05 | 2026-07-22 | 2029-07-11 | 2022-01-28 | 2024-09-05 | 2026-07-22 | 2029-07-11 | No Updates | 2022 | 2024 | 2026 | 2029 | PRE-PR6 | PRE-PR6 | Not Achieved | Not Achieved
CP1219 | Lickny 110 kV Station (Coole Wind Farm) | Westmeath | Portfolio | Group 5 | TRUE | Customer Connection | 110 | Pre PA | 2022-02-01 |  |  |  | 2022-02-01 | 2025-03-30 |  | 2026-06-01 | No Updates | 2022 |  |  |  | PRE-PR6 | Not Achieved | Not Achieved | Not Achieved
CP1221 | Mulgeeth 110 kV Station - Drehid Wind Farm | Kildare | Portfolio | Group 5 | TRUE | Customer Connection | 110 | Pre PA | 2022-02-01 |  |  |  | 2022-02-01 | 2025-03-31 |  | 2026-09-25 | No Updates | 2022 |  |  |  | PRE-PR6 | Not Achieved | Not Achieved | Not Achieved
CP1222 | Knockraha 220 kV Transformer Replacement | Cork | Portfolio | Group 3 | TRUE | Asset Refurbishment | 220 | Post PA | 2022-01-19 | 2022-12-15 |  | 2027-12-22 | 2022-01-19 | 2022-12-15 |  | 2027-12-24 | No Updates | 2022 | 2022 |  | 2027 | PRE-PR6 | PRE-PR6 | Not Achieved | Not Achieved
CP1223 | Bandon 110 kV Busbar Rating Needs | Cork | Portfolio | Group 3 | TRUE | System Reinforcement | 110 | Post PA | 2023-05-03 | 2025-04-01 | 2026-11-11 | 2029-07-11 | 2023-05-03 | 2025-04-01 | 2026-11-11 | 2029-07-11 | No Updates | 2023 | 2025 | 2026 | 2029 | PRE-PR6 | PRE-PR6 | Not Achieved | Not Achieved
CP1224 | Lysaghtstown 110 kV Station | Cork | Portfolio | Group 3 | TRUE | Customer Connection | 110 | Post PA | 2022-02-03 | 2023-03-02 | 2023-12-21 | 2026-07-31 | 2022-02-03 | 2023-03-02 |  | 2026-07-31 | Date(s) Updated | 2022 | 2023 | 2023 | 2026 | PRE-PR6 | PRE-PR6 | PRE-PR6 | Not Achieved
CP1225 | Finglas - Corduff 220 kV Protection Upgrade | Dublin | Portfolio | Group 3 | TRUE | Asset Refurbishment | 220 | Post PA | 2022-02-03 | 2022-12-13 |  | 2028-12-20 | 2022-02-03 | 2022-12-13 |  | 2026-11-30 | No Updates | 2022 | 2022 |  | 2028 | PRE-PR6 | PRE-PR6 | Not Achieved | Not Achieved
CP1227 | Cashla and Connected Stations 220 kV & 110 kV Protection Upgrade | Multiple | Portfolio | Group 3 | TRUE | Asset Refurbishment | 220 | Post PA | 2022-02-02 | 2022-09-21 | 2026-09-30 | 2027-11-30 | 2022-02-02 | 2022-09-21 |  | 2026-11-30 | Date(s) Updated | 2022 | 2022 | 2026 | 2027 | PRE-PR6 | PRE-PR6 | Not Achieved | Not Achieved
CP1228 | Shannonbridge and Connected Stations 220 kV & 110 kV Protection Upgrade | Multiple | Portfolio | Group 3 | TRUE | Asset Refurbishment | 220 | Post PA | 2022-02-03 | 2022-09-26 | 2025-06-24 | 2027-08-26 | 2022-02-03 | 2022-09-26 | 2025-06-24 | 2027-08-26 | No Updates | 2022 | 2022 | 2025 | 2027 | PRE-PR6 | PRE-PR6 | PRE-PR6 | Not Achieved
CP1230 | Darndale 110kV Station Phase 2 (Amazon Web Services) | Dublin | Portfolio | Group 3 | TRUE | Customer Connection | 110 | Post PA | 2022-06-17 | 2022-12-19 | 2026-09-30 | 2027-12-20 | 2022-06-17 | 2022-12-19 | 2026-02-23 | 2027-03-08 | No Updates | 2022 | 2022 | 2026 | 2027 | PRE-PR6 | PRE-PR6 | Not Achieved | Not Achieved
CP1237 | Ferry View 110 kV Station (Knockranny Wind Farm) | Galway | Portfolio | Group 5 | TRUE | Customer Connection | 110 | Pre PA | 2022-07-07 |  |  |  | 2022-07-07 | 2025-10-01 |  | 2026-10-01 | No Updates | 2022 |  |  |  | PRE-PR6 | Not Achieved | Not Achieved | Not Achieved
CP1238 | Arklow 220 kV Station Redevelopment | Multiple | Portfolio | Group 4 | TRUE | System Reinforcement | 220 | Pre PA | 2023-04-20 | 2027-03-09 | 2028-12-12 | 2032-06-08 | 2023-04-20 | 2026-09-08 | 2028-06-12 | 2032-06-08 | Date(s) Updated | 2023 | 2027 | 2028 | 2036 | PRE-PR6 | Not Achieved | Not Achieved | Not Achieved
CP1240 | Coumaclovane Solar Extension | Kerry | Portfolio | Group 3 | TRUE | Customer Connection | 110 | Pre PA | 2022-08-31 |  |  |  | 2022-08-31 | 2026-07-06 | 2026-10-30 | 2027-07-22 | No Updates | 2022 |  |  |  | PRE-PR6 | Not Achieved | Not Achieved | Not Achieved
CP1241 | Belcamp BSP Transfer | Dublin | Portfolio | Group 3 | TRUE | System Reinforcement | 220 | Post PA | 2022-09-01 | 2024-05-31 | 2026-08-06 | 2026-08-31 | 2022-09-01 | 2024-05-31 | 2025-11-13 | 2026-03-06 | No Updates | 2022 | 2024 | 2026 | 2026 | PRE-PR6 | PRE-PR6 | Not Achieved | Not Achieved
CP1242 | Great Island 220-110 kV transformer upgrades | Wexford | Portfolio | Group 2 | TRUE | System Reinforcement | 220 | Post PA | 2022-12-07 | 2023-12-20 | 2027-03-30 | 2027-12-31 | 2022-12-07 | 2023-12-20 | 2026-11-03 | 2026-11-26 | Date(s) Updated | 2022 | 2023 | 2027 | 2027 | PRE-PR6 | PRE-PR6 | Not Achieved | Not Achieved
CP1244 | North Arklow Solar Plus Storage | Wicklow | Portfolio | Group 3 | TRUE | Customer Connection | 110 | Post PA | 2022-10-06 | 2024-02-07 | 2026-11-06 | 2027-07-21 | 2022-10-06 | 2024-02-07 | 2026-06-30 | 2026-07-24 | Date(s) Updated | 2022 | 2024 | 2026 | 2027 | PRE-PR6 | PRE-PR6 | Not Achieved | Not Achieved
CP1245 | Castletreasure 110 kV Station (Ballinrea Solar Park) | Cork | Portfolio | Group 3 | TRUE | Customer Connection | 110 | Post PA | 2022-09-09 | 2024-12-12 | 2026-10-21 | 2026-10-21 | 2022-09-09 | 2024-12-12 | 2026-03-05 | 2026-12-10 | No Updates | 2022 | 2024 | 2026 | 2026 | PRE-PR6 | PRE-PR6 | Not Achieved | Not Achieved
CP1246 | Coomnaclohy 110 kV Station (Knocknamork Wind and Solar Park) | Cork | Portfolio | Group 3 | TRUE | Customer Connection | 110 | Pre PA | 2022-07-07 | 2026-08-21 |  |  | 2022-07-07 | 2026-02-28 | 2026-12-21 | 2027-11-01 | Date(s) Updated | 2022 | 2026 |  |  | PRE-PR6 | Not Achieved | Not Achieved | Not Achieved
CP1247 | New Ballyvouskill 220-110 kV Transformer | Cork | Portfolio | Group 3 | TRUE | System Reinforcement | 220 | Post PA | 2022-05-10 | 2023-08-28 | 2027-03-30 | 2027-03-30 | 2022-05-10 | 2023-08-28 | 2026-10-16 | 2026-12-23 | Date(s) Updated | 2022 | 2023 | 2027 | 2027 | PRE-PR6 | PRE-PR6 | Not Achieved | Not Achieved
CP1249 | Porterstown Battery 60MW Phase 2 | Kildare | Portfolio | Group 3 | TRUE | Customer Connection | 110 | Post PA | 2022-06-01 | 2023-11-10 | 2027-08-23 | 2028-11-01 | 2022-06-01 | 2023-11-10 | 2027-08-21 | 2028-11-01 | No Updates | 2022 | 2023 | 2027 | 2028 | PRE-PR6 | PRE-PR6 | Not Achieved | Not Achieved
CP1251 | North Wall Life Extension Project | Dublin | Portfolio | Group 5 | TRUE | Asset Refurbishment | 220 | Pre PA | 2024-07-03 | 2026-08-20 | 2031-07-12 | 2031-01-24 | 2024-09-30 | 2025-06-30 |  | 2029-12-20 | No Updates | 2024 | 2026 | 2031 | 2031 | PRE-PR6 | Not Achieved | Not Achieved | Not Achieved
CP1257 | T-3 P485 Kilshane Power Station | Dublin | Portfolio | Group 2 | TRUE | Customer Connection | 220 | Post PA | 2022-05-05 | 2025-12-12 | 2027-12-01 | 2027-12-01 | 2022-05-05 | 2025-12-08 | 2028-03-08 | 2028-09-01 | No Updates | 2022 | 2025 | 2027 | 2027 | PRE-PR6 | PRE-PR6 | Not Achieved | Not Achieved
CP1259 | Cuilleen 110kV Station (Greener Ideas) | Roscommon | Portfolio | Group 3 | TRUE | Customer Connection | 110 | Post PA | 2022-05-05 | 2024-03-06 | 2026-10-15 | 2026-10-15 | 2022-05-05 | 2024-03-06 |  | 2026-03-30 | Date(s) Updated | 2022 | 2024 | 2026 | 2026 | PRE-PR6 | PRE-PR6 | Not Achieved | Not Achieved
CP1260 | Dennistown 110 kV Station (Tracystown Solar) | Wexford | Portfolio | Group 3 | TRUE | Customer Connection | 110 | Post PA | 2022-05-30 | 2024-07-16 | 2026-11-23 | 2027-03-03 | 2022-05-30 | 2024-07-16 | 2026-01-12 | 2026-11-27 | Date(s) Updated | 2022 | 2024 | 2026 | 2027 | PRE-PR6 | PRE-PR6 | Not Achieved | Not Achieved
CP1263 | Rappareehill 110 kV Station (Derryadd Wind Farm) | Longford | Portfolio | Group 5 | TRUE | Customer Connection | 110 | Pipeline | [8 empty] | No Updates |  |  |  |  | Not Achieved | Not Achieved | Not Achieved | Not Achieved
CP1264 | Rhode ESS (DSO) | Offaly | Portfolio | Group 3 | TRUE | DSO | 110 | Post PA | 2022-06-23 | 2023-09-01 | 2027-10-07 | 2027-10-07 | 2022-06-23 | 2023-09-01 | 2027-08-20 | 2027-12-20 | Date(s) Updated | 2022 | 2023 | 2027 | 2027 | PRE-PR6 | PRE-PR6 | Not Achieved | Not Achieved
CP1265 | Corkagh 110kV Station Phase 2 (Microsoft) | Dublin | Portfolio | Group 3 | TRUE | Customer Connection | 110 | Post PA | 2022-07-26 | 2023-10-20 | 2026-04-02 | 2026-12-01 | 2022-07-26 | 2023-10-06 | 2025-11-21 | 2026-12-01 | Date(s) Updated | 2022 | 2023 | 2026 | 2026 | PRE-PR6 | PRE-PR6 | Amber | Not Achieved
CP1266 | Ballyragget 1 (Parksgrove) - DSO Parksgrove SF | Kilkenny | Portfolio | Group 3 | TRUE | DSO | 110 | Post PA | 2022-02-01 | 2023-03-01 | 2027-06-30 | 2027-06-30 | 2022-02-01 | 2023-03-01 | 2026-06-30 | 2026-09-01 | Date(s) Updated | 2022 | 2023 | 2027 | 2027 | PRE-PR6 | PRE-PR6 | Not Achieved | Not Achieved
CP1267 | Arklow 220kV - DSO Ballymanus WF | Wicklow | Portfolio | Group 3 | TRUE | DSO | 220 | Post PA | 2022-09-30 | 2023-11-06 | 2027-07-01 | 2027-07-01 | 2022-09-30 | 2023-11-06 | 2026-07-24 | 2026-07-24 | Date(s) Updated | 2022 | 2023 | 2027 | 2027 | PRE-PR6 | PRE-PR6 | Not Achieved | Not Achieved
CP1268 | Dunfirth 110kV - DSO Dysart PV | Kildare | Portfolio | Group 3 | TRUE | DSO | 110 | Post PA | 2022-09-30 | 2025-01-15 | 2027-09-30 | 2027-09-30 | 2022-09-30 | 2025-01-15 | 2026-07-04 | 2026-10-01 | Date(s) Updated | 2022 | 2025 | 2027 | 2027 | PRE-PR6 | PRE-PR6 | Not Achieved | Not Achieved
CP1275 | Cashla - Galway 110 kV Circuit 2 Uprate | Galway | Portfolio | Group 3 | TRUE | System Reinforcement | 110 | Pre PA | 2022-11-21 | 2027-09-14 | 2027-12-30 | 2028-12-30 | 2022-11-21 | 2027-03-30 | 2027-12-30 | 2028-12-30 | Date(s) Updated | 2022 | 2027 | 2027 | 2028 | PRE-PR6 | Not Achieved | Not Achieved | Not Achieved
CP1276 | Cashla - Galway 110 kV Circuit 3 Uprate | Galway | Portfolio | Group 3 | TRUE | System Reinforcement | 110 | Pre PA | 2022-11-21 | 2027-09-14 | 2027-12-30 | 2028-12-30 | 2022-11-21 | 2027-03-30 | 2027-12-30 | 2028-12-30 | Date(s) Updated | 2022 | 2027 | 2027 | 2028 | PRE-PR6 | Not Achieved | Not Achieved | Not Achieved
CP1280 | Ballyragget Future Proofed Cable | Kilkenny | Portfolio | Group 3 | TRUE | Customer Connection | 110 | Post PA | 2022-11-22 | 2025-06-25 | 2026-10-30 | 2026-10-30 | 2022-11-22 | 2025-06-25 | 2026-06-30 | 2026-08-26 | Date(s) Updated | 2022 | 2025 | 2026 | 2026 | PRE-PR6 | PRE-PR6 | Not Achieved | Not Achieved
CP1281 | Batter Lane DSO Station | Dublin | Portfolio | Group 3 | TRUE | DSO | 110 | Post PA | 2023-02-09 | 2024-11-20 | 2026-10-30 | 2026-10-30 | 2023-02-09 | 2024-11-20 |  | 2026-10-30 | No Updates | 2023 | 2024 | 2026 | 2026 | PRE-PR6 | PRE-PR6 | Not Achieved | Not Achieved
CP1282 | Clogher-Drumkeen 110 kV Line Alteration | Donegal | Portfolio | Group 3 | TRUE | Diversion | 110 | Pre PA | 2023-03-31 | 2029-12-14 | 2032-04-02 | 2032-10-19 | 2023-03-31 | 2025-08-25 |  | 2026-12-31 | Date(s) Updated | 2023 | 2029 | 2032 | 2032 | PRE-PR6 | Not Achieved | Not Achieved | Not Achieved
CP1283 | Belcamp cables masterplan | Dublin | Portfolio | Group 5 | TRUE | System Reinforcement | 110 | Pre PA | 2024-10-02 | 2027-06-17 |  |  | 2024-12-20 | 2026-12-20 |  | 2028-12-20 | No Updates | 2024 | 2027 |  |  | PRE-PR6 | Not Achieved | Not Achieved | Not Achieved
CP1284 | Walterstown 110kV Station DSO | Kildare | Portfolio | Group 3 | TRUE | DSO | 110 | Pre PA | 2024-01-19 | 2027-03-01 | 2029-07-10 | 2029-10-10 | 2024-01-19 | 2027-03-01 | 2029-07-10 | 2029-10-10 | No Updates | 2024 | 2027 | 2029 | 2029 | PRE-PR6 | Not Achieved | Not Achieved | Not Achieved
CP1285 | Barnahely - Raffeen No 2 110 kV Line | Cork | Portfolio | Group 3 | TRUE | Diversion | 110 | Post PA | 2023-08-04 | 2024-04-16 | 2024-11-29 | 2028-11-24 | 2023-08-04 | 2024-04-16 | 2024-11-30 | 2028-11-24 | No Updates | 2023 | 2024 | 2024 | 2028 | PRE-PR6 | PRE-PR6 | PRE-PR6 | Not Achieved
CP1291 | Carlow 110 kV Station Busbar Thermal Capacity Need | Carlow | Portfolio | Group 3 | TRUE | System Reinforcement | 110 | Post PA | 2023-06-07 | 2025-03-05 | 2027-06-11 | 2028-09-29 | 2023-06-07 | 2025-03-05 |  | 2028-09-29 | No Updates | 2023 | 2025 | 2027 | 2028 | PRE-PR6 | PRE-PR6 | Not Achieved | Not Achieved
CP1296 | Rinawade 110 kV GIS Station (Liffey Park) | Multiple | Portfolio | Group 3 | TRUE | Customer Connection | 110 | Post PA | 2023-10-02 | 2024-09-04 | 2027-04-27 | 2027-04-27 | 2023-10-06 | 2024-09-04 |  | 2026-10-01 | Date(s) Updated | 2023 | 2024 | 2027 | 2027 | PRE-PR6 | PRE-PR6 | Not Achieved | Not Achieved
CP1297 | Glansillagh 220kV Station S | Kerry | Portfolio | Group 3 | TRUE | Customer Connection | 220 | Pre PA | 2023-06-08 | 2027-09-06 |  |  | 2023-06-08 | 2027-09-04 | 2029-05-10 | 2029-12-06 | No Updates | 2023 | 2027 |  |  | PRE-PR6 | Not Achieved | Not Achieved | Not Achieved
CP1300 | Climate Change Adaptation Measures | Multiple | Portfolio | Group 5 | TRUE | Asset Refurbishment | 220 | Pre PA | 2023-04-05 | 2027-07-14 |  |  | 2023-04-05 | 2026-02-26 |  |  | No Updates | 2023 | 2027 |  |  | PRE-PR6 | Not Achieved | Not Achieved | Not Achieved
CP1301 | Dundalk Louth 110 kV Line Uprate | Louth | Portfolio | Group 3 | TRUE | Asset Refurbishment | 110 | Post PA | 2024-02-07 | 2025-02-28 |  | 2027-11-12 | 2024-02-07 | 2025-02-28 |  | 2026-08-13 | Date(s) Updated | 2024 | 2025 |  | 2027 | PRE-PR6 | PRE-PR6 | Not Achieved | Not Achieved
CP1302 | Killonan Shannonbridge 220 kV Line Refurbishment | Multiple | Portfolio | Group 2 | TRUE | Asset Refurbishment | 220 | Post PA | 2025-10-08 | 2026-04-23 | 2028-03-31 | 2029-03-01 | 2026-06-10 | 2028-03-14 | 2028-04-01 | 2029-03-01 | No Updates | 2025 | 2026 | 2028 | 2029 | PRE-PR6 | Green | Not Achieved | Not Achieved
CP1310 | Agannygal-Ennis Line Refurbishment | Multiple | Portfolio | Group 3 | TRUE | Asset Refurbishment | 110 | Post PA | 2024-12-09 | 2026-06-04 | 2027-12-10 | 2029-12-07 | 2024-12-09 | 2026-06-26 | 2027-06-11 | 2028-03-26 | Date(s) Updated | 2024 | 2026 | 2027 | 2029 | PRE-PR6 | Green | Not Achieved | Not Achieved
CP1311 | Athlone - Lanesboro 110 kV line uprate | Multiple | Portfolio | Group 2 | TRUE | System Reinforcement | 110 | Post PA | 2023-02-16 | 2025-09-26 | 2027-11-30 | 2030-09-16 | 2023-02-16 | 2025-09-30 | 2026-10-20 | 2030-09-16 | No Updates | 2023 | 2025 | 2027 | 2030 | PRE-PR6 | PRE-PR6 | Not Achieved | Not Achieved
CP1312 | Athy - Carlow 110 kV circuit 1 | Multiple | Portfolio | Group 2 | TRUE | System Reinforcement | 110 | Pre PA | 2024-06-05 | 2027-03-22 | 2028-09-20 | 2029-09-06 | 2024-06-05 | 2027-03-22 | 2027-06-22 | 2029-09-06 | Date(s) Updated | 2024 | 2027 | 2028 | 2029 | PRE-PR6 | Not Achieved | Not Achieved | Not Achieved
CP1314 | Baroda - Monread 110 kV circuit 1 (DLR) | Kildare | Portfolio | Group 2 | TRUE | System Reinforcement | 110 | Pre PA | 2024-07-03 | 2029-12-21 | 2032-06-21 | 2033-09-02 | 2024-09-30 | 2027-03-31 |  | 2029-12-20 | No Updates | 2024 | 2029 | 2032 | 2033 | PRE-PR6 | Not Achieved | Not Achieved | Not Achieved
CP1315 | Baroda - Newbridge 110 kV circuit 1 (DLR) | Kildare | Portfolio | Group 2 | TRUE | System Reinforcement | 110 | Pre PA | 2024-07-03 | 2029-12-21 | 2031-03-28 | 2031-03-28 | 2024-09-30 | 2028-03-31 |  | 2030-12-20 | No Updates | 2024 | 2029 | 2031 | 2031 | PRE-PR6 | Not Achieved | Not Achieved | Not Achieved
CP1316 | Replacement of substation Back-Up supply equipment – North-East Region | Multiple | Portfolio | Group 5 | TRUE | Asset Refurbishment | - | Pre PA | 2024-02-07 | 2027-04-14 |  |  | 2024-03-29 | 2025-06-30 |  | 2026-12-30 | Date(s) Updated | 2024 | 2027 |  |  | PRE-PR6 | Not Achieved | Not Achieved | Not Achieved
CP1318 | Binbane - Clogher - Cathaleens Fall - 110 kV Clogher tie in | Donegal | Portfolio | Group 3 | TRUE | System Reinforcement | 110 | Pipeline | 2029-02-21 | 2030-12-06 | 2031-09-05 | 2032-09-03 | 2024-12-20 | 2027-12-20 |  | 2029-12-20 | No Updates | 2029 | 2030 | 2031 | 2032 | Not Achieved | Not Achieved | Not Achieved | Not Achieved
CP1319 | Blake Maynooth Newbridge Uprate | Kildare | Portfolio | Group 3 | TRUE | Asset Refurbishment | 110 | Pre PA | 2025-09-03 | 2026-12-18 | 2027-09-17 | 2028-09-18 | 2025-09-03 | 2026-12-18 | 2027-09-18 | 2028-09-18 | No Updates | 2025 | 2026 | 2027 | 2028 | PRE-PR6 | Not Achieved | Not Achieved | Not Achieved
CP1320 | Barrymore Cahir Knockraha 110kV Line Uprate | Multiple | Portfolio | Group 3 | TRUE | System Reinforcement | 110 | Pre PA | 2022-07-31 | 2026-09-25 | 2028-07-27 | 2030-07-26 | 2022-09-30 | 2025-06-30 |  | 2028-12-20 | Date(s) Updated | 2022 | 2026 | 2028 | 2030 | PRE-PR6 | Not Achieved | Not Achieved | Not Achieved
CP1325 | Blundelstown Mullingar 110 kV Line Uprate | Multiple | Portfolio | Group 2 | TRUE | System Reinforcement | 110 | Pre PA | 2024-12-20 | 2026-12-21 | 2027-09-01 | 2030-05-08 | 2024-12-20 | 2026-12-01 | 2027-09-01 | 2030-05-08 | No Updates | 2024 | 2026 | 2027 | 2030 | PRE-PR6 | Not Achieved | Not Achieved | Not Achieved
CP1327 | Drumkeen - Clogher 110 kV circuit 1 | Donegal | Portfolio | Group 2 | TRUE | System Reinforcement | 110 | Pipeline | 2029-02-07 | 2030-07-26 | 2031-04-28 | 2032-04-27 | 2024-12-20 | 2026-09-30 |  | 2028-12-20 | No Updates | 2029 | 2030 | 2031 | 2032 | Not Achieved | Not Achieved | Not Achieved | Not Achieved
CP1331 | Rosspile 110kV Station (Rosspile Storage Facility) | Wexford | Portfolio | Group 3 | TRUE | Customer Connection | 110 | Pre PA | 2025-05-07 |  |  |  | 2025-05-07 | 2026-03-12 | 2022-05-20 | 2029-09-08 | No Updates | 2025 |  |  |  | PRE-PR6 | Not Achieved | Not Achieved | Not Achieved
CP1332 | Reask Solar Farm (ECP 2-2-12) | Meath | Portfolio | Group 5 | TRUE | Customer Connection | - | Pipeline |  |  |  |  | 2024-09-27 | 2025-09-30 |  | 2028-06-28 | No Updates |  |  |  |  | Not Achieved | Not Achieved | Not Achieved | Not Achieved
CP1334 | Newbarn 110 kV Station (Fieldstown Solar Farm) | Dublin | Portfolio | Group 3 | TRUE | Customer Connection | 110 | Post PA | 2023-08-01 | 2025-12-15 | 2027-11-19 | 2027-11-19 | 2023-08-01 | 2025-12-12 | 2027-07-08 | 2027-11-19 | Date(s) Updated | 2023 | 2025 | 2027 | 2027 | PRE-PR6 | PRE-PR6 | Not Achieved | Not Achieved
CP1335 | Garballagh 110kV Station (Garballagh 2 Solar Farm) | Meath | Portfolio | Group 5 | TRUE | Customer Connection | 110 | Pre PA | 2023-07-20 |  |  |  | 2023-07-20 | 2025-04-21 |  | 2026-01-30 | No Updates | 2023 |  |  |  | PRE-PR6 | Not Achieved | Not Achieved | Not Achieved
CP1338 | Effernoge 110kV Station (Tomsallagh Solar) | Wexford | Portfolio | Group 3 | TRUE | Customer Connection | 110 | Post PA | 2023-11-10 | 2026-04-09 | 2027-11-10 | 2027-11-10 | 2023-11-10 | 2025-10-31 | 2027-07-15 | 2027-07-15 | Date(s) Updated | 2023 | 2026 | 2027 | 2027 | PRE-PR6 | Amber | Not Achieved | Not Achieved
CP1341 | Cloon 110 kV_Barnacurragh Solar Park | Galway | Portfolio | Group 3 | TRUE | Customer Connection | 110 | Pre PA | 2023-04-04 | 2026-10-01 |  |  | 2023-04-04 | 2026-10-01 | 2027-09-30 | 2030-05-10 | No Updates | 2023 | 2026 |  |  | PRE-PR6 | Not Achieved | Not Achieved | Not Achieved
CP1342 | Drumcamill 110 kV Station (Monvallet Hybrid Solar and Battery Farm) | Louth | Portfolio | Group 3 | TRUE | Customer Connection | 110 | Post PA | 2023-10-06 | 2024-09-04 | 2026-07-22 | 2026-07-22 | 2023-10-06 | 2024-09-04 |  | 2026-07-01 | No Updates | 2023 | 2024 | 2026 | 2026 | PRE-PR6 | PRE-PR6 | Not Achieved | Not Achieved
CP1344 | Timahoe North Phase 2 Solar Farm (ECP 2-2-23) | Kildare | Portfolio | Group 5 | TRUE | Customer Connection | - | Pipeline |  |  |  |  | 2024-09-27 | 2025-01-28 |  | 2027-10-28 | No Updates |  |  |  |  | Not Achieved | Not Achieved | Not Achieved | Not Achieved
CP1345 | Golagh 110kV Station (Barnesmore WF Repower) | Donegal | Portfolio | Group 5 | TRUE | Customer Connection | 110 | Pre PA | 2024-03-06 | 2027-07-01 |  |  | 2024-02-16 | 2025-05-27 |  | 2027-11-25 | Date(s) Updated | 2024 | 2027 |  |  | PRE-PR6 | Not Achieved | Not Achieved | Not Achieved
CP1346 | Meath Hill 110 kV Station (Ardagh South Energy Storage) | Meath | Portfolio | Group 3 | TRUE | Customer Connection | 110 | Post PA | 2024-03-06 | 2025-09-26 | 2027-08-31 | 2027-08-31 | 2024-03-06 | 2025-09-26 | 2027-08-31 | 2027-10-07 | Date(s) Updated | 2024 | 2025 | 2027 | 2027 | PRE-PR6 | PRE-PR6 | Not Achieved | Not Achieved
CP1347 | Dunbrody 110 kV Station (Kilmannock Battery Storage Facility Phase 2) | Wexford | Portfolio | Group 3 | TRUE | Customer Connection | 110 | Pre PA | 2023-10-06 | 2026-10-30 |  |  | 2023-10-06 | 2026-01-30 |  | 2027-06-08 | No Updates | 2023 | 2026 |  |  | PRE-PR6 | Not Achieved | Not Achieved | Not Achieved
CP1351 | Ballynadrideen 110 kV Station (Ballyroe Solar) | Cork | Portfolio | Group 3 | TRUE | Customer Connection | 110 | Post PA | 2023-03-30 | 2024-05-29 | 2026-08-28 | 2026-10-15 | 2023-03-30 | 2024-04-03 | 2026-01-12 | 2026-10-15 | No Updates | 2023 | 2024 | 2026 | 2026 | PRE-PR6 | PRE-PR6 | Not Achieved | Not Achieved
CP1352 | Gortatleva 110 kV Station (Ballymoneen Solar Park) | Galway | Portfolio | Group 3 | TRUE | Customer Connection | 110 | Post EI | 2023-04-09 | 2024-09-23 | 2026-03-02 | 2026-03-02 | 2023-04-09 | 2024-09-23 | 2026-01-12 | 2026-12-12 | No Updates | 2023 | 2024 | 2026 | 2026 | PRE-PR6 | PRE-PR6 | Green | Green
CP1353 | Bendinstown 110kV Station (Garreenleen Solar) | Carlow | Portfolio | Group 3 | TRUE | Customer Connection | 110 | Post EI | 2023-04-20 | 2024-08-07 | 2026-05-05 | 2026-05-05 | 2023-04-20 | 2024-08-07 | 2025-11-28 | 2026-11-28 | No Updates | 2023 | 2024 | 2026 | 2026 | PRE-PR6 | PRE-PR6 | Amber | Green
CP1354 | Coolshamroge 110 kV Station (Manusmore Solar Park) | Clare | Portfolio | Group 3 | TRUE | Customer Connection | 110 | Pre PA | 2023-04-05 | 2026-08-13 |  |  | 2023-04-05 | 2026-11-20 | 2027-11-01 | 2029-08-01 | No Updates | 2023 | 2026 |  |  | PRE-PR6 | Not Achieved | Not Achieved | Not Achieved
CP1355 | Corbetstown 110 kV Station (Garr Solar and Storage) | Offaly | Portfolio | Group 3 | TRUE | Customer Connection | 110 | Pre PA | 2024-03-06 | 2027-04-22 |  |  | 2024-03-06 | 2027-04-22 | 2027-12-31 | 2027-12-31 | Date(s) Updated | 2024 | 2027 |  |  | PRE-PR6 | Not Achieved | Not Achieved | Not Achieved
CP1356 | Gortawee 110 kV Station (Mucklagh Battery Storage Facility) | Cavan | Portfolio | Group 5 | TRUE | Customer Connection | 110 | Pre PA | 2024-08-07 |  |  |  | 2024-08-07 | 2027-10-01 | 2029-03-19 | 2029-03-19 | No Updates | 2024 |  |  |  | PRE-PR6 | Not Achieved | Not Achieved | Not Achieved
CP1357 | Philipstown 110 kV Station (Kilcush solar farm) | Multiple | Portfolio | Group 5 | TRUE | Customer Connection | 110 | Pre PA | 2024-09-04 |  |  |  | 2024-09-17 | 2025-06-30 |  | 2028-02-21 | No Updates | 2024 |  |  |  | PRE-PR6 | Not Achieved | Not Achieved | Not Achieved
CP1358 | Thornsberry 110 kV Station (Ballycosney 150 MW BESS) | Offaly | Portfolio | Group 5 | TRUE | Customer Connection | 110 | Pre PA | 2025-02-05 |  |  |  | 2025-02-05 | 2027-04-19 | 2029-12-27 | 2029-12-27 | No Updates | 2025 |  |  |  | PRE-PR6 | Not Achieved | Not Achieved | Not Achieved
CP1360 | Coolcor 110KV (Coolavacoose Solar Farm) | Multiple | Portfolio | Group 5 | TRUE | Customer Connection | 110 | Pre PA | 2024-11-06 |  |  |  | 2024-12-10 | 2025-06-30 |  | 2027-03-31 | No Updates | 2024 |  |  |  | PRE-PR6 | Not Achieved | Not Achieved | Not Achieved
CP1361 | Booltaigh 110KV Station (Carncreagh Energy Storage) | Clare | Portfolio | Group 5 | TRUE | Customer Connection | 110 | Pre PA | 2024-11-06 |  |  |  | 2024-11-06 | 2026-02-12 | 2026-05-29 | 2027-05-21 | Date(s) Updated | 2024 |  |  |  | PRE-PR6 | Not Achieved | Not Achieved | Not Achieved
CP1362 | Bishopswood 110 kV Station (Blue Pine Solar) | Offaly | Portfolio | Group 5 | TRUE | Customer Connection | 110 | Pipeline |  |  |  |  | 2024-12-10 | 2025-06-30 |  | 2028-03-31 | No Updates |  |  |  |  | Not Achieved | Not Achieved | Not Achieved | Not Achieved
CP1363 | Curraghdoo 110 kV Station (Clonymeath Solar Farm) | Multiple | Portfolio | Group 5 | TRUE | Customer Connection | 110 | Pre PA | 2025-07-01 |  |  |  | 2025-01-30 | 2025-06-30 |  | 2028-03-31 | No Updates | 2025 |  |  |  | PRE-PR6 | Not Achieved | Not Achieved | Not Achieved
CP1364 | Moanalow 110 kV Station (Grangeford Solar PV) | Carlow | Portfolio | Group 5 | TRUE | Customer Connection | 110 | Pre PA | 2024-11-06 | [7 empty] | No Updates | 2024 |  |  |  | PRE-PR6 | Not Achieved | Not Achieved | Not Achieved
CP1365 | Mihanboy 110 kV station (Taduff Solar Park) | Roscommon | Portfolio | Group 5 | TRUE | Customer Connection | 110 | Pre PA | 2024-11-06 | 2026-10-12 |  |  | 2024-11-06 | 2027-03-06 | 2029-09-25 | 2029-11-01 | Date(s) Updated | 2024 | 2026 |  |  | PRE-PR6 | Not Achieved | Not Achieved | Not Achieved
CP1366 | Lysaghtstown 110 kV Station (Lysaghtstown Solar Farm Phase 2) | Cork | Portfolio | Group 5 | TRUE | Customer Connection | 110 | Pre PA | 2024-09-04 |  |  |  | 2024-09-04 | 2026-05-06 | 2027-12-20 | 2030-09-14 | No Updates | 2024 |  |  |  | PRE-PR6 | Not Achieved | Not Achieved | Not Achieved
CP1367 | Midleton 110kV Station (Carrigogna BESS) | Cork | Portfolio | Group 5 | TRUE | Customer Connection | 110 | Pre PA | 2025-02-05 |  |  |  | 2025-02-05 | 2027-01-09 | 2029-03-26 | 2029-03-26 | No Updates | 2025 |  |  |  | PRE-PR6 | Not Achieved | Not Achieved | Not Achieved
CP1368 | Crosspatrick 110 kV Station (Mullafarry BESS) | Mayo | Portfolio | Group 5 | TRUE | Customer Connection | 110 | Pre PA | 2025-01-15 |  |  |  | 2025-01-15 | 2027-08-10 | 2029-07-15 | 2029-07-15 | No Updates | 2025 |  |  |  | PRE-PR6 | Not Achieved | Not Achieved | Not Achieved
CP1369 | Colehill 110 kV Station (Ballyteige Solar Park) | Offaly | Portfolio | Group 5 | TRUE | Customer Connection | 110 | Pre PA | 2026-05-06 | [7 empty] | Date(s) Updated | 2026 |  |  |  | Green | Not Achieved | Not Achieved | Not Achieved
CP1372 | Drombeg 110 kV Station (Drombeg Solar Park Phase 2) | Kerry | Portfolio | Group 5 | TRUE | Customer Connection | 110 | Post PA | 2025-03-05 | 2026-03-10 | 2026-12-14 | 2026-12-14 | 2024-09-30 | 2025-09-30 |  | 2028-06-30 | Date(s) Updated | 2025 | 2026 | 2026 | 2026 | PRE-PR6 | Amber | Not Achieved | Not Achieved
CP1374 | Ballyvouskill 110 kV (ABO Wind Ireland) | Cork | Portfolio | Group 5 | TRUE | Customer Connection | 110 | Pre PA | 2025-07-25 | 2027-01-28 |  |  | 2025-01-30 | 2026-02-03 |  | 2027-12-31 | Date(s) Updated | 2025 | 2027 |  |  | PRE-PR6 | Not Achieved | Not Achieved | Not Achieved
CP1375 | Boggeragh 110 kV Station (Carragraigue Solar Extension) | Cork | Portfolio | Group 5 | TRUE | Customer Connection | 110 | Pre PA | 2024-06-05 |  |  |  | 2024-06-05 | 2025-03-31 |  | 2027-12-16 | No Updates | 2024 |  |  |  | PRE-PR6 | Not Achieved | Not Achieved | Not Achieved
CP1377 | Rathcoon 110 kV Station (Gorman Solar Farm) | Meath | Portfolio | Group 5 | TRUE | Customer Connection | 110 | Pre PA | 2024-07-03 |  |  |  | 2024-07-03 | 2025-07-15 |  | 2027-11-30 | No Updates | 2024 |  |  |  | PRE-PR6 | Not Achieved | Not Achieved | Not Achieved
CP1378 | Cooleeny 110 kV Station (Killoran Solar PV Farm) | Tipperary | Portfolio | Group 5 | TRUE | Customer Connection | 110 | Pre PA | 2024-08-07 | 2026-11-27 |  |  | 2024-08-07 | 2025-03-31 |  | 2027-12-31 | No Updates | 2024 | 2026 |  |  | PRE-PR6 | Not Achieved | Not Achieved | Not Achieved
CP1379 | Cauteen 110 kV Station (Barnaleen Solar Farm) | Tipperary | Portfolio | Group 5 | TRUE | Customer Connection | 110 | Pre PA | 2025-04-02 | 2026-11-12 |  |  | 2024-08-07 | 2025-03-31 |  | 2027-12-31 | Date(s) Updated | 2025 | 2026 |  |  | PRE-PR6 | Not Achieved | Not Achieved | Not Achieved
CP1380 | Craddanstown 110kV station (Bracklyn WF) | Multiple | Portfolio | Group 5 | TRUE | Customer Connection | 110 | Pre PA | 2024-12-04 | 2026-12-01 |  |  | 2024-09-16 | 2025-09-01 |  | 2027-12-31 | No Updates | 2024 | 2026 |  |  | PRE-PR6 | Not Achieved | Not Achieved | Not Achieved
CP1384 | Kilteel - Maynooth 110 kV | Kildare | Portfolio | Group 2 | TRUE | System Reinforcement | 110 | Pipeline | 2026-09-02 | 2028-06-09 | 2029-01-16 | 2029-01-16 | 2026-02-27 | 2027-03-01 | 2027-10-01 | 2027-10-01 | No Updates | 2026 | 2028 | 2029 | 2029 | Not Achieved | Not Achieved | Not Achieved | Not Achieved
CP1389 | Limerick - Rathkeale Line Uprate | Limerick | Portfolio | Group 3 | TRUE | Asset Refurbishment | 110 | Pre PA | 2024-08-12 | 2029-10-18 | 2033-02-14 | 2035-07-16 | 2024-09-30 | 2026-06-30 |  | 2029-12-20 | No Updates | 2024 | 2029 | 2033 | 2035 | PRE-PR6 | Not Achieved | Not Achieved | Not Achieved
CP1390 | Maynooth - Rinawade 110V line uprate | Kildare | Portfolio | Group 3 | TRUE | System Reinforcement | 110 | Post PA | 2023-06-06 | 2024-12-19 |  | 2027-04-02 | 2023-06-06 | 2024-12-19 |  | 2026-10-01 | Date(s) Updated | 2023 | 2024 |  | 2027 | PRE-PR6 | PRE-PR6 | Not Achieved | Not Achieved
CP1394 | Offshore Phase 1 - Codling Wind Park | Dublin | Portfolio | Group 5 | TRUE | System Reinforcement | 220 | Pre PA | 2022-12-15 | 2028-01-25 | 2032-02-19 | 2032-02-19 | 2022-12-20 | 2024-12-20 |  | 2027-12-20 | Date(s) Updated | 2022 | 2028 | 2032 | 2032 | PRE-PR6 | Not Achieved | Not Achieved | Not Achieved
CP1396 | Arklow Bank Wind Park Phase 2 (Offshore) | Wicklow | Portfolio | Group 5 | TRUE | System Reinforcement | 220 | Pre PA | 2022-12-15 | 2028-02-15 | 2031-12-22 | 2031-12-22 | 2022-12-20 | 2024-12-20 |  | 2028-12-20 | Date(s) Updated | 2022 | 2028 | 2031 | 2031 | PRE-PR6 | Not Achieved | Not Achieved | Not Achieved
CP1397 | Bremore 220 kV Station (North Irish Sea Array) | Dublin | Portfolio | Group 5 | TRUE | System Reinforcement | 220 | Pre PA | 2022-12-15 | 2028-02-15 | 2031-09-29 | 2031-09-29 | 2022-12-20 | 2024-12-20 |  | 2027-12-20 | Date(s) Updated | 2022 | 2028 | 2031 | 2031 | PRE-PR6 | Not Achieved | Not Achieved | Not Achieved
CP1398 | Offshore Phase 1 - Dublin Array | Dublin | Portfolio | Group 5 | TRUE | System Reinforcement | 220 | Pre PA | 2022-12-15 | 2028-06-26 | 2031-03-28 | 2031-03-28 | 2022-12-20 | 2024-12-20 |  | 2029-12-20 | Date(s) Updated | 2022 | 2028 | 2031 | 2031 | PRE-PR6 | Not Achieved | Not Achieved | Not Achieved
CP1402 | Platin 110kV Station Refurbishment | Meath | Portfolio | Group 3 | TRUE | Asset Refurbishment | 110 | Pre PA | 2025-06-04 | 2026-12-22 | 2028-03-23 | 2030-03-24 | 2025-06-04 | 2026-12-23 | 2028-03-23 | 2030-03-23 | No Updates | 2025 | 2026 | 2028 | 2030 | PRE-PR6 | Not Achieved | Not Achieved | Not Achieved
CP1403 | Rinawade – Dunfirth Tee – Kinnegad 110 kV Circuit Thermal Capacity | Kildare | Portfolio | Group 3 | TRUE | System Reinforcement | 110 | Pre PA | 2023-05-18 | 2026-10-20 | 2027-06-22 | 2028-06-22 | 2023-05-18 | 2026-09-22 | 2027-06-22 | 2028-06-22 | No Updates | 2023 | 2026 | 2027 | 2028 | PRE-PR6 | Not Achieved | Not Achieved | Not Achieved
CP1412 | Knockraha 220 kV Transformer Replacement (T2102) | Cork | Portfolio | Group 3 | TRUE | Asset Refurbishment | 220 | Post PA | 2023-03-08 | 2024-05-17 |  | 2026-12-01 | 2023-03-08 | 2024-05-17 |  | 2026-12-01 | No Updates | 2023 | 2024 |  | 2026 | PRE-PR6 | PRE-PR6 | Not Achieved | Not Achieved
CP1418 | Oaklands 110 kV Station Crag Wicklow | Multiple | Portfolio | Group 5 | TRUE | Customer Connection | 110 | Pre PA | 2023-07-24 | 2026-12-17 |  |  | 2023-07-24 | 2025-07-13 |  | 2028-01-13 | Date(s) Updated | 2023 | 2026 |  |  | PRE-PR6 | Not Achieved | Not Achieved | Not Achieved
CP1420 | North Wicklow Reinforcement | Multiple | Portfolio | Group 5 | TRUE | System Reinforcement | 110 | Pipeline | 2027-03-02 | 2030-06-30 | 2034-09-01 | 2034-12-01 | 2025-06-30 | 2027-03-31 |  | 2031-12-20 | No Updates | 2027 | 2030 | 2034 | 2034 | Not Achieved | Not Achieved | Not Achieved | Not Achieved
CP1421 | Crakenstown 220-110 kV Station | Multiple | Portfolio | Group 5 | TRUE | Customer Connection | 220 | Pre PA | 2025-09-17 | [7 empty] | No Updates | 2025 |  |  |  | PRE-PR6 | Not Achieved | Not Achieved | Not Achieved
CP1422 | Cashla - Prospect 220 kV Line Refurbishment | Multiple | Portfolio | Group 3 | TRUE | Asset Refurbishment | 220 | Pre PA | 2025-09-03 | 2028-06-13 | 2031-04-18 | 2032-04-16 | 2025-03-12 | 2026-09-03 |  | 2029-11-30 | Date(s) Updated | 2025 | 2028 | 2031 | 2032 | PRE-PR6 | Not Achieved | Not Achieved | Not Achieved
CP1423 | Cashla - Tynagh 220 kV Line Refurbishment | Galway | Portfolio | Group 3 | TRUE | Asset Refurbishment | 220 | Pre PA | 2025-06-04 | 2027-03-23 | 2031-04-09 | 2033-05-13 | 2025-04-14 | 2026-09-16 |  | 2029-11-30 | Date(s) Updated | 2025 | 2027 | 2031 | 2033 | PRE-PR6 | Not Achieved | Not Achieved | Not Achieved
CP1424 | Farrnawana 220 kV (SSE Tarbert OCGT) | Kerry | Portfolio | Group 3 | TRUE | Customer Connection | 220 | Post PA | 2023-08-02 | 2025-10-15 |  | 2027-05-11 | 2023-08-02 | 2025-10-10 |  | 2027-09-24 | Date(s) Updated | 2023 | 2025 |  | 2027 | PRE-PR6 | PRE-PR6 | Not Achieved | Not Achieved
CP1425 | Southwall 220kV GIS (ESB Poolbeg) (ESB G&T) | Dublin | Portfolio | Group 3 | TRUE | Customer Connection | 220 | Pre PA | 2023-07-11 |  |  |  | 2026-01-01 | 2027-03-20 | 2029-04-28 | 2029-04-28 | No Updates | 2023 |  |  |  | PRE-PR6 | Not Achieved | Not Achieved | Not Achieved
CP1426 | Derrygreenagh 220 kV, Rathcobican 400 kV SS (Cushaling Power Ltd) | Multiple | Portfolio | Group 3 | TRUE | Customer Connection | 400 | Pre PA | 2024-07-19 |  |  |  | 2024-07-19 | 2026-12-31 | 2029-07-02 | 2030-07-02 | No Updates | 2024 |  |  |  | PRE-PR6 | Not Achieved | Not Achieved | Not Achieved
CP1427 | Bellewstown 110kV Station – SSE Platin | Meath | Portfolio | Group 3 | TRUE | Customer Connection | 110 | Pre PA | 2023-08-02 | 2026-11-12 |  |  | 2023-08-02 | 2026-01-29 | 2028-06-23 | 2029-07-30 | Date(s) Updated | 2023 | 2026 |  |  | PRE-PR6 | Not Achieved | Not Achieved | Not Achieved
CP1428 | Cashla - Dalton 110kV Thermal Capacity Increase | Multiple | Portfolio | Group 2 | TRUE | System Reinforcement | 110 | Post PA | 2023-12-12 | 2026-03-31 | 2027-03-09 | 2028-11-02 | 2023-12-12 | 2026-06-09 | 2027-03-09 | 2028-11-02 | No Updates | 2023 | 2026 | 2027 | 2028 | PRE-PR6 | Green | Not Achieved | Not Achieved
CP1429 | Castlebar Dalton 110kV Thermal Capacity Increase | Mayo | Portfolio | Group 2 | TRUE | System Reinforcement | 110 | Post PA | 2023-12-12 | 2026-06-05 | 2028-05-30 | 2028-05-30 | 2023-12-12 | 2026-06-02 | 2027-03-02 | 2028-03-02 | Date(s) Updated | 2023 | 2026 | 2028 | 2028 | PRE-PR6 | Green | Not Achieved | Not Achieved
CP1434 | Drumline 110 kV Station Busbar Thermal Uprate | Clare | Portfolio | Group 5 | TRUE | System Reinforcement | 110 | Pre PA | 2026-06-18 | 2028-01-11 | 2031-09-11 | 2033-12-19 |  |  |  |  | Date(s) Updated | 2026 | 2028 | 2031 | 2033 | Green | Not Achieved | Not Achieved | Not Achieved
CP1435 | Drumline Ennis 110kV circuit DLR and related works | Clare | Portfolio | Group 2 | TRUE | System Reinforcement | 110 | Pre PA | 2024-02-07 | 2028-08-22 | 2031-03-14 | 2031-03-24 | 2024-03-31 | 2025-06-30 |  | 2028-12-20 | No Updates | 2024 | 2028 | 2031 | 2031 | PRE-PR6 | Not Achieved | Not Achieved | Not Achieved
CP1436 | Ardnacrusha Ennis 110kV circuit DLR and related works | Clare | Portfolio | Group 3 | TRUE | System Reinforcement | 110 | Pre PA | 2024-03-06 | 2028-08-22 | 2031-02-19 | 2031-08-15 | 2024-03-04 | 2025-03-31 |  | 2027-12-20 | No Updates | 2024 | 2028 | 2031 | 2031 | PRE-PR6 | Not Achieved | Not Achieved | Not Achieved
CP1442 | Fosterstown 110 kV Station Connection DSO | Multiple | Portfolio | Group 3 | TRUE | DSO | 110 | Pre PA | 2024-02-07 | 2026-11-25 | 2029-07-10 | 2029-10-31 | 2024-02-07 | 2026-11-25 | 2029-07-10 | 2030-04-16 | No Updates | 2024 | 2026 | 2029 | 2029 | PRE-PR6 | Not Achieved | Not Achieved | Not Achieved
CP1447 | Letterkenny - Golagh Tee 110 kV circuit thermal capacity needs | Donegal | Portfolio | Group 2 | TRUE | System Reinforcement | 110 | Pipeline | 2029-02-07 | 2030-07-26 | 2031-04-08 | 2032-12-14 | 2024-12-20 | 2026-09-30 |  | 2030-12-20 | No Updates | 2029 | 2030 | 2031 | 2032 | Not Achieved | Not Achieved | Not Achieved | Not Achieved
CP1448 | Carrickmines Phase Shift Transformer (PST) Replacement | Dublin | Portfolio | Group 5 | TRUE | System Reinforcement | - | Pipeline | 2028-11-20 | 2030-11-22 | 2032-02-23 | 2034-02-22 |  |  |  |  | No Updates | 2028 | 2030 | 2032 | 2034 | Not Achieved | Not Achieved | Not Achieved | Not Achieved
CP1449 | Midleton 110kV Transformer Uprate and Station works DSO | Cork | Portfolio | Group 3 | TRUE | DSO | 110 | Post PA | 2024-02-07 | 2025-05-22 | 2027-01-29 | 2027-05-31 | 2024-02-07 | 2025-05-22 | 2027-01-29 | 2027-05-31 | No Updates | 2024 | 2025 | 2027 | 2027 | PRE-PR6 | PRE-PR6 | Not Achieved | Not Achieved
CP1450 | Ardnacrusha Drumline 110kV thermal capacity needs | Clare | Portfolio | Group 3 | TRUE | System Reinforcement | 110 | Pre PA | 2024-03-06 | 2028-08-22 | 2031-05-16 | 2032-01-10 | 2024-03-04 | 2025-06-30 |  | 2028-06-30 | No Updates | 2024 | 2028 | 2031 | 2032 | PRE-PR6 | Not Achieved | Not Achieved | Not Achieved
CP1452 | Poolbeg OCGT (ESB G&T) | Dublin | Portfolio | Group 3 | TRUE | Customer Connection | 220 | Post PA | 2024-03-05 | 2025-03-05 | 2026-10-21 | 2026-10-21 | 2024-03-05 | 2025-03-05 | 2026-09-18 | 2026-10-21 | Date(s) Updated | 2024 | 2025 | 2026 | 2026 | PRE-PR6 | PRE-PR6 | Not Achieved | Not Achieved
CP1453 | Blake 110 kV Station Redevelopment | Kildare | Portfolio | Group 5 | TRUE | Asset Refurbishment | 110 | Pre PA | 2024-05-30 | 2029-10-05 | 2031-09-12 | 2034-05-22 |  |  |  |  | No Updates | 2024 | 2029 | 2031 | 2034 | PRE-PR6 | Not Achieved | Not Achieved | Not Achieved
CP1454 | Gorman - Maynooth 220 kV Circuit Capacity Needs | Multiple | Portfolio | Group 2 | TRUE | System Reinforcement | 220 | Pre PA | 2024-05-01 | 2026-12-17 | 2031-06-11 | 2033-09-02 | 2024-06-30 | 2026-12-20 |  | 2030-12-20 | Date(s) Updated | 2024 | 2026 | 2031 | 2033 | PRE-PR6 | Not Achieved | Not Achieved | Not Achieved
CP1456 | Clutterland 110kV Station Phase 2&3 (Amazon Web Services) | Dublin | Portfolio | Group 3 | TRUE | Customer Connection | 110 | Post PA | 2024-03-06 | 2024-12-04 | 2026-07-01 | 2026-08-21 | 2024-03-06 | 2024-12-04 | 2026-07-01 | 2026-08-21 | No Updates | 2024 | 2024 | 2026 | 2026 | PRE-PR6 | PRE-PR6 | Not Achieved | Not Achieved
CP1459 | East Kildare 110 kV Station | Multiple | Portfolio | Group 3 | TRUE | Customer Connection | 110 | Pre PA | 2024-03-25 |  |  |  | 2024-03-25 | 2027-03-31 | 2029-03-30 | 2030-08-21 | No Updates | 2024 |  |  |  | PRE-PR6 | Not Achieved | Not Achieved | Not Achieved
CP1464 | Tullabeg 110 kV Station (Tullabeg Solar Phase 2 | Wexford | Portfolio | Group 5 | TRUE | Customer Connection | 110 | Pre PA | 2024-06-05 | 2026-09-09 |  |  | 2024-06-30 | 2025-03-31 |  | 2028-03-29 | No Updates | 2024 | 2026 |  |  | PRE-PR6 | Not Achieved | Not Achieved | Not Achieved
CP1465 | Lisdrum 110kV Station Busbar Thermal Capacity Need | Monaghan | Portfolio | Group 5 | TRUE | System Reinforcement | 110 | Post PA | 2024-11-06 | 2025-12-19 | 2026-12-22 | 2031-05-06 |  |  |  |  | No Updates | 2024 | 2025 | 2026 | 2031 | PRE-PR6 | PRE-PR6 | Not Achieved | Not Achieved
CP1466 | Meath Hill 110kV Station Busbar Thermal Capacity Need | Meath | Portfolio | Group 3 | TRUE | System Reinforcement | 110 | Pre PA | 2024-11-06 | 2026-07-10 | 2027-10-08 | 2029-10-10 | 2024-11-06 | 2026-07-10 | 2027-10-10 | 2029-10-10 | No Updates | 2024 | 2026 | 2027 | 2029 | PRE-PR6 | Not Achieved | Not Achieved | Not Achieved
CP1467 | Caherhurly 110 kV Station (Carrownagowan Wind Farm) | Clare | Portfolio | Group 3 | TRUE | Customer Connection | 110 | Pre PA | 2024-05-01 | 2026-10-14 |  |  | 2024-05-01 | 2026-01-14 | 2028-03-30 | 2028-11-15 | No Updates | 2024 | 2026 |  |  | PRE-PR6 | Not Achieved | Not Achieved | Not Achieved
CP1468 | Kilvinoge 110 kV Station (Castlebanny Wind Farm) | Multiple | Portfolio | Group 3 | TRUE | Customer Connection | 110 | Pre PA | 2024-05-01 | 2027-07-08 |  |  | 2024-05-01 | 2027-02-17 | 2029-05-29 | 2029-05-29 | No Updates | 2024 | 2027 |  |  | PRE-PR6 | Not Achieved | Not Achieved | Not Achieved
CP1471 | Lisdrum Louth 110 kV DLR project | Multiple | Portfolio | Group 2 | TRUE | System Reinforcement | 110 | Pre PA | 2024-07-03 | 2028-04-21 | 2031-03-19 | 2031-10-24 | 2024-09-30 | 2025-09-30 |  | 2028-12-20 | No Updates | 2024 | 2028 | 2031 | 2031 | PRE-PR6 | Not Achieved | Not Achieved | Not Achieved
CP1473 | Louth - Meath Hill 110 kV DLR | Multiple | Portfolio | Group 2 | TRUE | System Reinforcement | 110 | Pre PA | 2024-07-03 | 2028-02-11 | 2031-02-28 | 2031-11-06 | 2024-09-30 | 2025-09-30 |  | 2028-12-20 | No Updates | 2024 | 2028 | 2031 | 2031 | PRE-PR6 | Not Achieved | Not Achieved | Not Achieved
CP1475 | East Galway 110 kV Station (DSO Connection) | Galway | Portfolio | Group 3 | TRUE | DSO | 110 | Pipeline | 2026-11-16 | 2027-09-01 | 2030-03-01 | 2030-06-04 | 2025-11-30 | 2027-09-01 | 2030-03-01 | 2030-06-01 | Date(s) Updated | 2026 | 2027 | 2030 | 2030 | Not Achieved | Not Achieved | Not Achieved | Not Achieved
CP1477 | Maynooth - Shannonbridge 220 kV Circuit Capacity Needs | Multiple | Portfolio | Group 2 | TRUE | System Reinforcement | 220 | Pre PA | 2026-06-04 | 2028-06-06 | 2029-03-06 | 2030-03-06 | 2026-06-04 | 2028-06-06 | 2029-03-06 | 2030-03-06 | No Updates | 2026 | 2028 | 2029 | 2030 | Green | Not Achieved | Not Achieved | Not Achieved
CP1478 | Donegal TEN-T Road Network Advanced Ducting | Donegal | Portfolio | Group 5 | TRUE | System Reinforcement | 220 | Pre PA | 2025-01-15 | 2029-11-25 | [6 empty] | No Updates | 2025 | 2029 |  |  | PRE-PR6 | Not Achieved | Not Achieved | Not Achieved
CP1479 | Ratrussan - Shankill 110 kV Dynamic Line Rating | Cavan | Portfolio | Group 2 | TRUE | System Reinforcement | 110 | Pre PA | 2024-12-20 | 2029-12-21 | 2032-12-02 | 2034-07-25 | 2025-03-31 | 2026-03-31 |  | 2028-12-20 | No Updates | 2024 | 2029 | 2032 | 2034 | PRE-PR6 | Not Achieved | Not Achieved | Not Achieved
CP1484 | Srananagh 220 kV Station (Quarry Lane LCIS) | Sligo | Portfolio | Group 3 | TRUE | Customer Connection | 220 | Post PA | 2025-04-02 | 2026-01-20 | 2027-08-26 | 2027-08-26 | 2025-04-02 | 2025-12-19 | 2027-08-26 | 2027-08-26 | No Updates | 2025 | 2026 | 2027 | 2027 | PRE-PR6 | Green | Not Achieved | Not Achieved
CP1485 | Wexford Synchronous Condenser | Wexford | Portfolio | Group 3 | TRUE | Customer Connection | 110 | Pre PA | 2025-11-03 | 2026-09-28 |  |  | 2025-09-30 | 2026-09-30 | 2027-12-23 | 2028-08-10 | No Updates | 2025 | 2026 |  |  | PRE-PR6 | Not Achieved | Not Achieved | Not Achieved
CP1486 | Athlone - Shannonbridge 110 kV Fibre Wrapping | Multiple | Portfolio | Group 5 | TRUE | System Reinforcement | 110 | Pre PA | 2026-03-20 | 2027-03-22 |  | 2029-05-15 | 2026-02-20 | 2027-02-20 |  | 2029-04-17 | No Updates | 2026 | 2027 |  | 2029 | Green | Not Achieved | Not Achieved | Not Achieved
CP1487 | CP1487 Corduff and Connected Stations Protection Upgrade | Dublin | Portfolio | Group 5 | TRUE | Asset Refurbishment | 220 | Pre PA | 2026-03-30 | 2029-02-07 | 2031-08-02 | 2034-10-26 |  |  |  |  | No Updates | 2026 | 2029 | 2031 | 2034 | Green | Not Achieved | Not Achieved | Not Achieved
CP1488 | CP1488 Tralee and Connected Stations Protection Upgrade | Kerry | Portfolio | Group 5 | TRUE | Asset Refurbishment | 110 | Pre PA | 2026-03-04 | 2029-02-06 | 2031-08-02 | 2034-10-26 |  |  |  |  | No Updates | 2026 | 2029 | 2031 | 2034 | Green | Not Achieved | Not Achieved | Not Achieved
CP1490 | Barrymore 110 kV busbar and new 110 38 transformer | Cork | Portfolio | Group 5 | TRUE | System Reinforcement | 110 | Pre PA | 2024-12-03 | 2027-09-14 | 2029-11-16 | 2030-12-18 |  |  |  |  | No Updates | 2024 | 2027 | 2029 | 2030 | PRE-PR6 | Not Achieved | Not Achieved | Not Achieved
CP1491 | Barrymore Land Acquisition | Cork | Portfolio | Group 5 | TRUE | System Reinforcement | - | Pre PA | 2024-12-06 | 2028-04-04 | [6 empty] | No Updates | 2024 | 2028 |  |  | PRE-PR6 | Not Achieved | Not Achieved | Not Achieved
CP1492 | Donore 110 kV Station (DSO Connection) | Multiple | Portfolio | Group 3 | TRUE | DSO | 110 | Pre PA | 2025-01-15 | 2026-11-13 | 2029-06-15 | 2029-09-17 | 2024-12-04 | 2027-03-25 | 2029-06-15 | 2029-09-15 | Date(s) Updated | 2025 | 2026 | 2029 | 2029 | PRE-PR6 | Not Achieved | Not Achieved | Not Achieved
CP1495 | Lodgewood-Great Island line uprate | Wexford | Portfolio | Group 5 | TRUE | System Reinforcement | 220 | Pre PA | 2025-02-26 | 2028-07-03 | 2031-04-22 | 2033-04-06 |  |  |  |  | No Updates | 2025 | 2028 | 2031 | 2033 | PRE-PR6 | Not Achieved | Not Achieved | Not Achieved
CP1496 | Cashla - Shannonbridge 110 kV | Multiple | Portfolio | Group 5 | TRUE | System Reinforcement | 110 | Pipeline | 2027-02-16 | 2029-11-23 | 2031-05-02 | 2033-01-06 |  |  |  |  | Date(s) Updated | 2027 | 2029 | 2031 | 2033 | Not Achieved | Not Achieved | Not Achieved | Not Achieved
CP1498 | Derryiron - Kinnegad 110 kV Fibre Wrapping | Multiple | Portfolio | Group 5 | TRUE | System Reinforcement | 110 | Pipeline | 2026-12-20 | 2028-04-01 | 2034-09-02 | 2035-09-02 | 2026-12-20 | 2028-04-01 | 2034-09-02 | 2035-09-02 | No Updates | 2026 | 2028 | 2034 | 2035 | Not Achieved | Not Achieved | Not Achieved | Not Achieved
CP1499 | Charleville - Glenlara 110 kV Fibre Wrapping | Cork | Portfolio | Group 5 | TRUE | System Reinforcement | 110 | Pipeline | 2027-12-02 | 2028-05-01 | 2034-09-02 | 2035-09-02 | 2027-12-02 | 2028-05-01 | 2034-09-02 | 2035-09-02 | No Updates | 2027 | 2028 | 2034 | 2035 | Not Achieved | Not Achieved | Not Achieved | Not Achieved
CP1500 | Butlerstown 110kV Station (Traffo Uprate) (DSO) | Waterford | Portfolio | Group 3 | TRUE | DSO | 110 | Pre PA | 2025-05-08 | 2026-10-30 | 2027-04-02 | 2028-03-01 | 2025-05-08 | 2026-03-01 | 2027-04-02 | 2028-03-01 | Date(s) Updated | 2025 | 2026 | 2028 | 2028 | PRE-PR6 | Not Achieved | Not Achieved | Not Achieved
CP1509 | Cathaleen’s Fall Srananagh 110 kV Circuit No 2 DLR | Multiple | Portfolio | Group 5 | TRUE | System Reinforcement | 110 | Pre PA | 2025-11-14 | 2030-10-28 | 2031-05-30 | 2031-12-22 |  |  |  |  | No Updates | 2025 | 2030 | 2031 | 2031 | PRE-PR6 | Not Achieved | Not Achieved | Not Achieved
CP1510 | Peamount 110 kV Station (Bulmer RICE) | Dublin | Portfolio | Group 3 | TRUE | Customer Connection | 110 | Pre PA | 2024-12-04 |  |  |  | 2024-12-04 | 2027-12-29 | 2029-08-30 | 2029-09-02 | No Updates | 2024 |  |  |  | PRE-PR6 | Not Achieved | Not Achieved | Not Achieved
CP1511 | Castleview 110kV Station DSO (Eastmont DC) | Cork | Portfolio | Group 5 | TRUE | DSO | 110 | Pre PA | 2025-02-05 | 2028-02-23 | 2031-09-08 | 2032-10-04 |  |  |  |  | No Updates | 2025 | 2028 | 2031 | 2032 | PRE-PR6 | Not Achieved | Not Achieved | Not Achieved
CP1512 | Cathaleens Fall 110kV DSO (Derrykillew Wind Farm) | Donegal | Portfolio | Group 5 | TRUE | DSO | 110 | Pre PA | 2025-04-22 | 2029-12-18 | 2032-09-06 | 2033-12-22 |  |  |  |  | No Updates | 2025 | 2029 | 2032 | 2033 | PRE-PR6 | Not Achieved | Not Achieved | Not Achieved
CP1513 | Ricetown 110kV Station (Mill Farm Solar) | Meath | Portfolio | Group 5 | TRUE | Customer Connection | 110 | Pre PA | 2025-01-15 | 2026-12-09 | [6 empty] | Date(s) Updated | 2025 | 2026 |  |  | PRE-PR6 | Not Achieved | Not Achieved | Not Achieved
CP1514 | Deenes - Drybridge 110 kV Circuit DLR | Multiple | Portfolio | Group 2 | TRUE | System Reinforcement | 110 | Pre PA | 2025-11-21 | 2030-03-15 | 2031-08-08 | 2032-10-29 |  |  |  |  | No Updates | 2025 | 2030 | 2031 | 2032 | PRE-PR6 | Not Achieved | Not Achieved | Not Achieved
CP1515 | Kellymount 110 kV Station (White Hill Wind) | Multiple | Portfolio | Group 5 | TRUE | Customer Connection | 110 | Pre PA | 2025-04-02 | [7 empty] | No Updates | 2025 |  |  |  | PRE-PR6 | Not Achieved | Not Achieved | Not Achieved
CP1516 | Kilmacogue 110 kV Station (Ballyvalode Solar) | Multiple | Portfolio | Group 5 | TRUE | Customer Connection | 110 | Pre PA | 2025-05-07 | [7 empty] | No Updates | 2025 |  |  |  | PRE-PR6 | Not Achieved | Not Achieved | Not Achieved
CP1517 | Kildinan 110 kV Station (Coom Green Energy Park) | Multiple | Portfolio | Group 5 | TRUE | Customer Connection | 110 | Pre PA | 2025-02-05 | [7 empty] | No Updates | 2025 |  |  |  | PRE-PR6 | Not Achieved | Not Achieved | Not Achieved
CP1518 | Glenart 220 kV Station (Pollahoney Autoproducer) | Multiple | Portfolio | Group 4 | TRUE | Customer Connection | 220 | Pre PA | 2025-03-05 | 2026-09-29 |  |  | 2025-03-05 | 2026-09-29 | 2029-06-29 | 2029-06-29 | No Updates | 2025 | 2026 |  |  | PRE-PR6 | Not Achieved | Not Achieved | Not Achieved
CP1519 | Crane - Wexford 110 kV (DLR) | Wexford | Portfolio | Group 2 | TRUE | System Reinforcement | 110 | Pre PA | 2025-05-07 | 2030-10-28 | 2032-02-16 | 2032-12-13 |  |  |  |  | No Updates | 2025 | 2030 | 2032 | 2032 | PRE-PR6 | Not Achieved | Not Achieved | Not Achieved
CP1520 | Great Island - Waterford 110 kV (DLR) | Multiple | Portfolio | Group 2 | TRUE | System Reinforcement | 110 | Pre PA | 2025-05-07 | 2030-07-12 | 2031-02-11 | 2031-02-11 |  |  |  |  | No Updates | 2025 | 2030 | 2031 | 2031 | PRE-PR6 | Not Achieved | Not Achieved | Not Achieved
CP1521 | Cappaneary 110kV Station(Dernacart Wind Farm) | Laois | Portfolio | Group 5 | TRUE | Customer Connection | 110 | Pre PA | 2025-09-30 | [7 empty] | No Updates | 2025 |  |  |  | PRE-PR6 | Not Achieved | Not Achieved | Not Achieved
CP1522 | New Lodgewood 220-110 kV Transformer | Wexford | Portfolio | Group 5 | TRUE | System Reinforcement | 220 | Pre PA | 2025-06-04 | 2030-06-12 | 2031-09-12 | 2033-09-12 |  |  |  |  | No Updates | 2025 | 2030 | 2031 | 2033 | PRE-PR6 | Not Achieved | Not Achieved | Not Achieved
CP1523 | Binbane 110 kV Station Busbar Thermal Capacity Need | Donegal | Portfolio | Group 5 | TRUE | System Reinforcement | 110 | Pre PA | 2025-11-17 | 2027-09-24 | 2031-08-26 | 2033-03-14 |  |  |  |  | Date(s) Updated | 2025 | 2027 | 2031 | 2033 | PRE-PR6 | Not Achieved | Not Achieved | Not Achieved
CP1526 | Baltrasna Corduff 110 kV Circuit DLR Project | Multiple | Portfolio | Group 5 | TRUE | System Reinforcement | 110 | Pre PA | 2025-11-21 | 2028-10-11 | 2031-08-22 | 2033-01-03 |  |  |  |  | No Updates | 2025 | 2028 | 2031 | 2033 | PRE-PR6 | Not Achieved | Not Achieved | Not Achieved
CP1527 | Buffy 110 kV (Ardderoo WF Phase 2) | Galway | Portfolio | Group 3 | TRUE | Customer Connection | 110 | Pre PA | 2026-05-15 |  |  |  | 2025-10-31 | 2026-09-01 | 2026-12-01 | 2026-12-01 | Date(s) Updated | 2026 |  |  |  | Amber | Not Achieved | Not Achieved | Not Achieved
CP1528 | Lislaughtin 110k V Station (Dromlivuan Solar Farm) | Kerry | Portfolio | Group 5 | TRUE | Customer Connection | 110 | Pipeline | [8 empty] | No Updates |  |  |  |  | Not Achieved | Not Achieved | Not Achieved | Not Achieved
CP1529 | Oldbridge Phase 2&3 | Multiple | Portfolio | Group 3 | TRUE | Customer Connection | 110 | Pre PA | 2025-04-22 | 2026-12-18 |  |  | 2025-04-22 | 2026-05-11 | 2027-10-29 | 2028-05-19 | No Updates | 2025 | 2026 |  |  | PRE-PR6 | Not Achieved | Not Achieved | Not Achieved
CP1530 | Ballycummin 110kV Station DSO | Limerick | Portfolio | Group 3 | TRUE | DSO | 110 | Pre PA | 2025-06-05 | 2026-10-23 | 2029-08-10 | 2029-11-10 | 2025-06-05 | 2026-08-01 | 2029-08-10 | 2029-11-10 | Date(s) Updated | 2025 | 2026 | 2029 | 2029 | PRE-PR6 | Not Achieved | Not Achieved | Not Achieved
CP1531 | Kilbarry Knockraha 110 kV Circuit 2 Uprate (Kilbarry Mallow) | Cork | Portfolio | Group 5 | TRUE | System Reinforcement | 110 | Pipeline | 2026-12-21 | 2028-08-10 | 2031-04-08 | 2032-10-22 |  |  |  |  | No Updates | 2026 | 2028 | 2031 | 2032 | Not Achieved | Not Achieved | Not Achieved | Not Achieved
CP1532 | NM20 Cork to Limerick - Advance Ducting | Multiple | Portfolio | Group 5 | TRUE | System Reinforcement | 400 | Pipeline | 2028-05-18 | 2030-06-02 | [6 empty] | No Updates | 2028 | 2030 |  |  | Not Achieved | Not Achieved | Not Achieved | Not Achieved
CP1533 | Raheenmeel 110 kV Station (Kilcormac Solar) | Multiple | Portfolio | Group 5 | TRUE | Customer Connection | 110 | Pre PA | 2025-06-04 | 2026-11-11 | [6 empty] | Date(s) Updated | 2025 | 2026 |  |  | PRE-PR6 | Not Achieved | Not Achieved | Not Achieved
CP1534 | Ennis 110 kV Station (Transformer Uprate) (DSO) | Clare | Portfolio | Group 3 | TRUE | DSO | 110 | Pre PA | 2025-11-14 | 2026-12-01 | 2027-10-29 | 2028-06-01 | 2025-11-30 | 2026-04-01 | 2027-10-29 | 2028-06-01 | No Updates | 2025 | 2026 | 2027 | 2028 | PRE-PR6 | Not Achieved | Not Achieved | Not Achieved
CP1535 | Trien 110 kV Station (Transformer Uprate) (DSO) | Kerry | Portfolio | Group 5 | TRUE | DSO | 110 | Pre PA | 2025-11-14 | 2029-08-13 | 2032-11-08 | 2034-06-02 |  |  |  |  | Date(s) Updated | 2025 | 2029 | 2032 | 2034 | PRE-PR6 | Not Achieved | Not Achieved | Not Achieved
CP1536 | Clogher 220kV Station | Donegal | Portfolio | Group 5 | TRUE | System Reinforcement | 220 | Pipeline | 2027-11-30 | 2029-12-12 | 2034-12-18 | 2035-12-03 |  |  |  |  | Date(s) Updated | 2027 | 2029 | 2034 | 2035 | Not Achieved | Not Achieved | Not Achieved | Not Achieved
CP1539 | Mullingar 110 kV Station (Transformer Uprate) (DSO) | Westmeath | Portfolio | Group 3 | TRUE | DSO | 110 | Pre PA | 2025-10-06 | 2026-12-01 | 2028-03-01 | 2028-06-01 | 2025-11-30 | 2026-04-01 | 2028-03-01 | 2028-06-01 | No Updates | 2025 | 2026 | 2028 | 2028 | PRE-PR6 | Not Achieved | Not Achieved | Not Achieved
CP1540 | CP1540 220 kV Composite pole – Pilot Energised Project | Kilkenny | Portfolio | Group 5 | TRUE | System Reinforcement | 220 | Pipeline | 2026-07-03 | 2028-09-06 | 2031-05-06 | 2033-06-09 |  |  |  |  | No Updates | 2026 | 2028 | 2031 | 2033 | Not Achieved | Not Achieved | Not Achieved | Not Achieved
CP1541 | Seven Hills Wind Farm | Multiple | Portfolio | Group 5 | TRUE | Customer Connection | 110 | Pre PA | 2025-10-08 | [7 empty] | No Updates | 2025 |  |  |  | PRE-PR6 | Not Achieved | Not Achieved | Not Achieved
CP1542 | Cauteen 110kV Station (DSO Gortdrum SF) | Tipperary | Portfolio | Group 5 | TRUE | DSO | 110 | Pre PA | 2025-12-01 | 2030-02-13 | 2032-09-09 | 2033-09-05 |  |  |  |  | No Updates | 2025 | 2030 | 2032 | 2033 | PRE-PR6 | Not Achieved | Not Achieved | Not Achieved
CP1543 | Srananagh 220kV Transformer and Bay Extension | Sligo | Portfolio | Group 5 | TRUE | System Reinforcement | 220 | Pre PA | 2026-02-04 | 2027-12-07 | 2031-07-28 | 2031-12-05 |  |  |  |  | Date(s) Updated | 2026 | 2027 | 2031 | 2031 | Green | Not Achieved | Not Achieved | Not Achieved
CP1544 | Belcamp 110 kV busbar extension and additional transformer capacity | Dublin | Portfolio | Group 5 | TRUE | System Reinforcement | 110 | Pre PA | 2025-11-28 | 2027-06-09 | 2028-05-18 | 2030-11-14 |  |  |  |  | No Updates | 2025 | 2027 | 2028 | 2030 | PRE-PR6 | Not Achieved | Not Achieved | Not Achieved
CP1545 | Maynooth Cable Routing Land Acquisition | Kildare | Portfolio | Group 5 | TRUE | System Reinforcement | - | Pre PA | 2020-11-19 | 2029-10-01 | [6 empty] | No Updates | 2020 | 2029 |  |  | PRE-PR6 | Not Achieved | Not Achieved | Not Achieved
CP1546 | Tincurry Solar Farm (Lodgewood Solar Farm Limited) (ECP 2-4-40) | Wexford | Portfolio | Group 5 | TRUE | Customer Connection | 110 | Pre PA | 2025-10-21 | [7 empty] | No Updates | 2025 |  |  |  | PRE-PR6 | Not Achieved | Not Achieved | Not Achieved
CP1547 | Newbridge East- 110 kV Cable Uprate | Kildare | Portfolio | Group 5 | TRUE | System Reinforcement | 110 | Pre PA | 2025-11-14 | 2030-04-26 | 2031-05-02 | 2032-08-12 |  |  |  |  | No Updates | 2025 | 2030 | 2031 | 2032 | PRE-PR6 | Not Achieved | Not Achieved | Not Achieved
CP1548 | Replacement of substation Back-Up supply equipment – Central Region | Multiple | Portfolio | Group 5 | TRUE | Asset Refurbishment | 220 | Pre PA | 2025-12-18 | 2027-05-11 | [6 empty] | Date(s) Updated | 2025 | 2027 |  |  | PRE-PR6 | Not Achieved | Not Achieved | Not Achieved
CP1549 | Replacement of substation Back-Up supply equipment – North-West Region | Multiple | Portfolio | Group 5 | TRUE | Asset Refurbishment | 220 | Pre PA | 2025-12-18 | 2027-04-28 | [6 empty] | Date(s) Updated | 2025 | 2027 |  |  | PRE-PR6 | Not Achieved | Not Achieved | Not Achieved
CP1550 | Replacement of substation Back-Up supply equipment – South Central Region | Multiple | Portfolio | Group 5 | TRUE | Asset Refurbishment | 220 | Pre PA | 2025-12-18 | 2027-04-29 | [6 empty] | Date(s) Updated | 2025 | 2027 |  |  | PRE-PR6 | Not Achieved | Not Achieved | Not Achieved
CP1551 | Replacement of substation Back-Up supply equipment – South-East Region | Multiple | Portfolio | Group 5 | TRUE | Asset Refurbishment | 220 | Pre PA | 2025-12-18 | 2027-04-29 | [6 empty] | Date(s) Updated | 2025 | 2027 |  |  | PRE-PR6 | Not Achieved | Not Achieved | Not Achieved
CP1552 | Replacement of substation Back-Up supply equipment – South-West Region | Cork | Portfolio | Group 5 | TRUE | Asset Refurbishment | 220 | Pre PA | 2025-12-18 | 2027-04-29 | [6 empty] | Date(s) Updated | 2025 | 2027 |  |  | PRE-PR6 | Not Achieved | Not Achieved | Not Achieved
CP1556 | Arklow Ballybeg Carrickmines Refurbishment | Multiple | Portfolio | Group 5 | TRUE | Asset Refurbishment | 220 | Pre PA | 2025-12-03 | 2027-02-19 | 2029-03-15 | 2031-04-02 |  |  |  |  | Date(s) Updated | 2025 | 2027 | 2029 | 2031 | PRE-PR6 | Not Achieved | Not Achieved | Not Achieved
CP1557 | Cow Cross 110kV Station Refurbishment | Cork | Portfolio | Group 5 | TRUE | Asset Refurbishment | 110 | Pipeline | 2027-02-25 | 2029-03-06 | 2031-08-30 | 2034-11-23 |  |  |  |  | No Updates | 2027 | 2029 | 2031 | 2034 | Not Achieved | Not Achieved | Not Achieved | Not Achieved
CP1559 | Ballymac Phase 2 (Ballymac Solar DAC) (ECP 2-4-07) | Waterford | Portfolio | Group 5 | TRUE | Customer Connection | - | Pipeline | [8 empty] | No Updates |  |  |  |  | Not Achieved | Not Achieved | Not Achieved | Not Achieved
CP1560 | Kilnap 110kV Station - 2 New DSO Transformer Bays | Cork | Portfolio | Group 3 | TRUE | DSO | 110 | Post PA | 2025-08-25 | 2026-06-29 | 2027-03-04 | 2027-10-01 | 2025-08-25 | 2026-02-01 | 2027-03-04 | 2027-10-01 | Date(s) Updated | 2025 | 2026 | 2027 | 2027 | PRE-PR6 | Amber | Not Achieved | Not Achieved
CP1562 | N3 Virginia Bypass Road Advance Ducting | Cavan | Portfolio | Group 5 | TRUE | System Reinforcement | - | Pipeline | 2028-09-15 | 2029-12-21 | [6 empty] | No Updates | 2028 | 2029 |  |  | Not Achieved | Not Achieved | Not Achieved | Not Achieved
CP1563 | N4 Mullingar to Longford Advance Ducting | Westmeath | Portfolio | Group 5 | TRUE | System Reinforcement | - | Pipeline | 2028-09-15 | 2029-12-21 | [6 empty] | No Updates | 2028 | 2029 |  |  | Not Achieved | Not Achieved | Not Achieved | Not Achieved
CP1564 | Affane 110kV Station (Modelligo Solar) | Waterford | Portfolio | Group 5 | TRUE | Customer Connection | 110 | Pre PA | 2026-02-04 | [7 empty] | No Updates | 2026 |  |  |  | Green | Not Achieved | Not Achieved | Not Achieved
CP1565 | Kilteel 110 kV Station (Transformer Uprate) (DSO) Project Setup | Kildare | Portfolio | Group 5 | TRUE | DSO | 110 | Pipeline | 2026-08-05 | 2027-06-24 | 2029-06-25 | 2029-06-25 |  |  |  |  | Date(s) Updated | 2026 | 2027 | 2029 | 2029 | Not Achieved | Not Achieved | Not Achieved | Not Achieved
CP1566 | Propoge 110 kV (Lyrenacarriga Windfarm and BESS) (Curns Energy Ltd) | Multiple | Portfolio | Group 5 | TRUE | Customer Connection | 110 | Pre PA | 2026-05-08 | [7 empty] | Date(s) Updated | 2026 |  |  |  | Green | Not Achieved | Not Achieved | Not Achieved
CP1567 | Knockdonagh 110kV (Ballyglass Solar Farm) | Clare | Portfolio | Group 5 | TRUE | Customer Connection | 110 | Pre PA | 2026-01-19 | [7 empty] | No Updates | 2026 |  |  |  | Green | Not Achieved | Not Achieved | Not Achieved
CP1568 | Arva-Carrick On Shannon 110 kV Line Alteration | Multiple | Portfolio | Group 5 | TRUE | Diversion | 110 | Pre PA | 2025-12-18 | 2027-09-01 | 2028-10-02 | 2028-12-18 |  |  |  |  | Date(s) Updated | 2025 | 2027 | 2028 | 2028 | PRE-PR6 | Not Achieved | Not Achieved | Not Achieved
CP1569 | Culmullin 220kV Station (Derryclare WF) | Multiple | Portfolio | Group 5 | TRUE | Customer Connection | 220 | Pre PA | 2026-02-04 | 2026-11-26 | [6 empty] | Date(s) Updated | 2026 | 2026 |  |  | Green | Not Achieved | Not Achieved | Not Achieved
CP1572 | Cregcarragh 110 kV Station (Ballymoneen Phase 2) | Galway | Portfolio | Group 5 | TRUE | Customer Connection | 110 | Pre PA | 2026-05-06 | [7 empty] | Date(s) Updated | 2026 |  |  |  | Green | Not Achieved | Not Achieved | Not Achieved
CP1573 | Kilbarry 110kV Station Redevelopment | Cork | Portfolio | Group 5 | TRUE | Asset Refurbishment | 110 | Pipeline | 2029-07-18 | 2030-08-08 | 2032-03-15 | 2033-03-15 |  |  |  |  | No Updates | 2029 | 2030 | 2032 | 2033 | Not Achieved | Not Achieved | Not Achieved | Not Achieved
CP1574 | Kellis- Kilkenny 110kV Circuit Refurbishment | Multiple | Portfolio | Group 5 | TRUE | Asset Refurbishment | 110 | Pipeline | 2027-06-30 | 2028-08-20 | 2031-09-24 | 2033-12-17 |  |  |  |  | No Updates | 2027 | 2028 | 2031 | 2033 | Not Achieved | Not Achieved | Not Achieved | Not Achieved
CP1575 | Rathkeale 110kV Station Redevelopment | Limerick | Portfolio | Group 5 | TRUE | Asset Refurbishment | 110 | Pipeline | 2029-06-07 | 2030-07-08 | 2032-11-04 | 2033-11-04 |  |  |  |  | No Updates | 2029 | 2030 | 2032 | 2033 | Not Achieved | Not Achieved | Not Achieved | Not Achieved
CP1576 | N25 Midleton to Youghal - Advance Ducting | Cork | Portfolio | Group 5 | TRUE | System Reinforcement | - | Pipeline | 2026-07-20 | 2030-01-18 | [6 empty] | No Updates | 2026 | 2030 |  |  | Not Achieved | Not Achieved | Not Achieved | Not Achieved
CP1577 | N6 Galway City Ring Road ​​- Advance Ducting | Galway | Portfolio | Group 5 | TRUE | System Reinforcement | - | Pipeline | 2026-12-01 | 2030-01-18 | [6 empty] | Date(s) Updated | 2026 | 2030 |  |  | Not Achieved | Not Achieved | Not Achieved | Not Achieved
CP1578 | N11-N25 Oilgate to Rosslare Harbour​-Advance Ducting | Galway | Portfolio | Group 5 | TRUE | System Reinforcement | - | Pipeline | 2029-01-24 | 2030-09-06 | [6 empty] | No Updates | 2029 | 2030 |  |  | Not Achieved | Not Achieved | Not Achieved | Not Achieved
CP1579 | N4 Active Travel Collooney to Castlebaldwin - Advance Ducting | Galway | Portfolio | Group 5 | TRUE | System Reinforcement | - | Pipeline | 2026-08-08 | 2029-03-20 | [6 empty] | No Updates | 2026 | 2029 |  |  | Not Achieved | Not Achieved | Not Achieved | Not Achieved
CP1580 | N24 Waterford to Cahir ​​​ - Advance Ducting | Multiple | Portfolio | Group 5 | TRUE | System Reinforcement | - | Pipeline | 2026-11-20 | 2030-01-18 | [6 empty] | No Updates | 2026 | 2030 |  |  | Not Achieved | Not Achieved | Not Achieved | Not Achieved
CP1581 | N72 Mallow Relief Road - Advance Ducting | Cork | Portfolio | Group 5 | TRUE | System Reinforcement | - | Pipeline | 2026-12-01 | 2029-03-20 | [6 empty] | Date(s) Updated | 2026 | 2029 |  |  | Not Achieved | Not Achieved | Not Achieved | Not Achieved
CP1582 | N3 M50 to Clonee - Advance Ducting | Donegal | Portfolio | Group 5 | TRUE | System Reinforcement | - | Pipeline | 2026-08-07 | 2029-03-20 | [6 empty] | No Updates | 2026 | 2029 |  |  | Not Achieved | Not Achieved | Not Achieved | Not Achieved
CP1583 | N24 Cahir to Limerick Junction​​ - Advance Ducting Project | Limerick | Portfolio | Group 5 | TRUE | System Reinforcement | - | Pipeline | 2026-08-07 | 2029-03-20 | [6 empty] | No Updates | 2026 | 2029 |  |  | Not Achieved | Not Achieved | Not Achieved | Not Achieved
CP1584 | Carlow Southern Relief Road - Advance Ducting | Carlow | Portfolio | Group 5 | TRUE | System Reinforcement | - | Pipeline | 2026-08-07 | 2030-01-18 | [6 empty] | No Updates | 2026 | 2030 |  |  | Not Achieved | Not Achieved | Not Achieved | Not Achieved
DSO-02 | Belmayne 110 kV/38 kV/MV | Dublin | Portfolio | Group 3 | TRUE | DSO | 110 | Pipeline | [8 empty] | No Updates |  |  |  |  | Not Achieved | Not Achieved | Not Achieved | Not Achieved
DSO-03 | New South East Carlow 110/20 kV | Carlow | Portfolio | Group 3 | TRUE | DSO | 110 | Pre PA | 2026-06-30 | 2027-05-04 | 2030-09-02 | 2030-12-03 | 2026-06-30 | 2027-05-02 | 2030-09-02 | 2030-12-03 | Date(s) Updated | 2026 | 2027 | 2030 | 2030 | Green | Not Achieved | Not Achieved | Not Achieved
DSO-06 | Bishopstown (Wilton) 110 kV/38 kV/MV | Waterford | Portfolio | Group 3 | TRUE | DSO | 110 | Pipeline | 2026-11-02 | 2027-08-01 | 2030-06-04 | 2030-10-02 | 2026-11-01 | 2027-08-01 | 2030-06-04 | 2030-10-02 | Date(s) Updated | 2026 | 2027 | 2030 | 2030 | Not Achieved | Not Achieved | Not Achieved | Not Achieved
CP1610 | Marina Phase 1 / Phase 2 | Cork | Portfolio | Group 3 | TRUE | DSO | 110 | Pre PA | 2026-03-30 | 2026-12-17 | 2028-01-10 | 2028-12-20 |  |  |  |  | Date(s) Updated | 2026 | 2026 | 2028 | 2028 | Green | Not Achieved | Not Achieved | Not Achieved
DSO-12 | Blundlestown 110/38 kV | Meath | Portfolio | Group 3 | TRUE | DSO | 110 | Pipeline | [8 empty] | No Updates |  |  |  |  | Not Achieved | Not Achieved | Not Achieved | Not Achieved
DSO-13 | New 110 kV/20 kV Killinick/Rosslare/Dennistown | Donegal | Portfolio | Group 3 | TRUE | DSO | 110 | Pipeline | 2026-12-01 | 2027-10-02 | 2030-08-02 | 2030-11-01 | 2026-12-01 | 2027-10-02 | 2030-08-02 | 2030-11-01 | Date(s) Updated | 2026 | 2027 | 2030 | 2030 | Not Achieved | Not Achieved | Not Achieved | Not Achieved
DSO-15 | 4th transformer in Carrickmines 220kV BSP (Detail ) | Dublin | Portfolio | Group 3 | TRUE | DSO | 220 | Pipeline | [8 empty] | No Updates |  |  |  |  | Not Achieved | Not Achieved | Not Achieved | Not Achieved
DSO-16 | New 110 kV/MV Station Fermoy | Cork | Portfolio | Group 3 | TRUE | DSO | 110 | Pipeline | 2026-10-01 | 2027-05-17 | 2030-06-03 | 2030-09-02 |  |  |  |  | Date(s) Updated | 2026 | 2027 | 2030 | 2030 | Not Achieved | Not Achieved | Not Achieved | Not Achieved
DSO-17 | New North-East Cashel 110 kV/MV station (Kill Hill) | Galway | Portfolio | Group 3 | TRUE | DSO | 110 | Pipeline | 2026-08-30 | 2027-06-01 | 2030-06-11 | 2030-11-04 | 2026-08-30 | 2027-06-01 | 2030-06-11 | 2030-11-04 | Date(s) Updated | 2026 | 2027 | 2030 | 2030 | Not Achieved | Not Achieved | Not Achieved | Not Achieved
DSO-18 | New Monaghan (Cavan) 110 kV/MV Station | Monaghan | Portfolio | Group 3 | TRUE | DSO | 110 | Pipeline | [8 empty] | No Updates |  |  |  |  | Not Achieved | Not Achieved | Not Achieved | Not Achieved
CP1609 | Newbridge G2 | Kildare | Portfolio | Group 3 | TRUE | DSO | 110 | Post PA | 2026-06-10 | 2026-06-10 | 2026-12-01 | 2027-03-01 |  |  |  |  | Date(s) Updated | 2026 | 2026 | 2026 | 2027 | Green | Green | Not Achieved | Not Achieved
CP1628 | Dungarvan G2 | Waterford | Portfolio | Group 3 | TRUE | DSO | 110 | Pipeline | 2026-09-01 | 2027-01-04 | 2027-12-01 | 2027-12-01 |  |  |  |  | No Updates | 2026 | 2027 | 2027 | 2027 | Not Achieved | Not Achieved | Not Achieved | Not Achieved
DSO-22 | Drybridge G1 | Louth | Portfolio | Group 3 | TRUE | DSO | 110 | Pipeline | 2026-07-01 | 2026-09-18 | 2027-07-01 | 2027-12-01 |  |  |  |  | Date(s) Updated | 2026 | 2026 | 2027 | 2027 | Not Achieved | Not Achieved | Not Achieved | Not Achieved
DSO-23 | Griffinrath G1 | Kildare | Portfolio | Group 3 | TRUE | DSO | 110 | Pipeline | 2026-10-01 | 2027-01-08 | 2026-12-01 | 2027-12-01 |  |  |  |  | Date(s) Updated | 2026 | 2027 | 2026 | 2027 | Not Achieved | Not Achieved | Not Achieved | Not Achieved
DSO-24 | Galway G4 | Galway | Portfolio | Group 3 | TRUE | DSO | 110 | Pipeline | 2027-06-01 | 2028-01-03 | 2028-06-01 | 2028-09-01 |  |  |  |  | No Updates | 2027 | 2028 | 2028 | 2028 | Not Achieved | Not Achieved | Not Achieved | Not Achieved
DSO-25 | Drumline G2 | Clare | Portfolio | Group 3 | TRUE | DSO | 110 | Pipeline | 2027-04-01 | 2028-01-01 | 2028-06-01 | 2029-07-12 | 2027-04-01 | 2028-01-01 | 2028-06-01 | 2029-07-12 | No Updates | 2027 | 2028 | 2028 | 2029 | Not Achieved | Not Achieved | Not Achieved | Not Achieved
CP1614 | New 110 kV/MV Station near Killacloyne | Cork | Portfolio | Group 3 | TRUE | DSO | 110 | Pipeline | [8 empty] | Date(s) Updated |  |  |  |  | Not Achieved | Not Achieved | Not Achieved | Not Achieved
CP1613 | Newbridge East 110/38 kV | Kildare | Portfolio | Group 3 | TRUE | DSO | 110 | Pre PA | 2026-06-26 | 2026-12-01 | 2030-08-01 | 2030-11-01 |  |  |  |  | Date(s) Updated | 2026 | 2026 | 2030 | 2030 | Green | Not Achieved | Not Achieved | Not Achieved
CP1627 | Athy G4 | Kildare | Portfolio | Group 3 | TRUE | DSO | 110 | Pipeline | 2026-07-01 | 2026-12-01 | 2027-11-01 | 2027-11-01 |  |  |  |  | No Updates | 2026 | 2026 | 2027 | 2027 | Not Achieved | Not Achieved | Not Achieved | Not Achieved
DSO-29 | Charleville G3 | Cork | Portfolio | Group 3 | TRUE | DSO | 110 | Pipeline | 2026-08-04 | 2026-12-30 | 2028-05-01 | 2029-04-10 | 2026-03-02 | 2026-12-30 | 2027-08-11 | 2029-04-10 | Date(s) Updated | 2026 | 2026 | 2028 | 2029 | Not Achieved | Not Achieved | Not Achieved | Not Achieved
DSO-30 | Oughtragh G3 | Kerry | Portfolio | Group 3 | TRUE | DSO | 110 | Pipeline | [8 empty] | Date(s) Updated |  |  |  |  | Not Achieved | Not Achieved | Not Achieved | Not Achieved
DSO-32 | New West Portlaoise 110 kV Station | Laois | Portfolio | Group 3 | TRUE | DSO | 110 | Pipeline | [8 empty] | No Updates |  |  |  |  | Not Achieved | Not Achieved | Not Achieved | Not Achieved
DSO-33 | New East Athlone 110 kV/38 kV/MV | Westmeath | Portfolio | Group 3 | TRUE | DSO | 110 | Pipeline | [8 empty] | No Updates |  |  |  |  | Not Achieved | Not Achieved | Not Achieved | Not Achieved
CP1634 | New Mayfield/Riverstown 110/MV 2 x 31.5 MVA | Mayo | Portfolio | Group 3 | TRUE | DSO | 110 | Pre PA | 2026-06-01 | 2026-12-01 | 2030-09-02 | 2030-12-02 |  |  |  |  | Date(s) Updated | 2026 | 2026 | 2030 | 2030 | Green | Not Achieved | Not Achieved | Not Achieved
DSO-35 | New 110 kV/MV station at Birdhill | Tipperary | Portfolio | Group 3 | TRUE | DSO | 110 | Pipeline | [8 empty] | No Updates |  |  |  |  | Not Achieved | Not Achieved | Not Achieved | Not Achieved
DSO-36 | Castleview 110 kV/MV (Little Island) | Cork | Portfolio | Group 3 | TRUE | DSO | 110 | Pipeline | [8 empty] | No Updates |  |  |  |  | Not Achieved | Not Achieved | Not Achieved | Not Achieved
DSO-37 | New Navan 110/38 kV or 110 kV/MV station | Meath | Portfolio | Group 3 | TRUE | DSO | 110 | Pipeline | [8 empty] | No Updates |  |  |  |  | Not Achieved | Not Achieved | Not Achieved | Not Achieved
DSO-38 | Rinwade 110/38/MV Station | Kildare | Portfolio | Group 3 | TRUE | DSO | 110 | Pipeline | [8 empty] | No Updates |  |  |  |  | Not Achieved | Not Achieved | Not Achieved | Not Achieved
DSO-40 | Bandon G2 | Cork | Portfolio | Group 3 | TRUE | DSO | 110 | Pipeline | 2026-08-03 | 2026-11-02 | 2028-09-01 | 2028-09-01 |  |  |  |  | No Updates | 2026 | 2026 | 2028 | 2028 | Not Achieved | Not Achieved | Not Achieved | Not Achieved
DSO-43 | Courtlough (M1) 110 kV/38 kV/MV | Dublin | Portfolio | Group 3 | TRUE | DSO | 110 | Pipeline | [8 empty] | No Updates |  |  |  |  | Not Achieved | Not Achieved | Not Achieved | Not Achieved
DSO-45 | Dalton G3 | Mayo | Portfolio | Group 3 | TRUE | DSO | - | Pipeline | 2026-09-01 | 2027-02-11 | 2028-06-01 | 2028-06-01 |  |  |  |  | Date(s) Updated | 2026 | 2027 | 2028 | 2028 | Not Achieved | Not Achieved | Not Achieved | Not Achieved
DSO-51 | Bellacorrick uprate to 2x63 MVA | Mayo | Portfolio | Group 3 | TRUE | DSO | - | Pipeline | [8 empty] | No Updates |  |  |  |  | Not Achieved | Not Achieved | Not Achieved | Not Achieved
DSO-52 | Limerick G1 | Limerick | Portfolio | Group 3 | TRUE | DSO | - | Pipeline | 2026-07-31 | 2026-12-30 | 2027-09-17 | 2029-05-28 | 2026-03-02 | 2026-12-30 | 2027-09-17 | 2029-05-28 | No Updates | 2026 | 2026 | 2027 | 2029 | Not Achieved | Not Achieved | Not Achieved | Not Achieved
CP1626 | Kinnegad G4 | Meath | Portfolio | Group 3 | TRUE | DSO | - | Pipeline |  | 2026-09-01 | 2027-12-01 | 2027-12-01 |  |  |  |  | Date(s) Updated |  | 2026 | 2027 | 2027 | Not Achieved | Not Achieved | Not Achieved | Not Achieved
DSO-57 | Macetown G4 | Dublin | Portfolio | Group 3 | TRUE | DSO | - | Pipeline | 2026-08-04 | 2026-12-30 | 2028-05-31 | 2028-07-31 | 2026-03-02 | 2026-12-30 | 2028-05-31 | 2028-07-31 | No Updates | 2026 | 2026 | 2028 | 2028 | Not Achieved | Not Achieved | Not Achieved | Not Achieved
DSO-58 | Blake G3 | Kildare | Portfolio | Group 3 | TRUE | DSO | - | Pipeline | 2027-04-30 | 2028-01-03 | 2028-06-01 | 2028-09-01 |  |  |  |  | No Updates | 2027 | 2028 | 2028 | 2028 | Not Achieved | Not Achieved | Not Achieved | Not Achieved
CP1607 | College Park G4 | Dublin | Portfolio | Group 3 | TRUE | DSO | - | Pre PA | 2026-03-13 | 2026-09-01 | 2027-11-01 | 2027-11-01 |  |  |  |  | Date(s) Updated | 2026 | 2026 | 2027 | 2027 | Green | Not Achieved | Not Achieved | Not Achieved
CP1608 | Crane G5 | Wexford | Portfolio | Group 3 | TRUE | DSO | - | Pipeline | 2026-07-17 | 2026-12-22 | 2028-10-02 | 2028-10-02 |  |  |  |  | Date(s) Updated | 2026 | 2026 | 2028 | 2028 | Not Achieved | Not Achieved | Not Achieved | Not Achieved
DSO-82 | Barrymore (Farran Solar) | Cork | Portfolio | Group 5 | TRUE | DSO | - | Pipeline |  | 2029-10-22 | 2033-03-15 | 2033-05-14 |  |  |  |  | Date(s) Updated |  | 2029 | 2033 | 2033 | Not Achieved | Not Achieved | Not Achieved | Not Achieved
DSO-83 | Macroom (Berrings Solar) ECP 2.2 | Cork | Portfolio | Group 5 | TRUE | DSO | - | Pipeline |  | 2030-05-24 | 2032-08-10 | 2033-03-29 |  |  |  |  | Date(s) Updated |  | 2030 | 2032 | 2033 | Not Achieved | Not Achieved | Not Achieved | Not Achieved
DSO-97 | Poolbeg (Ringsend) third transformer | Dublin | Portfolio | Group 5 | TRUE | DSO | - | Pipeline |  | 2030-05-05 | 2032-05-13 | 2033-04-19 |  |  |  |  | Date(s) Updated |  | 2030 | 2032 | 2033 | Not Achieved | Not Achieved | Not Achieved | Not Achieved
DSO-98 | Monread | Kildare | Portfolio | Group 3 | TRUE | DSO | - | Pipeline | 2026-12-01 | 2027-09-01 | 2028-05-31 | 2028-07-31 | 2026-12-01 | 2027-09-01 | 2028-05-31 | 2028-07-31 | No Updates | 2026 | 2027 | 2028 | 2028 | Not Achieved | Not Achieved | Not Achieved | Not Achieved
CP1615 | Tipperary DSO | Tipperary | Portfolio | Group 3 | TRUE | DSO | - | Pre PA | 2026-03-13 | 2026-08-06 | 2027-01-18 | 2027-12-14 |  |  |  |  | Date(s) Updated | 2026 | 2026 | 2027 | 2027 | Green | Not Achieved | Not Achieved | Not Achieved
ECP-2.4-07 | Coolcarrigan Solar P2 | Kildare | Portfolio | Group 5 | TRUE | Customer Connection | - | Pipeline | [8 empty] | No Updates |  |  |  |  | Not Achieved | Not Achieved | Not Achieved | Not Achieved
ECP-2.4-14 | Culmullin Solar Farm | Meath | Portfolio | Group 5 | TRUE | Customer Connection | - | Pipeline | [8 empty] | No Updates |  |  |  |  | Not Achieved | Not Achieved | Not Achieved | Not Achieved
ECP-2.4-18 | Fieldstown Extension No.2 | Dublin | Portfolio | Group 5 | TRUE | Customer Connection | - | Pipeline | [8 empty] | No Updates |  |  |  |  | Not Achieved | Not Achieved | Not Achieved | Not Achieved
CP1589 | Friarstown Solar Farm | Westmeath | Portfolio | Group 5 | TRUE | Customer Connection | - | Pipeline | [8 empty] | No Updates |  |  |  |  | Not Achieved | Not Achieved | Not Achieved | Not Achieved
ECP-2.4-21 | Ballyroe Solar Extension | Cork | Portfolio | Group 5 | TRUE | Customer Connection | - | Pipeline | [8 empty] | No Updates |  |  |  |  | Not Achieved | Not Achieved | Not Achieved | Not Achieved
ECP-2.4-23 | Barnaleen Solar Phase 2 | Cork | Portfolio | Group 5 | TRUE | Customer Connection | - | Pipeline | [8 empty] | No Updates |  |  |  |  | Not Achieved | Not Achieved | Not Achieved | Not Achieved
ECP-2.4-25 | Reask Phase 2 | Limerick | Portfolio | Group 5 | TRUE | Customer Connection | - | Pipeline | [8 empty] | No Updates |  |  |  |  | Not Achieved | Not Achieved | Not Achieved | Not Achieved
ECP-2.4-29 | Tawnaghmore DC Power | Mayo | Portfolio | Group 5 | TRUE | Customer Connection | - | Pipeline | [8 empty] | No Updates |  |  |  |  | Not Achieved | Not Achieved | Not Achieved | Not Achieved
ECP-2.4-37 | Tarbert BESS | Kerry | Portfolio | Group 5 | TRUE | Customer Connection | - | Pipeline | [8 empty] | No Updates |  |  |  |  | Not Achieved | Not Achieved | Not Achieved | Not Achieved
CP1641 | Kilmorna Energy Storage Facility | Kerry | Portfolio | Group 5 | TRUE | Customer Connection | - | Pipeline | [8 empty] | No Updates |  |  |  |  | Not Achieved | Not Achieved | Not Achieved | Not Achieved
CP1632 | Flagford Battery Storage | Roscommon | Portfolio | Group 5 | TRUE | Customer Connection | - | Pipeline | [8 empty] | No Updates |  |  |  |  | Not Achieved | Not Achieved | Not Achieved | Not Achieved
ECP-2.4-49 | Aghada Power Station | Cork | Portfolio | Group 5 | TRUE | Customer Connection | - | Pipeline | [8 empty] | No Updates |  |  |  |  | Not Achieved | Not Achieved | Not Achieved | Not Achieved
CP1616 | Tullabeg Phase 3 | Wexford | Portfolio | Group 5 | TRUE | Customer Connection | - | Pipeline | [8 empty] | No Updates |  |  |  |  | Not Achieved | Not Achieved | Not Achieved | Not Achieved
ECP-2.4-54 | Templemichael Solar Plus Storage Facility | Longford | Portfolio | Group 5 | TRUE | Customer Connection | - | Pipeline | [8 empty] | No Updates |  |  |  |  | Not Achieved | Not Achieved | Not Achieved | Not Achieved
ECP-2.4-55 | Clondardis Solar | Westmeath | Portfolio | Group 5 | TRUE | Customer Connection | - | Pipeline | [8 empty] | No Updates |  |  |  |  | Not Achieved | Not Achieved | Not Achieved | Not Achieved
ECP-2.4-57 | Darthogue Solar Farm Ext 2 | Meath | Portfolio | Group 5 | TRUE | Customer Connection | - | Pipeline | [8 empty] | No Updates |  |  |  |  | Not Achieved | Not Achieved | Not Achieved | Not Achieved
ECP-2.4-61 | Ballysumaghan BESS & SC | Clare | Portfolio | Group 5 | TRUE | Customer Connection | - | Pipeline | [8 empty] | No Updates |  |  |  |  | Not Achieved | Not Achieved | Not Achieved | Not Achieved
CP0848 | Castlebar-Cloon 110 kV Line Uprate-Refurb | Multiple | Portfolio | Group 3 | TRUE | System Reinforcement | 110 | Post PA | 2020-09-16 | 2023-12-15 | 2027-04-02 | 2028-11-30 | 2020-09-30 | 2023-12-20 |  | 2027-12-20 | Date(s) Updated | 2020 | 2023 | 2027 | 2028 | PRE-PR6 | PRE-PR6 | Not Achieved | Not Achieved
CP1004 | Killonan - Limerick No 1 110 kV Uprate | Limerick | Portfolio | Not in FD | FALSE | Asset Refurbishment | 110 | Post PA | 2024-09-12 | 2025-12-11 | 2028-11-30 | 2028-11-30 |  |  |  |  | Date(s) Updated | 2024 | 2025 | 2028 | 2028 | PRE-PR6 | PRE-PR6 | Not Achieved | Not Achieved
CP1078 | Lanesboro – Sliabh Bawn 110 KV Line Uprate | Multiple | Portfolio | Group 3 | TRUE | System Reinforcement | 110 | Post PA | 2021-02-18 | 2024-03-06 |  | 2030-11-01 | 2021-03-31 | 2024-03-31 |  | 2026-12-20 | No Updates | 2021 | 2024 |  | 2030 | PRE-PR6 | PRE-PR6 | Not Achieved | Not Achieved
CP1104 | Pollaphuca Refurbishment Project | Multiple | Portfolio | Group 3 | TRUE | Asset Refurbishment | 110 | Post PA | 2023-09-08 | 2025-12-22 | 2027-08-18 | 2029-06-22 | 2023-09-08 | 2025-06-13 |  | 2028-05-29 | Date(s) Updated | 2023 | 2025 | 2027 | 2029 | PRE-PR6 | PRE-PR6 | Not Achieved | Not Achieved
CP1108 | Dunstown Station 400-220 kV Protection Upgrade | Kildare | Portfolio | Not in FD | FALSE | Asset Refurbishment | 400 | Post PA | 2020-05-18 | 2021-03-19 |  | 2028-12-29 |  |  |  |  | Date(s) Updated | 2020 | 2021 |  | 2028 | PRE-PR6 | PRE-PR6 | Not Achieved | Not Achieved
CP1144 | Kinnegad 110 kV station, Derryiron 110 kV bay conductor uprate | Meath | Portfolio | Group 3 | TRUE | System Reinforcement | 110 | Post PA | 2021-01-22 | 2021-12-09 |  | 2028-11-30 | 2021-03-31 | 2021-12-20 |  | 2026-12-20 | Date(s) Updated | 2021 | 2021 |  | 2028 | PRE-PR6 | PRE-PR6 | Not Achieved | Not Achieved
CP1153 | Oldstreet Tynagh & Cashla 400 kV and 220 kV Protection Upgrade | Multiple | Portfolio | Not in FD | FALSE | Asset Refurbishment | 400 | Post PA | 2020-11-12 | 2021-08-05 | 2025-10-02 | 2027-11-30 |  |  |  |  | No Updates | 2020 | 2021 | 2025 | 2027 | PRE-PR6 | PRE-PR6 | PRE-PR6 | Not Achieved
CP1156 | Sligo 110 kV Station - Shrananagh 1 & 2 Bay uprates | Sligo | Portfolio | Group 3 | TRUE | System Reinforcement | 110 | Post PA | 2021-06-18 | 2022-06-02 | 2025-11-10 | 2028-11-30 | 2021-06-30 | 2022-06-30 |  | 2030-12-20 | No Updates | 2021 | 2022 | 2025 | 2028 | PRE-PR6 | PRE-PR6 | PRE-PR6 | Not Achieved
CP1207 | Lisheen - Thurles 110 kV Protection Upgrade | Tipperary | Portfolio | Not in FD | FALSE | Asset Refurbishment | 110 | Post PA | 2021-11-04 | 2022-10-25 |  | 2028-10-05 |  |  |  |  | No Updates | 2021 | 2022 |  | 2028 | PRE-PR6 | PRE-PR6 | Not Achieved | Not Achieved
CP1211 | Bandon Dunmanway 110 kV circuit thermal capacity | Cork | Portfolio | Group 3 | TRUE | System Reinforcement | 110 | Post PA | 2022-01-21 | 2024-08-07 | 2027-12-04 | 2028-12-04 | 2022-03-31 | 2024-09-30 |  | 2026-12-20 | Date(s) Updated | 2022 | 2024 | 2027 | 2028 | PRE-PR6 | PRE-PR6 | Not Achieved | Not Achieved
CP1250 | Sprecher and Schuh Circuit Breaker replacement | Multiple | Portfolio | Not in FD | FALSE | Asset Refurbishment | 110 | Post PA | 2023-10-09 | 2025-10-28 | 2027-04-01 | 2028-10-18 |  |  |  |  | No Updates | 2023 | 2025 | 2027 | 2028 | PRE-PR6 | PRE-PR6 | Not Achieved | Not Achieved
CP1322 | Cathaleens Fall - Coraclassy 110 kV circuit 1 (DLR) | Multiple | Portfolio | Group 2 | TRUE | System Reinforcement | 110 | Post PA | 2023-04-05 | 2024-09-27 | 2029-08-01 | 2029-08-01 | 2023-06-30 | 2024-12-20 |  | 2026-12-20 | Date(s) Updated | 2023 | 2024 | 2029 | 2029 | PRE-PR6 | PRE-PR6 | Not Achieved | Not Achieved
CP1470 | Galway - Salthill Thermal Capacity Need | Galway | Portfolio | Not in FD | FALSE | System Reinforcement | 110 | Post PA | 2024-12-20 | 2025-12-17 |  | 2029-11-20 |  |  |  |  | No Updates | 2024 | 2025 |  | 2029 | PRE-PR6 | PRE-PR6 | Not Achieved | Not Achieved
CP1538 | Prospect Land Acquisition | Multiple | Portfolio | Not in FD | FALSE | Asset Refurbishment | - | Post PA | 2025-04-01 | 2025-04-24 | [6 empty] | Date(s) Updated | 2025 | 2025 |  |  | PRE-PR6 | PRE-PR6 | Not Achieved | Not Achieved
CP1555 | Louth Woodland 220kV OHL diversion | Louth | Portfolio | Not in FD | FALSE | Diversion | 220 | Pre PA | 2025-10-01 | 2027-03-31 | 2027-03-31 | 2027-12-07 |  |  |  |  | Date(s) Updated | 2025 | 2027 | 2027 | 2027 | PRE-PR6 | Not Achieved | Not Achieved | Not Achieved
CP1269 | The Dell Solar Lodgewood 220kV Crory Station | Wexford | Portfolio | Group 3 | TRUE | Customer Connection | 110 | Post EI | 2022-09-01 | 2023-12-06 | 2026-04-02 | 2026-04-02 | 2022-09-30 | 2023-12-20 |  | 2026-12-20 | No Updates | 2022 | 2023 | 2026 | 2026 | PRE-PR6 | PRE-PR6 | Green | Green
CP0813 | Trien 110 kV Station Works | Kerry | Portfolio | Not in FD | FALSE | System Reinforcement | 110 | Post PA | 2019-04-04 | 2021-10-22 |  | 2026-12-31 |  |  |  |  | No Updates | 2019 | 2021 |  | 2026 | PRE-PR6 | PRE-PR6 | Not Achieved | Not Achieved
CP1022 | Maynooth - Turlough Hill PLC Replacement | Multiple | Portfolio | Not in FD | FALSE | Asset Refurbishment | 220 | Post PA | 2018-06-22 | 2019-12-06 |  | 2026-12-31 |  |  |  |  | No Updates | 2018 | 2019 |  | 2026 | PRE-PR6 | PRE-PR6 | Not Achieved | Not Achieved
CP1062 | Drombeg Solar - 110 kV Station | Kerry | Portfolio | Not in FD | FALSE | Customer Connection | 110 | Post EI | 2019-06-28 | 2020-12-17 | 2025-10-31 | 2026-03-26 |  |  |  |  | No Updates | 2019 | 2020 | 2025 | 2026 | PRE-PR6 | PRE-PR6 | PRE-PR6 | Green
CP1255 | T-3 P483 Castlelost FlexGen | Multiple | Portfolio | Not in FD | FALSE | Customer Connection | 220 | Post EI | 2022-05-04 | 2023-08-28 |  | 2026-05-29 |  |  |  |  | No Updates | 2022 | 2023 |  | 2026 | PRE-PR6 | PRE-PR6 | Not Achieved | Green
CP1256 | T-3 P481 Greener Ideas Profile Park | Dublin | Portfolio | Not in FD | FALSE | Customer Connection | 110 | Post PA | 2022-05-05 | 2024-05-17 |  | 2026-09-09 |  |  |  |  | Date(s) Updated | 2022 | 2024 |  | 2026 | PRE-PR6 | PRE-PR6 | Not Achieved | Not Achieved
CP1359 | Lenalea 110 kV station (Drumnahough Wind Farm) | Donegal | Portfolio | Group 5 | TRUE | Customer Connection | 110 | Post PA | 2024-09-04 | 2025-05-29 | 2027-03-01 | 2027-03-01 | 2024-12-10 | 2025-06-30 |  | 2029-03-31 | Date(s) Updated | 2024 | 2025 | 2027 | 2027 | PRE-PR6 | PRE-PR6 | Not Achieved | Not Achieved
CP1430 | Lanesboro 110 kV Station (Ballycore Solar) | Longford | Portfolio | Group 3 | TRUE | Customer Connection | 110 | Post PA | 2023-12-06 | 2024-12-04 | 2026-09-22 | 2026-09-22 | 2023-12-20 | 2024-12-20 |  | 2026-12-20 | No Updates | 2023 | 2024 | 2026 | 2026 | PRE-PR6 | PRE-PR6 | Not Achieved | Not Achieved
CP1480 | Cruiserath 220kV Station Phase 3 (Amazon Web Services) | Dublin | Portfolio | Not in FD | FALSE | Customer Connection | 220 | Post EI | 2024-05-29 | 2025-06-24 | 2025-11-07 | 2026-01-19 |  |  |  |  | No Updates | 2024 | 2025 | 2025 | 2026 | PRE-PR6 | PRE-PR6 | PRE-PR6 | Green
This shape represents a table slicer. Table slicers are not supported in this version of Excel. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2007 or earlier, the slicer can’t be used.
This shape represents a table slicer. Table slicers are not supported in this version of Excel. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2007 or earlier, the slicer can’t be used.
This shape represents a table slicer. Table slicers are not supported in this version of Excel. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2007 or earlier, the slicer can’t be used.
This shape represents a table slicer. Table slicers are not supported in this version of Excel. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2007 or earlier, the slicer can’t be used.
This shape represents a table slicer. Table slicers are not supported in this version of Excel. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2007 or earlier, the slicer can’t be used.
This shape represents a table slicer. Table slicers are not supported in this version of Excel. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2007 or earlier, the slicer can’t be used.

## 2 - Non-PR6 Projects
Non-PR6 Projects
The Non PR6 Projects worksheet provides transparency of transmission projects that are part of the wider transmission programme including projects at an early stage of development with indicative or unconfirmed timelines and projects not currently within the PR6 delivery scope. Any future proposal to progress a Non PR6 project within PR6 will be subject to the relevant regulatory and governance and regulatory processes.
CP Number | Project Name | Project Driver | Voltage (kV) | CA / GW3 | PA Signed | First Significant Energisation | Final Energisation
CP0817 | Flagford - Sliabh Bawn 110 kV circuit uprate | System Reinforcement | 110 | 2021-02-18 | 2022-06-02 |  | 2025-06-20
CP0857 | Paint Towers Nationwide and refurbish Kilbarry Marina double circuit | Asset Refurbishment | 220 | 2014-02-17 | 2014-11-24 |  | 2025-08-15
CP1031 | Flagford 220 kV Station Sprecher & Schuh CB Replacement | Asset Refurbishment | 220 | 2018-06-01 | 2019-10-21 |  | 2024-11-11
CP1055 | Harristown Solar Farm | Customer Connection | 110
CP1149 | Newbridge - Cushaling 110 kV line, Stations bay conductors and lead-in conductor uprate | System Reinforcement | 110 | 2021-01-22 | 2021-11-04
CP1158 | Rattin 110 kV Station (Clonfad Solar) | Customer Connection | 110 | 2021-01-19 | 2022-12-22 | 2025-12-12 | 2025-12-18
CP1167 | Drybride - Oldbridge - Platin 110 kV line uprate | Customer Connection | 110 | 2021-03-18 | 2023-10-27 | 2025-06-05 | 2025-08-18
CP1200 | Carrickmines Area 220 kV Cable Ducting | System Reinforcement | 220 | 2021-09-30 | 2022-12-20
CP1220 | Garrintaggart 110 kV Station - Pinewoods Wind Farm | Customer Connection | 110
CP1232 | Derryiron 110 kV Busbar Uprate | System Reinforcement | 110 | 2022-04-29 | 2023-07-06 |  | 2025-09-12
CP1262 | Shanonagh 110kV Station | Customer Connection | 110
CP1277 | Intel 110kV line diversion | Conflict | 110 | 2022-11-30 | 2024-11-29 | 2025-09-03 | 2025-09-04
CP1286 | Tonroe 110kV Station DSO | Customer Connection | 110 | 2023-07-19 | 2024-12-09
CP1304 | Strategic Spares for OHL, Stations and Cables | Asset Refurbishment | 110 | 2023-03-08 | 2024-12-16
CP1317 | Bellacorrick - Castlebar 110 kV circuit 1 (DLR) | System Reinforcement | 110
CP1321 | Cashla - Dalton 110 kV circuit 1 (DLR) | System Reinforcement | 110 | 2023-03-23 | 2024-06-28
CP1324 | Clashavoon - Knockraha or Cullenagh - Knockraha 220 kV lines (PFC) | System Reinforcement | 220
CP1370 | Connections Projects Placeholder (ECP 2-3-23) | Customer Connection | Pipeline
CP1371 | Connections Projects Placeholder (ECP 2-3-24) | Customer Connection | Pipeline
CP1376 | Pollagh 110kV Station (Shronowen Wind Farm) | Customer Connection | 110 | 2024-07-03
CP1381 | Maynooth - Rinawade 110V line uprate | System Reinforcement | 110
CP1382 | Increased capacity Cullenagh-Waterford | System Reinforcement
CP1383 | Killonan - Knockraha 220 kV line (PFC) | System Reinforcement | 220
CP1387 | Letterkenny - Cathaleen_s or Letterkenny - Clogher 110 kV lines (PFC) | System Reinforcement | 110
CP1388 | Letterkenny - Tievebrack - Binbane 110 kV lines (PFC) | System Reinforcement | 110
CP1391 | Maynooth-Derryiron-Timahoe 110 kV Line Uprate | System Reinforcement | 110 | 2023-04-06 | 2025-12-18
CP1393 | Offshore Phase 1 Project 1 - Skerd Rocks | Customer Connection | 220
CP1395 | Offshore Phase 1 Project 3 - Codling Wind Park 2 | Customer Connection
CP1399 | Offshore Phase 2 Project 1 - Placeholder | Customer Connection
CP1400 | Offshore Phase 2 Project 2 - Placeholder | Customer Connection
CP1404 | Sligo - Srananagh - Corderry 110 kV lines (PFC) | System Reinforcement | 110
CP1497 | Derrycarney - Portlaoise 110 kV Fibre Wrapping | System Reinforcement
DSO-01 | DSO Station 1 | TBC
DSO-04 | DSO Station 4 | TBC
DSO-05 | DSO Station 5 | TBC
DSO-07 | DSO Station 7 | TBC
DSO-08 | DSO Station 8 | TBC
DSO-09 | DSO Station 9 | TBC
DSO-11 | DSO Station 11 | TBC
DSO-14 | DSO Station 14 | TBC
DSO-20 | DSO Station 20 | TBC
DSO-31 | DSO Station 31 | TBC
DSO-39 | DSO Station 39 | TBC
DSO-41 | DSO Station 41 | TBC
DSO-42 | DSO Station 42 | TBC
EAM01 | Station Refurbishments Replacement | TBC
EAM02 | Transformer Replacements x6 | TBC
EAM03 | Replacement of existing SVC’s x2 | TBC
EAM04 | Replacement of Mobile Cap Banks x4 | TBC
EAM07 | Battery / Generator Replacements | TBC
EAM10 | Bay Control Unit Replacements | TBC
EAM11 | Asbestos Surveys Replacement | TBC
EAM12 | Dedicated Transmission Asset Storage Facility Study | TBC
EAM13 | Replacement Ungreased / Core Greased Conductors | TBC
EAM14 | Replacement of 110 kV Cut Poles | TBC
EAM15 | Tower Painting | TBC
EAM17 | FCI Insulator Replacements | TBC
EAM18 | Sediver Insulator Replacements | TBC
EAM19 | Pilot of Cathodic Protection for OHL | TBC
EAM20 | Artificial Intelligence Research for OHL inspections | TBC
EAM21 | Cables OLCM, PD Monitoring & DAS investigation | TBC
EAM22 | Improvements with reporting & data management | TBC
EAM23 | Production of Corrosion Map for Ireland | TBC
EAM24 | Climate Change Adaptation Studies | TBC
EAM25 | Review design and specs for Link Box | TBC
EAM26 | Link Box Replacements x 25 | TBC
ECP 2-3.18 | Connections Projects Placeholder (ECP 2-3-18) | TBC
ECP 2-3.22 | Connections Projects Placeholder (ECP 2-3-22) | TBC
ECP-2.4-01 | Seven Hills Wind Farm | TBC
ECP-2.4-02 | Coom Green Energy Park | TBC
ECP-2.4-03 | Lyrenacarriga Windfarm and BESS | TBC
ECP-2.4-04 | White Hill Wind Farm | TBC
ECP-2.4-05 | Ballylongford Solar | TBC
ECP-2.4-06 | Kilcormac Solar | TBC
ECP-2.4-08 | Ballyvalode Solar | TBC
ECP-2.4-09 | Knockroe Wind Farm | TBC
ECP-2.4-10 | Garreenleen Solar Farm Phase 2 | TBC
ECP-2.4-11 | Modelligo Solar Farm | TBC
ECP-2.4-12 | Tincurry Solar Farm | TBC
ECP-2.4-13 | Rath Solar PV Extension | TBC
ECP-2.4-15 | TULLYNAMOYLE WIND FARM 6 | TBC
ECP-2.4-16 | Tullamore Solar Farm & BESS | TBC
ECP-2.4-17 | Mill Farm Solar | TBC
ECP-2.4-19 | Drummin Solar | TBC
ECP-2.4-22 | Ballyroe Solar | TBC
ECP-2.4-24 | Ballylough Solar Farm | TBC
ECP-2.4-26 | Ballynahina Solar Farm**planning not finalised | TBC
ECP-2.4-27 | Golden Forth Solar Park | TBC
ECP-2.4-28 | Ballymac Phase 2 | TBC
ECP-2.4-30 | CherryOrchard Solar Park | TBC
ECP-2.4-31 | Ballycunneen PV | TBC
ECP-2.4-32 | Main Solar | TBC
ECP-2.4-33 | Mullagharoy Solar Farm | TBC
ECP-2.4-34 | Cloondara Solar Park | TBC
ECP-2.4-35 | Tonroe Battery Storage System | TBC
ECP-2.4-36 | Lissane West Solar Farm | TBC
ECP-2.4-39 | Silloge/Navan Battery Storage Facility | TBC
ECP-2.4-40 | Clare East BESS Facility | TBC
ECP-2.4-41 | RICHMOND BATTERY STORAGE FACILITY | TBC
ECP-2.4-42 | Horsepasture Battery Storage | TBC
ECP-2.4-44 | Ballyglasheen West BESS Facility | TBC
ECP-2.4-45 | Mothel PV and BESS | TBC
ECP-2.4-46 | Ballykenny Solar | TBC
ECP-2.4-47 | Tooraskeheen Solar & Storage | TBC
ECP-2.4-48 | Spion Kop Windfarm Ext. (Ext to DG978) | TBC
ECP-2.4-50 | Ballymoneen Phase 2 | TBC
ECP-2.4-51 | JOHNSTOWN SOLAR PARK | TBC
ECP-2.4-53 | Lismeen Solar Farm | TBC
ECP-2.4-56 | Sandford Energy Solar Farm Ext. | TBC
ECP-2.4-58 | Cronalaght 3 Wind Farm | TBC
ECP-2.4-59 | Mount Cronalaght Windfarm Repowering | TBC
ECP-2.4-60 | Leam Windfarm | TBC
TPSP 22 | Deenes - Drybridge 110 kV (DLR) | TBC
TPSP 24 | Baltrasna - Corduff 110 kV (DLR) | TBC
TPSP 25 | Crane - Wexford 110 kV (DLR) | TBC
TPSP 26 | Great Island - Waterford 1 110 kV (DLR) | TBC
TPSP 27 | Srananagh - Cathaleen's Fall 2 110 kV (DLR) | TBC
TPSPGrp01 | Macetown 110 kV Busbar Uprate | TBC
TPSPGrp02 | Castleview 110 kV Busbar Uprate | TBC
TPSPGrp03 | Cow Cross 110 kV Busbar Uprate | TBC
TPSPGrp04 | Dundalk 110 kV Busbar Uprate | TBC
TPSPGrp05 | Midleton 110 kV Busbar Uprate | TBC
TPSPGrp06 | Mullagharlin 110 kV Busbar Uprate | TBC
TPSPGrp07 | DSO Demand Driven Projects | TBC
TPSPGrp08 | Renewable / Critical Infrastructure / System Reinforcement / System Reinforcement Driven | TBC
TPSPGrp09 | SOPCM Driven Project A | TBC
TPSPGrp10 | SOPCM Driven Project B | TBC
TPSPGrp11 | TES Driven 2026 | TBC
TPSPGrp12 | TES Driven 2028 | TBC
TPSPGrp13 | Dublin 400 kV Project | TBC
TPSPGrp14 | Cork 220/400 kV Project | TBC
TPSPGrp15 | Maynooth - Shannonbridge - Killonan - Knockraha 400 kV Corridor Project | TBC
TPSPGrp16 | Offshore Supporting Infrastructure Project | TBC
TPSPGrp17 | Short Circuit Mitigation Project 2026 | TBC
TPSPGrp18 | Short Circuit Mitigation Project 2028 | TBC
TPSPGrp19 | Farranrory (CP1280 Ballyragget future proofed cable) | TBC
TPSPGrp20 | Toolestown Solar (CP1459 East Kildare) | TBC
TPSPGrp21 | Midlands (CP1453 - Blake) | TBC
TPSPGrp22 | Wexford DSO demand (Tracystown Solar (CP1260)) | TBC
TPSPGrp23 | NISA cable and remote end station | TBC
TPSPGrp24 | Dernacart (link to Bogtown) (ECP2.4) | TBC
TPSPGrp25 | Culmullin - additional bays for future connection options (ECP 2.4) | TBC
TPSPGrp26 | Friarstown (ECP 2.4) | TBC

## Insights Dashboard
Transmission Infrastructure Delivery Dashboard
Project Information - Q2 2026
The charts below provide an overview of the projects to be delivered or developed in PR6
Number Of PR6 Projects
405
PR6 Project Milestones Summary - Q2 2026
The charts below outlines the number of milestone achieved and forecasted in PR6 annually, in line with the current project schedules in this Q2 2026 TID report.
This chart isn’t available in your version of Excel. Editing this shape or saving this workbook into a different file format will permanently break the chart.

## Definitions
Definitions
CP Number | Unique Capital Project (CP) identifier used by EirGrid & ESB Networks.
Project Name | Official EirGrid & ESN Networks name to describe the project.
County | County of Ireland in which the project is located.
Portfolio | Indicates whether the project is designated as a priority or portfolio project.
Project Driver | Primary driver for which the project is required.
Voltage (kV) | Nominal operating volage of the project's associated infrastructure in kilovolts.
Stage | The project’s current position in the delivery lifecycle.
Capital Approval | EirGrid's formal governance approval for project scope, cost, and timeframe to proceed.
PA Signed | The Project Agreement between EirGrid & ESB Networks has been jointly signed & agreed.
First Significant Energisation | The date the first major part of the project is energised.
Final Energisation | The date the project is fully energised and operational.
Q2-26 Changes | Identifies projects with schedule changes this quarter of more than 30 days, against the previous quarterly TID.
Guidance Note | Please refer to EirGrid's website

## TID Future Development
Future Development
In this section we outline areas for future development of the TID Update throughout PR6. All timescales provided are indicative and subject to change.
Development | Expected Implementation
Summary of changes between TID quarterly updates. | Implemented in Q2-24
Comparison of achieved milestones against the PR6 baseline, via a RAG status | Implemented in Q2-24
Inclusion of the CRU PR6 Final Determination Baseline Dates (CRU2025260) | Implemented in Q2-24
Summary of Outputs & Outcomes for PR6 | Q4-26
Outputs & Outcomes per project following a detailed SO review in 2026. | Q1-27
Third party driven dependencies - A New Colour Coding | Q1-27

## Pivot data (hidden)
Row Labels | Count of CP Number | Row Labels | Count of CP Number | Year | CA Actual | PA Actual | FSEI Actual | FEI Actual | Count of CP Number
Asset Refurbishment | 80 | Post EI | 9 | 2026 | 50 | 63 | 46 | 37 | 405
Customer Connection | 125 | Post PA | 146 | 2027 | 9 | 44 | 55 | 59
System Reinforcement | 130 | Pre PA | 161 | 2028 | 4 | 28 | 31 | 46
DSO | 66 | Pipeline | 89 | 2029 | 6 | 26 | 15 | 33
Diversion | 4 | Grand Total | 405 | 2030 | 0 | 22 | 12 | 24
Grand Total | 405
County | # of projects
Carlow | 16
Cavan | 10
Clare | 23
Cork | 56
Donegal | 16
Dublin | 57
Galway | 28
Kerry | 19
Kildare | 51
Kilkenny | 7
Laois | 12
Leitrim | 1
Limerick | 13
Longford | 7
Louth | 17
Mayo | 13
Meath | 43
Monaghan | 5
Northern Ireland | 2
Offaly | 24
Roscommon | 17
Sligo | 10
Tipperary | 15
Waterford | 15
Westmeath | 8
Wexford | 21
Wicklow | 20

## Counties Map Data (hidden)
Project Code | Project Title | Project Info - County | County - CP in TID
CP0466 | North South 400 kV Interconnector - RoI | Meath | Meath
CP0466 | North South 400 kV Interconnector - RoI | Northern Ireland | Northern Ireland
CP0585 | Laois Kilkenny (Coolnabacky) 400 kV Station - New Station & Associated Lines & Station Works | Clare | Clare
CP0585 | Laois Kilkenny (Coolnabacky) 400 kV Station - New Station & Associated Lines & Station Works | Kildare | Kildare
CP0585 | Laois Kilkenny (Coolnabacky) 400 kV Station - New Station & Associated Lines & Station Works | Kilkenny | Kilkenny
CP0585 | Laois Kilkenny (Coolnabacky) 400 kV Station - New Station & Associated Lines & Station Works | Laois | Laois
CP0622 | Tarbert 220 kV Station Upgrade | Clare | Not In TID
CP0622 | Tarbert 220 kV Station Upgrade | Kerry | Not In TID
CP0624 | Killonan 220 kV Station Refurbishment - Killonan Station Works | Cork | Cork
CP0624 | Killonan 220 kV Station Refurbishment - Killonan Station Works | Kerry | Kerry
CP0624 | Killonan 220 kV Station Refurbishment - Killonan Station Works | Limerick | Limerick
CP0624 | Killonan 220 kV Station Refurbishment - Killonan Station Works | Offaly | Offaly
CP0624 | Killonan 220 kV Station Refurbishment - Killonan Station Works | Tipperary | Tipperary
CP0644 | Bracklone 110 kV Station - DSO | Kildare | Kildare
CP0644 | Bracklone 110 kV Station - DSO | Laois | Laois
CP0646 | Finglas 110 kV Station Redevelopment | Dublin | Dublin
CP0692 | Inchicore - 220 kV GIS Station Upgrade | Dublin | Dublin
CP0692 | Inchicore - 220 kV GIS Station Upgrade | Kildare | Kildare
CP0693 | Baroda 110 kV station - 2 x110 kV Trafo Bays DSO | Kildare | Kildare
CP0741 | Trabeg 110 kV station - uprate 2 x 110 kV transformer bays and control room extension DSO | Cork | Cork
CP0749 | Richardstown 220kV Station (Oriel Offshore WF) | Louth | Louth
CP0749 | Richardstown 220kV Station (Oriel Offshore WF) | Meath | Meath
CP0749 | Richardstown 220kV Station (Oriel Offshore WF) | N/A | N/A
CP0792 | Finglas 220 kV Reconfiguration Project | Dublin | Dublin
CP0796 | Knockraha station & installation of additional couplers | Cork | Cork
CP0799 | Louth 220 kV Station Refurbishment | Cavan | Cavan
CP0799 | Louth 220 kV Station Refurbishment | Louth | Louth
CP0799 | Louth 220 kV Station Refurbishment | Meath | Meath
CP0799 | Louth 220 kV Station Refurbishment | Monaghan | Monaghan
CP0799 | Louth 220 kV Station Refurbishment | Northern Ireland | Northern Ireland
CP0799 | Louth 220 kV Station Refurbishment | Roscommon | Roscommon
CP0808 | Maynooth 220 kV Station Reconfiguration | Kildare | Kildare
CP0816 | North Connacht 110 kV Project | Mayo | Mayo
CP0816 | North Connacht 110 kV Project | Roscommon | Roscommon
CP0817 | Flagford - Sliabh Bawn 110 kV circuit uprate | Roscommon | Not In TID
CP0823 | Maynooth - Turlough Hill 220 kV line refurbishment | Kildare | Kildare
CP0823 | Maynooth - Turlough Hill 220 kV line refurbishment | Wicklow | Wicklow
CP0835 | Coolnabacky - Portlaoise 110 kV line uprate | Laois | Laois
CP0841 | Arva - Carrick-on-Shannon 110 kV line uprate | Cavan | Cavan
CP0841 | Arva - Carrick-on-Shannon 110 kV line uprate | Roscommon | Roscommon
CP0848 | Castlebar-Cloon 110 kV Line Uprate-Refurb | Galway | Galway
CP0848 | Castlebar-Cloon 110 kV Line Uprate-Refurb | Mayo | Mayo
CP0857 | Paint Towers Nationwide and refurbish Kilbarry Marina double circuit | Cork | Not In TID
CP0866 | Great Island - Kellis 220 kV Line Uprate | Carlow | Carlow
CP0866 | Great Island - Kellis 220 kV Line Uprate | Waterford | Waterford
CP0866 | Great Island - Kellis 220 kV Line Uprate | Wexford | Wexford
CP0867 | Flagford - Louth 220 kV Line Refurbishment | Louth | Louth
CP0867 | Flagford - Louth 220 kV Line Refurbishment | Roscommon | Roscommon
CP0868 | Knockraha - Raffeen 220 kV line refurbishment | Cork | Cork
CP0871 | Galway 110 kV Station Redevelopment Project | Galway | Not In TID
CP0873 | Dunstown - Moneypoint 400 kV Refurbishment | Clare | Clare
CP0873 | Dunstown - Moneypoint 400 kV Refurbishment | Kildare | Kildare
CP0901 | Kilbarry - Knockraha 110 kV No 2 Line Refurbishment | Cork | Cork
CP0905 | Louth - Rathrussan 110 kV No 1 Line Uprate | Cavan | Not In TID
CP0905 | Louth - Rathrussan 110 kV No 1 Line Uprate | Louth | Not In TID
CP0907 | Dalton 110 kV Busbar | Mayo | Mayo
CP0917 | Prospect Tarbert 220 kV Cable Replacement Project | Clare | Clare
CP0917 | Prospect Tarbert 220 kV Cable Replacement Project | Kerry | Kerry
CP0919 | Lanesboro 110 kV Station Redevelopment Project | Longford | Longford
CP0949 | Kilnap 110 kV GIS Station | Cork | Cork
CP0966 | Kildare Meath | Kildare | Kildare
CP0966 | Kildare Meath | Meath | Meath
CP0967 | Moneypoint 400 kV Series Capacitor | Clare | Clare
CP0967 | Moneypoint 400 kV Series Capacitor | Laois | Laois
CP0968 | Dunstown 400 kV Series Capacitor | Kildare | Kildare
CP0968 | Dunstown 400 kV Series Capacitor | Laois | Laois
CP0969 | Oldstreet-Woodland 400 kV Series Capacitor | Galway | Galway
CP0969 | Oldstreet-Woodland 400 kV Series Capacitor | Meath | Meath
CP0970 | Cross Shannon 400 kV Cable | Clare | Clare
CP0970 | Cross Shannon 400 kV Cable | Kerry | Kerry
CP0973 | Knockraha Short Circuit Rating Mitigation | Cork | Cork
CP0976 | Portlaoise 110 kV Station Shallow Works | Laois | Not In TID
CP0982 | Flagford Sligo Capacity Needs | Roscommon | Roscommon
CP0982 | Flagford Sligo Capacity Needs | Sligo | Sligo
CP0983 | Point on Wave Controller for Glanagow 220 kV Station | Cork | Cork
CP0984 | Belcamp Shellybanks 220 kV Cable | Dublin | Dublin
CP1000 | Lanesboro - Mullingar 110 kV Thermal Uprate | Longford | Longford
CP1000 | Lanesboro - Mullingar 110 kV Thermal Uprate | Westmeath | Westmeath
CP1001 | Corduff - Finglas 1 & 2 220 kV line refurbishment | Dublin | Dublin
CP1002 | Cushaling - Newbridge 110 kV Thermal Uprate | Kildare | Kildare
CP1002 | Cushaling - Newbridge 110 kV Thermal Uprate | Offaly | Offaly
CP1003 | Cushaling - Portlaoise 110 kV line uprate | Laois | Laois
CP1003 | Cushaling - Portlaoise 110 kV line uprate | Offaly | Offaly
CP1004 | Killonan - Limerick No 1 110 kV Uprate | Limerick | Limerick
CP1021 | East Meath - North Dublin Reinforcement | Dublin | Dublin
CP1021 | East Meath - North Dublin Reinforcement | Meath | Meath
CP1022 | Maynooth - Turlough Hill PLC Replacement | Kildare | Kildare
CP1022 | Maynooth - Turlough Hill PLC Replacement | Wicklow | Wicklow
CP1023 | Letterkenny station redevelopment | Donegal | Donegal
CP1031 | Flagford 220 kV Station Sprecher & Schuh CB Replacement | Galway | Not In TID
CP1031 | Flagford 220 kV Station Sprecher & Schuh CB Replacement | Leitrim | Not In TID
CP1031 | Flagford 220 kV Station Sprecher & Schuh CB Replacement | Louth | Not In TID
CP1031 | Flagford 220 kV Station Sprecher & Schuh CB Replacement | Roscommon | Not In TID
CP1031 | Flagford 220 kV Station Sprecher & Schuh CB Replacement | Sligo | Not In TID
CP1032 | Cashla 220 kV Station Sprecher & Schuh CB Replacement | Galway | Galway
CP1041 | Timahoe 110 kV Station (Timahoe North Solar Farm) | Kildare | Not In TID
CP1041 | Timahoe 110 kV Station (Timahoe North Solar Farm) | Offaly | Not In TID
CP1048 | Power Flow Control Scheme | Donegal | Donegal
CP1059 | Raghra 220 kV Station (Shannonbridge B) | Offaly | Not In TID
CP1060 | Loughteague 110 kV solar farm | Laois | Laois
CP1062 | Drombeg Solar - 110 kV Station | Kerry | Kerry
CP1062 | Drombeg Solar - 110 kV Station | N/A | N/A
CP1064 | Finglas Pantograph Replacement Project | Dublin | Dublin
CP1069 | Ballinknockane 110 kV Station (Ballinknockane Solar Farm) | Kerry | Kerry
CP1069 | Ballinknockane 110 kV Station (Ballinknockane Solar Farm) | Limerick | Limerick
CP1073 | Croaghaun West 110 kV Station (Oweninny 3 Wind Farm) | Mayo | Mayo
CP1073 | Croaghaun West 110 kV Station (Oweninny 3 Wind Farm) | N/A | N/A
CP1078 | Lanesboro – Sliabh Bawn 110 KV Line Uprate | Longford | Longford
CP1078 | Lanesboro – Sliabh Bawn 110 KV Line Uprate | Roscommon | Roscommon
CP1084 | Lisdrumdoagh 110 kV Battery Storage | Monaghan | Monaghan
CP1086 | Dunstown T4201 and Woodland T4201 Transformer replacement | Kildare | Kildare
CP1086 | Dunstown T4201 and Woodland T4201 Transformer replacement | Meath | Meath
CP1092 | New 400 kV Strategic Spare Transformer | Kildare | Kildare
CP1093 | Barnageeragh 110 kV Station (Equinix) | Dublin | Not In TID
CP1096 | Transformer protection upgrade, 6 Stations | Cork | Cork
CP1096 | Transformer protection upgrade, 6 Stations | Galway | Galway
CP1096 | Transformer protection upgrade, 6 Stations | Leitrim | Leitrim
CP1096 | Transformer protection upgrade, 6 Stations | Mayo | Mayo
CP1096 | Transformer protection upgrade, 6 Stations | Sligo | Sligo
CP1096 | Transformer protection upgrade, 6 Stations | Tipperary | Tipperary
CP1100 | Finglas - North Wall Cable Replacement | Dublin | Dublin
CP1104 | Pollaphuca Refurbishment Project | Carlow | Carlow
CP1104 | Pollaphuca Refurbishment Project | Kildare | Kildare
CP1104 | Pollaphuca Refurbishment Project | Wicklow | Wicklow
CP1108 | Dunstown Station 400-220 kV Protection Upgrade | Kildare | Kildare
CP1109 | Gorman and Connected Stations 220-110 kV Protection Upgrade | Meath | Meath
CP1110 | Woodland Station 400-220 kV Protection Upgrade | Meath | Not In TID
CP1111 | Ballydine, Cahir and Connected Stations 110 kV Protection Upgrade | Tipperary | Tipperary
CP1112 | Limerick and Connected Stations 110 kV Protection Upgrade | Limerick | Limerick
CP1113 | Corduff 220 kV Station Deep Works | Dublin | Not In TID
CP1114 | Platin and Connected Stations 110 kV Protection Upgrade | Meath | Meath
CP1115 | Drybridge and Connected Stations 110 kV Protection Upgrade | Louth | Louth
CP1115 | Drybridge and Connected Stations 110 kV Protection Upgrade | Meath | Meath
CP1116 | Tipperary, Cahir and Connected Stations 110 kV Protection Upgrade | Cork | Cork
CP1116 | Tipperary, Cahir and Connected Stations 110 kV Protection Upgrade | Tipperary | Tipperary
CP1119 | Cashla Flagford 220 kV Line Refurbishment | Galway | Not In TID
CP1119 | Cashla Flagford 220 kV Line Refurbishment | Roscommon | Not In TID
CP1121 | Arklow Lodgewood Line Uprate | Wexford | Wexford
CP1121 | Arklow Lodgewood Line Uprate | Wicklow | Wicklow
CP1122 | Physical Security of Transmission Stations - Dublin Region | Dublin | Dublin
CP1122 | Physical Security of Transmission Stations - Dublin Region | Kildare | Kildare
CP1122 | Physical Security of Transmission Stations - Dublin Region | Meath | Meath
CP1123 | Physical Security of Transmission Stations - South Region | Cork | Cork
CP1123 | Physical Security of Transmission Stations - South Region | Tipperary | Tipperary
CP1123 | Physical Security of Transmission Stations - South Region | Waterford | Waterford
CP1123 | Physical Security of Transmission Stations - South Region | Wexford | Wexford
CP1123 | Physical Security of Transmission Stations - South Region | Wicklow | Wicklow
CP1124 | Physical Security of Transmission Stations - North Region | Cavan | Cavan
CP1124 | Physical Security of Transmission Stations - North Region | Louth | Louth
CP1124 | Physical Security of Transmission Stations - North Region | Meath | Meath
CP1124 | Physical Security of Transmission Stations - North Region | Monaghan | Monaghan
CP1124 | Physical Security of Transmission Stations - North Region | Roscommon | Roscommon
CP1125 | Physical Security of Transmission Stations - Central Region | Carlow | Carlow
CP1125 | Physical Security of Transmission Stations - Central Region | Cork | Cork
CP1125 | Physical Security of Transmission Stations - Central Region | Kildare | Kildare
CP1125 | Physical Security of Transmission Stations - Central Region | Kilkenny | Kilkenny
CP1125 | Physical Security of Transmission Stations - Central Region | Limerick | Limerick
CP1125 | Physical Security of Transmission Stations - Central Region | Wicklow | Wicklow
CP1126 | Mully Graffy 110 kV Station (Mully Graffy Windfarm) | Donegal | Donegal
CP1126 | Mully Graffy 110 kV Station (Mully Graffy Windfarm) | N/A | N/A
CP1128 | Ballynanelagh 110kV Substation (Ballyvatta solar farm) | Cork | Cork
CP1128 | Ballynanelagh 110kV Substation (Ballyvatta solar farm) | N/A | N/A
CP1132 | Cow Cross New 110 kV Transformer | Cork | Not In TID
CP1136 | Deenes 110 kV Station (Gaskinstown Solar Farm) | Louth | Not In TID
CP1136 | Deenes 110 kV Station (Gaskinstown Solar Farm) | Meath | Not In TID
CP1137 | Carlow, Kellis 110 kV Protection Upgrade | Carlow | Carlow
CP1139 | Sligo & Srananagh 220 & 110 kV Protection upgrade | Sligo | Sligo
CP1140 | Athy, Carlow and Connected Stations 110 kV Protection Upgrade | Carlow | Carlow
CP1140 | Athy, Carlow and Connected Stations 110 kV Protection Upgrade | Kildare | Kildare
CP1140 | Athy, Carlow and Connected Stations 110 kV Protection Upgrade | Wicklow | Wicklow
CP1141 | Kellis Station 220 kV & 110 kV Protection Upgrade | Carlow | Carlow
CP1142 | Firlough 110 kV Station (Firlough WF) | Mayo | Mayo
CP1142 | Firlough 110 kV Station (Firlough WF) | N/A | N/A
CP1143 | Derrylahan 110 kV Station (Blackwater Bog Solar) | N/A | N/A
CP1143 | Derrylahan 110 kV Station (Blackwater Bog Solar) | Offaly | Offaly
CP1144 | Kinnegad 110 kV station, Derryiron 110 kV bay conductor uprate | Meath | Meath
CP1146 | Carrickmines - Poolbeg 220 kV Cable Replacement | Dublin | Dublin
CP1149 | Newbridge - Cushaling 110 kV line, Stations bay conductors and lead-in conductor uprate | Kildare | Not In TID
CP1149 | Newbridge - Cushaling 110 kV line, Stations bay conductors and lead-in conductor uprate | Offaly | Not In TID
CP1150 | Inchicore - Poolbeg 2 220 kV Cable Replacement | Dublin | Dublin
CP1152 | Arva and Connected Stations 110 kV Protection Upgrade | Cavan | Cavan
CP1152 | Arva and Connected Stations 110 kV Protection Upgrade | Meath | Meath
CP1153 | Oldstreet Tynagh & Cashla 400 kV and 220 kV Protection Upgrade | Clare | Clare
CP1153 | Oldstreet Tynagh & Cashla 400 kV and 220 kV Protection Upgrade | Galway | Galway
CP1155 | Glenree - Moy 110 kV Line Uprate | Mayo | Not In TID
CP1156 | Sligo 110 kV Station - Shrananagh 1 & 2 Bay uprates | Sligo | Sligo
CP1157 | Inchicore - Poolbeg 1 220 kV Cable Replacement | Dublin | Dublin
CP1158 | Rattin 110 kV Station (Clonfad Solar) | Meath | Not In TID
CP1158 | Rattin 110 kV Station (Clonfad Solar) | Westmeath | Not In TID
CP1159 | Cullenagh and connected stations protection upgrade | Tipperary | Tipperary
CP1159 | Cullenagh and connected stations protection upgrade | Waterford | Waterford
CP1160 | Coolroe, Inniscarra & connected stations protection upgrade | Cork | Not In TID
CP1161 | Cathaleens Fall and connected stations 110 kV protection upgrade | Cavan | Cavan
CP1161 | Cathaleens Fall and connected stations 110 kV protection upgrade | Donegal | Donegal
CP1161 | Cathaleens Fall and connected stations 110 kV protection upgrade | Sligo | Sligo
CP1162 | Irishtown, Shellybanks and connected stations 220 kV protection upgrade | Dublin | Dublin
CP1163 | Butlerstown, Killoteran & Waterford 110 kV protection upgrade | Waterford | Waterford
CP1164 | West Cork 110 kV protection upgrade | Cork | Cork
CP1166 | Gorman - Platin 110 kV line uprate | Meath | Meath
CP1167 | Drybride - Oldbridge - Platin 110 kV line uprate | Louth | Not In TID
CP1167 | Drybride - Oldbridge - Platin 110 kV line uprate | Meath | Not In TID
CP1168 | Cashla-Salthill 110 kV Thermal Uprate | Galway | Galway
CP1168 | Cashla-Salthill 110 kV Thermal Uprate | Mayo | Mayo
CP1170 | Newbridge - Portlaoise 110 kV Line uprate | Kildare | Kildare
CP1170 | Newbridge - Portlaoise 110 kV Line uprate | Laois | Laois
CP1171 | Great Island 110 kV Station - 3 DSO Generators | Wexford | Not In TID
CP1172 | Crane - Wexford 110 kV Line uprate | Wexford | Wexford
CP1173 | Glencloosagh Phase 1 - Rotating Stabiliser | Kerry | Kerry
CP1177 | Whitegate 110 kV Station Refurbishment Project | Cork | Cork
CP1182 | Transformer Restoration Project | Carlow | Carlow
CP1182 | Transformer Restoration Project | Cork | Cork
CP1182 | Transformer Restoration Project | Galway | Galway
CP1182 | Transformer Restoration Project | Kildare | Kildare
CP1182 | Transformer Restoration Project | Louth | Louth
CP1182 | Transformer Restoration Project | Meath | Meath
CP1182 | Transformer Restoration Project | Offaly | Offaly
CP1182 | Transformer Restoration Project | Sligo | Sligo
CP1182 | Transformer Restoration Project | Waterford | Waterford
CP1183 | Mooretown 220 kV Station | Dublin | Dublin
CP1183 | Mooretown 220 kV Station | N/A | N/A
CP1186 | Agannygal, Ennis and connected stations 110 kV Protection Upgrade | Clare | Clare
CP1186 | Agannygal, Ennis and connected stations 110 kV Protection Upgrade | Galway | Galway
CP1186 | Agannygal, Ennis and connected stations 110 kV Protection Upgrade | Offaly | Offaly
CP1188 | Kilcarbery 110 kV Station (Profile Park Power Co 1 Ltd) | Dublin | Dublin
CP1188 | Kilcarbery 110 kV Station (Profile Park Power Co 1 Ltd) | N/A | N/A
CP1190 | Poolbeg 220 kV Station | Dublin | Dublin
CP1191 | Cashla-Galway 110 kV cot 1 Line uprate | Galway | Galway
CP1194 | Woodland 400 kV Station Redevelopment | Meath | Meath
CP1195 | Turlough Hill 220 kV Station Refurbishment | Wicklow | Wicklow
CP1196 | Arklow - Ballybeg - Carrickmines 110 kV capacity Needs | Dublin | Dublin
CP1196 | Arklow - Ballybeg - Carrickmines 110 kV capacity Needs | Wicklow | Wicklow
CP1197 | Dunstown Asset Replacements | Carlow | Carlow
CP1197 | Dunstown Asset Replacements | Dublin | Dublin
CP1197 | Dunstown Asset Replacements | Kildare | Kildare
CP1197 | Dunstown Asset Replacements | Wicklow | Wicklow
CP1198 | Barnakyle MIC Increase | Dublin | Dublin
CP1199 | Derryiron - Thornsberry 110 kV Line Uprate | Offaly | Offaly
CP1200 | Carrickmines Area 220 kV Cable Ducting | Dublin | Not In TID
CP1207 | Lisheen - Thurles 110 kV Protection Upgrade | Tipperary | Tipperary
CP1209 | Brown Boveri Circuit Breaker Replacements | Clare | Clare
CP1209 | Brown Boveri Circuit Breaker Replacements | Cork | Cork
CP1209 | Brown Boveri Circuit Breaker Replacements | Kerry | Kerry
CP1209 | Brown Boveri Circuit Breaker Replacements | Limerick | Limerick
CP1209 | Brown Boveri Circuit Breaker Replacements | Louth | Louth
CP1211 | Bandon Dunmanway 110 kV Circuit Thermal Capacity | Cork | Cork
CP1212 | Bandon Raffeen 110 kV Circuit Thermal Capacity | Cork | Cork
CP1213 | Belcamp 220 kV Busbar Extension | Dublin | Dublin
CP1214 | Fingal to East Meath Grid Reinforcement | Dublin | Dublin
CP1214 | Fingal to East Meath Grid Reinforcement | Meath | Meath
CP1214 | Fingal to East Meath Grid Reinforcement | N/A | N/A
CP1215 | Knockraha station Celtic IC Non contested works | Cork | Cork
CP1216 | Poolbeg - North Wall 220 kV Cable Replacement | Dublin | Dublin
CP1217 | Philipstown 110 kV Station (Cushaling Wind Farm) | Laois | Not In TID
CP1217 | Philipstown 110 kV Station (Cushaling Wind Farm) | Offaly | Not In TID
CP1219 | Lickny 110 kV Station (Coole Wind Farm) | N/A | N/A
CP1219 | Lickny 110 kV Station (Coole Wind Farm) | Westmeath | Westmeath
CP1221 | Mulgeeth 110 kV Station - Drehid Wind Farm | Kildare | Kildare
CP1221 | Mulgeeth 110 kV Station - Drehid Wind Farm | N/A | N/A
CP1222 | Knockraha 220 kV Transformer Replacement | Cork | Cork
CP1223 | Bandon 110 kV Busbar Rating Needs | Cork | Cork
CP1224 | Lysaghtstown 110 kV Station | Cork | Cork
CP1225 | Finglas - Corduff 220 kV Protection Upgrade | Dublin | Dublin
CP1226 | Kildare Dublin Grid Reinforcement | Dublin | Dublin
CP1226 | Kildare Dublin Grid Reinforcement | Kildare | Kildare
CP1226 | Kildare Dublin Grid Reinforcement | N/A | N/A
CP1227 | Cashla and Connected Stations 220 kV & 110 kV Protection Upgrade | Clare | Clare
CP1227 | Cashla and Connected Stations 220 kV & 110 kV Protection Upgrade | Galway | Galway
CP1228 | Shannonbridge and Connected Stations 220 kV & 110 kV Protection Upgrade | Offaly | Offaly
CP1228 | Shannonbridge and Connected Stations 220 kV & 110 kV Protection Upgrade | Roscommon | Roscommon
CP1228 | Shannonbridge and Connected Stations 220 kV & 110 kV Protection Upgrade | Tipperary | Tipperary
CP1230 | Darndale 110kV Station Phase 2 (Amazon Web Services) | Dublin | Dublin
CP1231 | Knockdrin 110 kV Station (Yellow River Wind Farm) (SSE) | Offaly | Not In TID
CP1232 | Derryiron 110 kV Busbar Uprate | Offaly | Not In TID
CP1233 | Donegal - Srananagh Corridor | Donegal | Donegal
CP1233 | Donegal - Srananagh Corridor | Sligo | Sligo
CP1234 | Clonin North Solar Farm (UTF into Derryiron 110kV) | Offaly | Not In TID
CP1235 | Louth - Woodland 220 kV Uprate | Louth | Louth
CP1235 | Louth - Woodland 220 kV Uprate | Meath | Meath
CP1236 | Timoney 110 kV Station (Erkina Solar Farm) | N/A | Not In TID
CP1236 | Timoney 110 kV Station (Erkina Solar Farm) | Offaly | Not In TID
CP1236 | Timoney 110 kV Station (Erkina Solar Farm) | Tipperary | Not In TID
CP1237 | Ferry View 110 kV Station (Knockranny Wind Farm) | Galway | Galway
CP1237 | Ferry View 110 kV Station (Knockranny Wind Farm) | N/A | N/A
CP1238 | Arklow 220 kV Station Redevelopment | Dublin | Dublin
CP1238 | Arklow 220 kV Station Redevelopment | Wexford | Wexford
CP1238 | Arklow 220 kV Station Redevelopment | Wicklow | Wicklow
CP1240 | Coumaclovane Solar Extension | Kerry | Kerry
CP1241 | Belcamp BSP Transfer | Dublin | Dublin
CP1242 | Great Island 220-110 kV transformer upgrades | Wexford | Wexford
CP1244 | North Arklow Solar Plus Storage | Wicklow | Wicklow
CP1245 | Castletreasure 110 kV Station (Ballinrea Solar Park) | Cork | Cork
CP1246 | Coomnaclohy 110 kV Station (Knocknamork Wind and Solar Park) | Cork | Cork
CP1247 | New Ballyvouskill 220-110 kV Transformer | Cork | Cork
CP1249 | Porterstown Battery 60MW Phase 2 | Kildare | Kildare
CP1250 | Sprecher and Schuh Circuit Breaker replacement | Cork | Cork
CP1250 | Sprecher and Schuh Circuit Breaker replacement | Kerry | Kerry
CP1250 | Sprecher and Schuh Circuit Breaker replacement | Kildare | Kildare
CP1250 | Sprecher and Schuh Circuit Breaker replacement | Waterford | Waterford
CP1251 | North Wall Life Extension Project | Dublin | Dublin
CP1255 | T-3 P483 Castlelost FlexGen | Kildare | Kildare
CP1255 | T-3 P483 Castlelost FlexGen | Offaly | Offaly
CP1256 | T-3 P481 Greener Ideas Profile Park | Dublin | Dublin
CP1257 | T-3 P485 Kilshane Power Station | Dublin | Dublin
CP1259 | Cuilleen 110kV Station (Greener Ideas) | N/A | N/A
CP1259 | Cuilleen 110kV Station (Greener Ideas) | Roscommon | Roscommon
CP1260 | Dennistown 110 kV Station (Tracystown Solar) | Wexford | Wexford
CP1263 | Rappareehill 110 kV Station (Derryadd Wind Farm) | Longford | Longford
CP1263 | Rappareehill 110 kV Station (Derryadd Wind Farm) | N/A | N/A
CP1264 | Rhode ESS (DSO) | Offaly | Offaly
CP1265 | Corkagh 110kV Station Phase 2 (Microsoft) | Dublin | Dublin
CP1266 | Ballyragget 110kV - DSO Parksgrove SF | Kilkenny | Kilkenny
CP1267 | Arklow 220kV - DSO Ballymanus WF | Wicklow | Wicklow
CP1268 | Dunfirth 110kV - DSO Dysart PV | Kildare | Kildare
CP1269 | The Dell Solar Lodgewood 220kV Crory Station | Wexford | Wexford
CP1273 | Dublin Central Bulk Supply Point 220kV Substation | Dublin | Dublin
CP1275 | Cashla-Galway 110 kV cct 2 Uprating | Galway | Galway
CP1276 | Cashla-Galway 110 kV cct 3 Uprating | Galway | Galway
CP1277 | Intel 110kV line diversion | Kildare | Not In TID
CP1277 | Intel 110kV line diversion | Meath | Not In TID
CP1280 | Ballyragget Future Proofed Cable | Kilkenny | Kilkenny
CP1281 | Batter Lane DSO Station | Dublin | Dublin
CP1282 | Clogher-Drumkeen 110 kV Line Alteration | Donegal | Donegal
CP1283 | Belcamp Cables Masterplan | Dublin | Dublin
CP1284 | Walterstown 110kV Station DSO | Kildare | Kildare
CP1285 | Barnahely - Raffeen No 2 110 kV Line | Cork | Cork
CP1286 | Tonroe 110kV Station DSO | Roscommon | Not In TID
CP1287 | Inchicore Number 2 220kV CAR Cable Diversion | Dublin | Not In TID
CP1291 | Carlow 110 kV Station Busbar Thermal Capacity Need | Carlow | Carlow
CP1294 | Temporary Emergency Generation Shannonbridge Phase 2 | Offaly | Not In TID
CP1296 | Rinawade 110 kV GIS Station (Liffey Park) | Kildare | Kildare
CP1296 | Rinawade 110 kV GIS Station (Liffey Park) | Meath | Meath
CP1297 | Glansillagh 220kV Station S | Kerry | Kerry
CP1300 | Climate Change Adaptation Measures | Cork | Cork
CP1300 | Climate Change Adaptation Measures | Kerry | Kerry
CP1300 | Climate Change Adaptation Measures | Offaly | Offaly
CP1300 | Climate Change Adaptation Measures | Roscommon | Roscommon
CP1300 | Climate Change Adaptation Measures | Waterford | Waterford
CP1301 | Dundalk Louth 110 kV Line Uprate | Louth | Louth
CP1302 | Killonan Shannonbridge 220 kV Line Refurbishment | Limerick | Limerick
CP1302 | Killonan Shannonbridge 220 kV Line Refurbishment | Offaly | Offaly
CP1304 | Strategic Spares for OHL, Stations and Cables | Kerry | Not In TID
CP1304 | Strategic Spares for OHL, Stations and Cables | Louth | Not In TID
CP1304 | Strategic Spares for OHL, Stations and Cables | Roscommon | Not In TID
CP1304 | Strategic Spares for OHL, Stations and Cables | Tipperary | Not In TID
CP1310 | Agannygal-Ennis Line Refurbishment | Clare | Clare
CP1310 | Agannygal-Ennis Line Refurbishment | Galway | Galway
CP1311 | Athlone - Lanesboro 110 kV line uprate | Longford | Longford
CP1311 | Athlone - Lanesboro 110 kV line uprate | Roscommon | Roscommon
CP1312 | Athy - Carlow 110 kV circuit 1 | Carlow | Carlow
CP1312 | Athy - Carlow 110 kV circuit 1 | Kildare | Kildare
CP1312 | Athy - Carlow 110 kV circuit 1 | Laois | Laois
CP1314 | Baroda - Monread 110 kV circuit 1 (DLR) | Kildare | Kildare
CP1315 | Baroda - Newbridge 110 kV circuit 1 (DLR) | Kildare | Kildare
CP1316 | Replacement of substation Back-Up supply equipment – North-East Region | Carlow | Carlow
CP1316 | Replacement of substation Back-Up supply equipment – North-East Region | Cavan | Cavan
CP1316 | Replacement of substation Back-Up supply equipment – North-East Region | Clare | Clare
CP1316 | Replacement of substation Back-Up supply equipment – North-East Region | Cork | Cork
CP1316 | Replacement of substation Back-Up supply equipment – North-East Region | Dublin | Dublin
CP1316 | Replacement of substation Back-Up supply equipment – North-East Region | Galway | Galway
CP1316 | Replacement of substation Back-Up supply equipment – North-East Region | Kildare | Kildare
CP1316 | Replacement of substation Back-Up supply equipment – North-East Region | Meath | Meath
CP1316 | Replacement of substation Back-Up supply equipment – North-East Region | Offaly | Offaly
CP1316 | Replacement of substation Back-Up supply equipment – North-East Region | Roscommon | Roscommon
CP1316 | Replacement of substation Back-Up supply equipment – North-East Region | Waterford | Waterford
CP1316 | Replacement of substation Back-Up supply equipment – North-East Region | Wicklow | Wicklow
CP1318 | Binbane - Clogher - Cathaleens Fall - 110 kV Clogher tie in | Donegal | Donegal
CP1319 | Blake Maynooth Newbridge Uprate | Kildare | Kildare
CP1320 | Barrymore Cahir Knockraha 110kV Line Uprate | Cork | Cork
CP1320 | Barrymore Cahir Knockraha 110kV Line Uprate | Tipperary | Tipperary
CP1321 | Cashla - Dalton 110 kV circuit 1 (DLR) | Galway | Not In TID
CP1321 | Cashla - Dalton 110 kV circuit 1 (DLR) | Mayo | Not In TID
CP1322 | Cathaleens Fall - Coraclassy 110 kV circuit 1 (DLR) | Cavan | Cavan
CP1322 | Cathaleens Fall - Coraclassy 110 kV circuit 1 (DLR) | Donegal | Donegal
CP1325 | Blundelstown Mullingar 110 kV Line Uprate | Meath | Meath
CP1325 | Blundelstown Mullingar 110 kV Line Uprate | Westmeath | Westmeath
CP1327 | Drumkeen - Clogher 110 kV circuit 1 | Donegal | Donegal
CP1331 | Rosspile 110kV Station (Rosspile Storage Facility) | Wexford | Wexford
CP1332 | Reask Solar Farm (ECP 2-2-12) | N/A | N/A
CP1334 | Newbarn 110 kV Station (Fieldstown Solar Farm) | Dublin | Dublin
CP1335 | Garballagh 110kV Station (Garballagh 2 Solar Farm) | Meath | Meath
CP1338 | Effernoge 110kV Station (Tomsallagh Solar) | Wexford | Wexford
CP1341 | Cloon 110 kV_Barnacurragh Solar Park | Galway | Galway
CP1342 | Drumcamill 110 kV Station (Monvallet Hybrid Solar and Battery Farm) | Louth | Louth
CP1344 | Timahoe North Phase 2 Solar Farm (ECP 2-2-23) | Kildare | Kildare
CP1345 | Golagh 110kV Station (Barnesmore WF Repower) | Donegal | Donegal
CP1346 | Meath Hill 110 kV Station (Ardagh South Energy Storage) | Meath | Meath
CP1347 | Dunbrody 110 kV Station (Kilmannock Battery Storage Facility Phase 2) | Wexford | Wexford
CP1351 | Ballynadrideen 110 kV Station (Ballyroe Solar) | Cork | Cork
CP1352 | Gortatleva 110 kV Station (Ballymoneen Solar Park) | Galway | Galway
CP1353 | Bendinstown 110kV Station (Garreenleen Solar) | Carlow | Carlow
CP1354 | Coolshamroge 110 kV Station (Manusmore Solar Park) | Clare | Clare
CP1355 | Corbetstown 110 kV Station (Garr Solar and Storage) | Offaly | Offaly
CP1356 | Gortawee 110 kV Station (Mucklagh Battery Storage Facility) | Cavan | Cavan
CP1357 | Philipstown 110 kV Station (Kilcush solar farm) | Laois | Laois
CP1357 | Philipstown 110 kV Station (Kilcush solar farm) | Offaly | Offaly
CP1358 | Thornsberry 110 kV Station (Ballycosney 150 MW BESS) | Offaly | Offaly
CP1359 | Lenalea 110 kV station (Drumnahough Wind Farm) | Donegal | Donegal
CP1360 | Coolcor 110KV (Coolavacoose Solar Farm) | Kildare | Kildare
CP1360 | Coolcor 110KV (Coolavacoose Solar Farm) | N/A | N/A
CP1360 | Coolcor 110KV (Coolavacoose Solar Farm) | Offaly | Offaly
CP1361 | Booltaigh 110KV Station (Carncreagh Energy Storage) | Clare | Clare
CP1362 | Bishopswood 110 kV Station (Blue Pine Solar) | N/A | N/A
CP1363 | Curraghdoo 110 kV Station (Clonymeath Solar Farm) | Meath | Meath
CP1363 | Curraghdoo 110 kV Station (Clonymeath Solar Farm) | N/A | N/A
CP1363 | Curraghdoo 110 kV Station (Clonymeath Solar Farm) | Westmeath | Westmeath
CP1364 | Moanalow 110 kV Station (Grangeford Solar PV) | Carlow | Carlow
CP1364 | Moanalow 110 kV Station (Grangeford Solar PV) | N/A | N/A
CP1365 | Mihanboy 110 kV station (Taduff Solar Park) | Roscommon | Roscommon
CP1366 | Lysaghtstown 110 kV Station (Lysaghtstown Solar Farm Phase 2) | Cork | Cork
CP1367 | Midleton 110kV Station (Carrigogna BESS) | Cork | Cork
CP1368 | Crosspatrick 110 kV Station (Mullafarry BESS) | Mayo | Mayo
CP1369 | Colehill 110 kV Station (Ballyteige Solar Park) | N/A | N/A
CP1369 | Colehill 110 kV Station (Ballyteige Solar Park) | Offaly | Offaly
CP1372 | Drombeg 110 kV Station (Drombeg Solar Park Phase 2) | Kerry | Kerry
CP1374 | Ballyvouskill 110 kV (ABO Wind Ireland) | Cork | Cork
CP1374 | Ballyvouskill 110 kV (ABO Wind Ireland) | N/A | N/A
CP1375 | Boggeragh 110 kV Station (Carragraigue Solar Extension) | Cork | Cork
CP1376 | Pollagh 110kV Station (Shronowen Wind Farm) | Kerry | Not In TID
CP1377 | Rathcoon 110 kV Station (Gorman Solar Farm) | Meath | Meath
CP1377 | Rathcoon 110 kV Station (Gorman Solar Farm) | N/A | N/A
CP1378 | Cooleeny 110 kV Station (Killoran Solar PV Farm) | N/A | N/A
CP1378 | Cooleeny 110 kV Station (Killoran Solar PV Farm) | Tipperary | Tipperary
CP1379 | Cauteen 110 kV Station (Barnaleen Solar Farm) | Tipperary | Tipperary
CP1380 | Craddanstown 110kV station (Bracklyn WF) | Meath | Meath
CP1380 | Craddanstown 110kV station (Bracklyn WF) | N/A | N/A
CP1380 | Craddanstown 110kV station (Bracklyn WF) | Westmeath | Westmeath
CP1384 | Kilteel - Maynooth 110 kV | Kildare | Kildare
CP1389 | Limerick - Rathkeale Line Uprate | Limerick | Limerick
CP1390 | Maynooth - Rinawade 110V line uprate | Kildare | Kildare
CP1391 | Derryiron-Timahoe-Maynooth 110 kV Line Uprate | Kildare | Not In TID
CP1391 | Derryiron-Timahoe-Maynooth 110 kV Line Uprate | Offaly | Not In TID
CP1394 | Offshore Phase 1 - Codling Wind Park | Dublin | Dublin
CP1396 | Arklow Bank Wind Park Phase 2 (Offshore) | Wicklow | Wicklow
CP1397 | Bremore 220 kV Station (North Irish Sea Array) | Dublin | Dublin
CP1397 | Bremore 220 kV Station (North Irish Sea Array) | N/A | N/A
CP1398 | Offshore Phase 1 - Dublin Array | Dublin | Dublin
CP1402 | Platin 110kV Station Refurbishment | Meath | Meath
CP1403 | Rinawade – Dunfirth Tee – Kinnegad 110 kV Circuit Thermal Capacity | Kildare | Kildare
CP1412 | Knockraha 220 kV Transformer Replacement (T2102) | Cork | Cork
CP1413 | Clonee 220 kV Station (Clonee -Bracetown Flexible Demand Arrangement) | Meath | Not In TID
CP1418 | Oaklands 110 kV Station Crag Wicklow | N/A | N/A
CP1418 | Oaklands 110 kV Station Crag Wicklow | Wexford | Wexford
CP1418 | Oaklands 110 kV Station Crag Wicklow | Wicklow | Wicklow
CP1420 | North Wicklow Reinforcement | Dublin | Dublin
CP1420 | North Wicklow Reinforcement | Wicklow | Wicklow
CP1421 | Crakenstown 220-110 kV Station | Louth | Louth
CP1421 | Crakenstown 220-110 kV Station | Meath | Meath
CP1422 | Cashla - Prospect 220kV | Clare | Clare
CP1422 | Cashla - Prospect 220kV | Galway | Galway
CP1423 | Cashla - Tynagh 220kV | Galway | Galway
CP1424 | Farrnawana 220 kV (SSE Tarbert OCGT) | Kerry | Kerry
CP1425 | Southwall 220kV GIS (ESB Poolbeg) (ESB G&T) | Dublin | Dublin
CP1426 | Rathcobican 400kV SS - Derrygreenagh 220kV (Cushaling Power Ltd) | Galway | Galway
CP1426 | Rathcobican 400kV SS - Derrygreenagh 220kV (Cushaling Power Ltd) | Meath | Meath
CP1427 | Bellewstown 110kV Station – SSE Platin | Meath | Meath
CP1428 | Cashla Dalton 110kV Thermal Capacity Increase | Galway | Galway
CP1428 | Cashla Dalton 110kV Thermal Capacity Increase | Mayo | Mayo
CP1429 | Castlebar Dalton 110kV Thermal Capacity Increase | Mayo | Mayo
CP1430 | Lanesboro 110 kV Station (Ballycore Solar) | Longford | Longford
CP1434 | Drumline 110 kV Station Busbar Thermal Uprate | Clare | Clare
CP1435 | Drumline Ennis 110kV circuit DLR and related works | Clare | Clare
CP1436 | Ardnacrusha Ennis 110kV circuit DLR and related works | Clare | Clare
CP1442 | Fosterstown 110 kV Station Connection DSO | Meath | Meath
CP1442 | Fosterstown 110 kV Station Connection DSO | Westmeath | Westmeath
CP1447 | Letterkenny - Golagh Tee 110 kV circuit thermal capacity needs | Donegal | Donegal
CP1448 | Carrickmines Phase Shift Transformer (PST) Replacement | Dublin | Dublin
CP1449 | Midleton 110kV Transformer Uprate and Station works DSO | Cork | Cork
CP1450 | Ardnacrusha Drumline 110kV thermal capacity needs | Clare | Clare
CP1452 | Poolbeg OCGT (ESB G&T) | Dublin | Dublin
CP1453 | Blake 110 kV Station Redevelopment | Kildare | Kildare
CP1454 | Gorman - Maynooth 220 kV Circuit Capacity Needs | Kildare | Kildare
CP1454 | Gorman - Maynooth 220 kV Circuit Capacity Needs | Meath | Meath
CP1456 | Clutterland 110kV Station Phase 2&3 (Amazon Web Services) | Dublin | Dublin
CP1459 | East Kildare 110 kV Station | Dublin | Dublin
CP1459 | East Kildare 110 kV Station | Kildare | Kildare
CP1460 | Balruntagh 110kV Station (Balrathboyne Solar) | Cavan | Not In TID
CP1460 | Balruntagh 110kV Station (Balrathboyne Solar) | Meath | Not In TID
CP1460 | Balruntagh 110kV Station (Balrathboyne Solar) | N/A | Not In TID
CP1464 | Tullabeg 110 kV Station (Tullabeg Solar Phase 2 | Wexford | Wexford
CP1465 | Lisdrum 110kV Station Busbar Thermal Capacity Need | Monaghan | Monaghan
CP1466 | Meath Hill 110kV Station Busbar Thermal Capacity Need | Meath | Meath
CP1467 | Caherhurly 110 kV Station (Carrownagowan Wind Farm) | Clare | Clare
CP1468 | Kilvinoge 110 kV Station (Castlebanny Wind Farm) | Kilkenny | Kilkenny
CP1468 | Kilvinoge 110 kV Station (Castlebanny Wind Farm) | Wexford | Wexford
CP1470 | Galway - Salthill Thermal Capacity Need | Galway | Galway
CP1471 | Lisdrum Louth 110 kV DLR project | Louth | Louth
CP1471 | Lisdrum Louth 110 kV DLR project | Monaghan | Monaghan
CP1473 | Louth - Meath Hill 110 kV DLR | Louth | Louth
CP1473 | Louth - Meath Hill 110 kV DLR | Meath | Meath
CP1475 | East Galway 110 kV Station (DSO Connection) | Galway | Galway
CP1476 | Rathlockstown Solar | Meath | Not In TID
CP1477 | Maynooth - Shannonbridge 220 kV Circuit Capacity Needs | Kildare | Kildare
CP1477 | Maynooth - Shannonbridge 220 kV Circuit Capacity Needs | Offaly | Offaly
CP1478 | Donegal TEN-T Road Network Advanced Ducting | N/A | N/A
CP1479 | Ratrussan - Shankill 110 kV Dynamic Line Rating | Cavan | Cavan
CP1480 | Cruiserath 220kV Station Phase 3 (Amazon Web Services) | Dublin | Dublin
CP1484 | Srananagh 220 kV Station (Quarry Lane LCIS) | Sligo | Sligo
CP1485 | Wexford Synchronous Condenser | Wexford | Wexford
CP1486 | Athlone - Shannonbridge 110 kV Fibre Wrapping | Offaly | Offaly
CP1486 | Athlone - Shannonbridge 110 kV Fibre Wrapping | Roscommon | Roscommon
CP1487 | Corduff and Connected Stations Protection Upgrade | Dublin | Dublin
CP1488 | Tralee and Connected Stations Protection Upgrade | Kerry | Kerry
CP1490 | Barrymore 110 kV busbar and new 110 38 transformer | Cork | Cork
CP1491 | Barrymore Land Acquisition | Cork | Cork
CP1492 | Donore 110 kV Station (DSO Connection) | Louth | Louth
CP1492 | Donore 110 kV Station (DSO Connection) | Meath | Meath
CP1492 | Donore 110 kV Station (DSO Connection) | N/A | N/A
CP1495 | Lodgewood-Great Island line uprate | Wexford | Wexford
CP1496 | Cashla - Shannonbridge 110 kV | Galway | Galway
CP1496 | Cashla - Shannonbridge 110 kV | Offaly | Offaly
CP1497 | Derrycarney - Portlaoise 110 kV Fibre Wrapping | Laois | Not In TID
CP1497 | Derrycarney - Portlaoise 110 kV Fibre Wrapping | Offaly | Not In TID
CP1498 | Derryiron - Kinnegad 110 kV Fibre Wrapping | Meath | Meath
CP1498 | Derryiron - Kinnegad 110 kV Fibre Wrapping | Offaly | Offaly
CP1499 | Charleville - Glenlara 110 kV Fibre Wrapping | Cork | Cork
CP1500 | Butlerstown 110kV Station (Traffo Uprate) (DSO) | Waterford | Waterford
CP1506 | Signalling Cables for Grid Meter Installation | Kerry | Not In TID
CP1506 | Signalling Cables for Grid Meter Installation | Offaly | Not In TID
CP1509 | Cathaleen’s Fall Srananagh 110 kV Circuit No 2 DLR | Donegal | Donegal
CP1509 | Cathaleen’s Fall Srananagh 110 kV Circuit No 2 DLR | Sligo | Sligo
CP1510 | Peamount 110 kV Station (Bulmer RICE) | Dublin | Dublin
CP1511 | Castleview 110kV Station DSO (Eastmont DC) | Cork | Cork
CP1512 | Cathaleens Fall 110kV DSO (Derrykillew Wind Farm) | Donegal | Donegal
CP1513 | Ricetown 110kV Station (Mill Farm Solar) | Meath | Meath
CP1513 | Ricetown 110kV Station (Mill Farm Solar) | N/A | N/A
CP1514 | Deenes - Drybridge 110 kV Circuit DLR | Louth | Louth
CP1514 | Deenes - Drybridge 110 kV Circuit DLR | Meath | Meath
CP1515 | Kellymount 110 kV Station (White Hill Wind) | Carlow | Carlow
CP1515 | Kellymount 110 kV Station (White Hill Wind) | Kilkenny | Kilkenny
CP1515 | Kellymount 110 kV Station (White Hill Wind) | N/A | N/A
CP1516 | Kilmacogue 110 kV Station (Ballyvalode Solar) | Limerick | Limerick
CP1516 | Kilmacogue 110 kV Station (Ballyvalode Solar) | N/A | N/A
CP1516 | Kilmacogue 110 kV Station (Ballyvalode Solar) | Tipperary | Tipperary
CP1517 | Kildinan 110 kV Station (Coom Green Energy Park) | Cork | Cork
CP1517 | Kildinan 110 kV Station (Coom Green Energy Park) | N/A | N/A
CP1517 | Kildinan 110 kV Station (Coom Green Energy Park) | Tipperary | Tipperary
CP1518 | Glenart 220 kV Station (Pollahoney Autoproducer) | Wexford | Wexford
CP1518 | Glenart 220 kV Station (Pollahoney Autoproducer) | Wicklow | Wicklow
CP1519 | Crane - Wexford 110 kV (DLR) | Wexford | Wexford
CP1520 | Great Island - Waterford 110 kV (DLR) | Waterford | Waterford
CP1520 | Great Island - Waterford 110 kV (DLR) | Wexford | Wexford
CP1521 | Cappaneary 110kV Station(Dernacart Wind Farm) | Laois | Laois
CP1521 | Cappaneary 110kV Station(Dernacart Wind Farm) | N/A | N/A
CP1522 | New Lodgewood 220-110 kV Transformer | Wexford | Wexford
CP1523 | Binbane 110 kV Station Busbar Thermal Capacity Need | Donegal | Donegal
CP1526 | Baltrasna Corduff 110 kV Circuit DLR Project | Dublin | Dublin
CP1526 | Baltrasna Corduff 110 kV Circuit DLR Project | Meath | Meath
CP1527 | Buffy 110 kV (Ardderoo WF Phase 2) | Galway | Galway
CP1528 | Lislaughtin 110k V Station (Dromlivuan Solar Farm) | Kerry | Kerry
CP1528 | Lislaughtin 110k V Station (Dromlivuan Solar Farm) | N/A | N/A
CP1529 | Oldbridge Phase 2&3 | Louth | Louth
CP1529 | Oldbridge Phase 2&3 | Meath | Meath
CP1530 | Ballycummin 110kV Station DSO | Limerick | Limerick
CP1530 | Ballycummin 110kV Station DSO | N/A | N/A
CP1531 | Kilbarry Knockraha 110 kV Circuit 2 Uprate (Kilbarry Mallow) | Cork | Cork
CP1532 | NM20 Cork to Limerick - Advance Ducting | Dublin | Dublin
CP1532 | NM20 Cork to Limerick - Advance Ducting | Limerick | Limerick
CP1533 | Raheenmeel 110 kV Station (Kilcormac Solar) | Laois | Laois
CP1533 | Raheenmeel 110 kV Station (Kilcormac Solar) | N/A | N/A
CP1533 | Raheenmeel 110 kV Station (Kilcormac Solar) | Offaly | Offaly
CP1534 | Ennis 110 kV Station (Transformer Uprate) (DSO) | Clare | Clare
CP1535 | Trien 110 kV Station (Transformer Uprate) (DSO) | Kerry | Kerry
CP1536 | Clogher 220kV Station | Donegal | Donegal
CP1537 | Letterkenny Station Redevelopment - Land Purchase | Donegal | Not In TID
CP1538 | Prospect Land Acquisition | Clare | Clare
CP1538 | Prospect Land Acquisition | Kerry | Kerry
CP1539 | Mullingar 110 kV Station (Transformer Uprate) (DSO) | Westmeath | Westmeath
CP1540 | 220 kV Composite pole – Pilot Energised Project | N/A | N/A
CP1541 | Cam & Feamore 110 kV Stations (Seven Hills Wind Farm) | Longford | Longford
CP1541 | Cam & Feamore 110 kV Stations (Seven Hills Wind Farm) | N/A | N/A
CP1541 | Cam & Feamore 110 kV Stations (Seven Hills Wind Farm) | Roscommon | Roscommon
CP1542 | Cauteen 110kV Station (DSO Gortdrum SF) | Tipperary | Tipperary
CP1543 | Srananagh 220kV Transformer and Bay Extension | Sligo | Sligo
CP1544 | Belcamp 110 kV busbar extension and additional transformer capacity | Dublin | Dublin
CP1545 | Maynooth Cable Routing Land Acquisition | Kildare | Kildare
CP1546 | Lodgewood 220kV Station (Tincurry Solar Farm) | Wexford | Wexford
CP1547 | Newbridge East- 110 kV Cable Uprate | Kildare | Kildare
CP1548 | Replacement of substation Back-Up supply equipment – Central Region | Carlow | Carlow
CP1548 | Replacement of substation Back-Up supply equipment – Central Region | Offaly | Offaly
CP1549 | Replacement of substation Back-Up supply equipment – North-West Region | Galway | Galway
CP1549 | Replacement of substation Back-Up supply equipment – North-West Region | Roscommon | Roscommon
CP1550 | Replacement of substation Back-Up supply equipment – South Central Region | Dublin | Dublin
CP1550 | Replacement of substation Back-Up supply equipment – South Central Region | Waterford | Waterford
CP1551 | Replacement of substation Back-Up supply equipment – South-East Region | Dublin | Dublin
CP1551 | Replacement of substation Back-Up supply equipment – South-East Region | Wicklow | Wicklow
CP1552 | Replacement of substation Back-Up supply equipment – South-West Region | Cork | Cork
CP1556 | Arklow Ballybeg Carrickmines Refurbishment | Dublin | Dublin
CP1556 | Arklow Ballybeg Carrickmines Refurbishment | Wicklow | Wicklow
CP1557 | Cow Cross 110kV Station Refurbishment | Cork | Cork
CP1559 | Ballymac Phase 2 (Ballymac Solar DAC) (ECP 2-4-07) | Waterford | Waterford
CP1560 | Kilnap 110kV Station - 2 New DSO Transformer Bays | Cork | Cork
CP1562 | N3 Virginia Bypass Road Advance Ducting | N/A | N/A
CP1563 | N4 Mullingar to Longford Advance Ducting | Westmeath | Westmeath
CP1564 | Affane 110kV Station (Modelligo Solar) | Waterford | Waterford
CP1565 | Kilteel 110 kV Station (Transformer Uprate) (DSO) Project Setup | Kildare | Kildare
CP1566 | Propoge 110 kV (Lyrenacarriga Windfarm and BESS) (Curns Energy Ltd) | Cork | Cork
CP1566 | Propoge 110 kV (Lyrenacarriga Windfarm and BESS) (Curns Energy Ltd) | N/A | N/A
CP1566 | Propoge 110 kV (Lyrenacarriga Windfarm and BESS) (Curns Energy Ltd) | Waterford | Waterford
CP1567 | Knockdonagh 110kV (Ballyglass Solar Farm) | Clare | Clare
CP1567 | Knockdonagh 110kV (Ballyglass Solar Farm) | N/A | N/A
CP1568 | Arva-Carrick On Shannon 110 kV Line Alteration | Cavan | Cavan
CP1568 | Arva-Carrick On Shannon 110 kV Line Alteration | Roscommon | Roscommon
CP1569 | Arodstown 220kV (Culmullin Solar) | Kildare | Kildare
CP1569 | Arodstown 220kV (Culmullin Solar) | Meath | Meath
CP1569 | Arodstown 220kV (Culmullin Solar) | N/A | N/A
CP1572 | Cregcarragh 110 kV Station (Ballymoneen Phase 2) | Galway | Galway
CP1573 | Kilbarry 110kV Station Redevelopment | Cork | Cork
CP1574 | Kellis- Kilkenny 110kV Circuit Refurbishment | Carlow | Carlow
CP1574 | Kellis- Kilkenny 110kV Circuit Refurbishment | Kilkenny | Kilkenny
CP1575 | Rathkeale 110kV Station Redevelopment | Limerick | Limerick
CP1576 | N25 Midleton to Youghal - Advance Ducting | Cork | Cork
CP1577 | N6 Galway City Ring Road ​​- Advance Ducting | N/A | N/A
CP1578 | N11-N25 Oilgate to Rosslare Harbour​-Advance Ducting | N/A | N/A
CP1579 | N4 Active Travel Collooney to Castlebaldwin - Advance Ducting | N/A | N/A
CP1580 | N24 Waterford to Cahir ​​​ - Advance Ducting | Tipperary | Tipperary
CP1580 | N24 Waterford to Cahir ​​​ - Advance Ducting | Waterford | Waterford
CP1581 | N72 Mallow Relief Road - Advance Ducting | N/A | N/A
CP1582 | N3 M50 to Clonee - Advance Ducting | N/A | N/A
CP1583 | N24 Cahir to Limerick Junction​​ - Advance Ducting Project | N/A | N/A
CP1584 | Carlow Southern Relief Road - Advance Ducting | N/A | N/A
DSO-02 | Belmayne 110 kV-38 kVMV | N/A | N/A
DSO-03 | New South East Carlow 110-20 kV | N/A | N/A
DSO-06 | Bishopstown (Wilton) 110 kV 38 kV MV | N/A | N/A
DSO-10 |  | Cork | Not In TID
DSO-12 | Blundlestown 110 38 kV | Meath | Meath
DSO-13 | New 110 kV 20 kV Killinick Rosslare Dennistown | N/A | N/A
DSO-15 | 4th transformer in Carrickmines 220kV BSP (Detail ) | Dublin | Dublin
DSO-16 | New 110 kV -MV Station Fermoy | N/A | N/A
DSO-17 | New North-East Cashel 110 kV MV station (Kill Hill) | N/A | N/A
DSO-18 | New Monaghan (Cavan) 110 kV MV Station | N/A | N/A
DSO-19 |  | Kildare | Not In TID
DSO-21 |  | Waterford | Not In TID
DSO-22 | Drybridge G1 | Louth | Louth
DSO-23 | Griffinrath G1 | Kildare | Kildare
DSO-24 | Galway G4 | Galway | Galway
DSO-25 | Drumline G2 | Clare | Clare
DSO-26 |  | N/A | Not In TID
DSO-27 |  | Kildare | Not In TID
DSO-28 |  | Kildare | Not In TID
DSO-29 | Charleville G3 | Cork | Cork
DSO-30 |  | Kerry | Kerry
DSO-32 | New West Portlaoise 110 kV Station | N/A | N/A
DSO-33 | New East Athlone 110 kV 38 kV MV | N/A | N/A
DSO-34 |  | N/A | Not In TID
DSO-35 | New 110 kV MV station at Birdhill | N/A | N/A
DSO-36 | Castleview 110 kV MV (Little Island) | Cork | Cork
DSO-37 | New Navan 110 38 kV or 110 kV MV station | N/A | N/A
DSO-38 | Rinwade 110 38MV Station | Kildare | Kildare
DSO-40 | Bandon G2 | Cork | Cork
DSO-43 | Courtlough (M1) 110 kV 38 kV MV | N/A | N/A
DSO-44 | Macroom G5 | Cork | Not In TID
DSO-45 | Dalton G3 | Mayo | Mayo
DSO-51 | Bellacorrick uprate to 2x63 MVA | Mayo | Mayo
DSO-52 | Limerick G1 | Limerick | Limerick
DSO-56 |  | Meath | Not In TID
DSO-57 |  | Dublin | Dublin
DSO-58 | Blake G3 | Kildare | Kildare
DSO-59 |  | Dublin | Not In TID
DSO-81 |  | Wexford | Not In TID
DSO-82 | Barrymore (Farran Solar) | Cork | Cork
DSO-83 | Macroom Berrings Solar ECP 2 2 | Cork | Cork
DSO-97 | Poolbeg Ringsend third transformer | Dublin | Dublin
DSO-98 | Monread | Kildare | Kildare
EAM01 | Station Refurbishments Replacement | N/A | Not In TID
EAM02 | Transformer Replacements x6 | N/A | Not In TID
EAM03 | Replacement of existing SVC’s x2 | N/A | Not In TID
EAM04 | Replacement of Mobile Cap Banks x4 | N/A | Not In TID
EAM07 | Battery_Generator Replacements | N/A | Not In TID
EAM10 | Bay Control Unit Replacements | N/A | Not In TID
EAM11 | Asbestos Surveys Replacement | N/A | Not In TID
EAM12 | Dedicated Transmission Asset Storage Facility Study | N/A | Not In TID
EAM13 | Replacement Ungreased_Core Greased Conductors | N/A | Not In TID
EAM14 | Replacement of 110 kV Cut Poles | N/A | Not In TID
EAM15 | Tower Painting | N/A | Not In TID
EAM17 | FCI Insulator Replacements | N/A | Not In TID
EAM18 | Sediver Insulator Replacements | N/A | Not In TID
EAM19 | Pilot of Cathodic Protection for OHL | N/A | Not In TID
EAM20 | Artificial Intelligence Research for OHL inspections | N/A | Not In TID
EAM21 | Cables OLCM, PD Monitoring & DAS investigation | N/A | Not In TID
EAM22 | Improvements with reporting & data magement | N/A | Not In TID
EAM23 | Production of Corrosion Map for Ireland | N/A | Not In TID
EAM24 | Climate Change Adaptation Studies | N/A | Not In TID
EAM25 | Review design and specs for Link Box | N/A | Not In TID
EAM26 | Link Box Replacements x 25 | N/A | Not In TID
ECP-2.4-07 | Coolcarrigan Solar P2 | N/A | N/A
ECP-2.4-09 | Knockroe Wind Farm | N/A | Not In TID
ECP-2.4-14 | Culmullin Solar Farm | N/A | N/A
ECP-2.4-15 | TULLYNAMOYLE WIND FARM 6 | N/A | Not In TID
ECP-2.4-18 | Fieldstown Extension No2 | N/A | N/A
ECP-2.4-19 | Drummin Solar | N/A | Not In TID
ECP-2.4-20 |  | N/A | Not In TID
ECP-2.4-21 | Ballyroe Solar Extension | N/A | N/A
ECP-2.4-23 | Barnaleen Solar Phase 2 | N/A | N/A
ECP-2.4-25 | Reask Phase 2 | N/A | N/A
ECP-2.4-26 | Ballynahina Solar Farm | N/A | Not In TID
ECP-2.4-27 | Golden Forth Solar Park | N/A | Not In TID
ECP-2.4-29 | Tawnaghmore DC Power | Mayo | Mayo
ECP-2.4-30 | CherryOrchard Solar Park | N/A | Not In TID
ECP-2.4-31 | Ballycunneen PV | N/A | Not In TID
ECP-2.4-32 | Main Solar | N/A | Not In TID
ECP-2.4-33 | Mullagharoy Solar Farm | N/A | Not In TID
ECP-2.4-34 | Cloondara Solar Park | N/A | Not In TID
ECP-2.4-36 | Lissane West Solar Farm | N/A | Not In TID
ECP-2.4-37 | Tarbert BESS | Kerry | Kerry
ECP-2.4-38 |  | N/A | Not In TID
ECP-2.4-39 | Silloge Navan Battery Storage Facility | N/A | Not In TID
ECP-2.4-41 | RICHMOND BATTERY STORAGE FACILITY | N/A | Not In TID
ECP-2.4-43 |  | Roscommon | Not In TID
ECP-2.4-46 | Ballykenny Solar | N/A | Not In TID
ECP-2.4-47 | Tooraskeheen Solar & Storage | N/A | Not In TID
ECP-2.4-48 | Spion Kop Windfarm | N/A | Not In TID
ECP-2.4-49 | Aghada Power Station | Cork | Cork
ECP-2.4-51 | JOHNSTOWN SOLAR PARK | N/A | Not In TID
ECP-2.4-52 |  | Wexford | Not In TID
ECP-2.4-53 | Lismeen Solar Farm | N/A | Not In TID
ECP-2.4-54 | Templemichael Solar Plus Storage Facility | N/A | N/A
ECP-2.4-55 | Clondardis Solar | N/A | N/A
ECP-2.4-56 | Sandford Energy Solar Farm | N/A | Not In TID
ECP-2.4-57 | Darthogue Solar Farm | N/A | N/A
ECP-2.4-58 | Cronalaght 3 Wind Farm | N/A | Not In TID
ECP-2.4-59 | Mount Cronalaght Windfarm Repowering | N/A | Not In TID
ECP-2.4-60 | Leam Windfarm | N/A | Not In TID
ECP-2.4-61 | Ballysumaghan BESS & SC | N/A | N/A
TPSPGrp01 | Macetown 110 kV Busbar Uprate | Dublin | Not In TID
TPSPGrp02 | Castleview 110 kV Busbar Uprate | Cork | Not In TID
TPSPGrp04 | Dundalk 110 kV Busbar Uprate | Louth | Not In TID
TPSPGrp05 | Midleton 110 kV Busbar Uprate | Cork | Not In TID
TPSPGrp06 | Mullagharlin 110 kV Busbar Uprate | Louth | Not In TID
TPSPGrp07 | DSO Demand Driven Projects | N/A | Not In TID
TPSPGrp08 | Renewable_Critical Infrastructure_System Reinforcement_System Reinforcement Driven | N/A | Not In TID
TPSPGrp09 | SOPCM Driven Project A | N/A | Not In TID
TPSPGrp10 | SOPCM Driven Project B | N/A | Not In TID
TPSPGrp11 | TES Driven 2026 | N/A | Not In TID
TPSPGrp12 | TES Driven 2028 | N/A | Not In TID
TPSPGrp13 | Dublin 400 kV Project | N/A | Not In TID
TPSPGrp14 | Cork 220_400 kV Project | N/A | Not In TID
TPSPGrp15 | Maynooth - Shannonbridge - Killon - Knockraha 400 kV Corridor Project | Cork | Not In TID
TPSPGrp15 | Maynooth - Shannonbridge - Killon - Knockraha 400 kV Corridor Project | Kildare | Not In TID
TPSPGrp15 | Maynooth - Shannonbridge - Killon - Knockraha 400 kV Corridor Project | Limerick | Not In TID
TPSPGrp15 | Maynooth - Shannonbridge - Killon - Knockraha 400 kV Corridor Project | Offaly | Not In TID
TPSPGrp16 | Offshore Supporting Infrastructure Project | N/A | Not In TID
TPSPGrp17 | Short Circuit Mitigation Project 2026 | N/A | Not In TID
TPSPGrp18 | Short Circuit Mitigation Project 2028 | N/A | Not In TID
TPSPGrp22 | Wexford DSO demand | Wexford | Not In TID
TPSPGrp23 | NISA cable and remote end station | N/A | Not In TID