## Wks 39 - 40
Report covers outages commencing/returning/spanning the period: 26/09/2022 - 09/10/2022
Outages commencing/returning in Week 39
OUTAGE ID | PLANT |  | Week 39 | [6 empty] | Week 40
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10
TO-22-BDA-T102-01 | BARODA T102 | bar: Week 39 Mo 26 to Week 39 Tu 27
TO-22-DLT-110SA1-03 | DALTON 110SA1 | bar: Week 39 Mo 26; Week 39 We 28 to Week 39 Th 29
TO-22-DLT-110SA2-02 | DALTON 110SA2 | bar: Week 39 Mo 26; Week 39 We 28 to Week 39 Th 29
TO-22-DLT-T142-02 | DALTON T142 | bar: Week 39 Mo 26; Week 39 We 28 to Week 39 Th 29
TO-22-ARV-COS-1-01 | ARVA CARRICK ON SHANNON | bar: Week 39 Mo 26; Week 39 We 28 to Week 39 Fr 30
TO-22-ATY-110SA1-01 | ATHY 110SA1 | bar: Week 39 Mo 26; Week 39 We 28 to Week 39 Fr 30
TO-22-ATY-110SA2-02 | ATHY 110SA2 | bar: Week 39 Mo 26; Week 39 We 28 to Week 39 Fr 30
TO-22-ATY-T101-02 | ATHY T101 | bar: Week 39 Mo 26; Week 39 We 28 to Week 39 Fr 30
TO-22-AUG-SK-4-01 | AUGHINISH SEALROCK 4 | bar: Week 39 Mo 26; Week 39 We 28 to Week 39 Fr 30
TO-22-CLW-110SA1-06 | CARLOW 110SA1 | bar: Week 39 Mo 26; Week 39 We 28 to Week 39 Fr 30
TO-22-CLW-110SA2-04 | CARLOW 110SA2 | bar: Week 39 Mo 26; Week 39 We 28 to Week 39 Fr 30
TO-22-CLW-KLS-1-06 | CARLOW KELLIS 1 | bar: Week 39 Mo 26; Week 39 We 28 to Week 39 Fr 30
TO-22-CLW-T141-04 | CARLOW T141 | bar: Week 39 Mo 26; Week 39 We 28 to Week 39 Fr 30
TO-22-220 kV A1 @ CKM GIS-03 | CARRICKMINES GIS 220 kV A1 | bar: Week 39 Mo 26 to Week 39 Fr 30
TO-22-220 kV A3 @ CKM GIS-04 | CARRICKMINES GIS 220 kV A3 | bar: Week 39 Mo 26 to Week 39 Fr 30
TO-22-CSH-DLT-1-02 | CASHLA DALTON | bar: Week 39 Mo 26; Week 39 We 28 to Week 39 Fr 30
TO-22-110 kV A2 @ CLG-03 | CLOGHRAN 110 kV A2 | bar: Week 39 Mo 26; Week 39 We 28 to Week 39 Fr 30
TO-22-110 kV B2 @ CLG-04 | CLOGHRAN 110 kV B2 | bar: Week 39 Mo 26; Week 39 We 28 to Week 39 Fr 30
TO-22-CDY-GRV-1-02 | CORDERRY GARVAGH | bar: Week 39 Mo 26; Week 39 We 28 to Week 39 Fr 30
TO-22-110 kV A1 @ CDU-03 | CORDUFF 110 kV A1 | bar: Week 39 Mo 26; Week 39 We 28 to Week 39 Fr 30
TO-22-110 kV B1 @ CDU-03 | CORDUFF 110 kV B1 | bar: Week 39 Mo 26; Week 39 We 28 to Week 39 Fr 30
TO-22-GRV-110K1-02 | GARVAGH 110K1 | bar: Week 39 Mo 26; Week 39 We 28 to Week 39 Fr 30
TO-22-GRV-T121-03 | GARVAGH T121 | bar: Week 39 Mo 26; Week 39 We 28 to Week 39 Fr 30
TO-22-GRV-T141-02 | GARVAGH T141 | bar: Week 39 Mo 26; Week 39 We 28 to Week 39 Fr 30
TO-22-400 kV A3 @ MP GIS-01 | MONEYPOINT GIS 400 kV A3 | bar: Week 39 Mo 26; Week 39 We 28 to Week 39 Fr 30
TO-22-400 kV B3 @ MP GIS-01 | MONEYPOINT GIS 400 kV B3 | bar: Week 39 Mo 26; Week 39 We 28 to Week 39 Fr 30
TO-22-110 kV B2 @ RYB GIS-01 | RYEBROOK GIS 110 kV B2 | bar: Week 39 Mo 26; Week 39 We 28 to Week 39 Fr 30
TO-22-110 kV B4 @ RYB GIS-01 | RYEBROOK GIS 110 kV B4 | bar: Week 39 Mo 26; Week 39 We 28 to Week 39 Fr 30
TO-22-RYB GIS-110SB2-4CB-02 | RYEBROOK GIS 110SB2-4CB | bar: Week 39 Mo 26; Week 39 We 28 to Week 39 Fr 30
TO-22-SK-T104-01 | SEALROCK T104 | bar: Week 39 Mo 26; Week 39 We 28 to Week 39 Fr 30
TO-22-COW-RAF-1-01 | COW CROSS RAFFEEN | bar: Week 39 Mo 26; Week 39 We 28 to Week 40 Tu 4
TO-22-KNY-UGL-1-01 | KNOCKRANNY UGGOOL | bar: Week 39 Mo 26 to Week 40 Fr 7
TO-22-UGL-110SA1-2CB-01 | UGGOOL 110SA1-2CB | bar: Week 39 Mo 26 to Week 40 Fr 7
TO-22-UGL-T131-01 | UGGOOL T131 | bar: Week 39 Mo 26 to Week 40 Fr 7
TO-22-UGL-T132-01 | UGGOOL T132 | bar: Week 39 Mo 26 to Week 40 Fr 7
TO-22-UGL-T134-01 | UGGOOL T134 | bar: Week 39 Mo 26 to Week 40 Fr 7
TO-22-WOO-T4204-01 | WOODLAND T4204 | bar: Week 39 Mo 26 to Week 40 Fr 7
TO-22-CKM GIS-220SA1-3CB-01 | CARRICKMINES GIS 220SA1-3CB | bar: Week 39 Mo 26 to Week 40 Sa 8
TO-22-CDU-RYB GIS-1-01 | CORDUFF RYEBROOK GIS | bar: Week 39 Mo 26; Week 39 We 28 to Week 40 Mo 10
TO-22-MP GIS-T4003-01 | MONEYPOINT GIS T4003 | bar: Week 39 Mo 26; Week 39 We 28 to Week 40 Mo 10
TO-22-CLE-T224-01 | CLONEE T224 | bar: Su 25 to Week 39 Mo 26
TO-22-ISH-T2001-01 | IRISHTOWN T2001 | bar: Su 25 to Week 39 Mo 26
TO-22-SOR-T124-01 | SORNE HILL T124
TO-22-COS-110SA1-2CB-01 | CARRICK ON SHANNON 110SA1-2CB | bar: Week 39 We 28
TO-22-COS-FLA-1-04 | CARRICK ON SHANNON FLAGFORD 1 | bar: Week 39 We 28
TO-22-COS-T141-01 | CARRICK ON SHANNON T141 | bar: Week 39 We 28
TO-22-MID-T102-01 | MIDLETON T102 | bar: Week 39 Tu 27 to Week 39 We 28
TO-22-BRT-T224-01 | BRACETOWN T224 | bar: Week 39 We 28 to Week 39 Th 29
TO-22-110 kV A1 @ KPG-02 | KILPADDOGE 110 kV A1 | bar: Week 39 We 28 to Week 39 Fr 30
TO-22-110 kV A3 @ KPG-01 | KILPADDOGE 110 kV A3 | bar: Week 39 We 28 to Week 39 Fr 30
TO-22-KPG-110SA1-3CB-01 | KILPADDOGE 110SA1-3CB | bar: Week 39 We 28 to Week 39 Fr 30
TO-22-220 kV A3 @ KPG-01 | KILPADDOGE 220 kV A3 | bar: Week 39 We 28 to Week 39 Fr 30
TO-22-220 kV B3 @ KPG-01 | KILPADDOGE 220 kV B3 | bar: Week 39 We 28 to Week 39 Fr 30
TO-22-KPG-220K3-01 | KILPADDOGE 220K3 | bar: Week 39 We 28 to Week 39 Fr 30
TO-22-CBT-MAY-1-06 | CASTLEBAGOT MAYNOOTH 1 | bar: Su 25 to Week 39 Mo 26
TO-22-IKE,T-THU-1-01 | IKERRIN tee THURLES | bar: Su 25 to Week 39 Mo 26
TO-22-LSN-110SA1-2-01 | LISHEEN 110SA1-2 | bar: Su 25 to Week 39 Mo 26
TO-22-LSN-110SA2-4-01 | LISHEEN 110SA2-4 | bar: Su 25 to Week 39 Mo 26
TO-22-LSN-T122-01 | LISHEEN T122 | bar: Su 25 to Week 39 Mo 26
TO-22-LSN-T142-01 | LISHEEN T142 | bar: Su 25 to Week 39 Mo 26
TO-22-LSN-THU-1-01 | LISHEEN THURLES | bar: Su 25 to Week 39 Mo 26
Report covers outages commencing/returning/spanning the period: 26/09/2022 - 09/10/2022
Outages commencing/returning in Week 39
OUTAGE ID | PLANT | Week 39 Mo 26: Week 39; Week 40 Mo 3: Week 40
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10
TO-22-THU-110SA1-2CB-01 | THURLES 110SA1-2CB | bar: Su 25 to Week 39 Tu 27
TO-22-THU-CAP2-01 | THURLES CAP2 | bar: Su 25 to Week 39 Tu 27
TO-22-THU-T142-01 | THURLES T142 | bar: Su 25 to Week 39 Tu 27
TO-22-220 kV A1/A2 @ ISH-01 | IRISHTOWN 220 kV A1/A2 | bar: Week 39 We 28
TO-22-220 kV B1/B2 @ ISH-01 | IRISHTOWN 220 kV B1/B2 | bar: Week 39 We 28
TO-22-110 kV A4 @ CBT-02 | CASTLEBAGOT 110 kV A4 | bar: Week 39 We 28 to Week 39 Fr 30
TO-22-110 kV B4 @ CBT-01 | CASTLEBAGOT 110 kV B4 | bar: Week 39 We 28 to Week 39 Fr 30
TO-22-CBT-110K4-02 | CASTLEBAGOT 110K4 | bar: Week 39 We 28 to Week 39 Fr 30
TO-22-CBT-110SA2-4CB-01 | CASTLEBAGOT 110SA2-4CB | bar: Week 39 We 28 to Week 39 Fr 30
TO-22-CBT-110SB2-4CB-01 | CASTLEBAGOT 110SB2-4CB | bar: Week 39 We 28 to Week 39 Fr 30
TO-22-CBT-T2104-01 | CASTLEBAGOT T2104 | bar: Week 39 We 28 to Week 39 Fr 30
TO-22-LET-TIV-1-03 | LETTERKENNY TIEVEBRACK | bar: Week 39 We 28 to Week 39 Fr 30
TO-22-BYH-BVK-1-01 | BALLYNAHULLA BALLYVOUSKILL | bar: Su 25 to Week 39 We 28
TO-22-110 kV B1 @ AA GIS-02 | ARDNACRUSHA GIS 110 kV B1 | bar: Week 39 Th 29
TO-22-110 kV B2 @ AA GIS-01 | ARDNACRUSHA GIS 110 kV B2 | bar: Week 39 Th 29
TO-22-AA GIS-110K2-03 | ARDNACRUSHA GIS 110K2 | bar: Week 39 Th 29
TO-22-AA GIS-110SB1-2CB-02 | ARDNACRUSHA GIS 110SB1-2CB | bar: Week 39 Th 29
TO-22-AA GIS-ENN-1-02 | ARDNACRUSHA GIS ENNIS | bar: Week 39 Th 29
TO-22-SNU-110SB1-2CB-02 | SNUGBOROUGH 110SB1-2CB | bar: Week 39 Th 29
TO-22-220 kV B1 @ TH-01 | TURLOUGH HILL 220 kV B1 | bar: Week 39 Th 29
TO-22-TH-T2001/2-02 | TURLOUGH HILL T2001/2 | bar: Week 39 Th 29
TO-22-LIS-SKL-1-04 | LISDRUM SHANKILL | bar: Week 39 Th 29 to Week 40 Fr 7
TO-22-CRO-IA-1-03 | COOLROE INNISCARRA | bar: Week 39 Fr 30
TO-22-IA-MAC-1-02 | INNISCARRA MACROOM | bar: Week 39 Fr 30
TO-22-IA-T101-02 | INNISCARRA T101 | bar: Week 39 Fr 30
TO-22-CLG-CDU-1-02 | CLOGHRAN CORDUFF | bar: Su 25 to Week 39 Fr 30
TO-22-CKG-KUD-1-01 | CORKAGH KILMAHUD | bar: Su 25 to Week 39 Fr 30
TO-22-CAH-DOO-1-03 | CAHIR DOON | bar: Week 39 Sa 1 to Week 39 Su 2
TO-22-KBY-KRA-1-05 | KILBARRY KNOCKRAHA 1 | bar: Week 39 Sa 1 to Week 39 Su 2
Outages commencing/returning in Week 40
OUTAGE ID | PLANT | Week 39 Mo 26: Week 39; Week 40 Mo 3: Week 40
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10
TO-22-CLN-110SA1-01 | CLOON 110SA1 | bar: Week 40 Mo 3 to Week 40 We 5
TO-22-CLN-110SA2-01 | CLOON 110SA2 | bar: Week 40 Mo 3 to Week 40 We 5
TO-22-CLN-LA-1-01 | CLOON LANESBORO | bar: Week 40 Mo 3 to Week 40 We 5
TO-22-CLN-T142-01 | CLOON T142 | bar: Week 40 Mo 3 to Week 40 We 5
TO-22-220 kV A1 @ CLE-01 | CLONEE 220 kV A1 | bar: Week 40 Mo 3 to Week 40 Th 6
TO-22-220 kV A2 @ CLE-02 | CLONEE 220 kV A2 | bar: Week 40 Mo 3 to Week 40 Th 6
TO-22-CLE-220K1-01 | CLONEE 220K1 | bar: Week 40 Mo 3 to Week 40 Th 6
TO-22-CLE-220K2-02 | CLONEE 220K2 | bar: Week 40 Mo 3 to Week 40 Th 6
TO-22-CLE-220SA1-2CB-01 | CLONEE 220SA1-2CB | bar: Week 40 Mo 3 to Week 40 Th 6
TO-22-CLE-WOO-1-04 | CLONEE WOODLAND | bar: Week 40 Mo 3 to Week 40 Th 6
TO-22-BVK-GRO-1-02 | BALLYVOUSKILL GARROW | bar: Week 40 Mo 3 to Week 40 Fr 7
TO-22-BAL-T122-01 | BALTRASNA T122 | bar: Week 40 Mo 3 to Week 40 Fr 7
TO-22-CD-KBY-1-07 | CARRIGADROHID KILBARRY | bar: Week 40 Mo 3 to Week 40 Fr 7
TO-22-CF-SRA-2-02 | CATHALEENS FALL SRANANAGH 2 | bar: Week 40 Mo 3 to Week 40 Fr 7
TO-22-110 kV A4 @ CDU-02 | CORDUFF 110 kV A4 | bar: Week 40 Mo 3 to Week 40 Fr 7
TO-22-110 kV B4 @ CDU-02 | CORDUFF 110 kV B4 | bar: Week 40 Mo 3 to Week 40 Fr 7
TO-22-220 kV A1 @ KPG-01 | KILPADDOGE 220 kV A1 | bar: Week 40 Mo 3 to Week 40 Fr 7
TO-22-220 kV B1 @ KPG-01 | KILPADDOGE 220 kV B1 | bar: Week 40 Mo 3 to Week 40 Fr 7
TO-22-RAF-T2101-01 | RAFFEEN T2101 | bar: Week 40 Mo 3 to Week 40 Fr 7
TO-22-BAL-CDU-1-02 | BALTRASNA CORDUFF | bar: Week 40 Mo 3 to Week 40 Mo 10
TO-22-CHA-GLE-1-02 | CHARLEVILLE GLENLARA | bar: Week 40 Mo 3 to Week 40 Mo 10
TO-22-INC-PB-1-04 | INCHICORE POOLBEG 1 | bar: Week 40 Mo 3 to Week 40 Mo 10
TO-22-INC-PB-1-06 | bar: Week 40 Mo 3 to Week 40 Mo 10
TO-22-KHL-THU-1-03 | KILL HILL THURLES | bar: Week 40 Mo 3 to Week 40 Mo 10
TO-22-PB-TF3-02 | POOLBEG TF3 | bar: Week 40 Mo 3 to Week 40 Mo 10
TO-22-PRO-TB-1-03 | PROSPECT TARBERT | bar: Week 40 Mo 3 to Week 40 Mo 10
TO-22-DER-T1/T2-01 | DERRYIRON RHODE T1/T2 | bar: Su 25 to Week 40 Mo 3
Report covers outages commencing/returning/spanning the period: 26/09/2022 - 09/10/2022
Outages commencing/returning in Week 40
OUTAGE ID | PLANT | Week 39 Mo 26: Week 39; Week 40 Mo 3: Week 40
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10
TO-22-ARV-110K1-2-02 | ARVA 110K1-2 | bar: Week 40 Tu 4 to Week 40 We 5
TO-22-INC-T2102-01 | INCHICORE T2102 | bar: Week 40 Tu 4 to Week 40 We 5
TO-22-KLN-NEN-1-03 | KILLONAN NENAGH | bar: Week 40 Tu 4 to Week 40 We 5
TO-22-NEN-T141-02 | NENAGH T141 | bar: Week 40 Tu 4 to Week 40 We 5
TO-22-BLC-110K3-01 | BELCAMP 110K3 | bar: Week 40 Tu 4 to Week 40 Th 6
TO-22-220 kV A1 @ TB-03 | TARBERT 220 kV A1 | bar: Week 40 Tu 4 to Week 40 Mo 10
TO-22-220 kV B1 @ TB-03 | TARBERT 220 kV B1 | bar: Week 40 Tu 4 to Week 40 Mo 10
TO-22-110 kV B1 @ CF-03 | CATHALEENS FALL 110 kV B1 | bar: Week 40 We 5
TO-22-CL-T101-05 | CLIFF T101 | bar: Week 40 We 5
TO-22-CL-T102-05 | CLIFF T102 | bar: Week 40 We 5
TO-22-CKM GIS-T2104-01 | CARRICKMINES GIS T2104 | bar: Week 40 We 5 to Week 40 Th 6
TO-22-BUT-KTN-1-02 | BUTLERSTOWN KILLOTERAN | bar: Week 40 We 5 to Week 40 Fr 7
TO-22-KTN-110SA1-01 | KILLOTERAN 110SA1 | bar: Week 40 We 5 to Week 40 Fr 7
TO-22-KTN-110SA2-01 | KILLOTERAN 110SA2 | bar: Week 40 We 5 to Week 40 Fr 7
TO-22-KTN-T101-01 | KILLOTERAN T101 | bar: Week 40 We 5 to Week 40 Fr 7
TO-22-DEY-110K2-02 | DERRYCARNEY 110K2 | bar: Su 25 to Week 40 We 5
TO-22-INC-T2106-01 | INCHICORE T2106 | bar: Week 40 Th 6 to Week 40 Fr 7
TO-22-SLI-110SA1-2CB-01 | SLIGO 110SA1-2CB | bar: Week 40 Fr 7
TO-22-SLI-CAP1-01 | SLIGO CAP1 | bar: Week 40 Fr 7
TO-22-SLI-SRA-1-02 | SLIGO SRANANAGH 1 | bar: Week 40 Fr 7
TO-22-KRA-RAF-1-01 | KNOCKRAHA RAFFEEN | bar: Week 40 Fr 7 to Week 40 Mo 10
TO-22-DSN-T4201-02 | DUNSTOWN T4201 | bar: Su 25 to Week 40 Fr 7
TO-22-SLI-T141-01 | SLIGO T141 | bar: Su 25 to Week 40 Fr 7
Outages spanning Weeks 39-40
OUTAGE ID | PLANT | Week 39 Mo 26: Week 39; Week 40 Mo 3: Week 40
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10
TO-22-ATY-CLW-1-01 | ATHY CARLOW
TO-22-COR-GWE-1-03 | CORRACLASSY GORTAWEE
TO-22-CUL-T2101-01 | CULLENAGH T2101
TO-22-110 kV A2 @ DEY-02 | DERRYCARNEY 110 kV A2
TO-22-110 kV B2 @ DEY-03 | DERRYCARNEY 110 kV B2
TO-22-DSN-400K1-2-01 | DUNSTOWN 400K1-2
TO-22-FIN GIS-110K6-02 | FINGLAS GIS 110K6
TO-22-110 kV B1/B2 @ FLA-02 | FLAGFORD 110 kV B1/B2
TO-22-FLA-110K1-2-01 | FLAGFORD 110K1-2
TO-22-GAL-SAL-1-01 | GALWAY SALTHILL
TO-22-GGO-220K1-2-02 | GLANAGOW 220K1-2
TO-22-GOR-PLA-1-01 | GORMAN PLATIN
TO-22-INC-220K1-2-03 | INCHICORE 220K1-2
TO-22-KNR-TRI-2-01 | KNOCKANURE TRIEN 2
TO-22-LET-M/CAP1-01 | LETTERKENNY M/CAP1
TO-22-220 kV B1 @ MAY-04 | MAYNOOTH 220 kV B1
TO-22-MAY-TH-1-01 | MAYNOOTH TURLOUGH HILL
TO-22-MAY-WOO-1-15 | MAYNOOTH WOODLAND
TO-22-MUL-CAP2-03 | MULLINGAR CAP2
TO-22-PB-R2002-01 | POOLBEG R2002
TO-22-TB-T101-02 | TARBERT T101
TO-22-TB-T2004-01 | TARBERT T2004
TO-22-TIP-T141-02 | TIPPERARY T141
TO-22-TRI-110SA1-2CB-02 | TRIEN 110SA1-2CB
TO-22-TRI-T142-01 | TRIEN T142