## Wks 43 - 44
Report covers outages commencing/returning/spanning the period: 24/10/2022 - 06/11/2022
Outages commencing/returning in Week 43
OUTAGE ID | PLANT |  | Week 43 | [6 empty] | Week 44
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7
TO-22-CUS-T103/5-02 | CUSHALING T103/5 | bar: Week 43 Mo 24
TO-22-220 kV A2 @ CLE-06 | CLONEE 220 kV A2 | bar: Week 43 Mo 24 to Week 43 Th 27
TO-22-220 kV B2 @ CLE-05 | CLONEE 220 kV B2 | bar: Week 43 Mo 24 to Week 43 Th 27
TO-22-CLE-220K2-03 | CLONEE 220K2 | bar: Week 43 Mo 24 to Week 43 Th 27
TO-22-110 kV A1 @ GI-01 | GREAT ISLAND 110 kV A1 | bar: Week 43 Mo 24 to Week 43 Th 27
TO-22-110 kV B1 @ GI-03 | GREAT ISLAND 110 kV B1 | bar: Week 43 Mo 24 to Week 43 Th 27
TO-22-BVK-CLA-1-01 | BALLYVOUSKILL CLASHAVOON | bar: Week 43 Mo 24 to Week 43 Fr 28
TO-22-BK-110SA1-02 | BELLACORICK 110SA1 | bar: Week 43 Mo 24 to Week 43 Fr 28
TO-22-BK-110SA2-03 | BELLACORICK 110SA2 | bar: Week 43 Mo 24 to Week 43 Fr 28
TO-22-BK-MOY-1-05 | BELLACORICK MOY | bar: Week 43 Mo 24 to Week 43 Fr 28
TO-22-BK-T141-02 | BELLACORICK T141 | bar: Week 43 Mo 24 to Week 43 Fr 28
TO-22-CUL-WAT-1-01 | CULLENAGH WATERFORD | bar: Week 43 Mo 24 to Week 43 Fr 28
TO-22-GI-WAT-1-02 | GREAT ISLAND WATERFORD 1 | bar: Week 43 Mo 24 to Week 43 Fr 28
TO-22-110 kV A1 @ KLN-01 | KILLONAN 110 kV A1 | bar: Week 43 Mo 24 to Week 43 Fr 28
TO-22-110 kV B1 @ KLN-01 | KILLONAN 110 kV B1 | bar: Week 43 Mo 24 to Week 43 Fr 28
TO-22-KLN-LIM-1-01 | KILLONAN LIMERICK 1 | bar: Week 43 Mo 24 to Week 43 Fr 28
TO-22-220 kV A1 @ KPG-03 | KILPADDOGE 220 kV A1 | bar: Week 43 Mo 24 to Week 43 Fr 28
TO-22-220 kV B1 @ KPG-04 | KILPADDOGE 220 kV B1 | bar: Week 43 Mo 24 to Week 43 Fr 28
TO-22-KPG-MP GIS-1-02 | KILPADDOGE MONEYPOINT GIS 1 | bar: Week 43 Mo 24 to Week 43 Fr 28
TO-22-400 kV B1 @ MP GIS-02 | MONEYPOINT GIS 400 kV B1 | bar: Week 43 Mo 24 to Week 43 Fr 28
TO-22-400 kV B3 @ MP GIS-02 | MONEYPOINT GIS 400 kV B3 | bar: Week 43 Mo 24 to Week 43 Fr 28
TO-22-MP GIS-400SB1-3CB-01 | MONEYPOINT GIS 400SB1-3CB | bar: Week 43 Mo 24 to Week 43 Fr 28
TO-22-110 kV A3 @ RYB GIS-01 | RYEBROOK GIS 110 kV A3 | bar: Week 43 Mo 24 to Week 43 Fr 28
TO-22-110 kV B3 @ RYB GIS-01 | RYEBROOK GIS 110 kV B3 | bar: Week 43 Mo 24 to Week 43 Fr 28
TO-22-RYB GIS-110K3-01 | RYEBROOK GIS 110K3 | bar: Week 43 Mo 24 to Week 43 Fr 28
TO-22-WAT-110SA1-03 | WATERFORD 110SA1 | bar: Week 43 Mo 24 to Week 43 Fr 28
TO-22-WAT-110SA2-02 | WATERFORD 110SA2 | bar: Week 43 Mo 24 to Week 43 Fr 28
TO-22-WAT-T142-01 | WATERFORD T142 | bar: Week 43 Mo 24 to Week 43 Fr 28
TO-22-GAL-KNY-1-01 | GALWAY KNOCKRANNY
TO-22-GAL-T141-01 | GALWAY T141
TO-22-CLG-FIN GIS-1-02 | CLOGHRAN FINGLAS GIS | bar: Su 23 to Week 43 Mo 24
TO-22-COL-FIN GIS-1-07 | COLLEGE PARK FINGLAS GIS | bar: Su 23 to Week 43 Mo 24
TO-22-110 kV A5 @ FIN GIS-04 | FINGLAS GIS 110 kV A5 | bar: Su 23 to Week 43 Mo 24
TO-22-110 kV B5 @ FIN GIS-03 | FINGLAS GIS 110 kV B5 | bar: Su 23 to Week 43 Mo 24
TO-22-110 kV A1 @ KPG-02 | KILPADDOGE 110 kV A1 | bar: Week 43 Tu 25 to Week 43 Fr 28
TO-22-110 kV A3 @ KPG-01 | KILPADDOGE 110 kV A3 | bar: Week 43 Tu 25 to Week 43 Fr 28
TO-22-KPG-110SA1-3CB-01 | KILPADDOGE 110SA1-3CB | bar: Week 43 Tu 25 to Week 43 Fr 28
TO-22-110 kV B1 @ KNR-02 | KNOCKANURE 110 kV B1 | bar: Week 43 Tu 25 to Week 43 Fr 28
TO-22-110 kV B2 @ KNR-01 | KNOCKANURE 110 kV B2 | bar: Week 43 Tu 25 to Week 43 Fr 28
TO-22-KNR-110SB1-2CB-02 | KNOCKANURE 110SB1-2CB | bar: Week 43 Tu 25 to Week 43 Fr 28
TO-22-SLI-CAP1-02 | SLIGO CAP1 | bar: Week 43 Tu 25 to Week 43 Fr 28
TO-22-ARV-SKL-2-02 | ARVA SHANKILL 2 | bar: Su 23 to Week 43 Tu 25
TO-22-220 kV A1 @ KYT-03 | KELLYSTOWN 220 kV A1 | bar: Su 23 to Week 43 Tu 25
TO-22-220 kV B1 @ KYT-04 | KELLYSTOWN 220 kV B1 | bar: Su 23 to Week 43 Tu 25
TO-22-KYT-220SA1-2CB-07 | KELLYSTOWN 220SA1-2CB | bar: Su 23 to Week 43 Tu 25
TO-22-KYT-220SA1-3CB-09 | KELLYSTOWN 220SA1-3CB | bar: Su 23 to Week 43 Tu 25
TO-22-KYT-220SB1-2CB-07 | KELLYSTOWN 220SB1-2CB | bar: Su 23 to Week 43 Tu 25
TO-22-KYT-220SB1-3CB-09 | KELLYSTOWN 220SB1-3CB | bar: Su 23 to Week 43 Tu 25
TO-22-CKG-T122-01 | CORKAGH T122 | bar: Week 43 We 26 to Week 44 Mo 7
TO-22-LOU-WOO-1-02 | LOUTH WOODLAND | bar: Su 23 to Week 43 We 26
TO-22-110 kV A1/A2 @ BYH-01 | BALLYNAHULLA 110 kV A1/A2 | bar: Week 43 Th 27
TO-22-110 kV B1/B2 @ BYH-01 | BALLYNAHULLA 110 kV B1/B2 | bar: Week 43 Th 27
TO-22-220 kV A1/A2 @ BYH-01 | BALLYNAHULLA 220 kV A1/A2 | bar: Week 43 Th 27
TO-22-220 kV B1/B2 @ BYH-01 | BALLYNAHULLA 220 kV B1/B2 | bar: Week 43 Th 27
TO-22-MP GIS-220K1-03 | MONEYPOINT GIS 220K1 | bar: Week 43 Th 27
TO-22-CLW-110SA1-01 | CARLOW 110SA1 | bar: Week 43 Fr 28
TO-22-CLW-110SA2-01 | CARLOW 110SA2 | bar: Week 43 Fr 28
TO-22-CLW-KLS-1-02 | CARLOW KELLIS 1 | bar: Week 43 Fr 28
TO-22-CLW-T141-01 | CARLOW T141 | bar: Week 43 Fr 28
TO-22-CTN-TIP-1-01 | CAUTEEN TIPPERARY | bar: Week 43 Fr 28
TO-22-TIP-110SA1-01 | TIPPERARY 110SA1 | bar: Week 43 Fr 28
Report covers outages commencing/returning/spanning the period: 24/10/2022 - 06/11/2022
Outages commencing/returning in Week 43
OUTAGE ID | PLANT | Week 43 Mo 24: Week 43; Week 44 Mo 31: Week 44
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7
TO-22-TIP-110SA2-01 | TIPPERARY 110SA2 | bar: Week 43 Fr 28
TO-22-ARI-T121-01 | ARIGNA T121 | bar: Su 23 to Week 43 Fr 28
TO-22-ARI,T-ARI-1-01 | ARIGNA tee ARIGNA | bar: Su 23 to Week 43 Fr 28
TO-22-ARI,T-COS-1-01 | ARIGNA tee CARRICK ON SHANNON | bar: Su 23 to Week 43 Fr 28
TO-22-ARI,T-CDY-1-02 | ARIGNA tee CORDERRY | bar: Su 23 to Week 43 Fr 28
TO-22-ATY-CLW-1-01 | ATHY CARLOW | bar: Su 23 to Week 43 Fr 28
TO-22-DSN-T4201-02 | DUNSTOWN T4201 | bar: Su 23 to Week 43 Fr 28
TO-22-KLN-KPG-1-01 | KILLONAN KILPADDOGE | bar: Su 23 to Week 43 Fr 28
TO-22-TIP-T141-02 | TIPPERARY T141 | bar: Su 23 to Week 43 Fr 28
TO-22-ARV-NAV-1-05 | ARVA NAVAN | bar: Week 43 Sa 29
TO-22-GOR-NAV-2-02 | GORMAN NAVAN 2 | bar: Week 43 Sa 29
TO-22-NAV-110SA1-2CB-03 | NAVAN 110SA1-2CB | bar: Week 43 Sa 29
TO-22-NAV-M/CAP1-03 | NAVAN M/CAP1 | bar: Week 43 Sa 29
TO-22-NAV-T141-02 | NAVAN T141 | bar: Su 23 to Week 43 Sa 29
Outages commencing/returning in Week 44
OUTAGE ID | PLANT | Week 43 Mo 24: Week 43; Week 44 Mo 31: Week 44
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7
TO-22-DRM-110SA1-01 | DRUMKEEN 110SA1 | bar: Week 44 Tu 1
TO-22-DRM-110SA2-01 | DRUMKEEN 110SA2 | bar: Week 44 Tu 1
TO-22-DRM-LET-1-05 | DRUMKEEN LETTERKENNY | bar: Week 44 Tu 1
TO-22-DRM-MEE-1-03 | DRUMKEEN MEENTYCAT | bar: Week 44 Tu 1
TO-22-MEE-T121-02 | MEENTYCAT T121 | bar: Week 44 Tu 1
TO-22-IKE-T141-04 | IKERRIN T141 | bar: Week 44 Tu 1 to Week 44 We 2
TO-22-IKE,T-IKE-1-04 | IKERRIN tee IKERRIN | bar: Week 44 Tu 1 to Week 44 We 2
TO-22-IKE,T-THU-1-07 | IKERRIN tee THURLES | bar: Week 44 Tu 1 to Week 44 We 2
TO-22-AUG-SK-3-02 | AUGHINISH SEALROCK 3 | bar: Week 44 Tu 1 to Week 44 Th 3
TO-22-SK-T103-02 | SEALROCK T103 | bar: Week 44 Tu 1 to Week 44 Th 3
TO-22-ARK-BOG-1-01 | ARKLOW BANOGE | bar: Week 44 Tu 1 to Week 44 Fr 4
TO-22-BOG-110SA1-02 | BANOGE 110SA1 | bar: Week 44 Tu 1 to Week 44 Fr 4
TO-22-BOG-110SA2-01 | BANOGE 110SA2 | bar: Week 44 Tu 1 to Week 44 Fr 4
TO-22-BOG-T122-01 | BANOGE T122 | bar: Week 44 Tu 1 to Week 44 Fr 4
TO-22-110 kV B2 @ FIN GIS-08 | FINGLAS GIS 110 kV B2 | bar: Week 44 Tu 1 to Week 44 Fr 4
TO-22-110 kV B4 @ FIN GIS-01 | FINGLAS GIS 110 kV B4 | bar: Week 44 Tu 1 to Week 44 Fr 4
TO-22-FIN GIS-110SB2-4CB-04 | FINGLAS GIS 110SB2-4CB | bar: Week 44 Tu 1 to Week 44 Fr 4
TO-22-110 kV B1 @ KPG-03 | KILPADDOGE 110 kV B1 | bar: Week 44 Tu 1 to Week 44 Fr 4
TO-22-110 kV B3 @ KPG-02 | KILPADDOGE 110 kV B3 | bar: Week 44 Tu 1 to Week 44 Fr 4
TO-22-KPG-110SB1-3CB-01 | KILPADDOGE 110SB1-3CB | bar: Week 44 Tu 1 to Week 44 Fr 4
TO-22-220 kV B1 @ KPG-05 | KILPADDOGE 220 kV B1 | bar: Week 44 Tu 1 to Week 44 Fr 4
TO-22-220 kV B3 @ KPG-02 | KILPADDOGE 220 kV B3 | bar: Week 44 Tu 1 to Week 44 Fr 4
TO-22-KPG-220SB1-3CB-01 | KILPADDOGE 220SB1-3CB | bar: Week 44 Tu 1 to Week 44 Fr 4
TO-22-DRY-LOU-1-03 | DRYBRIDGE LOUTH | bar: Week 44 Tu 1 to Week 44 Mo 7
TO-22-IKE,T-SH-1-05 | IKERRIN tee SHANNONBRIDGE | bar: Week 44 Tu 1 to Week 44 Mo 7
TO-22-NEW-PLS-1-01 | NEWBRIDGE PORTLAOISE | bar: Week 44 Tu 1 to Week 44 Mo 7
TO-22-220 kV A1/A2/A3/A4 @ CKM GIS-01 | CARRICKMINES GIS 220 kV A1/A2/A3/A4 | bar: Week 44 We 2
TO-22-220 kV B1/B2/B3/B4 @ CKM GIS-01 | CARRICKMINES GIS 220 kV B1/B2/B3/B4 | bar: Week 44 We 2
TO-22-CUN-GLR-1-01 | CUNGHILL GLENREE | bar: Week 44 We 2
TO-22-CBR-SVC-03 | CASTLEBAR SVC | bar: Week 44 We 2 to Week 44 Th 3
TO-22-220 kV A1/A2 @ BVK-02 | BALLYVOUSKILL 220 kV A1/A2 | bar: Week 44 We 2 to Week 44 Fr 4
TO-22-220 kV B1/B2 @ BVK-02 | BALLYVOUSKILL 220 kV B1/B2 | bar: Week 44 We 2 to Week 44 Fr 4
TO-22-CHA-MAL-1-01 | CHARLEVILLE MALLOW | bar: Week 44 We 2 to Week 44 Mo 7
TO-22-GLR-110SA1-2CB-01 | GLENREE 110SA1-2CB | bar: Week 44 Th 3
TO-22-220 kV B1 @ KYT-03 | KELLYSTOWN 220 kV B1 | bar: Week 44 Fr 4 to Week 44 Mo 7
TO-22-KYT-220SB1-2CB-03 | KELLYSTOWN 220SB1-2CB | bar: Week 44 Fr 4 to Week 44 Mo 7
TO-22-KYT-220SB1-3CB-04 | KELLYSTOWN 220SB1-3CB | bar: Week 44 Fr 4 to Week 44 Mo 7
TO-22-MP GIS-ST101-01 | MONEYPOINT GIS ST101 | bar: Week 44 Fr 4 to Week 44 Mo 7
TO-22-FIN GIS-T2101-01 | FINGLAS GIS T2101 | bar: Su 23 to Week 44 Fr 4
TO-22-DEY-110K2-03 | DERRYCARNEY 110K2 | bar: Week 44 Sa 5 to Week 44 Su 6
TO-22-DEY-PLS-1-01 | DERRYCARNEY PORTLAOISE | bar: Week 44 Sa 5 to Week 44 Su 6
TO-22-110 kV A2 @ DEY-02 | DERRYCARNEY 110 kV A2
Report covers outages commencing/returning/spanning the period: 24/10/2022 - 06/11/2022
Outages commencing/returning in Week 44
OUTAGE ID | PLANT | Week 43 Mo 24: Week 43; Week 44 Mo 31: Week 44
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7
TO-22-110 kV B2 @ DEY-03 | DERRYCARNEY 110 kV B2
TO-22-DEY-110K2-02 | DERRYCARNEY 110K2
TO-22-MP GIS-T4003-01 | MONEYPOINT GIS T4003
Outages spanning Weeks 43-44
OUTAGE ID | PLANT | Week 43 Mo 24: Week 43; Week 44 Mo 31: Week 44
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7
TO-22-110 kV A4 @ CDU-01 | CORDUFF 110 kV A4
TO-22-110 kV B4 @ CDU-01 | CORDUFF 110 kV B4
TO-22-CUL-220K1-2-04 | CULLENAGH 220K1-2
TO-22-FIN GIS-110K6-02 | FINGLAS GIS 110K6
TO-22-110 kV B1/B2 @ FLA-02 | FLAGFORD 110 kV B1/B2
TO-22-FLA-110K1-2-01 | FLAGFORD 110K1-2
TO-22-GGO-220K1-2-02 | GLANAGOW 220K1-2
TO-22-GOR-PLA-1-01 | GORMAN PLATIN
TO-22-INC-220K1-2-03 | INCHICORE 220K1-2
TO-22-KBY-MR-1-01 | KILBARRY MARINA 1
TO-22-KBY-MR-2-01 | KILBARRY MARINA 2
TO-22-KRA-110K1-2-03 | KNOCKRAHA 110K1-2
TO-22-LET-M/CAP1-01 | LETTERKENNY M/CAP1
TO-22-MAY-WOO-1-15 | MAYNOOTH WOODLAND
TO-22-MUL-CAP2-03 | MULLINGAR CAP2
TO-22-PB-R2002-01 | POOLBEG R2002
TO-22-RYB GIS-T131-01 | RYEBROOK GIS T131
TO-22-TB-T101-02 | TARBERT T101