## Wks 45 - 46
Report covers outages commencing/returning/spanning the period: 07/11/2022 - 20/11/2022
Outages commencing/returning in Week 45
OUTAGE ID | PLANT |  | Week 45 | [6 empty] | Week 46
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21
TO-22-KER-110SA1-02 | KNOCKEARAGH 110SA1 | bar: Week 45 Mo 7 to Week 45 We 9
TO-22-KER-110SA2-01 | KNOCKEARAGH 110SA2 | bar: Week 45 Mo 7 to Week 45 We 9
TO-22-KER-T142-01 | KNOCKEARAGH T142 | bar: Week 45 Mo 7 to Week 45 We 9
TO-22-OUG,T-KER-1-03 | OUGHTRAGH tee KNOCKEARAGH | bar: Week 45 Mo 7 to Week 45 We 9
TO-22-110 kV A2 @ ARV-01 | ARVA 110 kV A2 | bar: Week 45 Mo 7 to Week 45 Fr 11
TO-22-110 kV B2 @ ARV-01 | ARVA 110 kV B2 | bar: Week 45 Mo 7 to Week 45 Fr 11
TO-22-ARV-GWE-1-02 | ARVA GORTAWEE | bar: Week 45 Mo 7 to Week 45 Fr 11
TO-22-CSH-GAL-2-04 | CASHLA GALWAY 2 | bar: Week 45 Mo 7 to Week 45 Fr 11
TO-22-CBT-T2102-01 | CASTLEBAGOT T2102 | bar: Week 45 Mo 7 to Week 45 Fr 11
TO-22-110 kV A2 @ GI-02 | GREAT ISLAND 110 kV A2 | bar: Week 45 Mo 7 to Week 45 Fr 11
TO-22-110 kV B2 @ GI-01 | GREAT ISLAND 110 kV B2 | bar: Week 45 Mo 7 to Week 45 Fr 11
TO-22-GI-WAT-2-02 | GREAT ISLAND WATERFORD 2 | bar: Week 45 Mo 7 to Week 45 Fr 11
TO-22-110 kV A1 @ RYB GIS-01 | RYEBROOK GIS 110 kV A1 | bar: Week 45 Mo 7 to Week 45 Fr 11
TO-22-110 kV A2 @ RYB GIS-01 | RYEBROOK GIS 110 kV A2 | bar: Week 45 Mo 7 to Week 45 Fr 11
TO-22-RYB GIS-110SA1-2CB-01 | RYEBROOK GIS 110SA1-2CB | bar: Week 45 Mo 7 to Week 45 Fr 11
TO-22-CF-CLO-1-02 | CATHALEENS FALL CLOGHER 1 | bar: Week 45 Mo 7 to Week 46 Fr 18
TO-22-CF-CLO-2-01 | CATHALEENS FALL CLOGHER 2 | bar: Week 45 Mo 7 to Week 46 Fr 18
TO-22-220 kV A1 @ MAY-03 | MAYNOOTH 220 kV A1 | bar: Week 45 Mo 7 to Week 46 Fr 18
TO-22-220 kV B1 @ MAY-03 | MAYNOOTH 220 kV B1 | bar: Week 45 Mo 7 to Week 46 Fr 18
TO-22-MAY-TH-1-02 | MAYNOOTH TURLOUGH HILL | bar: Week 45 Mo 7 to Week 46 Fr 18
TO-22-220 kV A2 @ TH-02 | TURLOUGH HILL 220 kV A2 | bar: Week 45 Mo 7 to Week 46 Fr 18
TO-22-220 kV B2 @ TH-02 | TURLOUGH HILL 220 kV B2 | bar: Week 45 Mo 7 to Week 46 Fr 18
TO-22-INC-PB-1-06 | INCHICORE POOLBEG 1
TO-22-PB-TF1-01 | POOLBEG TF1
TO-22-DRY-LOU-1-03 | DRYBRIDGE LOUTH | bar: Su 6 to Week 45 Mo 7
TO-22-GAL-T141-01 | GALWAY T141 | bar: Su 6 to Week 45 Mo 7
TO-22-220 kV B1 @ KYT-03 | KELLYSTOWN 220 kV B1 | bar: Su 6 to Week 45 Mo 7
TO-22-KYT-220SB1-2CB-03 | KELLYSTOWN 220SB1-2CB | bar: Su 6 to Week 45 Mo 7
TO-22-KYT-220SB1-3CB-04 | KELLYSTOWN 220SB1-3CB | bar: Su 6 to Week 45 Mo 7
TO-22-FLA-SLI-1-07 | FLAGFORD SLIGO | bar: Week 45 Tu 8
TO-22-220 kV A1/A2 @ KYT-01 | KELLYSTOWN 220 kV A1/A2 | bar: Week 45 Tu 8 to Week 45 We 9
TO-22-220 kV B1/B2 @ KYT-01 | KELLYSTOWN 220 kV B1/B2 | bar: Week 45 Tu 8 to Week 45 We 9
TO-22-KYT-220K2-02 | KELLYSTOWN 220K2 | bar: Week 45 Tu 8 to Week 45 We 9
TO-22-KYT-220SA1-2CB-03 | KELLYSTOWN 220SA1-2CB | bar: Week 45 Tu 8 to Week 45 We 9
TO-22-KYT-220SA1-3CB-04 | KELLYSTOWN 220SA1-3CB | bar: Week 45 Tu 8 to Week 45 We 9
TO-22-KYT-220SB1-2CB-08 | KELLYSTOWN 220SB1-2CB | bar: Week 45 Tu 8 to Week 45 We 9
TO-22-KYT-220SB1-3CB-10 | KELLYSTOWN 220SB1-3CB | bar: Week 45 Tu 8 to Week 45 We 9
TO-22-KYT-WOO-1-02 | KELLYSTOWN WOODLAND | bar: Week 45 Tu 8 to Week 45 We 9
TO-22-RYB GIS-T131-03 | RYEBROOK GIS T131 | bar: Week 45 Tu 8 to Week 45 We 9
TO-22-110 kV B1/B2 @ FLA-02 | FLAGFORD 110 kV B1/B2 | bar: Su 6 to Week 45 Tu 8
TO-22-FLA-110K1-2-01 | FLAGFORD 110K1-2 | bar: Su 6 to Week 45 Tu 8
TO-22-110 kV A1/A2 @ KRA-01 | KNOCKRAHA 110 kV A1/A2 | bar: Week 45 We 9
TO-22-110 kV B1/B2 @ KRA-01 | KNOCKRAHA 110 kV B1/B2 | bar: Week 45 We 9
TO-22-RYB GIS-T131-01 | RYEBROOK GIS T131 | bar: Su 6 to Week 45 We 9
TO-22-GLN-PLA-1-02 | GALLANSTOWN PLATIN | bar: Week 45 Th 10 to Week 45 Fr 11
TO-22-PLA-110SA1-04 | PLATIN 110SA1 | bar: Week 45 Th 10 to Week 45 Fr 11
TO-22-PLA-110SA2-04 | PLATIN 110SA2 | bar: Week 45 Th 10 to Week 45 Fr 11
TO-22-PLA-T105-04 | PLATIN T105 | bar: Week 45 Th 10 to Week 45 Fr 11
TO-22-CHA-MAL-1-01 | CHARLEVILLE MALLOW | bar: Su 6 to Week 45 Th 10
TO-22-CKG-T122-01 | CORKAGH T122 | bar: Su 6 to Week 45 Fr 11
Outages commencing/returning in Week 46
OUTAGE ID | PLANT | Week 45 Mo 7: Week 45; Week 46 Mo 14: Week 46
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21
TO-22-220 kV B2 @ GOR-03 | GORMAN 220 kV B2 | bar: Week 46 Mo 14 to Week 46 Tu 15
TO-22-110 kV B2 @ KPG-03 | KILPADDOGE 110 kV B2 | bar: Week 46 Mo 14 to Week 46 Th 17
TO-22-110 kV B4 @ KPG-01 | KILPADDOGE 110 kV B4 | bar: Week 46 Mo 14 to Week 46 Th 17
TO-22-KPG-110SB2-4CB-01 | KILPADDOGE 110SB2-4CB | bar: Week 46 Mo 14 to Week 46 Th 17
Report covers outages commencing/returning/spanning the period: 07/11/2022 - 20/11/2022
Outages commencing/returning in Week 46
OUTAGE ID | PLANT | Week 45 Mo 7: Week 45; Week 46 Mo 14: Week 46
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21
TO-22-220 kV A2 @ CKM GIS-02 | CARRICKMINES GIS 220 kV A2 | bar: Week 46 Mo 14 to Week 46 Fr 18
TO-22-220 kV A4 @ CKM GIS-03 | CARRICKMINES GIS 220 kV A4 | bar: Week 46 Mo 14 to Week 46 Fr 18
TO-22-220 kV A2 @ CSH-01 | CASHLA 220 kV A2 | bar: Week 46 Mo 14 to Week 46 Fr 18
TO-22-220 kV A4 @ CSH-01 | CASHLA 220 kV A4 | bar: Week 46 Mo 14 to Week 46 Fr 18
TO-22-220 kV B2 @ CSH-01 | CASHLA 220 kV B2 | bar: Week 46 Mo 14 to Week 46 Fr 18
TO-22-220 kV B4 @ CSH-01 | CASHLA 220 kV B4 | bar: Week 46 Mo 14 to Week 46 Fr 18
TO-22-CSH-220K2-4-01 | CASHLA 220K2-4 | bar: Week 46 Mo 14 to Week 46 Fr 18
TO-22-CHA-KLN-1-01 | CHARLEVILLE KILLONAN | bar: Week 46 Mo 14 to Week 46 Fr 18
TO-22-CKN-KER-1-03 | CLONKEEN KNOCKEARAGH | bar: Week 46 Mo 14 to Week 46 Fr 18
TO-22-DSN-400K1-2-02 | DUNSTOWN 400K1-2 | bar: Week 46 Mo 14 to Week 46 Fr 18
TO-22-FLA-SLI-1-04 | FLAGFORD SLIGO | bar: Week 46 Mo 14 to Week 46 Fr 18
TO-22-220 kV A2 @ GOR-02 | GORMAN 220 kV A2 | bar: Week 46 Mo 14 to Week 46 Fr 18
TO-22-220 kV B2 @ GOR-02 | GORMAN 220 kV B2 | bar: Week 46 Mo 14 to Week 46 Fr 18
TO-22-GI GIS-LWD-1-02 | GREAT ISLAND GIS LODGEWOOD | bar: Week 46 Mo 14 to Week 46 Fr 18
TO-22-KER-110SA1-01 | KNOCKEARAGH 110SA1 | bar: Week 46 Mo 14 to Week 46 Fr 18
TO-22-KER-110SA2-02 | KNOCKEARAGH 110SA2 | bar: Week 46 Mo 14 to Week 46 Fr 18
TO-22-KER-T141-01 | KNOCKEARAGH T141 | bar: Week 46 Mo 14 to Week 46 Fr 18
TO-22-LA-MUL-1-03 | LANESBORO MULLINGAR | bar: Week 46 Mo 14 to Week 46 Fr 18
TO-22-LWD-220K1-2-02 | LODGEWOOD 220K1-2 | bar: Week 46 Mo 14 to Week 46 Fr 18
TO-22-MAY-T2102-01 | MAYNOOTH T2102 | bar: Week 46 Mo 14 to Week 46 Fr 18
TO-22-110 kV B1 @ RYB GIS-01 | RYEBROOK GIS 110 kV B1 | bar: Week 46 Mo 14 to Week 46 Fr 18
TO-22-110 kV B2 @ RYB GIS-02 | RYEBROOK GIS 110 kV B2 | bar: Week 46 Mo 14 to Week 46 Fr 18
TO-22-RYB GIS-110SB1-2CB-02 | RYEBROOK GIS 110SB1-2CB | bar: Week 46 Mo 14 to Week 46 Fr 18
TO-22-110 kV A1 @ ARK-02 | ARKLOW 110 kV A1 | bar: Week 46 Mo 14 to Week 46 Mo 21
TO-22-110 kV A2 @ ARK-01 | ARKLOW 110 kV A2 | bar: Week 46 Mo 14 to Week 46 Mo 21
TO-22-110 kV B1 @ ARK-02 | ARKLOW 110 kV B1 | bar: Week 46 Mo 14 to Week 46 Mo 21
TO-22-110 kV B2 @ ARK-01 | ARKLOW 110 kV B2 | bar: Week 46 Mo 14 to Week 46 Mo 21
TO-22-ARK-110K1-2-01 | ARKLOW 110K1-2 | bar: Week 46 Mo 14 to Week 46 Mo 21
TO-22-CKM GIS-220SA2-4CB-01 | CARRICKMINES GIS 220SA2-4CB | bar: Week 46 Mo 14 to Week 46 Mo 21
TO-22-GOR-LOU-1-01 | GORMAN LOUTH | bar: Week 46 Mo 14 to Week 46 Mo 21
TO-22-RYB GIS-T108-03 | RYEBROOK GIS T108 | bar: Week 46 Mo 14 to Week 46 Mo 21
TO-22-220 kV B1 @ BYH-02 | BALLYNAHULLA 220 kV B1 | bar: Week 46 Tu 15 to Week 46 Fr 18
TO-22-220 kV B2 @ BYH-03 | BALLYNAHULLA 220 kV B2 | bar: Week 46 Tu 15 to Week 46 Fr 18
TO-22-BYH-220SB1-2CB-01 | BALLYNAHULLA 220SB1-2CB | bar: Week 46 Tu 15 to Week 46 Fr 18
TO-22-110 kV A1/A2/A3/A4 @ CDU-01 | CORDUFF 110 kV A1/A2/A3/A4 | bar: Week 46 We 16
TO-22-110 kV B1/B2/B3/B4 @ CDU-01 | CORDUFF 110 kV B1/B2/B3/B4 | bar: Week 46 We 16
TO-22-NAV-110SA1-2CB-01 | NAVAN 110SA1-2CB | bar: Week 46 We 16
TO-22-CKG-T121-01 | CORKAGH T121 | bar: Week 46 Fr 18 to Week 46 Mo 21
TO-22-KBY-MR-1-01 | KILBARRY MARINA 1 | bar: Su 6 to Week 46 Fr 18
TO-22-KBY-MR-2-01 | KILBARRY MARINA 2 | bar: Su 6 to Week 46 Fr 18
Outages spanning Weeks 45-46
OUTAGE ID | PLANT | Week 45 Mo 7: Week 45; Week 46 Mo 14: Week 46
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21
TO-22-110 kV A4 @ CDU-01 | CORDUFF 110 kV A4
TO-22-110 kV B4 @ CDU-01 | CORDUFF 110 kV B4
TO-22-CUL-220K1-2-04 | CULLENAGH 220K1-2
TO-22-FIN GIS-110K6-02 | FINGLAS GIS 110K6
TO-22-GAL-KNY-1-01 | GALWAY KNOCKRANNY
TO-22-GGO-220K1-2-02 | GLANAGOW 220K1-2
TO-22-GOR-PLA-1-01 | GORMAN PLATIN
TO-22-IKE,T-SH-1-05 | IKERRIN tee SHANNONBRIDGE
TO-22-INC-220K1-2-03 | INCHICORE 220K1-2
TO-22-LET-M/CAP1-01 | LETTERKENNY M/CAP1
TO-22-MAY-WOO-1-15 | MAYNOOTH WOODLAND
TO-22-MUL-CAP2-03 | MULLINGAR CAP2
TO-22-NEW-PLS-1-01 | NEWBRIDGE PORTLAOISE
TO-22-PB-R2002-01 | POOLBEG R2002
TO-22-TB-T101-02 | TARBERT T101