## Wks 49 - 50
Report covers outages commencing/returning/spanning the period: 05/12/2022 - 18/12/2022
Outages commencing/returning in Week 49
OUTAGE ID | PLANT |  | Week 49 | [6 empty] | Week 50
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19
TO-22-COS-FLA-1-01 | CARRICK ON SHANNON FLAGFORD 1 | bar: Week 49 Mo 5 to Week 49 Fr 9
TO-22-220 kV B1 @ CSH-04 | CASHLA 220 kV B1 | bar: Week 49 Mo 5 to Week 49 Fr 9
TO-22-220 kV B2 @ CSH-04 | CASHLA 220 kV B2 | bar: Week 49 Mo 5 to Week 49 Fr 9
TO-22-CSH-220K1-2-05 | CASHLA 220K1-2 | bar: Week 49 Mo 5 to Week 49 Fr 9
TO-22-CRA-LWD-1-01 | CRANE LODGEWOOD | bar: Week 49 Mo 5 to Week 49 Fr 9
TO-22-110 kV A1 @ FLA-04 | FLAGFORD 110 kV A1 | bar: Week 49 Mo 5 to Week 49 Fr 9
TO-22-110 kV B1 @ FLA-04 | FLAGFORD 110 kV B1 | bar: Week 49 Mo 5 to Week 49 Fr 9
TO-22-KBY-KRA-1-06 | KILBARRY KNOCKRAHA 1 | bar: Week 49 Mo 5 to Week 49 Fr 9
TO-22-220 kV A3 @ KPG-03 | KILPADDOGE 220 kV A3 | bar: Week 49 Mo 5 to Week 49 Fr 9
TO-22-220 kV B3 @ KPG-03 | KILPADDOGE 220 kV B3 | bar: Week 49 Mo 5 to Week 49 Fr 9
TO-22-KPG-TB-1-02 | KILPADDOGE TARBERT 1 | bar: Week 49 Mo 5 to Week 49 Fr 9
TO-22-110 kV A1 @ KRA-02 | KNOCKRAHA 110 kV A1 | bar: Week 49 Mo 5 to Week 49 Fr 9
TO-22-110 kV B1 @ KRA-01 | KNOCKRAHA 110 kV B1 | bar: Week 49 Mo 5 to Week 49 Fr 9
TO-22-400 kV B2 @ MP GIS-01 | MONEYPOINT GIS 400 kV B2 | bar: Week 49 Mo 5 to Week 49 Fr 9
TO-22-400 kV B4 @ MP GIS-01 | MONEYPOINT GIS 400 kV B4 | bar: Week 49 Mo 5 to Week 49 Fr 9
TO-22-MP GIS-400SB2-4CB-01 | MONEYPOINT GIS 400SB2-4CB | bar: Week 49 Mo 5 to Week 49 Fr 9
TO-22-WOO-220K1-2-03 | WOODLAND 220K1-2 | bar: Week 49 Mo 5 to Week 49 Fr 9
TO-22-MP GIS-ST101-01 | MONEYPOINT GIS ST101 | bar: Week 49 Mo 5 to Week 50 Th 15
TO-22-220 kV B1 @ CKM GIS-03 | CARRICKMINES GIS 220 kV B1 | bar: Week 49 Mo 5 to Week 50 Fr 16
TO-22-220 kV B2 @ CKM GIS-02 | CARRICKMINES GIS 220 kV B2 | bar: Week 49 Mo 5 to Week 50 Fr 16
TO-22-CKM GIS-220SB1-2CB-01 | CARRICKMINES GIS 220SB1-2CB | bar: Week 49 Mo 5 to Week 50 Fr 16
TO-22-CKM GIS-220SB1-3CB-04 | CARRICKMINES GIS 220SB1-3CB | bar: Week 49 Mo 5 to Week 50 Fr 16
TO-22-CKM GIS-220SB2-4CB-04 | CARRICKMINES GIS 220SB2-4CB | bar: Week 49 Mo 5 to Week 50 Fr 16
TO-22-110 kV A1/A2 @ RAF-01 | RAFFEEN 110 kV A1/A2 | bar: Week 49 Tu 6
TO-22-110 kV B1/B2 @ RAF-01 | RAFFEEN 110 kV B1/B2 | bar: Week 49 Tu 6
TO-22-220 kV A1/A2 @ RAF-01 | RAFFEEN 220 kV A1/A2 | bar: Week 49 Tu 6
TO-22-220 kV B1/B2 @ RAF-01 | RAFFEEN 220 kV B1/B2 | bar: Week 49 Tu 6
TO-22-220 kV A1 @ MAY-04 | MAYNOOTH 220 kV A1 | bar: Week 49 Tu 6 to Week 49 We 7
TO-22-220 kV A2 @ MAY-08 | MAYNOOTH 220 kV A2 | bar: Week 49 Tu 6 to Week 49 We 7
TO-22-MAY-220K1-2-02 | MAYNOOTH 220K1-2 | bar: Week 49 Tu 6 to Week 49 We 7
TO-22-GAL-KNY-1-01 | GALWAY KNOCKRANNY | bar: Su 4 to Week 49 Tu 6
TO-22-220 kV A1/A2/A3/A4 @ CDU-01 | CORDUFF 220 kV A1/A2/A3/A4 | bar: Week 49 Th 8
TO-22-220 kV B1/B2/B3/B4 @ CDU-01 | CORDUFF 220 kV B1/B2/B3/B4 | bar: Week 49 Th 8
Outages commencing/returning in Week 50
OUTAGE ID | PLANT | Week 49 Mo 5: Week 49; Week 50 Mo 12: Week 50
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19
TO-22-AD-WHI-1-01 | AGHADA WHITEGATE | bar: Week 50 Mo 12 to Week 50 Fr 16
TO-22-MP GIS-220SA1-2CB-03 | MONEYPOINT GIS 220SA1-2CB | bar: Week 50 Tu 13
TO-22-110 kV B1 @ CBT-03 | CASTLEBAGOT 110 kV B1 | bar: Week 50 Tu 13 to Week 50 Th 15
TO-22-110 kV B2 @ CBT-01 | CASTLEBAGOT 110 kV B2 | bar: Week 50 Tu 13 to Week 50 Th 15
TO-22-CBT-110SB1-2CB-03 | CASTLEBAGOT 110SB1-2CB | bar: Week 50 Tu 13 to Week 50 Th 15
TO-22-DSN-220K1-2-03 | DUNSTOWN 220K1-2 | bar: Week 50 Tu 13 to Week 50 Th 15
TO-22-110 kV A1/A2 @ GOR-01 | GORMAN 110 kV A1/A2 | bar: Week 50 We 14
TO-22-110 kV B1/B2 @ GOR-01 | GORMAN 110 kV B1/B2 | bar: Week 50 We 14
TO-22-220 kV A1/A2 @ GOR-01 | GORMAN 220 kV A1/A2 | bar: Week 50 We 14
TO-22-220 kV B1/B2 @ GOR-01 | GORMAN 220 kV B1/B2 | bar: Week 50 We 14
TO-22-110 kV A1/A2 @ KBY-01 | KILBARRY 110 kV A1/A2 | bar: Week 50 We 14
TO-22-110 kV B1/B2 @ KBY-01 | KILBARRY 110 kV B1/B2 | bar: Week 50 We 14
TO-22-RYB GIS-T108-03 | RYEBROOK GIS T108 | bar: Su 4 to Week 50 Fr 16
Outages spanning Weeks 49-50
OUTAGE ID | PLANT | Week 49 Mo 5: Week 49; Week 50 Mo 12: Week 50
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19
TO-22-CUL-220K1-2-04 | CULLENAGH 220K1-2
TO-22-FIN GIS-110K6-02 | FINGLAS GIS 110K6
TO-22-GGO-220K1-2-02 | GLANAGOW 220K1-2
Report covers outages commencing/returning/spanning the period: 05/12/2022 - 18/12/2022
Outages spanning Weeks 49-50
OUTAGE ID | PLANT | Week 49 Mo 5: Week 49; Week 50 Mo 12: Week 50
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19
TO-22-INC-220K1-2-03 | INCHICORE 220K1-2
TO-22-LET-M/CAP1-01 | LETTERKENNY M/CAP1
TO-22-MAY-WOO-1-15 | MAYNOOTH WOODLAND
TO-22-MUL-CAP2-03 | MULLINGAR CAP2
TO-22-PB-R2002-01 | POOLBEG R2002
TO-22-RYB GIS-T132-01 | RYEBROOK GIS T132
TO-22-TB-T101-02 | TARBERT T101

## Wks 51 - 52
Report covers outages commencing/returning/spanning the period: 19/12/2022 - 01/01/2023
Outages commencing/returning in Week 51
OUTAGE ID | PLANT |  | Week 51 | [6 empty] | Week 52
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 19
TO-22-BLC-DND-1-03 | BELCAMP DARNDALE 1 | bar: Week 51 Mo 19
TO-22-110 kV A1 @ DND-01 | DARNDALE 110 kV A1 | bar: Week 51 Mo 19 to Week 51 Tu 20
TO-22-110 kV B1 @ DND-01 | DARNDALE 110 kV B1 | bar: Week 51 Mo 19 to Week 51 Tu 20
TO-22-DND-110K1-02 | DARNDALE 110K1 | bar: Week 51 Mo 19 to Week 51 Tu 20
TO-22-DND-110SA1-2CB-03 | DARNDALE 110SA1-2CB | bar: Week 51 Mo 19 to Week 51 Tu 20
TO-22-DND-110SB1-2CB-02 | DARNDALE 110SB1-2CB | bar: Week 51 Mo 19 to Week 51 Tu 20
TO-22-110 kV A1/A3 @ GAL GIS-01 | GALWAY GIS 110 kV A1/A3 | bar: Week 51 Mo 19 to Week 51 Tu 20
TO-22-GAL GIS-110K3-01 | GALWAY GIS 110K3 | bar: Week 51 Mo 19 to Week 51 Tu 20
TO-22-GAL GIS-110SA1-3CB-01 | GALWAY GIS 110SA1-3CB | bar: Week 51 Mo 19 to Week 51 Tu 20
TO-22-GAL-KNY-1-02 | GALWAY KNOCKRANNY | bar: Week 51 Mo 19 to Week 51 Tu 20
TO-22-110 kV A2 @ LOU-06 | LOUTH 110 kV A2 | bar: Week 51 Mo 19 to Week 51 Fr 23
TO-22-110 kV B2 @ LOU-06 | LOUTH 110 kV B2 | bar: Week 51 Mo 19 to Week 51 Fr 23
TO-22-220 kV A2 @ LOU-02 | LOUTH 220 kV A2 | bar: Week 51 Mo 19 to Week 51 Fr 23
TO-22-220 kV B2 @ LOU-02 | LOUTH 220 kV B2 | bar: Week 51 Mo 19 to Week 51 Fr 23
TO-22-LOU-T2104-06 | LOUTH T2104 | bar: Week 51 Mo 19 to Week 51 Fr 23
TO-22-GI GIS-220SB1-2CB-03 | GREAT ISLAND GIS 220SB1-2CB | bar: Week 51 Tu 20
TO-22-GOR-NAV-3-02 | GORMAN NAVAN 3 | bar: Week 51 Tu 20 to Week 51 We 21
Outages commencing/returning in Week 52
OUTAGE ID | PLANT | Week 51 Mo 19: Week 51; Week 52 Mo 26: Week 52
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 19
TO-22-INC-220K1-2-03 | INCHICORE 220K1-2
TO-22-MAY-WOO-1-15 | MAYNOOTH WOODLAND | bar: Su 18 to Week 52 Sa 31
TO-22-TB-T101-02 | TARBERT T101
Outages spanning Weeks 51-52
OUTAGE ID | PLANT | Week 51 Mo 19: Week 51; Week 52 Mo 26: Week 52
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 19
TO-22-CUL-220K1-2-04 | CULLENAGH 220K1-2
TO-22-FIN GIS-110K6-02 | FINGLAS GIS 110K6
TO-22-GGO-220K1-2-02 | GLANAGOW 220K1-2
TO-22-LET-M/CAP1-01 | LETTERKENNY M/CAP1
TO-22-MUL-CAP2-03 | MULLINGAR CAP2
TO-22-PB-R2002-01 | POOLBEG R2002
TO-22-RYB GIS-T132-01 | RYEBROOK GIS T132