## Wks 15 - 16
Report covers outages commencing/returning/spanning the period: 10/04/2023 - 23/04/2023
Outages commencing/returning in Week 15
OUTAGE ID | PLANT |  | Week 15 | [6 empty] | Week 16
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24
TO-23-CVW-KRA-1-01 | CASTLEVIEW KNOCKRAHA | bar: Week 15 Tu 11 to Week 15 Th 13
TO-23-KLN-KPG-1-01 | KILLONAN KILPADDOGE | bar: Week 15 Tu 11 to Week 15 Fr 14
TO-23-220 kV A4 @ KPG-03 | KILPADDOGE 220 kV A4 | bar: Week 15 Tu 11 to Week 15 Fr 14
TO-23-220 kV B4 @ KPG-03 | KILPADDOGE 220 kV B4 | bar: Week 15 Tu 11 to Week 15 Fr 14
TO-23-KPG-220K4-02 | KILPADDOGE 220K4 | bar: Week 15 Tu 11 to Week 15 Fr 14
TO-23-KPG-220SA2-4CB-02 | KILPADDOGE 220SA2-4CB | bar: Week 15 Tu 11 to Week 15 Fr 14
TO-23-KPG-220SB2-4CB-03 | KILPADDOGE 220SB2-4CB | bar: Week 15 Tu 11 to Week 15 Fr 14
TO-23-220 kV A1 @ TH-01 | TURLOUGH HILL 220 kV A1 | bar: Week 15 Tu 11 to Week 15 Fr 14
TO-23-220 kV A2 @ TH-01 | TURLOUGH HILL 220 kV A2 | bar: Week 15 Tu 11 to Week 15 Fr 14
TO-23-220 kV B1 @ TH-01 | TURLOUGH HILL 220 kV B1 | bar: Week 15 Tu 11 to Week 15 Fr 14
TO-23-220 kV B2 @ TH-01 | TURLOUGH HILL 220 kV B2 | bar: Week 15 Tu 11 to Week 15 Fr 14
TO-23-TH-220K1-2-01 | TURLOUGH HILL 220K1-2 | bar: Week 15 Tu 11 to Week 15 Fr 14
TO-23-LWD-T2102-01 | LODGEWOOD T2102 | bar: Week 15 Tu 11 to Week 16 Fr 21
TO-23-CLA-MAC-2-01 | CLASHAVOON MACROOM 2 | bar: Su 9 to Week 15 Tu 11
TO-23-110 kV A1/A2 @ PLS-01 | PORTLAOISE 110 kV A1/A2 | bar: Week 15 We 12
TO-23-110 kV B1/B2 @ PLS-01 | PORTLAOISE 110 kV B1/B2 | bar: Week 15 We 12
TO-23-KLN-T2104-01 | KILLONAN T2104 | bar: Week 15 We 12 to Week 16 Tu 18
TO-23-220 kV A2 @ FIN-04 | FINGLAS 220 kV A2 | bar: Su 9 to Week 15 We 12
TO-23-220 kV B2 @ FIN-04 | FINGLAS 220 kV B2 | bar: Su 9 to Week 15 We 12
TO-23-FIN-220K2-01 | FINGLAS 220K2 | bar: Su 9 to Week 15 We 12
TO-23-FIN-220SA1-2CB-01 | FINGLAS 220SA1-2CB | bar: Su 9 to Week 15 We 12
TO-23-FIN-220SB1-2CB-03 | FINGLAS 220SB1-2CB | bar: Su 9 to Week 15 We 12
TO-23-FIN GIS-T2106-01 | FINGLAS GIS T2106 | bar: Su 9 to Week 15 We 12
TO-23-220 kV A2 @ TB-01 | TARBERT 220 kV A2 | bar: Week 15 Th 13 to Week 16 Mo 24
TO-23-220 kV B2 @ TB-02 | TARBERT 220 kV B2 | bar: Week 15 Th 13 to Week 16 Mo 24
TO-23-110 kV A2 @ AA GIS-02 | ARDNACRUSHA GIS 110 kV A2 | bar: Week 15 Fr 14
TO-23-AA GIS-110K2-01 | ARDNACRUSHA GIS 110K2 | bar: Week 15 Fr 14
TO-23-AA GIS-110SA1-2CB-02 | ARDNACRUSHA GIS 110SA1-2CB | bar: Week 15 Fr 14
TO-23-AA GIS-T102-03 | ARDNACRUSHA GIS T102 | bar: Week 15 Fr 14
TO-23-220 kV B1/B2 @ LOU-02 | LOUTH 220 kV B1/B2 | bar: Su 9 to Week 15 Fr 14
TO-23-SK-T104-01 | SEALROCK T104 | bar: Su 9 to Week 15 Fr 14
TO-23-FLA-LOU-1-08 | FLAGFORD LOUTH | bar: Week 15 Sa 15 to Week 15 Su 16
TO-23-GOR-LOU-1-02 | GORMAN LOUTH | bar: Week 15 Sa 15 to Week 15 Su 16
TO-23-LOU-AT1-02 | LOUTH AT1 | bar: Week 15 Sa 15 to Week 15 Su 16
TO-23-LOU-AT3-02 | LOUTH AT3 | bar: Week 15 Sa 15 to Week 15 Su 16
TO-23-LOU-T2102-06 | LOUTH T2102 | bar: Week 15 Sa 15 to Week 15 Su 16
TO-23-LOU-T2104-04 | LOUTH T2104 | bar: Week 15 Sa 15 to Week 15 Su 16
TO-23-LOU-TAN-1-01 | LOUTH TANDRAGEE 1 | bar: Week 15 Sa 15 to Week 15 Su 16
Outages commencing/returning in Week 16
OUTAGE ID | PLANT | Week 15 Mo 10: Week 15; Week 16 Mo 17: Week 16
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24
TO-23-110 kV A1 @ CBT-04 | CASTLEBAGOT 110 kV A1 | bar: Week 16 Mo 17 to Week 16 Fr 21
TO-23-110 kV A2 @ CBT-01 | CASTLEBAGOT 110 kV A2 | bar: Week 16 Mo 17 to Week 16 Fr 21
TO-23-CBT-110K1-05 | CASTLEBAGOT 110K1 | bar: Week 16 Mo 17 to Week 16 Fr 21
TO-23-CBT-110SA1-2CB-01 | CASTLEBAGOT 110SA1-2CB | bar: Week 16 Mo 17 to Week 16 Fr 21
TO-23-CBT-110SA2-4CB-06 | CASTLEBAGOT 110SA2-4CB | bar: Week 16 Mo 17 to Week 16 Fr 21
TO-23-CBR-SVC-01 | CASTLEBAR SVC | bar: Week 16 Mo 17 to Week 16 Fr 21
TO-23-DRU-ENN-1-04 | DRUMLINE ENNIS | bar: Week 16 Mo 17 to Week 16 Fr 21
TO-23-110 kV A2 @ GOR-01 | GORMAN 110 kV A2 | bar: Week 16 Mo 17 to Week 16 Fr 21
TO-23-110 kV B2 @ GOR-01 | GORMAN 110 kV B2 | bar: Week 16 Mo 17 to Week 16 Fr 21
TO-23-KPG-TRL-2-01 | KILPADDOGE TRALEE 2 | bar: Week 16 Mo 17 to Week 16 Fr 21
TO-23-110 kV B1 @ RYB GIS-02 | RYEBROOK GIS 110 kV B1 | bar: Week 16 Mo 17 to Week 16 Fr 21
TO-23-110 kV B2 @ RYB GIS-01 | RYEBROOK GIS 110 kV B2 | bar: Week 16 Mo 17 to Week 16 Fr 21
TO-23-RYB GIS-110SB1-2CB-01 | RYEBROOK GIS 110SB1-2CB | bar: Week 16 Mo 17 to Week 16 Fr 21
TO-23-RYB GIS-110SB1-3CB-05 | RYEBROOK GIS 110SB1-3CB | bar: Week 16 Mo 17 to Week 16 Fr 21
TO-23-RYB GIS-110SB2-4CB-02 | RYEBROOK GIS 110SB2-4CB | bar: Week 16 Mo 17 to Week 16 Fr 21
TO-23-400 kV A2 @ WOO-01 | WOODLAND 400 kV A2 | bar: Week 16 Mo 17 to Week 16 Fr 21
TO-23-WOO-T4204-02 | WOODLAND T4204 | bar: Week 16 Mo 17 to Week 16 Fr 21
Report covers outages commencing/returning/spanning the period: 10/04/2023 - 23/04/2023
Outages commencing/returning in Week 16
OUTAGE ID | PLANT | Week 15 Mo 10: Week 15; Week 16 Mo 17: Week 16
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24
TO-23-CLA-KRA-1-01 | CLASHAVOON KNOCKRAHA
TO-23-CL-T102-02 | CLIFF T102
TO-23-CDU-RYB GIS-1-02 | CORDUFF RYEBROOK GIS
TO-23-220 kV A1/A2 @ KRA-01 | KNOCKRAHA 220 kV A1/A2
TO-23-KRA-220K1-04 | KNOCKRAHA 220K1
TO-23-KRA-220SA2-4CB-02 | KNOCKRAHA 220SA2-4CB
TO-23-IA-T101-02 | INNISCARRA T101
TO-23-220 kV B1/B2 @ KRA-01 | KNOCKRAHA 220 kV B1/B2
TO-23-KRA-220K1-05 | KNOCKRAHA 220K1
TO-23-KRA-220SB2-4CB-02 | KNOCKRAHA 220SB2-4CB
TO-23-220 kV A1/A2 @ TH-01 | TURLOUGH HILL 220 kV A1/A2
TO-23-220 kV B1/B2 @ TH-01 | TURLOUGH HILL 220 kV B1/B2
TO-23-MCE-SNU-1-02 | MACETOWN SNUGBOROUGH
TO-23-110 kV A2 @ PA-02 | POLLAPHUCA 110 kV A2
TO-23-PA-110SA1-04 | POLLAPHUCA 110SA1
TO-23-PA-110SA2-04 | POLLAPHUCA 110SA2
TO-23-PA-T101-04 | POLLAPHUCA T101
TO-23-AA GIS-T104-01 | ARDNACRUSHA GIS T104 | bar: Su 9 to Week 16 Th 20
TO-23-INC-ISH-1-01 | INCHICORE IRISHTOWN
TO-23-ISH-220K1-2-01 | IRISHTOWN 220K1-2
TO-23-ISH-SHL-1-01 | IRISHTOWN SHELLYBANKS
TO-23-KTL-MAY-1-01 | KILTEEL MAYNOOTH
TO-23-110 kV A1 @ MAY-01 | MAYNOOTH 110 kV A1
TO-23-110 kV B1 @ MAY-01 | MAYNOOTH 110 kV B1
TO-23-LOU-AT2-02 | LOUTH AT2
TO-23-LOU-T2101-01 | LOUTH T2101
TO-23-LOU-T2103-02 | LOUTH T2103
TO-23-LOU-TAN-2-02 | LOUTH TANDRAGEE 2
TO-23-LOU-WOO-1-01 | LOUTH WOODLAND
TO-23-LOU-220K1-2-01 | LOUTH 220K1-2
Outages spanning Weeks 15-16
OUTAGE ID | PLANT | Week 15 Mo 10: Week 15; Week 16 Mo 17: Week 16
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24
TO-23-220 kV A2 @ AD-01 | AGHADA 220 kV A2
TO-23-220 kV B2 @ AD-01 | AGHADA 220 kV B2
TO-23-AD-SA1-2CB-01 | AGHADA 220SA1-2CB
TO-23-AD-SB1-2CB-01 | AGHADA 220SB1-2CB
TO-23-AD-T2001-03 | AGHADA T2001
TO-23-CSH-CAP2-04 | CASHLA CAP2
TO-23-CSH-GAL-3-02 | CASHLA GALWAY 3
TO-23-CTN-TIP-1-01 | CAUTEEN TIPPERARY
TO-23-CLG-110K1-01 | CLOGHRAN 110K1
TO-23-110 kV A4 @ CDU-02 | CORDUFF 110 kV A4
TO-23-110 kV B4 @ CDU-02 | CORDUFF 110 kV B4
TO-23-CDU-220K1-3-04 | CORDUFF 220K1-3
TO-23-CDU-MUL-1-02 | CORDUFF MULLINGAR
TO-23-COR-PST-01 | CORRACLASSY ENNISKILLEN PST
TO-23-CUL-220K1-2-02 | CULLENAGH 220K1-2
TO-23-FIN GIS-110K6-01 | FINGLAS GIS 110K6
TO-23-FLA-T2101-02 | FLAGFORD T2101
TO-23-GAL-110K2-3-02 | GALWAY 110K2-3
TO-23-GAL-T102-02 | GALWAY T102
TO-23-GAL-T142-02 | GALWAY T142
TO-23-GGO-220K1-2-01 | GLANAGOW 220K1-2
TO-23-GOR-MTH-1-01 | GORMAN MEATH HILL
TO-23-INC-220K1-2-01 | INCHICORE 220K1-2
TO-23-KLS-KKY-1-01 | KELLIS KILKENNY
TO-23-KKY-110SA1-2CB-01 | KILKENNY 110SA1-2CB
TO-23-KKY-T141-01 | KILKENNY T141
Report covers outages commencing/returning/spanning the period: 10/04/2023 - 23/04/2023
Outages spanning Weeks 15-16
OUTAGE ID | PLANT | Week 15 Mo 10: Week 15; Week 16 Mo 17: Week 16
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24
TO-23-KRA-220K1-2-03 | KNOCKRAHA 220K1-2
TO-23-LET-M/CAP1-01 | LETTERKENNY M/CAP1
TO-23-LET-TIV-1-01 | LETTERKENNY TIEVEBRACK
TO-23-LIS-T141-01 | LISDRUM T141
TO-23-MUL-CAP1-02 | MULLINGAR CAP1
TO-23-MUL-CAP2-01 | MULLINGAR CAP2
TO-23-PB-R2002-02 | POOLBEG R2002
TO-23-PRO-TB-1-04 | PROSPECT TARBERT
TO-23-PRO-TB-1-02
TO-23-TB-T101-02 | TARBERT T101
TO-23-TB-T2003-03 | TARBERT T2003
TO-23-TB-T2004-02 | TARBERT T2004
TO-23-TB-T2101-02 | TARBERT T2101
TO-23-THU-CAP2-01 | THURLES CAP2