## Wks 31 - 32
Report covers outages commencing/returning/spanning the period: 01/08/2022 - 14/08/2022
Outages commencing/returning in Week 31
OUTAGE ID | PLANT |  | Week 31 | [6 empty] | Week 32
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
TO-22-110 kV B1 @ CF-03 | CATHALEENS FALL 110 kV B1 | bar: Week 31 Tu 2
TO-22-CL-T101-04 | CLIFF T101 | bar: Week 31 Tu 2
TO-22-CL-T102-02 | CLIFF T102 | bar: Week 31 Tu 2
TO-22-220 kV A2 @ KYT-02 | KELLYSTOWN 220 kV A2 | bar: Week 31 Tu 2 to Week 31 We 3
TO-22-220 kV B2 @ KYT-02 | KELLYSTOWN 220 kV B2 | bar: Week 31 Tu 2 to Week 31 We 3
TO-22-KYT-220K2-04 | KELLYSTOWN 220K2 | bar: Week 31 Tu 2 to Week 31 We 3
TO-22-KYT-220SA1-2CB-06 | KELLYSTOWN 220SA1-2CB | bar: Week 31 Tu 2 to Week 31 We 3
TO-22-KYT-220SB1-2CB-06 | KELLYSTOWN 220SB1-2CB | bar: Week 31 Tu 2 to Week 31 We 3
TO-22-MLN-T124-01 | MULLAGHARLIN T124 | bar: Week 31 Tu 2 to Week 31 We 3
TO-22-CSH-ENN-1-01 | CASHLA ENNIS | bar: Week 31 Tu 2 to Week 31 Th 4
TO-22-FIN GIS-T2106-02 | FINGLAS GIS T2106 | bar: Week 31 Tu 2 to Week 31 Th 4
TO-22-220 kV A1 @ TH-01 | TURLOUGH HILL 220 kV A1 | bar: Week 31 Tu 2 to Week 31 Th 4
TO-22-220 kV A2 @ TH-04 | TURLOUGH HILL 220 kV A2 | bar: Week 31 Tu 2 to Week 31 Th 4
TO-22-220 kV B1 @ TH-02 | TURLOUGH HILL 220 kV B1 | bar: Week 31 Tu 2 to Week 31 Th 4
TO-22-220 kV B2 @ TH-04 | TURLOUGH HILL 220 kV B2 | bar: Week 31 Tu 2 to Week 31 Th 4
TO-22-110 kV A2 @ BYH-03 | BALLYNAHULLA 110 kV A2 | bar: Week 31 Tu 2 to Week 31 Fr 5
TO-22-110 kV B2 @ BYH-03 | BALLYNAHULLA 110 kV B2 | bar: Week 31 Tu 2 to Week 31 Fr 5
TO-22-BYH-110K2-02 | BALLYNAHULLA 110K2 | bar: Week 31 Tu 2 to Week 31 Fr 5
TO-22-CBR-DLT-1-01 | CASTLEBAR DALTON | bar: Week 31 Tu 2 to Week 31 Fr 5
TO-22-CDY-SRA-1-01 | CORDERRY SRANANAGH | bar: Week 31 Tu 2 to Week 31 Fr 5
TO-22-CUL-220K1-2-02 | CULLENAGH 220K1-2 | bar: Week 31 Tu 2 to Week 31 Fr 5
TO-22-DLT-110SA1-02 | DALTON 110SA1 | bar: Week 31 Tu 2 to Week 31 Fr 5
TO-22-DLT-110SA2-03 | DALTON 110SA2 | bar: Week 31 Tu 2 to Week 31 Fr 5
TO-22-DLT-CAP1-01 | DALTON CAP1 | bar: Week 31 Tu 2 to Week 31 Fr 5
TO-22-DLT-T141-01 | DALTON T141 | bar: Week 31 Tu 2 to Week 31 Fr 5
TO-22-220 kV A2 @ TB-03 | TARBERT 220 kV A2 | bar: Week 31 Tu 2 to Week 31 Fr 5
TO-22-220 kV B2 @ TB-03 | TARBERT 220 kV B2 | bar: Week 31 Tu 2 to Week 31 Fr 5
TO-22-TH-220K1-2-01 | TURLOUGH HILL 220K1-2 | bar: Week 31 Tu 2 to Week 31 Fr 5
TO-22-TB-T2003-02 | TARBERT T2003 | bar: Week 31 Tu 2 to Week 32 Th 11
TO-22-GI-T2101-01 | GREAT ISLAND T2101 | bar: Su 31 to Week 31 Tu 2
TO-22-110 kV A1/A2 @ ARK-01 | ARKLOW 110 kV A1/A2 | bar: Week 31 We 3
TO-22-110 kV B1/B2 @ ARK-01 | ARKLOW 110 kV B1/B2 | bar: Week 31 We 3
TO-22-CLH-110SA1-01 | CLAHANE 110SA1 | bar: Week 31 We 3
TO-22-CLH-110SA2-01 | CLAHANE 110SA2 | bar: Week 31 We 3
TO-22-CLH-T122-01 | CLAHANE T122 | bar: Week 31 We 3
TO-22-CLH-TRL-1-01 | CLAHANE TRALEE | bar: Week 31 We 3
TO-22-CLW-T142-02 | CARLOW T142 | bar: Week 31 We 3 to Week 31 Th 4
TO-22-CLH-TRI-1-01 | CLAHANE TRIEN | bar: Su 31 to Week 31 We 3
TO-22-KYT-WOO-1-03 | KELLYSTOWN WOODLAND | bar: Su 31 to Week 31 We 3
TO-22-110 kV A1 @ TRI-01 | TRIEN 110 kV A1 | bar: Su 31 to Week 31 We 3
TO-22-TRI-110SA1-2CB-01 | TRIEN 110SA1-2CB | bar: Su 31 to Week 31 We 3
TO-22-TRI-110SA1-3CB-01 | TRIEN 110SA1-3CB | bar: Su 31 to Week 31 We 3
TO-22-TRI-CAP1-01 | TRIEN CAP1 | bar: Su 31 to Week 31 We 3
TO-22-TRI-T141-01 | TRIEN T141 | bar: Su 31 to Week 31 We 3
TO-22-CUS-110SA1-2CB-02 | CUSHALING 110SA1-2CB | bar: Week 31 Th 4 to Week 31 Fr 5
TO-22-CUS-MLC-1-04 | CUSHALING MOUNTLUCAS | bar: Week 31 Th 4 to Week 31 Fr 5
TO-22-CUS-PLS-1-02 | CUSHALING PORTLAOISE | bar: Week 31 Th 4 to Week 31 Fr 5
TO-22-CUS-PLS-1-04 | bar: Week 31 Th 4 to Week 31 Fr 5
TO-22-CUS-T101-02 | CUSHALING T101 | bar: Week 31 Th 4 to Week 31 Fr 5
TO-22-220 kV A3 @ KYT-02 | KELLYSTOWN 220 kV A3 | bar: Week 31 Th 4 to Week 31 Fr 5
TO-22-KYT-220K3-03 | KELLYSTOWN 220K3 | bar: Week 31 Th 4 to Week 31 Fr 5
TO-22-KYT-220SA1-3CB-02 | KELLYSTOWN 220SA1-3CB | bar: Week 31 Th 4 to Week 31 Fr 5
TO-22-MLN-T123-02 | MULLAGHARLIN T123 | bar: Week 31 Th 4 to Week 31 Fr 5
TO-22-NEW-PLS-1-06 | NEWBRIDGE PORTLAOISE | bar: Week 31 Th 4 to Week 31 Fr 5
TO-22-KNR-TRI-2-01 | KNOCKANURE TRIEN 2 | bar: Week 31 Th 4 to Week 32 Mo 15
TO-22-TRI-110SA1-2CB-02 | TRIEN 110SA1-2CB | bar: Week 31 Th 4 to Week 32 Mo 15
TO-22-TRI-T142-01 | TRIEN T142 | bar: Week 31 Th 4 to Week 32 Mo 15
TO-22-110 kV A2 @ LOU-04 | LOUTH 110 kV A2 | bar: Su 31 to Week 31 Th 4
TO-22-110 kV B2 @ LOU-04 | LOUTH 110 kV B2 | bar: Su 31 to Week 31 Th 4
TO-22-DDK-LOU-1-02 | DUNDALK LOUTH | bar: Week 31 Fr 5 to Week 32 Fr 12
TO-22-LOU-110K1-2-01 | LOUTH 110K1-2 | bar: Week 31 Fr 5 to Week 32 Fr 12
Report covers outages commencing/returning/spanning the period: 01/08/2022 - 14/08/2022
Outages commencing/returning in Week 31
OUTAGE ID | PLANT | Week 31 Mo 1: Week 31; Week 32 Mo 8: Week 32
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
TO-22-LOU-MTH-1-02 | LOUTH MEATH HILL | bar: Week 31 Fr 5 to Week 32 Fr 12
TO-22-LOU-T2102-02 | LOUTH T2102 | bar: Week 31 Fr 5 to Week 32 Fr 12
TO-22-LOU-T2104-02 | LOUTH T2104 | bar: Week 31 Fr 5 to Week 32 Fr 12
TO-22-CUS-MLC-1-02 | CUSHALING MOUNTLUCAS | bar: Su 31 to Week 31 Fr 5
TO-22-CUS-MLC-1-01 | bar: Su 31 to Week 31 Fr 5
TO-22-RYB GIS-T133-01 | RYEBROOK GIS T133 | bar: Su 31 to Week 31 Fr 5
Outages commencing/returning in Week 32
OUTAGE ID | PLANT | Week 31 Mo 1: Week 31; Week 32 Mo 8: Week 32
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
TO-22-LIM-MTN-1-01 | LIMERICK MONETEEN | bar: Week 32 Mo 8 to Week 32 We 10
TO-22-BIN-TIV-1-02 | BINBANE TIEVEBRACK | bar: Week 32 Mo 8 to Week 32 Th 11
TO-22-BEG-CKM GIS-1-01 | BALLYBEG CARRICKMINES GIS | bar: Week 32 Mo 8 to Week 32 Fr 12
TO-22-110 kV A2 @ CAH-02 | CAHIR 110 kV A2 | bar: Week 32 Mo 8 to Week 32 Fr 12
TO-22-110 kV B2 @ CAH-02 | CAHIR 110 kV B2 | bar: Week 32 Mo 8 to Week 32 Fr 12
TO-22-CAH-CAP2/4-01 | CAHIR CAP2/4 | bar: Week 32 Mo 8 to Week 32 Fr 12
TO-22-220 kV A3 @ CKM GIS-05 | CARRICKMINES GIS 220 kV A3 | bar: Week 32 Mo 8 to Week 32 Fr 12
TO-22-220 kV B3 @ CKM GIS-05 | CARRICKMINES GIS 220 kV B3 | bar: Week 32 Mo 8 to Week 32 Fr 12
TO-22-CLO-MRY-1-02 | CLOGHER MULREAVY | bar: Week 32 Mo 8 to Week 32 Fr 12
TO-22-GI-T2102-01 | GREAT ISLAND T2102 | bar: Week 32 Mo 8 to Week 32 Fr 12
TO-22-KPG-TB-1-02 | KILPADDOGE TARBERT 1 | bar: Week 32 Mo 8 to Week 32 Fr 12
TO-22-220 kV A2 @ KRA-04 | KNOCKRAHA 220 kV A2 | bar: Week 32 Mo 8 to Week 32 Fr 12
TO-22-220 kV B2 @ KRA-04 | KNOCKRAHA 220 kV B2 | bar: Week 32 Mo 8 to Week 32 Fr 12
TO-22-MLC-TSB-1-02 | MOUNTLUCAS THORNSBERRY | bar: Week 32 Mo 8 to Week 32 Fr 12
TO-22-MRY-T131-02 | MULREAVY T131 | bar: Week 32 Mo 8 to Week 32 Fr 12
TO-22-110 kV A1 @ RYB GIS-01 | RYEBROOK GIS 110 kV A1 | bar: Week 32 Mo 8 to Week 32 Fr 12
TO-22-110 kV A2 @ RYB GIS-01 | RYEBROOK GIS 110 kV A2 | bar: Week 32 Mo 8 to Week 32 Fr 12
TO-22-RYB GIS-110SA1-2CB-01 | RYEBROOK GIS 110SA1-2CB | bar: Week 32 Mo 8 to Week 32 Fr 12
TO-22-TB-220K1-2-01 | TARBERT 220K1-2 | bar: Week 32 Mo 8 to Week 32 Fr 12
TO-22-TB-T2004-01 | TARBERT T2004 | bar: Week 32 Mo 8 to Week 32 Fr 12
TO-22-TB-T2101-02 | TARBERT T2101 | bar: Week 32 Mo 8 to Week 32 Fr 12
TO-22-CVW-KRA-1-01 | CASTLEVIEW KNOCKRAHA | bar: Week 32 Mo 8 to Week 32 Mo 15
TO-22-KRA-T2102-01 | KNOCKRAHA T2102 | bar: Week 32 Mo 8 to Week 32 Mo 15
TO-22-220 kV A2 @ PB-01 | POOLBEG 220 kV A2 | bar: Week 32 Mo 8 to Week 32 Mo 15
TO-22-CD-MAC-1-02 | CARRIGADROHID MACROOM | bar: Su 31 to Week 32 Mo 8
TO-22-BRT-T222-01 | BRACETOWN T222 | bar: Week 32 Tu 9
TO-22-CLE-220K1-03 | CLONEE 220K1 | bar: Week 32 Tu 9
TO-22-110 kV B2 @ DEY-05 | DERRYCARNEY 110 kV B2 | bar: Week 32 Tu 9 to Week 32 We 10
TO-22-DEY-110K2-05 | DERRYCARNEY 110K2 | bar: Week 32 Tu 9 to Week 32 We 10
TO-22-LET-T141-01 | LETTERKENNY T141 | bar: Week 32 Tu 9 to Week 32 We 10
TO-22-ATY-PLS-1-03 | ATHY PORTLAOISE | bar: Week 32 Tu 9 to Week 32 Th 11
TO-22-110 kV A2 @ CBT-02 | CASTLEBAGOT 110 kV A2 | bar: Week 32 Tu 9 to Week 32 Th 11
TO-22-110 kV A4 @ CBT-06 | CASTLEBAGOT 110 kV A4 | bar: Week 32 Tu 9 to Week 32 Th 11
TO-22-CBT-110SA2-4CB-06 | CASTLEBAGOT 110SA2-4CB | bar: Week 32 Tu 9 to Week 32 Th 11
TO-22-CLA-MAC-2-02 | CLASHAVOON MACROOM 2 | bar: Week 32 Tu 9 to Week 32 Th 11
TO-22-BVK-110K1-02 | BALLYVOUSKILL 110K1 | bar: Week 32 Tu 9 to Week 32 Fr 12
TO-22-110 kV A2 @ DEY-02 | DERRYCARNEY 110 kV A2 | bar: Su 31 to Week 32 Tu 9
TO-22-110 kV B2 @ DEY-03 | DERRYCARNEY 110 kV B2 | bar: Su 31 to Week 32 Tu 9
TO-22-DEY-110K2-02 | DERRYCARNEY 110K2 | bar: Su 31 to Week 32 Tu 9
TO-22-BRT-T224-01 | BRACETOWN T224 | bar: Week 32 We 10
TO-22-220 kV A1/A2 @ KLN-01 | KILLONAN 220 kV A1/A2 | bar: Week 32 We 10
TO-22-220 kV B1/B2 @ KLN-01 | KILLONAN 220 kV B1/B2 | bar: Week 32 We 10
TO-22-BVK-220K1-01 | BALLYVOUSKILL 220K1 | bar: Week 32 Th 11
TO-22-BK-MOY-1-02 | BELLACORICK MOY | bar: Week 32 Th 11
TO-22-MOY-110SA1-2CB-01 | MOY 110SA1-2CB | bar: Week 32 Th 11
TO-22-MOY-CAP2-01 | MOY CAP2 | bar: Week 32 Th 11
TO-22-MOY-TAW-2-02 | MOY TAWNAGHMORE 2 | bar: Week 32 Th 11
TO-22-MOY-T142-01 | MOY T142 | bar: Su 31 to Week 32 Th 11
TO-22-BYH-220K1-03 | BALLYNAHULLA 220K1 | bar: Week 32 Fr 12
TO-22-FIN-NW-1-06 | FINGLAS NORTH WALL | bar: Week 32 Fr 12
Report covers outages commencing/returning/spanning the period: 01/08/2022 - 14/08/2022
Outages commencing/returning in Week 32
OUTAGE ID | PLANT | Week 31 Mo 1: Week 31; Week 32 Mo 8: Week 32
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
TO-22-COR-PST-01 | CORRACLASSY ENNISKILLEN PST | bar: Week 32 Fr 12 to Week 32 Mo 15
TO-22-TAW-T1/T2-01 | TAWNAGHMORE T1/T2
TO-22-220 kV A1/A2 @ FIN-02 | FINGLAS 220 kV A1/A2
TO-22-FIN-220K1-12 | FINGLAS 220K1
TO-22-FIN-220K2-02 | FINGLAS 220K2
TO-22-INC-PB-2-02 | INCHICORE POOLBEG 2
TO-22-LIS-LOU-1-03 | LISDRUM LOUTH
TO-22-110 kV A2 @ GI-01 | GREAT ISLAND 110 kV A2
TO-22-GI-WAT-2-01 | GREAT ISLAND WATERFORD 2
Outages spanning Weeks 31-32
OUTAGE ID | PLANT | Week 31 Mo 1: Week 31; Week 32 Mo 8: Week 32
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
TO-22-220 kV A2 @ AD-02 | AGHADA 220 kV A2
TO-22-220 kV B2 @ AD-03 | AGHADA 220 kV B2
TO-22-AD-SA1-2CB-02 | AGHADA 220SA1-2CB
TO-22-AD-SB1-2CB-02 | AGHADA 220SB1-2CB
TO-22-AD-T2001-02 | AGHADA T2001
TO-22-BDN-DOO-1-01 | BALLYDINE DOON
TO-22-BDN-MRK3-01 | BALLYDINE MRK3
TO-22-BYH-BVK-1-02 | BALLYNAHULLA BALLYVOUSKILL
TO-22-BYH-BVK-1-01
TO-22-220 kV A4 @ CDU-01 | CORDUFF 220 kV A4
TO-22-220 kV B4 @ CDU-01 | CORDUFF 220 kV B4
TO-22-CDU-MUL-1-01 | CORDUFF MULLINGAR
TO-22-CKG-KUD-1-01 | CORKAGH KILMAHUD
TO-22-GAL-SAL-1-02 | GALWAY SALTHILL
TO-22-GAL-SAL-1-01
TO-22-GGO-220K1-2-02 | GLANAGOW 220K1-2
TO-22-GGO-RAF-1-02 | GLANAGOW RAFFEEN
TO-22-GI-WEX-1-01 | GREAT ISLAND WEXFORD
TO-22-INC-220K1-2-03 | INCHICORE 220K1-2
TO-22-KPG-TB-1-01 | KILPADDOGE TARBERT 1
TO-22-LET-M/CAP1-01 | LETTERKENNY M/CAP1
TO-22-MAY-WOO-1-15 | MAYNOOTH WOODLAND
TO-22-MUL-CAP2-03 | MULLINGAR CAP2
TO-22-PB-R2002-01 | POOLBEG R2002
TO-22-RYB GIS-T133-02 | RYEBROOK GIS T133
TO-22-SKL-T142-01 | SHANKILL T142
TO-22-SLI-T141-01 | SLIGO T141
TO-22-220 kV A1 @ TB-01 | TARBERT 220 kV A1
TO-22-220 kV B1 @ TB-01 | TARBERT 220 kV B1
TO-22-TB-T101-02 | TARBERT T101