## Wks 41 - 42
Report covers outages commencing/returning/spanning the period: 10/10/2022 - 23/10/2022
Outages commencing/returning in Week 41
OUTAGE ID | PLANT |  | Week 41 | [6 empty] | Week 42
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24
TO-22-BVK-R2001-01 | BALLYVOUSKILL R2001
TO-22-CBT-MAY-1-06 | CASTLEBAGOT MAYNOOTH 1 | bar: Week 41 Mo 10 to Week 41 We 12
TO-22-MAY-T2101-01 | MAYNOOTH T2101
TO-22-220 kV A1 @ BVK-01 | BALLYVOUSKILL 220 kV A1
TO-22-220 kV A2 @ BVK-01 | BALLYVOUSKILL 220 kV A2
TO-22-BVK-220SA1-2CB-01 | BALLYVOUSKILL 220SA1-2CB
TO-22-BAL-T122-01 | BALTRASNA T122
TO-22-110 kV A1 @ ARV-01 | ARVA 110 kV A1
TO-22-110 kV B1 @ ARV-01 | ARVA 110 kV B1
TO-22-BAL-CDU-1-02 | BALTRASNA CORDUFF
TO-22-BK-110SA1-03 | BELLACORICK 110SA1
TO-22-BK-110SA2-02 | BELLACORICK 110SA2
TO-22-BK-CBR-1-05 | BELLACORICK CASTLEBAR
TO-22-BK-SKY-1-01 | BELLACORICK SRAHNAKILLY
TO-22-BK-T122-01 | BELLACORICK T122
TO-22-110 kV A2 @ CLG-04 | CLOGHRAN 110 kV A2
TO-22-110 kV B2 @ CLG-05 | CLOGHRAN 110 kV B2
TO-22-CLG-T122-04 | CLOGHRAN T122
TO-22-KNY-UGL-1-01 | KNOCKRANNY UGGOOL
TO-22-SKY-110SA1-01 | SRAHNAKILLY 110SA1
TO-22-SKY-110SA2-01 | SRAHNAKILLY 110SA2
TO-22-SKY-T131-02 | SRAHNAKILLY T131
TO-22-THU-110SA1-2CB-04 | THURLES 110SA1-2CB
TO-22-THU-CAP1-02 | THURLES CAP1
TO-22-THU-T141-01 | THURLES T141
TO-22-UGL-110SA1-2CB-01 | UGGOOL 110SA1-2CB
TO-22-UGL-T131-01 | UGGOOL T131
TO-22-UGL-T132-01 | UGGOOL T132
TO-22-UGL-T134-01 | UGGOOL T134
TO-22-220 kV A2 @ WOO-03 | WOODLAND 220 kV A2
TO-22-220 kV B2 @ WOO-04 | WOODLAND 220 kV B2
TO-22-400 kV A2 @ WOO-02 | WOODLAND 400 kV A2
TO-22-400 kV B2 @ WOO-02 | WOODLAND 400 kV B2
TO-22-ARV-NAV-1-01 | ARVA NAVAN | bar: Week 41 Sa 15 to Week 42 Tu 18
TO-22-ATH-SH-1-01 | ATHLONE SHANNONBRIDGE | bar: Week 41 Sa 15 to Week 42 Fr 21
TO-22-110 kV A1 @ SH-01 | SHANNONBRIDGE 110 kV A1 | bar: Week 41 Sa 15 to Week 42 Fr 21
TO-22-110 kV B1 @ SH-01 | SHANNONBRIDGE 110 kV B1 | bar: Week 41 Sa 15 to Week 42 Fr 21
TO-22-WOO-T4204-01 | WOODLAND T4204 | bar: Week 41 Sa 15 to Week 42 Fr 21
TO-22-KBY-MR-1-01 | KILBARRY MARINA 1 | bar: Week 41 Sa 15 to Week 42 Mo 24
TO-22-KBY-MR-2-01 | KILBARRY MARINA 2 | bar: Week 41 Sa 15 to Week 42 Mo 24
TO-22-BLC-110SA1-3CB-01 | BELCAMP 110SA1-3CB
TO-22-KKY-T141-01 | KILKENNY T141
TO-22-CUL-T2101-01 | CULLENAGH T2101 | bar: Su 9
TO-22-BLC-110SB1-3CB-01 | BELCAMP 110SB1-3CB
TO-22-KRA-WOH-1-01 | KNOCKRAHA WOODHOUSE
TO-22-WOH-110SA1-02 | WOODHOUSE 110SA1
TO-22-WOH-110SA2-01 | WOODHOUSE 110SA2
TO-22-WOH-T122-03 | WOODHOUSE T122 | bar: Week 41 We 12 to Week 41 Fr 14
TO-22-KNR-TRI-2-01 | KNOCKANURE TRIEN 2 | bar: Su 9
TO-22-TRI-110SA1-2CB-02 | TRIEN 110SA1-2CB | bar: Su 9
TO-22-TRI-T142-01 | TRIEN T142 | bar: Su 9
TO-22-DEY-T132-01 | DERRYCARNEY T132 | bar: Week 41 Th 13
TO-22-CLH-TRL-1-02 | CLAHANE TRALEE | bar: Week 41 Sa 15 to Week 42 Fr 21
TO-22-MP GIS-T4003-01 | MONEYPOINT GIS T4003 | bar: Week 41 Sa 15 to Week 42 Su 23
TO-22-CKM-CKM GIS-1-01 | CARRICKMINES CARRICKMINES GIS | bar: Su 9
TO-22-CKM-PB-1-01 | CARRICKMINES POOLBEG | bar: Su 9
TO-22-CKM-PST2201-01 | CARRICKMINES PST2201 | bar: Su 9
TO-22-CHA-GLE-1-02 | CHARLEVILLE GLENLARA | bar: Su 9
TO-22-DSN-T4201-02 | DUNSTOWN T4201 | bar: Su 9
TO-22-KHL-THU-1-03 | KILL HILL THURLES | bar: Su 9
TO-22-TAW-T3-02 | TAWNAGHMORE T3 | bar: Su 9
Report covers outages commencing/returning/spanning the period: 10/10/2022 - 23/10/2022
Outages commencing/returning in Week 42
OUTAGE ID | PLANT | Week 41 Mo 10: Week 41; Week 42 Mo 17: Week 42
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24
TO-22-BUT-CUL-1-01 | BUTLERSTOWN CULLENAGH | bar: Week 42 Mo 17 to Week 42 Fr 21
TO-22-CLW-110SA1-06 | CARLOW 110SA1 | bar: Week 42 Mo 17 to Week 42 Fr 21
TO-22-CLW-KLS-1-06 | CARLOW KELLIS 1 | bar: Week 42 Mo 17 to Week 42 Fr 21
TO-22-CLW-T141-04 | CARLOW T141 | bar: Week 42 Mo 17 to Week 42 Fr 21
TO-22-110 kV A2 @ CLG-05 | CLOGHRAN 110 kV A2 | bar: Week 42 Mo 17 to Week 42 Fr 21
TO-22-110 kV B2 @ CLG-06 | CLOGHRAN 110 kV B2 | bar: Week 42 Mo 17 to Week 42 Fr 21
TO-22-CLG-T124-01 | CLOGHRAN T124 | bar: Week 42 Mo 17 to Week 42 Fr 21
TO-22-DFR,T-KIN-1-05 | DUNFIRTH tee KINNEGAD | bar: Week 42 Mo 17 to Week 42 Fr 21
TO-22-220 kV A2 @ DSN-02 | DUNSTOWN 220 kV A2 | bar: Week 42 Mo 17 to Week 42 Fr 21
TO-22-220 kV B2 @ DSN-02 | DUNSTOWN 220 kV B2 | bar: Week 42 Mo 17 to Week 42 Fr 21
TO-22-400 kV A2 @ DSN-02 | DUNSTOWN 400 kV A2 | bar: Week 42 Mo 17 to Week 42 Fr 21
TO-22-400 kV B2 @ DSN-02 | DUNSTOWN 400 kV B2 | bar: Week 42 Mo 17 to Week 42 Fr 21
TO-22-KLN-KPG-1-01 | KILLONAN KILPADDOGE | bar: Week 42 Mo 17 to Week 42 Fr 21
TO-22-KPG-TRL-1-04 | KILPADDOGE TRALEE 1 | bar: Week 42 Mo 17 to Week 42 Fr 21
TO-22-KIN-110SA1-2CB-02 | KINNEGAD 110SA1-2CB | bar: Week 42 Mo 17 to Week 42 Fr 21
TO-22-KIN-T102-01 | KINNEGAD T102 | bar: Week 42 Mo 17 to Week 42 Fr 21
TO-22-LOU-AT3-05 | LOUTH AT3 | bar: Week 42 Mo 17 to Week 42 Fr 21
TO-22-REM-110SA1-02 | REAMORE 110SA1 | bar: Week 42 Mo 17 to Week 42 Fr 21
TO-22-REM-110SA2-02 | REAMORE 110SA2 | bar: Week 42 Mo 17 to Week 42 Fr 21
TO-22-REM-T141-02 | REAMORE T141 | bar: Week 42 Mo 17 to Week 42 Fr 21
TO-22-REM-T142-02 | REAMORE T142 | bar: Week 42 Mo 17 to Week 42 Fr 21
TO-22-REM-TRL-1-03 | REAMORE TRALEE | bar: Week 42 Mo 17 to Week 42 Fr 21
TO-22-TRL-T141-01 | TRALEE T141 | bar: Week 42 Mo 17 to Week 42 Fr 21
TO-22-ARI-T121-01 | ARIGNA T121 | bar: Week 42 Mo 17 to Week 42 Mo 24
TO-22-ARI,T-ARI-1-01 | ARIGNA tee ARIGNA | bar: Week 42 Mo 17 to Week 42 Mo 24
TO-22-ARI,T-COS-1-01 | ARIGNA tee CARRICK ON SHANNON | bar: Week 42 Mo 17 to Week 42 Mo 24
TO-22-ARI,T-CDY-1-02 | ARIGNA tee CORDERRY | bar: Week 42 Mo 17 to Week 42 Mo 24
TO-22-DSN-T4202-01 | DUNSTOWN T4202 | bar: Week 42 Mo 17 to Week 42 Mo 24
TO-22-FIN GIS-T2101-01 | FINGLAS GIS T2101 | bar: Week 42 Mo 17 to Week 42 Mo 24
TO-22-LOU-WOO-1-02 | LOUTH WOODLAND | bar: Week 42 Mo 17 to Week 42 Mo 24
TO-22-220 kV A1 @ TB-03 | TARBERT 220 kV A1 | bar: Su 9 to Week 42 Mo 17
TO-22-220 kV B1 @ TB-03 | TARBERT 220 kV B1 | bar: Su 9 to Week 42 Mo 17
TO-22-TB-T2004-01 | TARBERT T2004 | bar: Su 9 to Week 42 Mo 17
TO-22-GWE-CAP1-02 | GORTAWEE CAP1 | bar: Week 42 Tu 18 to Week 42 Fr 21
TO-22-CKG-T123-01 | CORKAGH T123 | bar: Su 9 to Week 42 Tu 18
TO-22-KRA-RAF-1-01 | KNOCKRAHA RAFFEEN | bar: Su 9 to Week 42 Tu 18
TO-22-110 kV A1/A2 @ CLA-01 | CLASHAVOON 110 kV A1/A2 | bar: Week 42 We 19
TO-22-110 kV B1/B2 @ CLA-01 | CLASHAVOON 110 kV B1/B2 | bar: Week 42 We 19
TO-22-ARV-SKL-2-02 | ARVA SHANKILL 2 | bar: Week 42 We 19 to Week 42 Mo 24
TO-22-CDU-RYB GIS-1-01 | CORDUFF RYEBROOK GIS | bar: Su 9 to Week 42 Fr 21
TO-22-GAL-SAL-1-01 | GALWAY SALTHILL | bar: Su 9 to Week 42 Fr 21
TO-22-GI-WEX-1-01 | GREAT ISLAND WEXFORD
Outages spanning Weeks 41-42
OUTAGE ID | PLANT | Week 41 Mo 10: Week 41; Week 42 Mo 17: Week 42
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24
TO-22-ATY-CLW-1-01 | ATHY CARLOW
TO-22-110 kV A4 @ CDU-01 | CORDUFF 110 kV A4
TO-22-110 kV B4 @ CDU-01 | CORDUFF 110 kV B4
TO-22-CUL-220K1-2-04 | CULLENAGH 220K1-2
TO-22-110 kV A2 @ DEY-02 | DERRYCARNEY 110 kV A2
TO-22-110 kV B2 @ DEY-03 | DERRYCARNEY 110 kV B2
TO-22-DEY-110K2-02 | DERRYCARNEY 110K2
TO-22-FIN GIS-110K6-02 | FINGLAS GIS 110K6
TO-22-110 kV B1/B2 @ FLA-02 | FLAGFORD 110 kV B1/B2
TO-22-FLA-110K1-2-01 | FLAGFORD 110K1-2
TO-22-GGO-220K1-2-02 | GLANAGOW 220K1-2
TO-22-GOR-PLA-1-01 | GORMAN PLATIN
TO-22-INC-220K1-2-03 | INCHICORE 220K1-2
Report covers outages commencing/returning/spanning the period: 10/10/2022 - 23/10/2022
Outages spanning Weeks 41-42
OUTAGE ID | PLANT | Week 41 Mo 10: Week 41; Week 42 Mo 17: Week 42
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24
TO-22-LET-M/CAP1-01 | LETTERKENNY M/CAP1
TO-22-MAY-WOO-1-15 | MAYNOOTH WOODLAND
TO-22-MUL-CAP2-03 | MULLINGAR CAP2
TO-22-NAV-T141-02 | NAVAN T141
TO-22-PB-R2002-01 | POOLBEG R2002
TO-22-TB-T101-02 | TARBERT T101
TO-22-TIP-T141-02 | TIPPERARY T141