## Wks 19 - 20
Report covers outages commencing/returning/spanning the period: 08/05/2023 - 21/05/2023
Outages commencing/returning in Week 19
OUTAGE ID | PLANT |  | Week 19 | [6 empty] | Week 20
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22
TO-23-MP GIS-T4002-01 | MONEYPOINT GIS T4002
TO-23-220 kV A1 @ CDU-03 | CORDUFF 220 kV A1
TO-23-220 kV A2 @ CDU-03 | CORDUFF 220 kV A2
TO-23-220 kV A3 @ CDU-02 | CORDUFF 220 kV A3
TO-23-220 kV A4 @ CDU-04 | CORDUFF 220 kV A4
TO-23-220 kV B1 @ CDU-03 | CORDUFF 220 kV B1
TO-23-220 kV B2 @ CDU-03 | CORDUFF 220 kV B2
TO-23-220 kV B3 @ CDU-02 | CORDUFF 220 kV B3
TO-23-220 kV B4 @ CDU-04 | CORDUFF 220 kV B4
TO-23-CDU-220K1-2-04 | CORDUFF 220K1-2
TO-23-CDU-220K1-3-05 | CORDUFF 220K1-3
TO-23-CDU-220SA2-4-04 | CORDUFF 220SA2-4
TO-23-CDU-220SB2-4-06 | CORDUFF 220SB2-4
TO-23-DFR-T122-01 | DUNFIRTH T122
TO-23-DFR,T-DFR-1-02 | DUNFIRTH tee DUNFIRTH
TO-23-DFR,T-KIN-1-04 | DUNFIRTH tee KINNEGAD
TO-23-DFR,T-RNW-1-04 | DUNFIRTH tee RINAWADE
TO-23-AUG-CFM-1-01 | AUGHINISH CASTLEFARM 1
TO-23-AGL-110SA1-01 | AGANNYGAL 110SA1 | bar: Week 19 Th 11 to Week 19 Fr 12
TO-23-AGL-110SA2-01 | AGANNYGAL 110SA2 | bar: Week 19 Th 11 to Week 19 Fr 12
TO-23-AGL-DYN-1-01 | AGANNYGAL DERRYBRIEN | bar: Week 19 Th 11 to Week 19 Fr 12
TO-23-AGL-ENN-1-02 | AGANNYGAL ENNIS | bar: Week 19 Th 11 to Week 19 Fr 12
TO-23-AGL-SH-1-03 | AGANNYGAL SHANNONBRIDGE | bar: Week 19 Th 11 to Week 19 Fr 12
TO-23-110 kV A2 @ CSH-05 | CASHLA 110 kV A2 | bar: Week 19 Th 11 to Week 19 Fr 12
TO-23-110 kV B2 @ CSH-06 | CASHLA 110 kV B2 | bar: Week 19 Th 11 to Week 19 Fr 12
TO-23-220 kV A2 @ CSH-01 | CASHLA 220 kV A2 | bar: Week 19 Th 11 to Week 19 Fr 12
TO-23-220 kV A4 @ CSH-01 | CASHLA 220 kV A4 | bar: Week 19 Th 11 to Week 19 Fr 12
TO-23-CFM-T101-01 | CASTLEFARM T101 | bar: Week 19 Th 11 to Week 19 Fr 12
TO-23-DYN-T121-01 | DERRYBRIEN T121 | bar: Week 19 Th 11 to Week 19 Fr 12
TO-23-110 kV A1 @ RAF-03 | RAFFEEN 110 kV A1 | bar: Week 19 Th 11 to Week 19 Fr 12
TO-23-110 kV A2 @ RAF-03 | RAFFEEN 110 kV A2 | bar: Week 19 Th 11 to Week 19 Fr 12
TO-23-110 kV B1 @ RAF-03 | RAFFEEN 110 kV B1 | bar: Week 19 Th 11 to Week 19 Fr 12
TO-23-110 kV B2 @ RAF-03 | RAFFEEN 110 kV B2 | bar: Week 19 Th 11 to Week 19 Fr 12
TO-23-RAF-110K1-2-01 | RAFFEEN 110K1-2 | bar: Week 19 Th 11 to Week 19 Fr 12
TO-23-WEX-CAP2-01 | WEXFORD CAP2 | bar: Week 19 Th 11 to Week 19 Fr 12
TO-23-WEX-CAP4-01 | WEXFORD CAP4 | bar: Week 19 Th 11 to Week 19 Fr 12
TO-23-110 kV A1 @ MR-01 | MARINA 110 kV A1 | bar: Week 19 Th 11 to Week 20 Tu 16
TO-23-110 kV B1 @ MR-01 | MARINA 110 kV B1 | bar: Week 19 Th 11 to Week 20 Tu 16
TO-23-CF-T104-01 | CATHALEENS FALL T104 | bar: Week 19 Th 11 to Week 20 We 17
TO-23-CHA-GLE-1-01 | CHARLEVILLE GLENLARA | bar: Week 19 Th 11 to Week 20 Fr 19
TO-23-110 kV A1 @ MAY-02 | MAYNOOTH 110 kV A1 | bar: Week 19 Th 11 to Week 20 Fr 19
TO-23-110 kV A2 @ MAY-01 | MAYNOOTH 110 kV A2 | bar: Week 19 Th 11 to Week 20 Fr 19
TO-23-110 kV B1 @ MAY-02 | MAYNOOTH 110 kV B1 | bar: Week 19 Th 11 to Week 20 Fr 19
TO-23-110 kV B2 @ MAY-01 | MAYNOOTH 110 kV B2 | bar: Week 19 Th 11 to Week 20 Fr 19
TO-23-MAY-110K1-2-01 | MAYNOOTH 110K1-2 | bar: Week 19 Th 11 to Week 20 Fr 19
TO-23-CDU-FIN-2-01 | CORDUFF FINGLAS 2 | bar: Week 19 Th 11 to Week 20 Sa 20
TO-23-220 kV A2 @ FIN-01 | FINGLAS 220 kV A2 | bar: Week 19 Th 11 to Week 20 Sa 20
TO-23-220 kV B2 @ FIN-01 | FINGLAS 220 kV B2 | bar: Week 19 Th 11 to Week 20 Sa 20
TO-23-ARV-GWE-1-03 | ARVA GORTAWEE | bar: Week 19 Th 11 to Week 20 Mo 22
TO-23-CUL-DGN-1-02 | CULLENAGH DUNGARVAN | bar: Week 19 Th 11 to Week 20 Mo 22
TO-23-WOH-T122-01 | WOODHOUSE T122 | bar: Week 19 Th 11 to Week 20 Mo 22
TO-23-BNK-CBT-1-01 | BARNAKYLE CASTLEBAGOT 1
TO-23-CDU-MCE-1-06 | CORDUFF MACETOWN
TO-23-110 kV A1 @ BVK-01 | BALLYVOUSKILL 110 kV A1 | bar: Week 19 Th 11 to Week 20 Tu 16
TO-23-110 kV B1 @ BVK-01 | BALLYVOUSKILL 110 kV B1 | bar: Week 19 Th 11 to Week 20 Tu 16
TO-23-BVK-110K1-01 | BALLYVOUSKILL 110K1 | bar: Week 19 Th 11 to Week 20 Tu 16
TO-23-BVK-110SA1-2CB-01 | BALLYVOUSKILL 110SA1-2CB | bar: Week 19 Th 11 to Week 20 Tu 16
TO-23-BVK-110SB1-2CB-01 | BALLYVOUSKILL 110SB1-2CB | bar: Week 19 Th 11 to Week 20 Tu 16
TO-23-BVK-T2101-01 | BALLYVOUSKILL T2101 | bar: Week 19 Th 11 to Week 20 Tu 16
TO-23-GOR-T122-01 | GORMAN T122 | bar: Week 19 Th 11
TO-23-110 kV A1 @ CBT-02 | CASTLEBAGOT 110 kV A1 | bar: Week 19 Th 11 to Week 19 Fr 12
Report covers outages commencing/returning/spanning the period: 08/05/2023 - 21/05/2023
Outages commencing/returning in Week 19
OUTAGE ID | PLANT | Week 19 Mo 8: Week 19; Week 20 Mo 15: Week 20
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22
TO-23-110 kV A4 @ CBT-01 | CASTLEBAGOT 110 kV A4 | bar: Week 19 We 10 to Week 19 Fr 12
TO-23-110 kV B1 @ CBT-01 | CASTLEBAGOT 110 kV B1 | bar: Week 19 We 10 to Week 19 Fr 12
TO-23-110 kV B4 @ CBT-01 | CASTLEBAGOT 110 kV B4 | bar: Week 19 We 10 to Week 19 Fr 12
TO-23-CBT-110K1-04 | CASTLEBAGOT 110K1 | bar: Week 19 We 10 to Week 19 Fr 12
TO-23-CBT-110K4-01 | CASTLEBAGOT 110K4 | bar: Week 19 We 10 to Week 19 Fr 12
TO-23-CBT-110SA1-2CB-05 | CASTLEBAGOT 110SA1-2CB | bar: Week 19 We 10 to Week 19 Fr 12
TO-23-CBT-110SA2-4CB-02 | CASTLEBAGOT 110SA2-4CB | bar: Week 19 We 10 to Week 19 Fr 12
TO-23-CBT-110SB1-2CB-02 | CASTLEBAGOT 110SB1-2CB | bar: Week 19 We 10 to Week 19 Fr 12
TO-23-CBT-110SB2-4CB-02 | CASTLEBAGOT 110SB2-4CB | bar: Week 19 We 10 to Week 19 Fr 12
TO-23-CBT-T2103-05 | CASTLEBAGOT T2103 | bar: Week 19 We 10 to Week 19 Fr 12
TO-23-220 kV A2 @ CDU-01 | CORDUFF 220 kV A2 | bar: Week 19 We 10 to Week 20 Sa 20
TO-23-220 kV B2 @ CDU-01 | CORDUFF 220 kV B2 | bar: Week 19 We 10 to Week 20 Sa 20
TO-23-DFR,T-RNW-1-06 | DUNFIRTH tee RINAWADE | bar: Week 19 We 10 to Week 20 Mo 22
TO-23-CRO-IA-1-04 | COOLROE INNISCARRA | bar: Week 19 Th 11
TO-23-110 kV A1 @ IA-01 | INNISCARRA 110 kV A1 | bar: Week 19 Th 11
TO-23-IA-MAC-1-04 | INNISCARRA MACROOM | bar: Week 19 Th 11
TO-23-IA-T101-03 | INNISCARRA T101 | bar: Week 19 Th 11
TO-23-CDU-GLN-1-03 | CORDUFF GALLANSTOWN | bar: Week 19 Fr 12 to Week 20 Tu 16
TO-23-BYH-T2101-01 | BALLYNAHULLA T2101 | bar: Week 19 Fr 12 to Week 20 Mo 22
TO-23-110 kV A1 @ SH-03 | SHANNONBRIDGE 110 kV A1 | bar: Su 7 to Week 19 Fr 12
TO-23-110 kV A2 @ SH-04 | SHANNONBRIDGE 110 kV A2 | bar: Su 7 to Week 19 Fr 12
TO-23-110 kV B1 @ SH-07 | SHANNONBRIDGE 110 kV B1 | bar: Su 7 to Week 19 Fr 12
TO-23-110 kV B2 @ SH-03 | SHANNONBRIDGE 110 kV B2 | bar: Su 7 to Week 19 Fr 12
TO-23-TH-T2001/2-01 | TURLOUGH HILL T2001/2 | bar: Su 7 to Week 19 Fr 12
Outages commencing/returning in Week 20
OUTAGE ID | PLANT | Week 19 Mo 8: Week 19; Week 20 Mo 15: Week 20
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22
TO-23-CLH-110SA1-01 | CLAHANE 110SA1 | bar: Week 20 Mo 15 to Week 20 Th 18
TO-23-CLH-110SA2-01 | CLAHANE 110SA2 | bar: Week 20 Mo 15 to Week 20 Th 18
TO-23-CLH-T122-01 | CLAHANE T122 | bar: Week 20 Mo 15 to Week 20 Th 18
TO-23-CLH-TRI-1-01 | CLAHANE TRIEN | bar: Week 20 Mo 15 to Week 20 Th 18
TO-23-110 kV A3 @ AA GIS-01 | ARDNACRUSHA GIS 110 kV A3 | bar: Week 20 Mo 15 to Week 20 Fr 19
TO-23-110 kV B3 @ AA GIS-01 | ARDNACRUSHA GIS 110 kV B3 | bar: Week 20 Mo 15 to Week 20 Fr 19
TO-23-AA GIS-110K3-02 | ARDNACRUSHA GIS 110K3 | bar: Week 20 Mo 15 to Week 20 Fr 19
TO-23-AA GIS-110SA1-3CB-01 | ARDNACRUSHA GIS 110SA1-3CB | bar: Week 20 Mo 15 to Week 20 Fr 19
TO-23-AA GIS-110SB1-3CB-01 | ARDNACRUSHA GIS 110SB1-3CB | bar: Week 20 Mo 15 to Week 20 Fr 19
TO-23-AA GIS-DRU-1-01 | ARDNACRUSHA GIS DRUMLINE | bar: Week 20 Mo 15 to Week 20 Fr 19
TO-23-110 kV A2 @ GAL GIS-03 | GALWAY GIS 110 kV A2 | bar: Week 20 Mo 15 to Week 20 Fr 19
TO-23-110 kV B2 @ GAL GIS-03 | GALWAY GIS 110 kV B2 | bar: Week 20 Mo 15 to Week 20 Fr 19
TO-23-GAL GIS-110K2-02 | GALWAY GIS 110K2 | bar: Week 20 Mo 15 to Week 20 Fr 19
TO-23-GAL GIS-110SA1-2CB-03 | GALWAY GIS 110SA1-2CB | bar: Week 20 Mo 15 to Week 20 Fr 19
TO-23-GAL GIS-110SB1-2CB-03 | GALWAY GIS 110SB1-2CB | bar: Week 20 Mo 15 to Week 20 Fr 19
TO-23-BEG-CKM GIS-1-01 | BALLYBEG CARRICKMINES GIS | bar: Week 20 Mo 15 to Week 20 Sa 20
TO-23-DDK-LOU-1-01 | DUNDALK LOUTH | bar: Week 20 Mo 15 to Week 20 Mo 22
TO-23-110 kV A2 @ LOU-01 | LOUTH 110 kV A2 | bar: Week 20 Mo 15 to Week 20 Mo 22
TO-23-110 kV B2 @ LOU-01 | LOUTH 110 kV B2 | bar: Week 20 Mo 15 to Week 20 Mo 22
TO-23-110 kV A4 @ CDU-02 | CORDUFF 110 kV A4 | bar: Su 7 to Week 20 Mo 15
TO-23-110 kV B4 @ CDU-02 | CORDUFF 110 kV B4 | bar: Su 7 to Week 20 Mo 15
TO-23-220 kV A1 @ SH-01 | SHANNONBRIDGE 220 kV A1 | bar: Su 7 to Week 20 Mo 15
TO-23-220 kV A2 @ SH-01 | SHANNONBRIDGE 220 kV A2 | bar: Su 7 to Week 20 Mo 15
TO-23-220 kV B1 @ SH-01 | SHANNONBRIDGE 220 kV B1 | bar: Su 7 to Week 20 Mo 15
TO-23-220 kV B2 @ SH-01 | SHANNONBRIDGE 220 kV B2 | bar: Su 7 to Week 20 Mo 15
TO-23-SH-220K1-2-01 | SHANNONBRIDGE 220K1-2 | bar: Su 7 to Week 20 Mo 15
TO-23-220 kV A1 @ INC-02 | INCHICORE 220 kV A1 | bar: Week 20 Tu 16
TO-23-220 kV A2 @ INC-02 | INCHICORE 220 kV A2 | bar: Week 20 Tu 16
TO-23-220 kV B1 @ INC-02 | INCHICORE 220 kV B1 | bar: Week 20 Tu 16
TO-23-220 kV B2 @ INC-02 | INCHICORE 220 kV B2 | bar: Week 20 Tu 16
TO-23-INC-220K1-2-03 | INCHICORE 220K1-2 | bar: Week 20 Tu 16
TO-23-CD-T103-01 | CARRIGADROHID T103 | bar: Week 20 Tu 16 to Week 20 Mo 22
Report covers outages commencing/returning/spanning the period: 08/05/2023 - 21/05/2023
Outages commencing/returning in Week 20
OUTAGE ID | PLANT | Week 19 Mo 8: Week 19; Week 20 Mo 15: Week 20
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22
TO-23-CDU-GLN-1-04 | CORDUFF GALLANSTOWN
TO-23-LIS-SKL-1-04 | LISDRUM SHANKILL
Outages spanning Weeks 19-20
OUTAGE ID | PLANT | Week 19 Mo 8: Week 19; Week 20 Mo 15: Week 20
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22
TO-23-220 kV A2 @ AD-01 | AGHADA 220 kV A2
TO-23-220 kV B2 @ AD-01 | AGHADA 220 kV B2
TO-23-AD-SA1-2CB-01 | AGHADA 220SA1-2CB
TO-23-AD-SB1-2CB-01 | AGHADA 220SB1-2CB
TO-23-AD-T2001-03 | AGHADA T2001
TO-23-BDN-T141-01 | BALLYDINE T141
TO-23-CSH-220K2-4-01 | CASHLA 220K2-4
TO-23-CSH-CAP2-04 | CASHLA CAP2
TO-23-CSH-GAL-3-02 | CASHLA GALWAY 3
TO-23-CLG-110K1-01 | CLOGHRAN 110K1
TO-23-CFN-SH-1-01 | CLONIFFEEN SHANNONBRIDGE
TO-23-CFN-T232-01 | CLONIFFEEN T232
TO-23-CDU-MUL-1-02 | CORDUFF MULLINGAR
TO-23-CDU-RYB GIS-1-02 | CORDUFF RYEBROOK GIS
TO-23-CUL-220K1-2-02 | CULLENAGH 220K1-2
TO-23-DRY-T141-02 | DRYBRIDGE T141
TO-23-FIN GIS-110K6-01 | FINGLAS GIS 110K6
TO-23-FLA-T2101-02 | FLAGFORD T2101
TO-23-GAL-110K2-3-02 | GALWAY 110K2-3
TO-23-GAL-T142-02 | GALWAY T142
TO-23-GGO-220K1-2-01 | GLANAGOW 220K1-2
TO-23-INC-220K1-2-01 | INCHICORE 220K1-2
TO-23-KLS-220K1-2-04 | KELLIS 220K1-2
TO-23-110 kV B2 @ KBY-03 | KILBARRY 110 kV B2
TO-23-KBY-MR-1-01 | KILBARRY MARINA 1
TO-23-KBY-MR-2-03 | KILBARRY MARINA 2
TO-23-220 kV B1/B2 @ KRA-01 | KNOCKRAHA 220 kV B1/B2
TO-23-KRA-220K1-05 | KNOCKRAHA 220K1
TO-23-KRA-220K1-2-03 | KNOCKRAHA 220K1-2
TO-23-KRA-220SB2-4CB-02 | KNOCKRAHA 220SB2-4CB
TO-23-LET-M/CAP1-01 | LETTERKENNY M/CAP1
TO-23-LET-SVC-01 | LETTERKENNY SVC
TO-23-LET-TIV-1-01 | LETTERKENNY TIEVEBRACK
TO-23-LIS-T141-01 | LISDRUM T141
TO-23-220 kV A1/A2 @ LOU-01 | LOUTH 220 kV A1/A2
TO-23-220 kV A1 @ MAY-02 | MAYNOOTH 220 kV A1
TO-23-220 kV B1 @ MAY-02 | MAYNOOTH 220 kV B1
TO-23-MAY-TH-1-02 | MAYNOOTH TURLOUGH HILL
TO-23-400 kV A3 @ MP GIS-02 | MONEYPOINT GIS 400 kV A3
TO-23-400 kV B3 @ MP GIS-01 | MONEYPOINT GIS 400 kV B3
TO-23-MP GIS-400K3-01 | MONEYPOINT GIS 400K3
TO-23-MP GIS-400SA1-3CB-02 | MONEYPOINT GIS 400SA1-3CB
TO-23-MP GIS-400SB1-3CB-01 | MONEYPOINT GIS 400SB1-3CB
TO-23-MP GIS-OST-1-01 | MONEYPOINT GIS OLDSTREET
TO-23-MP GIS-T4202-02 | MONEYPOINT GIS T4202
TO-23-MUL-CAP1-02 | MULLINGAR CAP1
TO-23-MUL-CAP2-01 | MULLINGAR CAP2
TO-23-PB-R2002-02 | POOLBEG R2002
TO-23-PRO-TB-1-04 | PROSPECT TARBERT
TO-23-PRO-TB-1-02
TO-23-220 kV A2 @ TB-01 | TARBERT 220 kV A2
TO-23-220 kV B2 @ TB-02 | TARBERT 220 kV B2
TO-23-TB-T101-02 | TARBERT T101
TO-23-TB-T2003-03 | TARBERT T2003
Report covers outages commencing/returning/spanning the period: 08/05/2023 - 21/05/2023
Outages spanning Weeks 19-20
OUTAGE ID | PLANT | Week 19 Mo 8: Week 19; Week 20 Mo 15: Week 20
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22
TO-23-TB-T2004-02 | TARBERT T2004
TO-23-TB-T2101-02 | TARBERT T2101
TO-23-THU-CAP2-01 | THURLES CAP2