## Wks 23 - 24
Report covers outages commencing/returning/spanning the period: 06/06/2022 - 19/06/2022
Outages commencing/returning in Week 23
OUTAGE ID | PLANT |  | Week 23 | [6 empty] | Week 24
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20
TO-22-220 kV A2 @ MAY-02 | MAYNOOTH 220 kV A2 | bar: Week 23 Mo 6 to Week 23 Fr 10
TO-22-CF-COR-1-03 | CATHALEENS FALL CORRACLASSY | bar: Week 23 Mo 6 to Week 23 Th 9; Week 23 Sa 11 to Week 24 Mo 20
TO-22-AUG-SK-3-01 | AUGHINISH SEALROCK 3 | bar: Week 23 Tu 7 to Week 23 Th 9
TO-22-CTN-110SA1-02 | CAUTEEN 110SA1 | bar: Week 23 Tu 7 to Week 23 Th 9
TO-22-CTN-110SA2-01 | CAUTEEN 110SA2 | bar: Week 23 Tu 7 to Week 23 Th 9
TO-22-CTN-T142-01 | CAUTEEN T142 | bar: Week 23 Tu 7 to Week 23 Th 9
TO-22-CTN-T144-01 | CAUTEEN T144 | bar: Week 23 Tu 7 to Week 23 Th 9
TO-22-CLE-WOO-1-07 | CLONEE WOODLAND | bar: Week 23 Tu 7 to Week 23 Fr 10
TO-22-CDU-MCE-1-01 | CORDUFF MACETOWN | bar: Week 23 Tu 7 to Week 23 Fr 10
TO-22-110 kV A6 @ FIN GIS-01 | FINGLAS GIS 110 kV A6 | bar: Week 23 Tu 7 to Week 23 Th 9
TO-22-110 kV B6 @ FIN GIS-01 | FINGLAS GIS 110 kV B6 | bar: Week 23 Tu 7 to Week 23 Th 9
TO-22-FIN GIS-110K6-01 | FINGLAS GIS 110K6 | bar: Week 23 Tu 7 to Week 23 Th 9
TO-22-FIN GIS-110SA4-6CB-02 | FINGLAS GIS 110SA4-6CB | bar: Week 23 Tu 7 to Week 23 Th 9
TO-22-FIN GIS-110SB4-6CB-02 | FINGLAS GIS 110SB4-6CB | bar: Week 23 Tu 7 to Week 23 Th 9
TO-22-220 kV A2 @ KPG-01 | KILPADDOGE 220 kV A2 | bar: Week 23 Tu 7 to Week 23 Th 9
TO-22-220 kV B2 @ KPG-01 | KILPADDOGE 220 kV B2 | bar: Week 23 Tu 7 to Week 23 Th 9
TO-22-KPG-220SA1-2CB-01 | KILPADDOGE 220SA1-2CB | bar: Week 23 Tu 7 to Week 23 Th 9
TO-22-KPG-220SA2-4CB-01 | KILPADDOGE 220SA2-4CB | bar: Week 23 Tu 7 to Week 23 Th 9
TO-22-KPG-220SB1-2CB-01 | KILPADDOGE 220SB1-2CB | bar: Week 23 Tu 7 to Week 23 Th 9
TO-22-KPG-220SB2-4CB-01 | KILPADDOGE 220SB2-4CB | bar: Week 23 Tu 7 to Week 23 Th 9
TO-22-KPG-T2102-01 | KILPADDOGE T2102 | bar: Week 23 Tu 7 to Week 23 Th 9
TO-22-220 kV A2 @ KNR-01 | KNOCKANURE 220 kV A2 | bar: Week 23 Tu 7 to Week 23 Th 9
TO-22-220 kV B2 @ KNR-01 | KNOCKANURE 220 kV B2 | bar: Week 23 Tu 7 to Week 23 Th 9
TO-22-KNR-220K2-01 | KNOCKANURE 220K2 | bar: Week 23 Tu 7 to Week 23 Th 9
TO-22-KNR-220SA1-2CB-01 | KNOCKANURE 220SA1-2CB | bar: Week 23 Tu 7 to Week 23 Th 9
TO-22-KNR-220SB1-2CB-01 | KNOCKANURE 220SB1-2CB | bar: Week 23 Tu 7 to Week 23 Th 9
TO-22-KNR-T2102-01 | KNOCKANURE T2102 | bar: Week 23 Tu 7 to Week 23 Th 9
TO-22-SK-T103-01 | SEALROCK T103 | bar: Week 23 Tu 7 to Week 23 Th 9
TO-22-MP GIS-T4202-02 | MONEYPOINT GIS T4202 | bar: Week 23 Tu 7 to Week 23 Th 9; Week 23 Sa 11 to Week 24 Tu 14
TO-22-CTN-TIP-1-03 | CAUTEEN TIPPERARY | bar: Week 23 Tu 7 to Week 23 Th 9; Week 23 Sa 11 to Week 24 Fr 17
TO-22-CD-KBY-1-05 | CARRIGADROHID KILBARRY | bar: Week 23 Tu 7 to Week 23 Th 9; Week 23 Sa 11 to Week 24 Mo 20
TO-22-CDY-T121-03 | CORDERRY T121 | bar: Week 23 Tu 7 to Week 23 Th 9; Week 23 Sa 11 to Week 24 Mo 20
TO-22-DSN-220K1-2-01 | DUNSTOWN 220K1-2 | bar: Week 23 Tu 7 to Week 23 Th 9; Week 23 Sa 11 to Week 24 Mo 20
TO-22-TH-T2001/2-01 | TURLOUGH HILL T2001/2 | bar: Week 23 Tu 7 to Week 23 Th 9; Week 23 Sa 11 to Week 24 Mo 20
TO-22-TH-T2003/4-01 | TURLOUGH HILL T2003/4 | bar: Su 5 to Week 23 Tu 7
TO-22-MP GIS-400SA1-2CB-01 | MONEYPOINT GIS 400SA1-2CB | bar: Week 23 We 8
TO-22-BAL-DRY-1-02 | BALTRASNA DRYBRIDGE | bar: Week 23 We 8 to Week 23 Th 9
TO-22-BRY-RAF-1-01 | BARNAHELY RAFFEEN 1 | bar: Week 23 We 8 to Week 23 Th 9
TO-22-MOY-TAW-1-02 | MOY TAWNAGHMORE 1 | bar: Week 23 We 8 to Week 23 Th 9; Week 23 Sa 11 to Week 24 We 15
TO-22-MP GIS-220SB1-2CB-01 | MONEYPOINT GIS 220SB1-2CB | bar: Week 23 Th 9
TO-22-BIN-CF-1-04 | BINBANE CATHALEENS FALL | bar: Su 5 to Week 23 Th 9
TO-22-BIN-110SA1-2CB-02 | BINBANE 110SA1-2CB
TO-22-BIN-CF-1-02 | BINBANE CATHALEENS FALL
TO-22-BIN-T142-02 | BINBANE T142
TO-22-DSN-MAY-2-01 | DUNSTOWN MAYNOOTH 2 | bar: Week 23 Fr 10
TO-22-MP GIS-400SA2-4CB-02 | MONEYPOINT GIS 400SA2-4CB
TO-22-AA GIS-DRU-1-01 | ARDNACRUSHA GIS DRUMLINE | bar: Week 23 Sa 11 to Week 24 Fr 17
TO-22-DRU-110SA1-01 | DRUMLINE 110SA1 | bar: Week 23 Sa 11 to Week 24 Fr 17
TO-22-DRU-110SA2-02 | DRUMLINE 110SA2 | bar: Week 23 Sa 11 to Week 24 Fr 17
TO-22-DRU-CAP2-01 | DRUMLINE CAP2 | bar: Week 23 Sa 11 to Week 24 Fr 17
TO-22-DRU-T142-01 | DRUMLINE T142 | bar: Week 23 Sa 11 to Week 24 Fr 17
TO-22-BIN-T142-01 | BINBANE T142 | bar: Su 5 to Week 23 Th 9
TO-22-220 kV A1 @ CDU-04 | CORDUFF 220 kV A1 | bar: Su 5 to Week 23 Th 9
TO-22-220 kV A3 @ CDU-03 | CORDUFF 220 kV A3 | bar: Su 5 to Week 23 Th 9
TO-22-220 kV B1 @ CDU-05 | CORDUFF 220 kV B1 | bar: Su 5 to Week 23 Th 9
TO-22-220 kV B3 @ CDU-03 | CORDUFF 220 kV B3 | bar: Su 5 to Week 23 Th 9
TO-22-CDU-220K1-3-03 | CORDUFF 220K1-3 | bar: Su 5 to Week 23 Th 9
TO-22-KLN-SH-1-01 | KILLONAN SHANNONBRIDGE | bar: Su 5 to Week 23 Th 9; Week 23 Sa 11
TO-22-ARK-BOG-1-02 | ARKLOW BANOGE | bar: Week 23 Su 12
TO-22-BOG-CRA-1-03 | BANOGE CRANE | bar: Week 23 Su 12
Report covers outages commencing/returning/spanning the period: 06/06/2022 - 19/06/2022
Outages commencing/returning in Week 24
OUTAGE ID | PLANT | Week 23 Mo 6: Week 23; Week 24 Mo 13: Week 24
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20
TO-22-KHL-T131-01 | KILL HILL T131 | bar: Week 24 Mo 13
TO-22-CLO-DRM-1-01 | CLOGHER DRUMKEEN | bar: Week 24 Mo 13 to Week 24 Tu 14
TO-22-DAL-T141-02 | DALLOW T141 | bar: Week 24 Mo 13 to Week 24 Tu 14
TO-22-DAL,T-DAL-1-02 | DALLOW tee DALLOW | bar: Week 24 Mo 13 to Week 24 Tu 14
TO-22-DAL,T-DEY-1-02 | DALLOW tee DERRYCARNEY | bar: Week 24 Mo 13 to Week 24 Tu 14
TO-22-ENN-110SA1-2CB-01 | ENNIS 110SA1-2CB | bar: Week 24 Mo 13 to Week 24 Tu 14
TO-22-MAY-220K1-2-05 | MAYNOOTH 220K1-2 | bar: Week 24 Mo 13 to Week 24 Tu 14
TO-22-MAY-WOO-1-15 | MAYNOOTH WOODLAND | bar: Week 24 Mo 13 to Week 24 Tu 14
TO-22-CUN-T121-01 | CUNGHILL T121 | bar: Week 24 Mo 13 to Week 24 Th 16
TO-22-ATH-M/CAP1-01 | ATHLONE M/CAP1 | bar: Week 24 Mo 13 to Week 24 Fr 17
TO-22-AUG-MTN-1-01 | AUGHINISH MONETEEN | bar: Week 24 Mo 13 to Week 24 Fr 17
TO-22-CLG-FIN GIS-1-04 | CLOGHRAN FINGLAS GIS | bar: Week 24 Mo 13 to Week 24 Fr 17
TO-22-DOO-CAP1-02 | DOON CAP1 | bar: Week 24 Mo 13 to Week 24 Fr 17
TO-22-GLE-T141-01 | GLENLARA T141 | bar: Week 24 Mo 13 to Week 24 Fr 17
TO-22-KHL-THU-1-01 | KILL HILL THURLES | bar: Week 24 Mo 13 to Week 24 Fr 17
TO-22-MTN-110SA1-01 | MONETEEN 110SA1 | bar: Week 24 Mo 13 to Week 24 Fr 17
TO-22-MTN-110SA2-01 | MONETEEN 110SA2 | bar: Week 24 Mo 13 to Week 24 Fr 17
TO-22-MTN-MUN-1-01 | MONETEEN MUNGRET 1 | bar: Week 24 Mo 13 to Week 24 Fr 17
TO-22-MLC-110SA1-01 | MOUNTLUCAS 110SA1 | bar: Week 24 Mo 13 to Week 24 Fr 17
TO-22-MLC-110SA2-01 | MOUNTLUCAS 110SA2 | bar: Week 24 Mo 13 to Week 24 Fr 17
TO-22-MLC-T121-01 | MOUNTLUCAS T121 | bar: Week 24 Mo 13 to Week 24 Fr 17
TO-22-MUN-T101-01 | MUNGRET T101 | bar: Week 24 Mo 13 to Week 24 Fr 17
TO-22-220 kV A1 @ PB-01 | POOLBEG 220 kV A1 | bar: Week 24 Mo 13 to Week 24 Fr 17
TO-22-220 kV B1 @ PB-01 | POOLBEG 220 kV B1 | bar: Week 24 Mo 13 to Week 24 Fr 17
TO-22-PB-R2001-05 | POOLBEG R2001 | bar: Week 24 Mo 13 to Week 24 Fr 17
TO-22-AUG-CFM-1-01 | AUGHINISH CASTLEFARM 1 | bar: Week 24 Mo 13 to Week 24 Mo 20
TO-22-CSH-SAL-1-01 | CASHLA SALTHILL | bar: Week 24 Mo 13 to Week 24 Mo 20
TO-22-CFM-T101-01 | CASTLEFARM T101 | bar: Week 24 Mo 13 to Week 24 Mo 20
TO-22-CDY-T121-01 | CORDERRY T121 | bar: Week 24 Mo 13 to Week 24 Mo 20
TO-22-ENN-SLC-1-01 | ENNIS SLIEVECALLAN | bar: Week 24 Mo 13 to Week 24 Mo 20
TO-22-INC-PB-1-04 | INCHICORE POOLBEG 1 | bar: Week 24 Mo 13 to Week 24 Mo 20
TO-22-PA-110SA1-03 | POLLAPHUCA 110SA1 | bar: Week 24 Mo 13 to Week 24 Mo 20
TO-22-PA-110SA2-03 | POLLAPHUCA 110SA2 | bar: Week 24 Mo 13 to Week 24 Mo 20
TO-22-PA-T101-03 | POLLAPHUCA T101 | bar: Week 24 Mo 13 to Week 24 Mo 20
TO-22-SLC-110SA1-01 | SLIEVECALLAN 110SA1 | bar: Week 24 Mo 13 to Week 24 Mo 20
TO-22-SLC-110SA2-01 | SLIEVECALLAN 110SA2 | bar: Week 24 Mo 13 to Week 24 Mo 20
TO-22-SLC-T121-01 | SLIEVECALLAN T121 | bar: Week 24 Mo 13 to Week 24 Mo 20
TO-22-SLC-T122-01 | SLIEVECALLAN T122 | bar: Week 24 Mo 13 to Week 24 Mo 20
TO-22-110 kV A1 @ GOR-02 | GORMAN 110 kV A1 | bar: Week 24 Tu 14 to Week 24 Fr 17
TO-22-110 kV B1 @ GOR-01 | GORMAN 110 kV B1 | bar: Week 24 Tu 14 to Week 24 Fr 17
TO-22-GOR-NAV-1-02 | GORMAN NAVAN 1 | bar: Week 24 Tu 14 to Week 24 Fr 17
TO-22-GOR-NAV-1-01 | bar: Week 24 Tu 14 to Week 24 Fr 17
TO-22-AA GIS-T102-01 | ARDNACRUSHA GIS T102 | bar: Week 24 Tu 14 to Week 24 Mo 20
TO-22-DAL,T-SH-1-02 | DALLOW tee SHANNONBRIDGE | bar: Su 5 to Week 24 Tu 14
TO-22-GOR-220K1-2-01 | GORMAN 220K1-2 | bar: Su 5 to Week 24 Tu 14
TO-22-KLN-T2101-02 | KILLONAN T2101 | bar: Su 5 to Week 24 Tu 14
TO-22-LOU-AT3-01 | LOUTH AT3 | bar: Su 5 to Week 24 Tu 14
TO-22-KLN-KPG-1-02 | KILLONAN KILPADDOGE | bar: Week 24 We 15
TO-22-KLN-T2101-03 | KILLONAN T2101 | bar: Week 24 We 15
TO-22-220 kV A2 @ BYH-01 | BALLYNAHULLA 220 kV A2 | bar: Week 24 We 15 to Week 24 Fr 17
TO-22-220 kV B2 @ BYH-01 | BALLYNAHULLA 220 kV B2 | bar: Week 24 We 15 to Week 24 Fr 17
TO-22-BYH-BVK-1-02 | BALLYNAHULLA BALLYVOUSKILL | bar: Week 24 We 15 to Week 24 Mo 20
TO-22-BYH-BVK-1-01 | bar: Week 24 We 15 to Week 24 Mo 20
TO-22-110 kV A2 @ LOU-01 | LOUTH 110 kV A2 | bar: Su 5 to Week 24 We 15
TO-22-110 kV B2 @ LOU-02 | LOUTH 110 kV B2 | bar: Su 5 to Week 24 We 15
TO-22-CLE-WOO-1-05 | CLONEE WOODLAND | bar: Week 24 Th 16 to Week 24 Mo 20
TO-22-CLE-WOO-1-03 | bar: Week 24 Th 16 to Week 24 Mo 20
TO-22-220 kV A4 @ CDU-01 | CORDUFF 220 kV A4 | bar: Week 24 Th 16 to Week 24 Mo 20
TO-22-220 kV B4 @ CDU-01 | CORDUFF 220 kV B4 | bar: Week 24 Th 16 to Week 24 Mo 20
TO-22-KLN-T2103-01 | KILLONAN T2103 | bar: Week 24 Th 16 to Week 24 Mo 20
TO-22-220 kV B2 @ MAY-02 | MAYNOOTH 220 kV B2 | bar: Week 24 Th 16 to Week 24 Mo 20
Report covers outages commencing/returning/spanning the period: 06/06/2022 - 19/06/2022
Outages commencing/returning in Week 24
OUTAGE ID | PLANT | Week 23 Mo 6: Week 23; Week 24 Mo 13: Week 24
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20
TO-22-MAY-WOO-1-06 | MAYNOOTH WOODLAND | bar: Week 24 Th 16 to Week 24 Mo 20
TO-22-220 kV A1 @ WOO-01 | WOODLAND 220 kV A1 | bar: Week 24 Th 16 to Week 24 Mo 20
TO-22-220 kV B1 @ WOO-02 | WOODLAND 220 kV B1 | bar: Week 24 Th 16 to Week 24 Mo 20
TO-22-WOO-220K1-2-02 | WOODLAND 220K1-2 | bar: Week 24 Th 16 to Week 24 Mo 20
TO-22-WOO-T4201-02 | WOODLAND T4201 | bar: Week 24 Th 16 to Week 24 Mo 20
TO-22-FIN-NW-1-06 | FINGLAS NORTH WALL
TO-22-220 kV A1/A2 @ FIN-01 | FINGLAS 220 kV A1/A2
TO-22-FIN-220K1-06 | FINGLAS 220K1
TO-22-FIN-220K2-01 | FINGLAS 220K2
Outages spanning Weeks 23-24
OUTAGE ID | PLANT | Week 23 Mo 6: Week 23; Week 24 Mo 13: Week 24
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20
TO-22-CSH-220K1-2-01 | CASHLA 220K1-2
TO-22-CBR-CLN-1-01 | CASTLEBAR CLOON
TO-22-CBR-SVC-04 | CASTLEBAR SVC
TO-22-CBR-T141-01 | CASTLEBAR T141
TO-22-CLH-TRI-1-01 | CLAHANE TRIEN
TO-22-CDU-PLA-1-01 | CORDUFF PLATIN
TO-22-CUS-MLC-1-02 | CUSHALING MOUNTLUCAS
TO-22-110 kV A2 @ DEY-02 | DERRYCARNEY 110 kV A2
TO-22-110 kV B2 @ DEY-03 | DERRYCARNEY 110 kV B2
TO-22-DEY-110K2-02 | DERRYCARNEY 110K2
TO-22-DDK-MLN-1-01 | DUNDALK MULLAGHARLIN
TO-22-GGO-220K1-2-02 | GLANAGOW 220K1-2
TO-22-GGO-RAF-1-02 | GLANAGOW RAFFEEN
TO-22-GI-KKY-1-01 | GREAT ISLAND KILKENNY
TO-22-INC-220K1-2-03 | INCHICORE 220K1-2
TO-22-KPG-TB-1-01 | KILPADDOGE TARBERT 1
TO-22-LET-M/CAP1-01 | LETTERKENNY M/CAP1
TO-22-LIS-LOU-1-03 | LISDRUM LOUTH
TO-22-MAY-WOO-1-02 | MAYNOOTH WOODLAND
TO-22-MAY-WOO-1-12
TO-22-MOY-T142-01 | MOY T142
TO-22-MUL-CAP2-03 | MULLINGAR CAP2
TO-22-NAV-M/CAP1-01 | NAVAN M/CAP1
TO-22-OST-T4202-03 | OLDSTREET T4202
TO-22-OST-TY-1-03 | OLDSTREET TYNAGH
TO-22-PB-R2002-01 | POOLBEG R2002
TO-22-RYB GIS-T133-02 | RYEBROOK GIS T133
TO-22-220 kV A1 @ TB-01 | TARBERT 220 kV A1
TO-22-220 kV B1 @ TB-01 | TARBERT 220 kV B1
TO-22-TB-T101-02 | TARBERT T101
TO-22-TB-T102-02 | TARBERT T102
TO-22-TB-T2004-03 | TARBERT T2004
TO-22-110 kV A1 @ TRI-01 | TRIEN 110 kV A1
TO-22-TRI-110SA1-2CB-01 | TRIEN 110SA1-2CB
TO-22-TRI-110SA1-3CB-01 | TRIEN 110SA1-3CB
TO-22-TRI-CAP1-01 | TRIEN CAP1
TO-22-TRI-T141-01 | TRIEN T141
TO-22-WOO-T4201-05 | WOODLAND T4201