## Wks 17 - 18
Report covers outages commencing/returning/spanning the period: 25/04/2022 - 08/05/2022
Outages commencing/returning in Week 17
OUTAGE ID | PLANT |  | Week 17 | [6 empty] | Week 18
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9
TO-22-DFR-T122-02 | DUNFIRTH T122 | bar: Week 17 Mo 25
TO-22-DFR,T-DFR-1-02 | DUNFIRTH tee DUNFIRTH | bar: Week 17 Mo 25
TO-22-DFR,T-KIN-1-02 | DUNFIRTH tee KINNEGAD | bar: Week 17 Mo 25
TO-22-DFR,T-RNW-1-06 | DUNFIRTH tee RINAWADE | bar: Week 17 Mo 25
TO-22-MAY-WOO-1-09 | MAYNOOTH WOODLAND | bar: Week 17 Mo 25
TO-22-AA GIS-T101-01 | ARDNACRUSHA GIS T101 | bar: Week 17 Mo 25 to Week 17 We 27; Week 17 Fr 29
TO-22-CF-COR-1-02 | CATHALEENS FALL CORRACLASSY | bar: Week 17 Mo 25 to Week 17 Fr 29
TO-22-PB-R2001-05 | POOLBEG R2001 | bar: Week 17 Mo 25 to Week 17 We 27; Week 17 Fr 29
TO-22-TB-T101-01 | TARBERT T101 | bar: Week 17 Mo 25 to Week 17 We 27; Week 17 Fr 29
TO-22-TB-T2101-01 | TARBERT T2101 | bar: Week 17 Mo 25 to Week 17 We 27; Week 17 Fr 29
TO-22-GOR-LOU-1-01 | GORMAN LOUTH | bar: Week 17 Mo 25 to Week 17 We 27; Week 17 Fr 29 to Week 18 Mo 2
TO-22-KPG-KNR-1-110-01 | KILPADDOGE KNOCKANURE 110 | bar: Su 24 to Week 17 Mo 25
TO-22-GI GIS-220K2-01 | GREAT ISLAND GIS 220K2 | bar: Week 17 Tu 26
TO-22-DND-T123-01 | DARNDALE T123 | bar: Week 17 Tu 26 to Week 17 We 27
TO-22-BVK-220SB1-2CB-01 | BALLYVOUSKILL 220SB1-2CB | bar: Week 17 Tu 26 to Week 17 We 27; Week 17 Fr 29
TO-22-CVW-COW-1-01 | CASTLEVIEW COW CROSS | bar: Week 17 Tu 26 to Week 17 We 27; Week 17 Fr 29 to Week 18 Mo 9
TO-22-COW-110SA1-01 | COW CROSS 110SA1 | bar: Week 17 Tu 26 to Week 17 We 27; Week 17 Fr 29 to Week 18 Mo 9
TO-22-COW-110SA2-01 | COW CROSS 110SA2 | bar: Week 17 Tu 26 to Week 17 We 27; Week 17 Fr 29 to Week 18 Mo 9
TO-22-COW-OLD-1-01 | COW CROSS OLDCOURT 1 | bar: Week 17 Tu 26 to Week 17 We 27; Week 17 Fr 29 to Week 18 Mo 9
TO-22-COW-WHI-1-01 | COW CROSS WHITEGATE | bar: Week 17 Tu 26 to Week 17 We 27; Week 17 Fr 29 to Week 18 Mo 9
TO-22-DFR,T-RNW-1-02 | DUNFIRTH tee RINAWADE | bar: Week 17 Tu 26 to Week 17 We 27; Week 17 Fr 29 to Week 18 Mo 9
TO-22-MAY-WOO-1-10 | MAYNOOTH WOODLAND | bar: Week 17 Tu 26 to Week 17 We 27; Week 17 Fr 29 to Week 18 Mo 9
TO-22-OLD-T101-01 | OLDCOURT T101 | bar: Week 17 Tu 26 to Week 17 We 27; Week 17 Fr 29 to Week 18 Mo 9
TO-22-110 kV A1/A2 @ ARV-01 | ARVA 110 kV A1/A2 | bar: Week 17 We 27
TO-22-110 kV B1/B2 @ ARV-01 | ARVA 110 kV B1/B2 | bar: Week 17 We 27
TO-22-DND-110SA1-2CB-01 | DARNDALE 110SA1-2CB | bar: Week 17 We 27
TO-22-MCE-T124-01 | MACETOWN T124 | bar: Week 17 We 27
TO-22-KNR-R2002-01 | KNOCKANURE R2002 | bar: Week 17 We 27
TO-22-KNR-T2101-01 | KNOCKANURE T2101 | bar: Week 17 We 27
TO-22-110 kV A2 @ CLG-01 | CLOGHRAN 110 kV A2 | bar: Week 17 We 27; Week 17 Fr 29
TO-22-110 kV B2 @ CLG-01 | CLOGHRAN 110 kV B2 | bar: Week 17 We 27; Week 17 Fr 29
TO-22-CLG-110K2-01 | CLOGHRAN 110K2 | bar: Week 17 We 27; Week 17 Fr 29
TO-22-CLG-110SA1-2CB-01 | CLOGHRAN 110SA1-2CB | bar: Week 17 We 27; Week 17 Fr 29
TO-22-CLG-110SB1-2CB-01 | CLOGHRAN 110SB1-2CB | bar: Week 17 We 27; Week 17 Fr 29
TO-22-CLG-CDU-1-01 | CLOGHRAN CORDUFF | bar: Week 17 We 27; Week 17 Fr 29
TO-22-CLG-T122-03 | CLOGHRAN T122 | bar: Week 17 We 27; Week 17 Fr 29
TO-22-FLA-SLB-1-01 | FLAGFORD SLIABH BAWN | bar: Su 24 to Week 17 We 27
TO-22-220 kV A2 @ GOR-02 | GORMAN 220 kV A2 | bar: Su 24 to Week 17 We 27
TO-22-220 kV B2 @ GOR-02 | GORMAN 220 kV B2 | bar: Su 24 to Week 17 We 27
TO-22-CKN-110SA1-2CB-01 | CLONKEEN 110SA1-2CB
TO-22-BK-CBR-1-01 | BELLACORICK CASTLEBAR | bar: Week 17 Fr 29
TO-22-220 kV B1/B2 @ CSH-01 | CASHLA 220 kV B1/B2 | bar: Week 17 Fr 29
TO-22-CBR-110SA1-2CB-01 | CASTLEBAR 110SA1-2CB | bar: Week 17 Fr 29
TO-22-CBR-110SA1-2CB-04 | bar: Week 17 Fr 29
TO-22-CSH-220K1-2-01 | CASHLA 220K1-2 | bar: Week 17 Fr 29 to Week 18 Mo 9
TO-22-CSH-220K1-2-02 | bar: Week 17 Fr 29 to Week 18 Mo 9
TO-22-CBR-CLN-1-01 | CASTLEBAR CLOON | bar: Week 17 Fr 29 to Week 18 Mo 9
TO-22-CBR-SVC-01 | CASTLEBAR SVC | bar: Week 17 Fr 29 to Week 18 Mo 9
TO-22-CBR-T141-01 | CASTLEBAR T141 | bar: Week 17 Fr 29 to Week 18 Mo 9
TO-22-GI-KKY-1-05 | GREAT ISLAND KILKENNY | bar: Week 17 Fr 29 to Week 18 Mo 9
TO-22-GI-KKY-1-01 | bar: Week 17 Fr 29 to Week 18 Mo 9
TO-22-GI-T141-01 | GREAT ISLAND T141 | bar: Week 17 Fr 29 to Week 18 Mo 9
TO-22-KKY-110SA1-2CB-01 | KILKENNY 110SA1-2CB | bar: Week 17 Th 28 to Week 18 Mo 9
TO-22-KKY-110SA1-2CB-03 | bar: Week 17 Fr 29 to Week 18 Mo 9
TO-22-KKY-CAP2-02 | KILKENNY CAP2 | bar: Week 17 Fr 29 to Week 18 Mo 9
TO-22-KKY-CAP2-03 | bar: Week 17 Fr 29 to Week 18 Mo 9
TO-22-KKY-T142-01 | KILKENNY T142 | bar: Week 17 Fr 29 to Week 18 Mo 9
TO-22-CBR-CLN-1-02 | CASTLEBAR CLOON | bar: Week 17 Fr 29 to Week 18 Fr 6
TO-22-BK-CBR-1-04 | BELLACORICK CASTLEBAR | bar: Su 24 to Week 17 We 27; Week 17 Fr 29
TO-22-220 kV B2 @ CKM GIS-01 | CARRICKMINES GIS 220 kV B2 | bar: Su 24 to Week 17 We 27; Week 17 Fr 29
TO-22-220 kV B4 @ CKM GIS-02 | CARRICKMINES GIS 220 kV B4 | bar: Su 24 to Week 17 We 27; Week 17 Fr 29
Report covers outages commencing/returning/spanning the period: 25/04/2022 - 08/05/2022
Outages commencing/returning in Week 17
OUTAGE ID | PLANT | Week 17 Mo 25: Week 17; Week 18 Mo 2: Week 18
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9
TO-22-CKM GIS-220SB2-4CB-01 | CARRICKMINES GIS 220SB2-4CB | bar: Su 24 to Week 17 Fr 29
TO-22-CLG-T122-01 | CLOGHRAN T122 | bar: Su 24 to Week 17 Fr 29
TO-22-LWD-T2102-01 | LODGEWOOD T2102 | bar: Su 24 to Week 17 Fr 29
TO-22-DSN-MAY-2-02 | DUNSTOWN MAYNOOTH 2 | bar: Week 17 Su 1 to Week 18 Mo 2
TO-22-INC-MAY-2-01 | INCHICORE MAYNOOTH 2 | bar: Week 17 Su 1 to Week 18 Mo 2
TO-22-MAY-220K1-2-01 | MAYNOOTH 220K1-2 | bar: Week 17 Su 1 to Week 18 Mo 2
TO-22-MAY-SH-1-02 | MAYNOOTH SHANNONBRIDGE | bar: Week 17 Su 1 to Week 18 Mo 2
TO-22-MAY-T2103-01 | MAYNOOTH T2103 | bar: Week 17 Su 1 to Week 18 Mo 2
TO-22-MAY-T2104-01 | MAYNOOTH T2104 | bar: Week 17 Su 1 to Week 18 Mo 2
TO-22-MAY-WOO-1-04 | MAYNOOTH WOODLAND | bar: Week 17 Su 1 to Week 18 Mo 2
Outages commencing/returning in Week 18
OUTAGE ID | PLANT | Week 17 Mo 25: Week 17; Week 18 Mo 2: Week 18
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9
TO-22-CLG-T121-01 | CLOGHRAN T121 | bar: Week 18 Tu 3
TO-22-DEY-110K2-07 | DERRYCARNEY 110K2 | bar: Week 18 Tu 3
TO-22-RYB GIS-T103-01 | RYEBROOK GIS T103 | bar: Week 18 Tu 3 to Week 18 We 4
TO-22-IA-MAC-1-01 | INNISCARRA MACROOM | bar: Week 18 Tu 3 to Week 18 Th 5
TO-22-CAH-DOO-1-02 | CAHIR DOON | bar: Week 18 Tu 3 to Week 18 Fr 6
TO-22-GOR-T122-01 | GORMAN T122 | bar: Week 18 Tu 3 to Week 18 Fr 6
TO-22-LA-RIC-2-01 | LANESBORO RICHMOND 2 | bar: Week 18 Tu 3 to Week 18 Fr 6
TO-22-REM-110SA1-01 | REAMORE 110SA1 | bar: Week 18 Tu 3 to Week 18 Fr 6
TO-22-REM-110SA2-01 | REAMORE 110SA2 | bar: Week 18 Tu 3 to Week 18 Fr 6
TO-22-REM-T141-01 | REAMORE T141 | bar: Week 18 Tu 3 to Week 18 Fr 6
TO-22-REM-T142-01 | REAMORE T142 | bar: Week 18 Tu 3 to Week 18 Fr 6
TO-22-REM-TRL-1-01 | REAMORE TRALEE | bar: Week 18 Tu 3 to Week 18 Fr 6
TO-22-AGL-ENN-1-01 | AGANNYGAL ENNIS | bar: Week 18 Tu 3 to Week 18 Mo 9
TO-22-220 kV A4 @ CKM GIS-02 | CARRICKMINES GIS 220 kV A4 | bar: Week 18 Tu 3 to Week 18 Mo 9
TO-22-220 kV B4 @ CKM GIS-01 | CARRICKMINES GIS 220 kV B4 | bar: Week 18 Tu 3 to Week 18 Mo 9
TO-22-CKM GIS-220K4-01 | CARRICKMINES GIS 220K4 | bar: Week 18 Tu 3 to Week 18 Mo 9
TO-22-CKM GIS-220SA2-4CB-03 | CARRICKMINES GIS 220SA2-4CB | bar: Week 18 Tu 3 to Week 18 Mo 9
TO-22-CKM GIS-220SB2-4CB-02 | CARRICKMINES GIS 220SB2-4CB | bar: Week 18 Tu 3 to Week 18 Mo 9
TO-22-FLA-SRA-1-02 | FLAGFORD SRANANAGH | bar: Week 18 Tu 3 to Week 18 Mo 9
TO-22-IA-T101-02 | INNISCARRA T101 | bar: Week 18 Tu 3 to Week 18 Mo 9
TO-22-KLN-KRA-1-01 | KILLONAN KNOCKRAHA | bar: Week 18 Tu 3 to Week 18 Mo 9
TO-22-OUG-T141-01 | OUGHTRAGH T141 | bar: Week 18 Tu 3 to Week 18 Mo 9
TO-22-OUG,T-KER-1-01 | OUGHTRAGH tee KNOCKEARAGH | bar: Week 18 Tu 3 to Week 18 Mo 9
TO-22-OUG,T-OUG-1-01 | OUGHTRAGH tee OUGHTRAGH | bar: Week 18 Tu 3 to Week 18 Mo 9
TO-22-OUG,T-TRL-1-01 | OUGHTRAGH tee TRALEE | bar: Week 18 Tu 3 to Week 18 Mo 9
TO-22-SRA-220SA1-02 | SRANANAGH 220SA1 | bar: Week 18 Tu 3 to Week 18 Mo 9
TO-22-SRA-220SA2-02 | SRANANAGH 220SA2 | bar: Week 18 Tu 3 to Week 18 Mo 9
TO-22-SRA-T2102-02 | SRANANAGH T2102 | bar: Week 18 Tu 3 to Week 18 Mo 9
TO-22-AA GIS-LIM-1-01 | ARDNACRUSHA GIS LIMERICK | bar: Su 24 to Week 18 Tu 3
TO-22-KLN-LIM-2-01 | KILLONAN LIMERICK 2 | bar: Su 24 to Week 18 Tu 3
TO-22-LIM-110SA1-01 | LIMERICK 110SA1 | bar: Su 24 to Week 18 Tu 3
TO-22-LIM-110SA2-01 | LIMERICK 110SA2 | bar: Su 24 to Week 18 Tu 3
TO-22-LIM-RAT-1-01 | LIMERICK RATHKEALE | bar: Su 24 to Week 18 Tu 3
TO-22-LIM-T142-01 | LIMERICK T142 | bar: Su 24 to Week 18 Tu 3
TO-22-220 kV A2 @ MAY-01 | MAYNOOTH 220 kV A2 | bar: Su 24 to Week 18 Tu 3
TO-22-220 kV B2 @ MAY-01 | MAYNOOTH 220 kV B2 | bar: Su 24 to Week 18 Tu 3
TO-22-MAY-WOO-1-03 | MAYNOOTH WOODLAND | bar: Su 24 to Week 18 Tu 3
TO-22-110 kV A1/A2 @ BVK-01 | BALLYVOUSKILL 110 kV A1/A2 | bar: Week 18 We 4
TO-22-110 kV B1/B2 @ BVK-01 | BALLYVOUSKILL 110 kV B1/B2 | bar: Week 18 We 4
TO-22-220 kV A1/A2 @ BVK-01 | BALLYVOUSKILL 220 kV A1/A2 | bar: Week 18 We 4
TO-22-220 kV B1/B2 @ BVK-01 | BALLYVOUSKILL 220 kV B1/B2 | bar: Week 18 We 4
TO-22-DND-T124-01 | DARNDALE T124 | bar: Week 18 We 4
TO-22-SNU-T102-01 | SNUGBOROUGH T102 | bar: Week 18 We 4
TO-22-CLA-110K1-2-01 | CLASHAVOON 110K1-2 | bar: Week 18 We 4 to Week 18 Th 5
TO-22-WOH-T122-01 | WOODHOUSE T122 | bar: Week 18 We 4 to Week 18 Th 5
TO-22-110 kV A2 @ FIN GIS-01 | FINGLAS GIS 110 kV A2 | bar: Week 18 We 4 to Week 18 Mo 9
Report covers outages commencing/returning/spanning the period: 25/04/2022 - 08/05/2022
Outages commencing/returning in Week 18
OUTAGE ID | PLANT | Week 17 Mo 25: Week 17; Week 18 Mo 2: Week 18
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9
TO-22-FIN GIS-110K2-01 | FINGLAS GIS 110K2 | bar: Week 18 We 4 to Week 18 Mo 9
TO-22-FIN GIS-110SA1-2CB-01 | FINGLAS GIS 110SA1-2CB | bar: Week 18 We 4 to Week 18 Mo 9
TO-22-FIN GIS-110SA2-4CB-01 | FINGLAS GIS 110SA2-4CB | bar: Week 18 We 4 to Week 18 Mo 9
TO-22-TH-T2003/4-01 | TURLOUGH HILL T2003/4 | bar: Week 18 We 4 to Week 18 Mo 9
TO-22-110 kV A2 @ LOU-02 | LOUTH 110 kV A2 | bar: Su 24 to Week 18 We 4
TO-22-110 kV B2 @ LOU-01 | LOUTH 110 kV B2 | bar: Su 24 to Week 18 We 4
TO-22-SNU-T104-01 | SNUGBOROUGH T104 | bar: Week 18 Th 5
TO-22-RYB GIS-T104-01 | RYEBROOK GIS T104 | bar: Week 18 Th 5 to Week 18 Fr 6
TO-22-220 kV A2 @ TH-03 | TURLOUGH HILL 220 kV A2 | bar: Week 18 Th 5 to Week 18 Mo 9
TO-22-220 kV B2 @ TH-03 | TURLOUGH HILL 220 kV B2 | bar: Week 18 Th 5 to Week 18 Mo 9
TO-22-SOM-T142-05 | SOMERSET T142 | bar: Week 18 Fr 6
TO-22-SOM,T-CSH-1-02 | SOMERSET tee CASHLA | bar: Week 18 Fr 6
TO-22-SOM,T-SH-1-02 | SOMERSET tee SHANNONBRIDGE | bar: Week 18 Fr 6
TO-22-SOM,T-SOM-1-02 | SOMERSET tee SOMERSET | bar: Week 18 Fr 6
TO-22-CUS-110SA1-2CB-01 | CUSHALING 110SA1-2CB | bar: Week 18 Fr 6 to Week 18 Su 8
TO-22-CUS-PLS-1-01 | CUSHALING PORTLAOISE | bar: Week 18 Fr 6 to Week 18 Su 8
TO-22-CUS-T101-01 | CUSHALING T101 | bar: Week 18 Fr 6 to Week 18 Su 8
TO-22-CUS-MLC-1-02 | CUSHALING MOUNTLUCAS | bar: Week 18 Fr 6 to Week 18 Mo 9
TO-22-CUS-MLC-1-01 | bar: Week 18 Fr 6 to Week 18 Mo 9
TO-22-CUS-PLS-1-03 | CUSHALING PORTLAOISE | bar: Week 18 Fr 6 to Week 18 Mo 9
TO-22-SOM-T142-01 | SOMERSET T142 | bar: Su 24 to Week 18 Fr 6
Outages spanning Weeks 17-18
OUTAGE ID | PLANT | Week 17 Mo 25: Week 17; Week 18 Mo 2: Week 18
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9
TO-22-AA GIS-T104-01 | ARDNACRUSHA GIS T104
TO-22-BDA-MON-1-02 | BARODA MONREAD
TO-22-BIN-T142-01 | BINBANE T142
TO-22-CBR-SVC-04 | CASTLEBAR SVC
TO-22-CDU-PLA-1-01 | CORDUFF PLATIN
TO-22-110 kV A2 @ DEY-02 | DERRYCARNEY 110 kV A2
TO-22-110 kV B2 @ DEY-03 | DERRYCARNEY 110 kV B2
TO-22-DEY-110K2-02 | DERRYCARNEY 110K2
TO-22-DRU-CAP2-02 | DRUMLINE CAP2
TO-22-DDK-MLN-1-01 | DUNDALK MULLAGHARLIN
TO-22-220 kV A1/A2 @ FIN-01 | FINGLAS 220 kV A1/A2
TO-22-FIN-220K1-06 | FINGLAS 220K1
TO-22-FIN-220K2-01 | FINGLAS 220K2
TO-22-FIN-MCD-1-01 | FINGLAS McDERMOTT
TO-22-GGO-220K1-2-02 | GLANAGOW 220K1-2
TO-22-GGO-RAF-1-02 | GLANAGOW RAFFEEN
TO-22-INC-220K1-2-03 | INCHICORE 220K1-2
TO-22-KPG-TB-1-01 | KILPADDOGE TARBERT 1
TO-22-LET-M/CAP1-01 | LETTERKENNY M/CAP1
TO-22-LIS-LOU-1-03 | LISDRUM LOUTH
TO-22-LIS-LOU-1-01
TO-22-MAY-WOO-1-02 | MAYNOOTH WOODLAND
TO-22-MAY-WOO-1-12
TO-22-MUL-CAP2-03 | MULLINGAR CAP2
TO-22-NAV-M/CAP1-01 | NAVAN M/CAP1
TO-22-PB-R2002-01 | POOLBEG R2002
TO-22-RYB GIS-T133-02 | RYEBROOK GIS T133
TO-22-220 kV A1 @ TB-01 | TARBERT 220 kV A1
TO-22-220 kV B1 @ TB-01 | TARBERT 220 kV B1
TO-22-TB-T101-02 | TARBERT T101
TO-22-TB-T102-02 | TARBERT T102
TO-22-TB-T2004-03 | TARBERT T2004
TO-22-WOO-T4201-01 | WOODLAND T4201
TO-22-WOO-T4201-05