## Wks 33 - 34
Report covers outages commencing/returning/spanning the period: 15/08/2022 - 28/08/2022
Outages commencing/returning in Week 33
OUTAGE ID | PLANT |  | Week 33 | [6 empty] | Week 34
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29
TO-22-TIV-110SA1-2CB-03 | TIEVEBRACK 110SA1-2CB
TO-22-BVK-COT-1-02 | BALLYVOUSKILL COOMATAGGART
TO-22-CSH-TY-1-05 | CASHLA TYNAGH
TO-22-COT-110SA1-01 | COOMATAGGART 110SA1
TO-22-COT-110SA2-01 | COOMATAGGART 110SA2
TO-22-COT-FILTER1-01 | COOMATAGGART FILTER1
TO-22-COT-T132-01 | COOMATAGGART T132
TO-22-COT-T141-01 | COOMATAGGART T141
TO-22-DER-MAY-1-01 | DERRYIRON MAYNOOTH | bar: Week 33 Mo 15 to Week 33 Fr 19
TO-22-DRU-110SA1-02 | DRUMLINE 110SA1
TO-22-DRU-110SA2-01 | DRUMLINE 110SA2
TO-22-DRU-ENN-1-01 | DRUMLINE ENNIS
TO-22-DRU-T141-01 | DRUMLINE T141
TO-22-110 kV A3 @ FIN-03 | FINGLAS 110 kV A3
TO-22-110 kV B3 @ FIN-02 | FINGLAS 110 kV B3
TO-22-220 kV A2 @ FIN-01 | FINGLAS 220 kV A2
TO-22-220 kV B2 @ FIN-01 | FINGLAS 220 kV B2
TO-22-GLE-KCR-1-01 | GLENLARA KNOCKACUMMER
TO-22-KCR-T121-01 | KNOCKACUMMER T121
TO-22-MOY-TAW-2-01 | MOY TAWNAGHMORE 2
TO-22-220 kV A2 @ PB-05 | POOLBEG 220 kV A2
TO-22-PB-220K2-3-04 | POOLBEG 220K2-3
TO-22-110 kV A1 @ RYB GIS-02 | RYEBROOK GIS 110 kV A1
TO-22-110 kV A3 @ RYB GIS-02 | RYEBROOK GIS 110 kV A3
TO-22-RYB GIS-110SA1-3CB-01 | RYEBROOK GIS 110SA1-3CB
TO-22-110 kV A2 @ SLB-01 | SLIABH BAWN 110 kV A2
TO-22-110 kV B2 @ SLB-01 | SLIABH BAWN 110 kV B2
TO-22-SLB-110K2-02 | SLIABH BAWN 110K2
TO-22-BAN-BRI-2-01 | BANDON BRINNY 2 | bar: Week 33 Sa 20
TO-22-BRI-T102-01 | BRINNY T102 | bar: Week 33 Sa 20
TO-22-220 kV A1 @ CKM-01 | CARRICKMINES 220 kV A1 | bar: Week 33 Sa 20 to Week 34 Fr 26
TO-22-220 kV B1 @ CKM-01 | CARRICKMINES 220 kV B1 | bar: Week 33 Sa 20 to Week 34 Fr 26
TO-22-CRO-IA-1-01 | COOLROE INNISCARRA | bar: Week 33 Sa 20 to Week 34 Fr 26
TO-22-DER-MAY-1-02 | DERRYIRON MAYNOOTH | bar: Week 33 Sa 20 to Week 34 Fr 26
TO-22-FIN-T2104-03 | FINGLAS T2104 | bar: Week 33 Sa 20 to Week 34 Fr 26
TO-22-KLN-LIM-2-02 | KILLONAN LIMERICK 2 | bar: Week 33 Sa 20 to Week 34 Fr 26
TO-22-CKM-CKM GIS-1-01 | CARRICKMINES CARRICKMINES GIS | bar: Week 33 Sa 20 to Week 34 Mo 29
TO-22-CKM-PB-1-01 | CARRICKMINES POOLBEG | bar: Week 33 Sa 20 to Week 34 Mo 29
TO-22-CKM-PST2201-01 | CARRICKMINES PST2201 | bar: Week 33 Sa 20 to Week 34 Mo 29
TO-22-CF-COR-1-01 | CATHALEENS FALL CORRACLASSY
TO-22-GLR-MOY-1-01 | GLENREE MOY
TO-22-GLR-MOY-1-03 | bar: Week 33 Sa 20 to Week 34 Mo 29
TO-22-CVW-KRA-1-01 | CASTLEVIEW KNOCKRAHA | bar: Su 14
TO-22-CBT-110K1-05 | CASTLEBAGOT 110K1
TO-22-CBT-110K4-03 | CASTLEBAGOT 110K4
TO-22-KBY-T101-05 | KILBARRY T101 | bar: Week 33 Tu 16 to Week 33 We 17
TO-22-TY-T2001/2-02 | TYNAGH T2001/2
TO-22-LET-110SA1-3CB-01 | LETTERKENNY 110SA1-3CB | bar: Week 33 We 17
TO-22-110 kV A1/A2 @ SRA-01 | SRANANAGH 110 kV A1/A2
TO-22-110 kV B1/B2 @ SRA-01 | SRANANAGH 110 kV B1/B2
TO-22-110 kV A1 @ CBT-04 | CASTLEBAGOT 110 kV A1
TO-22-110 kV A2 @ CBT-01 | CASTLEBAGOT 110 kV A2
TO-22-CBT-110SA1-2CB-03 | CASTLEBAGOT 110SA1-2CB
TO-22-CLA-MAC-2-02 | CLASHAVOON MACROOM 2
TO-22-TAW-T3-01 | TAWNAGHMORE T3 | bar: Week 33 Sa 20 to Week 34 Fr 26
TO-22-BRT-T222-02 | BRACETOWN T222 | bar: Week 33 Sa 20 to Week 34 Mo 29
TO-22-220 kV A4 @ CDU-01 | CORDUFF 220 kV A4 | bar: Su 14
TO-22-220 kV B4 @ CDU-01 | CORDUFF 220 kV B4 | bar: Su 14
TO-22-TAW-T1/T2-01 | TAWNAGHMORE T1/T2 | bar: Su 14
Report covers outages commencing/returning/spanning the period: 15/08/2022 - 28/08/2022
Outages commencing/returning in Week 34
OUTAGE ID | PLANT | Week 33 Mo 15: Week 33; Week 34 Mo 22: Week 34
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29
TO-22-BWR-CRA-1-01 | BALLYWATER CRANE | bar: Week 34 Mo 22 to Week 34 Th 25
TO-22-BWR-T124-01 | BALLYWATER T124 | bar: Week 34 Mo 22 to Week 34 Th 25
TO-22-110 kV A1 @ AA GIS-01 | ARDNACRUSHA GIS 110 kV A1 | bar: Week 34 Mo 22 to Week 34 Fr 26
TO-22-110 kV A3 @ AA GIS-01 | ARDNACRUSHA GIS 110 kV A3 | bar: Week 34 Mo 22 to Week 34 Fr 26
TO-22-AA GIS-110SA1-3CB-02 | ARDNACRUSHA GIS 110SA1-3CB | bar: Week 34 Mo 22 to Week 34 Fr 26
TO-22-AUG-SK-4-01 | AUGHINISH SEALROCK 4 | bar: Week 34 Mo 22 to Week 34 Fr 26
TO-22-BOL-110SA1-01 | BOOLTIAGH 110SA1 | bar: Week 34 Mo 22 to Week 34 Fr 26
TO-22-BOL-110SA1-3CB-01 | BOOLTIAGH 110SA1-3CB | bar: Week 34 Mo 22 to Week 34 Fr 26
TO-22-BOL-T121-03 | BOOLTIAGH T121 | bar: Week 34 Mo 22 to Week 34 Fr 26
TO-22-220 kV A2 @ CSH-01 | CASHLA 220 kV A2 | bar: Week 34 Mo 22 to Week 34 Fr 26
TO-22-220 kV A4 @ CSH-01 | CASHLA 220 kV A4 | bar: Week 34 Mo 22 to Week 34 Fr 26
TO-22-220 kV B2 @ CSH-01 | CASHLA 220 kV B2 | bar: Week 34 Mo 22 to Week 34 Fr 26
TO-22-220 kV B4 @ CSH-01 | CASHLA 220 kV B4 | bar: Week 34 Mo 22 to Week 34 Fr 26
TO-22-CSH-220K2-4-01 | CASHLA 220K2-4 | bar: Week 34 Mo 22 to Week 34 Fr 26
TO-22-CDU-WOO-1-02 | CORDUFF WOODLAND | bar: Week 34 Mo 22 to Week 34 Fr 26
TO-22-110 kV A2 @ FIN GIS-07 | FINGLAS GIS 110 kV A2 | bar: Week 34 Mo 22 to Week 34 Fr 26
TO-22-110 kV B2 @ FIN GIS-06 | FINGLAS GIS 110 kV B2 | bar: Week 34 Mo 22 to Week 34 Fr 26
TO-22-FIN GIS-110K2-07 | FINGLAS GIS 110K2 | bar: Week 34 Mo 22 to Week 34 Fr 26
TO-22-KTL-MAY-1-02 | KILTEEL MAYNOOTH | bar: Week 34 Mo 22 to Week 34 Fr 26
TO-22-KRA-MID-1-03 | KNOCKRAHA MIDLETON | bar: Week 34 Mo 22 to Week 34 Fr 26
TO-22-KNY-UGL-1-01 | KNOCKRANNY UGGOOL | bar: Week 34 Mo 22 to Week 34 Fr 26
TO-22-LA-SLB-1-01 | LANESBORO SLIABH BAWN | bar: Week 34 Mo 22 to Week 34 Fr 26
TO-22-220 kV A2 @ MAY-06 | MAYNOOTH 220 kV A2 | bar: Week 34 Mo 22 to Week 34 Fr 26
TO-22-220 kV B2 @ MAY-07 | MAYNOOTH 220 kV B2 | bar: Week 34 Mo 22 to Week 34 Fr 26
TO-22-SK-T104-01 | SEALROCK T104 | bar: Week 34 Mo 22 to Week 34 Fr 26
TO-22-UGL-110SA1-2CB-01 | UGGOOL 110SA1-2CB | bar: Week 34 Mo 22 to Week 34 Fr 26
TO-22-UGL-T131-01 | UGGOOL T131 | bar: Week 34 Mo 22 to Week 34 Fr 26
TO-22-UGL-T132-01 | UGGOOL T132 | bar: Week 34 Mo 22 to Week 34 Fr 26
TO-22-UGL-T134-01 | UGGOOL T134 | bar: Week 34 Mo 22 to Week 34 Fr 26
TO-22-GI-T2101-02 | GREAT ISLAND T2101 | bar: Week 34 Mo 22 to Week 34 Mo 29
TO-22-110 kV B1 @ AA GIS-02 | ARDNACRUSHA GIS 110 kV B1 | bar: Week 34 Tu 23
TO-22-110 kV B2 @ AA GIS-01 | ARDNACRUSHA GIS 110 kV B2 | bar: Week 34 Tu 23
TO-22-AA GIS-110K2-03 | ARDNACRUSHA GIS 110K2 | bar: Week 34 Tu 23
TO-22-AA GIS-110SB1-2CB-02 | ARDNACRUSHA GIS 110SB1-2CB | bar: Week 34 Tu 23
TO-22-AA GIS-ENN-1-02 | ARDNACRUSHA GIS ENNIS | bar: Week 34 Tu 23
TO-22-CBT-T2104-03 | CASTLEBAGOT T2104 | bar: Week 34 Tu 23 to Week 34 We 24
TO-22-LOU-110K1-2-05 | LOUTH 110K1-2 | bar: Week 34 Tu 23 to Week 34 We 24
TO-22-220 kV A2 @ SH-01 | SHANNONBRIDGE 220 kV A2 | bar: Week 34 Tu 23 to Week 34 Fr 26
TO-22-220 kV B2 @ SH-01 | SHANNONBRIDGE 220 kV B2 | bar: Week 34 Tu 23 to Week 34 Fr 26
TO-22-SH-220K1-2-02 | SHANNONBRIDGE 220K1-2 | bar: Week 34 Tu 23 to Week 34 Fr 26
TO-22-BAN-T141-01 | BANDON T141 | bar: Week 34 We 24 to Week 34 Fr 26
TO-22-DDK-LOU-1-05 | DUNDALK LOUTH | bar: Week 34 We 24 to Week 34 Fr 26
TO-22-CDK-LWD-1-02 | CASTLEDOCKRELL LODGEWOOD | bar: Week 34 Th 25 to Week 34 Fr 26
TO-22-CDK-T121-02 | CASTLEDOCKRELL T121 | bar: Week 34 Th 25 to Week 34 Fr 26
TO-22-KRA-T2102-01 | KNOCKRAHA T2102 | bar: Su 14 to Week 34 Fr 26
TO-22-LIS-LOU-1-03 | LISDRUM LOUTH | bar: Su 14 to Week 34 Fr 26
TO-22-110 kV A2 @ LOU-05 | LOUTH 110 kV A2 | bar: Su 14 to Week 34 Fr 26
TO-22-110 kV B2 @ LOU-05 | LOUTH 110 kV B2 | bar: Su 14 to Week 34 Fr 26
TO-22-TB-T2003-02 | TARBERT T2003 | bar: Su 14 to Week 34 Fr 26
TO-22-110 kV A2 @ DEY-02 | DERRYCARNEY 110 kV A2
TO-22-110 kV B2 @ DEY-03 | DERRYCARNEY 110 kV B2
TO-22-DEY-110K2-02 | DERRYCARNEY 110K2
TO-22-KPG-TB-1-01 | KILPADDOGE TARBERT 1
TO-22-MOY-T142-01 | MOY T142
TO-22-220 kV A1 @ TB-01 | TARBERT 220 kV A1
TO-22-220 kV B1 @ TB-01 | TARBERT 220 kV B1
Report covers outages commencing/returning/spanning the period: 15/08/2022 - 28/08/2022
Outages spanning Weeks 33-34
OUTAGE ID | PLANT | Week 33 Mo 15: Week 33; Week 34 Mo 22: Week 34
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29
TO-22-BDN-DOO-1-01 | BALLYDINE DOON
TO-22-BDN-MRK3-01 | BALLYDINE MRK3
TO-22-BYH-BVK-1-01 | BALLYNAHULLA BALLYVOUSKILL
TO-22-BYH-BVK-1-02
TO-22-CDU-MUL-1-01 | CORDUFF MULLINGAR
TO-22-CKG-KUD-1-01 | CORKAGH KILMAHUD
TO-22-GAL-SAL-1-02 | GALWAY SALTHILL
TO-22-GAL-SAL-1-01
TO-22-GGO-220K1-2-02 | GLANAGOW 220K1-2
TO-22-GGO-RAF-1-02 | GLANAGOW RAFFEEN
TO-22-GI-WEX-1-01 | GREAT ISLAND WEXFORD
TO-22-INC-220K1-2-03 | INCHICORE 220K1-2
TO-22-ISH-T2001-02 | IRISHTOWN T2001
TO-22-KNR-TRI-2-01 | KNOCKANURE TRIEN 2
TO-22-LET-M/CAP1-01 | LETTERKENNY M/CAP1
TO-22-MAY-WOO-1-15 | MAYNOOTH WOODLAND
TO-22-MUL-CAP2-03 | MULLINGAR CAP2
TO-22-PB-R2002-01 | POOLBEG R2002
TO-22-SKL-T142-01 | SHANKILL T142
TO-22-SLI-T141-01 | SLIGO T141
TO-22-TB-T101-02 | TARBERT T101
TO-22-TRI-110SA1-2CB-02 | TRIEN 110SA1-2CB
TO-22-TRI-T142-01 | TRIEN T142
TO-22-WOO-T4201-05 | WOODLAND T4201