## Wks 35 - 36
Report covers outages commencing/returning/spanning the period: 29/08/2022 - 11/09/2022
Outages commencing/returning in Week 35
OUTAGE ID | PLANT |  | Week 35 | [6 empty] | Week 36
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
TO-22-CRO-IA-1-03 | COOLROE INNISCARRA | bar: Week 35 Mo 29
TO-22-IA-MAC-1-02 | INNISCARRA MACROOM | bar: Week 35 Mo 29
TO-22-IA-T101-02 | INNISCARRA T101 | bar: Week 35 Mo 29
TO-22-220 kV A1 @ GI GIS-02 | GREAT ISLAND GIS 220 kV A1 | bar: Week 35 Mo 29 to Week 35 Th 1
TO-22-220 kV A2 @ GI GIS-02 | GREAT ISLAND GIS 220 kV A2 | bar: Week 35 Mo 29 to Week 35 Th 1
TO-22-GI GIS-220SA1-2CB-01 | GREAT ISLAND GIS 220SA1-2CB | bar: Week 35 Mo 29 to Week 35 Th 1
TO-22-110 kV A1 @ KPG-03 | KILPADDOGE 110 kV A1 | bar: Week 35 Mo 29 to Week 35 Th 1
TO-22-110 kV B1 @ KPG-02 | KILPADDOGE 110 kV B1 | bar: Week 35 Mo 29 to Week 35 Th 1
TO-22-220 kV A1 @ KPG-02 | KILPADDOGE 220 kV A1 | bar: Week 35 Mo 29 to Week 35 Th 1
TO-22-220 kV B1 @ KPG-02 | KILPADDOGE 220 kV B1 | bar: Week 35 Mo 29 to Week 35 Th 1
TO-22-CSH-T2104-03 | CASHLA T2104 | bar: Week 35 Mo 29 to Week 35 Fr 2
TO-22-220 kV A2 @ CLE-05 | CLONEE 220 kV A2 | bar: Week 35 Mo 29 to Week 35 Fr 2
TO-22-220 kV B2 @ CLE-04 | CLONEE 220 kV B2 | bar: Week 35 Mo 29 to Week 35 Fr 2
TO-22-110 kV A1 @ CUL-01 | CULLENAGH 110 kV A1 | bar: Week 35 Mo 29 to Week 35 Fr 2
TO-22-110 kV B1 @ CUL-01 | CULLENAGH 110 kV B1 | bar: Week 35 Mo 29 to Week 35 Fr 2
TO-22-220 kV A1 @ DSN-01 | DUNSTOWN 220 kV A1 | bar: Week 35 Mo 29 to Week 35 Fr 2
TO-22-220 kV B1 @ DSN-01 | DUNSTOWN 220 kV B1 | bar: Week 35 Mo 29 to Week 35 Fr 2
TO-22-220 kV A2 @ PB-04 | POOLBEG 220 kV A2 | bar: Week 35 Mo 29 to Week 35 Fr 2
TO-22-220 kV B2 @ PB-03 | POOLBEG 220 kV B2 | bar: Week 35 Mo 29 to Week 35 Fr 2
TO-22-PB-220K2-3-02 | POOLBEG 220K2-3 | bar: Week 35 Mo 29 to Week 35 Fr 2
TO-22-SH-T2102-01 | SHANNONBRIDGE T2102 | bar: Week 35 Mo 29 to Week 35 Fr 2
TO-22-TRL-110SA1-2CB-01 | TRALEE 110SA1-2CB | bar: Week 35 Mo 29 to Week 35 Fr 2
TO-22-TRL-T142-02 | TRALEE T142 | bar: Week 35 Mo 29 to Week 35 Fr 2
TO-22-KPG-T2101-01 | KILPADDOGE T2101 | bar: Week 35 Mo 29 to Week 36 Mo 5
TO-22-CHA-GLE-1-02 | CHARLEVILLE GLENLARA | bar: Week 35 Mo 29 to Week 36 Fr 9
TO-22-CKM-CKM GIS-1-01 | CARRICKMINES CARRICKMINES GIS
TO-22-CKM-PB-1-01 | CARRICKMINES POOLBEG
TO-22-CKM-PST2201-01 | CARRICKMINES PST2201
TO-22-CLE-T224-01 | CLONEE T224
TO-22-220 kV A2 @ CDU-01 | CORDUFF 220 kV A2
TO-22-220 kV B2 @ CDU-01 | CORDUFF 220 kV B2
TO-22-DSN-400K1-2-01 | DUNSTOWN 400K1-2
TO-22-DSN-T4201-02 | DUNSTOWN T4201
TO-22-GI-T2101-02 | GREAT ISLAND T2101 | bar: Su 28 to Week 35 Mo 29
TO-22-BK-SKY-1-02 | BELLACORICK SRAHNAKILLY | bar: Week 35 Tu 30
TO-22-GOR-110K1-2-02 | GORMAN 110K1-2 | bar: Week 35 Tu 30
TO-22-RYB GIS-T131-02 | RYEBROOK GIS T131 | bar: Week 35 Tu 30
TO-22-SKY-110SA1-02 | SRAHNAKILLY 110SA1 | bar: Week 35 Tu 30
TO-22-SKY-110SA2-02 | SRAHNAKILLY 110SA2 | bar: Week 35 Tu 30
TO-22-SKY-T131-03 | SRAHNAKILLY T131 | bar: Week 35 Tu 30
TO-22-SKY-T132-01 | SRAHNAKILLY T132 | bar: Week 35 Tu 30
TO-22-SNG-110SA1-2CB-01 | SINGLAND 110SA1-2CB | bar: Week 35 Tu 30 to Week 35 We 31
TO-22-SNG-T101-01 | SINGLAND T101 | bar: Week 35 Tu 30 to Week 35 We 31
TO-22-110 kV B2 @ CBT-02 | CASTLEBAGOT 110 kV B2 | bar: Week 35 Tu 30 to Week 35 Th 1
TO-22-110 kV B4 @ CBT-05 | CASTLEBAGOT 110 kV B4 | bar: Week 35 Tu 30 to Week 35 Th 1
TO-22-CBT-110SB2-4CB-05 | CASTLEBAGOT 110SB2-4CB | bar: Week 35 Tu 30 to Week 35 Th 1
TO-22-BRT-T222-02 | BRACETOWN T222 | bar: Su 28 to Week 35 Tu 30
TO-22-CRO-KBY-1-04 | COOLROE KILBARRY | bar: Week 35 We 31 to Week 36 Mo 12
TO-22-CUL-T2101-01 | CULLENAGH T2101 | bar: Week 35 We 31 to Week 36 Mo 12
TO-22-110 kV A1 @ ARV-02 | ARVA 110 kV A1 | bar: Week 35 Th 1 to Week 36 Mo 5
TO-22-110 kV B1 @ ARV-02 | ARVA 110 kV B1 | bar: Week 35 Th 1 to Week 36 Mo 5
TO-22-ARV-SKL-1-03 | ARVA SHANKILL 1 | bar: Week 35 Th 1 to Week 36 Mo 5
TO-22-SKL-110SA1-02 | SHANKILL 110SA1 | bar: Week 35 Th 1 to Week 36 Mo 5
TO-22-SKL-110SA2-02 | SHANKILL 110SA2 | bar: Week 35 Th 1 to Week 36 Mo 5
TO-22-SKL-M/CAP2-02 | SHANKILL M/CAP2 | bar: Week 35 Th 1 to Week 36 Mo 5
TO-22-TIP-T141-02 | TIPPERARY T141 | bar: Week 35 Th 1 to Week 36 Mo 12
TO-22-KLN-SH-1-03 | KILLONAN SHANNONBRIDGE | bar: Week 35 Fr 2
TO-22-KNY-UGL-1-01 | KNOCKRANNY UGGOOL | bar: Su 28 to Week 35 Fr 2
TO-22-UGL-110SA1-2CB-01 | UGGOOL 110SA1-2CB | bar: Su 28 to Week 35 Fr 2
TO-22-UGL-T131-01 | UGGOOL T131 | bar: Su 28 to Week 35 Fr 2
TO-22-UGL-T132-01 | UGGOOL T132 | bar: Su 28 to Week 35 Fr 2
Report covers outages commencing/returning/spanning the period: 29/08/2022 - 11/09/2022
Outages commencing/returning in Week 35
OUTAGE ID | PLANT | Week 35 Mo 29: Week 35; Week 36 Mo 5: Week 36
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
TO-22-UGL-T134-01 | UGGOOL T134 | bar: Su 28 to Week 35 Fr 2
Outages commencing/returning in Week 36
OUTAGE ID | PLANT | Week 35 Mo 29: Week 35; Week 36 Mo 5: Week 36
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
TO-22-CF-T104-01 | CATHALEENS FALL T104
TO-22-CDL-T141-03 | CORDAL T141
TO-22-BDA-T101-01 | BARODA T101
TO-22-ISH-T2001-01 | IRISHTOWN T2001 | bar: Week 36 Mo 5 to Week 36 We 7
TO-22-110 kV A2 @ KNY-03 | KNOCKRANNY 110 kV A2
TO-22-110 kV B2 @ KNY-03 | KNOCKRANNY 110 kV B2
TO-22-220 kV A1 @ AD-03 | AGHADA 220 kV A1 | bar: Week 36 Fr 9
TO-22-220 kV B1 @ AD-04 | AGHADA 220 kV B1 | bar: Week 36 Fr 9
TO-22-AD-LPT-1-01 | AGHADA LONG POINT | bar: Week 36 Fr 9
TO-22-110 kV A2 @ BYH-04 | BALLYNAHULLA 110 kV A2 | bar: Week 36 Fr 9
TO-22-110 kV B2 @ BYH-04 | BALLYNAHULLA 110 kV B2 | bar: Week 36 Fr 9
TO-22-BYH-CDL-1-02 | BALLYNAHULLA CORDAL | bar: Week 36 Fr 9
TO-22-CLW-110SA1-06 | CARLOW 110SA1 | bar: Week 36 Fr 9
TO-22-CLW-110SA2-04 | CARLOW 110SA2 | bar: Week 36 Fr 9
TO-22-CLW-KLS-1-06 | CARLOW KELLIS 1 | bar: Week 36 Fr 9
TO-22-CLW-T141-04 | CARLOW T141 | bar: Week 36 Fr 9
TO-22-CDL-110SA1-02 | CORDAL 110SA1 | bar: Week 36 Fr 9
TO-22-CDL-110SA1-01 | bar: Week 36 Fr 9
TO-22-CDL-110SA2-01 | CORDAL 110SA2 | bar: Week 36 Fr 9
TO-22-CDL-110SA2-02 | bar: Week 36 Fr 9
TO-22-CDL-T132-02 | CORDAL T132 | bar: Week 36 Fr 9
TO-22-CDL-T132-01 | bar: Week 36 Fr 9
TO-22-CDL-T141-01 | CORDAL T141 | bar: Week 36 Fr 9
TO-22-CDL-T141-02 | bar: Week 36 Fr 9
TO-22-220 kV A1 @ CUL-01 | CULLENAGH 220 kV A1 | bar: Week 36 Fr 9
TO-22-220 kV B1 @ CUL-01 | CULLENAGH 220 kV B1 | bar: Week 36 Fr 9
TO-22-DSN-MAY-1-01 | DUNSTOWN MAYNOOTH 1 | bar: Week 36 Fr 9
TO-22-110 kV A5 @ FIN GIS-02 | FINGLAS GIS 110 kV A5 | bar: Week 36 Fr 9
TO-22-110 kV B5 @ FIN GIS-02 | FINGLAS GIS 110 kV B5 | bar: Week 36 Fr 9
TO-22-FIN GIS-110K5-02 | FINGLAS GIS 110K5 | bar: Week 36 Fr 9
TO-22-110 kV A2 @ FLA-03 | FLAGFORD 110 kV A2 | bar: Week 36 Mo 5 to Week 36 Fr 9
TO-22-110 kV B2 @ FLA-03 | FLAGFORD 110 kV B2 | bar: Week 36 Mo 5 to Week 36 Fr 9
TO-22-220 kV A2 @ FLA-04 | FLAGFORD 220 kV A2 | bar: Week 36 Mo 5 to Week 36 Fr 9
TO-22-220 kV B2 @ FLA-01 | FLAGFORD 220 kV B2 | bar: Week 36 Mo 5 to Week 36 Fr 9
TO-22-FLA-T2102-01 | FLAGFORD T2102 | bar: Week 36 Mo 5 to Week 36 Fr 9
TO-22-110 kV A3 @ KPG-02 | KILPADDOGE 110 kV A3 | bar: Week 36 Fr 9
TO-22-110 kV B3 @ KPG-01 | KILPADDOGE 110 kV B3 | bar: Week 36 Fr 9
TO-22-KPG-110K3-01 | KILPADDOGE 110K3 | bar: Week 36 Fr 9
TO-22-KLH-KNY-1-01 | KNOCKALOUGH KNOCKRANNY | bar: Week 36 Fr 9
TO-22-LPT-T2002-01 | LONG POINT T2002 | bar: Week 36 Fr 9
TO-22-110 kV A1 @ LOU-01 | LOUTH 110 kV A1 | bar: Week 36 Fr 9
TO-22-110 kV B1 @ LOU-01 | LOUTH 110 kV B1 | bar: Week 36 Fr 9
TO-22-LOU-CAP1-02 | LOUTH CAP1 | bar: Week 36 Fr 9
TO-22-110 kV A2 @ RYB GIS-02 | RYEBROOK GIS 110 kV A2 | bar: Week 36 Fr 9
TO-22-110 kV A4 @ RYB GIS-01 | RYEBROOK GIS 110 kV A4 | bar: Week 36 Fr 9
TO-22-RYB GIS-110SA2-4CB-02 | RYEBROOK GIS 110SA2-4CB | bar: Week 36 Fr 9
TO-22-WHI-CKB-T102-01 | WHITEGATE CKB-T102 | bar: Week 36 Fr 9
TO-22-ATY-CLW-1-01 | ATHY CARLOW | bar: Week 36 Fr 9 to Week 36 Mo 12
TO-22-KLS-220K1-2-03 | KELLIS 220K1-2 | bar: Week 36 Fr 9 to Week 36 Mo 12
TO-22-110 kV A1 @ KRA-01 | KNOCKRAHA 110 kV A1 | bar: Week 36 Fr 9 to Week 36 Mo 12
TO-22-KRA-T2101-01 | KNOCKRAHA T2101 | bar: Week 36 Fr 9 to Week 36 Mo 12
TO-22-LOU-T2103-01 | LOUTH T2103 | bar: Week 36 Fr 9 to Week 36 Mo 12
TO-22-LSN-110SA1-2-05 | LISHEEN 110SA1-2 | bar: Su 28 to Week 35 Su 4
TO-22-LSN-T122-07 | LISHEEN T122 | bar: Su 28 to Week 35 Su 4
TO-22-LSN-T142-07 | LISHEEN T142 | bar: Su 28 to Week 35 Su 4
Report covers outages commencing/returning/spanning the period: 29/08/2022 - 11/09/2022
Outages commencing/returning in Week 36
OUTAGE ID | PLANT | Week 35 Mo 29: Week 35; Week 36 Mo 5: Week 36
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
TO-22-LSN-THU-1-07 | LISHEEN THURLES | bar: Su 28 to Week 36 Mo 5
TO-22-SKL-T142-01 | SHANKILL T142 | bar: Su 28 to Week 36 Mo 5
TO-22-AA GIS-T103-01 | ARDNACRUSHA GIS T103 | bar: Week 36 Tu 6 to Week 36 We 7
TO-22-GLN-PLA-1-01 | GALLANSTOWN PLATIN | bar: Week 36 Tu 6 to Week 36 We 7
TO-22-PLA-110SA1-03 | PLATIN 110SA1 | bar: Week 36 Tu 6 to Week 36 We 7
TO-22-PLA-110SA2-03 | PLATIN 110SA2 | bar: Week 36 Tu 6 to Week 36 We 7
TO-22-PLA-T105-03 | PLATIN T105 | bar: Week 36 Tu 6 to Week 36 We 7
TO-22-SLI-110SA1-2CB-04 | SLIGO 110SA1-2CB | bar: Week 36 Tu 6 to Week 36 We 7
TO-22-BUT-KTN-1-02 | BUTLERSTOWN KILLOTERAN | bar: Week 36 Tu 6 to Week 36 Th 8
TO-22-KTN-110SA1-01 | KILLOTERAN 110SA1 | bar: Week 36 Tu 6 to Week 36 Th 8
TO-22-KTN-110SA2-01 | KILLOTERAN 110SA2 | bar: Week 36 Tu 6 to Week 36 Th 8
TO-22-KTN-T101-01 | KILLOTERAN T101 | bar: Week 36 Tu 6 to Week 36 Th 8
TO-22-110 kV A2 @ KPG-02 | KILPADDOGE 110 kV A2 | bar: Week 36 Tu 6 to Week 36 Fr 9
TO-22-110 kV B2 @ KPG-01 | KILPADDOGE 110 kV B2 | bar: Week 36 Tu 6 to Week 36 Fr 9
TO-22-220 kV A2 @ KPG-02 | KILPADDOGE 220 kV A2 | bar: Week 36 Tu 6 to Week 36 Fr 9
TO-22-220 kV B2 @ KPG-02 | KILPADDOGE 220 kV B2 | bar: Week 36 Tu 6 to Week 36 Fr 9
TO-22-GOR-PLA-1-01 | GORMAN PLATIN | bar: Week 36 Tu 6 to Week 36 Mo 12
TO-22-KPG-T2102-02 | KILPADDOGE T2102 | bar: Week 36 Tu 6 to Week 36 Mo 12
TO-22-ARK-SHE-2-01 | ARKLOW SHELTON ABBEY 2 | bar: Week 36 We 7
TO-22-BDN-110SA1-01 | BALLYDINE 110SA1 | bar: Week 36 We 7
TO-22-BDN-110SA2-01 | BALLYDINE 110SA2 | bar: Week 36 We 7
TO-22-BDN-DOO-1-02 | BALLYDINE DOON | bar: Week 36 We 7
TO-22-GI-110K1-2-01 | GREAT ISLAND 110K1-2 | bar: Week 36 We 7
TO-22-SHE-T102-01 | SHELTON ABBEY T102 | bar: Week 36 We 7
TO-22-GLR-T142-01 | GLENREE T142 | bar: Week 36 We 7 to Week 36 Th 8
TO-22-BDN-DOO-1-01 | BALLYDINE DOON | bar: Su 28 to Week 36 We 7
TO-22-BDN-MRK3-01 | BALLYDINE MRK3 | bar: Su 28 to Week 36 We 7
TO-22-GI GIS-220K1-01 | GREAT ISLAND GIS 220K1 | bar: Week 36 Th 8
TO-22-CAH-TIP-1-02 | CAHIR TIPPERARY | bar: Week 36 Th 8 to Week 36 Fr 9
TO-22-GWE-T142-01 | GORTAWEE T142 | bar: Week 36 Th 8 to Week 36 Fr 9
Outages spanning Weeks 35-36
OUTAGE ID | PLANT | Week 35 Mo 29: Week 35; Week 36 Mo 5: Week 36
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
TO-22-BYH-BVK-1-01 | BALLYNAHULLA BALLYVOUSKILL
TO-22-BYH-BVK-1-02
TO-22-CF-COR-1-01 | CATHALEENS FALL CORRACLASSY
TO-22-CDU-MUL-1-01 | CORDUFF MULLINGAR
TO-22-CKG-KUD-1-01 | CORKAGH KILMAHUD
TO-22-110 kV A2 @ DEY-02 | DERRYCARNEY 110 kV A2
TO-22-110 kV B2 @ DEY-03 | DERRYCARNEY 110 kV B2
TO-22-DEY-110K2-02 | DERRYCARNEY 110K2
TO-22-FIN GIS-110K6-02 | FINGLAS GIS 110K6
TO-22-GAL-SAL-1-02 | GALWAY SALTHILL
TO-22-GAL-SAL-1-01
TO-22-GGO-220K1-2-02 | GLANAGOW 220K1-2
TO-22-GGO-RAF-1-02 | GLANAGOW RAFFEEN
TO-22-GOR-110K1-2-01 | GORMAN 110K1-2
TO-22-GI-WEX-1-01 | GREAT ISLAND WEXFORD
TO-22-INC-220K1-2-03 | INCHICORE 220K1-2
TO-22-KPG-TB-1-01 | KILPADDOGE TARBERT 1
TO-22-KNR-TRI-2-01 | KNOCKANURE TRIEN 2
TO-22-LET-M/CAP1-01 | LETTERKENNY M/CAP1
TO-22-MAY-WOO-1-15 | MAYNOOTH WOODLAND
TO-22-MOY-T142-01 | MOY T142
TO-22-MUL-CAP2-03 | MULLINGAR CAP2
TO-22-PB-R2002-01 | POOLBEG R2002
TO-22-SLI-T141-01 | SLIGO T141
TO-22-220 kV A1 @ TB-01 | TARBERT 220 kV A1
TO-22-220 kV B1 @ TB-01 | TARBERT 220 kV B1
Report covers outages commencing/returning/spanning the period: 29/08/2022 - 11/09/2022
Outages spanning Weeks 35-36
OUTAGE ID | PLANT | Week 35 Mo 29: Week 35; Week 36 Mo 5: Week 36
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
TO-22-TB-T101-02 | TARBERT T101
TO-22-TRI-110SA1-2CB-02 | TRIEN 110SA1-2CB
TO-22-TRI-T142-01 | TRIEN T142
TO-22-WOO-T4201-05 | WOODLAND T4201